## IDM 2.0 Deliverables Log _ Sign
Release | Phase | Completed? | Deliverable ID | Deliverable Type (Single/Multi-Instance) | Deliverable /Task | Deliverable / Artifact | Done | Due Date | GPO / Horizontal Leads Sign Off | IT Lead Signoff | Tower/Horizontal Name | Status | Comments | Deloitte Owner | Intel Owner | Approved Document Link | Coordination | Sign off Participants | In PMOFD Folder | PMO Audit | Approval Evidence Link (if required) | Final Deliverable Folder Link (PMO) | Tower Deliverable | Duplicate Check
All | Prepare | Y | IDM 2.0 DELID196 | Single Instance | Deliverable Sign off Tracker |  |  | 2024-02-09 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://app.smartsheet.com/sheets/G7mMrX69qX2F52VGwgjf4gQ2cw4Xqg3xp5X66291 | [7 empty] | 1
All | Prepare | Y | IDM 2.0 DELID188 | Single Instance | Deliverables Log |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://app.smartsheet.com/sheets/G7mMrX69qX2F52VGwgjf4gQ2cw4Xqg3xp5X66291 | [7 empty] | 1
All | All Phases | Y | IDM 2.0 DELID189 | Single Instance | Integrated Project & Sprint Plan |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete | Past Design Sprint Plan and Integrated Project Plan | Alpna Gainda | Uzma Ahmed | https://app.smartsheet.com/sheets/5RwMCq6HMxj39JPFwC82cGJjWR8ChcFp25Vf56J1 | [7 empty] | 1
All | Prepare | Y | IDM 2.0 DELID195 | Single Instance | Kick-off deck |  |  | 2024-02-09 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Intel%20IAO%20Kickoff%20Deck%202024.pptx?d=wf5d3d61028fd4032b2547a867b7d2683&csf=1&web=1&e=U8bfSV | [7 empty] | 1
All | All Phases | Y | IDM 2.0 DELID193 | Single Instance | Phase Exit Criteria |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/01%20Design/2.%20Non-Sprint%20Deliverables/PMO/Intel%20IDM%202.0%20-%20R1R2%20Design%20Exit%20approach.pptx?d=wc5feb70910be46d0a19374de203bf4d0&csf=1&web=1&e=bG48xB |  |  |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/Other%20Approvals/FW_%20PMO%20Detailed%20Design%20Deliverables.msg?csf=1&web=1&e=BYUEf8 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/Other%20Approvals/FW_%20PMO%20Detailed%20Design%20Deliverables.msg?csf=1&web=1&e=BYUEf8 |  | 1
All | All Phases | Y | IDM 2.0 DELID191 | Single Instance | Phase gate review summary / Phase kick-offs |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Intel%20IAO%20Kickoff%20Deck%202024.pptx?d=wf5d3d61028fd4032b2547a867b7d2683&csf=1&web=1&e=U8bfSV | [7 empty] | 1
All | All Phases | Y | IDM 2.0 DELID192 | Single Instance | Program Management Office (PMO) Framework & Processes (i.e., Change Control) |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Program%20Execution%20Methodology_19Jan24.pptx?d=we2e9431f13f5447295df36e33d70cd28&csf=1&web=1&e=eujiIn | [7 empty] | 1
All | Prepare | Y | IDM 2.0 DELID194 | Single Instance | Resource plan |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete | Deloitte FTE Tracker / Intel FTE Tracker | Alpna Gainda | Uzma Ahmed | https://app.smartsheet.com/sheets/QmCFXxc2w745HpR9jWh45FPRPM4c3w644W8GgHw1 | [7 empty] | 1
All | All Phases | Y | IDM 2.0 DELID190 | Single Instance | Risks, Actions, Issues and Decisions (RAID) Log |  |  | 2024-06-28 | TRUE | N/A | 01. PMO | 04. Complete |  | Alpna Gainda | Uzma Ahmed | https://app.smartsheet.com/sheets/9JP9rmxm964MwgCWVvmj82fc8MJ3Fc3GVfVPwGG1 | [7 empty] | 1
R1 | Detailed design | Y | IDM 2.0 DELID412 | Multiple instances | Architecture diagrams |  |  | 2024-06-28 | TRUE | N/A | 02. E2E Process Integration | 04. Complete |  | Kalpesh Shah | Craig Eastwood, Jo Guedes, Satyadeep Vajjala, Talbot Smith | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/E2E/R1%20Architecture?csf=1&web=1&e=pCLuli | [7 empty] | 1
R2 | Detailed design | Y | IDM 2.0 DELID413 | Multiple instances | Architecture diagrams |  |  | 2024-06-28 | TRUE | N/A | 02. E2E Process Integration | 04. Complete |  | Kalpesh Shah | Craig Eastwood, Jo Guedes, Satyadeep Vajjala, Talbot Smith | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/E2E/R2%20Architecture?csf=1&web=1&e=zT3RYS | [7 empty] | 1
R2 | Detailed design | Y | IDM 2.0 DELID414 | Multiple instances | E2E Process Flows |  |  | 2024-06-28 | TRUE | N/A | 02. E2E Process Integration | 04. Complete |  | Kalpesh Shah | Craig Eastwood, Jo Guedes, Satyadeep Vajjala, Talbot Smith | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/E2E/R2%20E2E%20Flows?csf=1&web=1&e=H6uKHD | [7 empty] | 1
R1 | Detailed design | Y | IDM 2.0 DELID225 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | Business Process Doc (word), Approval | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/FPR/BPD?csf=1&web=1&e=6wUOLc |  | 1
R1 | Build | Y | IDM 2.0 DELID546 | Multiple instances | Configuration Unit testing Results (CUT) |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=ysB9Hl&CID=051e0848%2D19bc%2D4c4c%2D8ae7%2D9d7c1c63f8f2&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&isAscending=false&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FFPR%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FDELID546%20Configuration%20Unit%20Testing%20Results%20%28CUT%29&sortField=Modified&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID203 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | All user stories dispositioned / approved | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID549 | Multiple instances | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/Functional%20Specifications%20Document%20(FDS)/DELID549%20FDS%20for%20ECA%20Objects%20with%20Unit%20Test%20Cases?csf=1&web=1&e=ysB9Hl |  | 1
R1 | Build | Y | IDM 2.0 DELID276 | Multiple instances | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/Functional%20Specifications%20Document%20(FDS)/DELID276%20FDS%20for%20RICEFW%20Objects%20with%20Unit%20Test%20Cases?csf=1&web=1&e=S9tLFl |  | 1
R1 | Build | Y | IDM 2.0 DELID556 | Multiple instances | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/Functional,%20Configuration%20Unit%20testing%20Results%20(FUT,%20CUT)/DELID556%20FUT%20for%20ECA%20Objects?csf=1&web=1&e=SinDl9 |  | 1
R1 | Build | Y | IDM 2.0 DELID487 | Multiple instances | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/Functional,%20Configuration%20Unit%20testing%20Results%20(FUT,%20CUT)/DELID487%20FUT%20for%20RICEFW%20Objects?csf=1&web=1&e=kaqWnY |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID201 | Multiple instances | Requirement/User stories |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | List of all user stories | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID278 | Multiple instances | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-10-25 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/_EXT_%20Re_%20Approval%20on%20the%20Deliverables%20for%20R1.msg?csf=1&web=1&e=9S679q | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/FPR/DELID278%20S4%20HANA%20Configuration%20Design%20Document%20(CDD)%20with%20Unit%20Test%20Cases?csf=1&web=1&e=catDr2 |  | 1
R1 | Build | Y | IDM 2.0 DELID279 | Multiple instances | S/4HANA System Configuration |  |  | 2024-10-25 | TRUE | N/A | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Jesse Moreno, Shane Bethune | [6 empty] | NA |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID202 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | Mapping of user stories to L3/RICEWF ID | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID250 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | Business Process Doc (word), Approval | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID228 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | User Story Tracker | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID424 | Multiple instances | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FPR/FDS?csf=1&web=1&e=qNhizg |  | 1
R2 | Build | Y | IDM 2.0 DELID880 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FPR/FDS?csf=1&web=1&e=qNhizg |  | 1
R2 | Build | Y | IDM 2.0 DELID488 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FFPR%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FCUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID226 | Multiple instances | Requirement/User stories |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | User Story Tracker | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID881 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE |  | 03. FPR | 03. In Deliverable Review |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID882 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FFPR%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FFUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID521 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FFPR%2FCDD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID510 |  | S/4HANA System Configuration |  |  | 2024-12-06 | N/A |  | 03. FPR | 03. In Deliverable Review |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | N/A |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID227 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 03. FPR | 04. Complete | User Story Tracker | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6wUOLc&CID=4fe67cb4%2D95c5%2D4a98%2D99ff%2Dfe60a63ffe47&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID275 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 03. FPR | 04. Complete | Conditional approval, potential for some addl. changes post-detailed review by scrum team 1 Process Stewards | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FBPD%2FFinal%20BPD%20Documents%20by%20L2&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Roberts, Matthew C; Johns, Kevin M; Goodwin, Karen P; Rojas, Doris R; Varela Molina, Ricardo J; Onopa, Amanda; Bethune, Shane; Meyer, Rea M; Shah, Twinkle; Lim, Alicia Jia Ping; Tan, Anson; Khan, Yousef; Goulding, Rachel M; Meyers, Chase; Ramsdell, Stacey; Bargovan, Mark C; Tames, Daniela; Bastos, Maureen; Philpot, Josh; Grudzien, Adam M; Rollman, Jason J; Koerbel, Shira; Luthra, Shivani; Kaza, Greeshma; Singh, Praveen; Ranu, Sukhwinde | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FBPD%2FBPD%20Approval%20emails%20by%20L2&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FBPD%2FFinal%20BPD%20Documents%20by%20L2&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID253 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 03. FPR | 04. Complete | Conditional approval, potential for some addl. changes post-detailed review by scrum team 1 Process Stewards | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FPR/RE_%20R3%20Design%20Closure%20Sign-Off.msg?csf=1&web=1&e=RWz8Qj | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID531 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID491 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID251 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 03. FPR | 04. Complete | Conditional approval, potential for some addl. changes post-detailed review by scrum team 1 Process Stewards | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B027383A2-A3D5-41C3-98DB-A18DC20A2BDA%7D&file=IDM%202.0%20DELID251%2C%20IDM%202.0%20DELID252%2C%20IDM%202.0%20DELID253%2C%20IDM%202.0%20DELID254_FPR%20User%20Story%20Tracker.xlsx&action=default&mobileredirect=true |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FPR/RE_%20R3%20Design%20Closure%20Sign-Off.msg?csf=1&web=1&e=RWz8Qj | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID524 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID513 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID252 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 03. FPR | 04. Complete | Conditional approval, potential for some addl. changes post-detailed review by scrum team 1 Process Stewards | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B027383A2-A3D5-41C3-98DB-A18DC20A2BDA%7D&file=IDM%202.0%20DELID251%2C%20IDM%202.0%20DELID252%2C%20IDM%202.0%20DELID253%2C%20IDM%202.0%20DELID254_FPR%20User%20Story%20Tracker.xlsx&action=default&mobileredirect=true |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FPR/RE_%20R3%20Design%20Closure%20Sign-Off.msg?csf=1&web=1&e=RWz8Qj | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID407 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 05. OTC IP | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC-IP/BPD?csf=1&web=1&e=wL6djs |  |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IP/BPD/BPD/BPD%20Approval%20Evidence%20OTC%20IP?csf=1&web=1&e=WZ5mMt | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=UBNIku&CID=800e85b1%2D4558%2D48f2%2D867e%2D721117344ce2&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FOTC%2DIP%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID391 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 05. OTC IP | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker/R3_Requirement%20User%20stories_IDM%202.0%20OTC%20IP%20User%20Story%20Tracker.xlsx?d=w8116448aa9d54178baa96e7a9cccf929&csf=1&web=1&e=GZbAU8 |  |  | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker?csf=1&web=1&e=kRwqpv |  | 1
R3 | Build | N/A | IDM 2.0 DELID893 |  | S/4HANA System Configuration |  |  | 2026-03-06 | N/A |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID894 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID895 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID896 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 03. FPR | 01. Not Started |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID897 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID898 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID899 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID900 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID532 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID492 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID389 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 05. OTC IP | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker/R3_Requirement%20User%20stories_IDM%202.0%20OTC%20IP%20User%20Story%20Tracker.xlsx?d=w8116448aa9d54178baa96e7a9cccf929&csf=1&web=1&e=GZbAU8 |  |  | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker?csf=1&web=1&e=kRwqpv |  | 1
R3 | Build | N/A | IDM 2.0 DELID525 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID514 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 05. OTC IP | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID390 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 05. OTC IP | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Shelly Lafree | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker/R3_Requirement%20User%20stories_IDM%202.0%20OTC%20IP%20User%20Story%20Tracker.xlsx?d=w8116448aa9d54178baa96e7a9cccf929&csf=1&web=1&e=GZbAU8 |  |  | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IP/User%20Story%20Tracker?csf=1&web=1&e=kRwqpv |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID366 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-28 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon |  |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables?csf=1&web=1&e=UBNIku |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID365 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon |  |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables?csf=1&web=1&e=UBNIku |  | 1
R2 | Build | Y | IDM 2.0 DELID884 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/OTC%20IF/FDS?csf=1&web=1&e=Y3apoq |  | 1
R2 | Build | Y | IDM 2.0 DELID885 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF%2FECA%20Reports%20Approval&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/OTC%20IF/FDS?csf=1&web=1&e=Y3apoq |  | 1
R2 | Build | Y | IDM 2.0 DELID886 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF%2FConfiguration%20and%20CUT%20Approval%2FConfiguration%20CUT%20Approval%20Emails&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FOTC%20IF%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FCUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID887 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review | Out of 30 objects o 19 already approved. o 5 Waiting for Intel approval. o 3 are in FUT progress ETA by 01/20 o 3 Straddle objects are owned by Intel to develop and not under Deloitte tracker. | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Y3apoq&CID=44f2dd4e%2D86f4%2D44d3%2D8228%2D562f730f9e33&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF%2FECA%20Reports%20Approval&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FOTC%20IF%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FFUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID423 | Single Instance | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FOTC%20IF%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29%2FFUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID363 | Multiple instances | Requirement/User stories |  |  | 2024-06-28 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon |  |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables?csf=1&web=1&e=UBNIku |  | 1
R2 | Build | Y | IDM 2.0 DELID522 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Y3apoq&CID=44f2dd4e%2D86f4%2D44d3%2D8228%2D562f730f9e33&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals%2FOTC%20%2D%20IF%2FConfiguration%20and%20CUT%20Approval&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?OR=Teams%2DHL&CT=1733307181749&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FOTC%20IF%2FCDD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID511 |  | S/4HANA System Configuration |  |  | 2024-12-06 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon, Kevin A Brown | NA | [5 empty] | NA |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID364 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon |  |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables?csf=1&web=1&e=UBNIku |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID406 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC%20-%20IF/BPD?csf=1&web=1&e=8aEi0V |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IF/BPD/BPD%20Approval%20Evidence%20OTC%20IF?csf=1&web=1&e=MGCW7x | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FOTC%2DIF%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&csf=1&web=1&e=UBNIku&CID=800e85b1%2D4558%2D48f2%2D867e%2D721117344ce2&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID388 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC%20-%20IF/User%20Story%20Tracker?csf=1&web=1&e=ow5xLO |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IF/User%20Story%20Tracker?csf=1&web=1&e=8zB7U5 |  | 1
R3 | Build | N/A | IDM 2.0 DELID901 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID902 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID903 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID904 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID533 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID493 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID386 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC%20-%20IF/User%20Story%20Tracker?csf=1&web=1&e=ow5xLO |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IF/User%20Story%20Tracker?csf=1&web=1&e=8zB7U5 |  | 1
R3 | Build | N/A | IDM 2.0 DELID526 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID515 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 04. OTC IF | 01. Not Started |  | Ellen Marie Nelson, Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID387 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Jill Matalon | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/OTC%20-%20IF/User%20Story%20Tracker?csf=1&web=1&e=ow5xLO |  | Jason Carmichael, Sariya Garza, Celia Zhao, Ryan V Le, Ray M O'Neill, Shahin Monfared | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/OTC-IF/User%20Story%20Tracker?csf=1&web=1&e=8zB7U5 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID408 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 06. PTP | 04. Complete |  | Murthy K P, Rajesh Tol | Cari H Shim | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/PTP%20Tower%20Deliverable%20Completion%20Tracker.pptx?d=w16762fbc2b9c437c9496b2c1d2b32d10&csf=1&web=1&e=EaZfxW https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/BPD?csf=1&web=1&e=bUQv0N |  | Cari Shim | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/EXT%20RE%20Design%20Deliverable%20Review%20%20Signoff%20-%20PTP.msg?csf=1&web=1&e=3u1VeW | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/BPD?csf=1&web=1&e=0kqRMq |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID394 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 06. PTP | 04. Complete |  | Murthy K P, Rajesh Tol | Cari H Shim | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/PTP%20Tower%20Deliverable%20Completion%20Tracker.pptx?d=w16762fbc2b9c437c9496b2c1d2b32d10&csf=1&web=1&e=EaZfxW https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/BPD?csf=1&web=1&e=bUQv0N |  | Cari Shim | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/EXT%20RE%20Design%20Deliverable%20Review%20%20Signoff%20-%20PTP.msg?csf=1&web=1&e=3u1VeW | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/User%20Story%20Tracker?csf=1&web=1&e=vDbPGH |  | 1
R3 | Build | N/A | IDM 2.0 DELID905 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID906 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID907 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID908 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID534 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID494 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID392 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 06. PTP | 04. Complete |  | Murthy K P, Rajesh Tol | Cari H Shim | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/PTP%20Tower%20Deliverable%20Completion%20Tracker.pptx?d=w16762fbc2b9c437c9496b2c1d2b32d10&csf=1&web=1&e=EaZfxW https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/BPD?csf=1&web=1&e=bUQv0N |  | Cari Shim | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/EXT%20RE%20Design%20Deliverable%20Review%20%20Signoff%20-%20PTP.msg?csf=1&web=1&e=3u1VeW | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/User%20Story%20Tracker?csf=1&web=1&e=vDbPGH |  | 1
R3 | Build | N/A | IDM 2.0 DELID527 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID516 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | Cari H Shim | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID393 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 06. PTP | 04. Complete |  | Murthy K P, Rajesh Tol | Cari H Shim | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/PTP%20Tower%20Deliverable%20Completion%20Tracker.pptx?d=w16762fbc2b9c437c9496b2c1d2b32d10&csf=1&web=1&e=EaZfxW https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/PTP/BPD?csf=1&web=1&e=bUQv0N |  | Cari Shim | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/EXT%20RE%20Design%20Deliverable%20Review%20%20Signoff%20-%20PTP.msg?csf=1&web=1&e=3u1VeW | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/PTP/User%20Story%20Tracker?csf=1&web=1&e=vDbPGH |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID409 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-21 | TRUE | N/A | 07. FTS IF | 04. Complete | Signed off by Dan Mahoney on behalf of Randy Eck with BPD confirmation from Chris Yeager | Ruben David Alvarez Carroz | Shamin A Shirodkar |  |  | Milan Junior, Zhao Celia, Chris Yeager |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/BPD?csf=1&web=1&e=DBKSBZ |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID397 | Multiple instances | Fit-Gap analysis |  |  | 2024-06-21 | TRUE | N/A | 07. FTS IF | 04. Complete | Signed off by Dan Mahoney on behalf of Randy Eck with User Story Tracker confirmation from Chris Yeager | Ruben David Alvarez Carroz | Shamin A Shirodkar |  |  | Milan Junior, Zhao Celia, Chris Yeager |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker/IDM%202.0%20DELID395_Requirement%20User%20stories_IDM%202.0%20FTS%20IF%20User%20Story%20Tracker.xlsx?d=w2b70ae1ad65548499d68caad36419af9&csf=1&web=1&e=CGP9ja |  | 1
R2 | Build | Y | IDM 2.0 DELID889 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/FDS?csf=1&web=1&e=YgCb02 |  | Rodolfo Alarcon, Neetu Ramireddi |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/FDS?csf=1&web=1&e=YgCb02 |  | 1
R2 | Build | Y | IDM 2.0 DELID890 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey |  |  | Rodolfo Alarcon, Neetu Ramireddi | [5 empty] | 1
R2 | Build | Y | IDM 2.0 DELID891 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/Functional,%20Configuration%20Unit%20testing%20Results%20(FUT,%20CUT)?csf=1&web=1&e=QEPqWP |  | Rodolfo Alarcon, Neetu Ramireddi |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=QEPqWP&CID=74ca1aff%2D5ac3%2D4139%2D8b57%2D31f85e1a2dbb&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FFTS%20IF%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29 |  | 1
R2 | Build | Y | IDM 2.0 DELID892 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey |  |  | Rodolfo Alarcon, Neetu Ramireddi | [5 empty] | 1
R2 | Build | Y | IDM 2.0 DELID425 | Single Instance | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 03. In Deliverable Review | 12/06 - Surya LOGI0519/520/521 are under development by Technical team 02/05: Still waiting for ECD FUT's. | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/Functional,%20Configuration%20Unit%20testing%20Results%20(FUT,%20CUT)?csf=1&web=1&e=QEPqWP | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=QEPqWP&CID=74ca1aff%2D5ac3%2D4139%2D8b57%2D31f85e1a2dbb&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FFTS%20IF%2FFunctional%2C%20Configuration%20Unit%20testing%20Results%20%28FUT%2C%20CUT%29 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID395 | Multiple instances | Requirement/User stories |  |  | 2024-06-21 | TRUE | N/A | 07. FTS IF | 04. Complete | Signed off by Dan Mahoney on behalf of Randy Eck with User Story Tracker confirmation from Chris Yeager | Ruben David Alvarez Carroz | Shamin A Shirodkar |  |  | Milan Junior, Zhao Celia, Chris Yeager |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker/IDM%202.0%20DELID395_Requirement%20User%20stories_IDM%202.0%20FTS%20IF%20User%20Story%20Tracker.xlsx?d=w2b70ae1ad65548499d68caad36419af9&csf=1&web=1&e=CGP9ja |  | 1
R2 | Build | Y | IDM 2.0 DELID523 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/CDD?csf=1&web=1&e=ASOHsQ |  | Rodolfo Alarcon, Neetu Ramireddi |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/CDD?csf=1&web=1&e=ASOHsQ |  | 1
R2 | Build | Y | IDM 2.0 DELID512 |  | S/4HANA System Configuration |  |  | 2024-12-06 | TRUE | N/A | 07. FTS IF | 04. Complete |  | Ruben David Alvarez Carroz | Jorge Sanchez, Stef Maxey | N/A | [5 empty] | N/A |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID396 | Multiple instances | Traceability matrix |  |  | 2024-06-21 | TRUE | N/A | 07. FTS IF | 04. Complete | Signed off by Dan Mahoney on behalf of Randy Eck with User Story Tracker confirmation from Chris Yeager | Ruben David Alvarez Carroz | Shamin A Shirodkar |  |  | Milan Junior, Zhao Celia, Chris Yeager |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker/IDM%202.0%20DELID395_Requirement%20User%20stories_IDM%202.0%20FTS%20IF%20User%20Story%20Tracker.xlsx?d=w2b70ae1ad65548499d68caad36419af9&csf=1&web=1&e=CGP9ja |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID418 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 07. FTS IF | 04. Complete | Pending GPO approval. Received approvals form process stewards | Rudra Sengupta | Shamin A Shirodkar | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/BPD/BPD%20Approval%20Evidence%20FTS%20IF/EXT%20RE%20FTS%20IF%20Plant%20Maintenance%20-%20Design%20Exit%20Review%20.msg?csf=1&web=1&e=tL9NMe | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFTS%2DIF%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID417 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 07. FTS IF | 04. Complete | Pending GPO approval. Received approvals form process stewards | Rudra Sengupta | Shamin A Shirodkar | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/BPD/BPD%20Approval%20Evidence%20FTS%20IF/EXT%20RE%20FTS%20IF%20Plant%20Maintenance%20-%20Design%20Exit%20Review%20.msg?csf=1&web=1&e=tL9NMe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker?csf=1&web=1&e=7Ykrps |  | 1
R3 | Build | N/A | IDM 2.0 DELID909 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID910 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID911 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 07. FTS IF | 04. Complete |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/CDD?csf=1&web=1&e=wKDk58 | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID912 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID535 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID495 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 07. FTS IF | 04. Complete |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/02%20Build/01.%20Sprint%20Deliverables/FTS%20IF/Functional,%20Configuration%20Unit%20testing%20Results%20(FUT,%20CUT)?csf=1&web=1&e=dkg3Ba | [7 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID415 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 07. FTS IF | 04. Complete | Pending GPO approval. Received approvals form process stewards | Rudra Sengupta | Shamin A Shirodkar | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/BPD/BPD%20Approval%20Evidence%20FTS%20IF/EXT%20RE%20FTS%20IF%20Plant%20Maintenance%20-%20Design%20Exit%20Review%20.msg?csf=1&web=1&e=tL9NMe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker?csf=1&web=1&e=7Ykrps |  | 1
R3 | Build | N/A | IDM 2.0 DELID528 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID517 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 07. FTS IF | 01. Not Started |  | Ruben David Alvarez Carroz | Shamin A Shirodkar | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID416 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 07. FTS IF | 04. Complete | Pending GPO approval. Received approvals form process stewards | Rudra Sengupta | Shamin A Shirodkar | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/BPD/BPD%20Approval%20Evidence%20FTS%20IF/EXT%20RE%20FTS%20IF%20Plant%20Maintenance%20-%20Design%20Exit%20Review%20.msg?csf=1&web=1&e=tL9NMe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IF/User%20Story%20Tracker?csf=1&web=1&e=7Ykrps |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID410 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 08. FTS IP | 04. Complete |  | Sekhar Lingam | Thomas M Sanger | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP/Design%20Deliverable%20Approval%20Evidence/FTS%20Intel%20Products%20-%20R3%20Design%20Deliverables%20GPO%20Approval_04.18.25.msg?csf=1&web=1&e=hT9mZd | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP?csf=1&web=1&e=GnAXLg |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID400 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 08. FTS IP | 04. Complete |  | Sekhar Lingam | Thomas M Sanger | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IP/User%20Story%20Tracker?csf=1&web=1&e=d6ukwS |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP/Design%20Deliverable%20Approval%20Evidence/FTS%20Intel%20Products%20-%20R3%20Design%20Deliverables%20GPO%20Approval_04.18.25.msg?csf=1&web=1&e=hT9mZd | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP?csf=1&web=1&e=GnAXLg |  | 1
R3 | Build | N/A | IDM 2.0 DELID913 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID914 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID915 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID916 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID536 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID496 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID398 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 08. FTS IP | 04. Complete |  | Sekhar Lingam | Thomas M Sanger | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IP/User%20Story%20Tracker?csf=1&web=1&e=d6ukwS |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP/Design%20Deliverable%20Approval%20Evidence/FTS%20Intel%20Products%20-%20R3%20Design%20Deliverables%20GPO%20Approval_04.18.25.msg?csf=1&web=1&e=hT9mZd | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP?csf=1&web=1&e=GnAXLg |  | 1
R3 | Build | N/A | IDM 2.0 DELID529 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID518 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | Thomas M Sanger | [8 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID399 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 08. FTS IP | 04. Complete |  | Sekhar Lingam | Thomas M Sanger | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IP/User%20Story%20Tracker?csf=1&web=1&e=d6ukwS |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP/Design%20Deliverable%20Approval%20Evidence/FTS%20Intel%20Products%20-%20R3%20Design%20Deliverables%20GPO%20Approval_04.18.25.msg?csf=1&web=1&e=hT9mZd | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FTS-IP?csf=1&web=1&e=GnAXLg |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID358 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/MDM/BPD?csf=1&web=1&e=AcPfrd |  | Kitty Jiang, Mauricio Otarola | [5 empty] | 1
R1 | Build | Y | IDM 2.0 DELID552 | Multiple instances | Configuration Unit testing Results (CUT) |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/RE%20R1%20Build%20Deliverable%20Sign-Off.msg?csf=1&web=1&e=HAzPeX | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/CUT?csf=1&web=1&e=hDplC3 |  | 1
R1 | Build | Y | IDM 2.0 DELID548 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-09-20 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/RE%20R1%20Build%20Deliverable%20Sign-Off.msg?csf=1&web=1&e=HAzPeX | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/Custom%20Code%20(RICEFW)?csf=1&web=1&e=90wfMV |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID357 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=zWDjUF |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Archive/01%20Design/1.%20Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker/IDM%202.0%20DELID359_R2%20Data%20User%20Story%20Tracker.xlsx?d=we4e5d3fe30a34b76a7c83b06aee9bd61&csf=1&web=1&e=yrz8Ge |  | 1
R1 | Build | Y | IDM 2.0 DELID550 | Multiple instances | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | NA | NA |  | 1
R1 | Build | Y | IDM 2.0 DELID551 | Multiple instances | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/RE%20R1%20Build%20Deliverable%20Sign-Off.msg?csf=1&web=1&e=HAzPeX | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/FDS?csf=1&web=1&e=aFOUJd |  | 1
R1 | Build | Y | IDM 2.0 DELID557 | Multiple instances | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | NA | NA |  | 1
R1 | Build | Y | IDM 2.0 DELID553 | Multiple instances | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/RE%20R1%20Build%20Deliverable%20Sign-Off.msg?csf=1&web=1&e=HAzPeX | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/FUT?csf=1&web=1&e=k6rvlr |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID355 | Multiple instances | Requirement/User stories |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=zWDjUF |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Archive/01%20Design/1.%20Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker/IDM%202.0%20DELID359_R2%20Data%20User%20Story%20Tracker.xlsx?d=we4e5d3fe30a34b76a7c83b06aee9bd61&csf=1&web=1&e=yrz8Ge |  | 1
R1 | Build | Y | IDM 2.0 DELID554 | Multiple instances | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/CDD_MDG/CDD_Approvals?csf=1&web=1&e=uKhxn6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/CDD?csf=1&web=1&e=pp86wo |  | 1
R1 | Build | Y | IDM 2.0 DELID555 | Multiple instances | S/4HANA System Configuration |  |  | 2024-09-20 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Kitty Jiang, Mauricio Otarola |  |  | NA | NA |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID356 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=zWDjUF |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Archive/01%20Design/1.%20Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker/IDM%202.0%20DELID359_R2%20Data%20User%20Story%20Tracker.xlsx?d=we4e5d3fe30a34b76a7c83b06aee9bd61&csf=1&web=1&e=yrz8Ge |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID362 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/BPD?csf=1&web=1&e=1rYW9K |  | Renata Propko, Jim Midkiff, Sean Tillman, Bigil Kuriyan, Jayant Kashikar | [5 empty] | 1
R2 | Detailed design | Y | IDM 2.0 DELID361 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | Renata Propko, Jim Midkiff, Sean Tillman, Bigil Kuriyan, Jayant Kashikar |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID359 | Multiple instances | Requirement/User stories |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | Renata Propko, Jim Midkiff, Sean Tillman, Bigil Kuriyan, Jayant Kashikar |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID360 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2024-06-28 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | Renata Propko, Jim Midkiff, Sean Tillman, Bigil Kuriyan, Jayant Kashikar |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker/IDM%202.0%20DELID355_IDM%202.0%20DATA%20User%20Story%20Tracker.xlsx?d=w29f926c3d4854433915cac4951f00228&csf=1&web=1&e=DfOlBa |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID411 | Multiple instances | Business Process Documents (BPDs) including L4 details of T-code, Fiori app and Role |  |  | 2025-03-15 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Master%20Data/BPD?csf=1&web=1&e=RRwdSB |  | Candice S Linnell <candice.s.linnell@intel.com> | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=1rYW9K&CID=4cef5765%2D4080%2D4702%2Daf1a%2Dfa863bc7eb67&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cshrutisingh7%40deloitte%2Ecom&OR=Teams%2DHL&CT=1738924152786&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEyMDEwMDIyMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID403 | Multiple instances | Fit-Gap analysis (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker?csf=1&web=1&e=1x0DQE |  | Candice S Linnell <candice.s.linnell@intel.com> | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=Afgmwf |  | 1
R3 | Build | N/A | IDM 2.0 DELID537 | Multiple instances | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  | TRUE | 2026-03-06 |  |  | 09A. Master Data | 02. Being Developed |  | Lilibeth Lejarde | Candice S Linnell | [6 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/02%20Build/01.%20Sprint%20Deliverables/Master%20Data/FDS?csf=1&web=1&e=IwwnWK |  | 2
R3 | Detailed design | N/A | IDM 2.0 DELID401 | Multiple instances | Requirement/User stories |  |  | 2025-03-15 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker?csf=1&web=1&e=1x0DQE |  | Candice S Linnell <candice.s.linnell@intel.com> | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=Afgmwf |  | 1
R3 | Build | N/A | IDM 2.0 DELID530 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID519 |  | S/4HANA System Configuration |  |  | 2026-03-06 |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID402 | Multiple instances | Traceability matrix (User story tracker) |  |  | 2025-03-15 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker?csf=1&web=1&e=1x0DQE |  | Candice S Linnell <candice.s.linnell@intel.com> | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/MDM/User%20Story%20Tracker?csf=1&web=1&e=Afgmwf |  | 1
All | Environment Setup | Y | IDM 2.0 DELID368 | Single Instance | Coordinate with Intel security team for SQL Server Service Account creation |  |  |  | TRUE | N/A | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All | Environment Setup | Y | IDM 2.0 DELID369 | Single Instance | Data Migration - BODS Architecture proposed and finalized |  |  |  | TRUE | N/A | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All | Environment Setup | Y | IDM 2.0 DELID367 | Single Instance | SQL server landing and staging database setup |  |  |  | TRUE | N/A | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
R1 | Environment Setup | Y | IDM 2.0 DELID370 | Single Instance | BODS connectivity established for Source and Target systems |  |  |  | TRUE | N/A | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
R1 | Environment Setup | Y | IDM 2.0 DELID371 |  | Coordinate with Intel Platform team for Soruce and Target datastore creation. |  |  |  | TRUE | N/A | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
R1 | Build | Y | IDM 2.0 DELID571 | Multiple instances | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=90wfMV&CID=d8f7a822%2D7b08%2D44e8%2D81a5%2Da293acecb8a3&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FMaster%20Data&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=90wfMV&CID=d8f7a822%2D7b08%2D44e8%2D81a5%2Da293acecb8a3&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FMaster%20Data&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID572 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-09-20 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=90wfMV&CID=d8f7a822%2D7b08%2D44e8%2D81a5%2Da293acecb8a3&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FMaster%20Data&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=90wfMV&CID=d8f7a822%2D7b08%2D44e8%2D81a5%2Da293acecb8a3&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FMaster%20Data&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID573 | Multiple instances | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-09-20 | TRUE | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/CDD/CDD_Approvals?csf=1&web=1&e=edwX5o |  | Kitty Jiang, Mauricio Otarola |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Master%20Data/CDD/CDD?csf=1&web=1&e=fJ3g2M |  | 1
R1 | Build | Y | IDM 2.0 DELID547 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-09-20 | TRUE | N/A | 09B. Data Migration | 04. Complete | To understand more on this task with PMO team. | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=vJ476c |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=HyEmd0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=vJ476c |  | 1
R1 | Build | Y | IDM 2.0 DELID540 | Multiple instances | Identify scope of objects for Release-1, PrepareTechnical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 09B. Data Migration | 04. Complete | 4 out of 4 automated conversions TDD identified and approved. | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=pyZbz4 |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=53WyQe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=pyZbz4 |  | 1
R1 | Build | Y | IDM 2.0 DELID479 | Multiple instances | Technical Unit testing Results (TUT) for Release-1 Objects |  |  | 2024-09-20 | TRUE | N/A | 09B. Data Migration | 04. Complete | 4 out of 4 automated conversion Build & Unit test case approved. | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=pyZbz4 |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=53WyQe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09B.Data%20Migration/3.Final%20Deliverables/R1?csf=1&web=1&e=pyZbz4 |  | 1
R2 | Build | Y | IDM 2.0 DELID541 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE | N/A | 09B. Data Migration | 04. Complete | 20 automated conversions TDD drafted and approved. Pending CR0097- GTS licenses | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/2.Approvals?csf=1&web=1&e=v5R4hF |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/2.Approvals?csf=1&web=1&e=v5R4hF | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/1.Documents(TDS%26TDD)?csf=1&web=1&e=qgbkeb |  | 1
R2 | Build | Y | IDM 2.0 DELID482 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE | N/A | 09B. Data Migration | 04. Complete | 20 automated conversion Build & Unit test case approved. Pending CR0097- GTS licenses | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/2.Approvals?csf=1&web=1&e=v5R4hF |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/2.Approvals?csf=1&web=1&e=v5R4hF | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Data%20Migration/1.Documents(TDS%26TDD)?csf=1&web=1&e=qgbkeb |  | 1
R3 | Build | N/A | IDM 2.0 DELID542 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2026-03-06 |  | N/A | 09B. Data Migration | 01. Not Started | [11 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID485 |  | Technical Unit testing Results (TUT) |  |  | 2026-03-06 |  | N/A | 09B. Data Migration | 01. Not Started | [11 empty] | 2
All |  | Y | IDM 2.0 DELID377 | Single Instance | D-Dash ABAP code review |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID376 | Single Instance | D-Dash BODS code review |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID382 | Single Instance | Data migration - Job template preparation as per Intel standards |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID381 | Single Instance | E2E template preparation for preload, post load and reconciliation reports |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID383 | Single Instance | E2E training on Intel code migration and approval process |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID375 |  | Guard Rails for FS key areas |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
R2 | Build | Y | IDM 2.0 DELID558 | Multiple instances | Identify scope of objects for Release-2 , Prepare Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 09B. Data Migration | 05. Not Applicable | Duplicate of 166 | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=pyZbz4&CID=a75324cb%2D8431%2D483e%2D9153%2D68a69b6a0ecd&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F09B%2EData%20Migration%2F3%2EFinal%20Deliverables%2FR2&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=53WyQe&CID=da937252%2D07a8%2D4c64%2D9053%2Db174acd3ec98&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | NA |  | 1
All |  | Y | IDM 2.0 DELID379 | Multiple instances | Participate in Design Workshops discussions for Big 3 |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
All |  | Y | IDM 2.0 DELID378 | Single Instance | Project Timelines Preparation |  |  |  | TRUE |  | 09B. Data Migration | 04. Complete |  | Jaya Krishna Boyapalli | [9 empty] | 1
R2 | Build | Y | IDM 2.0 DELID559 | Multiple instances | Technical Unit testing Results (TUT) for R2 objects |  |  | 2024-12-06 | TRUE |  | 09B. Data Migration | 05. Not Applicable | Duplicate of 167 | Jaya Krishna Boyapalli | Lavaughn Y Urbano | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=pyZbz4&CID=a75324cb%2D8431%2D483e%2D9153%2D68a69b6a0ecd&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F09B%2EData%20Migration%2F3%2EFinal%20Deliverables%2FR2&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=53WyQe&CID=da937252%2D07a8%2D4c64%2D9053%2Db174acd3ec98&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2FOther%20Approvals&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | NA |  | 1
R1 | Detailed Design | Y | IDM 2.0 DELID419 | Multiple instances | ECA Platform CI/CD configuration |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) Zone | Lilibeth Lejarde, Neha Mehta | Robert Posegay | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Analytics/RE%20Approval%20Request%20for%20Platform%20setup.msg?csf=1&web=1&e=h5at16 | [7 empty] | 1
R1 | Detailed Design | Y | IDM 2.0 DELID420 | Multiple instances | ECA Platform Setup |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) Zone | Lilibeth Lejarde, Neha Mehta | Robert Posegay | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Analytics/RE%20Approval%20Request%20for%20Platform%20setup.msg?csf=1&web=1&e=h5at16 | [7 empty] | 1
R1 | Build | Y | IDM 2.0 DELID578 | Multiple instances | Data Specifications Document (DSD) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 10. Analytics | 02. Being Developed | ECA team to update | Neha Mehta | Vanessa Clark | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FAnalytics%2FFSD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID543 | Multiple instances | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 10. Analytics | 02. Being Developed | Build is in progress. Estimated Delivery by 11/04/24 | Neha Mehta | Vanessa Clark | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics/TDS?csf=1&web=1&e=zdbhTy |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics/TDS%20Approval%20Evidence?csf=1&web=1&e=XNFBYz | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics?csf=1&web=1&e=SK2ug2 |  | 1
R1 | Build | Y | IDM 2.0 DELID480 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-09-20 | TRUE | N/A | 10. Analytics | 02. Being Developed | TUT is in progress. Estimated Delivery by 11/04/24 | Neha Mehta | Vanessa Clark | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics/TUT?csf=1&web=1&e=uCeY50 |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics/TUT%20Approval%20Evidence?csf=1&web=1&e=rSnNKi | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Sprint%20Deliverables/Analytics?csf=1&web=1&e=SK2ug2 |  | 1
R2 | Detailed Design | Y | IDM 2.0 DELID421 | Multiple instances | ECA Platform CI/CD configuration |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) and IF(N) Zone | Lilibeth Lejarde, Neha Mehta | Robert Posegay | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Analytics/RE%20Approval%20Request%20for%20Platform%20setup.msg?csf=1&web=1&e=h5at16 | [7 empty] | 1
R2 | Detailed Design | Y | IDM 2.0 DELID422 | Multiple instances | ECA Platform Setup |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) and IF(N) Zone | Lilibeth Lejarde, Neha Mehta | Robert Posegay | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Analytics/RE%20Approval%20Request%20for%20Platform%20setup.msg?csf=1&web=1&e=h5at16 | [7 empty] | 1
R2 | Build | Y | IDM 2.0 DELID544 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 |  | N/A | 10. Analytics | 03. In Deliverable Review |  | Indra Singh | Vanessa Clark | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=5KcVkc&CID=c0d8fc5c%2D0ae1%2D47b8%2D9834%2D7c58e7b626ea&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FAnalytics&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID483 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 |  | N/A | 10. Analytics | 03. In Deliverable Review |  | Indra Singh | Vanessa Clark | [6 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=5KcVkc&CID=c0d8fc5c%2D0ae1%2D47b8%2D9834%2D7c58e7b626ea&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F01%2E%20Sprint%20Deliverables%2FAnalytics&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID545 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2026-03-06 |  | N/A | 10. Analytics | 01. Not Started |  | Neha Mehta | Vanessa Clark | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID486 |  | Technical Unit testing Results (TUT) |  |  | 2026-03-06 |  | N/A | 10. Analytics | 01. Not Started |  | Neha Mehta | Vanessa Clark | [8 empty] | 2
R1 | Build | Y | IDM 2.0 DELID280 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | [6 empty] | NA |  | 2
R1 | Build | Y | IDM 2.0 DELID277 | Multiple instances | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID204 | Multiple instances | Technical Fit-Gap analysis |  |  | 2024-06-28 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://app.smartsheet.com/sheets/7XqhPqj7qjF8qWGw67HWmf4PHMH36hf32j2FrR81 |  | Chris Woodburn <christopher.b.woodburn@intel.com> | [5 empty] | 1
R1 | Build | Y | IDM 2.0 DELID478 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 2
R2 | Build | Y | IDM 2.0 DELID538 |  | Custom Code (RICEFW) |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | [6 empty] | NA |  | 2
R2 | Build | Y | IDM 2.0 DELID474 |  | Integration Testing Cycle (ITC) Plan |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | [6 empty] | NA |  | 1
R2 | Build | Y | IDM 2.0 DELID404 | Single Instance | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=sdVc1M | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=sdVc1M |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID229 | Multiple instances | Technical Fit-Gap analysis |  |  | 2024-06-28 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://app.smartsheet.com/sheets/7XqhPqj7qjF8qWGw67HWmf4PHMH36hf32j2FrR81 |  | Chris Woodburn <christopher.b.woodburn@intel.com> | [5 empty] | 1
R2 | Build | Y | IDM 2.0 DELID481 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=BmsW38 | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=sdVc1M |  | 2
R3 | Build | N/A | IDM 2.0 DELID539 |  | Custom Code (RICEFW) |  |  | 2026-03-06 |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | Chris Woodburn | [8 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID475 |  | Integration Testing Cycle (ITC) Plan |  |  | 2026-03-06 |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | Chris Woodburn | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID263 | Multiple instances | Interface Controls Framework |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Infrastructure/Intel_Interface%20%26%20Data%20Conversion_Control_Framework.xlsx?d=wdbe249629871443983e0060bdd0a430c&csf=1&web=1&e=y4yDNV |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID265 | Single Instance | SAP System Instances Delivery (Infra, OS, Basis, Security profile) |  |  | 2024-10-18 | TRUE | N/A | 12. Infrastructure | 04. Complete | Design completed. Build completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Infrastructure/Basis%20Activity%20Tracker.xlsx?d=wb33e1c77abec43a3bc9a89f1d9924b7f&csf=1&web=1&e=0b780e |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FInfrastructure&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID266 | Single Instance | System Basis Configuration |  |  | 2024-10-18 | TRUE | N/A | 11. Technology | 04. Complete | Design completed. Basis config completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Infrastructure/Basis%20Activity%20Tracker.xlsx?d=wb33e1c77abec43a3bc9a89f1d9924b7f&csf=1&web=1&e=0b780e |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FInfrastructure&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID267 | Single Instance | System Connectivity for Testing |  |  | 2024-10-18 | TRUE | N/A | 11. Technology | 04. Complete | SAP to SAP connectivity completed. Middleware team (Technology) will handle integrations from SAP S/4 to B-apps | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Infrastructure/Basis%20Activity%20Tracker.xlsx?d=wb33e1c77abec43a3bc9a89f1d9924b7f&csf=1&web=1&e=0b780e |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak | TRUE |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R3 | Build | N/A | IDM 2.0 DELID405 | Single Instance | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2026-03-06 |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | Chris Woodburn | [8 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID254 | Multiple instances | Technical Fit-Gap analysis |  |  | 2024-10-18 | N/A | TRUE | 03. FPR | 04. Complete |  | D DenDanto, Prabesh Acharya | Angela Wolf, Shane Bethune | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B027383A2-A3D5-41C3-98DB-A18DC20A2BDA%7D&file=IDM%202.0%20DELID251%2C%20IDM%202.0%20DELID252%2C%20IDM%202.0%20DELID253%2C%20IDM%202.0%20DELID254_FPR%20User%20Story%20Tracker.xlsx&action=default&mobileredirect=true |  |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/FPR/RE_%20R3%20Design%20Closure%20Sign-Off.msg?csf=1&web=1&e=RWz8Qj | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=Z6JAdo&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cmpuvvala%40deloitte%2Ecom&OR=Teams%2DHL&CT=1741759063951&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMzEwNjAxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=b0b189a1%2Dc000%2D8000%2D35aa%2D2f7e4fc80e0b&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FFPR%2FUser%20Story%20Tracker&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID484 |  | Technical Unit testing Results (TUT) |  |  | 2026-03-06 |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | Chris Woodburn | [8 empty] | 3
All | Detailed design | Y | IDM 2.0 DELID197 | Single Instance | System Landscape Strategy |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete |  | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID215 | Multiple instances | SAP System Instances Delivery (Infra, OS, Basis, Security profile) |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | Design completed. Build completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID216 | Multiple instances | System Basis Configuration |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | Design completed. Basis config completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID217 | Multiple instances | System Connectivity for Testing |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | SAP to SAP connectivity completed. Middleware team (Technology) will handle integrations from SAP S/4 to B-apps | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID240 | Multiple instances | SAP System Instances Delivery (Infra, OS, Basis, Security profile) |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | Design completed. Build completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID241 | Multiple instances | System Basis Configuration |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | Design completed. Basis config completed for PF, DEV, MC1/2 | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID242 | Multiple instances | System Connectivity for Testing |  |  | 2024-06-28 | TRUE | N/A | 12. Infrastructure | 04. Complete | SAP to SAP connectivity completed. Middleware team (Technology) will handle integrations from SAP S/4 to B-apps | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure?csf=1&web=1&e=Pbn9gD |  | 1
All | Detailed design | Y | IDM 2.0 DELID199 | Single Instance | Deep dive SAP S/4HANA Security Strategy and Approach (D) |  |  | 2024-06-21 | TRUE | N/A | 13. Security | 04. Complete |  | Alycia Steiner, Natasha Laramie (R1/R2), Ashish Mistry (R3), Yazdani Shaik, Vijay Chavan | Dean Wehsels, Jim Brennan, Kasiviswanathan Muthu, Kristen Lewis, Suresh Bala, Wendy Dye | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security/IDM%202.0%20DELID199_Security%20and%20Controls%20Strategy%20and%20Approach%20Document.pptx.url?csf=1&web=1&e=ZKpcAi |  | Dean Wehsels, Jim Brennan, Kasiviswanathan Muthu, Kristen Lewis, Suresh Bala, Wendy Dye | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/Strategy%20and%20Approach%20Deliverable/Approvals%20and%20Decisions?csf=1&web=1&e=gwKpO6 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security/IDM%202.0%20DELID199_Security%20and%20Controls%20Strategy%20and%20Approach%20Document.pptx.url?csf=1&web=1&e=ZKpcAi |  | 1
All | Detailed design | Y | IDM 2.0 DELID205 | Single Instance | GRC AC and PC design document (D) |  |  | 2024-06-21 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie | Joshua Wise, Kasi Muthu, Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/GRC%20Access%20Controls%20%26%20Process%20Control%20Design%20Document/GRC%20AC%20And%20PC%20Deliverable%20Approvals?csf=1&web=1&e=lFadQs |  | Raj Valluri, Kasi Muthu, Joshua Wise |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security?csf=1&web=1&e=Yz0Cpe | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security?csf=1&web=1&e=Yz0Cpe |  | 1
All | Detailed design | Y | IDM 2.0 DELID209 | Single Instance | Privacy Business Process and Object Risk Ranking/Triage Questionnaire (A) |  |  | 2024-05-10 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook/Intel%20RICEFW%20Triage%20Questionnaire%20v2.xlsx?d=w8e15ac32eab74900a1f3f848a24f8b03&csf=1&web=1&e=up0lAZ |  | Jim Brennan |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook/%5BEXT%5D%20Re_%20%5BApproval%20Request%5D%20Intel%20IAO%20DPP%20Deliverable%20Sign-Off%20.pdf?csf=1&web=1&e=TCQPPy | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook?csf=1&web=1&e=uhytpm |  | 1
All | Detailed design | Y | IDM 2.0 DELID198 | Single Instance | Privacy by Design (PbD) guidelines and training materials |  |  | 2024-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook/Intel%20PbD%20Guidelines_V2.pdf?csf=1&web=1&e=6GcAVx |  | Jim Brennan |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook/%5BEXT%5D%20Re_%20%5BApproval%20Request%5D%20Intel%20IAO%20DPP%20Deliverable%20Sign-Off%20.pdf?csf=1&web=1&e=drKyck | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design%20Guidebook?csf=1&web=1&e=z0uDck |  | 1
All | Detailed design | Y | IDM 2.0 DELID298 | Multiple instances | Record Of Processing Activities (ROPA) (A) |  |  | 2024-11-29 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | eric.carlsen@intel.com | N/A - final deliverable within OneTrust tool maintained by Intel |  | eric.carlsen@intel.com |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/RoPA%20Links?csf=1&web=1&e=6oEx7u | N/A - final deliverable within OneTrust tool maintained by Intel |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID210 | Multiple instances | AGS SAP Role integration design document |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Vijay Chavan | Joshua Wise, Kristen Lewis, Rajeshwari Valluri | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8D1E6E95-7496-48DC-A197-6C74C67BDB43%7D&file=Intel%20IAO%20-%20Security%20IAM%20Design%20Document%20(SDD).xlsx&action=default&mobileredirect=true |  | Raj Valluri, Kristen Lewis, Joshua Wise |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=kHB33g&CID=c37c70c0%2D8cd6%2D4229%2D958b%2Df5c3521f3f38&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FSecurity%20and%20Controls%2FIAM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID207 | Multiple instances | Business Process Controls Framework (BPC RACM) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Tower Security Champion | TRUE |  |  |  |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID214 | Multiple instances | Data Conversion Control Framework |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Gary Nilsen, Rajeshwari Valluri, Sucheta A Bakhle | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Gary Nilsen, Sucheta A Bakhle | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID208 | Multiple instances | General Information Technology Controls Framework (ITGC) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R1 | Build | Y | IDM 2.0 DELID434 | Single Instance | GRC access control (AC) and process control (PC) Unit test results (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20access%20control%20(AC)%20and%20process%20control%20(PC)%20Unit%20test%20results%20(Artifact)?csf=1&web=1&e=jRO2S1 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/GRC%20AC%20and%20PC%20Config%20Deliverables/Approvals?csf=1&web=1&e=ZNpGOZ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20access%20control%20(AC)%20and%20process%20control%20(PC)%20Unit%20test%20results%20(Artifact)?csf=1&web=1&e=jRO2S1 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID213 | Multiple instances | Interface Controls Framework |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID212 | Multiple instances | Privacy Impact Assessment (PIA) (A) |  |  | 2024-07-12 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | N/A - final deliverable within OneTrust tool maintained by Intel |  |  |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/GTS%20and%20BR%20PIA_Jim%20Sign-off.pdf?csf=1&web=1&e=O7UfCp | N/A - final deliverable within OneTrust tool maintained by Intel |  | 1
R1 | Build | Y | IDM 2.0 DELID440 | Multiple instances | Production security role configuration (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Production%20security%20role%20configuration%20(Artifact)?csf=1&web=1&e=GFeCj2 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Production%20security%20role%20configuration%20(Artifact)?csf=1&web=1&e=GFeCj2 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID206 | Multiple instances | Production Security Role Design Document (SDD) (D) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie | Joshua Wise, Kasi Muthu, Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/App%20Sec?csf=1&web=1&e=AMvROl |  | Raj Valluri, Kasi Muthu, Joshua Wise, Tower security champions | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/Security%20Design%20Document%20(SDD)/SDD%20Approvals/SDD%20-%20Security%20Design%20Deliverable%20-%20Approvals?csf=1&web=1&e=MXbuUo | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/App%20Sec?csf=1&web=1&e=AMvROl |  | 1
R1 | Build | Y | IDM 2.0 DELID443 | Single Instance | Privacy by Design Assessment |  |  | 2024-09-20 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | eric.carlsen@intel.com | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=GPLBbk&CID=dfb43776%2D173d%2D4e4a%2Daad4%2D3d06792138be&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F13%2E%20Security%2F03%20Data%20%26%20Privacy%2FDeliverables%2FRICEFWs&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Eric Carlsen |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/RICEFWs/Privacy%20Office%20Sign%20offs/%5BEXT%5D%20RE_%20Privacy%20-%20R1_R2%20Build%20Sign-off.pdf?csf=1&web=1&e=PjFke3 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=GPLBbk&CID=dfb43776%2D173d%2D4e4a%2Daad4%2D3d06792138be&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F13%2E%20Security%2F03%20Data%20%26%20Privacy%2FDeliverables%2FRICEFWs&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID430 | Multiple instances | SAP GRC Segregation of Duties and Sensitive access matrix |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20Access%20Matrix%20Deliverable/Approvals?csf=1&web=1&e=a9tNro | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | 1
R1 | Build | Y | IDM 2.0 DELID570 | Single Instance | GRC AC and PC configuration document |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/GRC%20AC%20and%20PC%20Config%20Deliverables/Approvals?csf=1&web=1&e=se7h5b | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | 1
R1 | Test |  | IDM 2.0 DELID200 | Single Instance | SAP Infrastructure Cyber Risk Assessment |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Raj Valluri, Joshua Wise | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R1 | Build | Y | IDM 2.0 DELID426 | Multiple instances | SAP Segregation of Duties ruleset (SOD) build and unit test in GRC |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20Access%20Matrix%20Deliverable/Approvals?csf=1&web=1&e=J2xHZK | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | 1
R1 | Build | Y | IDM 2.0 DELID437 | Multiple instances | Security role unit test results (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Security%20role%20unit%20test%20results%20(Artifact)?csf=1&web=1&e=NilHy9 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Security%20role%20unit%20test%20results%20(Artifact)?csf=1&web=1&e=NilHy9 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID211 | Multiple instances | Transfer Impact Assessment (TIA) (A) |  |  | 2024-07-12 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | N/A - No TIAs were required to be conducted during this release. Sign off obtained for the same. |  |  |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/R1.R2%20PIA%20and%20TIA%20Sign%20off_Privacy%20Officepdf.pdf?csf=1&web=1&e=0ckFGw | N/A - No TIAs were required to be conducted during this release. |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID235 | Multiple instances | AGS SAP Role integration design document |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Vijay Chavan | Joshua Wise, Kristen Lewis, Rajeshwari Valluri | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8D1E6E95-7496-48DC-A197-6C74C67BDB43%7D&file=Intel%20IAO%20-%20Security%20IAM%20Design%20Document%20(SDD).xlsx&action=default&mobileredirect=true |  | Raj Valluri, Kristen Lewis, Joshua Wise |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=rG0DWu&CID=f29d2004%2De029%2D405e%2D888b%2D8a4bb0447eef&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FSecurity%20and%20Controls%2FIAM&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID232 | Multiple instances | Business Process Controls Framework (BPC RACM) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Tower Security Champion | TRUE |  |  |  |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID239 | Multiple instances | Data Conversion Control Framework |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Gary Nilsen, Rajeshwari Valluri, Sucheta A Bakhle | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Gary Nilsen, Sucheta A Bakhle | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID233 | Multiple instances | General Information Technology Controls Framework (ITGC) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R2 | Build | Y | IDM 2.0 DELID230 | Single Instance | GRC AC and PC configuration document |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/GRC%20AC%20and%20PC%20Config%20Deliverables/Approvals?csf=1&web=1&e=se7h5b | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | 2
R2 | Build | Y | IDM 2.0 DELID302 | Single Instance | GRC AC and PC configuration document |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/GRC%20AC%20and%20PC%20Config%20Deliverables/Approvals?csf=1&web=1&e=se7h5b | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20configuration%20document?csf=1&web=1&e=HM781l |  | 2
R2 | Build | Y | IDM 2.0 DELID435 | Single Instance | GRC access control (AC) and process control (PC) Unit test results (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20access%20control%20(AC)%20and%20process%20control%20(PC)%20Unit%20test%20results%20(Artifact)?csf=1&web=1&e=nVatK1 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/R1,%20R2,%20R3_GRC%20Unit%20Testing%20Results_IDM%202.0%20DELID434/Approvals?csf=1&web=1&e=WPvxXK | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/GRC%20access%20control%20(AC)%20and%20process%20control%20(PC)%20Unit%20test%20results%20(Artifact)?csf=1&web=1&e=nVatK1 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID238 | Multiple instances | Interface Controls Framework |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID237 | Multiple instances | Privacy Impact Assessment (PIA) (A) |  |  | 2024-07-12 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | N/A - final deliverable within OneTrust tool maintained by Intel |  |  |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/GTS%20and%20BR%20PIA_Jim%20Sign-off.pdf?csf=1&web=1&e=O7UfCp | N/A - final deliverable within OneTrust tool maintained by Intel |  | 1
R2 | Build | Y | IDM 2.0 DELID441 | Multiple instances | Production security role configuration (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Production%20security%20role%20configuration%20(Artifact)?csf=1&web=1&e=GFeCj2 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Production%20security%20role%20configuration%20(Artifact)?csf=1&web=1&e=GFeCj2 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID231 | Multiple instances | Production Security Role Design Document (SDD) (D) |  |  | 2024-07-26 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie | Joshua Wise, Kasi Muthu, Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/App%20Sec?csf=1&web=1&e=5NEfta |  | Raj Valluri, Kasi Muthu, Joshua Wise, Tower security champions | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/Security%20Design%20Document%20(SDD)/SDD%20Approvals/SDD%20-%20Security%20Design%20Deliverable%20-%20Approvals?csf=1&web=1&e=MXbuUo | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/App%20Sec?csf=1&web=1&e=5NEfta |  | 1
R2 | Build | Y | IDM 2.0 DELID444 | Single Instance | Privacy by Design Assessment |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | eric.carlsen@intel.com | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=GPLBbk&CID=dfb43776%2D173d%2D4e4a%2Daad4%2D3d06792138be&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F13%2E%20Security%2F03%20Data%20%26%20Privacy%2FDeliverables%2FRICEFWs&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Eric Carlsen |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/RICEFWs/Privacy%20Office%20Sign%20offs/%5BEXT%5D%20RE_%20Privacy%20-%20R1_R2%20Build%20Sign-off.pdf?csf=1&web=1&e=PjFke3 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=GPLBbk&CID=dfb43776%2D173d%2D4e4a%2Daad4%2D3d06792138be&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F13%2E%20Security%2F03%20Data%20%26%20Privacy%2FDeliverables%2FRICEFWs&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Build | Y | IDM 2.0 DELID431 | Multiple instances | SAP GRC Segregation of Duties and Sensitive access matrix |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20Access%20Matrix%20Deliverable/Approvals?csf=1&web=1&e=J2xHZK | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/SAP%20GRC%20Segregation%20of%20Duties%20and%20Sensitive%20access%20matrix?csf=1&web=1&e=FJcYWv |  | 1
R2 | Test |  | IDM 2.0 DELID353 | Multiple instances | SAP Infrastructure Cyber Risk Assessment |  |  | 2024-09-20 |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley, Joshua Wise | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID427 | Multiple instances | SAP Segregation of Duties ruleset (SOD) build and unit test in GRC |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/Segregation%20of%20Duties%20ruleset%20(SOD)%20build%20and%20unit%20test%20in%20GRC%20Deliverable?csf=1&web=1&e=fEmrQJ |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/Segregation%20of%20Duties%20ruleset%20(SOD)%20build%20and%20unit%20test%20in%20GRC%20Deliverable/Approvals?csf=1&web=1&e=EnxFDD | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/Segregation%20of%20Duties%20ruleset%20(SOD)%20build%20and%20unit%20test%20in%20GRC%20Deliverable?csf=1&web=1&e=vkjYAM |  | 1
R2 | Build | Y | IDM 2.0 DELID438 | Multiple instances | Security role unit test results (Artifact) |  |  | 2024-10-18 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Security%20role%20unit%20test%20results%20(Artifact)?csf=1&web=1&e=NilHy9 |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Security/Security%20role%20unit%20test%20results%20(Artifact)?csf=1&web=1&e=NilHy9 |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID236 | Multiple instances | Transfer Impact Assessment (TIA) (A) |  |  | 2024-07-12 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | Jim Brennan | N/A - No TIAs were required to be conducted during this release. Sign off obtained for the same. |  |  |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/R1.R2%20PIA%20and%20TIA%20Sign%20off_Privacy%20Officepdf.pdf?csf=1&web=1&e=0ckFGw | N/A - No TIAs were required to be conducted during this release. |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID260 | Multiple instances | AGS SAP Role integration design document |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Mohd Raghib Khan | Joshua Wise, Kristen Lewis, Rajeshwari Valluri | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/R3%20Design%20-%20Intel%20IAO%20-%20AGS%20Entitlements%20and%20Roles_V1.xlsx?d=w40f15bab17b845b7bfa28ff5f9761321&csf=1&web=1&e=Fx1Nln |  | Raj Valluri, Kristen Lewis, Joshua Wise | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/IAM/R3/IAM%20SDD/Re%20R3%20AGS%20RolesEntitlements%20Design%20Approval.msg?csf=1&web=1&e=J0WgJ1 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID257 | Multiple instances | Business Process Controls Framework (BPC RACM) |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/R3%20Consolidated%20RACM.xlsx?d=w4f98b5a6ee6449b48c15a98796555f96&csf=1&web=1&e=uYXmz2 |  | Raj Valluri, Tower Security Champion | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/02%20R3/01.%20R3%20Consolidated%20RACM/R3%20Controls%20-%20GPO%20Approvals?csf=1&web=1&e=zLI88S | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID264 | Multiple instances | Data Conversion Controls Framework |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Gary Nilsen, Rajeshwari Valluri, Sucheta A Bakhle | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Gary Nilsen, Sucheta A Bakhle | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/00%20Consolidated%20RACM/01%20ITGC/ITGC%20Deliverable%20Approvals/EXT%20RE%20Finalization%20of%20ITGC%20Interface%20and%20Conversion%20Controls%20RACM_Raj%20Valluri.msg?csf=1&web=1&e=YPC9YH | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID258 | Multiple instances | General Information Technology Controls Framework (ITGC) |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Nishat Ahmed | Rajeshwari Valluri, Ralph Veloria, Wendy R Dye | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/Intel%20SAP%20ITGC%20Controls.xlsx?d=w4fbe1dcfbd4a4460a96bd1521f886da4&csf=1&web=1&e=nmY8vX |  | Raj Valluri, Wendy Dye, Ralph Veloria | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/00%20Consolidated%20RACM/01%20ITGC/ITGC%20Deliverable%20Approvals/EXT%20RE%20Finalization%20of%20ITGC%20Interface%20and%20Conversion%20Controls%20RACM_Raj%20Valluri.msg?csf=1&web=1&e=YPC9YH | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID433 |  | GRC AC and PC configuration document |  |  | 2026-03-06 |  | N/A | 13. Security | 05. Not Applicable |  | Natasha Laramie (R1/R2), Ashish Mistry (R3)/ Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise |  |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | [5 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID436 | Single Instance | GRC access control (AC) and process control (PC) Unit test results (Artifact) |  |  | 2026-03-06 |  | N/A | 13. Security | 05. Not Applicable |  | Natasha Laramie (R1/R2), Ashish Mistry (R3)/ Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/02.%20Build/R1%26R2/R1,%20R2,%20R3_GRC%20Unit%20Testing%20Results_IDM%202.0%20DELID434/Approvals?csf=1&web=1&e=WPvxXK |  |  | 2
R3 | Detailed design | N/A | IDM 2.0 DELID262 | Multiple instances | Privacy Impact Assessment (PIA) (A) |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Sameeksha Garg | eric.carlsen@intel.com | N/A - final deliverable within OneTrust tool maintained by Intel |  | eric.carlsen@intel.com |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/RoPAs%20and%20PIAs%20for%20R3%20Design%20Final%20Sign%20off_Privacy%20Office.pdf?csf=1&web=1&e=m0a542 | N/A - final deliverable within OneTrust tool maintained by Intel |  | 1
R3 | Build | N/A | IDM 2.0 DELID442 | Multiple instances | Production security role configuration (Artifact) |  |  | 2026-03-06 |  | N/A | 13. Security | 05. Not Applicable |  | Vamsi Kanderi | deborah.whitely@intel.com |  |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | N/A - Artifact |  |  | 2
R3 | Detailed design | N/A | IDM 2.0 DELID256 | Multiple instances | Production Security Role Design Document (SDD) (D) |  |  | 2025-03-15 | TRUE | N/A | 13. Security | 04. Complete |  | Natasha Laramie, Sreevani Tadepalli | Candice S Linnell, Cari H Shim, Jill Matalon, Jorge Sanchez, Joshua Wise, Kasi Muthu, Pradnya Patil, Rajeshwari Valluri, Shamin A Shirodkar, Shane Bethune, Shelly Lafree | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/Intel%20R3%20-%20Security%20Design%20Document%20(SDD)_1_11+.xlsx?d=wb3f8a7bf16984a3bb92b7f185f6ae35a&csf=1&web=1&e=3HtFYw |  | Raj Valluri, Amith Vallabhaneni/Kasi Muthu, Tower security champions, Tower GPOs | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F13%2E%20Security%2F01%20SAP%20Application%20Security%2F01%2E%20Design%2FR3%2FSecurity%20Design%20Document%20SDD%2FApprovals%2C%20Conditional%20sign%2Doffs%2FSDD%20Final%20Signoff&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FSecurity&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID445 | Single Instance | Privacy by Design Assessment |  |  | 2026-03-06 |  | N/A | 13. Security | 05. Not Applicable |  | Sameeksha Garg | eric.carlsen@intel.com | N/A - Final deliverable within OneTrust tool maintained by Intel | [5 empty] | N/A - Final deliverable within OneTrust tool maintained by Intel |  | 2
R3 | Test | N/A | IDM 2.0 DELID354 | Multiple instances | SAP Infrastructure Cyber Risk Assessment |  |  | 2024-10-25 |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | Raj Valluri, Joshua Wise | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID304 | Multiple instances | SAP Segregation of Duties ruleset (SOD) build and unit test in GRC |  |  | 2026-04-30 |  | N/A | 13. Security | 02. Being Developed |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | [5 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID439 | Multiple instances | Security role unit test results (Artifact) |  |  | 2026-03-06 |  | N/A | 13. Security | 02. Being Developed |  | Natasha Laramie | Joshua Wise, Kasi Muthu, Rajeshwari Valluri | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/02%20Build/01.%20Sprint%20Deliverables/Security%20and%20Controls/Intel%20R3%20-%20Security%20Role%20Unit%20Test%20Results%20(Artifact)%20IDM%202.0%20DELID439?csf=1&web=1&e=Tcpo4v | [7 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID261 | Multiple instances | Transfer Impact Assessment (TIA) (A) |  |  | 2024-11-29 | N/A | N/A | 13. Security | 05. Not Applicable | N/A - No TIAs were required to be conducted during this release. Sign off obtained for the same. | Sameeksha Garg | eric.carlsen@intel.com | N/A - No TIAs were required to be conducted during this release. Sign off obtained for the same. |  | eric.carlsen@intel.com |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/GTS%20and%20BR%20PIA_Jim%20Sign-off.pdf?csf=1&web=1&e=u1SnRh | N/A |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID224 | Single Instance | Awareness communications for cFin, ProdCo, Product Costing, and TMGF releases |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Build | Y | IDM 2.0 DELID287 | Single Instance | Change Awareness Assessment for cFin , ProdCo, Product Costing, and TMGF releases (A) |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:w:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Awareness%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)/IDM%202.0%20DELID287_Proposed%20Questions%20for%20IAO%20Awareness%20Survey_Approved.docx?d=w4f24f146632a45b6b75e67e58b2a6c32&csf=1&web=1&e=yqMDhe | [5 empty] | https://intel.sharepoint.com/:w:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Awareness%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)/IDM%202.0%20DELID287_Proposed%20Questions%20for%20IAO%20Awareness%20Survey_Approved.docx?d=w4f24f146632a45b6b75e67e58b2a6c32&csf=1&web=1&e=yqMDhe |  | 1
R1 | Build | Y | IDM 2.0 DELID288 | Single Instance | Change Impact Assessments for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Impact%20Assessments%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID288_FPR%20ChangeScout%20CIA%20(R1_R2)_Approved.xlsx?d=w23bfb17aaba64e9e8ee4b8e8a87949b8&csf=1&web=1&e=jC6lxC | [5 empty] | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Impact%20Assessments%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID288_FPR%20ChangeScout%20CIA%20(R1_R2)_Approved.xlsx?d=w23bfb17aaba64e9e8ee4b8e8a87949b8&csf=1&web=1&e=jC6lxC |  | 1
R1 | Build | Y | IDM 2.0 DELID291 | Single Instance | Change Impact Summary by cFin, ProdCo, Product Costing, and TMGF (A) |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Impact%20Summary%20by%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20(A)/IDM%202.0%20DELID291_FPR%20Change%20Impact%20Summaries%20(R1_R2)_Approved.pptx?d=wd86a24ae9deb45aa8e8d15787cdd680c&csf=1&web=1&e=p1RuKF | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Impact%20Summary%20by%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20(A)/IDM%202.0%20DELID291_FPR%20Change%20Impact%20Summaries%20(R1_R2)_Approved.pptx?d=wd86a24ae9deb45aa8e8d15787cdd680c&csf=1&web=1&e=p1RuKF |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID219 | Single Instance | Change Management Project Plan |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Build | Y | IDM 2.0 DELID297 | Single Instance | Change Network Kickoff and Meeting Materials for cFin, ProdCo, Product Costing and TMGF releases (A) |  |  | 2024-11-19 | TRUE | N/A | 14. OCM | 03. In Deliverable Review | 10/31/24 - Approved by CR0122 to be pushed out to 11/19/24. | Laura Winterton | Jodi McGowan | [8 empty] | 1
R1 | Build | Y | IDM 2.0 DELID296 | Single Instance | Change Network Toolkit |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Network%20Toolkit?csf=1&web=1&e=AUlHyk | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Change%20Network%20Toolkit?csf=1&web=1&e=AUlHyk |  | 1
R1 | Build | Y | IDM 2.0 DELID290 | Single Instance | Communication materials for cFin, ProdCo, Product Costing, and TMGF releases (A) |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Communication%20materials%20for%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)?csf=1&web=1&e=ooYac3 | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Communication%20materials%20for%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)?csf=1&web=1&e=ooYac3 |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID223 | Single Instance | Leadership Engagement Approach (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | Tracy Ross, Solvig Kwei, Angela Wolf, Shane Bethune, Patricia Johnson |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/Approval%20Requested%20%20ERP%20Change%20Management%20Outstanding%20Deliverables.msg?csf=1&web=1&e=vEMLbp | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID221 | Single Instance | Program Communications and Engagement Plan |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  |  |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/Approval%20Requested%20%20ERP%20Change%20Management%20Outstanding%20Deliverables.msg?csf=1&web=1&e=vEMLbp | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID220 | Single Instance | Program Communications and Engagement Strategy |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID218 | Single Instance | Refined Change Strategy (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Detailed design | Y | IDM 2.0 DELID222 | Single Instance | Refined Leadership Walking Deck (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=3STRUG |  | 1
R1 | Build | Y | IDM 2.0 DELID289 | Single Instance | Stakeholder Assessment for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Stakeholder%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID289_FPR%20ERP_Initial%20Stakeholder%20Assessment%20(R1_R2)_Approved.xlsx?d=w7e11635ad0ed4438a8c7d86b0ddfe6b3&csf=1&web=1&e=PMaOd0 | [5 empty] | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Stakeholder%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID289_FPR%20ERP_Initial%20Stakeholder%20Assessment%20(R1_R2)_Approved.xlsx?d=w7e11635ad0ed4438a8c7d86b0ddfe6b3&csf=1&web=1&e=PMaOd0 |  | 1
R1 | Build | Y | IDM 2.0 DELID295 | Single Instance | Training Curriculum for cFin, ProdCo, Product Costing and TMGF releases |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Curriculum%20for%20cFin,%20ProdCo,%20Product%20Costing%20and%20TMGF%20releases/IDM%202.0%20DELID295_Training%20Curriculum_Release%201%20and%202_Approved.xlsx?d=w657835b3c2f04fda8758d1374d0b8036&csf=1&web=1&e=hm4Tj1 | [5 empty] | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Curriculum%20for%20cFin,%20ProdCo,%20Product%20Costing%20and%20TMGF%20releases/IDM%202.0%20DELID295_Training%20Curriculum_Release%201%20and%202_Approved.xlsx?d=w657835b3c2f04fda8758d1374d0b8036&csf=1&web=1&e=hm4Tj1 |  | 1
R1 | Build | Y | IDM 2.0 DELID293 | Single Instance | Training Development Plan |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Development%20Plan/IDM%202.0%20DELID293_Intel%20ERP%20Training%20Plan_Approved.pptx?d=wd3a988343fb44036b0d499b44e87f3a6&csf=1&web=1&e=zdqvHO | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Development%20Plan/IDM%202.0%20DELID293_Intel%20ERP%20Training%20Plan_Approved.pptx?d=wd3a988343fb44036b0d499b44e87f3a6&csf=1&web=1&e=zdqvHO |  | 1
R1 | Build | Y | IDM 2.0 DELID294 | Single Instance | Training Needs Assessment (A) |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Needs%20Assessment%20(A)/IDM%202.0%20DELID294_IAO%20ERP%20Training%20Needs%20Analysis_Approved.pptx?d=w37070c7f7cb54aceb264a123b5ea3743&csf=1&web=1&e=azB7EE | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Needs%20Assessment%20(A)/IDM%202.0%20DELID294_IAO%20ERP%20Training%20Needs%20Analysis_Approved.pptx?d=w37070c7f7cb54aceb264a123b5ea3743&csf=1&web=1&e=azB7EE |  | 1
R1 | Build | Y | IDM 2.0 DELID292 | Single Instance | Training Strategy |  |  | 2024-09-20 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Strategy/IDM%202.0%20DELID292_IAO%20ERP%20Training%20Strategy_Approved.pptx?d=we78c7704069e4186b035b35189837142&csf=1&web=1&e=MlD53B | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/OCM/Training%20Strategy/IDM%202.0%20DELID292_IAO%20ERP%20Training%20Strategy_Approved.pptx?d=we78c7704069e4186b035b35189837142&csf=1&web=1&e=MlD53B |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID249 | Single Instance | Awareness communications for cFin, ProdCo, Product Costing, and TMGF releases |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  |  |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/Approval%20Requested%20%20ERP%20Change%20Management%20Outstanding%20Deliverables.msg?csf=1&web=1&e=vEMLbp | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Build | Y | IDM 2.0 DELID456 | Single Instance | Change Awareness Assessment for cFin , ProdCo, Product Costing, and TMGF releases (A/D) |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=MU7Zdt&CID=e8797a7f%2D33b1%2D4fa4%2D8ca0%2D5dd6e52035d9&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F02%2E%20Non%2DSprint%20Deliverables%2FOCM%2FChange%20Awareness%20Assessment%20for%20cFin%20%2C%20ProdCo%2C%20Product%20Costing%2C%20and%20TMGF%20releases%20%28AD%29 | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=MU7Zdt&CID=e8797a7f%2D33b1%2D4fa4%2D8ca0%2D5dd6e52035d9&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F02%20Build%2F02%2E%20Non%2DSprint%20Deliverables%2FOCM%2FChange%20Awareness%20Assessment%20for%20cFin%20%2C%20ProdCo%2C%20Product%20Costing%2C%20and%20TMGF%20releases%20%28AD%29 |  | 1
R2 | Build | Y | IDM 2.0 DELID457 | Single Instance | Change Impact Assessments for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Impact%20Assessments%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID457%20Release%202%20ERP%20Change%20Impacts_Approved.xlsx?d=wc72040097b584e3ab3d624f2856a6ae1&csf=1&web=1&e=fnOsNe |  | Jill Matalon, Jorge Sanchez, Candi Linnell, Angela Wolf, Shane Bethune |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Impact%20Assessments%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases/IDM%202.0%20DELID457%20Release%202%20ERP%20Change%20Impacts_Approved.xlsx?d=wc72040097b584e3ab3d624f2856a6ae1&csf=1&web=1&e=fnOsNe |  | 1
R2 | Build | Y | IDM 2.0 DELID460 | Single Instance | Change Impact Summary by cFin, ProdCo, Product Costing, and TMGF (A) |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Impact%20Summary%20by%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20(A)/IDM%202.0%20DELID460%20R2%20Change%20Impact%20Summary_Approved.pptx?d=w8d269b4d49eb4515aa7acada273e8b0d&csf=1&web=1&e=cbUtHp | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Impact%20Summary%20by%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20(A)/IDM%202.0%20DELID460%20R2%20Change%20Impact%20Summary_Approved.pptx?d=w8d269b4d49eb4515aa7acada273e8b0d&csf=1&web=1&e=cbUtHp |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID244 | Single Instance | Change Management Project Plan |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Build | Y | IDM 2.0 DELID450 | Single Instance | Change Network Kickoff and Meeting Materials for cFin, ProdCo, Product Costing and TMGF releases (A) |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Network%20Kickoff%20and%20Meeting%20Materials%20for%20cFin,%20ProdCo,%20Product%20Costing%20and%20TMGF%20releases%20(A)?csf=1&web=1&e=KHRMTC | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Network%20Kickoff%20and%20Meeting%20Materials%20for%20cFin,%20ProdCo,%20Product%20Costing%20and%20TMGF%20releases%20(A)?csf=1&web=1&e=KHRMTC |  | 1
R2 | Build | Y | IDM 2.0 DELID449 | Single Instance | Change Network Toolkit |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Network%20Toolkit/IDM%202.0%20DELID449_Change%20Agent%20Toolkit_Approved.pptx?d=wac663a88312f4da39422863645c4d27c&csf=1&web=1&e=J0Jki1 | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Change%20Network%20Toolkit/IDM%202.0%20DELID449_Change%20Agent%20Toolkit_Approved.pptx?d=wac663a88312f4da39422863645c4d27c&csf=1&web=1&e=J0Jki1 |  | 1
R2 | Build | Y | IDM 2.0 DELID459 | Single Instance | Communication materials for cFin, ProdCo, Product Costing, and TMGF releases (A) |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:w:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Communication%20materials%20for%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)/IDM%202.0%20DELID459_FPR%20R2%20Change%20Network%20Nomination%20Comm%20for%20FP%26A%20Leads_Approved.docx?d=wfd1814298b884429bc1386abac612a8b&csf=1&web=1&e=wHy86a | [5 empty] | https://intel.sharepoint.com/:w:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Communication%20materials%20for%20cFin,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases%20(A)/IDM%202.0%20DELID459_FPR%20R2%20Change%20Network%20Nomination%20Comm%20for%20FP%26A%20Leads_Approved.docx?d=wfd1814298b884429bc1386abac612a8b&csf=1&web=1&e=wHy86a |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID248 | Single Instance | Leadership Engagement Approach (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete | CSA of OTC leadership still pending due to GPO's jury duty. To be ratified 7/9. | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | Tracy Ross, Scott Gaudette, Jen Fullerton, Patricia Johnson |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/Approval%20Requested%20%20ERP%20Change%20Management%20Outstanding%20Deliverables.msg?csf=1&web=1&e=vEMLbp | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID246 | Single Instance | Program Communications and Engagement Plan |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  |  |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/Approval%20Requested%20%20ERP%20Change%20Management%20Outstanding%20Deliverables.msg?csf=1&web=1&e=vEMLbp | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID245 | Single Instance | Program Communications and Engagement Strategy |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID243 | Single Instance | Refined Change Strategy (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Detailed design | Y | IDM 2.0 DELID247 | Single Instance | Refined Leadership Walking Deck (A) |  |  | 2024-06-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management?csf=1&web=1&e=Grp7pn |  | 1
R2 | Build | Y | IDM 2.0 DELID458 | Single Instance | Stakeholder Assessment for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Stakeholder%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases?csf=1&web=1&e=LNPGT5 |  | Jill Matalon, Jorge Sanchez, Candi Linnell, Angela Wolf, Shane Bethune |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/Stakeholder%20Assessment%20for%20cFin%20,%20ProdCo,%20Product%20Costing,%20and%20TMGF%20releases?csf=1&web=1&e=LNPGT5 |  | 1
R2 | Build | Y | IDM 2.0 DELID448 | Single Instance | Training Curriculum for cFin, ProdCo, Product Costing and TMGF releases |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID448%20IAO%20ERP_Training%20Curriculum_Release%202_Approved.xlsx?d=wf56dc55557744d82a23fb4b7b5f8ea6a&csf=1&web=1&e=AfgOv9 |  | Jill Matalon, Jorge Sanchez, Candi Linnell, Angela Wolf, Shane Bethune |  |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID448%20IAO%20ERP_Training%20Curriculum_Release%202_Approved.xlsx?d=wf56dc55557744d82a23fb4b7b5f8ea6a&csf=1&web=1&e=AfgOv9 |  | 1
R2 | Build | Y | IDM 2.0 DELID446 | Single Instance | Training Development Plan |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID446%20R2%20Training%20Development%20Plan.pptx?d=wa92b366a019b40c789f5e6b8435e5660&csf=1&web=1&e=XuTKQ9 | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID446%20R2%20Training%20Development%20Plan.pptx?d=wa92b366a019b40c789f5e6b8435e5660&csf=1&web=1&e=XuTKQ9 |  | 1
R2 | Build | Y | IDM 2.0 DELID447 | Single Instance | Training Needs Assessment (A) |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID448%20IAO%20ERP_Training%20Curriculum_Release%202.xlsx?d=wf56dc55557744d82a23fb4b7b5f8ea6a&csf=1&web=1&e=B005yM | [5 empty] | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID448%20IAO%20ERP_Training%20Curriculum_Release%202.xlsx?d=wf56dc55557744d82a23fb4b7b5f8ea6a&csf=1&web=1&e=B005yM |  | 1
R2 | Build | Y | IDM 2.0 DELID461 | Single Instance | Training Strategy |  |  | 2024-10-18 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID461%20IAO%20ERP%20Training%20Strategy.pptx?d=w657143df9dfc4eb6845e6fd0094ddf07&csf=1&web=1&e=0iRrSw | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/OCM/IDM%202.0%20DELID461%20IAO%20ERP%20Training%20Strategy.pptx?d=w657143df9dfc4eb6845e6fd0094ddf07&csf=1&web=1&e=0iRrSw |  | 1
R3 | Test | N/A | IDM 2.0 DELID274 | Single Instance | Awareness communications for cFin, ProdCo, Product Costing, and TMGF releases |  |  | 2026-02-28 |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID462 |  | Change Awareness Assessment for cFin , ProdCo, Product Costing, and TMGF releases (A) |  |  | 2026-08-14 |  | N/A | 14. OCM | 01. Not Started | CR01618 | Laura Winterton | [9 empty] | 1
R3 | Detailed Design | N/A | IDM 2.0 DELID463 | Single Instance | Change Impact Assessments for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2025-03-15 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/ERP%20R3%20Change%20Impacts.xlsx?d=w765e6ecce44140a693c9db827981eb4a&csf=1&web=1&e=YS42Bo |  | Shane Bethune, Angela Wolf, Tom Sanger, Shelly LaFree, Jill Matalon, Shamin Shirodkar, Candie Linnell | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management?csf=1&web=1&e=2HTpdr |  | 1
R3 | Build | N/A | IDM 2.0 DELID466 | Single Instance | Change Impact Summary by cFin, ProdCo, Product Costing, and TMGF (A) |  |  | 2026-05-15 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID455 | Multiple instances | Change Network Kickoff and Meeting Materials for cFin, ProdCo, Product Costing and TMGF releases (A) |  |  | 2026-06-26 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID454 | Single Instance | Change Network Toolkit |  |  | 2026-06-26 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID465 | Single Instance | Communication materials for cFin, ProdCo, Product Costing, and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 05. Not Applicable | To be completed in Test | Laura Winterton | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID273 | Single Instance | Leadership Engagement Approach (A) |  |  | 2025-12-18 | TRUE | N/A | 14. OCM | 04. Complete | CR0618 | Laura Winterton | Cindie Blackmer | LINK | [5 empty] | LINK |  | 1
R3 | Build | N/A | IDM 2.0 DELID271 | Single Instance | Program Communications and Engagement Plan |  |  | 2026-04-13 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID270 | Single Instance | Program Communications and Engagement Strategy |  |  | 2026-04-13 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Detailed design | N/A | IDM 2.0 DELID268 | Single Instance | Refined Change Strategy (A) |  |  | 2026-03-13 | TRUE | N/A | 14. OCM | 04. Complete | CR0618 | Laura Winterton | Samantha Filoso | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management/Change%20Management/IDM%202.0%20DELID218%20and%20DELID243_R1_R2_Refined%20Change%20Strategy%20(A)_Approved.pptx?d=wed7739ce5a464ca4b2fadf392984f8c0&csf=1&web=1&e=ay1pcR |  |  |  | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Change%20Management?csf=1&web=1&e=2HTpdr |  | 1
R3 | Build | N/A | IDM 2.0 DELID272 | Single Instance | Refined Leadership Walking Deck (A) |  |  | 2026-12-19 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | Cindie Blackmer | LINK |  |  | TRUE |  |  | LINK |  | 1
R3 | Test | N/A | IDM 2.0 DELID464 | Single Instance | Stakeholder Assessment for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2026-10-09 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID453 | Single Instance | Training Curriculum for cFin, ProdCo, Product Costing and TMGF releases |  |  | 2026-06-19 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID451 | Single Instance | Training Development Plan |  |  | 2026-07-17 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID452 | Single Instance | Training Needs Assessment (A) |  |  | 2026-06-19 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID467 | Single Instance | Training Strategy |  |  | 2026-06-19 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R1 | Build | Y | IDM 2.0 DELID286 | Single Instance | Cutover plan for SIT/UAT |  |  | 2024-09-20 | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Non-Sprint%20Deliverables/Cutover/Cutover%20plan%20for%20SIT%20and%20UAT/FW%20Cutover%20Plan%20for%20SIT%20%20UAT.msg?csf=1&web=1&e=n9rr7l | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=fBZLKx&cid=e59d2453%2D380d%2D4ccb%2Db67a%2D6e133cc8a07b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&OR=Teams%2DHL&CT=1709655218221&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDAyMDExOTMwMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FNon%2DSprint%20Deliverables%2FCutover%2FCutover%20plan%20for%20SIT%20and%20UAT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID285 | Single Instance | Cutover strategy |  |  | 2024-09-20 | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [6 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/15.%20Cutover/07.%20Working%20Folder/R1%20Cutover%20Kick%20off/Cutover%20Kick%20Off.pptx?d=w2c74d01473884f0dbf75ac69d35ad137&csf=1&web=1&e=lXBpSn |  | 1
R1 | Build | Y | IDM 2.0 DELID428 | Single Instance | Mock Cutover Plan |  |  |  | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [6 empty] | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/15.%20Cutover/01.%20Release%201/MC%201/R1%20MC1%20IAO%20Cutover%20Plan%20Extract.xlsx?d=w35acdf9ab0634edc934b3f663ed27246&csf=1&web=1&e=nunftY |  | 1
R2 | Build | Y | IDM 2.0 DELID468 | Single Instance | Cutover plan for SIT/UAT |  |  |  | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/Cutover/R2_MC1%20Cutover%20plan%20for%20SIT%26UAT/_EXT_%20Re_%20Cutover%20deliverables%20for%20Release%202%20MC1.msg?csf=1&web=1&e=Oi1wpk | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/Cutover/R2_MC1%20Cutover%20plan%20for%20SIT%26UAT?csf=1&web=1&e=FecQqL |  | 1
R2 | Build | Y | IDM 2.0 DELID470 | Single Instance | Cutover strategy |  |  |  | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/Cutover/R2_MC1%20Cutover%20plan%20for%20SIT%26UAT/_EXT_%20Re_%20Cutover%20deliverables%20for%20Release%202%20MC1.msg?csf=1&web=1&e=Oi1wpk | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/15.%20Cutover/07.%20Working%20Folder/R2%20Cutover%20Kick%20off/R2%20MC1/R2%20Cutover%20Kick%20Off.pptx?d=w2a6e22dfae22415f93c175bf39bedf74&csf=1&web=1&e=HfBv7E |  | 1
R3 | Build | N/A | IDM 2.0 DELID469 |  | Cutover plan for SIT/UAT |  |  | 2026-03-06 |  | N/A | 15. Cutover | 01. Not Started |  | Jinesh Jain | Babu Jadam | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID471 |  | Cutover strategy |  |  | 2026-03-06 |  | N/A | 15. Cutover | 01. Not Started |  | Jinesh Jain | Babu Jadam | [8 empty] | 2
R1 | Build | Y | IDM 2.0 DELID283 | Single Instance | Integration Testing Cycle (ITC) Plan |  |  | 2024-09-20 | TRUE | N/A | 16. Testing | 04. Complete |  | Anurag Kumar | Chris Woodburn | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/07.%20Working%20Documents/ITC%201%20Kick-off/IAO%20Program%20R1%20ITC1%20Kick-off.pptx?d=web813ba39b214ba9ab0e9c211bad78f1&csf=1&web=1&e=Jw5fIL | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/07.%20Working%20Documents/ITC%201%20Kick-off/IAO%20Program%20R1%20ITC1%20Kick-off.pptx?d=web813ba39b214ba9ab0e9c211bad78f1&csf=1&web=1&e=fgitZT |  | 1
R1 | Build | Y | IDM 2.0 DELID284 | Single Instance | ITC Test catalog and Test cases |  |  | 2024-09-20 | TRUE | N/A | 16. Testing | 04. Complete |  | Anurag Kumar | Chris Woodburn | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals?csf=1&web=1&e=i2hXWa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1?csf=1&web=1&e=Kn1Xx9 |  | 1
R1 | Build | Y | IDM 2.0 DELID282 | Single Instance | Test strategy (including Testing approach, Responsibilities, Data requirements, Entry & Exit criteria, Signoff process and Bug management) |  |  | 2024-09-20 | TRUE | N/A | 16. Testing | 04. Complete |  | Anurag Kumar | Chris Woodburn | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/01.%20Plan/IAO%20Program%20Overarching%20Testing%20Strategy%20Draft.pptx?d=wc185a2b604dd444798dc2980d86406e6&csf=1&web=1&e=9FOKcy | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Test%20Strategy?csf=1&web=1&e=alyDdH&xsdata=MDV8MDJ8fDQ5MGNjNjdhNTkxNzRiYzg3MWEwMDhkZTBiMmFlZmQ0fDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg5NjA0NzYxNzM0MTM1NzN8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKRFFTSTZJbFJsWVcxelgwRlVVRk5sY25acFkyVmZVMUJQVEU5R0lpd2lWaUk2SWpBdU1DNHdNREF3SWl3aVVDSTZJbGRwYmpNeUlpd2lRVTRpT2lKUGRHaGxjaUlzSWxkVUlqb3hNWDA9fDF8TDJOb1lYUnpMekU1T21aaVltVTFPR1U0TVdRNE5EUTVPVEU0WldRd1pEUmlNMkl3WmpRMU5XWTFRSFJvY21WaFpDNTJNaTl0WlhOellXZGxjeTh4TnpZd05EVXdOelkwTURJMnw3NzY4NGU3YzhkNTU0YzlkOTE4YTA4ZGUwYjJhZWZkMnw4ZjU3ODZmODliMzI0YTg5OTM4NDg5NmJhNzhhNzYxNg%3D%3D&sdata=ZXVTSUZPNkJndE1hZWM4Z2ZtaGtUb0VMd1AvUGIxVndyY0V4NHpkeGJNdz0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Crnirantar%40deloitte.com |  | 1
R2 | Build | Y | IDM 2.0 DELID472 |  | ITC Test catalog and Test cases |  |  |  | TRUE | N/A | 16. Testing | 04. Complete |  | Anurag Kumar | Chris Woodburn | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2?csf=1&web=1&e=13vHfN |  |  |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals?csf=1&web=1&e=fEriAl | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2?csf=1&web=1&e=13vHfN |  | 1
R2 | Build | Y | IDM 2.0 DELID429 | Single Instance | Mock Cutover Plan |  |  |  | TRUE | N/A | 15. Cutover | 04. Complete |  | Jinesh Jain | Babu Jadam | [5 empty] | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/02.%20Non-Sprint%20Deliverables/Cutover/R2_MC1%20Cutover%20plan%20for%20SIT%26UAT/_EXT_%20Re_%20Cutover%20deliverables%20for%20Release%202%20MC1.msg?csf=1&web=1&e=Oi1wpk | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/15.%20Cutover/02.%20Release%202/MC%201/R2%20MC1%20IAO%20Cutover%20Plan%20Extract.xlsx?d=we5e8dc0308de41bba08a800a5fe08594&csf=1&web=1&e=3Qq0QT |  | 1
R2 | Build | Y | IDM 2.0 DELID476 |  | Test strategy (including Testing approach, Responsibilities, Data requirements, Entry & Exit criteria, Signoff process and Bug management) |  |  |  | TRUE | N/A | 16. Testing | 04. Complete |  | Anurag Kumar | Chris Woodburn | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/01.%20Plan/IAO%20Program%20Overarching%20Testing%20Strategy%20Draft.pptx?d=wc185a2b604dd444798dc2980d86406e6&csf=1&web=1&e=A2OHKe | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Test%20Strategy?csf=1&web=1&e=dVfRaz&xsdata=MDV8MDJ8fDQ5MGNjNjdhNTkxNzRiYzg3MWEwMDhkZTBiMmFlZmQ0fDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg5NjA0NzYxNzM0Mzg1NDN8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKRFFTSTZJbFJsWVcxelgwRlVVRk5sY25acFkyVmZVMUJQVEU5R0lpd2lWaUk2SWpBdU1DNHdNREF3SWl3aVVDSTZJbGRwYmpNeUlpd2lRVTRpT2lKUGRHaGxjaUlzSWxkVUlqb3hNWDA9fDF8TDJOb1lYUnpMekU1T21aaVltVTFPR1U0TVdRNE5EUTVPVEU0WldRd1pEUmlNMkl3WmpRMU5XWTFRSFJvY21WaFpDNTJNaTl0WlhOellXZGxjeTh4TnpZd05EVXdOelkwTURJMnw3NzY4NGU3YzhkNTU0YzlkOTE4YTA4ZGUwYjJhZWZkMnw4ZjU3ODZmODliMzI0YTg5OTM4NDg5NmJhNzhhNzYxNg%3D%3D&sdata=UUFEUGJIVGltS3g0U0dja1FqNmVRYjlQbGJJdE0xcTdyNDJJL0JERUNTMD0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Crnirantar%40deloitte.com |  | 1
R3 | Build | N/A | IDM 2.0 DELID473 |  | ITC Test catalog and Test cases |  |  | 2026-03-06 |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID305 | Single Instance | Mock Cutover Plan |  |  | 2026-03-06 |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID477 |  | Test strategy (including Testing approach, Responsibilities, Data requirements, Entry & Exit criteria, Signoff process and Bug management) |  |  | 2026-03-06 |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R1 | Test |  | IDM 2.0 DELID318 | Single Instance | 200 Automated test cases & Results |  |  |  |  | N/A | 16. Testing | 05. Not Applicable | 200 automation test cases are up to R5 | Vivekananda Maiya | Gunaranjan Viswanathan | N/A | Vivekananda Maiya |  | TRUE | TRUE | N/A | N/A |  | 1
R1 | Test |  | IDM 2.0 DELID319 | Single Instance | Business Continuity Plan (BCP) |  |  |  |  | N/A | 01. PMO | 01. Not Started | BCP documents uploaded into Intel eGRC | Viswa Anakkara Vadakkath | Aishwarya Bhat | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Business%20Readiness?csf=1&web=1&e=fXDnGg | Katie Kobernyk |  |  | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Business%20Readiness?csf=1&web=1&e=fXDnGg |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID351 | Single Instance | Change Management and Training knowledge transfer plan including ChangeScout data export (A) |  |  |  | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton |  | TRUE | TRUE |  | LINK |  | 1
R1 | Test |  | IDM 2.0 DELID326 | Single Instance | Change Readiness Assessment for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2025-05-19 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton |  | TRUE | TRUE |  | LINK |  | 1
R1 | Test |  | IDM 2.0 DELID327 | Single Instance | Communication materials for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2025-05-19 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton | Emily Bontrager, Solvig Kwei | TRUE | TRUE |  | LINK |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID350 | Single Instance | Communications and Stakeholder Engagement Materials for Cutover / Go-Live / Hypercare for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton |  | TRUE | TRUE |  | LINK |  | 1
R1 | Test |  | IDM 2.0 DELID337 | Single Instance | Controls test step requirements and validation results in SIT and/or UAT |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Controls%20test%20validations%20approval?csf=1&web=1&e=wdZhbF | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Controls%20test%20validations%20approval?csf=1&web=1&e=wdZhbF | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Controls%20test%20validations%20approval?csf=1&web=1&e=wdZhbF |  | 1
R1 | Test |  | IDM 2.0 DELID306 | Single Instance | Conversion Load Metrics based on Mock Cutover execution |  |  |  |  | N/A | 15. Cutover | 01. Not Started |  | Jaya Krishna Boyapalli | Julie Fawdington | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Conversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=ydmbBh | Jaya Krishna Boyapalli |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Conversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=Lo9wBU | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F03%20Test%2FConversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&newTargetListUrl=%2Fsites%2Finteldeloitteiao%2FShared%20Documents&viewpath=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID349 | Single Instance | Cutover validation results for manually configured controls in production and cutover dress rehearsal environment |  |  |  |  | N/A | 13. Security | 04. Complete | Controls confirmation should be security team. | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Controls%20test%20validations%20approval?csf=1&web=1&e=ursibQ | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F03%20Test%2FControls%20test%20validations%20approval%2FR1%20Automated%20controls%20ITC%20Approvals&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&csf=1&web=1&e=ursibQ&CID=2a8cfd59%2De015%2D43e5%2D8044%2D05fd7e80ba18&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Controls%20test%20validations%20approval?csf=1&web=1&e=ursibQ |  | 1
R1 | Test |  | IDM 2.0 DELID338 | Multiple instances | Data Privacy controls validation results in SIT and UAT |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R1 | Test |  | IDM 2.0 DELID320 | Single Instance | Detailed cutover plan for Go Live |  |  |  |  | N/A | 15. Cutover | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=0pJNDY | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=nzwPn3 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=0pJNDY |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID341 | Single Instance | Final Hypercare Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Final%20Hypercare%20Plan?csf=1&web=1&e=5qLS8K | Gaurav Tyagi, Vivek Sahni |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan/_EXT_%20Release%201%20Production%20Cutover%20Combined%20APAC_US%20Status%20Call-%20APPROVED%20TO%20START%204_18.msg?csf=1&web=1&e=eEae5z | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Final%20Hypercare%20Plan?csf=1&web=1&e=5qLS8K |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID339 | Single Instance | Final S/4HANA Cutover Plan |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=0pJNDY | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan/_EXT_%20Release%201%20Production%20Cutover%20Combined%20APAC_US%20Status%20Call-%20APPROVED%20TO%20START%204_18.msg?csf=1&web=1&e=UR0bda | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=0pJNDY |  | 1
R1 | Test |  | IDM 2.0 DELID322 | Single Instance | Go/No-Go criteria |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Alpna Gainda | Loni Adams | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20Go%20Live%20Criteria%20and%20Last%20checkpoint%20results/R1%20Go%20Live%20Readiness%20Evaluation%20Chkpt%203%20summary_WW19.5.xlsx?d=w2489f8ed53594ce686a0c8603d183d47&csf=1&web=1&e=B36f4l | Alpna Gainda |  | TRUE | TRUE |  |  |  | 1
R1 | Test |  | IDM 2.0 DELID332 | Single Instance | GRC AC and PC SIT test results (A) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls?csf=1&web=1&e=OCNBzP | Yazdani Shaik | N/A - artifact | TRUE | TRUE | N/A - artifact | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls?csf=1&web=1&e=OCNBzP |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID346 | Single Instance | Hypercare execution results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results?csf=1&web=1&e=havu2d | Gaurav Tyagi, Vivek Sahni |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results?csf=1&web=1&e=havu2d |  | 1
R1 | Test |  | IDM 2.0 DELID323 | Single Instance | Hypercare/Post Go-Live Support Strategy & Plan |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Gaurav Tyagi | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Post%20GoLive%20Support%20Strategy%20%26%20Plan?csf=1&web=1&e=1AIZkc | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Post%20GoLive%20Support%20Strategy%20%26%20Plan?csf=1&web=1&e=1AIZkc |  | 1
R1 | Test |  | IDM 2.0 DELID777 | Single Instance | ITC1 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete | ITC 1 Exit attached; Attached PPT with links to approval emails | Prabesh Acharya | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%201%20Test%20Results/IAO%20Program%20R1%20ITC1_Exit_TestResult.pptx?d=wa83feb9d55604232a68a13ceecade43f&csf=1&web=1&e=pXomfs | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%201%20Test%20Results/R1ITC1%20Test%20Result%20Approval_%5BEXT%5D%20RE-%20Requesting%20approval%20for%20R1%20ITC1,%20R1%20ITC2%20and%20R2%20ITC1%20FPR%20Test%20Results.eml?csf=1&web=1&e=8jieWO | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%201%20Test%20Results?csf=1&web=1&e=5xNZIB |  | 1
R1 | Test |  | IDM 2.0 DELID690 | Single Instance | ITC2 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete | ITC 2 Exit attached; Attached PPT with links to approval emails | Prabesh Acharya | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%202%20Test%20Results/R2%20ITC2%20Exit%20approval_FW-%20IAO%20PXT%20Minutes-%20%20ww02%2724.eml?csf=1&web=1&e=sv2p3Y | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%202%20Test%20Results?csf=1&web=1&e=nYgVxb |  | 1
R1 | Test |  | IDM 2.0 DELID778 | Single Instance | ITC1 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete | ITC 1 Exit attached; Attached PPT with links to approval emails | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%202%20Test%20Results/R2%20ITC2%20Exit%20approval_FW-%20IAO%20PXT%20Minutes-%20%20ww02%2724.eml?csf=1&web=1&e=sv2p3Y | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%201%20Test%20Results?csf=1&web=1&e=5xNZIB |  | 1
R1 | Test |  | IDM 2.0 DELID307 | Single Instance | ITC2 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete | ITC 2 Exit attached; Attached PPT with links to approval emails | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%202%20Test%20Results/R2%20ITC2%20Exit%20approval_FW-%20IAO%20PXT%20Minutes-%20%20ww02%2724.eml?csf=1&web=1&e=XJAdLi | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/ITC%202%20Test%20Results?csf=1&web=1&e=nYgVxb |  | 1
R1 | Test |  | IDM 2.0 DELID325 | Single Instance | Knowledge transfer plan |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Gaurav Tyagi | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=fiPuVc | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan/KT%20Signoff?csf=1&web=1&e=w0nwZr | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=fiPuVc |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID342 | Single Instance | Knowledge transfer plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=fiPuVc | Gaurav Tyagi, Vivek Sahni |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan/KT%20Signoff?csf=1&web=1&e=w0nwZr | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=Ji6nyp |  | 1
R1 | Test |  | IDM 2.0 DELID691 | Single Instance | Performance Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCycles?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/s/inteldeloitteiao/ESvX4XZKabpNpJ7bL26SKs8Bx2ROe1XBOjO7h1QmJmQ7XA?e=6BSgEb | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fb6joq |  | 1
R1 | Test |  | IDM 2.0 DELID316 | Single Instance | Performance Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCycles?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Cases%20and%20Scripts/RE_%20GPO%20approval%20for%20R2%20MDG%20Performance%20test%20cases.msg?csf=1&web=1&e=kSMeB6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fb6joq |  | 1
R1 | Test |  | IDM 2.0 DELID692 | Single Instance | Performance Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/FPR%20SLT%20Replication/RE_%20Offline%20GPO%20Approval%20for%20FPR%20Replication%20Performance%20Test%20.msg?csf=1&web=1&e=JEr8FW | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/FPR%20SLT%20Replication/RE_%20Offline%20GPO%20Approval%20for%20FPR%20Replication%20Performance%20Test%20.msg?csf=1&web=1&e=x38Y6v | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/FPR%20SLT%20Replication?csf=1&web=1&e=atHd80 |  | 1
R1 | Test |  | IDM 2.0 DELID317 | Single Instance | Performance Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance/RE_%20MDG%20Finance%20Performance%20Test%20Results%20.msg?csf=1&web=1&e=VfPdql | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance/RE_%20MDG%20Finance%20Performance%20Test%20Results%20.msg?csf=1&web=1&e=0wCrlH | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance?csf=1&web=1&e=hGitGb |  | 1
R1 | Test |  | IDM 2.0 DELID693 | Single Instance | Performance Test Script identification / Approval |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/ErPnaOmQ8q1LluN3eiFETMUBUmJVdAgzm1jpCXUh4ThH9w?e=rglZ4Z | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/FPR%20SLT%20Replication/RE_%20Offline%20GPO%20Approval%20for%20FPR%20Replication%20Performance%20Test%20.msg?csf=1&web=1&e=DRGhFk | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/FPR%20SLT%20Replication?csf=1&web=1&e=GNnEe9 |  | 1
R1 | Test |  | IDM 2.0 DELID308 | Single Instance | Performance Test Script identification / Approval |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/Eg3HeUafeg9JoCbzQX34go8BNb9unZwnniksUsSFhT5egQ?e=kq7tbt | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance/RE_%20MDG%20Finance%20Performance%20Test%20Results%20.msg?csf=1&web=1&e=53SDF7 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance?csf=1&web=1&e=E7Zbzw |  | 1
R1 | Test |  | IDM 2.0 DELID315 | Single Instance | Performance Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCycles?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/GPO%20Approvals?csf=1&web=1&e=TKWHqJ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Plan?csf=1&web=1&e=mY0Cwf |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID344 | Single Instance | Production Cutover Load Metrics |  |  |  |  | N/A |  | 01. Not Started |  | Jaya Krishna Boyapalli | Julie Fawdington | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Production%20Cutover%20Load%20Metrics/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=09qlAX | Jaya Krishna Boyapalli |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Production%20Cutover%20Load%20Metrics/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=9448Cp | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F04%20Deploy%2FProduction%20Cutover%20Load%20Metrics&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&newTargetListUrl=%2Fsites%2Finteldeloitteiao%2FShared%20Documents&viewpath=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID345 | Single Instance | Production go-live execution results |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results?csf=1&web=1&e=EjOMHZ | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=nzwPn3 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results?csf=1&web=1&e=EjOMHZ |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID347 | Single Instance | Production security & GRC setup |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=hbseJa | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup%20Approval_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=7ZgwOH | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=hbseJa |  | 1
R1 | Test |  | IDM 2.0 DELID331 | Single Instance | Production Support /IT Security Roles test results (A) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/R1%20R2%20FPR%20IT%20Support%20Role%20Build_Unit%20Test_IDM%202.0%20DELID331_IDM%202.0%20DELID657.xlsx.url?csf=1&web=1&e=xW9WPh | Yazdani Shaik |  | TRUE | TRUE | N/A - Artifact | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/R1%20R2%20FPR%20IT%20Support%20Role%20Build_Unit%20Test_IDM%202.0%20DELID331_IDM%202.0%20DELID657.xlsx.url?csf=1&web=1&e=xW9WPh |  | 1
R1 | Test |  | IDM 2.0 DELID321 | Single Instance | Production System Set-up |  |  |  | TRUE | N/A | 12. Infrastructure | 04. Complete | Production system CFIN & MDG, HANA Sidecar are completely setup | Sarathbabu Raguru | John Camarillo | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure/SAP_Landscape_Strategy/IAO%20Build%20Tracker.xlsx?d=w8fe51f00c0ec402f9ffd0b22108c6d3d&csf=1&web=1&e=Xe5TKF | Sarathbabu Raguru | John Camarillo | TRUE | TRUE | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Production%20System%20Set-up/%5BEXT%5D%20RE-%20IDM%202.0%20Deliverable%20Log%20%26%20Sign-off%20.pdf?csf=1&web=1&e=quapDO | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Production%20System%20Set-up?csf=1&web=1&e=LjcuKW |  | 1
R1 | Test |  | IDM 2.0 DELID334 | Single Instance | Production user to role mapping results |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID340 | Single Instance | Production user to role mapping results |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Intel_R1_Prod_Role%20to%20Position%20Mapping_RTPM_IDM%202.0%20DELID340.xlsx.url?csf=1&web=1&e=HXzj9p | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/R1%20Production%20RTPM%20Approvals_IDM%202.0%20DELID340.url?csf=1&web=1&e=yEtZKj | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Intel_R1_Prod_Role%20to%20Position%20Mapping_RTPM_IDM%202.0%20DELID340.xlsx.url?csf=1&web=1&e=HXzj9p |  | 1
R1 | Test |  | IDM 2.0 DELID324 | Single Instance | Readiness Review and Sign-Off (Go-Live Approval) |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao-IntelDeloitteERPMRCandOSCChannel/_layouts/15/Doc.aspx?sourcedoc=%7B74BAB561-C4D3-460E-9DD0-672D915F9608%7D&file=IAO%20ERP%20R3%20Design%20Readout%20-%20MRC%205.15.pptx&wdLOR=cA14EFD10-850E-4C9B-B88B-044CE72980B1&action=edit&mobileredirect=true | Alpna Gainda | Approved in MRC on May 15 |  | TRUE |  |  |  | 1
R1 | Test |  | IDM 2.0 DELID694 | Single Instance | Regression Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals/R1%20UAT3%20Test%20Scripts%20Approvals/Regression/FPR%20Regression%20-%20Treasury%20-%20Test%20Script%20Approval%20-%20R1%20UAT3.msg?csf=1&web=1&e=Gwd7zQ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=aiRnEx |  | 1
R1 | Test |  | IDM 2.0 DELID313 | Single Instance | Regression Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 05. Not Applicable | Regression testing is not applicable for R1 Master Data | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=aiRnEx | Vivekananda Maiya |  | TRUE | TRUE | NA | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=aiRnEx |  | 1
R1 | Test |  | IDM 2.0 DELID695 | Single Instance | Regression Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Results/R1%20Regression%20Email%20Approval?csf=1&web=1&e=uycJdF | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Results?csf=1&web=1&e=4aiv8b |  | 1
R1 | Test |  | IDM 2.0 DELID314 | Single Instance | Regression Test Results |  |  |  |  | N/A | 09A. Master Data | 05. Not Applicable | Regression testing is not applicable for R1 Master Data | Lilibeth Lejarde | Gunaranjan Viswanathan | N/A | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Results/R1%20Regression%20Email%20Approval?csf=1&web=1&e=888GHb | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Test%20Results?csf=1&web=1&e=4aiv8b |  | 1
R1 | Test |  | IDM 2.0 DELID312 | Single Instance | Regression Testing Plan |  |  |  |  | N/A | 16. Testing | 04. Complete |  | Vivekananda Maiya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/FW-%20IAO%20PXT%20Minutes-%20%20ww02%2724%20R1%20UAT1%20Test%20Cycle%20Go%20Decision%20Approval.eml?csf=1&web=1&e=sBJXZ0 https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/Re-%20%5BEXT%5D%20RE-%20Approval%20Requested-%20R1%20UAT%202%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=Zt4qcZ https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/RE-%20Approval%20Requested-%20R1%20UAT3%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=zIcNQ4 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Regression%20Testing%20Plan?csf=1&web=1&e=8IKprU |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID343 | Single Instance | S/4HANA Cutover execution results |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results?csf=1&web=1&e=EjOMHZ | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=4RVIy0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results?csf=1&web=1&e=EjOMHZ |  | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID348 | Single Instance | Security and GRC Standard Operation Procedures (SOP) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls?csf=1&web=1&e=Gmj5eA | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Security%20and%20GRC%20Standard%20Operation%20Procedures%20(SOP)%20Approvals_IDM%202.0%20DELID348.url?csf=1&web=1&e=JXz3Id | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls?csf=1&web=1&e=Gmj5eA |  | 1
R1 | Test |  | IDM 2.0 DELID335 | Single Instance | Segregation of Duties analysis - role level |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/R1%20Segregation%20of%20Duties%20analysis%20-%20role%20level_IDM%202.0%20DELID335.url?csf=1&web=1&e=tRslh4 | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/Risk%20Analysis%20Approvals_IDM%202.0%20DELID335_IDM%202.0%20DELID336.url?csf=1&web=1&e=pOZoFW | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/R1%20Segregation%20of%20Duties%20analysis%20-%20role%20level_IDM%202.0%20DELID335.url?csf=1&web=1&e=tRslh4 |  | 1
R1 | Test |  | IDM 2.0 DELID336 | Single Instance | Segregation of Duties analysis - user level |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/User%20Level%20Risk%20Analysis_IDM%202.0%20DELID336.url?csf=1&web=1&e=ebAy8k | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/Risk%20Analysis%20Approvals_IDM%202.0%20DELID335_IDM%202.0%20DELID336.url?csf=1&web=1&e=pOZoFW | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/Security%20and%20Controls/User%20Level%20Risk%20Analysis_IDM%202.0%20DELID336.url?csf=1&web=1&e=ebAy8k |  | 1
R1 | Test |  | IDM 2.0 DELID330 | Single Instance | Train the Trainer Materials (A) |  |  | 2025-05-19 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/OCM/Train%20the%20Trainer%20Materials%20(A)?csf=1&web=1&e=zXub9C | Laura Winterton | Solvig Kwei | TRUE | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/OCM/Train%20the%20Trainer%20Materials%20(A)?csf=1&web=1&e=zXub9C |  | 1
R1 | Test |  | IDM 2.0 DELID328 | Single Instance | Training Course Outlines for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2025-05-19 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton | Shane Bethune, Angela Wolf, Solvig Kwei | TRUE | TRUE |  | LINK |  | 1
R1 | Test |  | IDM 2.0 DELID329 | Single Instance | Training Courseware (such as Web Based Trainings, virtual instructor led trainings, simulations, quick reference guides, etc.) for cFIN, ProdCo, Product Costing and TMGF releases |  |  | 2025-05-19 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=hCHSae&CID=74176039%2Dade5%2D4b9d%2Dbe81%2D72a067dc9a8b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F03%20Test%2FNon%2DSprint%20Deliverables%2FOCM%2FTraining%20Courseware%20%28such%20as%20Web%20Based%20Trainings%2C%20virtual%20instructor%20led%20trainings%2C%20simulations%2C%20quick%20reference%20guides%2C%20etc%2E%29%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases | Laura Winterton | Shane Bethune | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=hCHSae&CID=74176039%2Dade5%2D4b9d%2Dbe81%2D72a067dc9a8b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F03%20Test%2FNon%2DSprint%20Deliverables%2FOCM%2FTraining%20Courseware%20%28such%20as%20Web%20Based%20Trainings%2C%20virtual%20instructor%20led%20trainings%2C%20simulations%2C%20quick%20reference%20guides%2C%20etc%2E%29%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases |  | 1
R1 | Test |  | IDM 2.0 DELID773 | Single Instance | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals/R1%20UAT%201%20Test%20Script%20Approvals/FPR?csf=1&web=1&e=WKpAaG | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=i7nrUi |  | 1
R1 | Test |  | IDM 2.0 DELID774 | Single Instance | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals/R1%20UAT2%20Test%20Script%20Approvals/FPR?csf=1&web=1&e=colugJ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=HxGb1X |  | 1
R1 | Test |  | IDM 2.0 DELID696 | Single Instance | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals/R1%20UAT%201%20Test%20Script%20Approvals/MDG?csf=1&web=1&e=jTBDTB | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=i7nrUi |  | 1
R1 | Test |  | IDM 2.0 DELID310 | Single Instance | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/01.%20R1/07.%20Approvals/R1%20UAT2%20Test%20Script%20Approvals/MDG?csf=1&web=1&e=ZV03bN | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=HxGb1X |  | 1
R1 | Test |  | IDM 2.0 DELID775 | Single Instance | UAT1 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Results/R1%20UAT%201_Test%20Results_Exit%20Approval.eml?csf=1&web=1&e=5y5ErH | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Results/IAO%20Program%20R1%20UAT1%20Test%20Results_Exit%20Review.pptx?d=wca69f8e7cd724e7b92b556971e76eb23&csf=1&web=1&e=Sng19x |  | 1
R1 | Test |  | IDM 2.0 DELID697 | Single Instance | UAT2 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Results/R1%20UAT2%20Exit%20Approval.eml?csf=1&web=1&e=sEJEPf UAT Approval: https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT3%20Test%20Results/R1%20UAT%203%20Exit%20Approval.eml?csf=1&web=1&e=5tAd6K | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Results/IAO%20Program%20R1%20UAT2%20Test%20Results_Exit%20Review.pptx?d=w4ce74ba077f8406099e7fa32a06593f9&csf=1&web=1&e=miv7nD |  | 1
R1 | Test |  | IDM 2.0 DELID776 | Single Instance | UAT1 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Results/R1%20UAT%201_Test%20Results_Exit%20Approval.eml?csf=1&web=1&e=5y5ErH | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT1%20Test%20Results/IAO%20Program%20R1%20UAT1%20Test%20Results_Exit%20Review.pptx?d=wca69f8e7cd724e7b92b556971e76eb23&csf=1&web=1&e=Sng19x |  | 1
R1 | Test |  | IDM 2.0 DELID311 | Single Instance | UAT2 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Results/R1%20UAT2%20Exit%20Approval.eml?csf=1&web=1&e=sEJEPf UAT Approval: https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT3%20Test%20Results/R1%20UAT%203%20Exit%20Approval.eml?csf=1&web=1&e=5tAd6K | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT2%20Test%20Results/IAO%20Program%20R1%20UAT2%20Test%20Results_Exit%20Review.pptx?d=w4ce74ba077f8406099e7fa32a06593f9&csf=1&web=1&e=miv7nD |  | 1
R1 | Test |  | IDM 2.0 DELID309 | Single Instance | UAT Testing Plan |  |  |  |  | N/A | 16. Testing | 04. Complete |  | Vivekananda Maiya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/FW-%20IAO%20PXT%20Minutes-%20%20ww02%2724%20R1%20UAT1%20Test%20Cycle%20Go%20Decision%20Approval.eml?csf=1&web=1&e=sBJXZ0 https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/Re-%20%5BEXT%5D%20RE-%20Approval%20Requested-%20R1%20UAT%202%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=Zt4qcZ https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan/RE-%20Approval%20Requested-%20R1%20UAT3%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=zIcNQ4 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/UAT%20Testing%20Plan?csf=1&web=1&e=xoudD9 |  | 1
R1 | Test |  | IDM 2.0 DELID333 | Single Instance | UAT user to role mapping results (A) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Intel_R1_UAT3_FPR_UAT%20RTPM_IDM%202.0%20DELID333.url?csf=1&web=1&e=JXPK6b | Yazdani Shaik |  | TRUE | TRUE | N/A - Artifact | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Intel_R1_UAT3_FPR_UAT%20RTPM_IDM%202.0%20DELID333.url?csf=1&web=1&e=JXPK6b |  | 1
R1 | Build | Y | IDM 2.0 DELID575 | Multiple instances | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE: 1 CR object remaining (FPRI0644) | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=iZyOnj | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R1 | Build | Y | IDM 2.0 DELID576 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE: 1 CR object remaining (FPRI0644) | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=iZyOnj | [5 empty] | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%201%2F02%20Build%2FSprint%20Deliverables%2FTechnology%2FTDD%20%26%20TUT&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 2
R1 | Build | Y | IDM 2.0 DELID577 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-09-20 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE: 1 CR object remaining (FPRI0644) | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/02%20Build/Other%20Approvals?csf=1&web=1&e=iZyOnj | [5 empty] | N/A |  | 2
R1 | Test |  | IDM 2.0 DELID615 | Single Instance | Performance Test Defect resolution |  |  |  |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | Chris Woodburn | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/EsHUBMDmZCxBq8pIhOgMIF8BAdBe7v4DcYNzUw8gtkeQmA?e=V40SFk | Keerti Nayak |  |  | TRUE | Issues Closed in Jira |  |  | 1
R2 | Test |  | IDM 2.0 DELID1129 | Single Instance | Go/No-Go criteria |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Alpna Gainda | Loni Adams | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20Go%20Live%20Criteria%20and%20Last%20checkpoint%20results/3.%20ERP%20-%20R2%20Go%20Live%20Readiness%20Evaluation.xlsx?d=we48c5df25c164612b1cd803c2e1b5d30&csf=1&web=1&e=LBcUzN | Alpna Gainda |  | TRUE | TRUE |  |  |  | 1
R1 | Test |  | IDM 2.0 DELID689 |  | Final S/4HANA Cutover Plan |  |  |  |  | N/A | 15. Cutover | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=EOIoG7 | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Execution%20Results/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=4RVIy0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/04%20Deploy/R1%20PCO%20Cutover%20Plan?csf=1&web=1&e=EOIoG7 |  | 1
R2 | Test |  | IDM 2.0 DELID616 |  | Conversion Load Metrics based on Mock Cutover execution |  |  |  |  | N/A | 15. Cutover | 01. Not Started |  | Jaya Krishna Boyapalli | Julie Fawdington | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Conversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=sR2Z9E | Jaya Krishna Boyapalli |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Conversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=EQPqsS | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Conversion%20Load%20Metrics%20based%20on%20Mock%20Cutover%20execution?csf=1&web=1&e=b3A7k9 |  | 1
R2 | Test |  | IDM 2.0 DELID779 |  | ITC1 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC1%20Results?csf=1&web=1&e=vlLlAb |  | 1
R2 | Test |  | IDM 2.0 DELID714 |  | ITC2 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC2%20Results?csf=1&web=1&e=gDgIlp |  | 1
R2 | Test |  | IDM 2.0 DELID780 |  | ITC1 Test Results |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC1%20Results?csf=1&web=1&e=vlLlAb |  | 1
R2 | Test |  | IDM 2.0 DELID617 |  | ITC2 Test Results |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC2%20Results?csf=1&web=1&e=gDgIlp |  | 1
R2 | Test |  | IDM 2.0 DELID781 |  | ITC1 Test Results |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC1%20Results?csf=1&web=1&e=vlLlAb |  | 1
R2 | Test |  | IDM 2.0 DELID719 |  | ITC2 Test Results |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC2%20Results?csf=1&web=1&e=gDgIlp |  | 1
R2 | Test |  | IDM 2.0 DELID782 |  | ITC1 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC1%20Results?csf=1&web=1&e=vlLlAb |  | 1
R2 | Test |  | IDM 2.0 DELID720 |  | ITC2 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC2%20Results?csf=1&web=1&e=gDgIlp |  | 1
R2 | Test |  | IDM 2.0 DELID708 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/Sidecar_Analytics/Re_%20Finance%20HANA%20Side%20Car%20Analytics%20Performance%20Test%20Results%20(GPO%20Approval).msg?csf=1&web=1&e=Xtzz2k | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/Sidecar_Analytics?csf=1&web=1&e=iJ9xX5 |  | 1
R2 | Test |  | IDM 2.0 DELID705 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/Ek3Wi8cV2dRLtdxDvT65AMcBnX-ZSVna_vS-jYdKfuV1dQ?e=Ko9wGL | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/OTC-IF/RE_%20Requesting%20OTC-IF%20%20GPO%20Exit%20Criteria%20for%20Performance%20Testing_%20.msg?csf=1&web=1&e=t3h5Op | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/OTC-IF?csf=1&web=1&e=MMN4HB |  | 1
R2 | Test |  | IDM 2.0 DELID702 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/EqXNgzU6Tg5NjZf4zWDLZEEBZnk1xB3qV8etkjHMjOGzFg?e=dDPmHi | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF/RE_%20Review%20FTS%20IF%20Inbound%20Delivery%20Distribution%20Performance%20Test.msg?csf=1&web=1&e=bnIel6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF?csf=1&web=1&e=Ewz64y |  | 1
R2 | Test |  | IDM 2.0 DELID618 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/s/inteldeloitteiao/Eu1oyWRf_AVDk5WPj78CNvUBjoEBLOFlHqk68J_PfR-Nzw?e=EjCjAr | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/MDG%20-%20Material%20Master/RE_%20GPO%20Approval%20request_%20MDG%20Customer%20Master%20data%20performance%20test%20results%20.msg?csf=1&web=1&e=a05edV | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/MDG%20-%20Material%20Master?csf=1&web=1&e=OntkAH |  | 1
R2 | Test |  | IDM 2.0 DELID619 |  | UAT Testing Plan |  |  |  |  | N/A | 16. Testing | 04. Complete |  | Vivekananda Maiya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts/Re-%20Approval%20Requested-%20R2%20ERP%20UAT1%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=785KbB https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=ExDkCr | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT%20Testing%20Plan?csf=1&web=1&e=LEYCHT |  | 1
R2 | Test |  | IDM 2.0 DELID783 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT1%20Test%20Script%20Approvals/FPR?csf=1&web=1&e=qU4hxU | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fHjUEd |  | 1
R2 | Test |  | IDM 2.0 DELID718 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT2%20Test%20Script%20Approvals/FPR?csf=1&web=1&e=Tvmccb | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=mbLnOl |  | 1
R2 | Test |  | IDM 2.0 DELID784 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT1%20Test%20Script%20Approvals/OTC%20IF?csf=1&web=1&e=3zGoIt | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fHjUEd |  | 1
R2 | Test |  | IDM 2.0 DELID715 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT2%20Test%20Script%20Approvals/OTC%20IF?csf=1&web=1&e=XnptoR | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=mbLnOl |  | 1
R2 | Test |  | IDM 2.0 DELID785 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT1%20Test%20Script%20Approvals/FTS%20IF?csf=1&web=1&e=d0ipJW | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fHjUEd |  | 1
R2 | Test |  | IDM 2.0 DELID711 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT2%20Test%20Script%20Approvals/FTS%20IF?csf=1&web=1&e=G0V2zV | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=mbLnOl |  | 1
R2 | Test |  | IDM 2.0 DELID786 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT1%20Test%20Script%20Approvals/MDG?csf=1&web=1&e=zQSWTy | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=fHjUEd |  | 1
R2 | Test |  | IDM 2.0 DELID620 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/18.%20Testing/05.%20Test%20Management/02.%20R2/10.%20Approvals/R2%20UAT2%20Test%20Script%20Approvals/MDG?csf=1&web=1&e=vMlK6m | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=mbLnOl |  | 1
R2 | Test |  | IDM 2.0 DELID787 |  | UAT1 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results/R2%20UAT%201%20Exit%20approval_Test%20Results.eml?csf=1&web=1&e=a5zecg | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results?csf=1&web=1&e=ZuiYF8 |  | 1
R2 | Test |  | IDM 2.0 DELID703 |  | UAT2 Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Closure.eml?csf=1&web=1&e=pJ13r5 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results?csf=1&web=1&e=KcVdpC |  | 1
R2 | Test |  | IDM 2.0 DELID788 |  | UAT1Test Results |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results/R2%20UAT%201%20Exit%20approval_Test%20Results.eml?csf=1&web=1&e=a5zecg | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results?csf=1&web=1&e=ZuiYF8 |  | 1
R2 | Test |  | IDM 2.0 DELID700 |  | UAT2 Test Results |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Closure.eml?csf=1&web=1&e=pJ13r5 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results?csf=1&web=1&e=KcVdpC |  | 1
R2 | Test |  | IDM 2.0 DELID789 |  | UAT1 Test Results |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results/R2%20UAT%201%20Exit%20approval_Test%20Results.eml?csf=1&web=1&e=a5zecg | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results?csf=1&web=1&e=ZuiYF8 |  | 1
R2 | Test |  | IDM 2.0 DELID698 |  | UAT2 Test Results |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Closure.eml?csf=1&web=1&e=pJ13r5 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results?csf=1&web=1&e=KcVdpC |  | 1
R2 | Test |  | IDM 2.0 DELID790 |  | UAT1 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results/R2%20UAT%201%20Exit%20approval_Test%20Results.eml?csf=1&web=1&e=a5zecg | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results?csf=1&web=1&e=ZuiYF8 |  | 1
R2 | Test |  | IDM 2.0 DELID621 |  | UAT2 Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Closure.eml?csf=1&web=1&e=pJ13r5 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results?csf=1&web=1&e=KcVdpC |  | 1
R2 | Test |  | IDM 2.0 DELID622 |  | Regression Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Vivekananda Maiya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Cases%20and%20Scripts/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=dmUdEg https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Cases%20and%20Scripts/Re-%20Approval%20Requested-%20R2%20ERP%20UAT1%20Test%20Cycle%20Go%20Decision.eml?csf=1&web=1&e=IMMs1s | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Testing%20Plan?csf=1&web=1&e=cuUint |  | 1
R2 | Test |  | IDM 2.0 DELID712 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval?csf=1&web=1&e=ay0aiJ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=TtihNa |  | 1
R2 | Test |  | IDM 2.0 DELID709 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 05. Not Applicable | Regression Testing is not applicable for R2 OTC IF | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval?csf=1&web=1&e=ay0aiJ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=TtihNa |  | 1
R2 | Test |  | IDM 2.0 DELID706 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 05. Not Applicable | Regression Testing is not applicable for R2 FTS IF | Rudra Sengupta | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval?csf=1&web=1&e=ay0aiJ | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=TtihNa |  | 1
R2 | Test |  | IDM 2.0 DELID623 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 05. Not Applicable | Regression Testing is not applicable for R2 Master Data | Lilibeth Lejarde | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval/R2%20MDG%20Regression%20Testing%20approval?csf=1&web=1&e=77uQD1 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=TtihNa |  | 1
R2 | Test |  | IDM 2.0 DELID699 |  | Regression Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT1%20Test%20Results/R2%20UAT%201%20Exit%20approval_Test%20Results.eml?csf=1&web=1&e=a5zecg https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/UAT2%20Test%20Results/Re-%20Approval%20Requested-%20R2%20ERP%20UAT2%20Test%20Cycle%20Closure.eml?csf=1&web=1&e=pJ13r5 | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Results/R2%20Regression%20Test%20Results.xlsx?d=wc58b3083b37649afb3dc5a8dd2972ab3&csf=1&web=1&e=TRcyTL |  | 1
R2 | Test |  | IDM 2.0 DELID721 |  | Regression Test Results |  |  |  |  | N/A | 04. OTC IF | 05. Not Applicable | Regression Testing is not applicable for R2 OTC IF | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval/R2%20OTC%20IF%20Regression%20Testing%20Approval%20Email.msg?csf=1&web=1&e=ZAcVPN | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Results/R2%20Regression%20Test%20Results.xlsx?d=wc58b3083b37649afb3dc5a8dd2972ab3&csf=1&web=1&e=TRcyTL |  | 1
R2 | Test |  | IDM 2.0 DELID716 |  | Regression Test Results |  |  |  |  | N/A | 07. FTS IF | 05. Not Applicable | Regression Testing is not applicable for R2 FTS IF | Rudra Sengupta | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval/R2%20FTS-IF%20Regression%20Testing%20Approval%20Email.msg?csf=1&web=1&e=Nlg9Zd | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Results/R2%20Regression%20Test%20Results.xlsx?d=wc58b3083b37649afb3dc5a8dd2972ab3&csf=1&web=1&e=TRcyTL |  | 1
R2 | Test |  | IDM 2.0 DELID624 |  | Regression Test Results |  |  |  |  | N/A | 09A. Master Data | 05. Not Applicable | Regression Testing is not applicable for R2 Master Data | Lilibeth Lejarde | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Cases%20and%20Scripts/R2%20Regression%20Email%20Approval/R2%20MDG%20Regression%20Testing%20approval?csf=1&web=1&e=77uQD1 | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Regression%20Test%20Results/R2%20Regression%20Test%20Results.xlsx?d=wc58b3083b37649afb3dc5a8dd2972ab3&csf=1&web=1&e=TRcyTL |  | 1
R2 | Test |  | IDM 2.0 DELID625 |  | Performance Testing Plan |  |  |  |  | N/A | 16. Testing | 04. Complete |  | Vivekananda Maiya | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Plan/GPO%20Approvals?csf=1&web=1&e=uEnOdv | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Plan?csf=1&web=1&e=V2deKb |  | 1
R2 | Test |  | IDM 2.0 DELID707 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 05. Not Applicable |  | Prabesh Acharya | Gunaranjan Viswanathan | NA | Vivekananda Maiya |  | TRUE | TRUE | NA | NA |  | 1
R2 | Test |  | IDM 2.0 DELID704 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/RE_%20GPO%20Approval%20request_%20MDG%20Customer%20Master%20data%20performance%20test%20results%20.msg?csf=1&web=1&e=CfyUB0 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=SeF4WH |  | 1
R2 | Test |  | IDM 2.0 DELID701 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF/RE_%20GPO%20approval%20for%20R2%20FTS%20Performance%20test%20cases.msg?csf=1&web=1&e=WdbnDk | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=SeF4WH |  | 1
R2 | Test |  | IDM 2.0 DELID626 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://jira.devtools.intel.com/secure/Tests.jspa#/v2/testCases?projectId=131900 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Cases%20and%20Scripts/RE_%20GPO%20approval%20for%20R2%20MDG%20Performance%20test%20cases.msg?csf=1&web=1&e=jAMhBs | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Cases%20and%20Scripts?csf=1&web=1&e=SeF4WH |  | 1
R2 | Test |  | IDM 2.0 DELID717 |  | Performance Test Results |  |  |  |  | N/A | 03. FPR | 04. Complete |  | Prabesh Acharya | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/Sidecar_Analytics/R2%20Analytics%20HANA%20SideCar%20NRT%20Finance%20Reports.pptx?d=w82fd5d4d19a54d829ed2861c48b565dd&csf=1&web=1&e=5Zgw13 | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results/MDG_Finance/RE_%20MDG%20Finance%20Performance%20Test%20Results%20.msg?csf=1&web=1&e=0wCrlH | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/Sidecar_Analytics?csf=1&web=1&e=bNdb8t |  | 1
R2 | Test |  | IDM 2.0 DELID713 |  | Performance Test Results |  |  |  |  | N/A | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/OTC-IF/OTC-IF%20R2%20Performance%20Test%20Results.pptx?d=w1ec184adc8e5404e9ac93af83268b565&csf=1&web=1&e=sPSZaN | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/OTC-IF/RE_%20Requesting%20OTC-IF%20%20GPO%20Exit%20Criteria%20for%20Performance%20Testing_%20.msg?csf=1&web=1&e=tNPnaP | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/OTC-IF?csf=1&web=1&e=AwjrzC |  | 1
R2 | Test |  | IDM 2.0 DELID710 |  | Performance Test Results |  |  |  |  | N/A | 07. FTS IF | 04. Complete |  | Rudra Sengupta | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF/FTS%20IF%20R2%20Performance%20Test%20Results.pptx?d=w105a287b5b8942b18abc993fb85185f2&csf=1&web=1&e=rhicEC | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF/RE_%20Review%20FTS%20IF%20Inbound%20Delivery%20Distribution%20Performance%20Test.msg?csf=1&web=1&e=RUQM4v | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF?csf=1&web=1&e=LhOnWm |  | 1
R2 | Test |  | IDM 2.0 DELID627 |  | Performance Test Results |  |  |  |  | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Gunaranjan Viswanathan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/MDG%20-%20Material%20Master/MDG%20R2%20Material%20Master%20Performance%20Test%20Results.pptx?d=w4581548d9d6c4dd6b9431020c1ff44c3&csf=1&web=1&e=X4mHOr | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/FTS%20IF/RE_%20Review%20FTS%20IF%20Inbound%20Delivery%20Distribution%20Performance%20Test.msg?csf=1&web=1&e=RUQM4v | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Results/MDG%20-%20Material%20Master?csf=1&web=1&e=MZzn6I |  | 1
R2 | Test |  | IDM 2.0 DELID628 |  | Performance Test Defect resolution |  |  |  |  | N/A | 11. Technology | 04. Complete |  | Keerti Nayak | Gunaranjan Viswanathan | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/03%20Test/Performance%20Test%20Results?csf=1&web=1&e=HucZSn | Vivekananda Maiya |  | TRUE | TRUE | NA | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Performance%20Test%20Defect%20Resolution/R2%20Performance%20Test%20Defect%20resolution.xlsx?d=w672574b3338b4e9bb06cae134f470880&csf=1&web=1&e=bJC2GR |  | 1
R2 | Test |  | IDM 2.0 DELID631 |  | 200 Automated test cases & Results |  |  |  |  | N/A | 16. Testing | 04. Complete | 1. 200 automation test cases are up to R5 2. 20 E2E Test Cases and 40 String Testcases Automated | Vivekananda Maiya | Gunaranjan Viswanathan | Functional Review and Feedbacks https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FAutomation%20TestCases%20and%20Result&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&newTargetListUrl=%2Fsites%2Finteldeloitteiao%2FShared%20Documents&viewpath=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FForms%2FAllItems%2Easpx | Vivekananda Maiya |  | TRUE | TRUE | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/ITC3%20Results/R1_R2%20Test%20Result%20Approval.pptx?d=w803aba31dbd743968b0c4d6cfab60234&csf=1&web=1&e=1epw4W | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FAutomation%20TestCases%20and%20Result&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&newTargetListUrl=%2Fsites%2Finteldeloitteiao%2FShared%20Documents&viewpath=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FForms%2FAllItems%2Easpx |  | 1
R2 | Test |  | IDM 2.0 DELID632 |  | Business Continuity Plan (BCP) |  |  |  |  | N/A | 01. PMO | 01. Not Started | BCP documents uploaded into Intel eGRC | Viswa Anakkara Vadakkath | Aishwarya Bhat | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Business%20Readiness?csf=1&web=1&e=gce8qA | Katie Kobernyk |  |  | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Business%20Readiness?csf=1&web=1&e=gce8qA |  | 1
R2 | Test |  | IDM 2.0 DELID634 |  | Detailed cutover plan for Go Live |  |  |  |  | N/A | 15. Cutover | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=alCM7O | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ |  | 1
R2 | Test |  | IDM 2.0 DELID637 |  | Production System Set-up |  |  |  | TRUE | N/A | 12. Infrastructure | 04. Complete | Production system IF, GTS, EWM, HANA sidecar are completely setup along with CFIN and MDG | Sarathbabu Raguru | John Camarillo | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/12.%20Infrastructure/SAP_Landscape_Strategy/IAO%20Build%20Tracker.xlsx?d=w8fe51f00c0ec402f9ffd0b22108c6d3d&csf=1&web=1&e=Xe5TKF | Sarathbabu Raguru | John Camarillo | TRUE | TRUE | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Production%20System%20Set-up/%5BEXT%5D%20RE-%20IDM%202.0%20Deliverable%20Log%20%26%20Sign-off%20.pdf?csf=1&web=1&e=be74gn | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Production%20System%20Set-up?csf=1&web=1&e=rhUbQQ |  | 1
R2 | Test |  | IDM 2.0 DELID640 |  | Hypercare/Post Go-Live Support Strategy & Plan |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Gaurav Tyagi | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Hypercare%20Post%20GoLive%20Support%20Strategy%20%26%20Plan?csf=1&web=1&e=nfKe2Y | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Hypercare%20Post%20GoLive%20Support%20Strategy%20%26%20Plan?csf=1&web=1&e=nfKe2Y |  | 1
R2 | Test |  | IDM 2.0 DELID643 | Single Instance | Readiness Review and Sign-Off (Go-Live Approval) |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Alpna Gainda | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao-IntelDeloitteERPMRCandOSCChannel/Shared Documents/ERP MRC and OSC Channel/Implementation/01. Intel Deloitte ERP MRC/IAO MRC - 7.30.2025.pptx?d=w701d044c34544b39a7bbe6849215706c&csf=1&web=1&e=IwC6xp&xsdata=MDV8MDJ8YWdhaW5kYUBkZWxvaXR0ZS5jb218ZGMwOGNiNDEzMWQ4NDhiZjA5Y2IwOGRlMTVkMTI3ODR8MzZkYTQ1ZjFkZDJjNGQxZmFmMTM1YWJlNDZiOTk5MjF8MHwwfDYzODk3MjE4NTY1MTA3MTE4M3xVbmtub3dufFRXRnBiR1pzYjNkOGV5SkZiWEIwZVUxaGNHa2lPblJ5ZFdVc0lsWWlPaUl3TGpBdU1EQXdNQ0lzSWxBaU9pSlhhVzR6TWlJc0lrRk9Jam9pVFdGcGJDSXNJbGRVSWpveWZRPT18MHx8fA%3d%3d&sdata=eXZpSkN2Um5CdmNnazlaZlNnY2hkV1dMdmM0S25HR1JQVHBTaUNUTmVvaz0%3d | Alpna Gainda | Approved in MRC on Jul 30 |  | TRUE |  |  |  | 1
R2 | Test |  | IDM 2.0 DELID644 |  | Knowledge transfer plan |  |  |  |  | N/A | 01. PMO | 01. Not Started |  | Gaurav Tyagi | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=MwWgIG | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Knowledge%20Transfer%20Plan/KT%20Signoff?csf=1&web=1&e=gkM0Ls | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Knowledge%20Transfer%20Plan?csf=1&web=1&e=MwWgIG |  | 1
R2 | Test |  | IDM 2.0 DELID646 | Single Instance | Change Readiness Assessment for cFIN, ProdCo, Product Costing and TMGF releases (K/A) |  |  | 2025-07-28 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=sJELB1&CID=ab1f6d43%2Daced%2D4b66%2Dab3d%2D6d7a3d45c29e&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FChange%20Readiness%20Assessment%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20%28KA%29 | Laura Winterton |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=sJELB1&CID=ab1f6d43%2Daced%2D4b66%2Dab3d%2D6d7a3d45c29e&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FChange%20Readiness%20Assessment%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20%28KA%29 |  | 1
R2 | Test |  | IDM 2.0 DELID648 | Single Instance | Communication materials for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2025-08-08 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=LjoWuM&CID=9b86156e%2D23bb%2D4308%2D8a5a%2D77762529e096&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FCommunication%20materials%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20%28A%29 | Laura Winterton |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=LjoWuM&CID=9b86156e%2D23bb%2D4308%2D8a5a%2D77762529e096&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FCommunication%20materials%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20%28A%29 |  | 1
R2 | Test |  | IDM 2.0 DELID651 | Single Instance | Training Course Outlines for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2025-01-27 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B180564D2-6532-4DB1-9F65-0104C4405327%7D&file=IDM%202.0%20DELID651%20IAO%20ERP_Training%20Course%20Outlines%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20(A)_Release%202_Approved.xlsx&action=default&mobileredirect=true | Laura Winterton |  | TRUE | TRUE |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B180564D2-6532-4DB1-9F65-0104C4405327%7D&file=IDM%202.0%20DELID651%20IAO%20ERP_Training%20Course%20Outlines%20for%20cFIN%2C%20ProdCo%2C%20Product%20Costing%20and%20TMGF%20releases%20(A)_Release%202_Approved.xlsx&action=default&mobileredirect=true |  | 1
R2 | Test |  | IDM 2.0 DELID652 | Single Instance | Training Courseware (such as Web Based Trainings, virtual instructor led trainings, simulations, quick reference guides, etc.) for cFIN, ProdCo, Product Costing and TMGF releases |  |  | 2025-08-11 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | Laura Winterton |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R2 | Test |  | IDM 2.0 DELID655 | Single Instance | Train the Trainer Materials (A) |  |  | 2025-05-16 | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FIDM%202%2E0%20DELID655%20R2%20Train%20the%20Trainer%20Material%5FApproved%2Epdf&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management | Laura Winterton |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management%2FIDM%202%2E0%20DELID655%20R2%20Train%20the%20Trainer%20Material%5FApproved%2Epdf&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%202%2F03%20Test%2FNon%2DSprint%20Deliverables%2FChange%20Management |  | 1
R2 | Test |  | IDM 2.0 DELID657 | Single Instance | Production Support /IT Security Roles test results (Artifact) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/R1%20R2%20FPR%20IT%20Support%20Role%20Build_Unit%20Test_IDM%202.0%20DELID331_IDM%202.0%20DELID657.xlsx.url?csf=1&web=1&e=nS447l | Yazdani Shaik |  | TRUE | TRUE | N/A - Artifact | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/R1%20R2%20FPR%20IT%20Support%20Role%20Build_Unit%20Test_IDM%202.0%20DELID331_IDM%202.0%20DELID657.xlsx.url?csf=1&web=1&e=kTLGRa |  | 1
R2 | Test |  | IDM 2.0 DELID659 |  | GRC AC and PC SIT test results (Artifact) |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Test |  | IDM 2.0 DELID660 |  | UAT user to role mapping results (Artifact) |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/UAT%20user%20to%20role%20mapping_IDM%202.0%20DELID660.url?csf=1&web=1&e=uYbGnr | Yazdani Shaik |  | TRUE | TRUE | N/A - Artifact | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/UAT%20user%20to%20role%20mapping_IDM%202.0%20DELID660.url?csf=1&web=1&e=uYbGnr |  | 1
R2 | Test |  | IDM 2.0 DELID663 |  | Production user to role mapping results |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Security%20and%20Controls/Production%20user%20to%20role%20mapping%20results_IDM%202.0%20DELID663.url?csf=1&web=1&e=xxiUgT | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Security%20and%20Controls/Production%20user%20to%20role%20mapping%20approvals_IDM%202.0%20DELID663.url?csf=1&web=1&e=HbkxVN | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Security%20and%20Controls/Production%20user%20to%20role%20mapping%20results_IDM%202.0%20DELID663.url?csf=1&web=1&e=xxiUgT |  | 1
R2 | Test |  | IDM 2.0 DELID665 |  | Segregation of Duties analysis - role level |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Consolidated%20Risk%20Analysis_IDM%202.0%20DELID665_IDM%202.0%20DELID667.xlsx.url?csf=1&web=1&e=JoV9sL | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Risk%20Analysis%20Approvals_IDM%202.0%20DELID665_IDM%202.0%20DELID667.url?csf=1&web=1&e=JigTly | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Consolidated%20Risk%20Analysis_IDM%202.0%20DELID665_IDM%202.0%20DELID667.xlsx.url?csf=1&web=1&e=JoV9sL |  | 1
R2 | Test |  | IDM 2.0 DELID667 |  | Segregation of Duties analysis – user level |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Consolidated%20Risk%20Analysis_IDM%202.0%20DELID665_IDM%202.0%20DELID667.xlsx.url?csf=1&web=1&e=JoV9sL | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Risk%20Analysis%20Approvals_IDM%202.0%20DELID665_IDM%202.0%20DELID667.url?csf=1&web=1&e=JigTly | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Non-Sprint%20Deliverables/Security%20and%20Controls/Consolidated%20Risk%20Analysis_IDM%202.0%20DELID665_IDM%202.0%20DELID667.xlsx.url?csf=1&web=1&e=JoV9sL |  | 1
R2 | Test |  | IDM 2.0 DELID668 |  | SAP Infrastructure Cyber Risk Assessment (Artifact) |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Test |  | IDM 2.0 DELID670 | Single Instance | Controls test step requirements and results in SIT and/or UAT |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval/R2%20UAT%20Approvals?csf=1&web=1&e=9MTUj6 | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval/R2%20UAT%20Approvals?csf=1&web=1&e=9MTUj6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval/R2%20UAT%20Approvals?csf=1&web=1&e=9MTUj6 |  | 1
R2 | Test |  | IDM 2.0 DELID672 |  | Data Privacy controls results in SIT and UAT (Artifact) |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Test |  | IDM 2.0 DELID675 |  | Final S/4HANA Cutover Plan |  |  |  |  | N/A | 15. Cutover | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=alCM7O | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ |  | 1
R3 | Test | N/A | IDM 2.0 DELID677 |  | Conversion Load Metrics based on Mock Cutover execution |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID791 |  | ITC1 Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID722 |  | ITC2 Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID792 |  | ITC1 Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID723 |  | ITC2 Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID793 |  | ITC1 Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID724 |  | ITC2 Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID794 |  | ITC1 Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID725 |  | ITC2 Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID795 |  | ITC1 Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID726 |  | ITC2 Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID796 |  | ITC1 Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID727 |  | ITC2 Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID797 |  | ITC1 Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID679 |  | ITC2 Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID728 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID729 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID730 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID731 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID732 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID733 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID681 |  | Performance Test Script identification / Approval |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID682 |  | UAT Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID798 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID734 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID799 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID735 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID800 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID736 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID801 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID737 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID802 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID738 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID803 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID739 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID804 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID683 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID805 |  | UAT1 Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID740 |  | UAT2 Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID806 |  | UAT1 Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID741 |  | UAT2 Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID807 |  | UAT1 Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID742 |  | UAT2 Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID808 |  | UAT1 Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID743 |  | UAT2 Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID809 |  | UAT1 Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID744 |  | UAT2 Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID810 |  | UAT1 Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID745 |  | UAT2 Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID811 |  | UAT1 Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID684 |  | UAT2 Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID685 |  | Regression Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID746 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID747 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID748 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID749 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID750 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID751 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID686 |  | Regression Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID752 |  | Regression Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID753 |  | Regression Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID754 |  | Regression Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID755 |  | Regression Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID756 |  | Regression Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID757 |  | Regression Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID687 |  | Regression Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID688 |  | Performance Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID758 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID759 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID760 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID761 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID762 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID763 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID579 |  | Performance Test Cases and Scripts |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID764 |  | Performance Test Results |  |  |  |  | N/A | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID765 |  | Performance Test Results |  |  |  |  | N/A | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID766 |  | Performance Test Results |  |  |  |  | N/A | 05. OTC IP | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID767 |  | Performance Test Results |  |  |  |  | N/A | 06. PTP | 01. Not Started |  | Murthy K P, Rajesh Tol | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID768 |  | Performance Test Results |  |  |  |  | N/A | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID769 |  | Performance Test Results |  |  |  |  | N/A | 08. FTS IP | 01. Not Started |  | Sekhar Lingam | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID770 |  | Performance Test Results |  |  |  |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID581 |  | Performance Test Defect resolution |  |  |  |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID582 |  | 200 Automated test cases & Results |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID583 |  | Business Continuity Plan (BCP) |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID584 |  | Detailed cutover plan for Go Live |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID585 |  | Production System Set-up |  |  |  |  | N/A | 12. Infrastructure | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID586 |  | Go/No-Go criteria |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID587 |  | Hypercare/Post Go-Live Support Strategy & Plan |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID588 |  | Readiness Review and Sign-Off (Go-Live Approval) |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID589 |  | Knowledge transfer plan |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID590 | Single Instance | Change Readiness Assessment for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID591 | Single Instance | Communication materials for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  | 2026-06-26 |  | N/A | 14. OCM | 01. Not Started | CR0618 | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID592 | Single Instance | Training Course Outlines for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID593 | Single Instance | Training Courseware (such as Web Based Trainings, virtual instructor led trainings, simulations, quick reference guides, etc.) for cFIN, ProdCo, Product Costing and TMGF releases |  |  | 2027-02-28 |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID594 | Single Instance | Train the Trainer Materials (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID595 |  | Production Support /IT Security Roles test results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID596 |  | GRC AC and PC SIT test results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID597 |  | UAT user to role mapping results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID598 |  | Production user to role mapping results |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID599 |  | Segregation of Duties analysis - role level |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID600 |  | Segregation of Duties analysis – user level |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID601 |  | SAP Infrastructure Cyber Risk Assessment (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID602 |  | Controls test step requirements and results in SIT |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Nishat Ahmed, Yazdani Shaik | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID603 |  | Data Privacy controls results in SIT and UAT (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID604 |  | Final S/4HANA Cutover Plan |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 2
R4 | Test | N/A | IDM 2.0 DELID605 |  | Conversion Load Metrics based on Mock Cutover execution |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID812 |  | ITC1 Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID606 |  | ITC2 Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID607 |  | Performance Test Script identification / Approval |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID608 |  | UAT Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID813 |  | UAT1 Test Cases and Scripts |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID609 |  | UAT2 Test Cases and Scripts |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID814 |  | UAT1 Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID610 |  | UAT2 Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID611 |  | Regression Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID612 |  | Regression Test Cases and Scripts |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID613 |  | Regression Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID614 |  | Performance Testing Plan |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID629 |  | Performance Test Cases and Scripts |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID630 |  | Performance Test Results |  |  |  |  | N/A |  | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID633 |  | Performance Test Defect resolution |  |  |  |  | N/A | 11. Technology | 01. Not Started |  | Keerti Nayak | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID635 |  | 200 Automated test cases & Results |  |  |  |  | N/A | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID636 |  | Business Continuity Plan (BCP) |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID639 |  | Detailed cutover plan for Go Live |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID641 |  | Production System Set-up |  |  |  |  | N/A | 12. Infrastructure | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID642 |  | Go/No-Go criteria |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID645 |  | Hypercare/Post Go-Live Support Strategy & Plan |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID647 |  | Readiness Review and Sign-Off (Go-Live Approval) |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID649 |  | Knowledge transfer plan |  |  |  |  | N/A | 01. PMO | 01. Not Started | [11 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID650 |  | Change Readiness Assessment for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID653 |  | Communication materials for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID654 |  | Training Course Outlines for cFIN, ProdCo, Product Costing and TMGF releases (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID656 |  | Training Courseware (such as Web Based Trainings, virtual instructor led trainings, simulations, quick reference guides, etc.) for cFIN, ProdCo, Product Costing and TMGF releases |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID658 |  | Train the Trainer Materials (A) |  |  |  |  | N/A | 14. OCM | 01. Not Started |  | Laura Winterton | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID661 |  | Production Support /IT Security Roles test results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID662 |  | GRC AC and PC SIT test results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID664 |  | UAT user to role mapping results (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID666 |  | Production user to role mapping results |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID669 |  | Segregation of Duties analysis - role level |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID671 |  | Segregation of Duties analysis – user level |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID673 |  | SAP Infrastructure Cyber Risk Assessment (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID674 |  | Controls test step requirements and results in SIT and/or UAT |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID676 |  | Data Privacy controls results in SIT and UAT (Artifact) |  |  |  |  | N/A | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 1
R4 | Test | N/A | IDM 2.0 DELID678 |  | Final S/4HANA Cutover Plan |  |  |  |  | N/A | 15. Cutover | 01. Not Started | [11 empty] | 1
R1 | Deploy and Hypercare |  | IDM 2.0 DELID772 | Single Instance | Parallel Run | [5 empty] | 01. PMO | 01. Not Started |  | Prabesh Acharya | Uzma Ahmed | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao-IntelDeloitteERPMRCandOSCChannel/Shared Documents/ERP MRC and OSC Channel/Implementation/01. Intel Deloitte ERP MRC/IAO MRC - 7.30.2025.pptx?d=w701d044c34544b39a7bbe6849215706c&csf=1&web=1&e=IwC6xp&xsdata=MDV8MDJ8YWdhaW5kYUBkZWxvaXR0ZS5jb218ZGMwOGNiNDEzMWQ4NDhiZjA5Y2IwOGRlMTVkMTI3ODR8MzZkYTQ1ZjFkZDJjNGQxZmFmMTM1YWJlNDZiOTk5MjF8MHwwfDYzODk3MjE4NTY1MTA3MTE4M3xVbmtub3dufFRXRnBiR1pzYjNkOGV5SkZiWEIwZVUxaGNHa2lPblJ5ZFdVc0lsWWlPaUl3TGpBdU1EQXdNQ0lzSWxBaU9pSlhhVzR6TWlJc0lrRk9Jam9pVFdGcGJDSXNJbGRVSWpveWZRPT18MHx8fA%3d%3d&sdata=eXZpSkN2Um5CdmNnazlaZlNnY2hkV1dMdmM0S25HR1JQVHBTaUNUTmVvaz0%3d | Alpna Gainda | Approved in MRC on Jul 30 |  | TRUE |  |  |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID815 | Single Instance | Prepare Final Cutover Plan |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=alCM7O | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Cutover%20Plan?csf=1&web=1&e=zaPmbJ |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID816 | Single Instance | Provide inputs to Production user to role mapping results |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID817 | Single Instance | Prepare Final Hypercare Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Prepare%20Final%20Hypercare%20Plan?csf=1&web=1&e=KJTgWp | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Prepare%20Final%20Hypercare%20Plan?csf=1&web=1&e=KJTgWp |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID818 | Single Instance | Prepare Knowledge transfer plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Prepare%20Knowledge%20Transfer%20Plan?csf=1&web=1&e=AbDBns | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Prepare%20Knowledge%20Transfer%20Plan?csf=1&web=1&e=AbDBns |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID819 | Single Instance | Document Cutover execution results |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results?csf=1&web=1&e=1cCM2N | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=HMDPx6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results?csf=1&web=1&e=1cCM2N |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID820 | Single Instance | Identify & document Production Cutover Load Metrics |  |  |  |  | N/A |  | 01. Not Started |  | Jaya Krishna Boyapalli | Julie Fawdington | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Production%20Cutover%20Load%20Metrics/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=HP3arF | Jaya Krishna Boyapalli |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Production%20Cutover%20Load%20Metrics/Fw_%20_URGENT_%20R1_R2%20Deliverable%20Milestone%20DUE%2010_9%20EOD.msg?csf=1&web=1&e=1C25Ww | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/Production%20Cutover%20Load%20Metrics?csf=1&web=1&e=OX8Myo |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID821 | Single Instance | Execute Production go live and document results |  |  |  |  | N/A |  | 04. Complete |  | William Adkins | Mark D Mahony | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results?csf=1&web=1&e=1cCM2N | William Adkins |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results/EXT%20Re%20Cutover%20deliverables%20-%20IAO%20ERP%20Releases%201%20%202.msg?csf=1&web=1&e=HMDPx6 | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/04%20Deploy/R2%20PCO%20Execution%20Results?csf=1&web=1&e=1cCM2N |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID822 | Single Instance | Execute Hypercare and document results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | Brian Ochoa | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Execute%20Hypercare%20%26%20Document%20Results?csf=1&web=1&e=kgs34r | Gaurav Tyagi |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Hypercare%20Execution%20Results/_EXT_%20Re_%20Approval%20needed%20on%20R1_R2%20Hypercare%20items.msg?csf=1&web=1&e=vlJ3Rj | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/05%20Hypercare/Execute%20Hypercare%20%26%20Document%20Results?csf=1&web=1&e=kgs34r |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID823 | Single Instance | Setup Production security & GRC |  |  |  |  | N/A | 13. Security | 04. Complete |  | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=hbseJa | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup%20Approval_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=7ZgwOH | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/05%20Hypercare/Security%20and%20Controls/Production%20security%20%26%20GRC%20setup_IDM%202.0%20DELID347_IDM%202.0%20DELID823.url?csf=1&web=1&e=hbseJa |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID824 | Single Instance | Prepare Security and GRC Standard Operation Procedures (SOP) |  |  |  |  | N/A | 13. Security | 05. Not Applicable |  | Yazdani Shaik | Debbie Whitley | N/A | Yazdani Shaik |  | TRUE | TRUE | N/A | N/A |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID825 | Single Instance | Document Cutover validation results for manually configured controls in production and cutover dress rehearsal environment |  |  |  |  | N/A | 13. Security | 04. Complete | Controls confirmation should be security team. | Yazdani Shaik | Debbie Whitley | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval?csf=1&web=1&e=qXMk0y | Yazdani Shaik |  | TRUE | TRUE | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval?csf=1&web=1&e=qXMk0y | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/03%20Test/Controls%20Test%20validations%20approval?csf=1&web=1&e=qXMk0y |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID826 | Single Instance | Develop and deliver Communications and Stakeholder Engagement Materials for Cutover / Go Live / Hypercare |  |  |  | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton |  | TRUE | TRUE |  | LINK |  | 1
R2 | Deploy and Hypercare |  | IDM 2.0 DELID827 | Single Instance | Develop Change Management and Training Knowledge Transfer plan and deliver ChangeScout data export |  |  |  | TRUE | N/A | 14. OCM | 04. Complete |  | Laura Winterton | Jodi McGowan | LINK | Laura Winterton |  | TRUE | TRUE |  | LINK |  | 1
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID828 |  | Prepare Final Cutover Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID829 |  | Provide inputs to Production user to role mapping results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID830 |  | Prepare Final Hypercare Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID831 |  | Prepare Knowledge transfer plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID832 |  | Document Cutover execution results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID833 |  | Identify & document Production Cutover Load Metrics |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID834 |  | Execute Production go live and document results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID835 |  | Execute Hypercare and document results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID836 |  | Setup Production security & GRC |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID837 |  | Prepare Security and GRC Standard Operation Procedures (SOP) |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID838 |  | Document Cutover validation results for manually configured controls in production and cutover dress rehearsal environment |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID839 |  | Develop and deliver Communications and Stakeholder Engagement Materials for Cutover / Go Live / Hypercare |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID840 |  | Develop Change Management and Training Knowledge Transfer plan and deliver ChangeScout data export |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID841 |  | Prepare Final Cutover Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID842 |  | Provide inputs to Production user to role mapping results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID843 |  | Prepare Final Hypercare Plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID844 |  | Prepare Knowledge transfer plan |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID845 |  | Document Cutover execution results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID846 |  | Identify & document Production Cutover Load Metrics |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID847 |  | Execute Production go live and document results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID848 |  | Execute Hypercare and document results |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID849 |  | Setup Production security & GRC |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID850 |  | Prepare Security and GRC Standard Operation Procedures (SOP) |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID851 |  | Document Cutover validation results for manually configured controls in production and cutover dress rehearsal environment |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID852 |  | Develop and deliver Communications and Stakeholder Engagement Materials for Cutover / Go Live / Hypercare |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R4 | Deploy and Hypercare | N/A | IDM 2.0 DELID853 |  | Develop Change Management and Training Knowledge Transfer plan and deliver ChangeScout data export |  |  |  |  | N/A |  | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 1
R2 | Build | Y | IDM 2.0 DELID858 |  | Configuration Unit testing Results (CUT) |  |  |  | TRUE | TRUE | 09A. Master Data | 04. Complete | CUTs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID859 |  | Custom Code (RICEFW) |  |  | 2024-12-06 | TRUE | N/A | 09A. Master Data | 04. Complete | Custom Code are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID860 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 05. Not Applicable | No ECA objects in scope for R2 build | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | N/A | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID861 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | FDSs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID862 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | No ECA objects in scope for R2 build | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | N/A | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID863 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | FUTs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID864 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | CDDs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | N/A | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID865 |  | S/4HANA System Configuration |  |  | 2024-12-06 | TRUE | N/A | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | N/A | N/A |  | 1
R2 | Build | Y | IDM 2.0 DELID866 |  | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE | N/A | 09A. Master Data | 04. Complete | TDDs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID867 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE | N/A | 09A. Master Data | 04. Complete | TUTs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R2 | Build | Y | IDM 2.0 DELID868 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | CDDs are under Sub Team folders | Lilibeth Lejarde | Candice S Linnell |  |  | Bigil Kuriyan, Sean Tillman, Andy Thomas, Jayant Kashikar |  |  | https://amedeloitte-my.sharepoint.com/my?id=%2Fpersonal%2Fshrutisingh7%5Fdeloitte%5Fcom%2FDocuments%2FAttachments&FolderCTID=0x012000E40A6C886A7D8945AB3B89FEDC08382B | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Master%20Data?csf=1&web=1&e=XK57p9 |  | 1
R3 | Build | N/A | IDM 2.0 DELID869 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID870 |  | Custom Code (RICEFW) |  |  | 2026-03-06 |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID871 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID873 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID874 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID875 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2026-03-06 |  |  | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID877 |  | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2026-03-06 |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID878 |  | Technical Unit testing Results (TUT) |  |  | 2026-03-06 |  | N/A | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | Candice S Linnell | [8 empty] | 2
R2 | Build | Y | IDM 2.0 DELID923 | Multiple instances | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/Other%20Approvals?csf=1&web=1&e=ak7kYO | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=XujgDM |  | 1
R2 | Build | Y | IDM 2.0 DELID924 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/Other%20Approvals?csf=1&web=1&e=ak7kYO | [5 empty] | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/01.%20Sprint%20Deliverables/Technology/TDD%20%26%20TUT?csf=1&web=1&e=XujgDM |  | 2
R2 | Build | Y | IDM 2.0 DELID925 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-12-06 | TRUE | N/A | 11. Technology | 04. Complete | MIDDLEWARE | Vijay Mavuduru | ravindra.b.neralakatte@intel.com | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/02%20Build/Other%20Approvals?csf=1&web=1&e=ak7kYO | [5 empty] | N/A |  | 2
R3 | Detailed design | N/A | IDM 2.0 DELID926 | Multiple instances | Architecture diagrams |  |  | 2025-03-15 | TRUE | TRUE | 02. E2E Process Integration | 04. Complete |  | Kalpesh Shah | Craig Eastwood, Jo Guedes, Satyadeep Vajjala, Talbot Smith | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=ms0Q7B&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cnamiagarwal%40deloitte%2Ecom&OR=Teams%2DHL&CT=1743773453018&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAzMDIwMTAxMCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=be3291a1%2D7000%2D8000%2D9206%2D5d7ed5323f31&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FE2E&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=YK4Vpg&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cabvasu%40deloitte%2Ecom&OR=Teams%2DHL&CT=1761640214039&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTEwMDIxMzgxMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=d4c1d3a1%2D6080%2Da000%2D972a%2D04123a21d4a2&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FE2E%2FR3%20Architecture |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID927 | Multiple instances | E2E Process Flows |  |  | 2025-03-15 | TRUE | TRUE | 02. E2E Process Integration | 04. Complete |  | Kalpesh Shah | Craig Eastwood, Jo Guedes, Satyadeep Vajjala, Talbot Smith | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=ms0Q7B&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cnamiagarwal%40deloitte%2Ecom&OR=Teams%2DHL&CT=1743773453018&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAzMDIwMTAxMCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=be3291a1%2D7000%2D8000%2D9206%2D5d7ed5323f31&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FE2E&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  | TRUE | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=IcCK7o&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cabvasu%40deloitte%2Ecom&OR=Teams%2DHL&CT=1761640218168&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTEwMDIxMzgxMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=d5c1d3a1%2D906e%2Da000%2D972a%2D0865f80f3f3e&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FE2E%2FR3%20E2E%20Flows |  | 1
R3 | Build | N/A | IDM 2.0 DELID930 | Multiple instances | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID931 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID932 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID934 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 |  |  | 03. FPR | 03. In Deliverable Review |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID935 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID936 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 03. FPR | 04. Complete |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID937 |  | S/4HANA System Configuration |  |  | 2024-12-06 |  |  | 03. FPR | 03. In Deliverable Review |  | Prabesh Acharya | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID941 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID942 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID943 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID944 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review | Out of 30 objects o 19 already approved. o 5 Waiting for Intel approval. o 3 are in FUT progress ETA by 01/20 o 3 Straddle objects are owned by Intel to develop and not under Deloitte tracker. | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID945 | Single Instance | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID947 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 04. OTC IF | 03. In Deliverable Review |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID948 |  | S/4HANA System Configuration |  |  | 2024-12-06 |  |  | 04. OTC IF | 04. Complete |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID952 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID953 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID954 |  | Configuration Unit testing Results (CUT) |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID955 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID956 | Single Instance | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 |  |  | 07. FTS IF | 03. In Deliverable Review | 12/06 - Surya LOGI0519/520/521 are under development by Technical team 02/05: Still waiting for ECD FUT's. | Rudra Sengupta | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID958 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete | Signed off by Rodolfo Alarcon on behalf of Jorge Sanchez with confirmation from Neetu Ramireddi | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID959 |  | S/4HANA System Configuration |  |  | 2024-12-06 | TRUE |  | 07. FTS IF | 04. Complete |  | Rudra Sengupta |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/FTS-IF/FTS-IF%20Deliverable%20Summary.pptx?d=wc9098344589f4125b2557d2b49b019de&csf=1&web=1&e=UrbJIa | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID965 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 09B. Data Migration | 04. Complete | 20 automated conversions TDD drafted and approved. Pending CR0097- GTS licenses | [10 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID966 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE |  | 09B. Data Migration | 04. Complete | 20 automated conversion Build & Unit test case approved. Pending CR0097- GTS licenses | [10 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID967 | Multiple instances | Identify scope of objects for Release-2 , Prepare Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 |  |  | 09B. Data Migration | 05. Not Applicable | Duplicate of 166 | [10 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID968 | Multiple instances | Technical Unit testing Results (TUT) for R2 objects |  |  | 2024-12-06 |  |  | 09B. Data Migration | 05. Not Applicable | Duplicate of 167 | [10 empty] | 1
R3 | Detailed Design | N/A | IDM 2.0 DELID969 | Multiple instances | ECA Platform CI/CD configuration |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) and IF(N) Zone | Aarti Sadarangani, Indra Singh | narsunil.narayanan@intel.com | Unity Catelog: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA167E8A5-488A-4FDF-B83A-9720D6615B7A%7D&file=Unity%20Catalog%20Migration%20Plan.pptx&action=edit&mobileredirect=true Speed Layer: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B578937D9-3F4C-49BB-84B4-397CC565F5C9%7D&file=ECA%20Speed%20Layer_POC%20Update_v1.pptx&action=edit&mobileredirect=true ECA Platform: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9075F96B-CC0C-4FFB-BB3F-F22F12CB0779%7D&file=ECA%20Platform%20Three%20Data%20Lake%20Architecture%20%25u2013%20Roadmap.pptx&action=edit&mobileredirect=true N and N+1: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8F95219-C62A-4031-9874-D402F125C89C%7D&file=N%20and%20N%201%20Dev%20Ops%20Landscape.pptx&action=edit&mobileredirect=true |  |  | TRUE | TRUE |  | Unity Catelog: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA167E8A5-488A-4FDF-B83A-9720D6615B7A%7D&file=Unity%20Catalog%20Migration%20Plan.pptx&action=edit&mobileredirect=true Speed Layer: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B578937D9-3F4C-49BB-84B4-397CC565F5C9%7D&file=ECA%20Speed%20Layer_POC%20Update_v1.pptx&action=edit&mobileredirect=true ECA Platform: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9075F96B-CC0C-4FFB-BB3F-F22F12CB0779%7D&file=ECA%20Platform%20Three%20Data%20Lake%20Architecture%20%25u2013%20Roadmap.pptx&action=edit&mobileredirect=true N and N+1: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8F95219-C62A-4031-9874-D402F125C89C%7D&file=N%20and%20N%201%20Dev%20Ops%20Landscape.pptx&action=edit&mobileredirect=true |  | 1
R3 | Detailed Design | N/A | IDM 2.0 DELID970 | Multiple instances | ECA Platform Setup |  |  | 2024-06-26 | TRUE | N/A | 10. Analytics | 04. Complete | For CORP(N) and IF(N) Zone | Aarti Sadarangani, Indra Singh | narsunil.narayanan@intel.com | Unity Catelog: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA167E8A5-488A-4FDF-B83A-9720D6615B7A%7D&file=Unity%20Catalog%20Migration%20Plan.pptx&action=edit&mobileredirect=true Speed Layer: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B578937D9-3F4C-49BB-84B4-397CC565F5C9%7D&file=ECA%20Speed%20Layer_POC%20Update_v1.pptx&action=edit&mobileredirect=true ECA Platform: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9075F96B-CC0C-4FFB-BB3F-F22F12CB0779%7D&file=ECA%20Platform%20Three%20Data%20Lake%20Architecture%20%25u2013%20Roadmap.pptx&action=edit&mobileredirect=true N and N+1: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8F95219-C62A-4031-9874-D402F125C89C%7D&file=N%20and%20N%201%20Dev%20Ops%20Landscape.pptx&action=edit&mobileredirect=true |  |  | TRUE | TRUE |  | Unity Catelog: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA167E8A5-488A-4FDF-B83A-9720D6615B7A%7D&file=Unity%20Catalog%20Migration%20Plan.pptx&action=edit&mobileredirect=true Speed Layer: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B578937D9-3F4C-49BB-84B4-397CC565F5C9%7D&file=ECA%20Speed%20Layer_POC%20Update_v1.pptx&action=edit&mobileredirect=true ECA Platform: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9075F96B-CC0C-4FFB-BB3F-F22F12CB0779%7D&file=ECA%20Platform%20Three%20Data%20Lake%20Architecture%20%25u2013%20Roadmap.pptx&action=edit&mobileredirect=true N and N+1: https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8F95219-C62A-4031-9874-D402F125C89C%7D&file=N%20and%20N%201%20Dev%20Ops%20Landscape.pptx&action=edit&mobileredirect=true |  | 1
R3 | Build | N/A | IDM 2.0 DELID971 |  | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 |  |  | 10. Analytics | 03. In Deliverable Review |  | Aarti Sadarangani | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID972 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 |  |  | 10. Analytics | 03. In Deliverable Review |  | Aarti Sadarangani | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID973 |  | Custom Code (RICEFW) |  |  | 2024-12-06 |  |  | 11. Technology | 04. Complete |  | Keerti Nayak | [9 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID974 |  | Integration Testing Cycle (ITC) Plan |  |  | 2024-12-06 |  |  | 11. Technology | 04. Complete |  | Keerti Nayak | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID975 | Single Instance | Technical design document (TDS) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 |  |  | 11. Technology | 04. Complete |  | Keerti Nayak | [9 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID976 | Multiple instances | Technical Fit-Gap analysis |  |  | 2025-03-15 | N/A | TRUE | 11. Technology | 04. Complete |  | Keerti Nayak | Chris Woodburn | 1.S4 Object Tracker https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Technology/S4%20R3%20Intel%20IDM%20Object%20Tracker_8May25.xlsx?d=wf08092b255fb438bb88db8e29d8f53d1&csf=1&web=1&e=Aoc17U 2. ECA Object Tracker - https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Technology/S4%20R3%20Intel%20IDM%20Object%20Tracker_8May25.xlsx?d=wf08092b255fb438bb88db8e29d8f53d1&csf=1&web=1&e=Aoc17U |  |  | TRUE | TRUE |  | https://app.smartsheet.com/sheets/8gcJJWPrqR26cPM5rPHqpJfmwj8fJ2crg4vCJ8r1 |  | 1
R3 | Build | N/A | IDM 2.0 DELID977 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 |  |  | 11. Technology | 04. Complete |  | Keerti Nayak | [9 empty] | 3
R3 | Detailed design | N/A | IDM 2.0 DELID981 | Multiple instances | System Landscape Strategy |  |  | 2024-07-26 | TRUE | TRUE | 12. Infrastructure | 04. Complete |  | Sarathbabu Raguru | Karl E Mailman | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F12%2E%20Infrastructure%2FSAP%5FLandscape%5FStrategy&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | Josh Wise, John Camarillo, Babu Jadam, Jinesh Jain, Keerti Nayak |  | TRUE |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F2%2E%20Non%2DSprint%20Deliverables%2FInfrastructure%2FSAP%5FLandscape%5FStrategy&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  | 1
R3 | Build | N/A | IDM 2.0 DELID985 | Single Instance | GRC AC and PC configuration document |  |  | 2024-10-18 | TRUE |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID986 | Single Instance | GRC AC and PC configuration document |  |  | 2024-10-18 | TRUE |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID987 | Single Instance | GRC access control (AC) and process control (PC) Unit test results (Artifact) |  |  | 2024-10-18 | TRUE |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 2
R3 | Detailed design | N/A | IDM 2.0 DELID989 | Single Instance | Privacy by Design (PbD) guidelines and training materials |  |  | 2024-07-12 | N/A | N/A | 13. Security | 05. Not Applicable | This is Single instance. Completed in R1 | Yazdani Shaik |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/PbD%20Guidelines%20%26%20Training%20Collateral?csf=1&web=1&e=EThEAO |  |  | TRUE |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/PbD%20Guidelines%20%26%20Training%20Collateral/%5BEXT%5D%20Re_%20%5BApproval%20Request%5D%20Intel%20IAO%20DPP%20Deliverable%20Sign-Off%20.pdf?csf=1&web=1&e=p1hEfF | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/PbD%20Guidelines%20%26%20Training%20Collateral?csf=1&web=1&e=EThEAO |  | 1
R3 | Build | N/A | IDM 2.0 DELID990 | Multiple instances | Production security role configuration (Artifact) |  |  | 2026-03-06 |  |  | 13. Security | 02. Being Developed |  | Natasha Laramie | deborah.whitely@intel.com | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/02%20Build/01.%20Sprint%20Deliverables/Security%20and%20Controls/Intel%20R3%20-%20Production%20Security%20Role%20Configuration%20(Artifact)%20IDM%202.0%20DELID990.xlsx?d=w51fe3f784c2e42e89190537bf2157432&csf=1&web=1&e=9f8Dif | [7 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID992 | Single Instance | Privacy by Design Assessment |  |  | 2024-10-18 |  |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID993 | Multiple instances | SAP GRC Segregation of Duties and Sensitive access matrix |  |  | 2026-04-30 |  |  | 13. Security | 02. Being Developed |  | Natasha Laramie (R1/R2)/Yazdani Shaik | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni |  |  | Raj Valluri, Kasiviswanathan Muthu, Joshua Wise, Amith Vallabhaneni | [5 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID994 | Multiple instances | SAP Infrastructure Cyber Risk Assessment |  |  | 2024-09-20 |  |  | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID995 | Multiple instances | SAP Segregation of Duties ruleset (SOD) build and unit test in GRC |  |  | 2024-10-18 |  |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID996 | Multiple instances | Security role unit test results (Artifact) |  |  | 2024-10-18 |  |  | 13. Security | 05. Not Applicable |  | Yazdani Shaik | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID999 | Single Instance | Change Awareness Assessment for cFin , ProdCo, Product Costing, and TMGF releases (A) |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1000 | Single Instance | Change Impact Assessments for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Detailed Design deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1003 | Single Instance | Change Network Kickoff and Meeting Materials for cFin, ProdCo, Product Costing and TMGF releases (A) |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test Deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1004 | Single Instance | Change Network Toolkit |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1005 | Single Instance | Communication materials for cFin, ProdCo, Product Costing, and TMGF releases (A) |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1012 | Single Instance | Training Curriculum for cFin, ProdCo, Product Costing and TMGF releases |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1013 | Single Instance | Training Development Plan |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1014 | Single Instance | Training Needs Assessment (A) |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1015 | Single Instance | Training Strategy |  |  | 2024-10-18 |  |  | 14. OCM | 05. Not Applicable | Test deliverable | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1016 | Single Instance | Cutover plan for SIT/UAT |  |  | 2026-03-06 | TRUE |  | 15. Cutover | 04. Complete | [11 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1017 | Single Instance | Cutover strategy |  |  | 2026-03-06 | TRUE |  | 15. Cutover | 04. Complete | [11 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1018 |  | ITC Test catalog and Test cases |  |  | 2026-03-06 | TRUE |  | 16. Testing | 04. Complete |  | Anurag Kumar | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1019 | Single Instance | Mock Cutover Plan |  |  | 2026-03-06 | TRUE |  | 15. Cutover | 04. Complete | [11 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1020 |  | Test strategy (including Testing approach, Responsibilities, Data requirements, Entry & Exit criteria, Signoff process and Bug management) |  |  | 2026-03-06 | TRUE |  | 16. Testing | 04. Complete |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1021 |  | Conversion Load Metrics based on Mock Cutover execution | [5 empty] | 15. Cutover | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1022 |  | ITC1 Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1023 |  | ITC2 Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1024 |  | ITC1 Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1025 |  | ITC2 Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1026 |  | ITC1 Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1027 |  | ITC2 Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1028 |  | ITC1 Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1029 |  | ITC2 Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1030 |  | Performance Test Script identification / Approval | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1031 |  | Performance Test Script identification / Approval | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1032 |  | Performance Test Script identification / Approval | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1033 |  | Performance Test Script identification / Approval | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1034 |  | UAT Testing Plan | [5 empty] | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1035 |  | UAT1 Test Cases and Scripts | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1036 |  | UAT2 Test Cases and Scripts | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1037 |  | UAT1 Test Cases and Scripts | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1038 |  | UAT2 Test Cases and Scripts | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1039 |  | UAT1 Test Cases and Scripts | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1040 |  | UAT2 Test Cases and Scripts | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1041 |  | UAT1 Test Cases and Scripts | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1042 |  | UAT2 Test Cases and Scripts | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1043 |  | UAT1 Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1044 |  | UAT2 Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1045 |  | UAT1Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID1046 |  | UAT2 Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1047 |  | UAT1 Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1048 |  | UAT2 Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1049 |  | UAT1 Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1050 |  | UAT2 Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1051 |  | Regression Testing Plan | [5 empty] | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1052 |  | Regression Test Cases and Scripts | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1053 |  | Regression Test Cases and Scripts | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1054 |  | Regression Test Cases and Scripts | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1055 |  | Regression Test Cases and Scripts | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1056 |  | Regression Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1057 |  | Regression Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1058 |  | Regression Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1059 |  | Regression Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1060 |  | Performance Testing Plan | [5 empty] | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1061 |  | Performance Test Cases and Scripts | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1062 |  | Performance Test Cases and Scripts | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1063 |  | Performance Test Cases and Scripts | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1064 |  | Performance Test Cases and Scripts | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1065 |  | Performance Test Results | [5 empty] | 03. FPR | 01. Not Started |  | Prabesh Acharya | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1066 |  | Performance Test Results | [5 empty] | 04. OTC IF | 01. Not Started |  | Ravi Vishwanathan, Shripad Deshpande | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1067 |  | Performance Test Results | [5 empty] | 07. FTS IF | 01. Not Started |  | Rudra Sengupta | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1068 |  | Performance Test Results | [5 empty] | 09A. Master Data | 01. Not Started |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1069 |  | Performance Test Defect resolution | [5 empty] | 11. Technology | 01. Not Started |  | Keerti Nayak | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1070 |  | 200 Automated test cases & Results | [5 empty] | 16. Testing | 01. Not Started |  | Anurag Kumar | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1071 |  | Business Continuity Plan (BCP) | [5 empty] | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1072 |  | Detailed cutover plan for Go Live | [5 empty] | 15. Cutover | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1073 |  | Production System Set-up | [5 empty] | 12. Infrastructure | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1074 |  | Go/No-Go criteria | [5 empty] | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1075 |  | Hypercare/Post Go-Live Support Strategy & Plan | [5 empty] | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1076 |  | Readiness Review and Sign-Off (Go-Live Approval) | [5 empty] | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1077 |  | Knowledge transfer plan | [5 empty] | 01. PMO | 01. Not Started | [11 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1083 |  | Production Support /IT Security Roles test results (Artifact) | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1084 |  | GRC AC and PC SIT test results (Artifact) | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1085 |  | UAT user to role mapping results (Artifact) | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1086 |  | Production user to role mapping results | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1087 |  | Segregation of Duties analysis - role level | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1088 |  | Segregation of Duties analysis – user level | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1089 |  | SAP Infrastructure Cyber Risk Assessment (Artifact) | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1090 |  | Controls test step requirements and results in UAT | [5 empty] | 13. Security | 01. Not Started |  | Nishat Ahmed, Yazdani Shaik | [9 empty] | 1
R3 | Test | N/A | IDM 2.0 DELID1091 |  | Data Privacy controls results in SIT and UAT (Artifact) | [5 empty] | 13. Security | 01. Not Started |  | Yazdani Shaik | [9 empty] | 2
R3 | Test | N/A | IDM 2.0 DELID1092 |  | Final S/4HANA Cutover Plan | [5 empty] | 15. Cutover | 01. Not Started | [11 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1093 |  | Prepare Final Cutover Plan | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1094 |  | Provide inputs to Production user to role mapping results | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1095 |  | Prepare Final Hypercare Plan | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1096 |  | Prepare Knowledge transfer plan | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1097 |  | Document Cutover execution results | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1098 |  | Identify & document Production Cutover Load Metrics | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1099 |  | Execute Production go live and document results | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1100 |  | Execute Hypercare and document results | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1101 |  | Setup Production security & GRC | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1102 |  | Prepare Security and GRC Standard Operation Procedures (SOP) | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1103 |  | Document Cutover validation results for manually configured controls in production and cutover dress rehearsal environment | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1104 |  | Develop and deliver Communications and Stakeholder Engagement Materials for Cutover / Go Live / Hypercare | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Deploy and Hypercare | N/A | IDM 2.0 DELID1105 |  | Develop Change Management and Training Knowledge Transfer plan and deliver ChangeScout data export | [6 empty] | 01. Not Started |  | Gaurav Tyagi, Vivek Sahni | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1106 |  | Configuration Unit testing Results (CUT) |  |  | 2026-03-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | CUTs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1107 |  | Custom Code (RICEFW) |  |  | 2024-12-06 | TRUE |  | 09A. Master Data | 04. Complete | Custom Code are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1108 |  | Functional specifications document (FDS) for in scope ECA objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 05. Not Applicable | No ECA objects in scope for R2 build | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1109 |  | Functional specifications document (FDS) for in scope RICEFW objects with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | FDSs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1110 |  | Functional Unit testing Results (FUT) for in scope ECA objects |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | No ECA objects in scope for R2 build | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1111 |  | Functional Unit testing Results (FUT) for in scope RICEFW objects |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | FUTs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1112 |  | S/4HANA Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | CDDs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID1113 |  | S/4HANA System Configuration |  |  | 2024-12-06 | TRUE |  | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1114 |  | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 09A. Master Data | 04. Complete | TDDs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1115 |  | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE |  | 09A. Master Data | 04. Complete | TUTs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 2
R3 | Build | N/A | IDM 2.0 DELID1116 |  | Configuration Design Document (CDD) with Unit Test Cases |  |  | 2024-12-06 | TRUE | TRUE | 09A. Master Data | 04. Complete | CDDs are under Sub Team folders | Lilibeth Lejarde | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1117 | Multiple instances | Technical design document (TDD) for in scope RICEFWs with Unit Test Cases |  |  | 2024-12-06 | TRUE |  | 11. Technology | 04. Complete | MIDDLEWARE | Keerti Nayak | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1118 | Multiple instances | Technical Unit testing Results (TUT) |  |  | 2024-12-06 | TRUE |  | 11. Technology | 04. Complete | MIDDLEWARE | Keerti Nayak | [9 empty] | 3
R3 | Build | N/A | IDM 2.0 DELID1119 | Multiple instances | Custom Code (RICEFW) |  |  | 2024-12-06 | TRUE |  | 11. Technology | 04. Complete | MIDDLEWARE | Keerti Nayak | [9 empty] | 3
R3 | Detailed design | N/A | IDM 2.0 DELID1124 | Multiple instances | Technical Fit-Gap analysis |  |  | 2024-06-28 | N/A | TRUE | 09A. Master Data | 04. Complete |  | Lilibeth Lejarde | Candice S Linnell | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Master%20Data/User%20Story%20Tracker?csf=1&web=1&e=1x0DQE |  | Candice S Linnell <candice.s.linnell@intel.com> | TRUE | TRUE | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/1.%20Sprint%20Deliverables/MDM/RE%20R3%20Master%20Data%20Design%20Sign%20Off%20-%20%20%20Ready%20to%20GO.msg?csf=1&web=1&e=lnhuwj | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=1rYW9K&CID=4cef5765%2D4080%2D4702%2Daf1a%2Dfa863bc7eb67&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F03%2E%20Final%20Deliverables%2FRelease%203%2F01%20Design%2F1%2E%20Sprint%20Deliverables%2FMDM%2FBPD&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Cshrutisingh7%40deloitte%2Ecom&OR=Teams%2DHL&CT=1738924152786&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEyMDEwMDIyMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID1125 | Single Instance | Deep dive SAP S/4HANA Security Strategy and Approach |  |  | 2025-03-15 | N/A | N/A | 13. Security | 05. Not Applicable | This is Single instance. Completed in R1 | Yazdani Shaik |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/IDM%202.0%20DELID199_Deep%20dive%20SAP%20S4HANA%20Security%20Strategy%20and%20_Approved.pptx?d=w0bd65bc7661e4bc58e748db0ba9e26aa&csf=1&web=1&e=Vs7VST |  |  | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/Strategy%20and%20Approach%20Deliverable/Approvals%20and%20Decisions?csf=1&web=1&e=gwKpO6 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security/IDM%202.0%20DELID199_Security%20and%20Controls%20Strategy%20and%20Approach%20Document.pptx.url?csf=1&web=1&e=ZKpcAi |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID1126 | Single Instance | GRC AC and PC design document |  |  | 2025-03-15 | N/A | N/A | 13. Security | 05. Not Applicable | This is Single instance. Completed in R1 | Yazdani Shaik |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/GRC%20AC%20and%20PC%20Design%20Document?csf=1&web=1&e=zg8pFs |  |  | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/01.%20Design/R1%20%26%20R2/GRC%20Access%20Controls%20%26%20Process%20Control%20Design%20Document/GRC%20AC%20And%20PC%20Deliverable%20Approvals?csf=1&web=1&e=lFadQs | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%201/01%20Design/2.%20Non-Sprint%20Deliverables/Security?csf=1&web=1&e=Yz0Cpe |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID1127 | Single Instance | Privacy Business Process and Object Risk Ranking/Triage Questionnaire (Artifact) |  |  | 2025-03-15 | N/A | N/A | 13. Security | 05. Not Applicable | This is Single instance Completed in R1 | Sameeksha Garg | eric.carlsen@intel.com, Jim Brennan | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%203/01%20Design/2.%20Non-Sprint%20Deliverables/Security/Intel%20RICEFW%20Triage%20Questionnaire%20v2.xlsx?d=w6f987b3a5fb0407999c33ea8372bf858&csf=1&web=1&e=MdQc8C |  | jim.brennan@intel.com | TRUE |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20by%20Design/PbD%20Triage/PbD%20Triage%20Approval%20by%20Jim%205.21.24.pdf?csf=1&web=1&e=Ppvb4x | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/00%20Consolidated%20RACM/01%20ITGC/ITGC%20Deliverable%20Approvals/EXT%20RE%20Finalization%20of%20ITGC%20Interface%20and%20Conversion%20Controls%20RACM_Raj%20Valluri.msg?csf=1&web=1&e=YPC9YH |  | 1
R3 | Detailed design | N/A | IDM 2.0 DELID1128 | Single Instance | Data Conversion Control Framework |  |  | 2025-03-15 | N/A | N/A | 13. Security | 05. Not Applicable | This is Single instance. Completed in R1 | Nishat Ahmed | Gary Nilsen, Rajeshwari Valluri, Sucheta A Bakhle | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/03.%20Final%20Deliverables/Release%202/01%20Design/1.%20Sprint%20Deliverables/Security%20and%20Controls/Controls?csf=1&web=1&e=feXGMr |  | Raj Valluri, Gary Nilsen, Sucheta A Bakhle | TRUE |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/02%20SAP%20Controls/01%20Design/01%20R1%20and%20R2/03%20Client%20Approval%20of%20the%20Design%20Document?csf=1&web=1&e=NGdclS |  |  | 1
R3 | Build | N/A | IDM 2.0 DELID1130 |  | Stakeholder Assessment for cFin , ProdCo, Product Costing, and TMGF releases |  |  | 2026-03-06 |  |  | 14. OCM |  |  | Laura Winterton | [9 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1131 |  | Integration Testing Cycle (ITC) Plan |  |  | 2026-03-06 |  |  | 16. Testing | 01. Not Started | [11 empty] | 1
R3 | Build | N/A | IDM 2.0 DELID1132 |  | Record Of Processing Activities (ROPA) (Artifact) |  |  | 2026-03-06 |  |  | 13. Security | 05. Not Applicable | [11 empty] | 1
R3 | Detailed design | Y | IDM 2.0 DELID1133 | Single Instance | Change Management Project Plan |  |  | 2025-10-28 | TRUE |  | 14. OCM |  | CR0618 | Laura Winterton | Cindie Blackmer | LINK | Laura Winterton |  |  |  |  | LINK |  | 1

## Comments
Row 217 | The sign off evidence is available here - https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/03%20Data%20%26%20Privacy/Deliverables/Privacy%20Assessments/Privacy%20Office%20Sign-Offs/RoPAs%20and%20PIAs%20for%20R3%20Design%20Final%20Sign%20off_Privacy%20Office.pdf?csf=1&web=1&e=80trYG | Sameeksha Garg | 03/31/25 3:47 PM
Row 229 | This can be removed. This is duplicate | Natasha Laramie | 10/28/24 2:00 PM
Row 230 | Deliverable was descoped in INT-CR0489​ | Natasha Laramie | 10/08/25 3:11 PM
Row 238 | Release should be all | Natasha Laramie | 10/28/24 1:46 PM
Row 239 | This is a duplicate and can be removed | Natasha Laramie | 10/28/24 1:03 PM
Row 239 | should say R1 | Natasha Laramie | 10/07/24 8:44 AM
Row 240 | Release should be all | Natasha Laramie | 10/28/24 1:59 PM
Row 247 | Deliverable was descoped in INT-CR0489​ | Natasha Laramie | 10/08/25 3:12 PM
Row 247 | should be tagged to Test, not Build | Natasha Laramie | 10/22/24 3:13 PM
Row 255 | this can be removed. this deliverable is a single instance | Natasha Laramie | 10/28/24 1:46 PM
Row 256 | This can be removed, this is duplicate | Natasha Laramie | 10/28/24 1:59 PM
Row 258 | This is a duplicate. Should be removed. we have IDM 2.0 DELID990 for r3 | Natasha Laramie | 10/27/25 12:30 PM
Row 259 | This is Sprint 1 to Sprint 11 Signed off. Exception topics will be signed off by Apr 25th. Review is in progress. | Sreevani Tadepalli | 03/31/25 4:10 PM
Row 260 | Deliverable was descoped per INT-CR0479​ | Natasha Laramie | 10/27/25 12:33 PM
Row 343 | Deliverable was descoped per INT-CR0479​ | Natasha Laramie | 10/08/25 3:16 PM
Row 348 | Release should say "All" | Natasha Laramie | 10/08/25 3:37 PM
Row 369 | This is a duplicate of IDM 2.0 DELID340. Marking this as not applicable so there is only one entry | Natasha Laramie | 10/08/25 4:00 PM
Row 378 | Release should say "All" | Natasha Laramie | 10/08/25 3:37 PM
Row 462 | This is a duplicate and can be removed | Natasha Laramie | 10/08/25 3:36 PM
Row 467 | Deliverable was descoped in INT-CR0489​ | Natasha Laramie | 10/08/25 3:12 PM
Row 469 | Deliverable was descoped per INT-CR0479​ | Natasha Laramie | 10/08/25 3:16 PM
Row 617 | This is not a deliverable | Natasha Laramie | 10/08/25 4:18 PM
Row 625 | This is a duplicate and can be removed | Natasha Laramie | 10/08/25 3:36 PM
Row 714 | this can be removed. this deliverable is a single instance | Natasha Laramie | 10/27/25 12:27 PM
Row 715 | this can be removed. this deliverable is a single instance | Natasha Laramie | 10/27/25 12:27 PM
Row 716 | This can be removed, this is duplicate | Natasha Laramie | 10/27/25 12:29 PM
Row 719 | Deliverable was descoped per INT-CR0479​ | Natasha Laramie | 10/27/25 12:33 PM
Row 722 | This can be removed. This is duplicate of IDM 2.0 DELID304 | Natasha Laramie | 10/27/25 12:36 PM
Row 723 | This can be removed. This is duplicate of IDM 2.0 DELID439 | Natasha Laramie | 10/27/25 12:37 PM
Row 839 | Was descoped | Natasha Laramie | 02/26/26 8:17 AM