## IDM 2.0 Program Change Request
Approved Release [PMO Only] | Intercepting Testing Cycle | Change ID (AC) | Approved/Denied | Next Steps | Program Scope | Requested Releases | Priority (Very High, High, Medium, Low) | Requestor Team* | Requestor Sub-team* | Logistics? | Impacted Towers/Horizontals (Multiple Selection) | Change Request Owner | Change Request IT Owner For The Function | Project Manager | Related Open Design Topic | Related CR | Related Risk/Issue [RAID #] | Related KDD [RAID #] | ServiceNow Reference | ServiceNow Delivery Status | B-App IAPM ID | B-App IAPM Name | Special Projects | Change Title* | Change Description | Rationale for the Change | Impact to Schedule | Ready for PMO Review? | Core vs Non-Core Functionality | Link to Approval Email | Link to Change Request Review Deck | CR Category | Type of Change [For Program Releases - R1-R5] | Impacted L3's | Will have BPM Standards (BIC/WIKI) Updates? | Complexity | Technical Effort Estimation | Design Complexity Value | Dollar Impact (US Design Hours) | Dollar Impact ($) | Functional Effort | CDI Tech Effort [SCP Build] | PDH Tech Effort [SCP Build] hrs | BY Tech Effort [SCP Build] hrs | ECA Tech Effort [SCP Build] hrs | Config Effort [ERP Build] | Tech Effort [ERP Build] | ECA Effort [ERP Build] | Data Migration [ERP Build] | Security Effort [ERP Build] | BApps Tech Effort | Total SCP Tech Effort | Total ERP Tech Effort | ERP Dev Team [For Build CR's Only] | Added/Pushed Object ID's? | Dev Team of New Object | Count of New Objects | Added Object ID's | RICEFW Console ID | S4 Object Tracker | Count of New S4 Objects | Deloitte ECA | Count of New Deloitte ECA Objects | Intel ECA | Count of New Intel ECA Objects | Count of New ECA Objects | SCP - RICEFW | Count of SCP RICEFW | SCP - PDH | Count of SCP - PDH | Count of New SCP Objects | Changed Build Objects | Count of Changed Objects | Changed S4 RICEFW's | Count of Changed S4 | Changed ECA ID's | Count of Changed ECA | Changed SCP ID's | Count of Changed SCP | Descoped RICEFW ID's | Replacement Object | Planned FUT Complete date | Count of Descoped RICEFW's | Change Status | Need Core Leadership approval? [PMO] | Need MRC Approval? [PMO] | Review Date with Change Ingestion | Notes from Change Ingestion | 2nd Review Date with CCB | Notes from 2nd CCB Review | Actual Review Date with CL [Stage 1] | Notes from Core Leadership Review [Stage 1] | Actual Review Date with CL [Stage 2] | Notes from Core Leadership Review [Stage 2] | Review Date with MRC | Notes From MRC Review | Comments for Rejection/Deferral | Design vs Build | Approval Level | Leadership Approval Date | Month of Approval | Final Month of Approval | Month of Creation | Creation Date | Days Open | Aging | Created By | Reconciliation Done? | For Future Release? | Completion Status (Build CR) | Completion Status (Object ID) | Completion Status (Manual) | Overall Completion | Added to Build CR Tracker | Applicable for R4
R1 (May 2025) | R1 | INT-CR0011 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) R4 (Release 4) | High | 09A. Master Data | 9A.3 Master Data - Customer |  | 04. OTC IF 05. OTC IP 09A. Master Data 13. Security | renata.prokop@intel.com | [11 empty] | KDDDAT002 change decision to share customer BP between ProdCo and TMGF | One of the 2 decisions in KDDDAT002 calls for the sharing of unique IDs for customers and suppliers across TMGF and ProdCo. We’d like to have separate IDs for customer only. | As we’ve gone through detailed design, its become clear that forcing the 2 to share IDs will add complexity to MDG and to the business processes, and there is no systemic way to keep this data fully secret from each side when IDs are shared. When IDs are being shared, each side of Intel has to share all of the General Data attributes that include name, address, bank account, industry code, customer contacts. It would not be possible to hide which customers are TMGF from ProdCo |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0011_Data_CR%20Deck_template.pptx?d=w19f4c3f3ca5c45039f3318f688caf6ca&csf=1&web=1&e=ihxEyo |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-07-18 |  |  |  | 2024-07-22 | [6 empty] | Design | CL/OSC | 2024-07-22 | 07, 2024 | 07, 2024 | 02, 2024 | 2024-02-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0013 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | Shane Bethune | [11 empty] | Change in Treasury Scope | Add APM and IHB-POBO in Scope | Intel Treasury Business decided to continue FX and Investment Management in Quantum and move all Inter-Company transactions including Non-IHC Loans to SAP. Business intends to channelize all Bank communications through single Channel to optimize cost and efforts of maintaining multiple Bank connectivities, hence Advance Payment Management will be used to achieve the objective. Payment on Behalf (POBO) functionality will be used for AP Payments in US and Israel to optimize Bank Accounts. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INTCR0013_FPR_CR.pptx?d=wab5fa74c7bbb4f6c946d95d6856db11d&csf=1&web=1&e=YVw3XH |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-03-12 | Ratified in CCB on 3/8. Does not need to be taken to OSC/CL again | [9 empty] | Design | Tower | 2024-03-12 | 03, 2024 | 03, 2024 | 03, 2024 | 2024-03-01 | 0 | < 15 Days | chgorantla@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0014 | Approved |  | ERP | R2 (Release 2) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF | Daniel Mahoney | [11 empty] | Additional Logistics L2/L3 to be included in R2 sprint plan | The R2 sprint plan will require additional Logistics L2's and L3's to receive and manage products at EWM warehouses.​ Additional L2's are core FTS process, and a new FTS sprint plan will be needed. | EWM warehouses will be setup as part of R2 Release. In order to move inventory from factory into EWM warehouses we will need to add Logistics Inventory receiving L2 and L3's into the sprint plan to facilitate the design discussions. 4 L2's and associated 31 L3's L2's - Receive Materials and services, Receive and Put away, Manage Lots/Batches, Internal storage and inventory movement. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/R2/INT-CR0014_OTC_CR%20Deck_R2.pptx?d=w41ad2811936841cdab3d26bd4ff5f4c5&csf=1&web=1&e=gua7ji |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-03-12 | Ratified in CCB on 3/8. Will be an Inform for OSC/CL on 3/12. | [9 empty] | Design | Tower | 2024-03-12 | 03, 2024 | 03, 2024 | 03, 2024 | 2024-03-05 | 0 | < 15 Days | maheshgowda@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0015 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.9 OTC IP - GTS |  |  | Dawn L Kahane | [11 empty] | Trade DFC Apps – SPT/CTM/MHB | Migrate DFC Apps IAPM #7799 X-Border Import-Export Tracker (SPT/CTM/MHB) from ICX platform to ERP | ICX is EOL’ng EO 2027. The ICX platform is not compatible with S/4 or GTS E4H. The applications capability is required for Duty Free Compliance. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | From: Hogg, Richard <richard.hogg@intel.com> Decision made based on Jeff/Keyvan 1:1 We will not be “Migrating DFC Apps IAPM #7799 X-Border Import-Export Tracker (SPT/CTM/MHB) from ICX platform to ERP”, instead we will be rebuilding it as a boundary app as per the decision ~one month ago Thank you Richard |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2024 | 2024-03-15 | 0 | < 15 Days | arpitsharma@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0016 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 06. PTP 11. Technology 17. B-App | achandrasekaran@deloitte.com | [11 empty] | Blackline vs CFIN JE Tool | To migrate Journal Posting Capability from Blackline to S4 (CFIN) as standard JE tool; eliminating Blackline-JET boundary apps | Standardized, leading approach to leverage standard S4 capability Transform and streamline process and eliminate boundary apps Blackline-JET​ Positive LT ROI of ~$200K yearly (after year 2026). ST once off cost ($142K) in 2024/2025 to re-engineer BL automated JE in S4 directly​ Easier to maintain and configure workflow, reduce dependency on vendor & reduce enhancement cost​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1BABD50A-5F90-470E-8FFE-90799A52D36F%7D&file=BL%20to%20S4%20JE%20posting_FPR_CR%20Deck_template.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-03-28 |  |  |  | 2024-04-05 | Approved | [5 empty] | Design | CL/OSC | 2024-04-05 | 04, 2024 | 04, 2024 | 04, 2024 | 2024-04-05 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0017 | Cancelled |  | ERP | R2 (Release 2) | High | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | suresavula@deloitte.com | [11 empty] | Shared Services Allocations (SSA) - PaPM | Additional scope for Profitability and Performance Management (PaPM) team to complete Shared Services Allocations based on the business requirement to keep the allocation process simple and the financial postings are only to be done in Company Code = 100 and at the Profit Center level. | Business need is for all SSA spending to go with one company code = 100. This is not possible in S/4. PaPM allows flexibility to do this without creating multiple allocation cycles for each Legal Entity. Both Plan/Forecast and Actual allocations will be handled via PaPM. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0017%20-%20SSA_PaPM%20FPR_CR%20Deck%20template.pptx?d=w144dcbc4dec54cc99931307053521516&csf=1&web=1&e=DeIpFa | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2024 | 2024-04-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0018 | Approved |  | ERP | R5+ (Post Release 5) | Low | 07. FTS IF | 7.1 FTS IF - ALL |  |  | Shamin A Shirodkar | [11 empty] | Replacement of SAP ME | Replace SAP ME with SAP DMC or one of MES300/ | SIMS BU uses SAP ME which is integrated to SAP ECC. As part of the IAO ERP program a decision was taken to keep SAP ME and not replace during IAO timelines. At some point before 2030 a transition will be needed to SAP DMC. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | Yes | 2024-03-04 |  |  |  | 2024-03-04 |  |  |  | 2024-03-04 |  |  | Design | MRC |  | 03, 2024 | 03, 2024 | 04, 2024 | 2024-04-06 | 0 | < 15 Days | againda@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0019 | Cancelled |  | ERP | R5+ (Post Release 5) | Medium | 04. OTC IF | 4.1 OTC IF - ALL |  | 09A. Master Data 09B. Data Migration | Shelly Lafree | [11 empty] | Eliminate Duplicate Customer ID | Systematically eliminate use cases for multiple customer ids by exploring various options including implementing sales contracts | Mitigate negative impact of duplicate customer IDs including negative impacts to Intel Compliance program |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | As per OTC PM, this CR is no longer needed as there will not be any additional changes from OTC for customer master data design. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2024 | 2024-04-06 | 0 | < 15 Days | againda@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0020 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) | High | 01. PMO | 1.1 PMO - ERP PMO |  | 03. FPR 04. OTC IF 07. FTS IF 09A. Master Data | Anand Jha | [11 empty] | Plant Maintenance effort for SWAP (WIINGS) |  |  |  | Yes |  |  |  |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 14. MRC Approved (end status) | Yes | Yes | 2024-05-24 |  |  |  | 2024-05-24 |  |  |  | 2024-05-24 |  |  | Design | MRC |  | 05, 2024 | 05, 2024 | 04, 2024 | 2024-04-27 | 0 | < 15 Days | againda@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0021 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) | High | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 06. PTP 07. FTS IF 09A. Master Data 09B. Data Migration 13. Security | surnagarajan@deloitte.com | [11 empty] | Spares - Quality Management | SIMS business is currently using SAP QM functionalities to manage incoming (purchased items from vendor) quality inspection process which is currently deemed out of scope for the program. This change request is for bringing the SIMS quality management functionality into scope. | Without addressing this the critical quality management process for purchased items cannot be performed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR0021_E2E_CR%20Deck_SIMS%20QM.pptx?d=w5d417a069f0b42f7add6d42f9fd310df&csf=1&web=1&e=QYYNlS |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | Yes | 2024-06-06 | Change request description being modified. It was determined that there is no need for QM for SIMS. The only need is for QM for Spares. Analysis has been completed by the PTP team and this CR will be rereviewed in OSC/CL on WW37.2 |  |  | 2024-09-25 | Approved |  |  | 2024-03-04 |  |  | Design | MRC |  | 03, 2024 | 03, 2024 | 05, 2024 | 2024-05-14 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0022 | New |  | ERP | R5+ (Post Release 5) | Low | 01. PMO | 1.1 PMO - ERP PMO |  | 03. FPR 06. PTP | Anand Jha | [11 empty] | “PO setup” for service | Implement PO for service to enable accrual for services at a detailed level. Currently the solution is being met by building a custom solution. | Reduce customization |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2B846E77-FE9F-486F-A200-9EE27A656D26%7D&file=IAO%20ERP%20OSC/CL%20-%205.13.2024.pptx&wdLOR=cD701DB52-81F5-4D82-8952-155B87C310D0&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 00. Identified | Yes | Yes | [11 empty] | Design | MRC |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2024 | 2024-05-25 | 683 | > 30 Days | againda@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0023 | Rejected |  | ERP | R3 (Release 3) R4 (Release 4) | Low | 04. OTC IF | 4.11 OTC IF - Order Management |  | 02. E2E Process Integration 04. OTC IF | kimberly.a.gomez@intel.com | [11 empty] | SIMS/TPTD scope increase for OTC IF from R3 to R4 | There is an incremental effort for SIMS/TPTD is needed for R3 through R5. Effort is for OTC-IF team resources. Resources working on OTC-IP will not need any extension as IP is big bang & for testing, deployment and post go-live support. | R3 would be through LE 101 but ship would follow the R2 interim model as not all sites are on S/4 in R3. R4 and onwards is full PO/SO model. Currently R4 is not in scope so need to do a change request to include in scope |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/0%20Admin/Change%20Control/INTCR0023_OTC%20IF_CR%20SIMS-SMD%20scope%20increase%20for%20OTC%20IF%20from%20R3%20to%20R4.pptx?d=w76222241b6354db7b78b39adbc6bce68&csf=1&web=1&e=18fpag |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | Yes |  | 2024-07-18 | As of 10/1, this CR was cancelled as OTC IF SIMS is not needed for R4; will be accommodated in R3. Hiring is on a freeze. This CR is tracked within the leadership decks as a RAID 959. We will revisit once the approval is given (WW37). | [9 empty] | Design | CL/OSC |  | Missing Review Date for Approval Level | 07, 2024 | 06, 2024 | 2024-06-11 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0024 | Approved | Should be tagged to LOGI0519_IF, LOGI0520_IF, LOGE0521_IF | ERP | R2 (Release 2) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 04. OTC IF 07. FTS IF 11. Technology 12. Infrastructure 13. Security 15. Cutover 16. Testing 17. B-App | Haritha Komma | [11 empty] | Foundry Quality and Reliability (FQR) team: R3 scoped to R2 change request: ECD (Excursion Containment and Disposition) - ABUS ECD Webservices needed in R2 Vs R3. | Foundry Quality and Reliability (FQR) team needs ECD-ABUS web services enabled for R2.Containment Disposition is an essential part of Excursion Management response where discrepant material is required to be hold for additional risk assessment. Intel Manufacturing has automated system with established business & system process to support containment across various portion of the supply chain. This is an centralize all product hold / Quarantine (PHQ) of lots across supply chain from FAB, Bump, DSDP,ATM and Warehouse with connection to INTEL Shopfloor of MES, Workstream and SAP to quarantine lot and prevent shipment to downstream /Customer. ECD is integration with issue documentation, traceability and containment/Disposition to provide holistic issue management across INTEL supply chain (Int Mfg and Ext Mfg) | Failed to timely contain the material in Warehouse and lead to escapee risk to INTEL customer which will impact to customer relationship. Indirectly, create a wrong perception to customer on Quality Management System. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR0024_Intel%20Foundry%20FTS_ECD%20Deck_R2.pptx?d=wb596183c9b8f4a589a96cfb9fd773334&csf=1&web=1&e=ilCJV4 |  | 13. Other Milestone Adjustments |  |  | Very High | 0 | 4 | [8 empty] | 1074 |  |  |  |  | 0 | 1074 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-06-27 | a. Share technical estimate across SAP, and Boundary (including functional and technical) with the PMO by Monday, 7/8 – Dinesh Basankar b. Capture the L3 process that the FG Shipping Involving Quality Process RICEFW will be tied to within the CR Template – Ramya Mathukumilli c. Include CR within the Tuesday, 7/9 OSC/CL meeting – Alpna Gainda / Uzma Ahmed |  |  | 2024-07-09 | The functionality will be ready for testing within R2 ITC3. Reviewed and approved by OSC/CL. | [5 empty] | Other | CL/OSC | 2024-07-09 | 07, 2024 | 07, 2024 | 06, 2024 | 2024-06-24 | 0 | < 15 Days | haritha.komma@intel.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0025 | Cancelled | This CR has been deferred for R4 | ERP | R4 (Release 4) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 04. OTC IF 05. OTC IP 13. Security 14. OCM 15. Cutover 16. Testing | JEAN-MARC LENC | [11 empty] | GTS ITAR (International Traffic in Arms Regulations) license check functionality for IAO | Amend IAO ERP SOW to add GTS ITAR (International Traffic in Arms Regulations) license check functionality to scope. | U.S. government agencies and U.S. defense contractors want to leverage Intel’s U.S. commercial fabrication facilities and process technologies to produce integrated circuits for their defense platforms. Shipment of such goods is subject to US International Traffic in Arms Regulations (ITAR) require special export license controls to ensure compliance. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Piyush and Prem that this is not required for an R4 plant | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2024 | 2024-07-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0026 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP 06. PTP 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | ryan.v.le@intel.com | [11 empty] | Boundary App integration with SAP GTS for Compliance screening | Amend IAO ERP SOW to support boundary app integration with SAP GTS. | Boundary apps interface with SAP GTS to perform SPL, Embargo, and License compliance check screening as well as retrieve product classification. Development on the GTS side is needed to update the interfaces and ensure compliance with Trade regulations. List of boundary apps for R3 scope. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-%20CR0026%20Change%20ID_Tower_CR%20Deck_GTS_Updated.pptx?d=w90a6c1b22e1b402c85af35cdd720f768&csf=1&web=1&e=VtQfag |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-08 | a. Update CR to remove this CR holding up L3 design. Close L3 design with the assumption that the integration will be enabled. This CR should only hold up Build of this integration. b. Finalize number of interfaces and complete effort & budget estimation – Eoin Dick/Hitesh Mayekar/Keerti Nayak c. Estimation needs to be end to end including ITC and UAT and determine options of supporting these as Intel responsibilities – Ryan Le/Hitesh Mayekar/Eoin Dick |  |  | 2024-09-04 | • As a result of detailed discussions in Boundary Apps workshops, the team realized the need for additional objects to be created in order to integrate certain boundary apps with SAP GTS. o The boundary apps track customer and vendor engagement, and a check is needed to ensure that the business partner is a part of a sanctioned party list.  If they are not, any engagements will be terminated. Therefore, this is a compliance requirement. o These checks need to be enabled in order to retire the legacy GTS system. • This CR will create an additional 14 interfaces, 5 enhancements, and 3 reusable API’s that boundary app interfaces can connect to; other boundary apps will be able to utilize them in the future. o A total of 26 L3’s will be impacted; the flows will be evaluated to determine which boundary app will be pulled for what information, and the design will be updated to include the appropriate screening. o The master data and enabling components will be set up in the GTS system. | [5 empty] | Design | CL/OSC | 2024-09-04 | 09, 2024 | 09, 2024 | 07, 2024 | 2024-07-08 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0027 | Approved | Re-visit the technical effort required once design is complete | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 11. Technology 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | JEAN-MARC LENC | [11 empty] | Broker Integration - Importer Centric - NL (1 broker) R3; US (4 brokers) R4 | Modify the IAO ERP Statement of Work (SOW) to transition from a Broker-Centric to an Importer-Centric GTS solution for integration with customs brokers. Request is a scope swap but adds some integration elements with the Broker and S/4. | SAP GTS offers two Broker Enablement solutions for integrating with brokers for customs clearance. Switching to the Importer-centric solution where Intel formulates the declaration and sends it to the broker is far more strategically aligned with Trade’s long-term vision to electronically self-file with customs authorities and save on brokerage fees. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0027%20-%20Broker%20Integration%20-%20Importer%20Centric%20-%20NL%20(1%20broker)%20R3;%20US%20(4%20brokers)%20R4.pptx?d=w4c67dcb4dd674fdd9690c771a04e2e3c&csf=1&web=1&e=zdt96b |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [8 empty] | 2500 |  |  |  |  | 0 | 2500 | N/A | Yes |  | 0 |  | 3166 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-15 |  |  |  | 2024-10-30 | OSC/CL Approved to proceed with work | [5 empty] | Design | CL/OSC | 2024-10-30 | 10, 2024 | 10, 2024 | 07, 2024 | 2024-07-08 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0028 | Cancelled |  | ERP | R4 (Release 4) | Medium | 06. PTP | 6.6 PTP - GTS |  | 06. PTP 13. Security 14. OCM 15. Cutover 16. Testing | ryan.v.le@intel.com | [11 empty] | GTS Broker Integration - US | Amend IAO ERP SOW to switch from Broker Centric to Importer Centric GTS solution for integrating with customs brokers of US for remaining 3 US Brokers. | SAP GTS offers two Broker Enablement solutions for integrating with brokers for customs clearance. Switching to the Importer-centric solution where Intel formulates the declaration and sends it to the broker is far more strategically aligned with Trade’s long-term vision to electronically self-file with customs authorities and save on brokerage fees. |  | Yes |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This is a duplicate of INT-CR0027 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2024 | 2024-07-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0029 | Approved | Should be tagged to OTCC0517 | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 09B. Data Migration | jason.carmichael@intel.com | [11 empty] | OTC- IF Order Conversion Automation | The OTC - IF team requires an automated process to facilitate the migration in R2 of open sales orders from SAP ECC to the S/4 system. | This need has become more pressing due to the inclusion of a new customer going live in Q3'24, which will substantially increase the volume of open sales order line items we need to transfer—from less than 150 to over 1000. Implementing this automated process is not only critical for the immediate transition but will also lay the groundwork for the R3 conversion program already in the pipeline. |  | Yes |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0029%20-%20OTC-IF%20Auto%20Order%20Migration.pptx?web=1 |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [10 empty] | 188 |  |  | 0 | 188 | Configuration | Yes |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-07-18 |  |  |  | 2024-08-01 | [6 empty] | Design | CL/OSC | 2024-08-01 | 08, 2024 | 08, 2024 | 07, 2024 | 2024-07-15 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0030 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | jason.carmichael@intel.com | [11 empty] | OTC- IF Adv Ship Notification | OTC - IF needs the L3 for EDI / 3B2 Advanced Ship Notification to be incorporated into the R2 release. | This L3, LO-190-120, was planned for R3, however with the inclusion of a new customer going live in Q3'24, we need to include the EDI 3B2 in R2 to not impact the customer when we move from ECC to the S/4 system. |  | Yes |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0030%20-%20OTC-IF%20ASN.pptx?web=1 |  | 1. Process Scope / Design Change | LO-190-120 |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-07-18 | o Shripad to work with Tech team to complete an estimation on the effort needed. o Uzma & Shawn to add CR to next week’s OSC/CL meeting agenda. |  |  | 2024-07-25 | Aligned and Approved with OSC/CL | [5 empty] | Design | CL/OSC | 2024-07-25 | 07, 2024 | 07, 2024 | 07, 2024 | 2024-07-15 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0031 | Approved |  | ERP | R2 (Release 2) | High | 14. OCM | 14.5 OCM - OTC Embedded |  | 04. OTC IF | Laura Winterton | [11 empty] | R2 Awareness items | Adjustments to the R2 Awareness Communications (to be replaced with Campaign) and R2 Awareness Assessment milestones required. | GPO requested shift of R2 awareness campaign (communications) and assessment to allow for leadership assessment and socialization ahead of formal communications. Stakeholders and leaders have been identified and assessed. Forum collection is underway and leadership alignment activities will occur over the summer in advance of an August awareness campaign and Sept awareness assessment. OTC Intel Foundry is the primary decider of this milestone as: • The tower is 85% of the stakeholder group • Finance stakeholders have already received an awareness communication earlier this year • FTS ERP information will be aligned with the SCP program |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0031%20-%20OCM%20R2%20Stakeholder%20Awareness%20and%20Assessment.pptx?d=w0b2e296ef7c34954b6a3b9f4e55ffc8b&csf=1&web=1&e=UrGGvX |  | 13. Other Milestone Adjustments | NA |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-07-22 | [10 empty] | Other | Tower | 2024-07-22 | 07, 2024 | 07, 2024 | 07, 2024 | 2024-07-16 | 0 | < 15 Days | lwinterton@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0032 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.4 FPR - Intercompany |  | 03. FPR 11. Technology | Alicia Lim | [11 empty] | Intercompany Transfer Pricing - PaPM | Intercompany TP (cost plus) process today relies upon macro-enabled excel files to complete end of period j/e postings (~2500 hours/year est. spent on process) with risk of errors due to manual steps. Solution is needed to automate TP cost plus calculation. A new technology solution is required to automate the process and enable users the ability to simulate entries prior to posting to the ledger. | PaPM's functionality and flexibility as a calculation engine and allocation solution is the recommended tool for TP use case. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2004%20-%20Interco%20%26%20Transfer%20Pricing/Transfer%20Pricing/INT-CR0032_Intercompany_TransferPricing.pptx?d=w865e048dcba9465f85efac1ecf606a00&csf=1&web=1&e=YN5cfo |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-11 |  |  |  | 2024-09-13 | Approved for Intel IT | [5 empty] | Design | CL/OSC | 2024-09-13 | 09, 2024 | 09, 2024 | 07, 2024 | 2024-07-29 | 0 | < 15 Days | dahahn@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0033 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 13. Security | Yazdani Shaik | [11 empty] | $0 Change Order to Non-ERP SOW | $0 Change Order to modify the Non-ERP SOW to adjust some of the milestone due dates and invoice issue dates given the engagement started a little later than expected. | Change in timeline for the Non-ERP original SOW which needed us to revisit the milestone dates |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA302A981-4063-40BB-BA96-51BFE6E85F16%7D&file=Change%20ID_Tower_CR%20Deck_Security%20Non%20ERP_08212024.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-08-08 | a. It was confirmed that Raj has approved this change. b. Update Change Request deck to include affected deliverables and date changes, and send to Uzma – Alycia Steiner c. Proceed with $0 Change Order – Alycia Steiner / Yaz Shaik | [9 empty] | Other | Tower | 2024-08-08 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-01 | 0 | < 15 Days | alsteiner@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0034 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data |  |  | 11. Technology | Lilibeth Lejarde | [11 empty] | Move DATI0394, Reltio to MDG Interface | CR for Moving RICEFW DATI0394 (Inbound Interface from Reltio to MDG to push UCD ID) from R2 to R3​ |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/CL/IAO%20ERP%20OSC/CL%20-%208.1.2024.pptx?d=w4959ae1526e945dd92884471c28cc9d5&csf=1&web=1&e=u6FbqR&nav=eyJzSWQiOjIxNDc0ODMwOTEsImNJZCI6MzIzNjYzODk2N30 |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  | DATI0394_IP, DATI0394_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATI0394 | 1 | DATI0394 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-07-25 |  |  |  | 2024-08-01 | [6 empty] | Design | CL/OSC | 2024-08-01 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-01 | 0 | < 15 Days | llejarde@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0035 | Approved |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology | Prabesh Acharya | [11 empty] | Release Change for Treasury Interface FPRI0168 and FPRI0169 | To move the release of FPRI0168 and FPRI0169 to R1 from R3 | The entire exchange rate functionality is part of R1 release, as a result of which Interfaces FPRI0168 and FPRI0169 relating to Exchange rate will be moved to R1 release aligning with the foreign exchange rate stream for downstream to different source systems |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/CL/OSC/CL%20Deck%20Archive/IAO%20ERP%20OSC/CL%20-%208.1.2024.pptx?d=w4959ae1526e945dd92884471c28cc9d5&csf=1&web=1&e=YwyZGm&nav=eyJzSWQiOjIxNDc0ODMwOTIsImNJZCI6MTEzNzUxNzA3MX0 |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRI0168, FPRI0169 | 2 | FPRI0168, FPRI0169 | 2 |  | 0 |  | 0 | FPRI0168, FPRI0169 |  |  | 2 | 10. OSC/CL Approved (end status) | Yes | No | 2024-07-25 |  |  |  | 2024-08-01 | [6 empty] | Other | CL/OSC | 2024-08-01 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-01 | 0 | < 15 Days | shoujain@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0036 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration 11. Technology | Prabesh Acharya | [11 empty] | Recon Reports for Automated Data Conversion Objects | Adding scope to develop recon reports in BODS for automated finance data conversion objects. | Recon reports are added to scope to aid in expediting the reconciliation of the data conversion objects (GL, Cost Center & Cost Center Hierarchies, Historical quarterly consolidated data from BCS to GR) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0036_Recon%20Reports%20for%20Automated%20Data%20Conversion%20Objects.pptx?d=w5b4e372416944792aeec85581fc06b8a&csf=1&web=1&e=6tX6vm |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 104 | 0 | [10 empty] | 104 |  |  | 0 | 104 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRC0009, FPRC0010, FPRC0011 | 3 | FPRC0009, FPRC0010, FPRC0011 | 3 |  | 0 |  | 0 | N/A |  | 2024-08-30 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-01 | a. Update FS and Build completion date in current Build Sprint plan as per what was shared in the CR – Keerti Nayak/Lauren Herschberg |  |  | 2024-08-09 | [6 empty] | Build | CL/OSC | 2024-08-09 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-02 | 0 | < 15 Days | navnegi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0037 | Approved | At the end of R3 design phase for Analytics, Deloitte will assess the overall scope and will then “true up” the balance between planned vs. actual efforts for Analytics for R1/R2/R3. | ERP | R1 (Release 1) R2 (Release 2) | Very High | 10. Analytics | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics 11. Technology 12. Infrastructure 13. Security 15. Cutover 16. Testing | Sunil Narayanan | [11 empty] | Near Real Time Reporting on HANA SideCar for FPR | Analytics current scope is to deliver models and reports for batch reporting on ECA (Azure, Databricks, Snowflake, Power BI). This CR is to build data models on HANA SideCar, and create reports on Analysis for Office for meeting Real Time/Near Real Time reporting requirements, which is a completely new tech stack. Per request from Intel, Deloitte will treat this in the interim as a $0 change order. At the end of R3 design phase for Analytics (Nov 2024), Deloitte will assess the overall scope and will then “true up” the balance between planned vs. actual efforts for Analytics for R1/R2/R3. | FPR needs RT/NRT reporting for PnL, Trial Balance, Consolidated Balance and Accounts Receivables. Their specific request is to have excel based reporting capabilities on RT/NRT basis to meet their goal of shortening period end close. These are to be met for R1/R2. Intel has selected, post OSC/CL decision, Side-Car as the backend solution for RT/NRT requirements and AO as frontend tools. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B16C1464C-D7A7-466F-BDFC-4C0CA54453A8%7D&file=INT-CR0037_Analytics_CR%20Deck.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | High | 9870 | 3 | [9 empty] | 9870 |  |  |  | 0 | 9870 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-08 | a. Update Change Request deck with scope of backend work (ingestion tables, data models etc.)– Sunil Narayanan/Neha Mehta/Karthik Subramanian b. Discuss best way to represent $0 CO – Anand Jha/Uzma Ahmed c. Bring CR details to ERP Huddle with Mike – Alpna Gainda d. Check with Rebecca Verette to see if she is available on Thursday, 8/15 from 12PM-1PM PST for ERP Huddle – Sunil Narayanan |  |  | 2024-08-27 | OSC/CL Approved to proceed with work | [5 empty] | Design | CL/OSC | 2024-08-27 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-08 | 0 | < 15 Days | nehamehta9@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0038 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | ECA/Analytics Recon Reports for Automated Data Conversion Objects | CFIN Initial load (transactions) & replication – Ability to reconcile accounting documents along with critical attributes (field by field) including exception reports and alerts. This would include validate account level activity (i.e., customer/vendor, IC customer/vendor, cost object mapping) between ECC and S4 (CFIN). ​ Group Reporting conversion – Ability to reconcile Group reporting historical balances (3 years) that are migrated into Group reporting from BCS during initial load. | Reconciling SAP transactional data with CFIN/Group Reporting transactional data during parallel run is essential for ensuring the accuracy, consistency, reliability of financial data and audit support. This will be critical during period close process to identify and address discrepancies if any , swiftly. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0038_Recon%20Reports%20for%20CFIN%20Transactional%20Data.pptx?d=w33b4b08e67104d519bcdc242b1ca961d&csf=1&web=1&e=f3WnZw |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-100 |  |  | 925 | 0 | [9 empty] | 925 |  |  |  | 0 | 925 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV033, FPRXV034, FPRXV035, FPRXV036 | 4 |  | 0 | FPRXV033, FPRXV034, FPRXV035, FPRXV036 | 4 |  | 0 | N/A |  | 2024-11-02 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-15 | Approved for effort estimation and for presentation to OSC/CL |  |  | 2024-08-21 | [6 empty] | Build | CL/OSC | 2024-08-21 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-12 | 0 | < 15 Days | sosil@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0039 | Cancelled |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) R4 (Release 4) | Low | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 04. OTC IF 07. FTS IF 09A. Master Data | Kelly Gerber | [11 empty] | Do not setup FERT's in IF S/4 | Do not setup FERT's in S/4 | Setting up in S/4 goes against future state design ,R3 where the part that customer orders needs to be connected to BOM. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber on 4/1 to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2024 | 2024-08-14 | 0 | < 15 Days | haritha.komma@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0040 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 10. Analytics | Clifford Wang | [11 empty] | R3 Stakeholder Assessment | Adjustment to milestone due date for R3 Stakeholder Assessment required. Request that due date be updated to mid Q1'25. | R3 Stakeholder Assessment is currently due 8/30/24, while R3 Design is still in progress. Stakeholder data has been captured each sprint to date, but a holistic view of stakeholder impacts won't be available until post-Design. Holding off until Q1 to finalize the Stakeholder Assessment will provide better data to inform R3 training deliverables, which are scheduled for mid Q2'2025. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0040%20-%20OCM%20R3%20Stakeholder%20Assessment.pptx?d=wf94df5c424954dfc823af63e9f4c1f6a&csf=1&web=1&e=a3jAVG |  | 13. Other Milestone Adjustments | NA |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-08-22 | Approved offline by Uzma | [9 empty] | Other | Tower | 2024-08-22 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-15 | 0 | < 15 Days | cliwang@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0041 | Approved |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | Prabesh Acharya | [11 empty] | Improve Criteria for Extracting Cost Center Hierarchy | Enhance the criteria for extracting data to ensure only active company codes created in the new S/4 MDG system are considered for extraction from SAP ECC. Exclude inactive company codes from the cost center hierarchy extraction process in SAP ECC. | Inactive company codes in ECC are not migrated to S/4 CFIN and should therefore be excluded from the Cost Center Hierarchy extraction in SAP ECC. Including these inactive codes results in unwanted data being extracted, which prolongs the data reconciliation process during cutover |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0041_Cost%20Center%20Hierarchy%20extraction%20criteria%20refinement.pptx?d=w0b4e17fa7cb848bd9623a00da1ec6352&csf=1&web=1&e=zJyRgy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 27 | 0 | [10 empty] | 27 |  |  | 0 | 27 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRC0009 | 1 | FPRC0009 | 1 |  | 0 |  | 0 | N/A |  | 2024-08-29 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-08-15 | Approved for effort estimation and for presentation to OSC/CL | [9 empty] | Build | Tower | 2024-08-15 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-15 | 0 | < 15 Days | navnegi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0042 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | ECA Recon Reports for Cost Center & Profit Center Hierarchy | Cost Center Hierarchy Recon Report – Ability to reconcile Cost Center Hierarchy between MDG & CFIN in ECA.​ Profit Center Hierarchy Recon Report– Ability to reconcile Profit Center Hierarchy between MDG & CFIN in ECA | The governance of Cost Center and Profit Center Hierarchies will be managed within the new S/4 MDG system and subsequently replicated to S/4 CFIN for both operational and reporting purposes. Ensuring reconciliation between the new S/4 MDG and CFIN is crucial for maintaining the accuracy, consistency, and reliability of these hierarchies, as well as for providing essential audit support. This process is vital for identifying and addressing any discrepancies that may arise. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0042_ECA%20Recon%20Reports%20for%20Cost%20Center%20%26%20Profit%20Center%20Hierarchy.pptx?d=w9423163ca19644a5813174b4c67fba89&csf=1&web=1&e=EAADkw |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-100 |  |  | 30 | 0 | [9 empty] | 30 |  |  |  | 0 | 30 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR028, FPRXR029, FPRXR030, FPRXR031, FPRXR032, FPRXR033 | 6 |  | 0 | FPRXR028, FPRXR029, FPRXR030, FPRXR031, FPRXR032, FPRXR033 | 6 |  | 0 | N/A |  | 2024-09-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-08-15 | Approved for effort estimation and for presentation to OSC/CL |  |  | 2024-08-27 | [6 empty] | Build | CL/OSC | 2024-08-27 | 08, 2024 | 08, 2024 | 08, 2024 | 2024-08-15 | 0 | < 15 Days | navnegi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0043 | Approved |  | ERP | R2 (Release 2) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology 12. Infrastructure | Shashank Kale | [11 empty] | Change in technical approach of MPL Waybill from queue based data transfer to Direct API Call | The technical approach of integration has changed from AMQ queue based to direct API call between MPL system and Mulesoft | AMQ is a legacy system for interfacing between systems. As part of IAO program, the idea is to improve and upgrade the integration to the latest technology. A direct API call will remove an additional layer of AMQ. This will require design change in both MPL and Mulesoft. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR0043%20Change%20in%20technical%20approach%20of%20MPL%20Waybill%20from%20queue%20based%20data%20transfer%20to%20Direct%20API%20Call.pptx?d=w020871eeaa69420e954f75b06d058271&csf=1&web=1&e=JlTDxL |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) | L-040-010 |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0303​ | 1 | LOGI0303​ | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-12 | o During detailed discussions on Middleware functionality, the team decided to switch from the initially approved AMQ to a direct API call. • This will upgrade the integration to the latest tech. o AR: Team to follow up on the impact of the technical approach change as AMQ was initially architecturally approved, and the information will now come from an API call. Send results of follow to Uzma. | [9 empty] | Other | Tower | 2024-09-12 | 09, 2024 | 09, 2024 | 08, 2024 | 2024-08-16 | 0 | < 15 Days | shkale@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0044 | Approved |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.13 OTC IP – Returns (Logistics Management) | Yes | 05. OTC IP 09A. Master Data 10. Analytics 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | sumeetrsharma@deloitte.com | [11 empty] | SAP Stock Room Management (SRM) for Returns Warehouse Management | Inclusion of SAP Stock Room Management (SRM) capability in IAO scope. | The S4 IM scope does not suffice to support the business requirements for 6 Returns warehouses operated by 3PLs. s. The top 3 warehouses use Dynamic bins ( 750 in Moduslink, 304 in Malaysia and 503 in Amsterdam). Given these are 3PL managed warehouses using Intel WMS ( no PIP integration) They would require WMS capabilities for Receiving , Receipt Discrepancy Management, Inspection, Usage decision and disposition management |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0044%20OTC-IP%20Returns%20Logistics%20SRM.pptx?d=w4906c0bf4769410d85cbb74d08ac388d&csf=1&web=1&e=a6GdCr |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-05 | a. Logistics team to open KDD and re-evaluate options: IM model, SRM, and EWM – Ruben, Randy i. Including technical and operational/process impacts b. This CR will be placed on hold until the above options analysis and decision is taken. |  |  | 2024-09-13 | OSC/CL approved EWM-Decentralized instead of Stock Room, agreeing to a revisited sprint schedule to add the new scope into the Returns L3. | [5 empty] | Design | CL/OSC | 2024-09-13 | 09, 2024 | 09, 2024 | 08, 2024 | 2024-08-21 | 0 | < 15 Days | sshettyk@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0045 | Approved |  | ERP | R2 (Release 2) | Very High | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data 11. Technology | Tadepalli Sarvani | [11 empty] | This CR is specifically to split the DATI0391 into 2 interface objects. DATI0391 handles Search before Create in Reltio and also send the Customer Master changes from Reltio to MDG, the changes received in MDG are displayed in Data Monitor Report | The change was already captured as DATI0391, but during technical design it was identified that technically separate interfaces are required and therefore resulting in a split Search Before Create Customer Data Monitor Report – to display discrepancies between MDG and Reltio details | Initially the requirement was captured in single object DATI091 but since Reltio and Mulesoft has to create multiple API calls, the interface object – DATI0391 has to be split into 2 objects |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/53_MDG_CR%20Customer%20Master%20Reltio%20Interfaces.pptx?d=w165bfafdaf1e471185f637d22573c7bc&csf=1&web=1&e=luhZ3a |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATI0391 | 1 | DATI0391 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-05 | [10 empty] | Other | Tower | 2024-09-05 | 09, 2024 | 09, 2024 | 08, 2024 | 2024-08-22 | 0 | < 15 Days | shrutisingh7@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0046 | Cancelled | Reviewed offline | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Naman Parti | [11 empty] | Change of integration mechanism from IDOC based response to custom API response for RICEFW Object: OTCI0257/OTCI0258 | Change of integration mechanism by Deloitte tech team from IDOC based response to custom API response for RICEFW Object: OTCI0257/OTCI0258 | The integration mechanism has been revised to align with the latest proposal from the tech team and Intel IT. By switching the response mechanism for OTCI0257 and OTCI0258 to a custom API instead of IDOC, we are adopting a more modern and potentially more efficient method of data exchange. This is a 0$ CR because there was no change requested by business (Intel) rather the integration mechanism was changed by Deloitte tech team from IDOC based response to custom API response’ Functional team needs 8 hours to incorporate the changes. |  | Yes |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | O-020-100 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  |  | Reviewed offline and will not need to go through CCB; team to work with Lauren / PMO team | [9 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2024 | 2024-08-22 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0047 | Rejected | Rejected; cannot move out the dates; ask the teams to cancel the CR in reply email | ERP | R3 (Release 3) | Very High | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | sapbansal@deloitte.com | [11 empty] | Extention of L3 plan dates | Need to get L3 plan covered under sprint 6 dates extended | Considering the scope, process complexity and data privacy for HRMM Data -> the sprint 6 specific L3 plan dates needs to be extended to sprint 7 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/L3%20date%20extension_HRMM_Deck_template.pptx?d=wfb9154a4a63d4a6c86f527beaefebf54&csf=1&web=1&e=Z2W6KG |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-08-22 | [10 empty] | Design | Not Assigned |  | Not Approved | 08, 2024 | 08, 2024 | 2024-08-22 | 0 | < 15 Days | sapbansal@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0048 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP 11. Technology 12. Infrastructure | Aditya Shinde | [11 empty] | Update of build plan and design plan dates for PTP TM | Need to get the dates updated for PTP design and build tasks | IAO ASN vs non-ASN design was re-opened as part of RAID/KDD #1690 & 1611. Due to the upstream impact , TM downstream design & build has to be re-opened and revise the dates |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0048%20_PTP%20TM_CR%20Deck_Revised%20plan%20for%20design%20and%20Build%20PTP%20TM%20logistics.pptx?d=w1c38bfa58f8d4402a9f8d37f524f99c2&csf=1&web=1&e=ZAe9aJ |  | 1. Process Scope / Design Change | LI-030-030 LI-030-170 LI-030-160 LI-030-100 LI-030-190 LI-030-210 |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-05 |  |  |  | 2024-09-06 | Approved for design and build activities to be updated | [5 empty] | Design | CL/OSC | 2024-09-06 | 09, 2024 | 09, 2024 | 08, 2024 | 2024-08-22 | 0 | < 15 Days | tanysinha@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0049 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.8 PTP - QM |  | 06. PTP | Cari H Shim | [11 empty] | SAP QM Proposal | - Retain SAP QM for AT Materials & re-use existing MQCS integrations from ECC  S4​ - Extend SAP QM solution design to include Fab & AT equipment spares. Include onsite (SAP EWM + QIE) and 3PL integrated warehouses (SAP IM)​ - DLT SOW change order to add QI-130 L3’s​ | - Phase 0 architectural discussion between DLT and GSC Q&R dispositioned SAP QM as out of scope, QI-130 L3’s scrubbed from DLT SOW​ - WIINGS replacement architecture mapping wasn’t complete at this time​ - GSC Q&R determined SAP QM couldn’t replace Intel Q&R quality tools. Wasn’t aware that the decision would limit Intel’s ability to coordinate quality inspection steps within Intel’s warehouses​ ​ - Design sprints uncovered capability gaps in To-Be architecture​ - SAP EWM lacks the capability to replace existing WIINGS quality inspection workflow without both SAP QM *and* SAP QIE​ - SAP QM is used in ECC by AT Materials to manage quality inspection workflow​ |  | No | [8 empty] | 38 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2024 | 2024-08-29 | 0 | < 15 Days | ralvarezcarroz@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0050 | Approved | Needs to be compiled within the current eHANA change order (CR0037) | ERP | R2 (Release 2) | High | 13. Security | 13.2 Security - Cyber/ App Security |  | 03. FPR 10. Analytics | vkanderi@deloitte.com | [11 empty] | IAO - eHana ( Sidecar Hana) reports - Security | Change Request for the new scope - Security roles and data restrictions to be defined on new eHana reports for R2. | New scope added on eHana reports which needed Security role design |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6002CD48-5CE7-4866-ADC4-E989F4DD07EC%7D&file=Change%20ID_Tower_CR%20Deck_Security%20Non%20ERP_08302024.pptx&action=edit&mobileredirect=true |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-05 | [10 empty] | Other | Tower | 2024-09-05 | 09, 2024 | 09, 2024 | 08, 2024 | 2024-08-29 | 0 | < 15 Days | vkanderi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0051 | Approved | 170 hours of configuration | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 06. PTP 15. Cutover 16. Testing | Prabesh Acharya | [11 empty] | Company code move to difference S4 instance 776/241/390/606/724/604/622/645/405/879/429/735/736/756/334 ​ | Change request for - Company code 776/390 to be moved from IF to IP, asset ledger is required to be changed accordingly.​ Company code 606 – to be added to IP box and AA S4 is required to be set up.​ Company code 241 to be added to CFIN only.​ Company code 724 – to be deleted from IF and keep CFIN only.​ Company code 604/622/645/405/879/429/735/736/756/334 – to be deleted from IP and keep them available in CFIN only. To enable non-leading ledger for 429​ | Legal Entity-776​​ LE776, Intel China Limited, was categorized as a “mixed entity”. It holds subsidiaries & employees that are IF and IP in nature. The entity was planned to be segregated to an IF company and an IP company via a demerger with LE776 being an IF Entity. The entity had been set up in S4 as IF. ​​ Now demerger is not going to happen. Given 776 is pre-dominantly IP LE, it's more appropriate to move it to IP instance.​​ Legal Entity-390​ Nature of entity is predominant IP Entity but holds mixed IF and IP subsidiaries. ​ The original POR proposed by KPMG was to demerge LE390; with the existing entity being an IF Entity holding the Israel Fab. ​ Subsequently, to minimized impact to LE390 Employees, the plan was revised so that LE390 will retain its employees and hold IP subsidiaries instead of the Fab. ​ Legal Entity – 606​ Legal entity 606 (Mobileye) is a non-integrated entities maintained in CFIN only. However, asset ledger will be required to manage intangible assets under 606. Asset ledger is not available in CFIN, thus, it needs to be set up in IP to leverage asset ledger.​ Legal Entity –241​​ Legal Entity 241 was excluded from CFIN/S4 build due to expected liquidation by 2024. The liquidation team now forecasts that 241 will not be closed by 2024. Therefore, we need to create Entity 241 in CFIN to ensure financial balance completeness.​ Legal Entity –724​ Currently designated as IF entity, it was the China NAND Fab until the sale of the NAND business to SK Hynix.​ After the 1st closing in 2021, the entity has a handful of Employees and activities and is designated as IF/CFIN​ Entity expected to be fully dormant after the 2nd closure in Q3’25 and will be liquidated. Thus, keep it in CFIN is sufficient.​ Legal Entity –604/622/645/405/879/429/735/736/756/334​ Currently designated as IP entities, they are on liquidation roadmap and only need to be in CFIN for liquidation capability. With R3 being pushed out, LE COE team now has more confidence to close these legal entities before R3.​ For company code 429, non-leading ledger needs to be enabled as it is in scope of UK consolidation. Though it is expected to be liquidated before R3, with GP replacing BCS as system of record in R2, we will still need 429 in non-leading ledger to ensure accurate UK consolidation |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0051_Company%20code%20CR.pptx?d=w9658f2263ff046d0a7aa09fc33685e8b&csf=1&web=1&e=DToHDR |  | 3. Configuration Change | DC-020-010 |  |  | 0 | 0 | [7 empty] | 170 | [5 empty] | 0 | 170 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-12-09 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-31 |  |  |  | 2024-11-01 | Approved to proceed with R1/R2 work | [5 empty] | Other | CL/OSC | 2024-11-01 | 11, 2024 | 11, 2024 | 08, 2024 | 2024-08-29 | 0 | < 15 Days | simransharma5@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0052 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Sindhuja Gangireddy | [11 empty] | RICEFW type change from Enhancement to Interface for the OTCE410- Replicate POLP-( Planned order- Sales Order Lot Pegging Table) from ECC to S4 | Change request to change object type from Enhancement to Interface for object OTCE0410 | Initially object OTCE0410 is identified as Enhancement and FS is approved. Further , since regular data transfer is required between ECC and S4 systems requesting to change object type as interface instead of Enhancement. Following are effort estimate for Tech and Middleware Tech = 30 hours ; , Functional = 6 hrs Total = 36 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0D4B044F-E7FF-4A0F-A657-32FFC400A6CE%7D&file=INT-CR0052_OTC%20IF_CR%20Deck_WW37%2724.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object | OM-030-010 |  |  |  | 0 |  |  | 6 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Less than 40 hours of effort. Therefore, the team was instructed to add these CR's into the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2024 | 2024-08-30 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0059 | Approved |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | Prabesh Acharya | [11 empty] | Split Load ready files in BODS & Improve extraction Criteria | Split the load ready files produced by BODS for GL account (SKB1), Cost Center, Cost Center Hierarchy | Currently large load ready files are produced by BODS, however MDG cannot load the large files therefore needs to split the files for GL account (SKB1), Cost Center, Cost Center Hierarchy. Improve extraction criteria and defect fixes. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0059_Split%20Load%20ready%20files%20in%20BODS%20%26%20Improve%20extraction%20Criteria.pptx?d=w57b5f86efb8c457f814d7f36b1f59aa1&csf=1&web=1&e=abTyfk |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 36 | 0 | [10 empty] | 36 |  |  | 0 | 36 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRC0011, FPRC0009 | 2 | FPRC0011, FPRC0009 | 2 |  | 0 |  | 0 | N/A |  | 2024-10-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-17 | Approved to proceed with work | [9 empty] | Build | Tower | 2024-10-17 | 10, 2024 | 10, 2024 | 09, 2024 | 2024-09-06 | 0 | < 15 Days | navnegi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0060 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 10. Analytics | sshettyk@deloitte.com | [11 empty] | Inclusion of logic for Batch Split scenario in R2 CI/PL Forms FSDs | Commercial invoice and packing list FSDs to be updated include the logic for various scenarios of Batch Split in Outbound Delivery. | In the event of a batch split in the outbound delivery, the format to display the line item details in the Commercial Invoice and Packing list forms would be dependent on the batch characteristic values i.e. COO and Lot no. Hence this logic needs to be updated in the FSDs. Impacted Objects- LOGF0343_IF, LOGF0344_IF, LOGF0345_IF, LOGF0348_IF, LOGF0353_IF, LOGF0346_IF, LOGF0357_IF, LOGF0347_IF, LOGF0342_IF and LOGF0354_IF |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/3%20Final%20Deliverables/Logistics/LE%20Functional%20Specifications/INT-CR0060_OTC_IF_Logistics_management_Batch_split_CI_PL.pptx?d=wf48a029005084f2c991f1d6b6ccc1903&csf=1&web=1&e=s92Azt |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0343_IF, LOGF0344_IF, LOGF0345_IF, LOGF0348_IF, LOGF0353_IF, LOGF0346_IF, LOGF0357_IF, LOGF0347_IF, LOGF0342_IF, LOGF0354_IF | 10 | LOGF0343_IF, LOGF0344_IF, LOGF0345_IF, LOGF0348_IF, LOGF0353_IF, LOGF0346_IF, LOGF0357_IF, LOGF0347_IF, LOGF0342_IF, LOGF0354_IF | 10 |  | 0 |  | 0 | N/A |  | 2024-11-01 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-26 | Work has been approved to go forward. No OSC/CL approval is needed. | [9 empty] | Build | Tower | 2024-09-26 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-06 | 0 | < 15 Days | sshettyk@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0061 | Approved |  | ERP | R2 (Release 2) R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 10. Analytics | junior.milan@intel.com | [11 empty] | Commercial Invoice ¦ KTBL Changes | + Additional data and text requirements for shipments originating in the countries below to ensure the documents Intel hands over to local customs are compliant. Essentially, this is a KTBL request. + To give Intel the ability to stay compliant and able to clearly address discrepancies, the Trade Group has requested the following changes to the Bailment Commercial Invoice | Changes being requested by ITG team are required to keep Intel legal (KTBL) when shipments are moving across countries (Internal and External shipments). |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0061_OTC%20IF_CR%20Deck_WW37%2724.pptx?d=w592b2718510d49a4a0c795e41beb7a82&csf=1&web=1&e=eucxeD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0343_IF, LOGF0344_IF, LOGF0345_IF, LOGF0353_IF, LOGF0346_IF, LOGF0357_IF, LOGF0347_IF, LOGF0342_IF, LOGF0354_IF | 9 | LOGF0343_IF, LOGF0344_IF, LOGF0345_IF, LOGF0353_IF, LOGF0346_IF, LOGF0357_IF, LOGF0347_IF, LOGF0342_IF, LOGF0354_IF | 9 |  | 0 |  | 0 | N/A |  | 2025-11-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-12 | o During detailed discussions, the team aligned that additional fields within the Bailment Commercial Invoice are needed to meet international trade compliance. • Additional data text logic and layout changes will need to be added within documentation. o The team will need to update 6 forms and their corresponding FS’s. o AR: Team to work with Tech team to do additional effort analysis. - @Alvarez Carroz, Ruben David o AR: Include CR in OSC/CL agenda for ww38 (9/17). – @Frost, Shawn |  |  | 2024-09-27 | Approved - will not meet ITC1 | [5 empty] | Build | CL/OSC | 2024-09-27 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-12 | 0 | < 15 Days | junior.milan@intel.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0062 | Approved | Should be tagged to FPRI0644. | ERP | R1 (Release 1) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology 17. B-App | shane.bethune@intel.com | [11 empty] | WRICEF object for Exchange Rates M,R,S,I - S4 converted data from MuleSoft to Treasury Suite | Requirement to feed Exchange Rats that are converted for S4 systems need to be fed to Treasury Suite for validation. There is an existing WRICEF object to feed Bloomberg unconverted data to Treasury suite. But the need to send converted data popped up during FUT of Bloomberg objects. Hence require a new WRICEF object (Interface) with Medium complexity to cover the new requirement. |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/S4%20(Direct%20Quote)%20.OUT%20Files%20for%20Treasury%20Suite%20CR%20.pptx?d=w28fe0e86b4144a1f8d09075ca2efb0b2&csf=1&web=1&e=NgayEe |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [8 empty] | 81 |  |  |  |  | 0 | 81 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-12 | o To enable data validation within the Treasury Suite, an additional interface is needed to connect the data flow from MDG to MuleSoft to NAS Drive to Treasury Suite. • The interface will be extra work, but it will be the same type of work as the other interfaces for Treasury Suite. • Tech team has aligned on the work and is planning to complete by November; team is aiming to include in R1 and R2 testing, but there is a fallback if the object is not done. o AR: Chris W and Debashish to confirm that the standard, built-in functionality within Treasury Suite to receive and validate data will be complete. - @Chris Woodburn, @Das, Debasish o AR: Update Architecture slide within deck to include another red arrow from MDG To MuleSoft and change arrow from MDG to ECA as blue. - @Acharya, Prabesh o AR: Update deck with build dates and effort estimation. - @Acharya, Prabesh |  |  | 2024-09-13 | Approved for further work | [5 empty] | Other | CL/OSC | 2024-09-13 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-12 | 0 | < 15 Days | chgorantla@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0063 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Kranthi Ranadheer Ranadheer | [11 empty] | Text ID's in Inbound Order create and change interfaces for IF | Requirement is to add new text ids in inbound order create and change objects OTCI0042 and OTCI0047. | These text id details sent by customer are required to be updated into sales order. These are important as they would be further used in processing of sales order(Holds, blocks and acknowledgements etc.) These are identified in discussion with the B2B team. Following are effort estimates for Tech and Functional Tech = 16 hours ; Functional = 4 hours Total = 20 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCI0042%20and%20OTCI0047/INT-CR0063_OTC%20IF_CR%20Deck_WW37%2724.pptx?d=w16c03db9f23f4e9fa2de7e0ead2b846f&csf=1&web=1&e=D6mkFJ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No |  |  | Reviewed offline; does not require CCB presentation as it is less than 40 hours (20 hours) | [8 empty] | Less than 40 hours of effort. Therefore, the team was instructed to add these CR's into the Build CR Log. | Build | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 09, 2024 | 2024-09-12 | 0 | < 15 Days | kranadheer@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0064 | Rejected |  | ERP | R2 (Release 2) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | shkale@deloitte.com | [11 empty] | Change the scope of Functional Specification | LOGI0336 was initially identified as a Functional Spec required by S/4 IM instance to provide the inventory status. Three additional RICEFW were identified which included LOGI0519, LOGI0520 and LOGE0521. As part of technical discussion and change in approach, initially identified asynchronous call was changed to synchronous call. Change in the approach led to change in FS scope and the functionality initially intended for LOGI0336 is not met with LOGI0519. | During the R2 ECD Architecture discussion of Middleware, it was identified that an additional RICEFW is required for Middleware Team. As the functionality of LOGI0336 is met with LOGI0519, the additional RICEFW LOGI0336 can be repurposed for Middleware usage. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR0064%20Change%20the%20scope%20of%20Functional%20Specification.pptx?d=wd6250fea9f3c45afb2387ab81759c184&csf=1&web=1&e=ZUZcNv |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-10-31 | [10 empty] | Build | Not Assigned |  | Not Approved | 10, 2024 | 09, 2024 | 2024-09-12 | 0 | < 15 Days | shkale@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0065 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [11 empty] | Order Create and change error validations for OTCE0441 | Requirement to add custom fields Status Code, Error Code, Reason Code, Error Message. Validations were identified as part of outbound interface discussions. The list was exhaustive. We concluded our discussion and updated the FS OTCE0441 | Requirement to add custom fields Status Code, Error Code, Reason Code, Error Message. Validations were identified as part of outbound interface discussions. These are necessary as they store the information of what response goes to a customer. The list was exhaustive. We concluded our discussion and updated the FS. Tech = 36 hours ; Functional = 3 hours Effort Estimate - 39 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCE0441/INT-CR0065_OTC%20IF_CR%20Deck_WW37%2724.pptx?d=w7bc56edf710d4ae09dad7dbc2a62ac47&csf=1&web=1&e=LgWvyz |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 |  |  | 3 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Less than 40 hours of effort. Therefore, the team was instructed to add these CR's into the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-13 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0066 | Approved | Need to add in the Manual Conversion ID | ERP | R2 (Release 2) | Very High | 09A. Master Data | 9A.6 Master Data - Material |  | 07. FTS IF 09B. Data Migration | mshabaz@deloitte.com | [11 empty] | Material Master-VERP Materials Manual Conversion | Packaging Materials (VERP) are required by Logistics Team for R2. | Addition of this Manual Conversion Object is changing the scope for R2 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0066_MDG_CR_Material%20Master%20Data.pptx?d=wb530882fd05c42b889d063c12eaf2057&csf=1&web=1&e=TCv1NI |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [10 empty] | 100 |  |  | 0 | 100 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-19 | Reviewed offline |  |  | 2024-09-20 | Approved at OSC/CL 9/18 | [5 empty] | Other | CL/OSC | 2024-09-20 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-17 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0067 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Naman Parti | [11 empty] | Order Create and change error validations for OTCE0443 | Requirement to add custom fields Status Code, Error Code, Reason Code, Error Message. Validations were identified as part of outbound interface discussions. The list was exhaustive. We concluded our discussion and updated the FS OTCE0443. | Requirement to add custom fields Status Code, Error Code, Reason Code, Error Message. Validations were identified as part of outbound interface discussions. These are necessary as they store the information of what response goes to a customer. The list was exhaustive. We concluded our discussion and updated the FS. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCE0441/INT-CR0067_OTC%20IP_CR%20Deck_WW37%2724.pptx?d=wba551d98653f4d46a22d67c6d8c70a30&csf=1&web=1&e=155yod |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 96 | 0 |  |  | 54 | [5 empty] | 96 |  |  |  |  | 0 | 96 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0443​, OTCI0038, OTCI0060​, OTCI0257​, OTCI0258​, OTCI0438​, OTCI0439 | 7 | OTCE0443​, OTCI0038, OTCI0060​, OTCI0257​, OTCI0258​, OTCI0438​, OTCI0439 | 7 |  | 0 |  | 0 | N/A |  | 2025-11-28 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | [10 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 09, 2024 | 2024-09-17 | 0 | < 15 Days | shravann9@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0068 | Approved |  | ERP | R3 (Release 3) | High | 01. PMO | 11.1 Technology - ALL |  | 03. FPR 11. Technology | kenayak@deloitte.com | [11 empty] | UIPath - Payment Remittance Advise | The number of implementation objects have increased from 1 to 9 (total of 8.5 medium equivalants) | Payment Remittance Advise is an existing UIPath solution built 6 years ago with the existing technology sets. The UIPath development needs modernization and a total revamp for reading data from 37 PDF formats, 76 Email formats and a couple of WWW sites for collection of information |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0068%20-%20UiPath%20Payment%20Remittance%20Advise.pptx?d=w6162c50307e242259c80c2f556ae3b1e&csf=1&web=1&e=gffHK5 |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 10 | FPRE0624, FPRE0623, FPRE0622, FPRE0621, FPRE0620, FPRE0619, FPRE0618, FPRE0617, FPRE0616, FPRE0282 |  | FPRE0624, FPRE0623, FPRE0622, FPRE0621, FPRE0620, FPRE0619, FPRE0618, FPRE0617, FPRE0616, FPRE0282 | 10 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-19 | Reviewed offline |  |  | 2024-09-20 | Approved at OSC/CL 9/18 | [5 empty] | Design | CL/OSC | 2024-09-20 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-18 | 0 | < 15 Days | kenayak@deloitte.com |  | No |  | Complete |  | Complete | No
R2 (Aug 2025) | R2 | INT-CR0069 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics | Sumit Sharma | [11 empty] | Debit Credit Memo Report with approval status - logic changes | Identified change in the approved Functional specifications for OTC report “Credit/Debit Memo Report with Approval Status” for OTCFR003. Mapping changed for four fields to S4 Tables - Approval Status, Approved/Rejected By, Approved/Rejected Date, Approved/Rejected Comments Total Technical Efforts - 72 Hrs | Sourcing for the below columns has been changed in approved version of FSD. To incorporate this, we need to ingest additional source tables from S4 and rebuild curated foundation and composition layer. Mapping changed for four fields to S4 Tables - Approval Status, Approved/Rejected By, Approved/Rejected Date, Approved/Rejected Comments based on the build and config activity done for Workflow setup. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B91BAF958-7518-4E92-86A4-E45B3CB56280%7D&file=INT-CR0069_OTC%20IF%20-%20Debit%20Credit%20Memo%20Report%20with%20approval%20status.pptx&action=edit&mobileredirect=true&CID=E2D5C74E-A7FE-443F-92AA-246E6D06D664&wdLOR=cAE86FB3A-9A7E-4374-B3B9-740F2AF0B43B |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 72 | 0 | [9 empty] | 72 |  |  |  | 0 | 72 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCFR003 | 1 |  | 0 | OTCFR003 | 1 |  | 0 | N/A |  | 2024-11-22 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-10 | Approved to continue with work and will not require OSC/CL approval | [9 empty] | Build | Tower | 2024-10-10 | 10, 2024 | 10, 2024 | 09, 2024 | 2024-09-19 | 0 | < 15 Days | eigupta@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0071 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF | vprashantpotphode@deloitte.com | [11 empty] | Credit check steps enhancements | Hi Team, We have to develop custom BAID's via standard BADI: 1. 000- No Credit check - The purpose of this BAdI enhancement is to DO NO Credit Check. There is no code. This check step will always pass and will be used as a place holder in a Credit Check Rule so the Horizon Values will populate. 2. 003-Review all Orders - The purpose of this BAdI enhancement is to always fail. It is used to force all orders to be reviewed and be released manually. | Following are the Effort estimates: Tech : 14 hrs. Functional : 10 hours Total Hours :24 hours |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0071_OTC%20IF_Credit%20check%20steps%20enhancements.pptx?d=w8dc1e8de98c345c9a368198128d763a6&csf=1&web=1&e=sxTUL7 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-19 | 0 | < 15 Days | pbathini@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0072 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 09A. Master Data 09B. Data Migration | smadlakha@deloitte.com | [11 empty] | R2-DATC0074-Material-Sales View - Tax classification logic | R2-DATC0074-Material-Sales View - Tax classification logic-Sales Org to Plant (TVKW & T001W) mapping to get the different Departure countries for each Sales Org | New Logic-Sales Org to Plant (TVKW & T001W) mapping to get the different Departure countries for each Sales Org. Effort estimate: Tech :27 hrs. Testing:9 hrs. Documentation (TDD & TUT):9 hrs. FUT Analysis & Fixes:9 hrs Total Hours:54 hrs |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0072_OTC%20IF_Material-Sales%20View.pptx?d=wda882fb12e394489bb46584dd96183c5&csf=1&web=1&e=16YiP7 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 54 | 0 | [10 empty] | 54 |  |  | 0 | 54 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0074_IF | 1 | DATC0074_IF | 1 |  | 0 |  | 0 | N/A |  | 2024-10-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-26 | Work has been approved to go forward. No OSC/CL approval is needed. | [9 empty] | Build | Tower | 2024-09-26 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-20 | 0 | < 15 Days | rameu@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0073 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  |  | Preeti Muni Burh | [11 empty] | Update Mapping sheet for WOM Order create and Change | OTCI0037 Mapping sheet update for below existing fields in STM sheet -etReturnTable.Type, etReturnTable.id, etReturnTable.number, etReturnTable.message, addreturn.id &addreturn.message - updated the folders(API object) for these fields from "SAP_message" to "_message" -All the “Z” fields in S4 should be capitalized. -headerline.xid is marked as NA (ZXID) -Rename API field name from Distributionchannel to "DistributionChannel" OTCI0061 Input.WOM was present for create order so now involved the same field for change order. As per input from tech team API field name is Customerpurchaseordertype to PurchaseOrderType. | OTCI0037 & OTCI0061 While building the interface Middleware and S/4 tech team raised the issue and the respective mapping changes were needed to fix the issue in S/4. Renaming of API object(Folder) and Fields needs as per custom API Technical: 16 Hours Functional:4 Hours Total:20 Hours |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3CEFA7F9-A55E-439D-856F-EE5EEBC8E1FA%7D&file=INT-CR0073_OTC%20IP_Update%20Mapping%20sheet%20for%20WOM%20Order%20create%20and%20Change.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object | O-020-190 |  |  |  | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-23 | 0 | < 15 Days | prburh@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0074 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) R5 (Release 5) | Very High | 02. E2E Process Integration | 2.4 E2E Process Integration - Cross Functional Topics |  | 02. E2E Process Integration 03. FPR 04. OTC IF 06. PTP 07. FTS IF 09A. Master Data 09B. Data Migration 17. B-App | talbot.smith@intel.com | [11 empty] | Match Trade Flows to Physical Flows | Change how we support tax requirements and associated trade flows. Current design is that each time a manufacturing legal entity completes work and ships the value added is transferred to the order taking entity (US or Singapore). This design creates significant complexity in both S/4 and Blue Yonder as well as boundary apps. The proposal is to modify the trade flows so that value transfers with the physical flow - i.e., to the next manufacturing site - and only transfers to the order taking entity prior to shipment to the customer. This removes significant complexity in S/4, in BY, and in boundary apps | Reduced complexity in S/4, BY, and boundary apps from simplified trade flow |  | Yes |  |  | https://intel.sharepoint.com/sites/intelspinnakerdeloitteiao/Shared%20Documents/E2E%20Arch/01.%20E2E%20Architecture/06.%20%20E2E%20Key%20Design%20Decisions/CR0074%20Match%20Trade%20Flows%20to%20Physical%20Flows.pptx?web=1 |  | 1. Process Scope / Design Change |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-09-25 |  |  |  | 2024-09-27 | Approved | [5 empty] | Design | CL/OSC | 2024-09-27 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-24 | 0 | < 15 Days | talbot.smith@intel.com | Yes | No |  | No Objects |  | In Progress | No | Yes
R1 (May 2025) | R1 | INT-CR0075 | Approved |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Consolidated Income Statement | Change the logic to get the number for Consolidated Income statement. | The numbers of this report must be derived in three different ways: • Few lines will be a combination of Functional Area and FS items. • Few lines will be just by FS Item or FS Item node. • Few lines will be just Functional Area or Functional Area node. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4199504C-1344-4EC9-92E3-46D7BAC610FA%7D&file=INT-CR0075_R1_EHana%20Income%20statement.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA4MTcwMDQyMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [9 empty] | 40 |  |  |  | 0 | 40 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR028 | 1 |  | 0 | FPRXR028 | 1 |  | 0 | N/A |  | 2024-11-01 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-26 | Work has been approved to go forward. No OSC/CL approval is needed. | [9 empty] | Build | Tower | 2024-09-26 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-25 | 0 | < 15 Days | kdey@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0076 | Cancelled |  | ERP | R2 (Release 2) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Statement of Equity QTD | QTD view of Statement of Shareholder's Equity | QTD view of Statement of Shareholder's Equity |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0076_R2%20Statement%20of%20Equity%20QTD%20Report.pptx?d=w6162ef8dd21e44bcb136dac4cd2d3ee0&csf=1&web=1&e=aMewhn | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Prabesh that the changes have been completed in R1 already. Therefore, cancelling CR. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-25 | 0 | < 15 Days | albrojas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0077 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Sindhuja Gangireddy | [11 empty] | OTCE0171 - To add logic for credit Hold status in user status profile in sales orders | As FSCM is not available in IF R2 , manual update of credit hold is applied in user status profile in sales orders both at header level and item level. The same logic must be updated in VOFM routine which will control the trigger of order confirmations when the order is credit blocked | As FSCM is not available in IF R2 , manual update of credit hold is applied in user status profile in sales orders both at header level and item level. The same logic must be updated in VOFM routine which will control the trigger of order confirmations when the order is credit blocked Effort Estimate : Tech = 16hours Functional : 2 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B75109486-397D-4CD0-B8DC-6027658DDF4B%7D&file=INT-CR0077_OTC%20IF_CR%20Deck_WW37%2724.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object | OM-030 |  |  |  | 0 |  |  | 2 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Less than 40 hours of effort. The team was instructed to add this CR to the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-25 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0078 | Cancelled |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Sindhuja Gangireddy | [11 empty] | RICEFW type change from Enhancement to Interface for the OTCE485- Send Sales order data from S4 to BY | Since the data must be sent from S4 to ECA system using BODS job the RICEFW type must be changed to Interface rather than enhancement. | The was supposed to be achieved via std connector based on the initial discussion with BY but upon deep diving the BY team confirmed that they would need an interface for this object. Since the data must be sent from S4 to ECA system using BODS job the RICEFW type must be changed to Interface rather than enhancement Effort estimate : Tech : 30hours Functional = 3 hrs |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBAA07A3A-31A6-45F4-9F65-C7DB90A1A3D4%7D&file=INT-CR0078_OTC%20IF_CR%20Deck_WW37%2724.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object | OM-030 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Less than 40 hours of effort. The team was instructed to add this CR to the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-25 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0079 | Cancelled |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.3 OTC IF - Billing and Rebates |  | 04. OTC IF | sariya.garza@intel.com | [11 empty] | Add Invoice Geo Code on Archive Form for EDDAR archiving processes | Invoice geo code needs to be added to IF S4 invoice archive form. The geo code must be displayed on PDF form in order for EDDAR to read it and use it for EDDAR archiving processes by geo and search capabilities used by business teams (Credit & Collections, Legal, CBA, etc..). This is current EDDAR invoice archiving process and must remain in place until new archive tool is available. | cancelled- moved to FS Build CR tracker. Archive invoice form was originally designed assuming new archiving system. As of 9/22/24 we have confirmation from Josh Wise that EDDAR will be used for R3 invoice archive process until new archive solution is available. This means we need to ensure same archive capabilities used in EDDAR today are still functioning as expected. Total – 10 Hrs​ Technical Efforts – 2 Hrs​, Functional Efforts – 8 Hrs (To redo FUT) |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Team added this CR to the FS Build tracker. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-25 | 0 | < 15 Days | sariya.garza@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0080 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.1 OTC IF - ALL |  | 04. OTC IF 10. Analytics | sbarmanroy@deloitte.com | [11 empty] | Initial ECA Code/TUT Planned End Date', 'ECA Code/TUT Plan Finish Date', 'ECA Code/TUT Rev/Actual End Date' Date change for 3 OTC objects | The following objects build completion is showing as 100% because the objects were picked for development in previous sprints, but blockers/ dependencies were found. Not all the sprint activities were incorporated/submitted initially. OTCFR001, OTCFR003, OTCFR026 Initial ECA code/ TUT end date has been updated to 10/25. ECA code TUT Plan Finish Date also needs to be updated to 10/25. The sprint plan has been sent to PMO. There is no impact on FUT dates. | These dates were provided as part of incomplete plan only for this sprint. ECA code TUT Plan Finish Date needs to be updated to 10/25 for these three objects: OTCFR001, OTCFR003, OTCFR026 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA47F9BE5-90C5-4034-A2F9-8FC61D7BA335%7D&file=INTCR0080_Analytics_CR%20Deck.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCFR001, OTCFR003, OTCFR026 | 3 |  | 0 | OTCFR001, OTCFR003, OTCFR026 | 3 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-26 | Reviewed offline; no development effort or downstream effect. Confirmed with OTC team that FUT date is not changing | [9 empty] | Other | Tower | 2024-09-26 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-26 | 0 | < 15 Days | lorzechowski@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0081 | Cancelled |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 8.6 FTS IP - MRP & Planning Integration |  | 02. E2E Process Integration 04. OTC IF 06. PTP 07. FTS IF | Anil Sankarapillai | [11 empty] | Intel Foundry inclusion of Intel Federal DPAS | Intel Federal/IP must send DPAS rating flags with orders to OTC-IF. To facilitate this, OTC-IF will need to update the EDI interface with IP to include the DPAS field, add the field to the Order screens, and incorporate it into the BY interface. This ensures correct order prioritization. Additionally, the R3 Supply Planning team will be impacted, as they must ensure DPAS ratings are sent to our suppliers. The potential impact on GLO is being assessed by Intel Federal. | Federal Government requires correct prioritization of all DPAS (Defense Priorities and Allocations System) rated orders. Companies receiving DPAS-rated orders are required to prioritize these orders and ensure timely delivery. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | FTS IP has completed design for DPAS, and RICEFW's are in place. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-26 | 0 | < 15 Days | jason.carmichael@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0083 | Approved |  | ERP | R2 (Release 2) | High | 07. FTS IF | 10.6 Analytics – FTS IF |  | 07. FTS IF 10. Analytics | sbarmanroy@deloitte.com | [11 empty] | Initial ECA Code/TUT Planned End Date', 'ECA Code/TUT Plan Finish Date', 'ECA Code/TUT Rev/Actual End Date' date change for 5 FTS objects | ‘Initial ECA Code/TUT Planned End Date’, ‘ECA Code/TUT Plan Finish Date’ fields need to be updated to the following dates for each object: FTSFV011- 11/18, FTSFV012- 11/18, FTSFV013- 11/18, LOGV006_FTSIF- 11/25, LOGV007_FTSIF- 11/25 | These objects initially had correct dates, however they were updated in error to the last day of the last sprint and need to be reverted back to the initial planned date. There is no impact on ITC or Towers as they have aligned their dates to the original (correct) dates. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B53931547-E792-43B8-A659-4180CCF2C892%7D&file=INT-CR0083_Analytics_CR%20Deck.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSFV011, FTSFV012, FTSFV013, LOGV006_FTSIF, LOGV007_FTSIF | 5 |  | 0 | FTSFV011, FTSFV012, FTSFV013, LOGV006_FTSIF, LOGV007_FTSIF | 5 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-09-26 | Reviewed offline; no development effort or downstream effect. Confirmed with FTS team that FUT date is not changing | [9 empty] | Other | Tower | 2024-09-26 | 09, 2024 | 09, 2024 | 09, 2024 | 2024-09-27 | 0 | < 15 Days | lorzechowski@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0084 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 04. OTC IF 05. OTC IP 09A. Master Data | rausingh@deloitte.com | [11 empty] | Changes in Text Ids for Downstream Replication (DATI0393) as per CMDB | As per the current requirement received for R2 for the approved object DATI0393, below Text ids are not to be replicated to downstream system. So, raising the change request to reconcile the new changes for CMDB that below text ids need to be replicated to the downstream systems: 1. Delivery Plants 2. Pre Alert and Broker Inform 3. Price Masking (Invoice Swap) 4. Enterprise Code USCI |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAFCB8999-3A46-4DF6-8EA2-9306E2147E64%7D&file=Changes%20in%20Sales%20Area%20Text%20IDs%20for%20Downstream%20Replication.pptx&wdOB=C59FCF07FD864999B45C9C1447099EB8&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the total technical work was discovered to be less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2024 | 2024-09-30 | 0 | < 15 Days | jatkhurana@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0085 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 10. Analytics | rsiddharth@deloitte.com | [11 empty] | OTC GTS Reporting - Two reports merged into single report OTCFR035 | The requirements from the following two reports are merged over to single report OTCFR035: Party Screening Result and RPL Screening Summary Dashboard. | Since the team has already started working on the above reports, we identified rework and additional efforts to merge the requirement as per the merged FSD. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Duplicate entry to CR0086 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-02 | 0 | < 15 Days | samstanley@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0086 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 10. Analytics | rsiddharth@deloitte.com | [11 empty] | OTC GTS Reporting - Two reports merged into single report OTCFR035 | The requirements from the following two reports are merged over to single report OTCFR035: Party Screening Result and RPL Screening Summary Dashboard. | Since the team has already started working on the above reports, the team identified rework and additional efforts to merge the requirement as per the merged FSD. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CE92806-D74F-4F4D-86C2-2C91DD4BB143%7D&file=INT-CR0086_OTC%20IF%20-%20Merging%202%20GTS%20ECA%20Reports%20into%20one.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Less than 40 hours | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort hours is 12 hours and will be moved to the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-02 | 0 | < 15 Days | samstanley@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0087 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.5 FTS IF - TM | Yes | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP | Jeet Bawra | [11 empty] | Transportation Management L3's Reopen | Inclusion of additional scope for SAP TM (Transportation Management) system for IAO scope | Intel has requested the addition of new processes like IMO, IMR, Assets and EMS because of which the closed L3 design and build tasks must be reopened. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR0087_FTS%20IF_Transportation%20Management%20L3%20Reopen.pptx?d=w273904e59ef743ed97f5ce79cf04fbe9&csf=1&web=1&e=VnCFcc |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-10 | Approved for estimations |  |  | 2024-10-16 | INT-CR0087 was approved as scheduled CR by OSC/CL solely for the carrier selection & VTRC retrofit topic with the caveat of finishing design by end of November 2024 and approval by December. Approval was only received for L3's which needed to be re-opened for retrofit and not for any new design with incremental cost and dollars. If that is needed, those portions need to be moved out from this CR to a new CR. | [5 empty] | Design | CL/OSC | 2024-10-16 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-02 | 0 | < 15 Days | ralvarezcarroz@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0088 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 17. B-App | shane.bethune@intel.com | [11 empty] | MuleSoft to stop sending Thursday run file for M rates to QT - NAS Folder and send only 7 files | Currently MuleSoft is sending 8 files for Quantum, i.e. Thursday run file(1file) and from Sunday to Saturday files (7 files). The requirement is Thursday rates are loaded on Friday applicable from Sunday to Saturday each day 1 file i.e. 7 files. Its also sending Thursday file without transformation of date change this additional file is not needed and is causing issues while transmission of interface to downstream systems. | Causing errors while transmitting the files to downstream systems. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0088-MuleSoft%20to%20stop%20sending%20Thursday%20run%20file%20for%20M.pptx?d=waecbbf39a92f40dbb2530e7953ebfb4d&csf=1&web=1&e=bUgfyf | [5 empty] | 27 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort hours is 12 hours and will be moved to the Build CR log. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-02 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0089 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | rahulx.ranjan@Intel.com | [11 empty] | Reopening the L3 : OR-140-090 for additional User Stories. | Reopening the L3 : OR-140-090 for additional L3's | There are additional requirements that have been received , and these user stories needs to be updated in the User Story Smartsheet Tracker. For FPR Team -10 all the L3's have been approved and closed in the Design Phase, so to accommodate user stories we need to reopen the L3: OR-140-090. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0089_FPR_Reopening%20of%20a%20L3%20OR-140-090.pptx?d=w525ba67f7c15479b912aa9ee0e626494&csf=1&web=1&e=jUWySX |  | 1. Process Scope / Design Change | OR-140-090 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This CR was cancelled as the L3 is marked as an Exception Topic during the R3 Replan and will be re-opened for rework. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-03 | 0 | < 15 Days | rahulranjan3@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0090 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Kranthi Ranadheer Ranadheer | [11 empty] | Requirement is to add CRED and BUID user status hold at item level based on payment terms. | To add logic to put sales order in CRED and BUID user status hold at item level during order creation if Payment terms are "Cash in advance" for relevant Sales order and Item category combinations. (Only CRED if material type is DIEN) | This requirement/design to add couple of order status to the order line item based on the payment term was finalized by C&C team , after the order creation FS was reviewed. Tech - 18 hours, Func - 4 hours |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCE0001/INT-CR0090_OTC%20IF_CR%20Deck_WW37%2724.pptx?d=wfd185b15f6aa4e62a440653050555bdf&csf=1&web=1&e=9FLYeD | [5 empty] | 18 | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort is less than 40 hours and approved by team to move to FS / Build CR Log. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-03 | 0 | < 15 Days | kranadheer@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0091 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Kranthi Ranadheer Ranadheer | [11 empty] | Requirement is to add CRED and BUID user status hold at item level based on payment terms. | To add logic to put sales order in CRED and BUID user status hold at item level during order creation if Payment terms are "Cash in advance" for relevant Sales order and Item category combinations(Only CRED if material type is DIEN) | This requirement/design to add couple of order status to the order line item based on the payment term was finalized by C&C team , after the order creation FS was reviewed. Tech - 22 hours, Func - 4 hours |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/FS%20Ready%20for%20Review/OTCE0406/INT-CR0091_OTC%20IP_CR%20Deck_WW37%2724.pptx?d=wf9c1f99405914c66a1ae49b216378516&csf=1&web=1&e=FgrhKH | [5 empty] | 22 | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort is less than 40 hours and approved by team to move to FS / Build CR Log. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-03 | 0 | < 15 Days | kranadheer@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0093 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | sashs@deloitte.com | [11 empty] | Requirement to change the File based Approach with Create Stream Method for IPAR/MyDeals to S4 Interface | Custom API will be created in S4 and File will be used as an attachment at middleware level. Payload will be received at S/4 end instead of file and payload will be processed to get the required data set. Custom API with POST will be used. CREATE STREAM method will be used to upload data & GET stream will be used to display content of attachment. | Requirement to change the approach from File Based approach to an ODATA based approach, as this will be a more efficient and future proof. This requirement came up after discussion with the technical architects from Intel and Deloitte. Tech - 36 hours Functional -4 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/FS%20Ready%20for%20Review/OTCI0081%20IPAR%20to%20SAP%20Interface/INT-CR0093_OTC%20IP_CR%20Deck_WW37%2724.pptx?d=wd4a1bc6801074839a7c093a368ffa345&csf=1&web=1&e=VOcEBO | [5 empty] | 36 | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort is less than 40 hours and approved by team to move to FS / Build CR Log. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-04 | 0 | < 15 Days | sashs@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0094 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [11 empty] | > Require a user status hold to be set at header if the value for the header text received in the B2B request for Order Create. This is be based on the order type ZOR. > Require a user status hold to be set at item if the value for the item text received in the B2B request for Order Create. This is be based on the order type ZOR. > Requirement to put the order on user status hold at the Header level for the specific customers (sold to). | > Require a user status hold to be set at header if the value for the header text received in the B2B request for Order Create. This is be based on the order type ZOR. > Require a user status hold to be set at item if the value for the item text received in the B2B request for Order Create. This is be based on the order type ZOR. > Requirement to put the order on user status hold at the Header level for the specific customers (sold to). | > Require a user status hold to be set at header if the value for the header text received in the B2B request for Order Create. This is be based on the order type ZOR. > Require a user status hold to be set at item if the value for the item text received in the B2B request for Order Create. This is be based on the order type ZOR. > Requirement to put the order on user status hold at the Header level for the specific customers (sold to). Following are effort estimates for Tech and Functional Tech - 40 hours, Functional - 8 hours Effort Estimate - 48 hours |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCE0001/INT-CR0094_OTC%20IF_CR%20Deck_WW37%2724.pptx?d=wa1ef813066aa4384b54edc5fcd627720&csf=1&web=1&e=ekgSGC | [5 empty] | 40 | 0 |  |  | 1.5 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Effort is less than 40 hours and approved by team to move to FS / Build CR Log. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-05 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0095 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 13. Security | Preeti Muni Burh | [11 empty] | Need Super CBA’s and CBA’s Role for NCNRR | Need Super CBA’s and CBA’s roles to control the changes to the sales order when it’s subjected to non-modifiable as per the NCNRR rules matrix. CBA Role : Should be able to modify the Sale Order line-item data ( Quantity, RDD, Loc/Plant & trigger new CMAD,NCNR) cannot be changed within the ‘order modification window’ Super CBA Role: Should be able to modify 1) Sale Order line-item data ( Quantity, RDD, Loc/Plant & trigger new CMAD,NCNR) can be changed within the ‘order modification window’ 2) modify orders/ SOLI flagged as NCNRR The above role changes/authorization object should not be applicable for Updates from Blue Yonder Intel Federal Sale Orders All KB/KE orders in IP IRC sale orders | Change in the role is needed to minimize the risk of CBAs making unauthorized changes to the orders which are subjected to non-modifiable. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0095_OTC%20IP_Need%20Super%20CBA%27s%20and%20CBA%27s%20role%20for%20NCNRR.pptx?d=w3deecdf310b04991be173405948d839d&csf=1&web=1&e=nSCims |  |  | O-030-060 |  |  |  | 0 |  |  | 16 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR moved to Build FS Log as it is less than 40 hours of technical effort |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-07 | 0 | < 15 Days | prburh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0096 | Rejected |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 07. FTS IF | jason.carmichael@intel.com | [11 empty] | PO Lot Pegging - WLA | This will be an change to an existing approved CCB that enabled PO Lot Pegging in R2. This Enhancement of the custom PO Lot Pegging design, originally created for PAT (Package Assembly Test), this would extend support to WLA (Wafer Level Assembly) in R2. This will necessitate a business process modification and an enhancement to capture customer lot information. | Furthermore, Returns scope is being added for PTP suppliers , for which dedicated New L3s need to be added. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0096_OTC%20IF%20-%20WLA%20PO%20Lot%20Pegging.pptx?d=w771f3beeffd74d0cba584e7cef784f49&csf=1&web=1&e=94JhY1 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No |  | 2024-10-10 | Approved for estimations | [8 empty] | Cancelled as this functionality will be captured within the approved CR0125 |  | Tower | 2024-10-10 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-08 | 0 | < 15 Days | jason.carmichael@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) |  | INT-CR0097 | Rejected |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 09B. Data Migration 11. Technology 12. Infrastructure | pipatil@deloitte.com | [11 empty] | Addition of ‘Remark’ Field to ECCN Conversion (OTCC0232) | Addition of ‘Remark’ Field to ECCN Conversion (OTCC0232) | A CR is required to modify the existing conversion with the ‘Remarks’ field. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0097_OTC%20IF%20-%20Addition%20of%20%27Remark%27%20Field%20to%20ECCN%20Conversion%20(OTCC0232).pptx?d=we11004cb7145444a870b169f36b9e6d7&csf=1&web=1&e=VqJSfI |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0232 | 1 | OTCC0232 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | No |  | 2024-10-17 | Approved to proceed with work | [8 empty] | This CR was approved to begin with work, but more changes were required. Therefore, CR0103 was created and approved to encompass all changes. Therefore, this CR0097 is a duplicate and is cancelled. | Build | Tower | 2024-10-17 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-08 | 0 | < 15 Days | samstanley@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0100 | Approved |  | ERP | R2 (Release 2) | High | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data 09B. Data Migration | rausingh@deloitte.com | [11 empty] | IF End Customer and Shared Payer to be added in R2 Scope | End Customer Account group to be added in R2 scope for IF workflows. New Account group to be created for Higher Level Payer (Shared Payer) and to be added in the scope of IF Conversion as well as IF workflows to support the credit team’s financial hierarchy. IF Conversion logic to be changed for identifying and loading the Higher-level payers with the new account group. |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF19FCD74-087E-4E24-BCE8-B958039616D6%7D&file=IF%20End%20Customer%20and%20Shared%20Payer%20to%20be%20added%20in%20R2%20Scope.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [10 empty] | 60 |  |  | 0 | 60 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0182_IF​, DATW0208​, DATW0206_IF, DATE0313​, DATE0395​, DATI0391​, DATI0392​, DATR0389​ | 8 | DATC0182_IF​, DATW0208​, DATW0206_IF, DATE0313​, DATE0395​, DATI0391​, DATI0392​, DATR0389​ | 8 |  | 0 |  | 0 | N/A |  | 2024-12-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-24 | Reviewed offline and will be included in OSC/CL |  |  | 2024-10-30 | Approved by OSC/CL to proceed with work | [5 empty] | Build | CL/OSC | 2024-10-30 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-08 | 0 | < 15 Days | jatkhurana@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0102 | Cancelled |  | ERP | R2 (Release 2) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF | Mohammad Shabaz | [11 empty] | DATC0074-Mapping Rule update in Tax Classification Data | Mapping Rule to convert Tax Classification View of Material Master Data is updated | Mapping Rule to convert Tax Classification View of Material Master Data is updated |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR has been cancelled as it is a duplicate of CR0072 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-09 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0103 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 09B. Data Migration 11. Technology 12. Infrastructure | pipatil@deloitte.com | [11 empty] | Addition of ‘Remark’ Field to HS Conversion (OTCC0233) | Addition of ‘Remark’ Field to HS Conversion (OTCC0233) | A CR is required to modify the existing conversion with the ‘Remarks’ field. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0103_OTC%20IF%20-%20Addition%20of%20%27Remark%27%20Field%20to%20HS%20Conversion%20(OTCC0233).pptx?d=w296994e00c6449b6b179c6d2d5e98000&csf=1&web=1&e=gfMJSr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 |  |  | 15 | [7 empty] | 80 |  |  | 0 | 80 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0233 | 1 | OTCC0233 | 1 |  | 0 |  | 0 | N/A |  | 2024-10-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-17 | Approved to proceed with work | [9 empty] | Build | Tower | 2024-10-17 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-09 | 0 | < 15 Days | samstanley@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0106 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data 13. Security | Karuna Singh | [11 empty] | Addition of Tasks in the Design Sprint Plan for Signavio Flows | L3's Task Addition will be required in the Design sprint plan for creating Signavio flows for Internal Ship to, and End Customers and Mass Processing. MDM-130-010D- Submit the Request (Internal Ship to Customer) | L3's are required to proceed with the creation of Signavio flows as per the Business requirement. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the parent L3 is already included in the E2E list and is still marked as in-scope |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-10 | 0 | < 15 Days | karunasingh9@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0107 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | R1 New User Stories | R1 New User Stories – User Stories related to Consolidate Cashflow - Automated reporting - •Mechanism to upload a CF statement that includes both the External Reporting view (parent) and management reporting view. •Process to add lines or move lines within the External Reporting and Management views of the CF statement and to make updates to historical data for added/moved lines. User Stories related to GR process changes - •Upload of Equity share count – Process to load share count for both QTD and YTD P&L info reports to get the EPS calculation. •Trial balance hierarchy – Hierarchy needed in all S4, ECA and EHANA. | Cash Flow Automated – With this change, CF statement includes both External and Management reporting Views, also able to add lines or move lines within the External Reporting and Management views. Hierarchy –Trail Balance hierarchy needed for the TB report in S4, ECA and EHANA. Upload of Equity share count – with this change, Users will be able to view the share count in Statement of Equity report and the complete report can be automated with EPS etc., |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0170_New%20User%20Strories.pptx?d=w8b721f36d59241e08189b182a7cbb1a8&csf=1&web=1&e=5bK2Se |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Prabesh to not be needed. Therefore, marking as cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-10 | 0 | < 15 Days | phaninkumar@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0108 | Rejected |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | collin.suen.ping.soon@intel.com | [11 empty] | Change method to call Spectrum API with MM# and ShipTo# | There will be no change to the structure of the API. The structure will remain the same as the delivery API structure. The only change will be sending material and ship-to in the URL instead of the delivery number. After sending material and ship-to to Spectrum, the response will be the same as it currently is (based on delivery). | Needed of Integration of S4 and MPL to accommodate label printing. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0108_OTC%20IF_API%20change.pptx?d=we2957574e5654ccfaaddd74d2a436a4f&csf=1&web=1&e=xrdGBm |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 38 | 0 |  |  | 6 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-10-17 | [9 empty] | Effort estimation is less than 40 hours, so the CR will be moved to the FS Build Tracker. | Build | Not Assigned |  | Not Approved | 10, 2024 | 10, 2024 | 2024-10-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0109 | Approved | Tech effort is 36 hours | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology 12. Infrastructure | Taposh Ganguli | [11 empty] | Custom Z table(DH) creation & updates to the outbound order acknowledgement interfaces in S4 to support open text | A custom table (DH) must be created in S4, to replace the 7 custom Z tables that are existing in ECC The data in this table in S4 will support open text on the outbound interfaces related to order acknowledgements(3A6,3A7,3A4C,3A8C) to determine the trading partner The table will be maintained & viewed by the B2B team through a Fiori App ,similar to the approach in ECC. | If this enhancement is not implemented then B2B team will not be able to route the outbound order acknowledgement details based on data maintained in the DH table. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0109_OTC%20IF_CR%20Deck_Custom%20table%20(ZDH)%20creation.pptx?d=w4e907eee2154484984440229eaf42d00&csf=1&web=1&e=dfDyFL |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 |  |  | 3.5 | [5 empty] | 36 |  |  |  |  | 0 | 36 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | o RICEFW was approved for IP; change request is to approve the RICEFW for IF, which is going live in R2.  Open Text is already receiving information for IP. | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-10 | 0 | < 15 Days | tganguli@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0110 | Approved | Tech effort is 24 hours | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics 11. Technology 12. Infrastructure | Taposh Ganguli | [11 empty] | Sold to party & Ship to party customer codes determination based on DUNS & DUNS4 numbers | Ability to determine the sold to party & ship to party customer numbers based on the DUNS numbers received on the inbound order interface & also referenced on the outbound interfaces. The DUNS & DUNS4 numbers will be maintained in the business partner general role tab “identification” of the sold to party & ship to party | If this enhancement is not implemented then Inbound orders will not be able to determine sold to party & ship to party customer codes in S4 and Outbound interfaces will not be able to populate the DUNS number on the order acknowledgements |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0110_OTC%20IF_CR%20Deck_DUNS%20DUNS4%20Sold%20to%20ship%20to.pptx?d=w95b791aa44814881ac4e60caf5918ccb&csf=1&web=1&e=fwLmmN |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 |  |  | 12 | [5 empty] | 24 |  |  |  |  | 0 | 24 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-15 | CR was taken straight to Core Leadership |  |  | 2024-10-16 | Approved | [5 empty] | Other | CL/OSC | 2024-10-16 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-10 | 0 | < 15 Days | tganguli@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0112 | Cancelled | To be moved to the FS/Build CR Log as it is less than 40 hours | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF | Pranjal Yadav | [11 empty] | Changes in RMA TPT and Credit Issued Report | Requirement for addition of underline columns for calculation of 3 TPT's as; 1. Customer Return order create Date(rename) - R15 2. Goods Receipt Date - R16 3. Disposition/Inspection Date - R17 Added and renamed columns - actual_goods_movement_dt as "Goods Receipt Date Added new column "Return Reason (Description)" mapped to 'return_reason_code_dsc’ CONCATENATE below columns in report 1. Order Reason + Order Reason (Description) 2. Return Reason + Return Reason (Description Geo Name mapped to "sales_organisation_geographical_name“ Added ' billing_document_type_cd' column and renamed as "Document Type" for slicer | Based on the additional fields added and concatenated (Return reason , Order reason) in the system , the system checks and provides response to the customer​ Tech = 6 hours ; Functional = 2 hours Effort Estimate - 8 hours​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0112_OTC%20IF%20-%20Changes%20in%20RMA%20TPT%20and%20Credit%20Issued%20Report.pptx?d=w91415bdeb5374dce880d936fc5eac9e1&csf=1&web=1&e=yREaW3 | [5 empty] | 8 | 0 |  |  | 2 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR has been cancelled as the technical effort is less than 40 hours and will not introduce a new RICEFW into scope. Team to move to the FS/Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-11 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0113 | Approved |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 12. Infrastructure 17. B-App | shane.bethune@intel.com | [11 empty] | When BBG - MuleSoft interface fails on the on Thursday and manually if we execute it again on Friday it should have run date of friday for TRSP. | Incase of failure of the BBG interface and manually if it is executed on next day it will pick run date for the day the program is executed. | Causing errors while transmitting the files to downstream systems. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0113%20When%20BBG%20-%20MuleSoft%20interface%20fails%20on%20the%20on%20Thursday.pptx?d=w1a9fa321a5354792ba6ad856f51fe84a&csf=1&web=1&e=UhRgjW |  | 8. Non-Build Infrastructure-related Change |  |  |  | 8 | 0 | [8 empty] | 8 |  |  |  |  | 0 | 8 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-31 | Reviewed offline in Daily Sync and aligned to not require CCB approval for the work to proceed. | [9 empty] | Other | Tower | 2024-10-31 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-11 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0114 | Cancelled |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | Prabesh Acharya | [11 empty] | "WBS_TO_IO_MAPPING" mass upload capability | Need mass upload capability to update "WBS_TO_IO_Mapping" capability | Current Fiori App for "WBS_TO_IO_MAPPING" doesn't have mass upload capability, we need this capability to provide business users an option. |  | Yes | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Prabesh that the changes have been completed in R1 already. Therefore, cancelling CR. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-12 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0115 | Cancelled | Move to the FS/Build CR Log as the technical development effort is 36 hours, which is less than 40 hours. | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 04. OTC IF 05. OTC IP | vprashantpotphode@deloitte.com | [11 empty] | Credit check steps enhancements | 1. 000- No Credit check - The purpose of this BAdI enhancement is to DO NO Credit Check. There is no code. This check step will always pass and will be used as a place holder in a Credit Check Rule so the Horizon Values will populate. Tech logic: No code in the badi. This is just a place holder in the credit check rule so the horizon values will populate 2. 003-Review all Orders - The purpose of this BAdI enhancement is to always fail. It is used to force all orders to be reviewed and be released manually. Tech logic: No checks are done in this BADI. Just raise an error message and exit. Error message: Review all orders check rule failed 3. Payment performance Check step logic to be enhanced to consider shared HLP. Tech Logic: Current payment performance logic will only work if the HLP has LLPs which belong to either IF or IP. If HLP has LLPs belonging to IF as well as IP (shared HLP), then the current logic will not work Tech = 36: Functional = 16: Total = 52 Hours. | 1. 000- No Credit check - The purpose of this BAdI enhancement is to DO NO Credit Check. There is no code. This check step will always pass and will be used as a place holder in a Credit Check Rule so the Horizon Values will populate. Tech logic: No code in the badi. This is just a place holder in the credit check rule so the horizon values will populate 2. 003-Review all Orders - The purpose of this BAdI enhancement is to always fail. It is used to force all orders to be reviewed and be released manually. Tech logic: No checks are done in this BADI. Just raise an error message and exit. Error message: Review all orders check rule failed 3. Payment performance Check step logic to be enhanced to consider shared HLP. Tech Logic: Current payment performance logic will only work if the HLP has LLPs which belong to either IF or IP. If HLP has LLPs belonging to IF as well as IP (shared HLP), then the current logic will not work Approval Status Approved/Rejected By Approved/Rejected Date Approved/Rejected comments |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0115_OTC%20IF_Credit%20check%20steps%20enhancements.pptx?d=wc5e0e8c24a134288b75ea36ea2b5be85&csf=1&web=1&e=wJyCeT | [6 empty] | 0 |  |  | 16 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort is less than 40 hours, so the CR will be moved to the Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-14 | 0 | < 15 Days | pbathini@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0116 | Rejected |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 06. PTP | Prabesh Acharya | [11 empty] | Company code move to different S4 instance 390/724/604/622/645/606 | Company code 390 - to be moved from IF to IP Company code 724 – to be deleted from IF and keep CFIN only. Company code 604/622/645 – to be deleted from IP and make them available in CFIN only. Company code 606 – to be added to IP box | Legal Entity-390 Nature of entity is predominant IP Entity but holds mixed IF and IP subsidiaries. The original POR proposed by KPMG was to demerge LE390; with the existing entity being an IF Entity holding the Israel Fab. Subsequently, to minimized impact to LE390 Employees, and reassessment by KPMG, the plan was revised so that LE390 will retain its employees and hold IP subsidiaries instead of the Fab. Legal Entity –724 Currently designated as IF entity, it was the China NAND Fab until the sale of the NAND business to SK Hynix. After the 1st closing in 2021, the entity has a handful of Employees and activities and is designated as IF/CFIN Entity expected to be fully dormant after the 2nd closure in Q3’25 and will be liquidated. Legal Entity –604/622/645 Currently designated as IP entities, they are on liquidation roadmap and only need to be in CFIN for liquidation capability. Legal Entity – 606 Both 606 (Mobileye) are non-integrated entities maintained in CFIN only. However, asset ledger will be required to manage intangible assets under these 2 company codes. Asset ledger is not available in CFIN, thus, they need to be added to IP to leverage asset ledger. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0116_Company%20code%20CR.pptx?d=w72b4adcb00254ea7b81fb539d2e56df9&csf=1&web=1&e=HVhAFe |  | 3. Configuration Change | DC-020-010 |  |  |  | 0 |  |  | 50 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-10-31 | [9 empty] | All details of this CR was combined with CR0051 | Other | Not Assigned |  | Not Approved | 10, 2024 | 10, 2024 | 2024-10-16 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0117 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Requirement to change attribute/technical field name | Requirement to Change technical field name from "CUSSADD" to "CUSADD" in outbound IDOC ORDERS05 from S/4 to E2open to make sure all of the fields with this attribute name/technical field name are aligned across Middleware and as per E2open Xpath. | To make sure all of the fields with this attribute name/technical field name are aligned across S/4 ,Middleware and as per E2open Xpath logic. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-16 | 0 | < 15 Days | subramani@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0118 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | yswaddeshpande@deloitte.com | [11 empty] | Requirement to change attribute/technical field name | Requirement to Change technical field name from "CUSSADD" to "CUSADD" in outbound IDOC ORDERS05 from S/4 to E2open to make sure all of the fields with this attribute name/technical field name are aligned across S/4, Middleware and as per E2open Xpath logic |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was a duplicate of CR0117 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0119 | Approved | Need tech estimation | ERP | R2 (Release 2) | Low | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR 04. OTC IF 09A. Master Data | suresavula@deloitte.com | [11 empty] | FPRE0574 - Margin Analysis Custom Characteristics addition | Operating Concern is to be updated with Custom Characteristics created in Custom Fields and Logics - Market Segment. This is part of additional COPA characteristics needed by business for tracking Tech node, End Customer and WBS fields | Operating Concern in R1 / R2 has only standard characteristics. Additional Characteristics are created as development through Custom Fields and Logics app (No code). These additional Characteristics are needed in operating concern for Margin Analysis reporting |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE23D815C-2A68-4C47-ADE1-38D5DD971F15%7D&file=INT-CR0119_FPR%20IF%2CIP_CR%20Deck_Custom%20profitability%20dimensions%20creation.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 67 |  |  |  |  | 0 | 67 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0574_IF, FPRE0574_CFIN​ | 2 | FPRE0574_IF, FPRE0574_CFIN​ | 2 |  | 0 |  | 0 | N/A |  | 2024-10-14 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-17 |  |  |  | 2024-10-18 | Approved | [5 empty] | Build | CL/OSC | 2024-10-18 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-16 | 0 | < 15 Days | subramani@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0120 | Cancelled | To be moved to the FS/Build CR Log as it is less than 40 hours | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 10. Analytics | Sumit Sharma | [11 empty] | GTS (Trade) Data Model changes - Multiple reports impacted | Due to the changes required to the Logical Data Model with the data issues found by Lei, which required more table ingestion and changes to field names. Below reports are impacted - 1. RPL List Summary 2. NumberSet 3. Encryption Report with US HS, US ECCN and US Pcode 4. RPL Screening Summary Dashboard 5. Party Screening Result 6. Export License Master Data | Due to the changes required to the LDM with the data issues, which required more table ingestion and changes to field names, the FUT required for ITC1 reports will be delayed, and consequently the reports development for ITC2 will be delayed by 2 weeks. Below all reports are impacted as part of ITC1 and ITC2 cycle - 1. RPL List Summary 2. NumberSet 3. Encryption Report with US HS, US ECCN and US Pcode 4. RPL Screening Summary Dashboard 5. Party Screening Result 6. Export License Master Data |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/OTC/INT-CR0120_OTC IF - GTS LDM Changes.pptx?d=wf2aa484c57654d8f9d38751d0767fd1c&csf=1&web=1&e=QeiK2L | [5 empty] | 31 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR has been cancelled as the technical effort is less than 40 hours and will not introduce a new RICEFW into scope. Team to move to the FS/Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-17 | 0 | < 15 Days | sumitsharma9@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0121 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.1 Master Data - ALL |  | 09A. Master Data | Harshvardhan Maheshwari | [11 empty] | L3s for Plant as Vendor for Process Flow tasks need to be added to the R3 Sprint 9 Design sheet. | The delay in identifying the ownership of the plant as either a customer or vendor has caused a delay in the MDG workflow design. | L3s for Plant as Vendor for Process Flow tasks need to be added to the R3 Sprint 9 Design sheet. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/14.%20OCM/00.%20Roadmap%20%26%20Project%20Planning/_Meeting%20Materials/PMO%20Meetings/CR-INT-CR0121.pptx?d=wfa841b6914cb47a88da984556b73646b&csf=1&web=1&e=pz1EJM |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Spillage of sprint activities will be tracked as overdue. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-17 | 0 | < 15 Days | harshmaheshwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0122 | Approved |  | ERP | R1 (Release 1) | Low | 14. OCM | 14.3 OCM - FPR Embedded |  | 14. OCM | Laura Winterton | [11 empty] | R1 CAN Kick Off Milestone | Defer R1 Change Agent Network (CAN) Kickoff to after Nov 15th and move from Build milestone to Testing for payment. | Current global comms guidance is to hold communications and engagement activities through the end of the year, modifying the FPR R1 change agent network approach. Aligned approach was ratified by OSC/CL on 9/18/2024. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/14.%20OCM/00.%20Roadmap%20%26%20Project%20Planning/_Meeting%20Materials/PMO%20Meetings/CR%20-%20R1%20Build%20CAN%20Network%20Kickoff.pptx?d=w09ee7a340efc4ee89fb234fc74765563&csf=1&web=1&e=mTWpgS |  | 13. Other Milestone Adjustments | NA |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-31 | Reviewed offline and approved. Integrated Plan will be updated with the new deliverable dates. | [9 empty] | Other | Tower | 2024-10-31 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-18 | 0 | < 15 Days | lwinterton@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0123 | Cancelled |  | ERP | R3 (Release 3) | Low | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | sashs@deloitte.com | [11 empty] | Reverting MW (MuleSoft) changes related to CR 0093 | CR0093 was created to change the Input file approach from File based approach to ODATA based approach. Since this change has been deemed to be not acceptable, hence creating this CR based on MW (MuleSoft) team request to revert the changes back to the File based approach. | CR0093 was created to change the Input file approach from File based approach to ODATA based approach. Since this change has been deemed to be not acceptable, hence creating this CR based on MW (MuleSoft) team request to revert the changes back to the File based approach. Tech - To be added by MW (MuleSoft) Team |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0123_OTC%20IP_CR%20Deck_OTCI0081%20and%20OTCI0082%20-%20Approach%20change%20from%20OData%20S4%20API%20to%20File%20-based%20in%20the%20Middleware.pptx?d=wd07f8cc600144aa0aa9dbbad4ed3c58b&csf=1&web=1&e=VmSuMf | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the middleware team confirmed that the work has been completed and was less than 40 hours of work. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-18 | 0 | < 15 Days | sashs@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0125 | Approved |  | ERP | R2 (Release 2) |  | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 10. Analytics | vprashantpotphode@deloitte.com | [11 empty] | R2_OTCFR057_Billing Details Report with Historical Data- ECA Report fields update | Currently we assuming only 3 changes 1. 5 new fields to be added Net Amt, Tax Amt, Total Amt, Accounting Doc Nbr, Credit Discount 2. Adding Pre-Query Filters 3. Adding 1 page for Filter with Navigation to report 4. Additional feature for Paginated report export in excel Tech = 100 : Functional = 18: Total = 78 Hours. | 1.5 new fields to be added Net Amt, Tax Amt, Total Amt, Accounting Doc Nbr, Credit Discount A. Net Amt = If VBRP-SHKZG(RetrunItemProcessingType) =' X VBRP-NETWR(NetAmt) * -1 otherwise VBRP-NETWR(NetAmt) B. Tax Amt = If VBRP-SHKZG(RetrunItemProcessingType) =' X VBRP-MWSBP(TaxAmt) * -1 otherwise VBRP-MWSBP(TaxAmt) C. Total Amt = Tax Amt + Net Amt D. Accounting Doc Nbr = Pass Billing document number in BKPF-AWKEY (Reference Key) and BKPF-BUKRS (company code). Get BELNR (value) Accounting Doc Nbr E. Credit Discount – I have asked billing team to confirm how this field is stored in billing tables. If it gets included in the Net Amt calculation at line item, then we don’t need it. 2. These are the billing types we have for IF up to today. I think we can this as default selection and any new billing types that created can be selected by the users to add onto the filter. ZC2 ZD2 ZF1 ZF2 ZFV ZRE ZRG 3. Pls remember to set the below fields for report selection. If you need to have a filter page/prompt for selecting before executing the report that we can utilize the “clear filter” function, then pls go ahead. Approval Status Approved/Rejected By Approved/Rejected Date Approved/Rejected comments |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0125_Billing%20Details%20Report%20with%20Historical%20Data-%20ECA%20Report.pptx?d=w5d171ec8388b48c58eed16678fff6287&csf=1&web=1&e=atwQ0H |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 100 | 0 |  |  | 18 | [6 empty] | 100 |  |  |  | 0 | 100 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCFR057 | 1 |  | 0 | OTCFR057 | 1 |  | 0 | N/A |  | 2024-12-05 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-24 | o AR: Update Impact slide with names of Intel IT approvers and ensure that all impacts across teams are captured o AR: Once Impact slide is filled out, send email to Rebecca Verette and Uzma Ahmed (CC Alpna Gainda and Anna Tam) for confirmation and approval |  |  | 2024-11-05 | Approved to continue with the work | [5 empty] | Build | CL/OSC | 2024-11-05 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-18 | 0 | < 15 Days | pbathini@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0126 | Approved |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Praveen Kumar Muppala | [11 empty] | Sales Org Inherited Pricing | When IPAR/MyDeals Interface sends price to S4 for AM01/AP01/EU01/JP01 sales org combinations in the payload, S4 program need to read the data in the file and create(multiply) pricing records for all S4 sales organization combinations. For example, if prices are received for AM01, then prices must be created for all AM* sales orgs in S4.AM* sales orgs are AM01,AM03,AM10,AM13 and AM15. Prices for AP01 received: Prices must be created for AP* sales orgs, AP* sales orgs are AP01,AP03,AP21, AP57 Prices for EU01 received: Prices must be created for EU* sales orgs, EU* sales orgs are EU01,EU02 Prices for JP01 received: Prices must be created for JP* sales orgs, JP* sales orgs are JP01 Sales org reference table in S4 is TVKO. This CR should be implemented for Interfaces OTCI0081 (Pricing feed from IPAR to S4)and OTCI0082(Pricing feed from My Deals to S4). The scenarios of Upload ad Expire scenarios should be considered here | IPAR/MyDeals load prices to S4 for main sales organizations(AM01, AP01,JP01, EU01) only but sales orders are created in S4 for super distis like AM03, AP03, EU02. In S4, we need to have prices for all super disti’s so, that during sales order creation the price can be determined automatically from the respective sales organization pricing condition tables |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0126_OTC%20IP_CR%20Deck_Sales%20Org%20inherited%20Pricing.pptx?d=w4fde99e8591a49e1bd0238e4eaa37213&csf=1&web=1&e=Y8Bn8j |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 |  |  | 16 | [5 empty] | 40 |  |  |  |  | 0 | 40 | Tech - S/4 | No |  | 0 | N/A |  | OTCI0082, OTCI0081 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0081, OTCI0082 | 2 | OTCI0081, OTCI0082 | 2 |  | 0 |  | 0 | N/A |  | 2025-02-07 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-11-21 | o Original RICEFW was rejected in OSC/CL, and this CR is to provide a second option. o AR: Update deck to include how CR was identified in “Options / Alternatives” on slide 1 and include a brief reference to the originally rejected RICEFW - @Muppala, Praveen Kumar o AR: Update Key Stakeholder field on Slide 1 with Intel business owner - @Muppala, Praveen Kumar o AR: Include within OSC/CL agenda - @Tam, Anna @Deolalikar, Sagar |  |  | 2024-12-06 | • This Change Request relates to Enhancement OTCE0684, Console ID 2059, which was presented to the OSC/CL in the ww41.5 mtg (10/11/24). See below for notes captured at that meeting. • At that time, the team was given an AR to find a different, less complex technical solution for the requirement, and they have. • Today, the team is requesting to address the requirement by using an interface rather than an enhancement. • This request requires 40 hours or work (to move from Enhancement to an Interface) | [5 empty] | Build | CL/OSC | 2024-12-06 | 12, 2024 | 12, 2024 | 10, 2024 | 2024-10-18 | 0 | < 15 Days | pmuppala@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0127 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.2 OCM - Change Core Team |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Re-alignment of Awareness Communications due to new R3 go live POR | Requesting the movement of the Awareness Communications for R3 to a due date of Jan 2026. | Q3/Q4 2024 is a reduced communications window With an updated R3 go live POR, end users do not need to be made aware of IAO efforts until Q1 2026. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0128 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Realignment of R3 Change Management Project Plan | Requesting moving the R3 Change Management Project Plan to end of R3 Build to allow for integrated IAO CM planning workshops. | With the updated R3 go live POR, alignment of change activities and communications will be workshopped across all IAO programs to support end user experience. Requesting a shift of due date to end of R3 Build to allow for workshop sessions. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0129 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Realignment of the R3 Leadership Engagement Approach | Requesting shift of the R3 Leadership Engagement Approach to realign with the R3 go live POR. Dependencies currently being worked that inform the Leadership Engagement Approach include: CM COE op model, Q3/Q4 2024 reduced comms environment, and aligned impacted stakeholders at the IAO level. | IAO dependencies for the leadership engagement approach need maturing and leaders would not be engaged until the end of 2025 based on the current POR go live date. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0130 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Realignment of the Program Communications & Engagement Plan for R3 | Requesting realignment of the program communications and engagement plan to align with new R3 go live POR. Request shift of deliverable to end of R3 Build. | As the organization is likely to change over the next year, the strategy and plan should be refined with information from R1 & R2 and updated with any changes to prepare end users for a 2027 go live. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0131 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Realignment of the Program Communications & Engagement Strategy for R3 | Requesting realignment of the program communications and engagement strategy to align with new R3 go live POR. Request shift of deliverable to end of R3 Build. | As the organization is likely to change over the next year, the strategy and plan should be refined with information from R1 & R2 and updated with any changes to prepare end users for a 2027 go live. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | lwinterton@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0132 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | lwinterton@deloitte.com | [11 empty] | Realignment of the Refined Leadership Walking Deck | Requesting realignment of the R3 refined leadership walking deck to align with new R3 go live POR. Request shift of deliverable to end of R3 Build. | As the organization is likely to change over the next year, the leadership walking deck should be refined with information from R1 & R2 and updated with any changes to prepare end users for a 2027 go live. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR0127-0132%20-%20R3%20CM%20Detailed%20Design%20Non%20Sprint%20Deliverables.pptx?d=w037ab824e90b4084ba615321a36367db&csf=1&web=1&e=lL5eoN |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-24 | Reviewed offline. Approved since R3 timeline has been replanned | [9 empty] | Other | Tower | 2024-10-24 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-19 | 0 | < 15 Days | lwinterton@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0133 | Approved |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli | [11 empty] | New L3’s needs to be added for Sprint 9 for the Partner Owned Equipment Process | L3’s associated with Partner Owned equipment needs to be created within the Design Sprint Plan for Sprint 9 | Based on the current process of looking into various design elements within a sprint, if a L3 is being used by multiple process then the L3 is copied multiple times within a sprint for each business process Effort : 2 Hrs |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0133_OTC%20IF_CR%20Deck_New%20L3%20for%20R3%20Partner%20Ownded%20Equip.pptx?d=w67b204a18c7c493290c6543624057e14&csf=1&web=1&e=fCmEgM |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-24 | o AR: Update deck with an analysis of what design work remains and which L3’s will be worked on in Sprint 9 o AR: Confirm that the ingestion of the remaining work will not affect the rest of the R3 Sprint 9 design o AR: Once the deck has been updated, send an email for offline approval to Uzma Ahmed with Alpna Gainda and Anna Tam CC’ed |  |  | 2024-10-30 | Approved by OSC/CL to proceed with work | [5 empty] | Design | CL/OSC | 2024-10-30 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-21 | 0 | < 15 Days | tganguli@deloitte.ca | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0134 | Cancelled |  | ERP | R3 (Release 3) | Low | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Praveen Kumar Muppala | [11 empty] | OTCI0081/OTCI0082 - Approach change from OData S4 API to File | 10/25: Praveen: This is a duplicate of CR#0123. This is not needed. Changes will be made via CR#0123. There is change in approach in OTCI0081/OTCI0082 and we are moving back to file based approach from API based approach, Middleware will need to make the necessary changes in the approved HLTA & TDD, along with build. | Based on technical feasibility in S4 this change is required. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0134_OTC%20IP_CR%20Deck_OTCI0081%20and%20OTCI0082%20-%20Approach%20change%20from%20OData%20S4%20API%20to%20File%20-based%20in%20the%20Middleware.pptx?d=w4ad2e1c94c6649bc9480e1d51ed15221&csf=1&web=1&e=XUgA3Y |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This CR Is a duplicate of CR0123. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-21 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0135 | Cancelled |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP 06. PTP | JEAN-MARC LENC | [11 empty] | Customs Tracker BApp Integration to GTS | As a logistics personnel/trade Analyst we would like to perform shipment’s data entry into Customs Tracker, thus during data entry we need to enter (PO/ISM/DN) for pulling these data from S4 system, so that we can complete data entry for Custom clearance and tracking in the CUSTOM TRACKER Boundary App. The interface is required for custom broker declarations for imports & exports and tracking. | Enables smooth filing of Customs declaration as this process change will allow the data to have a 4-way match between the PO, Invoice, Proof of Goods Received and CDS Number. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Approved by Jean-Marc to not require a Change Request. Interface request will only need a RICEFW that is reviewed by PTP tower for approval. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0136 | Rejected |  | ERP | R2 (Release 2) R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 09A. Master Data 17. B-App | eugene.celis@intel.com | [11 empty] | IFS Shuttle for R3 | Master Data and product orders on IFS Shuttle for R3 needed. IFS Shuttle design -same wafer had multiple products from different customers or same customer with different products Raid 2415 | IFS Shuttle orders required for R2/R3. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB2B79D72-4C82-4B1A-A4C3-9627F1E87368%7D&file=CR0136_Intel%20Foundry%20FTS_IFS_Shuttle%20Deck_R3.pptx&action=edit&mobileredirect=true | [5 empty] | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 11. OSC/CL Rejected (end status) | Yes |  | 2024-10-31 |  |  |  | 2024-11-05 | Not approved to proceed with work; No resources at this time; Acknowledge spill over Q1 20225 | [6 empty] | CL/OSC | 2024-11-05 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0137 | Approved | Tech effort is 80 hours | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology 12. Infrastructure 17. B-App | jason.carmichael@intel.com | [11 empty] | PO Lot Pegging (Soft) – Sync Orders in ECC and S/4 | This will be a change to an existing approved CCB (INT-CR0052) that enabled PO Lot Pegging for OTC-IF in R2 using both ECC and S/4. We need to automate syncing the orders created in S/4 into ECC.​ ​ | The original design enabled POLP using ECC tables and system and replicating the table in S/4. However, a significant design issue was encountered with keeping orders and deliveries in sync between ECC and S/4. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR00137%20PO%20Lot%20Pegging%20%E2%80%93%20%20Move%20functionality%20from%20ECC%20to%20IF.pptx?d=w1452c2d928204171b8c8072d27f54499&csf=1&web=1&e=EZT2Uk |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 230 |  |  |  |  | 0 | 230 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-31 |  |  |  | 2024-11-01 | Approved to proceed with work | [5 empty] | Other | CL/OSC | 2024-11-01 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0138 | Approved | Should be tagged to FPRXV033, FPRXV034, FPRXV035, FPRXV036 with 170 hours of tech effort | ERP | R1 (Release 1) R2 (Release 2) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | ECA/Analytics -Automate CFIN XREF Mapping Replication for Transactional Recon Reports | Automate the replication of CFIN data mapping tables (GL Account, Profit center, Cost Element) between CFIN into ECA.​ Logic to derive XREF mapping from various tables ingested into ECA. | SAP doesn’t provide transparent table storing the CFIN mapping that could be leveraged in ECA directly. Therefore, manual replication XREF files was planned originally. However, team have explored further and found out a way to automate the creation of XREF tables in ECA using Schema tables from CFIN.​ Manual replication of XREF files is error prone, time consuming and inefficient, which could lead to inaccurate reconciliation reporting between ECC & CFIN. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0138_ECA%20Recon%20Reports%20R1%20R2%20parallel%20run%20reconciliation%20reports.pptx?d=w0daf82bdb37b439aa6ceb252b3ab4473&csf=1&web=1&e=UQV8lM |  | 2. New RICEFW / ECA / Build Object | DC-010-100 |  | Low | 0 | 1 | [9 empty] | 170 |  |  |  | 0 | 170 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-10-24 | Reviewed offline and will be included in OSC/CL agenda |  |  | 2024-10-30 | Approved within OSC/CL to continue with work | [5 empty] | Other | CL/OSC | 2024-10-30 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-25 | 0 | < 15 Days | navnegi@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0139 | Approved |  | ERP | R2 (Release 2) | Medium | 14. OCM | 14.2 OCM - Change Core Team |  | 14. OCM | Laura Winterton | [11 empty] | R2 Build Comms Deliverables | Defer R2 Change Awareness Assessment, R2 Communication Materials and R2 Change Network Toolkit, Change Network Kickoff and Meeting Materials to Test Phase. | Current global comms guidance is to hold communications and engagement activities through the end of the year, modifying the R2 comms and change agent network approach. IAO work is underway to build an integrated CAN across IAO programs and towers. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/CR%20-%20R2%20Build%20Deliverables.pptx?d=w70351c9c74304ad4bd2fd298e88df5d8&csf=1&web=1&e=eqLIZL |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-10-31 | Reviewed offline and approved. Integrated Plan will be updated with the new deliverable dates. | [9 empty] | Other | Tower | 2024-10-31 | 10, 2024 | 10, 2024 | 10, 2024 | 2024-10-25 | 0 | < 15 Days | lwinterton@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0140 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data | rausingh@deloitte.com | [11 empty] | DQM report to review changes from MDG to Reltio | Currently, the DQM report is built to review the changes from Reltio in MDG. In future state, Whenever there is a change in customer master in MDG, DQM Report should show all the discrepancies between and MDG and Reltio. In order to keep the MDG and RELTIO data in sync. |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Raunaq that MDG team has decided to not go forward with this change anymore. Cancelling |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0141 | Cancelled |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | Sapna Bansal | [11 empty] | For transferring HRMM data by workersnapshot API from WCDS to MDG & CFIN, through middleware Mulesoft | For transferring HRMM data by workersnapshot API from WCDS to MDG & CFIN, through middleware Mulesoft | Through this interface MuleSoft would transfer the HRMM data retrieved by workersnapshot API from Source system WCDS to MDG system as target system. Mulesoft would push data to target system based on the logic defined in mapping. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/Mulesoft_SignatureAuthority%20API_HRMM_Deck.pptx?d=wd940ac92f9c54d7abc013f0e493c409a&csf=1&web=1&e=pBhiAO | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelling as this will go through the RICEFW intake process instead |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-29 | 0 | < 15 Days | sapbansal@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0142 | Cancelled |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | Sapna Bansal | [11 empty] | To transfer HRMM data retrieved by SignatureAuthority API from source system WCDS to target system MDG & CFIN by Mulesoft | To transfer HRMM data retrieved by SignatureAuthority API from source system WCDS to target system MDG & CFIN by Mulesoft | Through this interface Mulesoft would transfer the HRMM data retrieved by SignatureAuthority API from Source system WCDS to MDG system as target system. Mulesoft would push data to target system based on the logic defined in mapping. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/Mulesoft_Workersnapshot%20API_HRMM_Deck.pptx?d=wa901c02a90674b9092de950404bdfaef&csf=1&web=1&e=FXeEfi | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelling as this will go through the RICEFW intake process instead |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2024 | 2024-10-29 | 0 | < 15 Days | sapbansal@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0143 | Rejected |  | ERP | R2 (Release 2) | Very High | 15. Cutover | 15.2 Cutover – Cutover Planning & Execution |  | 15. Cutover | kevinx.obrien@intel.com | [11 empty] | IF Customer Planning Hierarchy attribute configuration and data load | The IF Customer Planning Hierarchy attributes need to be added to the Customer Master Data team’s data configurations and Data to be loaded. Scope is about 150 IF Customers. | Attributes must be added so the IF Customer Planning Hierarchy in SAP MDG Custom Objects can be populated as designed in MC2 through an automatic (as opposed to manual) process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/Change%20Request%20Template_PH_CustomerMaster.pptx?d=wd6b0e71ad734460eb5917bc359162aed&csf=1&web=1&e=RZgneb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-11-07 | [9 empty] | Given where the team is in R2, Candi confirmed that we will NOT be needing this CR. This data load for the 5 attributes that planning needs on the customer master will be done manually by Candi’s team as part of cutover vs. needing a change in the conversion object. Candi will align with the SCP team on this. | Build | Not Assigned |  | Not Approved | 11, 2024 | 10, 2024 | 2024-10-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0144 | Approved |  | ERP | R2 (Release 2) | High | 10. Analytics | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | kritajoshi@deloitte.com | [11 empty] | Building 7 MD/MD Recon Reports on ECA in parallel with InfoSteward | Update build timelines | Build dates were not updated post-alignment for ECA report development, causing discrepancies while tool POCs are ongoing. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B33A59E66-0554-4B94-B63D-31713A23DE69%7D&file=INT-CR0144_Analytics_CR%20Deck.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMDMyNDkxNiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR020​, FPRXR021​, FPRXR022​, FPRXV026​, FPRXV027​, FPRXV031​, FPRXV032​ | 7 |  | 0 | FPRXR020​, FPRXR021​, FPRXR022​, FPRXV026​, FPRXV027​, FPRXV031​, FPRXV032​ | 7 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-11-07 | [10 empty] | Other | Tower | 2024-11-07 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-31 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0145 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics 13. Security | Rea Meyer | [11 empty] | Asset Accounting : - LE setup and M&A functionality in S4 | Enable Asset subledger in S4 IF instance for LE 327 and 377 ​ Update the Mass Asset Acquisition and Mass Asset Transfer RICEFWs to accommodate M&A asset conversion requirements within S4 system | LE327 and LE 377 are setup in ECC with the requirement for a fixed asset subledger and corresponding update for S4 design was not captured​ M&A has customization within ECC that allows for the processing of mass assets during conversion. One aspect of the customization is not captured in the S4 AMT or Mass Tool design. This CR will allow for the S4 solution to meet the requirement that converted assets be captured at the original cost and accumulated depreciation amounts in the leading and non-leading ledger.​ ​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0145%20LE%20setup%20and%20M%26A%20functionality%20in%20S4.pptx?d=w410bd6d91738438ab11f702cbc45c8f8&csf=1&web=1&e=QeGEAN |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-040-0120 |  |  | 65 | 0 | [8 empty] | 65 |  |  |  |  | 0 | 65 | Tech - S/4 | No |  | 0 | N/A |  | FPRE0572_IP, FPRE0572_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0572_IF, FPRE0572_IP | 2 | FPRE0572_IF, FPRE0572_IP | 2 |  | 0 |  | 0 | N/A |  | 2025-07-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-11-21 | o This change request is to enable asset subledger in for LE 327/377 and update Mass Asset Acquisition & Transfer RICEFW’s with M&A asset conversion requirements. o There will be a minor impact to security. Approved to continue with the work | [9 empty] | Build | Tower | 2024-11-21 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-31 | 0 | < 15 Days | akatariya@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0146 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 09B. Data Migration 10. Analytics 13. Security 15. Cutover 16. Testing | Rea Meyer | [11 empty] | Requesting additional design sprints for FPR teams #2 (tax), #5 (fixed assets), and #11 (Capital Project Accounting) to assess and design for AMIC tax requirements and associated forecast and actuals reporting for grants | Requesting additional design sprints for FPR teams #2 (tax), #5 (fixed assets), and #11 (Capital Project Accounting) to assess and design for AMIC tax requirements and associated forecast and actuals reporting for grants | The business criteria for these grants were being developed in real time and the business operations teams were able to solidify design criteria at the end of R3 sprint 8. To do a complete review of the business requirements and develop a solution that meets all FPR needs, we are asking for a design extension from sprint 9 to sprint 11​ ​ Tax requirements:​ New books 16/17/18/19​ Changes to the California and AMIC books names​ Three new AMIC books​ ​ Finance Requirements​ Systematic ability to report on forecasted and actual grants at the project and asset level |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/FPR%20team%20%235%20-%20Sprint%209%20and%2010%20CR.pptx?d=w9d1be1b87990490bba8e082758d1494a&csf=1&web=1&e=hQ20pB |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) | DC-040-0120 |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-11-21 | o AR: Update R3 Consolidated Roadmap with new end sprint as Sprint 10 - @Tam, Anna Approved to continue with work. | [9 empty] | Other | Tower | 2024-11-21 | 11, 2024 | 11, 2024 | 10, 2024 | 2024-10-31 | 0 | < 15 Days | akatariya@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0149 | Rejected |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 05. OTC IP 11. Technology | vprashantpotphode@deloitte.com | [11 empty] | Automated BP Roles Assignment | Add automated BP role extension to new Payers as they move from MDG to CFIN. Changes needed: Implement BADI PARTNER_UPDATE in CFIN to automatically create Credit & Collection roles when a payer is created having specific account group | When a Payer is created in MDG and lands in S4/CFIN, the below roles should be extended automatically: Credit Management Collections Management Rationale: If payer role extension is manual, there is a risk that customer set-up will not be completed accurately, leading to overall delay in downstream processes (invoicing customers, credit checks, collections process) Manual payer set-up will be a new process. As a result, additional steps and time required to prevent or mitigate incorrect role extension This is a current OOB functionality available; loss of functionality in ECC today |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0149_OTC%20IP,IF%20-%20Automated%20BP%20Role%20Assignment.pptx?d=w32f8ffdabadb434daf57b571b7ee8b50&csf=1&web=1&e=W7QiEo |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 |  |  | 30 | [10 empty] | 0 | 0 | Configuration | No |  | 0 | N/A |  | OTCE0614_IP, OTCE0614_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0614 | 1 | OTCE0614 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-16 | 0 | 16. Cancelled by Requestor Tower | Yes | No | 2024-11-21 | o This CR is required to adhere to SOX compliance; alternative option is manual assignment of roles, but this option presents risks.  The technical effort is 80 hours of technical effort and is SAP approved. o AR: Include details regarding the original form and SAP notes, and update description to highlight that an additional BADI will be added to an existing enhancement. - @Awasthi, Akshay o AR: Clarify RICEFW status and whether FS has been completed; update slide to clarify whether 80 hours is total technical effort or is just for the BADI addition. - @Awasthi, Akshay o AR: Include in OSC/CL agenda. - @Tam, Anna @Deolalikar, Sagar |  |  | 2024-12-06 | • This Change Request is to automate the extension of two roles (Credit Management, Collections Management) to Payers created in SAP MDG upon movement to Central Finance (CFin). • This change is required to remain SOX compliant, and a program with custom table is required because the functionality doesn’t exist in S4 or CFin. o Note: this feature is currently available in ECC but is decommissioned, i.e., it is not available in S4. • The total effort is estimated at 110 hours, 80 technical and 30 functional. • SAP is aligned with the request. |  |  |  |  | Cancelled as a result of the approval of CR0891 | Build | CL/OSC | 2024-12-06 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-05 | 0 | < 15 Days | matthfisher@deloitte.com |  | No | CR Complete | No Objects |  | N/A | Yes
|  | INT-CR0150 | Cancelled |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | Low | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR 04. OTC IF 09A. Master Data | Akshatha R | [11 empty] | FPRE0574 - Margin Analysis Custom Characteristics addition | Operating Concern is to be updated with Custom Characteristics created in Custom Fields and Logics - Market Segment. This is part of additional COPA characteristics needed by business for tracking Tech node, End Customer and WBS fields | Development team need to re-design the development they did already for creating custom characters in COPA. Custom fields need to be created with value help and 16 new CDS views for Value Help and re-publish 6 custom fields again. Hence, Development Team need a CR to complete this activity. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE23D815C-2A68-4C47-ADE1-38D5DD971F15%7D&file=INT-CR0119_FPR%20IF%2CIP_CR%20Deck_Custom%20profitability%20dimensions%20creation.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 27 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Prabesh that the changes have been completed in R1 already. Therefore, cancelling CR. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 0 | < 15 Days | akshatr@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0151 | Cancelled |  | ERP | R2 (Release 2) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF 06. PTP 09A. Master Data | Mubashir Ghazi | [11 empty] | DATC0068 - Material master long description | Materials with description more than 40 Char are stored in Basic data long text. Currently there is no capability to extract and load long text through conversion program - DATC0068 | The extraction and load logic has to be incorporated in the conversion program |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0151_Material%20Master%20Long%20Description_R2.pptx?d=we9a5d9078cbe438daa838cca7a72bd79&csf=1&web=1&e=Gdyt9E |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-07 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0152 | Cancelled |  | ERP | R2 (Release 2) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology 15. Cutover | [12 empty] | Assignment of batch characteristics during batch master upload | 28 batch characteristics are in scope for R2 . batch master upload program today is only creating the batch master. Need to enhance the program to assign batch characteristics | Manual assignment of batch characteristics to the batches is cumbersome process and prone to errors. The extraction and load logic has to be incorporated in the conversion program |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR0152_FTS_IF_Assignment%20of%20batch%20characteristics%20during%20batch%20master%20upload.pptx?d=w37fded8aa7d049dfb7265f160fb48228&csf=1&web=1&e=0ffI1n |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | 11/14 - Team confirmed that this activity will be manual for R2. Therefore, the CR is cancelled. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-07 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0153 | Cancelled |  | ERP | R2 (Release 2) R3 (Release 3) | Medium | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | Bobby Saha | [11 empty] | Release needs to be changed from R2 to R3 | Release have been marked incorrectly to R2, it needs to be changed to R3 | Release have been marked incorrectly to R2 in the build plan and in the object tracker they are marked as R3 due to which the data is not getting reconciled as a result correct status is not getting reflected in the object tracker. |  | Yes |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | OR-140-050 |  |  | 4 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | 11/13 - Working with the team offline to correct changes in the build sprint plan and object tracker. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-08 | 0 | < 15 Days | bobsaha@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0154 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Realignment on table usage | As part of FS PTPE0543,PTPI0136/37 and PTPI0134/35 there is a realignment on table usage which requires Discarding ZTPTP_CONFIG_FIX table and Leveraging table ZTPTP_PARAMS instead since same functionality can be achieved using this table and additional table need not be created and maintained. | Since same functionality as be achieved using a existing table (ZTPTP_PARAMS) no need to create and maintain additional table (ZTPTP_CONFIG_FIX) |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-08 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0155 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | ysdeshpande@deloitte.com | [11 empty] | Realignment on table usage | As part of FS PTPE0543,PTPI0136/37 and PTPI0134/35 there is a realignment on table usage which requires Discarding ZTPTP_CONFIG_FIX table and Leveraging table ZTPTP_PARAMS instead since same functionality can be achieved using this table and additional table need not be created and maintained. | Since same functionality as be achieved using a existing table (ZTPTP_PARAMS) no need to create and maintain additional table (ZTPTP_CONFIG_FIX) |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This CR is a duplicate of CR0154 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0156 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Mohit Moreshwar Fating | [11 empty] | Descope of L3 DC-050-610B Define a Budget | L3 DC-050-610B Define a Budget will no longer be needed as per the discussion with Dassian (IFL) team | The decission to descope this L3 was taken in one of the working session with Dassian team |  | No |  |  |  |  | 1. Process Scope / Design Change | DC-050-610B |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-13 | Sent for offline approval | [9 empty] | Design | Tower | 2024-12-13 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-08 | 0 | < 15 Days | mmoreshwarfating@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0157 | Cancelled |  | ERP | R2 (Release 2) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | mshabaz@deloitte.com | [11 empty] | Material Master- MC1 Changes in Conversion Program | Changes identified in R2 MC1 for Material Master Conversion | This CR is required to track changes in Material Master Conversion |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | MDM-120-190 |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Moved to FS/Build CR log as the total effort hours is just 16 hours. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-11 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0158 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | High | 11. Technology | 11.3 Technology - Middleware |  | 12. Infrastructure | Divya Bajaj Kumar | [11 empty] | MuleSoft Interface updates for DBAAS and PAM changes | MuleSoft interface changes (technical in nature) in all the developed interfaces for R1,R2 and R3 to accommodate changes caused by the common usage of DBaaS (used for B2B support) and PAM (password access management)services | New password access management facilitating secure and compliant access to boundary system connection credentials and architectural changes to mitigate DBaaS service limitation to support proposed volume of transactions for IAO. This is impacting all the objects developed already for R1, R2 and R3 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Technology/INT-CR1058_MuleSoft_CR%20Deck_DBaaS%20and%20PAM%20changes.pptx?d=w03ef49f6f0874b00bcf1eaa576ef86e7&csf=1&web=1&e=eAyjFL |  | 8. Non-Build Infrastructure-related Change |  |  |  | 384 | 0 | [8 empty] | 384 |  |  |  |  | 0 | 384 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-12-20 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-11-12 | Reviewed in ERP Huddle with Mike on 11/14 |  |  | 2024-11-14 | [6 empty] | Other | CL/OSC | 2024-11-14 | 11, 2024 | 11, 2024 | 11, 2024 | 2024-11-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0159 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | High | 11. Technology | 11.3 Technology - Middleware |  | 12. Infrastructure | divya.bajaj.kumar@intel.com | [11 empty] | MuleSoft Interface updates for MuleSoft version 4.4 to 4.6 & Java 8 to 17 changes | MuleSoft will be phasing out support for Java 8 and will only support Java 17 going forward, Therefore as per recommendation from Intel MuleSoft platform team all previously developed MuleSoft applications for IAO program, need to upgrade with new MuleSoft runtime for 4.6 and should use Java 17 version before go live. This is impacting all the objects developed already for R1, R2 and R3 release. | This change is crucial for enhancing business value by mitigating the risks associated with deploying and operating MuleSoft applications on unsupported versions of Java and the MuleSoft server in the production environment. By ensuring that our MuleSoft applications run on supported versions, it improves Security , Enhances Performance , Ensures Compliance , Reduces Downtime and Leverage New Features. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC5108018-7E77-4601-A04B-86B31DDE46DF%7D&file=INT-CR1059_MuleSoft_CR%20Deck_MuleSoft%204.4%20to%204.6%20%26%20Java%208%20to%2017%20Upgrade.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 198 | 0 | [8 empty] | 198 |  |  |  |  | 0 | 198 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 41 RICEFW's | 1 | 41 RICEFW's | 1 |  | 0 |  | 0 | N/A |  | 2024-12-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-12 | o Infrastructure changes are being done in the background. All non-Deloitte interfaces are already in the works for the update.  No impact to teams outside of the testing. The team will prioritize R1/R2 objects. o Any new object being built will be built on the new platform. Only existing RICEFW’s will be moved. | [9 empty] | Build | Tower | 2024-12-12 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0160 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 11. Technology | Prabesh Acharya | [11 empty] | Enhancement to identify the PO line items between Accruals and Prepaids | Enhancement to identify the PO line items between Accruals and Prepaids | The current PO setup at Intel doesnt have any indicator to identify the line items within a PO as accrual or prepaid. Since the prepaid and accrual in the fiori dashboard has separate process defined for accruals and prepaids, it is required to identify the line items within a PO as accrual or Prepaid. This enhancement will enable the users to identify the lines in a PO appropriately which can be used later in the fiori dashboard. Impacted additional RICEFWs FPRE019, FPRE0322, FPRE0320, FPRE0321 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0160_%20Enable%C2%A0PO%20owners%20to%20classify%20PO%20line%20items%20as%20either%20a%20Prepaid%20or%20Accrual%20to%20enable%20the%20corresponding%20process%20in%20PAT%20tool.pptx?d=w3adc3c990f7b462c8564095927292fb1&csf=1&web=1&e=CpqsFG |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-030-020 |  |  | 150 | 0 | [8 empty] | 290 |  |  |  |  | 0 | 290 | Tech - S/4 | No |  | 0 | N/A |  | FPRE0322_IP, FPRE0322_IF, FPRE0321_IP, FPRE0321_IF, FPRE0320_IP, FPRE0320_IF, FPRE0319_IP, FPRE0319_IF | 8 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0319_IF, FPRE0320_IF, FPRE0321_IF, FPRE0322_IF, FPRE0319_IP, FPRE0320_IP, FPRE0321_IP, FPRE0322_IP | 8 | FPRE0319_IF, FPRE0320_IF, FPRE0321_IF, FPRE0322_IF, FPRE0319_IP, FPRE0320_IP, FPRE0321_IP, FPRE0322_IP | 8 |  | 0 |  | 0 | N/A |  | 2026-04-20 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-11-21 | o This change request is to add in liability accrual and prepaid expense into the PAT Tool.  The functionality was originally a placeholder in an approved KDD; pre-payment needed to be designed. Ariba couldn’t support the needed capabilities. o Total technical effort is 150 hours, and it will be used to build the front end application. o AR: Include brief details of original KDD and enhancement. - @Acharya, Prabesh o AR: Include in OSC/CL agenda. - @Tam, Anna @Deolalikar, Sagar |  |  | 2024-11-22 | Approved to continue with work | [5 empty] | Build | CL/OSC | 2024-11-22 | 11, 2024 | 11, 2024 | 11, 2024 | 2024-11-13 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No | FUT Not Started | No Objects |  | In Progress | Yes
|  | INT-CR0161 | Cancelled |  | ERP | R1 (Release 1) R2 (Release 2) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Kushal Maheshwaram | [11 empty] | FA should not be read through the Cost Center while posting transaction from ECC to CFIN | FA should not be read through the Cost Center while posting transaction from ECC to CFIN | The current logic is validating the functional area at cost center level which is picking the FA as is. The change is to fix the validation for the FA where it should not read through cost center. |  | No |  |  |  |  | 3. Configuration Change | DC-010-100, DC-010-090 |  |  | 9 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | 11/13 - Confirmed by Prabesh that the changes have already been made in R1. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-13 | 0 | < 15 Days | kmaheshwaram@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0162 | Approved | 50 hours of configuration effort | ERP | R2 (Release 2) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Statement of Equity | Upload and generate QTD and YTD Statement of Equity in SAP Group Reporting | The reports needs to show the following • Initial capital at the start of the period • Include any additional contributions • Incorporate net income • Subtract owner's withdrawals • Calculate the ending capital balance. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0162_R3%20Statement%20of%20Equity%20QTD%20Report.pptx?d=wdc785d02eb024b00b1256b6c9104c5ac&csf=1&web=1&e=xrPefn |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 50 | [5 empty] | 0 | 50 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-11-21 | o This CR will only require functional configuration, and FPR team confirmed that they will be able to ingest the work. Approved to continue with work | [9 empty] | Other | Tower | 2024-11-21 | 11, 2024 | 11, 2024 | 11, 2024 | 2024-11-14 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0163 | Cancelled |  | ERP | R1 (Release 1) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Non-GAAP report | Ability to manually upload Non-GAAP report numbers from RT/NRT to GR table and generate Non-GAAP PnL report. | The reports needs to show the walk from GAAP to Non-GAAP. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0163_R1%20Non-GAAP%20Report.pptx?d=wecaca2feb2224fb48eeb9b7f815710c9&csf=1&web=1&e=Xxh8Xb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR confirmed by Rafael, Shane, and Prabesh to be not needed. The team solutioned a different logic that required significantly less complexity, and the technical changes will be less than 40 hours of effort. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-14 | 0 | < 15 Days | kdey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0164 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 01. PMO 07. FTS IF | iathar@deloitte.ca | [11 empty] | Addition of L3s in Exception Topic for Design Sprint 10 | Need to add 3 L3s in Design Sprint 10 under OeS4 Exception Topic L-060-030 - Receive Material from Production or Receiving (OeS4) L-060-050 - Create Transfer posting for Intra-Facility Transfer (OeS4) L-060-080 - Confirm Material Receipt by Requester (OeS4) | Need to add 3 L3s in Design Sprint 10 under OeS4 Exception Topic L-060-030 - Receive Material from Production or Receiving (OeS4) L-060-050 - Create Transfer posting for Intra-Facility Transfer (OeS4) L-060-080 - Confirm Material Receipt by Requester (OeS4) |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-13 | Sent for offline approval | [9 empty] | Design | Tower | 2024-12-13 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0165 | Cancelled |  | ERP | R2 (Release 2) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 10. Analytics | sjulury@deloitte.com | [11 empty] | Additional fields in DS FTSFV011 for CATTS requirement. | Need to add Additional field for Handling Unit type from table /scwm/ordim_c field LETYP. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This CR is less than 40 hours of technical work. Therefore, it has been moved to the Build CR log as CR0091. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0166 | Approved | 50 hours of configuration effort | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Cash Flow Statement | Ability to manually upload and generate YTD and QTD external reporting and managerial cash flow statments. | The current report being developed is a YTD view consistent with the external reporting presentation. However, due to themanual inputs needed and the managerialpresentation with lower-level detail that needs to be reconciled with the external view, the reports needs to show both a QTD and YTD view. The team manages manual inputs using QTD values and uses formulas to determine YTD. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE0EB2628-7763-4810-87E6-435E399EA98A%7D&file=INT-CR0166%20R1%20Statement%20of%20CF_QTD_YTD_Report.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 50 | [5 empty] | 0 | 50 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-11-21 | o This CR will only require functional configuration, and FPR team confirmed that they will be able to ingest the work. Approved to continue with work | [9 empty] | Other | Tower | 2024-11-21 | 11, 2024 | 11, 2024 | 11, 2024 | 2024-11-21 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0168 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 06. PTP 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology | Sekhar Lingam | [11 empty] | IP to IF Turn-key Order Process | Implement turnkey order placement model between Intel Products and Intel Foundry for Fab thru AT stages. 11 L3s and 14 RICEFWs need to be revisited across FTS-IP, PTP and Logistics towers. | Support the turnkey ordering model accommodating Intel Foundry manufacturing network and processes |  | Yes |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/10.%20Change%20Requests/Sprint%209/FTS-IP%20Change%20Request%20%E2%80%93%20IP%20to%20IF%20Turnkey%20Order%20Placement.pptx?web=1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 200 | 0 |  |  | 80 | [5 empty] | 200 |  |  |  |  | 0 | 200 | Data Migration Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | PTPI0144_IP, PTPI0144_IF, PTPI0138, PTPI0136_IP, PTPI0136_IF, LOGI0267, LOGI0156, LOGI0155, LOGI0154, FTSC0434, DATE0926_IP, DATE0926_IF | 12 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSC0198_IP, FTSC0424_IP, FTSC0434, FTSI0268_IP, FTSI0491, FTSE0592_IP, FTSI0725, PTPI0136, PTPI0138, PTPI0144, LOGI0267, LOGI0154, LOGI0155, LOGI0156, DATE0926_IP, DATE0926_IF | 16 | FTSC0198_IP, FTSC0424_IP, FTSC0434, FTSI0268_IP, FTSI0491, FTSE0592_IP, FTSI0725, PTPI0136, PTPI0138, PTPI0144, LOGI0267, LOGI0154, LOGI0155, LOGI0156, DATE0926_IP, DATE0926_IF | 16 |  | 0 |  | 0 | N/A |  | 2025-10-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-12-05 | Approved by OSC/CL |  |  | 2024-12-05 | Approved to proceed with work | [5 empty] | Build | CL/OSC | 2024-12-05 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-20 | 0 | < 15 Days | parthakker@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0171 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 04. OTC IF | Sathyanarayanan Dhandapani | [11 empty] | Interface from Sales Force to S4 to read the Business Rules | Developing an interface from Salesforce to SAP S4 is currently mapped under B App, this need to be worked upon by S/4 Team | Developing an interface from Salesforce to SAP S4 is currently mapped under B App, this need to be worked upon by S/4 Team. RICEFW to be submitted as part of IAO and taken up for further approvals and development |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B74756471-E309-4942-B733-779D53A986C6%7D&file=Return%20Console_IP_R-190-010_Interface%20from%20SF%20to%20read%20the%20business%20rules.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR is not required as the RICEFW goes through the intake process. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-22 | 0 | < 15 Days | sadhandapani@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0172 | Cancelled |  | ERP | R1 (Release 1) | Medium | 03. FPR |  |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | 3 ECA Reports - R1 exception objects | 3 ECA Reports - R1 exception objects - FPRXV010 - 10Q Cost Consolidations Details HANA, FPRXV011 - 10Q Depreciation Consolidations Details HANA & FPRXV012 - 10Q Rollforward - Consol GL Balance Report | R1 exception objects |  | No | [5 empty] | DC-040-120 |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as reports are FUT approved |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-22 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0173 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP | Susan Strathman | [10 empty] | WIINGS | ISTART Pega (IAPM ID 37517): Change TIME from Migrate to Tolerate | Requesting TIME Category change from Migrate to Tolerate for IAPM ID 37517 ISTART Pega Work Flow |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_ISTART%20Pega%20IAPM%2037517_%20DRAFT%20WIP.pptx?d=w8687947ad2bc4f7fa6427a0372c1fc02&csf=1&web=1&e=SlyYWT |  | 1. Process Scope / Design Change |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-12-19 | Presented to OSC/CL directly |  |  | 2024-12-20 | • iStart is the system of record that connects with WIINGS today (where Pega is behind the scenes sending signals back and forth between the warehouse and either a supplier, a supplier planner, or someone in AP) as we try to disposition any number of exceptions at receipt. o The signal back could be saying to scrap the material, move it, return it under a different PO, etc. • The team worked with SAP to find solutions within SAP for this, but they’re all expensive and highly customized. o Deloitte’s guidance is that best known practice is a custom solution here. | [5 empty] | Design | CL/OSC | 2024-12-20 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-22 | 0 | < 15 Days | lisa.honeycutt@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0174 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 03. FPR 04. OTC IF 07. FTS IF | Lilibeth Lejarde | [11 empty] | Cross-Site Manufacturing | New Items and BOM Levels (appr. 3-5) to support FTS to accurately generate manufacturing and transportation schedules. This is needed when there is a planned flow that requires two sequential plants to complete a stage | This is a new requirement from FTS-IF. Without this, IF cannot do a proper capacity check and and will not be able to accurately commit to customers |  | No | [5 empty] | M-150-200 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this topic was discussed as a December FTF topic, and next steps were aligned. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-23 | 0 | < 15 Days | llejarde@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0175 | Cancelled |  | ERP | R2 (Release 2) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF | akashx.kambli@intel.com | [11 empty] | Change the execution Logic to update new Batch fields within SAP S/4 and mapping in Mulesoft. | The Change request is raised to update the mapping to new fields in S/4 Batch. After Triggering a WAYBILL XML from MPL, Mulesoft & Tech team will update the logic to complete the new mapping requirement in S/4 system. | Intel IT gave new mapping for Batch characteristics which requires Updating the Integration logic of WAYBILL XML triggered to Mulesoft & SAP S/4. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR0175-%20FTS_IF_Change%20in%20Execution%20logic%20to%20rename_update%20Batch%20Characteristics.pptx?d=w1270dd48698548fd959aef42ded98e2e&csf=1&web=1&e=kSHaPM | [5 empty] | 27 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR was less than 40 hours of effort. And the CR has been moved to the Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0176 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 13. Security 16. Testing | Amith Vallabhaneni | [11 empty] | GRC Business Role Management (BRM) Workflow Change | The proposed change in the SAP GRC BRM module workflow for managing task roles involves moving the role owner approval to occur immediately after defining the role, before maintaining authorizations. | This change is requested in order to ensure that the role owner reviews and approves the role definition before authorizations are maintained and access risks are analyzed. Currently, the role owner approval occurs later in the process, which can lead to delays and potential rework if the role owner is not aligned to the change to begin with |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT-CR0176_Security_CR%20Deck_BRM%20Workflow%20Change.pptx?d=wf671ddb061954f88981fbffdc4bf4841&csf=1&web=1&e=CwWufa |  | 1. Process Scope / Design Change |  |  | Low | 60 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-12 | o The Deloitte security team is ingesting the work and will build the workflow. The rollout will be for Release 1 with no impact to other security deliverables; it will be brought into UAT2, and the testing will be done by the security team  There will be no impact to other teams as the assignment of roles is not dependent on this change. | [9 empty] | Design | Tower | 2024-12-12 | 12, 2024 | 12, 2024 | 11, 2024 | 2024-11-25 | 0 | < 15 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0177 | Rejected |  | ERP | R1 (Release 1) | Low | 13. Security | 13.6 Security - Cyber/ Controls |  | 13. Security 16. Testing | Amith Vallabhaneni | [11 empty] | Additional CCM Controls | The proposed change involves adding additional automated controls leveraging GRC Continuous Control Monitoring (CCM). Initially, we had defined 14 ITGC controls in design, and the request is to add 5 additional controls to enhance monitoring and compliance.​ | The rationale for this change is to enhance monitoring and compliance by increasing the number of automated controls through GRC Continuous Control Monitoring (CCM).​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT-CR0177_Security_CR%20Deck_Additional%20CCM%20Controls.pptx?d=w93dad9af729e44d6ab28eb49345c40d1&csf=1&web=1&e=TlSoB9 |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-12-12 | [9 empty] | Cancelled as the technical effort is less than 40 hours. Therefore, the CR will be moved to the Build CR Log. | Design | Not Assigned |  | Not Approved | 12, 2024 | 11, 2024 | 2024-11-25 | 0 | < 15 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0178 | Rejected |  | ERP | R1 (Release 1) R2 (Release 2) | High | 13. Security | 13.2 Security - Cyber/ App Security |  | 12. Infrastructure 13. Security 16. Testing | Amith Vallabhaneni | [11 empty] | GRC Landscape Strategy Change | In the current landscape strategy (slide 3), Production GRC provisions to all SAP systems (both production and non-production). ​ The proposed change in the landscape strategy involves modifying the provisioning process such that non-production GRC will provision only to non-production SAP systems, while Production GRC will provision exclusively to production SAP systems (slide 4). This change aims to segregate the provisioning responsibilities to enhance system management and security. | The rationale for this change is to enhance system management and security by segregating the provisioning responsibilities between production and non-production environments​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT-CR0178_Security_CR%20Deck_GRC%20Landscape%20Strategy%20Change.pptx?d=w11832cade5b54e71b6fdc8b7a8176dc9&csf=1&web=1&e=bUxyQw |  | 8. Non-Build Infrastructure-related Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-01-20 | [9 empty] | Cancelled as the technical effort is 10 hours, which is less than 40. It has been aligned with the tower and horizontal leads, and it has been approved in the Build CR Log | Other | Not Assigned |  | Not Approved | 01, 2025 | 11, 2024 | 2024-11-25 | 0 | < 15 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0179 | Cancelled |  | ERP | R1 (Release 1) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | Prabesh Acharya | [11 empty] | Sort Load ready files in BODS & Improve extraction Criteria for Cost Center | Sort the GL account (SKB1) and split the load ready files and Improve criteria for Cost Center extraction | 1. During GL account validation, it’s difficult which load file contains the specific GL account, making it difficult to perform validation 2. Transformation & Reconciliation between ECC and S/4 will help during data conversion short timelines. 3. Improve Cost Center extraction criteria and defect fixes. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0179_Sort%20Load%20ready%20files%20in%20BODS%20%26%20Improve%20extraction%20Criteria%20for%20Cost%20Center.pptx?d=wcc7e729638b7491190bdb832607b4f47&csf=1&web=1&e=8RiAKm |  | 7. Non-Build Data Conversion Changes |  |  |  | 38 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-27 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0180 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 09A. Master Data 09B. Data Migration | Prabesh Acharya | [11 empty] | Company code move to difference S4 instance 606/604/622/645/405/879/429/735/736/756/334 | 1. Company code 606 – to be added to IP box and AA S4 is required to be set up. 2. Company code 604/622/645/405/879/429/735/736/756/334 – to be deleted from IP and keep them available in CFIN only. | Legal Entity – 606: R3 (addl. work) Legal entity 606 (Mobileye) is a non-integrated entities maintained in CFIN only. However, asset ledger will be required to manage intangible assets under 606. Asset ledger is not available in CFIN, thus, it needs to be set up in IP to leverage asset ledger. Legal Entity –604/622/645/405/879/735/736/756/334: R3 (less work) Currently designated as IP entities, they are on liquidation roadmap and only need to be in CFIN for liquidation capability. With R3 being pushed out, LE COE team now has more confidence to close these legal entities before R3. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0180_Company%20code%20move%20to%20difference%20S4%20instance%20(606,604,622,645,405,879,429,735,736,756,334).pptx?d=wc4323ff119924a1ca5ee14bd817b0a17&csf=1&web=1&e=s3FiTA |  | 3. Configuration Change | DC-020-010 |  |  | 35 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is less than 40 hours of technical effort; approved by Shane | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-27 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0182 | Cancelled |  | ERP | R2 (Release 2) R3 (Release 3) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 09B. Data Migration | R Prem Siddharth | [11 empty] | Logic Change in the FS for RICEF OTCC0231 | Extraction logic change in the conversion Program for Transferring License data from Legacy system to SAP GTS E4H |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by GTS team that this can be cancelled as it is not required. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-28 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0183 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Realignment for Table usage | INT-Build-CR0080 | Discarding ZTPTP_CONFIG_FIX table and Leveraging table ZTPTP_PARAMS instead since same functionality can be achieved using this table and additional maintenance for table is not required |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0184 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Deepanshu Lnu | [11 empty] | Restrict commit from E2Open | INT-Build-CR0099 | As per existing logic- SAP should restrict the commit from E2OPEN once the DCI box is checked. But now the requirements is even the DCI box is checked still , S4 should allow commit till the under and over tolerance limit. which will require the code changes. 2 - We have dependency on ASN signal to adjust the commit in PO. hence the validation should be incorporated to restrict the PO and po line item commit ,if there is a failure of ASN for that particular combination, which again require the extra validation on this interface. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0185 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Ramagiri Pradeep Kumar | [11 empty] | Structure change in the existing Routing table. | INT-Build-CR0090 | Existing Routing table need to split into two. Creation of New DH table. Updating the existing routing table. Updating the mapping sheets for all the outbound interfaces. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0186 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Ramagiri Pradeep Kumar | [11 empty] | Change in the approach of sending AS2 Header details | INT-Build-CR0069 | AS2 header details will no longer be part of custom idoc segments. AS2 header details will be added to XML payload which will be sent out to MuleSoft from S4 system. To add the AS2 header details to XML BADI: IDOC_XML_ENVELOPE_OU will be used. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0187 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Philip Chun Hong Ng | [11 empty] | Remove AIF functionality and Download payload in JSON | INT-Build-CR0066 | Below changes are required : 1. Remove AIF functionality for this RICEFW 2. Add capability to download the payload in JSON format into local PC Rationale: Production support team would need the functionality to download the payload files in case of any failures, also AIF functionality need to be removed for this RICEFW |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0188 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Requirement to change attribute/technical field name | INT-Build-CR0054 | Requirement to change technical field name from "CUSSADD" to "CUSADD" in outbound IDOC ORDERS05 from S/4 to E2open to make sure all of the fields with this attribute name/technical field name are aligned across Middleware and as per E2open Xpath. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Technical effort was less than 40 hours. Approved in the Build CR log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-03 | 0 | < 15 Days | ryapark@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0199 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology 12. Infrastructure 17. B-App | shane.bethune@intel.com | [11 empty] | Descope I rates from Mulesoft to MDG and NAS Drive. | I rates code for MDG and NAS Drive should be removed from the interface. | UK was using this rate for Conversion in BCS for consolidation purposes, UK has moved on from GBP to USD and hence I rate is not needed anymore. The team will be using M rates for reporting purposes. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0199%20Descope%20I%20rates%20from%20Mulesoft%20to%20MDG%20and%20NAS%20Drive.pptx?d=we013232f40f14376b19d262c588b9223&csf=1&web=1&e=sKyCxD | [5 empty] | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-04 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0200 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology 12. Infrastructure 17. B-App | shane.bethune@intel.com | [11 empty] | Mulesoft to Round up 5th decimal while sending .Out file (MDG data) to NAS Drive for TR suite | Mulesoft to append the code to include logic for rounding up to 5 decimal places only while sending file from MDG to NAS Drive. | Reconciliation of the rates in TR suite is off due to the fact that SAP can only consume upto 5 decimal places while creating the .out file it is being sent for 6 decimal places. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0200%20Mulesoft%20to%20Round%20up%205th%20decimal%20while%20sending%20.Out%20file%20(MDG%20data)%20to%20NAS%20Drive%20for%20TR%20suite.pptx?d=w6d8264f8babf415482655e495afb9047&csf=1&web=1&e=WmMgIs | [5 empty] | 5 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-04 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0201 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 06. PTP 07. FTS IF | Ruben David Alvarez Carroz | [11 empty] | Reopen L3s for Gases/Chemicals | Reopen L3s for Gases/Checmicals Stream L3 Number L3 Description PTP L-060-110 Maintain Warehouse L-040-080 Record Receipt and label L-040-120 Putaway Destination Bin L-040-130 Stage apprpriate zone moves L-040-150 Transport porducts to storage L-040-160 Confirm/Adjust Location L-040-170 Record Stock Location FTS LO-160-010 Allocate Inventory to Shipments/Deliveries LO-160-020 Plan Daily Pick Flow LO-160-030 Consolidate Appropriate Pick Items LO-160-040 Generate Pick Tickets LO-160-050 Pick Order Items LO-160-070 Note and Record Exceptions LO-160-080 Confirm Quantity and Location Picked L-060-070 Manage Storage & Internal Movement of Inventory-Move/Deliver Materials | Gases/Chemicals was part of LE scope initally and discussion was closed with the LE process but upon further discussion during WIINGS ,direction was changed for it to be EWM managed. Hence these L3s need to reopen for further discussion for EWM processes. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0201_FTS_Reopen%20L3s%20for%20Gases%20%26%20Chemicals.pptx?d=w472ce30391d04919abc0ea3b872f6bd1&csf=1&web=1&e=dmoDbu |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-13 | Sent for offline approval | [9 empty] | Design | Tower | 2024-12-13 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-04 | 0 | < 15 Days | nramireddi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0204 | Rejected |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | [11 empty] | Consolidated packing list for Chengdu | A new RICEFW to be logged for the creation of Consolidated packing list form for Chengdu plant. |  |  | Yes |  |  | https://intel-my.sharepoint.com/:p:/p/paola_rodriguez/EVD0iQht8iBJhP_3IwGIWeMB97NaMsbVs7xJYJZcKp7mMw?e=VaFQHy |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2024-12-12 | [9 empty] | Cancelled as this needs to go through the RICEFW intake process instead | Other | Not Assigned |  | Not Approved | 12, 2024 | 12, 2024 | 2024-12-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0205 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP | Susan Strathman | [10 empty] | WIINGS | SCT Control Tower: Manage My Supply Line MSL GFM (IAPM ID 20386): Change TIME from Migrate to Tolerate | Requesting TIME Category change from Migrate to Tolerate for IAPM ID 20386 - SCT Control Tower: Manage My Supply Line-MSL GFM |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0205_B%20App_CR%20Deck_SCT%20Control%20Tower%20Manage%20My%20Supply%20Line%20MSL%20GFM%20IAPM%2020386_%20DRAFT%20WIP.pptx?d=we49e7f9e5cdc46a1823840f6e64ef9e9&csf=1&web=1&e=dOdYcJ |  | 1. Process Scope / Design Change |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-27 | o This change is to retro-fit 2 capabilities within the PEGA application that helps with communications and expediting / reconciliation.  Post-IAO, the team will have time to further refine the E2Open capability. o Full-stack developers are needed and will require $310K to build the React application on top of the HANA database. |  |  | 2025-02-28 | • Requesting TIME Category change from Migrate to Tolerate for IAPM ID 20386 – SCT Control Tower: Manage My Supply Line MSL GFM • There was a hope to eliminate this app but during WIINGs design sessions it was concluded that the app is still needed. o WIINGs design is still in progress. • Requesting a portion of this to continue for a portion of this work alive as tolerate. Machine Down open and Machi • It is anticipated there will be 1 API/1 RICEFW (to maximum of 3) as the integration point for this tool. • $310K Incremental Opex o Pega - 2 incremental CWs for 6 quarter at 16K/qtr. Starting Q3'25 o ECA - 1 SA, 1AD for 2 quarters at 20k/qtr. Start date not determined o Full stack developer - 17.k/qtr for at least 2 quarters. Start date not determined. o Denodo/Mulesoft - Pending Estimate due to difficulty estimating before design phase finalized. Current estimate 2 HC 16K/quarter for 2 quarters Approved by Rick Antonellis | [5 empty] | Design | CL/OSC | 2025-02-28 | 02, 2025 | 02, 2025 | 12, 2024 | 2024-12-05 | 0 | < 15 Days | lisa.honeycutt@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0206 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR | Jaime Sutton | [11 empty] | Asset Management Control Time category change | Time category change from Migrate to Tolerate | AMC is a system of record to track the assets of Intel Costa Rica to comply with Free Trade Zone local regulation (Procomer). There is fit / gap assessment for S/4 (slide 3) based on the following requirements: storing complete information on assets, asset physical tracking, keep record of fixed assets for US GAAP vs LOCAL GAAP, document attachment, asset scanning. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0206_FPR_Asset_Management_Control_Time_Category_Migrate_to_Tolerate.pptx?d=w57e7bec4cc694d328c8611a08cde190b&csf=1&web=1&e=0s6X3h |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 107 |  |  |  |  | 0 | 107 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-12 | o There is no connection to SAP. Therefore, no RICEFW’s are needed. o AR: Add in comments from SAP regarding the solution – Bethune, Shane o AR: Add in Boundary Apps impact from changing the category from “Migrate” to “Tolerate” (i.e. ECA data) - @Gerber, Kelly A | [9 empty] | Build | Tower | 2024-12-12 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-05 | 0 | < 15 Days | ying.nee.sim@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0207 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | iathar@deloitte.ca | [11 empty] | Correct L3 to be added under exception topic OeS4 under FTS IF - Logistics inplace of incorrect L3 | Correct L3 (L-060-130) to be added to exception topic OeS4 under FTS IF - Logistics in place of incorrect L3 (L-060-030) which is there in Design Sprint 10. L-060-130 - Manage Inventory Placement and Movement L-060-030 - Receive Material from Production or Receiving | L-060-030 was incorrectly given while uploading the design sprint 10 plan. In place of it, correct L3 (L-060-130) needs to be added. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-13 | Sent for offline approval | [9 empty] | Design | Tower | 2024-12-13 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0208 | Cancelled |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Soumik Sil | [11 empty] | Custom enhancement is required for trade customer and vendor for N:1 Mapping cardinality in CFIN | Currently we are using standard N:1 Mapping for Default Customer / Vendor. According to SAP recommendation we need to have custom enhancement for this mapping to avoid performance issue as system does various checks during the standard mapping |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-090 - CFIN Initial Load & DC-010-100 - CFIN Replication |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Prabesh as not required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-05 | 0 | < 15 Days | kmaheshwaram@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0209 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) R5 (Release 5) | High | 13. Security | 13.1 Security - ALL |  | 13. Security 17. B-App | vkanderi@deloitte.com | [11 empty] | Change Order – to Non ERP Security and Controls SOW | This change request outlines the change in timelines for the non-ERP security and controls design deliverables with respect to ERP program timelines |  |  | Yes |  |  | https://secure-web.cisco.com/10ThmvLeg19OXmQE6cwwJq1wafLopzVHfdeYIa6glU5LPu5Urip1KBPvCt3nvQhCE3sWTuub-kzuL8zvI5Ki9XoP-QHGuwOoL8ZBwt322Ett55QDeHai2489I7nR7_bO3J-0a60K08mq61DgiNTUsxi1VG0TRpQSWk6mir3RA_fgorP2XbVBJ7H60OnqLl8wcJIQVCwV8uiSXj045FcWXWUF0nBEllM3WZ9fyQRL9PbeN_KnNZCEa8BH0bsk3bek9Q2qjAT46OGsf8DMvdd965m97kGyyrmvsbFPiN3KGr7DiubzdHNTM7FfjtPZCy8HfA-TpDrK-WDpaPCGFTHMSXimomToSdia6CrPj7aUM0GaZI-6N_pg3cRUQLeIf4hIivqkZy_4L439wYS9js4VZ9SFWEWbRJrl7KAtIBxzV344vZNotF4VRrEoFeZ5aXKO_6OYn7BE1a0fHIzrc8ALzbzy83cmKvDaZ_xWYTXEz1TNNx6R-v3tLyaz1hsKzrnEq/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F01.%2520PMO%2F05.%2520Scope%2520and%2520Change%2520Control%2FChange%2520Control%2FChange%2520Request%2520Decks%2FSecurity%2520%2526%2520Controls%2FINT-CR0209%2520-%2520Change%2520Order%2520to%2520Non-ERP%2520Security%2520and%2520Controls%2520SOW.pptx%3Fd%3Dw71c7c17277f4487e8bb5fc932da45519%26csf%3D1%26web%3D1%26e%3Dj48v8i |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-19 | o CR is aligned with Boundary Apps and Supply Chain Planning timelines, but milestone payment dates will be updated.  Raj will follow up with the procurement team, and the integrated plan will be updated. | [9 empty] | Other | Tower | 2024-12-19 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0210 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR | kevin.m.johns@intel.com | [11 empty] | Add SAP HR License to support Federal timekeeping processes | Add SAP HR License (~$150k + ~$26k yearly Maintenance) to support Federal timekeeping processes supporting Planned working time (Infotype 0007) and default value for timesheets (infotype 315) | We utilize these capabilities today in ECC, however are not part of our license agreement with SAP. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Federal%20SAP%20Planned%20Working%20Time%20and%20Default%20Value%20for%20timekeeping.pptx?d=w355c033ebe5142fc8b4daf34ea0eb964&csf=1&web=1&e=bR9f1H |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-12-05 | Approved by OSC/CL |  |  | 2024-12-05 | Approved to proceed with work; Chris and Kevin to work through related CR/KDD and present other Infotype options to OSC/CL on WW50 | [5 empty] | Other | CL/OSC | 2024-12-05 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-06 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0211 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 03. FPR 04. OTC IF 11. Technology 17. B-App | Praveen Kumar Muppala | [11 empty] | Revenue by stage | Load material stage wise pricing in ZREV pricing condition in S4 from SAC | FPR will need revenue by stage for accounting posting. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0211_OTC%20IF_CR%20Deck_Changes%20to%20SAC%20To%20S4%20Pricing_OTCI0442_Revenue%20By%20Stage.pptx?d=w7634f85725b04983a5b0906e0a7402e7&csf=1&web=1&e=L0WdgU |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 30 | 0 |  |  | 7 | [5 empty] | 30 |  |  |  |  | 0 | 30 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0442 | 1 | OTCI0442 | 1 |  | 0 |  | 0 | N/A |  | 2025-02-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-18 | Approved within ad hoc meeting with OTC leadership and Uzma | [9 empty] | Build | Tower | 2025-02-18 | 02, 2025 | 02, 2025 | 12, 2024 | 2024-12-06 | 0 | < 15 Days | pmuppala@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0213 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | Rea Meyer | [11 empty] | FPRC0260 GR Historical Data loader - opening balances data load | Opening balances (period 0) data load need to be loaded as part of historical data loader for reporting accuracy of reports where opening balances is needed like OCI. All the existing transformation logics applies to period 0 file transformation and in addition the subitem field needs to be defaulted with “900“ ​ ​ | For reporting accuracy dependent on historical opening balances.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0213_R1_GR%20Historical%20data%20loader.pptx?d=w50439e16583f45c0a5b1adc56acbeea0&csf=1&web=1&e=W4KQnr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 15 | 0 | [10 empty] | 15 |  |  | 0 | 15 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRC0260 | 1 | FPRC0260 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-12 | o This is a BODS change that will be a part of the R1 MC3. Tech team and conversion team are aligned to making the change. | [9 empty] | Build | Tower | 2024-12-12 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-09 | 0 | < 15 Days | kkrishnatulasi@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0214 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR 10. Analytics | Subramani . | [11 empty] | Ingestion of Tables in ECA for CO Transaction Reconciliation Report | Ingest below tables in ECA for building CO Transaction Reconciliation report: AUFK - Internal Order data (ECC) PRPS - WBS Element (ECC) | Tables AUFK and PRPS are added to the logic to fetch the Cost object and Profit Center in the ECA report for CO Transaction Reconciliation. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0214_Ingestion%20of%20Tables%20in%20ECA%20for%20CO%20Transaction%20Reconciliation%20Report.pptx?d=w76fcea7067c04a16adb7efab535aeb4a&csf=1&web=1&e=aFSgVE |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 27 | 0 | [9 empty] | 27 |  |  |  | 0 | 27 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV035, FPRXV036 | 2 |  | 0 | FPRXV035, FPRXV036 | 2 |  | 0 | N/A |  | 2025-06-02 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-01-09 | Approved offline by Sunil and Uzma | [9 empty] | Build | Tower | 2025-01-09 | 01, 2025 | 01, 2025 | 12, 2024 | 2024-12-09 | 0 | < 15 Days | subramani@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0215 | Approved | 1/27/25 - Confirmed with Subhajit that it is aligned with Ranju and PEGA team that they will make the necessary changes to the ECM API endpoints and associated payload to call PDM translator. Approached is aligned with Kunal, Jayant, and Candi as well. Assumption is that there will be no impact to PDM transistor. | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP | Susan Strathman | [10 empty] | WIINGS | SCT Control Tower: Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI (IAPM ID 17296): Change TIME from Migrate to Tolerate | Requesting TIME Category change from Migrate to Tolerate for IAPM ID 17296– Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0215_B%20App_CR%20Deck_PSI_Pega%20IAPM%2017296_DRAFT%20WIP.pptx?d=w28b7a93cbe534d828dff01666c0d5276&csf=1&web=1&e=9dSqQg |  | 1. Process Scope / Design Change |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-12-19 | Presented to OSC/CL directly |  |  | 2024-12-20 | • To enable, the work is relatively simple, updating flows for all the necessary attributed. The requirement is one CW for 2025 at an estimated $64K. o There will then be a signal coming to SAP from Pega for PSI items and ECM for everything else. • There is no change to the inbound SAP interface; it will be the same interface used for ECM. No RICEFWs are required to achieve. • Though no changes were anticipated to the PLM translator to support this, it’s possible that moving to a more standard data structure (than the PLM translator was planning to utilize) has accompanying changes needed to accommodate the move. • Planned budget to support will come from Boundary App savings. Of the $700K given back: o $64K would support this request. o Two other requests are incoming, the one that follows this one and another related to NSO. | [5 empty] | Design | CL/OSC | 2024-12-20 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-11 | 0 | < 15 Days | lisa.honeycutt@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0216 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 07. FTS IF 08. FTS IP 09B. Data Migration 11. Technology | Prabesh Acharya | [11 empty] | Integration from PDH to S4 to capture yield and scrap for BOMs | Integration from PDH to S4 to capture yield and scrap for all BOMs except PROC BOMS​ | This is required to correctly calculate cost |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB7121821-7BAC-4F8E-980F-05C2A2BD15B8%7D&file=CR00216%20-%20Integration%20between%20PDH%20to%20S4%20to%20capture%20yield%20and%20scrap.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes | S4 | 2 | DATI1132_IP, DATI1132_IF |  | DATI1132_IP, DATI1132_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2024-12-12 | o This change request is to update Master Data design for BOM to include Yield and Scrap.  Only Master Data design will re-open so that the data will come from PDH instead of SPEED; it was originally thought SPEED contained the needed functionality. o AR: Work with Boundary Apps team & Kelly to understand the source of the data upstream to PDH and update BOM data flow on slide 4. – @Lejarde, Lilibeth o AR: Update slide 3 with the full list of L3’s that will be affected (FTS and PTP) – @Lejarde, Lilibeth o AR: Include in OSC/CL agenda - @Tam, Anna |  |  | 2024-12-16 | • This Change Request is to integrate PHD and S4 to enable capture of Yield and Scrap for all BOMs except PROC BOMs, as the description indicates. • There is a requirement to include Yield and Scrap in the BOM, and the data will not come from Speed, which was the original source of the BOM. o Including this detail supports product cost estimates (input from FPR team) as well as planning/forecasting (enhances accuracy of Yield forecasts). • This request would approve the creation of an interface from PDH to SAP for the purposes of sending the detail. | [5 empty] | Other | CL/OSC | 2024-12-16 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-12 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR0217 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | sheela.lakshminarasimhasastry@intel.com | [11 empty] | Rebates and Customer agreement system design push to end of Q1'25 | Extending the Vistex/RCA (Rebate and customer agreement) apps design closure date from 31st Jan’25 to 31st Mar’25 RCA Teams are working with all the key stake holders ensuring alignment and “GO” from biz for development with detailed design discussions. No impact to the budget and overall Program Schedule, plan to complete Build by end of 12/25. | Influx of new (2H'24) requirements (CNY currency, Geo hierarchy, Vertical/Op Code, GTS) and other WIP design items require extensive analysis/design closure​ Dependencies on Master data/ECA Design, Biz alignment |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB4BF1718-98DF-44C0-9110-BE0D55D08253%7D&file=Vistex_Rebates%20B_App%20CR_WW50.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-12 | o Due to the influx of design changes coming into scope in addition to S4 design, Vistex is requesting the design closure to be extended to the end of March 2025  The team is committed to finish all object build for R3 ITC1. o AR: Update “Key Stakeholders” with the Business owners and tower leaders on slide 1 – @Chaudhry, Lopa | [9 empty] | Other | Tower | 2024-12-12 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0218 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Chandrakanth Elancheran | [11 empty] | Extended Warranty (EMS) scope extension for Order Management in sprint 10 | Change request to extend the scope for additional EMS workshops to be conducted within sprint 10 , for reviewing the business requirements for implementing extended warranties | Additional workshops sessions are to conducted to review how extended warranty service orders created in S4 HANA will be integrated with EMS for ‘active key generation’ & linked to hardware orders. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0218_EMS%20scope%20extension%20for%20OM%20in%20sprint%2010.pptx?d=w3580796224df411ea2d9be7674214a0d&csf=1&web=1&e=mTtM2R |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as Extended Warranty will be a topic under SO/PO, which is already a topic in the Roadmap. The 2 L3's have been added to the R3 Roadmap and will be completed in Sprint 11. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-13 | 0 | < 15 Days | celancheran@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0219 | Cancelled |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | R1 - ECA Exception FI Reports | R1/R2 Reconciliation - Summary FI Report (FPRXV033), R1/R2 Reconciliation - Drill Down Line Item Report for GL(FPRXV034) | FUT testing- R1 Exception reports |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was already FUT testing and approved. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-13 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0220 | Approved | Reports are being built by DARC team; ETA 1/10 | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | R2- ECA Exception FI Reports | FPRXR020-GL account reconciliation report,FPRXR021-Cost Center reconciliation report,FPRXR022-Profit Center reconciliation report,FPRXV026-GL accounts with missing company code report,FPRXV027-Cost Center replacement report,FPRXV031-Cost Center Hierarchy Reconciliation Report,FPRXV032-Profit Center Hierarchy Reconciliation Report | FUT testing - R2 exception reports |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0220_R2%20-%20ECA%20Exception%20FI%20Reports.pptx?d=w52b5715931114812b253e3d94c01cdba&csf=1&web=1&e=PdD69C |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [9 empty] | 10 |  |  |  | 0 | 10 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR020, FPRXR021, FPRXR022, FPRXV026, FPRXV027, FPRXV031, FPRXV032 | 7 |  | 0 | FPRXR020, FPRXR021, FPRXR022, FPRXV026, FPRXV027, FPRXV031, FPRXV032 | 7 |  | 0 | N/A |  | 2025-01-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-01-09 | Approved offline by Uzma | [9 empty] | Build | Tower | 2025-01-09 | 01, 2025 | 01, 2025 | 12, 2024 | 2024-12-13 | 0 | < 15 Days | sharikrishnan@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0221 | Cancelled |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.4 E2E Process Integration - Cross Functional Topics |  | 05. OTC IP 08. FTS IP 09A. Master Data | sabrina.patino@intel.com | [11 empty] | IP Customer Bailment Enablement | Develop future looking automated bailment capabilities to leverage when IP customers desire bailment for memory and/or other piece parts. Change will enable Buy sell model for R3 intercept (phase 1): Intel Products sells product with customer sold components, offsetting the price of component | Previously not included in scope. As business environment evolves, IP customer requests for bailment are increasing. Buy sell is the easiest short term option to implement but will require new business process development to stand it up w/ SCP and ERP impacts. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Namit Agarwal from the E2E Team to be closed. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0222 | Cancelled |  | ERP | R2 (Release 2) R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | ralvarezcarroz@deloitte.com | [11 empty] | Logistics: POLP table update relevant for specific order | a. New Requirement: only selective sales order types and Material Market code should go through POLP table check. Details below i. Material market code name is the main criteria for POLP and only for those orders deliveries should pick batch from POLP table for others it can be via 3PL or other sources. 1. Material market code check is done during POLP table check but not as a selection criterion. Needs code change. ii. If POLP Market code name is missing and customer lot number is present , no need to send that order for WIP inventory. | Request from OTC team to ensure correct deliveries are created based on the Sales Order Document Type and Material Market Code while deriving the batches in the deliveries. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0222%20PO%20Lot%20Pegging%20-%20Logistics%20Changes.pptx?d=wacfb840161b34d03af0c3fd46b856d4e&csf=1&web=1&e=UVUKTA |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 16 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was moved to the Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0223 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR | Jaime Sutton | [11 empty] | Capital Asset Lifecycle Time category change | Time category change from Tolerate to Migrate | PEGA tools for wbs create/change is approved to move to S4 Fiori app. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelling as the decision to move Time Category from Tolerate to Migrate in an earlier change request. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-17 | 0 | < 15 Days | ying.nee.sim@intel.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0224 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) | Medium | 09A. Master Data | 13.1 Security - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 13. Security 16. Testing | Srinivas Kolli | [11 empty] | SAP Role Build to Align to Tower based Apps/Transaction Grouping | Grouping of SAP Apps/Transactions by Towers in setting up SAP Roles, this helps us align to Data Ownership and Data Governance best practices. |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/Change%20INT-CR0224_IAO_CR%20ERP_Security.pptx?d=w662cb74247f841599181eff8f4f33f17&csf=1&web=1&e=crqLNr |  | 6. Build Security-Related Changes |  |  |  | 30 | 0 | [11 empty] | 30 |  | 0 | 0 | Security | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2024-12-19 | o The changes described in this CR will be applied to R3 as well. o There are no impacts to the current R1/R2 security commitments. | [9 empty] | Build | Tower | 2024-12-19 | 12, 2024 | 12, 2024 | 12, 2024 | 2024-12-18 | 0 | < 15 Days | srinivas.kolli@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0226 | Cancelled |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF | Vivek Prashant Potphode | [11 empty] | Enhance current R2 credit hold/release program in S/4 to reduce the number of unnecessary credit blocks placed on orders within 14-day credit horizon. | TBD |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0226_OTC%20IF_Enhance%20R2%20Credit%20Hold-Release%20Program%20to%20Account%20for%20Increased%20Order%20Count.pptx?d=w8d84aafe1f99441d925fa70701eab3f5&csf=1&web=1&e=e4qFax |  | 1. Process Scope / Design Change | CM-050-020 |  |  | TBD | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-19 | 0 | < 15 Days | matthfisher@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0227 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Naman Parti | [11 empty] | Triggering only order acknowledgements upon creation | Upon order creation, an order acknowledgement output should be sent. If the criteria for the order confirmation output type are also met at the time of order creation, only the order acknowledgement outputs should be triggered, and the order confirmation outputs should not be sent. | By sending only order acknowledgements upon order creation, redundant communications are avoided, ensuring customers receive clear and concise information. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/FS%20Ready%20for%20Review/OTCE0191/CRS/INT-Build-CR0227-Streamlining%20Order%20Communication%20in%20the%20object%20OTCE0191%20Triggering%20Only%20Order%20Acknowledgements%20Upon%20Creation.pptx?d=we22fa5d7e76143bc816c97f433fcbc31&csf=1&web=1&e=7H4gYy |  | 4. Change to Existing RICEFW / ECA/ Build Object | O-020-100 |  |  | 46 | 0 |  |  | 8 | [5 empty] | 46 |  |  |  |  | 0 | 46 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0191​ | 1 | OTCE0191​ | 1 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-01-16 | Changes were captured during FUT and will only require 46 hours of effort. Slated to complete by 2/14/25 | [9 empty] | Build | Tower | 2025-01-16 | 01, 2025 | 01, 2025 | 12, 2024 | 2024-12-19 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0228 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Soumik Sil | [11 empty] | Field Name Change in ECA Line Item and Summary Report | The G/L Account field name needs to be changed from "SAKNR" to "HKONT" in the ECA FI Line Item & Summary Report. RICEFW ID: FPRXV033, FPRXV034 | HKONT field in BSEG is holding the maximum data at the time of pulling from ECC and S/4 systems. SAKNR has limited data. Hence, the field name needs to be updated. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 6 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is less than 40 hours of technical effort; approved by Shane | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-19 | 0 | < 15 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0229 | New |  | ERP | R5+ (Post Release 5) | Medium | 11. Technology | 11.3 Technology - Middleware |  | 11. Technology | IV Rao | [11 empty] | BTP Integration suite Vs Mulesoft | We suggest utilyzing BTP's integration for integrations across the SAP ecosystem at Intel over Mulesoft, not just for SAP to SAP integrations but also for SAP to non-SAP integrations. | Mulesoft lacks standard adapters, leading to more custom development. Here are a few examples: Workday & Salesforce adapters into S/4HANA was missing in Mulesoft but were available in the BTP Integration suite. TPM on Integration suite can reduce EDI integration development time considerably. Event Mesh for the O/B API integrations can help with real-time integrations but is missing in Mulesoft. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0230 | New |  | ERP | R5+ (Post Release 5) | Medium | 11. Technology | 11.1 Technology - ALL |  | 11. Technology | IV Rao | [11 empty] | Deploy CALM alongside other tools for a smooth running Operations Control Center | SAP believes Intel should pursue the implementation of best-practice, best-run Build & Run operations. SAP CALM alongisde SAP Solution Manager, Signavio and other non-SAP applications are recommended to be the foundation of the implementation of SAP's best practice Operations Control Center. We recommend having CALM in the landscape as soon as possible, ideally before testing of IAO starts. So that project operational data can begin to get captured. | The combination of SAP CALM, Solution Manager and Signavio offers capabilities that can ensure "SAP Application and Business Process Operations" can be seamlessly monitored for not only KTLO but also be continously improved. These tools will also set the path for clean-core adherence & transport management in the short-term and help Intel's SAP applications become cloud-deployment ready through an establishment of DevOps. We are suggesting Solution Manager alongside CALM (both Application lifecycle Management tools) is that Intel gets complete ALM capabilities given CALM is an ALM tool for a cloud environment and Intel's SAP systems would be on-premise. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0231 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF | Tyrone Griffin Jr | [11 empty] | ACS Warranty | ACS warranty management prepackaged solution can not only offer a solid baseline for meeting Intel’s requirements, but also help the solution adhere to clean core principles | The ACS warranty management prepackaged soluton offers: Pre-configured functionality such as integration to PM processes, core waranty management foundation solution on which further functionality can be built. The solutio cuts down implementation timeline and reduces the solution risk significantly. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by JR Hoover that this CR is no longer required: This was only because we needed to give SAP a chance to show their warranty solution that did not fit the client needs. Client decided to move forward with our solution, so this can be removed. Thanks! | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 0 | < 15 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0233 | New |  | ERP | R5+ (Post Release 5) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 04. OTC IF 05. OTC IP 09A. Master Data | Upendra Vykuntum | [11 empty] | BP role Vs New BP for Treasury | Use a new BP role functionality within an existing BP instead of creating separate BPs for suppliers who are also customers and vice versa. Combine Treasury Intercompany BPs that are similarly related. KDD Reference: KDDDAT002B | One of the pillars of "Clean Core Standards" is clean and streamlined (harmonized, free of duplication) Master Data. One of the early phase 0 decisions for IAO was to seperate suppliers and customers into seperate Business Partners. This decision in return now forces the addition of another BP for Treasury Intercompany BP's. For future optimizations aiming at better Master Data quality and BP Harmonization to improve clean core standards, we recommend to harmonize those various BP's and use the BP roles in one BP instead of a seperate BP, if the entity reflected by the BP is the same. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0234 | New |  | ERP | R5+ (Post Release 5) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP | Tyrone Griffin Jr | [11 empty] | Limited use of Std QM in various towers. For Eg: Quality inspection for RMAs is missing. | The OSC/CL’s recent decision (Sept. 2024) to include SAP QM in scope is a positive move. SAP is delighted to endorse this plan. SAP recommends that IAO utilize the SAP QM module to its fullest extent. Intel will derive value from SAP’s best in class solution (e.g. consider using QM in S/4 HANA manufacturing processes). | Various manufacturing processes require products to be inspected, stored in a given location to be dispositioned, and then released into available inventory or scrapped. Quality Management has embedded functionality to create a quality inspection lot, record inspection results, and release stock into the respective stock status (unrestricted, blocked, scrap). Using SAP QM even for SAP Manufacturing processes will help Intel retire the corresponding boundary apps, reducing the TCO through reduced RICEFWs and decreased licensing & maintenance costs for boundary app(s). |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0235 | New |  | ERP | R5+ (Post Release 5) | Medium | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology | Varun Vijh | [11 empty] | AI Capabilities and innovation supported by a cloud deployment | Consider moving to the Cloud under RISE with SAP to have access to cutting edge AI innovation. Moreover, using BTP, is a low hanging fruit, especially for getting access to all the innovation in the AI space. | SAP announced in 2023 that it will, going forward, offer innovations only on cloud deployments that are either on Public cloud or private cloud. With AI, especially GenerativeAI, slowly becoming the cornerstone for competitive edge, missing out on such innovations can get tricky. Overall, out of a total of 203 AI use cases available as of now, only 103 use cases, mainly in the situation handling space, are available to Intel (They are embedded in SAP S/4HANA). Only 6 of those are in the Gen/AI space. 92 use cases are not available to Intel as they are available only on SAP BTP. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0237 | New |  | ERP | R5+ (Post Release 5) | Medium | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology | Varun Vijh | [11 empty] | SAP Build Process automation for Workflow, RPA, decision management, process visibility and embedded AI capabilities | Utilize SAP Build process automation, a SAP BTP app, for your workflow, automation, and low-/no-code citizen (End users) development, utilizing standard API's for integration with S/4HANA | Many processes at Intel require workflows mainly for approvals and other automation customization (wrapper programs for mass processing, bundling functionalities into more central user interfaces, etc.). Most of these functionalities are introduced in the project as custom coding (mimicking existing ECC6.0 custom programs). However, the "SAP Clean Core" imperatives and "Digital Solution" strategies foresee concepts, where core functionality resides in S4, while specific enhancements and individualization are achieved outside of, but closely interacting with, S4. The BTP app "SAP Build" with its capabilities for Process Automation, Bot creation and deployment, workflow management and low-/no-code citizen developer functionality can entirely replace the current automation related customizations at Intel and further enhance and improve processes as well as infuse those with predelivered automation functions, and intelligent functions as well as detailed process intelligence reporting of exceptions and deviations. These capabilities will further be expanded by SAP "outside" but highly integrated with S4HANA. SAP Build on BTP and its capabilities communicate with S4HANA via standard API's. RICEFW ID 2170, 2169 and many more related to BOT creations could have been eliminated by using SAP Build process automation. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0240 | New |  | ERP | R5+ (Post Release 5) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Chandra Putcha | [11 empty] | Utilizing SAP's AATP functionality in the IP S/4HANA box. | We suggest that for IP S/4HANA, Intel should consider utilizing SAP's AATP functionality instead of relying on BY for order promising. This is not applicable for IF, which is a MTO (Make-To-Order) scenario. For IP, AATP + BOP within S/4HANA can be the way to go. | Since IP does not have manufacturing at all, and since IP runs mostly on an MTS ( Make to stock) scenario, there may be no value in using BY for available-to-promise functionality. Rather Standard SAP-AATP with BOP ( Back order processing) provides way more flexibility with even a provision for manual reallocation when needed. Overall, this will help reduce integrations with BY. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0241 | New |  | ERP | R5+ (Post Release 5) | Medium | 05. OTC IP | 5.7 OTC IP - Entitlement Management |  | 05. OTC IP | Chandra Putcha | [11 empty] | IRC tool Vs SAP EMS | SAP-EMS is currently only being set up for Physical products related warranties but not for software entitlments. We suggest extending the use of SAP EMS for software entitlements. | Intel Currently has multiple Entitlement management tools, and they can consolidate them all and use SAP EMS instead, leading to reduction in overall TCO. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0242 | New |  | ERP | R5+ (Post Release 5) | Medium | 07. FTS IF | 7.3 FTS IF - EM/GTT |  | 07. FTS IF | Sunny Bhatia | [11 empty] | Integrations with Carriers through standard providers Vs the current OpenText has caused extra development. | Intel's carriers post the in-execution/transit events to Intel via GXS/OpenText. GXS/OpenText forwards the events to Intel's SAP EM system in the as-is scenario. In future state, the events will be received in SAP GTT from GXS/OpenText. Intel wants to integrate SAP GTT with GXS/OpenText which will require a major change on GXS/OpenText side to consume the standard OData Services provided by SAP GTT. IT is a huge development effort to consume these services by GTT into GXS/OpenText. Since Intel is bringing their own vendor to consume GTT services instead of preferred vendors, the integration has to be setup from scartch instead of using a pre-set integration with our preferred partners. We suggest that the integrations with carriers should be done through standard preferred providers. | SAP GTT also has preffered visibility providers onboarded on the network which can be levereged to get the visibility into the shipments from the carriers. The visibility providers internally connect to the carriers to get the events into SAP GTT. Following this approach will require much less effort from an onboarding perspective. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2024 | 2024-11-05 | 519 | > 30 Days | varun.vijh01@sap.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0244 | Cancelled |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Soumik Sil | [11 empty] | Logic update for Functional Area derivation | Functional Area derivation logic in FPRE0023 & FPRE0024 needs to be updated as mentioned below. 1) If the transaction from ECC has a functional area for the 5, 6, and 8 series GL accounts - Keep source functional area 2) If the transaction from ECC does not have a functional area or is a 4 or 9 series GL account - map based on GL Account 3) If the transaction from ECC has functional area COS for the 5, 6, and 8 series GL accounts - map by GL account for COGS and INVI, all else goes to OCOS |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-090 - CFIN Initial Load & DC-010-100 - CFIN Replication |  |  | 20 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is less than 40 hours of technical effort; approved by Shane | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2024 | 2024-12-20 | 0 | < 15 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0245 | Cancelled |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 09A. Master Data 09B. Data Migration | Prabesh Acharya | [11 empty] | New company code added to R1 scope | 1. Company code 329 to be added to CFIN for R1. 2. Company code 251/252/253/255/256/613 to be added to CFIN for R1 and R2/R3 for IF/IP 3. Company code 099 to be moved from IP to IF. 4. Company code 833 deactivated in ECC, thus, need to be removed from IP/CFIN | Legal Entity – 329: R1 329 was on liquidation roadmap and was expected to be liquidated by Dec 2024, thus, was not included in R1 scope. Now due to delay in liquidation process, 329 will not be liquidated by Dec. Requesting to add it to CFIN to ensure completeness of financials. Legal Entity – 251 (IF)/252 (IP)/253 (CF)/255 (IF)/256 (IP) /613 (IP) to be added to CFIN for R1, R2 & R3 New holding legal entities requested by tax. Only requiring general ledger functions. Legal Entity – 099 to be moved from IP to IF S4 instance Tax/Legal decided to repurpose company code 099 for Intel West – a previously announced arrangement with UMC which is an IF entity. 099 is currently configured in IP instance, thus, need to be removed from IP and added to IF. Whether or not procurement capability is needed is still TBD at this moment. Legal Entity – 833 Currently configured in IP and CFIN. It has been liquidated and liquidation entries posted in Dec. Posting period variant removed in ECC. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0245_Company%20code%20CR%20R1%20scope.pptx?d=wef52f2dd083548fb9d839e6c492dc27b&csf=1&web=1&e=3ca5LK |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-020-010 |  |  | 36 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR is less than 40 hours of technical effort. It has been moved to the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-07 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0247 | Approved | Need RICEFW ID of Report | ERP | R2 (Release 2) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Alter group PNL and BS reports in ECA | Build the group structure table in ECA to refer the group structure and validity period of the units with the group. | To view reports specific to each consolidation group – Altera, Intel Corporate etc. with time dependency. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0247_R1_Group%20filter%20in%20ECA%20reports.pptx?d=wb96a4cfe1fe54192a7a551b8bacbe585&csf=1&web=1&e=gJkL6R |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 27 | 0 | [9 empty] | 27 |  |  |  | 0 | 27 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-03-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-01-08 | Approved by Shane through offline email chain with Scott and Uzma. | [9 empty] | Build | Tower | 2025-01-08 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-06 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0248 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Sathyanarayanan Dhandapani | [11 empty] | Additional fields for Return Order create interface | Below 2 fields are needed to be added to interface OTCI0294 (Return Order Create) from Sales force into S/4 to support the downstream activities, 1. Batch ID - for EWM process 2. Actual Invoice Indicator - For VISTEX | These fields are needed from Sales Force to support the downstream processes - EWM and VISTEX |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0248_OTC%20IP%20-%20Additional%20fields%20for%20Return%20Order%20create%20interface.pptx?d=w9084b9d3baed41fd9ab1fa41e52dfdc5&csf=1&web=1&e=ulUp6y |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 24 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is less than 40 hours of technical effort | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-08 | 0 | < 15 Days | sadhandapani@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0249 | Approved | Need RICEFW ID of Report | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Std. P&L logic updates in ECA–FA and FS item | To align Std. P&L to Consol IS for consistent and accurate reporting. Std P&L logic is the basis for other P&L reports and the update would ensure these are all accurate and consistent. ​ | To be able to compare and tie our existing reports to S4 reports. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0249_R1_FA%20changes%20in%20ECA%20reports.pptx?d=w43834c990d5242c7903037d0d2d5417d&csf=1&web=1&e=ayJSMx |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 37 | 0 | [9 empty] | 37 |  |  |  | 0 | 37 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-03-03 | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-01-08 | Approved by Uzma offline on priority through email chain. |  |  | 2025-01-08 | Approved by Scott Gawel in offline email chain | [5 empty] | Build | Tower | 2025-01-08 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-09 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0250 | Approved | 232 hours of tech effort | SCP | R3 (Release 3) | High | 07. FTS IF | 11.1 Technology - ALL |  | 04. OTC IF 07. FTS IF 11. Technology 16. Testing | Naren.Mangtani@intel.com | [11 empty] | IF R3 - OTC RICEFW for Order Confirmation (using PDH instead of BY-OP) | Leverage PDH instead of BY-OP adaptor for Sales Order Confirmations and Updates, | A review of the sales order confirmation technical architecture revealed that orders are promised based on BY-ESP results, with BY-OP merely reformatting and transmitting the data to S4. Since BY-OP was not determining the promise dates and only served to pass data, its use was deemed unnecessary and incurred an unneeded licensing fee. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B598E716B-9B49-4DB2-A692-13FC17F895E1%7D&file=Change%20ID_Order%20Mgmt%20OTC%20S4%20RICEFW%20-%20IF%20ESP%20R3.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [8 empty] | 232 |  |  |  |  | 0 | 232 | N/A | Yes | SCP | 0 |  | 3165 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-16 | CR was taken straight to Core Leadership |  |  | 2025-01-17 | Presented and approved during Core Leadership Meeting | [5 empty] | Other | CL/OSC | 2025-01-17 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0252 | Cancelled |  | ERP | R2 (Release 2) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  |  | Anubhi Purohit | [11 empty] | Removal of 1-year batches from extractions & Transformation rule change for Supplier | Removal of 1-year batches from extractions & Transformation rule change for Supplier |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR was less than 40 hours of effort. And the CR has been moved to the Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-13 | 0 | < 15 Days | anupurohit@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0253 | Cancelled |  | ERP | R2 (Release 2) | Medium | 07. FTS IF | 4.8 OTC IF - EWM | Yes |  | Anubhi Purohit | [11 empty] | EWM Inventory data extraction - File to Source system change | EWM Inventory data extraction - File to Source system change |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR was less than 40 hours of effort. And the CR has been moved to the Build CR Log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-13 | 0 | < 15 Days | anupurohit@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0254 | Cancelled |  | ERP | R2 (Release 2) | Low | 09A. Master Data | 9A.6 Master Data - Material |  |  | Anubhi Purohit | [11 empty] | Extension of Plants for DIEN Materials(TBD) |  |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to be an internal CR and has been cancelled |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-13 | 0 | < 15 Days | anupurohit@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0255 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 05. OTC IP 11. Technology | junior.milan@intel.com | [11 empty] | CI Print Logic - Secondary Screening | To stay legally compliant to US Government party screening requirements for “in-process” orders, Intel will require a GTS check at export document generation to ensure that none of the parties or products being shipped have been flagged by US Government while the order was in the pick/pack process. | Natively, SAP runs a final GTS screening procedure at the time of PGI. Because of the way Intel applies Risk & Controls/SOX compliance to physical cargo departure, the Intel PGI only occurs after the freight physically departs the dock. This means that the check occurs when the goods are no longer in control by Intel. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INTCR0255_OTC%20IF_CR.pptx?d=wecfcd8ae41f1493095433fcac842e40d&csf=1&web=1&e=KEhGR3 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 30 | 0 |  |  | 45 | [5 empty] | 30 |  |  |  |  | 0 | 30 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0343_IF​​, LOGF0344_IF​​, LOGF0345_IF​​, LOGF0348_IF​​, LOGF0353_IF​​, LOGF0346_IF​​, LOGF0357_IF​​, LOGF0347_IF, LOGF0342_IF​​, LOGF0354_IF​​ | 10 | LOGF0343_IF​​, LOGF0344_IF​​, LOGF0345_IF​​, LOGF0348_IF​​, LOGF0353_IF​​, LOGF0346_IF​​, LOGF0357_IF​​, LOGF0347_IF, LOGF0342_IF​​, LOGF0354_IF​​ | 10 |  | 0 |  | 0 | N/A |  | 2025-03-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-01-30 | o The process of printing CI is triggered once packing is complete. When designing, the team went with the routine approach. o The changes are slated to be tested in ITC3. | [9 empty] | Build | Tower | 2025-01-30 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-15 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0256 | Cancelled |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF | Sathyanarayanan Dhandapani | [11 empty] | Original PO Number to be captured on the Returns Authorization form for SIMS Returns | For SIMS Internal returns Customer Original PO will be captured in the Returns PO header Text, will be added to Return SO while creating and captured in Authorization document, For SIMS external returns SIMS front desk will update the Original PO manually while creating the Return SO. CR need to be created to update the existing Authorization form for SIMS Existing IF Returns Authorization FSD - OTCF0172 need to be updated with logic to capture the Original PO | The details of Original PO from Customer is needed for SIMS on the Authorization Document this is needed for the Customers to map the relevant Return Orders. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT%20CR0256%20OTC%20IF%20Original%20PO%20Number%20to%20be%20captured%20on%20the%20Returns%20Authorization%20form%20for%20SIMS%20Returns.pptx?d=we3ae2560aaf5481b81e02ca6df9edb43&csf=1&web=1&e=QC8Lpt |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is less than 40 hours of technical effort. CR has been moved to the Build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-15 | 0 | < 15 Days | sadhandapani@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0257 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP 11. Technology 13. Security 14. OCM 16. Testing | pipatil@deloitte.com | [11 empty] | BRIM Integration with GTS E4H | Integrate BRIM with new GTS E4H for compliance screening as BRIM is being implemented in S4 IP system. | As BRIM would be getting implemented in NEW S4 IP system, it needs to integrate with GTS to get all the compliance screening for Quotation and Subscription contracts to have the system complaint. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0257_Tower_CR%20Deck_GTS_BRIM.pptx?d=w848cbc0a9a7944ce91da28563874f19e&csf=1&web=1&e=QSEcdw |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3163 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-16 |  |  |  | 2025-01-22 | Approved by Core Leadership in the 1/22 meeting during Jan FTF | [5 empty] | Design | CL/OSC | 2025-01-22 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0258 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 09A. Master Data 09B. Data Migration | Jill Matalon | [11 empty] | Addition of fields in mapping sheet and overall scope for Open Sales order R2 IF | Addition of Pricing date, Net Value to the mapping sheet and overall scope of Open Sales order Conversion for R2 IF. | Based on Mock cutover 2 observations, business suggested it would be helpful to add pricing date, Net value and Delivery/Billing blocks into the scope of open Sales order conversion to ensure that Pricing data is picked up accurately and also business will be able to validate in Recon report if we add these 2 fields |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/Conversion/INT-Build-CR0258%20-%20Mapping%20of%20source%20and%20target%20Pricing%20Data%20with%20respect%20to%20the%20object%20OTCC0517.pptx?d=w9bb4ced5879a4e868ecc60ae28238db2&csf=1&web=1&e=INjQaN |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 90 | 0 | [10 empty] | 90 |  |  | 0 | 90 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0517 | 1 | OTCC0517 | 1 |  | 0 |  | 0 | N/A |  | 2025-06-04 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-23 | Approved in offline email with Rebecca, Mike, and Uzma |  |  | 2025-01-23 | Approved in offline email with Rebecca, Mike, and Uzma | [5 empty] | Build | CL/OSC | 2025-01-23 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-16 | 0 | < 15 Days | shubhamsharma6@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0259 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | sergio.boraschi@intel.com | [11 empty] | Publish scenario design in BY | Current R2 SP design has a system batch job that publishes wafer output downstream for PRs and PRF on Friday of FE supply planning solve week. Given S&OP forum timing and decisions requiring PO and PRF ratification in the Exec meeting in Week 3, new publish requirement is needed. To avoid issues with this in the future, recommending a user initiated publish vs. a scheduled batch job. This change would need to include all jobs related to: PRF publication, PR creation, conversion of PR’s to PO’s, and associated report publications | If we do not make this change, PRs will be created in Week 2 without exec approval. Any adjustment requested from S&OP exec leaders will require Planners to manually adjust them in SAP. This also require re-adjustments of the recently ratified type 2 Recon process for external foundries If we do not make this change, PRF will be sent to Intel and External Foundries in Week 2 without executive approval. If we continue with scheduled batch jobs, we will need a way to work with IT to pull-in and push-out as required based on scheduling, etc. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/20250116%20Change%20ID_Tower_CR%20Deck_template%20-%20R2%20IP%20SP%20plan%20publication%20CCB%20.pptx?d=w4bcec87e614345fe97407d40fbb6c2c5&csf=1&web=1&e=o4xTlb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 40 | 0 | [6 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-16 |  |  |  | 2025-01-31 | • CR0259: Publish scenario design by BY approved by Rick Antonellis • Key Points: o The timing change from R2 to R3 is non-negotiable. o The need for a user-triggered event rather than a fixed system batch job was discussed. o The team agreed to simplify the requirements and focus on the minimum necessary changes for now. • AR: Scott Gerwig to update the timeline and confidence level post WW09. • As a follow-up Sergio Boraschi provided the attached the modified CR0259 Publish scenario design in BY, following the approval of the change for the system batch job benchmark from wk2 to wk3. It also states that the change in the publication method from system batch job to user triggered is not approved but postpone as something to explore post -R2 go live. | [5 empty] | Build | CL/OSC | 2025-01-31 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0260 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | Savannah Hoover | [11 empty] | IP Gaplog Intake Process & MVP Tool | Original intake tool, using PROMISE, no longer viable. Team proposing low-cost/MVP alternative | Original design being revised to support MVP capabilities while industry-aligned design is investigated. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR0260%20-%20IP%20Gaplog%20Intake%20Process%20%26%20MVP%20Tool.pptx?d=w8941d18a27cd476694246723eaafb5ed&csf=1&web=1&e=v3Cxdr |  | 2. New RICEFW / ECA / Build Object |  |  | Low |  | 1 |  |  |  | 0 | 0 | 0 | 40 | [6 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-30 | o Current expedite module within Promise will no longer meet IAO needs. There are plans to decide a long-term solution, but it will not be ready for R2. Therefore, the team aligned on an interim solution. o The deliverable is an Excel file with calculations and data validation, and only formatting changes are left.  Affected business users are familiar with the tool. o AR: Update change request deck to include build completion date and testing date. - @Hoover, Savannah |  |  | 2025-01-31 | • CR0260: IP Gaplog Intake Process & MVP Tool approved by Rick Antonellis • Business Process Changes: The team discussed the need to adapt business processes to account for the changes in tool capabilities. • Key Points: o The tool is 90% complete and will be finished end of WW06. o The importance of documenting the business process was emphasized. o The tool is a temporary solution until a long-term solution is ready. • AR: Savannah Hoover to ensure the business process is documented and communicated to the relevant teams. | [5 empty] | Other | CL/OSC | 2025-01-31 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0261 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data | Bigil Kuriyan T | [11 empty] | Asset Location - Extend Itego Data model with custom attributes |  | Change in build timelines for Asset Location - Extension with custom attributes.The custom development for Asset location couldn't start on the planned start date as the dependent activity of standard configuration of the same was delayed by Deloitte team. Hence our planned dates for the build activities are delayed. We want the new build time lines to be updated in the February 2025 Sprint so that the actual progress can be tracked. This object is part of R3 and there is no business impact due to the timeline changes. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is confirmed to no longer be required by Lynn Asbury |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-20 | 0 | < 15 Days | shrutisingh7@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0263 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Esha Esha | [11 empty] | Calendar Logic for Extraction of data based on previous quarter & previous periods | Calendar logic required for the extraction data for previous quarter & period as part of the RICEFWs - FPRE0474, FPRE0475, FPRE0476 accordingly. | If we do not add this change in the current development, the extraction of data for previous quarter & period will not be possible as the calculations for the mentioned RICEFWs is dependent on the billing & returns data of the previous quarter, pervious period & 24 days respectively. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-100-020 |  |  | 36 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | esesha@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0264 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Ms Avasthi | [11 empty] | FPRE0315_IF for Activation of custom enhancement tab on portfolio bucket for custom fields. | Capex Changes: Two custom fields are to be created. PM by plant and Approving PM by plant on WBS level. Value Help based on custom table/CBO must be created for custom fields. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-300 |  |  | 32 hrs | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0265 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Ms Avasthi | [11 empty] | FPRE0315_IF for Activation of custom enhancement tab on portfolio bucket for custom fields. | Capex Changes: Two custom fields are to be created. PM by plant and Approving PM by plant on WBS level. Value Help based on custom table/CBO must be created for custom fields. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-300 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael Quesada that this CR has been created in Build Tracker | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | snavasthi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0266 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Ms Avasthi | [11 empty] | Change to FPRE0315_IP for Activation of custom enhancement tab on portfolio bucket for custom fields. | Capex Changes: Two custom fields are to be created. PM by plant and Approving PM by plant on WBS level. Value Help based on custom table/CBO must be created for custom fields. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-300 |  |  | 24 hrs | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0267 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Ms Avasthi | [11 empty] | Change to FPRE0495_IF - Custom Fields in WBS element Master Data | Opex Changes : • Portfolio Item – 4 new custom fields to be added. • Portfolio Bucket -- 4 new custom field and 1 existing field change • Remove existing Project group ID and name fields. • Profit Centre logic to be added. User Defined Field • Custom logic to be implanted for Investment type and new columns of around 30 to be added in the existing table for Investment Type determination. User Defined Field. Changes: • L2 flip dates for the different subtypes (on different WBS Element) should be in sequence. All the dates cannot overlap or occur before each other in the sequence of OCOS subtypes RND, SUP, ONG, EOL in that order. • Params table will be maintained with OCOC Subtypes sequence. • Validation will be implemented at SAVE exit level. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-500 |  |  | 30 hrs | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0268 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Ms Avasthi | [11 empty] | Change to FPRE0495_IP - Custom Fields in WBS element Master Data | Opex Changes : • Portfolio Item – 4 new custom fields to be added. • Portfolio Bucket -- 4 new custom field and 1 existing field change • Remove existing Project group ID and name fields. • Profit Centre logic to be added. User Defined Field • Custom logic to be implanted for Investment type and new columns of around 30 to be added in the existing table for Investment Type determination. User Defined Field. Changes: • L2 flip dates for the different subtypes (on different WBS Element) should be in sequence. All the dates cannot overlap or occur before each other in the sequence of OCOS subtypes RND, SUP, ONG, EOL in that order. • Params table will be maintained with OCOC Subtypes sequence. • Validation will be implemented at SAVE exit level. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-500 |  |  | 12 hrs | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0269 | Cancelled |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Soumik Sil | [11 empty] | Logic update for Functional Area derivation in FPRE0023 & FPRE0024 | This is a 0$ CR. Functional Area derivation logic in FPRE0023 & FPRE0024 needs to be updated as mentioned below: 1. If the transaction from ECC has a functional area for the 5 & 6 series GL accounts (Field HKONT) - Keep source functional area unless in GL range 588000 – 588999 2. If the transaction from ECC does not have a functional area or is a 4 or 9 series GL (9 Series exception GL 919111, 919112, or 919113 account) or 5 & 6 series GL accounts (Field HKONT) - map based on Target GL Account 3. If the transaction from ECC has a functional area for GL (Field HKONT) range 588000- 588999 – map based on Target GL Account 4. If the transaction from ECC has a functional area for GL account 919111 or 919112, or 919113 clear the functional area at target system CFIN and proceed 5. If the transaction from ECC has a functional area COS for the 5 & 6 series GL accounts (unless in GL Range 588000 – 588999)- map by Target GL account for COGS and INVI, all else goes to OCOS. | According to the business requirement, the existing functional area logic needs to be updated to be aligned with Group Reporting. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0269_CFIN%20FA%20Mapping%20Logic.pptx?d=w867e1fcbda1a46f5894dd2f96a51bf3c&csf=1&web=1&e=VkJCBg |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-090 - CFIN Initial Load & DC-010-100 - CFIN Replication |  |  | 15 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR is less than 40 hours of technical effort. It has been moved to the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-22 | 0 | < 15 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0270 | Cancelled |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF 05. OTC IP | Kartik Sanjay Pawar | [11 empty] | Shipment Start date and Pickup time in HAWB assignment form | Actual shipment start date and Pickup time are to be maintained by warehouse operator manually in TU. Hence changes are needed to fetch the date and time from EWM TU to TM freight order. | This change is needed in R3 since the current date and time available in HAWB assignment form is not correct. In current setup, planned departure dates are considered however the carrier needs the actual shipment date which will be updated by warehouse operator manually into transportation unit. This form will be handed over to carrier upon PGI. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0270%20-%20Shipment%20Start%20date%20and%20Pickup%20time%20in%20HAWB%20assignment%20form.pptx?d=w8793723f89d04b6eb6df0e965e51ef04&csf=1&web=1&e=DCpZnM |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 104 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne Ramirez (Intel PM) that this CR can be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-23 | 0 | < 15 Days | ksanjaypawar@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0271 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | Chandrasekhar Gorantla | [11 empty] | Addition of Limit field in FS FPR0117 - IHC Current Account Creation | Addition of Limit field in FS FPRC0117 - Conversion – In House Cash: Current Account creation, Cash Concentration Hierarchy Creation and Current Account Balance upload | New additional business requirement in the FS FPRC0117 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0271_Addition%20of%20Limit%20field%20in%20FS%20FPR0117%20-%20IHC%20Current%20Account%20Creation.pptx?d=w63ddef3c923b4715ad46b58748108e9d&csf=1&web=1&e=4gxLqm |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0272 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.4 FPR - Intercompany |  | 03. FPR | Prabesh Acharya | [11 empty] | $0 Change Request: Tax calculation (VAT amount) required in the FPRF0230_IP_Invoice Layout Form. | R3 - This is required to accommodate for the change in FS related to the Tax calculation (VAT amount) required in the FPRF0230_IP_Invoice Layout Form. As per request from tech team a 0 dollar CR is required to accommodate for the further changes in the object. | FPRF0230 - Conditional FSD approval was provided with pending alignment on the finalization of the tax model and requirement. Build was completed and later to accomodate the technical changes required in the RICEFW the CR is needed. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0272_FPRF030.pptx?d=w0ec451f816094d1e89a9521b703b0b38&csf=1&web=1&e=lXgz3X |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-110-080 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Moved to build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-24 | 0 | < 15 Days | karansingh94@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0274 | Cancelled |  | ERP | R2 (Release 2) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | aravind.narasimhan@intel.com | [11 empty] | Adding Storage Location to AQUA CF | With the addition of storage location to AQUA, there are a couple of joins to raw datasets (scwm_tcat / scwm_tmapstloc ) needed to bring in SLOC in AQUA CF | Storage location is needed for these reports and for other use cases consuming this dataset. The datasets needed to bring in SLOC are only fully available in the RAW layer and have not been curated. Hence, the change is requested for CF. |  | No | [8 empty] | 26 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR only required 26 hours of technical effort. Moved to Build CR log |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0275 | Rejected | To be combined with Open Topics list & presented to Core Leadership during WW7 | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 05. OTC IP 06. PTP | kevin.m.johns@intel.com | [11 empty] | Intel Federal/Dassian design push to March | Extend the Federal/Dassian design completion date from 31st Jan’25 to 15th Mar’25, specifically​ for equipment/spares, large/small construction, CLM integration, and reporting. Build target completion date remains unchanged for Dec '25, so overall timeline is not impacted. | Decision to use a manual process for equipment/spares in WW03 requires a fit gap analysis to ensure that the processes can be adjusted from the ECC to the S/4 Design. Large and small construction requirements were not originally comprehended but arose later due to new business contracts signed by IGT. CLM integration design is nearly complete but was started late due to timeframe required to complete SOW with supplier and requires a bit more time. Reporting requires a bit more time to complete due to the effort placed on other design issues such as those above which we could not fully absorb within the original design timeline due to resource constraints. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Dassian_January_2025_Change.pptx?d=w8addb7a4a4ec47a4a0184a83602f09cc&csf=1&web=1&e=iyUwOG | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No |  | 2025-01-30 | o AR: Work with PMO team to combine open topics - @Gainda, Alpna @Johns, Kevin M @Chaudhry, Lopa | [8 empty] | To be combined with Open Topics list & presented to Core Leadership during WW7 |  | Tower | 2025-01-30 | 01, 2025 | 01, 2025 | 01, 2025 | 2025-01-27 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0276 | Rejected |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP | junior.milan@intel.com | [11 empty] | CI Print Logic - Secondary Screening | To stay legally compliant to US Government party screening requirements for “in-process” orders, Intel will require a GTS check at export document generation to ensure that none of the parties or products being shipped have been flagged by US Government while the order was in the pick/pack process. | Natively, SAP runs a final GTS screening procedure at the time of PGI. Because of the way Intel applies Risk & Controls/SOX compliance to physical cargo departure, the Intel PGI only occurs after the freight physically departs the dock. This means that the check occurs when the goods are no longer in control by Intel. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INTCR0276_OTC%20IF_CR.pptx?d=w2b8b21fa214447a5ab55ced43aeaf923&csf=1&web=1&e=YAu3WQ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 25 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-01-30 | [9 empty] | Cancelled as this is only 10 hours of technical effort for R3. This is to be incorporated into the Build CR Log | Build | Not Assigned |  | Not Approved | 01, 2025 | 01, 2025 | 2025-01-28 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0277 | Rejected |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 09A. Master Data 17. B-App | debradas@deloitte.com | [11 empty] | MDM: Vendor Change to switch DUNS number from Name 4 to Identification field | Carriers DUNS is required field in PIP messages for Logistics. Messages that are going out of S/4. EX: 3B2 ASN, 3B12 R Delivery Drop to 3 PL. With Standardization of DUNS proposal was storing DUNS in Name 4 field of Vendor Master. However, Name 4 is already utilized for some other purpose. Hence alternative field “Identification Number” is proposed in Vendor Master | Changes needs to be applied in MDM – Graphite and Conversion program in S/4 for Vendor Master |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBDF98944-5B65-4399-A552-DDF0E9EBF8AB%7D&file=INT0277_OTC%20IF_IP_MDM_DUNS%20Changes.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-02-27 | [9 empty] | Cancel CR# 277 OTC team have an alignment with MDM team. RICEF is not worth the volume of Carrier that needs change and hardly few Carrier are onboarded every year. Confirmed by Debranjan Das. | Build | Not Assigned |  | Not Approved | 02, 2025 | 01, 2025 | 2025-01-29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0278 | Approved |  | SCP | R2 (Release 2) | High | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  |  | Rocco P Demarino | [11 empty] | Ability to publish scenario as POR​ | The Business needs the ability to run What-if scenarios in BY ESP , publish these scenarios/solves to IF-PDH, designate 1 of these as the POR and push chosen scenario to downstream applications via PDH. This is required in case the Tuesday baseline solve is infeasible, or non-optimal. ​ Every week, the previous week's archived solve should represent the POR output (either baseline constrained solve or what-if scenario) | In case the Tuesday baseline solve run produces infeasible or non-optimal results, planners can run what-ifs to:​ Optimize solve results​ Avoid unnecessarily perished capacity​ Resolve cases of demand not met, or met late​ Resolve cases of capacity underutilization​ Make capacity changes across Capacity Groups in order to increase demand satisfaction ​ Change input parameters in BY due to various reasons (See next slide) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/Ability%20to%20publish%20scenario%20as%20POR.pptx?d=w1b9002b5b0794f8bafbc5e77ef71b8f9&csf=1&web=1&e=lKy64R |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 20 | 20 | 0 | [6 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-01-30 | o The changes provided by this CR will allow for the team to make changes and correction prior to the POR publication.  The development will be in BY with some work required from the BY configuration team. o AR: Work with team to get a detailed technical estimation and testing schedule & document team impacts - @Demarino, Rocco P @Cassalia, Robert J o AR: Work with Stacee Mattrazzo and Alpna Gainda to be added to the Core Leadership schedule - @Demarino, Rocco P @Cassalia, Robert J |  |  | 2025-02-07 | • CR0278: Ability to publish scenario as POR approved by Rick Antonellis • Change Request Overview: Team presented the need for the business to run "what if" scenarios in Blue Yonder ESP and publish these scenarios downstream. The goal is to designate one of these scenarios as the POR to optimize results, avoid unnecessary capacity, and ensure demand is met on time. The team assumes this would be a medium effort (2 weeks) and would be ready for UAT 1 testing. The change is necessary to provide feasible and optimal plans for factories and customers, minimizing the risk of capacity issues and potential revenue losses. • Concerns and Questions: o John Heiney confirmed that the team could absorb the change without impacting other policies. o Uzma Ahmed clarified that the scenarios are user-triggered and not event-based. • Decision: Change Request was approved. • AR: John Heiney, Chad Smith to sync with Jo Guedes to review the approach approved in CR0278 and determine if it is usable for IP. | [5 empty] | Build | CL/OSC | 2025-02-07 | 02, 2025 | 02, 2025 | 01, 2025 | 2025-01-31 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0279 | Rejected | The request will be deferred for further discussion. Jo Guedes will engage with the relevant stakeholders to review the business case and options before bringing it back to the forum. | ERP | R2 (Release 2) | High | 02. E2E Process Integration |  |  | 02. E2E Process Integration 03. FPR | shenfeng.zhu@intel.com | [11 empty] | Wafer sell support to IPG in IAO R2 release | Pull in wafer sell support to IPG in IAO R2 release | Support DCAI’s custom Si project Steel Mountain |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0279%20-%20Wafer%20sell%20support%20to%20IPG%20in%20IAO%20R2%20release.pptx?d=w932d7b9d1db84604a24c7b1ee2b25638&csf=1&web=1&e=xTL7f8 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-02-06 |  |  |  | 2025-02-07 | • CR0279: Wafer sell support to IPG in IAO R2 release - Not approved at this time Change Request Overview: Team presented a request from DCAI to sell wafers to a customer who will manage the back-end assembly test with a local vendor in China. This would change the sell point, which is currently supported in R3 for Intel Products. However, this change is needed between R2 and R3. • Options and Alternatives: o Transact sales through ECC until R3, incurring additional costs for shipping. o Treat the DCAI customer as an Intel foundry customer at R2, requiring manual finance adjustments. o Accelerate the go-live for this product. • Concerns: o Jo Guedes expressed surprise at hearing about this request for the first time and emphasized the need for proper review and alignment with the IP team. • Decision: The request will be deferred for further discussion. Jo Guedes will engage with the relevant stakeholders to review the business case and options before bringing it back to the forum. |  |  |  |  | Confirmed by Jo Guedes that the CR is no longer required as the team is addressing business requirements using standard functionality. |  | Not Assigned |  | Not Approved | 02, 2025 | 01, 2025 | 2025-01-31 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0280 | Cancelled |  | ERP | R3 (Release 3) | Low | 01. PMO |  |  | 01. PMO 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App 18. SCP | Anna Tam | [11 empty] | R3 L3 Descoping | Consolidated List of Descoped L3's for R3 |  |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2025 | 2025-01-31 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0281 | Approved | 39 hours of tech effort | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Detailed IS report in sidecar | Ability to generate detailed IS in sidecar​ ​ The reports need to show the following​ IS line item​ GL accounts detail for IS line items: opening balance, activity , closing balance and % change​ | Consol IS report includes a summary report and detail report that are required for ER/MR reporting. The summary report was created but the detail report has not been built. ​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0281_R1%20Detailed%20Consol%20IS%20sidecar.pptx?d=w4b7585a99dfc409fba0656b179a4ad08&csf=1&web=1&e=hpDXfD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [9 empty] | 39 |  |  |  | 0 | 39 | Configuration | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-10 | Approved offline by Uzma | [9 empty] | Build | Tower | 2025-02-10 | 02, 2025 | 02, 2025 | 01, 2025 | 2025-01-31 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0282 | Approved |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics 13. Security | Rea Meyer | [11 empty] | Managerial Cash Flow report in S4 | This is a new report need to view the managerial cash flow number in S4 Group Reporting. The reports need to show the following​ Beginning cash​ Changes in cash​ External Reporting nodes and Managerial Reporting lower -level detail​ | It was identified that the original request to add the Management CF Hierarchy to S4 did not include downstream reporting. The existing CF reporting will only support the external reporting requirement. We need an additional report to fulfil the Management Reporting requirements for the ability to view this data in a consistent format​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0282_R1%20Statement%20of%20CF_MH_QTD_YTD_Report.pptx?d=wdfbda5b260504749a37c3ddffeac0370&csf=1&web=1&e=eCyChT |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [8 empty] | 39 |  |  |  |  | 0 | 39 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-10 | Approved offline by Uzma | [9 empty] | Other | Tower | 2025-02-10 | 02, 2025 | 02, 2025 | 01, 2025 | 2025-01-31 | 0 | < 15 Days | kdey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0283 | Approved | 39 hours of configuration | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | New Elimination task | New Elimination Task | New GLs were created in the last two quarters of 2024 which were mapped to a new elimination task.. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CRXXX_R1_GR%20Create%20New%20elimination%20tasks.pptx?d=w1d91355e0339404f8fd57f2de00cced5&csf=1&web=1&e=FcokOb |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 39 | [5 empty] | 0 | 39 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-10 | Approved offline by Uzma | [9 empty] | Other | Tower | 2025-02-10 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-04 | 0 | < 15 Days | kdey@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0284 | Approved | 35 hours of configuration | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Update to existing elimination task | Update to existing elimination task | Update of existing configuration of Reclass - Intersegment Sales/COS (RN), MWP Intersegment Revenue(RP) and Elimination - Intercompany Rev/COS (A3) with new GLs added. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CRXXX_R1_GR%20Update%20Existing%20Elimination%20Tasks.pptx?d=we8515bd996854aa98e359e548e01d179&csf=1&web=1&e=HJSgcg |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 35 | [5 empty] | 0 | 35 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-10 | Approved offline by Uzma | [9 empty] | Other | Tower | 2025-02-10 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-04 | 0 | < 15 Days | kdey@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0285 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 08. FTS IP 12. Infrastructure | stef.maxey@intel.com | [11 empty] | OSAT 7B1 integration for IP using SMH | Use the PDF-SMH hub for updating IP S4 for production orders., instead of using Mulesoft to process 7B1s received via E2O​ | This can reuse a lot of IF S4-MES/WS integration design on SMH platform. Easier to do with PDF-SMH , reusing most of the design built for IF MES-S4 integration, for Merge and Split scenarios, sequencing 7B1s, error handling and process orchestration.​ This approach can be cost effective to move completely to PDF-SMH for OSAT – IP S4 manufacturing integration and get off of E2Open for 7B1. ​ Synergy with having similar software in IP and IF to be able to support Manufacturing integration.​ Aligns with Strategic direction to use PDF-SMH for Manufacturing and ERP integration platform​ Remnants requirements for IP needs Merge and Split of Production orders. SMH is best suited to handle this. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6DE2FD71-692F-4AE7-926D-8CE2E742FD8F%7D&file=Change%20ID_OSAT%207B1%20IP.pptx&action=edit&mobileredirect=true | Design / Build Gap | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-06 | To be brought into the CR Meeting |  |  | 2025-02-14 | The CR was approved. The team acknowledging the need to address incremental cost concerns and will work to identify budget for expense. • Estimates for SMH option: o $850K for license approx. - On going after go live [ 2027 onwards] o Total cost - For 2025 – approx. - $1 Million(includes consulting, hardware, and installation) o 2026/2027 – 500K(testing and go live support) o 2027 onwards - $850K/per year – licensing o From 2026 Q3 additional 3 HC across regions for support on the Intel team | [5 empty] | Design | CL/OSC | 2025-02-14 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0286 | Approved |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Group Reporting hierarchy replication in ECA | Group Reporting hierarchy replication in ECA | To ensure all group reporting hierarchies are made available in ECA to ensure accurate financial reporting. Currently only 6 hierarchies are available which impedes effective financial reporting. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/NT-CR0286_FS_Item_Hierarchies%20in%20ECA.pptx?d=w39415d80158a447fb96b482ef03002e9&csf=1&web=1&e=ZYhZ8h |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 15 | 0 | [9 empty] | 15 |  |  |  | 0 | 15 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV002​, FPRXV001​ | 2 |  | 0 | FPRXV002​, FPRXV001​ | 2 |  | 0 | N/A |  | 2025-02-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-05 | Confirmed by Rafael Quesada that Shane Bethune received offline approval for CR | [9 empty] | Build | Tower | 2025-03-05 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-05 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0288 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology 12. Infrastructure | YASH DESHPANDE | [11 empty] | FDS and Mapping changes for interface PTPI0136/37_138_39 | FS and mapping changes required to incorporate multiple new design requirements which are as follows: 1.scenariors related to Returns PO, Rework PO, Replacement PO, FAB PO , Expedite PO, STO PO need to be added in the FS. 2.Realignment on BILL_TO_DETAILS table which requires table structure and logic change for all the addresses related fields. 3. DPAS custom item text needs to be sent to E2open and opentext. This change will impact objects PTPI0136/37,PTPI0138/39, PTPF0014, PTPF0015, PTPE0543 and PTPE0259. | PTPI0136/37, PTPI0138/39 are PO outbound interfaces which use IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary apps E2open, Opentext. If the changes are not incorporated certain necessary fields and accurate information will not be sent to suppliers . |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0288%20and%20289_PTP_IF_IP.pptx?d=wb26651540b3045adba8dbc062338ff20&csf=1&web=1&e=vlmNo1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 48 | 0 | [8 empty] | 48 |  |  |  |  | 0 | 48 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | PTPF0014_IP, PTPE0543_IP, PTPE0543_IF, PTPE0259_IP, PTPE0259_IF | 5 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0136_IP, PTPI0136_IF​, PTPI0137_IP, PTPI0137_IF, PTPI0138_IP, PTPI0138_IF, PTPI0139_IP, PTPI0139_IF,​ PTPE0259_IP, PTPE0259_IF​, PTPE0543_IP​, PTPE0543_IF, PTPF0014_IP​, PTPF0015_IF​ | 14 | PTPI0136_IP, PTPI0136_IF​, PTPI0137_IP, PTPI0137_IF, PTPI0138_IP, PTPI0138_IF, PTPI0139_IP, PTPI0139_IF,​ PTPE0259_IP, PTPE0259_IF​, PTPE0543_IP​, PTPE0543_IF, PTPF0014_IP​, PTPF0015_IF​ | 14 |  | 0 |  | 0 | N/A |  | 2025-10-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | o This change request is an consolidation of small changes across 10 reports. Most of the changes are to fine-tune and touch-up the view | [9 empty] | Build | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-06 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0289 | Rejected |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | yswaddeshpande@deloitte.com | [11 empty] | FDS and Mapping changes_PTPI0136/37_PTPI0138/39 | FS and mapping changes are required to incorporate multiple new design requirements which are as follows: 1.scenariors related to Returns PO, Rework PO, Replacement PO, FAB PO , Expedite PO, STO PO need to be added in the FS. 2.Realignment on BILL_TO_DETAILS table which requires table structure and logic change for all the addresses related fields. 3. DPAS custom item text needs to be sent to E2open and opentext. This change will impact objects PTPI0136/37,PTPI0138/39, PTPF0014, PTPF0015, PTPE0543 and PTPE0259. | PTPI0136/37, PTPI0138/39 are PO outbound interfaces which used IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary apps E2open, Opentext. If the changes are not incorporated certain necessary fields and accurate information will not be sent to suppliers . |  | Yes |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-02-20 | [9 empty] | Cancelled as CR0288 is the same | Build | Not Assigned |  | Not Approved | 02, 2025 | 02, 2025 | 2025-02-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0290 | Rejected |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP 18. SCP | andrew.d.whipple@intel.com | [11 empty] | R3 Weekly Wafer Planning | Moving from BY IBP planning 0-24mths to BY ESP 0-9mths S&OE and BY IBP 10-24mths S&OP | Eliminate GapLog process Simplify Bloodbank process with R3’s Push/Pull/Cancel process and improve inventory health Faster reaction of demand mix changes within PO month and minimize potential excess and better demand satisfaction Faster reaction of supply changes due to yield change or excursion Industry standard |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4C1ACFC5-F21C-4E66-8063-6F19E21A85A4%7D&file=R3%20Weekly%20Wafer%20Planning%20Design2.pptx&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No |  | 2025-02-13 | CR will be closed in the Program CR Log and will be converted to KDD; Will be presented in CR meeting on Friday, 2/14 | [8 empty] | CR will be closed in the Program CR Log and will be converted to KDD; Will be presented in CR meeting on Friday, 2/14 |  | Tower | 2025-02-13 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0291 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 06. PTP 07. FTS IF | junior.milan@intel.com | [11 empty] | Wafer/Die Bailment CI and PL ¦ New Fields | To align to new requirements for a new customer deal (Spire), changes are being made to the existing Intel Commercial Invoice and Packing List in ECC. To remain compliant to this customer request, we will need to make the changes to our existing Wafer/Die Commercial Invoice in time to launch in R2. Customer is requesting Intel include the Intel batch in the “Customer Lot” field. | Align designed document for R2 with customer requirement of including Intel Batch information in the “Customer Lot” field. Change is being made in ECC to the existing Commercial Invoice and Packing List. Changes to IF document in S/4 will be required. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0291_OTC%20IF_CR.pptx?d=w466b9d1f1cdc47aeac865b8b019ffdc0&csf=1&web=1&e=rNWkzs |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne Ramirez (Intel PM) to be cancelled. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-10 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0292 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 05. OTC IP 10. Analytics 11. Technology | Linda Y Nguyen | [11 empty] | Credit Release report changes | Additional updates to be incorporated into the Credit Release Report for R2 IP exposure data for shared customer (Delivery Note total, Backlog total) Only need to display IF customers where both LLP and HLP are Intel Foundry + shared customer in report Need to include correct order/contract/DMR related backlog information (A&D total, DN total, etc.) | During creation of report, only IF related data was considered. Business would like to integrate IP shared customer data into the report to provide a one-stop shop to view all customer exposure. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0292_OTC_Report%20Changes%20for%20R2%20Credit%20Release%20Report.pptx?d=wd5eebe34462741e38539b8b9b0072b3c&csf=1&web=1&e=DxZNnl |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 109 | 0 | [9 empty] | 109 |  |  |  | 0 | 109 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCFR020 | 1 |  | 0 | OTCFR020 | 1 |  | 0 | N/A |  | 2025-03-10 | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-02-18 | Reviewed with OTC leadership and Uzma within ad hoc meeting. Will need to go to CR Meeting with Core Leadership for final approval. |  |  | 2025-02-21 | Marked as "Inform" only. Any questions or concerns should be addressed to Linda Nguyen | [5 empty] | Build | CL/OSC | 2025-02-21 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-10 | 0 | < 15 Days | brianne.ramirez@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0293 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Rishav Kumar | [11 empty] | RTC can not be used for Subcon POs for SIMS ODM Process - LOGI0753_IF | RTC can not be used for Subcon POs for SIMS ODM as RTC requires PO line item with account assignment F and accounting Object – Costing Production Order but for SIMS since its PO-SO Model & it has been decided to use Sales Order no as accounting Object. Since we can’t use both at the same time, it has been decided in SIMS workshop to use Backflush for SIMS ODM Subcon PO and not use RTC & accordingly we have initiated the cancellation of the respective WRICEF for IF environment. | LOGI0753_IF for which FSD & HLTA both are approved but now since SIMS ODM is going to use Backflush instead of Real-time Consumption against Subcon PO due to technical complexity |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI0753_IF |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | No response from team regarding validity. Cancelling as it has been open for far too long | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 02, 2025 | 2025-02-11 | 0 | < 15 Days | rishavkumar4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0294 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | Medium | 13. Security | 13.1 Security - ALL |  | 01. PMO 16. Testing | Nishat Ahmed | [11 empty] | Controls to be mapped at L4 in Signavio | The proposed change involves adding the control IDs and control names to the L4 task level in Signavio process flows. Initially, the control attributes were aligned with Intel to be mapped at the L3 subprocess level; however, it has been requested that these attributes be mapped at the L4 task level to be of valuable use for SOX and Audit purpose. This change will involve mapping and validating the updated L4 level control names, updating the mappings in the Signavio flow accordingly, and ensuring that all control names are accurately reflected at the L4 level to enhance the accuracy and relevance of the control management process. Approval is sought to proceed with this update to meet the revised specifications. | The rationale for this change is to enhance the accuracy and relevance of the control attributes mapping for the SOX & Audit purpose, thereby improving the overall effectiveness of the control management process and meeting the revised specifications. |  | Yes |  |  | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/Shared%20Documents/General/13.%20Bridge/Signavio/Signavio%20Controls%20update/Signavio%20Controls%20Update%20and%20Reapproval%20process.pptx?d=wde2123e2af0d48e181942d76077112e7&csf=1&web=1&e=c259Vo |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | Security | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | o Initially, the team aligned that the controls attribute would be mapped to the L3.  After reviewing the Signavio flow, the SOX and Audit team asked for the mapping to be done at the L4 level. o Signavio processes will be updated by next week. | [9 empty] | Other | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-12 | 0 | < 15 Days | anntam@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0295 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 10. Analytics 18. SCP | shashank.kolhe@intel.com | [11 empty] | To add Disaggregation calculation output (key figure) to reporting | Disaggregation calculation currently stored only in CDP, need to be made available in ECA (Analytics) | This calculation is used extensively during testing and stabilization phases until the solution is well understood and adopted. CDP is a new product, and it does not offer the audit tracking capability to depth and breadth to meet our requirement. This reporting is crucial to support explainability of the calculated forecast |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDD05F85C-5125-489F-BCC9-1931283256D1%7D&file=IP-DP-Disagg-Measure-Reporting-Change%20ID_Tower_CR%20Deck_template.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 80 | 40 | 80 | [6 empty] | 200 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-13 | o This change will allow disaggregation calculations to become available for PDH/ECA for reporting; this was local only when exiting design.  Team explore workarounds, but the capability did not suffice. o Only IP will be affected, and there will be no process change.  CDP, IP PDH, and IP ECA teams will require 1 sprint (2 weeks) to complete the work.  The changes will be intercepted and tested within UAT. | [9 empty] | Build | Tower | 2025-02-13 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0297 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.1 PTP - ALL | Yes | 06. PTP 11. Technology | Rajesh Tol | [11 empty] | Change request to Enable Acceptance at Origin - perform 107 at ASN receipt to enable CPP payment processing | Enable Acceptance at Origin capability for intel which allows transfer of ownership from a financial standpoint based on incoterms | Intel currently has a custom program to accrue PO invoice processing based on ASN receipts. Acceptance at Origin is a recommendation from SAP to achieve financial postings at the time of ASN receipt from the supplier Update as of 11/27: Chandra P and Lars: ​ Standard functionality of "Acceptance at Origin" can be used to avoid having to post an accrual. Please refer to the following section in the SAP Help Create Purchase Order - Advanced ¦ SAP Help Portal, and the corresponding SAP Blog post : Procurement with Origin Acceptance - SAP Community. This functionality posts the relevant FI-AR document (blocked invoice) at the time of shipment from the vendor (technically into stock in transit with movement type 107). The issue with Vendors that do not send ASN's remains. We need to identify a trigger or calculation for vendors that do not send ASN's as to when to create the inbound delivery. ​ With this Standard functionality, most aspects of this proposed RICEFW are obsolete and not justifiable. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0297_PTP_IF_IP.pptx?d=w8e76beb5eff8481a9067ce1cf207fbde&csf=1&web=1&e=b3xaEo |  | 4. Change to Existing RICEFW / ECA/ Build Object | LI-120-080, LI-120-100 |  |  | 30 | 0 | [8 empty] | 30 |  |  |  |  | 0 | 30 | Tech - S/4 | No |  | 0 | N/A |  | PTPE0365, LOGI0502, LOGI0197_IF | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0197_IF​, LOGI0501​, LOGI0502​, PTPE0365_IP, PTPE0365_IF ​ | 5 | LOGI0197_IF​, LOGI0501​, LOGI0502​, PTPE0365_IP, PTPE0365_IF ​ | 5 |  | 0 |  | 0 | N/A |  | 2026-02-13 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-13 | o This CR was created after evaluating design impact for the accruals KDD that was presented to OSC/CL.  A total of 4 RICEFW’s will be impacted, and there are no downstream impacts | [9 empty] | Build | Tower | 2025-02-13 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-13 | 0 | < 15 Days | sumeetrsharma@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0298 | Rejected |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes |  | Ruben David Alvarez Carroz | [11 empty] | Movement type 107 and 109 needs to be applied for all inventoried commodities. | Movement type 107 and 109 needs to be applied for all inventoried commodities. | Movement type 107 and 109 needs to be applied for all inventoried commodities. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI0197 LOGI0501 LOGI0502 |  |  | 1 | 16. Cancelled by Requestor Tower | No |  | 2025-02-13 | [9 empty] | Covered by CR0297 | Other | Tower | 2025-02-13 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-13 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0300 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Creation of Consolidated CMR | Creation of Consolidated CMR | In Old design, When the Confirm button was clicked, the GR was posted automatically in the background, and then system would then evaluate discrepancy results and post a separate CMR document according to different scenarios: a)No Discrepancy: GR was posting immediately but CMR generation occurred only when the discrepancy status at the subline level was marked as "Cleared for Credit." b) Discrepancy Identified : GR was posting immediately but If discrepancies were not resolved through the Discrepancy Action Matrix rules, the subline item was marked as discrepant. Salesforce would then provide the discrepancy resolution, and auto CMR Generation would be generated automatically only when the Discrepancy Status was "Accept = Cleared for Credit" using the same API. This old approach led to challenges in account reconciliation for the business. To improve the reconciliation process during settlement, it was suggested to generate consolidated CMRs based on RMA number, MMID, unit price, original PO, and return PO. In the new design, the process for posting the Goods Receipt (GR) document remains unchanged. However, the consolidated CMR document will now be posted through a separate batch job, which groups subline records based on RMA number, MMID, subline status “Cleared for Credit,” unit price, original PO and Return PO. When the Confirm button is clicked, the GR will be posted automatically in the background and then new batch job program will only consider sublines with the status “Cleared for Credit.” It will then verify that the RMA number, material code (MMID), and unit price are identical across these sublines. If all these criteria match, the program will generate a single consolidated CMR document. Note – If Original PO and Original Invoice Number is needed in CMR and CN then we need to use the custom routine. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0300%20OTC%20IP%20CM%20Item%20Level%20Consolidation.pptx?d=w7699f07e41d6467fad408d8d0551e026&csf=1&web=1&e=l4Tnh8 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | OTCF1629, LOGE1314 |  | OTCF1629, LOGE1314 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-28 | o CR for consolidation of credit memo line items to reduce the number of credit memos issued to customers. o AR: Validate with Keerti for the timeline. If Keerti is aligned, bring through the RICEFW review process. @Park, Ryan | [9 empty] | Other | Tower | 2025-08-28 | 08, 2025 | 08, 2025 | 02, 2025 | 2025-02-13 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0301 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Prabesh Acharya | [11 empty] | R3-GL Interface – Cut-Off date implementation for JE | GL Interface – Cut-Off date implementation for JE A cutoff date restriction should be implemented to prevent Incorrect posting during month-end activities. | Currently, the GL interface architecture does not have Cut-Off date logic implemented to restrict the posting of the Journal Entry in S/4 system after Cut-Off date. A cutoff date restriction should be implemented to prevent Incorrect posting during month-end activities. To limit the posting of journal entries in the S/4 system during month-end activities, a program must be created to determine the cutoff date. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/FPR_GL_GL%20Interface%20%E2%80%93%20Cut-Off%20date%20implementation%20for%20JE%20.pptx?d=we156ca24b78c453fb169f9b29b988fb1&csf=1&web=1&e=q2RhKx |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-010-010 DC-030-040 DC-030-120 |  |  | 30 Hrs | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is less than 40 hours of technical effort | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-14 | 0 | < 15 Days | shubhambpatil@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0302 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 11. Technology | Vivek Prashant Potphode | [11 empty] | Change in the Billing Date for the contract order types and Debit Memo Request to put them on Line item Block (CRED) | Change in the Billing Date for the contract order and Debit Memo Request to put them on Line item Block (CRED) | With this change the Contract orders and Debit Memo Request order types will be put on CRED line item block for Credit hold. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0302_Update%20credit%20horizon%20logic%20for%20contracts%20and%20debit%20memo%20requests%20within%20R2%20credit%20check%20program.pptx?d=w8ec70701265d461b8d7ef773a2edfa73&csf=1&web=1&e=2qgWvo |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 16 | 0 | [8 empty] | 16 |  |  |  |  | 0 | 16 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0067 | 1 | OTCE0067 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | [10 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-17 | 0 | < 15 Days | ritiaggarwal@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0303 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | shkale@deloitte.com | [11 empty] | Cancel Objects: LOGI0336, LOGI0518, LOGI0519_IP, LOGI0520_IP, LOGE0521_IP | Cancel objects added in error under R3 | As part of object tracker update during the approval process of ECD Design of ‘R2’, a few objects were added in assumption that a same design will be followed in R3 IP. However, the R3 Design is quite different from what was developed in R2. The following objects were added in error during the R2 design and are currently sitting in the object tracker causing issues with our reporting and capacity planning. LOGI0336, LOGI0518, LOGI0519_IP, LOGI0520_IP, LOGE0521_IP |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0303,%20CR0476,%20CR0469/FW_%20R3%20FTS_LE%20logistics%20CR%27s%20Requesting%20Cancellation%20approval%20-CR0469,%20CR0303%20%26%20CR0476.pdf?csf=1&web=1&e=fLmiUK |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI0336, LOGI0518, LOGI0519_IP, LOGI0520_IP, LOGE0521_IP |  |  | 5 | 10. OSC/CL Approved (end status) | No | No | 2025-04-10 | [10 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 02, 2025 | 2025-02-17 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0304 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancel Objects: FTSI0560 - SAP IBP to SAP S4 - Planned Independent Requirement Creation (Descoping) | Cancel objects added under R3 | This decision was taken due to process change for ALPS and after consulting client leads (Shilpa/Kim H/Stef M). |  | Yes |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR0304%20-%20Cancel%20Objects%20FTSI0560.pptx?d=w1408fd96b47448499fc8c10e22107c6a&csf=1&web=1&e=awLbOe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0560 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | [10 empty] | Other | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-17 | 0 | < 15 Days | vchaudhari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0305 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 11. Technology | Shiva Shankar Harikrishnan | [11 empty] | Cancellation of Marcom PC update using custom program | The PCH has been revised in S4. Therefore, Business have requested to cancel the RICEFW FPRE0932 | Intel has requirement to update the marcom PCs for accrual calculation using the REICEFW ID FPRE0932. However, in S4, the PCH will have only one Marcom PC. Hence Intel agreed to update the details manually in TVARVC instead of custom program; Cancelled because the requirement will be handled using a variable which will be maintained by business team members. Confirmed by Intel business team |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0932_IF, FPRE0932_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by Uzma offline through email. | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-18 | 0 | < 15 Days | sharikrishnan@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0306 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Rishav Kumar | [11 empty] | Re-bailment ASN from IP to IF via E2O- LOGI0834_IP and LOGE0754_IP(Associated Enhancement) | Inbound interface for WLA Hold scenario to trigger Outbound ASN with Non-Valuated material iDoc up on receiving Inbound ASN with Valuated material from IP-SAP System to e2open system for PTP-IF | Based on the Goods receipt against Production order for WLA Hold scenario, IP SAP system would trigger Outbound ASN data to e2open with Non valuated material., which eventually calls 3B2 from e2open to PTP-IF. |  | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Neetu that this functionality is already taken care of as part of WRICEF – LOGI0834 and supporting enhancement LOGE0754_IP. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-18 | 0 | < 15 Days | rishavkumar4@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0308 | Rejected |  | ERP | R1 (Release 1) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 09A. Master Data | harshaharshavardh@deloitte.com | [11 empty] | Company Codes are not being selected while copying GL's via COPY | Company Codes are not being selected while copying GL's in Manage GL Governance App | This requirement is required for copying Company Codes while copying GL's, as this is a custom change in Legacy MDG. We want to implement the same in current MDG |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9755CFC1-84AF-4612-9CF5-E3D70862727F%7D&file=CR0308_MD_Company%20Codes%20are%20not%20being%20copied%20automatically%20while%20creating%20GL%27s%20via%20copy%25u200b.pptx&wdLOR=c497544B4-79CA-45D1-864F-5D78260B0839&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-03-06 | [9 empty] | Confirmed by Mauricio: CR308 will be developed internally by Intel. | Other | Not Assigned |  | Not Approved | 03, 2025 | 02, 2025 | 2025-02-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0309 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.3 OTC IF - Billing and Rebates |  | 04. OTC IF 11. Technology | Eina Gupta | [11 empty] | Bank Address Logic to be modified to pick from ADRC instead of BNKA for Customer Invoices | Bank Address fields need to be fetched from the ADRC table based on the address number stored in BNKA Table instead of fetching directly from BNKA Table fields for the Customer Invoice Form | Once Treasury team maintained the zip code for bank address, we noticed that SAP standard is concatenating that with the City field in BNKA Table. Currently, only zip code is being fetched from ADRC Table, therefore now, zip code is coming twice on the customer invoice form. Post alignment with business, complete address needs to be fetched from ADRC Table to ensure the address fields come accurately in the Bank Remittance information |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0309_OTC%20IF-Customer%20Billing%20Output%20form%20-%20Bank%20Address.pptx?d=w139b980893c647e188f02882465280be&csf=1&web=1&e=UJ1xkB |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 8 | 0 | [8 empty] | 8 |  |  |  |  | 0 | 8 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCF0054 | 1 | OTCF0054 | 1 |  | 0 |  | 0 | N/A |  | 2025-02-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | o This change request is to update the logic for pulling zip codes and printing it within the form.  Zip code is not available within the BNKA table. o Tech team is aligned with the change and will deliver by ITC3. | [9 empty] | Build | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-19 | 0 | < 15 Days | eigupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0310 | Cancelled |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 11. Technology | Prabesh Acharya | [11 empty] | New Cost Center field addition to GUI & Fiori app | Enhancement is needed in S/4 system (CFIN/IF/IP) to add the "New cost center" (Replacement) attribute in GUI & Fiori apps. | Business users need an ability to validate the “New Cost Center” attribute replication from MDG into CFIN/IF & IP systems. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0310_New%20Cost%20Center%20field%20on%20GUI%20%26%20Fiori%20App.pptx?d=w1bed49c7111542d7bb0644d2402417e7&csf=1&web=1&e=dbjg0S |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-020-030 |  |  | 16 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael Quesada, Kitty Huang, and Scrum lead to not be needed | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-19 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0311 | Approved | 16 Hours of Additional DARC effort | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Prabesh Acharya | [11 empty] | Release change from R2 to R1 for ECA MD reports | Update the release schedule for ECA-Finance MD reports from Release 2 to Release 1 | The business initially requested the ECA-Finance MD reports to be included in Release 1. However, due to constraints in the development team's bandwidth, the build was initially rescheduled to align with the Release 2 build timeline with an understanding reports will be available for testing during the R1 UAT cycle and will be deployed to production in R1. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0311_ECA%20MD%20reports%20release%20change%20from%20R2%20to%20R1.pptx?d=w7ef07adeddcf4f1db80c4508ca47362e&csf=1&web=1&e=bgrvpd |  | 4. Change to Existing RICEFW / ECA/ Build Object | DC-020-010, DC-020-020, DC-020-030 |  |  | 12 | 0 | [9 empty] | 12 |  |  |  | 0 | 12 | ECA | No |  | 0 | N/A |  |  | 0 | FPRXR001 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | FPRXR020​, FPRXR021​, FPRXR022, FPRXV026, FPRXV027, FPRXV031, FPRXV032​, FPRXR034​, FPRXR020_01​, FPRXR021_01​, FPRXR022_01, FPRXV026_01, FPRXV027_01​, FPRXV031_01​, FPRXV032_01​ | 15 |  | 0 | FPRXR020​, FPRXR021​, FPRXR022, FPRXV026, FPRXV027, FPRXV031, FPRXV032​, FPRXR034​, FPRXR020_01​, FPRXR021_01​, FPRXR022_01, FPRXV026_01, FPRXV027_01​, FPRXV031_01​, FPRXV032_01​ | 15 |  | 0 | FPRXR001, FPRXV001_01 |  | 2025-01-10 | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved by Uzma through offline email o This one related to one of the late cycle CRs that we received after our intake for R1/R2 was already closed. We committed to delivering this for R2 but agreed to pull this ahead into R1 since we were able to get this ready in time. o This should help the FPR team automate some of the data validation steps in R1 UAT2 and pull ahead the test cases for reporting to earlier weeks of testing. | [9 empty] | Build | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-19 | 0 | < 15 Days | navnegi@deloitte.com | No | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0312 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR 11. Technology | Esha Esha | [11 empty] | Descope of the object - FPRE0534 Accounting for Disti Rebate Accrual on Ending On Hand Inventory, Unissued Returns & In Transit Deferral | To simplify the current solution for Disti & Direct RICEFW related to both In transit & Rebate return accrual components we have proposed a solution wherein we will proceed with incorporating the logic and calculation of Disti – (FPRE0534-Acc for Disti Rebate Accrual on Ending On Hand Inventory) in FS – FPRE0477 Rebate for Direct Customer. | This approach will further satisfy the requirement of In transit Deferral posting for both Disti & Direct customers as a part of single RICEFW which is FPRE0477, thereby eliminating the requirement for separate development object for Disti i.e., FPRE0534. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Phase%200/02.%20Process%20Integration%20Architecture/04.L2-L3%20Details/Final%20Documents/Change%20in%20L2%20L3/FPR/EXT%20RE%20RAR%20-%20Approval%20required%20for%20cancellation%20of%20object%20-%20FPRE0534.msg?csf=1&web=1&e=fbgLiR |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0534 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-25 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-25 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-19 | 0 | < 15 Days | esesha@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0314 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 09B. Data Migration 11. Technology | Karthik Reddy Reddy | [11 empty] | New requirement change in the business process due to IP-IF Turnkey order and which impacts FTSI0209 RICEFW objects | To include PROC materials production orders and Turn Key ordering process in FTSI0209 object, we may require to update the above mentioned RICEFW objects. | FTSE0592 deals with the customization of “API” which transfers “User Fields” data those user fields deal with capturing DCR data and DPAS rating. As we are heading with BAPIs instead of APIs from BODS system, we are cancelling the object FTSE0592 and capturing this document’s purpose in FTSI0209. As per IP-IF alignment, we are including transferring of WLA PROC production order’s BoM changes into IP SAP S4 HANA system and documenting the process in FTSI0209 As BODS cannot transfer the data through APIs as per Intel BODS POC, we may need to update the mapping sheet of FTSI0209 object with BAPI fields |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEA68108E-4ED8-44B0-AC84-52EF46092E15%7D&file=INT-CR0314%20-%20New%20requirement%20change%20in%20the%20business%20process%20due%20to%20IP-IF%20Turnkey%20order%20and%20VMILAFI%20process%20which%20impacts%20two%20RICEFW%20objects%2C%20FTSI0209%20and%20FTSI0210.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 | [8 empty] | 80 |  |  |  |  | 0 | 80 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | FTSI0209 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0209​, FTSE0592​_IP | 2 | FTSI0209​, FTSE0592​_IP | 2 |  | 0 |  | 0 | N/A |  | 2026-02-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | o Prior to Turnkey order design, the original design was to create a production order in one step.  With the introduction of PROC materials in WLA, the process is now 2 steps: production order creation and a BOM change. o Therefore, some existing objects will need to be remodeled to fit this new design.  There are no boundary app implications, but there will be some process and technical change.  This will only affect the integration between PDH and S4. | [9 empty] | Build | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-19 | 0 | < 15 Days | karthreddy@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0315 | Approved |  | SCP | R2 (Release 2) | High | 05. OTC IP | 5.1 OTC IP - ALL |  | 05. OTC IP | sandeep.sastry@intel.com | [11 empty] | BY IBP Custom Reporting Solution | The problem is the native BY reporting capability (workbench) uses the heuristic solver rather than the LP solver that is used for the actual build plan. We are working with BY to address what they can within the product, but we are not confident that they will be able to address all critical items within the R2 timeline. As such, we are planning on building custom reports that would supplement the native BY capabilities and enable visibility to the underlying LP solve data. Hope that helps – adding Sandeep who can provide further details. | This difference is resulting in discrepancies that are being raised as critical defects during the business validation. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR0315%20-%20BY%20IBP%20Custom%20Report.pptx?d=w0e1dea2a95794245b55b833c77cdfa13&csf=1&web=1&e=AbhbmT |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 200 | 120 | 240 | 0 | [6 empty] | 560 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-20 | o This change is to create reports that will utilize the BY IBP data; the current view is distorted.  The MVP for R2 will be further expanded upon in R3, and the work initiated by this CR is scalable.  Most of the work will be done by the CDI Team. All 3 teams (CDI, PDH, and BY) are aligned to ingest the work. o Testing will be done in UAT2.  To mitigate this risk, the team will work with the operations team through the process during the first month.  By the second month cycle, the team plans to work out all of the bugs. o The business team is working to align on the definition of the MVP, and the alignment will be concluded during the 15 week development. |  |  | 2025-03-21 | • CR0315 - BY IBP Custom Reporting Solution approved with the understanding that further work is needed to finalize timelines and resources. • Proposal for an MVP version of offline reporting due to issues with the heuristic solver in BY, IBP. • BY is working on options to address this gap in their current SW functionality. Mike Lange is engaged with BY. The request is to resolve by R2 however it’s not clear if this would be completed within this timeline. • Identified risks include resource allocation and alignment with business stakeholders. • Emphasis on the need for control over external reporting to prevent dependency on non-standard solutions. • Discussion on the necessity of offline reports for undistorted views and cycle analysis. • Agreement on the need for governance and approval for any external reporting solutions. • The requirements have been defined by the business and IT has responded. • It was agreed that any additional reporting use cases outside of BY require Core Leadership Team approval. This is to ensure that the use of external solutions is controlled and justified. | [5 empty] | Build | CL/OSC | 2025-03-21 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0316 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 09A. Master Data 09B. Data Migration | Linda Y Nguyen | [11 empty] | R2 Payer Master Data Conversion | Data Conversion: Replicate IF LLPs with new number/account in MDG/IF S/4 Changes needed: 1) For the LLPs, create new LLP with new # in new MDG under both 101/AM21 & 798/SG01. 2) Delink the old LLP from existing Sold To under IP LE/sales area and link the new LLP to the existing Sold To under IF LE/sales area. | Payers act as subledgers, which is why we need to keep IP related payers separate from IF payers to keep financial postings on the subledgers separate. This is common Intel practice for any large M&A activities where we separate business by LE. By keeping financial postings on separate subledgers, we avoid multiple financial reconciliation issues such as: cross-company postings, misdirected cash postings, etc. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0316_OTC%20IF_R2%20Payer%20Master%20Data%20Conversion.pptx?d=w61fc36149934478c92b124d29c171cf3&csf=1&web=1&e=jEhXPr |  | 4. Change to Existing RICEFW / ECA/ Build Object | NA |  |  | 40 | 0 | [10 empty] | 40 |  |  | 0 | 40 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0182_IF​, DATC0179_IF, DATC0184_IF​ | 3 | DATC0182_IF​, DATC0179_IF, DATC0184_IF​ | 3 |  | 0 |  | 0 | N/A |  | 2025-03-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | o With the shift in legal entities, this change is to enable new financial transactions on the new legal entities.  This was discovered in this MC cycle as the team has started to analyze the effect on ECC and G/L and Sales teams.  This change will not affect the underlying MDG code. | [9 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | matthfisher@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0317 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 18. SCP | joseph.t.chen@intel.com | [11 empty] | IP Demand - Node Creation | To further fine tune the daily batch process for base-level node creation to include the following measures: BAB, Backlog RMAD, Backlog RGID and Delq Backlog RGID | Base-level node must exist in BY-CDP in order to consume the transactional data listed above |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP-DP-Nodes.pptx?d=w15776872da864e96865ad8c8034b262f&csf=1&web=1&e=EMkWmZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 60 | 0 | 0 | [6 empty] | 60 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | o Missing nodes were identified during load of transactional data.  Capability is needed in the complete solution, and this change will be to create nodes. 4 other data elements will be brought in as sources.  Work will be completed by PDH team and will be completed by 2/28. | [9 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0318 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 09B. Data Migration 11. Technology | Prashant Chauhan | [11 empty] | Descope of the Object - FPRC0914 Conversion of Forecast data from BPC to SAC through BODS and Flat file load. | We initially planned to use BODS (BusinessObjects Data Services) for pushing historical data from BPC (Business Planning and Consolidation) to SAC (SAP Analytics Cloud) by performing the necessary conversions. Upon further review, we realized that BPC can handle the conversions, allowing us to export the data directly to SAC using standard connections. Therefore, we have decided to cancel the RICEFW. | This approach will further simplify the process and third party conversion tool and connections are not needed here. BPC will handle the conversions and SAC will pull the data from the Source BPC with 1:1 mapping. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRC0914 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | mmaheshreddy@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0319 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology 17. B-App | VIJASHARMA@DELOITTE.COM | [11 empty] | CR for VMI interfaces(PTPI0368 and PTPI0671) to include supplier initiated change scenarios | Currently RICEFW objects PTPI0368(Supplier shipment inbound from E2Open to S/4) and PTPI0671 (Response to inbound message to E2Open) contain receiving shipment message and creating PO and Inbound Delivery documents in S/4. The automation of supplier initiated changes is not included as part of these RICEFW objects. The to-be process with technical team is aligned with efforts required. | If the supplier initiated changes are not included in the existing RICEFW objects, business needs to manually clean up the incorrect PO and Inbound delivery documents in SAP S/4 and EWM systems. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Vijay that the changes are only needed in RICEFW PTPI0368, and the total effort is less than 40 hours of technical effort. Therefore, the CR has been moved to the Build CR Log. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0320 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Amit Kumar | [11 empty] | Cancellation of FPRI0910_IF-Import Projects, WBS elements & Hierarchies from S4 to HAT​ | Now this will be a interface between ECA and HAT so Intel business has asked to cancel this object. | Initially requirement was to export Project and WBS Element related fields from S4 to HAT for headcount allocation however later on it was decided to export these fields from ECA to HAT as these fields will be available in the ECA. Intel has asked to cancel this object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0910_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | amitkumar55@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0321 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Amit Kumar | [11 empty] | Cancellation of FPRI0910_IP-Import Projects, WBS elements & Hierarchies from S4 to HAT​ | Now this will be a interface between ECA and HAT so Intel business has asked to cancel this object. | Initially requirement was to export Project and WBS Element related fields from S4 to HAT for headcount allocation however later on it was decided to export these fields from ECA to HAT as these fields will be available in the ECA. Intel has asked to cancel this object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0910_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | amitkumar55@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0322 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Amit Kumar | [11 empty] | Cancellation of FPRI0911_IF-Import cost center hierarchy from S4 MDG layer to HAT | Now this will be a interface between ECA and HAT so Intel business has asked to cancel this object. | Initially requirement was to export Cost Center hierarchy related fields from S4 to HAT for headcount allocation however later on it was decided to export these fields from ECA to HAT as these fields will be available in the ECA. Intel has asked to cancel this object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0911_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | amitkumar55@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0323 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Amit Kumar | [11 empty] | Cancellation of FPRI0911_IP-Import cost center hierarchy from S4 MDG layer to HAT | Now this will be a interface between ECA and HAT so Intel business has asked to cancel this object. | Initially requirement was to export Cost Center hierarchy related fields from S4 to HAT for headcount allocation however later on it was decided to export these fields from ECA to HAT as these fields will be available in the ECA. Intel has asked to cancel this object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0911_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by Uzma offline through email. ECA number to be added in the comments | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | amitkumar55@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0325 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Prashant Chauhan | [11 empty] | Descope of the object - FPRI0912_IF, FPRI0912_IP Interface between HAT and SAC using Mulesoft | As per the revised direction from the system architecture team, SAC will be feeding into ECA and HAT will source HC information from ECA. | There is no need for the interface between HAT and SAC. As SAC will directly be feeding into ECA and HAT will source HC information from ECA. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0912_IF, FPRI0912_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved in offline email to Shane and Uzma | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | mmaheshreddy@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0327 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Prashant Chauhan | [11 empty] | FPR - Cancellation CR for RICEFW - - FPRE0893_IF, Derive FCS FTQ data by Capex WBS L2 & Mfr. Process Node CC | There is a RICEFW FPRE0882_IF which was already approved by business in Sprint 9. | FPRE0893_IF was created in error, and a duplicate object (FPRE0882) has been created for the same requirement. The functional specs have been completed for the correct object RICEFW FPRE0882 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0893_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-03 | Approved by Uzma through offline email | [9 empty] | Other | Tower | 2025-03-03 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | mmaheshreddy@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0328 | Approved |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | [11 empty] | Additional changes for the Recon Report | 1. Add filters to the detailed view similar that in summary view 2. Line item view should also run as a standalone report 3. Display the output only after user inputs 4. Provide range in all input filters 5. Add company code filter in all CO reports | Intel requires the modification to the recon reports to increase the performance of the report and also increase usability |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0328_%20Additional%20Changes%20to%20the%20Recon%20report.pptx?d=w4ba0bb38f075420081ef496879010702&csf=1&web=1&e=wIe5gQ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 32 | 0 | [9 empty] | 32 |  |  |  | 0 | 32 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV033​, FPRXV034​, FPRXV035​, FPRXV036​ | 4 |  | 0 | FPRXV033​, FPRXV034​, FPRXV035​, FPRXV036​ | 4 |  | 0 | N/A |  | 2025-03-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | • Similar to 359, but instead of addressing base performance defect above, this CR is adding some additional slicer flexibility so users can drill into better identify outliers in the reconciliation report. | [9 empty] | Build | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-20 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0329 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli | [11 empty] | ​ Consider the latest output processed for order Confirmation | Consider the latest output processed for order Confirmation, order status and significant change outputs and remove the non-processed outputs at the day end when batch job is executed to send the details to the customer | Minimize redundant outputs to customers by considering the latest output triggered.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE65ACC09-6905-41E7-94ED-64305AF369E2%7D&file=INT-CR0329-Consider%20the%20latest%20output%20processed%20for%20order%20Confirmation.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 26 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Brianne that the OTC IF team has cleared another option with legal | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-21 | 0 | < 15 Days | brianne.ramirez@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0330 | Approved |  | ERP | R2 (Release 2) R3 (Release 3) | Medium | 11. Technology | 11.3 Technology - Middleware |  | 12. Infrastructure | Vijay Mavuduru | [11 empty] | Capture additional detail during Mulesoft logging; to be used for B2B dashboard | Capture additional attributes in the payload that is logged in DBAAS database to be used for representing in B2B Dashboard. This change is needed only for B2B MuleSoft Interfaces.Capture additional attributes in the payload that is logged in DBAAS database to be used for representing in B2B Dashboard. This change is needed only for B2B MuleSoft Interfaces. | As part of the B2B payload logging in database, Intel has requirement to also capture additional attribute whenever a transaction is initiated in MuleSoft for B2B interfaces. This change is only for the B2B interfaces that are ‘Build’ complete for R2 and R3 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Technology/CR%200330-%20B2B%20MuleSoft%20Interface%20Enhancement.pptx?d=w1fa6aae1e9a448899a630e68219cb1bd&csf=1&web=1&e=5vO2Ub |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 92 | 0 | [8 empty] | 92 |  |  |  |  | 0 | 92 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0042, OTCI0047, OTCI0301, OTCI0302, OTCI0275, OTCI076, OTCI0043, LOGI0612, OTCI0038, OTCI0060, PTPI0136_IP, PTPI0136_IF, PTPI0138_IP, PTPI0138_IF, PTPI0140_IP, PTPI0140_IF, PTPI0142_IP, PTPI0142_IF, PTPI0144_IP, PTPI0144_IF, LOGI0237_IP, LOGI0237_IF, OTCI0257, OTCI0258, LOGI0415, PTPI0134_IP, PTPI0134_IF, PTPI0369_IP, PTPI0369_IF, OTCI0296, OTCI0414, LOGI0157_IP | 32 | OTCI0042, OTCI0047, OTCI0301, OTCI0302, OTCI0275, OTCI076, OTCI0043, LOGI0612, OTCI0038, OTCI0060, PTPI0136_IP, PTPI0136_IF, PTPI0138_IP, PTPI0138_IF, PTPI0140_IP, PTPI0140_IF, PTPI0142_IP, PTPI0142_IF, PTPI0144_IP, PTPI0144_IF, LOGI0237_IP, LOGI0237_IF, OTCI0257, OTCI0258, LOGI0415, PTPI0134_IP, PTPI0134_IF, PTPI0369_IP, PTPI0369_IF, OTCI0296, OTCI0414, LOGI0157_IP | 32 |  | 0 |  | 0 | N/A |  | 2025-04-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-06 | o This change is to add additional attributes to support a dashboard that is being built to track the utilization of B2B interfaces.  All interfaces in build are being updated with this attribute, but there are 32 R2/R3 B2B interfaces that are already built and will require rework.  There is no functional or testing requirement. The MuleSoft team will check on the backend that the correct attributes are being pulled in. | [9 empty] | Build | Tower | 2025-03-06 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | anntam@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0331 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes |  | debradas@deloitte.com | [11 empty] | Create transformation logic for GEWEI field | Create transformation logic for GEWEI field ,as Open text is compatible with only KGM,GRM and LB units | if not fixed, Customer ASN will be fail in Open text and ASN will not send to customer |  | No | [8 empty] | 4 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Deb to be Cancelled as the team cannot perform the work. |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-21 | 0 | < 15 Days | brianne.ramirez@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0332 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 11. Technology | Ruben David Alvarez Carroz | [11 empty] | Changes for CI/PL FORMS coming from ITC2 observations | Changes for CI/PL FORMS coming from ITC2 observations | These changes are new requirements as these were not identified during the initial development hence these changes require an FSD update and development. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0209_OTC%20IF_CR.pptx?d=w4a0804a26e0a477181da0f2f9d3c2fb2&csf=1&web=1&e=jdgeGU |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 38 | 0 | [8 empty] | 38 |  |  |  |  | 0 | 38 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0343_IF​, LOGF0344_IF​​, LOGF0345_IF​​, LOGF0348_IF​​, LOGF0353_IF​​, LOGF0346_IF​​, LOGF0357_IF​​, LOGF0347_IF, LOGF0342_IF​​, LOGF0354_IF​​ | 10 | LOGF0343_IF​, LOGF0344_IF​​, LOGF0345_IF​​, LOGF0348_IF​​, LOGF0353_IF​​, LOGF0346_IF​​, LOGF0357_IF​​, LOGF0347_IF, LOGF0342_IF​​, LOGF0354_IF​​ | 10 |  | 0 |  | 0 | N/A |  | 2025-03-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | o The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary apps.  The affected interfaces are PO outbound and uses IDOC to send necessary PO data to boundary apps. o Only the PTP, Logistics, and Tech team will be affected, and they are all aligned to make the changes. | [9 empty] | Build | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | anntam@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0333 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 11. Technology | Ruben David Alvarez Carroz | [11 empty] | Wafer/Die Bailment Commercial Invoice for Spire | To align to new requirements for a new customer deal (Spire), changes are being made to the existing Intel Commercial Invoice and Packing List in ECC. To remain compliant to this customer request, we will need to make the changes to our existing Wafer/Die Commercial Invoice in time to launch in R2. Customer is requesting Intel include the Intel batch in the “Customer Lot” field. | Align designed document for R2 with customer requirement of including Intel Batch information in the “Customer Lot” field. Change is being made in ECC to the existing Commercial Invoice and Packing List. Changes to IF document in S/4 will be required. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-BUILD-CR0210%20Wafer-Die%20Bailment%20CI%20and%20PL.pptx?d=w466b9d1f1cdc47aeac865b8b019ffdc0&csf=1&web=1&e=dYvl5X |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 8 | 0 | [8 empty] | 8 |  |  |  |  | 0 | 8 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0357_IF​, LOGF0347_IF | 2 | LOGF0357_IF​, LOGF0347_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-03-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-20 | o With the decision of using SAP IBP, this change is to descope the RICEFW related to ERP: FTSI0560. o AR: Update deck to reflect changes. - @Lingam, Sekhar @Alpha, Michael | [9 empty] | Build | Tower | 2025-02-20 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | anntam@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0334 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Bapuji Reddy | [11 empty] | Cancellation of PTP Objects in Sprint 10 - Build | Cancellation of Sprint 10 Objects for Enable Payments and Procurement Scope: 1. PTPI0670_IP Non PO tool interface to send invoices not linked to a Purchase Order to SAP for processing - PTP 2. PTPI0670_IF Non PO tool interface to send invoices not linked to a Purchase Order to SAP for processing - PTP 3. PTPI0811_IP Intel WebSuite – Web Invoice – Interface to send invoice request data to B2B Staging DB eInvoice/ePO and back to S4 4. PTPI0811_IF Intel WebSuite – Web Invoice – Interface to send invoice request data to B2B Staging DB eInvoice/ePO and back to S4 5. PTPI0814_IP Intel B2B – XML (3C3 & 810) – Interface to send B2B invoice request data from Supplier to B2B Staging DB eInvoice/ePO and back to S4 6. PTPI0814_IF Intel B2B – XML (3C3 & 810) – Interface to send B2B invoice request data from Supplier to B2B Staging DB eInvoice/ePO and back to S4 7. PTPE0728_IP Enhancement for MIRO, MRRL and MRKO from SAP to Readsoft _IP 8. PTPE0728_IF Enhancement for MIRO, MRRL and MRKO from SAP to Readsoft _IF | Business concluded that due to customized complex logics and large data sets, interfaces are better addressed via ECA instead of S4 ERP. So objects are descoped from Enable Payment Scope. For PTPE0728_IP & IF - ReadSoft will handle the customization to capture the standard posting and create the PD Document instead. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0334?csf=1&web=1&e=bqayTa |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0670_IP, PTPI0670_IF, PTPI0811_IP, PTPI0811_IF, PTPI0814_IP, PTPI0814_IF, PTPE0728_IP, PTPE0728_IF |  |  | 8 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | mmalhan@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0337 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Kolleru Venkatesh | [11 empty] | Descope these objects : FTSI0411,FTSI0254,FTSI0688,FTSE0798, FTSI0829,FTSE0756,FTSE0788, FTSE0789,FTSI1101,FTSE0757,FTSI0861 | Email approval attached. GPO approved these objects no more required, hence cancelling these objects FTSI0411- This will be managed locally in PDF supported by calls into ECA FTSI0254– This will be managed locally in PDF supported by calls into ECA FTSI0688- agreed this is not a valid scenario FTSE0798– This is moving to PDF/ECA FTSI0829- This is moving to PDF/ECA FTSE0756- – Not needed as above objects are moving out of S4 FTSE0788-Aligned with Kim, Sunil and Kumar that this will be owned by SCP IT team FTSE0789-Aligned with Kim, Sunil and Kumar that this will be owned by SCP IT team FTSI1101- Not required as this will be managed through the 7B1 changes FTSE0757- – Aligned , this feed will come from FSCO. We are replacing this with an interface RICEF. FTSI0861– Aligned with Devendra that this does not require a separate RICEF, a previous RICEF for creating new production orders can be reused. | Email approval attached. GPO approved these objects no more required, hence cancelling these objects "Email approval attached. FTSI0411- This will be managed locally in PDF supported by calls into ECA FTSI0254– This will be managed locally in PDF supported by calls into ECA FTSI0688- agreed this is not a valid scenario FTSE0798– This is moving to PDF/ECA FTSI0829- This is moving to PDF/ECA FTSE0756- – Not needed as above objects are moving out of S4 FTSE0788-Aligned with Kim, Sunil and Kumar that this will be owned by SCP IT team FTSE0789-Aligned with Kim, Sunil and Kumar that this will be owned by SCP IT team FTSI1101- Not required as this will be managed through the 7B1 changes FTSE0757- – Aligned , this feed will come from FSCO. We are replacing this with an interface RICEF. FTSI0861– Aligned with Devendra that this does not require a separate RICEF, a previous RICEF for creating new production orders can be reused." |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0411, FTSI0254, FTSI0688, FTSE0798, FTSI0829, FTSE0756, FTSE0788, FTSE0789, FTSI1101, FTSE0757, FTSI0861 |  |  | 11 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | kollevenkatesh@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0338 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Sindhuja Gangireddy | [11 empty] | Cancellation of OTC IF objects: OTCE1121, OTCE0485 | GPO approved these objects no more required, hence cancelling these objects | Objects Descoped |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Brianne to not be required. Therefore, the CR is cancelled. | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 02, 2025 | 2025-02-21 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0339 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Sindhuja Gangireddy | [11 empty] | Cancellation of OTC IP objects: OTCI0539, OTCM018_IP, OTCI0436, OTCI0437,OTCI0740 | GPO approved these objects no more required, hence cancelling these objects | OTCI0539:​ Sales order which is created in S4 without any filter data will be landed in the ECA S4 Zone then SF DW will have the generic view for consumption.​ PDH will apply the Business Rule ( like GTS check, Credit check etc.) to filter the data which is relevant for scheduling.​PDH will send data to BY ESP for Scheduling and ESP planning ​ OTCM018_IP:​ Earlier created as a Manual conversion object, but Material ratio table (GPU Products) is not required as per the design in IP R3. Confirmed over mail by Shawn to remove from object list.​​ OTCI0436:​ Change trigger mentioned in the object OTCI0436 (Inbound on order change) is not applicable because once IRC2 fulfills the sales order there will be no new changes made. Once IRC@ creates IRC2 order for an SAP sales order and PO combination(Transaction ID generated), no new IRC2 order or changes to the order will be done.​ OTCI0437:​ Change trigger mentioned in the object OTCI0437 (Inbound on order change) is not applicable because once IRC2 fulfills the sales order there will be no new changes made. Once IRC@ creates IRC2 order for an SAP sales order and PO combination(Transaction ID generated), no new IRC2 order or changes to the order will be done.​ OTCI0740:​ Since this RICEFW object is specific to Panasonic label data intake that was not approved for migration to S4, its scope needs to be excluded from the build. As the object is not GPO approved, this RICEFW object should be excluded in the scope.​ |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0339?csf=1&web=1&e=Qe0NUh |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0539, OTCM018_IP, OTCI0436, OTCI0437,OTCI0740 |  |  | 5 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-21 | [10 empty] | Other | Tower | 2025-03-21 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | kgajananchaporkar@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0340 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 11. Technology | Kaushik Mhatre | [11 empty] | FPR - Cancellation of RICEFW object FPRE0498_IP & FPRE0498_IF (GIT accruals) | FPR - Cancellation of RICEFW object FPRE0498_IP & FPRE0498_IF (GIT accruals) - Reason : implemented 107/ 109 movement type which will post GR and hence accrual will be posted automatically STD SAP Process via F.19 GR/IR reclass. Hence RICEFW is not needed any more. | Approach was changed per SAP guidance and now the objects have been logged under Logistics tower as per the new approved design from the OSC/CL. Finance will not need to handle these RICEF’s |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0498_IP, FPRE0498_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by Uzma offline through email. ECA number to be added in the comments | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | kamhatre@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0341 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV013 (Capital Prepaid View) | FPR - Cancellation of ECA View object- FPRXV013 (Capital Prepaid View) - Since we have this report covered in R1/R2 (FS in the link- FDS_Capital_Prepaid_Capital.xlsx ), thus we will not require this report. The details will be further covered in the PO report which is covered in the future sprint. | Report requirement was withdrawn by business |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV013 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-03 | Approved offline through email to Uzma | [9 empty] | Other | Tower | 2025-03-03 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | kamhatre@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0342 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Taposh Ganguli | [11 empty] | ​ Blanket CR for ITC2 testing Defects | Further to the discussion with PMO and tech team, blanket CR has been created to address some of the issues highlighted in ITC2 testing | One blanket CR to address all the issues highlighted in ITC2 which needed a change request |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR_0342_OTC%20IF%20Blanket%20CR%20ITC%20Defects-.pptx?d=w1bf60aaeb0da46fb9501c636374a8fc0&csf=1&web=1&e=mxZosl |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 66 | 0 | [8 empty] | 66 |  |  |  |  | 0 | 66 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0042​, OTCI0047​, OTCI0043​, OTCI0301​, OTCI0302 | 5 | OTCI0042​, OTCI0047​, OTCI0043​, OTCI0301​, OTCI0302 | 5 |  | 0 |  | 0 | N/A |  | 2025-03-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-25 | Approved offline via ad hoc meeting with Uzma | [9 empty] | Build | Tower | 2025-02-25 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-21 | 0 | < 15 Days | tganguli@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0343 | Approved | 24 hours of configuration | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | 1. FS Item restriction - mandatory trading partner 2. Consolidated data validation | Change 1: Trading Partner validation set up in Group Reporting​ To implement a validation in Group Reporting that will prevent a posting to an Intercompany GL Account without a TP​ ​ Change 2: Update Cons Validation task in Group Reporting​ Modify task to include additional IC elimination/reclass GLs to alert Consolidation Analysts about outages. ​ | Change 1: Ensure JEs posted to an IC GL includes TP so intercompany eliminations can be completed accordingly. ​ Change 2: To include all Interco GLs/reclass so it provides Conso Analysts an initial view of Interco outages at GL level.​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBD4BFAB3-F951-4897-981D-8D73246E75C1%7D&file=INT-CR0287_R1%20Trading%20Partner%20Config.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 24 | [5 empty] | 0 | 24 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | • In UAT it was identified a validation is needed to prevent journal entries being posted to intercompany general ledger accounts without a trading partner included, as well as, inclusion of an alert for users that there is an intercompany outage. | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-22 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0344 | Approved | Need to add in RICEFW ID of Report | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics 13. Security | Rea Meyer | [11 empty] | 1. Two new views of Op Segment report in S4 - OPEX and COS | Request from the business to include COS and OPEX fields in Fiori and ECA Operating segment reports​ ​ The reports need to show the following by segment, in addition to existing FS:​ COS (COGS, INVI OCOS and PCOS)​ OPEX​ | New segment reporting requirements associated with ASU 2023-07 need to be implemented. Disclosure of significant expenses regularly presented to the CEO, such as COS and OPEX is required, and this is a business process change for 2025.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6862CE95-44F5-4910-A8C7-1AE3F8B98F37%7D&file=INT-CRXXXX_R1_Op_segment_COS_OPEX.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 29 | 1 | [9 empty] | 29 |  |  |  | 0 | 29 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved offline with Uzma There is no ECA development on this item from my understanding. This is for Tech (Fiori) and DARC (FPR Tower) to confirm. | [9 empty] | Other | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-22 | 0 | < 15 Days | kdey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0345 | Approved |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 02. E2E Process Integration 04. OTC IF | KEVIN.W.LI@INTEL.COM | [11 empty] | ATM Harvest for Repurpose with SIMS transition to Jabil | Due to SIMS lights off, all SIMS business will transit to ODM (Jabil), thus team need change current harvesting for repurpose process | Due to SIMS lights off, all SIMS business will transit to ODM (Jabil), thus team need change current harvesting for repurpose process |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR0345_Harvest%20for%20repurpose%20Rev2.pptx?d=w8006b88999b14afeaa6c52236507773c&csf=1&web=1&e=iJsh8e | New Requirement / Scope | 1. Process Scope / Design Change |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-27 | o When design was closed, the team was working with the assumption that the Harvest process would be done external of SAP.  However, with a change in requirements, the process will be pushed back into SAP/ODM. o The E2E is finalizing details of the high-level flow, but an assessment is required.  The team does not anticipate additional RICEFW’s and is leaning towards the standard functionality, but the process |  |  | 2025-03-21 | • The integration is necessary to avoid customs compliance exposure, and the team is pushing back on major customizations due to the limited impact on the business. There are no significant RICEFWs anticipated as it has been communicated that no major customization will be supported for this effort. • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-03-21 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0346 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 09A. Master Data | Yashrshah@deloitte.com | [11 empty] | Change in ownership of FS: FPRW0930 and FPRE0929 to MDG Team | Change in ownership of FS: FPRW0930 and FPRE0929 to MDG Team | Change in ownership of FS: FPRW0930 and FPRE0929 to MDG Team. Development under way by MDG team. MDG Finance is the correct owner of the objects |  | No |  |  |  |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved offline through email to Uzma. FPR objects to be sunsetted, and MDG objects will be created and linked. | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | web-form@smartsheet.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0347 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Poonam Dhouni | [11 empty] | To merge RICEFW OTCI0662 into OTCI0291 and cancel OTCI0662 | To merge RICEFW OTCI0662 into OTCI0291 and cancel OTCI0662 as the acknowledgement is handled synchronously and does not need an separate RICEFW | To merge RICEFW OTCI0662 into OTCI0291 and cancel OTCI0662 as the acknowledgement is handled synchronously and does not need an separate RICEFW |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0347/RE%20CR347-status.msg?csf=1&web=1&e=nOBusC |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0662 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0348 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 11. Technology | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: 1.FTSI0834_IF (Duplicate object ID created) 2. FTSE0592 (BODS can not call custom API or Standard API to update the user fields) | Cancel objects added under R3 | FTSI0834_IF: Logistics team would be handling the ‘Bailment process’ from Intel Products to Intel Foundry. Therefore, it is indispensable to make this duplicate RICEF ID as an Obsolete. FTSE0592: There is a requirement to update production order operations with user fields data. “User fields” are available in standard BAPI, but not in the “standard operations API”., but we went ahead with usage of API by customizing, because APIs would be the primary source of transferring the data between two systems. As per the instructions from Intel BODS Data Services POC, we are supposed to use RFC calls i.e. custom or standard BAPI’s for loading data into S4 systems rather than APIs. This RICEFW ID FTSI0592 deals with the Customization of ‘standard API’ to load user fields data into the IP SAP HANA system. |  | Yes |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDF9931A8-D20C-4C3C-8A64-726FFA0FEF3D%7D&file=INT-CR0348%20-%20Cancel%20Objects%20FTSI0834_IF%2C%20FTSE0592.pptx&action=edit&mobileredirect=true |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0834_IF, FTSE0592 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | akindore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0349 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 11. Technology | Rishav Kumar | [11 empty] | Cancellation of WRICEF - LOGI1063 & LOGI1072 | Cancel Object | LOGI1063- Functionality merged into existing WRICEF – LOGI0954 & LOGI0502 LOGI1072- Functionality merged into existing WRICEF – LOGI0954 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1063, LOGI1072 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | rishavkumar4@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0350 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology | Aditya Tiwari | [11 empty] | Cancellation of RICEFW Object: LOGI1151 (Duplicate object ID created) | Cancel Object added under R3 | LOGI1151 object needs to be descoped/Cancelled as this was created as a duplicate object ID for LOGI1063. The requirements are already covered in the other object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1151 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-24 | 0 | < 15 Days | aditiwari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0351 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Bapuji Reddy | [11 empty] | Cancellation of PTP- Enable Payable Objects | Cancellation of PTP- Enable Payment Objects- 1. PTPI0815_IP Intel B2B – XML (3C6) Remittance Invoice – Interface to send B2B Remittance Invoice (3C6) data to Supplier from EDW 2. PTPI0815_IF Intel B2B – XML (3C6) Remittance Invoice – Interface to send B2B Remittance Invoice (3C6) data to Supplier from EDW 3. PTPI0813_IF Intel WebSuite – Pmt Tracker – Interface to get Invoice and Payment status data from B2B Staging DB eInvoice/ePayment tables from S4 4. PTPI0813_IP Intel WebSuite – Pmt Tracker – Interface to get Invoice and Payment status data from B2B Staging DB eInvoice/ePayment tables from S4 5. PTPI0264_IP Intel WebSuite – Web Invoice – Send invoice request data to Staging DB B2B eInvoice/ePO_IP 6. PTPI0264_IF Intel WebSuite – Web Invoice – Send invoice request data to Staging DB B2B eInvoice/ePO_IF | Business concluded that due to customized complex logics and large data sets, interfaces are better addressed via ECA instead of S4 ERP. So objects are descoped from Enable Payment Scope. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0351%20%26%20CR0374?csf=1&web=1&e=J5wtnI |  |  | 5. Cancel RICEFW / ECA / Build Object | PM-150-130 |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0815_IP, PTPI0815_IF, PTPI0813_IF, PTPI0813_IP, PTPI0264_IP, PTPI0264_IF |  |  | 6 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | suggupta@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0352 | Rejected |  | ERP | R3 (Release 3) | High | 05. OTC IP | 13.1 Security - ALL |  | 03. FPR 05. OTC IP 13. Security | olga.moskaleva-hughes@intel.com | [11 empty] | BRIM Security Design | The proposed BRIM security change includes design, build, and testing of the security roles for 30 L3s identified by Tower Deloitte and BRIM Deloitte team as part of the Release 3. Business Role Up to 8 business Roles Process Roles (Master) up to 20 process roles Derived Roles – up to 40 derived roles | The OTC-IP team has requested the BRIM security design to align with the IAO S4 security. Upon review, the Security team discovered that security was not included in the original BRIM Statement of Work (SOW) or the BRIM IDM 2.0 SOW. This represents an additional scope of work for the Security team. As we are finalizing the R3 Design, BRIM security will need to be integrated into S4 for IP. Therefore, it is necessary to define the appropriate business and security roles for the BRIM business process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4D33A09F-99F8-4BC3-8C19-028511B72FB0%7D&file=INT-CR0XXX_INT-CR0XXX_BRIM_Security_CR%20Deck.pptx&action=edit&mobileredirect=true |  | 9. Non-Build Security-related Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | Yes |  | 2025-03-06 | o AR: Add in approximate cost estimates to complete the changes. - @Tadepalli, Sreevani | [8 empty] | Confirmed by Sreevani to cancel as BRIM is descoped | Other | CL/OSC |  | Missing Review Date for Approval Level | 03, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0353 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 18. SCP | shashank.kolhe@intel.com | [11 empty] | IP Demand - Key Measures | Change to Key Figures impacting PDH Current “Billing Net BOM Adj Qty”  “Billing Net Adj Qty” Change to “Billing Net Adj Qty”  “Billing Net Adj Qty” | Meet biz need |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP%20DP%20Key%20Figure%20Change%20-%20Billing%20Net%20Adj%20BOM%20Qty.pptx?d=w1949a76898ed4ad28789fefa97ed0a25&csf=1&web=1&e=kZk670 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 20 | 20 | 0 | [6 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by Rick Antonellis | [9 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0354 | Approved |  | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | PC hierarchy change | Profit Center Hierarchy Change (Current: 0106/INTC/INTEL_PROF ¦ To Be: H106/INTC/INTEL_PROF or CS04/INTC/INTEL_CONS_PC ) in NRT SideCar FPR Close Reports (applicable 4 reports : FPRXR029, FPRXR030, FPRXR032, FPRXR034) , and rename ECA profit center hierarchy view naming from “Income statement hierarchy’ to “ Finance Group reporting Hierarchy” | To ensure that profit center hierarchy is same as S4 in Group Reports in SideCar for easier reconciliation and consistency across, and the ECA hierarchy include all Group Reporting hierarchy , such as profit center hierarchy, income statement hierarchy, balance sheet hierarchy etc. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0354_SideCar_ProfitCenterHierarchyChange.pptx?d=w011eaf8aa513411794b8917101abcb36&csf=1&web=1&e=j0yeOf |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 17 | 0 | [9 empty] | 17 |  |  |  | 0 | 17 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR029, FPRXR030, FPRXR032, FPRXR034 | 4 |  | 0 | FPRXR029, FPRXR030, FPRXR032, FPRXR034 | 4 |  | 0 | N/A |  | 2025-03-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | o This change will enable a change in hierarchy that a Sidecar report needs to utilize.  ECA change is aligned, and the change needs to be consistent across ECA, Sidecar, and HANA.  There will be no impact to UAT2 as it will be available immediately. o AR: Add in FS/Build/FUT dates within the deck - @Ma, Liang | [9 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0356 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP | Jeson Noronha | [11 empty] | Cancellation of RICEFW Object: OTCE0650_IF Incorrectly created as only 1 Object(OTCE0650) is applicable for GTS | Cancel Object ( incorrect ID created for IP & IF ) but applicable only for 1 GTS system | We have other two dependency RICEFW which is where we are sending additional data from both S4 systems to GTS. These are separate for each S4 IF and IP. a. OTCE0651_IF Enrich the delivery data transfer data from S/4 IF to GTS with the 'new' vs 'used indicator b. OTCE0651_IP Enrich the delivery data transfer data from S/4 IP to GTS with the 'new' vs 'used indicator The RICEFW OTCE0650 is the dependent object, to be developed only in GTS system and process the country regulations as per data send from both S4 instances. Thus, we don’t need two separate objects but just 1 for OTCE0650, and we have two for S4 side OTCE0651_IF & OTCE0651_IP. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE0650_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by offline email to Uzma | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | jenoronha@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0358 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.12 OTC IF - TM | Yes |  | Kartik Sanjay Pawar | [11 empty] | Freight units date change at FU header for backdated scenario |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR is blank | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-25 | 0 | < 15 Days | ksanjaypawar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0359 | Approved |  | ERP | R1 (Release 1) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | [11 empty] | Improve Performance of the Recon reports | Improve Performance of FICO reports | Intel requires the modification to the recon reports to increase the performance of the report and also increase usability |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0359_%20Improve%20Performance%20of%20the%20Recon%20report.pptx?d=wbf056395a11148b2a9eacaf1bc2f1dae&csf=1&web=1&e=m8ZElQ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 38 | 0 | [9 empty] | 38 |  |  |  | 0 | 38 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV033​, FPRXV034​, FPRXV035​, FPRXV036​ | 4 |  | 0 | FPRXV033​, FPRXV034​, FPRXV035​, FPRXV036​ | 4 |  | 0 | N/A |  | 2025-05-02 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-26 | Approved offline with Uzma o Given the criticality to FPR team, our team can take this up. We are expecting to be able to deliver this by early next week upon approval o Current reports are being used in R1 UAT2. However, it can take up to 5 mins to return results with very large datasets, so this is being looked at. o This will have a small impact on our R3 build as we will have to push some things out to fit this in, but we don’t expect an impact to overall timeline / schedule | [9 empty] | Build | Tower | 2025-02-26 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-25 | 0 | < 15 Days | navnegi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0360 | Approved | 15 hours of OM configuration effort; 10 hours of EDDAR BApps effort | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.3 OTC IF - Billing and Rebates |  | 04. OTC IF 12. Infrastructure 17. B-App | Eina Gupta | [11 empty] | Addition of EDDAR Scope in R2 for Invoice Archiving | Addition of EDDAR in scope for R2 for Invoice Archiving. EDDAR target to implement during UAT2 if the EDDAR system is ready early June | EDDAR has been included in R3 scope however, it was determined that between R2 and R3 the manual process for archiving cannot be followed due to increased timelines. Hence EDDAR will be included in R2 scope and implemented in UAT2 once EDDAR system is ready with upgrade in June 2025 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0360_OTC%20IF-%20EDDAR%20In-scope%20for%20R2.pptx?d=w01cf8375f48042e6b785f59fc24e00cd&csf=1&web=1&e=h594JH |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 15 | [5 empty] | 0 | 15 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | Based on Sunil's response and Jason's confirmation that there is a back-up plan, I approve the CR0360. Uzma | [9 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-26 | 0 | < 15 Days | eigupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0361 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | kritajoshi@deloitte.com | [11 empty] | Descope R3 PAPM Reporting Requirements from Deloitte Object Tracker | FPRXV090 FPRXV097 FPRXV098 FPRXV099 FPRXV100 FPRXV101 FPRXV102 These requirements aren't needed in the Deloitte ECA tracker. | Requested report requirements get the data only from PAPM system. This requirements need to be tracked into the Intel IDM tracker as these objects aren’t owned by Deloitte ECA team for build. These are already added in Intel tracker and can be removed from Deloitte tracker to eliminate double counting. PAPM is being considered a Boundary app, and Intel team is already working on data ingestion into ECA. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV090, FPRXV097, FPRXV098, FPRXV099, FPRXV100, FPRXV101, FPRXV102 |  |  | 7 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | Approved by offline email to Uzma | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0362 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 09A. Master Data | erin.irby@intel.com | [11 empty] | Profit Center (PC) Hierarchy for Supply Chain Planning | Finance MD has agreed to provide a new PC Product Planning Hierarchy to meet the needs of Supply Chain Planning. As a result: Need to change how Demand Planning is filtering for the right PCs (Intel Product, Only for Product Planning and not Software) Need to change how Demand Planning Reporting Stakeholders can view historical changes | The new MDG Finance MD Design did not account for a way to cleanly identify which PCs belong to Intel Products vs Intel Foundry, which PCs are ONLY for product planning (vs. software) and which PCs are active vs. historical. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP-DP-Master-Data-Filters-Change%20ID_Tower_CR%20Deck_template.pptx?d=w7272b20ed5844b8f894f616be2cc2213&csf=1&web=1&e=QKtJDB |  | 2. New RICEFW / ECA / Build Object |  |  | Low |  | 1 |  |  |  | 0 | 24 | 0 | 32 | [6 empty] | 56 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | o AR: Add in effort estimation - @Kolhe, Shashank o AR: Align on why current hierarchy will not meet R3 needs - @Kolhe, Shashank Eastwood, Craig @Irby, Erin @Jiang, Huiying | [9 empty] | Other | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-27 | 0 | < 15 Days | brian.staab@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0363 | Rejected |  | ERP | R1 (Release 1) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 09A. Master Data | harshaharshavardh@deloitte.com | [11 empty] | Reference Finance Data - ITEGO Harmonization Process | Reference Finance Data - ITEGO Harmonization Process | This requirement is to provide ability to add filter during Itego Harmonization |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE40037DA-4A70-4566-9B38-83F0ACFDC58D%7D&file=CR0363_MD_Reference%20Finance%20Data%20-%20ITEGO%20Harmonization%20Process.pptx&wdLOR=c372A4BC2-B33D-4F4D-BC05-A703CA26BACB&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-03-06 | [9 empty] | Confirmed by Mauricio: CR0363 was rejected as there is a manual OOB process that can be executed and is very tied for R1 |  | Not Assigned |  | Not Approved | 03, 2025 | 02, 2025 | 2025-02-27 | 0 | < 15 Days | karnayak@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0364 | Cancelled |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 02. E2E Process Integration 06. PTP 07. FTS IF 12. Infrastructure | christopher.j.martin@intel.com | [11 empty] | Oregon GXO Warehouse EWM Implementation | Extend SAP EWM scope to include Oregon GXO Huffman warehouse, convert from GXO’s custom WMX warehouse management system | GXO has recently (2/25/25) declared that they expect to replace their custom WMS within 5yrs with Blue Yonder or JDA Initial discussions with GXO indicate support for this change to reduce complexity of operations that straddle onsite and offsite warehouses GXO Huffman warehouse is 100% dedicated to Intel, no other customers are supported. Already operates as an extension of Ronler/Aloha warehouses Extending EWM to this warehouse reduces or eliminates design complexities across towers (real-time data exchange, availability check, order fulfillment, MRP functionality, warehouse VAS, QM workflow) |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Christopher to be a duplicate CR | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2025 | 2025-02-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0365 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration 11. Technology | thj@deloitte.com | [11 empty] | PTPC0537_IP_IF_Addition of logic, mapping changes and transformation during PIR conversion | 1. Scale Data Extraction from KONM and KONW Tables to capture scales break in PIR Fields to be extracted from ECC KONM: KSTBM, KBETR KONW: KSTBW, KBETR Objective: Load these fields into the S4 system. 2. Conditional Loading Based on Vendor/Material/Plant Combination: During the transformation phase, the EINE-CO_ORDER field needs to be checked for specific vendor/material/plant combinations during transformation and same should be loaded into the S4 system. 3. Logic needs to be added in BODS system during transformation to create PIR to all the subdivided plants in S4 system | 1. Scales break for PIR will not be updated during conversion 2. Real Time Consumption Post will not checked in PIR created through conversion which will later affect on real time consumption posting for all those applicable suppliers 3. As there is division of single plants into multiple plants, PIR needs to be created in all the divided plants otherwise PIR will not be created in all the divided plants |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B02B22E29-CFF9-4A66-9682-C0C3F03947DE%7D&file=INT-CR0365_PTP_IF_IP.pptx&wdLOR=cF5CE3A65-8CE6-483B-BF9B-89B75C15E787&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 45 | 0 | [10 empty] | 45 |  |  | 0 | 45 | Data Migration | No |  | 0 | N/A |  | PTPC0537_IP, PTPC0537_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPC0537_IP, PTPC0537_IF​ | 2 | PTPC0537_IP, PTPC0537_IF​ | 2 |  | 0 |  | 0 | N/A |  | 2025-10-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | Approved by Todd in offline email: Hi Anna, INT-CR0365: Approved INT-CR0367: Approved INT-CR0413: Approved INT-CR0408: Approved These are all R3 so I’m generally less worried about risk Todd | [9 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0366 | Approved | Need to add in RICEFW ID of Report | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Non-GAAP report structure change | Add column for valuation allowance and interest on annulled EC fine.​ ​ The report needs to include these new non-gaap columns which are manually input fields. The inclusion of these will also require updates to calcs in colums ​ | New non-gaap exclusions beginning in 2H 2024.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA534334D-EFB9-40BA-AD2F-50C75BA4BA1A%7D&file=INT-CRXXXX_R1_Non-GAAP_report_updates.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Low | 28 | 1 | [9 empty] | 28 |  |  |  | 0 | 28 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-03-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-02-27 | o Non-GAAP report needs to be updated to include 2 more columns. This was a new ask from Financial Disclosures that was introduced in UAT1. o AR: Add in FS/Build/FUT dates within the deck - @Ma, Liang | [9 empty] | Build | Tower | 2025-02-27 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-27 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0367 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration 11. Technology | surensurendra@deloitte.com | [11 empty] | Change Request for FSD_PTPC0509_IP_IF_Purchase Contracts Conversion ECC to S4 | 1.Exclude the extraction logic for calculating Open Target Value, Target Quantity & input file logic - Purchase Org, and Purchase Group from the existing design. 2.Add a Manual Load file scenario: The Intel Business/IT team will provide the load file in the specified format. The BODS team needs to assist with the transformation and loading into the S4 system. 3.Add 4 fields (Currency, Partner Function ,Plant, Partner) to the mapping sheet. 4.Implement an additional transformation rule for the Target Value & Target Qty fields to keep as blank or 999999999 scenario wise. | Businesses may struggle to obtain accurate or valid open contracts data during extraction, which is crucial for the entire conversion process, as it is a prerequisite for the subsequent transformation and loading stages. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC28F96FB-419C-4A98-B2AC-C661F318B452%7D&file=INT-CR0367_PTP_IF_IP.pptx&wdLOR=cDADF2285-0A3C-461A-ADD3-3937FE1A7EC9&action=edit&mobileredirect=true&CID=6F46AF32-9313-4C97-BDB2-88068756EAA1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 104 | 0 | [10 empty] | 104 |  |  | 0 | 104 | Data Migration | No |  | 0 | N/A |  | PTPC0509_IP, PTPC0509_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPC0509_IP, PTPC0509_IF | 2 | PTPC0509_IP, PTPC0509_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-12-29 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | Approved by Todd in offline email: Hi Anna, INT-CR0365: Approved INT-CR0367: Approved INT-CR0413: Approved INT-CR0408: Approved These are all R3 so I’m generally less worried about risk Todd | [9 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0368 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.3 PTP - EWM | Yes | 06. PTP | christopher.j.martin@intel.com | [10 empty] | WIINGS | Oregon GXO Warehouse EWM Implementation | Extend SAP EWM scope to include Oregon GXO Huffman warehouse, convert from GXO’s custom WMX warehouse management system Enterprise Structure: Eliminate Plant 1016 (Oregon GXO Huffman Warehouse) from enterprise hierarchy, add additional S.Locs to Ronler and Aloha warehouses (TBD) Business Process Design: GXO Huffman whse adopts all EWM business process designs Scope: Add KSI Autostore integration to R3 scope (60-80% of orders originate from autostore) | GXO has recently (2/25/25) declared that they expect to replace their custom WMS within 5yrs with Blue Yonder or JDA Initial discussions with GXO indicate support for this change to reduce complexity of operations that straddle onsite and offsite warehouses GXO Huffman warehouse is 100% dedicated to Intel, no other customers are supported. Already operates as an extension of Ronler/Aloha warehouses Extending EWM to this warehouse reduces or eliminates design complexities across towers (real-time data exchange, availability check, order fulfillment, MRP functionality, warehouse VAS, QM workflow) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/05.%20Working%20Documents/EWM%20documents/Change%20Request%20-%20EWM%20implementation%20for%20Oregon%20GXO%20offsite%20warehouse.pptx?d=we577c3d9334c485286fb822a44212612&csf=1&web=1&e=diHX6N | Design / Build Gap | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-27 | o Although this change would be a lot of work, it will reduce the complexity. o AR: Specify resources and other needs required to scope out change - @Martin, Christopher J |  |  | 2025-02-28 | • INT-CR0368: Chris and team to nail down timing and scope then bring back for review • As R3 functional spec development progressed in 2025, the team identified operational complexities with 3PL WMS integration that add complexity to core functionalities or reduce capabilities. The team questioned the assumption that 3PL WMS integration is the best fit for the GXO offsite warehouse, approached GXO with the idea, and learned of the mutual interest in SAP EWM implementation • Extend SAP EWM scope to include Oregon GXO Huffman warehouse, convert from GXO’s custom WMX warehouse management system • Scope of Work: Add KSI Autostore integration to R3 scope (60-80% of orders originate from autostore) • Deloitte, Intel IT, Intel Business agreement that replacing 3PL WMS with EWM reduces or eliminates design complexities across towers (real-time data exchange, availability check, order fulfillment, MRP functionality, warehouse VAS, QM workflow) • The request to Core Leadership to approve diverting 3 Deloitte resources for WW10 and WW11, 1 EWM and 1 infrastructure expert to assist with sizing. o Mike Q. What is the trade-off to divert these resources from R3 design? o Jorge A. There is still one POR item being worked on. Currently there isn't bandwidth to do this work. o AR: Chris: Investigate the size what ASRS integration would be and report back the findings . Mike Lange approved in offline email to Chris Martin. | [5 empty] | Design | CL/OSC | 2025-02-28 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-28 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0369 | Approved | Approved to do analysis - size cloning of SNTrax | ERP | R2 (Release 2) R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 04. OTC IF | Kalpesh K Shah | [11 empty] | Capability to track build, shipment, and warranty information for IF | The capability to trace the build, shipment and warranty information was not included in IAO scope for IF. | SIMS changed manufacturing from Internal to External. The information was tracked in SAP ME and ECC while it is manufactured internally. We need capability to track for the same in IF. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR0369_OTC_CR%20SIMs.pptx?d=wd4be5dfe7b864a268d45f9f3343bfe9c&csf=1&web=1&e=pRHNBs |  | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-02-27 | o This change is a request to look through solution options to enable tracing and tracking on the returns process and perform warranty checks.  It was planned to be done manually by the SNTrax application. However, it will be IP-owned post-R4 go-live. o SIMS team will need a solution within the IF environment or clone SNTrax.  The IP instance cannot be utilized.  Cloning will require a lot of effort and incur high costs. o AR: Update deck to clearly call out which teams are required to perform the assessment - @Smith, Todd @Shah, Kalpeshkumar o AR: Update deck with an options analysis - @Smith, Todd @Shah, Kalpeshkumar |  |  | 2025-02-28 | • The capability to trace the build, shipment and warranty information was not included in IAO scope for IF. • Serial Number are being implemented with Jabil. Testers are serialized, parts have Serial Number. • SIMS changed manufacturing from Internal to External. The information was tracked in SAP ME and ECC while it is manufactured internally. We need capability to track for the same in IF. • Share SNTrax Boundary App between IP and IF until IF solution is implemented. • Approved to do analysis - size cloning of SNTrax. | [5 empty] | Design | CL/OSC | 2025-02-28 | 02, 2025 | 02, 2025 | 02, 2025 | 2025-02-28 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0371 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF 11. Technology | Deepak Jassal | [11 empty] | In case of Backdated Orders ,Dates of Delivery Note getting changed on TU activation. | In case of Backdated Orders ,Dates of Delivery Note getting changed on TU activation. | This change is needed since at the time of TU activation ,updates are received in LE which is causing date changes on DN. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0371-Delivery%20Date%20Change%20restriction%20on%20DN%20while%20activating%20TU.pptx?d=w433896e51a8d44d1af6d0ccaed08ee10&csf=1&web=1&e=pt6aIs |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 20 | 0 | [8 empty] | 20 |  |  |  |  | 0 | 20 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0064_IF | 1 | LOGE0064_IF | 1 |  | 0 |  | 0 | N/A |  | 2025-03-25 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o These changes will result in inconsistencies between TM and S4 dates.  This is the current process now, and business teams are aligned. | [9 empty] | Build | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-28 | 0 | < 15 Days | dejassal@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0372 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 04. OTC IF 05. OTC IP 11. Technology | Shameek Dhir | [11 empty] | Descope of RICEFW objects # WOM - LOGE0627_IF, MySample - LOGE0690_IF, ETA Calculation - LOGE0631_IF as Intel foundry does not use WOM/MySample | Cancellation of RICEFW objects # WOM - LOGE0627_IF, MySample - LOGE0690_IF, ETA Calculation - LOGE0631_IF | During the FS discussion for RICEFW # LOGE0631_IF with Intel Business and IT, it was decided that LOGE0631_IF is not valid anymore because WOM and My Sample boundary apps are not used by Intel Foundry. Based on this decision the other 2 RICEFW's which are already approved but Development not yet started, we want cancel LOGE0627_IF and LOGE0690_IF as well. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0372%20%26%200421%20%26%200433/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%20Logistics%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=dptiJh |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE0627_IF, LOGE0690_IF, LOGE0631_IF |  |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 02, 2025 | 2025-02-28 | 0 | < 15 Days | shadhir@deloitte.ca | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0373 | Approved | Need to add in RICEFW ID of Report | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | New Income statement hierarchy in GR | Creation of new Net Income hierarchy with Spending subcategories in Group Reporting​ | New Net Income Hierarchy is being created in CFIN to support management reporting by GL account grouping (i.e. subcategories for spending). The creation of the hierarchy in Group Reporting enables consolidated reporting using this same structure. Reporting on the hierarchy within GDA and Sidecar will occur once report views are finalized |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4116cb28-7115-447a-917a-1166c12af84e%7D&action=edit&wdPreviousSession=af7d712f-45de-1d1b-c222-28ae7afacf77 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Low | 8 | 1 | [9 empty] | 8 |  |  |  | 0 | 8 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-03-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-06 | Approved | [9 empty] | Build | Tower | 2025-03-06 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-01 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0374 | Approved |  | ERP | R3 (Release 3) | Very High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09A. Master Data | Mehak Malhan | [11 empty] | PTPI0734 Interface to fetch Ariba attributes for AN enabled vendors from Ariba Network to MDG need to be cancelled. | Requirement to descope PTPI0734 Interface to fetch Ariba attributes for AN enabled vendors from Ariba Network to MDG. | For AN enabled vendors from Ariba Network to MDG, automation is not going to be pursued anymore as common alignment between teams, process will continue to be manual hence RICEWF PTPI0734 will not be required. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0351%20%26%20CR0374?csf=1&web=1&e=J5wtnI |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0734 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | yswaddeshpande@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0376 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Raj Chakraborty | [11 empty] | FPR - Cancellation CR for RICEFW - - FPRE0883_IP FTQ Input to drive Disaggregation to Allocation Cycle) for Actuals and Forecast. | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW | FTQ related logic in depreciation calculation is not applicable for IP system design |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0883_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | hatewari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0377 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Raj Chakraborty | [11 empty] | FPR - Cancellation CR for RICEFW - - FPRE0892_IP Derive ICS FTQ data by Capex WBS L2 & Mfr. Process Node CC | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW | FTQ related logic in depreciation calculation is not applicable for IP system design |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0892_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | hatewari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0378 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Raj Chakraborty | [11 empty] | Descope of the Object - FPRE0893_IP Derive FCS FTQ data by Capex WBS L2 & Mfr. Process Node CC | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW | FTQ related logic in depreciation calculation is not applicable for IP system design |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0893_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | hatewari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0379 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Kolleru Venkatesh | [11 empty] | Descope these objects : FTSI0268_IF | Email approval attached confirmation from all concerned teams associated with the object. FTSI0268_IF - Create Build Instructions requirement is taken care in OTCI1126, OTCI1162 created by OTC team. This FTSI0268_IF object is a duplicate and needs to be cancelled Current RICEFW ID is OTCI0268_IF renamed from FTS to OTC | GPO approval mail attached/ Email approval attached confirmation from all concerned teams associated with the object. FTSI0268_IF requirement is taken care in OTCI1126, OTCI1162 created by OTC team. This FTSI0268_IF object is a duplicate and needs to be cancelled Current RICEFW ID is OTCI0268_IF renamed from FTS to OTC |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0379?csf=1&web=1&e=K3meno |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0268_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | [10 empty] | Other | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0380 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV140 (Tax Localization - Singapore: Red asset for local Tax Compliance ) | FPR - Cancellation of ECA View object- FPRXV140 (Tax Localization - Singapore: Red asset for local Tax Compliance ) - Since the requirement of this is covered in the ECA object- "FPRXV051 - PO Research Report" | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV140 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0381 | Approved | 15 hours of configuration work | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 16. Testing | Naveen Negi | [11 empty] | Enhance CFIN BADI to remove cross-company reference for Comp Code 925 & 926 in cross-company documents. | SK Hynix company codes 925 & 926 are on liquidation path and are expected to be liquidated before R1 Go Live. Therefore, the two company codes will remain active in ECC until liquidation is complete. To resolve the remaining cross-company code errors in CFIN initial load and allow posting of cross-company document in active company codes, SAP Max Attention team have recommended to enhance the CFIN BADI to remove cross-company reference in field CFIN_ACCIT-BVORG where company code in following two scenarios: 1. Company Code 925 or 926 are leading company codes. 2. Company Code 925 or 926 is the only non-leading company code in transaction. | Sk Hynix company codes are not in future scope therefore need to exclude transactions from cross company referrence. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0381_Enhance%20CFIN%20BADI%20to%20remove%20cross-company%20reference%20for%20SK%20Hynix%20CC%20925%20%26%20926%20in%20cross-company%20documents.pptx?d=wf4b810f9b33c43e4a9c4e21e8a092940&csf=1&web=1&e=fGmgAj |  | 3. Configuration Change | DC-010-090 - CFIN Initial Load |  |  | 0 | 0 | [7 empty] | 15 | [5 empty] | 0 | 15 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-06 | Approved | [9 empty] | Other | Tower | 2025-03-06 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-03 | 0 | < 15 Days | smakarandbokil@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0382 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF 11. Technology | ray.m.oneill@intel.com | [11 empty] | RMA Authorization Form Formatting and Config Updates | Formatting and configuration updates to the RMA authorization discovered as part of ITC2 testing phase | Address Formatting /Display Issues on Form (populate address information completely, display currency values correctly, format fields to ensure visual appeal, ensure correct T+C messaging is displayed depending on the return order type) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0382_OTC_IF_Returns%20-%20RMA%20Authorization%20Form%20Formatting%20and%20Configuration%20Updates.pptx?d=w7bf6f34d5ddf4ecfafb16f08ffa0ea96&csf=1&web=1&e=39exbE |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [8 empty] | 18 |  |  |  |  | 0 | 18 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCF0172 | 1 | OTCF0172 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-06 | o AR: Update “BA” to “Business Analyst” within deck - @Dhandapani, Sathyanarayanan | [9 empty] | Build | Tower | 2025-03-06 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0383 | Approved | Work will be done by Intel ECA team | ERP | R2 (Release 2) R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 10. Analytics 18. SCP | Haritha Komma | [11 empty] | ECA -Lot Projection TPT Report | Reporting Capability needed from ECA for Lot completion Date involving Planned Orders, Sales Order and TPT Calculation | Built a consumption view in ECA FSCO->FSTP will give the shiftly Lot Projection of when the lot will complete the stage ..data will flow to ECA including TPT In ECA we have to build the view to add remaining stage(s) TPTs come up with projected ECD date FSSD will get the data from ECA |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR0383_IF%20FTS_CR%20ECA%20POLP%20Report.pptx?d=wbe7a453e4cb34fa282fbb3449c1ee73b&csf=1&web=1&e=MyS9pe |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [9 empty] | 80 |  |  |  | 0 | 80 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | o This change is to enable the capability to calculate the ECD, estimated completion date. • This change has been aligned and approved with the Intel ECA team for UAT2. • This requirement came about due to the turnkey order changes. | [9 empty] | Other | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | haritha.komma@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0385 | Approved | This will be deployed right after R2 go-live during Hypercare. Defect and Incident should be logged during the first day. | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 11. Technology 12. Infrastructure 16. Testing | R Prem Siddharth | [11 empty] | GTS - Alfresco Integration | Currently the files for GTS are stored in repository with some system generated numbers and its difficult to trace the files with respect to transaction or functionality directly in Alfresco. Proposed change will create the new aligned folder structure and functionality separation for better use of Alfresco repository | The RFC-enabled function module provided by Alfresco works well with S/4 HANA system but is incompatible with GTS due to its different technical stack. This incompatibility prevents the standard function module from being activated in GTT and generates ABAP dumps. ​ Development of a custom function module is needed which will allow us to extract GTS-specific metadata, SAP Object type associated with the attachments and transfer them to Alfresco effectively. We discussed this problem with the vendor (Alfresco), and they have approved the implementation of a custom solution to extract the metadata. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2AC3D36A-0CC7-4CAD-A3AF-D4D5AD16D7BA%7D&file=INT-CR0385_%20GTS%20-%20Alfresco%20Integration.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | o Standard functionality in GTS does not support this metadata.  In ITC1, this was tested on a high-level, and the gap was discovered.  In ITC2, a fix was introduce, but the connection was not properly installed.  In ITC3, random folders were created, and the Basis team requested additional help from the Deloitte team to fix. o Within the legacy system, the integration worked as it was a single folder. Within the new GTS system, there are now multiple folders. Hence, a change in architecture. o AR: Work with SAP architect to assess if a customization is required and assess the change in architecture - @Patil, Piyush Ashok o AR: Work with tech team to finalize effort and new FS/Build/FUT dates - @Patil, Piyush Ashok o AR: Once above AR’s are completed, bring CR back for approval - @Tam, Anna | [9 empty] | Other | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | gvarude@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0387 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | Subramani . | [11 empty] | FPR - Cancellation CR for RICEFW - FPRE0699_IP- Enhancement for Excess Capacity – Fixed Spending Adjustment | Cancellation of FPRE0699_IP - Enhancement for Excess Capacity – Fixed Spending Adjustment | RICEFW object - FPRI0699_IP is not needed as Excess cap fixed spending adjustment process is specific to IF |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0699_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | subramani@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0388 | Cancelled |  | ERP | R1 (Release 1) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data | harshaharshavardh@deloitte.com | [11 empty] | Additional Finance Validations for GL, Profit Center & Cost Center | Additional MDG validations. 1. Duplicate name check: My team logged a defect but she was told that the duplicate name validation is only checked against backend table, not staging table. In legacy MDG, the validation is performed against staging table. Let’s say 2 GLs or 2 cost centers are created using the same name in 2 separate CRs and are both pending for approval, if the validation is only done against backend table, we will not know there is a duplicate until one is approved, right? I think it makes more sense to validate against staging table to make sure nodes with pending CRs are taken into consideration. 2. Profit center is not a required field in cost center master data, can we make it a required field? We have it as required field in cost center user story and it is considered a fit, thus, we didn’t call it out as a custom validation. But it seems profit center can be left blank in our testing. 3.Similarly we need medium text as a required field for GL account, cost center and profit center. | Required to create / update GL accounts, Profit Centers & Cost Centers |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 30 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to not be required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0389 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 11. Technology | Jeson Noronha | [11 empty] | Cancellation of RICEFW Object: FPRI0703_IP Incorrectly created as only 1 Object(FPRI0703) is applicable for IF Cancellation of RICEFW Object: FPRI0704_IF Incorrectly created as only 1 Object(FPRI0704) is applicable for IP | Cancellation of RICEFW Object: FPRI0703_IP Incorrectly created as only 1 Object(FPRI0703) is applicable for IF Cancellation of RICEFW Object: FPRI0704_IF Incorrectly created as only 1 Object(FPRI0704) is applicable for IP | Incorrect creation of Object , which is now validated by the FPR tower |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0703_IP, FPRI0704_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | jenoronha@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0390 | Approved |  | ERP | R2 (Release 2) R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 09B. Data Migration | R Prem Siddharth | [11 empty] | Additional validations for RICEF OTCC0231 (License conversion) | Additional validation steps for RICEF OTCC0231 (License conversion) 1. Add validation for BP and Material availability in the target system 2.Add additional field in extraction file as Concatenation of External license number (EXTNO) and Internal number (EXLIC) to have a unique primary key | .License upload via Object OTCC0231 is failing for 1.Validation for BP and Material availability in the target system during the transformation step. 2. Same External license number (EXTNO) for more than one license in legacy system. Thus, missing the unique license number for license upload " |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0390%20Additional%20validations%20for%20RICEF%20OTCC0231(License%20conversion%20).pptx?d=wf6acd8a9e2974744bccb8f8b64baf6b4&csf=1&web=1&e=Tcb9R8 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 78 | 0 | [10 empty] | 78 |  |  | 0 | 78 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0231 | 1 | OTCC0231 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | o A unique license number is required for the upload process to work in this conversion. However, it was discovered that the same code was given to multiple licenses.  Manually modifying the license number in the load file will take at lease 10 hours in the cutover cycle depending on the load.  This CR is to concatenate the external and internal license number to create a unique license number. | [9 empty] | Build | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-04 | 0 | < 15 Days | gvarude@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0391 | Approved |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 10.4 Analytics - OTC IF |  | 04. OTC IF 05. OTC IP 10. Analytics | Fabian Reginold | [11 empty] | Transferring Objects from Deloitte Object Tracker to Intel Object Tracker | Based on Intel APT and Business proposal, the ownership of the reports is changing.to Intel. The following objects will be taken off of the Deloitte Object Tracker as Intel Business will be taking ownership of the report development. These will be under the category of "3rd Party Reports" in the Intel Object Tracker. Deloitte will still build the necessary consumption views, which will remain on the Deloitte Object Tracker. Objects to be removed from the Deloitte ECA Object Tracker: OTC IP: OM, Return and logistics 3rd party reports OTCPR032 OTCPV028 OTCPR031 OTCPV039 OTCPR019 OTCPV002 OTCPV001 OTCPV005 OTCPV015 OTCPV018 OTCPR021 OTCPR030 OTCPV030 OTCPR033 OTCPR034 OTCPR035 OTC IF reports OTCFR066 OTCFR025 OTCFR087 OTCFR086 OTCFR092 OTCFR095 OTCFR022_01 OTCFR076 OTC2064 OTCFR091 OTCFR083 OTCFR081 OTCFR080 OTCFR079 LOGV026_IF LOGV041_IF GTS objects transferred to intel tracker(ECA Reports) These are end reports which are built by the Intel APT team end to end and will be therefore tracked on the Intel Tracker as "ECA Reports" OTCFR098 OTCFR099 OTCFR100 OTCFR101 OTCFR097 OTCFR102 OTCPR038 OTCPR039 OTCPR040 OTCPR041 OTCPR042 OTCPR043 Cancelled objects OTCPV029 OTCPR001 OTCFR096 OTCFR068 OTCFR084 | Since Deloitte is not developing the report, it would not be correct to have the report on the Deloitte Object Tracker. We are making this change to distinguish what Deloitte is owning vs. what is Intel owning in terms of objects. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCPR032, OTCPV028, OTCPR031, OTCPV039, OTCPR019, OTCPV002, OTCPV001, OTCPV005, OTCPV015, OTCPV018, OTCPR021, OTCPR030, OTCPV030, OTCPR033, OTCPR034, OTCPR035, OTCFR066, OTCFR025, OTCFR087, OTCFR086, OTCFR092, OTCFR095, OTCFR022_01, OTCFR076, OTC2064, OTCFR091, OTCFR083, OTCFR081, OTCFR080, OTCFR079, LOGV026_IF, LOGV041_IF, OTCFR098, OTCFR099, OTCFR100, OTCFR101, OTCFR097, OTCFR102, OTCPR038, OTCPR039, OTCPR040, OTCPR041, OTCPR042, OTCPR043, OTCPV029, OTCPR001, OTCFR096, OTCFR068, OTCFR084 |  |  | 49 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-05 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0393 | Approved |  | SCP | R2 (Release 2) | Very High | 07. FTS IF | 7.1 FTS IF - ALL |  | 07. FTS IF 11. Technology | tnachnani@deloitte.com | [11 empty] | Plan for delinquent RDD | We need the ability to plan and consume current allocations for orders that have a request date within lead time and start these wafers immediately if allocations exist Technical solution would be to push delinquent RDDs to CW in PDH prior to solve (only for new orders SO with no CDD), provide original RDD in BY for reference, and netting logic for orders will need to be extended to LT+ x weeks and will be different for each process | OTC has confirmed that customers can place orders with RDD in the future (e.g. tomorrow) and that RDD may be in the past when it reached BY, once hold is released. RDD cannot be changed in S4 due to customer restriction Technical team confirmed that any orders that show up in BY with RDD prior to CW cannot not be planned as they are considered delinquent. Thus RDD in BY needs to be updated to CW RDD between CW and CW+LT-12 for LT >12 will also be treated as “order with no RTF” even though capacity commits might exist for starts in CW+1. Thus change to the netting horizon is needed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB56D3311-59E9-4C06-8062-B0E1F1A5DE60%7D&file=SCP-CR.070_FTS_Plan%20for%20delinquent%20RDD.pptx&wdLOR=c66BC7D1F-7DF3-46E6-B613-97C4F37FE112&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | High |  | 3 |  |  |  | 0 | 40 | 40 | 0 | [6 empty] | 80 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o This change will have no downstream impact and will be contained. Slated for SCP UAT2. | [9 empty] | Design | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0394 | Rejected | On hold due to Separation - Planned for 3/7, but not reviewed. | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 06. PTP 17. B-App 18. SCP | Craig Eastwood | [11 empty] | SIMS – Change front office ops from LE-745 to LE-750 | In mid-2024, Intel decided to outsource the manufacture of Test Interface Units “TIU’s” and Testing Units “TU’s” to 3rd party contract manufacturers previously manufactured internally by the SIMS team in LE-745. Intel Global Trade (GTS) team assessed which Intel Malaysia entity would be most appropriate to conduct front office support for coordination of ordering TIU’s / TU’s from 3rd party contract manufacturers (e.g., Jabil). Transactions include receiving intercompany orders for TIU’s/TU’s from various Intel Foundry entities that require them, and placing orders to 3rd party contract manufacturers. Upon completion of manufacture, transact the receipt of the TIU/TU into LE-750 and fulfill the intercompany PO to the Intel Foundry entity that ordered it. It was determined that LE-750 would be most appropriate – this combines retained SIMS processes and employees into one Malaysian entity. In mid-2024, Intel decided to outsource the manufacture of Test Interface Units “TIU’s” and Testing Units “TU’s” to 3rd party contract manufacturers previously manufactured internally by the SIMS team in LE-745. Intel Global Trade (GTS) team assessed which Intel Malaysia entity would be most appropriate to conduct front office support for coordination of ordering TIU’s / TU’s from 3rd party contract manufacturers (e.g., Jabil). Transactions include receiving intercompany orders for TIU’s/TU’s from various Intel Foundry entities that require them, and placing orders to 3rd party contract manufacturers. Upon completion of manufacture, transact the receipt of the TIU/TU into LE-750 and fulfill the intercompany PO to the Intel Foundry entity that ordered it. It was determined that LE-750 would be most appropriate – this combines retained SIMS processes and employees into one Malaysian entity. | Supports optimization of Legal Entities and outsourcing decision |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR03xx_SIMS_LE_Change_from_745_to_750.pptx?d=w4de1dcef8aab4be68acf8e3b66290319&csf=1&web=1&e=zRe3fh |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | Yes |  | 2025-03-06 | o All designs will be collapsed into LE750 with other already occurring activities.  Multiple towers as well as the E2E team will drive the changes. There might be some technical work, but it will be assessed later down the line. o This change is driven by the need for legal entity optimization. | [9 empty] | Design | CL/OSC |  | Missing Review Date for Approval Level | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0395 | Approved | Tech effort is 90 hours | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 04. OTC IF 05. OTC IP 09B. Data Migration 11. Technology | Sukhwinder Ranu | [11 empty] | Create automation program for Payer Relationship data conversion | Create automation program for Payer Relationship data conversion. Changes needed: Cancel current manual conversion item Create replacement RICEFW ID for automated conversion program | During initial disposition of these data conversion objects, volume of payers was provided as 900. However, during detailed discussion for manual conversion, it was uncovered that the total number of records to be converted for this object under these payers will be between 5,000 and 10,000. The original plan to utilize LSMW data conversion (manual) will not be acceptable for this number of records and an automation program is needed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0395_OTC_Create%20automation%20program%20for%20Payer%20Relationship%20data%20conversion.pptx?d=w9792cf541bbd4e8f94f46a1820b0aa01&csf=1&web=1&e=Bkpe4k |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [10 empty] | 90 |  |  | 0 | 90 | N/A | Yes | S4 | 1 | OTCC1339 |  | OTCC1339 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCM029 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o When doing initial disposition for data objects, there were some miscommunication about the volume of payers affected by the manual conversion. o When manual conversion started, the team found out that there were around 500-10000 records per payer, and it would take too long to convert during the MC timeline. | [9 empty] | Other | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | matthfisher@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0396 | Approved | Tech effort is 90 hours | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 04. OTC IF 05. OTC IP 09B. Data Migration 11. Technology | Sukhwinder Ranu | [11 empty] | Create automation program for Payer Profile data conversion | Create automation program for Payer Profile data conversion. Changes needed: Cancel current manual conversion item Create replacement RICEFW ID for automated conversion program | During initial disposition of these data conversion objects, volume of payers was provided as 900. However, during detailed discussion for manual conversion, it was uncovered that the total number of records to be converted for this object under these payers will be between 5,000 and 10,000. The original plan to utilize SAP Migration Cockpit (manual) will not be acceptable for this number of records and an automation program is needed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0396_OTC_Create%20automation%20program%20for%20Payer%20Profile%20Data.pptx?d=wfdbd5d18492445f58ca57fe34821fb66&csf=1&web=1&e=yBUnxU |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [10 empty] | 90 |  |  | 0 | 90 | N/A | Yes | S4 | 1 | OTCC1341 |  | OTCC1341 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCM030 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o When doing initial disposition for data objects, there were some miscommunication about the volume of payers affected by the manual conversion. o When manual conversion started, the team found out that there were around 500-10000 records per payer, and it would take too long to convert during the MC timeline. | [9 empty] | Other | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | matthfisher@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0397 | Approved | Tech effort is 90 hours | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 04. OTC IF 05. OTC IP 09B. Data Migration 11. Technology | Sukhwinder Ranu | [11 empty] | Create automation program for Payer Segment data conversion | Create automation program for Payer Segment data conversion. Changes needed: Cancel current manual conversion item Create replacement RICEFW ID for automated conversion program | During initial disposition of these data conversion objects, volume of payers was provided as 900. However, during detailed discussion for manual conversion, it was uncovered that the total number of records to be converted for this object under these payers will be between 5,000 and 10,000. The original plan to utilize SAP Migration Cockpit (manual) will not be acceptable for this number of records and an automation program is needed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0397_OTC_Create%20automation%20program%20for%20Payer%20Segment%20Data.pptx?d=w50a2c7e142604a7fab0c23b1dbeb514b&csf=1&web=1&e=oDJn29 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [10 empty] | 90 |  |  | 0 | 90 | N/A | Yes | S4 | 1 | OTCC1340 |  | OTCC1340 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCM031 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o When doing initial disposition for data objects, there were some miscommunication about the volume of payers affected by the manual conversion. o When manual conversion started, the team found out that there were around 500-10000 records per payer, and it would take too long to convert during the MC timeline. | [9 empty] | Other | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | matthfisher@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0399 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Jill Matalon | [11 empty] | Shifting the Legacy Sales order and Line items details from Fields under Order Data tab to Header and Line item texts | Earlier it was aligned in FSD that Legacy Sales order number and Item number will be stored in Order data tab in fields: BSTKD_E and POSEX_E but now since those fields have been repurposed to use for other OM functionality, we need to shift the Legacy order and Line-item details to Texts ID ZF16(header level Text) and ZF13 (Line item level text) | Earlier we algined with business to use the fields in Order data tab, but since those fields have now been repurposed to other OM functionality, we need to shift the Legacy Order data to texts now. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/Conversion/INT-CR0399%20-%20Shifting%20the%20Legacy%20Sales%20order%20and%20Line%20items%20details%20from%20Fields%20under%20Order%20Data%20tab%20to%20Header%20and%20Line-item%20texts.pptx?d=wacabc3434a7a4536b5aae9a9ff24bec0&csf=1&web=1&e=3z22D3 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 90 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianned Ramirez to be cancelled as the GPO has agreed to do this manually instead. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-06 | 0 | < 15 Days | shubhamsharma6@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0400 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Raj Chakraborty | [11 empty] | FPR - Cancellation CR for RICEFW - FPRI0894_IP:Import Tool Sharing Forecasted Data from ICS to S4 & derive FTQ data by Capex WBS L2 & Mfr. Process Node CC | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW | IP doesn’t require to use FTQ drivers from FCS/ICS. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0894_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-07 | [10 empty] | Other | Tower | 2025-03-07 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | mmaheshreddy@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0401 | Approved |  | Other (Boundary Apps, Data Transformation) | R2 (Release 2) | Very High | 14. OCM | 14.6 OCM - Other Horizontals Embedded |  | 09A. Master Data 14. OCM 17. B-App 18. SCP | lwinterton@deloitte.com | [11 empty] | IAO Data Training | Additional R2 courses added to the IAO Data Transformation curriculum, resulting in additional Deloitte training development to support the creation and review of ILTs, WBTs, Job Aids and to support identification of any net new or upskilling gaps uncovered from training feedback review cycles​ | IAO data design efforts resulted in key design processes and decisions requiring data fundamental changes training to upskill end users |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/Change%20ID_Data_IAO%20Training%20Materials.pptx?d=wf3a123fbdd9a4930b88df56518306e4f&csf=1&web=1&e=0Cdd5D&nav=eyJzSWQiOjIxNDc0ODExNDMsImNJZCI6Nzg5NjQ4MDg5fQ |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 2,900 development hours | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-07 |  |  |  | 2025-04-08 | Discussed with Uzma offline and approved during Core Leadership FTF | [5 empty] | Other | CL/OSC | 2025-04-08 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0402 | Approved | Need tech effort estimation | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.1 Master Data - ALL |  | 04. OTC IF 07. FTS IF 08. FTS IP 09A. Master Data 17. B-App | andrew.t.austin@intel.com | [11 empty] | Master Data Configuration for ISM Fiori App Design | To stay legally compliant to Trade regulatory requirements and fit IAO MVP design strategy for Non-inventory shipment order in ISM, HRMM, Customer Master, Supplier Master, and Material Master must build /design for relevant master data and functions in S4 to secure ISM functionalities fitting business needs. | Currently, Supplier/Customer information for ISM creation is mainly relying on user manual inputs, and Material master identifier is optional for ISM submission and GTS compliance checks. And some of data configuration and partner function in SAP ECC is unique for ISM. Because of complaint to IAO design requirements for Capital, EIMS/Labs items and Non-inventory materials ship thru ISM, the Change must be happened in S4 and conducted by MDG team |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0402%20MDG_CR%20Deck_FTS%20IP%20ISM.pptx?d=w369099bdf309460d9dcfd6b007dccb72&csf=1&web=1&e=tf6VuS |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | tbd | 0 | [10 empty] | 149 |  |  | 0 | 149 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0182_IP​, DATC0120_IP​, DATC0179_IP​, DATC0184_IP, DATW0207​, DATW0205_IP​, DATE0313_IP​, DATR0389_IP​, DATC0178_IP​ | 9 | DATC0182_IP​, DATC0120_IP​, DATC0179_IP​, DATC0184_IP, DATW0207​, DATW0205_IP​, DATE0313_IP​, DATR0389_IP​, DATC0178_IP​ | 9 |  | 0 |  | 0 | N/A |  | 2026-01-30 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | o This request is for a change to customer master design for ISM  When NSO is used, business needs them created as customers  Building codes are mapped to employees o Team went through detailed design process with MDG to create separate rows for NSO users, and a different set of governance processes will be followed. o This change is required to become compliant.  Business is not compliant today. o Conversion cannot be manual and needs to be automated. o AR: Follow up with conversion team (Jaya and Julie) to get confirmation with hours - @Athar, Imran o If the work cannot be completed in R3, then the CR will be slotted for R4/R5. | [9 empty] | Build | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0403 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Sindhuja Gangireddy | [11 empty] | Trigger ZBA2 and ZBA4 outputs only on the first confirmation post removal of delivery block | Update routine 902 or creation of new routine as 902 is used for other outputs such that it only triggers automatically one time after the delivery block is removed and it is not triggered automatically during other significant changes after the first confirmation sent | IF Business wants change in Routine 902 for sending ZBA2 and ZBA4 outputs only on the first confirmation (after the delivery block is removed by updating the confirmed dates using the Update CMAD app) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0247%20Routine%20update%20for%20sending%20ZBA2%20and%20ZBA4%20outputs%20only%20on%20the%20first%20confirmation.pptx?d=w870387beb0dd40d38f28c225a0340df4&csf=1&web=1&e=tgL8e1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 20 | 0 | [8 empty] | 20 |  |  |  |  | 0 | 20 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0171 | 1 | OTCE0171 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-19 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-10 | Approved offline with Uzma | [9 empty] | Build | Tower | 2025-03-10 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0404 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV166 (Localization - FAA subledger - non-leading ledger for CR) | FPR - Cancellation of ECA View object- FPRXV166 (Localization - FAA subledger - non-leading ledger for CR) - Since the requirement of this is covered in the ECA object- "FPRXV108 (Tax Cost Roll Forward Report) & FPRXV047 (Asset Accounting Transactions) | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV166 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0405 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV167 (Localization - Aging AUC Raw Data report - non-leading ledger for CR) | FPR - Cancellation of ECA View object- FPRXV167 (Localization - Aging AUC Raw Data report - non-leading ledger for CR) - Since the requirement of this is covered in the ECA object- FPRXV046 (Aging AUC Raw Data) | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV167 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0406 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV124 (FAA Prepaid Activity) | FPR - Cancellation of ECA View object- FPRXV124 (FAA Prepaid Activity) - Since the requirement of this is covered in the ECA object- FPRXV051 (PO Research Report) | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV124 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0408 | Approved | 60 hours of E2Open work; 12 hours of functional work | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology 12. Infrastructure 18. SCP | Yash Mathur | [11 empty] | PTPI0369 Interface for Inventory/MRP Report from S/4 to E2Open | Add below fields in the report: 1. Batch Management Indicator 2. Serial No Profile | These fields are required to analyze whether a material is batch managed or serial number managed |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1B7C735C-7A5C-48D3-8A74-331E46D7CD3D%7D&file=INT-CR0408_PTP_IF_IP.pptx&wdLOR=c85396B35-895E-4A3E-A32F-1980F9EEC55E&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 76 | 0 | [8 empty] | 76 |  |  |  |  | 0 | 76 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | PTPI0369 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0369_IP, PTPI0369_IF | 2 | PTPI0369_IP, PTPI0369_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-04-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | Approved by Todd in offline email: Hi Anna, INT-CR0365: Approved INT-CR0367: Approved INT-CR0413: Approved INT-CR0408: Approved These are all R3 so I’m generally less worried about risk Todd | [9 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | yamathur@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0409 | Approved |  | ERP | R2 (Release 2) |  | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Naman Parti | [11 empty] | Blanket CR for all the defects (capturing new requirements) recorded in the ITC3 testing | Blanket CR for all the defects (capturing new requirements) recorded in the ITC3 testing | Blanket CR for all the defects (capturing new requirements) recorded in the ITC3 testing |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0409_OTC%20IF_ITC3_Blanket%20CR%20for%20Defects%20recording%20new%20requirements.pptx?d=w4886e12ec35440aab2a41d6b10f02e87&csf=1&web=1&e=ohOxxW |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 62 | 0 | [8 empty] | 62 |  |  |  |  | 0 | 62 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0047​, OTCI0275​, OTCI0276​, OTCI0301​, OTCI0302 | 5 | OTCI0047​, OTCI0275​, OTCI0276​, OTCI0301​, OTCI0302 | 5 |  | 0 |  | 0 | N/A |  | 2025-03-17 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-10 | Approved offline with Uzma | [9 empty] | Build | Tower | 2025-03-10 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | nparti@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0410 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 09A. Master Data 11. Technology 12. Infrastructure | junior.milan@intel.com | [11 empty] | Make FAB POLP table data available in S/4 to automatically allocate batch to delivery notes. | Make FAB POLP table data available in S/4 to automatically allocate batch to delivery notes. | To reduce manual work and limit quality issues, include FAB POLP table data in S/4 to allow the ADNC program to automatically allocate batches to delivery notes upon creation. The manual delivery note process represents ~70% of the existing business. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA03E4A1B-C256-4E39-9319-B0BA5623D8F6%7D&file=INT-CRXXXX_OTC%20IF_CR%20(FAB%20POLP).pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [8 empty] | 18 |  |  |  |  | 0 | 18 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0400 | 1 | LOGE0400 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-28 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | o The data currently comes from ECC to S4, and the source of the batch information is pushed through EWM  When it comes through the FAB materials, there is some disconnect. Therefore, the delivery dates does not have a batch, and it will fail. o This change will allow for the POLP process to follow the WLA process.  Otherwise, the batch needs to be manually entered when a TM is created. This will be there when R4 goes live.  Not having this automation will provide a lot of risk to customers as promise dates will not be met.  This process will be only for external customer wafers. o AR: Capture DeNodo and FSSD team efforts. - @Das, Debranjan o AR: Ensure build plan and testing are aligned in UAT. - @Das, Debranjan | [9 empty] | Build | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0411 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR | kritajoshi@deloitte.com | [11 empty] | Cancellation of ECA Views Objects from Object tracker / Transfer of Objects into Intel ECA Tracker FPRXV064​ - HC Report: Ops1 Operations Headcount EXCEL.url​ FPRXV065​ - Ops1 Headcount Detail​ FPRXV066​ - Headcount Report India​ FPRXV170​ - Project Deactivation​ FPRXV171​ - Guardband Checkbook​ FPRXV221​ - Employee Related Expenses Report​ FPRXV223​ - Targets and Transfers​ FPRXV225​ - Anchor Products​ FPRXV226​ - Financial Health​ FPRXV227​ - PLC Execution Performance​ FPRXV228​ - Portfolio​ FPRXV231​ - Date Comparisons​ FPRXV181​ - Headcount Pipeline Details Report​ FPRXV149​ - Forward Looking Judged Demand & ASP MMID (SSRS)​ FPRXV173​ - HC actuals vs POR by Business Unit and Project Master Data (OpEx)​ FPRXV183​ - Headcount Trends/Geo Mix (OPEX)​ FPRXV069​ - Reporting for project level actuals (OpEx)​ | ECA Objects for Release 3 are getting cancelled due to 1) Some other object catering the requirement 2) No longer needed by business Transfer of objects into Intel ECA Tracker 1) Due to non-S/4 sources of data Object ID: FPRXV064​ - HC Report: Ops1 Operations Headcount EXCEL.url​ FPRXV065​ - Ops1 Headcount Detail​ FPRXV066​ - Headcount Report India​ FPRXV170​ - Project Deactivation​ FPRXV171​ - Guardband Checkbook​ FPRXV221​ - Employee Related Expenses Report​ FPRXV223​ - Targets and Transfers​ FPRXV225​ - Anchor Products​ FPRXV226​ - Financial Health​ FPRXV227​ - PLC Execution Performance​ FPRXV228​ - Portfolio​ FPRXV231​ - Date Comparisons​ FPRXV181​ - Headcount Pipeline Details Report​ FPRXV149​ - Forward Looking Judged Demand & ASP MMID (SSRS)​ FPRXV173​ - HC actuals vs POR by Business Unit and Project Master Data (OpEx)​ FPRXV183​ - Headcount Trends/Geo Mix (OPEX)​ FPRXV069​ - Reporting for project level actuals (OpEx)​ | FPRV064, FPRXV065, and FPRXV066 will be replaced by FPRXV063. FPRXV173 is a duplicate of FPRXV229. FPRXV183 is a duplicate of FPRXV181. FPRXV069's report specs will be captured separately. FPRXV221, FPRXV225, FPRXV226, FPRXV227, FPRXV228, FPRXV231, FPRXV181, FPRXV149 are all transferred to Intel ECA team as S/4 Data is not required; corresponding replacements are ECAFPRV2358, ECAFPRV2359, ECAFPRV2360, ECAFPRV2361, ECAFPRV2362, ECAFPRV2363, ECAFPRV2365, ECAFPRV4636. FPRXV223 will also be transferred to Intel ECA team as S/4 Data is not required; ECA object to be created. https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0411_R3_FPR_ECA%20Objects%20Cancellations.pptx?d=w48fa5f36f28440fd93041a358a697f0f&csf=1&web=1&e=5YIXkO&nav=eyJzSWQiOjIxNDc0ODE4MzcsImNJZCI6MTY4NTc0OTY2fQ |  | Yes |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0411_R3_FPR_ECA%20Objects%20Cancellations.pptx?d=w48fa5f36f28440fd93041a358a697f0f&csf=1&web=1&e=gqqgK8 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 | FPRXV064, FPRXV065, FPRXV066, FPRXV069, FPRXV149, FPRXV170, FPRXV171, FPRXV173, FPRXV181, FPRXV183, FPRXV221, FPRXV223, FPRXV225, FPRXV226, FPRXV227, FPRXV228, FPRXV231 | 17 |  | 0 | 17 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV064​, FPRXV065, FPRXV066, FPRXV170, FPRXV171, FPRXV221, FPRXV223​, FPRXV225​, FPRXV226, FPRXV227, FPRXV228​, FPRXV231, FPRXV181​, FPRXV149, FPRXV173, FPRXV183, FPRXV069 |  |  | 17 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0413 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration 11. Technology | vijasharma@deloitte.com | [11 empty] | Changes required for Source Lists conversion object PTPC0536_IP_IF - ECC extraction criteria and S/4 load logic changes as per business requirements | Following changes/additions to be done in the FSD for source list conversion object as per this CR - 1. There are some ECC plants which have mapping to multiple plants in S/4. We need to create Source list records for all those plants in S/4 with same ECC data which are procurement plants. 2. Change in extraction logic for source list records where scheduling agreements are there currently. We need to additionally identify contracts from scheduling agreement with EKPO table, currently we are not doing this. 3. Filter SL records during the extraction for OSAT process area where production order process would be followed  We need to put additional filter to identify such records with MARA table and remove these records. 4. Include MPN part number field in the IDOC structure, as currently it is not getting loaded into S/4. | During the FUT review these gaps were identified in the Source List conversion object. These changes are required to be done otherwise, for the above scenarios source list records cannot be loaded in S/4 system at the time of conversion. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B91F8C06E-0621-4040-8A2C-8551766A16FC%7D&file=INT-CR0413_PTP_IF_IP.pptx&wdLOR=c842C0C28-DF91-46FA-A09C-55FD4F25666C&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 152 | 0 | [10 empty] | 152 |  |  | 0 | 152 | Data Migration | No |  | 0 | N/A |  | PTPC0536_IP, PTPC0536_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPC0536_IP, PTPC0536_IF | 2 | PTPC0536_IP, PTPC0536_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-09-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | Approved by Todd in offline email: Hi Anna, INT-CR0365: Approved INT-CR0367: Approved INT-CR0413: Approved INT-CR0408: Approved These are all R3 so I’m generally less worried about risk Todd | [9 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0414 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Aditya Tiwari | [11 empty] | Cancellation of RICEFW Object: LOGE1051_IF (Duplicate object ID created) | Cancel Object added under R3 | LOGE1051_IF object needs to be descoped/Cancelled as this was created as a duplicate object ID for LOGE1052_IF. The requirements are already covered in the other object. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0414/%5BEXT%5D%20Re_%20R3%20FTS_LE%20logistics%20CR%27s%20Requesting%20Cancellation%20approval%20-CR0414,%20CR0469,%20CR0303%20%26%20CR0476.pdf?csf=1&web=1&e=0jogUe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1051_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | [10 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | aditiwari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0415 | Approved |  | ERP | R2 (Release 2) | Very High | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF 09A. Master Data 09B. Data Migration | mshabaz@deloitte.com | [11 empty] | Material Master Data Change in Extraction Criteria for Service Materials | Change in Extraction criteria of Service Materials | Change in extraction criteria of Service Materials is required to exclude Inactive Materials |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0415-Change%20in%20Extraction%20criteria%20of%20Service%20Materials%20for%20R2.pptx?d=w2519a3fac53045cfae8c8e34cfff8cde&csf=1&web=1&e=giXA5d |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 20 | 0 | [10 empty] | 20 |  |  | 0 | 20 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0068_IF | 1 | DATC0068_IF | 1 |  | 0 |  | 0 | N/A |  | 2025-03-14 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-13 | Approved in Daily Sync with Uzma. | [9 empty] | Build | Tower | 2025-03-13 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0418 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration | Surendra Kusumuru | [11 empty] | PTPC0633_IP_Purchase Requisition Conversion ECC to S4 Need to be cancelled | 03/10 : PTPC0633_IP Need to be canceled | 03/10:As per the Intel IT team alignment . EMS PRs are only applicable for IF. We can cancel the IP conversion RICEFW. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0418/FW_%20FSD_PTPC0633_IP_Purchase%20Requisition%20Conversion%20ECC%20to%20S4%20-%20Descoping%20Approval%20request%20CR%23418.pdf?csf=1&web=1&e=yUj7Zb |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPC0633_IP |  |  | 1 | 10. OSC/CL Approved (end status) | No | No | 2025-04-10 | [10 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | surensurendra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0419 | Approved | Need to add RICEFW ID | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics | Chalumuri Kumar Srinivas | [11 empty] | Change in logic for the fields in confirmed line item in schedule line level, KPI fields and add 2 more fields. | Change in Logic for Fields in Confirmed Line Items at the Schedule Line Level: Currently, the system confirms the sales order quantity regardless of stock availability and ATP interim block at the schedule line level, which is determined by schedule line category CN. For R2, we must change the logic so that if there is an ATP interim block at the schedule line level. Once the block is removed, the confirmed quantity and date will be accurately reflected. The fields requiring changes are: Confirmed Quantity, Confirmed Delivery Date (CDD), Confirmed Material Availability Date (CMAD), and Confirmed GI Date (CGID). Additionally, due to the changes in the above fields, there is an impact on the Customer Order Response Time KPI, and the logic needs to be adjusted for the original confirmation entry date. Currently, this field is calculated as follows: if the CDD is generated at the time of creation, then the Sales Order Line Create Date is used; if there is a CDD update after the sales order creation, then the date is taken from the change log tables. Now, due to the above changes, we need to adjust this logic. Furthermore, two additional fields need to be added to capture the ECC sales order numbers and sales order line numbers in the backlog and Customer Order Inquiry Report from S4 Hana. | Change in Logic for Fields in Confirmed Line Items at the Schedule Line Level: Currently, the system confirms the sales order quantity regardless of stock availability and ATP interim block at the schedule line level, which is determined by schedule line category CN. For R2, we must change the logic so that if there is an ATP interim block at the schedule line level. Once the block is removed, the confirmed quantity and date will be accurately reflected. The fields requiring changes are: Confirmed Quantity, Confirmed Delivery Date (CDD), Confirmed Material Availability Date (CMAD), and Confirmed GI Date (CGID). Additionally, due to the changes in the above fields, there is an impact on the Customer Order Response Time KPI, and the logic needs to be adjusted for the original confirmation entry date. Currently, this field is calculated as follows: if the CDD is generated at the time of creation, then the Sales Order Line Create Date is used; if there is a CDD update after the sales order creation, then the date is taken from the change log tables. Now, due to the above changes, we need to adjust this logic. Furthermore, two additional fields need to be added to capture the ECC sales order numbers and sales order line numbers in the backlog and Customer Order Inquiry Report from S4 Hana. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDD34EAED-7557-4695-B6E4-D235A8D5E7D1%7D&file=INT-CR0419%20Change%20in%20logic%20for%20the%20fields%20in%20confirmed%20line%20items%20in%20schedule%20line%20level.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 38 | 0 | [9 empty] | 38 |  |  |  | 0 | 38 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-03-27 | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-03-25 | Email approval from Todd on 3/26: I have reviewed both submissions. Looks like both are defects identified in testing, relatively low effort, and needed for UAT. Given this I am willing to approve both without further discussion. Please advise the team(s) accordingly Todd | [9 empty] | Build | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-10 | 0 | < 15 Days | ckumarsrinivas@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0421 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 04. OTC IF 11. Technology | Ganesh Kumaresan | [11 empty] | Cancellation/Descope of RICEFW LOGE0064_IF ZXCI output | Cancellation of RICEFW LOGE0064_IF | Chronology of events:​ 1.During initial design/discussion it was decided to build the output ZXCI for both IF/IP and the design will be same for both IF/IP​ 2.During the FS prepping it has been confirmed by Business that AMS cross dock only uses this output and no longer needed for IF​ There is no scope of this interface in Intel Foundry system, as ZXCI interface is only valid for Amsterdam (NL) location. Amsterdam (NL) is cross dock location for Intel Products shipments But, not relevant for Intel Foundry. Hence, No requirement of ZXCI interface in Intel foundry. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0372%20%26%200421%20%26%200433/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%20Logistics%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=dptiJh |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE0064_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-11 | 0 | < 15 Days | gakumaresan@deloitte.ca | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0422 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRI0556 - SKF Interface to get file from source system DOT (WLA), tranform in Muelsoft to S4 format | FPR - Cancellation CR for RICEFW - FPRI0556 - SKF Interface to get file from source system DOT (WLA), tranform in Muelsoft to S4 format | As per new design , source systems will send data to ECA, this will be transformed in ECA layer to S4 format and values. Hence only one RICEF is required to get data from ECA to S4, so all other RICEF created per system are cancelled. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0556 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-11 | 0 | < 15 Days | hgore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0423 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRI0557 - SKF Interface to get file from source system SNOWFLAKE, tranform in Muelsoft to S4 format | FPR - Cancellation CR for RICEFW - FPRI0556 - SKF Interface to get file from source system SNOWFLAKE, tranform in Muelsoft to S4 format | As per new design , source systems will send data to ECA, this will be transformed in ECA layer to S4 format and values. Hence only one RICEF is required to get data from ECA to S4, so all other RICEF created per system are cancelled |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0556 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-11 | 0 | < 15 Days | hgore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0424 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 11. Technology | Siddharth Asitkumar Desai | [11 empty] | Cancellation of WRICEF - LOGI0834_IF | CR for Cancellation of WRICEF - LOGI0834_IF (Inbound interface for WLA Hold scenario to trigger Outbound ASN with Non-Valuated material iDoc up on receiving Inbound ASN with Valuated material from IP-SAP System to e2open system for FTS-IF) | For sending the Outbound ASN (3B2) for Re-bailment from IP to IF, WRICEF - LOGI034_IP was created however at the same time WRICEF - LOGI0834_IF was also created for IF environment. However, LOGI0834_IF is not required as there is no re-bailment happening from IF to IP. Hence, WRICEF - LOGI0834_IF needs to be cancelled as the functionality not required in IF environment. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0424%20%26%20441?csf=1&web=1&e=FSvYF5 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI0834_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-25 | [10 empty] | Other | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-12 | 0 | < 15 Days | siddesai@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0425 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Chalumuri Kumar Srinivas | [11 empty] | Cancellation of RICEFW OTCPV029, OTCPR001 | Cancellation of RICEFW OTCPR001 – Pricing Analytics Report and OTCPV029 – Volume Price Audit | There is no scope for these objects in IP. Chronology of events:​ During initial design/discussion it was decided to build the reports for both Volume price audit and price analytical report.​ During the FS requirement gathering it has been confirmed by Business that the reports are not required. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0425/EXT%20RE%20Reg-%20Object%20ID%20cancellation%20request.msg?csf=1&web=1&e=kyKeLr |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCPV029, OTCPR001 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 03, 2025 | 2025-03-12 | 0 | < 15 Days | ckumarsrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0426 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Naman Parti | [11 empty] | 1. Update Order Confirmation Output to Include Only Modified Line Items. 2. Update the rule matrix to include the new validations for triggering suppressing the outputs | This change request aims to update the logic for generating order confirmation outputs so that only the line items to which changes have been made are included. Line items that remain untouched should not be included in the change confirmation outputs. It also aims to incorporate specific validations for triggering or suppressing the outputs in various scenarios. The validations will ensure that the order acknowledgement and confirmation/change outputs are generated accurately based on the status of the line items and sales orders. Current Behavior: The order confirmation output currently includes all line items, regardless of whether changes have been made to them or not. Proposed Change: Modify the order confirmation output to include only the line items that have been modified. Line items that are untouched should be excluded from the change confirmation outputs. | To ensure that the order confirmation outputs are concise and only reflect the changes made to the order, thereby providing clear and relevant information to the customer. To ensure that the outputs are triggered or suppressed accurately based on the status of the line items and sales orders, providing clear and relevant information to the customer. This change will enhance the accuracy and relevance of the information provided in the outputs, reducing potential confusion and improving customer communication. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0426-Update%20Order%20Confirmation%20Output%20to%20Include%20Only%20Modified%20Line%20Items.pptx?d=w459b87137e9440e2b7487858539151d5&csf=1&web=1&e=YvW8Qm |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0191, OTCF0004_IP | 2 | OTCE0191, OTCF0004_IP | 2 |  | 0 |  | 0 | N/A |  | 2026-04-17 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | [10 empty] | Build | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-12 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR0427 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | [12 empty] | Cancellation of RICEFW OTCI0615 | Cancellation of RICEFW OTCI0615: During initial design/discussion it was decided to build the interface for create a KB orders. Later, we decided to go for an Enhancement to create a KB order from staging table and to update staging table with the KB order number (BY OP) We got an approval mail from Process Steward / GPO (Lafree, Shelly ) for the cancellation object : OTCI0615 (cancellation CR: CR0427) Could you please help us to get approval. Shelly approval mail attached FYI | Cancellation of Interface object OTCI0615 because there is no scope in Intel Products. There is a replacement of Enhancement RICEFW – OTCE1108 (This object is dependent from FTS to confirm if the staging table FS is already started) for this interface. During initial design/discussion it was decided to build the interface for create a KB orders. Later, we decided to go for an Enhancement to create a KB order from staging table and to update staging table with the KB order number (BY OP) We got an approval mail from Process Steward / GPO (Lafree, Shelly ) for the cancellation object : OTCI0615 (cancellation CR: CR0427) Could you please help us to get approval. Shelly approval mail attached FYI |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0427?csf=1&web=1&e=bOQLyQ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0615 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-12 | 0 | < 15 Days | rameshx.u@intel.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0428 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 11. Technology | Raj Chakraborty | [11 empty] | FPR - Cancellation CR for RICEFW - FPRI0895_IP:Import Tool Sharing Forecasted Data from FCS & EMS thru ECA to S4 | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW | It is not applicable for IP system design as there is no FTQ related logic applicable in depreciation calculation in IP. It only relates to IF system. Hence cancelling the IP related RICEFW (IP doesn’t require to use FTQ drivers from FCS/ICS) |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0895_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-12 | 0 | < 15 Days | hatewari@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0429 | Approved | 20 hours of configuration changes | ERP | R1 (Release 1) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Posting Level change from 10 to 30 for Reclass tasks | Posting Level change from 10 to 30 for following Reclass tasks within Group Reporting– Restructure Intercompany Realized / Unrealized Derivatives Gain / Loss NPSG and NDTM Third party reclass Intersegment Sales/COS MWP Intersegment Revenue RND MWP Intersegment Revenue OCOS PSG Intersegment Revenue and COS Altera Intersegment AR/AP Altera Intersegment Sales/COS | PL10 impacts all sub-consolidation areas, this change is required to ensure reclass impact is limited to US GAAP |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0429_Change%20PL10%20to%20PL30.pptx?d=w5905f4abe5024013a189733f2d5e4721&csf=1&web=1&e=o4xH4f |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 20 | [5 empty] | 0 | 20 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-14 | Approved offline in email to Uzma | [9 empty] | Other | Tower | 2025-03-14 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-13 | 0 | < 15 Days | kdey@deloitte.com | Yes | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0430 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Boopathi Raja Palanisamy | [11 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV153 - Expense report in BPC to reclass from RnD to COS | SBC team is changing the reclass process and will work with the project team to get it included in their design. FPRXV153 RnC to COS reclass is no longer needed. Hence Business has requested to Cancel FPRXV153 | SBC team is changing the reclass process and will work with the project team to get it included in their design. FPRXV153 RnC to COS reclass is no longer needed. Hence Business has requested to Cancel FPRXV153 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV153 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-13 | 0 | < 15 Days | bopalanisamy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0431 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRI0555 - SKF Interface to get file from source system ION (BE), tranform in Muelsoft to S4 format | FPR - Cancellation CR for RICEFW - FPRI0555 - SKF Interface to get file from source system ION (BE), tranform in Muelsoft to S4 format | As per new design , source systems will send data to ECA, this will be transformed in ECA layer to S4 format and values. Hence only one RICEF is required to get data from ECA to S4, so all other RICEF created per system are cancelled |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0555 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-13 | 0 | < 15 Days | hgore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0432 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Manidipa Gupta | [11 empty] | FPR - Cancellation CR for RICEFW FPRI1238_IF Pull Foundry WBS from HAT and create in LE 199 in IP S/4 for Foundry Employees moved to LE 199. | FPR - Cancellation CR for RICEFW FPRI1238_IF Pull Foundry WBS from HAT and create in LE 199 in IP S/4 for Foundry Employees moved to LE 199. | ECA will provide the required information to IP for creating copy of Foundry WBS, a new interface is not needed in IF to support the process |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI1238_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-13 | 0 | < 15 Days | manidgupta@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0433 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP 11. Technology | Aditya Shinde | [11 empty] | Cancel object LOGE0451_IF/IP | Cancel object LOGE0451_IF/IP | Chronology of events :​ Design Phase : Std solution to integrate PO based on Purchase order type , Purchase org , purchase group was discussed and need to integrate based on additional custom parameter was identified.​ Initial requirement for LOGE0451 : PO integration based on custom parameters.​ Subsequent requirement to added in LOGE0451 : Custom parameters to be checked at item level.​ Subsequent requirement to cancel LOGE0451 : Deactivate custom logic and system should perform standard integration as discussed during design discussion.​ Rationale : With recent change in Capital business and the way PO line items will be created, business communicated that items which aren't GR relevant won't be marked for GR. Here by as per standard SAP TM, automatically non-GR relevant times be excluded for TM integration and FU won't get generated for the line items as we create 1 line item = 1 FU. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0372%20%26%200421%20%26%200433/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%20Logistics%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=dptiJh |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE0451_IF, LOGE0451_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-13 | 0 | < 15 Days | gakumaresan@deloitte.ca | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0434 | Approved |  | ERP | R2 (Release 2) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Anson Tan | [11 empty] | Costa Rica Sub-consolidation de-scope | As part of the IAO LE restructuring, Costa Rica subsidiaries (LE233 & LE247) will be removed from the current group structure (LE230) by March 2025, eliminating the need for group reporting in SAP. Since the system design for Costa Rica’s sub consolidation had already begun, this change request is necessary to exclude Costa Rica from the SAP Group Reporting Module and update related configurations. | This change aligns the SAP Group Reporting Module with the updated legal entity structure. Maintaining an accurate consolidation scope ensures compliance with countries’ financial reporting requirements while accommodating the restructuring adjustments. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0434_Costa%20Rica%20Subconsolidation%20change.pptx?d=w80a63dc759ce494c8f69d6c247d621b6&csf=1&web=1&e=SrqCYf |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | [10 empty] | Design | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-14 | 0 | < 15 Days | kdey@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0435 | Approved | 25 hours of configuration | ERP | R2 (Release 2) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Anson Tan | [11 empty] | Change Group structure for Malaysia sub-consolidation | This change aligns the SAP Group Reporting Module with the updated legal entity structure. Maintaining an accurate consolidation scope ensures compliance with countries’ financial reporting requirements while accommodating the restructuring adjustments. | This change aligns the SAP Group Reporting Module with the updated legal entity structure. Maintaining an accurate consolidation scope ensures compliance with countries’ financial reporting requirements while accommodating the restructuring adjustments. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0435_Malaysia%20Subconsolidation%20change.pptx?d=w5809ebe6fddd465f875394f71aae6801&csf=1&web=1&e=mfKY4T |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 25 | [5 empty] | 0 | 25 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | [10 empty] | Other | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-14 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0436 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | George Bakare | [11 empty] | FPR - Cancellation CR for RICEFW FPRW0902_IF: Custom Workflow - Approve CPA Request and allocate budget to PPM Item and transfer to PS | FPR - Cancellation CR for RICEFW FPRW0902_IF: Custom Workflow - Approve CPA Request and allocate budget to PPM Item and transfer to PS (As is it a duplicate of FPRW0445_IF & IP) | We have object FPRW0445_IF & IP - Approve CPA request and allocate budget to PPM item and transfer to PS project to handle this requirement. Hence RICEFW FPRW0902_IF is a duplicate and is not required. Received Process Steward Approval |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRW0902_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-14 | 0 | < 15 Days | cneramballivenkat@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0437 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | George Bakare | [11 empty] | FPR - Cancellation CR for RICEFW FPRW0902_IP: Custom Workflow - Approve CPA Request and allocate budget to PPM Item and transfer to PS | FPR - Cancellation CR for RICEFW FPRW0902_IP: Custom Workflow - Approve CPA Request and allocate budget to PPM Item and transfer to PS (As is it a duplicate of FPRW0445_IF & IP) | We have object FPRW0445_IF & IP - Approve CPA request and allocate budget to PPM item and transfer to PS project to handle this requirement. Hence RICEFW FPRW0902_IP is a duplicate and is not required. Received Process Steward Approval |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRW0902_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-14 | 0 | < 15 Days | cneramballivenkat@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
|  | INT-CR0438 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.1 PTP - ALL |  | 06. PTP 09B. Data Migration 11. Technology | thj@deloitte.com | [11 empty] | PTPC0176_Addition of logic and fields for Open PO conversion | Incorporated logic to identify and retrieve the address when the ADRN2 value is provided during the Purchase Order (PO) creation process. Introduced several new fields to support scenarios involving multiple account assignments, ensuring comprehensive data capture and accurate allocation. Developed logic to determine the appropriate tax procedure during data extraction, facilitating the identification of the relevant tax code during the transformation phase. | If the ADRN2 value is not passed into the ADRC table, the address used during PO creation will not be picked up for extraction. Without these fields, there is a risk of missing crucial data in converted open POs with account assignments for certain scenarios Enabling accurate tax code mapping into S4 for open POs |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 37 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Should be moved to the Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0439 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Sindhuja Gangireddy | [11 empty] | Additional requirements for OTCI0061 | Creation of new line item while increasing order quantity | This requirement is necessary to ensure correct changes are being made to the sales order 04/15:To be cancelled as aligned with the OM Team, as this requirement is no longer required. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0439_Creation%20of%20new%20line%20item%20for%20increased%20quantity.pptx?d=w78a016e770bd4fd0b00aa40d93b4d16f&csf=1&web=1&e=t05wgc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Chandrakanth Elancheran that this CR is not required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-17 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0440 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 02. E2E Process Integration 04. OTC IF 11. Technology 16. Testing | Vinay Kumar Khandelwal | [11 empty] | Site code & Lot Ship to logic changes in POLP table "ZTOTC_POLP_TRX" | Site code & Lot Ship to logic changes in POLP table "ZTOTC_POLP_TRX" | Initially for object OTCE0397 got requirement to put Site code field as Plant and Lot ship to field as Ship to party . Now it has been changed and now Site code field will be some code and Lot Ship to field will be plant code . Following are effort estimate for Tech and Middleware Tech = 9 hours ; , Functional = 7 hrs Total = 16 hours |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7a0cb7b0-127f-40e9-94be-2c8406ad3f0c%7D&action=edit&wdPreviousSession=e7403f11-11f7-50e3-3898-f877abed5116 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 9 | 0 | [8 empty] | 9 |  |  |  |  | 0 | 9 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0397 | 1 | OTCE0397 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-25 | Reviewed with Uzma in offline call during 3/25/25. This was approved as the work is small. | [9 empty] | Build | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-17 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0441 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 11. Technology | Siddharth Asitkumar Desai | [11 empty] | Cancellation of WRICEF - LOGI1207_IP & LOGI1207_IF | CR for Cancellation of WRICEFs - LOGI1207_IP & LOGI1207_IF | WRICEFs - LOGI1207_IF & LOGI1207_IP were created initially considering Subcon Suppliers (ODM/BOX/OSAT) will be able to support B2B collaboration for sending ASN against Return PO via E2Open once they will ship the Return Material to third-party Suppliers. However, during our discussion with respective business stake holders, it is found that the volume of the respective transactions are very low and it is more feasible to follow the manual process to update the shipment details and perform PGI against the Return Delivery instead of enabling the B2B collaboration for the same. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0424%20%26%20441?csf=1&web=1&e=cTWorU |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1207_IP, LOGI1207_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | [10 empty] | Other | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-17 | 0 | < 15 Days | siddesai@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0442 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 10. Analytics | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRV002 | FPR - Cancellation CR for RICEFW -FPRFV002 : Volume/Units report for WIFs - Intel Foundry | This will be covered in ECA scope due to no dependency on S4 data and hence new ECA ID ECAFPRS2271 created for this |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRFV002 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-17 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0443 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 10. Analytics | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRV003 | FPR - Cancellation CR for RICEFW - FPRPV003 : Volume/Units report for WIFs - Intel Products Group | This will be covered in ECA scope due to no dependency on S4 data and hence new ECA ID ECAFPRS2271 created for this |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRPV003 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-18 | [10 empty] | Other | Tower | 2025-03-18 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-17 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0444 | Approved | Update deck with RICEFW IDs | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 06. PTP | Lopa Chaudhry | [11 empty] | CF BApp - ILM FOAM: Addition of new scope, budget request and design extension due to PTP Tower need for S4 QM integration wtih ILM FOAM along with Master Data | New Scope for ILM FOAM to enable time sensitive Quality Module Activation interacting with SAP S4 and MDG, using a system that users are familiar and effective. ILM FOAM is the POR system for materials excursion. Additional scope for ILM FOAM includes: S4 QM integration/interfaces + Enhancements + Support MDG manual interface. Schedule change: Need extension of design till end of April, will continue to target EOY Build completion. Budget Request: $99k to cover the new scope of work in ILM FOAM. B-Apps will be funding the increased cost through Q1 underspends hence no additional ask for OSC/CL | S4 Quality Module allows Intel to segregate materials of concern and document the decision process for use. The Quality Module (QM) activation is use-case driven and cannot be done during Material Master setup. If QM is active all the time, material would be inefficiently over contained. QM is activated by the signals from the business including quality, stability, and readiness. Inspection needs are derived from severity of excursions scenarios. ILM is the POR system to material excursions which triggers QM activation. MDG did not comprehend the dynamic nature of the QM Master Data. QM activation will be simplified with automated/integrated solution b/w ILM, MDG and S4. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B98EC586A-2C9D-43F9-95E6-01A67DDCE407%7D&file=ILM%20FOAM_Scope_Budget_Schedule%20CR%20Mar%2725.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | Very High |  | 4 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-03-20 | o From a previous CR, 2 interfaces were introduced into the PTP S4 development.  ILM FOAM team was not aware of the work required from their end.  Therefore, this CR will be to extend design and obtain $99K in budget to begin the work. o The ongoing separation design might affect this work, and the team is capturing the impacts.  The team will need to come up with a back up plan in case this CR does not go through. o AR: Add in statement that this will be the design going forward; no decisions are being re-opened - @Chaudhry, Lopa o AR: Add in details about the high-level timeline on main CR template (Slide 1) - @Chaudhry, Lopa |  |  | 2025-03-21 | • Discussion took place regarding the ILM foam boundary apps, focusing on the manual and automated processes required for quality management. The team needs to formalize the decision to accept manual solutions for R3 while debating R4 automation. The cost is incremental $100K. The manual process involves triggering notifications for MDG users to enter data manually, as the automation with MDG was not approved. The team is working on new interfaces for ILM foam, which require UI changes and data inspection plans. • Concerns raised about the expanding scope of quality automation, but the team agreed to focus on essential capabilities without overextending. • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-03-21 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-18 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0445 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 06. PTP | 6.8 PTP - QM |  | 06. PTP | Nagapushpa Nagapushpa | [11 empty] | PTPR1102-Expansion of current reporting and emailing functionality to encompass the addition of the quality inspection stock (MQCS relevant) | Expansion of current reporting and emailing functionality to encompass the addition of the quality inspection stock (MQCS relevant) | This RCIEFW PTPR1102 is been dropped and instead of this RICEFW ECA team will take care of RICEFW PTPXR103 |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0445,%20CR0446,%20CR0471?csf=1&web=1&e=Lyrk2A |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPR1102 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-18 | 0 | < 15 Days | magehlot@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0446 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.8 PTP - QM |  |  | mmalhan@deloitte.com | [11 empty] | Cancellation of below Manual Conversion Objects PTPM0002 Update ZTPTP_PARAMS table for Open Text Integration [with Maintenance view] PTPM0004 Update Bill to Address Custom Table ZTPTP_BILL_TO_DT [with maintenance view] PTPM0005 Update TVARVC table to maintain Incoterms for E2open integration [With Maintenance view] PTPM0006 Master Inspection Characteristics upload [T-Code - QS21] PTPM0007 Inspection Plan upload [T-Code - QP01] PTPM0001 Update PO ZTPTP_ROUTING Table for E2Open Integration [With maintenance view] PTPM0009 Create Inspection rules in EWM PTPM0010 Sampling Procedures for QM [T-Code - QDV1] PTPM0013 QM relevant TVARVC variables PTPM0014 Custom table for VMI suppliers, their purchase groups and MRP controllers PTPM0016 Custom table maintenance for Copper Repair suppliers PTPM0017 Output condition records for Purchasing Documents PTPM0018 Update plant determination table ZTPTP_GR_MAP for Ariba integration (with Maintenance view) PTPM0019 Update error message table ZTPTP_ERROR_MSG for Ariba integration (with Maintenance view) PTPM0020 Update Material group characteristics table ZTITR_MATL_GROUP for Ariba integration (with Maintenance view) PTPM0021 Update Ariba Bill TO table ZTPTP_BILLID for Ariba integration (with Maintenance view) PTPM0022 Update GR exclusion & Amazon supplier table ZTPTP_SUPPLIER for Ariba integration (with Maintenance view) PTPM0023 Update ichem Hazardous codes in ZTPTP_PARAMS for ichem integration (with Maintenance view) PTPM0024 Maintain Custom Table ZTPTP_DH: PTP Distribution Hierarchy PTPM0025 Maintain Custom Table ZTPTP_DH_TRANS: PTP Distribution Hierarchy Transactions PTPM0026 Update ZTPTP_PARAMS table for E2Open Integration [with Maintenance view PTPM0011 QM Z-Table for Plant Vendor Combination for which MQCS is to be checked PTPM0012 QM Z- Table with MQCS disposition status for Lots/Batches | Mentioned objects need be canceled | 03/18:As earlier suggested by Data team, for the below objects identified as Manual Conversions the ask was to create a lean FS (with upload template) for these manual conversions and hence, they got in the object tracker. But as discussed and finalized last week with data conversion team, these are Cutover tasks and will be added directly in the cutover plan for R3. The data uploads for these will be executed directly during Mock cutover and there is no need to create FS for the mentioned objects. Thus, we need to create a CR to have these objects removed from Object Tracker. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0445,%20CR0446,%20CR0471?csf=1&web=1&e=Lyrk2A |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPM0002, PTPM0004, PTPM0005, PTPM0006, PTPM0007, PTPM0001, PTPM0009, PTPM0010, PTPM0013, PTPM0014, PTPM0016, PTPM0017, PTPM0018, PTPM0019, PTPM0020, PTPM0021, PTPM0022, PTPM0023, PTPM0024, PTPM0025, PTPM0026, PTPM0011, PTPM0012 |  |  | 23 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-18 | 0 | < 15 Days | surensurendra@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0447 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Yousef Khan | [11 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV194 - WHT-IC | Tax team is cancelling ECA object FPRXV194 (WHT-IC) since requirement can be satisfied by FBL3N report. User story is marked as a FIT. | FBL3N Interco Payable Report meets requirements for Interco WHT reporting. Hence, customized report is not needed. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0447%20%26%20CR0451%20%26%20CR0455?csf=1&web=1&e=ry800j |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV194 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-25 | [10 empty] | Other | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-18 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0448 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Ganesh Kumaresan | [11 empty] | Cancellation of Object (LOGR0837) intake (Console 2321) for Inbound & Outbound Manifest and Escort reports | Cancellation of Object (LOGR0837)/ intake (Console 2321) for Inbound & Outbound Manifest and Escort reports | Chronology of events: In the initial design and discussion phase, the decision was made to develop the object under TM, and the resulting object was created. However, during discussions with the LE team, it was confirmed that the object is already accounted for under LE with four separate Intake forms. As a result, there is no need for this object in the IP under the TM sub-tower, leading to the cancellation of the object. TM will assist the LE team for any TM related mapping and FUT support. LE team’s objects. for reference are below: LOGR1173 – 2DN Outbound Manifest report​ LOGR1172 – 2DN Inbound Manifest report​ LOGR1236 – 2DN Outbound Escort report​ LOGR1252 – 2DN Inbound Escort report |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0448?csf=1&web=1&e=u2eSEj |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGR0837 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-19 | 0 | < 15 Days | gakumaresan@deloitte.ca | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0449 | Approved |  | ERP | R2 (Release 2) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF 11. Technology 17. B-App | rodolfo.alarcon@intel.com | [11 empty] | FTS IF – Update the execution Logic to capture Excursion Number in SAP EWM’s Custom MRB table | The Change request is raised to update the XML to Idoc mapping at Mulesoft level in S/4 and creating Custom code in EWM to update MRB table. | Excursion Numbers (MRB numbers) are currently received within Waybill XML in SAP S/4. The same should get automatically updated in SAP EWM’s Custom MRB table with the help of new code in SAP EWM. “How was the change identified?” This was a known functional spec requirement from the summer, which we are closing the loop on. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0EA2F62C-F384-44BB-A545-AEF2277D1E7B%7D&file=INT-Build-CR0269-%20Updating%20Excursion%20Number%20to%20SAP%20EWM%20Custom%20MRB%20table%20.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 14 | 0 | [8 empty] | 14 |  |  |  |  | 0 | 14 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0519​, LOGI0521​, LOGI0303​ | 3 | LOGI0519​, LOGI0521​, LOGI0303​ | 3 |  | 0 |  | 0 | N/A |  | 2025-04-11 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | o Excursion number needs to be captured in a custom table, and this change request is to approve the build of the table. • When the team was testing the ECD process, the MIP numbers were not in the system, resulting in a failed test. o The changes will be complete by UAT1. | [9 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0450 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Nuria Galceran | [11 empty] | Assessment of review & analysis for absorbing BRIM scope into S4 | This change request is to assess the effort estimates for reviewing the scope of work (from BRIM) that must be implemented in S4. | BRIM capabilities has been descoped from the project In order to continue sales of services(recurring , professional services) ,the capabilities that were initially scoped to be in BRIM must be built into S4 service sales scenarios. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0450-Assesment%20for%20review%20%26%20analysis%20for%20absorbing%20BRIM%20scope%20into%20S4.pptx?d=wb83032d636a948d6b9aae004acad7d56&csf=1&web=1&e=rKuQyj |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR0454 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-20 | 0 | < 15 Days | celancheran@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0451 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 10. Analytics | Hari Gore | [11 empty] | FPR - Cancellation CR for RICEFW - FPRXV141 | FPR - Cancellation CR for RICEFW - FPRXV141 (Wafer Cost (SSRS)) | This report is merged with ECA Report RICEF ID FPRXR037 (Wafer Cost Analysis) |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0447%20%26%20CR0451%20%26%20CR0455?csf=1&web=1&e=ry800j |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV141 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-25 | [10 empty] | Other | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-20 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0452 | Cancelled |  | ERP | R1 (Release 1) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data | Paineti Rajesh | [11 empty] | In the Node change Report Cost Center there are missing fields, this report requires a column for 'New Cost Center' and one for 'Hierarchy Area' | In the Node change Report Cost Center there are missing fields, this report requires a column for 'New Cost Center' and one for 'Hierarchy Area' Hierarchy area is a required field in SAP and new cost center is called out in the sample layout. | This report requires a column for 'New Cost Center' and one for 'Hierarchy Area' |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 30 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to not be required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-20 | 0 | < 15 Days | harshaharshavardh@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0453 | Approved |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology 17. B-App | Divya D | [11 empty] | Changes in OTCI0081(IPAR)OTCI0082(My Deals )Interface- Output Log File and Adding Ship To party field | As part of FUT review of IPAR and My Deals Interfaces , Following new requirements received. Changes in the Output log file format (Sales Org inherited pricing) Enable interface to process a new field "Ship To party" for condition type ZPMS | As part of FUT review of IPAR and My Deals Interfaces , Following new requirements received. Changes in the Output log file format (Sales Org inherited pricing) - The Output log file representation of total records were not meeting auditing requirements Enable interface to process a new field "Ship To party" for condition type ZPMS : To enable more flexibility in determining price for commercial Invoices |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0453_OTC%20IP_CR%20Deck_Changes%20to%20Interfaces%20OTCI0081_OTCI0082_Output%20Log%20and%20Addition%20of%20ShipTo%20field.pptx?d=w47be9676a95347788cba903aee8f93a3&csf=1&web=1&e=ZbqmXK |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 22 | 0 | [8 empty] | 22 |  |  |  |  | 0 | 22 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0081, OTCI0082 | 2 | OTCI0081, OTCI0082 | 2 |  | 0 |  | 0 | N/A |  | 2025-09-26 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-17 | o Workaround will be really difficult on the Boundary App side if this is not done. • No impact for R1/R2 resources. |  |  | 2025-04-18 | • The changes involved collapsing data to match input files and ensuring no audit problems. • Mike Lange provided a simplified explanation of the changes. • The effort estimates were discussed, and it was confirmed there was no impact on other deliverables. | [5 empty] | Build | CL/OSC | 2025-04-18 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-20 | 0 | < 15 Days | divyad4@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0454 | Approved |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.1 OTC IP - ALL |  | 11. Technology 13. Security 14. OCM | Chandrakanth Elancheran | [11 empty] | Assess effort estimates and scope of work for S4 resulting from BRIM descoping | This change request is to assess the effort estimates for reviewing the scope of work (from BRIM) that must be implemented in S4. | BRIM capabilities has been descoped from the project​ In order to continue sales of services(recurring , professional services) ,the capabilities that were initially scoped to be in BRIM must be built into S4 service sales scenarios. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB83032D6-36A9-48D6-B9AA-E004ACAD7D56%7D&file=INT-Build-CR0450-Assesment%20of%20review%20&%20analysis%20for%20absorbing%20BRIM%20scope%20into%20S4.pptx=&action=edit&mobileredirect=true | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-03-20 | o With the descoping of BRIM capabilities from S4, an assessment of the current S4 SD design and an analysis of the RAR business requirements will need to be done.  The estimated time needed for the assessment is around 2-3 weeks. o AR: Include timeline of when the team will begin the assessment and an estimate of how much effort is required - @Elancheran, Chandrakanth @Vishwanathan, Ravi |  |  | 2025-03-21 | • Presented the impact assessment required due to the descoping of BRIM. The assessment will identify the scope impacts and effort estimates needed to support the functions previously covered by BRIM. The duration for this assessment is roughly three weeks, and the team will return with the total effort required to bring over the capabilities of software and services. The focus is on maintaining manual processes and minimizing complexity, as BRIM was not justified due to the size of the business. • Decision: Approved to proceed with the effort estimate. | [5 empty] | Design | CL/OSC | 2025-03-21 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-20 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0455 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR 10. Analytics | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV165 (Grant Automation) | FPR - Cancellation of ECA View object- FPRXV165 (Grant Automation) - Since the requirement of this is covered in the ECA objects - FPRXV051 (PO Research Report), FPRXV041 (Asset List Report) & FPRXV048 (Asset Retirement Report). | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/RICEFW%20Descope%20Approval%20Emails/CR0447%20%26%20CR0451%20%26%20CR0455?csf=1&web=1&e=ry800j |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV165 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-25 | [10 empty] | Other | Tower | 2025-03-25 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0456 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | Hailey Weller | [11 empty] | Cancel Standard conversion IDs in favor of Manual conversion IDS for same scope (FTSC0922, FTSC0923) | Cancel IDS (FTSC0922, FTSC0923) in favor of Alternate Manual conversion IDs issued for same scope. (FTSM016 and FTSM002) | GPO approval received: 3/6/25. Alternate Manual conversion IDs issued for same scope. (FTSM016 and FTSM002) Conversion of Process Equipment and Work center data to be handled manually vs. standard conversion. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSC0922, FTSC0923 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-21 | [10 empty] | Other | Tower | 2025-03-21 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | ducoffman@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0457 | Approved |  | ERP | R3 (Release 3) | Very High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | Hailey Weller | [11 empty] | Cancel UI Objects not required for Custom Fiori | Cancel IDs: FTSI0997, FTSI0998, FTSI0999, FTSI1000, FTSI1001, FTSI1002, FTSI1003, FTSI1004, FTSI1005, FTSI1006, FTSI1012. These interfaces are not required following the UI decision for Custom Fiori | GPO approval received: 3/18. 11 objects are no longer required with the direction for UI Factory Portal to be Custom Fiori. Additional Change request for New objects will be submitted. This change is only to remove null objects no longer required. |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0997, FTSI0998, FTSI0999, FTSI1000, FTSI1001, FTSI1002, FTSI1003, FTSI1004, FTSI1005, FTSI1006, FTSI1012 |  |  | 11 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-21 | [10 empty] | Other | Tower | 2025-03-21 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | ducoffman@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0458 | Approved | 120 hours of tech effort | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | Hailey Weller | [11 empty] | New enhancement - (console ID 2916), Reusable Warranty Data upload | New Ricefw object requested via console (console ID 2916), Reusable Warranty Data upload | GPO approval received: 3/18. Tech approval received: 4/1; Outcome of CR ingestion meeting on 4/10 was to take through the RICEFW process for approval; OSC/CL approval received on 4/17. New requirement not encompassed in existing conversion object. (console ID 2916) Object impacted ID not yet available. Following go live, Business will require for capturing new warranty equipment data |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0458%20-%20New%20enhancement%20(console%20ID%202916)%20Reusable%20Warranty%20Data%20upload%20.pptx?d=w441bfb3d7b5e42088c015e15ec4a268d&csf=1&web=1&e=XxpurG |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [8 empty] | 120 |  |  |  |  | 0 | 120 | N/A | Yes | S4 | 1 | FTSE1413 |  | FTSE1413 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | o This CR is a request for a new custom enhancement to be created as the standard SAP conversion does not meet the new requirements. • The enhancement will update warranty information in SAP S/4 Equipment Master after the initial data conversion. o AR: Provide tech effort estimates & new build dates - @Weller, Hailey o AR: Update deck to reflect no other impacts to current R3 work - @Weller, Hailey | [9 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | ducoffman@deloitte.com |  | No |  | Complete |  | Complete | No
R1 (May 2025) | R1 | INT-CR0459 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09A. Master Data | naveenx.negi@intel.com | [11 empty] | Company Codes are not being copied automatically while creating GL's via copy in MDG | Company Codes are not being copied automatically while creating GL's via copy | The current MDG system does not provide an option to automatically select all company codes when creating a GL account via copy. Users must manually select each company code, which is time-consuming and prone to errors. |  | Yes |  | Tech effort is 40 hours | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA300B51E-D48E-4D78-95E6-A7D8AA7D9F4F%7D&file=INT-CR0459_FPR_Company%20Codes%20are%20not%20being%20copied%20automatically%20while%20creating%20GL%27s%20via%20copy%25u200b.pptx&wdLOR=cAD73A725-ABA4-4E3F-A864-AF316A866D31&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [10 empty] | 40 |  |  | 0 | 40 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-20 | o This ask was previously denied due to its customization.  It is being brought back as the volume of manual work will scale and will be onerous. | [9 empty] | Other | Tower | 2025-03-20 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0460 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: FTSE1141 (we did not identify any custom program requirement in the production order lot merge scenario based on the scope of Intel Products) | Cancel objects added under R3 | Cancellation of RICEFW Objects: FTSE1141 - Enhancement to merge child production order with another production order for OSATs in IP SAP HANA system for managing the remnants FTS-IP is referring Lot Merge process from Intel Foundry for production orders to manage Remnants.. PDF middleware system will call multiple Custom APIs for each transaction to be happen in IP SAP S4 HANA System. Therefore, there is no scope to create a custom program in S4 system to call multiple transactions. Hence, we are de-scoping this object and making it as an obsolete. Functionality will be covered by FTSI1140 - Lot Merge interface from e2open to IP SAP HANA system to merge the production orders for remnant lots. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0460%20%26%20CR0526/RE%20FTS%20IP-%20CR%20for%20Descoping%20RICEFW.msg?csf=1&web=1&e=vLthL8 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE1141 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | [10 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | akindore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0461 | Approved |  | ERP | R2 (Release 2) R3 (Release 3) | High | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF 05. OTC IP 09A. Master Data 09B. Data Migration 11. Technology 12. Infrastructure | andrew.t.austin@intel.com | [11 empty] | SCAC added to Vendor Master, Carrier partner | SCAC code on vendor master is a TM requirement. The current MDG to S4 mapping for SCAC code field is updating in LFA1-SCACD field in vendor role. Additionally, SCAC code is also needed to be maintained under carrier role as transport data with carrier category as “Carrier”. This will be a change to the MDG SCAC mapping and will be taken up as part of the MDG cutover activity. MDG RICEFW's - DATC0589,DATI0582 BODS: 37 hrs for DATC0589​ Mulesoft: 5 hrs for DATI0582​ MDG Tech: 8 hrs for DATI0582​ MDG Functional: 8 hrs for both DATC0589 and DATI0582​ Total: 58 hrs | TM uses the SCAC as a key field in many TM tables and transactional programs. Master data for carrier must include SCAC on the Carrier tab in order for the SCAC to be passed to TM for outbound delivery and freight order planning. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0461-SCAC%20added%20to%20Vendor%20Master%20Carrier%20partner.pptx?d=wa5095c92ecc148b2b07dfd10a86eef15&csf=1&web=1&e=HKCStP |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 50 | 0 | [10 empty] | 50 |  |  | 0 | 50 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0589, DATI0582 | 2 | DATC0589, DATI0582 | 2 |  | 0 |  | 0 | N/A |  | 2025-07-11 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | [10 empty] | Build | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0462 | Approved |  | SCP | R2 (Release 2) | Very High | 07. FTS IF | 7.14 FTS IF - New Product Supply Planning Enablement |  | 03. FPR 06. PTP | Michael Arciniaga | [11 empty] | Remove iCost for Revenue Engineering R2 solution | Remove iCost as the system of record for assigning Revenue Engineering Lots to Purchase orders in IAO R2. Revert to a manual reporting method to retrieve completed lots, assign to PO’s and perform the GR in ECC manually. | The hope was that by pulling in engineering lots into iCost that the data would line up sufficiently to treat them as production revenue. Over the last few months Finance has uncovered data quality issues and challenges in handling Engineering using iCost. iCost is an EOL B-app and not supposed to be touched. Continuing down a path to solve this for R2 would result in unnecessary throw away work. We need to focus on root causing ahead of R3. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B02667B5D-7C13-4DA1-82AA-2D0F7D47CB34%7D&file=Revenue%20Engineering%20iCost%20change.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | Medium |  | 2 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | [10 empty] | Design | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0463 | Approved |  | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | [11 empty] | Fine tune FICO recon report | 1. Restrict the ECC data selections in ECA to company codes part of future state of IAO program – FI and CO reports – Point#4 2. Implement logic to combine activities for intercompany recon GL accounts so that they display in unmatched status only if there is PC mismatch or dollar value mismatch. Also restrict the document document type YY from ECC data query – FI reports – Point#2 3. Display the reason for record mismatch (error message) between ECC & S/4: Documents not posted from ECC into S4, PC mismatch and GL Account mismatch in the FI line item report | Users need reconciliation reports modified to incorporate additional filters, improve performance and usability, making them more efficient and user-friendly |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR0463_%20Additional%20Changes%20to%20the%20Recon%20report%20and%20new%20GL%20balance%20report.pptx?d=w5568caa8438e4438acf220535a26c5ef&csf=1&web=1&e=h9G9oi |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 175 | 0 | [9 empty] | 175 |  |  |  | 0 | 175 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXV033, FPRXV034 | 2 |  | 0 | FPRXV033, FPRXV034 | 2 |  | 0 | N/A |  | 2025-04-07 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-04 | CR was taken straight to Core Leadership |  |  | 2025-04-04 | Per Stacee's email, this was approved | [5 empty] | Build | CL/OSC | 2025-04-04 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-24 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0464 | Cancelled | Need RICEFW ID's and new build dates | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 10. Analytics | Imran Athar | [11 empty] | Need ECA Report for Inventory Reconciliation for FTS IF | The ECA report for inventory reconciliation is required in the FTS IF space. | The report was initially planned to be built for both FTS IP and FTS IF. However, the requirement was not submitted from FTS IF side at the time of ECA report intake. We need this inventory reconciliation report in FTS IF LE space. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-%20CR0464_%20Need%20ECA%20Report%20for%20Inventory%20Reconciliation%20for%20FTS%20IF.pptx?d=w51e76a5561a846a2a8bbb8a6ea0eb9d1&csf=1&web=1&e=pYfs1q |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the effort is less than 40 hours of tech effort | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-24 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0465 | Cancelled |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.11 FTS IP - New Product Supply Planning Enablement |  | 04. OTC IF 05. OTC IP | michael.p.arciniaga@intel.com | [11 empty] | Engineering PO Closure process for IAO R2 | Request to remove iCost from the process to close PO's for Revenue Engineering in IAO R2 and revert to a manual process | Finance recommended change as there are too many identified risks with how engineering is run. |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  | N/A | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR0462, which has been approved | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0466 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 11. Technology | debradas@deloitte.com | [11 empty] | Customer ASN interface from outbound delivery | Change in DUNS logic for WE (Ship to Party) | Correct WE DUNS to be send for ASN |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC04A9D3F-3EA6-4345-B78B-59C255B9C2E3%7D&file=INT-Build-CR0276_WE%20DUNS%20number.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 4 | 0 | [8 empty] | 4 |  |  |  |  | 0 | 4 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0612 | 1 | LOGI0612 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-16 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | [10 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0468 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Sindhuja Gangireddy | [11 empty] | Requirement to include ATP delivery block as significant change and include items that only changed within 24hrs in IDOC | Requirement to include ATP delivery block as significant change and include items that only changed within 24hrs in IDOC | Requirement to include ATP delivery block as significant change and include items that only changed within 24hrs in IDOC |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0468_OTC%20IF_OTCE0171.pptx?d=wd0cd3600cb384fc1afea70da7a810426&csf=1&web=1&e=0pGa3H |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 13 | 0 | [8 empty] | 13 |  |  |  |  | 0 | 13 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0171 | 1 | OTCE0171 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-01 | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-03-26 | Email approval from Todd on 3/26: I have reviewed both submissions. Looks like both are defects identified in testing, relatively low effort, and needed for UAT. Given this I am willing to approve both without further discussion. Please advise the team(s) accordingly Todd | [9 empty] | Build | Tower | 2025-03-26 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0469 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Aditya Tiwari | [11 empty] | Cancellation of RICEFW ID - LOGI1042 (Requirement covered in LOGI0237_IF, LOGE0239_IF) | Cancel Objects added under R3 | Need to cancel LOGI1042 because the requirements are already covered in LOGI0237_IF and LOGE0239_IF |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0303,%20CR0476,%20CR0469/FW_%20R3%20FTS_LE%20logistics%20CR%27s%20Requesting%20Cancellation%20approval%20-CR0469,%20CR0303%20%26%20CR0476.pdf?csf=1&web=1&e=fLmiUK |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1042 |  |  | 1 | 10. OSC/CL Approved (end status) | No | No | 2025-04-10 | [10 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0470 | Cancelled |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Divya D | [11 empty] | Changes in OTCI0081(IPAR)OTCI0082(My Deals )Interface- Bisecting Of Price requirement | As part of FUT review of IPAR and My Deals Interfaces , Following new requirements received. Bisecting Prices should happen in S4 During creation and Expiration |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0470_OTC%20IP_CR%20Deck_Changes%20to%20Interfaces%20OTCI0081_OTCI0082_Bisecting%20Prices.pptx?d=wa81df2203efe45f28932c75175923797&csf=1&web=1&e=bapTMO |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-26 | 0 | < 15 Days | divyad4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0471 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Ramagiri Pradeep Kumar | [11 empty] | Cancellation of Duplicate WRICEF ID:PTPI0810_IF_IP_Intel WebSuite Web Contract | Cancellation of Duplicate WRICEF ID:PTPI0810_IF_IP_Intel WebSuite Web Contract | Functionality has been covered in PTPI0211_IP and PTPI0211_IF. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0445,%20CR0446,%20CR0471?csf=1&web=1&e=Lyrk2A |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0810_IF, PTPI0810_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | ramagkumar@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0472 | Approved |  | ERP | R3 (Release 3) | Very High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 03. FPR 07. FTS IF 09A. Master Data 09B. Data Migration 11. Technology | eugene.celis@intel.com | [11 empty] | Cross Site Manufacturing Change Request | With the source being shifted from MES Workstream to MOR system for routings, need to design new overall flow and logic. Changes are identified for all the L3's impacted with this shift. High-level impacted design items - 1. Routing Design – Change in source of routings impacts the existing design ​ 2. Straddle solution for production orders - Design for Closing Out Production Orders when moving from S4 Plant to Non S4 Plant (Mid Stage)​ 3. UNBW strategy | Change has been identified as part of cross-site manufacturing taskforce meeting and need a change request to address the impacts to the L3's and RICEFs identified across multiple teams - FTS-IF, FPR and Master Data. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B0DC750FE-3476-446B-8754-9D1FFA6A5359%7D&file=FTS-IF%20Change%20Request%20%E2%80%93%20Cross%20Site%20Manufacturing.pptx&action=edit&mobileredirect=true&CID=762F0B0E-F2B8-4C04-AC5F-B409F22F50CB&wdLOR=cF58997DF-ECA8-48C6-B732-E9C8A595302F&previoussessionid=89b85f21-6d6f-de8f-5ed9-4f66011351e4 | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Very High | 402 | 4 | [8 empty] | 402 |  |  |  |  | 0 | 402 | Data Migration Tech - Middleware Tech - S/4 | Yes | S4 | 4 | FTSI0481, FTSI0422, FTSI0311, FTSI0310 |  | FTSI0481, FTSI0422, FTSI0311, FTSI0310 | 4 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0311, FTSI0310, FTSI0422, FTSC0051, FTSI0337, FTSI0481 | 6 | FTSI0311, FTSI0310, FTSI0422, FTSC0051, FTSI0337, FTSI0481 | 6 |  | 0 |  | 0 | N/A |  | 2025-09-26 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-08 | o With the new direction in the cross-site manufacturing process, the team has performed an analysis on what previously completed design needs to be re-opened: • Routing Design – Change in source of routings impacts the existing design • Straddle solution for production orders - Design for Closing Out Production Orders when moving from S4 Plant to Non S4 Plant (Mid Stage) • UNBW material strategy • Product Costing : Procurement alternative need to be created based on production versions & supplying plant's PIR • Product Costing : Mixing Ratio need to be updated for each of the procurement alternative based on forecast production volume. o This will be fully contained in IF. o The Prospal WIP shipping team is engaged, and the new process will seamlessly integrate into the shipping team’s current process. o AR: Present detailed design changes and new RICEFW’s in Core Leadership FTF - @Sengupta, Rudra |  |  | 2025-04-15 | Approved during the Core Leadership FTF | [5 empty] | Design | CL/OSC | 2025-04-15 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | Complete |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0473 | Approved | Tech effort is estimated to be 180 hours | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | [11 empty] | GL balance Recon Report | 1. Require separate GL balance recon report to effectively tie out & identify the discrepancy in balances between ECC and S4 GLs by GL activity and by period end balance – FI report | Users need reconciliation reports modified to incorporate additional filters, improve performance and usability, making them more efficient and user-friendly |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR0473_%20New%20GL%20balance%20report.pptx?d=w887692cf310941eb853b42d597c0d3bf&csf=1&web=1&e=D53HZQ |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [9 empty] | 150 |  |  |  | 0 | 150 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-03 | CR was taken straight to Core Leadership |  |  | 2025-04-04 | Per Stacee's email, this was approved | [5 empty] | Other | CL/OSC | 2025-04-04 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0474 | Approved |  | SCP | R2 (Release 2) | Medium | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | prasad.jahagirdar@intel.com | [11 empty] | Build Ahead Limits | Since the demand prioritization scheme has a long span, there is a need to bake in Solver objectives that will limit the build ahead for the demand. At the same time, there is also a need to fine tune the build late parameter. The build late parameter is a configuration available in BY. | Currently, the Solver builds ahead for the demand that may be far out in future if the JIT capacity is constrained and there is some capacity to spare ahead of time. In this case, the demand will be met late. In some cases, the very far out demand is not known with high level of confidence so starting the wafers for that demand may result in excess inventory if the demand/forecast does not materialize. So users need a way to control how early the wafers can be started for future demand. ​ Similarly, if the current demand cannot be met within capacity constraints the demand is scheduled for future. If the demand is committed far out in future, there is a possibility of order cancellation and wafer started for that demand may result in excess inventory. So there is a need to control the build late parameter also. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR0474%20-%20BuildAheadLimits.pptx?d=w771aa38ada1e49578d705a79413117bc&csf=1&web=1&e=fAZhP6 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 80 | 0 | [6 empty] | 80 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-03-27 | Will require further approval from Core Leadership; o AR: Quantify the “medium-high” effort and assess resource availability to perform the work - @Arciniaga, Michael P |  |  | 2025-04-04 | [6 empty] | Build | CL/OSC | 2025-04-04 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (May 2025) | R1 | INT-CR0475 | Approved | Need to add RICEFW ID of report | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | Add column for Non-GAAP NCI Adjustment | Missing non-gaap exclusion column that was identified by UAT2 tester. ​ | Required for alignment with previously reported non-gaap financials and ongoing layout of report. ​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA1393D36-A8B5-4E39-81EC-E557E3884774%7D&file=INT-_R1_Non-GAAP_report_updates.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Low | 14 | 1 | [9 empty] | 14 |  |  |  | 0 | 14 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-04-01 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-03-27 | [10 empty] | Build | Tower | 2025-03-27 | 03, 2025 | 03, 2025 | 03, 2025 | 2025-03-27 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0476 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Karthikeyan P P | [11 empty] | Cancellation of RICEFW Object: LOGE1038 As there is no enhancement needed | Cancel Object added under R3 | LOGE1038 object needs to be descoped/Cancelled as there is no requirement for an enhancement |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0303,%20CR0476,%20CR0469/FW_%20R3%20FTS_LE%20logistics%20CR%27s%20Requesting%20Cancellation%20approval%20-CR0469,%20CR0303%20%26%20CR0476.pdf?csf=1&web=1&e=fLmiUK |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1038 |  |  | 1 | 10. OSC/CL Approved (end status) | No | No | 2025-04-10 | [10 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-27 | 0 | < 15 Days | karthp@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0477 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 09B. Data Migration | Jill Matalon | [11 empty] | Payer Transformation logic required to be added for Open Sales order Conversion, due to impact from CR: INT-CR0316 raised by CnC team | Under CR INT-CR0316, Payer BP IDs now have different ID (BP Number) in S/4, for Open Sales order conversion, we need to add transformation logic now to ensure that correct BP IDs are passed for Sales order creation, failing to do so will cause the Conversion program to terminate with Error. | As per current design ECC and S/4 BP code remains the same for all the Partners (Sold to, Ship To, Payer, Bill To), hence there was no transformation rule added for these, Open SO Program passes the extracted BP IDs as is, but now since Payer code changes in S/4 if we pass same ECC values, Program will run into error failing to create Sales order in S/4, therefore we need to put a transformation logic to convert the Payer BP IDs. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0477%20Payer%20transformation%20logic%20required%20to%20b%20added%20for%20Open%20Sales%20order%20conversion%20due%20to%20impact%20fromCR%20INT-CR0316%20raised%20by%20CnC%20team.pptx?d=w0ca6086875774573b819583e3087a666&csf=1&web=1&e=KUAYtZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 9 | 0 | [10 empty] | 9 |  |  | 0 | 9 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0517 | 1 | OTCC0517 | 1 |  | 0 |  | 0 | N/A |  | 2025-03-31 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | Approved in offline email to Todd | [9 empty] | Build | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-27 | 0 | < 15 Days | shubhamsharma6@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0478 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 10. Analytics 11. Technology | junior.milan@intel.com | [11 empty] | Additional Changes on Wafer/Die Bailment Forms (Original CR# INT-CR0333) | After INT-CR0333 was approved and put into the design cycle, the production team in ECC made additional changes to the form and logic that require a new CR to capture required production changes.. | New ECC Commercial Invoice has 10-fields and will be creating a new column/section for Intel batch. IF CI template has 13 fields and cannot accommodate the additional column/field. Consolidation of fields, plus a change to the consolidation logic (at the Intel batch and not the Customer Lot Id) will meet the spirit of the form created in ECC.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9A17FBD7-F97B-40F2-835C-FCFCB0D36237%7D&file=INT-CR0XXX_Wafer-Die%20Bailment%20CI%20and%20PL.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 12 | 0 | [8 empty] | 12 |  |  |  |  | 0 | 12 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0357_IF | 1 | LOGF0357_IF | 1 |  | 0 |  | 0 | N/A |  | 2025-04-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | Confirmed by Brianne Ramirez that it was approved Offline | [9 empty] | Build | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0479 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) | Very High | 13. Security | 13.3 Security - Cyber/ Data & Privacy |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 13. Security 17. B-App 18. SCP | Raj Valluri | [11 empty] | Descope Data Privacy - Intel Privacy Office has decided to stop all the IAO S&C Privacy work because it is considered low risk for privacy concern | S&C Deloitte's Privacy by Design, RoPAs, Privacy Impact assessments, Transfer Impact assessments - design, Build, Test activities will be stopped | Intel Privacy Office has decided to stop all the IAO S&C Privacy work because it is considered low risk for privacy concerns. After conducting thorough due diligence, the Privacy Office has concluded that S&C Deloitte's privacy deliverables should be stopped in the privacy domain |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/Intel%20Security%20and%20Controls%20PMO_Raj/Change%20Requests/Descope%20Privacy%20CR%20479.pptx?d=wac9bcf1bc12d4764bc340bb1f06ef9ed&csf=1&web=1&e=9uG4Mv |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | Security | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-03 | [10 empty] | Other | Tower | 2025-04-03 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-27 | 0 | < 15 Days | raj.valluri@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0480 | Approved |  | SCP | R2 (Release 2) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 11. Technology 18. SCP | Tushar Nachnani | [11 empty] | IAO R2 BY design –Priority routing, split ratio for bump sort​ | Current requirement is for planning to be able to select the planned sites and routing for products to enable business continuity, efficient use of available labor resources, WLA requirements for co-location on tray line, customer driven requests, and cost minimization. Current BY capabilities will manage TPT minimization (at weekly level) and will only use current sites defined on the BOM to create production methods. | Currently sites that are loaded in BOM are not always qualified to run revenue material, and are in the BOM for other downstream systems (e.g., Prospal needs D1C, site needs to be on the BOM to extend material and start qualification on site). This can cause BY to plan wafers on non valid sites​ As TPTs are rounded to the weekly level, BY can plan to send wafers from OR to NM instead of keeping wafers in OR even though that would be the preferred route​ Colocation strategy in sort for BE and ATM capacity. Changes monthly​ BY transportation schedules are currently not synced with the execution schedule in SPAN. Having least impact on manufacturing was a key tenant for R2​ Not enough overall demand can push one site to be 100% loaded while the other to have less than optimal loading |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2B1A3B4A-D73B-4098-BAD2-7E91506CB3AC%7D&file=CR0480_FTS_Priority%20routing%2C%20split%20ratio%20for%20bump%20sort.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | Very High |  | 4 |  |  |  | 0 | 100 | 100 | 0 | [6 empty] | 200 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-03-27 | o This change request is for the IF instance of BY. o AR: Work with team to assess whether changes will be able to meet UAT1 – @Vytla, Kumar |  |  | 2025-04-04 | Approved during CR Meeting | [5 empty] | Design | CL/OSC | 2025-04-04 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0481 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV136 - Localization - Malaysia: Tax Compliance requirements for Balancing Allowance/Balancing Charge (BA/BC) | FPR - Cancellation of ECA View object- FPRXV136 - (Localization - Malaysia: Create and manage assets) - Since the requirement of this is covered in the ECA objects - FPRXV048 (Asset Retirement Report). | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0481,%20CR0482,%20CR0483,%20%26%20CR0493/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%204%20FPR%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=4Wc18Q |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV136 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0482 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV137- Localization - Malaysia: Tax Compliance requirements for Pioneer vs Non-Pioneer vs Common | FPR - Cancellation of ECA View object- FPRXV137- Localization - Malaysia: Tax Compliance requirements for Pioneer vs Non-Pioneer vs Common -- Since the requirement of this is covered in the ECA objects - FPRXV041 (Asset List Report). | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0481,%20CR0482,%20CR0483,%20%26%20CR0493/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%204%20FPR%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=4Wc18Q |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV137 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0483 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV139 - Localization - Malaysia: Split tax depreciation for common assets | FPR - Cancellation of ECA View object- FPRXV139 - Localization - Malaysia: Split tax depreciation for common assets -- Since the requirement of this is covered in the ECA objects - FPRXV041 (Asset List Report) & FPRXV043 (Depreciation Actual Report). | Objects Descoped since the requirement is covered under other ECA object. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0481,%20CR0482,%20CR0483,%20%26%20CR0493/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%204%20FPR%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=4Wc18Q |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV139 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0484 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 11. Technology | debradas@deloitte.com | [11 empty] | Carrier DUNS number validation in customer ASN | Validation needs to be added ,when output type YDN1 is being generated in S4.currently in system we have validation on sales org, shipping point and sold to duns ,Now carrier duns number validation is needed as per new requirement from b2B | To send correct ASN information to customer. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0484_carrier%20DUNS%20number%20validation.pptx?d=wae393f57a0d0469db30e4275b5b70e8b&csf=1&web=1&e=zoFRyZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 3 | 0 | [8 empty] | 3 |  |  |  |  | 0 | 3 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0612 | 1 | LOGI0612 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-08 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | Approved in offline email to Todd | [9 empty] | Build | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | preetiwari@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0485 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [11 empty] | Setup copy control between different types of sales documents | when an order is created with reference to another document, cust reference filed is blank and should pull the cust ref from the document you are referencing (whether billing to credit/debit, order to order, order to credit debit, etc) |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 03, 2025 | 2025-03-28 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0486 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | Hailey Weller | [11 empty] | New RICEFWs for Custom Fiori UI - (console ID 2923) | New Ricefw objects requested via console (console ID 2923) for Custom Fiori UI | GPO alignment received: 3/31. Tech Alignment 4/1; Core Leadership approval received 4/29. New objects required as a result of decision for Deloitte to develop Custom Fiori UI (console ID 2916) Object impacted ID not yet available. |  | Yes |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  | High |  | 3 | [8 empty] | 5630 |  |  |  |  | 0 | 5630 | N/A | Yes | S4 | 26 | FTSR1364, FTSF1361, FTSE1385, FTSE1383, FTSE1382, FTSE1381, FTSE1379, FTSE1378, FTSE1376, FTSE1374, FTSE1373, FTSE1368, FTSE1367, FTSE1366, FTSE1365, FTSE1363, FTSE1359, FTSE1358, FTSE1354, FTSE1353, FTSE1351, FTSE1350, FTSE1349, FTSE1348, FTSE1347, FTSE1344 |  | FTSR1364, FTSF1361, FTSE1385, FTSE1383, FTSE1382, FTSE1381, FTSE1379, FTSE1378, FTSE1376, FTSE1374, FTSE1373, FTSE1368, FTSE1367, FTSE1366, FTSE1365, FTSE1363, FTSE1359, FTSE1358, FTSE1354, FTSE1353, FTSE1351, FTSE1350, FTSE1349, FTSE1348, FTSE1347, FTSE1344 | 26 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-07 | Presented and approved during Core Leadership FTF. |  |  | 2025-04-08 | Direction is already approved by Paul, Mike, and Uzma; this CR is to bring in RICEFW's for the Factory Portal UI. RICEFW intakes are taking place. Presented and approved during Core Leadership FTF | [5 empty] | Other | CL/OSC | 2025-04-08 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-28 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR0487 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP 10. Analytics | Hannah Bui | [11 empty] | Descope BRIM related Build RICEFW for Credit and Collections | Cancel the following RICEFW due to program wide descope of BRIM functionality: OTCI1181 OTCI1182 OTCI1183 OTCI1185 OTCI1186 OTCE1113 OTCPR022 OTCPR023 OTCPR025 | Our team received Intel directive that BRIM implementation will not be pursued for IAO project. As a result, we request to descope and remove our related build objects |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0487/Approval.pdf?csf=1&web=1&e=QBYP34 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI1181, OTCI1182, OTCI1183, OTCI1185, OTCI1186, OTCE1113, OTCPR022, OTCPR023, OTCPR025 |  |  | 9 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-31 | 0 | < 15 Days | matthfisher@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0488 | Approved |  | ERP | R2 (Release 2) R3 (Release 3) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 07. FTS IF 10. Analytics | aravind.narasimhan@intel.com | [11 empty] | Enable Description Columns in AQUA & LAGP CF | Adding stock description to AQUA CF. Enable remaining capacity in LAGP dataset (will be exposed in combined AQUA and LAGP dataset in CC) | Requested by report owner to enable description columns |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Temp/AQUA_LAGP_CR_3_31.pptx?d=w684025f3981840e495452b82f2884332&csf=1&web=1&e=vLjuxn |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 84 | 0 | [9 empty] | 84 |  |  |  | 0 | 84 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSFV013, FTSFV012 | 2 |  | 0 | FTSFV013, FTSFV012 | 2 |  | 0 | N/A |  | 2025-04-04 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-03 | Work has been completed and loaded into the system for UAT1. | [9 empty] | Build | Tower | 2025-04-03 | 04, 2025 | 04, 2025 | 03, 2025 | 2025-03-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (May 2025) | R1 | INT-CR0489 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) | High | 13. Security |  |  | 12. Infrastructure 13. Security | Raj Valluri | [11 empty] | Descope Penetration testing for R1 & R2 | InfoSec Red team, Risk management team and SAP Architect - After conducting thorough due diligence, the teams have agreed that the risk associated with the R1/R2 go-live is low. Subsequently, the Intel Security team will revisit the controls assessment | Descope Pen testing deliverables for R1 & R2 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/Intel%20Security%20and%20Controls%20PMO_Raj/Change%20Requests/Descope%20Infrastructure%20security_CR%20489.pptx?d=w379d5dff446f48d7b6de7dc0d751df79&csf=1&web=1&e=sU5bML |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-03 | o As R3 will have all modules and R1/R2 is low risk for go-live, the team will re-evaluate penetration testing for R3. |  |  | 2025-04-04 | Confirmed by Raj to have been approved with the extended team on Fri with Mike | [5 empty] | Other | CL/OSC | 2025-04-04 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-01 | 0 | < 15 Days | raj.valluri@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0490 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Govind Ballav Pradhan | [11 empty] | Cancellation of RICEFW Object: PTPI0508_IF, PTPI0508_IP, PTPI0723_IP/PTPI0723_IF ,PTPI0708_IP/ PTPI0708_IF, PTPI0722_IP/ PTPI0722_IF | Cancel Object added under R3 | Cancellation of RICEFW Object: PTPI0508_IF, PTPI0508_IP, PTPI0723_IP/PTPI0723_IF ,PTPI0708_IP/ PTPI0708_IF, PTPI0722_IP/ PTPI0722_IF RICEWF Objects linked to RFXUI, with decision made to not move forward with functionality and instead leverage manual process to exchange FRx response and SAP price upload |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0490?csf=1&web=1&e=wUEfuH |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0508_IF, PTPI0508_IP, PTPI0723_IP, PTPI0723_IF, PTPI0708_IP, PTPI0708_IF, PTPI0722_IP, PTPI0722_IF |  |  | 8 | 10. OSC/CL Approved (end status) | No | No | 2025-04-10 | [10 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-01 | 0 | < 15 Days | mochawla@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0491 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Surendra Kusumuru | [11 empty] | PTPI0809_IP_IF - Inbound Interface from SPEED to S/4 to bring AMPL (Approved Manufacturer Part List) | PTPI0809_IP & IF Need to be cancelled | As discussed in the workshop and in alignment with Ranju, it was decided to cancel the AMPL interface object and create an Enhancement object instead to reduce the complexity of AMPL creation. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0491/RE%20PTPI0809_IP%20%20IF%20-%20Inbound%20Interface%20from%20SPEED%20to%20S4%20to%20bring%20AMPL%20-%20Descoping%20Approval%20request.msg?csf=1&web=1&e=vUhmTx |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0809_IP, PTPI0809_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 04, 2025 | 2025-04-01 | 0 | < 15 Days | surensurendra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0492 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Divya D | [11 empty] | Addition of a key combination of Customer/Condition group/ Material in the NRE combinations | The NRE key combination of Customer/Condition Group/Material needs to be added in the ZNRE access sequence | This change is required make sure that the NRE discount is correctly applied to the correct materials. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FCDEEF6-C3C9-4E15-A590-4E639B177A5A%7D&file=INT-CR0492_OTC%20IF_CR%20Deck%20for%20configuration%20addition%20for%20NRE%20key%20combination.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | Approved in offline email to Todd | [9 empty] | Design | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-02 | 0 | < 15 Days | prshyamkul@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0493 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | NAMAN JAIN | [11 empty] | FPR - Cancellation of Object FPRE1103 - Determination of the Revenue GL accounts for revenue postings based on account assignment group | FPR - Cancellation of Object FPRE1103 - Determination of the Revenue GL accounts for revenue postings based on account assignment group - Since BRIM is descope from R3 IP- This object is not required | This enhancement was regarding the BRIM module, and we had included it earlier to streamline with the R3 release for RAR, due to design descope from BRIM side this object is not required. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0481,%20CR0482,%20CR0483,%20%26%20CR0493/%5BEXT%5D%20RE_%20%5BApproval%20Needed%5D%204%20FPR%20CR%27s%20to%20Descope%20RICEFW%27s.pdf?csf=1&web=1&e=4Wc18Q |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 | OTCI0302_IF | 1 |  | 0 |  | 0 | FPRE1103 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-02 | [10 empty] | Other | Tower | 2025-04-02 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-02 | 0 | < 15 Days | ppranavyogesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0494 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 03. FPR 05. OTC IP 09A. Master Data 11. Technology | Naman Parti | [11 empty] | To implement quantity contracts in S4 to include BRIM related changes within the existing OM solution design in S4 | To implement the below listed system & process changes in S4 design, against the current Software and Services requirements in ECC.​ OM:​ System changes :​ Creation of a new material characteristic within the MMID, it will indicate that the SOLI for this MMID needs to be put on hold. ​ Addition of an enhancement to put the service line items in inbound orders from B2B & WOM on hold, based on the above material characteristic maintained in the material master. ​ A new 'user status hold' for the sale order item must be configured to support the earlier step​ Business Process changes:​ Relevant MMID will be set up with new Characteristic value​ CBA's will manually update the item category & save the order​ Followed by RAR users manually processing the 'time & event based' contracts directly in RAR using manual fulfillment.​ The validity dates can be captured within "internal processing notes" for reporting requirements.hrough which we will use a new template for contract creation in S4 | The scope of work on BRIM has been descoped from the project To continue sales of services (recurring , professional services) ,the quantity contracts had to be added in S4 to include BRIM related changes within the existing OM solution design in S4. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0494-%20Implementing%20quantity%20contracts%20in%20S4%20(to%20add%20BRIM%20capabilities)%20for%20Professional%20services.pptx?d=wddedccaa85904b50b94369ac8145365a&csf=1&web=1&e=C6Asej | New Requirement / Scope | 2. New RICEFW / ECA / Build Object | O-020-100 |  | Low | 14 | 1 | [8 empty] | 14 |  |  |  |  | 0 | 14 | N/A | Yes | S4 | 1 | OTCE0406 |  | OTCE0406 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-30 | Reviewed offline with Uzma. As long as 35 hours is the total technical effort to retrofit all of the BRIM services to S/4 (Tech, MDG, etc.), then it will be considered approved. | [9 empty] | Other | Tower | 2025-04-30 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-02 | 0 | < 15 Days | celancheran@deloitte.com |  | No |  | Complete |  | Complete | No
R1 (May 2025) | R1 | INT-CR0495 | Approved | Need RICEFW ID of report | ERP | R1 (Release 1) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Rea Meyer | [11 empty] | R1 Segment Eliminations report updates | R1 update for Segment Elims report– to change the report layout from posting level to FS item view. ​ | Initial design used posting level as the identifier which presented inter-company transactions and eliminations. During UAT2 the end user clarified the requirement-correct identifier is FS item to get the intersegment eliminations view. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF630357A-0AFA-456A-A6F5-CD67300DD488%7D&file=INT-_R1_Segment_Elims_report_updates_INT_.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Low | 38 | 1 | [9 empty] | 38 |  |  |  | 0 | 38 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-04-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-03 | [10 empty] | Build | Tower | 2025-04-03 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-02 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0497 | Cancelled |  | ERP | R3 (Release 3) | [18 empty] | Further, the logic must be added to send CI price and DS flag to WOM as per Drop Ship flag indicator. If DS flag is enabled do not send CI price and show CI price if DS flag is disabled. CI price must be same as the price populated in commercial price. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Accidentally created as part of another CR | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-03 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0498 | Cancelled |  | ERP | R3 (Release 3) | [18 empty] | Additionally, logic must be incorporated for change indicator field to enable/ disable based on shipping status. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Accidentally created as part of another CR | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-03 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0499 | Cancelled |  | ERP | R3 (Release 3) | [18 empty] | Also populate Drop ship address in S4 response if the sales order is having Drop ship customer. |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Accidentally created as part of another CR | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-03 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0500 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | snavasthi@deloitte.com | [11 empty] | Cancellation of ECA report FPRXV123 Change Order Data Custom Report | Cancellation of ECA report FPRXV123 Change Order Data Custom Report as this report is not required for constructions. | This report is not required anymore as confirmed by Steven from construction side. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV123 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0505 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 11. Technology | rishabhx.hingmire@intel.com | [11 empty] | Label Printing from Spectrum | The logic for determining the printer for label printing needs to be updated, as multiple PCs might be present in the packing workstation, each connected to different printers based on label types (MBB, IBOX, or SBOX). Therefore, an additional column will be added to the custom table ZTOTC_STD_LABELS to include the PC name, and new logic will be implemented to identify the PC name from which the user has logged in. Add Date Code IFS field in mapping and send same value as date code for this field.​ | 1 warehouse would have multiple lanes.​ Each lane normally houses 2 systems (PC) example Hupast 1 (packing) and Hupast 2 (processing)​ Each PC could have multiple label printer attached, example Hupast1 can attached to 2 printers (one for media, one for ibox), Hupast 2 could attach to 1 printer (ship box)​ .So, by right the PC-printer mapping design will need to be based on the client PC (you might need to add additional column in that mapping to store that) so ewm can send the correct printer path based on which PC the user is triggering from. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCD482E47-97F7-4ED9-A988-FB3D99CE6E33%7D&file=INT-CR0264%20Label_Printing_LOGI0278.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 20 | 0 | [8 empty] | 20 |  |  |  |  | 0 | 20 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | Confirmed by Brianne Ramirez that it was approved Offline | [9 empty] | Build | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-04 | 0 | < 15 Days | nramireddi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0506 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 11. Technology | rishabhx.hingmire@intel.com | [11 empty] | MPL –Plant determination | The logic for determining the plant Number (example 1003) instead of warehouse number (Example RA01) while sending the data to open MPL​ | EWM is passing to the plant code parameter as warehouse number (Example RA01) but MPL is recognizing on plant code (example 1003). Required help to update to pass as plant code (example 1003) to ensure standardization in MPL​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0FDEB5BD-E04F-413D-8A87-E2228DE208ED%7D&file=INT-CR0265_LOGE0279_Open_MPL_Screen.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 5 | 0 | [8 empty] | 5 |  |  |  |  | 0 | 5 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0279 | 1 | LOGE0279 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-18 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-04 | Approved offline with Todd: "CR0506 is approved as it is < 8 hours and can be reviewed here" | [9 empty] | Build | Tower | 2025-04-04 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-04 | 0 | < 15 Days | nramireddi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0507 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli | [11 empty] | Inclusion of hold logic in PIPSTATUS and ACKSTATUS at line-item level under segment E1EDP01 / ZOTC_ORDER_LINE_STATUS_01 | Inclusion of hold logic in PIPSTATUS and ACKSTATUS at line-item level under segment E1EDP01 / ZOTC_ORDER_LINE_STATUS_01 | The PIPSTATUS and ACKSTATUS should be ‘Pending’, if there is a hold applied at item level |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/OTCI0301%20%26%20OTCI0302/CRs/INT-CR0507%20Inclusion%20of%20hold%20logic%20in%20PIPSTATUS%20and%20ACKSTATUS%20at%20SOLI%20under%20E1EDP01%20ZOTC_ORDER_LINE_STATUS_01.pptx?d=wcfe3eb933e81452ea1c48e47aa915b79&csf=1&web=1&e=pcCWaP | [5 empty] | 8 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-04 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0508 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 11. Technology | Siddharth Asitkumar Desai | [11 empty] | LOGI0501 Fab Materials Expedite Process - ASN Creation for Non-MMID POs & captures ETA in Hours/Minuets | For FAB Material - Expedite Process, system should have the ability to capture the ASN details for non-MMID POs along with ETA in hours/minute to help in tracking expedited orders more closely. | Coming from the arising from FAB Material - Expedite Process - Ask from the business to keep ETA in hours & system should have the ability to capture the ASN details for non-MMID POs |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR0508_PTP%20LE_Fab%20Materials%20Expedite%20Process%20-%20ASN%20Creation%20for%20Non-MMID%20POs%20%26%20captures%20ETA%20in%20Hours%20%26%20Minutes.pptx?d=w43aacc75253b4bfe9b5ca11465b533e0&csf=1&web=1&e=jUw5FZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 100 | 0 | [8 empty] | 100 |  |  |  |  | 0 | 100 | Tech - S/4 | No |  | 0 | N/A |  | LOGI0501 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0501 | 1 | LOGI0501 | 1 |  | 0 |  | 0 | N/A |  | 2025-09-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o There are 2 fields that need to change from an ASN perspective. It cannot process blank fields. So, the logic is to use a variable through S4 (non-MMID and non-ASM). • This will require changes from both tech and E2Open side. o Interfaces have been built for the original FS, and this is a delta change on top of it. | [9 empty] | Build | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-04 | 0 | < 15 Days | pradmishra@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0509 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar | [11 empty] | Cancellation of ECA report FPRXV183- Headcount Trends/Geo Mix (OpEx) | Cancellation of ECA report FPRXV183- Headcount Trends/Geo Mix (OpEx) as this report is not required | This report is not required anymore as confirmed by Ricardo and Amanda from Opex business. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV183 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-04 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0510 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | Hailey Weller | [11 empty] | New Enhancement - Console ID (2930): Trigger interface between S4 and SAP ME | New RICEFW object requested via console (console ID 2930), Trigger Interface between S4 and SAP ME | GPO alignment received 4/21; CR ingestion approval recevied 5/8; tech approval needed; new requirement not existing in interface object (console ID 2930; object ID not yet available) Enhancement required for triggering Interface between S4 and SAP ME from the save user exit of a work order with conditions to check the Order Type and Release Status |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/FTS/R3/INT-CR0510_New Enhancement to Trigger Interface between S4 and SAP ME.pptx?d=w69a0c2a8a174420e9bf3d770c4b93e49&csf=1&web=1&e=mIDaL6 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 130 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 1 | FTSE1451 |  | FTSE1451 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | Approved to go through intake | [9 empty] | Other | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-05 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0511 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 16. Testing | Sindhuja Gangireddy | [11 empty] | If both SHLT and MVOU are available for SO LI , then 397 program should not update qty in sale sorder | Requirement is If both SHLT and MVOU are available for SO LI , then 397 program should not update qty in sale sorder | If both SHLT and MVOU are available for SO LI , then 397 program should not update qty in sale sorder |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7a0cb7b0-127f-40e9-94be-2c8406ad3f0c%7D&action=edit&wdPreviousSession=e7403f11-11f7-50e3-3898-f877abed5116 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne Ramirez to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-07 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0512 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP 18. SCP | erin.irby@intel.com | [11 empty] | Forecast Reprofiling | IP BY CDP batch re-profiling capability is missing in the current solution design. Requesting implementation of forecast re-profiling solution by ww18.1 in Dev for smoke testing and ww19.3 in UAT1, cycle 2 testing | High level & detailed level requirements were documented but there was a gap in the SDD document which resulted in the solution not being developed ahead of ITC. This is a critical piece of R2 Demand Planning’s business value and must be delivered for R2. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP%20DP%20R2%20Forecast%20Reprofiling.pptx?d=wc39aec02d41a4f46b37e5dd27c378eb9&csf=1&web=1&e=hrgaXA |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 40 | 80 | 0 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | [10 empty] | Build | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-07 | 0 | < 15 Days | brian.staab@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0513 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 10. Analytics | kritajoshi@deloitte.com | [11 empty] | Update the Build Sprint 12 ECA FPR Objects | 10 Sprint 12 FPR Objects impacted because of FI/CO Recon CRs and the Build sprint needs to be adjusted as the delivery of the object's catchup will be done by Sprint 13(9 Objects) and Sprint 14 (1 Object) | Delivery impacted due to the CR and functional spec changes of the FI/CO INT-CR0463 ¦ 175 Hours INT-CR0473 ¦ 1 FTE ¦ 180 Hours/Sprint |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0513_R3_Update%20the%20Build%20Sprint%2012%20ECA%20FPR%20Objects.pptx?d=w5b2bb496e2094934be9c25774611f643&csf=1&web=1&e=CNroJq |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR013, FPRXR017, FPRXV087, FPRXV088, FPRXV095, FPRXV096, FPRXV120, FPRXV132, FPRXV133, FPRXV134 | 10 |  | 0 | FPRXR013, FPRXR017, FPRXV087, FPRXV088, FPRXV095, FPRXV096, FPRXV120, FPRXV132, FPRXV133, FPRXV134 | 10 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-10 | Related to CR0463 / CR0473; created by Aarti | [9 empty] | Other | Tower | 2025-04-10 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0514 | Rejected |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Aditya Tiwari | [11 empty] | Addition of 'Quality Stock' field in LOGI0237_IF and LOGE0239_IF | The 'Quality Stock' field needs to be added in the mapping for LOGI0237_IF and LOGE0239_IF. These 2 objects are Fully completed objects. We have a requirement to make few additions in the mapping. | For the reconciliation to happen correctly, quality stock field needs to be added. FS Build CR - 0286 has already been raised. (efforts less than 40 hrs) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/CR%20-%20514_%20Need%20to%20add%20Quality%20Stock%20field%20in%20interface%20mapping%20and%20custom%20table.pptx?d=w23bca1bcef9f47bb8e147dfc82e9a673&csf=1&web=1&e=wyB7br |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 12 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-04-24 | [9 empty] | Confirmed to have been moved to Build CR Log as technical effort is less than 40 hours | Build | Not Assigned |  | Not Approved | 04, 2025 | 04, 2025 | 2025-04-08 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0515 | Rejected |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | doug.utberg@intel.com | [11 empty] | ECA Report to show SAC Change Log | Create an ECA view and report to conslidate/sort the changes that have been made in SAP Analytics Cloud for oversight & change management | Change log in SAC-P is standard out of box functionality. However to use this requires user to select the right model, dimensions and drill down to the exact intersection to see before change, after change and delta. Users want an easier, report like interface which will be quicker to use and easily report on the changes made. Security might also become an issue if standard SAC change log functionality is rolled out to all users as Model wise security is not applicable to change log view. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INTCR0515%20%20SAC%20Change%20Log%20Report%20in%20ECA%20.pptx?d=wcba6eb4233874c8d8c45a3e672a1a022&csf=1&web=1&e=vlKnY2 |  | 1. Process Scope / Design Change |  |  |  | 60 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No |  | 2025-05-08 | [9 empty] | Confirmed by Matt Wycoff, Doug Utberg, and Dan Skiendziel to be cancelled as the ability of SAC to structure data in a manner that meets the reporting requirements. Therefore, this ECA report is not required. | Design | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-08 | 0 | < 15 Days | hatewari@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0516 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | Suresh Nagalingam Muniandi | [11 empty] | Descope interface object FPRI0868 | For WOM related customer payment advice creation, we have 3 object, interface to receive the file from WOM, enhancement to create the payment advice in CFIN, and another interface to send respond back to WOM from CFIN. Initially these 3 objects are created as the process type is asynchronous. | During requirement gathering it was decided to have the process type as synchronous. Also the volume of the record is very less and we will API for passing the data and not file based. So request and response will be handled in one interface. That is why need to descope FPRI0868 (Interface for receiving response from SAP once WOM related payment advice created in SAP). |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0868 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-08 | 0 | < 15 Days | sureshx.nagalingam.muniandi@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0517 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 4.11 OTC IF - Order Management |  | 05. OTC IP | Vinayak Prabhu | [11 empty] | Cancellation of object OTCI0660 _ALPS Outbound Interface | Cancellation of object OTCI0660 _ALPS Outbound Interface | Sales order cancellation in ALPS application and the SAP will be a manual process (S4 data accessed from ECA), instead of going through the outbound interface design, which is implemented for My samples interface. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0517?csf=1&web=1&e=UEWcSN |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0660 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | [10 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-08 | 0 | < 15 Days | vinayprabhu@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0520 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shubham Sharma | [11 empty] | Cancellation of OTC IP Objects: OTCM026_IP - Open Value Contract | As per business requirement this Value Contract is no longer needed. | OTCM026_IP : As per business requirement Value Contract is not needed. Hence it needs to be descoped. Requirement captured under OTCM028_IP. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0520/RE%20Descoping%20CR%20Approval%20Email%20from%20GPO%20required.msg?csf=1&web=1&e=zKGlw5 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCM026_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | [10 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | atrajput@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0521 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Sindhuja Gangireddy | [11 empty] | Changes required in OTCE0171 related to CRDH block | As per alignment with business, removal of credit block at header (CRDH) and item (CRED) should not be considered as significant change hence Z3A7 output should not be triggered for removal of block. Also, credit block (CRDH & CRED) should not affect trigger of Z3A7 output if any significant changes are done to the order. | If removal of credit block is considered as significant change; it will trigger Z3A7 output (Order confirmation) to the customer multiple times. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0521_OTC%20IF_Removal%20of%20CRDH%20block%20not%20to%20be%20considered%20as%20significant%20change.pptx?d=w795bd3133fa247db9cd8dffee1bd05f8&csf=1&web=1&e=CvO49f |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0171 | 1 | OTCE0171 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | FUT has already been passed. Approved in offline email with Uzma | [9 empty] | Build | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0522 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV193 - Generic vendors location details | FPR - Cancellation of ECA View object- FPRXV193 - Generic vendors location details -- Since the requirement of this is covered in the ECA objects - FPRXV041 (Asset List Report) & FPRXV043 (Depreciation Actual Report), Asset Accounting Transactions, Depreciation Forecast Asset, Depreciation Actuals by Asset | Objects Descoped since the requirement is covered under other ECA object: FPRXV041 (Asset List Report) & FPRXV043 (Depreciation Actual Report), Asset Accounting Transactions, Depreciation Forecast Asset, Depreciation Actuals by Asset |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV193 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0523 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre | [11 empty] | FPR - Cancellation of ECA View object- FPRXV138- Localization - Malaysia: Generate tax schedules /reports in the format needed for tax filing | FPR - Cancellation of ECA View object- FPRXV138- Localization - Malaysia: Generate tax schedules /reports in the format needed for tax filing -- Since the requirement of this is covered in the ECA objects - FPRXV038 (Combined Asset Tax Roll Forward Report) | Objects Descoped since the requirement is covered under other ECA object: FPRXV038 (Combined Asset Tax Roll Forward Report) |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV138 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0524 | Cancelled | Move to Build CR log as it is less than 40 hours of tech effort for R3 | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Balu Praveen M. | [11 empty] | Changes required in OTCE0083 related to Price Swamp | As per the alignment with business, the open sales orders filtration logic for price swamp should be based on packing status | The current logic is based on Delivery status, when we reprice sales orders without considering packing status, this leads to deviation in prices between commercial invoice and customer invoice. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0524%20Changes%20required%20in%20OTCE0083%20related%20to%20Price%20Swamp,%20open%20sales%20orders%20logic.pptx?d=wccf71622a0bd48a4a6518c173f13f984&csf=1&web=1&e=xdadrE |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Tech effort is less than 40 hours. this needs to be moved to the Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-09 | 0 | < 15 Days | balupm@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0525 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Balu Praveen M. | [11 empty] | Changes required in OTCE0486 related to Price Swamp | As per the alignment with business, the open sales orders filtration logic for price swamp should be based on packing status | The current logic is based on Delivery status, when we reprice sales orders without considering packing status, this leads to deviation in prices between commercial invoice and customer invoice. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0525%20Changes%20required%20in%20OTCE00486%20related%20to%20Price%20Swamp,%20open%20sales%20orders%20logic.pptx?d=we67fcefa61ec42c2898a01f06a764095&csf=1&web=1&e=D0cgX2 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Moved to build CR log as it was less than 40 hours of technical effort. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-09 | 0 | < 15 Days | balupm@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0526 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: FTSE1145 - Enhancement to update BoM components data against child and merging Production Orders from e2open to IP SAP S4 HANA system for IF (We will add this functionality to both the Lot split (FTSI1142) and Lot merge (FTSI1140) interfaces and handle it from both Therefore, this enhancement is no longer required.) | Cancel objects added under R3 | To update BoM components data against child and merging Production Orders from e2open to IP SAP S4 HANA system for IF. We will add this functionality to both the Lot split (FTSI1142) and Lot merge (FTSI1140) interfaces and handle it from both. Therefore, this enhancement is no longer required. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0460%20%26%20CR0526/RE%20FTS%20IP-%20CR%20for%20Descoping%20RICEFW.msg?csf=1&web=1&e=vLthL8 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE1145 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | [10 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | akindore@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0527 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | mpuvvala@deloitte.com | [11 empty] | Descoping of 3 subprocess - Division Transfer use case in PaPM | The following division transfer sub process logic has to be removed from Division Transfer PaPM model (NPG CS Plug, CSV eODM, NPG eODM). Split CPU CS Mapping Rules Table for IOT CS Plug into 2 tables in PaPM - CPU Mapping Rules Table for IOT CS Plug, CS Mapping Rules Table for IOT CS Plug. | The following division transfer sub process will be EOLed and no longer required. (NPG CS Plug, CSV eODM, NPG eODM). Splitting of CPU CS Mapping Rules Table for IOT CS Plug into 2 tables in PaPM for ease of maintenance and avoiding errors. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0527%20%E2%80%93%20Descoping%20of%203%20subprocesses%20%E2%80%93%20Division%20Transfer%20use%20case%20in%20PaPM.pptx?d=w3b9a0c8791e545be92bda7401c0a5623&csf=1&web=1&e=HXsFW1 | New Requirement / Scope | 3. Configuration Change | DC-100-020 |  | Low | 40 | 1 | [7 empty] | 40 | [5 empty] | 0 | 40 | Configuration |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  | 2025-04-25 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | o This change will be performed by 2 offshore resources, and the process is contained to just the PaPM module. • The capability of doing division transfer is not going away with this sub-process logic removal. • There is something built already, so the teams will need to remove that tech components as well. | [9 empty] | Other | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0528 | Approved |  | ERP | R3 (Release 3) | Low | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shishir Kumar Dwivedi | [11 empty] | Cancellation of RICEFW objects in S4 R3 IDM object tracker OTCC1233 Intel Federal Data conversion for Flex rates (labor rate deck) OTCC1234 Intel Federal Data conversion for Federal Sales Orders OTCC1226 Data conversion for clause assignments to Intel Federal Contracts OTCC1230 Intel Federal Data conversion for Contract Flow Down Assignment | OTCC1234 - In the new Dassian design, a material list is first created in the Dassian contract, which then creates the S4 sales order. Dassian is an in-built tool in S4, and they have standard RFC connections. | those objects will be added as a part of conversion tracker to avoid duplicates removing in OTC S4 tracker |  | No |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=8dGgpg&ovuser=36da45f1%2Ddd2c%2D4d1f%2Daf13%2D5abe46b99921%2Canntam%40deloitte%2Ecom&OR=Teams%2DHL&CT=1748634199745&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA0MTcxOTMxNiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=4f4ea3a1%2Dd01a%2D9000%2D025d%2D03fcef6985a4&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FINT%2DCR0528%2F%5FEXT%5F%20RE%5F%20CR%20approval%20needed%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FINT%2DCR0528 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCC1233, OTCC1234, OTCC1226, OTCC1230 |  |  | 4 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-10 | 0 | < 15 Days | balupm@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0529 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Poonam Dhouni | [11 empty] | Objects to be removed from Deloitte object tracker | These Objects are to be removed from Deloitte object tracker: OTCI0947 - Create Entitlements for Hardware in EMS [SAP SCI to SAP EMS] OTCI0937 - Display Component Assembly [OL to EMS] OTCI0938 - RMA case serial number validation [OL to EMS] OTCI0939 - RMA case serial number validation [OL to EMS] - R4C OTCI0940 - Return (Cancel or Reactivate) Serial Number from R4C (New) [OL to EMS] OTCI0948 - Sales Order Report in Entitlement Hub (Internal Portal) [OL to EMS] OTCI0949 - Query Serial Number by using Delivery Note from R4C [OL to EMS] | OL to EMS interfaces build/development will be owned by Intel IT team. During EMS workshops, it was agreed that EMS will be treated as a boundary app. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FChange%20Request%20Decks%2FOTC%2FRE%20EMS%20RICEFW%20objects%20status%20to%20be%20updated%20in%20Smartsheet%20%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FChange%20Request%20Decks%2FOTC |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0947, OTCI0937, OTCI0938, OTCI0939, OTCI0940, OTCI0948, OTCI0949 |  |  | 7 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | There are no replacements for these descoped EMS objects. All the EMS related RICEFWs were descoped for Deloitte development as they were moved to boundary app ownership. Confirmed by Kim Moore and approved by Shelly | [9 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-10 | 0 | < 15 Days | pranjayadav@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0530 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Descoping of object IP_PTPI1152_Interface from IRIS to S4 to send NSR to Generate PR and STR in S4 | Descoping of object IP_PTPI01152_Interface from IRIS to S4 to send NSR to Generate PR and STR in S4 | Rational for change - It was decided to descope the PTPI1152_IP object as there is a decision made that IRIS will not be interfacing with IP. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0530?csf=1&web=1&e=514Mra |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI01152_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-16 | Decision email for IRIS to not interface with IP is included in the linked folder. Now that the interfaces are descoped: Purchase documents will be created manually in IP system, no automatic creation through IRIS interface. | [9 empty] | Other | Tower | 2025-04-16 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-10 | 0 | < 15 Days | yswaddeshpande@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0531 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics 11. Technology 16. Testing | Naman Parti | [11 empty] | Update new version Terms & Conditions for OM Output Forms | This change request aims to update text for the generic Terms & Conditions attached to all output forms and email bodies in OM. (ZBA1, ZBA2, ZBA3 and ZBA4) | A generic version of Terms and Conditions is required on order outputs as a legal safeguard in cases where an order is created without signed customer-specific Ts&Cs. With Intel Foundry establishing a separate legal entity, new generic terms and conditions are needed on order output documentation. The current Ts&Cs are specific to Intel Products. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDB0D434E-E46D-4056-8CE1-44589E101842%7D&file=INT-Build-CR0304-Update%20new%20version%20Terms%20&%20Conditions%20for%20OM%20Output%20Forms.pptx=&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 8 | 0 | [8 empty] | 8 |  |  |  |  | 0 | 8 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCF0004_IP | 1 | OTCF0004_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-04-16 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | Confirmed by Brianne Ramirez and Uzma that this was approved offline | [9 empty] | Build | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-10 | 0 | < 15 Days | tganguli@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0533 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | marloncarrillogonzalez@deloitte.com | [11 empty] | Cancellation for WRICEF Object ID LOGC0970_IP WIINGs to EWM, Open Inventory Conversion for IP and IF (as applicable) , ECC/WM to EWM | Object ID LOGC0970_IP WIINGs to EWM, Open Inventory Conversion for IP and IF (as applicable) , ECC/WM to EWM', needs to be cancelled | Object LOGC0970_IP is not relevant object ID for IF R3 scope. For IF inventory conversion a different object ID is created, therefore this needs to be cancelled |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0533%2C%20CR0534&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGC0970_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | [10 empty] | Other | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-11 | 0 | < 15 Days | mayankverma4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0534 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 6.3 PTP - EWM | Yes | 07. FTS IF | marloncarrillogonzalez@deloitte.com | [11 empty] | Cancellation for WRICEF Object ID LOGC0971_IP Open Inventory Conversion for IP and IF (as applicable) , WIINGs to EWM | LOGC0971_IP Open Inventory Conversion for IP and IF (as applicable) , WIINGs to EWM' needs to be cancelled | Object LOGC0971_IP is not relevant object ID for IF R3 scope. For IF inventory conversion a different object ID is created, therefore this needs to be cancelled |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0533%2C%20CR0534&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGC0971_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | [10 empty] | Other | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-11 | 0 | < 15 Days | mayankverma4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0535 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Connie Wei | [11 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV192 - LE Stitching Report | Tax team is cancelling ECA object FPRXV192 (LE Stitching Report) since the GLAP Report meets all the requirements of the LE Stitching Report, as the fields required are the same. | The GLAP Report meets all the requirements of the LE Stitching Report, as the fields required are the same. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0500,%20CR0509,%20CR0516,%20CR0522,%20CR0523,%20CR0535,%20CR0411/EXT%20RE%20FPR%20-%20Objects%20Cancellation%20CR%27s%20and%20CR%27s%20for%20CBB%20meeting.msg?csf=1&web=1&e=ubtDHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV192 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-12 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0536 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 09A. Master Data | Rachel M Goulding | [11 empty] | PC Derivation Overwrite | There are scenarios where MM characteristics are insufficient to achieve the desired PC via derivation. For these cases, we need the ability to directly choose the PC and overwrite the rule derivation result. The business is requesting a UI ability to manage an overwrite table with MM, effective date and the desired PC. | If we are unable to alter the PC at the source to ensure accuracy, all applications using PC would need to reference correction logic and where financial transaction were booked, correcting Journal Entries would be posted. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT%20CR0536%20PC%20overwrite.pptx?d=w0fddcd69bd624eba9749d036910ac85b&csf=1&web=1&e=lc1Nkq |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 Hours | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael that that Candice approved this to not be required. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-14 | 0 | < 15 Days | rachel.m.goulding@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0537 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 09A. Master Data 11. Technology | Subramani . | [11 empty] | IC Mark up IF - Value add logic from Program run time | Calculate value addition based on runtime of the Costing run program instead of CKIS program | FPRE0698 enhancement is to calculate markup based on Value addition. As per the initial logic value addition need to be calculated as per table CKIS, But the values are not available in CKIS table during runtime and hence the revised logic to calculate value addition from runtime is updated. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0537_Value_Addition_From_Runtime.pptx?d=w703a6d9b62cc4bdb8764eeedd84c2c4c&csf=1&web=1&e=NIKFjZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 65 | 0 | [8 empty] | 65 |  |  |  |  | 0 | 65 | Tech - S/4 | No |  | 0 | N/A |  | FPRE0698 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0698 | 1 | FPRE0698 | 1 |  | 0 |  | 0 | N/A |  | 2025-09-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | [10 empty] | Build | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | subramani@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0538 | Approved | Configuration will be 8 hours | ERP | R2 (Release 2) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Kalyan Dey | [11 empty] | UK Sub-consolidation BS/PL Hierarchy Update | Need to update UK sub-consolidation Balance Sheet and Income Statement hierarchy, as well as Income Statement Reporting Rule, given previous version mainly considered LE420 sub-consolidation reporting requirements, and we've recently completed the standardization between LE420 group and LE417 group reporting requirements, to fit for both groups. | This change fulfills the reporting requirements for both LE420 group and LE417 group after analysis and standardization between two country teams. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE207FA6B-7D48-4D74-9B6E-483E9CCC4DE3%7D&file=INT-CR0538%20_R2_UK%20Sub-consolidation%20BS%2CPL%20Hierarchy%20Update.pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 8 | [5 empty] | 0 | 8 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | This is configuration work only, and the team has confirmed changes will be completed by 4/25. Approved in offline email with Uzma | [9 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | kkrishnatulasi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0539 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 08. FTS IP | Yash Mathur | [11 empty] | Cancel object ID PTPE0473_IF Demand Change - Automatic update of PR/PO/STR/STO/Scheduling agreement and Production Order in S/4 based on input signal from planning engine | The DCR spec applies for IP and no IF design/technical impacts expected | DCR scope covers Semi-finished / Finished-good material and the capability does not cover materials planning. Since the DCR process is allowing a break-in during frozen period exception to edit an already replaced PO (for finished good), the use case is IP focused. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0539/EXT%20RE%20CR%20Approval%20Request%20-%20Cancel%20RICEFW%20PTPE0473_IF%20-%20DCR.msg?csf=1&web=1&e=7ygGhK | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=gbb8Ok&CID=c362d29d%2Db206%2D4bd4%2Dbab8%2D31832e1a56b0&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0539%2FEXT%20RE%20CR%20Approval%20Request%20%2D%20Cancel%20RICEFW%20PTPE0473%5FIF%20%2D%20DCR%2Emsg&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0539 |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | yamathur@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0540 | Approved | Should be tagged to PTPE1436_IP, PTPE1436_IF, PTPE1437_IP, PTPE1437_IF | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Ramagiri Pradeep Kumar | [11 empty] | Console: 2910/2911_PTP_PM-090-040_Enhancement required to populate custom logic for BLAORD & BLAOCH_IF _IP | 2910/2911_PTP_PM-090-040_Enhancement required to populate custom logic for BLAORD & BLAOCH_IF _IP | Enhancement required to populate custom logic for BLAORD & BLAOCH_IF _IP |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR0540_PTP_IF_IP.pptx?d=w7d9cac5c051c477994793db9b31cbc56&csf=1&web=1&e=mDKyYw |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 |  |  | 13 | [5 empty] | 25 |  |  |  |  | 0 | 25 | Tech - S/4 | Yes | S4 | 2 | PTPE1437_IP, PTPE1437_IF |  | PTPE1437_IP, PTPE1437_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPE1436_IP, PTPE1436_IF, PTPE1437_IP, PTPE1437_IF​ | 4 | PTPE1436_IP, PTPE1436_IF, PTPE1437_IP, PTPE1437_IF​ | 4 |  | 0 |  | 0 | N/A |  | 2025-08-08 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This request is to add custom fields that Web Suite requires. | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | ramagkumar@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
| N/A | INT-CR0541 | Cancelled |  | ERP |  |  | 06. PTP | [15 empty] | Descoping of object PTPE1009_Returns to 3PL |  |  |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Duplicate of CR0542 | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-15 | 0 | < 15 Days | pvemuri@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0542 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Prabhakar Vemuri | [11 empty] | Descoping of object PTPE1009_Returns to 3PL | Descoping of object PTPE1009_Returns to 3PL | This is based on the decision to move the GXO 3PL warehouse to EWM (Movement of stock from Onsite Warehouse to 3PL warehouse will no longer require an STO (Plant to Plant transfer) | NA | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0542/RE%20PTP_%20Descoping%20the%20object%20PTPE1009_PMO%20approval%20requested.msg?csf=1&web=1&e=3IoqxV |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE1009 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-06 | [10 empty] | Other | Tower | 2025-08-06 | 08, 2025 | 08, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | pvemuri@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0543 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 09A. Master Data 09B. Data Migration | Naveen Negi | [11 empty] | R3-New company codes required for Foundry entities in India (843), Taiwan (708) and Japan (652) & Dummy company codes in IF & IP for HRMM to allow cross-box workflow | Request to create 3 new company codes in IF/CFIN for R3 for new Foundry entities in India (843), Taiwan (708) and Japan (652). Create 2 dummy company codes for HRMM to allow cross-box workflow, 1 for IF (998) and 1 for IP (997) | 1. Legal Entity – 652/708/843 New legal entities to be established to support R3 IAO. 2. Legal Entity – 998/997 To enable approval workflow across different S4 boxes, we need to create 2 dummy company codes, 1 in IF and 1 in IP so that employees in IP box can be assigned to the dummy company in IF to execute various approval and vice versa. These 2 company codes should not have any financial transactions going through, thus, posting period variant will be set as blank. We will only create 1 profit center and 1 cost center under each company code to allow employees to be assigned in S4. |  | Yes |  | 100 hours of configuration effort | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0543_R3_Company%20code%20CR%20R3%20scope%20April%20request.pptx?d=wd059f46186ba49c5afe27eeb7eab5051&csf=1&web=1&e=1uAGPp | Design / Build Gap | 1. Process Scope / Design Change | DC-020-010 |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-17 | o AR: Add in PTP configuration hours – @Acharya, Prabesh |  |  | 2025-04-18 | • Discussed adding three company codes for Intel Foundry due to new legal entities in China and India. • The creation of new legal entities is for testing purposes. • The process for handling legal entity changes was discussed, emphasizing the need for governance. | [5 empty] | Design | CL/OSC | 2025-04-18 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-15 | 0 | < 15 Days | navnegi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0544 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | sbugulu@deloitte.com | [11 empty] | Cancellation of FTS-IF object FTSI1015, FTSI1018,FTSC0199 | Confirmation and goods receipt is covered under the object “FTSI1014 - Interface from SAP ME to S4 for auto confirmation of production orders” hence FTSI1015 is no longer needed. FTSI1018-IMO - Interface from NBS to S4 to delete STO line item based on the cancellation signal from NBS - Covering in another object FTSC0199- Conversion - Open Production Orders- this object no more required- covering in another object GPO approved email attached | Confirmation and goods receipt is covered under the object “FTSI1014 - Interface from SAP ME to S4 for auto confirmation of production orders” hence FTSI1015 is no longer needed. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/EXT%20RE%20FTS-IF%20RICEF%20Cancellation%20Request.msg?csf=1&web=1&e=FtXkdz |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-19 | Approved in ad hoc meeting. - AR: Include Stef, Sunil P, and Devendra to see if there is any objection. Otherwise, CR is considered approved. | [9 empty] | Other | Tower | 2025-05-19 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0545 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Surendra Kusumuru | [11 empty] | Request for the creation of new enhancement object for the AMPL record creation in S4 for both IP & IF | New Enhancement will be needed to create AMPL using HERS record in S4. | As discussed in the PTP sub team workshop and in alignment with @Pancholi, Ranju , it was decided to hold the AMPL interface object and create a new Enhancement object instead to reduce the complexity of AMPL creation. 04/24: by creating this enhancement, we can avoid creation of multiple interfaces from SPEED to S4 by using the existing HERS record, which is already created through the SPEED to S4 interface, to generate AMPL. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0545/Enhancement%20Request%20for%20CR0545.eml?csf=1&web=1&e=sjJImc | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0545/INT-CR0545%20for%20AMPL%20records.pptx?d=w263676dee60f43fca9e0f10b751823df&csf=1&web=1&e=8d3Fc1 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 2 | PTPE1452_IP, PTPE1452_IF |  | PTPE1452_IP, PTPE1452_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | [10 empty] | Other | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-16 | 0 | < 15 Days | surensurendra@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0547 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Sindhuja Gangireddy | [11 empty] | Inbound Interface from WOM to S4 HANA to send customer hierarchy | Requirement is to develop an interface to fetch customer information from WOM to S4 HANA . WOM users will have multiple sold to’s and ship to assigned in WOM portal and the details such as Name , address and the ship to’s assigned to sold to’s must be sent from S4 to WOM dynamically. WOM needs to access customer master data dynamically( it does not store it) to there is just one interface for customer master. Ship to party data is required in real time in WOM with latest data as it would impact business and user experience. | WOM users will not have visibility to customer information as the data cannot be stored in WOM portal. Hence , an interface is required to retrieve customer information from S4 IP system. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0547_OTC%20IP_CR%20Deck.pptx?d=w302feb5199944a8e84ecb2fb496f5b35&csf=1&web=1&e=yNV7he |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 1 | OTCI1498 | 2996, 3161 | OTCI1498 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o The team tried looking for other options for send customers to WOM in real-time. There is a lot of criteria for how WOM pulls the customer. • Decided to come back and pull from S4 • WOM is a thin layer and doesn’t store data. o AR: Go through intake process for a new RICEFW ID - @Deolalikar, Sagar @Nayak, Keerti @Vishwanathan, Ravi | [9 empty] | Other | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-16 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0548 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Sindhuja Gangireddy | [11 empty] | To incorporate WOM user email ID field in WOM-S4 order create/change payload and update it in sales order text ID .Additionally, by extracting the WOM user email ID from the sales order text, the system can automatically generate and send out order acknowledgments or confirmation emails to the respective WOM users. | WOM users should be able to receive email for order confirmations from SAP. When an order is created in SAP through WOM interface , WOM user ID is stored in VBAK- BNAME where as WOM user email ID is not stored in SAP as part of standard functionality. Hence , to accommodate WOM user email ID in sales order text ID is created in S4. Addition of WOM user email ID field is required in WOM to S4 payload in OTCI0037 and OTCI0061 payload. Further , an enhancement is requirement to read email ID from text ID available in sales order and send order Acknowledgement/confirmation output to WOM user. | Change in WOM order create/change payload is required to accommodate WOM user email ID and enhancement is required to read the email ID from sales order while sending order Acknowledgement/output to WOM user email ID. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0548_OTC%20IP_CR%20Deck_OTCI0419.pptx?d=w4fd0a1e378dc48598b972255756c4bc9&csf=1&web=1&e=8hESeQ |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 20 |  |  |  |  | 0 | 20 | Tech - S/4 | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0419, OTCI0037, OTCI0061 | 3 | OTCI0419, OTCI0037, OTCI0061 | 3 |  | 0 |  | 0 | N/A |  | 2025-09-01 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o 2 new RICEFW objects that have to be created; it is an existing functionality in ASN between WOM and ECC. o This was not in scope as it originally for ASN. It was supposed to be Logistics.  There is a custom table that is used today to grab the correct email address.  The custom table isn’t necessary as the team has found a better way to retrieve the email ID. | [9 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-16 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0549 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shubhangi Mehrotra | [11 empty] | Cancellation of RICEFW Object: LOGI1290, LOGI1291, LOGI1292 | ECD objects were on Hold for a long time due to IP/IF segregation. Then, when the design was picked up, it was picked up, it was found that R3 design architecture needs to be updated. Therefore, we are marking these objects as "Cancelled" in Sprint 12 and will add them in Sprint 13 upload. | Delay in the IP/IF segregation object dates need to be pushed from Sprint 12 to Sprint 13 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Cancelled as this CR is to replan sprint activities, not descope RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-16 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2.3MR (Aug 2026) | R2.3 ITC | INT-CR0550 | Approved | Approved, but pending finalization of deployment strategy | ERP | R2.3 Aug 2026 | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | jason.carmichael@intel.com | [6 empty] | TBD | Open |  |  |  | Implement new SFTP mapping for order creation and changes to support the updated customer PO file format | Implement new SFTP mapping for order creation and changes to support the updated customer PO file format. Modify the current SFTP process to read the new file format and convert it into orders or update existing ones. Creation and updates will be sent separately but in the same format. The process must linearize monthly quantities into separate PO lines and capture the customer's customer PO (PO Reference No) in the sales order Ship-To Party Customer Reference field. ​ Update the Backlog Report in ECA to include Customer’s final Ship To ID and Ship-To Party Customer Reference field. | New Customer Change |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0550%20Create_Change_Upload.pptx?d=w7689fb869d3f4f7b9cd70fb3d02a6495&csf=1&web=1&e=Cmtylv |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 100 | 0 | [8 empty] | 306 |  |  |  |  | 0 | 306 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-24 | o This CR is to introduce a new format for the SFTP mapping that the team currently has. o AR: Determine when customer response is required and customer expectations - @Wu, Keith @Loh, Anna o AR: PMO team to come back with new Post-R2 / Pre-R3 CR Tracker, details on who would complete the work, and timeline for deployment - @Gainda, Alpna @Anna Tam |  |  | 2025-05-02 | • The change request is for a new customer who requires Intel to read their specific SFTP format for order creation and changes. • Code requires modification to read the new format and handle specific nuances, such as splitting quantities and storing customer-specific purchase order information. • The request is considered strategic, necessitating functional changes to support the customer and ensure a successful deal. • This change request is being reviewed for awareness as the integration with the S4 environment requires regression testing to ensure capabilities are maintained. • The work will be completed by non-IAO IT resources and is out of IAO scope. Uzma Ahmed will align with Kevin Brown to take CR0550 into an IT Forum to track it. • Tariff Changes: Post R2, there will be a need to address tariff changes, potentially requiring another fast-track approach. • The discussion highlights the need for visibility and coordination between program and non-program resources to manage customer onboarding efficiently. o Discussed utilizing existing resources that manage customer onboarding daily, rather than relying solely on program resources. o There are concerns about the time and effort required to ingest new formats into EDI, suggesting inefficiencies that need addressing. o There is an ongoing effort to develop a clear process for handling customer requests, ensuring alignment between project and non-project teams. o A fast-track approach is proposed to quickly address urgent customer requests, allowing business development managers to negotiate deals with confidence. | [5 empty] | Build | CL/OSC | 2025-05-02 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | brianne.ramirez@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0551 | Approved | 112 hours of tech effort | ERP | R3 (Release 3) |  | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 10. Analytics | sosina.gebregziabher@intel.com | [11 empty] | New ECA View Object: PDF-SMH(Sapience Manufacturing Hub) Integration Platform boundary application needs the production order type configuration data | PDF-SMH(Sapience Manufacturing Hub) Integration Platform boundary application needs the production order type configuration data | This is a new request from the PDF-SMH application, which integrates manufacturing applications such as MES with SAP S4. To accurately map data between the manufacturing systems and SAP S4, access to the S4 production order type configuration is required. This configuration includes a comprehensive list of possible values and descriptions for order types.​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD182700C-06E8-47A8-9A9B-DDA858C3F445%7D&file=Change%20ID_Tower_CR%20Deck_PDF_SMH_ProdOrderTypeConfig.pptx&action=edit&mobileredirect=true&previoussessionid=c1d693c2-8894-1364-a67e-7cf3ac83225b&isSPOFile=1&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cnjalaliheravi%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAzMTMyMTAxNCIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [8 empty] | 32 |  |  |  |  | 0 | 32 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-04-17 | o Because PDF-SMH will be a Boundary App, the guidance is to have the data go through ECA. o AR: Add in confirmation that there will be no impact to teams within the “Effort” row - @Sadarangani, Aarti |  |  | 2025-04-18 | • Discussed the effort required for scheduling and production order types. • Clarified that the plan for R3 was approved and discussed the mapping of production order types. • The effort required for the change was estimated to be 112 hours, involving Deloitte and Intel. • Confirmed there was no impact on current work. | [5 empty] | Other | CL/OSC | 2025-04-18 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | njalaliheravi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0552 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV039- Link Asset to the Purchase order | FPR - Cancellation of ECA View object- FPRXV039- Link Asset to the Purchase order- Since the requirement of this is covered in the ECA objects - FPRXV051 (PO Research Report) | Objects Descoped since the requirement is covered under other ECA object: FPRXV051 - PO Research Report |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0592,%20CR0590,%20CR0591,%20CR0552%20%26%20CR0553/RE_%20R3%20-%20Fixed%20Asset%20Team%20-%20ECA%20Objects%20Cancellation%20Approval.msg?csf=1&web=1&e=nHa1qb |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV039 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0553 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV042- Asset list HANA Report | FPR - Cancellation of ECA View object- FPRXV042- Asset list HANA Report - Since the requirement of this is covered in the ECA objects - FPRXV041 (Asset List Report) | Objects Descoped since the requirement is covered under other ECA object: FPRXV041 - Asset List Report |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0592,%20CR0590,%20CR0591,%20CR0552%20%26%20CR0553/RE_%20R3%20-%20Fixed%20Asset%20Team%20-%20ECA%20Objects%20Cancellation%20Approval.msg?csf=1&web=1&e=nHa1qb |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV042 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0554 | Rejected |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [11 empty] | Implementation of custom fields to capture and retain the original requested quantity | To enhance the tracking and comparison of requested quantities in the KPI report by capturing original values in custom fields. 1. The original requested quantity will be captured in a custom field upon the customer's initial submission. 2. If the customer revises the Purchase Order (PO), the standard requested quantity. The custom field will retain the original values, allowing for a comparison between the original and current requested quantity in the KPI report. Only the CBA has access to manually update the original requested quantity in the custom field. | The primary purpose of this change is to improve the accuracy and reliability of tracking requested and confirmed quantities in KPI reports. By capturing and retaining the original values in custom fields, we can facilitate a more precise comparison between the initial and revised quantities. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0_Original%20Requested%20Quanity%20and%20Original%20Confirmed%20Quantity.pptx?d=wbefd0174e08541019f865ea7edfb0347&csf=1&web=1&e=hz7IWy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 24 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-04-23 | [9 empty] | Confirmed by Brianne Ramirez to be rejected during GPO meeting | Build | Not Assigned |  | Not Approved | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0555 | Approved |  | ERP | R2 (Release 2) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 09B. Data Migration 11. Technology | syed.s.nawaz@intel.com | [11 empty] | Batch Master Extraction | Batch Master Extraction Logic | Only Batches with Inventory should be converted from Legacy system |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR0555-%20Batch%20Master%20Extraction%20Logic%20Change_LOGC0305.pptx?d=w9a3a54a73f954966a5ed28aba8aad39d&csf=1&web=1&e=8w7aDe |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 35 | 0 | [10 empty] | 35 |  |  | 0 | 35 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGC0305 | 1 | LOGC0305 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-24 | [10 empty] | Build | Tower | 2025-04-24 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0557 | Cancelled |  | ERP | R3 (Release 3) | Very High | 07. FTS IF |  |  |  | eugene.celis@intel.com | [11 empty] | Cross Site Manufacturing Change Request | Cancellation of objects FTSC0051. FTSI0337 due to cross manufacturing scenario | Cancellation of objects FTSC0051. FTSI0337 due to cross manufacturing scenario |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-17 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0559 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data | Harshavardhan Harshavardhan | [11 empty] | DATE0667_IP - Customizing Technode or stage field while creating cost center in IP system | This Technode customization functionality belongs to MDG,CFIN & IF systems not to the IP system. | This functionality not required in IP system, hence we are withdrawing the RICEFW. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0559/EXT%20FW%20FS_Technode%20%20Stage%20field%20customization%20Business%20review%20and%20approval.msg?csf=1&web=1&e=PfNMMo |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | DATE0667_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | [10 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | harshaharshavardh@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0561 | Cancelled | Need approval email from Shane and Sunil | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar | [11 empty] | FPR - Cancellation of ECA report FPRXV232-Pre vs. Post Reorg Report | Cancellation of ECA report FPRXV232-Pre vs. Post Reorg Report as this report is not required | This report is not required anymore as confirmed by Ricardo and Amanda and Eri from Opex business. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by George Bakare that this CR is no longer needed | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-17 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0566 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 7.4 FTS IF - EWM | Yes | 07. FTS IF | [12 empty] | Cancellation of LOGE1060- Enhancement to populate Factory Order @ the line level - Requested date/time and OBD Priority at header. | Cancel the Build for RICEFW LOGE1060 for populating PM Priority and Requirement Date & Time in EWM screens. | According to the solution proposed by Deloitte, which follows standard EWM practices, the business has decided to eliminate the complex custom enhancement. Proposed solution: Factory order is created with Priorities either expedite or standard then in the EWM system the respective Warehouse Process Types (WPT) ZEXP or ZSTD will be determined. WPT will be used to recognize priority in EWM system. Standard Planned Goods Issue Date & time is used for requested date and time for visibility at header & item level. Link (Page 9-11): https://intel.sharepoint.com/:w:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8F191250-AA66-4613-9FD3-7612A74DABAF%7D&file=Draft_FS-LOGE1060%20-%20Enhancement%20to%20populate%20Factory%20Order%20at%20line%20level%20-%20Requested%20%20date%20time%20and%20OBD%20Priority%20at%20header.docx&action=default&mobileredirect=true |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0566/EXT%20RE%20GPO%20Approval%20for%20Cancellation_R3_FTS-EWM_LOGE1060_Proposed%20Solution%20for%20populating%20Priority%20and%20Requirement%20Date%20%20Time.msg?csf=1&web=1&e=Dr2jOz |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1060 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | [10 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | vgulhane@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | N/A | INT-CR0567 | Approved |  | SCP | R2 (Release 2) R3 (Release 3) | Very High | 09A. Master Data | 9A.1 Master Data - ALL |  | 18. SCP | ANDREW THOMAS | [11 empty] | Additional SCP Support Role | Modify Planning Hierarchy Support role to Additional SCP Support, featuring expansion in responsibilities and extension from End Date 3/28/25 to 8/1/25. Total fees $172,706.40 | 1. Planning Hierarchy Support still needed as team is in various ERP/SCP testing cycles as well as R3 Build 2. Additional help needed designing and building upstream data entry business process 3. Additional help needed coordinating SCP/ERP Data coordination program beginning Mar. 2025 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0567%20-%20Additional%20SCP%20Support%20Role.pptx?d=w58be56879ead4257b5f55de60e583281&csf=1&web=1&e=0WKdnK |  | 14. Other Resource Adjustments |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | o This change is to extend a Deloitte resource that is working on hierarchy; this is a 4 month extension. • The SOW is already signed. • This will be the only extension ask; there is budget for this, so it is not an incremental amount. | [9 empty] | Other | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | vgulhane@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0568 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 18. SCP | ashok.sivanandi@intel.com | [11 empty] | R2 IBP/PDH Inventory Data Transition – CIBR to SPAN | Execute the inventory back-projection process from WLA UPI_BUMP and WLA UPI_DIE_PREP 2 to primary UPL_DIE_PREP items, ensuring precise adjustments for yield loss at each stage utilizing SEGMENT_YIELD parameters. | Inaccurate adjustments for yield loss and imprecise back-projection could result in substantial discrepancies in inventory levels, thereby adversely impacting production schedules. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR0568%20-%20R2%20IBP%20PDH%20Inventory%20Data%20Transition%20-%20CIBR%20to%20SPAN.pptx?d=w39ca0314bd8445e1bb51b8a5f7662d9b&csf=1&web=1&e=BtIhPV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 120 | 0 | 0 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-17 | o This small change will be implemented in the existing inventory file to improve accuracy. Using existing resources, it will be around 6 weeks to complete. • The plan is to start next Monday. There are 3 people in the PDH team and support from other impacted teams. o Does this impact other work? • There is a safety stock new requirement that came in. There won’t be any impact to existing deliverables; not in BY (just asking for some clarification) • Only when we have this scenario, then we will have the incorrect inventory numbers. o Have to do it and no impact to other deliverables. | [9 empty] | Build | Tower | 2025-04-17 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0569 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Kolleru Venkatesh | [11 empty] | Cancel objects : FTSI1015 | FTSI1015-IMR - Interface from SAP ME to auto send Production orders Goods Receipt to SAP S/4 after the completion of Manufacturing​ Cancelling due to | This object is not required as functionality covering in another existing object |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-18 | 0 | < 15 Days | kollevenkatesh@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0570 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Shubhangi Mehrotra | [11 empty] | Cancellation of RICEFW Object: LOGV005 | LOGV005_FTSIP is the requirement in IP, but there is no such requirement in IF hence cancelling LOGV005 from IF stand point | This object is not required from IF stand point. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0570%20%26%20CR0549?csf=1&web=1&e=rrdCVq |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGV005 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-18 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0571 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 11. Technology | 11.4 Technology - Boundary Apps |  | 11. Technology | [12 empty] | Ownership change from Deloitte to intel for R4C integration objects​ | Change in ownership for GRL R4C 7 existing integrations connecting to ECC in the existing landscape to be changed to S/4 as part of IAO | As the scope is firmed to rewire ¦ re-map the existing 7 integrations from ECC to S/4 leveraging the knowledge of intel CoE middleware team​ Divya and Ravi approval: https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0571/EXT%20RE%20Approval%20Needed%20CR0571%20for%20R4C%20Integration%20Objects.msg?csf=1&web=1&e=wFwlCc |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5846D977-FD82-417E-92A2-546EA8257651%7D&file=CR%20%23%20-%20GRL%20R4C%20MuleSoft%20Interface%20Enhancement.pptx&action=edit&mobileredirect=true |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-07 | Approval dependent on approval from Divya | [9 empty] | Other | Tower | 2025-05-07 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-19 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0572 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP |  |  | 05. OTC IP | [12 empty] | Cancellation of RICEF Objects: LOGF1284 & LOGF1285 - CI/PL Forms for Scrap & IRC inhouse | Cancel Object added under R3 | LOGF1284 object needs to be descoped/cancelled as there are no CI form requirements for Scrap and IRC inhouse scenarios LOGF1285 object needs to be descoped/cancelled as there are no PL form requirements for Scrap and IRC inhouse scenarios |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0572/RE_%20LOGF1284%20_%20LOGF1285%20-%20Approval%20required%20for%20RICEFs%20cancellation%20.pdf?csf=1&web=1&e=yHYTSl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGF1284, LOGF1285 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-30 | [10 empty] | Other | Tower | 2025-04-30 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-21 | 0 | < 15 Days | tukhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2m (November 2025) | N/A | INT-CR0573 | Approved | Post-R2 / Pre-R3; Confirmed by Brianne | ERP | R2 Nov 2025 | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | jason.carmichael@intel.com | [6 empty] | TBD | Open |  |  |  | PDF Formatted Invoice | Add an output condition record to enable PDF formatted invoice output by customer to a configurable SFTP folder. | New Customer Change |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0573%20Invoice%20PDF%20SFTP.pptx?d=w663c5b2348654b008a3ec94667b9a0a0&csf=1&web=1&e=bPKyQa |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-04-24 | o This is a contractual requirement for a customer; it is needed by October before the R3 go-live. o AR: PMO team to come back with new Post-R2 / Pre-R3 CR Tracker, details on who would complete the work, and timeline for deployment - @Gainda, Alpna @Anna Tam | [9 empty] | Build | CL/OSC |  | Missing Review Date for Approval Level | 04, 2025 | 04, 2025 | 2025-04-22 | 0 | < 15 Days | brianne.ramirez@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0574 | Approved |  | ERP | R3 (Release 3) | High | 10. Analytics | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | kritajoshi@deloitte.com | [11 empty] | FPR Analytics - Update Build Sprint 13 Plan and Object Tracker | Update the Build Sprint 13/14 with the below​ 8 ECA Views that the analytics team will build to support the 29 FPR Accounts Receivables reports currently planned for sprint 13 and 14​ 29 AR reports will be moved to the Intel Tracker | The object tracker currently consists of the FPR Reports whereas Deloitte Analytics team is delivering the backend views for those reports. As part of streamlining the build optics requesting updates in the Object tracker/build sprint plan and creating correct build sprint activities. |  | Yes |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0574/RE%20Action%20Required%20%20Build%20Sprint%2013%20Sign%20Off%20on%20ECA%20Views.msg?csf=1&web=1&e=CK2I3w |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR003, FPRXR004, FPRXR005, FPRXR006, FPRXR009, FPRXR010, FPRXR011, FPRXR012, FPRXR014, FPRXR015, FPRXR016, FPRXR018, FPRXR019, FPRXR007, FPRXR008, FPRXR013, FPRXR017, FPRXV087, FPRXV088, FPRXV095, FPRXV096, FPRXV120, FPRXV126, FPRXV091, FPRXV092, FPRXV094, FPRXV199, FPRXV206, FPRXV207 | 29 |  | 0 | FPRXR003, FPRXR004, FPRXR005, FPRXR006, FPRXR009, FPRXR010, FPRXR011, FPRXR012, FPRXR014, FPRXR015, FPRXR016, FPRXR018, FPRXR019, FPRXR007, FPRXR008, FPRXR013, FPRXR017, FPRXV087, FPRXV088, FPRXV095, FPRXV096, FPRXV120, FPRXV126, FPRXV091, FPRXV092, FPRXV094, FPRXV199, FPRXV206, FPRXV207 | 29 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-30 | [10 empty] | Other | Tower | 2025-04-30 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0575 | Rejected |  | ERP | R3 (Release 3) | High | 05. OTC IP | 9A.3 Master Data - Customer |  | 05. OTC IP 09A. Master Data 17. B-App | sarah.a.miller@intel.com | [11 empty] | Sales Region -new custom object in MDG | OTC-IP is requesting the creation of Sales Region as a custom governed object in MDG to support SMG & OTC-IP requirements to group Sales Organizations. | Today we have 4 different Geo Location Hierarchy Types – EN (enterprise), SM (Sales & Marketing), SMA (Sales & Marketing Analytics) and AC (Accounting). As part of IAO, we are moving toward an industry standard single Global Geo Location Hierarchy (GL) with 3 Geo’s (APAC, AMER, EMEA). It was initially proposed to break out China and India as independent sub geos in the IAO Global Geo Hierarchy to support the strategic importance and increased business focus on those regions specifically within SMG & OTC-IP After analysis, it was determined that the Geo Location Hierarchy has been used by SMG to model their Sales Regions to support their business operations versus a true Geo Hierarchy. Sales Orgs were then associate to those SM “Geo’s”. The proposal is to create a Newly Governed object called Sales Region and to associate Sales Orgs to those Sales Regions. It is recommended that the updates to the GL Hierarchy to include China and India as Sub-regions be reverted as the new Sales Region will support the reason for the previous recommendation. Sales Region/Org Association and GL Geo Hierarchy will be two separate dimensions that can be used to roll up and filter transactional data as ALL customers have a Sales Org (Sales Region/Org Association) and a Country (Geo Hierarchy). Sales Region will be separately governed by SMG Governing Body. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT%20CR0575%20Sales%20Region%20Custom%20MDG%20Object.pptx?d=w7fd2eafd6ba54033857238fc651af7a9&csf=1&web=1&e=y6CIfp |  | 1. Process Scope / Design Change |  |  |  | 35 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-05-01 | [9 empty] | This CR is less than 40 hours of work, and a non-ERP RICEFW will be created and developed by the Intel team. | Design | Not Assigned |  | Not Approved | 05, 2025 | 04, 2025 | 2025-04-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0576 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shubham Sharma | [11 empty] | Cancellation of OTC IP Objects: OTCC0652 - Listing and Exclusion Conversion for IP R3 Release | As confirmed by Ericka Ferguson(GTS Team) via mail, business no longer requires conversion for listing records. Since GTS team were the only users for Listing and Exclusion functionality, we will not take this object any further. Trade will take a final call in their internal workshop in June if listing is required or not. since the conversion is not required, we are moving ahead and descoping the requirement. | OTCC0652 : As per GTS team via mail, business no longer requires conversion for listing records. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0576/EXT%20FW%20CR0576-Approval%20needed.msg?csf=1&web=1&e=i9VQKY |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCC0652 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-01 | [10 empty] | Other | Tower | 2025-05-01 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-22 | 0 | < 15 Days | atrajput@deloitte.com | Yes | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0579 | Cancelled |  | ERP | R2 (Release 2) |  | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [11 empty] | Descoping the interface objects OTCI0275 (Order change response 3A8C from OpenText validation context) and OTCI0301 (Sales order status 3A6) for IF R2. | Descoping the interface objects OTCI0275 (Order change response 3A8C from OpenText validation context) and OTCI0301 (Sales order status 3A6) for IF R2. | There are no customers in IF R2 who will be using the PIPs (Partner Interface Processes) 3A8C and 3A6. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0579-Descoping%20the%20interface%20objects%20OTCI0275%20(Order%20change%20response%203A8C)%20and%20OTCI0301%20(Sales%20order%20status%203A6)%20for%20IF%20R2%20(1).pptx?d=w7ac7728819b24bc7978646fbce56a1a4&csf=1&web=1&e=Iyir43 |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Taposh Ganguli that the team is not descoping RICEFW but deprioritizing. Therefore, cancelling the CR. | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 04, 2025 | 2025-04-23 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0580 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | shisdwivedi@deloitte.com | [11 empty] | PAT/FAB POLP Identifier from S/4 to ECC | Identifier needs to be sent from S/4 to ECC that is FAB or PAT and Market Code in the existing interface | Since we are going to use the same table and program to call the Denodo for WIP information and we need to identify which API call to make to Denodo (PAT, WLA, FAB). With the existing design we can identify WLA using your reference field, but it would be not possible to differentiate between PAT & FAB at ECC |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0580_OTC%20IF_CR%20(FAB%20POLP).pptx?d=w6fc3ff3fb6a5434a8c3ec50bdfbd3ca4&csf=1&web=1&e=wepnnH |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 15 | 0 | [8 empty] | 15 |  |  |  |  | 0 | 15 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0410 | 1 | OTCE0410 | 1 |  | 0 |  | 0 | N/A |  | 2025-04-30 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | Related to approved CR0410. Approved in offline email with Uzma. | [9 empty] | Build | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0581 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) |  | 01. PMO | 1.1 PMO - ERP PMO |  | 01. PMO 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 10. Analytics 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App 18. SCP | Alpna Gainda | [11 empty] | Adjust WIINGS milestones to match IAO Replan | The CO to adjust WIINGS milestones to match IAO replan is pending the approval of all scope items. Therefore, this program CR is created to adjust the descriptions while the change order is being finalized and approved. | With the replan of the R3-R5 ERP timeline, the WIINGS milestones need to be adjusted to match. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PMO/INT-CR0581%20-%20WIINGS%20Milestones.pptx?d=w32c839f9553f471dbe7749b06e0ffa59&csf=1&web=1&e=nq9qii |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-04-23 | Approved in offline email with Uzma. | [9 empty] | Other | Tower | 2025-04-23 | 04, 2025 | 04, 2025 | 04, 2025 | 2025-04-24 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0582 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 04. OTC IF 08. FTS IP | Karthik Reddy Reddy | [11 empty] | Change Request for Build Instructions object - FTSI0268 | Contents in the change request: 1. Update AS2 Header section directly in the payload, previous alignment was to include it as a custom segment in the outbound IDoc. 2. Include DUNS4 and Sold to DUNS field logics in the mapping sheet and payload. 3. Add "Starting Location" custom field in the Build Instructions mapping sheet and payload. 4. Remove " Alternate Item Group" & "Usage Probability %" attributes from the mapping sheet and payload. 5.Remove this field from the mapping as PIR does not have any line-item number = E1ZAFKOL-BICONREFITEM​ 6.DCR Reason Code: As per the latest alignment, we may need to create an internal ABAP table to capture "Reason Code" and send the value as a concatenated value (Reason Code + Description)​ 7.Need to add "Production Order" number in all the BI Custom tables and BI Custom Report.​ 8. Creation of a report to trigger the BI Outbound IDoc, error handling and request to create background job. This background job must run post successful P2P background job to convert Text PR to Text PO. | Rationale behind the change is to incorporate Intel Foundry DUNS logics for LE suppliers !! and to know the starting location of the Die-Prep production process for Intel Foundry. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0582-%20Change%20Request%20for%20Build%20Instructions%20Outbound%20Interface%20_%20FTSI0268.pptx?d=w3c382132f9614340a6e93ddc7e82c8f9&csf=1&web=1&e=Gmnx1O |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 72 | 0 | [8 empty] | 72 |  |  |  |  | 0 | 72 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0268 | 1 | FTSI0268 | 1 |  | 0 |  | 0 | N/A |  | 2025-10-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | o The RICEFW is completed, but there are a lot of changes going on with the recently closed KDD and others. o This request is a consolidation of a lot of different changes into one request. • It was flushed out in various meetings and FTF. | [9 empty] | Build | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-25 | 0 | < 15 Days | karthreddy@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0583 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | snavasthi@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of Object FPRC1212_IF Project Actuals Conversion including Intel Federal | Cancellation of Object FPRC1212_IF Project Actuals Conversion including Intel Federal - This was an admin error, we never had an IF intake form | Cancellation of Object FPRC1212_IF Project Actuals Conversion including Intel Federal - This was an admin error, we never had an IF intake form |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0583,%20CR0629,%20CR0607%20%26%20CR0608/RE_%20ECA%20report%20_%20Conversion%20Object%20cancellation%20__%20FPRXV182_%20FPRXV218_%20FPRXV219_%20FPRC1212_IF.msg?csf=1&web=1&e=jG7flm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRC1212_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0584 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 05. OTC IP 17. B-App | kjell.wangaard@intel.com | [11 empty] | Remove Icertis Interface with S4/Dassian from Project Scope | Remove from scope the planned interface between boundary app "44878-Icertis Government CLM" and S4/Dassian. This includes the cancellation of the following 5 object IDs in the B-App R3 S4 Object Tracker: OCTI1243, 44, 45, 46, and 47. | This planned interface is proving to be more complex and expensive than originally perceived and no longer considered cost/benefit justified. Integration can be achieved manually in the foreseeable future. We will reduce/repurpose budget for this as part of JPOR. https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEC9FF25C-30A9-4BB8-89BC-DF7DFCB45D88%7D&file=INT-CR0584_Removal%20of%20IFL%20Icertis%20RICEFWs.pptx&action=edit&mobileredirect=true |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0584/EXT%20RE%20INT-CR0584.msg?csf=1&web=1&e=SquNHw |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI1243, OTCI1244, OTCI1245, OTCI1246, OTCI1247 |  |  | 5 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-07 | [10 empty] | Other | Tower | 2025-05-07 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0585 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 17. B-App | Brian LeBlanc | [11 empty] | Update the IRC2 relevant material characteristics validation checks | This change request aims to update the logic related to material characteristics that are relevant to IRC2. Descope the existing checks and update the latest validation checks in params table. | Intel team has simplified the IRC2 relevant material validation checks. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0585-Update%20new%20IRC2%20relevant%20material%20characteristic%20validation%20checks%20.pptx?d=w5880c9ee528f4881ba23355c3e17fec0&csf=1&web=1&e=p2QOhf | [5 empty] | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this change is less than 40 hours of effort for R3 |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-28 | 0 | < 15 Days | maabraham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0587 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Mehak Malhan | [11 empty] | Descoping of PTP objects: 1. Manual Conversion - PTPM0015 – Condition records maintenance for Decontamination suppliers & Service Charges 2. PTPI0447 - Oversight Integration Interface IP/IF S4 - To be moved to ECA | Descoping of PTP objects: 1. Manual Conversion - PTPM0015 – Condition records maintenance for Decontamination suppliers & Service Charges - To be handled manually because of low volume 2. PTPI0447 - Oversight Integration Interface IP/IF S4 - To be moved to ECA - to be sourced from ECA | Descoping of PTP objects: 1. Manual Conversion - PTPM0015 – Condition records maintenance for Decontamination suppliers & Service Charges - To be handled manually because of low volume 2. PTPI0447 - Oversight Integration Interface IP/IF S4 - To be moved to ECA - to be sourced from ECA |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0587?csf=1&web=1&e=hpEoQV |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPM0015, PTPI0447 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 04, 2025 | 2025-04-28 | 0 | < 15 Days | mmalhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0588 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Aditya Tiwari | [11 empty] | Cancellation of RICEFW ID - LOGW0994 (Requirement covered in LOGE1054) | Cancel Objects added under R3 | Need to cancel LOGW0994 because the requirements are already covered in LOGE1054 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/INT-CR0588/EXT%20RE%20FTS%20IF%20-%20Logistics%20%20CR%20-%200588%20%20RICEFW%20Cancellation%20%20Requesting%20Approval.msg?csf=1&web=1&e=D4ZN9J |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGW0994 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 04, 2025 | 2025-04-28 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0589 | Cancelled | Confirmed with Vamsi to not be a critical requirement; security and tech team are slowly work through tech effort requirements | ERP | R5+ (Post Release 5) | High | 13. Security | 13.1 Security - ALL |  | 10. Analytics | Srinivas Kolli | [11 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc2.aspx?action=edit&sourcedoc=%7B78626911-1826-4ba9-b5e8-f4a879baf5c9%7D&wdOrigin=TEAMS-MAGLEV.teamsSdk_ns.rwc&wdExp=TEAMS-TREATMENT&wdhostclicktime=1745905974997&web=1 |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-29 | 0 | < 15 Days | raj.valluri@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0590 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV055 - Location blocked for states with no registration | FPR - Cancellation of ECA View object- FPRXV055 - Location blocked for states with no registration - To cancel based on Validation Object FPRE0499 & Asset List ECA object - FPRXV041 | Objects Descoped since the requirement is covered under other ECA object: FPRXV041 (Asset List Report) & location validations are covered in the RICEFW Object FPRE0499 |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0592,%20CR0590,%20CR0591,%20CR0552%20%26%20CR0553?csf=1&web=1&e=MAmozQ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV055 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-29 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0591 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV056 - Alert on assets in closed/inactive locations | FPR - Cancellation of ECA View object- FPRXV056 - Alert on assets in closed/inactive locations - To cancel based on Validation Object FPRE0499 & Asset List ECA object - FPRXV041 | Objects Descoped since the requirement is covered under other ECA object: FPRXV041 (Asset List Report) & location validations are covered in the RICEFW Object FPRE0499 |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0592,%20CR0590,%20CR0591,%20CR0552%20%26%20CR0553?csf=1&web=1&e=MAmozQ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV056 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-29 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0592 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV054 - Location Listed Matched to Real Estate Database | FPR - Cancellation of ECA View object- FPRXV054 - Location Listed Matched to Real Estate Database - Since the requirement of this is covered in the ECA objects - FPRXV037 (Plant Overview Report) | Objects Descoped since the requirement of this is covered in the ECA objects - FPRXV037 (Plant Overview Report) |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0592,%20CR0590,%20CR0591,%20CR0552%20%26%20CR0553?csf=1&web=1&e=MAmozQ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV054 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-29 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0593 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Rishav Kumar | [11 empty] | Mapping fields Order changes from Item level to Header level in LOGI0502 | 5/9- Please consider this requirement as cancelled. Mapping fields Order changes from Item level to Header level in LOGI0502 FOR 7 fields | Requirement from Middleware team side for the mapping fields |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Neetu Ramireddi that this is not required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-29 | 0 | < 15 Days | rishavkumar4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0594 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | rudrsengupta@deloitte.com | [11 empty] | Interface from FSCO for lot level material staging by shift | FSCO publishes to S4 the list of lots required at production sites by dates/time which needs to be captured in a custom table in S4. This will be an interface to load the data published from FSCO into the custom table. ​ This table will be used to issue out lots either through a 313 movement if the warehouse location is same as production plant or through STO if warehouse is not the same as the production plant. This is part of the approved enhancement object FTSE0507. | Without this interface there is no information available in S4 to determine when the lots are required at the production sites which would lead to delays and disoriented manufacturing process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAF7F3B6E-177C-44B3-9B9C-196D01A75575%7D&file=INT-CR0594_FTS-IF_Interface%20from%20FSCO%20for%20lot%20level%20material%20staging%20by%20shift.pptx&action=edit&mobileredirect=true | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-05-01 | o All task force team meetings have been completed to work through manufacturing integration. • This CR is to bring in the needed interfaces and enhancements. o AR: Include summary slide of the work that has been going on – Rudra o There will be some effort required from FSCO or Planning/PDH perspective, so we will need to bring it in through a similar CR • There is no data or tech team impact as of now. Most of it is just from the FSCO and PDH Boundary Apps. |  |  | 2025-05-02 | • The recent changes to the ERP system are driven by new requirements identified by the manufacturing task force. These changes aim to optimize inventory management and logistics processes, particularly concerning the movement and scheduling of wafers and dies, as well as site-to-site transportation. • The process will now be driven by production scheduling at a more granular level, such as daily or shift-based requirements. This change requires: o An interface from FSCO to determine required lots shift by shift. o Storage of this data in a custom table. o Site-to-Site Transportation • New Plan: An algorithm in the Planning Data Hub (PDH) will assign shipments, necessitating: o A new interface from PDH to S4. o Shipping and STOs • S4 Role: S4 will act as a data provider in a hub-and-spoke model, but it also needs to execute shipping against STRs. • Instead of bulk STOs, lot-level STOs will be created when a lot is ready to ship, allowing logistics processes to create outbound deliveries. | [5 empty] | Design | CL/OSC | 2025-05-02 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0595 | Rejected |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | rudrsengupta@deloitte.com | [11 empty] | Custom Table to store FSCO lot level material staging | This is a new RICEF. FSCO publishes to S4 the list of lots required at production sites by dates/time which needs to be captured in a custom table. This table will be used to issue out lots either through a 313 movement if the warehouse location is same as production plant or through STO if warehouse is not the same as the production plant. | Without this table there is no information available in S4 to determine when the lots are required at the production sites which would lead to delays and disoriented manufacturing process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B37C1A1F8-DB55-4F58-A7A1-0A6C40755B8A%7D&file=INT-CR0595_FTS-IF_Custom%20table%20to%20store%20FSCO%20lot%20level%20material%20staging.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-05-01 | [9 empty] | Will be combined with CR0594 | Design | Not Assigned |  | Not Approved | 05, 2025 | 04, 2025 | 2025-04-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0596 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | rudrsengupta@deloitte.com | [11 empty] | Custom Table to store PO Lot Pegging (POLP) | New custom POLP table is required to store PO - SO pegging details. | The current table only supports R2 and straddle. Need a new table to support R3. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B374530A8-D118-4DBA-A7E3-FD1920CC5C6F%7D&file=INT-CR0596_FTS-IF_Custom%20table%20to%20store%20PO%20Lot%20pegging.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 04, 2025 | 2025-04-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0597 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | rudrsengupta@deloitte.com | [11 empty] | Custom ABAP report for SIMS PO Exceptions | This report will be used to determine the quantity on the POs that needs to be rescheduled when the FG demand changes. Exceptions across all materials cannot be viewed at one go instead can only view them material by material. | Without this there is No visibility into the POs that need to be rescheduled when demand changes. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4E762972-51E1-48A6-BAF4-D6C01F6CB507%7D&file=INT-CR0597_FTS-IF_Custom%20ABAP%20report%20for%20SIMS%20PO%20Exceptions.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 1 | FTSR1466 |  | FTSR1466 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o SIMS team wants to re-create a report that they are using now in S/4. It is medium complexity enhancement. o There is standard functionality, but that only pulls in one material at a time. • MD04/MD05 will not pull in the purchase orders or purchase requisitions data related to it. Will need to go through RICEFW intake meeting | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR0598 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Poonam Dhouni | [11 empty] | Objects to be removed from Deloitte object tracker | Object - OTCI0968 ( Return (Cancel, Replace and Update) from ISVC (R4E) [OL to EMS] ) to be removed from Deloitte object tracker: | OL to EMS interfaces build/development will be owned by Intel IT team. During EMS workshops, it was agreed that EMS will be treated as a boundary app. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/FW%20Approval%20needed%20to%20disposition%20Object%20-%20OTCI0968%20-%20Return%20(Cancel%20Replace%20and%20Update)%20from%20ISVC%20(R4E)%20OL%20to%20EMS.msg?csf=1&web=1&e=Erh6tQ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0968 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-01 | [10 empty] | Other | Tower | 2025-05-01 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-30 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0599 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.14 FPR - Boundary Apps |  | 02. E2E Process Integration 03. FPR 09A. Master Data 09B. Data Migration 10. Analytics 13. Security 16. Testing 17. B-App | kevin.m.johns@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Intel Federal Timekeeping | Due to the Kronos project Cancellation a Timekeeping solution for intel Federal is needed to be developed. Our approach is assess what SAP out of the box can offer and then modify to meet the business needs. High level requirements: Employee time data entry portal similar to todays ECC entry (currently customized) Employee time data entry portal supporting Long term leaves Approver portal Approver Delegation process adhering to compliance rules Integration from IFED to SAP with WBS projects for employees working on Federal Security adjustments Reporting | Kronos project Cancellation due to that application not meeting the needs of the business nor the Intel application standards that we have https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EcNAI01dNB9IpiTcPSvT9GsBskIknelDl6HIQTogzj6Jdw?email=lopa.chaudhry%40intel.com&e=2yjw9P |  | Yes |  |  | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EcNAI01dNB9IpiTcPSvT9GsBskIknelDl6HIQTogzj6Jdw?email=lopa.chaudhry%40intel.com&e=2yjw9P |  | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-05-01 | o The team will try to figure out if they can perform the work within SAP. Discussions have begun with Deloitte and Dassian. o AR: Include details on why POR / Kronos does not work - Kevin |  |  | 2025-05-30 | Confirmed by Kjell Wangaard and Kevin Johns that this was approved and can be closed. • IFL planned to implement Kronos in Dec'24 for timekeeping. However, during the deployment process, it was determined that Kronos was not viable due to integration issues with SAP and inconsistent feedback from the vendor. • Issues with Kronos o The integration between Kronos and SAP faced significant data quality issues, affecting the reliability of data exchange. o Intel received varying feedback from Kronos on how their solution would address the problems, leading to repeated setbacks. • The decision was made to cancel the Kronos program for both ECC and S4 environments. • A small team is conducting an assessment to understand the scope and cost implications of moving to an SAP based time keeping solution for IFL. A proposal is expected to be brought back to the Change Request meeting on May 16 to outline the total body of work required. • Replacement of the IFL timekeeping system is outside of the IAO scope of work and budget. | [5 empty] | Design | CL/OSC | 2025-05-30 | 05, 2025 | 05, 2025 | 04, 2025 | 2025-04-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0600 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 10. Analytics | junior.milan@intel.com | [11 empty] | Malaysia Customs Reporting Request | While testing in UAT1, a critical gap in local Customs reporting was uncovered. We need an interim solution in both SAP (BRF+ Table) and ECA (stitching and consumption) for us to bridge the gap and keep the business legal. | Keep Intel Legal in Malaysia Bonded Zone (PG10). |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this will be merged with CR0600 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0601 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Julin Zhou |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV160 - GLAA Tax Company Code Hierarchy | Tax team is cancelling ECA object FPRXV160 (GLAA Tax Company Code Hierarchy). | Universal allocation will be implemented for S/4. This change will eliminate any differences between cost centers and profit centers, ensuring consistency between the two. As a result, Julin and the team will no longer need to reconcile these items, making the GLAA report unnecessary. Instead, the GLAP report can be used, as they will be able to generate a report by GL. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0601%20%26%20CR0617%20%26%20CR0618/RE_%20Tax%20RICEFW%20Object%20Cancellations.msg?csf=1&web=1&e=7J83mm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-01 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0603 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 16. Testing | 16.4 Testing – Test Boundary App |  | 16. Testing | Kelly Gerber | [11 empty] | Boundary Apps Test Coordinators​ | Requesting two(2) Test Coordinators to support R3, R4, R5 Boundary App Testing. ​ Duration: 7/1/2025 – 7/31/2027 (end of UAT for R5)​ Requesting India-based Deloitte resources to be cohesive with existing Boundary Apps resources​ Current B-App Deloitte resources: 1 PMO (US), 1 Tech Lead (US), 1 PMO (India), 1 Test Analyst (India) | The number of Boundary Apps requiring testing during ITC and UAT is much larger for R3. Additional resources required to communicate with the apps and track testing. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDD1E1715-0A5D-4495-A12C-336C80692B01%7D&file=INT-CR0-%20%20Boundary%20Apps%20Test%20Coordinators.pptx&action=edit&mobileredirect=true |  | 14. Other Resource Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-05-01 | o This CR is an ask for 2 Deloitte USI test coordinators. o AR: Break down costs by year - Kelly |  |  | 2025-05-02 | [6 empty] | Other | CL/OSC | 2025-05-02 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-01 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0604 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) | High | 13. Security | 13.2 Security - Cyber/ App Security |  | 13. Security | yashaik@deloitte.com | [11 empty] | $0 Change Order to Non-ERP Security & Controls SOW | $0 change order to Non-ERP SOW to modify some of the milestone dates and invoice due dates due to delays in ECA FSD completion which is a dependency for ECA Security design | Downstream impact to Non-ERP S&C R3 ECA design due to delays in ECA FSD completion by functional tower teams |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B41AE8590-DDE8-4E25-94DC-CBD39ED67624%7D&file=INT-CR0604%20-%20Change%20Order%20to%20Non-ERP%20Security%20and%20Controls%20SOW.pptx&wdOrigin=TEAMS-WEB.p2p_ns.rwc&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | Approved in ad hoc meeting - This change to align deliverables to the milestone dates as ECA FS is impacting security. | [9 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0605 | Cancelled | Need approval email from Shane and Sunil | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | [12 empty] | FPR - Cancellation of ECA report FPRXV218 Spending and Headcount Report | Cancellation of ECA report FPRXV218 Spending and Headcount Report | Reason (By Intel Business): All fields are covered by another ECA report (FPRXV212 - Consolidated Spending and Headcount Report) that we have reviewed in Sprint 12. There are two separate reports in the current DARC environment, but we confirmed that we can consolidate them into one report. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by George Bakare that this CR is no longer needed | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-02 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0606 | Cancelled |  | ERP | R3 (Release 3) | [17 empty] | Cancellation of ECA report FPRXV219 PO and Shopping Cart Report | Cancellation of ECA report FPRXV219 PO and Shopping Cart Report |  |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed to not be required | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-02 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0607 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA report FPRXV218 Spending and Headcount Report | Cancellation of ECA report FPRXV218 Spending and Headcount Report | Reason (Intel Business): All fields are covered by another ECA report (FPRXV212 - Consolidated Spending and Headcount Report) that we have reviewed in Sprint 12. There are two separate reports in the current DARC environment, but we confirmed that we can consolidate them into one report. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0583,%20CR0629,%20CR0607%20%26%20CR0608/RE_%20ECA%20report%20_%20Conversion%20Object%20cancellation%20__%20FPRXV182_%20FPRXV218_%20FPRXV219_%20FPRC1212_IF.msg?csf=1&web=1&e=jG7flm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV218 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-02 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0608 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA report FPRXV219 PO and Shopping Cart Report | Cancellation of ECA report FPRXV219 PO and Shopping Cart Report | Reason: Duplicate another report (FPRXV182 Purchase Order and Shopping Cart) |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0583,%20CR0629,%20CR0607%20%26%20CR0608/RE_%20ECA%20report%20_%20Conversion%20Object%20cancellation%20__%20FPRXV182_%20FPRXV218_%20FPRXV219_%20FPRC1212_IF.msg?csf=1&web=1&e=jG7flm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV219 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-02 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0609 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 11. Technology | Piyush Ashok Patil | [11 empty] | Bailment Value to be transferred to GTS Declarations | The Export declaration in GTS should have Bailment value included in the Total value. Currently the Bailed Value is not transferred to the declarations |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0609%20Bailment%20vaue%20to%20be%20transferred%20to%20GTS%20declarations.pptx?d=wb9ae26ebc3b248b29e447750f5b1f67a&csf=1&web=1&e=JHRA9v |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 16 | 0 | [13 empty] | 0 | 0 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0398 | 1 | OTCE0398 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | [10 empty] | Build | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-03 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0610 | Approved |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 11. Technology | Piyush Ashok Patil |  |  |  | CR0609 | [7 empty] | Bailment Value to be transferred to Compliance Documents ( SO and DN ) from S4 to GTS | The Compliance Documents in GTS should have Bailment value included in the Total value. | Impacts accurate License decrementation for IVL licenses. Will include other transactions as well. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0610%20Bailment%20vaue%20to%20be%20transferred%20to%20Compliance%20documents%20(%20SO%20and%20DN%20)%20from%20S4%20to%20GTS.pptx?d=w6cfe6a20e0ab40afa13e6bda581ca5a8&csf=1&web=1&e=uaMbUI |  | 2. New RICEFW / ECA / Build Object |  |  | Low |  | 1 |  |  | 5 | [5 empty] | 16 |  |  |  |  | 0 | 16 | Tech - S/4 | Yes | S4 | 2 | OTCE1668_IP, OTCE1668_IF | 3143 | OTCE1668_IP, OTCE1668_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0398_IP | 1 | OTCE0398_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-10-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | This was tested as a part of ITC but it didn't cover this particular scenario. Another set of eyes identified the discrepancy in UAT1. This is a new RICEFW, medium to large complexity to cover the new regulation on May 15 to trigger licenses for around 50% of IF products. The recommendation is a manual workaround, but this is a risk as there are no resources available to do this today. Needs to go to CR Meeting | 2025-10-16 | Approved in RICEFW intake and okayed in CR Ingestion | [7 empty] | Other | Tower | 2025-10-16 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-03 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0611 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Sindhuja Gangireddy | [8 empty] | 19569, 18863 | SAP Ariba Cloud, I-CHEM - Chemical Management System |  | Cancellation of RICEFW object OTCE0771 | Cancellation of RICEFW object OTCE0771 | The requirement for updating the custom table specifically for Non dampened orders has already been addressed within the FS OTCI0876. We had decided to keep OTCE0771 open for potential refinements related to the BRU program. As there are no further requirements provided by Intel team that should be incorporated into OTCE0771, we are cancelling this object. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?noAuthRedirect=1&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0611%2FEXT%20RE%20RICEFW%20Cancellation%20%2D%20OTCE0771%2Emsg&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0611 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-05 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0612 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Govind Ballav Pradhan | [11 empty] | Enhancement to support ICHEM validation for chem & gas PR created from Ariba during Straddle period R3 through R5 go-live | Continue chemical and gases procurement in Ariba for R4/R5 sites during straddle period, enhancement to be included in S4 to validate with ICHEM application utilizing validate and enrich interface. | As part of IAO, we decided to move chemical and gases procurement (MMID related procurement) from Ariba to S4HANA. ARIBA will be big-bang in R3, we would need straddle solution for R4/R5 sites.​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR0612_PTP_IF_IP.pptx?d=wf55cae29397047d6b382b5f4893715dc&csf=1&web=1&e=2vXphK | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 30 |  |  |  |  | 0 | 30 | N/A | Yes | S4 | 2 | PTPE1424_IP, PTPE1424_IF |  | PTPE1424_IP, PTPE1424_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This validation is required if plant is not live. Then the purchasing will happen from Ariba. • After the plants are live in S4, the functionality will shift back to S4. This is based off the straddle | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-05 | 0 | < 15 Days | pabharshavardhan@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0613 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | No information | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-05 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0614 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP 11. Technology | Sugandh Gupta | [11 empty] | Enhancement for PDF printout of SAP self-billing invoices (ERS/Consignments) archives it to EDDAR | Enhancement for PDF printout of SAP self-billing invoices (ERS/Consignments) archives it to EDDAR [Console ID - 2932] PTPE1440_IP & IF | Enhancement required to archives ERS and consignment Invoices |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/06. PTP/3 Final Deliverables/2. Build/Sub-team - Procurement/2. Interfaces/E2Open Interfaces/PTPI0369_IF-IP Develop an interface to send inventory reports and MRP parameters from S4(IF) %26 S4(IP) to suppliers/INT-CR0614_PTP_IF_IP.pptx?d=waac13142e02f4ee7b9bbb39983211235&csf=1&web=1&e=MnKhb9 |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [8 empty] | 160 |  |  |  |  | 0 | 160 | Tech - Middleware Tech - S/4 | Yes | S4 | 2 | PTPE1440_IP, PTPE1440_IF |  | PTPE1440_IP, PTPE1440_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0094_IP, PTPI0094_IF | 2 | PTPI0094_IP, PTPI0094_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-11-19 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o These customizations are currently in ECC as well. So, the team is re-creating it in S4. • It was not considered in the original design. | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-05 | 0 | < 15 Days | suggupta@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0615 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP 11. Technology | Swati Ashok Jogi | [8 empty] | 19569 | SAP Ariba Cloud |  | Enhancements required for the existing planned Invoice status interface between S4 IP & IF to ARIBA. | Enhancements required for the existing planned Invoice status interface between S4 IP & IF to ARIBA. [Console ID - 2933] PTPE1422_IP & IF | Develop an enhancement that will create an entry for PAID status for relevant invoice based on the payment status flowing from CFIN to IP/IF system |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/06. PTP/3 Final Deliverables/2. Build/Sub-team - Procurement/2. Interfaces/E2Open Interfaces/PTPI0369_IF-IP Develop an interface to send inventory reports and MRP parameters from S4(IF) %26 S4(IP) to suppliers/INT-CR0615_PTP_IF_IP.pptx?d=w663da4d39abb4c81a84c100f6ca242a9&csf=1&web=1&e=KzRMCA |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 67 |  |  |  |  | 0 | 67 | N/A | Yes | S4 | 2 | PTPE1422_IP, PTPE1422_IF |  | PTPE1422_IP, PTPE1422_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o These requested 3 enhancements will enable communication back to Ariba. • For Intel, we are doing APM approval, and aspects are missing in the standard. o Population of the Z-table is covered in another interface. | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-05 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0616 | Approved | 40 hours of configuration effort | ERP | R3 (Release 3) | Medium | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | mpuvvala@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | Actual Cost Logic change from Quarterly to Monthly in PaPM Division Transfer model | Actual Cost Logic change from Quarterly to Monthly in PaPM Division Transfer model | Actual Cost Logic change from Quarterly to Monthly in PaPM Division Transfer model based on latest alignment with Joey (joey.huang@intel.com). Earlier, assumption was to run PaPM model to post the cost data to S/4 based on Actual Cost only on Day 4 of the Quarter, now it is aligned to run PaPM model to post the cost data to S/4 based on Actual Cost only on Day 4 of Fiscal Period for previous period true-up/true-down. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0616%20%E2%80%93%20Actual%20Cost%20Logic%20change%20in%20PaPM%20Division%20Transfer%20model.pptx?d=w97e9112aef474af8aee66b5c7e7eaa04&csf=1&web=1&e=4q1Q3s | New Requirement / Scope | 3. Configuration Change | DC-100-020 |  |  | 0 | 0 | [7 empty] | 40 | [5 empty] | 0 | 40 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-16 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o This request is to change the frequency of the actual cost calculation from quarterly to monthly o The configuration work will be done by the FPR team. | [9 empty] | Other | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0617 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Connie Wei |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object - FPRXV161 - BS - Tax Company Code Hierarchy and - FPRXV162 - TB - Tax Company Code Hierarchy | Tax team is cancelling ECA object FPRXV161 - BS - Tax Company Code Hierarchy and FPRXV162 - TB - Tax Company Code Hierarchy | Team determined that Balance Sheet/Income Statement Multidimensional and the standard Trial Balance report, should satisfy the tax requirements to be able to pull reports TB, IS, and BS based on the company code hierarchy “US_FILING”. Therefore, we plan to mark the user stories related to these requirements as "fits” |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0601%20%26%20CR0617%20%26%20CR0618/RE_%20Tax%20RICEFW%20Object%20Cancellations.msg?csf=1&web=1&e=7J83mm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0618 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Yousef Khan |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV189 - SCIP Partner Financials - Extension Ledger; FPRXV190 - SCIP FS - Extension Ledger; FPRXV191 - IS - Extension Ledger Requirement and FPRXV196 - Balance Sheet - Extension Ledger Requirement | Tax team is cancelling ECA object FPRXV189 - SCIP Partner Financials - Extension Ledger; FPRXV190 - SCIP FS - Extension Ledger; FPRXV191 - IS - Extension Ledger Requirement and FPRXV196 - Balance Sheet - Extension Ledger Requirement | Team determined that there is a requirement to have an extension ledger for the income statement and balance sheet to produce non-GAAP reports as well as SCIP financials. The extension ledger requirement will be implemented by Team 1 for R3, and we will mark these user stories as "fits". |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0601%20%26%20CR0617%20%26%20CR0618/RE_%20Tax%20RICEFW%20Object%20Cancellations.msg?csf=1&web=1&e=7J83mm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0619 | Cancelled |  | ERP | R2 (Release 2) | [21 empty] | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0620 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Aditya Shinde | [11 empty] | cancel Manual conversion objects: LOGM014_IF/IP - Transshipment assignment to Transportation zones LOGM020_IP/IF-TM Trade Lanes | Transshipment locations and Trade lanes are not in scope as per R3 IAO design. cancel Manual conversion objects: LOGM014_IF/IP - Transshipment assignment to Transportation zones LOGM020_IP/IF-TM Trade Lanes | Cancelling below objects as Intel doesn't create trade lanes as independent master data. Further Transshipment locations are not part of the design.i.e. out of scope. cancel Manual conversion objects |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0622,CR0620/%5BEXT%5D%20RE_%20Cancellation%20of%20RICEFWs-%20INT-CR0622_CR0620.pdf?csf=1&web=1&e=exYh13 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0621 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | No information | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0622 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP 11. Technology | Aditya Shinde | [11 empty] | Cancel object LOGR0857_IF/IP | Cancel object LOGR0857_IF/IP .ECA report will be leveraged instead developing a report in S/4. | There is an ECA report LOGV003 which will be leveraged instead of a custom built report. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0622,CR0620/%5BEXT%5D%20RE_%20Cancellation%20of%20RICEFWs-%20INT-CR0622_CR0620.pdf?csf=1&web=1&e=exYh13 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0623 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Ganesh Kumaresan | [11 empty] | Cancel RICEFW objects LOGE1274_IF/IP | Cancel RICEFW objects LOGE1274_IF/IP. The transfer of carrier number and details to S/4HANA delivery is handled through standard functionality, which will be a standard configuration done by the TM team. Aligned with Intel’s IT and business teams to cancel the custom RICEFW development | Chronology: 1.Initially, we collaborated with Intel’s IT and business teams to define the need for transferring carrier number/details to S/4HANA delivery using a custom object. 2.Subsequently, Deloitte conducted a POC Per Intel IT’s request, discovering a standard method to transfer these details to S/4HANA delivery by mapping the Business Partner (BP) forwarding agent as the carrier. As a result, we aligned with Intel’s IT and business teams to cancel the custom RICEFW development. |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/INT-CR0623?csf=1&web=1&e=3Nlbpx |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0624 | Cancelled |  | ERP | R2 (Release 2) | [17 empty] | Logic changes to OTCFR038 ECA Report |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0625 | Cancelled |  | ERP | R3 (Release 3) | Medium | [16 empty] | Addition of Consumption Views to the Deloitte IDM Tracker |  |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as there is no information |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | freginold@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0626 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Khee Kuan Lim |  | FPR - Aubrey Hinderlider | [9 empty] | S4 RICEFW FPRI0378 Change Request | Changes required for FPRI0378_IF, FPRI0378_IP and FPRI0378_CFIN RICEFW: 1. Title to "GL Interface - File Processing in Mulesoft- S4 API Demo Depot and Flex One Stop Tool" 2. B-App Name to "Demo Deport, Flex One Stop Tool" only. | B-apps wrongly mapped |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52FF66E3-AEDB-4D56-A19D-B82DB47F7604%7D&file=5_6_25%20INT-CR0626%20-%20S4%20RICEFW%20FPRI0376%20FPRI0377%20FPRI0378%20FPRI0379%20Change%20Request%20-%20Copy.pptx&action=edit&mobileredirect=true |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | ying.nee.sim@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0627 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | soo.chin.yeoh@intel.com | [11 empty] | Add two new fields in the mapping between S4 (3A7) and MuleSoft | As part of OTCI1126, the B2B team needs the two fields below to be populated in the open text to differentiate the nature of the material and the customer PO type E1EDP01/PSTYV (Sale Order Item Category) E1EDK01/BSART (Customer Purchase Order Type) | B2B team needs the two fields to be populated in the open text to differentiate the nature of the material and the customer PO type |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CR0627_OTC%20IF-Include%20SO%20item%20Category%20%26%20customer%20PO%20type%20fields%20in%20mulesoft%20mapping.pptx?d=wedaa271de3c649868b32ba077aa9f507&csf=1&web=1&e=2hRBEM |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 8 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the effort is less than 40 hours of tech effort | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | maabraham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0628 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Poonam Dhouni | [11 empty] | Objects to be removed from Deloitte object tracker | Objects to be removed from Deloitte object tracker OTCI0980 - WOM Validation - Scenario 1 [OL to EMS] OTCI1242 - Update GR Confirmation flag in Entitlement Orchestration layer - Interface | OL to EMS interfaces build/development will be owned by Intel IT team. During EMS workshops, it was agreed that EMS will be treated as a boundary app. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0628/RE%20Help%20Needed-INT-CR0628%20.msg?csf=1&web=1&e=bu2PwK |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0980, OTCI1242 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0629 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA report FPRXV182 PO and Shopping Cart Report | Cancellation of ECA report FPRXV182 PO and Shopping Cart Report | Reason: There are some other ECA report on P2P side which is fulfilling requirement for this ECA report |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0583,%20CR0629,%20CR0607%20%26%20CR0608/RE_%20ECA%20report%20_%20Conversion%20Object%20cancellation%20__%20FPRXV182_%20FPRXV218_%20FPRXV219_%20FPRC1212_IF.msg?csf=1&web=1&e=jG7flm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV182 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0630 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 11. Technology | rishabhx.hingmire@intel.com | [11 empty] | Label Printing from Spectrum | The current label printing program does not include the logic to update specific fields such as HAWB, SCAC code, CDD, HU ID and PO Line on the Shipping box and Carrier Labels post overpacking of boxes. This Change Request is necessary to ensure that all relevant information is accurately reflected on the labels after the overpacking process. | The proposed change to the label printing program is essential for improving the accuracy, compliance, efficiency, and overall effectiveness of the shipping process. By updating the labels to include critical fields such as HAWB, SCAC code, CDD, HU ID and PO Line the organization can achieve significant operational benefits and enhance its logistics capabilities. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR630-%20Label_Printing_LOGI0278.pptx?d=we776422f737f432fa1783d7923a6cf8d&csf=1&web=1&e=TAGxsv |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne that this CR is a duplicate of CR0639 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | rhingmire@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0631 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Cancellation of generate docking report Interface LOGI1411 | Cancellation of the Interface object in the Docking Report. | After moving the docking report requirement to Alfresco, the interface is not needed anymore. Alfresco team were involved in the discussions about the integration. Also, the Dev team knows about this integration to Alfresco for our objects. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0631,%20CR0632,%20CR0668,%20CR0669,%20CR0671/FW%20CRs%20for%20cancelling%20RICEFWs.msg?csf=1&web=1&e=sbixXl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1411 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | AR: For CR0631, it mentions that the functionality will be covered in Alfresco. Has this been communicated to their team and will there be configurations involved? Answer: Yes, Alfresco team were involved in the discussions about the integration. Also, the Dev team knows about this integration to Alfresco for our objects. | [9 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0632 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | LOGE1222 was not in the original approved list of RICEFWs | This object was dropped even before the GPO meeting. But since the object ID was already created, raising this CR to officially drop the object. | This object was dropped even before the GPO meeting. But since the object ID was already created, raising this CR to officially drop the object. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0631,%20CR0632,%20CR0668,%20CR0669,%20CR0671/FW%20CRs%20for%20cancelling%20RICEFWs.msg?csf=1&web=1&e=sbixXl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0633 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP 10. Analytics 11. Technology | Ciprian Ciobanoiu | [11 empty] | OTC GTS ECA Report OTCFR058 logic change to accommodate UoM | To accommodate the UoM and region issue identified during UAT1 testing, we will need to change the FS logic to fetch the expected data set | Change in logic to accommodate the UoM and modify the logic to fetch the region data which appears blank for routed declarations in ECA report for OTCFR058 (US Export Declaration report). ​ Currently the UoM displayed in the report is the internal SAP UoM but the business wants to see the HS code supplementary UoM used in the declaration to be appearing the ECA reports. ​ The region logic to fetch the data from declarant but for routed transaction will be further modified as declarant partner will not be available and will use the Legal Unit partner information in the declaration to fetch in the ECA report.​ ​ Both the changes need minor logic change in FS to fetch the right set of data. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B208D7EB2-0BEF-4876-8466-6EE04E883F39%7D&file=INT-Build-CR0633%20Change%20in%20logic%20to%20capture%20the%20right%20UoM%20in%20Export%20declarations.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 12 | 0 | [9 empty] | 12 |  |  |  | 0 | 12 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCFR058 | 1 |  | 0 | OTCFR058 | 1 |  | 0 | N/A |  | 2025-05-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | Work has been completed and UAT tested | [9 empty] | Build | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-29 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0634 | Approved | Presenter: Jeffery Maclauren | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 08. FTS IP 17. B-App | Carl.Avery@intel.com | [11 empty] | Mutiple versions of PRF (Solve week Day 0,Solve week Day 3 & Executive week Thursday ) to be shared to Compass | Mutiple versions of PRF (Solve week day 0, Solve week day 3 & Executive week Thursday) to be shared to Compass | This data is required to take decision during executive week from Compass. Today we are getting PRF after executive week's decision. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR0634%20-%20BY%20IBP%20to%20Send%20Day%200%20and%20Day%203%20Planned%20output%20to%20Compass%20%26%20OneMPS.pptx?d=w5893314670244ceea281fba3d2dfd3ca&csf=1&web=1&e=YOyZaD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 120 | 120 | 0 | [6 empty] | 240 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o We have a business design that requires our front-end and back-end processes to be aligned to have an effective single operating plan across all teams. • On the Day 0, the change is to have the PRF (planning output) to be sent to Compass from BY IBP. • On Day 3, we will have both constrained and unconstrained to be sent out. o One of the biggest risks is the need to re-test. The current process is to have it manually loaded into OneMPS. • The testing scenario is already in UAT2. It was just a requirement that got missed. | [9 empty] | Build | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0635 | Rejected | Not approved | SCP | R2 (Release 2) | High | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP | Anderson.stephanie@intel.com | [11 empty] | For BY IBP, PSG/Altera and SiPH items are out of scope. | For BY IBP, PSG/Altera and SiPH items are out of scope. | PSG/Altera and SiPH items are not scoped for BY IBP planning. The PRFs for these items are manually imported to E2Open |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/2025%20Change%20Requests/Change%20ID_FTS_CR%20PSG_SiPH.pptx?d=wc3733789054f4a3ebdbc1a42b894c92a&csf=1&web=1&e=paEodY |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 07. OSC/CL rejected - no further analysis (end status) | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0636 | Approved | Presenter: Jeff Miller | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP 18. SCP | Anderson.Stephanie@intel.com | [11 empty] | Unable to generate DLCP Calendar | Current design generates BY DLCP UPI/BOM for items linked to SPEED FG items with SPAN die seg value > “0” . Change would keep current logic, then also generate BY DLCP Calendar for die prep items not linked to SPEED FG BOM and/or with SPAN die seg value “null” or = “0”. Exclude RJ DLCP die prep items from being identified as Primary, and from the logic validation DLCP split sum must = “1” . RJ DLCP die prep items also must be included in the BY DLCP Calendar. DLCP to be generated for the following use cases: We have Complete BOM IN Speed and Respective Die preps are with valid value in Die Segmentation We have Reject component not in SPEED (Simplified BOM) , found in SPAN Die Segmentation We have Complete BOM IN Speed and no Match in SPAN Die Segmentation We have Complete BOM IN Speed and Respective Die preps are not having valid value in Die Segmentation. ( 0 Die segmentation) | If dieprep with die segmentation 0 are null, not present in production yield file for BY IBP ,it doesn't have visibility of the inventory, so the planning engine will start planning for the demand without looking at the inventory |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR0636_FTS_CRnnn_DLCPCalender_not_showing_Updated%20(2).pptx?d=w05c59e1bddca4b1592ed6dc42bb0f49b&csf=1&web=1&e=B53uAw |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 56 | 80 | 0 | [6 empty] | 136 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o There are currently 5 open bugs that are tagged to this change. • This request will help fix them by pulling in the correct capability for die prep. o It will be ready for UAT2, and the risks can be mitigated. • There are 2 PDH resources that were allocated to bug fixes, and they are in charge of the changes. | [9 empty] | Build | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0637 | Rejected | Not approved | SCP | R2 (Release 2) | Low | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 18. SCP | ting.shaw@intel.com | [11 empty] | Apply Filter on Completion delivery of Committed PO | Apply Filter on Completion delivery of Committed PO | If we are not applying this filter on the delivery of committed quantity our sched rcpts for the planning engine will be doing a double count. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/2025%20Change%20Requests/Change%20ID_FTS_CRnnn_PO_Delivery_Completion_Ind-Filter.pptx?d=w15901f0f9dc24ebc92d009145ea94e6c&csf=1&web=1&e=M2vGWy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 07. OSC/CL rejected - no further analysis (end status) | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0638 | Approved | 65 hours of ECA effort | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 10. Analytics | junior.milan@intel.com | [11 empty] | Malaysia Customs Mandatory Reporting | Additional data required to submit compliant reports to Malaysia Customs for PG10 Bonded Zone. Data to be stored in Share Point and feed into ECA for report generation. | To remain compliant to Malaysia Customs requirements, the PG10 Warehouse must submit a rolling 30-day report for all transactions incurred within the PG10 Bonded Zone. To ensure reporting is accurate, the local Operations team uses a custom transaction in SAP WM (YCUST_LOT_DATA) to link the Malaysia Customs license by lot to the inventory on-hand. This information is carried thru the process and is reported at the time required. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_Malaysia%20Customs%20Reporting.pptx?d=wc018eed0e1124857b0ba722cf08cb7e1&csf=1&web=1&e=yD7lUc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [9 empty] | 65 |  |  |  | 0 | 65 | ECA | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | ECAOTCIFV5638, ECAOTCIF5639-OTC425 | 2 |  | 0 | ECAOTCIFV5638, ECAOTCIF5639-OTC425 | 2 |  | 0 | N/A |  | 2024-10-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | This is a report that is submitted to Malaysia every month, and the ask is to have a Sharepoint location and an ECA report. Sunil and Rebecca and team approved. Sharepoint is existing, just need to get the data connection. The Sharepoint is a custom transaction in SAP. Once the user uploads to Sharepoint, then the data will be consumed by the ECA. Asked for 2 weeks to go through ingestions and get the viewing ready. Then there will be some time before going through UAT2. | [9 empty] | Build | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0639 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 11. Technology | junior.milan@intel.com | [11 empty] | Additional Labels Required | Additional labels needed for new customer products (2), and fixing issues with the Shipping and Carrier Labels. | Introduce two new labels types (Product and Ship Label ) for 7 products being manufactured in New Mexico. Additional work to fix standard Shipping and Carrier Label to add additional fields required by the Operations. New labels went into production in late Q4’25 and program team was not notified until start of UAT1. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_Additional%20Labels.pptx?d=we53b88a8f2a94bb9888bdb9cfc1f9b38&csf=1&web=1&e=T7WSVg |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 20 | 0 | [8 empty] | 20 |  |  |  |  | 0 | 20 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-13 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | • AR: Confirm with tech team that it will be done in UAT2 @Tam, Anna | [9 empty] | Build | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0640 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 5.10 OTC IP - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 10. Analytics 11. Technology | junior.milan@intel.com | [11 empty] | Chengdu Ebook Serial Number Changes | Aligning system and business process with the information required by China Customs. | Clean-up misunderstanding between Operations team and the design team on what is required by China Customs. There are two types of data with similar names. Ebook Serial number refers to the company/operator who is shipping/receiving within the country. This can be considered a company Id for Customs filing purposes and is a fixed number at the plant level. Ebook number refers to the unique number assigned to a product within the plant. This is used to track goods and assess tariffs and taxes due. ​ Today, the export documentation only has the “Ebook Serial Number” which is incorrect. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_Chengdu%20EBook%20Serial%20Number%20Changes.pptx?d=w6dd81d968b6146c49c0d886cd0d58828&csf=1&web=1&e=83iIsq |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0353_IF, LOGF0354_IF | 2 | LOGF0353_IF, LOGF0354_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-06-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | [10 empty] | Build | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0641 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP 16. Testing 18. SCP | joseph.t.chen@intel.com | [11 empty] | Demand data publish from PDH to Compass via Denodo view | Compass requested to have the same demand feed as BY-IBP coming from PDH. | Compass and BY-IBP should share the same demand feed. As-Is IAO R2 design: Compass source demand from BY-CDP, missing Module Dep Dmd + EPG dmd. To-Be: Compass source demand from PDH (same as BY-IBP), which has Module Dep dmd + EPG dmd. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20CCB%20PXT%20Demand%20feed%20for%20Compass.pptx?d=w824654d5005341f184d956767e8291b5&csf=1&web=1&e=tIiWjg |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 40 | 0 | 40 | [6 empty] | 80 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-08 | Approved during Ingestion | [9 empty] | Build | Tower | 2025-05-08 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0642 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 11. Technology 18. SCP | ximena.bustamante@intel.com | [11 empty] | Capacity Group/Capacity Corridor Item Attribute Data Source | Currently CG/CC is sourced from WSPW which is a DSA. For IAO purposes, ROO must be changed to an MDG system. The option presented entailed manual mapping of a CC/CG to ALL items, which would not only require additional resources given the volume, but also require a lot of data quality enforcement and governance given the high risk for human error while doing manual uploads. | We are requesting a table to be created and maintained in MDG with the dot process to CC/CG mapping, which would then be derived for each item. Thus, eliminating any need to manually update/maintaining values for each item, as well as eliminating the need for DQ efforts. |  | No |  |  | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EU_Gzp808NJLs1LqMWllsUkB_oprXVUH3Cbc2WS-XBPG8g?ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA0MTcxOTMwOSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 1 | DATE1499 |  | DATE1499 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o We don’t have a standard PLM. Will need to go to the RICEFW Meeting | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
| N/A | INT-CR0643 | Cancelled |  | ERP | R3 (Release 3) | Low | 10. Analytics | 5.1 OTC IP - ALL |  | 05. OTC IP | Fabian Reginold | [11 empty] | Transfer of Deloitte Owned Consumption Views from Intel To Deloitte Tracker | Based on Intel APT and Business proposal, the following objects are consumption views built by Deloitte Analytics. Hence,these objects will be taken off of the Intel Object Tracker to the Deloitte Object Tracker. Deloitte will then build the necessary consumption views needed to build Reports.. Object ID Object ID Object Type Object Description OTCPCV009 ECA View sales_contract_billing OTCFCV012 ECA View billing_document_detail OTCFCV015 ECA View sales_document_detail OTCFCV016 ECA View sales_document_schedule_line OTCPCV001 ECA View Customer Master Database OTCFCV001 ECA View Customer Master Database OTCPCV002 ECA View Country of Origin Compliance KPI OTCFCV002 ECA View Country of Origin Compliance KPI OTCPCV005 ECA View sales_document_detail OTCPCV006 ECA View sales_document_schedule_line OTCPCV008 ECA View sales_transaction_flow OTCPCV003 ECA View SCTRE Data Health Monitoring OTCPCV012 ECA View delivery_note_detail OTCFCV003 ECA View SCTRE Data Health Monitoring OTCPCV004 ECA View SCTRE Historical Risk Scenario Planning OTCFCV004 ECA View SCTRE Historical Risk Scenario Planning OTCFCV006 ECA View SIM_Sales_Order_Delivery_billing_details (1-4) OTCFCV007 ECA View SIM_Credit_billing_details (1) OTCFCV008 ECA View SIMS_Sales_transaction_incompletion_log_detail (1) OTCFCV013 ECA View credit_debit_billing_detail OTCFCV014 ECA View sales_contract_billing OTCFCV017 ECA View order_batch_detail OTCFCV019 ECA View sales_transaction_flow OTCFCV020 ECA View sales_transaction_incompletion_log_detail OTCPCV013 ECA View inventory_adjustments | Since Deloitte is developing the consumption views, it would be correct to have the views tracked on the Deloitte Object Tracker. We are making this change to track the effort involved in developing the consumption views built by the Deloitte Analytics Team. . |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed to not be required | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-07 | 0 | < 15 Days | freginold@deloitte.ca |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0644 | Cancelled | Need approval email from Shane and Sunil | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | snavasthi@deloitte.com | [11 empty] | FPR - Cancellation of ECA Object FPRXV230 Project Actuals vs Forecast Capex | Cancellation of Object FPRXV230 ‘Project Actuals vs Forecast Capex its a Duplicate because we already have report FPRXV187 CAPEX forecasting report for similar requirements. | Cancellation of Object FPRXV230 ‘Project Actuals vs Forecast Capex its a Duplicate because we already have report FPRXV187 CAPEX forecasting report for similar requirements. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by George Bakare that this CR is no longer needed | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0645 | In Progress |  | SCP | R3 (Release 3) | High | 10. Analytics | 10.8 Analytics - PTP |  | 06. PTP 10. Analytics | NITIN.PATIL@INTEL.COM |  |  | No known design open | [8 empty] | MaPPS data in ECA for Reporting | MaPPS Data in ECA | This data is required for Direct Material projected Excess Inventory Report which is intends to analyze the demand and supply to calculate the excess inventory, Without MaPPS data, we can’t proceed substrate supply & demand analysis. This report will monitor each part's projected DOI and point out the risk part based on projected DOI Vs target DOI. The report provide visibility to buyer/management/Commodity Manager to quickly identify the risk part and take action accordingly |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0645-MaPPS.pptx?d=w3624abea01754dd68134b87843c0bb86&csf=1&web=1&e=kgJcEG |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | n/a | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 05. Ready for OSC/CL review for further analysis | Yes | No | 2025-10-16 | o This data is not currently in ECA; it comes from MaPPS. o This is related to Direct Materials, but it is specifically for substrates. o This report is needed for scenarios where IF is managing their own substrates, and request is from the ATM team o Cannot be fully tested in ITC1 o AR: Include any alternatives or methods - @Jain, Nitin P o AR: Include MDD PDH effort - @Jain, Nitin P |  |  | 2025-10-17 | • Focused on developing reports within the ECA system to consolidate software inventory data procured by IF. • The reports aim to provide daily excess inventory risk analysis across multiple ATM sites and maintain visibility for operational decision-making. • Currently, data flows through Hana and Power BI, but the initiative seeks to transition from legacy sources to improve reporting efficiency. • The team debated whether the need for these reports might be impacted by changes in inventory holding practices, particularly regarding substrates held at supplier locations. • It was noted that while the reports remain necessary, evolving business models could alter data requirements, and thus the work was deferred for a month until clarity on inventory management strategies was achieved. • This was to avoid wasted effort given the constraints and competing priorities related to the constraint impacting substrates supply. • Decision: Not approved - review in 1 month | [5 empty] | Build | CL/OSC | 2025-10-17 | 10, 2025 | 10, 2025 | 05, 2025 | 2025-05-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0646 | Cancelled |  | ERP | R3 (Release 3) | [17 empty] | Cancel RICEFW MC object |  |  |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-07 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0647 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Aditya Shinde | [11 empty] | Cancel RICEFW Manual conversion object LOGM017_IP and LOGM017_IF | Cancel RICEFW Manual conversion object LOGM017_IP and LOGM017_IF Scales are managed as configuration and will be assigned to the rate table hence this is no longer a MC task however configuration which is already complete | Scales are managed as configuration and will be assigned to the rate table hence this is no longer a MC task however configuration which is already complete |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0647?csf=1&web=1&e=w5csWG |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-07 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0648 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-07 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0649 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | Ricardo J Varela Molina |  | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | Non HAT assignment spend allocation to P&L PC's based on % generated in SAC | Non HAT assignment spend allocation to P&L PC's based on % generated in SAC | Non HAT assignment spend allocation to P&L PC's based on % generated in SAC |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA3A38892-33D6-43BD-B133-C3140146F9DC%7D&file=INT-CR0649%25u00a0-%20Non%20HAT%20assignment%20spend%20allocation%25u00a0to%20P&L%20PC%27s%20based%20on%20%25%20generated%20in%25u00a0SAC.pptx=&action=edit&mobileredirect=true | Design / Build Gap | 1. Process Scope / Design Change |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o This request is to update the logic so that all dollars will be allocated to the correct cost center. • There are no upstream and downstream impacts, ant there is no impact to the current workload. • There will be SAC development and S4 configuration. | [9 empty] | Design | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-07 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0650 | Rejected |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 17. B-App | rudrsengupta@deloitte.com | [11 empty] | Inventory conversion for R3 | Need a conversion object to load inventory into S4 | This is identified as change needed to the current interface load approach. The current interface only handles WIP inventory. For the lots which are in inventory need to be loaded into S4 via a conversion object. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR650_FTS-IF_Inventory%20Conversion%20for%20R3.pptx?d=we111a99529a940dcacd19799be188f7e&csf=1&web=1&e=5nNrqq |  | 2. New RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-05-22 | [9 empty] | Cancelled as this is tagged to an Open Design Topic (Inventory Conversion). Therefore, a CR will not be required to create a new RICEFW. | Other | Not Assigned |  | Not Approved | 05, 2025 | 05, 2025 | 2025-05-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0651 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Julin Zhou |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV195 - Trial Balance | Tax team is cancelling ECA object FPRXV195 - Trial Balance | Team aligned that the ability to produce a report for a short period is a standard functionality in S/4 which renders the user story to be a fit. Whereas the ability to have the income statement accounts be zeroed out at the beginning of the new short period (June-December) and rolled up into retained earnings is more of a process gap and not a reporting solution. We can leverage the standard reports to get the fields to be able to do the manual process of clearing up the accounts. Hence, user story is a FIT. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0651/RE_%20Tax%20RICEFW%20Object%20Cancellation%20-%20Trial%20Balance.msg?csf=1&web=1&e=ahd6gK |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-08 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0652 | Approved | Yes | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | Hari Gore |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation CR for RICEFW - FPRE1328 CR0710 has been incorporated into this CR0652, and the approval email will list as CR0710 | FPR - Cancellation CR for RICEFW FPRE1328: Legal Valuation standard cost calculation enhancement | List price from IF to IP will be updated in Info record at Routing, this can be captured for standard cost purpose with standard functionality. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0652%2FRE%5F%20Cancellation%20of%20RICEF%20FPRE1328%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0652 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-08 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0653 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shubham Sharma | [11 empty] | Cancellation for OTC IP Objects : OTCM019_IP: Order cancellation Window and OTCM020_IP: Consignment/Location table. | Object was captured as manual conversion but as aligned with Intel business the conversion process is not required and we’ll ensure table entries are maintained through cutover tasks. | OTCM019_IP: Order cancellation Window: In ECC, the records were maintained for customer combinations; therefore, the number of entries required for the order cancellation window was large. However, going forward in S/4, the design has been simplified, and entries will be maintained based on the customer tier, resulting in considerably fewer required entries. There is no need for an explicit Extraction and Transformation from ECC; hence, the need to have a separate Conversion object or a Conversion document is not required. OTCM020_IP: Consignment/Location Table.: Since the final design from OTC side is not yet finalized for Consignment process, the table structure in S/4 is not yet finalized. This requirement will be covered under OTCE1199. As aligned for this object as well we have 2 tables for which data is to be converted but since business also has to ensure that data is cleansed in ECC and the nature of table in not complex. Hence, the object is no longer required. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?noAuthRedirect=1&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0653%2F%5BEXT%5D%20RE%5F%20CR0653%20%2D%20Approval%20Needed%2Epdf&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0653 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-08 | 0 | < 15 Days | atrajput@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0655 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | [11 empty] | Cancellation for object PTPI0138_IP_Interface from S4 to OpenText to send New Purchase Orders & Purchase Order Changes) | Require Cancellation of RICEFW - PTPI0138_IP_Interface from S4 to OpenText to send New Purchase Orders & Purchase Order Changes | Since 3PLs are planned to be configured in IF system now, so PO output need not be sent to OpenText, it was discussed and aligned to not trigger ZP01 output to OpenText and hence PTPI0138_IP RICEFW is no longer required |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?noAuthRedirect=1&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0655%2FEXT%20RE%20Approval%20required%20to%20Descope%20the%20object%20PTPI0138%5FIP%2Emsg&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0655 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 377 |  |  |  |  | 0 | 377 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-08 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0656 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shubhangi Mehrotra | [11 empty] | Cancellation for object LOGV030_FTSIP - W-lot priority ranking report (from OMD) & LOGV031_FTSIP - Warehouse ULT Performance report (from OMD) | Object LOGV030_FTSIP & LOGV031_FTSIP need to be cancelled since these reports are ODM related and are not related to S4. | Since the objects LOGV030_FTSIP - W-lot priority ranking report (from OMD) & LOGV031_FTSIP - Warehouse ULT Performance report (from OMD) these are related to ODM and not in scope for S4. Hence these objects are no longer required. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0656&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&noAuthRedirect=1 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-09 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0657 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Ganesh Kumaresan | [11 empty] | Cancel RICEFW Manual conversion objects 1.LOGM009_IF/IP-Upload of UNLOC Code (for sea ports) 2.LOGM010_IF/IP-Upload of IATA Code (for air ports) | IATA and UNLOC codes are configuration elements in TM, aligned with Intel IT(Ramesh, Suresh, Letchu) & Syed to update IATA/UNLOC entries as config - CDD under PTP TM L3 LI-030-150 | IATA and UNLOC codes are configuration elements in TM, aligned with Intel IT(Ramesh, Suresh, Letchu) & Syed to update IATA/UNLOC entries as config - CDD under PTP TM L3 LI-030-150 What new process will be or What will replace the cancelled RICEFW: It will be a configuration change, documented in the CDD under PTP TM L3 - LI-030-150 Who will own the work of building the new process / replacement: TM functional Team RICEFW's: LOGM009_IF/IP LOGM010_IF/IP |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0657?csf=1&web=1&e=v7ygKe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-09 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0658 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 10. Analytics 11. Technology | junior.milan@intel.com | [11 empty] | CI: Export Document Forms | Aligning multiple forms to follow import and export regulations in multiple geographies.​ | Original design for Export Commercial Invoice was tied to inter-company document being generated to accommodate sales, but direction changed and Export Commercial Invoice requirements with Deloitte were not revisited. Impact is incorrect Seller and Consignee information is incorrect. Pricing (Transfer Pricing) is also incorrect.​ End Customer Bailment CI does not show the bailment value segregated from the total value on the document. Impact is the customers ability to properly Import their goods at end destination, as the value expressed will be more than the actual import cost.​ The Delivery quantity was initially removed during the design phase, but this will now impact the declaration and clearance processes in the US and Ireland. This will need to be reintroduced to the forms that are missing it.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B26793FD3-14D5-400D-A5EB-C43A47D98870%7D&file=INT-CRXXXX_Export%20Document%20Forms_R2.pptx&action=edit&mobileredirect=true&previoussessionid=f97a9604-8bb3-a994-862a-51905d35321a |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [8 empty] | 18 |  |  |  |  | 0 | 18 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0344_IF, LOGF0346_IF, LOGF0353_IF, LOGF0354_IF, LOGF0345_IF, LOGF0354_IF, LOGF0346_IF | 7 | LOGF0344_IF, LOGF0346_IF, LOGF0353_IF, LOGF0354_IF, LOGF0345_IF, LOGF0354_IF, LOGF0346_IF | 7 |  | 0 |  | 0 | N/A |  | 2025-05-30 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | Approved in ad hoc meeting. - This change is to fix errors in a form for Chengdu: missing field used to declare customs, mismatching customer addresses, bailment field in customer bailment. | [9 empty] | Build | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0659 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Yousef Khan |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV156 - Costa Rica - TERADATA CLASS REPORT | Tax team is cancelling ECA object FPRXV156 - Costa Rica - TERADATA CLASS REPORT | Cancel and will be combined with FPRXV155 - Costa Rica - AP INVOICE REPORT |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0659,%20CR0660%20%26%20CR0661/RE_%20Additional%20Tax%20RICEFW%20Cancellations.msg?csf=1&web=1&e=FCCVdp |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV156 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-10 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0660 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Yousef Khan |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV133 - Tax Rollforward - provisions and FPRXV134 - Tax Rollforward - reserves | Tax team is cancelling ECA object FPRXV133 - Tax Rollforward - provisions and FPRXV134 - Tax Rollforward - reserves | Cancel and will be combined with FPRXV132 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0659,%20CR0660%20%26%20CR0661/RE_%20Additional%20Tax%20RICEFW%20Cancellations.msg?csf=1&web=1&e=FCCVdp |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV133, FPRXV134 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-10 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0661 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Yousef Khan |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA Report - Cancellation of Object FPRXV154 - Vietnam customized report | Tax team is cancelling ECA object FPRXV154 - Vietnam customized report | New enhancement RICEFW to be created for Fiori app tile customization |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0659,%20CR0660%20%26%20CR0661/RE_%20Additional%20Tax%20RICEFW%20Cancellations.msg?csf=1&web=1&e=FCCVdp |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV154 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-10 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0662 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology 17. B-App | YASH DESHPANDE | [11 empty] | PTPI0139_IF_Requirement to incorporate new custom fields in the FSD and mapping. | PTPI0139_IF is PO outbound interfaces which uses IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary app OpenText by incorporating the new custom field. | PTPI0139_IF is PO outbound interfaces which uses IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary app OpenText. If the changes are not incorporated accurate information might not be received by suppliers which can have significant business process impact. FS and mapping changes are required to incorporate multiple new fields as part of business requirement which are as follows: Take Batch from EKET-CHARG, and retrieve LICHA field from this batch => customer batch number EKKO- IHREZ – your reference – Packing slip – delivery reference => field used by VMI EKPO- AFNAM – customer Po number EKPO- BEDNR - customer PO line number |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/2.%20Interfaces/E2Open%20Interfaces/PTPI0138_PTPI0139_Interface_S4_to_OT_PO_New_Update/INT-CR0662_PTP_IF.pptx?d=w1df19450626044d8a7afe7601712a644&csf=1&web=1&e=C8S1aB |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 77 | 0 | [8 empty] | 77 |  |  |  |  | 0 | 77 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0139_IF | 1 | PTPI0139_IF | 1 |  | 0 |  | 0 | N/A |  | 2025-09-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | Confirmed with Boundary App OpenText team | [9 empty] | Build | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0663 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR0664 | Approved | Approved for interim release | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Sindhuja Gangireddy | [6 empty] | INC14863522 | Work In Progress |  |  |  | Update Delivery tolerance in SOLI based on difference between SO qty and POLP qty and Delivery creation with the quantity in POLP table | Update Delivery tolerance in SOLI based on difference between SO qty and POLP qty and Delivery creation with the quantity in POLP table | As the existing logic to update order qty in SOLI is restoring CMAD , new logic must be implemented to update Delivery tolerance in Sales order |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3AA0379C-B2A6-4798-B289-B1F33CC4DD00%7D&file=INT-CR0664_OTC%20IF_CR%20Delivery%20Tolerance.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 26 | 0 | [8 empty] | 26 |  |  |  |  | 0 | 26 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0397 | 1 | OTCE0397 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | Reviewed and Approved in ad hoc meeting - Titanium ramps up in Q4, and this change will be required before then to handle the volume. - Would be risky to deliver in R2, so the aim was for Hypercare - This is a stabilization update, not an enhancement; for scalability and customer impact - THIS IS A PRIORITY | [9 empty] | Build | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR0665 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [6 empty] | INC14918264 | Work In Progress |  |  |  | If there are multiple line items, and if there is at least one valid material / CPN / GTIN; then the sales order needs to be created for the valid line items (valid material / CPN / GTIN) and reject the line items with invalid line items (invalid material / CPN / GTIN). | SO creation for the combination of valid and invalid SOLI | If there are multiple line items, and if there is at least one valid material / CPN / GTIN; then the sales order needs to be created for the valid line items (valid material / CPN / GTIN) and reject the line items with invalid line items (invalid material / CPN / GTIN). |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0665%20-%20SO%20creation%20for%20the%20combination%20of%20valid%20and%20invalid%20SOLI.pptx?d=w36fd64aaaf8c44b583833c765bb17796&csf=1&web=1&e=0OLqlC |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0441 | 1 | OTCE0441 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | o For the future state, an error message will be sent back for failed materials in an order.  It was discovered during UAT1, but the team didn’t want to touch the code. o These changes will allow for the sales order to be created despite the failed materials, and the failed materials will come back as line items in the same sales order.  A new sales order will not be created, and will not override anything. o This is the current functionality for the B2B team. | [9 empty] | Build | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR0666 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [6 empty] | INC14918271 | Work In Progress |  |  |  | Additional fields to be added to the custom table ZOTC_DH table. | We have received 3 new requirements from a conversion front on DH table design. The same is being listed below. 1. Display of SoldTo party name and ShipTo party name. 2. If all the entries in the DH table for a particular SoldTo and ShipTo combination intended to be added is similar to the existing SoldTo and ShipTo combination entry with all the associated values, then do not allow the addition of the entry to the DH table. 3. S4 auto populate running number for any new entry added (without user entering new unique running number). | We have received 3 new requirements from a conversion front on DH table design. The same is being listed below. 1. Display of SoldTo party name and ShipTo party name. 2. If all the entries in the DH table for a particular SoldTo and ShipTo combination intended to be added is similar to the existing SoldTo and ShipTo combination entry with all the associated values, then do not allow the addition of the entry to the DH table. 3. S4 auto populate running number for any new entry added (without user entering new unique running number). |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0666%20-%20Additional%20fields%20to%20be%20added%20to%20the%20custom%20table%20ZOTC_DH%20table.pptx?d=wd786b5563fe64eb697df0848cbd866ab&csf=1&web=1&e=mS1jRi |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0441 | 1 | OTCE0441 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | o The DH table does not currently have the sold-to or ship-to name which is how the DUNS identifier is mapped.  Only a number is shown, and it is hard to know what it is without the name and description. | [9 empty] | Build | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0667 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Naman Parti | [11 empty] | List of changes that to be incorporated from IF ITC observations to IP | List of changes that to be incorporated from IF ITC observations to IP on the plot articulated in the change request presentation | This change needs to be implemented to ensure that the changes and bug fixes found in R2 IF ITC’s are not being encountered again in R3 IP | No impact to S4 system | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/List%20of%20CR%27s/INT-CR0667%20-%20List%20of%20changes%20that%20to%20be%20incorporated%20from%20IF%20ITC%20observations%20to%20IP.pptx?d=w259521f5496f4bf081fac497ce0a7de2&csf=1&web=1&e=lmb7S2 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-12 | 331 | > 30 Days | shravann9@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0668 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | FAC enhancement LOGE1299 to be dropped. The logic is covered under the Interface LOGI1300 | FAC enhancement LOGE1299 to be dropped. The logic is covered under the Interface LOGI1300 | Covered under the Interface object LOGI1300 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0631,%20CR0632,%20CR0668,%20CR0669,%20CR0671/FW%20CRs%20for%20cancelling%20RICEFWs.msg?csf=1&web=1&e=sbixXl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0669 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | GR confirmation flag objects to be dropped LOGI1242 and LOGE1304. These are covered under the interface object LOGI1263 | GR confirmation flag objects to be dropped LOGI1242 and LOGE1304. These are covered under the interface object LOGI1263 | Covered under the Interface object LOGI1263 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0631,%20CR0632,%20CR0668,%20CR0669,%20CR0671/FW%20CRs%20for%20cancelling%20RICEFWs.msg?csf=1&web=1&e=sbixXl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0670 | Cancelled |  | ERP | R1 (Release 1) R3 (Release 3) | [21 empty] | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0671 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Business Rules for Disposition Process LOGE1278 to be dropped. This is covered under the respective Static and dynamic disposition RICEFW objects. | Business Rules for Disposition Process LOGE1278 to be dropped. This is covered under the respective Static and dynamic disposition RICEFW objects. | Business Rules for Disposition Process LOGE1278 to be dropped. This is covered under the respective Static and dynamic disposition RICEFW objects. The replacement IDs are LOGE1281 and LOGE1310. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0631,%20CR0632,%20CR0668,%20CR0669,%20CR0671/FW%20CRs%20for%20cancelling%20RICEFWs.msg?csf=1&web=1&e=sbixXl |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1278 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | AR: For CR0671, what is the ID of the replacement “Static and dynamic disposition RICEFW objects.”? Can you please help to update? Answer: The replacement IDs are LOGE1281 and LOGE1310. | [9 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0672 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 11. Technology | Linda Y Nguyen | [11 empty] | Put sales orders specific to DMR on hold | For order types ZOR, ZDR, ZDR2 and ZWV (which are in scope for CRED hold), we should not check if item categories for these order types are in scope or not. If order is created with these order types and none of the item categories are not given in ZPARAMS table, the CRED hold needs to be applied as and when order is created. |  |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0672/RE%20OTC-IF%20CR%20Approved%20in%20GPO%20review%20-%20CR0672%20%20CR0664.msg?csf=1&web=1&e=aVUiQJ |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0067 | 1 | OTCE0067 | 1 |  | 0 |  | 0 | N/A |  | 2025-05-28 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-19 | Reviewed offline. Uzma has approved | [9 empty] | Build | Tower | 2025-05-19 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-13 | 0 | < 15 Days | aksawasthi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0673 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 06. PTP | Mohammad Shabaz | [11 empty] | De-Scope Material Master Quality Management IP Conversion Object | Material Master Quality Management Data is only required for IF and it is not required for IP( DATC1237_IP) | As per the outcome of design Material Master Quality Management View Data is only required for IF and it is not required for IP |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-08-07 |  |  |  | 2025-08-08 | [6 empty] | Other | Tower | 2025-08-07 | 08, 2025 | 08, 2025 | 05, 2025 | 2025-05-13 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0674 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF 09A. Master Data | [12 empty] | IC customers extension for all sales areas. | IC Customers extension for all sales areas. | IC Customers needs to be extended for all sales organizations for Intercompany Returns transaction. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0674_OTC_IF_Returns%20-%20IC%20Customers%20extension%20for%20all%20sales%20areas.pptx?d=wdc3f064d999a43e28e0dc37de8c4a2d4&csf=1&web=1&e=i4lqNu | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne that a workaround was found, and this CR can be cancelled |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-13 | 0 | < 15 Days | sbharathalkude@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0675 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Naman Parti | [11 empty] | The functionality for OTCI1155 is already covered in OTCI1179 and OTCE1115 | The RICEFW intake 2592 was incorrectly split by tech team into interface and enhancement though an equivalent interface object was already approved by intel as part of intake 2590.​ • Hence, to keep it consistent with Intel’s alignment and avoid discrepancies, can tech team remove the RICEFW OTCI1155 from the object tracker and keep OTCI1179 and OTCE1115.​ ​ | The functionality for OTCI1155 is already covered in OTCI1179 and OTCE1115 |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?noAuthRedirect=1&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0675%2FEXT%20RE%20Descoping%20Request%20for%20OTCI1155%2Emsg&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0675 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-14 | [10 empty] | Other | Tower | 2025-05-14 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-13 | 0 | < 15 Days | nparti@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0676 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration | llejarde@deloitte.com |  | Data - Julie Fawdington | [9 empty] | Stages Unit of Measure | Change Base unit of Measure for certain manufacturing Stages. | This is to properly account for the accurate unit of measure on each of the BOM levels as well as manufacturing stage. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0676_Material%20Master%20UOM.pptx?d=w6a55395ff3934a13bdd9f2a5e468cc5d&csf=1&web=1&e=YsGmSV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-13 | 330 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0677 | Cancelled |  | ERP | R3 (Release 3) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | llejarde@deloitte.com |  | Data - Julie Fawdington | [9 empty] | PROC WLA BOM Structure Changes | WLA BOM structure for PROC Items has to be changed to accommodate FTS- requirements for PROC BOM to be more flexible | LA BOM structure for PROC Items has to be changed to accommodate FTS- requirements for PROC BOM to be more flexible | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0677_MDG_BOM_CR%20Change%20in%20BOM%20Structure%20of%20PROC%20WLA%20Enchancement.pptx?d=w00dd900063e94ae6804fbec549c799da&csf=1&web=1&e=HVAKbY |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Lilibeth to cancel as the build has not started yet. So, the tech effort will be less than 40 hours. FS changes will be tracked and changed in the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0678 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Ramagiri Pradeep Kumar | [11 empty] | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for Web suite relevant DSL for doc type: LP (PTPI0812_IP/IF). | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for Web suite relevant DSL for doc type: LP (PTPI0812_IP/IF). | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for Web suite relevant DSL for doc type: LP (PTPI0812_IP/IF). |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR0678_PTP_IF_IP.pptx?d=w0f0fa836edb34fda8fff599c01983541&csf=1&web=1&e=3uQGHp |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as per Murthy | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-13 | 0 | < 15 Days | ramagkumar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0679 | Rejected |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 09A. Master Data 11. Technology | nidhi.wadhwani@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Turnkey Indicator on IP and IF UPI & FG Items in MDG | A Turkey Indicator attribute/characteristic is needed on Intel Products and Intel Foundry's UPI and FG items in MDG with Release 3. | This indicator would be used by FPR, OTC and PTP in the IP-IF PO/SO process. Revenue recognition process in S4 ERP environment will need this indicator on the Turnkey Products as well. This indicator would have to be there for IP items because when they pull the price into the PO, they need to know when the product is a Turnkey product. | Impact to Conversion of Item Master Data (Classification View) RICEFW | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0679_Material%20Master_Turnkey%20in%20Material%20Master.pptx?d=wac908a807c4643fcab069615e6af0786&csf=1&web=1&e=eKksfn |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes | S4 | 0 |  | 3158 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | Yes | No | 2025-06-05 | o When this CR was taken through the RICEFW intake process, the tech team determined that an interface, not an enhancement, was required. o AR: Review the request change to an interface - @Linnell, Candice S o AR: Size the interface and come back to CR with the effort - @Lejarde, Lilibeth |  |  | 2025-06-06 | [6 empty] | Other | CL/OSC | 2025-06-06 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R1 (May 2025) | R1 | INT-CR0680 | Approved |  | ERP | R1 (Release 1) R2 (Release 2) R3 (Release 3) |  | 13. Security | 13.6 Security - Cyber/ Controls |  | 13. Security | nisahmed@deloitte.com |  | Security - Raj Valluri | [9 empty] | Change Order to ERP IT & Business Controls Narratives | This change request proposes incorporating IT & Business controls narrative into the project scope to provide a more comprehensive understanding of the organization's IT systems and business processes embedded within IT systems and each business process, which includes system description, risks, controls, roles and responsibilities, respectively. Initially, this element was not included in the project scope; however, as we finalize the design and testing phases, we seek approval to proceed with this update to align with the revised requirements | The rationale for including IT and business narratives in the project scope, particularly for SOX/Audit compliance, is to ensure thorough documentation and integration of controls that align business objectives with IT capabilities, thereby enhancing compliance, risk management, and operational efficiency. | No Impact to Existing Deliverables | No |  |  | https://secure-web.cisco.com/1itXl26VIKUVHiVSzHkGdAQwgTTs2Ax8lfV8A2UGsZnXYicNnu9P5PNF-Wl6TVTX-S1aGNnJlx9DKZa9GGbwjcsj9l8_h32SMgl6Wl6FDoDRzLyVBL2Ado73xrtv3nLqVoZGjB4PdH3zt9fdf06Nk64QcBe_SGUBxapFgF2gdoyiMo3vEvvT777jt-qL5C7pwSzYS2eLh5JQwD4TP9LVIAgLn0lXdD999gMQsHLU1wKBxF0Dmfle1Mf7NQxLrkYV-jypPVuDeRzaF4EYCvb-LkQC8puHyOn5yun6DUkVURGOoqGo3QxRFIuFGGicwUJU4i-wgL1VVRFDCIqy_UUumu78RrRjejE2LxCz8LgwcY4oMAjbKogbYMdnnlTvHQARiWVgj9a4CoRXrQQ6yNx8sy0xDlj-uH-xUIo9M-XaONFgpIW7cx8bZwWG4hoXMM0GHvNel48FQgbE5KWrvkGID1oSR99XQRuLzl-u-lqTIjZ57QiJT6CVervuxN7y7ticgce6V0wisfLQfWrcFXU2MHA/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F01.%2520PMO%2F05.%2520Scope%2520and%2520Change%2520Control%2FChange%2520Control%2FChange%2520Request%2520Decks%2FSecurity%2520%2526%2520Controls%2FINT-CR0680_Security%2520CR_IT%2520%2526%2520Business%2520Controls%2520narrative.pptx%3Fd%3Dwe6651a9c3f11462da11ca297bdae3afb%26csf%3D1%26web%3D1%26e%3DYeuSmY |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | Security | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2024-09-23 | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-05-14 | - This change is for Deloitte to document the controls and process narratives for each process. Each E2E process is listed out with all of the roles and security controls that are involved. - There are some existing roles narratives, but the security team will enhance it with best practices and ensure consistency across as there are a lot of roles being added for R1/R2. - The control narrative is owned currently by the control owner, and there are many. So, there a slight differences. - High-level security roles are different from the controls narrative. It is the entire lifecycle of a role to be executed, including post-go-live. If a role needs to be executed after everything is live, then defined process needs to be executed to make sure that everything passes. - Original SOW was only scoped to identify risks. As the team progressed, they realized that this is missing to fulfill external auditors who will be examining the new system in Q3. The security narratives are not linked to go-live. - The team will need an answer in the next 2 weeks to complete the narratives on time, but it is not a showstopper. - AR: Determine whether there is a trade-off to the current work in flight. - Yaz - AR: Determine how much credit was given back from descoping DPP and understand how much the security narratives cost. - Yaz, Alpna, Anand |  |  | 2025-05-20 | Per our discussion last week, the estimate for the Security team’s change request (CR0680) to add Business Controls narrative and Non Production Security roles work to Deloitte scope, is $259K. Security team is requesting this be netted off against the already approved change request (CR0479) that was done to descope Data Privacy. That approved CR would have credited back $227K. | [5 empty] | Other | CL/OSC | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0681 | Cancelled |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.13 OTC IF – Returns (Logistics Management) | Yes | 04. OTC IF 10. Analytics | Ray O'Neill |  | OTC IF - Angela Laskowski | [9 empty] | LSS Shipment Report | Develop new report to be used by Logistics Support Services (LSS), global 3PL logistics supplier, to support management / communication of inbound return order shipments to plant warehouses | LSS group support global logistics shipments / tracking, they were not originally part of the operational support model for IF return orders. As part of operationalizing the return process, logistics team determined value add that LSS team can provide for managing the tracking and communication of return orders, they were therefore added to the operational model. | No Impact | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0681_OTC_IF_Returns-LSS_Shipment_Report_R2.pptx?d=w284f805c62424aaea107027bc9d73ed3&csf=1&web=1&e=6s6zdB |  | 2. New RICEFW / ECA / Build Object |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brianne to be cancelled as a workaround was identified | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-14 | 0 | < 15 Days | ray.m.oneill@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0682 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 09A. Master Data | rudrsengupta@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Shipping Taskforce Change Request | New objects are identified for changes related to Non-Rev Shipments, Lot Level Shipping Exceptions​, KM2/KM5 design and updated requirements for existing objects - FTSI0677 and FTSI0830 | As part of the shipping task force changes are identified which would need 11 new RICEF objects and changes to 2 of the existing objects | FTSI0677 and FTSI0830 which are initially planned for sprint 13 will now be part of sprint 14 and 15 respectively. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0682_FTS-IF_Shipping%20taskforce%20change%20request.pptx?d=w9e01f5e5b5e6416489959f8c390b606a&csf=1&web=1&e=0ArpVo | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Very High |  | 4 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o The shipping task force FTF completed last week. As Prospal is being retired in its entirety, all capabilities will need to be re-built in SAP, including Prospal lite. • The team will need a lot of new UI’s and mappings that weren’t required in SAP. o This is very similar to what was done for WIINGS; it is the PROSPAL equivalent. | [9 empty] | Design | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0683 | Approved |  | SCP | R2 (Release 2) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP 18. SCP | erin.irby@intel.com |  | FTS IP - Loni Adams | [9 empty] | Product Hierarchy Alignment | Update the technical names for the hierarchy attributes in BY CDP to align with the display names and updated hierarchy. | Due to SPEED BOM and SPAN Die segmentation mismatch, We are not able to generate DLCP Calendar. RJ die is required to be modeled to support OneMPS WLA process steps for Foveros products (CWF, MTL, etc). | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/Product%20hierarchy%20level%20mismatch.pptx?d=w2a564babae4a4e51b84ffeeae78810f3&csf=1&web=1&e=pu8LLX |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 40 | 0 | [6 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o No impact to R3, and the work will be completed by a BY resource. • ECA and PDH are showing the correct hierarchy, and the error is just in BY. • It is in the same environment, and the team has a 1 week window to fix. | [9 empty] | Build | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0684 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP 10. Analytics | Shashank.kolhe@intel.com |  | FTS IP - Loni Adams | [9 empty] | Demand Planning Prioritization in ECA | Change data source for IAO R2 Demand Planning Prioritization from Profisee to BY SCP | Outdated requirement in functional spec regarding source for Demand Prioritization data | Will be available in UAT2 instead of UAT1 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/Reporting%20for%20Demand%20Prioritization.pptx?d=w446d30bd972842a58246d518ecaba30a&csf=1&web=1&e=WXXaz2 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 100 | [6 empty] | 100 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o This request comes from an ECA standpoint as there is a disconnect in the data sources. • The computation happens in PDH and is correct. The error comes during the reporting due to a gap in output requirements. • The SAP SAC data to enable this will be available in R2. • This is part of the work that the team did to identify all of the ECA gaps and foundational work required. o ECA work is 3 weeks because there are codes in different layers required. o AR: Capture all of the ECA efforts that have already been completed - @Mathew, Saji S @Kolhe, Shashank | [9 empty] | Build | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0685 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 11. Technology | Shiva Shankar Harikrishnan |  | FPR - Aubrey Hinderlider | [9 empty] | Update existing custom table ZTFPR_ACRENG02 to store the calculation of PO line items accrual details that will be used for ECA reports | Update existing custom table ZTFPR_ACRENG02 to store the calculation of PO line items accrual details that will be used for ECA reports | Currently, the PAT Fiori dashboard receives the consumption data for prepaids and accruals at PO header level. ECA reports for accruals require details of the accruals and inputs at the line item details. Therefore, S4 will perform the calculations and store the information in the custom table. ECA will consume the data from the table ZTFPR_ACRENG02 to generate the reports required for accruals. The below items will be part of the new change request Custom program to calculate the line item accrual details from Header data from PAT Fiori dashboard Update the existing custom table with additional fields to support ECA accrual reporting Update three fields in ZTFPR_ACRENG01 table to support reporting (Validity, PO Header Description and PO order date fields) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0685%20-%20Update%20existing%20custom%20table%20ZTFPR_ACRENG02%20to%20store%20the%20calculation%20of%20PO%20line%20items%20accrual%20details%20that%20will%20be%20used%20for%20ECA%20reports%201.pptx?d=w2ebb3ff498e84de1922bb8513bf4bbac&csf=1&web=1&e=pDydQw |  | 2. New RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [9 empty] | 364 |  |  |  | 0 | 364 | N/A | Yes | S4 | 2 | FPRE1599_IP, FPRE1599_IF |  | FPRE1599_IP, FPRE1599_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-17 | o This is related to procurement approval. After lots of discussion with ECA team, the teams figured out that doing this in ECA is really complex. • So, the solution is to do it in the S4 layer and re-populate before sending the data to ECA. • It is a new object that we have the build that will calculate the accrual amounts and update the table | [9 empty] | Other | Tower | 2025-07-17 | 07, 2025 | 07, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | ythirupathi@deloitte.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR0686 | Cancelled |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | [12 empty] | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to Web suite_IF _IP | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to Web suite_IF _IP | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to Web suite_IF _IP |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as per Murthy | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-14 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0687 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Naman Parti | [11 empty] | Change request to descope the object OTCI0964 as the required functionality is already covered in RICEFW objects OTCE1108. | • For creating consignment fill-up orders, we initially scoped OTCI0964, which served as an interface with BY for order creation. However, following final discussions with the BY/PDH team, it was agreed to use the custom FTS stagging table for this purpose instead. As a result, OTCE1108 was scoped and approved, and OTCI0964 should now be descoped. | Change request to descope the object OTCI0964 as the required functionality is already covered in RICEFW objects OTCE1108. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?noAuthRedirect=1&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0687%2F%5BEXT%5D%20RE%5F%20Descoping%20Request%20for%20OTCI0964%2Epdf&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0687 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | nparti@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0688 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Deepanshu Lnu | [11 empty] | change request to descope the object PTPI1330_IP_IF, as this functionality is not required from Websuite for construction & equipment, instead this would be covered under SIRFIS to S4 interface, | change request to descope the object PTPI1330_IP_IF, as this functionality is not required from Websuite for construction & equipment, instead this would be covered under SIRFIS to S4 interface, | change request to descope the object PTPI1330_IP_IF, as this functionality is not required from Websuite for construction & equipment, instead this would be covered under SIRFIS to S4 interface- PTPI0018, PTPI0019, PTPI0494 |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0688/EXT%20RE%20Approval%20required%20to%20Descope%20the%20object%20PTPI1330_IPIF.msg?csf=1&web=1&e=bGiKdY | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0688/EXT%20RE%20Approval%20required%20to%20Descope%20the%20object%20PTPI1330_IPIF.msg?csf=1&web=1&e=bGiKdY |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI01330_IP, PTPI01330_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0689 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View: ECAFPRV2175 - ECA view cost center master and hierarchy from ECA MDG layer for HAT (FPRI0911_IF) | FPR - Cancellation of ECA View: ECAFPRV2175 - ECA view cost center master and hierarchy from ECA MDG layer for HAT (FPRI0911_IF) | Object descoped as the requirement is covered under the ECA object ECAFPRV2197 - ECA View to be built receiving from HAT for S/4 IF consumption - Interface for importing the Headcount details by Person# and WBS element combination from HAT to ECA for burden allocation. FPRI0909_IF |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0689,%20CR0690,%20CR0691,%20CR0692,%20CR0693/Approval%20by%20Shane%205-14-25%20-%205%20ECA%20View%20Cancellations%20CR.pdf?csf=1&web=1&e=R6tY72 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | ECAFPRV2175 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0690 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-ECAFPRV2176-ECA view master data and cost center hierarchy from ECA MDG layer for HAT (FPRI0911_IP) | FPR - Cancellation of ECA View object-ECAFPRV2176-ECA view master data and cost center hierarchy from ECA MDG layer for HAT (FPRI0911_IP) | Object descoped as the requirement is covered under the ECA object ECAFPRV2196 - ECA View to be built receiving from HAT for S/4 IP consumption - Interface for importing the Headcount details by Person# and WBS element combination from HAT to ECA for burden allocation. FPRI0909_IP |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0689,%20CR0690,%20CR0691,%20CR0692,%20CR0693/Approval%20by%20Shane%205-14-25%20-%205%20ECA%20View%20Cancellations%20CR.pdf?csf=1&web=1&e=R6tY72 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | ECAFPRV2176 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0691 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-ECAFPRV2198-ECA View to be built Pull Foundry WBS from HAT and create in LE 199 in IP S/4 for Foundry Employees moved to LE 199. | FPR - Cancellation of ECA View object-ECAFPRV2198-ECA View to be built Pull Foundry WBS from HAT and create in LE 199 in IP S/4 for Foundry Employees moved to LE 199. | Object descoped as the requirement is covered under the ECA object ECAFPRV2196 - ECA View to be built receiving from HAT for S/4 IP consumption - Interface for importing the Headcount details by Person# and WBS element combination from HAT to ECA for burden allocation. FPRI0909_IP |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0689,%20CR0690,%20CR0691,%20CR0692,%20CR0693/Approval%20by%20Shane%205-14-25%20-%205%20ECA%20View%20Cancellations%20CR.pdf?csf=1&web=1&e=R6tY72 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | ECAFPRV2198 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0692 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-ECAFPRV2199-ECA View to be built Pull Foundry WBS from HAT and create in LE 199 in IF S/4 for Foundry Employees moved to LE 199. | FPR - Cancellation of ECA View object-ECAFPRV2199-ECA View to be built Pull Foundry WBS from HAT and create in LE 199 in IF S/4 for Foundry Employees moved to LE 199. | Object descoped as the requirement is covered under the ECA object ECAFPRV2197 - ECA View to be built receiving from HAT for S/4 IF consumption - Interface for importing the Headcount details by Person# and WBS element combination from HAT to ECA for burden allocation. FPRI0909_IF |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0689,%20CR0690,%20CR0691,%20CR0692,%20CR0693/Approval%20by%20Shane%205-14-25%20-%205%20ECA%20View%20Cancellations%20CR.pdf?csf=1&web=1&e=R6tY72 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | ECAFPRV2199 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0693 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Amit Kumar |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-ECAFPRV2200-ECA IP View for Federal (WBS_IF from HAT) | FPR - Cancellation of ECA View object-ECAFPRV2200-ECA IP View for Federal (WBS_IF from HAT) | Object descoped as the requirement is covered under the ECA object ECAFPRV2196 - ECA View to be built receiving from HAT for S/4 IP consumption - Interface for importing the Headcount details by Person# and WBS element combination from HAT to ECA for burden allocation. FPRI0909_IP |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0689,%20CR0690,%20CR0691,%20CR0692,%20CR0693/Approval%20by%20Shane%205-14-25%20-%205%20ECA%20View%20Cancellations%20CR.pdf?csf=1&web=1&e=R6tY72 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | ECAFPRV2200 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0694 | Approved | Need RICEFW ID of ECA View | ERP | R2 (Release 2) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 10. Analytics | ashish.chaurasia@intel.com |  | Data - Julie Fawdington | [9 empty] | Addition of Attributes to Warehouse Task View to Provide End to End Visibility to Goods Receipts and Putaway Process | Add 6 new columns to an existing ECA View to provide complete information of all open shipments, received shipments and shipments which completed putaway, which will shorten the action time and improve the efficiency. | GLO Business users need the receipt and putaway visibility to enable the signal from factory and the visibility of custody and SLA, and this is critical for R2 because Wafers may not be picked up from the factory. The current ECA View is missing some critical information, without this change, the users will not have complete visibility into the goods receipt and putaway process. | No risk/impact on R2. R3 build deliverables might be delayed for a couple of objects | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BADFFAA3B-BDB5-4A64-B881-C93B24601B37%7D&file=INT-CR0694-Addition%20of%20Attributes%20to%20Warehouse%20Task%20View%20to%20Provide%20End%20to%20End%20Visibility%20to%20Goods%20Receipts%20and%20Putaway%20Process-%20Copy.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 58 | 0 | [9 empty] | 58 |  |  |  | 0 | 58 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-13 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-15 | o Logistics requires the report as part of the Power BI strategy. • The only workaround is to check shipments one-by-one. | [9 empty] | Build | Tower | 2025-05-15 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0696 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | rudrsengupta@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Need a new custom report for the Operating Supplies orders placed from Factory Portal | This report will be used to list all the orders which were placed by the Technician(s) from the Factory Portal UI. The report will have both Reservations and Stock Transport Number in the output along with the other required details. | Report need is identified for the Technicians using the Factory Portal to order the Operating Supplies. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0696_FTS-IF_Custom%20Report%20for%20OperationalSuppliesInFactory%20Portal.pptx?d=wa0cc8ee6c0a444509583143518ce190c&csf=1&web=1&e=asgSps | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [9 empty] | 110 |  |  |  | 0 | 110 | N/A | Yes | S4 | 1 | FTSE1467 |  | FTSE1467 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This requested report will enable user to view both reservations and STO’s all together. o This will be an enhancement for operating supplies. Will need to go to RICEFW intake meeting | [9 empty] | Other | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-15 | 0 | < 15 Days | njain42@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0697 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration 11. Technology | mshabaz@deloitte.com | [11 empty] | Additional requirement for Material Master Class and Characteristics conversion | Changes are required in conversion program of Material Master Class and Characteristics conversion to include additional requirements for R3 | Minimize Manual Intervention and improve quality of data |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0697_Material%20Master%20Class%20and%20Characteristics%20Conversion.pptx?d=wdb71d086fe6c4e76acd517165c421d5f&csf=1&web=1&e=Cuh0UL |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 300 | 0 | [10 empty] | 300 |  |  | 0 | 300 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0077, DATC0078 | 2 | DATC0077, DATC0078 | 2 |  | 0 |  | 0 | N/A |  | 2025-12-19 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o The team has a conversion program for Material Master Class and Characteristics for R2, but they will need to be adjusted for R3 into a different format and logic as there are different requirements. • This will be done by the tech team. | [9 empty] | Build | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-15 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0698 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Manjunath M Meti | [11 empty] | Change request to descope the object OTCI0739 as the required functionality does not require any additional Interface development and handled by SLT | Order sim data are stored in custom table . Requirement is to transfer the data to ECA. As this functionality can be achieved by the SLT and Side car setup, OTCI0739 needs to be descoped . Discussion was carried out with SLT team, Intel OTC architect to descope the RICEFW | Change request to descope the object OTCI0739 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0698/EXT%20RE%20Descoping%20Request%20for%20OTCI0739.msg?csf=1&web=1&e=JnTaM9 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-15 | 0 | < 15 Days | mmeti@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0699 | Cancelled |  | ERP | R2 Q4 '25 Anafi enablement |  | 04. OTC IF | 4.11 OTC IF - Order Management |  | 02. E2E Process Integration 03. FPR 04. OTC IF 09A. Master Data 15. Cutover 16. Testing 18. SCP | angela.c.laskowski@intel.com |  | OTC IF - Angela Laskowski | [8 empty] | Anafi | Anafi Integration | Convert Anafi to an external customer at 12/28/2025. Enable B2B interfaces with Anafi, setup master data in R2, create/migrate initial orders | Required | No change to functionality. This is a change to scope to move Anafi to R2+ | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Dilky Bruggerman and Keith Wu to be cancelled as this CR has been replaced now with multiple other CRs as confirmed by Keith | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0700 | New |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | sumeetrsharma@deloitte.com |  | PTP - Richard Taylor |  | CR1262 | [7 empty] | IMR orders from IP to IF, Impact on Logistics needs to be analyzed and evaluated. | For IMR Rework orders between IP and IF the following points are required to be discussed : 1. Decision on the Lab being a separate entity/Plant - Do we need inventorized Lab Materials? Can we use ISM process of non inventory items to ship material from IP to IF for Repair/Rework? 2. Impact on Shipping Documents - is there a requirement to print the shipping documents from Intel S/4 environment or will it be managed offline by Intel Labs? 3. Impact on RTC or backflush needs to be analyzed for the Subcon PO 4. Impact of GR posted in EWM and its communication to IP 5. Transportation requirements - Will it be owned by IP or IF ? 10/22 - CR to be cancelled - Neetu+Imran to own closure | For covering IMR Rework between IP and IF; overall impact on Inbound Logistics needs to be analyzed |  | No | Non-Core |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-15 | 328 | > 30 Days | divytrivedi@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0701 | Approved |  | ERP | R2 (Release 2) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 04. OTC IF 09A. Master Data 09B. Data Migration 16. Testing | Fabian Castro |  | FPR - Aubrey Hinderlider | [9 empty] | E2E_009_S09-RMA for Direct Customers with physical receipt of the product - test case 28215: needs to change material groups from goods to service. | E2E_009_S09-RMA for Direct Customers with physical receipt of the product - test case 28215: needs to change material groups from goods to service for ONESOURCE to trigger correct tax results for 3 materials (Joshua Rock BUMP, Joshua Rock WLA, Caicos). | For US, sale of services to customers are non-taxable. Hence, need to change material groups from goods to service for ONESOURCE to trigger correct tax result (no tax) for 3 materials (Joshua Rock BUMP, Joshua Rock WLA, Caicos). |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5B3FC736-C5CA-4B5D-9894-CA8C9969A903%7D&file=INT-CR0701%20E2E_009_S09-RMA%20for%20Direct%20Customers%20with%20physical%20receipt%20of%20the%20product%20-%20test%20case%2028215.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | Tech - MDG | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-13 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o This came out of the UAT1 testing and needs a master data change to denote tax logic. • The change in here is to change the commodity code in material master from goods to service. • Is it a config or data conversion? It has to be done from conversion and moving forward o AR: Confirm that MDG can make this change – Lilibeth | [9 empty] | Build | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-15 | 0 | < 15 Days | ropham@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR0702 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bala.gottumukkala@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-FPRFV001-Product Cost Actuals vs Standard Analysis - IF | FPR - Cancellation of ECA View object-FPRFV001-Product Cost Actuals vs Standard Analysis - IF | Objects Descoped since the requirement of this is covered in the ECA objects FPRFR001 -[Real Time] Product Cost Actuals vs Standard Analysis - IF | No Impact to Existing Deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRFV001 |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael to be cancelled as the team is keeping these RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0703 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bala.gottumukkala@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-FPRFV004-Stage Cost Report - IF | FPR - Cancellation of ECA View object-FPRFV004-Stage Cost Report - IF | Objects Descoped since the requirement of this is covered in the ECA objects FPRFR003 -[Real Time] Stage Cost Report - IF | No Impact to Existing Deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRFV004 |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael to be cancelled as the team is keeping these RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0704 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bala.gottumukkala@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-FPRPV002-Product Cost Actuals vs Standard Analysis - IP | FPR - Cancellation of ECA View object-FPRPV002-Product Cost Actuals vs Standard Analysis - IP | Objects Descoped since the requirement of this is covered in the ECA objects FPRPR001 -[Real Time] Product Cost Actuals vs Standard Analysis - IP | No Impact to Existing Deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRPV002 |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael to be cancelled as the team is keeping these RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0705 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bala.gottumukkala@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-FPRPV005-Stage Cost Report - IP | FPR - Cancellation of ECA View object-FPRPV005-Stage Cost Report - IP | Objects Descoped since the requirement of this is covered in the ECA objects FPRPR003 -[Real Time] Stage Cost Report - IP | No Impact to Existing Deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRPV005 |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael to be cancelled as the team is keeping these RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0706 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bala.gottumukkala@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object-FPRXV143-Stage Cost Breakdown | FPR - Cancellation of ECA View object-FPRXV143-Stage Cost Breakdown | Objects Descoped since the requirement of this is covered in the ECA objects FPRXR038 -[Real Time] Stage Cost Breakdown | No Impact to Existing Deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV143 |  |  | 1 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael to be cancelled as the team is keeping these RICEFW's | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0707 | Approved |  | ERP | R1 Hypercare |  | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | kritajoshi@deloitte.com |  | Data - Julie Fawdington | [9 empty] | Additional Changes to FICO Recon Report | New changes to the FICO Recon Reports have been requested by the tower team. 1) CO Recon - Unmatched Reason Code 2) CO Recon - Top Down Summary Recon Report 3) Additional changes to FI Recon | There are some complicated scenarios where the ECA report is not able to programmatically match the CO and FI line items for COIN transactions. There are some other scenarios where ECC CO tables do not have corresponding FI line items. The report cannot match CO and FI without this. To circumvent these challenges, Intel has asked for a top down summary report. CO line items from ECC will be summarized by Controlling Area, Company Code, GL Account, Doc Type, Cost Center, Functional Area, LC and GC. Similar summarization will be pulled from S4 (CFIN). Report should pull matched/unmatched based on this summarization | FPR, Analytics Team | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-%20CR0707_%20Additional%20Changes%20to%20the%20FICO%20Recon%20Reports.pptx?d=w689b46355eb04c53927edd9e5ff6d528&csf=1&web=1&e=7j8lkD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 320 | 0 | [9 empty] | 320 |  |  |  | 0 | 320 | ECA | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-05-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-27 | Approved during Hypercare Meeting | [9 empty] | Build | Tower | 2025-05-27 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0708 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Capture header comments on return request to include on disposition and receiving screens | Renaming of the header text | The purpose of making these comments visible to downstream (Receiving & Dispo screen) is part of case management to efficiently communicate any specific direction |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0708_OTC%20IP%20%E2%80%93%20Capture%20header%20comments%20on%20return%20request%20to%20include%20on%20disposition%20and%20receiving%20screens.pptx?d=w9d42f33442d54246be3536e69340fcaa&csf=1&web=1&e=1HHyc5 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the effort is less than 40 hours of tech effort | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-16 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0709 | Approved |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 09A. Master Data 09B. Data Migration | Mariana Campos |  | OTC IF - Angela Laskowski | [9 empty] | Creation of new Carrier vendors in MDG system for AES filing | For ITS/ AES filing purposes, there is a need for additional carriers to be created in MDG system. |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR0709%20%20Request%20for%20creation%20of%20new%20Carriers%20%20Logistics%20Vendors%20in%20MDG%20for%20R2.pptx?d=w0162590ed2dc43aa84c7128c8eddc3aa&csf=1&web=1&e=7y6GQG |  | 2. New RICEFW / ECA / Build Object |  |  | Low | 48 | 1 | [10 empty] | 40 |  |  | 0 | 40 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o MDG to perform the data conversion and load into R2 o There was a disconnect between freight-forwarder and carrier. This will fix the gap. | [9 empty] | Other | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-17 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0711 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Rebeca Meza Redondo | [11 empty] | Step Pricing based on cumulative quantity of Sales orders | Step Pricing based on cumulative quantity of Sales orders |  | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B300AF734-A835-49C7-B1B1-BCD82C6DA15F%7D&file=INT-Build-CR0XXX_OTC%20IP_CR%20Deck_Step_pricing.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpmuppala%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA0MTcxOTMxMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 1. Process Scope / Design Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Sarah that this functionality was added to the post-R3 dev CIP list. Therefore, the CR can be cancelled. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-19 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0712 | Cancelled | Awaiting Sunil's approval | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 07. FTS IF 08. FTS IP 10. Analytics | Neshat Jalali Heravi | [11 empty] | Descope LOGV023_FTSIP, LOGV013_FTSIF, and LOGV018_FTSIP | Cancel objects as they are covered in other ECA or S/4 objects. Rationale updated with replacement object ID's | - LOGV023_FTSIP: Non-S4. Been captured in the Intel ECA IDM Object Tracker as ECAPTPV4804 (IF) & ECAPTPV4805 (IP). To be developed by Intel APT Team - LOGV013_FTSIF: Fields are covered in LOGV043_FTSIP & LOGV044_FTSIF (Inbound Logistics IP/IF). Hence they can be cancelled. To be developed by Deloitte Team - LOGV018_FTSIP: Fields are covered in LOGV043_FTSIP & LOGV044_FTSIF (Inbound Logistics IP/IF). Hence they can be cancelled. To be developed by Deloitte Analytics Team | No Impact to Existing Deliverables | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Neshat Jalali Heravi that this CR is no longer required. | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 05, 2025 | 2025-05-20 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0713 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift Ownership of Budget Verification Report to Team 6 | FPRXV213 - Budget Verification Report ¦ Change of ownership from FPR team 11 to team 6. | Out of Scope for project accounting (Tm.11) ¦ Shifting ownership to cost & profitability (Tm.6) | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0712%20-%20Budget%20Verification%20Report.pptx?d=w516daf7f7f974bdd98905691bb6de7e4&csf=1&web=1&e=LKsjQy |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0714 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift Ownership of Burden Details Report to Team 6 | Shift ownership of the Burden Details Report to Team 6 (Cost & Inventory) FPRXV220 | Report was assessed as 'Out of Scope' for Project Accounting | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0713%20-%20Burden%20Details%20Report.pptx?d=wb53263a9e2e44095bf593a4c2dddbed4&csf=1&web=1&e=dPVEEH |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0715 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift Ownership of the FX Impact Report to Team 6 | Shift ownership of the FX Impact Report from team 11 to team 6. FPRXV222 | The report was assessed as out of scope for project accounting. | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0714%20-%20FX%20Impact%20Report.pptx?d=w4716adf3301045f293b9d46bba0f4343&csf=1&web=1&e=NHOu7C |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0716 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift Ownership of the Headcount Pipeline Details Report to Team 6 | The Headcount Pipeline Details Report needs to move from Project Accounting (Team 11) to Cost & Profitability (Team 6) ECAFPRV2365 | The report was assessed as 'out of scope' for Project Accounting | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0715%20-%20Headcount%20Pipeline%20Details%20Report.pptx?d=wb5c6888e2d8b4496924085fc3f7a58c6&csf=1&web=1&e=Ib1qph |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0717 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift ownership of the LTRCA report to Team 6 (Cost & Profitability) | The Long Term Restricted Cash Award (LTRCA) report needs to shift from Project Accounting (Team 11) to Cost & Profitability (Team 6) FPRXV224 | The report was assessed as 'out of scope' for project accounting | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0716%20-%20LTRCA%20Report.pptx?d=w283ede0a0376404b9e9623eee73544ea&csf=1&web=1&e=pEjEBQ |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0718 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift ownership of the Pre vs. Post Reorg Report to Team 6 | Move ownership of the Pre vs. Post Reorg Report from Project Accounting (Team 11) to Cost & Profitability (Team 6) FPRXV232 | The report was assessed as 'out of scope' for Project Accounting. | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0717%20-%20Pre%20vs.%20Post%20Reorg%20Report.pptx?d=w99291a8180484c998b45c1454d1285a8&csf=1&web=1&e=aZsaKv |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0719 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Shift ownership of the Targets & Transfers report to Team 6 | Moving ownership of the Targets & Transfers report from Project Accounting (Team 11) to Cost & Profitability (Team 6) ECAFPRV5247 | Report was assessed as 'out of scope' for Project Accounting | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0718%20-%20Targets%20and%20Transfers%20Report.pptx?d=w7f983b77c4b54438a3d6e8b2a93e66da&csf=1&web=1&e=pZmvDO |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-20 | [10 empty] | Other | Tower | 2025-05-20 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0720 | Approved |  | ERP | R3 (Release 3) |  | 11. Technology | 11.3 Technology - Middleware |  | 11. Technology 12. Infrastructure | ravindra.b.neralakatte@intel.com |  | Tech & Dev - John Camarillo | [9 empty] | Governance check update for R3 Objects | Update needed to 65 R3 Mule Interfaces to change the error handler and connector configuration in JWT package to comply with the additional Governance check rules configured in Intel Mulesoft CI/CD process | To comply with the Governance check for seamless code deployment via CI/CD, error handler and connector configuration change in JWT package is required. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Technology/CR%20XXX%20-%20Governance%20check%20update%20for%20R3%20Objects.pptx?d=w55d8595ce95b43758c4dd87c8bba0be6&csf=1&web=1&e=peXa25 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 65 | 0 | [8 empty] | 65 |  |  |  |  | 0 | 65 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 65 RICEFW's | 1 | 65 RICEFW's | 1 |  | 0 |  | 0 | N/A |  | 2025-05-16 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This is a change required on 65 interfaces that have been built. • The Intel IT team has changed the tool for governance check. So, there is an addition of rules. • Therefore, the governance rules need to be retrofitted and making those minor changes to each of the interfaces. o AR: Work with Ravi and OTC Team to determine deployment schedule of the changes – @Mavuduru, Vijay | [9 empty] | Build | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0721 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Namrata Dwarakanath | [8 empty] | 19569 | SAP Ariba Cloud |  | Change PTPI0094_IF & PTPI0094_IP to remove Mulesoft from the architecture & use APIGEE only and change the service in S4 from a REST to SOAP service. | Change PTPI0094_IF & PTPI0094_IP to remove Mulesoft from the architecture & use APIGEE only and change the service in S4 from a REST to SOAP service. Add five to four business validations on this interface that check currency, ship to address, supplier, commodity and/or country of PR’s and return an error message to Ariba if the rules are not followed. | The change in architecture is needed to align this interface with the approved technologies and other interfaces already approved and created. The additional validation are required to ensure the purchases created follow standards that keep them legal and complaint with company and country purchasing rules. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B456B2C64-87B1-4BBD-8354-07C7356B877E%7D&file=INT%20CR0721_PTP_IF_IP.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 292 | 0 | [8 empty] | 292 |  |  |  |  | 0 | 292 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | PTPI0094_IP, PTPI0094_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0094_IF, PTPI0094_IP | 2 | PTPI0094_IF, PTPI0094_IP | 2 |  | 0 |  | 0 | N/A |  | 2025-07-04 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This is the only interface that remains on MuleSoft and needs to be moved. o FS has not started, but this is a blocker for everything that is done in Ariba. • Will need to adjust the next sprint, but the team will take on in priority. | [9 empty] | Build | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | pabharshavardhan@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0722 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Descoping PTPI0685_IP object and Renaming PTPI0685_IF into PTPI0685_CFIN | Initially for sending the Transactions (Invoices) from IP and IF system to Illumis, we created PTPI0685_IP and PTPI0685_IF. But right place for this development is CFIN system. PTP- EP team want to rename one existing object into CFIN object and the other one to be cancelled. Functionality and requirement from business standpoint remain the same. | We can send transaction data from CFIN system only. | N/A | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0722/EXT%20RE%20Request%20for%20GPO%20alignment%20related%20to%20object%20PTPI0685_IP%20and%20IF.msg?csf=1&web=1&e=XcE7P8 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | [10 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-20 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0723 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of ECA View object- FPRXV089 - CPLG Variance Report (Team 6) | FPR - Cancellation of ECA View object- FPRXV089 - CPLG Variance Report | The CPLG Variance Report was identified as a duplicate of the Close Forecast Variance Report in rationalization | No Impact on existing deliverables. | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0723/Approval_%201%20ECA%20View%20Cancellation%20CR%20for%20Cost%20%26%20Profitability.msg?csf=1&web=1&e=m0S8gq |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV089 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0724 | Approved |  | ERP | R2 (Release 2) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 12. Infrastructure | Chandrasekhar Gorantla |  | FPR - Aubrey Hinderlider | [9 empty] | Change Calendar API | Change the Calendar API to the Latest version, since the api that is being used is deprecated. | The existing API has been deprecated and should be changed to newer version to ensure support. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0724%20Mulesoft%20to%20change%20Calendar%20API.pptx?d=w3a90ad8cdd1043778fed572699995c64&csf=1&web=1&e=nJVw9b |  | 8. Non-Build Infrastructure-related Change |  |  |  | 30 | 0 | [8 empty] | 30 |  |  |  |  | 0 | 30 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | o This request is to update Calendar API to the correct version in order to determine the correct work week. • This will be correct in Mulesoft. o AR: Include timeline and dates of when the changes will be completed - @Mishra, Gaurav @Mavuduru, Vijay | [9 empty] | Other | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0725 | Approved |  | ERP | R2 (Release 2) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology | Chandrasekhar Gorantla |  | FPR - Aubrey Hinderlider | [9 empty] | Change the logic to filter the TR Ratios from the MDG API | The API for FX Ratios picks all the currencies that are available with no single entries and that are not part of the 97 currencies that are coming from the request. The system should always pick the latest ratios. | The API output is not filtered causing issues in the design and configurations. We should be using 97 currencies only to filter the entire table and then pick latest ratios. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0725%20Mulesoft%20to%20change%20Ratios%20API.pptx?d=w088daadb69ea4a38895f1af733d655cf&csf=1&web=1&e=1glgDR |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 35 | 0 | [8 empty] | 35 |  |  |  |  | 0 | 35 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | - Configuration needs to be changes so that the latest ratios (not historical) should be pulled in. - There are only 97 currencies at the time. If currencies are added, then it will be picked up automatically. - | [9 empty] | Build | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Aug 2025) | R2 | INT-CR0726 | Approved |  | SCP | R2 (Release 2) |  | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | erin.irby@intel.com |  | FTS IP - Loni Adams | [9 empty] | Node Expiration Management | 1. Export Node Master BDM view (with NodeEndDate) from CDP --> PDH --> ECA 2. Build "Node Expiration" operational report in ECA to help facilitate the node expiration process. | Node Expiration is required when a product is retired, canceled, or renamed (there are more business use cases). To ensure a closed-loop process, higher-level measure values must be retained when a node is expired at the leaf-lvl. The Node Expiration rpt will support the business in facilitating the node expiration process. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20CCB%20PXT%20Node%20Expiration%20Mgmt.pptx?d=we3c79f9fce8c4f1996953ae2d0094692&csf=1&web=1&e=mtkn1P |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 8 | 40 | 0 | 120 | [6 empty] | 168 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o This request is to incorporate logic to figure out which nodes need to be expired. o Total effort is 15 days. The team can do development in parallel by sending mock up data to CDP | [9 empty] | Build | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0727 | Approved |  | ERP | R1 Hypercare | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 12. Infrastructure | Chandrasekhar Gorantla |  | FPR - Aubrey Hinderlider | [9 empty] | Change the logic for Quantum logic for populating BID/OFFER/MID rates | Change the logic for sending the BID and MID rate because of quantum logic. | The rates needed in QT should be same for BID and ASK to MID Rate. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0727%20Change%20the%20logic%20for%20Quantum%20logic%20for%20populating%20MID%20rates.pptx?d=we106e784a02c499c93530d4073da71f7&csf=1&web=1&e=eF54be |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 35 | 0 | [8 empty] | 35 |  |  |  |  | 0 | 35 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-05-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-22 | o Tech is already done, and it is being tested. | [9 empty] | Build | Tower | 2025-05-22 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0728 | Approved | Presenter: Ranju | ERP | R3 (Release 3) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 06. PTP 07. FTS IF 08. FTS IP 11. Technology | Susan Strathman |  | FTS IF - Haritha Komma | [8 empty] | WIINGS | Material Hazmat Profile Management Capability | Request: Need to enable maintenance of Hazardous Material Profile to be used within the Factory Portal Application. The hazmat profile advises Factory and Warehouse workers on proper handling and shipping of hazardous inventory returns. ​ Recommendation: Build a new application to enable maintenance of hazardous material profile using UI5 technology stack. The data is created and accessed from the same system.​ | The design for maintenance of hazmat profile for materials was not finalized during L3 Design Phase. Options were explored but not decided. This CR is to review options considered and get approval for the proposed option. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B90FB3E7E-AD62-4563-A172-F19E3C847D2D%7D&file=Material%20Hazmat%20Profile%20Management%20CR%20Apr%2725.pptx&action=edit&mobileredirect=true | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 260 |  |  |  |  | 0 | 260 | N/A | Yes | S4 | 2 | FTSE1360, DATE1613 |  | FTSE1360, DATE1613 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-05-22 | o Need a profile to be generated and tagged to materials so that the hazardous material team will know how to handle it. It will come through the Factory Portal UI. o This is not part of the original design scope. • The original plan was to explore options in ECM, SAP EHS module, eCUDL, and custom REACT application. • eCUDL said no because it is not their scope of work. High-volume use cases are taken care of by MBOM. It would be a re-write if they took on the work. • MBOM would have to be changed to a Tolerate Boundary App o The aligned option is a small footprint application. Will need to go to CR Meeting |  |  | 2025-05-23 | o Required to enable maintenance of Hazardous Material Profile to be used within the Factory Portal Application. The hazmat profile advises factory and warehouse workers on proper handling and shipping of hazardous inventory returns. o Existing WIINGS module is too deeply embedded to extract. o Alternatives (React app, EHS Center of Excellence, SAP EHS module) were evaluated and rejected due to complexity, cost, or misalignment with needs. o Recommended solution: Build a lightweight UI5 app in NF4. o Estimate: 260 hours (~$21K), to be funded by Intel Foundry vs. IAO. o Concerns Raised, Mike Lange and Todd Smith questioned the long-term strategy of building custom apps instead of leveraging SAP modules. Clean core violations were discussed but clarified as standard SAP customizations, not core modifications. Cari Shim supported the short-term tradeoff for cost and expediency. o Confirmed that only two modules remain: eDFIT and the hazardous material profile app. | [5 empty] | Other | CL/OSC | 2025-05-23 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-21 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | Complete |  | Complete | No
R1 (Hypercare) | R1 | INT-CR0729 | Approved |  | ERP | R1 Hypercare | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Inactivate four fiori reportss. ​ | R1 Make the following Fiori reports inactive:​ 1.Operating Segment report​ 2.Segment Balance Sheet​ 3. Segment Eliminations​ 4. IS test​ ​ | Segment reporting uses a C14 table to report actuals that reflect the impact of reorgs and restatements. This solution requires ACDOCA, ACDOCU, CC to PC relationships for historical data from MDG and restatement data from SAC. As these elements are not all in Group reporting, the Fiori reports designed will not meet the segment report requirement. ​ The IS test is not useful to the team because of a) a new accounting standard that is expected to change the presentation and disaggregation of expenses on the IS. b) The report identifies IS items that should be disclosed on the face of the IS. However a majority of the IS lines are already disclosed and the few that are reviewed for disclosure are relatively immaterial amounts that are unlikely to trigger disclosure outside of a material event ​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B77F16633-3D29-4461-975E-303BEF809795%7D&file=INT-CRXXXX%20_R1_report_inactivation_.pptx&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  |  | Low | 11 | 1 | [11 empty] | 11 |  | 0 | 0 | Configuration |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  | 2025-08-07 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-21 | o This request is to remove security access and Fiori apps to prevent unintended users. The custom reports will remain as the team assess whether they can be re-used in the future. o AR: Reword CR so that it is clear that only security will be removed and reports will remain - @Shah, Twinkle o AR: Include enhancement RICEFW ID’s - @Ch, Bharathi o AR: Include dates on when the security team can perform the work - @Dey, Kalyan o Link to Deck | [9 empty] | Build | Tower | 2025-05-21 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-22 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0733 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 04. OTC IF 06. PTP 11. Technology 17. B-App | YASH DESHPANDE |  | PTP - Richard Taylor | [9 empty] | Mapping and FSD changes due to new requirement in RICEFW PTPI0136_IP_IF | Mapping and FSD changes due to following changes 1.IP DUNS - value will be sent in the Secondarybusinessdata fields of AS2 headers. (Existing field from AS2 header will be utilized) 2.IP DUNS 4 - value will be sent in the SecondaryBusinessDesc field of AS2 header. (Existing field from AS2 header will be utilized) 3.Build instructions number – New custom item field will be introduced to fetch the BI number. 4. Shipping type field level changes. 5.DCM Change ID field logic changes. 6.IP_IF_Route_Scenario - Logic changes to add new identifiers. Impacted FSD - PTPI0136_PTPE0606_PTPI0816 | PTPI0136/37 are PO outbound interfaces which use IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary apps E2open, Opentext. If the changes are not incorporated certain necessary fields and accurate information will not be sent to suppliers . |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0733/RE%20Approval%20required%20for%20CR%20INT-CR0733%20%20Object%20PTPI013637.msg?csf=1&web=1&e=6dgI0Z | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0733/INT-CR0733.pptx?d=w5fa868402377435fbf12433d2a614010&csf=1&web=1&e=BW4bjO |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 45 | 0 | [8 empty] | 45 |  |  |  |  | 0 | 45 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0136_IP, PTPI0136_IF, PTPI0137_IP, PTPI0137_IF, PTPE0606_IP, PTPE0606_IF, PTPI0816_IP, PTPI0816_IF, PTPI1134_IF | 9 | PTPI0136_IP, PTPI0136_IF, PTPI0137_IP, PTPI0137_IF, PTPE0606_IP, PTPE0606_IF, PTPI0816_IP, PTPI0816_IF, PTPI1134_IF | 9 |  | 0 |  | 0 | N/A |  | 2025-11-28 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | o 160 hours can be absorbed within the current workload that the team has. o The team is asking to move ahead with the build. During the next week, the team will be working with stakeholders to see if the build can be done in a different manner to pull in FUT. | [9 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-23 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0734 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.4 FPR - Intercompany |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Combining 4 Intercompany reports into 1 object ID | FPR - Cancellation of ECA View object-FPRXV064-HC Report: Ops1 Operations Headcount EXCEL.url FPR - Cancellation of ECA View object-FPRXV065-Ops1 Headcount Detail FPR - Cancellation of ECA View object-FPRXV066-Headcount Report India *These reports are being consolidated into FPRXV063 ¦ OPS1 Standard BnP HC Report: OLAP | Result of ECA object rationalization exercise to combine/reduce the inventory of development items. these 3 ECA RICEFW are being consolidated into FPRXV063 ¦ OPS1 Standard BnP HC Report: OLAP | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0734/Approval%203%20ECA%20View%20Cancellation%20CR%20for%20Intercompany.msg?csf=1&web=1&e=omGLA3 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV064, FPRXV065, FPRXV066 |  |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0735 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | [12 empty] | Enhancement required to add custom logics to multiple fields in the PO outbound IDOC as per Websuite requirement (PTPI0816/PTPI1329_IP_IF) | Enhancement required to add custom logics to multiple fields in the PO outbound IDOC as per Websuite requirement (PTPI0816/PTPI1329_IP_IF) | Enhancement required to add custom logics to multiple fields in the PO outbound IDOC as per Websuite requirement (PTPI0816/PTPI1329_IP_IF) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR0735_PTP_IF_IP%20(Vers-1).pptx?d=we46e3e583c50424e91d4eeefc6100e2e&csf=1&web=1&e=kl6Yxu |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [8 empty] | 225 |  |  |  |  | 0 | 225 | N/A | Yes | S4 | 2 | PTPE1495_IP, PTPE1495_IF |  | PTPE1495_IP, PTPE1495_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o Commercial details are sent to Websuite, and the information needs to be slightly different to support the invoice. o AR: When creating the intake form, address open questions about whether the team can re-use E2Open code - @K P, Murthy | [9 empty] | Other | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-26 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0736 | Cancelled |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 09A. Master Data | rawasthi@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | shipping point naming convention change | shipping point naming convention needs to be changed to make it more user friendly. | In FTS-LOG WIP discussion (shipping point/Dock), business has aligned to have identical naming convention for Storage Type in EWM/Shipping Point so the warehouse operator will know where to receive it”. If we don’t follow this approach, then we need to have a separate WRICEF to link the shipping point to sloc so that warehouse operator knows where to receive it. | Impact on CUT activities related to STO's as there these shipping points are required. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0736_FTS_IF_Logistics_management_shipping%20point%20naming.pptx?d=w47f82a4fefcf4ceab88ebd6ef9edf6e4&csf=1&web=1&e=31Ys6c |  | 1. Process Scope / Design Change |  |  |  | low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as tech effort was less than 40 hours | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0738 | Cancelled |  | ERP | R2 (Release 2) | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 11. Technology | rishabhx.hingmire@intel.com | [11 empty] | Label Printing from Spectrum | To update the label printing program to transmit details to Spectrum. The changes include implementing ship label sequencing and resolving carrier label weight issues. The Box Sequence number field should not require user entry and should increase incrementally as the user clicks “Print” until all of the labels are printed. | This change is required to print correct sequence and correct weight on Labels |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0738_OTC_IF_EWM-%20Label_Printing_LOGI0278.pptx?d=w269b291f27564f0ebdad39af0e0ce823&csf=1&web=1&e=gQBKQN |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Ruben to have already been implemented and tested | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-27 | 0 | < 15 Days | rhingmire@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0739 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 08. FTS IP 09A. Master Data | Lilibeth Lejarde |  | Data - Julie Fawdington | [9 empty] | IP BOM Structure Change | Change in IP BOM Structure | Change in IP BOM Structure |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0739%20IP%20BOM%20structure%20change.pptx?d=wee89f2a64a434d25a343565162611d7e&csf=1&web=1&e=XFXxEf |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-27 | 316 | > 30 Days | nagirreddy@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0740 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-27 | 0 | < 15 Days | nagirreddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0741 | Cancelled |  | ERP | R3 (Release 3) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | llejarde@deloitte.com |  | Data - Julie Fawdington | [9 empty] | Systems and Boards/SIM BOMs: Removal of 6-3 Material | Systems and Boards/SIM BOMs: Removal of 6-3 Material or MMID from the BOM Conversion. | Systems and Boards/SIM BOMs: Removal of 6-3 Material or MMID from the BOM Conversion. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0741_Systems%20%26%20Boards_SIM%20BOM_Remove%206-3%20Material.pptx?d=wccbce09d95594e7496b256cab95b1ffa&csf=1&web=1&e=w6GW8f |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Lilibeth to cancel as the build has not started yet. So, the tech effort will be less than 40 hours. FS changes will be tracked and changed in the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-27 | 0 | < 15 Days | nagirreddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0742 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Vijay Sharma | [11 empty] | Develop the custom report for auto PR to PO conversion fallout in SAP S/4 HANA instead in ECA | Develop the custom report for auto PR to PO conversion fallout in SAP S/4 HANA instead in ECA | PR to PO conversion in S/4 HANA system will be automatic as per aligned business process based on the master data setup material, supplier, PIR and Source Lists. Currently PRs are converted manually to PO by buyers. Therefore, a report needs to be developed to capture the failed non converted PRs with the failure reasons so that buyers can take appropriate actions. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR0742_PR%20to%20PO%20auto%20conversion%20fallout%20report%20-%20Change%20Request.pptx?d=w486155a9736048c2bf20db1d8ba547e5&csf=1&web=1&e=HnGwat |  | 2. New RICEFW / ECA / Build Object |  |  | Very High | 0 | 4 | [8 empty] | 288 |  |  |  |  | 0 | 288 | N/A | Yes | S4 | 2 | PTPI1529_IP, PTPI1529_IF | 3025 | PTPI1529_IP, PTPI1529_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o This request is for a new custom report that will display all errors if a PR is not converted to a PO. • This was originally an ECA report, but not all of the information can be configured in ECA. • There is a standard error log, but it only displays the errors one-by-one. o AR: Include reasoning for the high effort in RICEFW intake form - @K P, Murthy | [9 empty] | Other | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-27 | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0743 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Vinayak Prabhu | [11 empty] | Shipment interface to S4 | We need to set up two new interface between WOM and S4 system via middle ware to retrieve the information related to the shipping information and the tracking details such as POD ( proof of delivery) from GTT system to WOM. Mapping of the fields and the payload request already exist as of today for the ECC system, we need to implement similar design for S4 System | WOM users will not have visibility to the shipping and the tracking information in WOM portal. Hence, an interface is required to retrieve shipping details from S4 IP system. |  | Yes |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0743_OTC%20IP.pptx?d=w54d0cad5f41b4417994e1b3d3a2e3490&csf=1&web=1&e=krifEK | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B54D0CAD5-F41B-4417-994E-1B3D3A2E3490%7D&file=INT-CR0743_OTC%20IP.pptx&action=edit&mobileredirect=true&previoussessionid=81c2a8ae-9b6b-898a-8aee-ccb08b684c8d |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes | S4 | 1 | OTCI1568 |  | OTCI1568 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | [10 empty] | Other | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-28 | 0 | < 15 Days | vinayprabhu@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0744 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.3 OTC IP - Billing and Rebates |  | 05. OTC IP 11. Technology | Sandhya Sandhyarani | [11 empty] | CR for all the IP-B2B requirements(capturing new requirements) recorded in the IF-ITC testing | CR for all the IP-B2B requirements(capturing new requirements) recorded in the IF-ITC testing | During ITC Testing, B2B Team is mapping the target payload with As-is. It has been identified that certain fields are not populating. Object ID's- OTCI0296_IP OTCE0654_IP |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0744_OTC%20IP_CR%20for%20Defects%20recording%20new%20requirements.pptx?d=w94c104e6c5a243a19f7ffb40c5cc21a3&csf=1&web=1&e=o38Zul |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | 40 | 2 | [8 empty] | 40 |  |  |  |  | 0 | 40 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0296_IP​, OTCE0654_IP | 2 | OTCI0296_IP​, OTCE0654_IP | 2 |  | 0 |  | 0 | N/A |  | 2025-06-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | o AR: Change effort to 0 – Prakash Veerasivaji | [9 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-28 | 0 | < 15 Days | sandsandhyarani@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0745 | Cancelled |  | ERP | R2 (Release 2) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data | Harshavardhan Harshavardhan | [11 empty] | DATE0192 - Filter cost center based on company codes | All cost centers are replicated over in cost center hierarchies in IF S4 even though cost centers are not valid in IF due to company code is in IP, thus, creating replication failure and confusion on data reconciliation between cost center and cost center hierarchy. | This functionality is required in IF and IP systems |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Build has already been incorporated and tested. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 05, 2025 | 2025-05-28 | 0 | < 15 Days | karnayak@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0746 | Approved |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics | mike.s.lenau@intel.com |  | FTS IF - Haritha Komma | [9 empty] | IAO R2 BY-SPAN Schedule (FSCO FAB , BUMP , SORT WIP + BY Planned Order) | IAO R2 BY-SPAN Schedule is not the combination of FSCO FAB , BUMP , SORT WIP + BY Planned Order | In the current design, the previous cycle BY Planned Orders roll into the frozen horizon and are not adjusted. However, in BY we are not using the previous planned orders as our statement of supply, we are using the FSCO Projections, so BY will adjust the forward-looking planned orders based on how much WIP is in the line. Whenever the WIP in line varies from the original planned order in either quantity or time, we get a misalignment when we stitch together the old planned orders within frozen and the new planned orders outside frozen to generate the POR schedule. This existing design does not meet the need for reliable supply schedules or demand schedules described above. | Solution won't be ready until cycle 2 of UAT2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/IAO%20R2%20BY-SPAN%20Schedule%20is%20not%20the%20combination%20of%20FSCO%20FAB%20,%20BUMP%20,%20SORT%20WIP%20+%20BY%20Planned%20Order.pptx?d=w409d253c8d094379bea8e4733ad27529&csf=1&web=1&e=fyyFnj |  | 8. Non-Build Infrastructure-related Change |  |  |  | 0 | 0 |  |  |  | 0 | 40 | 0 | 80 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-05-29 | o The target is to complete all of the work in UAT2 at the start, but the second requirement won’t be ready until the end of UAT2. • Will impact some of the current R3 deliverables to complete this work, but it is relatively small. The team is hopeful to recover. o There is no viable manual workaround. |  |  | 2025-05-30 | • Proposal: Split the POR schedule into two: o Supply Schedule: Reflects expected output from Fab, Bump, and Sort. o Demand Schedule: Reflects what is needed to meet demand, back projected from sales orders. • Effort Estimates: o Supply schedule: ~1 week (low effort). o Demand schedule: ~5 weeks (higher effort, spans UAT2 Cycle 1). • Risks: o Span team resource reallocation may delay R3 deliverables. o Manual workarounds deemed too complex and error prone. • Decision: Proceed with changes despite risks, leveraging lighter Sprint 14–15 capacity. | [5 empty] | Other | CL/OSC | 2025-05-30 | 05, 2025 | 05, 2025 | 05, 2025 | 2025-05-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0748 | Approved | Ganesh | ERP | R3 (Release 3) | High | 07. FTS IF | 7.5 FTS IF - TM | Yes | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP 11. Technology | Ganesh Kumaresan | [11 empty] | VTRC for Freight forwarders -Initial design is to update Manually the HAWB however Intel/Syed/Biz advised to bring a new Intake to automate the HAWB assignment to TM FO with number ranges based on shipping point/location | VTRC for Freight forwarders -Initial design is to update Manually the HAWB however Intel/Syed/Biz advised to bring a new Intake to automate the HAWB assignment to TM FO with number ranges based on shipping point/location | HIGH volume of HAWB assignments to Freight forwarders |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0748%20-Automatic%20HAWB%20assignment%20for%20Freight%20Forwarders(%20ISM%20Prospal%20STO%27s)%20.pptx?d=w6fabddceb2a9465796ab4218a39fcb45&csf=1&web=1&e=U6ESl8 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 2 | LOGE1526_IP, LOGE1526_IF | 3003 | LOGE1526_IP, LOGE1526_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | Already went through RICEFW and tech intake; CR is approved | [9 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 05, 2025 | 2025-05-29 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR0749 | Approved |  | ERP | R3.X (Post-R3) | Medium | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | ECA Object Rationalization exercise for Team 5, 14 object tag for be deleted. | FPR - Cancellation of ECA View object-FPRXV044-10Q Cost Asset Class Details FPR - Cancellation of ECA View object-FPRXV045-10Q Depreciation Asset Class Details FPR - Cancellation of ECA View object-FPRXV048-Asset Retirements HANA FPR - Cancellation of ECA View object-FPRXV049-FAA GL Account Activity FPR - Cancellation of ECA View object-FPRXV078-AUC Details FPR - Cancellation of ECA View object-FPRXV083-AUC Validation FPR - Cancellation of ECA View object-FPRXV105-PO Details FPR - Cancellation of ECA View object-FPRXV108-Tax Cost Roll Forward FPR - Cancellation of ECA View object-FPRXV109-Tax Depreciation Roll Forward Report FPR - Cancellation of ECA View object-FPRXV123-Change Order Data Custom Report FPR - Cancellation of ECA View object-FPRXV138-Localization - Malaysia: Generate tax schedules /reports in the format needed for tax filing FPR - Cancellation of ECA View object-FPRXV193-Generic vendors location details FPR - Cancellation of ECA View object-FPRXV237-Asset List Orphan FPR - Cancellation of ECA View object-FPRXV238-Asset Missing UAI (Unique Asset Identifier) | FPR - Cancellation of ECA View object-FPRXV044-10Q Cost Asset Class Details-->This report can be combined with FPRXV047 - Asset Accounting Transactions FPR - Cancellation of ECA View object-FPRXV045-10Q Depreciation Asset Class Details-->This report can be combined with FPRXV047 - Asset Accounting Transactions FPR - Cancellation of ECA View object-FPRXV048-Asset Retirements HANA-->This report can be combined with FPRXV047 - Asset Accounting Transactions FPR - Cancellation of ECA View object-FPRXV049-FAA GL Account Activity-->Eliminate, replaced by a fiori app FPR - Cancellation of ECA View object-FPRXV078-AUC Details-->This report can be combined with FPRXV047 - Asset Accounting Transactions FPR - Cancellation of ECA View object-FPRXV083-AUC Validation-->This report can be combined with FPRXV046 - Aging AUC Raw Data FPR - Cancellation of ECA View object-FPRXV105-PO Details-->This report can be combined with FPRXV051 - PO Research Report FPR - Cancellation of ECA View object-FPRXV108-Tax Cost Roll Forward-->This report can be combined with FPRXV038 - Tax Rollforwards (Cost/ Depreciation/Tax) FPR - Cancellation of ECA View object-FPRXV109-Tax Depreciation Roll Forward Report-->This report can be combined with FPRXV038 - Tax Rollforwards (Cost/ Depreciation/Tax) FPR - Cancellation of ECA View object-FPRXV123-Change Order Data Custom Report-->Eliminate, this is not needed as per Shin, Steven FPR - Cancellation of ECA View object-FPRXV138-Localization - Malaysia: Generate tax schedules /reports in the format needed for tax filing-->This report can be combined with FPRXV038 - Tax Rollforwards (Cost/ Depreciation/Tax) FPR - Cancellation of ECA View object-FPRXV193-Generic vendors location details-->This report can be combined with FPRXV041 - Asset list Report FPR - Cancellation of ECA View object-FPRXV237-Asset List Orphan-->This report can be combined with FPRXV041 - Asset list Report FPR - Cancellation of ECA View object-FPRXV238-Asset Missing UAI (Unique Asset Identifier)-->This report can be combined with FPRXV041 - Asset list Report | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0749/Approval%20View%20Cancellation%20CR%27s%20for%20Fixed%20Assets.msg?csf=1&web=1&e=LrUt4h |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV044, FPRXV045, FPRXV048, FPRXV049, FPRXV078, FPRXV083, FPRXV0105, FPRXV0108, FPRXV0109, FPRXV0123, FPRXV0138, FPRXV0193, FPRXV0237, FPRXV0238 |  |  | 14 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0750 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | njain42@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSI1017 | Request the cancellation of Object FTSI1017. The primary requirement for this object—STR generation—is now fully addressed within FTSI1020 | Request the cancellation of Object FTSI1017. The primary requirement for this object—STR generation—is now fully addressed within FTSI1020 |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Interface/FTSI1017-IMO-Create%20STR/EXT%20RE%20FTS-IF%20RICEF%20Cancellation%20Request%20FTSI1017.msg?csf=1&web=1&e=GZMzR0 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 126 |  |  |  |  | 0 | 126 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1017 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-04 | [10 empty] | Other | Tower | 2025-06-04 | 06, 2025 | 06, 2025 | #INVALID OPERATION |  | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0751 | New |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 09A. Master Data | Nisa Khatun | [11 empty] | Existing CMIR records to be marked for deletion for materials that will go under FERT To HALB conversion for IF R3 release. Object - OTCC0564. | Existing CMIR records to be marked for deletion for materials that will go under FERT To HALB conversion for IF R3 release. Update OTCC0564 to ensure these changes are added in current structure and loaded properly in the S/4 system. | Business users want the capability to have CMIR updated for the specific Materials which will go under FERT To HALB Conversion during R3 Cutover, this activity will be specific for IF system, CMIR to be deleted automatically for materials which will undergo FERT to HALB Conversion. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR0751%20-%20Existing%20CMIR%20records%20to%20be%20changed%20for%20materials%20that%20will%20go%20under%20FERT%20To%20HALB%20conversion%20for%20IF%20R3%20release..pptx?d=w0d37e126b48844e5b1d46a0522cdc2cb&csf=1&web=1&e=1na4kp |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | #INVALID OPERATION |  |  | < 15 Days | nikhatun@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0752 | Approved |  | SCP | R2 (Release 2) | Very High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 18. SCP | Wen-Ting Shaw | [11 empty] | Modeling PO Request Date to align with BY weekly buckets | Suppliers require that our order due dates align to a specific day of the week, rather than be scattered throughout the week. This request is to adjust the due date when creating the orders in SAP ECC, aligning to the specified day of the week. The targeted day of the week must fall within the same Blue Yonder weekly bucket. This change should only apply to PDH, no change required in BY and no impact to PRF. Current PDH logic edits the RDD for Internal (-1D) and External (-2D). Change request is to change logic for Internal (+6D) and External (+5D). Additionally, scheduled receipts should be adjusted to the beginning of the Blue Yonder weekly bucket (on Sunday). | Prior requirement was to adjust due date by going backwards to the defined day of the week. However, this crossed BY time buckets causing a disconnect between the bucket in which the order was planned and the time bucket in which the order is placed. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR%20-%20Adjust%20Day%20of%20Week%20for%20PR%20Create.pptx?d=wb7251637cab8468b9b1c01701d3999b8&csf=1&web=1&e=mU4x92 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 80 | 0 | 0 | [6 empty] | 80 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-05-29 | o Change the PO request date in PDH to align better what both external and internal customers expect • This is a change in logic to push it to the +6 or +5, and use the next Friday/Saturday that the PO’s are created. • Need support from PDH team to support adjustments in the logic; R3 resource has been allocated o AR: Update the scheduled dates to be 2 weeks – Ashok | [9 empty] | Build | Tower | 2025-05-29 | 05, 2025 | 05, 2025 | #INVALID OPERATION |  | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0753 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  |  | NITIN.PATIL@INTEL.COM | [11 empty] | Cancellation of ECA report "Fall Out Report for Component PO Conversion" and "Fall Out Report for Subcon PR to PO Conversion" Object ids - PTPFR104 and PTPFR105 | Descoping these two objects ids as the requirement cannot be met through ECA reports | As per initial assessment this requirement was dispositioned as ECA reporting requirement. During the ECA report DSD preparation it was identified that this capability cannot be developed within ECA as the auto PR to PO conversion batch job data is not stored in SAP tables. Therefore, the proposal is to have this capability developed within S4. that facilitates buyers to identify the issues with the PRs and get them processed to PO. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0753,%20CR0905,%20CR0901/RE%20Deloitte%20ECA%20Objects%20Cancellation.msg?csf=1&web=1&e=QhxdY2 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPFR105, PTPFR106 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-23 | [10 empty] | Other | Tower | 2025-07-23 | 07, 2025 | 07, 2025 | #INVALID OPERATION |  | 0 | < 15 Days | abtibrewal@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0754 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 11. Technology | Vivek Yadav | [11 empty] | Enhancement required in Purchase order Standard API to send descriptions from S4 to Customs Tracker_IF _IP to Support RICEFW PTPI1137 | Enhancement to Get Purchase order details like Payee, Supnam, Purchase group description, Purchase organization description, payment term description, material description, and material group description from IF & IP system to Customs tracker to support PTPI1137 interface. | To meet the requirement for interface PTPI1137 , we need to create an enhancement/extension in standard API API_PURCHASEORDER_2 (Odata V4)​?Assumptions:​ Standard API will extension/Enhancement to capture and send to Customs tracker from IF/IP system. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B60E7C77F-C93D-49E8-9E01-85299B8E3D10%7D&file=INT-CR0754_PTP_Enhancement%20required%20in%20Purchase%20order%20Standard%20API%20to%20send%20descriptions%20from%20S4%20to%20Customs%20Tracker_IF%20_IP%20(Vers-1).pptx&wdLOR=c08A65DAF-9207-41B5-8094-08BACACBABF2&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes | S4 | 1 | PTPE1465_IP |  | PTPE1465_IP | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o Approved in RICEFW meeting. | [9 empty] | Other | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | #INVALID OPERATION |  | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0755 | New |  | ERP | R3 (Release 3) |  | 07. FTS IF | 9A.9 Master Data – PDM |  | 07. FTS IF 08. FTS IP 09A. Master Data 10. Analytics 17. B-App | suneel.deshpande@intel.com |  | FTS IF - Haritha Komma | [9 empty] | Master data management to support SFP renames due to Prospal EOL | Requesting MD team to own SFP to SFP mapping data which could be consumed by TD automation and others for new SFP Rename capability being developed to support Prospal EOL. Work involves 1) 2 sets of mapping to enable TD apps for End of FAB/SORT shipments 2) Setup business process to manage missing UPIs for the MES Shop floor products 3) Providing data consumption methods to new apps. | Prospal EOL | Business Impact: This is a must have capability, as Factory uses Shop Floor Product Names for shipments and S/4 uses UPIs, without mapping factory won't be able to ship the products. Prospal currently provides this capability, which will begin it's EOL from IAO R3 to R5. | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | #INVALID OPERATION |  |  | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0756 | Cancelled |  | SCP | R2 (Release 2) |  | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | i.piacentini@yahoo.com |  | FTS IP - Loni Adams | [9 empty] | ASP Fcst & Rev POR Parent Level Node Creation | Do not trigger parent level node (MM/PC) creation from ASP Fcst or Rev POR signal. | Creating a parent-level node without children clutters the CDP UI with non-editable nodes, consuming screen space and make forecasting process cumbersome. Parent-level nodes will be 100% derived from leaf-level nodes. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/ASP%20Fcst%20%26%20Rev%20POR%20Parent%20Level%20Node%20Creation.pptx?d=we3dc23855f484c018ba68811345b19b7&csf=1&web=1&e=765soh |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Erin and Joseph to be cancelled as the effort is only 2 days, and it has been set for re-testing as the changes have been completed. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | #INVALID OPERATION |  | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0757 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | Passthrough Locations (Modification to FTSE0982) | Update FTSE0982: Enhancement to Capture Reason Codes for Return to include more specific passthrough location options (quartz, chemicals) and storage location (Copper/Heavy Metal/Non-contaminated) (new ztable) | This is new requirement not included in the existing Enhancement FTSE0982. This will add more conditions for technicians to filter the list of Passthrough Locations. | FS Date: 7/18 Build Date: TBD FUT Date: 7/21 – 9/5 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0757%20-%20Passthrough%20locations%20(Modification%20to%20FTSE0982).pptx?d=w3e2b4083d9894093b0c203965259cc8c&csf=1&web=1&e=dPZauz |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 70 | 0 | [8 empty] | 70 |  |  |  |  | 0 | 70 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSE0982 | 1 | FTSE0982 | 1 |  | 0 |  | 0 | N/A |  | 2026-02-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o This request is for additional hours to add filter to pick up passthrough locations. • There is a lot of data, and the list will become unbearable without assistance. | [9 empty] | Build | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-31 | 0 | < 15 Days | hweller@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0758 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | Interface between XEUS and S4 for Cu/HM flag – new RICEFW | New RICEFW object requested; Interface between XEUS and S/4HANA to pull the user status of copper, heavy metal, or non-contaminated (CU/HM/NC) | This interface is required to facilitate the accurate identification of copper or heavy metal contaminated tools during maintenance processes | FS Date: 6/16 – 7/18 (Sprint 15) Once the CR is approved, schedule will be planned by Tech team. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0758-%20New%20Interface%20(console%20ID%202997)%20between%20XEUS%20and%20S4%20for%20Cu%20HM%20flag.pptx?d=wec20e1b081b84c5c8703a11682a6203d&csf=1&web=1&e=ixa6zo |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes | S4 | 1 | FTSI1527 |  | FTSI1527 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-06-05 | o This was identified during the passthrough discussions. Since the data is maintained in NES, this is a request to change the data source to XEUS. o AR: Update wording to reflect that the original source was EMS - @Hoover, JR o AR: Work with the EMS team to understand the updates that are required from their side - @Hoover, JR o AR: Size the effort in RICEFW intake meeting and include in the deck - @christopher.b.woodburn@intel.com | [9 empty] | Other | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-31 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0759 | Approved | Bringing back as there were questions as to why the new RICEFW would ping E2Open | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | Enhancement for Warranty claim Output for non E2O supplier – new RICEFW | New RICEFW object requested; Enhancement for Warranty Claim for Non E2Open Supplier | This is a new requirement not encompassed in the existing Interface. The business wants to track warranty claims of Suppliers who are unavailable in E2Open. The primary objective of this enhancement is to validate that the Supplier is available in E2Open. If the Supplier is unavailable, user will create a Zero $ PR and close the warranty claim. | FS Date: 7/21 – 8/15 (sprint 16) Build Date: 8/21 – 8/27 FUT Date: 9/10 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0759%20-%20New%20Enhancement%20(console%20ID%202998)%20Enhancement%20for%20Warranty%20claim%20output%20for%20non-E2Open%20suppliers.pptx?d=w8e018d53380643359f0f38a81800fa58&csf=1&web=1&e=j19ENO |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 86 |  |  |  |  | 0 | 86 | N/A | Yes | S4 | 1 | FTSE1528 |  | FTSE1528 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | o AR: Amend the description to include reasons for pinging E2Open - @Shim, Cari H | [9 empty] | Other | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-31 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0760 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | Update fields for E2Open Outbound Interface (Modification to FTSI0983) | Add Custom Fields for Outbound Interface to E2Open | This is a new requirement not encompassed in the existing Interface FTSI0983: SAP Warranty Claim Document to E2Open. The business will be required to capture & send more information to E2Open. The primary objective of this request is to add 3 more custom fields (Warranty Start date, Warranty End Date and Consumable flag for Part) in the mapping sheet along with the logic to send to E2Open, remove 1 of the existing custom field (Name of Supplier FSE) and update logic for the claim phase when a claim is under Part warranty. | FS Date: 7/18 Build Date: 7/24 – 7/31 FUT Date: 8/25 – 10/3 (no change) | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0760-%20Update%20fields%20for%20E2Open%20Outbound%20Interface%20(Modification%20to%20FTSI0983).pptx?d=wc789d6fd85524827b4f6a164393a1105&csf=1&web=1&e=EARi3q |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 76 | 0 | [8 empty] | 76 |  |  |  |  | 0 | 76 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0983 | 1 | FTSI0983 | 1 |  | 0 |  | 0 | N/A |  | 2025-09-25 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o AR: Include impacts and risks to E2Open once the work is taken on - @Vargas Lepiz, Jose | [9 empty] | Build | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-31 | 0 | < 15 Days | hweller@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0761 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | New Decision for Repaired Part from Supplier (Modification to FTSI0985) | Add Decision based on the valuation of the part being returned from the supplier | The primary objective of this request is to configure the decision codes and update the logic in the existing Interface FTSI0985: Claim Status Update from E2Open to S4 (Inbound Interface). With this change, the business will be required to capture the repaired valuation when a damaged part is repaired & returned by Supplier. | FS Date: 7/18 Build Date: 7/24 - 8/12 FUT Date: 8/25 -10/3 (no change) | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0761%20-%20New%20decision%20for%20repaired%20part%20from%20supplier%20(Modification%20to%20FTSI0985).pptx?d=w761c66823aac4a0fb745ee3a246e6607&csf=1&web=1&e=yJ5IpG |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 24 | 0 | [8 empty] | 24 |  |  |  |  | 0 | 24 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0985 | 1 | FTSI0985 | 1 |  | 0 |  | 0 | N/A |  | 2025-09-25 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o This modification will also pose a risk to the E2Open team as this request will change an interface. | [9 empty] | Build | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 05, 2025 | 2025-05-31 | 0 | < 15 Days | hweller@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0762 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Nisa Khatun | [11 empty] | IC customers extension for all sales areas. | R3 Intercompany (IC) customers extension for Sales areas to enable creation of IC Sales and Billing Document involved in R3. | IC Customers needs to be extended for relevant sales areas for Intercompany process in R3. This is a build change CR for including the master data extension in MC. The master data set is required to enable usage of IC plant within the sales order. Hence this master data extension is required. Need to ensure this task has been added in the mock cutover for R3. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR0762_IC%20customer%20to%20sales%20area%20extension%20for%20seamless%20IC%20processes%20involved%20in%20R3%20..pptx?d=w64e2380db4014c30aac92ce3e2fd8940&csf=1&web=1&e=zK6hkV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-02 | 310 | > 30 Days | nikhatun@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0764 | Approved |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 11. Technology | Jeet Bawra | [11 empty] | Split of TM tendering functionalities in granular RICEFW's | We have completed the R3 TM Functional specs covered in RICEFW IDs LOGE0625_IP/IF LOGE1197_IP/IF LOGE1196_IP/IF However, as each of the RICEFWs have several major functionalities within them, the tech team has split the big functionalities into granular more RICEFWs Hence raising this CR to add these new RICEFWs in the build plan | Granular RICEFW's needed to track the build of various TM tendering functionalities originally given under LOGE0625_IP/IF LOGE1197_IP/IF LOGE1196_IP/IF |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BA87461C4-D1A3-4F5E-BAFC-960A98B15012%7D&file=INT-CR0764%20-%20R3%20TM%20Tendering%20RICEFWs%20Split.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cgakumaresan%40deloitte.ca&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA1MDQwMTYyNCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  | LOGE1488_IP, LOGE1488_IF, LOGE1487_IP, LOGE1487_IF, LOGE1486_IP, LOGE1486_IF, LOGE1485_IP, LOGE1485_IF, LOGE1484_IP, LOGE1484_IF, LOGE1483_IP, LOGE1483_IF, LOGE1482_IP, LOGE1482_IF, LOGE1481_IP, LOGE1481_IF | 16 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1481_IF, LOGE1481_IP, LOGE1482_IF, LOGE1482_IP, LOGE1483_IF, LOGE1483_IP, LOGE1484_IF, LOGE1484_IP, LOGE1485_IF, LOGE1485_IP, LOGE1486_IF, LOGE1486_IP, LOGE1487_IF, LOGE1487_IP, LOGE1488_IF, LOGE1488_IP | 16 | LOGE1481_IF, LOGE1481_IP, LOGE1482_IF, LOGE1482_IP, LOGE1483_IF, LOGE1483_IP, LOGE1484_IF, LOGE1484_IP, LOGE1485_IF, LOGE1485_IP, LOGE1486_IF, LOGE1486_IP, LOGE1487_IF, LOGE1487_IP, LOGE1488_IF, LOGE1488_IP | 16 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | o This request is to split the parent RICEFW functionalities amongst the associated enhancements to better track build. • The functionality will be more granular and will be tested. | [9 empty] | Other | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-02 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0765 | Cancelled |  | ERP | R2 (Release 2) | [21 empty] | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 06, 2025 | 2025-06-03 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0766 | Cancelled |  | ERP | R2 (Release 2) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Fabian Castro |  | FPR - Aubrey Hinderlider | [9 empty] | Custom Fiori App for access to FTXA and SE16N | Custom Fiori App for Indirect Tax Analyst Role’s Access to 2 T-codes below: FTXA SE16N | Per Intel’s policy, a custom Fiori app is needed if the request is asking for access to less than 5 tables in SE16N (we are asking for access to table T007A and /IDT/D_TAX_DATA). |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  | 1 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Rose Pham that this was a JIRA issue that has been resolved. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-03 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0767 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 07. FTS IF 08. FTS IP 17. B-App | Priti C Shah | [11 empty] | Remove Intel Demo Depot/DES Bapp (8902) Interface with S4 ISM from Project Scope | Remove from scope the planned interface between boundary app "8902 Intel Demo Depot" and S4/ISM. This includes the cancellation of the following 2 object IDs in the B-App R3 S4 Object Tracker: LOGI1073_IF & LOGI1073_IP | Intel Demo Depot is SMG owned BApp and the ISM integration is a low priority for SMG; Intel Demo Depot did not commit to ISM integration in 2025 from the start. ISM planned to develop the API in IAO scope and listed IDD as a partner, as IDD is the sole user of this API currently. API planned to be generic and potential use by any Intel BU in future. Reqts are still being flushed and there are resource constraints to hit R3 build by EOY. Intel Demo Depot will use ISM Fiori UI app and create shipments manually post R3. S4/ISM automatic integration/interface need will be assessed post IAO. It has been confirmed with the ISM team that removal of this integration from IAO does not impact ISM IAO timeline. SMG Leadership is also aligned. https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EYJM-5gXCWxHludt5w2iazQBJEACC6DXKVn7qPtSmwIrZw?e=rRpPLy |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0767/EXT%20Re%20Offline%20GPO%20approval%20obtained%20for%20removal%20of%20Intel%20Demo%20Depot%20BApp%20-%20S4ISM%20RICEFWs%20-%20LOGI1073_IF%20%20LOGI1073_IP.msg?csf=1&web=1&e=nX9kJh |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Lopa to be cancelled | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 06, 2025 | 2025-06-03 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0768 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP 10. Analytics 17. B-App | rafael.a.finol.soto@intel.com |  | PTP - Richard Taylor | [9 empty] | Request to Pull In 2 PTP ECA Views | LOGV001_PTPX: Current ETA is 10/10. FPRXV193: Current ETA is 11/07. Both views are scheduled to get completed after October by ECA team. Request to pull them in so it does not delay development until after 2025. B Apps need views provided by 8/29. | If objects are provided as per the current schedule, B Apps team will not be able to complete their Build by 12/31/2025. 6/6: Objects linked to this request are required for a consignment report where will not represent significant impact if tested after Sept 30th, deadline for Critical B Apps. Dev can be ready before ITC so no need to pull in ECA views |  | No |  |  |  |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-03 | 309 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0769 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 09A. Master Data 09B. Data Migration 15. Cutover | Karthik Reddy Reddy | [11 empty] | Change Request for Intel Products Production order conversion (for Ext OSATs) – FTSC0434 | Change Request for Intel Products Production order conversion (for Ext OSATs) – FTSC0434 | Currently this conversion only handles one used case – Conversion of Open Scheduling Agreements into production orders Need to incorporate two more Used cases for Ext. OSATs as part of this conversion. Conversion of Open Engineering orders into production orders Conversion of Open Rework Purchase orders into rework production orders |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0769-%20Production%20order%20conversion%20-FTSC0434.pptx?d=w84581a3ef347417e9e49e7d82a37e93a&csf=1&web=1&e=HdP1Yt |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 50 | 0 | [10 empty] | 50 |  |  | 0 | 50 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSC0434 | 1 | FTSC0434 | 1 |  | 0 |  | 0 | N/A |  | 2025-12-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | o FS to be replanned to finish Sprint 15 | [9 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-03 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0770 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology 15. Cutover | Karthik Reddy Reddy | [11 empty] | Conversion of Open PO/Engineering/Rework Orders into Production orders from IF to IP. | Conversion of Open PO/Engineering/Rework Orders into Production orders from IF to IP. | Need to incorporate Used cases for Intel Foundry as part of this conversion. a) Conversion of Open Purchase orders into production orders b) Conversion of Open Zero Dollar Purchase Orders into production orders c) Conversion of Open Engineering orders into production orders d) Conversion of Open Rework Purchase orders into rework production orders |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0770%20%E2%80%93Change%20Request%20for%20New%20RICEFW%20Conversion%20of%20Production%20Orders%20from%20Intel%20Foundry.pptx?d=w21b56bd4766047afb9267f19d6a231a0&csf=1&web=1&e=M2aNpL | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | Very High | 0 | 4 | [10 empty] | 72 |  |  | 0 | 72 | N/A | Yes | S4 | 1 | FTSC1559 |  | FTSC1559 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | Will need to go through RICEFW intake | [9 empty] | Other | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-03 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR0771 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | amitkumar55@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | Cancellation of Object: FPRE0891_IP-Split from primary Cost centers to PCOS & R&D/OCOS | Cancellation of Object: FPRE0891_IP-Split from primary Cost centers to PCOS & R&D/OCOS | After ironing out the details between Team 11 and other teams, the PCOS/OCOS split topic was found to only be relevant to the IF design, not IP. The original creation of this IP object was in-essence an insurance policy as we worked through the design in case we needed these processes in the IP environment as well. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0771/Approved_%20Cancellation%20of%20object%20__%20FPRE0891_IP-Split%20from%20primary%20Cost%20centers%20to%20PCOS%20%26%20R%26D_OCOS%20__%20CR%20Number_%20INT-CR0771.msg?csf=1&web=1&e=gkk6yT |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0891_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0772 | Approved | Presenter: Debranjan Das | ERP | R3 (Release 3) |  | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 11. Technology 17. B-App | junior.milan@intel.com |  | OTC IF - Angela Laskowski | [9 empty] | Sales Order ASN for IP as a customer | Customer ASN (LOGI0612_IF) needs to incorporate additional attributes required by IP as a customer | Post R3 release, IP will be treated as external customer to IF. IP requires Advanced Shipping notification to be sent when sales order is complete. The signal is critical for IP to close purchase order, allow payment and track inventory in-transit. IP needs specific attributes such as: secondary lot number, manufacturing dates, countries of diffusion/WLA/assembly, etc to be included into ASN to keep IP inventory records up to date. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0772_IF_R3%20Customer%20ASN.pptx?d=w216fa13ef4aa4ef89a054136bd1a50f8&csf=1&web=1&e=b86Sbs |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | Medium | 2 | [8 empty] | 80 |  |  |  |  | 0 | 80 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0612_IF | 1 | LOGI0612_IF | 1 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | o IP will be treated as a customer from IF perspective, and additional fields are identified to require to be sent out to IP. o The impacted RICEFW is already live in R2, and the changes to the R2 object is required for R3. o AR: Include OpenText effort @Das, Debranjan o AR: Update tech effort to 80 hours - @Das, Debranjan | [9 empty] | Build | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 06, 2025 | 2025-06-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0773 | Approved |  | ERP | R3 (Release 3) |  | 05. OTC IP | 4.11 OTC IF - Order Management |  |  | Vinayak Prabhu | [11 empty] | Requirement is to convert standard S4 error & warning messages into 80 WOM custom messages. | Requirement is to convert standard S4 error & warning messages into 80 WOM custom messages. | WOM users will not have visibility to check custom error which is mapped to the standard S4 error messages in WOM portal. Hence, an interface is required to send the custom error messages to WOM from S4 IP system via Middle ware. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B63C347C3-12CF-4DB7-9F97-9CCE812020FE%7D&file=INT-INT-CR0773_OTC%20IP_CR%20Deck.pptx&wdOB=B029061B6B564F1DBBB718E579F9052C&action=edit&mobileredirect=true&previoussessionid=7fbc3131-dfd9-041b-62fd-f159e9801dd6 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 30 | [5 empty] | 35 |  |  |  |  | 0 | 35 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0413, OTCI0037, OTCI0061 | 3 | OTCI0413, OTCI0037, OTCI0061 | 3 |  | 0 |  | 0 |  |  | 2026-04-17 | 0 | 04. Tower/Horizontal Approved (end status) | [12 empty] | Cancelled as tech effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-04 | 0 | < 15 Days | vinayprabhu@deloitte.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
R2 (Aug 2025) | R2 | INT-CR0774 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF |  |  | 04. OTC IF 06. PTP 07. FTS IF 10. Analytics | meenakshi lawrence |  |  |  | CR0914 | [7 empty] | Legal Requirement for compliance with changing International Trade laws | Tariff Rule changes for Country Of Origin (COO), New compute/Functional die determination logic to be followed. Impacts Rule engine configurations for COO determination, Shipping documents – Commercial Invoice, Packing List, IPLA– Itemized Packing List, Shipping Label, IBox Label, Reports, b2b Rnet PIP’s, COO validations across internal/external manufacturing - Finished Goods, Semi-finished Goods, Direct Materials.. – See more details in foil 4 | Compliance and quick response to changing cross-border Trade rules. Recently China customs announcing a new Rule 58 for Tariffs, impacting all shipments to China and from China. ITG confirmed (1) fabrication country as Country Of Origin (COO) for integrated circuits (instead of Assembly country) for imports into China (2) New Logic for determination of Functional / Compute Die (3) New Label formats for MBB, iBox, Shipping Labels. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0774_OTC_R2_Country%20Of%20Origin%20COO.pptx?d=w0d91ffaaa49448f882f55c57cb59cf30&csf=1&web=1&e=Qhx8dj |  | 1. Process Scope / Design Change |  |  | High | 50 | 3 | [8 empty] | 50 |  |  |  |  | 0 | 50 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-12 | Will need to go through CR Meeting |  |  | 2025-06-13 | Analyses has been completed, and CR0914 was created and approved offline by Uzma to go forward with the work | [5 empty] | Design | CL/OSC | 2025-06-13 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-04 | 0 | < 15 Days | meenakshi.lawrence@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0775 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Rekha Bhat | [11 empty] | Add - Freight type (shipping condition mapping) and new create new custom table. Add - CPN item mapping that is coming from SF customer material number in line item. Remove - RTC Tzone and Collection Tzone field. | Add - Freight type (shipping condition mapping) and new create new custom table. Add - CPN item mapping that is coming from SF customer material number in line item. Remove - RTC Tzone and Collection Tzone field. | Add - Freight type (shipping condition mapping) and new create new custom table. Add - CPN item mapping that is coming from SF customer material number in line item. Remove - RTC Tzone and Collection Tzone field. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 18 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as per Sarah Miller | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-04 | 0 | < 15 Days | pranjayadav@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0776 | Cancelled | To be moved to the Build CR Log | ERP | R3 (Release 3) |  | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Print Ship To- PO in Packing List | Currently, customers can enter a "Ship to Party PO" during the order creation process. However, the Ship-to PO # is not printed on the packing list in S4, unlike ECC. This CR aims to enable the printing of "Ship-to Party PO" on packing lists in S4, thereby maintaining consistency with ECC and meeting customer expectations. | Standard considers the Sold-To PO number in PL even though both Sold-To and Ship-To POs exist (Refer to Slide 3 for details). | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0776_OTC%20IP_CR%20Ship-To%20PO%20in%20PL.pptx?d=wbc7d44a4421a444eb506e8e23e9bad7e&csf=1&web=1&e=1XkYkz |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 8 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Debranjan Das to be cancelled as the tech effort is only 8 hours, which is less than the 40 hour threshold | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0777 | Approved |  | ERP | R3 (Release 3) |  | 10. Analytics | 10.1 Analytics - ALL |  | 03. FPR 05. OTC IP 11. Technology | indrsingh@deloitte.com |  | Data - Julie Fawdington | [9 empty] | R3 Additional Scope ECA - NRT Reports | The development of Near Real Time (NRT) reports will transition from the eHANA/Sidecar platform to ECA. To facilitate this move and enhance overall efficiency, a dedicated speed layer will be implemented within ECA, resulting in significant gains in both development and ongoing support. | R3 reports will be built in ECA Speed Layer and not in SideCar. | - | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-%20CR0777_%20R3%20Additional%20Scope%20ECA%20-%20NRT%20Reports.pptx?d=wb23cb9fe58824b74a7f2535c4a1fc1dc&csf=1&web=1&e=hVfPZL | New Requirement / Scope | 1. Process Scope / Design Change |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-05 | Approved in ad hoc meeting | [9 empty] | Design | Tower | 2025-06-05 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR0778 | Approved |  | ERP | R2 Hypercare | High | 13. Security | 13.1 Security - ALL |  | 04. OTC IF 13. Security | Natasha Laramie | [6 empty] | INC14842867 | Work In Progress |  |  |  | Security Grouping and Role Changes in GTS system for R2 | To accommodate the final list of Fiori App grouping and Role mapping from Intel Business team, we will need to do a config/setup change in the system | During UAT1 the testers experienced several gaps of not having access to key transactions to perform daily jobs. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR%200778%20Security%20Grouping%20and%20Role%20Changes%20in%20GTS%20system%20for%20R2.pptx?d=w70fe999505304904862bc68f1a26e5d7&csf=1&web=1&e=CUFTx3 |  | 6. Build Security-Related Changes |  |  |  | 30 | 0 | [11 empty] | 30 |  | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-17 | o The GTS team has 5 roles that will be used after go-live, and there is a request to add additional transactions for the security roles. o This CR will be delivered right after R2 go-live during Hypercare. o AR: Create a bug/defect that will remain open until Hypercare | [9 empty] | Build | Tower | 2025-07-17 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-05 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0779 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Low | 06. PTP | 6.10 PTP - Boundary Apps |  | 10. Analytics | Shweta V Aurangabadkar | [11 empty] | Request to add new ECA object (s) for ILM FOAM BApp (CF Misco) | Need to create a new view in ECA for the ILM FOAM B-app to be able to access the Inspection plan Data | S4 Quality Module will allow Intel to segregate materials of concern and document the decision process for use. ILM FOAM is the POR system for material excursions which will trigger QM activation. The Quality Module (QM) activation is use-case driven and is activated by the signals from the business including quality, stability, and readiness. Inspection needs are derived from severity of excursions scenarios. QM activation will be simplified with automated/integrated solution b/w ILM, MDG and S4. Will need to trigger the QM activation using the inspection plan data. Inspection plan is new data from the Quality Management (QM) module from a PTP . This QM module was recently added to PTP, and scope/demand was not captured by the BApp earlier in the BApp-ECA Tracker https://intel.sharepoint.com/:p:/s/inteldeloitteiao/ERjAEZ4vcKlJqtMFuvNxe4QB_v5TFCNCyquU4Jr8UPdyxA?e=iGrXqU | ILM FOAM will not meet 12/31/2025 Development due date. New ETA to be identified. | No |  | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/ERjAEZ4vcKlJqtMFuvNxe4QB_v5TFCNCyquU4Jr8UPdyxA?e=iGrXqU |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Sri Hari Kothanoor that this was cancelled in August | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-05 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0780 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration | Tanmaya H J |  | PTP - Richard Taylor | [9 empty] | PTPC0176_IP_IF_Logic addition/change for PO conversion | PTPC0176_IP_IF_Logic addition/change for PO conversion | 1. In S4 for STO related to ODM, vendor material number will be in 6 digit format which is different from ECC value 2. Extraction of field values from RESB is required to get components details for Subcon PO with doc type ZNB in ECC purchase order scenario 3. Multiple PO is converted to single PO in S4 with doc type ZNB based on delivery date, material, storage location and plant 4. Transform std Rework PO to Subcon Rework PO 5. Converting Single PO into return PO and replacement PO from ECC to S4 system in WIINGS scenario 6. To extract MMID from non MMID POs to convert it into POs with MMID in S4 7. Converting STO into external std PO in SIMS scenario. 8. To convert construction PO with network into Construction PO with WBS Element |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B07705C6B-897F-426F-9F8C-C75BB255B248%7D&file=INT-CR0780.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 135 | 0 | [10 empty] | 135 |  |  | 0 | 135 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPC0176_IP, PTPC0176_IF | 2 | PTPC0176_IP, PTPC0176_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-12-26 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | o This is related to the inventory conversion open design. • There is no change for scheduling agreements as everything is captured. o Technical work is done by the BODS team. | [9 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-05 | 0 | < 15 Days | thj@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0781 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R2 (Release 2) |  | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 08. FTS IP 10. Analytics 17. B-App 18. SCP | elena.kaufman@intel.com |  | FTS IP - Loni Adams | [9 empty] | Plan sort-out wafer purchases in BY IBP | In UAT1 it was discovered that both OneMPS and BY IBP are planning a subset of products. These are unique in that they do not have a fab part on the SPEED BOM and appear as Sort only products (Examples: Carlsville, Linkville, Gothic Bridge). In today’s environment, these would be treated as OSAT purchases and the OneMPS team reacted accordingly. Subsequently, the determination was made that these are initial wafer purchases that belong in BY IBP. Change is to remove these from planning in OneMPS which requires changes to both SPAN and OneMPS. | Ensure that only one planning system is generating requirements for this set of products | SPAN team will have to comment on details | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CRXXXXX-Wafer%20purchases%20to%20plan%20in%20BY.pptx?d=w5bd1af2d110641e78f145650950c79f6&csf=1&web=1&e=8fT8bf |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Duplicate of CR0847 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0782 | Approved |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 10.1 Analytics - ALL |  | 10. Analytics | Leah Orzechowski | [11 empty] | Addition of new data products object in ECA tracker | Addition of new objects into the ECA tracker that ECA team has newly identified as additional data products for build. |  |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/Analytics/INT-CR0782_Analytics Sprint 15 FPR Objects_CR Deck.pptx?d=w1b138faf2c7145f2a8aaf5b109a13a55&csf=1&web=1&e=h30HpB |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-17 | Approved in Offline email to Uzma | [9 empty] | Other | Tower | 2025-06-17 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | lorzechowski@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0783 | Approved | Will need to go to CR Meeting | SCP | R2 (Release 2) |  | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP 10. Analytics | erin.irby@intel.com |  | FTS IP - Loni Adams | [9 empty] | Measures with Billing enhancement | Modify the “Measures with Bill” calculation in the ECA reporting layer to align with the Live Measure (CD Draft, TopsDown Draft, BottomsUp Draft) submitted in the UI for the current quarter. | The current quarter total is inconsistent between the Live Draft measure in the CDP UI versus Measures with Bill in the Reporting Cube. | No capacity to start until WW26. Some R2 scope (DQ reports) will be pushed further out. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20CR%20CD%20Draft%20Qty%20w%20Bill,%20CD%20Pub%20Amt%20w%20Bill,%20CD%20Draft%20Amt%20w%20Bill%20enhancement.pptx?d=w140724b52f2546429bdc76860eb68f54&csf=1&web=1&e=HlJ388 |  | 2. New RICEFW / ECA / Build Object |  |  | Very High |  | 4 |  |  |  | 0 | 0 | 100 | 240 | [6 empty] | 340 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | Will need to go through CR Meeting | [9 empty] | Other | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | brian.staab@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0784 | New |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | erin.irby@intel.com | [11 empty] | Update formula for existing calculated measures in CDP | Update formula for existing calculated measures in CDP?Data Measures(R2).xlsx - under "Calculated Measures" tab | Formulas have to be updated based on business’s expectation. Targeting post R2 go live. | No impact if started after WW23 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20Update%20formula%20for%20existing%20calculated%20measures%20in%20CDP.pptx?d=w5f089d6ec26c4e0c89c3060fc81acab2&csf=1&web=1&e=DmW9SR |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [5 empty] | 160 | [7 empty] | 160 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-06 | 306 | > 30 Days | brian.staab@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0785 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | LOGE1217 needs to be dropped. | LOGE1217 - Storage Bin Population and Batch Determination based on RMA from Ship Item Screen needs to be dropped. It can be covered under LOGE1221. | LOGE1217 needs to be dropped. It can be covered under LOGE1221 - Custom Fiori screen to capture shipping details and start the shipping process.. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0785/EXT%20RE%20Help%20Needed-Approval%20on%20CR0785%20.msg?csf=1&web=1&e=7PkYYR |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1217 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0786 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Surendra Kusumuru | [11 empty] | PTPE0365_IF DPAS enhancement IF object descope | PTPE0365_IF DPAS enhancement IF object descope , since no code development is required from the PTP side (such as CDS logic or OSAT PR code). | As recommended by Technical team, we have aligned with business(Ron) to remove (descope) this IF object from the object tracker, since no code development is required from the PTP side (such as CDS logic or OSAT PR code). Consequently, also aligned to include test cases within the FTS-dependent object to ensure that the DPAS value is retrieved from PDH (BY) and the PR is updated in S/4. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0786/RE%20PTPE0365_IF%20DPAS%20enhancement%20object%20descope%20Require%20PMO%20approval.msg?csf=1&web=1&e=ZHg3xw |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE0365_IF |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | surensurendra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0787 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns | [14 empty] | Requirement to change to develop logic for SubLineClosed, LineAutoClosed and AutoClosed |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by OTC team to not be required as the effort is less than 40 hours of effort. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-06 | 0 | < 15 Days | rekbhat@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0788 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Rekha Bhat | [11 empty] | Development of SubLineClosed, LineAutoClosed, AutoClosed | Need to development for the additional logic updated in the FS for 1. SubLineClosed 2. LineAutoClosed 3. AutoClosed | Need to development for the additional logic updated in the FS for 1. SubLineClosed 2. LineAutoClosed 3. AutoClosed |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0788_OTC%20IP%20%20Addition%20of%20Auto%20Closure.pptx?d=w387d038e1d0e4c14a872228642409d81&csf=1&web=1&e=dJQZYr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 27 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by OTC team to be less than 40 hours of effort. Build CR has been created. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-06 | 0 | < 15 Days | rekbhat@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0789 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP | ahingne@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of RICEFW LOGI1073_IF AND LOGI1073_IP | Descoping ISM-DES Integration | Based on the internal discussion from IDD (DES), DES is out of IAO scope totally | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0789/EXT%20RE%20Request%20for%20cancellation%20of%20LOGI1073_IFLOGI1073_IP.msg?csf=1&web=1&e=rzCgnB |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1073_IF, LOGI1073_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0790 | Approved | Added | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns | Yes | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Addition of Decoder custom table and to change existing EEPM customer table to BRF+ table | Addition of Decoder Matrix and EEPM table | EEPM: The EEPM Rule will used for Entitlement Check process. EPPM matrix determines Warranty period and Credit period of ULT based on parameters like Service type, Return Reason, Customer, Sales Organization, Product family, material Id etc. Without this table, it would be tough to determine entitlement criteria. Decoder Matrix: When the ULT is not from any of the source system(CATTS, EMS, Syntrax)Decoder matrix determines position of relevant characters to derive a ULT Build Date (Base warranty Start date). |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0790_OTC%20IP%20%20To%20add%20Decoder%20custom%20table%20and%20to%20change%20existing%20EEPM%20customer%20table%20to%20BRF+%20table.pptx?d=w0d4d45a481144a1ebc951d912c20285c&csf=1&web=1&e=MKsAym |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 44 | 0 | [8 empty] | 44 |  | 44 |  |  | 0 | 88 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0404 | 1 | OTCE0404 | 1 |  | 0 |  | 0 | N/A |  | 2025-11-28 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-31 | o This is a request to add 2 new business rules to the enhancement. • This is to store the data, and the new interface from CR0906 is to extract | [9 empty] | Build | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-06 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0791 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology 17. B-App | YASH DESHPANDE |  | PTP - Richard Taylor | [6 empty] | 19569 | SAP Ariba Cloud |  | PTPI0735_IP_IF - Ariba/Capital PO details to be retrieved from SAP S/4 at the time of receiving in WIINGS - New custom fields need to added. | PTPI0735_IP_IF - Ariba/Capital PO details to be retrieved from SAP S/4 at the time of receiving in WIINGS - Requires custom fields to added in the FSD as per business requirement. | For FSD PTPI0735 it is aligned with business to shift from standard API to Custom API since there are few custom fields which are required in the PO retrieval process. To GET the critical PO details from S4. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B021856A1-81FA-4B01-B4B3-047F941BEDCC%7D&file=INT-CR0791.pptx&wdLOR=c5432FB9B-C1B6-4C1E-8117-5C6AB0177787&action=edit&mobileredirect=true&previoussessionid=933e4587-13b1-b54b-de9b-50472b863eb2&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA1MTgwMDIxOSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 59 | 0 | [8 empty] | 59 |  |  |  |  | 0 | 59 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0735_IP, PTPI0735_IF | 2 | PTPI0735_IP, PTPI0735_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-10-31 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o Changing approach from standard API to custom API because the team has identified additional fields that are required • When the interface was created, the WIINGS design continued. So, this is a request to update the built interfaces. | [9 empty] | Build | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-09 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0792 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | [12 empty] | Change request to align on descoping the CHM object OTCI0738, OTCI0845 and OTCI0846 as the required functionality does not require any additional Interface development and could be handled by RFC connection between S/4 and CHM | Interface the Customer master data , Material master data and Pricing condition records to CHM and S/4 | Change request to align on descoping the CHM object OTCI0738, OTCI0845 and OTCI0846 |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0792?csf=1&web=1&e=jrT8Jf |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0738, OTCI0845, OTCI0846 |  |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-11 | [10 empty] | Other | Tower | 2025-06-11 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-09 | 0 | < 15 Days | mmeti@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0793 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | dikotha@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | Incorporate WIP Inventory into Reserves Calculation | Incorporate WIP Inventory and Value along with regular Inventory and Cost for Reserves Calculation in both IP and IF instances | WIP Inventory logic was missed initially which we wanted to incorporate now in Reserves Calculation | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0793%20%E2%80%93%20Incorporate%20WIP%20Inventory%20into%20Reserves%20Calculation.pptx?d=w4d71317a9c59425a8101a8798ea94510&csf=1&web=1&e=ce21DB | New Requirement / Scope | 3. Configuration Change |  |  |  | 0 | 0 | [7 empty] | 40 | [5 empty] | 0 | 40 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-11 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | [10 empty] | Other | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0794 | Approved | Presenter: Prabesh, Rose | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | lam thi kim hanh |  | FPR - Aubrey Hinderlider |  | INT-CR0661 | [7 empty] | Reinstate ECA object FPRXV154 and split it into two objects for Vietnam’s Capital Tool Report and Service Revenue Report | Originally, FPRXV154 was an ECA object including both Vietnam’s Capital Tool Report and Service Revenue Report. On 5/12/2025: A new RICEFW object was raised because the Service Revenue Report was deemed to be a Fiori app tile that needed to be developed. It was pushed back during review with leadership team because it is supposed to be developed as an ECA report first. Hence the RICEFW is now inactive. After further analysis performed by Analytics team, it is concluded that both Capital Tool Report and Service Revenue Report can be developed as ECA reports, though they need to be 2 separate ECA objects. Hence, this CR is raised to reinstate the FPRXV154 object for the Capital Tool Report and add another ECA object for the Service Revenue Report. | The original object FPRXV154 for Vietnam Customized Reports was for both Capital Tool Report and Service Revenue Report. Given the difference in the reports’ build dependency, they need to be split into 2 different ECA objects. Hence, this CR is raised to reinstate FPRXV154 as object for Capital Tool Report, and add another ECA object for Service Revenue Report. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0794_Reinstate%20ECA%20object%20FPRXV154%20and%20split%20it%20into%20two%20objects%20for%20Vietnam%E2%80%99s%20Capital%20Tool%20Report%20and%20Service%20Revenue%20Report.pptx?d=w0b157a287d624c728518032df1d3c23f&csf=1&web=1&e=GAl8zr |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-09 | o The original ECA report was cancelled because FPR thought that the S4 report would work.  However, it did not.  Therefore, this CR is to re-instate the ECA report. o AR: Forward approval email from Sunil to Uzma - @Tam, Anna | [9 empty] | Other | Tower | 2025-10-09 | 10, 2025 | 10, 2025 | 06, 2025 | 2025-06-10 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0795 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data | Harshavardhan Harshavardhan | [11 empty] | DATE0667_CFIN & DATE0667_IF - Customizing Technode or stage field in S/4 FIori Apps in CFIN & IF system | Technode Filed should be in S/4 Fiori App in both CFIN & IF System | As this is a new add on requirement while reviewing FS with the business |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 302 | > 30 Days | harshaharshavardh@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0796 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Addition of NCNR Rules Table | The NCNR matrix is designed to manage materials that cannot be cancelled or returned, ensuring compliance with business rules and contractual obligations. | The NCNR rules table should be added in this interface as well. Ideally we should be checking the NCNR flag on the actual sales order the return is being processed for. But if that’s not technically feasible, this rules table should be included in the interface so the logic can be replicated. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0796_%20OTC%20IP%20%E2%80%93%20Addition%20of%20NCNR%20Rules%20Table.pptx?d=w4abfd7db4e454f659ac32218dbc663aa&csf=1&web=1&e=HeyLqV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelling as the technical effort is less than 40 hours. Team has been instructed to log into Build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0797 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Addition of "Row Number" field | Addition of "Row Number" field | There are Many validations in SAP Webdynpro for each matrix, such us duplicate check, error handling (bulk upload displaying the error with Row Numbers) etc. If we are not adding the Row number field now, it will impact the error handling when user uploads bulk rules in Portal. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0797_OTC%20IP%20%20Addition%20of%20Row%20Number%20field.pptx?d=wdfe8397d63654238a7f54aa281deb477&csf=1&web=1&e=R8Qoec |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by OTC team to be less than 40 hours of tech effort. Build CR has been created. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0798 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP | Ketul Ashokkumar Pitroda | [11 empty] | SCTRE Constant Feed from S4 to Dbaas for COO Data | Change request to “LOGI0842_IP - Interface from SAP S4 to DBaaS to Fetch Actual COF for FVR batch and COA for AVR batch.” Request for a constant feed from SAP S4 & ECA/S4 to Dbaas when a DN is created as well as anytime there is an update back to the DN. (Previous RICEF included only the requirement of S4 data flowing to ECA)/DBaaS. | Changes being requested by OTC IP team are required for Dbaas system to be able to do the transformations and send back COO data. COO data required for SCTRE Bapp to assign COx with the intention of minimalizing tariffs. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/INT-CR0798_OTC%20IP_SCTRE%20CR%20Rev%2001%20.pptx?d=wec540fe7ea854398886eb921ef50a52c&csf=1&web=1&e=AUpodw |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 32 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the tech effort is less than 40 hours. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | kpitroda@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0799 | Approved | Following up with Venkatesh and Nikhil on reasons why | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | njain42@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSI1322,FTSM001 | Request the cancellation of Object FTSI1322 : M-100-170_API 8 is for ‘UNSCHEDULE’ Manual Ship (SS): FTSM001: Manual conversion object for PV not required | FTSI1322:Ship server does not required a change to lot status which is the purpose of this interface, Because SS not changing the status hence we no need to request to change back FTSM001: Standard program to create PV standard ones, Enhancement will create PV for Rescreen, hence manual conversion object not required |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/EXT%20Re%20Descope%20FTSI1322FTSM001.msg?csf=1&web=1&e=5p9X00 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1322, FTSM001 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-25 | [10 empty] | Other | Tower | 2025-06-25 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0800 | Cancelled |  | ERP | R3 (Release 3) | Very High | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | sukhwinder.ranu@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | CR To be marked as Cancelled - Reinstate AR reports and Deloitte will do E2E View and visualization in PBI | To be Cancelled - CR requested by Sunil to reinstate AR repots to be developed by Deloitte E2E | To be Cancelled - E2E Business process was not able to be satisfied by DARC | Deloitte will be impacted by additional build | Yes |  | Asked to be cancelled in Smartsheet | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EUhA9g7uGMlLmBh8tGYplsQB_ySyjt-hyt5_RzNE3EyhlQ?CID=7D249562-3F68-4771-A10F-03C48F2D12F4&wdLOR=cE3D44ADB-9444-4BE4-BF2F-BEFDB461D0CE |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0801 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | [12 empty] | OTCI0291 - Outbound Interface changes to send data from S4 to SF. | Changed and updated fields needs to be share with SF. TM fields will be shared with SF once freight order is created or any changes made in carrier details. Also, to share the updated events with SF custom table and custom program will be required to check the for the change field values and share with the SF. |  | Deloitte will be impacted by additional build | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0801%20OTC%20IP%20%E2%80%93%20OTCI0291%20-%20Outbound%20Interface%20changes%20to%20send%20data%20from%20S4%20to%20SF.pptx?d=w185b8e1de2be4f5299f40a0dfd5b1c81&csf=1&web=1&e=9YQVZD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelling as the technical effort is less than 40 hours. Team has been instructed to log into Build CR log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | sbharathalkude@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0802 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 04. OTC IF 05. OTC IP | sukhwinder.ranu@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Change Ownership of AR reports from OTC to FPR | Due to the nature of the OTC AR reports the expertise lies with FPR so the business is requesting that the ownership move from OTC and move to FPR | Simplification of build process | Needs to be managed by Deloitte Analytics | Yes |  |  | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/Eey7bNVw4U1Mg2Ct_U2hlmsBKXFrbJ4pHNj50cvfhKCUSA?CID=D758ED87-6084-4E7F-A56F-A1FAACAA7D37&wdLOR=cC45314A4-331E-4204-8168-11EF29CE8A52 |  | 14. Other Resource Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-24 | Does not require PMO approval. FPR team has approved, and they are the new owners of OTC objects. | [9 empty] | Other | Tower | 2025-06-24 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0803 | New |  | ERP | R3 (Release 3) | Low | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 02. E2E Process Integration 09A. Master Data 09B. Data Migration | Shradhashree Nayak | [11 empty] | Position ID mapping | Position ID mapping | Change in extraction criteria |  | No |  |  |  |  | 7. Non-Build Data Conversion Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 302 | > 30 Days | shranayak@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0804 | Cancelled |  | ERP | R3 (Release 3) | Low | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 02. E2E Process Integration 09A. Master Data | Shradhashree Nayak | [11 empty] | Position ID mapping | Position ID mapping | Change in extraction criteria |  | No |  |  |  |  | 7. Non-Build Data Conversion Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR0803 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-10 | 0 | < 15 Days | shranayak@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0805 | New |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 02. E2E Process Integration 06. PTP 07. FTS IF 09A. Master Data | christopher.j.martin@intel.com |  | FTS IF - Haritha Komma | [9 empty] | R3 EWM S.Loc Add/Deletes resulting from other approved CRs | As changes such as the GXO Huffman EWM decision, a new warehouse planned for construction in Chandler, updates to customer bailment segregation, expectation of MES not being modified for Raw Silicon batch mgmt, and the introduction of new Heavy Metals segregation within the factory network, we must now adapt the S.Loc structure for R3 sites to fit these decisions. | Alignment with other approved CRs, business process updates, | Impact in the process of being quantified | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-11 | 301 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0806 | Approved |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Taposh Ganguli | [11 empty] | New WRICEF console creation associated with FERT to HALB conversion for OM team to update existing SO and CMIR | New WRICEF console creation associated with FERT to HALB conversion for OM team to update existing SO and CMIR | Existing SO/CMIR with FERT lines to be updated with HALB lines as a part of the FERT to HALB conversion |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0806%20New%20WRICEF%20Console%20%20FERT%20to%20HALB%20conversion.pptx?d=w84d79f6ebff547ae951d4735f527ff7f&csf=1&web=1&e=QLBEq5 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [10 empty] | 122 |  |  | 0 | 122 | N/A | Yes | S4 | 2 | OTCE1558, OTCE1557 |  | OTCE1558, OTCE1557 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | Will need to go through RICEFW intake | [9 empty] | Other | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | tganguli@deloitte.ca |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0807 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | SGP New RICEFWs Change Request | New objects are identified coming from SGP for inventory status and reservation status(order status) | As part of the this Change Request, 1. new RICEFWs will be created for interfaces from SGP to S4 with Inventory status and 2. RICEFWs will be changed for interfaces from SGP to S4 with Reservation status - this will be included in reservation create interface. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0807/Re%20CR%20807%20to%20get%20Si%20Stock%20Status%20for%20SGP.msg?csf=1&web=1&e=qvbUbA | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Interface/INT-CR0807_FTS-IF_NEW%20RICEFWs%20Change%20Request.pptx?d=w2980f2d10105409a9efedbd3ab56e837&csf=1&web=1&e=9NeZwz |  | 2. New RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 168 |  |  |  |  | 0 | 168 | N/A | Yes | S4 | 1 | FTSI1602 |  | FTSI1602 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o The BApp owners wanted a real-time API call for the inventory status o AR: Include what issues the latency (1 hour) of the ECA call will cause for the Business – Eugene Celis, Rudra Sengupta  Include Stef, Kelly, and Chris in correspondence | 2025-08-19 | Approved in offline email; Chris and Keerti confirmed that 2 RICEFW's can be accommodated for R3 ITC1. Approval email linked | [7 empty] | Other | Tower | 2025-08-19 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | hbornare@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0808 | Approved | Logistics Team | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Siddharth Asitkumar Desai | [11 empty] | LOGI0267- From DUNS will be added. From DUNS number sent from Opentext also Fab_LOT number field should be added LOGI0953 -Logic to fetch From DUNS number to AS2 header and a logic to determine condition to Output and IDOC from S/4 side. | An additional field From DUNS will be added. The DUNS number, which is provided as open text, will be captured in the S/4 item text field for non-valuated purchase orders (POs). and interface name will be added as our reference field. | Require to capture IP Duns number so that once GR posted IDOC generated with IP Duns number and send to OpenText from IF system. In this way system call the right path to opentext |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0808_PTP_LE-%20FromDuns%20field%20added%20in%20receiving%20signal%20from%20OpenText%20to%20S4.pptx?d=wa7c8a264b3954f6b90675158f2d8a1a0&csf=1&web=1&e=prchJb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 55 | 0 | [8 empty] | 55 |  |  |  |  | 0 | 55 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0267, LOGI0953 | 2 | LOGI0267, LOGI0953 | 2 |  | 0 |  | 0 | N/A |  | 2025-11-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | o AR: Check whether the Open Text team will be able to complete the 120 hours of Open Text work on time – Kevin Brown | [9 empty] | Build | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | vaibgupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R4 (Jul 2027) | R4 ITC1 | INT-CR0809 | Approved |  | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | DMRA New Change Request | New objects are identified coming from DMRA for automatic batch determination and assigning batch to STO | As part of the this Change Request, 1. new enhancement RICEFW ID needs to be created to cater automatic batch determination while emptying the Kanban empty solution |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0809%20RE%20New%20RICEFW%20ID%20creation.msg?csf=1&web=1&e=CQDRTu | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0809-%20Batch%20determination%20in%20Kanban%20Board.pptx?d=w9e293a67351a4b60a16ac938d14d64fa&csf=1&web=1&e=D6a0UE |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-24 | o The user wants to manually change the status of a field to trigger a user exit to create an STO o DMRA is an R4/R5 functionality, but the team wants to start working on functional specs in R3 • There is no implication of this code being moved into R3 o AR: Update Release to be R4 - @Tam, Anna | [9 empty] | Other | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | No Objects |  | In Progress | No | Yes
|  | INT-CR0810 | Cancelled |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 02. E2E Process Integration 07. FTS IF | bharadwaj.wuppalapati@intel.com |  | FTS IF - Haritha Komma | [9 empty] | IF/IP Labs Shipping | Recommendation: IF factory to ship to IP lab. PO-SO process. SMH needs to bring Rejects inv from NIMS and EIMS to S4. | Scope changed. | ERP : "No Impact to Existing Deliverables" SMH: Impacted | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/IP_Ship_Change%20ID_Tower_CR%20Deck_template.pptx?d=we374c08e30794cb6adbd6222dde8a0d1&csf=1&web=1&e=MQ2lb7 |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Aditya Tiwari, Imran Athar, and Pushpdev Rai to be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-11 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0811 | Approved | The decision is to wait for clarification on the authorization object; if authorization issues can be resolved, the standard MIGO transaction will be used for reclaim wafer material movement, avoiding custom development. If authorization cannot be resolved, a basic custom Fiori app may be considered, but only to address authorization needs, not to restrict process flexibility. Further discussion and decision are pending Stef's input on the authorization object. | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 02. E2E Process Integration | sri.harisha.sai.kasturi@intel.com |  | FTS IF - Haritha Komma |  | INT-CR1035 | [7 empty] | Reclaim Wafer material movement - I/b and O/B - Design needs | The Reclaim Wafer Working Group (X-Tower) has aligned on the need to initiate a CR to support the program’s progression and enable formal resource assignment based on the findings derived from the MES analysis. This CR is a critical step to ensure that we have the appropriate backing and resources required to address the identified issues effectively and move forward with solution implementation. Additionally, during the recent trade discussions, Marianna raised concerns regarding the viability of incorporating ISM in the proposed "To-Be" state. She indicated that achieving this integration may not be feasible given the current system and process constraints. We recommend moving forward with the CR creation to formally capture the required changes and to align stakeholders on next steps - FTS RAID 01395 created. | The CR is driven by a design miss from Deloitte in the end-to-end process mapping where reclaim wafer handling is not included, which has resulted in critical gaps that now require remediation through formal change control. | E2E design ( process impact) of reclaim wafer handling needs to be completed and be incorporated into the existing build to support R3 IAO timelines. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B922220B0-3A81-47FB-8365-22EE93FB6391%7D&file=CR0811_Reclaim%20wafer%20material%20handling.pptx&action=edit&mobileredirect=true&CID=15CBE538-9181-4DD0-8712-684258A704FD&wdLOR=cD9BB4DCD-8B1C-46C6-ABDE-FF1D0958CA4D&previoussessionid=db36bf05-7017-02b2-caf5-2bbd93e7d502&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA2MDIwNjYxNCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | Design / Build Gap | 1. Process Scope / Design Change |  |  | Very High | 0 | 4 |  |  | 112 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  | FTSE1645 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-26 | o There is a process for reclaim wafers, and it is handled through ISM. However, the team found out that it cannot continue in that app. o This request is to ask for E2E team involvement to include in the To-Be design and for a path-finding effort to map wafers out to suppliers. • The team has a conceptual design, and they have done a high-level estimate. |  |  | 2025-08-01 | • The reclaim wafers process must be redesigned due to compliance issues with ISM, which is no longer viable. • A new process flow has been designed. The key challenge is how to induct reclaim wafer inventory into S4. • Option 1: Integration with SMH (original recommendation) is not feasible within the current timeline. • Option 2: A custom Fiori wrapper transaction around MEGO is proposed to simplify user interaction and ensure compliance. • Option 3: Use standard MEGO directly, but this poses risk due to complexity and potential for user error. • The wrapper transaction will not be ready for ITC1 but can be tested in ITC2. MEGO will be used as a fallback for ITC1. o The process is low risk because: • It affects a small portion of the overall flow. • A known manual workaround (MEGO) exists. • Concerns were raised about volume (up to 2,000 transactions/week), which may strain manual processing. • There are compliance-related data requirements (e.g., country of origin, diffusion) that must be addressed in the wrapper. • The CR was not approved in this meeting. A follow-up review is required to finalize design details and validate assumptions. • AR: Todd Smith and Eugene Celis: Finalize wrapper transaction design. Address compliance fields, batch creation and usability. • AR: Todd Smith: schedule a review with Roman Vorel. Clarify RICEF scope, conflicts and finalize proposal. • AR: Todd Smith bring CR-0811 back WW32.5. Include one-pager justification for late ITC2 entry. | 2025-09-19 | • Followed up on a previously rejected CR regarding reclaim wafer outbound handling. • The team proposed a custom GUI wrapper application with a Fiori tile to reduce complexity and effort compared to the original high-complexity Fiori UI approach. • This medium-risk CR is scheduled for ITC2 and involves coordination across multiple teams including FTC, PTP, LE, and EWM. o Master data and PTP teams will each spend 32 hours setting up and mapping six generic MM IDs for the process. o LE, EWM, and TM scope for inventory movement and outbound processes is covered in CR1035. • The solution aims to streamline the process of returning inventory from the factory floor to suppliers • Decision: Approved |  |  |  | Design | CL/OSC | 2025-09-19 | 08, 2025 | 08, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0812 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Aditya Shinde | [11 empty] | Descope LOGE0969 as business do not require to capture of escort services and export taxes before invoice. | Descope LOGE0969 as business do not require the capture of escort services and export taxes before invoice. | Descope LOGE0969 as business do not require to capture of escort services and export taxes before invoice. The updated charges will be posted in the freight order via carrier invoicing. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0812%20%26%20CR0813/RE%20Cancellation%20of%20TM%20RICEFW%27s%20-%20CR0813CR0812.msg?csf=1&web=1&e=pHcOSZ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE0969 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | [10 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-11 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0813 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Ganesh Kumaresan | [11 empty] | Cancel LOGE1275_IF/IP objects VTRC for integrators - Transfer of tracking ID from S4 delivery to TM Freight unit is no longer needed since we are achieving this via standard field mapping | Cancel LOGE1275_IF/IP objects VTRC for integrators - Transfer of tracking ID from S4 delivery to TM Freight unit is no longer needed since we are achieving this via standard field mapping | The SAP-recommended standard field HU Identification 2 in S4 delivery will full fill this requirement LE aligned to switch from a custom field to the standard field “HU Identification 2.” LE will conduct an effort analysis and submit a CR for the related RICEF (LOGE1052_IF/IP Custom fields for delivery screen) |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0812%20%26%20CR0813/RE%20Cancellation%20of%20TM%20RICEFW%27s%20-%20CR0813CR0812.msg?csf=1&web=1&e=pHcOSZ |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1275_IF, LOGE1275_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | [10 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0814 | Approved | Need to create a separate deck for the "nice-to-haves" | SCP | R2 (Release 2) |  | 08. FTS IP | 8.2 FTS IP - Business |  | 06. PTP 10. Analytics | isabella.piacentini@intel.com |  | FTS IP - Loni Adams | [9 empty] | Extend ASP forecast (Finance) horizon and ASP Forecast determination logic | 1. POR ASP forecasted quarterly by Finance using Revenue (SAP IBP) solution. This forecast currently done for ~4-5Qs (DPOR goes 5 Qs). However, Consensus Demand covers 10Qs. This gap leads to partial dollarization of the demand. 2. Missing ASPs for products introduced between Quarterly POR ASP forecast process. Leads to understatement of dollarized demand. We can take an algorithmic approach to derive ASPs for such products 3. Store/report ASPs derived algorithmically. Original ASPs received from Finance are already preserved. | - Dollarized demand values are with gaps (horizon as well as missing products) - Agreement is in place with Finance to forecast the entire horizon, but systemic changes are needed to extract the data for entire horizon - Algorithmic approach is good enough for missing products. We need to preserve such computed ASPs for traceability purposes |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/ASP%20Forecast%20Determination%20Logic.pptx?d=we3b51a0ac99249b08ff4d73c583c436f&csf=1&web=1&e=AkEU36 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 120 | 0 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-12 | o If this is not done, then the dollarized demand values will be lower than normal. o The 10Q ASP is a must-have part of the request, and the team is planning to deliver in UAT2. • The other requests will be delivered afterwards in WW42. • The change is contained in IP. o AR: Add in the effort required from the SAP IBP Team – Shashank Kolhe, Milind Konnur o AR: Create new CR for the second portion of the request – Shashank Kolhe | [9 empty] | Build | Tower | 2025-06-12 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0815 | Approved |  | ERP | R1 Hypercare |  | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data 13. Security | mauricio.otarola.guevara@intel.com |  | Security - Raj Valluri | [9 empty] | Creating new BU approver roles for new supergroup due to reorg | New BU approver security roles need to be created for MDG for R1 | New supergroups are requested by Finance as a result of reorgs announced by CEO to create leaner organizations. For MDG approval, the workflow is created by supergroup, thus, new supergroups mean new BU approver role needed. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0815%20new%20BU%20approver%20roles%20for%20New%20supergroups.pptx?d=w9bfe18628e5745cdbc66bd35ca55e425&csf=1&web=1&e=e3Qd2p |  | 1. Process Scope / Design Change |  |  | Low | 6 | 1 | [11 empty] | 6 |  | 0 | 0 | Security | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-13 | Uzma approved offline. Therefore, ad hoc meeting was cancelled | [9 empty] | Design | Tower | 2025-06-13 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0816 | Approved |  | ERP | R3 (Release 3) | Low | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Mohit Chawla |  | PTP - Richard Taylor | [9 empty] | Ariba config CUT objects require replanning due to dependency with Ariba CIG | Ariba config CUT were added to Sprint 14 however ARIBA CIG was recently aligned to be completed by June 30th making not possible to complete CUT for 4 objects. | We need to replan those objects and not leaving for prior sprints delayed activities because these have a lot of dependency with ARIBA and S4 Build alignment for FUT and TUT execution in parallel and will make more difficult to have correct sprint planning later on. Alignment with Keerti & PMO already made for Ariba FUT/TUT, this needs to be consistent with that. |  | No |  |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/INT-CR0816/RE%20CUT%20for%20Ariba%20Config.msg?csf=1&web=1&e=y3cvYL |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-17 | Approved in offline email with Uzma | [9 empty] | Other | Tower | 2025-06-17 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) |  | INT-CR0817 | In Progress | Approved for further analysis | ERP | R3 (Release 3) | Very High | 05. OTC IP |  |  | 05. OTC IP 06. PTP 08. FTS IP 10. Analytics | meenakshi lawrence | [10 empty] | Tariff | Legal Requirement for compliance with changing International Trade laws | Tariff Rule changes for Country Of Origin (COO), New compute/Functional die determination logic to be followed. Impacts Rule engine configurations for COO determination, Shipping documents – Commercial Invoice, Packing List, IPLA– Itemized Packing List, Shipping Label, IBox Label, Reports, b2b Rnet PIP’s, COO validations across internal/external manufacturing - Finished Goods, Semi-finished Goods, Direct Materials.. – See more details in foil 4 | Compliance and quick response to changing cross-border Trade rules. Recently China customs announcing a new Rule 58 for Tariffs, impacting all shipments to China and from China. ITG confirmed (1) fabrication country as Country Of Origin (COO) for integrated circuits (instead of Assembly country) for imports into China (2) New Logic for determination of Functional / Compute Die (3) New Label formats for MBB, iBox, Shipping Labels. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0817_OTC_R3_Country%20Of%20Origin%20COO.pptx?d=wc10725e4e2ca40dc88e3b61136a5f418&csf=1&web=1&e=eqtWin |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 06. OSC/CL approved for further analysis | Yes |  | 2025-06-12 | Will need to go to CR Meeting |  |  | 2025-06-13 | Approved for further analysis | [5 empty] | Build | CL/OSC | 2025-06-13 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0818 | Approved |  | ERP | R2 (Release 2) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 11. Technology | rishabhx.hingmire@intel.com |  | OTC IF - Angela Laskowski | [9 empty] | 3PV Form- Change in Length for TRUCK No field | To increase the Length of Truck Number Field on 3PV Form. As per operation team along with truck number they need to enter form ID and Destination in this field. | This change is required to print correct information on TRUCK Number field. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0818-%203PV_Form_Truck_NO.pptx?d=w911b20f460cf45f68860373030a61f3b&csf=1&web=1&e=8Pky2i |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 6 | 0 | [8 empty] | 6 |  |  |  |  | 0 | 6 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0334 | 1 | LOGF0334 | 1 |  | 0 |  | 0 | N/A |  | 2025-06-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-13 | Approved in offline email to Uzma | [9 empty] | Build | Tower | 2025-06-13 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | rhingmire@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0819 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Descoping Conversion objects PTPC1165 and PTPC1166 | These object are created for conversion of open invoices in IP and IF system. But as per business confirmation, they don’t require conversion object for open invoices. We need to descope these objects. | At first, we thought we might need a conversion program to support ReadSoft team. The idea was that ReadSoft would download invoices in the reconciliation stage and send them to Deloitte, where the Deloitte conversion program would map old POs to new POs. However, after a detailed discussion with Intel , we decided to reject all invoices that are in reconciliation status in ARIBA or ReadSoft, no matter where they came from (Fieldglass, Business Network, B&I, WebSuite, Government, ECC, Non-PO invoices, or contract invoices). Once we reject these invoices, suppliers will be notified and will create new invoices with the new PO.So, we technically do not need the RICEFWs listed below. | N/A | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/Regarding%20descoping%20in%20the%20IDM%20tracker%20PTP%20Conversion%20Open%20Invoices%20FSD.msg?csf=1&web=1&e=N1VFRs |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPC1165, PTPC1166 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0820 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.5 Master Data - Finance |  |  | Harshavardhan Harshavardhan | [11 empty] | DATR0569 - Report to send notification to Direct managers about the inactive Cost Center Approvers | This Change is not required for IF system | This requirement is mainly required in MDG, hence we are cancelling this Report RICEFW |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0820/RE%20FS%27s%20Cancellation%20Approval%20Required%20-%20DATE0667_IP%20%20DATR0569.msg?csf=1&web=1&e=7LU0wY |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | DATR0569 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | [10 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | harshaharshavardh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0821 | Cancelled |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 10.1 Analytics - ALL |  | 10. Analytics | Aarti Sadarangani | [11 empty] | Sprint 16 Objects: Addition of new data product objects in ECA tracker | Sprint 16: Addition of new objects into the ECA tracker that ECA team has newly identified as additional data products for build |  |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Leah to not be required: we created it to add data products to go with the build objects but then I think we didnt need it | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-12 | 0 | < 15 Days | lorzechowski@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0822 | Approved |  | ERP | R1 Hypercare |  | 09A. Master Data | 9A.5 Master Data - Finance |  | 09A. Master Data 13. Security | mauricio.otarola.guevara@intel.com |  | Security - Raj Valluri | [9 empty] | Adding cost element Fiori app authorization to existing MDG GL user roles | Adding 2 Fiori apps to 2 MDG GL user role authorization so that users can view/edit data. User role impacted: FPR CORP - MDG - GL Account - Governance Team Approver/FPR CORP - MDG - GL Account - Non-Cash Account Requester Fiori apps to be authorized: Manage Cost Element Governance/Manage Cost Element - Multi-Object Processing | In S4, cost element is the same as GL account. We can use central governance Fiori app to manage both at the same time. However, when performing update using file upload for name change, cost element and GL account need to be managed separately and they need to be updated at the same time. Thus, we need authorization to cost element governance app to make sure we can edit/view data. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0822%20Adding%20cost%20element%20fiori%20apps%20authorization%20to%20existing%20user%20roles%20(002).pptx?d=wd667e62a62e14e7fa15cc342c37a948c&csf=1&web=1&e=Lc6w8S |  | 1. Process Scope / Design Change |  |  | Low | 3 | 1 | [11 empty] | 3 |  | 0 | 0 | Security | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-06-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-13 | Uzma approved offline. Therefore, ad hoc meeting was cancelled | [9 empty] | Design | Tower | 2025-06-13 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0823 | Approved | Confirm with Sunil and Analytics | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Descope FPRXV224 ¦ LTRCA Report | LTRCA report and ECA object are being cancelled | It has been determined that the LTRCA is not critical in the future state environment | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0823/Approval%20CR0823_%20CR%20to%20Cancel%20FPRXV224%20_%20LTRCA%20Report%20.msg?csf=1&web=1&e=EHxIc7 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV224 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-23 | [10 empty] | Other | Tower | 2025-07-23 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0825 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Timothy.Zilmer@Intel.com |  | FTS IF - Haritha Komma | [9 empty] | IF PDF SMH - Feature Drop 7 Addition | IF PDF SMH - Error Handling & Reconciliation requirements is driving a need for an additional functionality drop due to prior drops at capacity | New requirements were discovered during the solutioning phase for IF PDF SMH - Error Handling & Reconciliation requirements. Additional application troubleshooting and data quality solution gaps were identified during the solutioning as well. | The PDF SMH product drops schedule with the inclusion of Drop 7 will be extended one month (mid Sept 25 -> mid Oct 25). Build completion is still scheduled by WW51 but change will remove the remaining schedule contingency | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B689FEE96-C2DA-4847-9DD3-0BD8DE808143%7D&file=CR0825%20%25u2013%20IF%20PDF%20SMH%20%25u2013%20Feature%20Drop%207%20Addition.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-17 | o The product team does not have the do anything after the Drop • This is more PDF internal so that they can figure out the issues and bugs in the PDF environment o There is no E2E impact, and all towers are in agreement and signed off. | [9 empty] | Other | Tower | 2025-07-17 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0826 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Add the Country of Origin information in the Ship Item screen. RICEFW ID LOGE1221 | Intel has a new requirement to add the Country of Origin information in the Ship Item screen. | Intel has a new requirement to add the Country of Origin information in the Ship Item screen. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the tech effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-14 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0827 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | On Hold until a final decision take place - Reinstate 9 ECA objects from Fixed Assets | To be Cancelled - Reinstatement of ECA View object-FPRXV044-10Q Cost Asset Class Details Reinstatement of ECA View object-FPRXV045-10Q Depreciation Asset Class Details Reinstatement of ECA View object-FPRXV048-Asset Retirements HANA Reinstatement of ECA View object-FPRXV049-FAA GL Account Activity Reinstatement of ECA View object-FPRXV078-AUC Details Reinstatement of ECA View object-FPRXV083-AUC Validation Reinstatement of ECA View object-FPRXV105-PO Details Reinstatement of ECA View object-FPRXV237-Asset List Orphan Reinstatement of ECA View object-FPRXV238-Asset Missing UAI (Unique Asset Identifier) | Deloitte has recommended that the prior direction to consolidate ECA reports sharing common data in a single report | No Impact to Existing Deliverables | No |  | On hold | On Hold |  | 2. New RICEFW / ECA / Build Object |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Aarti to not need reinstatement as the objects are already created in the Intel ECA tracker. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0828 | New |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Siddharth Asitkumar Desai | [11 empty] | LOGI0154/ LOGI0155 -Increase length of PO field from 10 character to 12 character because BI + Text PO = Build instruction will come in the field. | LOGI0154/ LOGI0155 -Increase length of PO field from 10 character to 12 character because BI + Text PO = Build instruction will come in the field. | Increase length of PO field from 10 character to 12 character because BI + Text PO = Build instruction will come in the field. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 80 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-16 | 296 | > 30 Days | vaibgupta@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0829 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP |  |  | 05. OTC IP | [12 empty] | Cancellation of RICEF Objects: LOGF0806 & LOGF0807 - CI/PL Forms for Return to customer | Cancellation of RICEF Objects: LOGF0806 & LOGF0807 - CI/PL Forms for Return to customer | LOGF0806 object needs to be descoped/cancelled as they will be covered as part of LOGF1283. LOGF0807 object needs to be descoped/cancelled as they will be covered as part of LOGF1282. For the process of returning product to the customer, the standard outbound CI (Commercial Invoice) and PL (Packing List) can be utilized as all the templates are currently generated out of ISM in ECC. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0829/RE_%20LOGF0806%20_%20LOGF0807%20-%20Approval%20required%20for%20RICEFs%20cancellation%20.pdf?csf=1&web=1&e=v0XwQU |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGF0806, LOGF0807 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-25 | [10 empty] | Other | Tower | 2025-06-25 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-16 | 0 | < 15 Days | tukhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0831 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | New RICEFW needed for Ship Action Queue screen. (Enhancement) | Ship Action queue is needed to perform Confirm & Undo Disposition. | Ship Action queue is needed to perform Confirm & Undo Disposition. |  | Yes | Non-Core |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-16 | 296 | > 30 Days | sjulury@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0832 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes |  | Surendra Julury | [11 empty] | LOGW1412 needs to be dropped. | LOGW1412 needs to be dropped as this can be covered under LOGE1280. | LOGW1412 needs to be dropped as this can be covered under LOGE1280. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0832/RE%20Help%20Needed-CR%20for%20Dropping%20RICEFW%20LOGW1412%20approval%20.msg?csf=1&web=1&e=R3m75l |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGW1412 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-25 | [10 empty] | Other | Tower | 2025-06-25 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-16 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0834 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 04. OTC IF 05. OTC IP 07. FTS IF 11. Technology | Surendra Julury | [11 empty] | New Enhancement to implement the custom solution recommended by SAP on TM-EWM Integration issue. | To implement custom enhancement suggested by SAP in Case no. 632900/2025 to enable the integration of both IF(BI1) and IP(DI0) TM system with EWM system (EI1). | Unable to establish an Integration between EWM (EI1) and TM systems (DI0 and BI1), when an existing service group defined in one integration, is been referenced again, for another Integration scenario. Case 63200/2025 was raised to SAP regarding this issue. SAP has suggested to enhance a std. method “/SCWM/CL_BIF_SR_TOLDAP_NO_SRV->PROXY_CALL” with a custom enhancement so that the system filters out the correct receiving system during communication between EI1 and the respective TM systems i.e. BI1 or DI0 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/FS%20Drafts%20-%20OTC%20IP%20Returns%20EWM/EWM-TM%20Integration/CR0834%20EWM-TM%20Integration.pptx?d=w7f0369c371ca463ab29593712a69926a&csf=1&web=1&e=1GNzhI |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 32 |  |  |  |  | 0 | 32 | N/A | Yes | S4 | 1 | LOGE1507 |  | LOGE1507 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o This is a custom enhancement recommended by SAP.  The team raised a ticket when the team encountered a roadblock during the setup of the integration between TM and EWM systems, and SAP responded that this is a not a standard feature. o This request will create a custom enhancement so that it doesn’t touch clean core code. | [9 empty] | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-16 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | Complete |  | Complete | No
| N/A | INT-CR0836 | Cancelled |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP | karthp@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of Object - LOGW0994 | This object was initially owned by the PM team, however once the requirement got formalized, the intent was agreed to trigger email to a DL provided for a warehouse operator to initiate the returns picking from a factory location. | Since the requirement eventually formalized to restrict the capability to send the email rather than any approval process hence workflow object needs to be converted to the Enhancement. | No Impact to existing deliverables | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 06, 2025 | 2025-06-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0837 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09A. Master Data 11. Technology | Surendra Kusumuru | [11 empty] | Request for the creation of new interface object to retrieve the list of approvers from a custom MDG table(MDG system) when a PR/PO creation or change workflow is triggered in S/4HANA.​ | Request for the creation of new interface object to retrieve the list of approvers from a custom MDG table(MDG system) when a PR/PO creation or change workflow is triggered in S/4HANA.​ | When PR/PO creation or change workflow scenarios based on the predefined conditions system should fetch the approvers(Finance Analyst) list from the custom MDG table and need to validate the signature of authority with PR/PO value and trigger the workflow accordingly, to achieve this we need to have interface b/w S4 and MDG system. This requirement is needed for ZCAP/ZSI/ZCME doc types (PR/PO) relevant workflow scenarios & Managerial Hierarchy scenarios aswell |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-17 | 0 | < 15 Days | surensurendra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0839 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Deepanshu Lnu | [11 empty] | validation requires for PTPI0144 interface for ASN interfaces | This change request (CR) requires implementing validation in PTPI0144_IP_IF to ensure that commits for the purchase order (PO) and line item are sent to S4 only when there is no ASN signal for the corresponding PO and line item in an error state. | This change request (CR) requires implementing validation in PTPI0144_IP_IF to ensure that commits for the purchase order (PO) and line item are sent to S4 only when there is no ASN signal for the corresponding PO and line item in an error state. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/2.%20Interfaces/E2Open%20Interfaces/PTPI0144_PTPI0145_Interface_E2O_to_PO_Supplier_Commit/EXT%20RE%20Approval%20required%20for%20CR%20INT-CR0839%20%20Object%20PTPI014445_IP_IF.msg?csf=1&web=1&e=h7tXPH | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/2.%20Interfaces/E2Open%20Interfaces/PTPI0144_PTPI0145_Interface_E2O_to_PO_Supplier_Commit/INT-CR0839.pptx?d=w5dbc16477bfb434a92e01c8ed4c23ec9&csf=1&web=1&e=FCLkLc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 60 | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0144_IP, PTPI0144_IF | 2 | PTPI0144_IP, PTPI0144_IF | 2 |  | 0 |  | 0 | N/A |  | 2025-10-31 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | o This request is to add a small logic change into the E2Open interface so that the PO commit field is populated. • PO commit is the quantity that the supplier has committed to, and the ship-out quantity is how much logistics have shipped out. • This logic will then deciding which number to send out. | [9 empty] | Build | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-17 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0841 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Naman Parti | [11 empty] | If there are multiple line items, and if there is at least one valid material / CPN / GTIN; then the sales order needs to be created for the valid line items (valid material / CPN / GTIN / Zero / decimal) and reject the line items with invalid line items (invalid material / CPN / GTIN / Zero qty / decimal qty).. | SO creation for the combination of valid and invalid SOLI | If there are multiple line items, and if there is at least one valid material / CPN / GTIN; then the sales order needs to be created for the valid line items (valid material / CPN / GTIN / Zero / decimal) and reject the line items with invalid line items (invalid material / CPN / GTIN / Zero qty / decimal qty).. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B23A6BBBD-64AC-4CE0-A312-95C5566F4536%7D&file=INT-CR0841%20-%20SO%20creation%20for%20the%20combination%20of%20valid%20and%20invalid%20SOLI.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 28 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the tech effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-17 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0842 | Rejected |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | New RICEFW object for FFS | New RICEFWs object identified for FFS to get PO Lot pegging data for Backend transactions: 1. Interface from FFS to S/4 to maintain POLP table | Earlier suggestion was to get the PO lot pegging data from Production Scheduling FSCO. As per the recent conversations, Business notified that only data for Frontend transactions can be fetched from FSCO, and for backend the data needs to be fetched from FFS. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/RE%20New%20RICEFW%20ID%20Creation-INT-CR0842.msg?csf=1&web=1&e=ziSMhC | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0842_FTS-IF_NEW%20RICEFWs%20for%20FFS%20Change%20Request.pptx?d=w0189d8e738614a53976e46f2ed97e99c&csf=1&web=1&e=TXaCqm |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes | S4 | 0 |  | 3156 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | No | No | 2025-06-18 | o We need to have a new interface for POLP because Production scheduling is split into 2 apps.  The second interface is to pull the backend data for POLP | [8 empty] | Descoped by CR1500. The replacement object is FTSI1159 | Other | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-17 | 0 | < 15 Days | avinayakpatil@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0844 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Naman Parti | [11 empty] | Inclusion of indicator fox box plant identification in material characteristics which ensures for the materials relevant to box plant, the material master plant is derived. | Inclusion of indicator for box product at the material master attributes i.e., class and characteristics and further default the delivering plant from the material master ignoring the CMIR and Ship to record delivering plants | Box Planning/ Finished Good Inventory - Network design confirmed post 2DN OM design. All Box Finished Good MMID SOLI should ship via 1DN and be mapped to Regional Box Finished Goods warehouse. ​ Incorrect Plant ID / Loc ID will be assigned to SOLI If Distributor Ship To, has been set up for 2DN as Ship to BPID Default Plant will be XDOCK Plant ID. ​ Requirement for some Channel 02, Distributor Ship to, to map to 1DN Plant ID (Regional Finished Goods Box Plant ID) for Box and 2DN XDOCK Plant ID for non Box. ​ MM-SHIP-MED is a characteristic of Material. All Box MMIDs will have a characteristic value of BOX |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E96EABC-3AB0-43D0-9977-9D5CB91E7C4B%7D&file=INT-CR0844%20-%20Inclusion%20of%20indicator%20for%20box%20product%20identification%20via%20material%20attribute.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the tech effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-17 | 0 | < 15 Days | shravann9@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0845 | Approved |  | ERP | R1 Hypercare |  | 09A. Master Data | 9A.5 Master Data - Finance |  | 03. FPR 09A. Master Data 10. Analytics | mauricio.otarola.guevara@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Custom MDG report logic change to get rid of dependency on next edition | Custom MDG report logic needs to be change to get rid of dependency on next edition given Next edition is not maintained in MDG based on new business process. Without the change, the report will not return any data. The reports are leveraged by IT to enable data load to legacy MDG. | Custom MDG reports compare CR creation date with the valid from date of the edition in the prompt as well as the valid from date of the next edition in the edition table. However, next edition is not maintained in the new business process to prevent users from misusing the wrong edition to create hierarch related changes, thus, the logic is broken and no data is returned. This issue was not applicable in UAT testing because next edition was maintained in UAT. It’s in production that we decided to not maintain next edition to avoid the version issues from UAT results. We need to change the report logic to make report work. Instead of using next edition to derive the end date, the report should look for DAY7 edition of the same month. If DAY7 edition is not available either, just take today’s date. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDC6C5E24-B560-4D8F-A322-854D592B1B51%7D&file=CR0845%20MDG%20custom%20report%20logic%20change.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 16 | 0 | [8 empty] | 16 |  |  |  |  | 0 | 16 | Tech - MDG | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATR0277 | 1 | DATR0277 | 1 |  | 0 |  | 0 | N/A |  | 2025-06-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o This request is a small logic change to see both future and current editions. The team can only see the current edition. | [9 empty] | Build | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0846 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF 11. Technology | rodolfo.alarcon@intel.com | [11 empty] | Requesting for additional overpack functionality – Label change & HU Close | Requesting for additional overpack functionality – Label change & HU Close | In the WIP process when the goods movement happens from one factory to another, warehouse will be printing the overpack label . In R3, when dealing with multiple deliveries packed in a single overpack HU, the over pack label should be printing DN reference as XXXX to avoid confusion during order fulfilment. Printing of the overpack label should be enabled from the HU Close step for efficiency.​ Additionally, while the HU’s of multiple DNs are manually overpacked which are to be delivered in single TU, then the overpacking should happen only for the HUs which are tagged to the deliveries assigned to the TU ie., HU’s related to other TU’s should not be allowed to be overpacked mistakenly. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0846_FTS%20IF%20-%20Enhancement%20related%20to%20WIP%20in%20OBD%20process.pptx?d=wbc473550c4a24948a901c3d252bca64b&csf=1&web=1&e=ov4g3M | Missed Requirement | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 282 |  |  |  |  | 0 | 282 | N/A | Yes | S4 | 2 | LOGE1522, LOGE1521 |  | LOGE1522, LOGE1521 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-18 | o This CR is trying to replicate the current process and initiate cost savings.  We need enhancements and interfacing to make it happen. o All work will be contained in SAP. |  |  | 2025-06-19 | • Background & Proposal: Rodolfo explained the current overpacking process is using B-apps. Overpacking involves consolidating multiple delivery notes into one large box, simplifying the shipping process. Path of least resistance involves shipping smaller boxes individually, which may lead to increased freight costs and packaging material usage. The redesign aims to mimic the current process in SAP EWM, focusing on label redesign and handling unit closing. If approved Rodolfo to lead the implementation of the overpacking process in SAP EWM, including label redesign and handling unit closing. • Cost Implications: Discussed the cost savings associated with the overpacking process, estimating a difference of around $200K if the process is implemented correctly. Overpacking provides substantial savings, especially for R3 and Ronler Acres and Aloha sites. Increased freight costs and minimum charges are considerations if smaller boxes are shipped individually. Cost Analysis Team to conduct a detailed cost analysis considering increased freight costs and minimum charges for shipping smaller boxes. • Technical and Functional Assessment: Approximately 232 hours are estimated for label redesign, technical and functional unit tests, and integration with the current R2 process. The customization is included in the 232 hours, with no additional RICEFWs expected. Logistics and tech teams have reviewed the redesign and confirmed capacity to handle it without impacting other work. There are no master data changes or B-Apps impacts are expected. The team has confirmed capacity to handle the redesign without impacting other workstreams. • Decision: Approved to proceed with the overpacking process redesign in SAP EWM, focusing on label redesign and handling unit closing. | [5 empty] | Other | CL/OSC | 2025-06-19 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-17 | 0 | < 15 Days | psowale@deloitte.com |  | No |  | Complete |  | Complete | No
R2 (Aug 2025) | R2 | INT-CR0847 | Approved |  | SCP | R2 (Release 2) |  | 05. OTC IP | 5.1 OTC IP - ALL |  | 05. OTC IP 10. Analytics | elena.kaufman@intel.com |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Plan Sort Out Wafer Purchases | In UAT1 it was discovered that both OneMPS and BY IBP are planning a subset of products. These are unique in that they do not have a fab part on the SPEED BOM and appear as Sort only products (Examples: Carlsville, Linkville, Gothic Bridge). In today’s environment, these would be treated as OSAT purchases and the OneMPS team reacted accordingly. Subsequently, the determination was made that these are initial wafer purchases that belong in BY IBP. Change is to remove these from planning in OneMPS which requires changes to both SPAN and OneMPS. | Ensure that only one planning system is generating requirements for this set of products. | There won’t be availability for the analysis of any other R2 CR’s Thorough testing will be required to ensure no impact to production release No capacity to support R3 microplanning sessions | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5BD1AF2D-1106-41E7-8F14-5650950C79F6%7D&file=INT-CRXXXXX-Wafer%20purchases%20to%20plan%20in%20BY.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 120 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-18 | o These wafer purchases need to be removed from planning in OneMPS as it was not considered for SPAN and OneMPS. • BY is sending out discreet PO’s, and OneMPS Is using scheduline lines. Therefore, if it is not removed, BY will fail to plan wafers and products properly. o The team is pulling in additional resources to support this. Otherwise, both BY and OneMPS will do the planning. • It will be delivered in WW29, and there will be parallel testing done to mitigate the risk. • On SPAN side, we are pulling some non-IAO resources. As a tradeoff, if there are changes in the upstream, then the team will not be able to support it. No capacity to support R3 microplanning sessions. | [9 empty] | Build | Tower | 2025-06-18 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0849 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | njain42@deloitte.com |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSC0831 | Request the cancellation of Object FTSC0831. The primary requirement for this object—Add WIP value to the open production orders—is now fully owned by FPR team where they will be addressing the issue by "FPR team will load values for WIP against open production orders created during cutover following below steps" 1. Create Production Order 2. Get values in KB15N format Cost 3. Secondary CE wise values (1CE per CCS) from ICost 4. Dr to Production Order withSecondary GL and Cr to COPA with Profit Center / Internal Order | Request the cancellation of Object FTSC0831. The primary requirement for this object—Add WIP value to the open production orders—is now fully owned by FPR team where they will be addressing the issue by "FPR team will load values for WIP against open production orders created during cutover following below steps" 1. Create Production Order 2. Get values in KB15N format Cost 3. Secondary CE wise values (1CE per CCS) from ICost 4. Dr to Production Order withSecondary GL and Cr to COPA with Profit Center / Internal Order |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/EXT%20RE%20Cancellation%20CR-%20INT-CR0849%20-%20FTSC0831%20WIP%20value%20to%20Open%20Production%20order.msg?csf=1&web=1&e=d4TNan | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0849_FTS-IF_CANCEL%20for%20Conversion%20Object%20FTSC0831%20Request.pptx?d=wfcfc824e26234da3bbeec36fb8ba0cce&csf=1&web=1&e=eXxXCh |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSC0831 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 06, 2025 | 2025-06-18 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0851 | Cancelled |  | SCP | R2 (Release 2) |  | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 10. Analytics 18. SCP | elena.kaufman@intel.com |  | FTS IP - Loni Adams | [9 empty] | Enable user-edited constrained plans, and publish complete plans to OneMPS & Compass | - Provide capability to refine the Constrained scenario through re-solves and post-solve edits. - Enable publishing of the edited constrained solve (Team C), along with Team A or B Flex Constrained, and baseline Flex and Constrained solves to OneMPS and Compass per defined schedule (solve week .0, .3 and exec week .4), inclusive of all foundry suppliers - Ensure that all publications to OneMPS and Compass use a consistent signal for all suppliers (no differentiation between Intel Foundry and other foundries) | Through the course of solve week, users may need to re-run a constrained version. Reasons vary but could be to drive level loading, recognize manual overrides to the purchase requirements, or other cases that should be reflected in our Single Operating Plan. Key goal is to ensure that we can give the S&OP process the best constrained plan that represents how we intend to operate. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/2025%20Change%20Requests/CR%20-%20Make%20TeamC%20a%20constrained%20scenario.pptx?d=we04489b22e3340ebb050297a45a71e30&csf=1&web=1&e=nwEUzY |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel Olvera, Sergio Boraschi, and Elena Kaufman to be cancelled. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0852 | Approved |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 10. Analytics 18. SCP | maureen.gallagher@intel.com |  | FTS IF - Haritha Komma | [9 empty] | Processing Stage attribute data to project the correct BUMP inventory | For processing Stage attribute data to project the correct BUMP inventory due to CIBR error of capturing it as Sort inventory | Without this change there are ~2 million die that are miscategorized in our inventory capture | TBD - solution is still being worked | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B03D450C4-61AD-4513-940B-8041DAD31FDF%7D&file=INT-CR0852%20-%20Processing%20Stage%20attribute%20data%20to%20project%20the%20correct%20BUMP%20inventory.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 120 | [6 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-26 | Reviewed in CL Meeting and added directly to the CR Meeting on Friday. |  |  | 2025-06-27 | • Problem: The CIBR system prematurely overrides the shop floor product name from the bump operation to the sort operation due to shared operations between the two. This misclassification causes inventory to appear under the wrong product, leading to planning and capacity misalignments. A concern was raised regarding the impact on the SMART System, John acknowledged but noted that the exact impact needs further verification. • Impact: Inventory appears as if it has passed through sort when it is still at bump, affecting sort TPT and capacity planning. • Proposed Solution: Leverage a new lot attribute from factory automation that indicates the planning stage. This attribute will be used to traverse the BOM and correctly associate the inventory with the appropriate UPI. • Timeline: SPAN team, 6 weeks expected to be ready by WW32. ECA team, 8 weeks expected to be ready by WW33. Teams have already begun work on the implementation. Risk: The changes lands late in the SCP UAT2 cycle, POR end date of WW34 providing minimal time for testing. • Decision: Approved. o Deployment timing and Go Live Risk will be handled separately from the CR approval. • AR: John Heiney to confirm whether SMART requires a code change, as it was flagged as a potential consumer of CIBR data. • AR: John Heiney, Rebecca Verette and Sunil Narayanan to assess B-App impact and provide a holistic view. • AR: Rebecca Verette and John Heiney to coordinate and close out of data quality concerns. | [5 empty] | Build | CL/OSC | 2025-06-27 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0853 | Approved | Rick Antonellis and team to provide comprehensive risk assessment and Go Live recommendation for R2 SCP. | SCP | R2 (Release 2) |  | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 10. Analytics 18. SCP | maureen.gallagher@intel.com |  | FTS IF - Haritha Komma | [9 empty] | Processing Planning Owner Site data for projecting Bump stage inventory and actuals | For processing Planning Owner Site data for projecting Bump stage inventory and actuals to align with the new design of IF BY/PDH - SPAN- FSCO flow | FSCO will only project the schedule for physical sites, but BY creates the schedule based off the sort capacity | TBD - solution is still being worked | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2110FE88-F25E-4ED7-BA82-65F9AA3376E7%7D&file=INT-CR0853%20-%20Plng%20Owner%20Site%20data%20for%20Bump%20stage%20inventory%20and%20actuals.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-06-26 | Reviewed in CL Meeting and added directly to the CR Meeting on Friday. |  |  | 2025-06-27 | • Objective: Align inventory actuals and schedules to prevent over/under capturing of material due to discrepancies in factory cut-off times and cross-site processing. • Problem: There are differences in how FSCO and PDH handle demand and inventory timing resulting in misalignment. Disconnects exist between where schedules are owned and where lots are physically processed. FSCO must adjust for within-stage cross-site processing and planning owner mismatches. • Status: The FSCO effort sizing estimate is high (13 weeks) and options are being worked to reduce this. Even with reductions, the timeline is tight and may not allow for adequate testing before Go Live. PDH sizing is 6 weeks, and there is no additional effort for SPAN and ECA to what is already included in CR0852. • Impact: This adds Risk to R2 SCP Go Live. This does not pose a risk to R2 ERP Go Live. o There was a discussion about delaying the R2 SCP Go Live by ~4 weeks to the Oct'25 cycle. Further delay risks entering finance blackout periods (Nov–Dec'25), which is undesirable. o PDH R3 is behind 1 Sprint and accepting this CR will likely result in additional Sprint delays. The team is working options to expand CW resources as part of risk mitigation • Decision: Approved. • AR: Shamin Shirodkar to provide an updated detailed sizing and FSCO timeline estimate by EOD WW27.1. • AR: Rick Antonellis and team to provide comprehensive risk assessment and Go Live recommendation for R2 SCP. • AR: John Heiney, Rebecca Verette, and Sunil Narayanan to provide CW resource expansion proposal for risk mitigation. | 2025-08-01 | CR01017 was created and approved during 8/1 CL. |  |  |  | Build | CL/OSC | 2025-08-01 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0856 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 08. FTS IP 11. Technology | Mehak Malhan | [5 empty] | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7bBCD96950-865F-41F7-92C8-B99EF06B32BE%7d&file=Interaction+Model+for+Engineering+&%20Rework%20KDD.pptx=&action=edit&mobileredirect=true | [5 empty] | New Objects Identified + Change in Existing Objects Global Design Change for Engineering/Rework/HVM Orders .​​ Rationale: Introduction of PDF for IP and impact on effort and schedule to support existing Intel Foundry models​ Consistent model for OSAT’s for HVM/Engineering/Rework ​ Consistent model for Intel Foundry for HVM/Engineering/Rework For purchasing documents (PR/PO) that are not account assigned, the Finance Analyst approval step should be skipped since cost center details are not available. | Global Design Change for Engineering/Rework/HVM Orders .​​ | Introduction of PDF for IP and impact on effort and schedule to support existing Intel Foundry models​ Consistent model for OSAT’s for HVM/Engineering/Rework ​ Consistent model for Intel Foundry for HVM/Engineering/Rework ​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5AA7535E-6096-482A-99A7-8A654818C9ED%7D&file=INT-CR0XXX_PTP_IF_IP.pptx&action=edit&mobileredirect=true&CID=80BEE91A-9C78-4ACB-9B2C-5C1741BAAD0F&wdLOR=cC719408F-6B06-41A6-A74B-13D7A7BB714B | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | Very High | 803 | 4 | [8 empty] | 803 |  |  | 10 |  | 0 | 803 | Tech - S/4 | Yes | S4 | 7 | PTPE1700, PTPE1699, PTPE1532, PTPE1531, LOGE1570, FTSE1597, FTSE1586 | 3028, 3029, 3030, 3040 | PTPE1700, PTPE1699, PTPE1532, PTPE1531, LOGE1570, FTSE1597, FTSE1586 | 7 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPW0362_IP, PTPW0366_IP, PTPE1050_IP, PTPI0136_IP, PTPE0606_IP, PTPE0259_IP, FTSI0491, FTSI0725, FTSI1023, FTSC0434, FTSI0268, FTSE0593, LOGI0154, LOGI0155, LOGI0158, LOGI0156, LOGE0952, LOGI0834, LOGE0754_IP, LOGI0956, FPRE0648, FPRI0864, DATC0589, DATC0586, DATC0588, DATC0587, DATI0582, OTCI1162, OTCI1126, OTCE1124 | 30 | PTPW0362_IP, PTPW0366_IP, PTPE1050_IP, PTPI0136_IP, PTPE0606_IP, PTPE0259_IP, FTSI0491, FTSI0725, FTSI1023, FTSC0434, FTSI0268, FTSE0593, LOGI0154, LOGI0155, LOGI0158, LOGI0156, LOGE0952, LOGI0834, LOGE0754_IP, LOGI0956, FPRE0648, FPRI0864, DATC0589, DATC0586, DATC0588, DATC0587, DATI0582, OTCI1162, OTCI1126, OTCE1124 | 30 |  | 0 |  | 0 | N/A |  | 2026-04-17 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-26 |  |  |  | 2025-06-27 | • Background: The original design for engineering and rework orders relied on initiating subcon POs, which was inconsistent with the HVM model that starts with production orders. This inconsistency caused issues with the PDF layer and required redesign. • Objective: Align the engineering/rework order process with the HVM model to ensure compatibility with the PDF layer and streamline external OSAT and IF flows. • Assessment Process & Scope o A KDD was presented and approved in the previous sprint. o A FTF was held and impacted teams conducted a detailed impact analysis. The assessment identified new and impacted RICEFW items, including security, and configuration changes across multiple towers and horizontals. o Scope. This change affects all IP Towers. OTC IF is also impacted due to 3 existing RICEFW items. • Timeline: o Latest FUT completion date is WW44.5. o All teams, including tech, middleware, and E2Open, have aligned on their readiness and build timelines. o The build milestone is not impacted, and integration testing cutoff in Dec'25 will be met. • Decision: Approved. | [5 empty] | Other | CL/OSC | 2025-06-27 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-20 | 0 | < 15 Days | mmalhan@deloitte.com |  | No | FUT In Progress | Complete |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0857 | Approved | Following up with Tushar to get standard solution | ERP | R3 (Release 3) |  | 05. OTC IP | 5.13 OTC IP – Returns (Logistics Management) | Yes | 05. OTC IP | sshettyk@deloitte.com |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Cancellation of RICEFW Object:LOGE1336 | LOGE1336 dealt with the development of a custom screen to manage Commercial Invoices/Packing list created as part of the customer returns process. This enhancement would be used to update the price in the commercial invoice and packaging information in the CI/Pl forms. However leadership did not want a custom screen just for updating the CI/PL and wanted to go with the standard solution. The standard solution was discussed with the Intel Business and Intel IT and all were aligned that the standard solution can be adopted. Hence cancelling the object. | Standard solution of using a statistical price condition in the delivery to update the price will be used. | No Impact | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0857/%5BEXT%5D%20RE_%20Help%20Needed-CR0857%20approval%20needed.pdf?csf=1&web=1&e=bYK2d5 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1336 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-25 | [10 empty] | Other | Tower | 2025-06-25 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0859 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | Interface required to send signal to Workstream from S4 to set lot attributes to Workstream, upon Kanban bin full signal received from when Lot details needs to be sent from S4 to Workstream. This additional interface is required from Mulesoft side because they will be using console ID 2843 for create Lot signal and get response back. And this console ID will be used to Set Lot attributes from SAP and get response back from Workstream.?ABAP team will work on the RICEFW ID generated using 2843 console ID and drive the functionality as stated in previous intake. | Interface required to send signal to Workstream from S4 to set lot attributes to Workstream, upon Kanban bin full signal received from when Lot details needs to be sent from S4 to Workstream. This additional interface is required from Mulesoft side because they will be using console ID 2843 for create Lot signal and get response back. And this console ID will be used to Set Lot attributes from SAP and get response back from Workstream.?ABAP team will work on the RICEFW ID generated using 2843 console ID and drive the functionality as stated in previous intake. | Mulesoft requires 2 RICEFW objects . 1. Create Lot 2. For Set Lot Attributes |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0859%20-%20Interface%20to%20send%20Lot%20attribute%20signal%20to%20Workstream%20from%20SAP%20S4.pptx?d=w6b8b7e16c1694b5482b40ab464766a91&csf=1&web=1&e=gULTgY |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Murthy to be a duplicate CR. Therefore, it is cancelled | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-23 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0862 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.1 Security - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP | Sreevani Tadepalli |  | Security - Raj Valluri | [9 empty] | Cancel R3 Sprint 4 - 15 SFUT activities and Fiori Apps | Cancel Bulld Sprint entries for SFUT as the apps have been descoped from design | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7B8234A6-1E0A-4A97-8751-7D0FBC5B3A76%7D&file=Descoped%20Apps%20List%20from%20till%20Sprint%2015.xlsx&wdLOR=cDFF8CF4A-6999-4128-94C2-A94A70A50F88&action=default&mobileredirect=true |  | Yes |  |  |  |  | 9. Non-Build Security-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-16 | Approved offline with Uzma | [9 empty] | Other | Tower | 2025-07-16 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-24 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0863 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP 17. B-App | Boon Pin Teoh | [11 empty] | 2 Interfaces PTP10710 - IP& IF - Manual release required additional 2 fields from table: BSEG-BUZID & BSEG-TBTKZ | 2 Interfaces PTP10710 IP & IF - Manual release required additional 2 fields from table: BSEG-BUZID & BSEG-TBTKZ. No impact our existing schedule because current scope including BSEG table, we just need to include additional 2 fields from it | Customs Tracker pulling invoices data from S4 to be able to reconcile against shipment data entry and returned shipment data back to S4 for invoice releasing activity, thus one of the functionality in customs tracker called subsequent adjustment which allowed AP user to review and approved blanket PO invoice transaction | No Impact | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0863/EXT%20RE%20INT-CR0863%20-%20change%20request%20to%20include%20additional%202%20fields%20-%20Approved%20by%20Cari%20Shim.msg?csf=1&web=1&e=dX2OZ2 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA1CA9B99-9337-4E7D-8EE0-67A17F711209%7D&file=INT-CR0863%25u00a0%25u2013%20Customs%20Tracker%20BApp%20-%20Additional%202%20fields%20for%20PTP10710%20(PTP%20manual%20release).pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 10 | 0 | [8 empty] | 10 |  |  |  |  | 0 | 10 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0710_IP, PTPI0710_IF | 2 | PTPI0710_IP, PTPI0710_IF | 2 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-24 | Approved offline with Cari | [9 empty] | Build | Tower | 2025-06-24 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-24 | 0 | < 15 Days | boon.pin.teoh@intel.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0865 | Cancelled |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shubhangi Mehrotra | [11 empty] | Cancellation of RICEFW LOGI1292 & LOGI1294 | The requirements of LOGI1292 are getting covered in LOGI1291 objects whereas the requirement of LOGI1294 are getting covered in LOGI1293. Therefore we need to get the objects LOGI1292 and LOGI1294 to be cancelled. | *Closed per Shubhanji |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Shubhangi to be closed. | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 06, 2025 | 2025-06-24 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0866 | Cancelled |  | ERP | R3 (Release 3) |  | 05. OTC IP | 5.13 OTC IP – Returns (Logistics Management) | Yes | 05. OTC IP | sshettyk@deloitte.com |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Ship To Scrap Vendor- Design Reassessment | In IP Returns process, once the returned materials have been received and inspected , one of the disposition alternatives is to Ship to Scrap Vendor. In order to ship to scrap vendor initially it was considered to leverage the Return PO process. However during the FSD discussion for LOGE1221, when this process was discussed in detail it was understood that the scrap vendor is charged and this a revenue generating operation hence a new process should be defined for the same, for which an E2E discussion is needed. | Ship to Scrap Vendor is revenue generating operation, hence a new process to be defined. | Impact to close out LOGE1221 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0866_OTC-IP_Ship%20To%20Scrap%20Vendor-%20Design%20Reassessment.pptx?d=wbf70c4466f524fcd9fed87734abf016c&csf=1&web=1&e=YwuCmf |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Deb to no longer be needed. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0867 | In Progress | The decision is to proceed with detailed design and technical review for the custom Fiori app, with the intent to avoid impacting ITC1; if it is determined that the timeline cannot be met, the team will revisit the risk and decide whether to accept a late delivery, as the UI is not a showstopper for testing core functionality. Final approval is pending completion of the RICEFW process and further review with more details. | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Addition of Custom Fiori Tile | Addition of custom Fiori tile as part of the interface/enhancement object ID | This was initially missed in the FS and now we need to incorporate as part of critical business requirement | This is a critical development and basis this there are dependencies on other developments as well. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0867_OTC%20IP%20%E2%80%93%20Addition%20of%20Custom%20Fiori%20Tile%20or%20Dashboard.pptx?d=w07e67779227249c8b8447337a3b7cc59&csf=1&web=1&e=EgqIYS |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 01. Proposed | Yes | No | 2025-07-31 | o This is a requirement to create custom Fiori dashboard • Since Webdyn Pro is being EOL’ed, the SAP suggestion was to go for Fiori apps • Webdyn Pro was the original tool when the design was closed (Boundary UI). Data is in S4 environment, and the future UI will be Fiori. o AR: Understand is there was a recent decision regarding status of Webdyn Pro (was it always a Migrated app) - @Lafree, Shelly o AR: Review processes to see if there are other impacts to Returns - @Lafree, Shelly |  |  | 2025-08-08 | • There is increased demand for custom Fiori apps, especially for returns disposition management, leading to resource augmentation efforts with Deloitte. The team is working to avoid missing the ITC 1 timeline, but there is acknowledged risk due to the iterative nature of Fiori UI development and user-driven changes. The detailed design for the Fiori app is not yet complete; the team will finalize requirements and review technical options before confirming if ITC 1 can be met. • If the Fiori UI is not ready by ITC 1, testing can proceed using backend rules, with the UI to be delivered later if necessary. The team does not intend to switch to React solely for timeline reasons, as Fiori remains the preferred and more efficient UI platform in their environment. The risk of missing the December deadline remains, even with additional resources, due to the high number of UI iterations and user feedback cycles. • Decision: The decision is to proceed with detailed design and technical review for the custom Fiori app, with the intent to avoid impacting ITC1; if it is determined that the timeline cannot be met, the team will revisit the risk and decide whether to accept a late delivery, as the UI is not a showstopper for testing core functionality. Final approval is pending completion of the RICEFW process and further review with more details. • AR: Kevin Brown to complete the detailed design and tech review for the custom Fiori app for returns disposition management and return to the team with findings and a recommendation on whether the ITC1 timeline can be met or if risks remain. | [5 empty] | Other | CL/OSC | 2025-08-08 | 08, 2025 | 08, 2025 | 06, 2025 | 2025-06-24 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0868 | Cancelled |  | ERP | R4 (Release 4) | High | 04. OTC IF | 4.1 OTC IF - ALL |  | 05. OTC IP | Biplab Rout |  |  |  | CR1212 | [7 empty] | Implementation of SIMS Processes for Release 4 | Implementation of SIMS processes as part of R4 |  |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this CR will be combined with CR1212 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-24 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0869 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | graeme.johnson@intel.com |  | FTS IF - Haritha Komma | [8 empty] | WIINGS | EWM Addition of SiGaC Inventory Interface | Requesting an additional interface so SiGaC can extract inventory data from EWM to meet their existing business needs | SiGaC system needs to continue its business process of determining chemical aging and handling use cases which are based upon several inventory data points. These data points are currently accessible to SiGaC, but in the future they will be contained within EWM. The interface is required for EWM and SiGaC to share these data points. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0869%20-%20SiGaC%20Interface%20from%20EWM%20for%20GM%20data.pptx?d=w66d04afd20e646bcb16a0c5699355f8b&csf=1&web=1&e=K1EDUG | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | [10 empty] | Design | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R4 (Jul 2027) | R3 ITC1 | INT-CR0870 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [10 empty] | WIINGS | eDFIT Scope (Console ID 3035) | eDFIT retirement & implementation into S/4HANA Option 1: recommended based on lower costs and longer-term architectural benefits and alignment of moving to S/4 based architecture. Program to work on change management & adoption with key stakeholders and minimize the user productivity delta for end users post the initial change & adoption driven productivity dips | eDFIT (enterprise Duty Free Inventory Tracker) is an application within the WIINGS ecosystem used across sites in APAC (Malaysia, Chengdu, Vietnam, Costa Rica). Since WIINGS must be retired, a change request is required to determine how to re-implement eDFIT. | High: 3 conversion objects part of R3 scope​ Low: remaining 17 objects are a part of the R4 scope​ TBD: 12 ECA objects​ ​ Activity re-scheduling for 2 existing CMMS interface that are part of R4 scope:​ FTSI1371 – shifting FS end date from Sprint 15 to Sprint 16​ FTSI1355 – FS end date was Sprint 14, but will be completed in Sprint 15 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE74D6763-2F40-45BD-89BF-FCB1E98633BA%7D&file=INT-CR0870%20-%20eDFIT%20Scope.pptx&wdLOR=cAA7E7655-BF23-45F8-8758-FCF37CFD15B1&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 20 | FTSW1372, FTSI1538, FTSI1537, FTSI1536, FTSI1371, FTSI1370, FTSI1355, FTSE1549, FTSE1548, FTSE1547, FTSE1546, FTSE1545, FTSE1544, FTSE1543, FTSE1542, FTSE1541, FTSE1540, FTSE1539, FTSE1369, FTSE0982 |  | FTSW1372, FTSI1538, FTSI1537, FTSI1536, FTSI1371, FTSI1370, FTSI1355, FTSE1549, FTSE1548, FTSE1547, FTSE1546, FTSE1545, FTSE1544, FTSE1543, FTSE1542, FTSE1541, FTSE1540, FTSE1539, FTSE1369, FTSE0982 | 20 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-24 | o This request for new RICEFW’s are related to the recently closed eDFIT KDD | [9 empty] | Other | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-24 | 0 | < 15 Days | colkennedy@deloitte.com |  | No |  | In Progress |  | In Progress | No | Yes
|  | INT-CR0871 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 13. Security | gary.nilsen@intel.com |  | FPR - Aubrey Hinderlider |  |  | N/A | [6 empty] | FPR R3 Security Roles​ | 1- Add, remove, and modify various t-codes/Fiori apps to Treasury roles and add a check for the BP access to the rule set​ 2- Add various t-codes to FPR CORP - IT Support - Project Accounting role and merging it with the FPR CORP - IT Support – Fixed Asset and Project Accounting role​ 3- Create a display-only role both for general accounting and users outside of Finance​ 4- Transition cost accounting t-codes/Fiori apps from FTS-IF role to already-designed FPR roles​ 5- Duplicating the OTC-IF Finance Analyst role into OTC-IP​ 6- Duplicating the FPR IF – Intercompany Accountant role into IP​ 7- Remove access to sensitive BP groupings as ID’d by Treasury from roles where BP values are | Additional access needed outside defined L3 processes. Often, this access is needed for investigation and support and is almost always display only and low risk. ​ The new display-only role (#3) is intended to streamline access and reduce unnecessary silos and complexity. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0871,%200911,%200912/RE_%20SAP%20Security%20CRs%20has%20been%20updated_%20waiting%20your%20concurrence%20for%20be%20submitted%20to%20Anna.msg?csf=1&web=1&e=HNufpy | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/05.%20Security%20Champions/FPR/R3%20Change%20Request%20Info/Change%20Request%20-%20FPR%20R3%20Security%20Roles.pptx?d=w6863897783514aacb1079d5def3ad7bc&csf=1&web=1&e=LVV95Y |  | 6. Build Security-Related Changes |  |  |  | 39 | 0 | [11 empty] | 39 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Team is instructed to log into Build CR | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0872 | New |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF 05. OTC IP 09A. Master Data 11. Technology | Akshay Awasthi | [11 empty] | MDG changes to payers will be replicated in CFIN post Credit/Collections Roles extension to Payers in CFIN | MDG changes to payers will be replicated in CFIN post Credit/Collections Roles extension to Payers in CFIN |  |  | No | Core |  |  |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-25 | 287 | > 30 Days | aksawasthi@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0873 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [8 empty] | Anafi | Consumption of DTC to PCC and Interface between S4 and MAPPS to move DIE from IF to Substrate Supplier | Consumption of the DTC (component of the Substrate) against the PCC/ Interface requirement with MAPPS to get the STR created for shipping the Die to Substrate Supplier. | New Requirement for Anafi Supplier |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0873_FTS-IF_Consumption%20of%20DTC%20to%20PCC.pptx?d=w80b6642c395546a2adae5ceede42e3cf&csf=1&web=1&e=z75E2p | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | Yes |  | 1 | FTSI1573 |  | FTSI1573 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | [10 empty] | Other | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-25 | 0 | < 15 Days | njain42@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0874 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | New Requirements for PROSPAL replacement​ | A new interface for the Believe Handheld application will allow users to fetch lot list from S4 using either RSQ Batch ID or STO#​ A custom table to map and capture the relationship between RSQ Batch ID/STO# and the associated lots. | New requirement for Believe Integration ( PROSPAL replacement​) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0874_FTS-IF_New%20API%20from%20believe%20STO%20lots%20assigned%20to%20RSQ%20batch%20id.pptx?d=wf520b47263894b40994ffcee7021bee6&csf=1&web=1&e=rRaFUM | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  | 0 | 0 | [8 empty] | 800 |  |  |  |  | 0 | 800 | N/A | Yes |  | 2 | FTSI1574, FTSE1582 |  | FTSI1574, FTSE1582 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-17 | o In shipping, we are creating lot-level STO’s, and there is a feature in die prep or backend (RSQ) o This is required to scan the lots so that the shipments are completed. | [9 empty] | Design | Tower | 2025-07-17 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-25 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0875 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | Need a new Interface from SMH to S/4 to UNDO START. Production which will Reverse the Component Consumption of previous stage and Technically Complete Production Order | Need a new Interface from SMH to S/4 to UNDO START. Production which will Reverse the Component Consumption of previous stage and Technically Complete Production Order | New Object required for the interface from SMH to SAP to perform cancellation of goods issue |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/FTS/R3/PDF Orchestration INT-CR0875 - UNDO START.pptx?d=w54b12f5c6cd44678bbc6a6d56dce7680&csf=1&web=1&e=1ZEZAi |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes |  | 1 | FTSI1580 |  | FTSI1580 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-06-26 | [10 empty] | Other | Tower | 2025-06-26 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-25 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0877 | Approved | Added | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 09A. Master Data 11. Technology 16. Testing | chgorantla@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPRC0117 - Addition of new product types and Cash concentration fields in the input file | FPRC0117 - Addition of new product types and Cash concentration fields in the input file | The addition of the new product types - INTX and STDX to object FPRC0117 is required to support recently introduced business offerings. Furthermore, to ensure accurate creation of current accounts, it is necessary to include the cash concentration fields in the input file. | No Impact to existing deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0877_FPR_FPRC0117%20-%20Addition%20of%20new%20product%20types%20and%20Cash%20concentration%20fields%20in%20the%20input%20file.pptx?d=w44b2aa0ddd3f420ab116d5dbc8031533&csf=1&web=1&e=8pFexY |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 44 | 0 | [10 empty] | 44 |  |  | 0 | 44 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRC0117 | 1 | FPRC0117 | 1 |  | 0 |  | 0 | N/A |  | 2026-01-30 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-24 | o This is a request to add 2 new product types and cash concentration fields in the input file • This is only done in the CFIN box and is contained in treasury | [9 empty] | Build | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0878 | Approved | 2/24 - Based on Amy's feedback that this was ITC1*, but it needs to be brought back through a different CR | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 07. FTS IF 08. FTS IP 10. Analytics 13. Security 17. B-App | ron.bidgood@intel.com |  | FTS IP - Loni Adams | [6 empty] | 6032, 8785 | Commonality Analysis and Traceability Tools Suite (CATTS), Excursion Containment Disposition |  | Retain CATTS/TCA (traceability) and ECD (functionality) for IP | Ensure continued access to CATTS/TCA and ECD for the Intel Products QREs with the responsibility to trace and contain lots in the IP Warehouse.​ Request an exception to allow the CATTS/TCA system to pull data from both IF ECA and IP ECA and allow both IF and IP users to access the CATTS/TCA and ECD systems. ECD system must be able to block/contain inventory in both IF S/4 and IP S/4 | Intel Products (IP) faces critical challenges in managing traceability and containment across its supply chain, especially as it transitions under IDM 2.0. The current Plan of Record (POR) does not support scalable, automated traceability, and lot holds/disposition in the warehouse essential due to the complexity of operations involving lot splits, merges, and unit-level tracking.​ CATTS/TCA and ECD are currently used to trace and contain all IF and IP inventory, including inventory from external foundry and OSAT for IP. IP does not have an alternative method to trace IP owned inventory​ | Potential impact depending on how much effort is required from CATTS/TCA team to apply security. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Intel%20Products%20warehouse%20lot%20hold%20and%20containment%20CR.pptx?d=wdb7d93f633364b9f830989c474e33283&csf=1&web=1&e=cvlfT4 |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | Yes |  | 20 | FTSFV011_01, OTCPCV005, OTCPCV006, OTCPCV012, OTCFCV015, OTCFCV016, ECAFTSIPV6425, ECAFTSIPV4855, ECAFTSIPV5723, ECAFTSIFV6420, ECAMDV1974, ECAMDV2010, ECAMDV2023, ECAMDV2065, ECAMDV2069, ECAMDV2073, ECAMDV2083, ECAMDV2101, ECAMDV2110, ECAMDV2121 | 3095 |  | 0 | FTSFV011_01, OTCPCV005, OTCPCV006, OTCPCV012, OTCFCV015, OTCFCV016 | 6 | ECAFTSIPV6425, ECAFTSIPV4855, ECAFTSIPV5723, ECAFTSIFV6420, ECAMDV1974, ECAMDV2010, ECAMDV2023, ECAMDV2065, ECAMDV2069, ECAMDV2073, ECAMDV2083, ECAMDV2101, ECAMDV2110, ECAMDV2121 | 14 | 20 |  | 0 |  | 0 | 0 | ECAMDV1964, ECAMDV1948, ECAMDV1954, ECAMDV1997, ECAFTSIFV764, ECAFTSIFV766, FTSFV011_01 | 7 |  | 0 | ECAMDV1964, ECAMDV1948, ECAMDV1954, ECAMDV1997, ECAFTSIFV764, ECAFTSIFV766, FTSFV011_01 | 7 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-06-26 | o The boundary condition was that these would be IF only apps when the team went through it during the design workshops. • This request is to add for IP. • The team has a high-level idea of the design and efforts. |  |  | 2025-06-27 | • Issue: There was a discrepancy in the POR regarding whether CATTS, TCA, and ECD, tools used for quality traceability and holds—should be shared applications. • Problem: Without shared application status, IP cannot effectively trace quality issues through complex warehouse operations (e.g., merged/split lots). Manual processes have already led to quality escapes in Altera. • Next Steps: The E2E team confirmed these tools must be treated as shared applications to support IP traceability and compliance. • Technical Considerations: o Integration is needed with both IP S4 and IF S4 systems (previously only ECC). o Security and data access controls must be implemented to ensure appropriate visibility and permissions based on aligned with IP or IF. o Two integration options are being evaluated: direct connection vs. gateway-based separation. o Team to evaluate both simple (direct) and complex (gateway) integration options between CATTS TCA and IP systems. • Decision: Approved to proceed with the assessment. Return to Change Request Meeting for next steps. • AR: Anand Jha to conduct assessment from Deloitte perspective and provide the cost and timeline for design completion. • AR: Paul Whitlock to ensure IF (TD) can support the shared application model until a long-term IP quality solution is developed. • AR: Kelly Gerber and Todd Smith to validate the extent of changes required due to the dual S4 system integration and ensure security and data flow implications are fully understood. | 2025-08-15 | • Originally designed for IF only, the CR proposes extending CATTS, TCA, and ECD to IP due to missing traceability and containment capabilities on the IP side. • The design work was completed over six weeks by the TD automation team and logistics teams, including integration changes to support lot holds. • Development scope includes: o 3 new RICEFWs (medium complexity) o 1 modified RICEFW (~50 hours) o 1 new low-complexity customization in IPS4 o 2 ECA views (one for IP sized at 64 hours, IF view not yet sized) • The IF ECA view was recently designed and may be split into a separate CR if needed. • Targeted for ITC2 testing due to insufficient data maturity in ITC1. • Factory automation development will spill into Q1, aligning with ITC2. • Contingent approval was granted for the IF ECA view, pending sizing. • AR - Vanessa Clark - Size the IF ECA view and report back to team if estimates are significantly off |  |  |  | Other | CL/OSC | 2025-08-15 | 06, 2025 | 06, 2025 | 06, 2025 | 2025-06-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0879 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Need to drop LOGE1218 - Warehouse Monitor report on Disposition type. | LOGE1218 needs to be dropped. This reporting functionality can be achieved by a combination of Ship items screen RICEFW LOGE1221 and also the SAP standard Transportation cockpit. | LOGE1218 needs to be dropped. This reporting functionality can be achieved by a combination of Ship items screen RICEFW LOGE1221 and also the SAP standard Transportation cockpit. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0879%20and%20CR0882/RE%20Approval%20needed%20for%202%20CRs;%20CR879%20%20CR882.msg?csf=1&web=1&e=njIOTz |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1218 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-26 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0880 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 06. PTP 08. FTS IP 17. B-App | ananthakrishnan.padmanaban@intel.com |  | FTS IP - Loni Adams | [9 empty] | DTC & LSC Functionality for CMP IP | Type B Passive LSC(Land Side Capacitors) and DTC (Deep trench Capacitors) forecasting and Procurement capabilities in Intel Products | Type B passive –LSC and DTC forecasting for IP products was originally classified as a combined process & ownership under Intel Foundry with DSC (Die Side Capacitors). Later, based on IP/IF split, this functionality has been re-classified as IP ownership. With the ownership change, the LSC forecasting capabilities have to be separated out for IP & IF. | Additional Development work for Material PDH, ECA and CMP IBP functional team, which will go beyond current committed R3 build timelines of end of 2025 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_CMP-LSC-DTC-IP.pptx?d=w42bfac0d36ff40eba539b76c3e7121cb&csf=1&web=1&e=wPjVBF |  | 1. Process Scope / Design Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Duplicate of CR0925 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0881 | Cancelled |  | SCP | R3 (Release 3) |  | 08. FTS IP | 8.1 FTS IP - ALL |  | 03. FPR 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 10. Analytics 15. Cutover 18. SCP | kenneth.j.trueba@intel.com |  | Data - Julie Fawdington | [9 empty] | Material/Item Internal Description Attribute for FTS/OTC/FPR/Analytics | Enable the creation of an Internal Item description to be stored as a derived attribute of the material ID and made available for consumption in ECA. | *Approved and close per Ken. Several IAO towers & other business functions provided requirements that Internal Item descriptions include more intrinsic and usable information about the material IDs and that descriptions are standardized across the towers as master data. | No. If this change is not approved it will require additional development for each Tower/DSA to create their own Internal Item descriptions | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0xxx_FTS_CR_Internal_Item_Description.pptx?d=w5d1143cfcde2484a8fc6159a0fea90f4&csf=1&web=1&e=3om3gt |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CLOSED per Ken. Several IAO towers & other business functions provided requirements that Internal Item descriptions include more intrinsic and usable information about the material IDs and that descriptions are standardized across the towers as master data. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0882 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Need to drop LOGE1223 - Sending ULT update on Goods Issue | The ULT details can be populated in Ship Item screen instead of updating a Custom table, which can be utilized for tracking and tracing purpose. So the requirement can be captured in the existing object Ship item Screen object - LOGE1221 | The ULT details can be populated in Ship Item screen instead of updating a Custom table, which can be utilized for tracking and tracing purpose. So the requirement can be captured in the existing object Ship item Screen object - LOGE1221 |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0879%20and%20CR0882/RE%20Approval%20needed%20for%202%20CRs;%20CR879%20%20CR882.msg?csf=1&web=1&e=njIOTz |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1223 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-27 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0884 | Cancelled |  | ERP | R2 (Release 2) | [21 empty] | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-27 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0885 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Vinay Kumar Khandelwal | [11 empty] | The logic in the BADI for check SO Save must include the following: For the Sales Document Number and Line-Item Number, check LIPS table by passing SO number as VGBEL and SO Line number as VGPOS VGBEL Reference Document VGPOS Reference Item If no document found, then the custom code logic should be skipped completely. If documents found in LIPS but the sum of the value LIPS- LFIMG is Zero, then also skip the custom logic completely. Only when these two conditions are not met, the logic in the BADI check SO save must be executed | "The logic in the BADI for check SO Save must include the following: For the Sales Document Number and Line-Item Number, check LIPS table by passing SO number as VGBEL and SO Line number as VGPOS VGBEL Reference Document VGPOS Reference Item If no document found, then the custom code logic should be skipped completely. If documents found in LIPS but the sum of the value LIPS- LFIMG is Zero, then also skip the custom logic completely. Only when these two conditions are not met, the logic in the BADI check SO save must be executed" | There was defect 5723 , 5716 & 5678 as part of UAT2 defect which were blocking E2E scenario progression Hence this logic was implemented |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7Bffdc4320-c3aa-4046-bf89-4416ac4825b2%7D&action=edit&wdPreviousSession=3a2e8221-7b16-b3fa-fa89-2159260e5132 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-27 | 285 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0887 | Cancelled |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Vipul Shah |  |  |  | CR | [7 empty] | To add CIBR (Non - SAP System) as part of IP Batch Conversion | In R3 Batch Conversion for Intel Product – IP the scope considered under object FTS-IF-LOGC0972_IP-Batch Master Conversion was only from SAP ECC to S4 system. Recently we have identified that Non-SAP Systems like CIBR which will also be part of Batch conversion. For External OSAT, CIBR is the source of truth for Batch conversion. | Non-SAP Systems like CIBR for External OSAT which will also be part of Batch conversion as these batches must be migrated during the R3. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/INT-CR0887_FTS_IP_LE_To%20Add%20CIBR%20(non%20SAP%20system)%20as%20part%20of%20IP%20Batch%20Conversion.pptx?d=wceeac941edb34582ba4989816d54299b&csf=1&web=1&e=ajd76G |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | FDS is already developed. We are working through FUT. Status needs to be corrected in the Program CR tracker. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-27 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0888 | Rejected |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 10. Analytics | amanda.onopa@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | FPR Team 11 Needs an enterprise level view for a complete WBS ECA View Build | Deloitte Analytics is requesting a CR to add additional fields to the project accounting views they are currently building which would satisfy an enterprise level view catering to comprehensive reporting and B-Apps need. | A comprehensive view to meet WBS requirements end-to-end for all audiences. | Increase to 120 hours of work (estimated to finish this work within S15 per Farhan on Kritarth's team). Worst case S16. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B53320821-E600-496E-99A7-94FCCF30A17C%7D&file=CR0888%20-%20FPR%20Team%2011%20Needs%20an%20enterprise%20level%20view%20for%20a%20complete%20WBS%20ECA%20View%20Build.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-07-24 | [9 empty] | Confirmed by Aarti to not be required. | Build | Not Assigned |  | Not Approved | 07, 2025 | 06, 2025 | 2025-06-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0889 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) R4 (Release 4) R5 (Release 5) |  | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 08. FTS IP | benny.lee@intel.com |  | FTS IF - Haritha Komma |  | CR TBD for combining IP & IF in ECA Corp Zone | [7 empty] | MO Request & Response Process for Substrates | Consolidation of MO Request/Forecast, MO Response and BOH, WIP, On-Hold, Intransit data at ECA Corp Zone for data collaboration between Substrate Suppliers and Intel | IP & IF information should not be shared with each other. However, Intel needs to interact with Substrate supplier as one. Corp Zone is where consolidation of data will happen to Substrate supplier and disaggregation between IP & IF once data received back from Substrate Supplier | Additional Development work for Material PDH, ECA and ECA Corp Zone teams, which can potnetially go beyond current committed R3 build timelines of end of 2025 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_MO%20Request%20Response-Substrate.pptx?d=wd929ffcd4f954a6f8ddab9d51cce4077&csf=1&web=1&e=9CmfkY |  | 8. Non-Build Infrastructure-related Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This is a duplicate of CR0924 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 06, 2025 | 2025-06-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2m (October 2025) | N/A | INT-CR0890 | Approved | Confirmed with Shubham to be delivered after R2 | ERP | R2 Oct 2025 | Medium | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF 10. Analytics | [7 empty] | NA | Work In Progress |  |  |  | Calculation Change in ECA report. Report Name - RMA TPT | Incorrect Calculations in ECA Report | In RMA TPT report calculation is incorrect for field - TPT Goods Receipt Disposition / Inspection date |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0890%20OTC%20IF%20%E2%80%93%20Calculation%20Formula%20Changes%20in%20ECA%20Reports.pptx?d=wf4be0965ea184ba983c0ce4cce38ed52&csf=1&web=1&e=dUAWul |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 4 | [6 empty] | 20 |  |  |  | 0 | 20 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-22 | Confirmed by Vivek Sahni that this is approved, and the work is documented in Service Now | [8 empty] | Confirmed by Aarti and Neshat that it can be cancelled | Build | Tower | 2025-10-22 | 10, 2025 | 10, 2025 | 06, 2025 | 2025-06-30 | 0 | < 15 Days | sbharathalkude@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0891 | Approved | Presenter: Akshay Awasthi | ERP | R3 (Release 3) |  | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP 11. Technology | vprashantpotphode@deloitte.com |  | OTC IP - Teresa McNicol/Jon Benoist |  | INT-CR0149 | [7 empty] | Auto extension of C & C Roles AND CFIN replication issue for existing Payers from MDG | Changes needed: 1) Add automated BP role extension to new Payers as they move from MDG to CFIN. Implement BADI PARTNER_UPDATE in CFIN to automatically create Credit & Collection roles when a payer is created having specific account group 2) When Payer changes are replicated from MDG to CFIN, where Payer is already having Credit & Collection Roles, the Changes should be synced with CFIN and It should NOT give Sync error - "Unable to delete Credit & Collection roles" | 1) When a Payer is created in MDG and lands in S4/CFIN, the below roles should be extended automatically: Credit Management Collections Management Rationale: If payer role extension is manual, there is a risk that customer set-up will not be completed accurately, leading to overall delay in downstream processes (invoicing customers, credit checks, collections process) Manual payer set-up will be a new process. As a result, additional steps and time required to prevent or mitigate incorrect role extension This is a current OOB functionality available; loss of functionality in ECC today 2) When Payer changes are replicated from MDG to CFIN, where Payer is already having Credit & Collection Roles, the Changes should be synced with CFIN and It should NOT give Sync error - "Unable to delete Credit & Collection roles" Rationale: MDG system is always in Sync with CFIN system. However, as per Intel Design, Credit & Collections roles will be ONLY assigned in CFIN and not MDG. Hence, there is a Sync issue which happens whenever Payer is replicated from MDG to CFIN. Hence, In order to sync both the Systems, Whenever Changes are migrated from MDG to CFIN for already existing Payers, the C & C roles should be copied to Replication framework for incoming MDG data, so that the Incoming data from MDG & CFIN system are in Sync | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B25DB3B0A-E216-4944-AED6-B5A2BEE91889%7D&file=INT-CR0891%20-%20Auto%20extension%20of%20C%20%26%20C%20Roles%20AND%20CFIN%20replication%20issue%20for%20existing%20Payers%20from%20MDG.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [10 empty] | 115 |  |  | 0 | 115 | Data Migration Tech - MDG | No | Conversion | 0 | N/A | 3169 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0182_IP, DATE0313_IP, DATI0393_IP | 3 | DATC0182_IP, DATE0313_IP, DATI0393_IP | 3 |  | 0 |  | 0 | N/A |  | 2025-10-31 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o If we don’t proceed, then we can do a manual creation; there are risks. o Requirement will be ready for MC1 o This will cancel CR0149 (build has not started because there were technical challenges). o Conversion team is aligned to deliver by MC1. | [9 empty] | Build | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 06, 2025 | 2025-06-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0892 | Approved | Ganesh | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP 11. Technology | Ganesh Kumaresan | [11 empty] | BRF+ Extractor (API interface) to fetch the data saved in the BRF+ decision tables in S4 system for consumption in ECA. Send the Data to ECA system. | BRF+ Extractor (API interface) to fetch the data saved in the BRF+ decision tables in S4 system for consumption in ECA. Send the Data to ECA system. | This requirement has come from ECA team – Technical requirement ECA can be ingested with Standard & Custom (GUI) tables only , but TM based ECA Object contains data that is available within BRF+ condition decision tables which is a rule-based table of input and output columns & which cannot be ingested to ECA which is a limitation with ECA. Therefore, a custom extractor program needs to be developed. Along with the mechanism to send the data to ECA. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-%20CR0892-BRF+%20Extractor(API%20interface)%20to%20fetch%20the%20data%20saved%20in%20the%20BRF+%20conditions_.pptx?d=w01c6305ba6fa4016a163923296fdf10b&csf=1&web=1&e=WsUb7g |  | 2. New RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [8 empty] | 189 |  |  |  |  | 0 | 189 | N/A | Yes |  | 2 | LOGI1534_IP, LOGI1534_IF |  | LOGI1534_IP, LOGI1534_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | Already went through RICEFW and tech intake; CR is approved | [9 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 06, 2025 | 2025-06-30 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | Complete |  | Complete | No
|  | INT-CR0893 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 07. FTS IF 08. FTS IP | Ganesh Kumaresan | [11 empty] | ISM VMF scenario to be brought inscope for R3 | Bring ISM VMF scenario in scope for R3.ISM VMF scenario volume in 2025 is about 600 DN/Month with total of 704,000KG/Month | During the design discussion it was concluded that ISM VMF is not needed and later if business needed to bring it to scope. However now business advised that ISM VMF scenario volume in 2025 is about 600 DN/Month with total of 704,000KG/Month and this qualifies to bring in scope |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Ganesh that the work is less than 40 hours of tech effort | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-01 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0894 | Approved |  | ERP | R3 (Release 3) | Low | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Pabbisetty Harshavardhan | [11 empty] | Descoping PTPI0113_IF/IP: PO Close from Ariba to S/4 | Need to descope PTPI0113_IF/IP | Separate RICEFW was already approved & created for this same functionality. PTPI1128_IP/IF to send closure from S/4 to Ariba |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0894/EXT%20RE%20PO%20Closure%20Design%20Alternatives.msg?csf=1&web=1&e=5IAyqc |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0113_IF, PTPI0113_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-10 | [10 empty] | Other | Tower | 2025-09-10 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-01 | 0 | < 15 Days | pabharshavardhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0895 | Approved | Presenter: Murthy | ERP | R3 (Release 3) | Medium | 06. PTP | 6.1 PTP - ALL |  | 06. PTP | kalyan.r.dhanwantry@intel.com |  | PTP - Richard Taylor |  |  | RAID-TBD | [6 empty] | PTP Custom T codes | Total 4 T Codes: YMDAUDIT: Not having this transaction code, planners will have to manually update various Material Master fields in MM during the NPI YWDA_CAP_OA_UPLOAD: To upload ZCVO Outline agreement to validate the Supplier payment YWDA_CAP_DOWNLOAD: : To download the ZCVO agreement YWDA_CAP_RESULTS: Not having these 3 sequentially executed transaction would result in risk of over payment to supplier | Business functionality was provided in February as part of design, each T-Code Functionality will be listed withing the Template | No Impact to Existed Deliverables | Yes |  | Yes - Cari Shim | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0895_PTP%20PTP%20Custom%20T%20codes.pptx?web=1 | Missed Requirement | 1. Process Scope / Design Change |  | Yes | Medium |  | 2 | [12 empty] | n/a | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-04 | o The business knows the requirement, and this request is to explore the T-code in ECC and see if it can be encompassed in a Fiori app. o This is a request for an assessment. This is actually not a tech CR.  The PTP tower team will look through it from a process and design standpoint.  And then the team will come back with the tech estimates by 10/6. | [9 empty] | Design | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0896 | Approved |  | ERP | R3 (Release 3) | Medium | 11. Technology | 11.3 Technology - Middleware |  | 08. FTS IP | Harikrishna Vadigepalli Raghunath |  | Tech & Dev - John Camarillo | [9 empty] | Cancellation ¦ Removal of the RICEFW Object “LOGI0933” | Cancellation ¦ Removal of the RICEFW Object “LOGI0933” | "LOGI0933" object was considered for R3 release of IAO scope for middleware development. FS document was prepared by business and Deloitte functional consultants. When we started the HLTA document, Intel architects confirmed they do not need to build a new integration. Existing one can be leveraged. Hence, this object id will not fall under RICEFW bucket. This integration will take route of Retrofit (i.e rewiring the existing integrations to new endpoints). | No Impact | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0896/LOGI0933%20-%20cancelation%20of%20the%20RICEFW%20object.pdf?csf=1&web=1&e=L0rumS |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI0933 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-02 | 0 | < 15 Days | harikrishna.vadigepalli.raghunath@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0897 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 11. Technology 17. B-App | YASH DESHPANDE |  | PTP - Richard Taylor | [9 empty] | PTPI0136_IP_IF - Logic validation and mapping changes are needed as part of SAP S/4 to E2open outbound interface identified during FUT | PTPI0136 is PO outbound (3A13) interfaces which uses IDOC in SAP S/4 to send necessary PO data to E2open boundary app. Below logic and mapping changes are required to ensure accurate information to be sent to the suppliers which are onboarded on the boundary app E2open. Changes identified: 1. Business unit ID logic (E1EDK35 - CUSADD – 905) need to add logic validation for plant for FERT condition. 2. For E1EDP19 segment due to technical constraints we need to remove E1EDP19 “902 and 903” for EAN and UPC field as the IDOC is getting extended 7 time creating IDOC syntax error. As per alignment with MDG team captured in FSD a common field E1EDP19 003 standard field from IDOC can be used for this. 3. FTS team confirmed they have not received requirement to maintained MDMA table (MRP area for materials) , MRP group and MRP group description logic needs to change from MDMA table to MARC table. 4. Logic validation for E2open Doctype field/ Usage indicator fields. -> Need to add BOX validation for 3 fields , Usage Indicator,E2open Doc Type, Original receiving site. -> Usage indicator -> "For GR – If Business group ODM and EKKO-BSART – ZNB, then Display GR else blank " Logic condition needs to be removed. -> Need to remove "If Business Group(Value 3) – ODM, then Display ASN , Else blank" validation from logic. -> For SIMS plant , Display ASN value in usage indicator field. -> For ZSUB Doc type for SIMS, Doc type validation needs to be added under ODM BIZ for Custom fields wherever applicable. 5. PARVW BP/AG - ZTPTP_BILL_TO_DT table -> BP and AG are not partner functions, these will be a custom segment in IDOC, and address values will be fetched directly from BILL_TO table based on the given logic in each field. 6.To update the E2openDocType/Usage Indicators field with new values with IAO in them , this to Handle the Straddle in effective way from E2open Side. | PTPI0136/37 is PO outbound interfaces which use IDOC to send necessary PO data to boundary apps. The changes provided by this CR will allow accurate information to be sent to the suppliers which are onboarded on the boundary app E2open. If the changes are not incorporated certain necessary fields and accurate information will not be sent to suppliers |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAA10F36F-F21A-41C9-AB72-39816EBC7D00%7D&file=INT-CR0897.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 78 | 0 | [8 empty] | 78 |  |  |  |  | 0 | 78 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0138_IF, PTPI0136_IF, PTPI0136_IP, PTPI0137_IF, PTPI0137_IP | 5 | PTPI0138_IF, PTPI0136_IF, PTPI0136_IP, PTPI0137_IF, PTPI0137_IP | 5 |  | 0 |  | 0 | N/A |  | 2025-08-29 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | o This is a standard change and procedure. • The request came in from the E2Open team during testing of this object and originated from changes to the IDOC. It is a request to add in fields. o The team is aiming to have the changes completed to meet the original FUT date. | [9 empty] | Build | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-02 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0898 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Kolleru Venkatesh |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSI1324 | Request the cancellation of Object FTSI1324 Inteface- M-100-170_API 10 is for Lab manual traveler connecting to HVPIP app | As PROSPAL is going to be replace by WIP Inventory in S4,All shipment from Factory to IP Lab will follow sales order process and Lab location details we should be able to pull from SAP Plant Location. Hence this interface no longer needed in WIP inventory. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/EXT%20RE%20Req%20for%20Cancellation%20of%20FTS-IF%20object%20FTSI1324.msg?csf=1&web=1&e=BH5NHe |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1324 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | [10 empty] | Other | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-03 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0899 | Rejected |  | ERP | R2 (Release 2) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | suprabhas@deloitte.com |  | FTS IF - Haritha Komma |  |  | N/A | [6 empty] | Access Request to new Standard Fiori App in EWM system | This CR is created for access of Fiori App - Stock Comparison Fiori app (/SCWM/ERP_STOCKCHECK) and being requested for all site-specific Ground Controller and Inventory Area Manager roles. | Stock Comparison Fiori app (/SCWM/ERP_STOCKCHECK) is a report and used check for stock differences between S/4HANA and EWM for specific materials on daily basis by business | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8F94ACF9-6DE2-4C9D-8FC7-77A1D9CBC242%7D&file=INT-CR0899-Change%20Request%20for%20EWM%20Fiori%20App.pptx&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  |  |  | 10 | 0 | [11 empty] | 10 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-07-31 | [9 empty] | Confirmed by Ruben that this change is already in the environment. Therefore, this CR is no longer required. | Build | Not Assigned |  | Not Approved | 07, 2025 | 07, 2025 | 2025-07-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | R2 | INT-CR0900 | Approved |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics 17. B-App | yacov.torchinsky@intel.com |  | FTS IF - Haritha Komma |  | CR0746 | [7 empty] | IAO R2 – Unexpected Design Change Requires Boundary Applications Change (POWER/XETA)- Showstopper | The recent design change initiated by R2 Architecture Team has introduced a new signal called "Demand Schedule." Demand signal will replace the existing POR schedule used by Manufacturing and Planning as the weekly target. POWER and XETA systems need to adjust their sources to pull Demand Schedules from SPAN. POWER is the POR tool used to monitor current week actual PAS by stage and facility, including the OTD indicator. XETA remains the scheduling and production control system for the manufacturing floor in R2 as POR system in D1 and F11x, while other facilities transition to FSCO. With the introduction of the Demand Schedule, both POWER and XETA systems must switch to consume this signal as the schedule target. *FSCO has development in process to get the demand signal from SPAN. | Failure to implement these changes will result in factories lacking a POR schedule to meet floor targets and fulfill customer commitments. The absence of the POWER system in R2 means there will be no capability to track the current week's customer commit PAS or monitor the OTD indicator. Change needs to be implemented before UAT2 to be able to test POWER and XETA within R2 architecture. | The CR is a showstopper for R2 from MFG and Planning perspective. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR0900%20%E2%80%93%20Unexpected%20Design%20Change%20Requires%20Boundary%20Applications%20Change%20POWER%26XETA%20Showstopper.pptx?d=w0fb15759e06344ed9b920c43744df889&csf=1&web=1&e=iRvyxU |  | 8. Non-Build Infrastructure-related Change |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-10 | o CR0746 didn’t fully encompass the E2E impact. So, this CR will expand upon it as it is critical for R2. o Everything is the same format. This request is to adjust the logic to point to different data. o The POWER and XETA teams will be impacted. o AR: Include this risk to the list of risks impacting R3 – Sunil N. |  |  | 2025-07-11 | • Minor change is needed to switch from the POR supply schedule to the demand schedule for Power and Zeta applications. • The change is technically simple—just a filter switch—but requires a minor update on the Power side. • Confirmed the change intersects with UAT2 which adds a small risk, and has low impact on R3 due to internal adjustments. • Delivery is expected by WW30, following the availability of the Span solution in WW28.4. • Estimated effort: 50–60 hours total, with 20–30 hours for build. | [5 empty] | Other | CL/OSC | 2025-07-11 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0901 | Approved |  | ERP | R3 (Release 3) | Low | 04. OTC IF | 10.4 Analytics - OTC IF |  | 04. OTC IF 05. OTC IP 10. Analytics | Sheila Nguyen |  | OTC IF - Angela Laskowski | [9 empty] | Cancelling OTCFV027 - Manufacturing | Cancelling an object on the Deloitte ECA object tracker. Discovered that a similar report under R2 is able to fulfill the requirement | Since a similar report is able to meet business requirements, keeping the object would result in duplicate work. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0753,%20CR0905,%20CR0901/RE%20Deloitte%20ECA%20Objects%20Cancellation.msg?csf=1&web=1&e=QhxdY2 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCFV027 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-23 | [10 empty] | Other | Tower | 2025-07-23 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-04 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0902 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 10. Analytics 11. Technology | Sekhar Lingam | [11 empty] | Change Request for New RICEFW_Interface to post inventory in SAP S/4HANA using a custom movement type from ECA to S4 via MuleSoft.​ | Interface to post inventory in SAP S/4HANA using a custom movement type from ECA to S4 via MuleSoft. | Business requires an automated process to post EMIB Die inventory in SAP S/4HANA using a custom movement type to support the costing and inventory visibility in S4 ​​Scheduled MuleSoft. job runs twice daily (end of day) to pull inventory data from the ECA.​ MuleSoft. performs standard SAP validations, transforms and maps the data to the structure required by the SAP BAPI, and logs results and errors and notifies support team as needed​ MuleSoft. calls the standard SAP BAPI (e.g., BAPI_GOODSMVT_CREATE) to post inventory in S/4HANA using the custom movement type, and S/4HANA processes the posting and returns the status to MuleSoft.ECA will be fed from CIBR the 7B1 message for EMIB Die from external substrate supplier​ Once inventory data is captured in S4, PCC will consume the EMIB Die (This is captured in iCost today and needs to be replicated in S4 in R3)​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0902%20%E2%80%93Change%20Request%20for%20Interface%20to%20post%20inventory%20in%20SAP%20S4HANA%20using%20a%20custom%20movement%20type%20from%20ECA%20to%20S4%20via%20BODS.pptx?d=w151bd6ba9d0440af8ad362e927adada7&csf=1&web=1&e=b1DvYa |  | 2. New RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | LOGI1584 |  | LOGI1584 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-24 | o Change Description: Change Request for New RICEFW_Interface to post inventory in SAP S/4HANA using a custom movement type from ECA to S4 via BODS o Purpose of this interface is to support EMIB process using product cost collector model, and the business requirement is to consume the EMIB die. o AR: Update slide to remove “custom movement type” from the details o AR: Add in process flow for clarification o AR: Review effort with Sunil and bring back to CR Ingestion | 2025-07-31 | o Purpose of this interface is to support EMIB process using product cost collector model. • This process is being used currently and is being standardized in S4. FPR team is aligned to this change. • POC is demonstrated and aligned with all of the stakeholders o Confirmed with ECA, and the tech team wants to do this work sooner as there is an ECA complexity • It has been confirmed that ECA has all of the data objects | [7 empty] | Other | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-04 | 0 | < 15 Days | akindore@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0903 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Ramagiri Pradeep Kumar | [11 empty] | Need to cancel the Enhancement PTPE1436_IP/IF. | PTPE1436_IP/IF - Enhancement required to populate custom logic for BLAOCH | PTPE1436 & PTPE1437 are the enhancement of the IDOC and both carry same logic and same user exit except different message type. From technical point of view, it make no difference. Hence, we are requesting to combine these two RICEFW into one. | NA | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0903/RE%20INT-CR0903%20cancelling%20WRICEF%20ID%20PTPE1436_IP_IF.msg?csf=1&web=1&e=lGlwXt |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 30 |  |  |  |  | 0 | 30 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE1436_IP, PTPE1436_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | [10 empty] | Other | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-04 | 0 | < 15 Days | ramagkumar@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0904 | Cancelled |  | ERP | R3 (Release 3) | Low | 10. Analytics | 10.4 Analytics - OTC IF |  | 04. OTC IF 05. OTC IP 10. Analytics | Sheila Nguyen |  | OTC IF - Angela Laskowski | [9 empty] | Cancelling OTCFV027 (R3) report as a similar report in R2 can fufill business requirements. | Canceling object OTCFV027. Business has realized that a similar report created in R2 can satisfy the reporting requirements. | Will result in duplicate work if not cancelled |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Sheila that CR0904 is a duplicate of CR0901 | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 07, 2025 | 2025-07-07 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0905 | Approved |  | ERP | R3 (Release 3) | Low | 06. PTP | 10.8 Analytics - PTP |  | 06. PTP 10. Analytics | Sheila Nguyen |  | PTP - Richard Taylor | [9 empty] | Cancelling 4 PTP ECA Objects on the Deloitte ECA Object Tracker | Cancelling 4 objects on the Deloitte ECA Object Tracker. LOGV011_PTPX is replaced by PTPV012. LOGV012_PTPX is replaced by PTPV010. LOGV013_PTPX is replaced by ECAPTPV021 (Intel build). LOGV015_PTPX is replaced by ECAPTPV033 (Intel build). All are FS not started. | Will result in duplicate work if not cancelled |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0753,%20CR0905,%20CR0901/RE%20Deloitte%20ECA%20Objects%20Cancellation.msg?csf=1&web=1&e=QhxdY2 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGV011_PTPX, LOGV012_PTPX, LOGV013_PTPX, LOGV015_PTPX |  |  | 4 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-23 | [10 empty] | Other | Tower | 2025-07-23 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-07 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0906 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP 11. Technology | Pramod Kalli Srinivas | [11 empty] | Interface to Read the EEPM and DECODER Matrix | An outbound Interface to Read the EEPM and DECODER Matrix from S4 to OL | OTCI1178 -Need an interface from OL to S4 for R4C (Sales Force) to read the EEPM and Decoder Matrix. EEPM Matrix and Decoder Matrix are used only for Entitlement Check from OL and not to read from Salesforce directly like other matrices. Also, both EEPM & Decoder matrices are not relevant for SAP EMS. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0906_OTC%20IP%20%20An%20interface%20to%20Read%20the%20EEPM%20and%20DECODER%20Matrix.pptx?d=w7c03dfa03ae245f4a18ece688b9e18b8&csf=1&web=1&e=9cqGR7 |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | OTCI1598 |  | OTCI1598 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-31 | o This is a new interface requirement to have one that reads EEPM and Decoder Matrix from S4 • These business matrixes will be stored in S4 and will be read from OL through interface o This is needed because it is decoupled | [9 empty] | Other | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-07 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0907 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [11 empty] | Board Failure Form Scope (Console ID 3042) | Board Failure Form Scope | Solution Description:​ A custom UI screen to capture the Board Failure Form details.​ 3 Custom tables to store the BFF config details​ CRD Screen updates for BFF​ Interface FTSI0924 update to capture the custom fields from BFF |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B595F80B3-CA22-4117-A4C2-5E88E34E5F17%7D&file=INT-CR0907%20-%20Board%20Failure%20Form%20Scope.pptx&wdLOR=c28490A19-6E5F-4DBD-ABEC-F258076D3523&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [8 empty] | 42 |  |  |  |  | 0 | 42 | Tech - Middleware Tech - S/4 | Yes |  | 1 | FTSI0924 |  | FTSI0924 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSE1358, FTSI0924 | 2 | FTSE1358, FTSI0924 | 2 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-24 | o This is board failure form needs 3 new custom Z tables and will interface the data over to IMR • Pre-approval of this to proceed with work that needs to get done as it is business critical for IMR | [9 empty] | Other | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-08 | 0 | < 15 Days | colkennedy@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0908 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.1 PTP - ALL |  | 06. PTP 11. Technology | Sugandh Gupta | [11 empty] | CR required to change the structure of ZTPTP_BILL_TO_DT table as per latest alignment with business. | CR required to change the structure of ZTPTP_BILL_TO_DT table as per latest alignment with business to include the ARIBA related changes in table. 1. We have to input the company code, company code country key – Plant region in field State ISO code and get the address. 2. If the address is not maintained with state ISO key combination, we should consider default address maintained for each company code with default key maintained with “X”. 3. User has to maintain state ISO key with “company code country key-Plant region key” (example: “IN-KA”) without any space between the values. | To include ARIBA related changes in table, we need to change the structure of table. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5FEE210B-D7F8-44BA-8EFB-65EC32EFD2BC%7D&file=INT-CR0908_PTP_IP_IF.pptx&wdLOR=c52C0B47C-C023-4B13-8C9D-7516D4820D42&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [8 empty] | 90 |  |  |  |  | 0 | 90 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPE0543_IP, PTPE0543_IF, PTPI0136_IP, PTPI0136_IF, PTPI0138_IF, PTPF0014_IF, PTPF0015_IP | 7 | PTPE0543_IP, PTPE0543_IF, PTPI0136_IP, PTPI0136_IF, PTPI0138_IF, PTPF0014_IF, PTPF0015_IP | 7 |  | 0 |  | 0 | N/A |  | 2025-10-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-31 | o This is for build to order. There is a table to store the details, and the addresses are recorded when creating invoices. The invoices need to be communicated to Ariba. • A few modifications are required (mainly in region code level). | [9 empty] | Build | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-08 | 0 | < 15 Days | suggupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR0909 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 02. E2E Process Integration 05. OTC IP | Chandrakanth Elancheran |  |  |  |  | RAID 01365 | [6 empty] | CR for IDD E2E requirement gathering & design review​ | The CR is for requirement gathering & review of design solution for the below user story :​ Intel is reevaluating the Intel Demo Depot (IDD) fulfillment process following the removal of the planned ISM integration from the IAO scope. ​ The ISM interface was deprioritized due to resource constraints, shifting business priorities, and minimal impact to business value.​ To ensure continuity and compliance, a replacement process is needed. A SO/PO model using a generic IPN has been proposed but will need overall E2E coordination for completion. | The ISM interface was deprioritized due to resource constraints, shifting business priorities, and minimal impact to business value. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7A947F04-4718-4DEC-9A7D-03A4E1B38665%7D&file=INT-BUILD-CR0909%20-%20CR%20for%20IDD%20E2E%20requirement%20gathering%20&%20design%20review.pptx=&action=edit&mobileredirect=true&previoussessionid=812d2329-82ff-a0cc-5dcd-b392b0f18e4f | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  | 80 | 0 |  |  | 80 | [10 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-17 | o This is a CR to understand the process for IDD (demo depot) and propose alternatives • This request is to do the requirements gathering and propose design o AR: Update slide to ensure all impacted teams are captured and what roles are required to complete the analysis o AR: Include when the analysis will be complete |  |  | 2025-07-18 | Request: Requirement gathering and review of design solution for the below user story : • Intel is reevaluating the Intel Demo Depot (IDD) fulfillment process following the removal of the planned ISM integration from the IAO scope. • The ISM interface was deprioritized due to resource constraints, shifting business priorities, and minimal impact to business value. • To ensure continuity and compliance, a replacement process is needed. The new SAP Fiori App that replaces ISM is NSO, No Stock Orders. • A SO/PO model using a generic IPN has been proposed but will need overall E2E coordination for completion. • Effort: Functional Estimate is 80 hours for the initial assessment E2E, OM, Logistics, PTP. Team will perform assessment in less time than 80 hours. o FPR, Master Data, B-Apps representatives will only be included in the assessment if SO/PO model isn't viable. • Decision: Approved to assess the requirements gathering and review of design solution for Intel Demo Depot with E2E, OM, Logistics, PTP and IDD representatives. | 2025-09-05 | • Presented a follow-up on a previous change request (CR) regarding Intel Demo Depot (IDD) shipping processes. The team was asked to explore Option 1, which treats IDD as outside IAO, allowing them to build and ship products using the new Intel shipping memo capability. • During investigation, it was found that inappropriate items (e.g., wafers, finished goods) were being shipped under the Demo Depot category, raising concerns from the trade group. • The proposed solution includes: o Proceeding with Option 1. o Creating non-valuated, non-inventory materials for IDD. o Consulting with Global Trade for compliance. o Introducing a new item class specific to IDD to restrict access via security controls. o Using the NSO (Non-Stock Shipping Order) Fiori app with added security layers. • The goal is to prevent unauthorized use of shipping categories and enforce proper trade compliance through process controls and security restrictions. • The design is considered closed, and the next step is to implement the solution through new CRs. • Next steps: o Finalize Security Design: Define and implement security controls to restrict access to the new item class for authorized IDD personnel only. o Coordinate with Global Trade: Ensure IDD consults with Global Trade for each shipment to maintain compliance. o Develop New CRs: Submit new change requests to implement the proposed item class and security enhancements. o Assign Ownership: Identify and assign long-term ownership for maintaining the new item class and associated processes. • AR - Jo Guedes - Confirm Deloitte’s resourcing and timing for Demo Depot (NSO) security changes. • Decision: Intel Demo Depot will proceed with option one and implement the solution through new CRs. |  |  |  | Design | CL/OSC | 2025-09-05 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-08 | 0 | < 15 Days | celancheran@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0910 | Cancelled |  | ERP | R3 (Release 3) |  | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP 13. Security | rawasthi@deloitte.com |  | FTS IP - Loni Adams |  |  | NA | [6 empty] | To Add new security role and update exiting one’s based on business requirement for ISM process | After finalizing the FDS for the ISM Fiori app, we identified role-related gaps and updated existing application accesses to better align with changing business requirements. | The business team identified a new role requirement after the design phase was finalized by the Deloitte Security team, necessitating the creation of this Change Request (CR). These changes are being implemented to provide business users with the access they have requested in order to effectively perform their tasks and meet operational requirements while using the ISM Fiori app within the S4 environment. | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0909_ISM%20Security%20roles%20changes.pptx?d=w62c0fe1be7b248ab88f4f9a2e5f39b8c&csf=1&web=1&e=v4O9tw |  | 6. Build Security-Related Changes |  |  |  | 6 | 0 | [11 empty] | 6 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Less than 40 hours of technical effort. Build CR created | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0911 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 13. Security | gary.nilsen@intel.com |  | FPR - Aubrey Hinderlider |  |  | N/A | [6 empty] | FPR Security – Treasury Role Adjustments | 1- Add, remove, and modify various t-codes/Fiori apps to Treasury roles and add a check for the BP access to the rule set 2- Remove access to sensitive BP groupings as ID’d by Treasury from roles where BP values are “*” | Additional access needed outside defined L3 processes. Often, this access is needed for investigation and support and is almost always display only and low risk. Also ensures privacy requirements are met. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0871,%200911,%200912/RE_%20SAP%20Security%20CRs%20has%20been%20updated_%20waiting%20your%20concurrence%20for%20be%20submitted%20to%20Anna.msg?csf=1&web=1&e=HNufpy | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/05.%20Security%20Champions/FPR/R3%20Change%20Request%20Info/Change%20Request%20-%20FPR%20Security%20-%20Treasury%20Role%20Adjustments.pptx?d=w57dc7bbbd20745829881f90faa6639b2&csf=1&web=1&e=SEzx21 |  | 6. Build Security-Related Changes |  |  |  | 25 | 0 | [11 empty] | 25 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is less than 40 hours of technical effort. Team instructed to log into the Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0912 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 13. Security | gary.nilsen@intel.com |  | FPR - Aubrey Hinderlider |  |  | N/A | [6 empty] | FPR Security – Role Changes | 1- Create a display-only role both for general accounting and users outside of Finance 2- Transition cost accounting t-codes/Fiori apps from FTS-IF role to already-designed FPR roles 3- Duplicating the OTC-IF Finance Analyst role into OTC-IP 4- Duplicating the FPR IF – Intercompany Accountant role into IP | Additional access needed outside defined L3 processes. Often, this access is needed for investigation and support and is almost always display only and low risk. The new display-only role (#1) is intended to streamline access and reduce unnecessary silos and complexity. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0871,%200911,%200912/RE_%20SAP%20Security%20CRs%20has%20been%20updated_%20waiting%20your%20concurrence%20for%20be%20submitted%20to%20Anna.msg?csf=1&web=1&e=HNufpy | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/05.%20Security%20Champions/FPR/R3%20Change%20Request%20Info/Change%20Request%20-%20FPR%20Security%20-%20Role%20Changes.pptx?d=wa389b6a4da99435da837942660a485a3&csf=1&web=1&e=yr4NEV |  | 6. Build Security-Related Changes |  |  |  | 25 | 0 | [11 empty] | 25 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is less than 40 hours of technical effort. Team instructed to log into the Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0913 | Approved |  | SCP | R2 (Release 2) |  | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP 13. Security 16. Testing | anthony.romano@intel.com |  | FTS IP - Loni Adams |  |  | N/A | [6 empty] | BY CDP View (UI/UX) Changes | Change in Sub processes and Planning view structure in BY CDP based on UAT 1 Learnings and to align with business defined planner workflow. | Initial/current pivot views were as per SDD but considering the learnings in UAT1 and To-Be workflows , there is need to reconfigure the subprocesses and pivot views in CDP for better adoption of tool | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20CCB%20BY%20CDP%20View%20Changes.pptx?d=w8595f931d1284a67b1168027b1e77bd4&csf=1&web=1&e=EYuFZp |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 65 | 0 | [6 empty] | 65 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-10 | o This is a low risk as the changes are confined to BY; data will not be pulled or sent. • This will become part of our R3 design if we do not implement now for R2. So, this is not a risk for R3, and this work will not impact the BY developers working through the current bug fixes. • This is not a showstopper as there is a process to export and import data, but it is not smooth. These changes will greatly enhance the value of the views for the teams | [9 empty] | Build | Tower | 2025-07-10 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0914 | Approved |  | ERP | R2 (Release 2) | Very High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 06. PTP 07. FTS IF 11. Technology 16. Testing | Meenakshi.lawrence@intel.com |  | OTC IF - Angela Laskowski |  | CR0774 | [7 empty] | China Tariff Impact - Shipping Label Changes | CR0774 was approved to proceed with the impact analysis. The analysis has been completed, and the build impacts are detailed in this request. | Compliance and quick response to changing cross-border Trade rules. Recently China customs announcing a new Rule 58 for Tariffs, impacting all shipments to China and from China. ITG confirmed (1) fabrication country as Country Of Origin (COO) for integrated circuits (instead of Assembly country) for imports into China (2) New Logic for determination of Functional / Compute Die (3) New Label formats for MBB, iBox, Shipping Labels. | No impact to existing deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0914%20-%20China%20Tariff%20Impact%20-%20Shipping%20Label%20Changes%20.pptx?d=w4190b6ee8eef4a64982bf8ef6f849767&csf=1&web=1&e=o98Lfc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 50 | 0 | [8 empty] | 50 |  |  |  |  | 0 | 50 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0354_IF, LOGF0342_IF, LOGF0347_IF, LOGF0357_IF, LOGF0346_IF, LOGF0353_IF, LOGF0345_IF, LOGF0344_IF, LOGF0343_IF, LOGI0278 | 10 | LOGF0354_IF, LOGF0342_IF, LOGF0347_IF, LOGF0357_IF, LOGF0346_IF, LOGF0353_IF, LOGF0345_IF, LOGF0344_IF, LOGF0343_IF, LOGI0278 | 10 |  | 0 |  | 0 | N/A |  | 2025-07-15 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-09 | Approved offline with Uzma on 7/9. Tech to proceed with work | [9 empty] | Build | Tower | 2025-07-09 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0915 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Prabesh Acharya | [11 empty] | Inclusion of only Non Bailed Orders into RAR (Incoterm D) - IF | For Intel Foundry, only Incoterm D orders are applicable for RAR processing. Additionally, there is a new requirement to include only non-bailed orders in RAR. To address this, it is necessary to identify and evaluate potential options, as well as to consider required customizations and modifications to the existing design. Collaboration will be required between the OTC-OM, MM-Master Data, and RAR team to design and implement this solution. | Requirement of Business to do Revenue deferrals and postings for Order having non bailed Materials needs to be done thru RAR only. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0915%20-%20Inclusion%20of%20only%20Non%20Bailed%20orders%20Into%20RAR.pptx?d=w8ba1b04e0bb041a99748f2804901375d&csf=1&web=1&e=e8etDb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is confirmed by Pramod Kulkarni that this is a build CR, not a design one. Technical effort is less than 30 hours. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-09 | 0 | < 15 Days | ppranavyogesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0916 | Cancelled |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 07. FTS IF 08. FTS IP | Mubashir Ghazi | [11 empty] | Material master Image attachment conversion | Images from WIINGS system need to be uploaded in S4 system against the material master | Required for PM and EWM processes |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0916_MDG_Material%20Master_CR%20Material%20master%20Image%20attachment%20conversion%20.pptx?d=w5189d25f0eee4288a200d3098ef0414b&csf=1&web=1&e=f0HCih |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Lilibeth that a conversion program was already created to complete this work: DATC1556 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-09 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0917 | Cancelled |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 03. FPR 09A. Master Data | Mubashir Ghazi | [11 empty] | Capacity Corridor and Capacity Group Characteristic | Derive the value of CC/CG based on DOT process and update material master | Finance process require the data |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0917_MDG_Material%20Master_CR%20Capacity%20Corridor%20and%20Capacity%20Group%20Characteristic.pptx?d=w315759555d7a4aa6950cc3d784e0c55b&csf=1&web=1&e=U7NrHb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the technical effort is less than 40 hours. Instructed team to log in Build CR Log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-09 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0918 | Approved | Presenter: Lilibeth | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP 09A. Master Data | Mubashir Ghazi |  |  |  |  | RAID 0936 | [6 empty] | Enhancement to create PROC material | Automate the material master creation process based on the information received from SPEED | To avoid manual intervention |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0918_MDG_Material%20Master_CR%20Enhancement%20to%20create%20PROC%20material.pptx?d=we1725344c7784a418cac4f5f87b1ab62&csf=1&web=1&e=0ocx0X |  | 2. New RICEFW / ECA / Build Object | MDM-150-010 MDM-150-020 MDM-150-030 MDM-150-040 MDM-150-050 MDM-150-060 MDM-150-070 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 3 | DATI1618_IP, DATI1618_IF, DATE1615 |  | DATI1618_IP, DATI1618_IF, DATE1615 | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-08-07 | o RAID 0936 was created in anticipation of the BOM activities growing beyond what the team can manage. CR0918 and CR1013 was created to bring in automations that will reduce the data load. • FTS IF and IP are aligned. o AR: Add in the following details to the deck: - @Linnell, Candice S @Lejarde, Lilibeth • Details on why the team is changing now • There is no budget implications. • It will miss ITC1 and will not affect anyone but the MDG team • The CR is a request for an extension of time, and there are no tradeoffs. • Not a priority for MDG, but the team will prioritize it and reassess in December |  |  | 2025-08-08 | • The enhancement aims to automate the creation of PROC materials (a new material type used to consolidate or group core products) in SAP MDG, rather than manually generating them in SPEED, to reduce manual effort and improve data consistency as item BOM data volume increases. The automation will apply business rules to generate PROC items directly in MDG, leveraging data from UPI and BOMs in S4, with the possibility to exclude certain scenarios (e.g., OSAT/vendor-sourced materials) during detailed design. The solution will involve an interface between MDG and S4 to read BOM data, and the automation logic will be refined during detailed design to handle exceptions and ensure correct PROC creation. • There are concerns about complexity, budget implications, and readiness for review; further design work and clarification are needed before final approval. The topic will be revisited in a future meeting after more detailed analysis. • Decision: No final decision was made; the enhancement is considered a draft and requires further design work, clarification of business rules, and assessment of budget implications before approval. | 2025-08-15 | • Objective: Automate creation of procurement items directly in SAP to reduce manual effort and improve data quality. • Rationale: These items are not needed in Speed or future PLM; automation eliminates redundancy. • Status: Alignment achieved with Kumar Vytla on business rules and rationale. • Approved: Confirmed by Mike Lange • Testing: Manual creation will be used during ITC1; automation will be implemented for ITC2. |  |  |  | Other | CL/OSC | 2025-08-15 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-09 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0919 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Mubashir Ghazi | [11 empty] | Descope Turnkey RICEFW Objects | Descope DATI1496 DATI1497_IP DATI1497_CFIN DATI1497_IF objects related to Turnkey Indicator | Functionality descoped for R3 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-08-07 |  |  |  | 2025-08-08 | [6 empty] | Other | Tower | 2025-08-07 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-09 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0920 | New |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | karthp@deloitte.com |  | FTS IF - Haritha Komma |  |  | NA | [6 empty] | Commercial Invoice, Consolidated commercial invoice and Packing list for WIP | 3 forms to be printed for WIP (semi-finished goods) as this documentation is required to support the movement and tracking of these items. Form 1: Packing list Form 2: Commercial invoice Form 3: Consolidated commercial invoice. | The current R2 commercial invoice, consolidated commercial invoice, and packing list will be enhanced by adding several additional fields to meet new business requirements. To prevent any disruptions to existing forms, these updated versions will be created as new forms. | No Impact to existing deliverables | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-09 | 273 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0921 | Cancelled |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF | lorinda.m.braun@intel.com |  | E2E - Aishwarya Bhat |  | CR | [7 empty] | Addition of Demand Schedule in POWER application | With the introduction of the Demand Schedule, it is imperative that both POWER and XETA systems switch to consuming this signal as their schedule target. | Failure to implement these changes will result in factories lacking a POR schedule, hindering their ability to meet floor targets and fulfill customer commitments. | R2 Showstopper | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/SCP/CR0900 %E2%80%93 Unexpected Design Change Requires Boundary Applications Change POWER%26XETA Showstopper.pptx?d=w0fb15759e06344ed9b920c43744df889&csf=1&web=1&e=iRvyxU |  | 11. Boundary Apps-related Change |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR0900 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0922 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 10.8 Analytics - PTP |  | 06. PTP 10. Analytics | Sheila Nguyen |  | PTP - Richard Taylor | [8 empty] | WIINGS | Adding PM Views to the Deloitte ECA Object Tracker (WIINGS related) | There were 25 SAP Domains that were related to WIINGS. ECA currently has 21/25 views for those SAP Domains. The ones we are currently missing are 4 views which are all related to Factory. The 4 are: Equipment Master, PM Work Order, Task List, and Warranty. The change is the additional scope of adding those 4 objects to the Deloitte ECA Object Tracker | B-app + reporting requirements will not be met. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B55B86E1C-0575-4F22-BFED-4047E3894916%7D&file=INT-CR0922.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA2MTIxNjQyNCIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  | 450 | 0 | [9 empty] | 450 |  |  |  | 0 | 450 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-17 | o WIINGS have identified 5 new views (PM and Quality management) that were not a part of the core scope. • The boundary apps affected are listed • These views will help with the reports are foundational to the reports that will consume them o We only have 1 boundary app (XEUS) that has a lot of work • There are about 100 attributes | [9 empty] | Other | Tower | 2025-07-17 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-09 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0923 | Approved | Confirm with Sunil and Analytics | ERP | R3 (Release 3) |  | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | doug.utberg@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | Cancelling Deloitte Object for Pre vs. Post Reorg Report ¦ FPRXV232 | Cancelling the Deloitte Object since DARC already has an object ID sourced. | Reorg reporting will not be coming from S4, so the Deloitte object is no longer needed. DARC has confirmed that the report is in on their list. (Object ID is currently TBD ... will be issued when the spec is reviewed) | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0923/Approval%20CR%20to%20Cancel%20FPRXV232%20_%20Deloitte%20Object%20for%20Pre%20vs_%20Post%20Reorg%20Report.msg?csf=1&web=1&e=czTrgC |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV232 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-23 | [10 empty] | Other | Tower | 2025-07-23 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0924 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 09A. Master Data 10. Analytics 13. Security | benny.lee@intel.com |  | FTS IF - Haritha Komma |  | CR TBD for combining IP & IF in ECA Corp Zone | [7 empty] | MO Request & Response Process for Substrates | Consolidation of MO Request/Forecast, MO Response and BOH, WIP, On-Hold, Intransit data at ECA Corp Zone for data collaboration between Substrate Suppliers and Intel | IP & IF information should not be shared with each other. However, Intel needs to interact with Substrate supplier as one. Corp Zone is where consolidation of data will happen to Substrate supplier and disaggregation between IP & IF once data received back from Substrate Supplier | Additional Development work for Material PDH, ECA and ECA Corp Zone teams, which can potnetially go beyond current committed R3 build timelines of end of 2025 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_MO%20Request%20Response-Substrate.pptx?d=wd929ffcd4f954a6f8ddab9d51cce4077&csf=1&web=1&e=9CmfkY |  | 1. Process Scope / Design Change |  |  |  | 0 | 0 |  |  |  |  | 80 |  | 880 | [6 empty] | 960 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 | ECAFTSIPV6336, ECAFTSIPV6337, ECAFTSIFV6338, ECAFTSIFV6339, ECAFTSIFV6341, ECAFTSIPV6340, ECAFTSIFV6342, ECAFTSIFV6343, ECAFTSIFV6344 | 9 | 9 |  | 0 | SCPIFSPPDH0251 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-07-10 | o These MO signals are required for PO. o For data that needs to be shared, Corp Zone is utilized. • Substrate is customer and material specific. o E2Open is the only boundary app that will need to pull and send o AR: Add in what teams are needed to do the sizing, if there are any tradeoffs, and how long the assessment will take |  |  | 2025-07-11 | • The team presented a plan to consolidate IP and IF manufacturing order requests into a single file for substrate suppliers. • The response will be split appropriately to maintain data separation and compliance. • No changes are expected for E2Open or software suppliers; existing interfaces will be reused. • Sizing estimates will be available late next week or early the following week. • AR: Sunil Parida and Rebecca Verette - Provide sizing for MO consolidation by EOW WW29 • AR: Sunil Parida - Confirm no changes to E2Open with minor interface reuse • AR: Sunil Parida - Provide design diagrams (as-is/to-be) to add clarity in next review | 2025-08-08 | • The process starts with the supply plan generating overall substrate demand, which is then allocated to suppliers using MAPPS logic. MAPPS sends a consolidated Manufacturing Order (MO) request to the substrate supplier, aggregating both IP and IF requirements to present a unified Intel demand. Upon receiving responses from the substrate supplier, Intel disaggregates the information for internal IP and IF tracking. This approach is intended to prevent suppliers from distinguishing between IP and IF orders, supporting strategic alignment and volume management. • The change request to support this process involves ECA work to enable aggregation and disaggregation, with a 22-week estimated effort and no impact to POR R3 timelines. The rationale is to appear as a single Intel entity to suppliers, simplifying interactions and avoiding supplier-driven prioritization between IP and IF. • Decision: The decision is to proceed with the change request enabling MAPS to send consolidated MO requests and aggregate/disaggregate substrate demand, ensuring suppliers see a unified Intel order and supporting strategic alignment, with no impact to POR R3 timelines. |  |  |  | Design | CL/OSC | 2025-08-08 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0925 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 06. PTP 08. FTS IP 10. Analytics 17. B-App | ananthakrishnan padmanaban |  | FTS IP - Loni Adams |  | INT-CR1142 | N/A |  |  |  | 40617 | SAP IBP Consolidated Materials Planning |  | DTC & LSC Functionality for CMP IP | Type B Passive LSC(Land Side Capacitors) and DTC (Deep trench Capacitors) forecasting and Procurement capabilities in Intel Products | *Approved. Type B passive –LSC and DTC forecasting for IP products was originally classified as a combined process & ownership under Intel Foundry with DSC (Die Side Capacitors). Later, based on IP/IF split, this functionality has been re-classified as IP ownership. With the ownership change, the LSC forecasting capabilities have to be separated out for IP & IF. | Additional Development work for Material PDH, ECA and CMP IBP functional team, which will go beyond current committed R3 build timelines of end of 2025 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_CMP-LSC-DTC-IP.pptx?d=w42bfac0d36ff40eba539b76c3e7121cb&csf=1&web=1&e=wPjVBF |  | 1. Process Scope / Design Change |  |  |  | 0 | 0 |  |  |  |  | 280 | 240 | 1040 | [6 empty] | 1560 | 0 | N/A | Yes | ECA | 13 | ECAFTSIFV6355, ECAFTSIFV6353, ECAFTSIPV6346, ECAFTSIFV6348, ECAFTSIPV6345, ECAFTSIFV6354, ECAFTSIPV6350, ECAFTSIFV6347, ECAFTSIPV6356, ECAFTSIFV6351, ECAFTSIFV6349, ECAFTSIFV6357, ECAFTSIPV6352 |  |  | 0 |  | 0 | ECAFTSIFV6355, ECAFTSIFV6353, ECAFTSIPV6346, ECAFTSIFV6348, ECAFTSIPV6345, ECAFTSIFV6354, ECAFTSIPV6350, ECAFTSIFV6347, ECAFTSIPV6356, ECAFTSIFV6351, ECAFTSIFV6349, ECAFTSIFV6357, ECAFTSIPV6352 | 13 | 13 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-10 | o This functionality doesn’t exist as part of the current substrate planning. • This is not an IAO-driven change, but it will need to be carried into the IAO timeframe and will affect the build timeline. o This request is for the teams to perform the sizing of the impact, timing of delivery, and re-evaluate whether design will be re-opened. o AR: Add in all of the teams that need to do the sizing and when the sizing will be done. |  |  | 2025-07-11 | • DTC is a high ASP, long-lead-time component critical to substrate manufacturing. • The team plans to aggregate procurement files (PRF/RTF) for DTC and LSC into a single feed via CorpZone. • This change is driven by a business model shift to consigned material. • Estimated effort includes 3 sprints for PDH, 2 sprints for SAPIBP, and additional work from ECA. • Concerns were raised about feasibility due to PDH capacity constraints and the need for alternative solutions or simplification. • AR: Sunil Parida - Need to clarify 3-spring estimate including detailed task list for DTC/LSC change • AR: John Heiney - Assess feasibility of PDH effort and explore simplification or deferral | 2025-08-08 | • Deep Trench Capacitor (DTC) is a specialized, high-cost component etched into silicon substrates, required at the start of substrate manufacturing for advanced packaging solutions. The new business model requires Intel to procure and consign DTCs to substrate suppliers due to their criticality and cost, differing from conventional Land Side Capacitors (LSC). The process involves CMP (Consolidation Materials Planning) generating purchase requests for DTCs, which are then sent to ECC (and in the future, S4). • The change request is to enable this consignment and planning process for IP in CMP, with a new planning area in SAP IBP, ensuring DTC supply aligns with substrate manufacturing orders. The solution is designed to be ready for ITC one, with no impact to critical timelines, and is distinct from the IF process, which is being designed separately. The rationale for this approach is the critical nature and long lead time of DTCs, and the need for Intel to manage supply and ownership directly. • Decision: The decision is to approve the change request to implement DTC consignment and planning for IP in CMP, using a new planning area in SAP IBP, with the solution targeted for ITC one and no impact to critical timelines. |  |  |  | Design | CL/OSC | 2025-08-08 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0926 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | JR Hoover | [11 empty] | Cancel UI objects: FTSI1377 & FTSE1375 | Cancel UI Factory Comm Interface for alternates and notifications (FTSI1377, and UI FComm Alternate Search screen (FTSE1375), as determined these are not required | Cancel FTSI1377: Custom Fiori UI – Admin (Factory Comm/Alternate Contacts Search Screen) Interface with Factory Comm for alternates and notifications: for alternate contacts, instead of the interface, pulling data from HRMM; for notifications Factory Comm does not have the functionality that was originally requested Cancel FTSE1375: Custom Fiori UI – Admin (Factory Comm/ Alternate Contacts Search Screen): Additional screen not needed; functionality covered in FTSE1373: Admin Screen - My Profile; determined upon development on of the FS for FTSE1373 | No Impact | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0926/FW%20Approval%20for%20Object%20Cancellation%20(FTSI1377%20%20FTSE1375).msg?csf=1&web=1&e=brczqY |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1377, FTSE1375 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | No Objects |  | In Progress | No
R4 (Jul 2027) | N/A | INT-CR0927 | Approved | Presenter: JR | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | JR Hoover | [11 empty] | eDFIT Object Date Changes to R4: FTSI1371, FTSI1370, FTSE1369, & FTSE1372 | Object Date Changes to R4: FTSI1371 – CMMS Create/Update Equipment (S4 to CMMS): Date Change from R3 to R4; cancel Activities 1.3 & 1.4 in Sprint 15 Build Plan​ FTSI1370 – Custom Fiori UI - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT)​) Interface to Factory Comm: Date Change from R3 to R4; cancel Activities 1.3 & 1.4 in Sprint 15 Build Plan​ FTSE1369 - Custom Fiori UI - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT) ): Date Change from R3 to R4; cancel Activities 1.3 & 1.4 in Sprint 16 Build Plan​ FTSE1372 - Custom Fiori UI - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT) ) Workflow for check in reminder: Date Change from R3 to R4; cancel Activities 1.1, 1.2, 1.3 & 1.4 in Sprint 16 Build Plan | FTSI1371 & FTSI1380 – It was determined during the eDFIT design closure process (aligned on 6/13) that these interfaces were not needed until R4. We need to push these activities out until R3 activities are complete. Requesting to cancel the activities included in the Sprint 15 Build plan FTSE1369 - As this UI screen is part of the eDFIT scope, it is not needed until R4. We need to push these activities out until R3 activities are complete.​ Requesting to cancel the activities included in the Sprint 16 Build plan. FTSW1372 - As this Workflow for the UI screen (FTSE1368) is part of the eDFIT scope, it is not needed until R4. We need to push these activities out until R3 activities are complete.​ Requesting to cancel the activities included in the Sprint 16 Build plan. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R4/INT-CR0927%20-%20Object%20Date%20Changes.pptx?d=w7d30906df1a543c7b409bd7bbf3fa73d&csf=1&web=1&e=Uau2kR |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI1371, FTSI1370, FTSE1369, FTSE1372 | 4 | FTSI1371, FTSI1370, FTSE1369, FTSE1372 | 4 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-15 | Approved offline by Anand Jha and Uzma Ahmed | [9 empty] | Other | Tower | 2025-10-15 | 10, 2025 | 10, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | colkennedy@deloitte.com |  | No |  | No Objects |  | In Progress | No | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0928 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.8 PTP - QM |  | 06. PTP 11. Technology | Nagapushpa Nagapushpa | [11 empty] | Develop Enhancement to Auto Block the Expired batches in IM storage locations | Develop Enhancement to Auto Block the Expired batches in IM storage locations | This is required to make sure expired batches are not used for further production process |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3797C43D-D72A-48CA-B33B-CE2AF44A145F%7D&file=INT-CR0928_PTP_QM_IF.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | PTPE1603 |  | PTPE1603 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-31 | o If batches expire, there is no way to automatically move it out. • In order to prevent influx of maintenance orders, there is a need to block expired batches. • The solution is a report (enhancement) with selection screen to select expired batches and manually move it to blocked stock status. • It sends a signal to 3PL to block the batch as well. o Deadline monitoring is the standard SAP program. This process works if going through quality inspection, but the team is not sending all materials through quality inspection. • We don’t want to turn it on all of the time, and we can’t afford to turn it on all of the time. o AR: Provide names of OES4 contacts to Cari - @Alarcon, Rodolfo o AR: Communicate change to OES4 team due to 3PL impact - @Shim, Cari H @K P, Murthy | [9 empty] | Other | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | nnagapushpa@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0929 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 11. Technology | Afroz Khursheed Mohammad | [11 empty] | Stored Procedure changes for Websuite interface. | Stored Procedure changes for Websuite interface. | Stored Procedure getting changed for below objects. PTPI0819_IP PTPI0819_IF PTPI1307_IP PTPI1307_IF PTPI0211_IP PTPI0211_IF PTPI1308_IP PTPI1308_IF |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Lisa Honeycutt and Jose Vargas Lepiz to not be required. Approved to be cancelled by Cari | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-10 | 0 | < 15 Days | ramagkumar@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0931 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 02. E2E Process Integration 03. FPR 11. Technology | Gaurav Malhotra |  | FPR - Aubrey Hinderlider |  |  | N/A | [6 empty] | Change in N rates for using Reference table | Change in the logic to derive the tickers from the reference rates and if inversion is needed or no. | Mapping cannot be done using TVARVC table and we have to follow IAO standards | NA | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0486%20N%20Rates%20Changes.pptx?d=w5ab9138706d34941b9b8e16f0b38f91c&csf=1&web=1&e=b8A6ls |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High | 30 | 3 |  |  | 40 |  |  |  | 40 | [6 empty] | 40 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR-Build-0486 was created as the technical effort is less than 40 hours of technical work. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-10 | 0 | < 15 Days | gaumalhotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0932 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta | [11 empty] | Pay@accept – Inbound Interface to fetch the values from FCE ODS to SAP S/4 HANA IF | SAP IF System should have the ability to fetch the values through interface with FCE ODS Boundary Application. An Interface needs to be developed to bring the required fields from FCE ODS B. App to SAP S/4 HANA IF system. Pay@accept program will consume the required fields and determine to remove the block indicator from the invoice. | This interface is needed for the Pay@Accept's payment block release, as the functional specification approved on design was under the assumption that all required data was to be sourced from S/4 tables (replicating today’s scenario). Technical team concluded that schedule data will no longer exist on the Equipment Record on S/4, based on IAO design. This is triggering the need for an interface to fetch this data directly from the B.App FCE ODS. |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Murthy to be replaced by CR1045 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-10 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0933 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Prabesh Acharya |  | FPR - Aubrey Hinderlider | [9 empty] | Inclusion of expedite Fee in Current RAR Design (Fulfillment Based on POD of Hardware) | Currently, for hardware orders under Incoterm D with a revenue trigger based on Proof of Delivery (POD), both IP and IF are managed in RAR, while software and services are handled through Manual Fulfilment in RAR for IP only. The OTC team now plans to introduce a new line item in the sales order called "Expedite Fees." This fee will apply when customers request faster delivery of hardware within the same sales order. To support this change: A new POB (Performance Obligation) for Expedite Fees will need to be created, along with all necessary configurations in RAR for both IP and IF. The fulfilment of Expedite Fees will be tied to the POD of the associated hardware item. This will require updates to the logic in the FPRE0760_IP and FPRE0760_IF objects, so that the TM module can trigger the fulfilment based on the hardware’s POD. | The business requires that revenue for hardware items is recognized or deferred based on when the Proof of Delivery (POD) occurs. Since the Expedite Fees are directly related to delivering that hardware faster, it makes sense to recognize or defer the revenue for these fees in the same way as the hardware itself. This ensures that both the hardware and the associated expedite fees are treated consistently from a revenue accounting perspective. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B17EFC42C-54AE-445A-B8CD-DE490844B888%7D&file=INT-CR0933%20-%20Inclusion%20of%20expedite%20Fee%20in%20Current%20RAR%20Design%20(Fulfillment%20Based%20on%20POD%20of%20Hardware).pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 40 |  |  |  |  | 0 | 40 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0760_IP, FPRE0760_IF, FPRE0500_IP, FPRE0500_IF | 4 | FPRE0760_IP, FPRE0760_IF, FPRE0500_IP, FPRE0500_IF | 4 |  | 0 |  | 0 | N/A |  | 2025-12-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-21 | Approved in Change Ingestion 8/21 | [9 empty] | Build | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | ppranavyogesh@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0934 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-10 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0935 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | JR Hoover | [11 empty] | HAZMAT Interface for Parts Return (Interface to Enhancement) | HAZMAT Interface for Parts Return (Interface to Enhancement) This object was already approved under FTSI1360. This object is being developed as an Enhancement now instead of Interface. | This was originally a BApp. Recent decision has determined this will be a new FIORI app. This object needs to change to an Enhancement & be pushed out. | This enhancement is being shifted from Sprint 15 to Sprint 16 | No |  |  |  |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-20 | Per Hailey- INT-CR0935 is closed; the HAZMAT scope has an independent CR, and this was just to change the existing object we had from an Interface to an Enhancement, which was done offline, did not need to go into CR ingestion. | [9 empty] | Other | Tower | 2025-08-20 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | colkennedy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0936 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | JR Hoover | [10 empty] | WIINGS | Convert Item/Part Warranty Information upload to SAP S/4 Master Warranty (update FTSC0988 to FTSE0988) | Convert Item/Part Warranty Information upload to SAP S/4 Master Warranty (update FTSC0988 to FTSE0988) The main goal of this enhancement is to enable the storage of items/parts, and Tools (Sustain & Extend) warranties within the Master Warranty, allowing warranty validation to be carried out according to established business rules. Note this object was previously approved as Conversion, but is changing to an Enhancement | The main goal of this enhancement is to enable the storage of items/parts, and Tools (Sustain & Extend) warranties within the Master Warranty, allowing warranty validation to be carried out according to established business rules. Note this object was previously approved as Conversion, but is changing to an Enhancement | High | No |  |  |  |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-20 | Per Hailey - INT-CR0936 is closed, it was approved in the IAO RICEFW Leadership review last week; it was just a change from a conversion to an enhancement, so Anna instructed me to create an entry for it in the CR tracker, but that it did not need to go through CR ingestion, just RICEFW intake; therefore there is no CR review deck. | [9 empty] | Other | Tower | 2025-08-20 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | colkennedy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0937 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Kolleru Venkatesh |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSI1434 | Request the cancellation of Object FTSI1434 Mid Stage Transfers from S4 to Non S4 plant will leave behind open production orders in SAP and will need to be closed​ | Cross site straddle design was completed 2 months back and better solution was found with PDF (SMH) |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0937/EXT%20RE%20Req%20for%20Cancellation%20of%20FTS-IF%20object%20FTSI1434.msg?csf=1&web=1&e=UxmcM3 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1434 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) |  | INT-CR0938 | Approved | 8/14 Conditionally Approved- Change Request Ingestion: o AR: Include timeline for when the security changes will be complete and tested - @K P, Murthy | ERP | R3 (Release 3) | High | 06. PTP | 6.1 PTP - ALL |  | 06. PTP 13. Security | Dan Cirignani | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | Optimize and Update S4 Business roles based on additional analysis | Deloitte security team updates the roles and transaction codes/Fiori Apps in design documents and complete the build and test activities based on these optimizations. PTP Teams completed additional analysis of T codes/Fiori Apps based on the request from Deloitte Security team. PTP Teams also aligned with non-PTP tower teams on using some of the T Codes/Fiori Apps owned by non-PTP towers. PTP Teams also optimized the requirements (removed many from the original list and added few T codes/Fiori Apps and business roles). PTP Team expects the Deloitte security team updates the roles and t codes/Fiori Apps in design documents. All these optimizations are done in consultation with Deloitte tower teams as suggested by Deloitte Security team. | This CR aims to update the R3 security role design for PTP. The initial request included a large number of transaction codes/Fiori Apps and roles that spanned multiple towers. After review and collaboration with other towers, we have finalized the list of required transaction codes/Fiori Apps and roles, which can be found [here]. This updated list will provide revisions to the R3 security design and the subsequent build activities. Since the design is closed, we are requesting a new CR to complete the additional role design, build and testing activities. | No Impact to Existing Deliverables | Yes |  | Yes - Cari Shim | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD24AF906-A16C-4594-AE86-BE8A37B880D6%7D&file=Change%20ID_PTP_CR%20Deck_Security%20.pptx&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  | No |  | High | 0 | [11 empty] | 250 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | [10 empty] | Build | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0939 | Cancelled |  | SCP | R3 (Release 3) |  | 07. FTS IF | 7.12 FTS IF - IF R3 FE Supply Planning & Adv Packaging |  | 10. Analytics | anil.sankarapillai@intel.com |  | FTS IF - Haritha Komma |  |  | NA | [6 empty] | Obtaining Capacity data from ICS systems for WLA | Establish ICS as SOR to house WLA Capacity Model param inputs that feed into BY solve. PDH/BY: Establish capability and reporting to support WLA Capacity Model solution. | IE community has aligned and formally agreed that ICS will be our primary future-state SOR/ROO for BY parameter inputs into the WLA capacity model. DxCR was reviewed as a possible supplemental POR system, and it was decided among the entire IE community to use ICS as the SOR for BY param inputs feeding BY. Key rationale was that DxCR is not an SOR for anything, as it’s a solver, and the outputs require manual work and is not adopted by OR and doesn’t have the ability to handle the dynamic needs of TD. Capacity data coming from ICS has been a key part of the design, PDH team has since determined that it will need ECA changes to get the capacity data flow in to BY ICS -> ECA integration for Yields (planning req) and FTQ( Finance req) were comprehended for Mapp day but Capacity data was not comprehended it is a significant amount of data and there is transformation needed from ECA team and hence this change request. | TBD | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | CR0939 is a duplicate of CR0951 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0940 | Cancelled |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP | Sekhar Lingam |  | FTS IP - Loni Adams | [9 empty] | Migration of existing Office of CTO (OCTO) business process into ALPS and integration with SAP S/4 HANA | Migration of existing Office of CTO (OCTO) business process into ALPS and integration with SAP S/4 HANA | Approved WW29 by CL and divided into IP and IF CRs. The existing OCTO boundary app will be EOL by 2025. Hence OCTO BU needs to be brought onto ALPS platform and integrated with SAP S/4HANA. Here are a few of the justifications for this change. ​We will be leveraging the already established list of plants, but we need to set up new storage locations for OCTO All key data objects related to OCTO need to be migrated from ECC to S/4 HANA MRP run will be executed for OCTO plants using MRP Area Purchase Requisitions will be triggered in S/4 for “Buy” items Planned orders will be generated for “Make” items which will be converted to Production orders. This is different from the previous SubCon PO process Manufacturing Execution: OCTO uses SAP ME system along with ECC. This is not part of IAO scope. This will be a net new addition to IAO, if SAP ME needs to be continued. SAP ME will not be supported by SAP beyond 2027 RICEFW objects, if any will be identified in the detailed sessions Participation of all the teams (FTS, OTC, PTP, LE, FPR, E2E) is required to assess and finalize the solution for R3 |  | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0940%E2%80%93Change%20Request%20for%20OCTO%20BU%20scope%20in%20S4.pptx?d=wd0efe3f7b39e44b38388e21db4b5b4cd&csf=1&web=1&e=fazJPw |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed that CR0940 is a duplicate of CR1078 and can be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-14 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0941 | Approved | Presenter: Murthy | ERP | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | chin.chai.ng@intel.com |  | PTP - Richard Taylor |  |  | N/A | [6 empty] | SIMS subcon PO BOM comparison and change report | The BOM will get updated in SAP S/4 system with latest component details with and existing interface from SPEED. Therefore, SIMS business users need a report developed in SAP S/4 which could be executed manually, and shows the comparison of components in BOM and the components in open subcon POs. Based on this report, users need to analyze the existing on hand inventory and then decide to update the subcon PO with latest BOM changes. | Finished Goods BOM for SIMS materials change very frequently as compared to HVM BOMs. The avg. number of BOM changes expected in a year 6k to 8k. 318 TA BOM (no part number change at BOM level, but consigned component could change), 5-7 components, 3-4 update = 6k to 8k. | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/1%20Sprint%20Roadmap/SIMS%20User%20Stories/INT-CR0941_SIMS%20Subcon%20PO%20BOM%20comparison%20and%20change%20report%20-%20Change%20Request.pptx?d=waa0ccf4c00874c6186fb7ca87b2161a5&csf=1&web=1&e=Dy93AE |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | PTPE1628_IP, PTPE1628_IF | 3096 | PTPE1628_IP, PTPE1628_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-07 | o This CR is for a new enhancement and will impact the 3 processes (SIMS, ODM, Box CPO) when creating subcon PO. • These orders are subject to frequent changes in the product BOM, and it is hard to identify which PO’s are affected by BOM changes. o This enhancement will be run by the buyers and identify the quantity/component that was updated in the BOM. • The effort is high and has a Fiori component. Therefore, it cannot be committed to ITC1. o This is the current process, and manual process does not happen today. There is a risk to introduce errors if a new process is adopted. |  |  | 2025-08-15 | • The CR originates from ODM, Sims, and Box CPU business processes. • The current ECC process tracks BOM changes after subcontracting purchase orders (POs) are created. • The proposed enhancement in S4 will: o Automatically detect BOM changes (new components or quantity updates). o Display a report of BOM changes. o Automatically update the subcontracting PO based on BOM changes. • Challenge: If a subcontractor has already consumed the original BOM components, automation must ensure it doesn’t overwrite or misalign physical consumption. o The system will only update POs if goods are not yet received. o New components or quantity increases will be issued; otherwise, no changes will be made. • Complexity: High, due to volume and functional depth. • Timeline: Will miss ITC1; targeted for ITC2. • Development Needs: Requires a new high-complexity Fiori app and RICEF objects. • Keerti Nayak and team are assessing feasibility. • May add developers to support the effort. • AR - Keerti Nayak & Team Complete assessment for ITC2 readiness | [5 empty] | Other | CL/OSC | 2025-08-15 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
|  | INT-CR0942 | Cancelled |  | ERP | R2 (Release 2) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 10. Analytics | thienne.johnson@intel.com |  | FTS IF - Haritha Komma |  |  | No RAID created | [6 empty] | Missing Delivery Note (DN) for overpack Handling Unit (HU) scenario | Current ECA logic is not able to pick DN in case of an overpack scenario in EWM (Impacted ObjectID: FTSFV011 | CATTS/TCA cannot provide box/unit level traceability for warehouse box which involved in the repack/overpack process. This can impact downstream which leverage TCA data for customer requirement and may lead to major customer escalations. Although impacted transactions are small, the quantity/value could be high due to overpacking. This may lead to Customer Order cancellation in extreme case and impacts Intel brand reputation. In addition, TCA information is critical for quality excursion disposition and customer warranty program. | 28 hours of work for R2, late delivery for testing, R3 work would be effectively pulled into R2 | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 28 hours | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Vanessa to no longer be required. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0943 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | bareddy@deloitte.com |  | FPR - Aubrey Hinderlider |  |  | 3053 | [6 empty] | FPR_CO_ECA Report Development Plan Change | ECA Team have to change CO ECA Development plan throughout each sprint so that we can test thoroughly. As currently 25 ECA developments are planned in second last sprint - Sprint#21 which would impact on testing and sign off. | According to current ECA Plan, all 25 Team-7 reports are scheduled for January 2026. These reports are too complex. Deloitte ECA will only create the model, and the Dark team will build the reports. We do not know how long it will take the Dark team to finish designing these reports. This could impact deliverables on ECA report from COPC | According to current ECA Plan, all 25 Team-7 reports are scheduled for January 2026. These reports are too complex. Deloitte ECA will only create the model, and the Dark team will build the reports. We do not know how long it will take the Dark team to finish designing these reports. This could impact deliverables on ECA report from COPC | No |  |  |  |  | 10. Non-Build Analytics-related Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Hari Gore to no longer be needed. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0944 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR | suresavula@deloitte.com | [11 empty] | Import Revenue Customer Hierarchy from ECA to S4 | Revenue Customer Hierarchies are needed as part of profitability reporting in S4. Hence this change request is to import hierarchies from ECA to S4 as customer hierarchies will be available in ECA only. | Profitability Reports based on Revenue Customer Hierarchies in S4 |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Suresh Avula that this CR was dropped | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-15 | 0 | < 15 Days | akshatr@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0945 | Cancelled |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 07. FTS IF 08. FTS IP | Mubashir Ghazi |  | Data - Julie Fawdington | [9 empty] | Material Freight Group field derivation | Activate Material Freight Group field in Basic data 1 and define the logic to auto derive the value in MDG | The change is required to automate the material freight group field | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR0945_MDG_Material%20Master_CR%20Derivation%20of%20Material%20Freight%20Group.pptx?d=wb2f61fe9342948978c1ac11c6120f185&csf=1&web=1&e=1dEVts |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Lilibeth that this is an internal CR as the work is less than 40 hours of tech effort. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-15 | 0 | < 15 Days | mghazi@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0946 | Approved |  | ERP | R3 (Release 3) | Low | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: Object: FTSE1143(Prod Order split in IP S4 system to form a Child Order with reference to Lot Split Signal from OSATs for managing the remnants) | Cancel objects added under R3 | Implementing the solution in the custom API in an interface object without having a need to enhance any standard program |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=hY2weu&CID=3b6cfa29%2De1f9%2D4fa2%2D9a4a%2D30414858a36b&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0946%2FFW%5F%20FTS%20IP%2D%20CR%20for%20Descoping%20RICEFW%20%2D%20FTSE1143%2Epdf&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0946 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0946%20-%20Cancellation%20of%20RICEFW%20Objects%20FTSE1143.pptx?d=wa38e581941ad4ca4b29dbb72888f2f6a&csf=1&web=1&e=rfo5yg |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE1143 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | [10 empty] | Other | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0947 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF | rodolfo.alarcon@intel.com | [11 empty] | R2 RICEFW impact of adoption to Internal batch number | Implications on R2 RICEFWs on using the SAP internal batches from R3 onwards, while the developments for R2 objects are completed considering SAP LOT ID and sap batch remain same. | Impact of adoption of SAP Internal number range for batches in SAP from R3 onwards. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0947%20-%20Internal%20Number%20range%20for%20Batches.pptx?d=w124e6b5ae18e4de980f732758e0ee915&csf=1&web=1&e=IFNhm9 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 120 |  |  |  |  | 0 | 120 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0357_IF, LOGF0347_IF, LOGF0343_IF, LOGI0612_IF, LOGE0400, LOGF0354_IF, LOGF0280, LOGI0278, LOGI0303, LOGE0306 | 10 | LOGF0357_IF, LOGF0347_IF, LOGF0343_IF, LOGI0612_IF, LOGE0400, LOGF0354_IF, LOGF0280, LOGI0278, LOGI0303, LOGE0306 | 10 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-31 | o Impact of this change will be on R2 RICEFW’s that have been completed • R2 is custom batch, and R3 will use the standard SAP batch number. • R2 RICEFW’s will be adjusted and re-tested in the R3 ITC1. | [9 empty] | Build | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-15 | 0 | < 15 Days | anugiri@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0950 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 10. Analytics | Aldo Obregon Pineda | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | CR1697 | [7 empty] | To import EMS sourced Capacity Free Date (CFD) from ECA to S4. | To import EMS sourced Capacity Free Date (CFD) from ECA to S4. CFD date is maintained by CEIDs & Capex WBS L2. This is needed for OCOS/PCOS Split derivation. Apigee Work - C | Earlier the PCOS and OCOS split was driven by WTQ and CFD date coming from EMS system. Existing EMS to S4 interface does not have CFD date (FPRI0188). On further clarification Business confirmed that CFD is not updated in the WBS master data after the WBS is Capitalized. This WBS master data is sent to EMS to S/4 under existing interface. However updated CFD date is sent to ECA as part of ‘POR Needs’ Feed from EMS to ECA. Rational for this change is to create a view on top of this ECA view and make this CFD date available in S/4 to allow use for PCOS/OCOS split. | No Impact | Yes | Non-Core | Approved on 11/06 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0950%20-%20To%20import%20EMS-Source%20Capacity%20Free%20Date%20(CFD)%20from%20ECA%20to%20S4.pptx?d=w06684bd19c4b48be87692457522f93ed&csf=1&web=1&e=s5cxHX |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [9 empty] | 20 |  |  |  | 0 | 20 | N/A | Yes | ECA | 1 | ECAFPRV6471 | 3191 |  | 0 |  | 0 | ECAFPRV6471 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - The new interface will import capacity free date available in ECA and load it into SAP - AR: Confirm that the ECA API has been built and is available – Prabesh Acharya - AR: Update description so that this is listed as an enhancement to an existing interface – Bharath Paturi | [9 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 07, 2025 | 2025-07-15 | 0 | < 15 Days | mmaheshreddy@deloitte.com |  | No |  | Object Missing in OT | Complete | Complete | No
|  | INT-CR0951 | Rejected |  | SCP | R3 (Release 3) |  | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics | anil.sankarapillai@intel.com |  | FTS IF - Haritha Komma |  |  | NA | [6 empty] | Obtaining Capacity data from ICS systems for WLA | Establish ICS as SOR to house WLA Capacity Model param inputs that feed into BY solve. ECA/PDH/BY: Establish capability and reporting to support WLA Capacity Model solution. | IE community has aligned and formally agreed that ICS will be our primary future-state SOR/ROO for BY parameter inputs into the WLA capacity model. DxCR was reviewed as a possible supplemental POR system, and it was decided among the entire IE community to use ICS as the SOR for BY param inputs feeding BY. Key rationale was that DxCR is not an SOR for anything, as it’s a solver, and the outputs require manual work and is not adopted by OR and doesn’t have the ability to handle the dynamic needs of TD. Capacity data coming from ICS has been a key part of the design, PDH team has since determined that it will need ECA changes to get the capacity data flow in to BY ICS -> ECA integration for Yields (planning req) and FTQ( Finance req) were comprehended for Mapp day but Capacity data was not comprehended it is a significant amount of data and there is transformation needed from ECA team and hence this change request. | ECA TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR08XX%20-%20ICS%20-%20ECA_PDH%20Integration.pptx?d=w222e22a882494ac9a806b7a71990b409&csf=1&web=1&e=scEdxO |  | 10. Non-Build Analytics-related Change |  |  |  | tbd | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | Yes | No | 2025-07-17 | • ECA/PDH/BY: Establish capability and reporting to support WLA Capacity Model solution. o Prior to R3, there are no system that will provided the data record. • The team aligned on ICS as the data record, but they discovered during Detailed Design discussions that there will be some changes to the ECA scope. o This request is to analyze the ECA effort required. o AR: Add to WW31 CR Meeting | [8 empty] | Confirmed by Vanessa that it is a design open rather than a CR. Topic has been added to Design Open Tracker. | Other | CL/OSC |  | Missing Review Date for Approval Level | 07, 2025 | 07, 2025 | 2025-07-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR0952 | Approved |  | ERP | R3 (Release 3) |  | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Praveen Kumar Muppala |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Cancellation of OTCE0635 - Duty calculation in sales orders | Duty rate percentage maintained in GTS needs to be considered in sales order pricing | Descoping the object OTCE0635 - The decision was to de-scope the duty rate calculation on customer invoices from R3 capabilities. The rationale is that the capability was only being used by one SKU (stock keeping unit) that is scheduled for EOL. Since there are no other requests from customers or BUs, no other known corner cases as well, and this was not impacting Intel from paying customs duties, GTS capabilities, or compliance standards. As a conclusion, it was finalized not to proceed with this enhancement in S4/Hana. | No Impact | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0952/FW%20Cancellation%20Request%20for%20IP%20OTCE0635%20-%20Duty%20calculation%20in%20sales%20orders.msg?csf=1&web=1&e=1h1x2D | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8E1A6F78-66AF-4F81-9D40-EA4985C643AB%7D&file=CR%20(cancellation)%20-%20OTCE0635%20.pptx&action=edit&mobileredirect=true |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 216 |  |  |  |  | 0 | 216 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE0635 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-16 | 0 | < 15 Days | kpteja@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0953 | New |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | Vaidehi Avinash Gulhane | [11 empty] | Enhancement for WIP movement in EWM (Console# 2992) | Enhancement to enable WIP movement for receiving between Factory to EWM Warehouse and STO from Warehouse to Factory location.​ | WIP movement for receiving at Warehouse and factory location will not follow standard processes as per design. Business requirement is to utilized the pick-up points and factory passthrough location details provided in WIP movement order as a part of the attention to (unloading point) information. This object will be covering the deliveries with 311 movement type and STO movements. | No Impact | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0953_Enhancement%20for%20WIP%20movement%20in%20EWM%20(Console%23%202992).pptx?d=w2e99667302674bcda1c9e55730c3ba32&csf=1&web=1&e=oY1lOV |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-16 | 266 | > 30 Days | vgulhane@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0954 | Approved | Presenter: Prakash Veerasivaji | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.3 OTC IP - Billing and Rebates |  | 05. OTC IP 11. Technology | Eina Gupta | [11 empty] | Enhancement to invoice hardware and linked service on the same day with same profit center and the link displayed in the output form | New RICEFW required for IP - Billing and Rebates to create custom routine for service line item to restrict Billing for service item if it is linked to a higher level item where the higher level item PGI is not complete and billing is pending. | The enhancement ensures accurate RAR posting of both Hardware and associated VAS in the same period |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR0954_Enhancement%20to%20invoice%20hardware%20and%20linked%20service%20on%20the%20same%20day%20with%20same%20profit%20center.pptx?d=w112bc144173048d0a0b7e4deec938deb&csf=1&web=1&e=lV4GVO |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | OTCE1605 |  | OTCE1605 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | o This is required in Billing copy control, and it is coming in from an RAR requirement o A small check needs to be added to ensure that invoicing functions properly | [9 empty] | Other | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-16 | 0 | < 15 Days | nparti@deloitte.com |  | No |  | Complete |  | Complete | No
| R4 ITC1 | INT-CR0955 | New | 4/7: Followed up with JR/Laura/Ramadas | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 10. Analytics | Sheila Nguyen |  | PTP - Richard Taylor | [8 empty] | WIINGS | Adding 8 objects for EDFIT (4 views and 4 reports) |  | B-app + reporting requirements will not be met. |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-17 | 265 | > 30 Days | shenguyen@deloitte.com |  | No |  | No Objects |  | N/A | No | Yes
|  | INT-CR0956 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Shameek Dhir | [11 empty] | SAP S/4 Return Deliveries relevant for TM are not propagating to BN4L GTT under “Monitor Outbound Deliveries” | SAP S/4 Return Deliveries relevant for TM are not propagating to BN4L GTT under “Monitor Outbound Deliveries” | GTT Product limitation. Currently it only considers the Outbound deliveries. But Returns deliveries are required as well to be propagated to GTT so that the Freight order document flow can be displayed correctly. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Propagate%20S4%20Returns%20Delivery%20to%20GTT.pptx?d=w6cbea0c6f7d94fb9896005c33bac6ac2&csf=1&web=1&e=331DNv |  | 2. New RICEFW / ECA / Build Object |  |  | Low |  | 1 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-17 | 265 | > 30 Days | shadhir@deloitte.ca |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0958 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | FTS_IP_Manufacturing_New Interface to capture 3B2 and Virtual 3B2 signals from Intel Foundry to Intel Products | Creation of new interface to Capture 3B2 and Virtual 3B2 | Original 3B2 and Virtual 3B2 signals from Intel Foundry to Intel products were captured and processed by MuleSoft as a middleware in the initial alignment. But, in the latest alignment, all the production order related transactions coming from e2open must be processed through PDF(SMH) middleware only. Therefore, we are capturing and processing original 3B2 and Virtual 3B2 signals through SMH !! |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0958%E2%80%93Change%20Request_FTS_IP_New%20Interface%20to%20capture%203B2%20and%20Virtual%203B2%20signals%20from%20Intel%20Foundry%20to%20Intel%20Products%20S4.pptx?d=w7e772230e2204fb498c04ea27a74d81a&csf=1&web=1&e=7fJ8ub |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FTSI1619 |  | FTSI1619 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-31 | o This is a new interface related to 3B2, and it is related to the CR to put IP onto PDF. • The functionality was originally performed by a Logistics object. Scope was changed with SMH was added, and a new connection needs to be made. o This functionality is a must for production orders to be placed. o There will be some CR’s for 7B1 because API changes will come out of it • AR: Bundle everything that will be impacted by the IP to PDF move and bring in as a consolidated CR - @Holloway, Kim o AR: Convert this to a KDD and bring into the WW32 CR Meeting - @Vytla, Kumar @Lingam, Sekhar @Maxey, Stef • AR: Add in details on the risk to meeting ITC1 and add in mitigation details (impact to schedule or compromise architecture) |  |  | 2025-08-08 | • The change request stems from the decision to place IP on its own PDF instance. • It involves rerouting production order messages (3B2) from MuleSoft to PDF, enabling orchestration of multiple steps within PDF. • The main concern is whether E2Open will be ready in time for ITC1 testing. • Two mitigation options were discussed: o Insert test messages manually into PDF to simulate EDI input. o Fund additional resources at E2Open to accelerate readiness. • Option 1 was deemed acceptable and preferred by Stef Maxey, Mike Lange, and Cari Shim. • Uzma Ahmed confirmed that Roman Vorel and E2Open leadership are aligned and exploring resource options. • Devendra assessed the risk as medium, not high. • The solution is like what’s already implemented for IF, with minor differences due to virtual plant shipment handling. • The team confirmed readiness for ITC1 testing, except for E2Open dependency. • Approval: Confirmed for option 1 by Uzma Ahmed • AR - Sujay Kumar - Explore what additional resources would mean if Option 2 is pursued. | [5 empty] | Other | CL/OSC | 2025-08-08 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-17 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R1 (Hypercare) | R1 | INT-CR0960 | Approved |  | ERP | R1 Hypercare | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Naveen Negi | [11 empty] | Utility Program for Resolving AIF Errors Linked to Reference Documents/Invoices from Previous Years | Currently, accounting documents or invoices that reference documents posted in previous years (FY24 or earlier) encounter posting failures in Central Finance (CFIN) and become stuck in the Application Interface Framework (AIF) due to errors related to these references. SAP recommends resolving this issue by manually removing the reference field value from the line item during debugging, allowing the documents to be successfully posted in CFIN. | To address these error scenarios more effectively, it is proposed to develop a Utility Program that can automatically reprocess AIF messages without the need for manual value changes during debugging. This program is designed to streamline the process, reducing or eliminating the need for debugging in the production environment in the future, thereby enhancing system stability and efficiency. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF9F64BF2-114D-4711-B480-2B80ACE0FE11%7D&file=INT-CR0960%20Utility%20Program%20for%20AIF%20Errors%20related%20to%20reference%20documentsinvoices%20from%20previous%20years.pptx&wdLOR=c443172B8-EA5C-4DED-9D38-F8A4B1F0E364&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [8 empty] | 70 |  |  |  |  | 0 | 70 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-29 | o We are finding defect issues and need a BADI to clear some posting failures/information. • Things that are failing because of clearing information that is missing, and the solution will require a new BADI • Hypercare incident resolution o It is a part of the R1 high-level messages • SAP did tell team that we didn’t have any other solution unless we have a BADI • This BADI will help to systematically solve it rather than manually remove it o The tech team is required to do the work • It is 70 hours, and the estimate is from the Hypercare team o Manual workaround is not efficient and not ideal • EY will ask why we are changing in production o AR: Confirm with Keerti that it is okay to take this on without impacting his current commitments | [9 empty] | Other | Tower | 2025-07-29 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-17 | 0 | < 15 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0961 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.5 FPR - Fixed Assets |  | 03. FPR | Kaushik Mhatre |  | FPR - Aubrey Hinderlider | [9 empty] | FPR - Cancellation of RICEFW FPRI1315_IP - "Add MuleSoft API and APIGEE Proxy for EMS to call STD BAPI to Create / Change / Delete Asset master records for procurement process" | FPR - Cancellation of RICEFW FPRI1315_IP - "Add MuleSoft API and APIGEE Proxy for EMS to call STD BAPI to Create / Change / Delete Asset master records for procurement process" | Object descoped since EMS will not have any interface with S4-IP at all as confirmed by "Wilson, Sean M <sean.m.wilson@intel.com>". It is only needed for S4-IF. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0961/RE_%20R3_Fixed%20Asset%20Team_RICEFW%20ID-FPRI1315_IP%20-%20Asset%20Creation%20Interface%20from%20EMS%20to%20S4-IP.msg?csf=1&web=1&e=izplRn |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-17 | 0 | < 15 Days | kamhatre@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR0962 | Approved |  | ERP | R2 Q4 '25 Anafi enablement |  | 04. OTC IF | 4.1 OTC IF - ALL |  | 03. FPR 04. OTC IF 10. Analytics | jason.carmichael@intel.com |  | OTC IF - Angela Laskowski |  |  | N/A | [5 empty] | Anafi | SAP Pricing Customer Segregation | Add customer segregation to the IAO Pricing Tool in SAC to support the IF pricing tool, enabling clear separation of IP and IF pricing and data extraction for Anafi pricing. We would likely unitize customer code, a value stored in speed, not the customer’s true name. | FE & BE pricing can be temporarily supported via spreadsheet. However, clear identification of IP vs IF products is needed in the SAC Pricing Tool. As Anafi ramps up and additional changes are expected in H1'2026, greater support from the SAC tool will be needed. Adding the separation now will set the foundation for those changes. As the H1, 2026 requirements become clear, it will be address within the architecture groups. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX%20SAC%20Pricing%20Customer%20Segregation.pptx?d=w262874c2164d49caa8ac87f3ceaeef28&csf=1&web=1&e=YqzThH |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-05 | - In order to extract the pricing information from the SAC tool, we need this small change to differentiate whether it is for an IF/IP product and what customer it is for. This also allows for the downstream (DARC teams) to see what the data is more clearly. - Impacted teams are SAC pricing tool, DARC, and ECA. it is simply to pull in this field. - It is currently being done manually. We don't have to do it at a scaled level now, but it is crucial for when Anafi goes live. This is not throwaway work as it will be utilized after Anafi as well. - This is not in the S4 space and will be fully in the SAC space. It is a different set of resources. AR: Check all of the estimates and provide the names of everyone who provided the effort sizing - Sunil N AR: Add a statement that CR will be managed by the Anafi Team | [9 empty] | Other | Tower | 2025-08-05 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0963 | Cancelled |  | SCP | R2 Hypercare |  | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | elena.kaufman@intel.com |  | FTS IP - Loni Adams |  |  | N/A | [6 empty] | Reticle Usage Report | Provide a report that compares Reticle Capacity to Reticle Usage. Reticle Capacity should reflect the latest data given from Intel Foundry to Intel Products. Reticle Usage will be based on user selection of Scenario, and show the number of wafers planned in a period that use the specific reticle or reticle group. User should have ability to view aggregation by weekly/monthly/quarterly. Additionally, user should have a quick way to spot cases with high usage. | Reticles will not be input to BY IBP unless there are constraints. Capacity planners need a way to analyze cases where reticles present a constraint that is necessary to add to BY to ensure our orders are feasible. | Impact to job training and successful execution of job roles during WW39 go live. High Impact | No |  |  | Uploaded into SCP Change Request Decks - Titled: Change Form - Reticle Usage Report |  | 2. New RICEFW / ECA / Build Object |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it was not included in Upali's list of open CR's | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0964 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  |  |  |  | N.A. | [6 empty] | Cancel Objects: PTPE0732_IP Pay@Accept Custom Program to release the invoice - SAP S/4 HANA IP (Descoping) | PTP-EP team drafted Pay@accept for both IP and IF system and taken approval from business. As per latest alignment with Wilson Sean, business required Pay @ accept in only IF system. So we need to descope PTPE0732_IP. | Business not required Pay@accept in IP system because business is not implementing Pay@accept functionality in IP system. | N.A. | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/EXT%20RE%20Discussion%20on%20Pay@%20Accept%20.msg?csf=1&web=1&e=pZhJY9 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-18 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0965 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Chandrika Chaudhary |  | PTP - Richard Taylor | [9 empty] | Layout changes for mass utility | Layout changes | All the Mass utility PO,PR,SL, PIR, OA, QA needs changes on layout side as requested by Pavan |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Murthy to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-18 | 0 | < 15 Days | mochawla@deloitte.com |  | No |  | No Objects |  | In Progress | No
R1 (Hypercare) | R1 | INT-CR0966 | Approved |  | ERP | R1 Hypercare |  | 09A. Master Data | 9A.5 Master Data - Finance |  | 09A. Master Data | mauricio.otarola.guevara@intel.com |  | Data - Julie Fawdington |  |  | INC14739822 | [6 empty] | Adding a field in MDG node change report – GL account | A new field (G/L Account Type) needs to be added to MDG node change report – GL account | Node change report – GL account is a custom MDG report used by IT to get new GL or GL changes from new MDG to be loaded to legacy MDG or from new MDG Production to new MDG QA. G/L account type is a required field to be loaded but is missing in the report. | No | No |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0966%20Adding%20a%20field%20in%20MDG%20custom%20report.pptx?web=1 |  | 3. Configuration Change |  |  |  | Low | 0 | [7 empty] | 8 | [5 empty] | 0 | 8 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-29 | o This request is to add a required field in order to identify the change required (GL Account Type). • Work will be performed by the Master Data Team, and there is no impact to the current work | [9 empty] | Other | Tower | 2025-07-29 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0967 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | Hari Gore | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | Cancellation of Object: FPRR1418 - Reconciliation of mixed ratio costing | FPR - Cancellation CR for RICEFW - FPRR1418 - Reconciliation of mixed ratio costing | Expected output details already available in FPRE1438, hence this report can be cancelled. | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0967/RE_%20CR%20for%20cancellation%20of%20RICEF.msg?csf=1&web=1&e=8YpX4B | N/A |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRR1418 | FPRE1438 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-29 | [10 empty] | Other | Tower | 2025-10-29 | 10, 2025 | 10, 2025 | 07, 2025 | 2025-07-21 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0968 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | hgore@deloitte.com |  | FPR - Aubrey Hinderlider |  |  | NA | [6 empty] | MiddleWare Approach Change for Interfaces | As per the confirmation from middle ware team , for few RICEFW's ( FPRI1288, FPRI1273, FPRI0554, FPRI1287), we need to change the middle ware from BODS to Mule soft as the data volume for these interfaces would eb less than 20MB. | Data volume is less than 20MB, hence we need to change the approach from BODS to Mulesoft for few interfaces. | Impacting the deliverables of FPRI1288, FPRI1273, FPRI0554, FPRI1287 objects from middle ware. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0968%20-%20FPR%20team%20%237%20-%20BODS%20to%20Mulesoft%20Change%20.pptx?d=w7dfe307fa1c0469c8ad1b89da51bc7cc&csf=1&web=1&e=JY2awM |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Low | 0 | [8 empty] | 64 |  |  |  |  | 0 | 64 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRI1288, FPRI1273, FPRI0554, FPRI1287 | 4 | FPRI1288, FPRI1273, FPRI0554, FPRI1287 | 4 |  | 0 |  | 0 | N/A |  | 2025-09-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-31 | o Since this is not a huge volume, Mulesoft should be used as the primary middleware for these types of situations. • These objects are designed (HLTA was started - High Level Technical Assessment), and the build has not been started | [9 empty] | Build | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0969 | Cancelled |  | ERP |  | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Rekha Bhat | [11 empty] | Add - Header - shipping condition, Rma header comments , Line Item - currency , pricing date, intel po, batch id, sublineqty and box id. | Add - Header - shipping condition, Rma header comments , Line Item - currency , pricing date, intel po, batch id, sublineqty and box id. | Add - Header - shipping condition, Rma header comments , Line Item - currency , pricing date, intel po, batch id, sublineqty and box id. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Pramod to be cancelled as an internal CR was created. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-21 | 0 | < 15 Days | rekbhat@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0970 | Cancelled |  | ERP | R1 Hypercare |  | 09A. Master Data | 9A.5 Master Data - Finance |  | 09A. Master Data | Huiying Jiang |  |  |  |  | DATR0787 | [6 empty] | Report to send notification to direct managers about the Inactive cost center Approvers | A new PDF of all the list of inactive cost center approvers to attach the file in that email. | A new PDF of list of inactive cost center approvers in the email , instead of share those data into email body |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-21 | 0 | < 15 Days | harshaharshavardh@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0971 | Approved | Presenter: Venkata | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP | Sekhar Lingam |  | FTS IP - Loni Adams |  |  | 01596 | [6 empty] | Change Request for MRP Process of Pre PRQ Substrates in SAP S/4 | MRP Process of Pre PRQ Substrates in SAP S/4 | Substrate planning for HVM and Engineering products is handled by existing planning application 'MAPPS'. This generates procurement proposals after netting with inventory. These procurement proposals will be created in SAP S4 as Purchase Requisitions via PDH and BODS. However, substrate planning for pre PRQ will not be handled by MAPPS and need to be taken of by S4 directly or manually. Hence it is proposed to automate this process in S4 by executing MRP Run |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0971%20%E2%80%93%20Change%20Request%20for%20MRP%20Process%20of%20Pre%20PRQ%20Substrates%20in%20SAP%20S4.pptx?d=w196d3018620743b8bd6b5ea61c918820&csf=1&web=1&e=P95Tp6 | Design / Build Gap | 1. Process Scope / Design Change |  |  | Very High |  | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-07 | o This is introducing planning process via MRP for pre-PRQ substrates in SAP S4 • MAPPS is catering to HVM and Engineering and will continue to R5 • It was not meant for commercial products. • Pre and post-PRQ will have different MRP Areas, which will be controlled by using different reference data. o AR: Adjust wording to clarify what is new work (MRP Configuration) and what impacts there will be. Need dates on when everything will be completed – @Vytla, Kumar @Lingam, Sekhar @Maxey, Stef | 2025-08-07 | o FTS IP team connected with PTP and MDG to confirm the work required. • PIR is already in conversion scope, and the Materials already exist in ECC. o This CR will only require configuration changes, and the team is planning to complete in the next 2 sprints. Will meet ITC1. o AR: Need to add in details that there is no impact to MDG and PTP team. Configuration will be done by FTS IP team - @Kamineni, Venkata Ramana | [7 empty] | Design | Tower | 2025-08-07 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-21 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR0972 | Approved |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | john.p.heiney@intel.com |  | FTS IF - Haritha Komma |  |  | CR | [6 empty] | Frozen Period for Demand Schedules | Create a Frozen Period for changes to the Demand Schedule that is passed to the factories and to Production Scheduling as the Factory output goal | When multiple factories are producing the same item, it is possible for the Demand schedule linearity to change at one factory due to changes in the projected outs at another factory, even in the first week of the horizon. | no | No |  |  | https://intel-my.sharepoint.com/:p:/p/john_p_heiney/EdxWQp6kZOhLjWy2JO8qHMIBzz_pwVbu3T-2qkYYRWxv2w?e=1ltk9b |  | 1. Process Scope / Design Change |  |  | Low | N/A | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-22 | Approved by Uzma offline | [9 empty] | Design | Tower | 2025-07-22 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0973 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data 13. Security | rahulx.nazar@intel.com | [11 empty] | Security Role correction for Reference master data | - New security role requested especially for Shipping Conditions approver role and not to re-use existing customer role, which was previously decided. | - As per discussion with Andrew T Austin, the expectation is to create a new dedicated role for Shipping Conditions approver rather than reusing any existing role. This is because the current role may not always align with the position as there is an anticipation of role loss and reorgs to happen between now and 2027. |  | No |  |  |  |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-22 | 260 | > 30 Days | shrutisingh7@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR0974 | Approved | Added | ERP | R2 Hypercare | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [6 empty] | INC14847461 | Delivered |  |  |  | The change aims to update Customer Group 2(CG2) in the Sales Order by determining it exclusively from the Ship-To master, rather than from Sold-To. This is applicable for both create and change scenarios. Update determination logic so that CG2 in the SO is sourced only from the Ship-To master. Ensure these changes are reflected across all relevant interfaces and documentation. | Populate Customer Group 2(Ship ahead window) from Ship-To-Party instead of sold to party​ | The change aims to update Customer Group 2(CG2) in the Sales Order by determining it exclusively from the Ship-To master, rather than from Sold-To. This is applicable for both create and change scenarios. Update determination logic so that CG2 in the SO is sourced only from the Ship-To master. Ensure these changes are reflected across all relevant interfaces and documentation. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B069993E5-9127-4C69-9180-4EE1C9A65585%7D&file=INT-IF-Build-CR0499_Populate%20Customer%20Group%202(CG2)%20from%20Ship-To-Party%20Master%20Data.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | 25 | 2 |  |  |  | 25 |  |  |  |  | 25 |  |  |  |  | 25 | 25 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0002_IF | 1 | OTCE0002_IF | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-24 | o This change was a originally a defect and was discovered during a window when the team did not want to make changes • This does not impede go-live and is a small change that will complete in 2-3 days o This will be implemented during Release 2 Hypercare | [8 empty] | Cancelled as tech effort was less than 40 hours of effort. Instructed teams to move to Build CR log | Build | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-22 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0975 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Descoping PTPI0470_IP object and Renaming PTPI0470_IF into PTPI0470_CFIN | Initially for sending the Payment proposal from IP and IF system to Ariba, we created PTPI0470_IP and PTPI0470_IF. But right place for this development is CFIN system. PTP- EP team want to rename one existing object into CFIN object and the other one to be cancelled. Functionality and requirement from business standpoint remain the same. | We can send payment proposal data from CFIN system only. | N/A | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/EXT%20RE%20GPO%20Approval%20for%20CR%20-%20Switch%20Payment%20Proposal%20Interface%20to%20CFIN%20.msg?csf=1&web=1&e=lgUtOw |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 30 |  |  |  |  | 0 | 30 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0470_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-22 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0976 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 09A. Master Data | susan.strathman@intel.com |  | FTS IF - Haritha Komma |  |  | No | [5 empty] | WIINGS | Enterprise Structure Configuration Change | This change initiative will close identified gaps in the initial Enterprise structure (ES) design for R3 sites, ensuring alignment with commodity segregation and compliance requirements. The current enterprise structure has been updated to: Accommodate a new plant integration in Chandler, AZ (Lotus) Incorporate additional storage locations for Bailment, Chemicals & Gases, and Heavy Metals, which were not in the business plan during the initial design phase | After completing the initial Enterprise Structure design, business decisions were made between Intel and the US Government that changed the Chandler, AZ campus warehouse usage and required utilization of the Lotus warehouse – which previously was planned to sunset in 2026 and therefore not in initial designs Material segregation conversations with the Copper Czar revealed we needed a Heavy Metals storage location (in addition to existing Copper and Non-Copper) While we worked on building the internal system processes it became clear that our initial design could not handle Bailment or Chemical & Gas materials to meet business requirements. (See Risk below). | Teams can accommodate with existing schedule by end of Sprint 19 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/R3%20Enterprise%20Structure%20CR/INT-CR0976%20Enterprise%20structure.pptx?d=wbcc817d82b6c4735a349bdb3ca0967f4&csf=1&web=1&e=fvh2bJ | Design / Build Gap | 1. Process Scope / Design Change |  |  |  | Very High (because multiple towers but I believe the work is High) | 0 | [7 empty] | 25 | [5 empty] | 0 | 25 | Configuration | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-24 | o AR: Add detailed breakdown of the 537 hours of EWM effort - @Johnson, Graeme o AR: Add in list of plants that will be changed - @Alvarez Carroz, Ruben David |  |  | 2025-08-01 | • The CR involves updates to the enterprise structure for storage locations across Chandler, Oregon, and Aloha due to: o A new building in Chandler replacing CH4. o The need for better visibility into inventory, especially for rail-in processes. o The changes include both simplification and expansion of storage locations, impacting configuration, documentation, and master data. • The effort was initially estimated at over 550 hours but was reduced detailed review: o Enterprise Team Estimate Efforts: 25 hours for structure changes, to be completed by EO of Sprint 17. o EWM Estimate Efforts: 347 hours for 3 Sprints, Sprint 17-Sprint 19 o Master Data Estimate Efforts: <40 hours o Execution is planned for Sprints 18 and 19, aligning with testing timelines for DXO and 3PL integration. o The team emphasized that this is a must-do change, with no expected displacement of other work if executed as planned. o Dustin from warehouse operations validated assumptions and helped reduce design time by leveraging prior discussions for CH4. • Mike Lange and Rick Antonellis stressed accountability: if this CR causes delays, the change team must own the impact. • AR: Susan Strathman add CR number to the PPT documentation. | [5 empty] | Design | CL/OSC | 2025-08-01 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR0977 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | NJAIN42@deloitte.com |  | FTS IF - Haritha Komma |  |  | NA | [6 empty] | Automated Batch Status Update Based on MRB Release Date | Develop an automated process to release batches of SFG materials that are placed on hold due to MRB events, ensuring their release is triggered automatically when the MRB release date becomes current. | Recent discussions discovered that to search, and update Batches within SAP, based on MRB date, will be much efficient, and right place to do it rather depending on the signal from SMH as SAP serves a source system of Inventory. | No impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/EXT%20RE%20New%20CR%23%203068%20Automated%20Batch%20Status%20update%20based%20on%20MRB%20date.%20(Approval%20Required).msg?csf=1&web=1&e=KVC9fo | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0xxx_FTS-IF_Automated%20Batch%20Status%20Update%20Based%20on%20MRB%20Release%20Date.pptx?d=w8bf11d6bb003475788477aa262f02a65&csf=1&web=1&e=TmIWfl |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | FTSE1581 |  | FTSE1581 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-24 | o This request is to support the release capability; the ability to receive and change the signal is already present o Will wait until November to get into the queue for tech team o There was no plan to do this on the PDF side o AR: Provide tech effort estimate - @Nayak, Keerti | [9 empty] | Other | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R2 (Aug 2025) | R2 | INT-CR0978 | Rejected |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF | greg.underhill@intel.com |  | FTS IF - Haritha Komma |  |  | CR | [6 empty] | Run additional BY Tech Solve on Monday | R2: Run additional BY Tech Solve on Monday as an interim solution for Informatica DQ reporting (minor change). Requesting to be reviewed in Change Ingestion ww30.Thurs. | low-cost interim solution, due to informatica delays | None. this is very low-impact. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/Change%20Requests/Pending/IAO%20R2%20BY%20design%20-%20Run%20Weekly%20Monday%20Technical%20Solves%201.pptx?d=w6c5e0ab10dd24a5ea140c8c2811d9d27&csf=1&web=1&e=2oocmw&xsdata=MDV8MDJ8fDZlNmVmZDNhNDliMzRjMzc5ZTQ4MDhkZGM5N2M5MGY0fGQ1MmM5ZWExN2MyMTQ3YjE4MmEzMzNhNzRiMWY3NGI4fDB8MHw2Mzg4ODgyNTkwMDE1NTk3MTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKRFFTSTZJbFJsWVcxelgwRlVVRk5sY25acFkyVmZVMUJQVEU5R0lpd2lWaUk2SWpBdU1DNHdNREF3SWl3aVVDSTZJbGRwYmpNeUlpd2lRVTRpT2lKUGRHaGxjaUlzSWxkVUlqb3hNWDA9fDF8TDJOb1lYUnpMekU1T2paa1lqQXdNalkxTFRReE5Ua3RORFZtTlMxaE56RXpMVGRrWXpBd1pXRXpZV000WTE5bFpHSmhaVGt4T1MwNU0yVTJMVFJqWmpRdE9UQm1ZUzFqTmpGaE0yUTVNems1T0RKQWRXNXhMbWRpYkM1emNHRmpaWE12YldWemMyRm5aWE12TVRjMU16SXlPVEE1T1RneE13PT18MmE5MjZiMWU1YjM3NDExYTI1MTcwOGRkYzk3YzkwZjR8OGM5NzdkOTA1ZDE5NGM1MDljMDljOWU2YWIyMzg0ODI%3D&sdata=MzhVOURQMytzbUo2MG5UUlpDTm90dy8xTklrVmgvT3ZsQlZWbTlGN1IzMD0%3D&ovuser=46c98d88-e344-4ed4-8496-4ed7712e255d%2Cmonax.kamath%40intel.com |  | 1. Process Scope / Design Change |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-07-24 | o AR: Clarify if there would be any tradeoffs to R3 work to complete this change - @Underhill, Greg o AR: Explore whether this capability can be done manually if change is not approved - @Underhill, Greg o AR: Understand who will be performing the Informatica work - @Underhill, Greg o AR: Provide details on which teams are needed to perform the work and how long will be required | [8 empty] | Confirmed by Rocco to be cancelled as the team was able to get the DQ timeline pulled back-in intime to intercept R2 deployment | Design | Not Assigned |  | Not Approved | 07, 2025 | 07, 2025 | 2025-07-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0979 | Approved | Added | ERP | R3 (Release 3) |  | 10. Analytics | 10.3 Analytics - FPR |  | 03. FPR | kritajoshi@deloitte.com |  | Data - Julie Fawdington |  |  | NA | [6 empty] | ECA Views objects additions in Deloitte Object Tracker | ECA Views objects [Intel Approved] need to be added to the object instead of adding every sprint. The previous objects have been identified as 3rd party objects and have moved into Intel tracker as they would be building the front-end. Also, update the Sprint 16 build sprint plan. | The objects previously in the Deloitte Tracker were identified as 3rd Party reports and have transitioned into Intel Tracker. In place of that the backend views to support those end-reports have been identified post data modeling workshops. | No Impact. | No |  |  | https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0979%20-%20ECA%20Views%20to%20be%20added%20to%20Object%20Tracker.xlsx?d=wbd19e2c6a84e41e3b9b3e735c4caddc4&csf=1&web=1&e=5o0w7m |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-24 | o This is a request to add all of the ECA views required to support 3rd party reports. | [9 empty] | Other | Tower | 2025-07-24 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0980 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan |  | FPR - Aubrey Hinderlider | [9 empty] | New GL Trial Balance report functionality and output display | 1. Ensure that the report is not using PBI but generates only excel based output 2. Use static table for P0, Fixed table for past periods and Variable table for current period 3. Ensure that report output has balances for both ECC and S4 eventhough it is not matched 4. Manually build the report initial period balance till Go-live period | 1. The report cannot be run as background job 2. The output has both summary and detailed view 3. The report runs only for S4 company codes 4. The report doesnt display the balances directly posted in S4 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR0980_Trial%20Balance%20update%20CR.pptx?d=w443b580937b64da286b1c60a63a5459c&csf=1&web=1&e=vD6dOB | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  | Very High |  | 4 | [9 empty] | 389 |  |  |  | 0 | 389 | ECA | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRXR350 | 1 |  | 0 | FPRXR350 | 1 |  | 0 | N/A |  | 2025-08-22 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-29 | o The recon work is being done manually in the system. o It is a part of the production support activities, and we don’t want to do it manually. This report will help automate • The team spends a lot of time at month end to do the recon, and it is affecting R3 work. • It usually takes around 1 week for the team to do the recon work, and the report will be to help efficiency for 1.5 years. • The report will be tweaked during R3 so that it will be implemented there. It is required functionality going forward for all 3 systems. • Need to make sure that balances tie in as part of month end. They are straddling right now until R3. o It was planned to be delivered in Hypercare while the team did workarounds in the meantime o It will impact R3 work and will require additional resources, but it is a critical report • Plan is to move certain things out of the next sprint and add an additional resource (3 objects) • The 3 reports being pushed out will still make the build timeline, but it will be delivered in Sprint 18/19 out of the 21 sprints. o AR: Include sentence that Deloitte ECA will be doing the work o AR: Add in the total effort and people required to do the manual reconciliation o AR: Add details on the manual workaround that exists o AR: Add in comment that it is required for all Releases o A different recon report has already been built. This request is to add in all of the robust requirements that were missed in the other one. |  |  | 2025-08-01 | • This CR is the final component of a multi-part report suite initiated in R1, following the FI and C reconciliation reports. The goal is to compare ECC and S4 data to support audit requirements. The report is already in progress, but due to unexpected complexity, the team is requesting additional hours to complete it. • A manual workaround exists and was used during R1 parallel testing, but it is labor-intensive and not sustainable long-term. • Shane Bethune and Rebecca Verette confirmed the report is required and that Deloitte is scaling resources to deliver it. • To accommodate this, some R3 deliverables will be delayed by one sprint, but the team plans to catch up quickly. • The CR will be updated to reflect this sequencing change and remove the R2 hypercare tag, treating it as a standard R3 object. • Mike Lange approved the CR but requested a change in sequencing: prioritize R3 testing first, then proceed with this report to avoid adding risk to R3. • AR: Indra Singh: Share and finalize the CR document. Ensure updated scope and sequencing are reflected. | [5 empty] | Other | CL/OSC | 2025-08-01 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-23 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0981 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 03. FPR 07. FTS IF 08. FTS IP 09A. Master Data | lilibethx.lejarde@intel.com |  | Data - Julie Fawdington |  |  | N/A | [6 empty] | Product Costing on BOM extended to Multiple Plants | Product Costing on BOMs that are extended to multiple plants | Product costing needs to explode to the lowest level and needs to be as accurate as possible | N/A | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-24 | 258 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
| N/A | INT-CR0982 | Cancelled |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shubhangi Mehrotra | [11 empty] | Cancellation of below objects - LOGI1292 - ECD_Interface from ECD to S4 for inventory status call LOGI1294 - ECD_Interface between S4 to 3PL for inventory status webservice LOGI1296 - ECD_Interface between S4 to ECD for inventory status response | These RICEFW IDs need to be cancelled, as these requirements are getting captured under the different RICEFWs - LOGI1571, LOGI1575, LOGI1576 | Requirement is getting captured under different RICEFWs. This cancellation is happening because of the ECD re-design. |  | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0982%2FEXT%20RE%20Requesting%20approvals%20CR%20ID%20INT%2D%20CR0982%2Emsg&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR0982 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | To be combined with all other ECD changes. Original CR was CR0878 | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 07, 2025 | 2025-07-24 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0983 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | hgore@deloitte.com |  | FPR - Aubrey Hinderlider |  | CR1111 | NA | [6 empty] | New CR - Drive Overhead Cost Center – Standard Cost Estimation and Actual Template Allocation | As per Tech team - Required a Separate CR/WRICEF for enhancement "Replace Corporate overhead cost center for overhead template" | Currently we have one WRICEF FPRE1419 to apply Overhead and Cost from the sourcing Plant but the program is different for Template allocation. New CR required for Replace Corporate overhead cost center for overhead template. | Functional Specification is already prepared and Approved from Business. No impact to existing Deliverables. | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Hari Gore to no longer be needed. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0984 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Naved Naved | [11 empty] | Additional change in existing object LOGE1266- Copy to all functionality to be included in Fiori App | Copy to all functionality to be included in Custom receiving screen fiori applicationat header level for bulk and serialized receiving and also at line item level for multiple sub lines. | In case of bulk and serialized receiving, copy to all functionality to be included for the fields in the sublines for the custom receiving screen at header as well as line item level. |  | Yes |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Build CR0652 was created as tech effort was less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-24 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0985 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 07. FTS IF 08. FTS IP 09A. Master Data 10. Analytics | llejarde@deloitte.com |  | Data - Julie Fawdington |  |  | N/A | [6 empty] | Product Costing for BOMs extended to Multiple Plants | Product Costing for BOMs extended to Multiple Plants | •Production of finished goods can go from one plant to another in any stage •Full Product Costing functionality will be done in S/4 •To achieve a more accurate product cost estimate, the capability, "Mixed Product Costing”, will be used. This functionality is standard when products are manufactured using multiple production plants (or BOMs in another plants). As the planning is done outside of S/4, the capability needs ratio or volume for each items and locations. This information is in PDH and ECA. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR0985%20-%20Product%20Costing%20for%20BOMs%20extended%20to%20Multiple%20Plants.pptx?d=w57b8a9edf79f417c8f5c4dd80c545a28&csf=1&web=1&e=SNgxj3 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | High | 0 | [8 empty] | 32 |  |  |  |  | 0 | 32 | Tech - S/4 | No |  | 0 | N/A | 3164 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE1419, FPRE1438, FPRI1439, ECAFPRV887 | 4 | FPRE1419, FPRE1438, FPRI1439 | 3 | ECAFPRV887 | 1 |  | 0 | N/A |  | 2026-02-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | o This request is required for product costing when BOM is extended to multiple plant. o If business is buying from 3 different plants, then there needs to be a weight based on the different plants for product costing.  It is for inventory valuation and standard cost, and it will required a BY connection. o Design is complete, and the changes will be available before ITC1. o AR: If the complexity is not low, then the CR will need to come back to Ingestion. - @Tam, Anna | [9 empty] | Build | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R1 (Hypercare) | R1 | INT-CR0986 | Approved |  | ERP | R1 Hypercare | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [11 empty] | Security roles for Sub consolidation | Enhance security roles so that Subconsolidation owners only have access to modify the group structure for the subconsolidation group(s) they own and to limit report access to those that are specific to their subconsolidations group They are permitted to change the divestiture period for a consolidation unit within any SubConsolidation Group they have access to, enabling them to remove that unit from the group structure. SubConsolidation owner cannot make changes to the group structure or utilize data/cons monitor of any subconsolidation groups outside their access permissions Subconsolidations owner can only access reports related to their subconsolidations area (i.e. exclude US GAAP) | To restrict the ability to change the group structure or view reports related to the subconsolidation group they own |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CRXXXX_R1_Group%20Structure%20Access.pptx?d=wa9f7c1a03028474280aade3275f9d9e6&csf=1&web=1&e=QroBuD |  | 6. Build Security-Related Changes |  |  | High | 10 | 3 | [11 empty] | 10 |  | 0 | 0 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-08-07 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-29 | o This security change at the sub-consolidation level is required to proceed with US GAAP consolidation. | [9 empty] | Build | Tower | 2025-07-29 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-24 | 0 | < 15 Days | kdey@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR0987 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.4 FPR - Intercompany |  | 03. FPR 11. Technology | Swati Ashok Jogi | [11 empty] | FPRE0289_IP/IF - Bailment Indicator should be populated in XREF3 field for all IC revenue and IC COS lines. | Bailment Indicator should be populated in XREF3 field for all IC revenue and IC COS lines. | We identified to bifurcate the materials as Bailed / non Bailed the Bailment Indicator is Required. | NA | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR0987Bailment%20Indicator%20should%20be%20populated%20in%20XREF3%20field%20for%20all%20IC%20revenue%20and%20IC%20COS%20lines..pptx?d=w92f5effef6304f38a98252d37f501c73&csf=1&web=1&e=1UtkSa |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Low |  | 1 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael that INT-Build-CR0918 was created for it | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-24 | 0 | < 15 Days | sashokjogi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0988 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-25 | 0 | < 15 Days | automation@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR0989 | Cancelled |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP 13. Security | shivkulkarni@deloitte.com |  | FTS IP - Loni Adams |  | CR | NA | [6 empty] | Cancellation of SFUT role FTS IP - Divisional Planner - [Plant] BSPID-39755 | This role is not applicable for FTS IP so request for cancellation | Not related to FTS IP |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | All SFUT activities are captured in a consolidated CR | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 07, 2025 | 2025-07-25 | 0 | < 15 Days | shivkulkarni@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0990 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | posunil@deloitte.com |  | FPR - Aubrey Hinderlider | [9 empty] | Cancel ECA object FPRXV040 - Cost center approver report | Finance team is cancelling ECA object FPRXV040 - Cost center approver report | Object (FPRXV040 - Cost center approver report) to be cancelled, as it will be developed by MDG team and not GL Close team. New customized MDG (DATR1430) report to generate cost center approver report | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0990/RE_%20GL%20Close%20RICEF%20Cancellation%20FPRXV040.msg?csf=1&web=1&e=wVbEjU |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV040 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0991 | New |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 02. E2E Process Integration 04. OTC IF 06. PTP 07. FTS IF 09A. Master Data | dinesh.r.basankar@intel.com |  | E2E - Aishwarya Bhat |  |  | NA | [6 empty] | WIP Inventory Movement of reject lots | Todd provided direction that reject lot shipment should use STO or SO against inventory in S4 for below scenarios. Do not use ISM to ship Intel product. Need to define the traceability process and inventory creation process in S4, so that Shipping TF can define the shipping process using STO and SO. Following scenarios should be covered: - IF Factory <-> IF Lab - IF Lab <-> IF Lab - IF Factory <-> IF Factory - IF Factory / Lab -> IP / IFS customer | Since this is a WIP inventory it is critical to have trace of the inventory. | Completion of Build phase by end of year, and hence start of testing next year | No | Non-Core |  |  |  | 1. Process Scope / Design Change |  | Yes |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-28 | 254 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0992 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP | dinesh.r.basankar@intel.com |  | E2E - Aishwarya Bhat |  |  | NA | [6 empty] | Usage of DUNS for Logistics Supplier | DUNS number is required to communicate with logistics supplier - carrier, broker. Intel has a common contract with them for IF and IP. Decision should be made if we can use common DUNS. | Need to keep IF and IP arms length distance However these will huge impact to supplier | This will impact B2B Build and testing timelines | No | Non-Core |  |  |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-28 | 254 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0993 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as there is no data |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-28 | 0 | < 15 Days | harshitapandey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR0994 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF 10. Analytics | Srikrishna Iyer | [11 empty] | Cancellation of ECA objects- 1. FTSFV023 (Sprint 15) 2. FTSFV026 (Sprint 15) 3. LOGV034_FTSIF (Sprint 16) | Duplicates to existing ECA objects. | Cancellation of objects due to the duplication. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR0994?csf=1&web=1&e=fo3BxG |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSFV023, FTSFV026 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-07-30 | [10 empty] | Other | Tower | 2025-07-30 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-28 | 0 | < 15 Days | harshitapandey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR0995 | Approved | Presenter: Murthy; Need ECA report complexity and alignment with Analytics | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 10. Analytics | vijasharma@deloitte.com |  | PTP - Richard Taylor |  |  | N/A | [6 empty] | New ECA report requirement for SIMS R3 straddle to send customer PO details from S/4  ECC | It is required to develop a report in ECA to extract the customer PO details from SAP S/4 IF system for SIMS in a CSV format and place in a shared folder. – All the key PO fields which are required for SIMS to create sales order in ECC and process needs to be extracted from S/4 and placed in a shared folder. In ECC system there is already a custom program which can mass create the sales order, this needs small change to process these files placed in shared folder. | As per SIMS business process customers from IP and IF systems create purchase orders to SIMS. Based on the orders received , SIMS front office creates sales order and then issues subcon POs to ODM supplier for manufacturing. ODM supplier will directly ship the materials to customer. Since SIMS is planned to go-live in S/4 as part of release 4, but various SIMS customers in IP and IF are going live in release 3. Therefore, it is required to send the customer purchase order details from SAP S/4 to ECC system. Without the customer PO details SIMS cannot fulfil those orders. | ECA team needs to provide the build plan for this object | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B04D1ACBB-C63F-4B24-BD40-E95A025B875C%7D&file=INT_CR0995_SIMS%20R3%20Straddle%20PO%20details%20from%20ECA%20to%20ECC.pptx&wdLOR=cF9DFB98C-DD17-4645-A022-9CD5BC637777&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-08-28 | o AR: Confirm that ECA team can deliver in Sprint 20 @Sadarangani, Aarti |  |  | 2025-08-29 | • Decision - Approved o The ECA team committed to completing the report prior to R3 ITC1, and the CR was approved without trade-offs. | [5 empty] | Other | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0996 | Rejected | Presenter: Murthy | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | pvemuri@deloitte.com |  | PTP - Richard Taylor |  |  | N/A | [5 empty] | WIINGS | Develop a Fiori Dashboard to monitor PM orders and related purchasing documents and error management | Develop a Fiori dashboard to monitor the PM orders related to return document creation processes. This is required to provide real-time visibility into the status of various purchasing documents (e.g., return & repair purchase orders, STO documents, Warranty PRs etc.) generated through multiple RICEFW objects PTPE0961, PTPE0962. | Currently, there is no standard mechanism to monitor the end-to-end processing of PM orders and their associated purchasing documents. Users lack visibility into whether documents are created successfully or if errors have occurred, resulting in manual tracking and delayed issue resolution. Considering the huge volume of PM order items, this enhancement addresses the need for a centralized, automated monitoring solution. | New RICEFW objects needs to be planned for Build and FUT | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Change%20Request%20Decks/INT_CR0996_WIINGS%20-%20Fiori%20UI%20dashboard%20requirement%20for%20PM%20orders%20processing.pptx?d=wb49d0d32059048bb8295c455338d7580&csf=1&web=1&e=DbawJF |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 07. OSC/CL rejected - no further analysis (end status) | Yes |  | 2025-08-07 | o As this will add to the WIINGS work, there is a risk to meeting ITC1. |  |  | 2025-08-15 | • The WIINGS business unit currently uses a dashboard that tracks all documents linked to Plant Maintenance (PM) orders, including: o Purchase requisitions and orders o Inbound/outbound deliveries o Stock transport orders (STOs) o Expedited orders o Follow-on documents and related errors • The request is to replicate this dashboard functionality in S4 via a Fiori app, enabling visibility into document flow and bottlenecks across logistics and maintenance processes. • Concerns Raised: o Anand Jha and Mike Lange flagged the high complexity and cost of building a custom Fiori app for error management across all document types. o Cari Shim clarified that the priority is error management, not necessarily a Fiori interface. o The team agreed that factory downtime and expedite monitoring justify a responsive solution, but customization should be minimized. • The team will explore standard SAP tools and processes to meet the error management needs with minimal customization. • The solution must simulate and display errors that prevent document creation (e.g., failed PO creation from PM order). • AR - Murthy KP to sync with Kalpesh Shah and Keerti Nayak regarding a scalable, maintainable alternative solution for WIINGS error management that avoids over-customization | [5 empty] | Other | CL/OSC | 2025-08-15 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0997 | New |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma | [9 empty] | New Enhancement for PROSPAL replacement​- KM2/KM5 | New Enhancement for PROSPAL replacement​- KM2/KM5 Shipping WG in the Manual ship custom SAP Shipping Fiori app to enable KM to KM WIP inventory movement | New requirement for KM2/KM5 flow ( PROSPAL Replacement​) |  | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0997_FTS-IF_NEW%20RICEFWs-KM2KM5%20flow%20from%20manual%20ship%20.pptx?d=wa6d0fe3b98e64319a5dd7e4ba5f82396&csf=1&web=1&e=PHUait |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-28 | 254 | > 30 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR0998 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Prashant Shinde | [11 empty] | Additional change in existing object LOGE1266-Label functionality to be included | Addition of check box at line item level to select all sublines for mass printing and 2nd Check box to ON/OFF (Activate and Deactived)“ Auto Print” functionality. Updatation of “X” indicator against each subline records if .XML message sent to loftware to classify whether label is printed successfully. | LOGI1312 interface object covered all the requirement related to Label interface. Addition of check box at line item level to select all sublines for mass printing and 2nd Check box to ON/OFF (Activate and Deactived)“ Auto Print” functionality. Updatation of “X” indicator against each subline records if .XML message sent to loftware to classify whether label is printed successfully. |  | Yes |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Build CR0653 was created as the tech effort was less than 40 hour | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-29 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR0999 | Cancelled |  | ERP | R2 Hypercare | Medium | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data | rahulx.nazar@intel.com | [11 empty] | Email notification Load template for FS DATE1044 | - Include target system ID in the template - include Rejection comments - Prepare a different template for Load file | - Need to add a section that describes the system to which the data gets replicated - Need to add the reason for rejection and display it - Load CR should not have the details of all the records been created/updated. Hence, a separate template is required for Load scenario |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Aditya Pandey to be for R3 and less than 40 hours of technical effort. INT-Build-CR0597 is created. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-29 | 0 | < 15 Days | adityaspandey@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1000 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data 13. Security | rahulx.nazar@intel.com | [11 empty] | Security Role correction for Reference master data | Security role created for requestor is segregated, but it should have been CORP. | This is because initially it was decided to have segregation in place, but eventually it was decided not to proceed with segregation, which is in alignment with the design as well. Security team needs to change MDG [XX] - Reference Data - Sales Org & Dist. Channel, Division - Requestor as CORP role |  | No |  |  |  |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-29 | 253 | > 30 Days | adityaspandey@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1001 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.3 OTC IF - Billing and Rebates |  | 04. OTC IF | Eina Gupta | [11 empty] | Enhancement to invoice hardware and linked service on the same day with same profit center and the link displayed in the output form | . New RICEFW required for IF - Billing and Rebates to create custom routine for service line item to restrict Billing for service item if it is linked to a higher level item where the higher level item PGI is not complete and billing is pending. | The enhancement ensures accurate RAR posting of both Hardware and associated VAS in the same period |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1001__OTCIF_New%20Enhancement%20to%20invoice%20hardware%20and%20linked%20service%20on%20the%20same%20day%20with%20same%20profit%20center.pptx?d=w57f5db75e7724124ae00a630f411f1db&csf=1&web=1&e=bKsvzf |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-30 | 0 | < 15 Days | eigupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1002 | Approved |  | ERP | R2 Hypercare | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 13. Security | Amith Vallabhaneni |  | Security - Raj Valluri |  |  |  |  | Standalone | Delivered |  |  |  | Enterprise_SOX Audit Role Updates | 1 ) It was identified that the SAP GRC - Enterprise Auditor – Prod role and SAP GRC - IT SOX AUDIT – Prod roles have wider access compared to what is actually needed. The roles have sensitive risks that can be remediated. As part of this change, we will be removing the Tcodes that are sensitive from these roles and updating them with the additional display transactions required as part of their role. Note: These were existing roles created by Intel and not part of the IAO program 2) 13 task roles in GRC are impacted due to the SU24 changes that were performed so far. These roles will be maintained in expert mode with their current authorizations so that the role status is green and no additional authorizations as part of previous SU24 update are pulled into the roles during further changes | 1) To remediate sensitive and SOD risks in External audit and IT SOX roles and grant display only access 2) To avoid manual and changed authorization maintenance of roles by use of SU24 update | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/R1_Enterprise%20Auditor_IT%20SOX%20Audit%20Role%20Update.pptx?d=w820f101454b54395b6349c2193992c9e&csf=1&web=1&e=gF7NkT |  | 6. Build Security-Related Changes |  | No | Low |  | 1 | [11 empty] | 20 | 0 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-05 | Approved in Hypercare CR meeting with OSC | [9 empty] | Build | Tower | 2025-09-05 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-30 | 0 | < 15 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1003 | Approved | Presenter: Surendra | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP 11. Technology | Surendra Julury | [11 empty] | Custom Receiving screen (ZPRDI) to have functionalities to process receiving of customer Returned Materials | Validation of Intel Part number field entered by the user w.r.to the material in the custom receiving screen. On click on verify API call to be made to ECA to validate the Intel Part number entered and send the response back to EWM system. | Validation of Intel Part number field entered by the user w.r.to the material in the custom receiving screen. On click on verify API call to be made to ECA to validate the Intel Part number entered and send the response back to EWM system. |  | Yes |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/05. OTC - Intel Products/4 Working Documents/IP Returns-EWM/CRs/INT-CR1003 OTC IP EWM IPN API.pptx?d=wcf1571ae62a74ba0ba9463664cd926f1&csf=1&web=1&e=g34pNi | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCF1571AE-62A7-4BA0-BA94-63664CD926F1%7D&file=INT-CR1003%20OTC%20IP%20EWM%20IPN%20API.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 40 | [5 empty] | 90 |  |  |  |  | 0 | 90 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI1271 | 1 | LOGI1271 | 1 |  | 0 |  | 0 | N/A |  | 2026-04-17 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-21 | o This particular piece of knowledge is written in the FS of the enhancement, but tech team wants the logic to be written to the interface as well. • This validation is required because we need to do it at the ECA level o AR: Review process to understand why validation is occurring in ECA (as EWM should be able to validate material number) - @Julury, Surendra @Miller, Sarah A | 2025-09-11 | o AR: Update deck to better represent the chain of events and include the business value (needed for the receiving process) - @Julury, Surendra  All required data is provided in SPEED, not BOM. Therefore, there is a requirement to connect to ECA.  The logic was originally captured in the FS of the enhancement (when the source of the information was BOM), but that logic needs to be embedded into the LOGI1271 so that it can read the information from ECA.  No ECA work is required. | 2025-09-19 | • Introduced a change request for validating Intel part numbers during the receiving process by connecting SAP EWM to ECA for master data verification. • The enhancement involves transitioning logic from an enhancement object to an interface object for better alignment with technical standards. • This CR is planned for ITC2 and involves only data fetching from ECA, not writing. • The CR was approved, with confirmation that it is ready for ITC2 and does not impact ECA resources. • Decision: Approved | [5 empty] | Build | CL/OSC | 2025-09-19 | 09, 2025 | 09, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | sjulury@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1004 | Approved | Presenter: Surendra | ERP | R3 (Release 3) | High | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP 11. Technology | Naved Naved | [11 empty] | Fiori App development for Static disposition | Seperate enhancement object is required to capture the requirement of Static disposition Fiori Application | New enhancement object is required for the development of Fiori application for static disposition which was earlier combined with batch job enhancement of static disposition. According to tech team, Different object is required as the console was descoped (Console ID: 2849) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDD15F2E7-695A-414C-A66F-57A593A0670E%7D&file=INT-CR1004%20OTC%20IP_EWM_Static%20Dispo%20Fiori%20App.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | LOGE1608 |  | LOGE1608 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1310 | 1 | LOGE1310 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-21 | o Note to team: This does not need additional approval as it has already gone through the RICEFW review meeting. | [9 empty] | Other | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1005 | Approved | Presenter: Surendra | ERP | R3 (Release 3) | High | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP 11. Technology | Naved Naved | [11 empty] | Fiori App development for Dynamic disposition | Seperate enhancement object is required to capture the requirement of Dynamic disposition Fiori Application | New enhancement object is required for the development of Fiori application for Dynamic disposition which was earlier combined with batch job enhancement of dynamic disposition. According to tech team, Different object is required as the console was descoped (Console ID: 2849) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BE0B24ED5-7954-4DA5-8F16-F506C4CB3D38%7D&file=INT-CR1005%20OTC%20IP%20Dynamic%20disposition%20Fiori%20App.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | LOGE1609 |  | LOGE1609 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1281 | 1 | LOGE1281 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-21 | o Note to team: This does not need additional approval as it has already gone through the RICEFW review meeting. | [9 empty] | Other | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1007 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP 11. Technology | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Custom enhancement to edit the posted accounting document for Payment Term, Baseline date, and Withholding tax fields in IP/IF (Source System) vs CFIN | We will create a custom enhancement in standard T code's (FB02, FBL1N, FBL1H). This custom enhancement will include logic to bypass the ALE-Extern indicator restriction, allowing changes to specific fields Payment Term, cash discount fields, Baseline date, and Withholding tax fields in posted accounting documents without directly deleting or modifying database tables. After changes are made, the updated fields will automatically synchronize with the Central Finance (CFIN) system to maintain consistency between source and CFIN systems. ​ | The business needs to create a custom solution to get around the ALE-Extern indicator and clearing date restrictions, so they can update certain fields in posted accounting documents in the source system. | NA | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/2.%20Interfaces/E2Open%20Interfaces/PTPI0369_IF-IP%20Develop%20an%20interface%20to%20send%20inventory%20reports%20and%20MRP%20parameters%20from%20S4(IF)%20%26%20S4(IP)%20to%20suppliers/INT-CR1007_PTP_IP_IF.pptx?d=waf84a6702cca438797ae73f7d72cbfd7&csf=1&web=1&e=TzKb0D |  | 2. New RICEFW / ECA / Build Object |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A | Yes |  | 3 | PTPE1606_IP, PTPE1606_IF, PTPE1606_CFIN |  | PTPE1606_IP, PTPE1606_IF, PTPE1606_CFIN | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-07-31 | Withholding tax fields in posted accounting documents without directly deleting or modifying database tables. After changes are made, the updated fields will automatically synchronize with the Central Finance (CFIN) system to maintain consistency between source and CFIN systems. o This request is for a custom enhancement to prevent a reporting issues after payment. • The boundary applications are connected to S4 and not CFIN. So, all data is flowing from S4 rather than from CFIN. o The team worked with SAP for the past 2 months to identify a fix. The functionality is in the SAP roadmap, there is no set date. • Therefore, a new enhancement is required | [9 empty] | Other | Tower | 2025-07-31 | 07, 2025 | 07, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1008 | Approved | Presenter: Ganesh | ERP | R3 (Release 3) | High | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP 11. Technology | Pham Minh Phuoc Bui | [11 empty] | Change for (LOGI0663_IP/IF and LOGI0664_IP) Interface object in Transportation Management | The change involves re-arranging fields and updating logic in the XML structure for ZXCI and ZCUS interfaces between S4, MuleSoft, and OpenText. (LOGI0663_IP/IF and LOGI0664_IP). Change involves logic change, structure change, & fields addition & removals from Intel business & Open text team | This is a technical requirement from OpenText. Post TUT this was identified by OpenText. The current XML structure contains misalignments that could result in data loss or inaccuracies when transferring information to OpenText. Correcting these issues is essential to meet integration requirements and prevent downstream process failures. The changes ensure data integrity and compliance with OpenText standards. | NA | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1008%20-%20ZXCI%20%26%20ZCUS_PL_IPLA%20_CI%20outputs%20to%20carrier%20and%20customs%20broker%20output%20to%20carrier%20and%20customs%20broker.pptx?d=wf848d3c455494cbca99e56432faefb97&csf=1&web=1&e=y1PZk4 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High |  | 3 | [8 empty] | 82 |  |  |  |  | 0 | 82 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0663_IP, LOGI0663_IF | 2 | LOGI0663_IP, LOGI0663_IF | 2 |  | 0 |  | 0 | N/A |  | 2026-02-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-14 | o These changes were discovered during TUT. There are some fields that need to be changed where the structure of the XML file needs to be updated.  It is just a tech effort as there is no design change or functional effort o If this data is not sent to the customs broker, the shipment will not clear customs. It is also used for taxations.  There is no other options as it is technical fix.  There is no OpenText impact | [9 empty] | Build | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | ninema@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1009 | Approved | Presenter: Prabesh | ERP | R3 (Release 3) |  | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | hgore@deloitte.com |  | FPR - Aubrey Hinderlider |  |  | NA | [6 empty] | OSS Note 2358961 to allow COGS split based on Aux CCS | Implement OSS Note 2358961 to allow COGS split based on Aux CCS at time of delivery/PGI transaction. | COGS split required based on Aux Cost component structure , OSS note 2358961 instructions need to be applied to allow COGS split as per Aux CCS at the time of delivery/PGI transaction. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1009%20-%20FPR%20team%207%20-%20COGS%20split%20break%20up%20as%20per%20CCS%20during%20the%20PGI%20.pptx?d=wdf29d211e0b144efa684395c6c761619&csf=1&web=1&e=IXJ0zR |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 2 | FPRE1620_IP, FPRE1620_IF |  | FPRE1620_IP, FPRE1620_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-08-14 | This was approved 8/14/25 (refer to CR Ingestion recap 8/14/25) | [9 empty] | Other | Tower | 2025-08-14 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | Objects Cancelled |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1010 | Approved |  | ERP | R3 (Release 3) |  | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 11. Technology 17. B-App | lilibethx.lejarde@intel.com |  | Data - Julie Fawdington |  |  | 1096 | [6 empty] | 2A1 Message from S/4 to 3PL | Need an interface from S/4 to 3PL to send master data information | This is to replicate the 2A1 message that is flowing from ECC to 3PL. This functionality should carry over to S/4. | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1010%20-%202A1%20Message%20from%20S4%20to%203PL.pptx?d=wc3b27aaf42d44d0c93ef74fdfe0a346d&csf=1&web=1&e=EMXhEN |  | 2. New RICEFW / ECA / Build Object |  | N/A |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 4 | DATI1612_IP, DATI1612_IF, DATE1611_IP, DATE1611_IF |  | DATI1612_IP, DATI1612_IF, DATE1611_IP, DATE1611_IF | 4 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-08-07 | o This functionality is a part of the current process, but it was not covered in design. • So, this is a CR to replicate the same process in S4 so that 3PL’s don’t have to make the changes. o AR: Confirm which ITC cycle it will go through – @Nayak, Keerti • If the CR can be done in ITC1, CR will go through RICEFW intake • If the CR will be done in ITC2, CR will go through the CR Meeting | [9 empty] | Other | Tower | 2025-08-07 | 08, 2025 | 08, 2025 | 07, 2025 | 2025-07-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1011 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.5 FTS IF - TM | Yes | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP | Randall Paniagua | [11 empty] | New requirement to print the Bill of lading BOL (consolidated delivery document) from TM freight order | New Requirement: Print BOL for consolidated deliveries in TM Freight order As-Is: Manual, outside the system | No BOL for R2 FTS/OTC today because no stock transfers in US, but business recently identified that BOL is needed for DOT requirement - R3, this would be applicable for any inland transfers or sales of goods between any US sites for either FTS or OTC towers. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-%20CR1011-%20Bill%20of%20lading%20form%20output%20-%20FTS%20IF%20and%20IP.pptx?d=w119985da3c364b349f12c8451d366eeb&csf=1&web=1&e=lgPhXD |  | 1. Process Scope / Design Change |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Ganesh that the tech effort is less than 40 hours. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 07, 2025 | 2025-07-31 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1012 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | JR Hoover | [11 empty] | Cancel UI Object: FTSI1380 | Cancel Xeus/MARS interface to get Counter for hybrid maintenance | Per “Guiding Principles”, equipment maintenance will continued to be managed by the factory TD Automation, therefore interface is not required. | No Impact | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1012/EXT%20Re%20Approval%20for%20Object%20Cancellation%20FTSI1380.msg?csf=1&web=1&e=P63fgu |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1380 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | [10 empty] | Other | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-01 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1013 | Approved |  | ERP | R3 (Release 3) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 06. PTP 08. FTS IP 09A. Master Data | lilibethx.lejarde@intel.com |  | Data - Julie Fawdington |  |  | 0936 |  |  |  | 11140 | SPEED PDM (Next Generation SPEED) |  | External BOM - Extension Automation | Implement External BOM Extension functionality in S4 | Today’s process is incredibly manual, and user needs to perform multiple steps in SPEED system to trigger this followed by additional steps in SAP system. . Additionally, current process doesn't synchronize post-BOM extension updates from SPEED to SAP ECC. | No Impact to existing deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/New_CR_BOM_Automation_Draft.pptx?d=w0099a3d71a4d4efd990a93010a395029&csf=1&web=1&e=akqTRF |  | 2. New RICEFW / ECA / Build Object | MDM-150-200, MDM-150-150 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | DATE1616_IP, DATE1616_IF |  | DATE1616_IP, DATE1616_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-07 | o RAID 0936 was created in anticipation of the BOM activities growing beyond what the team can manage. CR0918 and CR1013 was created to bring in automations that will reduce the data load. • FTS IF and IP are aligned. o AR: Add in the following details to the deck: - @Linnell, Candice S @Lejarde, Lilibeth • Details on why the team is changing now • There is no budget implications. • It will miss ITC1 and will not affect anyone but the MDG team • The CR is a request for an extension of time, and there are no tradeoffs. • Not a priority for MDG, but the team will prioritize it and reassess in December |  |  | 2025-08-15 | • Objective: Automate the extension of BOMs to external sites/vendors using a simplified UI in S4. • Current Process: Manual in Speed and ECC; thousands of items handled manually. • Enhancement: BOM created in Speed, imported into S4, and extended via UI to specific sites/vendors. • UI Location: Confirmed to be in S4, not Speed. • Ownership: Tech team will handle this automation; master data team will manage the first CR. • Scope: Applies to both IP and IF; reuse across sites reduces complexity. • Approved: Confirmed by Mike Lange | [5 empty] | Other | CL/OSC | 2025-08-15 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1014 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Kimberly Moore | [11 empty] | Trigger Order details emails fro TM FO to customer based on preferred language | Business identified the need to send TM FO details during the course of time | Provide FO details to customer and trigger the actions from every order |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-%20CR1014-%20Returns%20scope%20Design,%20Fit%20build.pptx?d=w72aa5839642d46d1b6262865b69dc527&csf=1&web=1&e=n2ot4Y |  | 2. New RICEFW / ECA / Build Object | R-220-080 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | LOGF1632 | 3105 | LOGF1632 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-11 | o There is a requirement to send freight order details through email in customer-specific language, and this new form will send that information in an email attachment o This was supposed to be done in Salesforce, but there was a move to TM for this type of comms  LE interface does not have all of the data required to send, but that interface from LE to Salesforce will continue to send other information o AR: Update Options/Alternatives to say that the POR was Salesforce to LE – @Kumaresan, Ganesh @Shinde, Aditya o AR: Update deck so that all details are captured – @Kumaresan, Ganesh @Shinde, Aditya |  |  | 2025-09-19 | • Discussed the OTC-IP returns process, emphasizing the need to send order and collection details in the customer’s preferred language. • Two options were evaluated: sending data via Salesforce or leveraging the standard output management in Transportation Management. • The team favored using TM’s out-of-the-box capabilities to reduce complexity and development effort, aligning with business approval and scheduling this work for ITC2. • There is no significant impact on other ongoing work; the change will be implemented when resources are available and will enter testing late. It is not considered a high ITC risk item. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-09-19 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-01 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | Complete |  | Complete | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1015 | Approved | Presenter: Lilibeth, Candice | ERP | R4 (Release 4) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 06. PTP 07. FTS IF 09A. Master Data | lilibethx.lejarde@intel.com |  | Data - Julie Fawdington |  |  | FUT Defect from FTS IF, PTP | [6 empty] | Update the Lead time offset for SIMS BOM Component | Update the Lead time offset for SIMS BOM Component | Lead time offset either delays or advances the requirement date of the component, ensuring the component is available when its actually needed for Production at the CM Location. If the Lead time offset field is not maintained, then the components will be delivered early at the CM locations | No Impact to existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/New_CR_BOM_Component_Lead_Time_offset.pptx?d=wef5d54bf6f204df38cf4deb88d10bc0b&csf=1&web=1&e=pDTeLd |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | DATE1633 |  | DATE1633 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-25 | o This is for a BOM enhancement; isolated from the teams’ BOM’s  Enhancement will call upon 2 fields in material master for in-house production time to ensure that o It needs to be done at the component-level, not at the header-level o AR: Confirm that timelines can be met and send back to Anna for offline approval with Uzma - @Lejarde, Lilibeth @Arora, Nishant | [9 empty] | Other | Tower | 2025-09-25 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | In Progress |  | In Progress | No | Yes
|  | INT-CR1016 | Cancelled |  | ERP | R4 (Release 4) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 09A. Master Data | lilibethx.lejarde@intel.com |  | Data - Julie Fawdington |  |  | N/A | [5 empty] | WIINGS | ECM Design change - Handling of Alternate Items and CEID between ECM and S4 | ECM Design change - Handling of Alternate Items and CEID between ECM and S4 (R4 related) | The current design is to have the global alternate items in the Classification view of the material master and alternate items will be treated as characteristics. CEID is not to be brought in IAO. Alternate items will be represented in the BOM after reading the characteristics. However, during a deeper discussion, it has been a misalignment of the design and treating alternate items as characteristics will not work especially if there are changes. Now there are two options being discussed. | This may not be delivered in ITC1 and need impact analysis and timeline. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1016%20-%20Handling%20of%20Alternate%20Items%20and%20CEID%20between%20ECM%20and%20S4.pptx?d=w6ac181c26ddd4f4fab0b939883575963&csf=1&web=1&e=yNaWef |  | 1. Process Scope / Design Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Chris Birely to be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
R2 (Aug 2025) | R2 | INT-CR1017 | Approved |  | SCP | R2 (Release 2) |  | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics | jose.ramirez@intel.com |  | FTS IF - Haritha Komma |  | CR0853 | IF Anafi/Altera products demand is not available to pull into Compass | [5 empty] | Anafi | IF Anafi/Altera products demand is not available to pull into Compass | Create a Denodo layer on top of an existing HANA view inside DSA extract folder d.Extracts.DemandForecasting (where we have our other existing DSA views) which will refer the above view and push the data to Denodo view using the same existing connection set up. | Anafi/Alter product current state: Has been automated into COMPASS from SAP IBP as part of consensus demand. With this, team gets 75% of the products and 25% is manual. Starting with R2 the consensus goes away thus making 100% of the products manual. | None | No |  |  | https://secure-web.cisco.com/185bPQd5IgOOXMpxAD4xCeJNBdoJ-mAk7WLm1UIUBTWNrRRfJCrMFrXjuprXyaN_fOO6rzx56xw17m-Fy1hclh7psOtvxOE5GvsAvhxW3ftp_etFK42Gn4NysJPseCpTGKZnAdQy5xE9W84MSDzL2velkjUCtDds3FW9pz-q6IwsbN3OiO3p51rhHeTGBZcuOb_RPL0ufuWPmwtfj9qjOYGeCYd7Ev_fX_R8YJUv7jDlHnPWYgdSbx8U6OxXFtavGiOtXlwUXT62DqKtADf6_QnDFuF0ei0V1FWm5EK18xIfXfywvPbTbhCnbFdJ0YNrvhxOxihoJ2ko4fyOFha2jSYTo81xDmoYQzEB0-7tbbdH08p6ncHMCfga6oGrCOra2eZv0OSQeEGtI80xcyKDOq5k8F0ttJE3op1oY6BxcDnF_ZdjMcvibMJ7F62XRJ-z9gNFon24okU6PndQsG3x-uYLXRroeKQCKuo-3JQf6jfPqYHRAly8f8tChKFb-6jFiJ6-x0sROBSaEPgf85_Hs3w/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F01.%2520PMO%2F05.%2520Scope%2520and%2520Change%2520Control%2FChange%2520Control%2FChange%2520Request%2520Decks%2FFTS%2FR2%2FCR1017-%2520ECA_COMPASS.pptx%3Fd%3Dwcfed562b0e23408e8a85d8863ed79fe8%26csf%3D1%26web%3D1%26e%3DnHd7ki |  | 3. Configuration Change |  | Yes |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-07-31 | This CR was created as an update to CR0853, which is the design CR. Thus, CR1017 is Stage 2 and went directly to the CR Meeting |  |  | 2025-08-01 | • A defect was identified during R2UAT2 testing: Anafi product demand was not available in Compass, impacting both Compass and Altera products. • The issue stems from missing data in the existing HANA view, which requires a Denodo wrapper with 12 additional attributes to make the data consumable by Compass. • This change is self-contained, low risk, and does not affect external systems—but it is considered a showstopper for forecasting and readiness. • Compass has traditionally handled internal products only, but Anafi is an external customer. This workaround is a temporary solution until Anafi transitions to Blue Yonder CDP in January. • The team confirmed that this fix is a light lift, can be tested WW32, and will not delay other deliverables. • Concerns were raised about test coverage and the possibility of other similar data flow issues. The team agreed to review remaining test scenarios and validate actual data usage. • AR: Jose Ramirez update CR-1017 in place of CR-0853 on PPT documentation. | [5 empty] | Other | CL/OSC | 2025-08-01 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1018 | Cancelled |  | ERP | R4 (Release 4) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology | JR Hoover | [10 empty] | WIINGS | Cu Repair loop - 500 to 6** | Evaluate changing process for returning Copper repair loop items; Request to evaluate changing the design of the "Cu repair loop process - 500-6** series MMIDs“; New Enhancement and modification to existing (R4 related) | Evaluate if there is an option to automate the update and change of equipment records from 500 series to 6** series MMIDs on returns. This has historically been done by the WH/Buyer, but with their force reduction team is looking at ways to find automation | TBD | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B90DD926C-7CD5-4D64-B665-E896196452C5%7D&file=INT-CR-1018%20-%20Cu%20Repair%20loop%20-%20500%20to%206.pptx&wdLOR=c6C15B0EB-D2E3-496D-A62E-65948C914D0E&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Stacee to no longer be needed as it is a duplicate | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-02 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | No Objects |  | In Progress | No | Yes
R3 (Feb 2027) | N/A | INT-CR1019 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | shivkulkarni@deloitte.com |  | FTS IP - Loni Adams |  | CR-0612 | NA | NA | [5 empty] | Cancellation of WIP IP forms | Cancellation of WIP IP forms | As the OTC forms are being leveraged for the WIP there is no need for these separate objects. Hence the WIP objects needs to be cancelled. | NA | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1019/RE%20Request%20For%20approval%20on%20INT-CR1019%20%20INT-CR0612.msg?csf=1&web=1&e=C1ZxfC | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGF1523_IP, LOGF1524_IP, LOGF1525_IP |  |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | [10 empty] | Other | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR1020 | Approved |  | Other (Boundary Apps, Data Transformation) | R2 (Release 2) | High | 04. OTC IF | 10.4 Analytics - OTC IF |  | 04. OTC IF 10. Analytics | nitin.p.jain@intel.com | BApps — Kelly Gerber | E2E - Aishwarya Bhat |  | N/A | 1682 | N/A | [5 empty] | Time Zone issue - ECA Reporting | 15 FSSD reports are impacted. Once ECA change is done, FSSD will need to make change across as some biz reports needed local time and some pacific. Risk of not making this change: customers will be sent data with incorrect timestamp. | This directly impacts Intel’s Foundry customers. Impact is high and applies on 15 reports across 5 customers. No change is not an option as we will be sending incorrect data to customers. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Change%20ID_Timezone_issue_CR%20Deck.pptx?d=wa18317710aa9460f855f5a4eda3f4243&csf=1&web=1&e=nIHm8I |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | 48 | 0 | [12 empty] | 48 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-06 | Approved offline in email entitled "PRIORITIZE - R2 FSSD Delivery not Time zone issue". As the work has already in-progress (probably in testing), this CR is approved. @Tam, Anna please ensure that all teh documentation is up-to-date. | [9 empty] | Build | Tower | 2025-08-06 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1021 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF 10. Analytics | Srikrishna Iyer |  |  |  | Cancellation of objects due to the duplication. | [7 empty] | Cancellation of ECA objects- 1. FTSFV040 2. FTFSV033 3. FTFSV039 | Duplicates to existing ECA objects. | Cancellation of objects due to the duplication. |  | Yes |  |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1021?csf=1&web=1&e=96cqdC |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-05 | 0 | < 15 Days | harshitapandey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2.1MR (Feb 2026) | R2.1 ITC | INT-CR1022 | Approved |  | ERP | R2 Jan 2026 R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 10.4 Analytics - OTC IF |  | 04. OTC IF 10. Analytics | Praveen Kumar Muppala | [11 empty] | Pricing Report for ZMAN Sales Orders | New requirement to add pricing report for ZMAN sales orders | After the R2 go-live, there is a requirement to add a new ECA report to help the business to identify ZMAN sales orders​ Manual Price override Report: This report will display all sales orders where the ZMAN condition type (manual pricing) is active. It will also include change logs to identify who made pricing changes and when those changes occurred and manual price override text.​ This report is needed to support SOX compliance audit requirements. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1022%20-Pricing%20Report%20for%20ZMAN%20Sales%20Orders%20.pptx?d=wc96b695dab6a46b3a5ecf82b76035848&csf=1&web=1&e=9Euvp7 |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-23 | Should be presented in the R2.X Ingestion | [9 empty] | Other | Tower | 2025-09-23 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-05 | 0 | < 15 Days | ckumarsrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1023 | Cancelled |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 10. Analytics | stacey.carter@intel.com | Data & Analytics - Rebecca Verette | FTS IP - Loni Adams |  | N/A | 01768 | N/A | [5 empty] | R2 S&OP Critical Key Figure - BY FG Supply | Request for additional 1 critical key figure BY FG Supply & associated dimensions needed for this key figure. This key figure will create a stitched measure to give us a full year view of finished good out. ​ | Without this critical key figure will not be able to run the full scope S&OP Reviews successfully including: finished goods, full year view of finished goods outputs from BY (BY does not have the finished goods actuals, it only includes finished goods out forecast), cycle over cycle comparisons, comparison with POR, etc. We have not found an alternative work around. Impact – we will not have all the data required to make effective decisions. ​ | N/A | No |  |  | https://intel-my.sharepoint.com/:p:/p/jessica_grosse/EeImcoL46T9PotD4orFAR70B4CykoHgDkyTMU_D8vjKHRw?e=IKLfcX |  | 10. Non-Build Analytics-related Change |  | N/A |  | 1 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it was not included in Upali's list of open CR's | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1024 | Approved | Presenter: Ravi | ERP | R2 Q4 '25 Anafi enablement | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Naman Parti | [10 empty] | Anafi | Anafi scope of work for order management | Scope of work for the Anafi design factored for Release 2.5. | Anafi an Intel customers can place an order via the B2B channel. Anafi generates a file for Build Instruction which will be converted to XML file. This XML file can then be processed and integrated within the S4 system, enabling automated handling and execution of the order details leading to the creation of the SO. Hence design discussion, interface build and FIORI import is required to enable the automated sales order creation and modification at the IF instance. The same XML file would be used to populate the ZUDF tables used by the FTS team for wafter start Sales Org/Plant for Israel to be setup in order to cater to Logistics requirements. Virtual shipments from MY would be in scope to support multiple invoice points |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT%20Build%20CR1024_ANAFI%20scope%20of%20work%20for%20OM.pptx?d=w02c1598e85a04ffcb5490f36e361679a&csf=1&web=1&e=ClUXFj |  | 1. Process Scope / Design Change |  |  | Very High |  | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3130 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-21 | o This is the first CR for Anafi changes, and it is to bring the process for R2 scope  B2B message needs to be fed from Anafi and converted to sales order automatically  Need to send to ECA to allow for manufacturing to do the wafer start  This process is too big to do manually o Changes needs to be done by December 2025 o AR: Add in statement that there are additional CR’s coming in for Kulin Plant and Master Data - @Vishwanathan, Ravi o AR: Add in statement about what is already in R3 scope, what is new, and what we are pulling in - @Vishwanathan, Ravi o AR: Team to develop and bring in slide to core leadership detailing who is funding and staffing this project to ensure there are no impacts on other parts of the program. @Vishwanathan, Ravi |  |  | 2025-08-22 | • Pilot Approach & Timeline o 400 MM IDs for pilot approach with plans to expand in 2026. The pilot is a risk mitigation strategy, with a go/no-go decision in Q1'26. If successful, all Anafi products will convert to the new solution, but a further CR will be needed for R3 deployment in 2027. Estimated 3,000 sales orders/month. o Requires onboarding into B2B landscape and support for ERO Sales orders. o Virtual shipment process will bypass EWM and TM systems. • Build Instructions & Fiori App o Custom table from R3 to be extended for Anafi’s needs. o Fiori import app under evaluation for build instruction integration. • Resource Planning o ~10 Deloitte resources needed across OM and Logistics. o Intel business and IT teams to support with overlapping responsibilities between R3 and Anafi requirements. o Concerns raised about resource stretch and burnout. o There is not currently enough information for confidence in the resource forecast. • Timeline & Risk o Aggressive schedule aiming for December 28, 2025, go-live. o Design phase only 3 weeks; risk of impacting R3 deliverables. • Governance & Funding o M&A funding is assumed but confirmation is required. o Data conversion resources are covered however other resources need to be considered . o The funding source for additional Deloitte resources being onboarded is unclear. o Proposal to escalate to executive committee for support and funding. o Suggestion to consider Anafi as a small program versus several Change Requests. Decision: Approved to move forward to conduct a risk and resource assessment with impacts and return ww35 with the details to Core Leadership. • AR - Uzma Ahmed to provide Paul Whitlock with summary of additional resource costs for Anafi. • AR - Anand Jha and Shripad Deshpande to assess risk and resource impacts and gaps due WW35.2. • AR - Paul Whitlock and Jorge Sanchez to determine the logistics resource constraints and potential options for filling them. • AR - Kevin Brown, Paul Whitlock, and Mike Lange to meet regarding options for funding Deloitte resources from existing budget. | [5 empty] | Design | CL/OSC | 2025-08-22 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-06 | 0 | < 15 Days | tganguli@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1025 | Rejected | CLOSED, THIS IS BEEN PUSHED TO R5. If there is no memory bailment, as outlined above, the NEX BU margin could degrade up to 10%. This violates the margin targets set by Intel’s executive management. This is a massive opportunity with lifetime revenue of ~$1B, and the NEX BU cannot afford to take a margin degradation for this design win. | ERP | R5 (Release 5) | Very High | 08. FTS IP | 8.11 FTS IP - New Product Supply Planning Enablement |  | 03. FPR 05. OTC IP 06. PTP 08. FTS IP 09A. Master Data | sameer.shurpalekar@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | N/A | N/A | N/A | [5 empty] | NEX BU Mount Morgan Memory Bailment Support | Pushed to R5. The NEX business unit has won a couple of designs with Google to sell them the Mount Morgan IPU device. Approximate lifetime revenue is $1B. •During mid-2024, Intel negotiated a bailment model for MMG 400 SoC memory. •The bailment model meant a 3rd party agent would own memory on MMG 400 when assembled for Google, helping avoid a margin deterioration of ~10%. •All plans and forecasts have assumed the bailment model, with memory being excluded from product ASP and cost for MMG 400 and MMG 800. To meet Intel management’s product margin targets for the IPU, the business unit requests memory bailment. Google will not allow us to mark up the memory that is integrated into the IPU device. In this case, Google has already agreed to memory bailment. Depending on timeframes, NEX BU margins could degrade up to 10% if there is no memory bailment. | CLOSED, THIS IS BEEN PUSHED TO R5. If there is no memory bailment, as outlined above, the NEX BU margin could degrade up to 10%. This violates the margin targets set by Intel’s executive management. This is a massive opportunity with lifetime revenue of ~$1B, and the NEX BU cannot afford to take a margin degradation for this design win. | ~12-week push out (conservative) to original schedule | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Change%20ID_Tower%20-%20NEX%20MMG%20Memory%20Bailment%20(20250805).pptx?d=wc53d4c4b0b9947738a6e4ffef5f7c3c4&csf=1&web=1&e=b7gtv4 |  | 1. Process Scope / Design Change |  | No | Very High | 300 | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | Yes |  | 2025-08-07 | o Between Mount Morgan 400/800, support is required for the IPU Memory Bailment Program. The immediate focus for the process support is focused on MMG 400. • Between the 2 SKU’s, Intel is expected to ship 5 Million units all built at Intel Foundry. o The team will need the business process to enable sub-bailment by WW6’26 to ensure that there is support. • Mount Morgan is part of the divestiture and will be an external customer to IF after R3 go-live. o AR: Update change request with the following details: • Understand scope and whether there are any impacts to IP design post-R3 - @Shurpalekar, Sameer @Niepoky, Brian J • Work with M&A team to understand whether functionality needs to land in ECC first, whether there are budget implications and funding sources, and what the timing would be - @Niepoky, Brian J • Work with IP team (Sabrina Patino) and IF team to clarify who is required to design the interim solution - @Shurpalekar, Sameer @Niepoky, Brian J • Understand when the New Co is being set up and whether it will be in IP or supported by IF | [8 empty] | Confirmed by Sekhar and Venkata to be a duplicate of CR1550, which has now been pushed to R5 | Design | CL/OSC |  | Missing Review Date for Approval Level | 08, 2025 | 08, 2025 | 2025-08-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1026 | Approved | Combine with all other ECD descopings | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | [12 empty] | Cancellation of object - LOGI1293 ECD_Interface between 3PL and S/4 for 3PL hold inventory confirmation for webservice plants | The requirement of this the object LOGI1293 ECD_Interface between 3PL and S/4 for 3PL hold inventory confirmation for webservice plants are being captured under the LOGI1291. Therefore LOGI1293 is no longer needed | LOGI1293 requirements getting captured under LOGI1291 therefore LOGI1293 is no longer needed. This change is happening because of the ECD re-design |  | Yes |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1026?csf=1&web=1&e=Vg3i6D |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-06 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1 | INT-CR1027 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shelly Lafree | [11 empty] | Addition of Demand Priority (VBAP-ASSIGNMENT_PRIORITY) field as both an input filter and output column in the standard Fiori Manage Sales Orders app. | New reuirement to add the Demand Priority (VBAP-ASSIGNMENT_PRIORITY) field as both an input filter and output column in the standard Fiori Manage Sales Orders app. | By adding Demand priority field in input and output in Manage Sales order standard Fiori app, it helps users easily see and filter sales order line items that need urgent supply by adding the Demand Priority field to the app. It makes it simpler to find and prioritize these orders in real time. This is important for preparing for supply chain meetings and making sure urgent orders are not missed. Overall, it improves how quickly and accurately supply priorities are managed. | CR was not approved | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1027%20-%20New%20field%20addition%20in%20Manage%20Sales%20order%20Fiori%20app.pptx?d=wf960bed0dbb8412a8efba6270aaee6c6&csf=1&web=1&e=u0QNMb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-06 | 245 | > 30 Days | ckumarsrinivas@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1028 | New | Anna to confirm with Lilibeth that it is not a duplicate of CR1561 | ERP | R4 (Release 4) | Very High | 09A. Master Data | 9A.1 Master Data - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | 0024 | N/A | 1733 | N/A | [5 empty] | Tariff Requirements Impact on Master Data | Tariff Requirements Impact on Master Data | This is a new requirement | TBD | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1028%20-%20Tariff%20Requirements%20Impact%20on%20Master%20Data.pptx?d=w72fa884813154471ba7f68f6d828f911&csf=1&web=1&e=ynov75 |  | 1. Process Scope / Design Change |  | No |  | 1000 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-07 | 244 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1029 | Approved | Presenter: Nikhil | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | rudrsengupta@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Transfer Die To Reel Process | Transfer Die to Reel in DIEPREP and STACK (WLA) orders. | : Transfer Die to Reel in DIEPREP and STACK (WLA) orders are mapped to Complete Event. This will lead to complete the goods receipt of Production Orders in S/4 and put the stock in TRDI location. But physically the units are still on the Reel and not in TRDI and waiting for the slots of the Reel to get filled up before transfer to the TRDI. | We will make all efforts to complete this year 2025 | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/EXT%20RE%20New%20Change%20Request%20Transfer%20Die%20to%20Reel%20(INT-CR1029).msg?csf=1&web=1&e=18nFwh | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0xxx_FTS-IF_Transfer_Die_To_Reel_.pptx?d=wa35b7d7c84e044df982a3a256ff7dd1d&csf=1&web=1&e=yGglhr |  | 2. New RICEFW / ECA / Build Object |  | N/A | Medium | 120 | 2 | [8 empty] | 120 |  |  |  |  | 0 | 120 | N/A | Yes |  | 1 | FTSI1610 |  | FTSI1610 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-07 | o This is a medium complexity interface and will meet the build milestone. | [9 empty] | Other | Tower | 2025-08-07 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1030 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 10.8 Analytics - PTP |  | 06. PTP 07. FTS IF 08. FTS IP 10. Analytics | susan.strathman@intel.com | Data & Analytics - Rebecca Verette | PTP - Richard Taylor | [8 empty] | WIINGS | ~23 reports related to WIINGS to be added to the Deloitte ECA Object Tracker | Background: these reports went through the intake process back in 2024 and were determined to be reports that Intel Business would build (3rd party reports) and were placed on the Intel ECA Object Tracker. They are 6 placeholders on the Intel Object Tracker under "AR: Suraj: PTP: FSD XX Placeholder". These are as-is reports that need to go through workshops to determine the to-be state. Needed by go-live but not mandatory by ITC1. | Support business requirements after WIINGS is being sunset | TBD | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B944bc626-87b3-422d-9cbd-128c13120652%7D&action=edit&wdPreviousSession=ae7bd6bb-49a7-d489-a4c1-c1894f063756 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 7 | PTPFR122, PTPFR123, PTPFR120, PTPV079, ECAPTPR7102, ECAPTPR7103, ECAPTPR7101 |  |  | 0 | PTPFR122, PTPFR123, PTPFR120, PTPV079 | 4 | ECAPTPR7102, ECAPTPR7103, ECAPTPR7101 | 3 | 7 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-09-11 | o These are the ECA views and reports required to support WIINGS  This CR is to approve the impact analysis for the 23 reports o AR: Include any business impacts if the views and reports from this CR is not ready for testing - @Strathman, Susan |  |  | 2025-09-23 | o Summary: The discussion included the prioritization and delivery of 22 reports critical for the WINGS R3 go-live, weighing options between deferring SIMS reports or funding additional Deloitte resources at $50K. The team emphasized securing the funding to avoid delays, while working to reduce report scope and addressing concerns about numerous design opens and change requests. o Report Requirements: Susan presented 22 reports, focusing on 12 for immediate prioritization and discussing options for their inclusion in scope, including a potential trade-off with 7 SIMS reports that are not required until R4. o Two options were presented • Option 1: deferring SIMS reports to free up resources for WINGS reports • Option 2: adding two Deloitte resources at a cost of $50K to deliver by ITC2 o Key Risks discussed • Funding Uncertainty: There is no confirmed funding for the additional $50K needed to deliver the WINGS reports, and even the resource swap option may not be cost-neutral due to program budget constraints and RICEFW object consumption. • Resource Bottlenecks: Development teams are at or above capacity, raising concerns about the ability to deliver all required reports and CRs within the planned timeline. • Deferral Impact: Deferring SIMS reports to free up resources for WINGS could create future delivery and budget risks, especially as post-R3 budgets decline, and deferred work may become unaffordable or create downstream issues. The group agreed that finding the $50K to fund the work directly is preferable to deferring SIMS, to avoid future budget and delivery risks. • Late Requirements: The WIINGS reports are coming in late, increasing the risk of missing ITC2 deadlines and compressing the time available for functional spec completion, build, and testing. o AR: Carrie Shim to secure $50K funding for Deloitte resources enabling WIINGS CR1030 to be updated from conditional approval to approved. o AR: Susan Strathman continue reducing list of additional WIINGS reports to minimize scope/cost and provide update WW40. | [5 empty] | Other | CL/OSC | 2025-09-23 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-07 | 0 | < 15 Days | shenguyen@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1031 | Cancelled | Presenter: Lorinda | SCP | R2 Hypercare | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | lorinda.m.braun@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | Deployment Readiness Finding | 1851 | N/A | [5 empty] | Production Cut-over Schedule Conversion Alignment | For R2 Production Cut-over, FSMP/DMOP (supported this activity during UAT) is not able to manually support converting the existing Sort Out POR schedule into schedules for Fab/Bump/Sort due to the complexity. The challenge to offset the schedules for TPT/Yield/Capacity, doing the location splits, and also doing the netting to account for how much WIP is post fab or post-bump. Different than UAT mock cutover, the cut over activity will need to take in consideration the actual wip position to create the Fab/Bump/Sort cut over. Only 1-2 days in WW40 to covert the schedules. | Risk/Impact: schedule conversion is very complicated given the above, resulting in high risk to data integrity. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/Change%20Requests/Pending/IAO%20R2%20IF%20Production%20Cut-over%20Schedule%20Conversion%20Alignment.pptx?d=wf66ae2358ed9439eb6596a196531944e&csf=1&web=1&e=BwBlZj |  | 1. Process Scope / Design Change |  | N/A |  | 1 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1032 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09B. Data Migration | Venkat Venkatesh | [11 empty] | Incorporating IFL Time Keeping additional fields in DATC0583 | 1. Default Payroll Areas - 02 & 04 to be captured for Time Keeping Employees having IFL TK indicator as Y and IFL TK Approver Flag as Y in IP. 2. Dynamic Work Schedule check box 3. If we receive Null for Company Code or cost center data from WCDS. Discard the WWID completely and do not send it to MDG 4. PA0105 subtypes should not be updated if the Subtypes are having null value coming from WCDS. 5. Employment percent 6. Weekly working hours 7. Daily working hours 8. Weekly workdays 9. Part time & Dynamic work schedule check boxes to be checked if capacity Utilization is less than 100 10. ZBIZ - Pass CompanyCd into this field. 11. Position ID mapping 12. Work Hours / Period 13. Time Keeping Approver Flag 14. Payscale Type 15. Payscale Area 16. Mapping changes for P0003 segment 17. Org Unit Mapping | These fields are required to show accurate details in Planned Working Time & Basic Pay for the calculation of CATS hours. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1032_Incorporating%20IFL%20Time%20Keeping%20additional%20fields%20in%20DATC0583.pptx?d=w6974b0618feb48ea9b06f0cd13e69135&csf=1&web=1&e=jlEJFj |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-07 | 244 | > 30 Days | venkvenkatesh@deloitte.com |  | No |  | No Objects |  | N/A | No
| R3 ITC1 | INT-CR1033 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | saisen@deloitte.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | NA | ALM- 993 | NA | [5 empty] | IF-IP Plant logic change in Functional Specification | IF-IP Plant logic change in Functional Specification. | Here there is a PARAM table where, we linked between the IP & IF plant. So, whatever the IC sales order/ billing has been created the same plant we maintained in this table: - ZTOTC_PARAMS. This logic has mentioned in the FS: - OTCE1106_Enhancement to support Inbound interface and manual upload to create the sales order via Build Instructions. | NA | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | N/A |  | 4 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Hari Gore to no longer be needed. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1034 | Cancelled | [34 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-08 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1035 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP | michael.elumeze@intel.com | [10 empty] | WIINGS | Activate E2E TM scope for returns PO ( PTP -IF GFM) | Scenario for R3 IF Returns to Vendor scope (includes Repairs) was missed during the design process, required to support GFM end to end (WINGS replacement). Change is to complete design solutioning new / delta Processes which were not design signed off as of Jan 24, 2025. | Chronology of events:​ 1.Oct 2024 – A common CR 0087 was presented to OSC for additional scenarios across GLO/GFM, which was rejected by OSC. ​ 2.Oct / Nov 2024 – A walkthrough of signed off GLO scenarios was done to GFM team , and GFM team was reminded to ensure must have requirements are brought with biz justification + present the CR to OSC. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5DA3518C-FDD0-4663-BE7A-AC77D8F750FE%7D&file=INT-CR1035-%20PTP%20IF%20TM%20GFM%20returns%20design%20scope.pptx&action=edit&mobileredirect=true | Missed Requirement | 1. Process Scope / Design Change | 14 L3s under LI-030. | Maybe |  |  | 0 | 318 | 43000 | 84 | [5 empty] | 114 |  |  |  |  | 0 | 114 | Configuration | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-11 | o AR: Include the background on how the gap came about and was identified (no formal requirement in E2E flows, CR0067 was rejected, design was signed off) – @Kumaresan, Ganesh o AR: Work with Paul Whitlock and Cari on funding - @Strathman, Susan |  |  | 2025-09-26 | • Susan Strathman explained a critical missed requirement regarding return to vendor processes for GFM spares supply chain, which was not included in the original scope of a previously rejected CR. This omission affects about 20,000 returns regularly processed to suppliers, including IMR. Following identification of this gap during the wafer reclaim call, extensive collaboration between Intel and Deloitte led to a refined scope and sizing for the CR, aiming to implement a MVP that reuses existing configurations and out-of-the-box solutions where possible. • The work requires ITC2 testing and additional resources, with no trade-offs to reduce scope due to the necessity of the return process for supply chain functionality. • Susan emphasized the importance of this CR despite it arriving late and acknowledged the associated costs are pay-as-you-go as initial RICEFW allotments have been exhausted. • The team plans to avoid design exploration to expedite delivery, focusing on configuration and validation activities within the projected budget of $43K . Roman Vorel and others discussed the design effort, confirming that about 84 hours are allocated for design validation and documentation within the $43K budget without expecting new developments. The approach discourages exploration of additional fit features to keep efforts focused on reusing existing capabilities. Data implications were briefly reviewed, with the consensus that no new data requirements are anticipated, but configuration of customer data to suppliers will be necessary post-approval. • The team confirmed that this CR will miss ITC1 and be included in ITC2, agreement from business leadership that no later inclusion, such as ITC3 would be accepted. Funding responsibility was clarified to be with Foundry or Cari Shim, and the solution is expected to be out-of-the-box. • Customer Data Follow-Up • Susan confirmed that after CR approval, she will reach out to the customer data team to ensure configuration is completed and to check for any unexpected issues. She mentioned having a template ready and that people are already asking for it, but the source of the data needs to be clarified. Rebecca Verette clarified that the configuration involves Intel as the customer, and Susan agreed, noting the need to ensure proper setup for supplier interactions. • Cari added that this approach to returns is consistent with previous decisions, and Susan agreed, emphasizing that the data team is prepared and just waiting for the go-ahead. • AR: Susan Strathman to connect with the customer data team and verify there are no new surprises or problems related to data requirements. • Decision: CR is approved | [5 empty] | Design | CL/OSC | 2025-09-26 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-08 | 0 | < 15 Days | adshinde@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1036 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | [19 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-08 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1037 | Approved | Presenter: Naren, David Park | SCP | R3 (Release 3) | High | 07. FTS IF | 7.13 FTS IF - IF BE Supply Planning |  | 07. FTS IF | john.p.heiney@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Build HB Loader capability in IF-PDH and integrate with MARS | Build the Heartbeat (HB) Loader Capability in IF PDH and Integrate with MARS For Straddle integrate with SPAN | Heartbeat or “HB” is the tool used when processing the “Outs” schedule (for example, test outs, etc.) for products, which drive Assembly “Ins”. The primary purpose of the tools is to translate the schedules from PDRS (Product Device Rev Step, also known as L3 or BOM), and HRI (Human Readable Identifier) to the appropriate Main Cell and Sub Cell | Delivery date – Feb’ 2026 for ITC 2 The R3 build schedule is completely packed and work can't start until WW02'2026 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B81236286-FDF5-44A7-BF1B-C8B0AF92D659%7D&file=Change%20ID_FTS%20-IF_HB%20loader.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0168 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-14 | o These changes are for manufacturing automation and will be used for straddle and for end state. o Only impact is to PDH from an effort perspective |  |  | 2025-08-26 | • HB Loader, a tool used primarily in the backend assembly, test, and finish areas of Intel Foundry. Its main function is to translate product device references into factory-executable instructions for assembly and testing. The current system resides in SPAN, and there is a plan to migrate it into the Intel Foundry Planning Data Hub and integrate it with MARS to support factory teams exclusively. • Concerns were raised about the architectural implications of this move. The Planning Data Hub, originally designed as a clean, foundational planning data store, risks becoming overloaded with factory scheduling and preprocessing functions, potentially replicating the messy architecture of the legacy SPAN system. The split of scheduling functionality across different teams and systems (TD, SMDS, and Planning Data Hub) was highlighted as a challenge. It was noted that the initial idea to place this functionality inside production scheduling was rejected, leading to the current plan for IFPDH integration. The group agreed on the need to bring this topic to the IF Architecture Committee for review to ensure a long-term, clean solution rather than a quick fix. • HB Loader translates product device references to factory execution instructions. • Migration from SPAN to IF PDH is planned due to rejection of production scheduling ownership. Architectural concerns about overloading the Planning Data Hub were expressed. • Agreement to pursue architecture committee review before proceeding further. • AR - Sunil Parida - Sync with Paul Whitlock for assistance with scheduling this CR at the WW35.3 IF Architecture Committee for review. • AR - Paul Whitlock - Sync with Mike Lange regarding next steps following the WW35.3 IF Architecture Committee review. • AR - Sunil Parida - Conduct high-level sizing for MPDS to determine delivery feasibility if the integration is approved. • AR - Rebecca Verette - Revisit the supply chain process for non-standard enhancements and follow up with Roman regarding the special review and approval mechanism. | 2025-09-12 | • Originally rejected by both the production scheduling and factory automation teams. This was reintroduced due to lack of viable alternatives. • The IF Architecture Committee, including Rebecca Verette and Roman Vorel ww37.3, agreed to place it in PDH despite capacity constraints. • HB loader is critical for execution, not planning, and will be implemented in PDH. HB loader t is essential for execution and sits between planning and execution. • This feature will miss ITC1 and is scheduled for ITC2. Team to provide exception handling for ITC 1 due to the absence of the HB loader integration. • No additional budget is needed if the timeline specified in the CR is achieved. • Rick Antonellis expressed strong reservations but acknowledged the necessity and lack of alternatives. • Decision: Approved |  |  |  | Design | CL/OSC | 2025-09-12 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1039 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 05. OTC IP | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | INC14824783 | Delivered |  |  |  | MBB Label Format Change | Current FS design direction provided to Deloitte was for YYMM, when the actual Factory Requirement was YYWW | Align label requirements with Factory labeling requirements | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1039_IF_R2_MBB%20Label%20Change.pptx?d=w6cacdbbb0b1b4feb97a719c67e065a93&csf=1&web=1&e=sC0IYA |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Low |  | 1 | [8 empty] | 12 |  |  |  |  | 0 | 12 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | Approved as changes are already in production. Ad hoc meeting with Uzma. Recording uploaded. | [9 empty] | Build | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-11 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1040 | Approved |  | Other (Boundary Apps, Data Transformation) | R2 Hypercare | Medium | 10. Analytics | 10.4 Analytics - OTC IF |  | 04. OTC IF 10. Analytics | nitin.p.jain@intel.com | Data & Analytics - Rebecca Verette |  |  | NA | IAODTM-6776 |  | Standalone | Delivered |  |  |  | if_supply_chain.warehouse_management_base.delivery_note_handling_unit.external_handling_unit_weight_uom_cd is showing incorrect Unit of Measure (UOM). | Tare or packing material UOM (VEKP.GEWEI) is currently mapped as the UOM Code for shipment gross weight, which is incorrect. Correct gross weight for goods shipped is VEKP.GEWEI_MAX. FSSD Packing slip will have incorrect data for new S4 shipments and custom clearance might be a problem. Both historical and S4 mapping needs to be corrected. | Tare or packing material UOM (VEKP.GEWEI) is currently mapped as the UOM Code for shipment gross weight, which is incorrect. Correct gross weight for goods shipped is VEKP.GEWEI_MAX. FSSD Packing slip will have incorrect data for new S4 shipments and custom clearance might be a problem. Both historical and S4 mapping needs to be corrected. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/CR-INT-Build-CR1040%20-%20Incorrect%20UOM%20in%20Delivery%20Note%20Handling%20Unit.pptx?d=wf4d576d13d3d43c2a1ec55b3f4c9205e&csf=1&web=1&e=tSZrQN |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGV042_FTSIF | 1 |  | 0 | LOGV042_FTSIF | 1 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-05 | Approved in Hypercare CR meeting with OSC | [9 empty] | Build | Tower | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-11 | 0 | < 15 Days | sumitsharma9@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1041 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 06. PTP | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | S/4 BOM Manual Changes Impact on Automated integration of BOM from SPEED to S/4 | S/4 BOM Manual Changes Impact on Automated integration of BOM from SPEED to S/4 | PTP requested to have access to make changes in BOM directly in S/4. This is needed as SPEED has no capability to make changes for future date. | N/A | No | Non-Core |  | N/A |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 239 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) |  | INT-CR1042 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP 10. Analytics | Surendra Julury | [11 empty] | Move the Price variance report to ECA | The price variance report for physical inventory is not needed in real-time and can be moved to ECA as this is a historical analysis of data. | The price variance report for physical inventory is not needed in real-time and can be moved to ECA as this is a historical analysis of data. |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 1 | OTCPV047 |  |  | 0 | OTCPV047 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1043 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Cancel the Price variance Report LOGE1213 in SAP | Price Variance Report is moving to SAP and has to be canceled in SAP. Object ID - LOGE1213 | Price Variance Report is moving to SAP and has to be canceled in SAP. Object ID - LOGE1213 |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1043/FW%20Approval%20needed-INT-CR1043.msg?csf=1&web=1&e=hiWsVM |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1213 | OTCPV047 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-12 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1046 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Rahul Shrinivas Kelkar | [11 empty] | Addition of new field in Shipping instruction in object LOGE1268 | New field ATTN To: (Attention to) to be added in shipping instruction output screen and same to be populated in the Shipping instructions table. | New business requirement for addition of New field ATTN To: (Attention to) to be added in shipping instruction output screen and same to be populated in the Shipping instructions table required to mention the contact name. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Surendra to be cancelled as it is captured in Build CR0688 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1045 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Cancel Objects: PTPI1429_IP and PTPI1429_IF Outbound Interface for sending Invoice Release Statuses to SPT/GTT (Global Trade and Tax)System (Descoping) PTPE0317_IP and PTPE0317_IF | Descoping of below mentioned RICEFW object: 1. PTPI1429_IP and PTPI1429_IF [Outbound Interface for sending Invoice Release Statuses to SPT/GTT (Global Trade and Tax)System] 2. PTPE0317_IP and PTPE0317_IF [Custom Program to Release the block indicator from the invoice - SAP S/4 HANA IP and IF] | There are two RICEFWs PTPI1428_IP & IF and PTPI1429_IP & IF and these two are merged into one. The requirement is to receive a response from the SPT tool, process it in SAP S/4, and then send the response back to SPT in a synchronous manner. This can all be managed within the same API, so there is no need for a separate RICEFW for sending an outbound message to SPT. So we want to descope outbound interface object i.e. PTPI1429_IP & IF. 2. We covered requirement of PTPE0317_IP and IF in PTPI0710_IP and IF and we don't need PTPE0317_IP and IF. | N.A. | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/EXT%20RE%20Request%20for%20GPO%20alignment%20related%20to%20Descoping%20PTPE0317_IP%20%20IF%20and%20PTPI1429_IP%20%20IF%20CR%20ID%20INT-CR1045..msg?csf=1&web=1&e=8mtjjV |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE0317_IP, PTPE0317_IF, PTPI1429_IP, PTPI1429_IF | PTPI1428_IP, PTPI1428_IF, PTPI0710_IF, PTPI0710_IP |  | 4 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-29 | [10 empty] | Other | Tower | 2025-10-29 | 10, 2025 | 10, 2025 | 08, 2025 | 2025-08-12 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1047 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | [19 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1049 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Naved Naved | [11 empty] | Creation of New Storage location and new disposition code requirement for SCE (Scrap External) and addition of new field in Dynamic Ship to Site matrix | New Disposition to be created for SCE (Scrap External) and information in Disposition FS's including Static and dynamic disposition FS's, Manual Disposition, Ship Action Queue screen FS and Ship Item Screen FS. New field also to be added in Dynamic disposition Ship to site matrix table. | Given that we have two distinct Scrap Dispositions, 'Scrap External' will be represented as ‘SCE’ and will require configuration of a new storage location. The 'SC' code will continue to be used for in-house scrap disposition, as previously planned. This new disposition type (SCE) must be incorporated into the Static, Dynamic, and Manual Disposition FS documents, as well as any other relevant areas. Additionally, a new column—'Ship to Vendor'—should be added to the Dynamic Ship-to-Site matrix. This field can be utilized by CF/CRO/RP and the newly introduced SCE disposition. Impacted FS: Static disposition FS, Dynamic disposition FS, Manual disposition FS, Ship Action Queue Screen FS, Ship Item Screen FS. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Sarah Miller that the tech effort is less than 40 hours. Therefore, the CR will be moved to the Build CR Log as CR0722. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1048 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | llejarde@deloitte.com |  | Data - Julie Fawdington | [9 empty] | Update BOM Synchronous response Logic for SPEED, ECM, and Plant-Specific Material Validation in S/4 | Update the BOM synchronous response in S/4 to ensure that responses to SPEED and ECM changes are dynamically updated. Additionally, implement component material validation in alignment with the specific requirements of each plant. | Previously, SPEED and ECM teams shared a common response structure for BOM synchronous response. Now, distinct response structures are needed to meet their specific requirements | N/A | No |  |  | N/A |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 239 | > 30 Days | nagirreddy@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1050 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1051 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nanaved@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1052 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.8 PTP - QM |  | 06. PTP | Anant Joshi |  | PTP - Richard Taylor | [9 empty] | Enhancement to existing MQCS Interface table to accommodate Bailment materials processing | To Enhance the existing MQCS disposition custom table in PTPI1032 interface in order to accommodate the UNBW Material type mapping in IF. This change is necessary to support the Bailment process. | To Enhance the existing MQCS disposition custom table in PTPI1032 interface in order to accommodate the UNBW Material type mapping in IF. This change is necessary to support the Bailment process. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Murthy to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-12 | 0 | < 15 Days | nnagapushpa@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1053 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 05. OTC IP | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | INC14845309 | Delivered |  |  |  | Shipping Label Date Code | Date Code logic and format needs to align to Factory requirements of YYWW. | Custom Shipping Label for Customer requires that it contains a properly formatted Intel Factory Date Code. This issue is tied to INT-CR1039, but a separate CR is being created to track the releases for different objects. | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1053_IF_R2_Ship%20Label%20Date%20Code.pptx?d=w8f3adbc3e38143ef89178873c8acb31b&csf=1&web=1&e=2i8D7e |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  |  | 0 | [8 empty] | 6 |  |  |  |  | 0 | 6 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | Approved in ad hoc meeting with Uzma. Changes are already in Production | [9 empty] | Build | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-12 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR1054 | Approved | Presenter: Prabesh A, Bharath | SCP | R2 (Release 2) | Very High | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 08. FTS IP 10. Analytics 15. Cutover 16. Testing 17. B-App | soman.patil@intel.com | Data & Analytics - Rebecca Verette | FTS IP - Loni Adams |  | N/A | RAID# 01860 | N/A | [5 empty] | DLCP Reporting for ICOST Reserves Process | Report is official publication provided on a monthly basis for determining DLCP (Die-Level Cherry Picking) Reserve type; If report is not provided, there is a risk of financial misstatement. We want to ensure that this report is prioritized for development and developed in a timely manner, early enough for testing. Details: Existing report PSC5 from SDA Team in Planning is being EOL'd after WW43 due to Blue Yonder implementation; Report is currently provided as a manual offline report via MS Teams. As of WW29, the FPR Division Costing Execution team was told first that the report was not impacted in R2, but later told it would be EOL'd | Process subject to SOX Control COS-108R; Report is required on a monthly basis for determining DLCP (Die-Level Cherry Picking) Reserve type; Inventory Impact accuracy (~$400M 2025Q2); | Impact to Schedule TBD as scope of work is being evaluated | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR______%20-%20DLCP%20Reporting%20Change%20Request%20Form.pptx?d=w7f2fcb86666e426da750a3c504c38673&csf=1&web=1&e=BkVCGG |  | 1. Process Scope / Design Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-08-14 | o This is a request is a must-have for R2 SCP as it is related to a SOX compliance issue. o AR: Include t-shirt sizing of the analysis effort (High, Medium, Low) to capture the tech work and schedule impacts. Include details on whether the teams doing the analysis will be impacted – @Patil, Soman o AR: Include back-up plan and workarounds if CR is not approved - @Patil, Soman |  |  | 2025-08-29 | • Decision - Approved o The report development was approved to proceed with implementation, with contingency plans for raw data delivery if the report is not ready for 10'25. Full report delivery is expected by 12'25 | [5 empty] | Design | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1055 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 02. E2E Process Integration 07. FTS IF | eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | CR0811 | 01802,01803,01804 | 01802,01803,01804 | [5 empty] | Shipping Rejects/Scraps from ISM to Non-ISM | Change Request for E2E assessment of replacing ISM/SAP ISM Fiori on Shipping Rejects/Scraps that are non inventoried in MES systems (as they are intended to go for physical scrap unless there is a requested to be shipped either to IF lab, IP lab, External for material evaluation (i.e. MRB evaluation, etc.). | This process was designated part of the ISM non-compliance process, but given E2E has found some solution on “Reclaim Wafer Non-Inventoried from ISM to Non-ISM, we want l to leverage almost similar process to address ISM non-compliance. Shipments of Reject/Scrap is not of a re-occurring and high frequency compared to wafer reclaim. Without this CR, the program risks operational inefficiencies, audit exposure, and non-compliance with environmental and trade requirements | Dependent on the Proposed E2E flow | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B119BEADB-F406-4A83-A4E1-57558C5C4711%7D&file=CR_1055_IF%20FTS_Shipping%20Rejects%20from%20ISM%20to%20Non_ISM.pptx&action=edit&mobileredirect=true | Design / Build Gap | 1. Process Scope / Design Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3162 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-14 | This is an impact analysis of CR0811. Therefore, it will go straight to CR Meeting for approval. |  |  | 2025-08-15 | • The current process uses ISM and Fiori ISM, but due to tax and compliance issues, a new approach is needed. • The team proposes leveraging the reclaim wafer solution for handling non-inventoried scrap and rejects. • The new process will use standard SAP transactions like MIGO to bring materials into inventory as blocked stock, followed by a stock transport order. • This is an ad hoc, low-volume process, unlike reclaim wafers which are high-frequency. • Key considerations include: o Customs valuation: Scrap should not be valued at zero; statistical pricing may be used. o Material types: Potential use of UNBW or multiple UW materials for pricing combinations. o Master data: Minimal impact expected, but part numbers need to be defined. o Security/configuration: May require minor setup. o The process will support shipments between IF and IP, including labs and external customers. • Approved: Confirmed by Uzma Ahmed. Team to bring back if they discover any master data impacts. | [5 empty] | Design | CL/OSC | 2025-08-15 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1056 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Sindhuja Gangireddy | [11 empty] | Cancellation of RICEFW object OTCI0419 | Cancellation of RICEFW object OTCI0419 - Inbound Interface from WOM to S4 to send the output preference | WOM users will utilize existing ZBA1 and ZBA3 outputs instead of separate WOM outputs hence this interface is not required anymore |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1056/RE%20Approval%20needed-CR1056-Cancellation%20of%20RICEFW%20object%20OTCI0419.msg?csf=1&web=1&e=MvmGkN |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 126 |  |  |  |  | 0 | 126 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCI0419 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-13 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1057 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF 05. OTC IP | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | INC14824443 | Delivered |  |  |  | MBB Label CoF Logic Adjustment | Change data source of CoF from MPL to Batch Classification in SAP | For data accuracy, we are changing source of CoF to the Batch Classification in SAP. For all documents and labels, this should be single point of data consumption |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1057_IF_R2_CoF%20Logic%20Adjustment%20MBB%20Label.pptx?d=wd1829966ad01486695b1cc3e89652eaa&csf=1&web=1&e=a4LPFf |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 6 |  |  |  |  | 0 | 6 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-13 | Approved in ad hoc meeting with Uzma. Recording uploaded. This request is to change the source of an interface as Boundary app should not be sending this. | [9 empty] | Build | Tower | 2025-08-13 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-13 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1058 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | posunil@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA | NA | NA | NA |  | NA | #INVALID VALUE |  | RICEFW Cancellation request for ECA object FPRXV130 - Automated Rebate and Marketing Accruals (Reclass) | Cancelling ECA object FPRXV130 - Automated Rebate and Marketing Accruals (Reclass) | Object to be cancelled as business has confirmed that all fields in the Invoice listing were available in the standard Fiori app, | No impact. | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1058/RE_%20GL%20Close%20RICEF%20Cancellation%20FPRXV130.msg?csf=1&web=1&e=MXeT0I | NA | Missed Requirement | 5. Cancel RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRXV130 | Standard AP report (configuration) will be used in S4 as all the data required exists in standard Fiori app. |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-25 | [10 empty] | Other | Tower | 2026-02-25 | 02, 2026 | 02, 2026 | 08, 2025 | 2025-08-13 | 0 | < 15 Days | posunil@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1060 | Approved |  | SCP | R3 (Release 3) | High | 05. OTC IP | 5.14 OTC IP - IP Allocation Planning & Order Promise |  | 05. OTC IP 08. FTS IP 10. Analytics | Jon Benoist | FTS (SCP IP & OP) — Chad Smith | OTC IP - Teresa McNicol/Jon Benoist |  | CR0716 | n/a | n/a | [5 empty] | Original CMAD | Capture the original Confirmed Material Availability Date (CMAD) in each Sales Order/Line Item (SOLI). Leverage Original CMAD to ensure BY ESP and OP pull in all orders for a given material to their Original CMAD prior to attempting to pull orders into their Requested Material Availability Date (RMAD). | KDD to honor original commitment, therefore we should not be improving sales orders to their RMADs if other sales orders are beyond their original CMAD for a given material. | No | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1060_APOP_Original_CMAD.pptx?d=w02bed6497f0745e08f5bdb7889d20dc2&csf=1&web=1&e=rN7IfV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Low | Low | 1 |  |  |  |  | 40 |  | 24 | [6 empty] | 64 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPAPOPPDH0013, SCPIPAPOPPDH0011 | 2 | 2 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-11 | o This is related to a couple of other ERP CR’s, and this CR will allow for the CMAD and original CDD to be picked up from sales order.  It will be communicated out before attempting to pull orders into RDD o AR: Review ECA estimates – @Narayanan, Sunil @Clark, Vanessa M Vanessa confirmed that Sunil has reviewed the ECA estimates. Therefore, marked as approved. | [9 empty] | Build | Tower | 2025-09-11 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-14 | 0 | < 15 Days | jon.benoist@intel.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1 | INT-CR1061 | Cancelled |  | SCP | R3 (Release 3) | High | 05. OTC IP | 5.14 OTC IP - IP Allocation Planning & Order Promise |  | 05. OTC IP 08. FTS IP | cristopher.r.oltmann@intel.com | FTS (SCP IP & OP) — Chad Smith | OTC IP - Teresa McNicol/Jon Benoist |  | Mike Lange suggested this out of review with the Business. It was not a miss, but an improvement based on Mike's experience. | n/a | n/a | [5 empty] | Original CMAD | Capture the original Confirmed Material Availability Date (CMAD) in each Sales Order/Line Item (SOLI). Leverage Original CMAD to ensure BY ESP and OP pull in all orders for a given material to their Original CMAD prior to attempting to pull orders into their Requested Material Availability Date (RMAD). | KDD to honor original commitment, therefore we should not be improving sales orders to their RMADs if other sales orders are beyond their original CMAD for a given material. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Allocation%20and%20Order%20Promising/2.%20Feasibility%20Phase/CCB%20WIP/IAO%20PXT%20CCB%20BY%20APOP%20Original%20CMAD.pptx?d=wdb9593dca9684112bfa549f7bcb25b66&csf=1&web=1&e=mODQ2a |  | 1. Process Scope / Design Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Jon Benoist that this is a duplicate of CR1060 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1062 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 13. Security | Taposh Ganguli | OTC — Kevin Brown | OTC IF - Angela Laskowski |  |  |  |  | INC14831364 | Delivered |  |  |  | Allow CBA to have access for Import Sales Orders & Mass Change Sales Orders | The CBA (Customer Business Analyst) role will be updated to expand its transaction capabilities. Specifically, the following functionalities will be added to the CBA role: Mass Change Sales Orders(5211):?Grant the ability to perform mass changes on sales orders, enabling the CBA to efficiently update multiple sales orders in a single operation. Import Sales Orders(F4293):?Provide access to import sales documents, allowing the CBA to upload and process sales-related documents in bulk. | These enhancements are intended to streamline sales order management and document processing for users with the CBA role, improving operational efficiency | CBA will be able to process and update sales orders in bulk more efficiently, leading to faster order management and improved customer service. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BACE2113F-9996-4618-84B7-6638C2FCF60E%7D&file=INT-CR1062_Allow%20CBA%20to%20have%20access%20for%20Import%20Sales%20Orders%20&%20Mass%20Change%20Sales%20Orders.pptx=&wdOB=A3F6E62981794965B93E72145688B6C2&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [11 empty] | 10 |  | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2025-08-21 | Approved in CR Ingestion 8/21. | [9 empty] | Build | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-14 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1064 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-14 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1067 | Approved |  | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | rudrsengupta@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | [9 empty] | Additional WRICEF to support Interface to deliver the MM, BOM, Vendor master, Batch and STO details | Enhancement to create program which can run query and retrieve data on the MM, BOM, Vendor master, STO detail and batch detail | Issue: To facilitate the DMRA process, key data such as associated Material Master, Bill of Material, Vendor Master, Batch SLED (shelf-life expiration date), and STO details—must be provided. The DMRA team will utilize this information to evaluate material requests and make recommendations for the next material replenishment cycle. This program will be invoked through a Batch Job which will run daily. It will extract MM, BOM and Vendor data from SAP and send it to DMRA Existing program can be copied over. Proposed Solution: A single driver program will be implemented to send data—including Material Master, BOM, Vendor Master, Batch SLED, and STO details—to DMRA in intervals. This program will query standard tables, apply custom logic to identify the relevant objects, and utilize the interface to call the MuleSoft API, transmitting the required structure. The interface ensures that DMRA receives near-real-time data updates approximately every 15 minutes. An enhancement ID will be needed with this change request to enable scheduling the program as a background job. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/RE%20INT-%20CR%201067%20-%20Approval%20Required.msg?csf=1&web=1&e=u61zcD | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1067_FTS-IF_Enhancement%20to%20trigger%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20periodical%20basis.pptx?d=w17055112313a4024a732bf65e686ebd5&csf=1&web=1&e=0y8UWT&nav=eyJzSWQiOjIxNDc0ODExNDMsImNJZCI6Nzg5NjQ4MDg5fQ |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | Yes |  | 1 | FTSE1641 |  | FTSE1641 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-11 | o Additional data needs to be sent to DMRA, and this interface will be utilized to collect that data | [9 empty] | Other | Tower | 2025-09-11 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-14 16:19 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | In Progress |  | In Progress | No | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1065 | Approved | Presenter: Akshay Awasthi | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 04. OTC IF 05. OTC IP | Nilesh Dattatraya Sawkar | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Additional WRICEF for Credit Limit Request Workflow | Additional WRICEF object required to build Credit Limit Request workflow to cater for customized email notifications. | To cater for the requirement around Credit Limit Request functionality, BADI Enhancement and Custom Workflow are required. Existing WRICEF OTCE0737 is ‘enhancement’ type of object. Custom workflow is required to trigger email to multiple parties involved (not just to the next approver), also it is required to have customized email content which would convey more detail information to the recipient to act upon. Technical team would need a ‘workflow’ type of WRICEF to build the custom workflow and deliver the entire solution. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC78D9157-F820-43B1-A8EE-E7C95DBAE8E6%7D&file=INT-CR1065%20for%20CLR%20-%20Additional%20RICEFW%20for%20Credit%20Limit%20Request%20workflow.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA5MTExNjAxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | OTCW1683 | 2065, 3153 | OTCW1683 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-16 | o This was not discovered until FS discussions when team got into the granular details. o To deliver the workflow side of the work, then a new RICEFW is required. Not a new requirement, and design is done.  Everything is documented, but we need this RICEFW to be created for build to move forward. Functional inputs are added already. o AR: Include statement that there is no design work. - @Awasthi, Akshay o AR: This is not a core functionality so missing ITC1 is not a risk. - @Awasthi, Akshay |  |  | 2025-10-17 | • Another key topic was the enhancement of the CLR functionality within the OTC credit and collections team. • The existing system provides basic email notifications for credit limit increase requests but lacks detailed content and multi-level approval notifications required by the business. • The proposed solution involves implementing a custom workflow to send tailored notifications reflecting the requested changes and to support group-level approvals. • The team confirmed that while the functionality exists in ECC as customization, this enhancement is necessary in the new system to meet business requirements. • The request is for a medium complexity change request to build this workflow, with the functional design already approved. • The discussion recognized the uniqueness of the credit and collections process and the need for high-touch automation to manage credit lines effectively. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-17 | 10, 2025 | 10, 2025 | 08, 2025 | 2025-08-14 14:48 | 0 | < 15 Days | nsawkar@deloitte.com |  | No |  | Complete |  | Complete | No
| N/A | INT-CR1066 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Descope-R3-DATC0073-Material Master Data Warehouse Management View Conversion | As per EWM Team Warehouse Management Views will be directly extended in EWM Box and these extensions are not required in MDG and S/4 Systems | As per EWM Team Warehouse Management Views will be directly extended in EWM Box and these extensions are not required in MDG and S/4 Systems |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1066%20Descope%20Material%20Master%20Data%20WM%20View%20Conversion%20Object.pptx?d=wde828024d44a49e990f626a2c766927f&csf=1&web=1&e=S92JV3 |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 08, 2025 | 2025-08-14 16:15 | 237 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1068 | Approved |  | ERP | R2 Hypercare | Very High | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | josh.philpot@intel.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | Standalone | Delivered |  |  |  | SAP Finance Security Role change needed for 2 SAP related roles | Add various t-codes to OTC IF Finance Analyst role and FPR CORP - IT Support - Finance Close and Group Reporting. | Product Costing: Additional access needed outside defined L3 processes. Primarily, this access is needed for investigation and support for product costing team to confirm unit information with S/4, ECC, and ICOST. ​ CFIN/Group Reporting: IT support t-codes are needed to maintain MM periods in IF. | No impacts to existing Deliverables. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6838F938-BC4E-4656-B7DC-1E19576C952B%7D&file=Change%20Request%20-%20FPR%20Security%20-%20OTC%20IF%20Finance%20Analyst%20Role.pptx&wdLOR=c0CFEB4EA-91AA-416F-9317-E295C1EC6B8F&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  | No |  | Low | 0 | [11 empty] | 12 |  | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-19 | Approved by Uzma offline |  |  | 2025-08-19 | [6 empty] | Build | CL/OSC | 2025-08-19 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-14 17:43 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1069 | Approved |  | ERP | R2 Hypercare |  | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP 10. Analytics | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | Standalone | Delivered |  |  |  | Add MAWB Field Data to ECA​ | Customer (Mykonos) requires that the Master Airwaybill (MAWB) is provided in their Advanced Ship Notice (ASN) | To remain compliant to customer ASN requirement, we will need to populate MAWB field in Freight Order |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_R2_Add%20MAWB%20Field%20to%20ECA.pptx?d=wd1829966ad01486695b1cc3e89652eaa&csf=1&web=1&e=faiCeO |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-05 | Approved in Hypercare CR meeting with OSC | [9 empty] | Build | Tower | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-14 17:50 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1070 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP 17. B-App | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | INC14899448 | Work In Progress |  |  |  | Multiple COO Label | Intel will print Country of Origin and Quantity on a separate label to accommodate shipments with multiple origins. ​ | Compliance requirement in multiple countries requiring a breakdown of product origins on outer box.​ |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR10XX_IF_R2_Multiple%20COO%20Label.pptx?d=w6c3ffc5c155844fcb8e75007c5821837&csf=1&web=1&e=Dc4wN3 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 30 |  |  |  |  | 0 | 30 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-21 | Approved in CR Ingestion 8/21. | [9 empty] | Build | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-15 10:02 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1071 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com |  | OTC IF - Angela Laskowski | [9 empty] | Ireland Specific Consolidated Export CI​ | Local Export regulation requires consolidation and declaration at the product level and country of origin level. Existing form is providing information at the Delivery Note level. | Compliance to local export regulations, declaration data accuracy. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR10XX_IF_R3_Ireand%20Specific%20Consolidated%20Export%20CI.pptx?d=w5adca99377774093a06a1a803f8e45e2&csf=1&web=1&e=0JNGsl | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | LOGF1673, LOGF1672 | 3152 | LOGF1673, LOGF1672 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o Consolidation should happen at the product-level, but Ireland needs to have it happen at the product-level and country of origin-level. o This was identified during R2 UAT1, but it was really late. So, we have brought it in for R3. o We got the green light to use the form as is for R2, but the higher volumes will not work for it. o We can test everything in ITC1, but we won’t be testing this particular form | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 08, 2025 | 2025-08-15 10:08 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | Complete |  | Complete | No
R2.1MR (Feb 2026) | R2.1 ITC | INT-CR1072 | Approved |  | ERP | R2.1 Feb 2026 | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR1072 | N/A | N/A | [5 empty] | Wafer Die Export Invoice Forms Clean-up​ | Remove Wafer Quantity and Die Quantity fields from the Export Commercial Invoice and the End-Customer Invoice | Align Export Commercial forms with a request from ITG to remove Wafer and Die fields from our forms.​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B488EAF12-D27D-4C75-889C-014D2324FF79%7D&file=INT-CR1072_IF_R3_Wafer%20Die%20CI%20Forms%20Clean-up.pptx&wdLOR=c325C7926-4225-49BE-89D4-444CA0131F58&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 4 |  |  |  |  | 6 | [5 empty] | 0 | 6 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-16 | o Want to remove wafer quantity and die quantity from the invoice form o Work will be done by the Operate Team and deliver for Release 2.1 | [9 empty] | Build | Tower | 2025-09-16 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-15 10:41 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2m (October 2025) | R2 Hypercare | INT-CR1073 | Approved |  | ERP | R2 Oct 2025 | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | Standalone | Work In Progress |  |  |  | Commercial Invoice Line Item Numbering​ | Commercial Invoices and Packing Lists with multiple batches to show the Line Item on the form as "10-X" | For customer consumption and OpenText messages, create unique identifier on the form per new line item when multiple batches or countries of origin are present in the form. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR10XX_IF_R2_Commercial%20Invoice%20Line%20Item%20Numbering%E2%80%8B.pptx?d=wd35409719a674db282f4759187e0e177&csf=1&web=1&e=tPsj0S |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 8 |  |  |  |  | 0 | 8 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0342_IF, LOGF0344_IF, LOGF0345_IF, LOGF0346_IF, LOGF0346_IF, LOGF0347_IF, LOGF0357_IF, LOGF0353_IF, LOGF0354_IF | 9 | LOGF0342_IF, LOGF0344_IF, LOGF0345_IF, LOGF0346_IF, LOGF0346_IF, LOGF0347_IF, LOGF0357_IF, LOGF0353_IF, LOGF0354_IF | 9 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | o This change is to number and order the splits within the invoice and packing lists based on the number of items.  This helps customs when they review the commercial invoice. o Delivery notes will have the same splits, and there will be traceability between the invoice and delivery note. | [9 empty] | Build | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-15 10:47 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1075 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | syed.s.nawaz@intel.com | OTC — Kevin Brown | [9 empty] | Anafi | Anafi scope of work for Logistics Management Outbound | Scope of work for the Anafi design factored for Release 2.5. | - The Anafi process will involve three Sales orders & invoices. A "Virtual Shipment" is required for the 1st and 2nd orders from Anafi. The 3rd invoice will be a physical shipment, following the standard R2 shipping process. - The Finished Goods receiving to inventory will go through the MPL process, consistent with the current R2 solution. - The team needs to define a solution to differentiate virtual vs. physical shipments in the MPL process, ensuring virtual shipment quantities are posted to a separate inventory. - The proposed solution will bypass EWM and TM; the PGI process will occur in the IM module. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/Logistics%20Scrum%20of%20Scrum/Change%20Requests%20Forms/INT%20Build%20CR1075%20Anafi%20LOG%20Scope.pptx?d=waf8dc29eb8f5496eab41e675412e4630&csf=1&web=1&e=DQr72L |  | 1. Process Scope / Design Change |  |  | Very High |  | 4 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3110, 3111, 3112 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0612_IF | 1 | LOGI0612_IF | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-08-21 | o AR: Team to develop and bring in slide to core leadership detailing who is funding and staffing this project to ensure there are no impacts on other parts of the program. @Vishwanathan, Ravi |  |  | 2025-08-22 | • Pilot Approach & Timeline o 400 MM IDs for pilot approach with plans to expand in 2026. The pilot is a risk mitigation strategy, with a go/no-go decision in Q1'26. If successful, all Anafi products will convert to the new solution, but a further CR will be needed for R3 deployment in 2027. Estimated 3,000 sales orders/month. o Requires onboarding into B2B landscape and support for ERO Sales orders. o Virtual shipment process will bypass EWM and TM systems. • Build Instructions & Fiori App o Custom table from R3 to be extended for Anafi’s needs. o Fiori import app under evaluation for build instruction integration. • Resource Planning o ~10 Deloitte resources needed across OM and Logistics. o Intel business and IT teams to support with overlapping responsibilities between R3 and Anafi requirements. o Concerns raised about resource stretch and burnout. o There is not currently enough information for confidence in the resource forecast. • Timeline & Risk o Aggressive schedule aiming for December 28, 2025, go-live. o Design phase only 3 weeks; risk of impacting R3 deliverables. • Governance & Funding o M&A funding is assumed but confirmation is required. o Data conversion resources are covered however other resources need to be considered . o The funding source for additional Deloitte resources being onboarded is unclear. o Proposal to escalate to executive committee for support and funding. o Suggestion to consider Anafi as a small program versus several Change Requests. Decision: Approved to move forward to conduct a risk and resource assessment with impacts and return ww35 with the details to Core Leadership. • AR - Uzma Ahmed to provide Paul Whitlock with summary of additional resource costs for Anafi. • AR - Anand Jha and Shripad Deshpande to assess risk and resource impacts and gaps due WW35.2. • AR - Paul Whitlock and Jorge Sanchez to determine the logistics resource constraints and potential options for filling them. • AR - Kevin Brown, Paul Whitlock, and Mike Lange to meet regarding options for funding Deloitte resources from existing budget. | [5 empty] | Design | CL/OSC | 2025-08-22 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-16 05:46 | 0 | < 15 Days | ralvarezcarroz@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1076 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.8 PTP - QM |  | 06. PTP | Anant Joshi |  | PTP - Richard Taylor | [8 empty] | WIINGS | Changes to the existing Enhancement LOGE1034_ IBD creation to consider QIR record into consideration while determining the stock type in IBD | Enhance the logic in LOGE1034_IBD so that, during IBD creation, the system references the "Inspection control" settings in the QIR record. The stock type in the IBD should be determined based on these settings. | Enhance the logic in LOGE1034_IBD so that, during IBD creation, the system references the "Inspection control" settings in the QIR record. The stock type in the IBD should be determined based on these settings. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Murthy to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-18 13:13 | 0 | < 15 Days | nnagapushpa@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1077 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Taposh Ganguli | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Enhancement to update departure country key to Ireland for tax condition determination | Previously, SAP only captured the transit plant code, omitting the physical plant code assigned by BY, which led to inaccurate tax code determinations and prompted an enhancement request. However, recent assessments confirm that BY will now correctly update the delivering plant code in SAP, enabling accurate tax code determination via OneSource and rendering the enhancement unnecessary. To address this, it is aligned that the object OTCE0973 will be descoped and need to comment out the related code from the system. This change is required as the Intel Tax team no longer requires the enhancement that was previously requested, based on updated business requirements. | The enhancement-OTCE0973 is no longer required, as the Intel Tax team has revised their business requirements. Based on recent discussions, the team has decided not to proceed with this enhancement. Therefore, the related code needs to be removed or commented out to align the system with the updated business needs and avoid unnecessary functionality. | CR will ensure that the system aligns with the revised business requirements from the Intel Tax team | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCF3507DC-FDCE-48D2-93FB-6C3E56C1DD0E%7D&file=INT-Build-CR0_Descope%20Object-OTCE0973%20to%20Align%20with%20Revised%20Intel%20Tax%20Team%20Requirements.pptx&action=edit&mobileredirect=true&CID=E1619569-B78A-406A-995F-7743A35EA8E0&wdLOR=c1F859B18-7FB4-4FD9-961A-22654F6E65A3 |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 |  |  | 10 | [5 empty] | 20 |  |  |  |  | 0 | 20 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE0973 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-07 | [9 empty] | Confirmed by Steve Spotts to be cancelled | Other | Tower | 2026-01-07 | 01, 2026 | 01, 2026 | 08, 2025 | 2025-08-18 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1078 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams |  | N/A | RAID # | [6 empty] | OCTO Business solution | OCTO Business solution for Intel Products | The existing OCTO solution in ECC will be migrated to both Intel Products and Intel Foundry and ensure the continuity in R3 and beyond without interruption to business. The BUs associated with OCTO will be distributed between IP and IF. 2 CRs will be presented, CR1 for IP and CR2 for IF. Intel Products: NEX EPS - Enabling Platforms & Services Intel Federal Intel Foundry: SDL - System Development Lab BDL - Boards Development Lab Note: 2 CRs will be presented and this CR deals with IP scope only and a separate CR will be presented by IF |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1078_FTS_IP_OCTO%20Business%20Solution.pptx?d=w5351ed677cdb4bcf9634cf2fdd9e43b9&csf=1&web=1&e=0fZhuc | New Requirement / Scope | 1. Process Scope / Design Change |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-21 | o AR: Team to create detailed execution plan prior to bringing it to the CR meeting. @Lingam, Sekhar |  |  | 2025-08-26 | • This is the next significant topic covered by the OCTO business solution focusing on Intel Products. The solution involves splitting change requests for Intel Products and Intel Foundry, with the current presentation addressing Intel Products. The strategy is to create purchase orders in ECC for products manufactured by Intel Foundry, which will then be received as sales orders by Intel Foundry. • The implementation requires master data migration (materials, vendors) and configuration setup such as plant creation and MRP area configuration to avoid conflicts with other business units like My Samples and Elpis. A utility tested for My Samples will be leveraged for uploading planned independent requirements for OCTO. • The scope includes: o Setting up plants and MRP areas dedicated to OCTO. o Migrating up to 1000 finished product materials. o Configuring a limited number of US manufacturing vendors. o Utilizing existing utilities for planned independent requirements upload. o Planning to finalize design and configuration in Sprint 18 with no major risks anticipated. • The solution aligns with previous work done for My Samples and Elpis and aims to leverage existing configurations and utilities to minimize complexity. | [5 empty] | Design | CL/OSC | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-19 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1079 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 17. B-App | Florian Kaesen | PTP — Kenneth Salazar | PTP - Richard Taylor | [6 empty] | 12208 | E2open |  | Translation of plants to MLC codes for External Manufacturers (OSATs) for straddle | Translation logic from internal plant codes to manufacturing location codes (MLCs) needs to be implemented in E2Open to enable external OSATs to generate 7B1 data according to CIBR required format (during R3-R5 straddle) | Post R3 release, external OSATs will receiving plant codes ( e.g. 4001) from Intel IP as identifier of shipping and receiving destinations. But to support CIBR during the straddle period (R3-R5), external OSATs need to send a RECEIPT and SHIP events as part of 7B1 (Manufacturing WIP) using manufacturing location codes (e.g. site = TDS and stockroom = RDS) as destination identifiers. As per IAO definitions, it is possible to have 1:N plant-MLC relationship, translation of plant to MLC codes is needed in outbound supplier communications |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1079/RE%20Change%20Request%20-%20Need%20Approval%20before%20Mike%20is%20oop.msg?csf=1&web=1&e=bG158s | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1079_IP_R3%20E2O%20Plant%20to%20MLC%20translation%20(004).pptx?d=w9f972b548779493fb815ca18064eb31b&csf=1&web=1&e=HYe3kH |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0491, FTSI0492, FTSI0725, FTSI0724, FTSI1140, FTSI1142 | 6 | FTSI0491, FTSI0492, FTSI0725, FTSI0724, FTSI1140, FTSI1142 | 6 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-21 | o AR: Confirm that E2O can take this in and be ready for ITC1 and that there are no other impacts to taking on this scope. @Ramirez Gonzalez, Jose |  |  | 2025-08-26 | • This is an additional critical discussion involved a change request related to e2Open, focusing on translating procurement signals between OSETS and CIBR systems. The goal is to implement a translation process within e2Open to map manufacturing location codes (laser codes) to site codes understood by CIBR. • This translation is considered a temporary solution during a straddle until CIBR is phased out post R5. The rationale for placing the translation in e2Open includes ease of implementation and minimizing changes to CIBR and SAP interfaces. • The discussion highlighted: o Estimated 275 hours of work for implementing the translation in e2Open. o Concerns about touching e2Open multiple times and the complexity of future removals. o The need for a detailed architectural review involving multiple architects and system owners (CIBR, e2Open, SAP). o Agreement to defer approval pending a deeper dive and architectural alignment. • AR - Jose Vargas Lepiz - Provide a flow diagram to help stakeholders understand the data transmission and translation process. Clarify the flow of data from OSATS → e2Open → CIBR, including SAP interface implications. • AR - Jose Vargas Lepiz - Follow up with Satya Vajjala and Kelly Gerber to provide the list of architects to schedule a design review with. | 2025-08-29 | Approved offline by Mike. Approval email linked in the "Approval Email" column |  |  |  | Build | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-19 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1 | INT-CR1080 | New |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 10.1 Analytics - ALL |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 10. Analytics 17. B-App | sunil.narayanan@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | INC14822487 | N/A | [5 empty] | Update ECA fields to enable timezone conversions/identification | ECA would rename a lot of existing timestamp fields in ECA to clearly prefix the timezone in the field, then we will also be introducing some converted (into PST or UTC) additional field for certain timestamp fields. Boundary apps and ECA reports may need to use appropriate columns, thus the whole change could impact boundary apps and reports | Apps/reports are currently dealing with multiple timezones and don't know which need to be converted | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Change%20IDXX_ECA_Timezone_Issue.pptx?d=w3f6075e8f6e1466ba5e22bbcc511f8d9&csf=1&web=1&e=XGBupp |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-19 | 232 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1081 | Approved |  | SCP | R3 (Release 3) | High | 05. OTC IP | 5.14 OTC IP - IP Allocation Planning & Order Promise |  | 05. OTC IP | cristopher.r.oltmann@intel.com | FTS (SCP IP & OP) — Chad Smith | OTC IP - Teresa McNicol/Jon Benoist |  | Mike Lange suggested this out of review with the Business. It was not a miss, but an improvement based on Mike's experience. | n/a | n/a | [5 empty] | Allocation Start / End Dates | Allocations will be created in OP from our ESP supply output each cycle. As of now, allocations can be turned on/off by Item/Location/Customer Division without a time horizon component (not time phased). This change will provide the ability to specify a start and end date per Item/Location. Supply outside of the start/end dates will not be allocated.​ | Avoid allocating supply in a horizon where it’s healthy. Ex. If supply is only constrained in months 5-7, don’t allocate months 1-4 of the promise horizon as this will prevent FIFO based scheduling.​ | No | Yes |  |  | https://intel.sharepoint.com/sites/intelspinnakerdeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Fintelspinnakerdeloitteiao%2FShared%20Documents%2FIP%20Allocation%20and%20Order%20Promising%2F2%2E%20Feasibility%20Phase%2FCCB%20WIP&viewid=471d4bf9%2Dad76%2D42fb%2Db265%2D6264c35a709e&csf=1&web=1&e=AyURJp&OR=Teams%2DHL&CT=1723743113017&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA3MTEyODgyNSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=8048ce55%2D636a%2D4c4a%2Dadd4%2D651cca88ead5&FolderCTID=0x01200088C52C175B711D41896AB37BBAA6726D&siteid=00481f88%2Dfa4b%2D4942%2Dbc89%2Dd667fa72ef30&webid=efbf8a34%2De7e1%2D4520%2D867c%2De2a03bd5040d&uniqueid=a61a9855%2D29eb%2D4dea%2D8835%2Dc4a0b6a5ecda |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | High | 0 |  |  |  |  | 28 | 24 | 8 | [6 empty] | 60 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPAPOPPDH0030, SCPIPAPOPPDH0029, SCPIPAPOPPDH0036, SCPIPAPOPPDH0018 | 4 | 4 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-21 | Approved in CR Ingestion 8/21. | [9 empty] | Build | Tower | 2025-08-21 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| R2 Hypercare | INT-CR1082 | Cancelled |  | ERP | R2 Hypercare R2.X (Between Release 2 & 3) | Medium | 09A. Master Data | 10.9 Analytics - Master Data |  | 09A. Master Data 10. Analytics | Thienne.Johnson@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | SAP S4 tables contain fields with different time zone formats UTC PST local time. J | RAID #1602 | N/A | [5 empty] | Calendar Time zone Daylight Saving Bugfix | SAP-S4 table contain date/time in different time zones such as UTC, PST, Local time zones. A Master date calendar view is used to change time zone from one to another to do throughput (TPT) calculations that span different time zones. The view currently in use doesn't consider daylight saving during this time zone conversation resulting on wrong calculations | To accurately measure throughput between different time zone, the master data views need to consider daylight saving, while converting datetime fields between different time zones for SAP S4 tables. This will enable us to accurately measure throughput and other calculations which bring data from different time zones | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR1082-%20Calendar%20Time%20zone%20Bugfix%20Request.pptx?d=w6bebd7d602654cb0856427b38fa1c787&csf=1&web=1&e=T5SWth |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Being tracked in separate Hypercare log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| R5 ITC1 | INT-CR1083 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 17. B-App | eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | 1590 | NA | [5 empty] | BDL SAP ME to S4 Design inclusion with IMR R3 Development | Enhance integration with SAP ME (already in scope for IMR) to support SDL, BDL businesses.Key Changes within IF FTS: Specific to SAP ME changes used by IMR is part of R3, to add incremental change from IF BDL using SAP ME per Factory Automation Request to comprehend 1 time development. SAP ME incremental change from IMR from Factory automation initial assessment: Incremental change from IMR: Shop Order (aka Prod Ord), intefrace with S4 IM (BDL) Other BDL/SDL changes is part of the CR1101 requiring E2E process – part of R4 work (not included in this CR) | Factory Automation Request to comprehend one time development due to constraint SAP ME resource that is unlikely to support parallel R3 ITC and R4 Development.. | No impact pending requirements assessment | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR_1083%20BDL%20SAP%20ME%20R4%20to%20R3%20.pptx?d=w1ad85afca81847c0a47d43cc7e9145a7&csf=1&web=1&e=EvH5Q1 |  | 1. Process Scope / Design Change |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 231 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1084 | Cancelled |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF | Mariana Campos |  | OTC IF - Angela Laskowski |  |  |  | NA | [5 empty] | XML File movement from PRD to QA share drive | We require that files placed by Descartes in the Mulesoft production shared drive also be copied to the Mulesoft QA shared drive, specifically to the country inbox. This is necessary to support master data loading in JC0 for updates. | To keep the files updated in the test environment will be usefull for testing in lower environment | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1084%20XML%20File%20transfer%20from%20PRD%20to%20QA%20share%20drive.pptx?d=w1e1eab7a7a044c2f90d671058a7025da&csf=1&web=1&e=rrMGxR |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Dilky that this is no longer required. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 0 | < 15 Days | kamohanan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Aug 2025) | R2 | INT-CR1085 | Approved |  | SCP | R2 (Release 2) | High | 16. Testing | 16.4 Testing – Test Boundary App |  | 06. PTP | mary.chen@intel.com | BApps — Kelly Gerber | Testing - Guna Vishwanathan |  | No CR# created yet | IAODTM-6816 | No Raid created | [5 empty] | E2Open : R2 SCP's Order Management Defect | Change is from 55 series multiple line items and 45 series single litem PO between current functionality when compared to R2 SCP functionality | In the scenario where an order change the ship-to location, external foundry suppliers TSMC and UMC are expected to see a value of "Revise" at the line level in the B2B file so that they can receive into their systems and identify the order has been revised. Given that change the ship-to location is the most common reason for DCM requests, this would result in TSMC and UMC being unable to correctly receive our order changes after the R2 system goes live. Therefore, will need E2Open help to implement the new logic as soon as possible. | High Impact since solution can only be provided b ww3.1, post UAT2 cycle end. | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1085/EXT%20CR-1085%20FW%20R2%20SCP%27s%20Order%20Management%20Defect%20JIRA%20%23%206816%20-%20CR%20Approved.msg?csf=1&web=1&e=LK0cE5 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/CCB_PO%20Change_ship-to_%20E2Open_v2%20.pptx?d=w94f4fb962a53445eb322ceeefa2cad87&csf=1&web=1&e=CtrcBH |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-20 | [10 empty] | Design | Tower | 2025-08-20 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1087 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 17. B-App | Siddharth Asitkumar Desai | PTP — Kenneth Salazar | PTP - Richard Taylor | [6 empty] | 12208 | E2open |  | DTC Bailment to Substrate Supplier | Change require in Logistics interfaces of ASN (3B2), GR (4B2) and 4C1 (Inventory Adjustment) for IP & IF to support the process of DTC Bailment to Substrate Supplier | In this Scenario, Intel (IP/IF) raises a PO to DTC suppliers to drop-ship DTC Materials to Substrate Suppliers. 1. ASN (3B2) will be sent by DTC Supplier to Intel and the same will be processed by Intel, Changes require in IP & IF ASN interfaces to add Expiry Date field in Payload. 2. Substrate suppliers will send GR (4B2) on receiving the DTC materials from DTC Suppliers. Changes require in IP & IF interfaces to exclude the logic for transfer posting to SPV. 3. Substrate supplier will send Inventory Adjustment (4C1) to report the consumption of DTC materials, Changes require in IP & IF 4C1 interfaces to add Reason code field in payload and new transaction types needs to be configured. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR1087_PTP%20LE_DTC%20Bailment%20to%20Substrate%20Suppliers.pptx?d=we913d41e0f3d4ce98bf0f3f1ee7521c8&csf=1&web=1&e=E7JM9P |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | High |  | 3 | [8 empty] | 84 |  |  |  |  | 0 | 84 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0253, LOGI0139, LOGI0157_IF, LOGI0157_IP, LOGI0163_IP, LOGI0163_IF | 6 | LOGI0253, LOGI0139, LOGI0157_IF, LOGI0157_IP, LOGI0163_IP, LOGI0163_IF | 6 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-04 | o Intel will buy materials from DTC and then drop them to the substrate suppliers, and there needs to be some signal changes o There will be changes on both the S4 and E2Open side, and E2Open confirmed that they will be able to test in ITC2. o AR: Reword sentence in description to be “self-funded by BApps” and “Part of 6 other requests” - @Gerber, Kelly A o AR: Identify whether there are dependent test cases/scenarios and what measures will be used to address them - @Santhanam, Srivatsan |  |  | 2025-09-05 | • Change request is to enable DTC substrate suppliers for B2B connectivity via E2open. The planning side (PDAGCA and IBP) was previously approved, but E2open was not ready for assessment at that time. • SAP Impact: Minimal changes required—just adding attributes to three interfaces, leveraging the existing Bellman design. • E2open Impact: Significant effort (294 hours), primarily due to configuration and inventory bifurcation processes. E2open is at full capacity, so this work will be deferred to ITC2. • Funding: Already secured via Boundary Apps and included in six recent change requests. No additional S4 budget impact. • Design Alignment: The changes follow standard supplier flows and Bellman design, with minor updates for batching and expiry dates. • Timing & Risk: Substrate suppliers won’t be ready until later in the year, making ITC2 timing acceptable. The team confirmed that this delay does not impact other critical deliverables. • Decision: Approved to proceed with implementation in ITC2. | [5 empty] | Build | CL/OSC | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-20 | 0 | < 15 Days | siddesai@deloitte.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1086 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Prabesh Acharya |  | FPR - Aubrey Hinderlider | [9 empty] | Changes in COGS calculation and posting as per legal and group valuation. | According to the original design, the COGS (Cost of Goods Sold) calculation and posting for the FPRE0475 ( Unissued Return Credit not Accrual) were based on the transfer price (ZTPR). However, following the latest alignment, COGS calculation and posting should now be performed using the standard cost (VPRS). Currently, COGS calculation and posting occur only for legal valuation. Based on recent discussions, the business requires COGS to be posted for both legal and group valuations. We need to identify the logic to capture group valuation at the material and plant levels, so it can be used for posting the FPRE0475 ( Unissued Return Credit not Accrual). | Requirement for Business to Recognize the COGS at group and legal valuation level by using standard cost. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1086%20%E2%80%93%20Changes%20in%20COGS%20calculation%20and%20posting%20as%20per%20legal%20and%20group%20valuation..pptx?d=wfd1af8406963402793a0ea43428f2fdd&csf=1&web=1&e=eQNA6f |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Manidipa that it can be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 0 | < 15 Days | namanx.jain@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1088 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 0 | < 15 Days | namanx.jain@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1089 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Prabesh Acharya |  | FPR - Aubrey Hinderlider | [9 empty] | Changes in COGS calculation and posting as per legal and group valuation. | In the original design, COGS (Cost of Goods Sold) calculation and posting for FPRE0476 (Stock Rotation Reserve) were performed based on the COGS for legal valuation only. With the recent changes, postings are now required for both legal and group valuations. To support this, we need to determine the logic for capturing group valuation at the material and plant levels, enabling accurate posting for FPRE0476 (Stock Rotation Reserve). | Requirement for Business to Recognize the COGS at group and legal valuation level. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1089%20-%20Changes%20in%20COGS%20calculation%20and%20posting%20as%20per%20legal%20and%20group%20valuation..pptx?d=w2c4c6a7dd54542f98f83cf184dcfba7e&csf=1&web=1&e=kIWkS3 |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Manidipa that it can be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-20 | 0 | < 15 Days | namanx.jain@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1090 | Approved | Presenter: Mauricio Missing key fields | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | Venkat Venkatesh | [10 empty] | Federal | Incorporating IFL Time Keeping additional fields in HRMM API | 1. Default Payroll Areas - 02 & 04 to be captured for Time Keeping Employees having IFL TK indicator as Y and IFL TK Approver Flag as Y in IP. 2. Dynamic Work Schedule check box 3. If we receive Null for Company Code or cost center data from WCDS. Discard the WWID completely and do not send it to MDG 4. PA0105 subtypes should not be updated if the Subtypes are having null value coming from WCDS. 5. Employment percent 6. Weekly working hours 7. Daily working hours 8. Weekly workdays 9. Part time & Dynamic work schedule check boxes to be checked if capacity Utilization is less than 100 10. ZBIZ - Pass CompanyCd into this field. 11. Position ID mapping 12. Work Hours / Period 13. Time Keeping Approver Flag 14. Payscale Type 15. Payscale Area 16. Mapping changes for P0003 segment Start and End Dates 17. Org Unit Mapping 18. AEDTM mapping changes to SY-DATUM 19. EG mapping for POI and SDW | These fields are required to show accurate details in Planned Working Time & Basic Pay for the calculation of CATS hours. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1090_Incorporating%20IFL%20Time%20Keeping%20additional%20fields%20in%20DATI0959.pptx?d=w5df954c27348464a88445fec38b7c8cc&csf=1&web=1&e=B09mzx |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [8 empty] | 28 |  | 140 |  |  | 0 | 168 | Data Migration Tech - MDG | No |  | 0 | N/A |  | DATE1623 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0583​, DATI0959​, DATE1623​ | 3 | DATC0583​, DATI0959​, DATE1623​ | 3 |  | 0 |  | 0 | N/A | N/A | 2026-01-30 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-16 | o Requested by Intel Federal to add a few more fields to help them with their time-keeping o All 3 teams have validated their portion of the hours involved and confirmed for ITC1 without any commercial impacts. | [9 empty] | Build | Tower | 2025-10-16 | 10, 2025 | 10, 2025 | 08, 2025 | 2025-08-20 | 0 | < 15 Days | venkvenkatesh@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Hypercare) | R2 Hypercare | INT-CR1091 | Approved |  | ERP | R2 Hypercare | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF | rodolfo.alarcon@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | INC14845309 | Delivered |  |  |  | Date Code Update Request in Batch and Shipping Label | These changes are related to change of characteristics and master data in Batch that is automatically populated when information being sent from MPL via Waybill ID | This change request is required so that Date Code in Factory Label and Warehouse Shipping Label will be unique without any dicrepancies | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/FTS_IF_R2_Date%20Code%20in%20Batch.pptx?d=w4257b3af3c6c400fa1d3247524cccac6&csf=1&web=1&e=IWfyx5 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [8 empty] | 20 |  |  |  |  | 0 | 20 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278, LOGI0303, LOGE0306 | 3 | LOGI0278, LOGI0303, LOGE0306 | 3 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-26 | 8/26: Approved in R2 Hypercare Change Ingestion | [9 empty] | Build | Tower | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1092 | Cancelled |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com |  | OTC IF - Angela Laskowski | [9 empty] | Outbound Net Weight Capture | Bring over existing Intel Net Weight Logic that applies covers against non-compliance of MM# set-up in Speed.​ Unlock field in VL02N so that Operations can make changes as needed prior to PGI/departure. | Ensure Intel is within Import/Export requirements with the reporting of the correct Net Weight on a product. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR10XX_IF_R2_Net%20Weight%20Capture.pptx?d=w876ac637a12d459c9f5ad19c08e00209&csf=1&web=1&e=vWKvU0 |  | 3. Configuration Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Jason Carmichael and Junior Milan that this is no longer required. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-21 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1 | INT-CR1094 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) R5+ (Post Release 5) | Low | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 09A. Master Data 17. B-App | lynn.asbur@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | na | na | na | [5 empty] | Change B-App IBDS-21841 Time from Migrate to Tolerate | Requesting a change in the IAO Time in the B-App Tracker for IBDS-21841 from Migrate to Tolerate. | IBDS has 2 parts - 1 DW/ROR portion that is migrating to ECA and 1 ROO portion that is tightly coupled with SPEED & OCPLM. This portion will need to remain while SPEED & OCPLM are in the ecosystem. | No impact to schedule. This application should have always been Tolerate vs Migrate. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT%20-%20CR%20%20MD%20IBDS%20Time%20Change%20Request.pptx?d=wdb3470ce0b794e819b78fcfd6eb7e1a8&csf=1&web=1&e=rqlEgy |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-21 | 230 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1095 | New |  | ERP | R2.1 Feb 2026 R3 (Release 3) | High | 04. OTC IF | 10.4 Analytics - OTC IF |  | 04. OTC IF 10. Analytics | Praveen Kumar Muppala | [11 empty] | Pricing Report for NRE Discount | Generate an NRE Price Report that lists all sales orders where the ZNRE condition type is applied. For each customer, show the total NRE discount consumed to date and the remaining NRE discount balance, based on their agreed NRE allocation. | Currently, we do not have a report in place that allows us to check how much NRE discount has been offered to a customer, how much has been consumed, and what remains available for the customer's future consumption | This is ECA report and approved for R2.1 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1095-Pricing%20Report%20for%20NRE%20Discount%20.pptx?d=w552500949088423e94788c53434ce8e1&csf=1&web=1&e=6Aighh |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-22 | 229 | > 30 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1096 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 10. Analytics | Harshal Bornare |  |  |  | Cancellation of this object as this requirement is already covered in PTP object. | [7 empty] | Cancellation of ECA object - FTSFV037 | Cancellation of objects due to the duplication. | This object need to be cancelled as this is no longer needed by PTP and PTP has already covered Simulation Order covered in one of the object - PTPFR112 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Analytics%20Ingestion%20Objects/EXT%20Re%20Cancellation%20of%20FTSFV037.msg?csf=1&web=1&e=hxJV9e |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-02 | [10 empty] | Other | Tower | 2025-09-02 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-22 | 0 | < 15 Days | hbornare@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1097 | Approved |  | ERP | R2 Hypercare | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | rodolfo.alarcon@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | L-040-120 | N/A | N/A | INC14829131 | Delivered |  |  |  | Change in Putaway Strategy in MY01, CD01 Warehouse | Currently, multiple batches of the same product are allocated to different bins during putaway. This leads to the same product being distributed across several storage locations, regardless of bin capacity. Under the new putaway strategy, multiple batches of the same product will be allocated to the same bin until the bin reaches its maximum capacity threshold. Only after a bin is full will subsequent batches be directed to additional bins. This change will be implemented across all AT sites, specifically MY01 and CD01 | Improved Space Utilization: Allocating multiple batches to the same bin maximizes bin capacity, reducing unused space and optimizing warehouse storage. | No impact | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD27D0A63-796E-4617-8231-61FF5BC2CDD8%7D&file=INT-CR1091_FTS_EWM_R2_Change%20Request%20for%20Putaway%20Strategy.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 3. Configuration Change |  | No |  | Medium | 0 | [7 empty] | 20 | [5 empty] | 0 | 20 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-26 | 8/26: Approved in R2 Hypercare Change Ingestion | [9 empty] | Other | Tower | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1098 | Approved |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  |  |  |  | INC14844401 | Delivered |  |  |  | Additional Processing Lines MY | Add Packing Stations PC02 (Lane 27) and PC03 (Lane 28) to support IF business in Malaysia. | Additional processing capacity in R2 for Malaysia Ops. | No impact | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR10XX_IF_R2_Additional%20Processing%20Lines%20MY.pptx?d=wee39aebab65b49d0afe70d7b7d28a1b1&csf=1&web=1&e=uF9ZwG |  | 3. Configuration Change |  |  |  |  | 0 | [7 empty] | 5 | [5 empty] | 0 | 5 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-26 | 8/26: Approved in R2 Hypercare Change Ingestion | [9 empty] | Other | Tower | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-22 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1099 | Approved |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.3 E2E Process Integration - Process Design |  | 02. E2E Process Integration 04. OTC IF 07. FTS IF | talbot.smith@intel.com | OTC — Kevin Brown | E2E - Aishwarya Bhat |  | New customer requirement | 1107 | NA |  |  |  |  | Anafi | Anafi Wafer Sales R3 Design | Implement a design that supports wafer sales in a die sort environment to support Anafi at R3. The R2+ design being pursued by the New Customer Integration team will not work for manufacturing sites that are live on S/4, so beginning at R3 | Existing R3 design for wafer sales at die sort out (PROC item) is intended for Intel Products. Anafi will not be able to use this solution and we need an alternative solution to support this customer. The interim solution currently being proposed for Anafi at R2+ will not work post-R3 | Incremental to existing deliverables. Sizing TBD based on design | No |  |  | https://secure-web.cisco.com/1VluMF6UXl0aAtNIKaSwRKq6vfTN_XwRW8f-pUCx4V18Kmy3DDZBKu_q8aQjiYvzpfPYxQggPIQ4aBIXcZZZTTTpUUtEfW1rl9a23wEURtIPIu79DF0XQQiezG9yfgU6-Kd3aonpbeimvhJyPY4iUuDLfrFERiQEoqC4H46OUoaRDGzTZlkxUnSH_LbctNuFzUYyZ_SIFEhOUG_L6zcRZt6Z5n9Snt9jp7TrzN1gEgrOq-bFQgSX7NllbIVSWfyKiXK72Z20FZFahrJ-EW4wlTv9IFz1eIwC7jbVvPTZU8vpdR9lI0RS5tsn2QNVS4T7sb_UB2pRlBvwIeUUogKPSGECAYdb_XJYYFtBdQSt--p8YELkP41QAbMRuFuaj9QVTd_A6CNN3RNLBbu-DAJ29OTR1fd7MysOJYQpNmGf8pkW7wpbuNs5K-wf6rrgw5-OtFbRehWg93iei1zFzUxO1fg0DnFZCZjoAXAZ4S959U_-D-qdWBq1vgRPFrhRUZl7O_YGD4ljXyD_IKYdQDcx8MA/https%3A%2F%2Fintel.sharepoint.com%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F01.%2520PMO%2F05.%2520Scope%2520and%2520Change%2520Control%2FChange%2520Control%2FChange%2520Request%2520Decks%2FOTC%2FINT-CR1099%2520Anafi%2520Wafer%2520Sales%2520Long-Term.pptx%3Fweb%3D1 | New Requirement / Scope | 1. Process Scope / Design Change | OTC IF and FTS IF L3s | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-26 | 8/27: Not taken to Change Ingestion, Approved offline as per Alpna |  |  | 2025-08-26 | • Anafi Interim Solution for Invoicing and Production Order Changes • The meeting also addressed an interim solution for Anafi related to invoicing changes driven by the shift to SAP production orders and the phasing out of CIBR. The current design relying on CIBR will break as sites convert to S4 with production orders starting at R3. • Key aspects include: o Designing an end-to-end flow to trigger billing without Cyber. o A 3 to 4-week design effort involving E2E and other teams. o There aren't any expected conflicts with existing work and resources can absorb this task. o The solution is required for R3 go-live for Oregon, with subsequent sites at requiring this for R4 and R5. o Emphasis on leveraging existing designs with minor tweaks. | [5 empty] | Design | CL/OSC | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1100 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | High | 13. Security | 13.1 Security - ALL |  | 04. OTC IF | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | INT-CR1024, INT-CR1075 | NA | NA |  |  |  |  | Anafi | Anafi scope of work for Security & Controls | Scope of work for the Anafi Security & Controls design factored for Release 2.5 | As part of Anafi release 2.5, there are changes expected to multiple L3’s across OTC – OM, Logistics and MDG . Security & Controls team need to work on design, build, test and deployment for all the changes including regression testing for existing design for R2 and R3 (If any) | NA | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT%20Build%20CR_ANAFI%20scope%20of%20work%20for%20Security%20%26%20Controls.pptx?d=webda1343daa3489c9c5756edb9f2ed4d&csf=1&web=1&e=JGK5R3 |  | 1. Process Scope / Design Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-26 |  |  |  | 2025-08-26 | • The final major topic covered a change request for Anafi security and controls to support design, build, test, and deployment phases. This includes updates to order management and logistics subprocesses, business process controls, risk metrics, segregation of duties, and remediation activities. • Highlights: o Changes driven by pulling forward capabilities originally planned for R3, including a new plant setup (1074). o The work has commercial impact and requires additional resources. o Estimated resource need is 1.5 incremental Deloitte consultants from the current date through EOY'2025. There is no IAO funding approved to support this request today. o Debbie Whitely confirmed Intel BB resources will continue to be funded/absorbed within existing budgets. There is no IAO funded request for BB HC. o Discussions on funding and resource allocation are ongoing, with conditional approval to proceed with design and support work not including the incremental 1.5 incremental Deloitte consultants. o Coordination with conversion teams is pending to clarify business support needs. • AR - Alpna Gainda - Coordinate across conversion teams for a comprehensive roll-up of incremental resource funding requests by ww35.3 morning for the MRC pre-review. • AR - Jill Matalon - Determine if business support is needed from OTC-IF for conversion activities and ensure conversion resource implications are communicated to Anand Jha no later than ww35.3 morning for the MRC pre-review. Decision: Approved for design work, but not approved for incremental Deloitte consultant funding | [5 empty] | Design | CL/OSC | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1101 | Rejected |  | ERP | R5 (Release 5) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 03. FPR 07. FTS IF 09A. Master Data | eugene.celis@intel.com | E2E/Architecture — Satya Vajjala | FTS IF - Haritha Komma |  | INT-CR1915 | [7 empty] | SDL IF Factory Operation & Organization | SDL (Systems Development) underwent some organizational changes. | Most development will be for R5 intercept, except for SAP ME which Factory automation will need to prioritize for R3 development with resource constraint. W33 MRC approved that both will be supported using IF Applications. | R5 ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR_1101_R5_SDL%20Change%20Request.pptx?d=w91e2365aa918414a82f73ee4eab90d67&csf=1&web=1&e=JjXNr9 |  | 0. Request for Investigation |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-09-04 | To be reviewed offline | [9 empty] | Other | Not Assigned |  | Not Approved | 09, 2025 | 08, 2025 | 2025-08-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1102 | Rejected |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 03. FPR 04. OTC IF 06. PTP 07. FTS IF 09A. Master Data 10. Analytics | eugene.celis@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat |  | New Business Model to support worldwide shortage | TD Substrates Factory Business Model Change | No KDD | [5 empty] | TD Substrates Factory Business Model Change | TD Substrates factory from 100% TD Non-Revenue to becoming an OSAT in substrates business (assembly of semi-fg) in addition to support TD development. IT has unique and complex process flow. Need E2E flow - affecting multiple towers with new complexities: IF FTS, E2E, IF TD Substrates Factory Business Model Change OTC, P2P, FPR, Logistics, Master Data - Master Data: Need new layer of substrates core (blank panel, partial panel (receiving UNBW), semi-finish substrates, Finish Substrates) IF FTS: MRP Planning parameter config, WS-MARS-SMH-S4 integration for REV lots, Shipping using ISM for Semi-FG subs to Ext Supplier to S4, P2P: Procurement potential new process flow; supplier/B2B integration from IF to Supplier/Customer FRP: Finance costing and accounting options- Intel gets discounted price for mfg service or service fee with supplier; integration with P2P (TBD) IF OTC: Complex flow  potential to-be flow (IFS Alignment with Supplier and IF Subs Factory  Customer POIF SOPO from IF to supplier Boundary App: iCATCH (macro to Workstream shipment)- potentially no change, but need to revisit with shipping design. | New Business Model to support worldwide shortage to bring new Substrates technology to support IFS and IP future packaging needs. | Need E2E resource and x-tower interdependencies. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR_1102%20R3_TD%20Substrates%20Factory%20Change%20Request.pptx?d=wc2fd7fd5a7c140ec9f0d5092b3e37885&csf=1&web=1&e=7OXCYx |  | 0. Request for Investigation |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2025-08-28 | 8/28 CR Ingestion meeting: Was not presented (Ran out of Time) | 2025-10-30 | - E2E to walk the towers through flow - AR: Call out what will be automated versus what will be manual processes - AR: Log as open design and track - Aishwarya | 2025-08-29 | • Decision - Not approved o Prioritization of Anafi and other critical work through WW38/39. A "light" E2E TD substrates factory analysis approved post WW38/39 timeframe to be led by Todd Smith with only key SMEs to determine if standard SAP processes can support the factory’s needs for R3 or continue manual processes and defer changes to later releases. | 2025-10-28 | o From WW35.5 Change Request Meeting Minutes: CR1102 was Rejected - Prioritization of Anafi and other critical work. A "light" E2E TD substrates factory analysis approved post WW38/39 timeframe with only key SMEs to determine if standard SAP processes can support the factory’s needs for R3 or continue manual processes and defer changes to later releases. o Was flagged as a potential Master Data Risk but Candi Linnell and Eugene Celis confirmed no technical design change required; risk for ITC2 reduced. o Candi advised that this is no longer a Design Open. o ww44.2 CR Meeting Candice Linnell and Eugene Celis advised this is no longer a design open. The teams will do this manually. |  |  |  | Other | CL/OSC | 2025-10-28 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1103 | Rejected |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 04. OTC IF 06. PTP 07. FTS IF | sunil.k.parida@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat |  | NA | NA | NA | [5 empty] | Bailment returns (IF to IFS and IF to IP) | Bailment returns (IF to IFS and IF to IP) | Bailment returns (IF to IFS and IF to IP) | Yes | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1103_E2E_OTC_PTP_FTS_MDG_Change%20Request%20for%20Bailment%20returns%20design.pptx?d=we51b71e1b0dd4b68b0b542d63e836c70&csf=1&web=1&e=QKdWxi |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | Yes |  | 2025-08-28 | o AR: Pull in the teams that are impacted, and a T-Shirt size of how many people are needed and for how long. @K P, Murthy | [9 empty] | Design | CL/OSC |  | Missing Review Date for Approval Level | 08, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1104 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Tse Pei Tan | [6 empty] | INC14854308 | Delivered |  |  |  | ​ New requirement to add Internet Comment fields into Backlog report | ​ New requirement to add Internet Comment fields into Backlog report | After the R2 go-live, there is a requirement to add Internet Comment fields to ECA Backlog Report.​ CBA require to set the Free of Charge Sales Order if customer denote Engineering in the B2B pip.​ Internet comments are used for Customer T to identifying Prod Vs Eng order. ​ B2B does not have report for CBA.​ ECA backlog report have been identified as possible report for CBA reference. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1104%20-%20Internet%20Comment%20fields%20add%20to%20Backlog%20Report.pptx?d=w9ba09fb8b81b499898e5b2885a7acd90&csf=1&web=1&e=3EIAn6 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [9 empty] | 26 |  |  |  | 0 | 26 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-05 | Approved in Hypercare CR meeting with OSC | [9 empty] | Build | Tower | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | ckumarsrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1105 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics | Tse Pei Tan | [6 empty] | INC14854201 | Delivered |  |  |  | ​New requirement to add historical data to ECA reports | ​New requirement to add historical data to ECA reports | After the R2 go-live, there is a requirement to add historical data to ECA reports to enable the business to conduct analysis on time period ranges which extend prior to R2 go-live.​ We are needing historical data to enable sales discussion for all areas of the business from revenue, planning, billings.​ Historical data is required combines in OM and Billings Reports,(Backlog, KPI dashboard, Revenue Report, etc.​ Historical data going back to SAP ECC day 1 for IFS business. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B18E5C085-187D-43C7-89DA-914CAC6787FF%7D&file=CRXXXX%20-%20Historical%20Data%20incorporated%20into%20ECA%20reports.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [9 empty] | 80 |  |  |  | 0 | 80 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-05 | Approved in Hypercare CR meeting with OSC | [9 empty] | Build | Tower | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | ckumarsrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1106 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli |  | OTC IF - Angela Laskowski |  |  |  |  | INC14853440 | Delivered |  |  |  | To enhance operational efficiency and support evolving business requirements, the following user roles will be updated to include additional transaction capabilities. Specifically, these roles will be granted access to the designated SAP transaction codes (T.codes) and/or relevant Fiori applications. Roles:?OTC IF - Order to Cash - Display Only?OTC IF - CBA Business Manager?OTC IF - Customer Business Analyst?OTC IF - Business Analyst/Program Manager Additional Transactions/Fiori Apps to add: ?List Incomplete Sales Orders - V.02 List Incomplete Sales Contracts - V.06?Sales Orders Blocked for Delivery-V.14?Release Customer Expected Price-V.25 | Expanding access will allow users to execute additional transactions, utilize enhanced functionalities, and leverage modern user interfaces provided by Fiori apps. | Expanding SAP roles to include additional transaction codes and Fiori apps enables users to work more efficiently and accurately, reducing process bottlenecks and errors. This enhancement drives measurable ROI through time savings, lower support costs, and improved compliance, ultimately supporting business growth and agility. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1106_Allow%20CBA%20to%20have%20access%20for%20given%20Fiori%20Apps.pptx?d=w68774e1f0a4145ec95eeef9dc7ea5cdb&csf=1&web=1&e=m2cgP1 |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [11 empty] | 10 |  | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-26 | 8/26: Approved in R2 Hypercare Change Ingestion | [9 empty] | Build | Tower | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1107 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Custom API for Good consumptions | To introduces Custom API approach to capture Batch Attribute values and Goods Receipt against Text PO | Introduction of Custom API approach for Batch Attribute Values: Using Std. API, we could post only one Characteristic attribute at once and we may need to call multiple Std. API calls to post multiple Characteristics. Using Custom API, we could call Std BAPI internally in S4 system and post multiple attribute values at once. Introduction of Custom API for Goods Receipt against Text PO: If a Text PO contains multiple line items, whenever for the 1st line item, if the “Delivery Complete Indicator” is set, then automatically post the remaining line items Goods Receipt as well. Introduction of custom logic to fetch “Manufacture Date” attribute value of the header material from consumption batch(s). |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/Approval%20for%20FTS-IP_%20CR%20Intake%20Forms_INT-CR1107_INT-CR1121.pdf?csf=1&web=1&e=tlQKQm | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1107%20Introduction%20of%20Custom%20API%20to%20post%20Batch%20Attribute%20Values%20and%20Goods%20Receipt%20against%20Text%20PO%20in%20IP%20SAP%20S4%20System%E2%80%8B.pptx?d=w354c1c950517483381a25760a623e11f&csf=1&web=1&e=pemvkO |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | 8 |  | 60 | [5 empty] | 108 |  |  |  |  | 0 | 108 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0492, FTSI0724, FTSI0725 | 3 | FTSI0492, FTSI0724, FTSI0725 | 3 |  | 0 |  | 0 | N/A |  | 2026-02-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-04 | o This request is for posting goods receipt based on first PO and then to check inventory status and release lots automatically prior to posting consumption. o There is no way to meet business requirement with standard SAP process. o SMH is not a concern as they have planned for this work and created a placeholder for it. Therefore, there will not be much impact, and the team will make ITC1. o AR: Add SMH plan to complete the CR into the deck - @Lingam, Sekhar o AR: Add in the details regarding what is required to be delivered by 9/15 - @Lingam, Sekhar o Dollar Impact is 8 US Design hours. | [9 empty] | Build | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1108 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Remnants process design changes | To provide visibility to remnants in IP SAP S4 System to support upstream planning processes | Limitation of OSATs to provide Remnant identifier in the last shipment of a production order. To mitigate this, the following processes need to be implemented in SMH and IP SAP S4 System. Receive 7B1 – SPLIT signal from OSATs/IF (for aligned operations. Ex: 8500 for Ext OSATs). SMH to update lot-order relationship table. The split signals will not be sent to S/4 from SMH Update the Production order quantities (reduce the quantity of the order merged from and increase the quantity of the order merged to) based on 7B1 – MERGE signal received from OSATs/IF (for aligned operations. Ex: 8500 for Ext OSATs) Remnants are visible as open WIP on production order. Order gets DLV status if within under delivery tolerance limits |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/FTS-IP_%20CR%20INT-CR1108%20and%20INT-CR1109.pdf?csf=1&web=1&e=BVMrrs | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1108_Remnants%20Splits%20and%20Merges%20Updated%20%20Process%20Alignment%20.pptx?d=wbbc174b651514728a1baec888a4d44c3&csf=1&web=1&e=0vMi0I | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  |  | High | 0 | 48 | [12 empty] | 0 | 0 | N/A | Yes |  | 1 | FTSI1631 |  | FTSI1631 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1140, FTSI1142 |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-04 | o This request is a new RICEFW due to process change. o These changes will give the team 120 hour buffer for other CR’s. o This is for external OSAT’s, so there is no change currently for IF remnants. o Dollar Impact is 48 US Design hours. | [9 empty] | Other | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1109 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP 17. B-App | Sekhar Lingam | [8 empty] | 59283 | PDF Sapience Manufacturing Hub Integration Platform - IP |  | Reversal Transactions for 7B1 interfaces | To capture the cancellation/reversal requirements for FTS-IP Manufacturing objects. | With the existing OSAT/IF processes, there is a need to automate the reversals for 7B1 transactions associated with production orders. Introduction of cancellation/reversal transactions in the scope for FTS-IP from e2open. Consistent model between CIBR and IP SAP S4 System regarding transaction cancellations. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/FTS-IP_%20CR%20INT-CR1108%20and%20INT-CR1109.pdf?csf=1&web=1&e=BVMrrs | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1109_Introduction%20of%20Reversal%20Transactions%20for%20FTS-IP%20Manufacturing%20Objects%20from%20e2open%20to%20IP%20SAP%20S4%20System.pptx?d=w0eecdd63a7824017b26da9ed18b2e420&csf=1&web=1&e=Kdzx9P |  | 4. Change to Existing RICEFW / ECA/ Build Object | M-100-070 |  |  | High | 0 | 24 |  | 60 | [5 empty] | 99 |  |  |  |  | 0 | 99 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0492, FTSI0491, FTSI0725 | 3 | FTSI0492, FTSI0491, FTSI0725 | 3 |  | 0 |  | 0 | N/A |  | 2026-02-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-04 | o In the initial stages, the team didn’t consider reversals because it was thought to be exceptions.  However, the volume was too high to utilize the manual method. o IF is already using this, and IP will use the same cadence. o This will be for ITC2, and ITC1 will be tested manually. o Dollar Impact is 24 US design hours. |  |  | 2025-09-05 | • Proposal to automate the reversal of various transactions (goods consumption, receipts, scrap/yield confirmations, auto confirmations) across OSATs and Intel Foundry. • Initially considered a manual exception process, deeper analysis revealed high transaction volumes: ~250/month from external OSATs and ~1000/month from Intel Foundry, making manual handling unsustainable. • Stakeholders including GEMS, Intel Foundry, PDF, SMH, IT leads, and GPOs aligned on automating and standardizing the reversal process across systems (IF, Cyber, etc.). • Effort estimate: o ~99 hours for one new custom API and technical unit testing. o Functional testing effort primarily falls on SMH. o Minor contributions from ECA (7B1 straddle) and APZ. o Mapping files will be shared with SMS team in parallel to functional spec development. • Target: Functional spec completion in Sprint 18, possibly spilling into Sprint 19. • Testing: Manual testing possible in ITC1; full automation planned for ITC2. • Stef Maxey and Kumar Vytla supported the plan, noting that while manual testing is feasible short-term, automation is necessary for scalability. • Decision: Approved, confirming no impact to PDF commitments for ITC1. | [5 empty] | Build | CL/OSC | 2025-09-05 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Hypercare) | R2 Hypercare | INT-CR1110 | Approved |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics | Vinay Kumar Khandelwal | OTC — Kevin Brown | OTC IF - Angela Laskowski |  |  |  |  | INC14826298 | Delivered |  |  |  | Change in logic for determining Original CDD | Aligned on the requirement to keep the Original CDD intact in case of orders changes/block unless planners specifically remove the original CDD. Current system behavior resets the original CDD when any schedule line delivery block is applied (including block 20) | If this change is not implemented then it will cause reporting to not be in sync and give the wrong information |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B08c7a734-60c5-49e3-8b46-acbf5b9bec32%7D&action=edit&wdPreviousSession=d07e76fa-72a2-9a31-93b7-6e01235b865f |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 18 |  |  |  |  | 0 | 18 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0339 | 1 | OTCE0339 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-08-26 | 8/26: Approved in R2 Hypercare Change Ingestion | [9 empty] | Build | Tower | 2025-08-26 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1111 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | hgore@deloitte.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  |  | NA | [6 empty] | FPR - Cancellation CR for RICEFW - FPRR1492 - Conversion of WIP value as per Cost Component structure in S4 - Front End IF | FPR - Cancellation CR for RICEFW - FPRR1492 - Conversion of WIP value as per Cost Component structure in S4 - Front End IF | New CR1009 created for COGS split required for WIP. Hence this RICEF need to be cancelled | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1111/Re_%20INT-CR1111%20for%20Cancellation%20of%20FPRR1492%20.msg?csf=1&web=1&e=Sb5y4g |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRR1492 | FPRE1620_IP, FPRE1620_IF |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-26 | 0 | < 15 Days | hgore@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1112 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF |  | OTC — Kevin Brown | OTC IF - Angela Laskowski | [8 empty] | Anafi | Data conversion - Anafi | Scope of work for the Anafi design factored for Release 2.5. for Data Conversion ( PILOT + INTERIM) | Data Conversion will be required to migrate key information, like Sales Orders, Inventory and batch information from legacy systems to SAP S4 as a part of the cutover activities |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT%20Build%20CR1112_Data%20Conversion%20ANAFI%20.pptx?d=weaa8cd853fce4743968310dd611d8c14&csf=1&web=1&e=iQ7wAG |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3144 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-28 | o AR: Call out its not only for pilot but for all products @Vishwanathan, Ravi o AR: Confirm the effort slide and that GTS is not included. @Vishwanathan, Ravi |  |  | 2025-08-29 | • Decision - Approved o The Anafi data conversion scope was approved to proceed, with the team agreeing to move forward with the implementation as presented. o Any additional CRs related to GTS will be addressed separately once further evaluation is complete. | [5 empty] | Design | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-27 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1113 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | High | 10. Analytics | 10.1 Analytics - ALL |  | 09A. Master Data 10. Analytics | Jill Matalon | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  |  |  | Anafi | Anafi scope of work for Data (CDI) | Data Scope of work for the Anafi design factored for Dec'2025 Go Live. | To support onboarding of Anafi customers, there are data changes identified across master data (ROO and ROR), Supply planning (SPAN), additional table ingestion from S/4 and ECA design for ERO table, data flow between ECA and HANA and finally a custom solution to determine CMAD for ATP process. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT%20Build%20CRXXXX_ANAFI%20Data%20CDI%20scope%20for%20OTC.pptx?d=w0c103c56a1024fcca1492d438d7c0593&csf=1&web=1&e=hvIsEc |  | 1. Process Scope / Design Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-28 | o CR regarding the ECA scope needs to have approval from Mike since it is being funded by IAO. |  |  | 2025-08-29 | • Decision - Not approved o The team agreed to provide a more complete estimate and revisit the topic in WW39. | 2025-08-29 | Received email from Stacee that this was approved during the CR Meeting: Sunil, I went back again and re-reviewed every sentence. The first Anafi CR was approved and then we said we wouldn’t take up time reviewing the next Anafi CR (CR1113) and that we would follow-up with a deep dive on Anafi. What I missed is despite stating that we would not review CR1113 the statement was made that the CR is already in progress, funded outside of IAO, and the direction was to keep moving. I will follow up and get the CR log updated to reflect CR1113 is approved. Regards, Stacee |  |  |  | Design | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1114 | Approved |  | SCP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.1 OTC IF - ALL |  | 04. OTC IF 07. FTS IF | kelley.way@intel.com | OTC — Kevin Brown | FTS IF - Haritha Komma |  | No POs for Anafi Straddle | Business Process Change | N/A |  |  |  |  | Anafi | No POs for Anafi Straddle | Support Anafi products without POs in SAP ECC for the Anafi straddle period (WW43-52’25); covering HVM and Revenue Engineering. | With a small window of 9 weeks and a Finance solution to recognize the revenue from Anafi, the lift to get them setup in SAP ECC doesn’t constitute the need for POs. Anafi will move directly to SAP S4 in WW01’26 as an external customer. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared Documents/2.1 Program Mgt Channel/CCB/Change Requests/Pending/IAO R3 CR - No POs for Anafi Design Forum WW34%2725.pptx?d=wababcc60b8494a0ab619865c9c393396&csf=1&web=1 |  | 1. Process Scope / Design Change |  | Yes |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-04 | o Given that straddle will be a short 10 week window prior to go-live, and the SAP ECC set up will is not worth the effort. o The team has approximated that it will take around 160 hours for the setup, and all stakeholders have agreed to bypass this and perform without PO’s. o PO’s are still in OneMPS. Planning is aligned, and Blue Yonder will continue to load the forecast. | [9 empty] | Design | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1115 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) R5 (Release 5) | High | 06. PTP | 6.1 PTP - ALL |  | 02. E2E Process Integration 03. FPR 04. OTC IF 06. PTP 08. FTS IP 09A. Master Data 15. Cutover 16. Testing | krishna.subramanian@intel.com | E2E/Architecture — Satya Vajjala | PTP - Richard Taylor |  | none | none | none | [5 empty] | Bailed Material Straddle Architecture R3-R4, R4-R5 | Bailed material straddle architecture definition to handle IP bailment to IF sites which will be partly S4 and partly ECC until R5 | R3 design is defined for S4. IP is big bang, while IF is not. Hence many HVM locations will still be on ECC when R3 goes live. IP bailment of material to such locations need to be managed through ECC straddle design for non valuated material PO creation, GR at IF 3PL, STO between S4 and ECC sites and bailment return process. This will also have ‘conversion’ implications to revalue material in ECC to $0 and convert them into IP S4. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CRxxxx%20%E2%80%93%20Bailed%20Material%20Straddle%20Architecture%20R3-R4,.pptx?d=wb90d8268ecc941858e0eaf2e104b427d&csf=1&web=1&e=FfaAnw | New Requirement / Scope | 1. Process Scope / Design Change |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-08-28 |  |  |  | 2025-08-29 | • The build materials straddle design addresses scenarios involving material movements between IP, IF, and ECC sites across releases R3 to R5, including complex logistics with 3PL providers. • The team is working on detailed designs for 10+ scenarios, including process changes and technical impacts. The assessment is expected to conclude by WW39, aligning with ITC2 timelines. The straddle scenarios are not currently in the IAO Designs Opens Tracker. • The team emphasized that only missed or new issues will generate change requests, with ongoing efforts to integrate these straddles into the overall design process. No technical build or process changes are being implemented yet; this is an assessment phase. Actual change requests for build will follow the design is finalized. • AR: Alpna Gainda add all Bailed Material Straddle Scenarios to the IAO Design Open Tracker, with weekly updates for visibility to progress and gaps. • Decision - Approved to proceed with assessment o This item is currently in assessment and design phase. No formal CR approval yet; the team is working on scenarios and will submit CRs after finalizing the design and fit-gap analysis. | [5 empty] | Design | CL/OSC | 2025-08-29 | 08, 2025 | 08, 2025 | 08, 2025 | 2025-08-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
R2m (October 2025) | R2 Hypercare | INT-CR1116 | Approved |  | ERP | R2 Hypercare | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Soumik Sil | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  |  |  |  | INC14918377 | Work In Progress |  |  |  | Time log for CFIN table to support C14 reporting | Implement time dependent Profit Center mapping in S4 CFIN environment to support C14 reporting and Trial Balance reconciliation | Out of Box, Profit Center mapping in Central Finance (CFIN) does not support time dependency. Consequently, any updates to Profit Center mapping are applied immediately, and transactions replicated from ECC reflect the most recent mapping.​ This approach has several implications:​ Transactions occurring during overlapping periods are posted to the new Profit Center. ​ Historical reporting for external and segment reports using C14 (reorganization) is inaccurate due to the absence of time-dependent mapping. ​ Trial Balance reconciliation reports cannot be generated for historical periods. ​ FICO reconciliation reports (ECC to CFIN) are impacted.​ | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1116/Re_%20R2-Hypercare_New%20CR%20-%20Implement%20time%20dependent%20Profit%20Center%20Mapping%20in%20CFIN.msg?csf=1&web=1&e=MCCaUe | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1116%20-%20%20Time%20log%20for%20CFIN%20table%20to%20support%20C14%20reporting.pptx?d=wd9de6ab0c5154c03a62cec277d5d9915&csf=1&web=1&e=myNJHx |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [7 empty] | 80 | [5 empty] | 0 | 80 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-16 | o This is to implement time-dependency to the profit center; there is no standard solution, so a custom table is required  This is a BADI work, and it is an enhancement | [9 empty] | Other | Tower | 2025-09-16 | 09, 2025 | 09, 2025 | 08, 2025 | 2025-08-28 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1 | INT-CR1117 | New |  | SCP | R3 (Release 3) | Low | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF | priya.c@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | "Publish" check box doesn't check after User publish to PDH | Enable publish check box after User publish to PDH | New publication process from Mapps to PDH for R2 | No impact | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Change%20ID_FTS_PublishCheckbox.pptx?d=w8eaee33f14734a5da36740c05bd52a54&csf=1&web=1&e=gDmIxi |  | 1. Process Scope / Design Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 08, 2025 | 2025-08-29 | 222 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1118 | Approved |  | ERP | R3 (Release 3) | Low | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Pabbisetty Harshavardhan | [11 empty] | Descoping PTPI0104_IF/IP: PO Header status interface between Ariba & S/4 | Need to descope PTPI0104_IF/IP | Required PO Header status updates are already taken care as part of GR Carbon copy interface (PTPI0463_IF/IP) for Ariba Network enabled suppliers. Also, it was confirmed by Jorge & Luis that there will be no impact of descoping this object for Ariba Pos created for non-Ariba enabled suppliers (Websuite). |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1118/EXT%20RE%20Descoping%20of%20PTPI0104_IFIP%20PO%20header%20update.msg?csf=1&web=1&e=2myASc |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0104_IF, PTPI0104_IP |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-03 | [10 empty] | Other | Tower | 2025-09-03 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-01 | 0 | < 15 Days | pabharshavardhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1119 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Deepanshu Lnu | [11 empty] | Descoping PTPI0142_IP_IF : Supplier commits for SA. | Need to descope PTPI0142_IF/IP | Per IAO E2E design, scheduling agreements (SAs) are not expected to be used by any biz group for regular operations. Due to that, it was aligned to descope this interface . |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0142_IP, PTPI0142_IF | N/A |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-08 | [10 empty] | Other | Tower | 2025-10-08 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-01 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1120 | Approved | Presenter: Sekhar Missing: new enhancement complexity, RICEFW ID's and new dates, and ITC2 | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP 09A. Master Data | Sekhar Lingam | [11 empty] | Text PO changes in Build Instructions & automation of Routing and production version for ext OSAT | To trigger Text PO changes from into Build Instructions IDoc to send to External Suppliers and to Introduce Creation of Routing and Prod Version based on SPEED data | Approved. Text PO Change Requirement Rationale: It is a business requirement to capture the Text PO changes related to Commercial pricing data and Quantity/date adjustments in the Build Instructions IDoc to send them to External Suppliers. MDG Team Requirement Rationale: To automate the creation of Routings and PVs based on the creation of SPEED BoM in the IP SAP S4 HANA System. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1120_To%20trigger%20Text%20PO%20changes%20into%20Build%20Instructions%20IDoc%20to%20send%20to%20External%20Suppliers%20and%20to%20Introduce%20Creation%20of%20Routing%20and%20Prod%20Version%20based%20on%20SPEED%20data.pptx?d=w55c58201bdaa415cb44bc470878afeaf&csf=1&web=1&e=T9Ex7j |  | 4. Change to Existing RICEFW / ECA/ Build Object | M-090-110, M-090-130 |  |  |  | 0 |  |  | 20 | [5 empty] | 50 |  | 90 |  |  | 0 | 140 | Tech - S/4 | No |  | 0 | N/A | 3157 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0268, DATI0927_IP | 2 | FTSI0268, DATI0927_IP | 2 |  | 0 |  | 0 | N/A |  | 2026-03-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-25 | o There is a manual workaround since this will not come in until ITC2.  Someone will have to manually key in the information, and text PO changes will be sent via email communication o We eventually want this automation because manual is limited. o This is for external OSATs only. o AR: Refine tech effort - @Lingam, Sekhar |  |  | 2025-10-03 | • When there is a change in the text PO (Purchase Order) associated with a production order, the system must resend the updated text PO to the external OSAT (Outsourced Semiconductor Assembly and Test) partner. • The team is automating the creation of routings and production versions for external routings in IPS4. • Currently, when a routing is created, a purchase info record (PIR) is attached, which contains service charge details. By default, the system picks a standard PIR. • The enhancement introduces custom logic to select the correct PIR based on the specific MM ID, as designed by the P2P team. • This automation will be ready for ITC2. For ITC1, a manual workaround is required: testers must check and update the PIR price in master data before running test scripts. • The enhancement is considered high complexity (estimated at 160 hours) due to the routing logic, but complexity may be reduced if requirements are clarified. • No resource contention is expected; the plan is to test manually in ITC1 and automate in ITC2. • Some objects will be deferred to ITC2 to prioritize this automation for ITC1. • Decision: Approved, with a note to document which objects are deferred and why. | [5 empty] | Build | CL/OSC | 2025-10-03 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-02 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1121 | Rejected |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | DLCP Bin Splits | To capture BIN Splits and their Quantities as Batch Characteristics for SORT UPI Stage | DLCP requirement rationale: It is a business requirement to capture BIN Splits IDs and Quantities as Batch Characteristic Values for SORT UPI stage |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/Approval%20for%20FTS-IP_%20CR%20Intake%20Forms_INT-CR1107_INT-CR1121.pdf?csf=1&web=1&e=tlQKQm | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1121_To%20capture%20BIN%20Splits%20and%20their%20Quantities%20as%20Batch%20Characteristics%20for%20SORT%20UPI.pptx?d=w93e0bb10f7fa4270af52cbf7ba2a715c&csf=1&web=1&e=V2vCX9 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Low | 0 | 24 |  | 12 | [5 empty] | 18 |  |  |  |  | 0 | 18 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0724 | 1 | FTSI0724 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | No | No | 2025-09-04 | o The S4 effort is to capture the documentation. The team is aiming to complete this in 2 sprints and is confident that they will be ready for ITC1. o Dollar Impact is 24 US design hours. | [8 empty] | Confirmed by Sekhar Lingam and Venkata Kamieni to be cancelled. | Build | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-02 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1122 | Cancelled |  | ERP |  | Medium | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Validation and action while updating Unit Credit Price in Returns Order. | Validation and action while updating Unit Credit Price in Returns Order. | While updating the Unit Credit Price in Returns Order at time below validations and actions needs to done. Check if Credit Memo is created or not. If Credit Memo is created, then don’t update the price in Returns order. If Credit Memo is not created, then check Credit Memo Request is created or not. If Credit Memo request is created, then apply Reason of Rejection on Credit Memo and update the price in returns order by changing item category to ZRNN (free of charge item). |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1122_OTC_IP_Validation%20and%20action%20while%20updating%20Unit%20Credit%20Price%20in%20Returns%20Order.pptx?d=wd09c942b0b644bb0b9635494b428e148&csf=1&web=1&e=XTVzCn |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Pamod Kalli Srinivas that this CR is less than 40 hours of tech effort. Therefore, the CR will be moved to the Build CR Log. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-02 | 0 | < 15 Days | sbharathalkude@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1123 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 09A. Master Data 10. Analytics 17. B-App | isaac.utter@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | Not Applicable | Not applicable | Not Applicable | [5 empty] | Persisting PV Straddle | In the goal state design IF SMH will persist the PV assignment on the Production Orders​ On the IF side there is a Production Order for every lot in WIP​ SMH will only be going live for two Plants at R3​ Due to this, SAP will not have a Production Orders at all sites until R5​ We need a place that can persist the PV until R5​ It was determined that ECA would be the best place to do this | This was a gap in the Straddle design( R3-R4) | ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1123%20-%20Persisting%20PV%20Straddle.pptx?d=w2870ee5c9e0841d9a39d2dad8e5815ec&csf=1&web=1&e=LdhGsf | Design / Build Gap | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 1 | ECAFTSIFV6364 |  |  | 0 |  | 0 | ECAFTSIFV6364 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-04 | o This will impact all WA and SCX flow, and it will be a P1 risk o AR: Include the list of conflicts, tradeoffs, and decision owners - @Shukla, Mohal |  |  | 2025-09-05 | • In R5, PV will be stored on the production order via SMH and SAP. However, due to limited site go-lives in R3, ECA was proposed as the best alternative for persisting PV. • This is a core functionality. Found while doing the detailed design for the straddle. • Design Decision: The team debated whether the design decision was finalized. Rebecca Verette emphasized the need for a formal design review before approving the CR. Isaac Utter confirmed the decision was made after consulting multiple groups. • Effort Estimate: Estimated at 400 hours over 10 weeks. Isaac noted the team wouldn’t be fully dedicated to this and highlighted potential trade-offs, such as delaying certain inventory reports to ITC2. • Concerns Raised: o Kumar Vytla expressed concern about descoping items from ITC1 to ITC2. o Uzma Ahmed and Roman Vorel stressed the need for structured prioritization and ingestion processes. • Decision: The CR was not approved. A cohesive plan and full team alignment are required before reconsideration. The team will bring the CR back ww37.5. • AR - Isaac Utter - Route the design decision through the Monday design review meeting managed by Aishwarya Bhat to ensure cross-functional alignment. • AR - Isaac Utter - Work with Kumar Vytla and Sunil Parida to assess trade-offs and competing priorities. Identify which ITC1 items can be delayed or descoped to accommodate the PV straddle work. | 2025-09-12 | • This CR/work is being prioritized over other CRs due to its foundational importance for testing and go-live readiness. • Trade-offs were made; IDW reports and IF consumption views will be deferred to ITC2/ITC3 to free up ~1000 hours for this CR (~800 hours required). • Alignment confirmed among GPOs for the trade-offs including Kumar Vytla, Rick Yamada, and Rebecca Verette. Kumar agreed that manual workarounds are feasible for the deprioritized items in the interim. • The team provided advance notice that additional large CRs are coming and that future trade-off decisions will be required. The Persisting PV Straddle is the current top priority CR. • Decision: Approved |  |  |  | Design | CL/OSC | 2025-09-12 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1124 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 03. FPR 06. PTP | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | NA | NA | NA | [5 empty] | Sprint 17 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 17 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | No |  | NA | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-10 | [10 empty] | Other | Tower | 2025-09-10 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1126 | Approved | Chandra Elancheran | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Nisa Khatun | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | CR for Sales organization Transition AM03 to IN01 | To support Intel’s strategic initiative to differentiate India revenue streams, a new Sales Organization—IN01—is being established under Company Code LE15. This organization will be the replication of existing structure of AM03. During the conversion process, the following objects will be impacted and require careful migration: Open Sales Orders: All relevant open orders for selected customers will be reassigned to IN01. Customer-Material Info Records (CMIR): CMIRs will be updated to reflect the new Sales Organization for the relevant customers. Output Conditions: Output condition records will be reviewed and adjusted to support IN01. DH Table Entries: Necessary DH Table data will be migrated accordingly. Pricing Conditions: Prices under AM03 for specific customers to be moved into IN01. | Enable India revenue differentiation in S/4HANA by moving select customers from AM03 to IN01. Scope: 16 Sold-to Parties 22 Ship-to Parties 6 Payers Impacted objects: CMIR (OTCC0564), DH Table (OTCE0795), Open Sales Orders (OTCC0563), Output Conditions (OTCC0636), Pricing Conditions (OTCC0717) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1126%20for%20Sales%20organization%20Transition%20AM03%20to%20IN01.pptx?d=wf2565363fa804b479031bd7a01c861e7&csf=1&web=1&e=hpPiwj |  | 4. Change to Existing RICEFW / ECA/ Build Object | O-020-020 |  |  |  | 0 |  |  | 85 | [7 empty] | 237 |  |  | 0 | 237 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0564, OTCE0795, OTCC0563, OTCC0636, OTCC0717, DATC0179_IP​, DATC0184_IP​, DATE0313_IP, DATC0074_IP​ | 9 | OTCC0564, OTCE0795, OTCC0563, OTCC0636, OTCC0717, DATC0179_IP​, DATC0184_IP​, DATE0313_IP, DATC0074_IP​ | 9 |  | 0 |  | 0 | N/A |  | 2025-11-21 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o AR: Fix Schedule to deliver in MC2 - @Elancheran, Chandrakanth o There are no workarounds needed since this is a new sales org. | [9 empty] | Build | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-03 | 0 | < 15 Days | nikhatun@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1127 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Deepanshu Lnu | [11 empty] | need to change the logic for receiving site | There is a requirement change from Business to change the logic for Receving site for PTPI0140_IP_IF |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-03 | 217 | > 30 Days | deepanlnu@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Aug 2025) | N/A | INT-CR1128 | Approved |  | Other (Boundary Apps, Data Transformation) | R2 (Release 2) | Medium | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 17. B-App | dana.kalev@intel.com | Data & Analytics - Rebecca Verette | E2E - Aishwarya Bhat |  | Duplicate actuals not accounted for in transition. | NA | NA | [5 empty] | Approved: OTD Report Adjustment: Exclude Duplicate Lots During Transition Period | OTD (On-Time Delivery) Report (formerly POWER) to exclude duplicate lots during transition period. | During the transition period, there is a potential for WIP double counting that could impact all process flows, especially F3B products due to change to new commit point that adds +5-7 days of CT. | No impact to schedule. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/CR%20for%20OTD%20Report%20Adjustment%20Exclude%20Duplicate%20Lots%20During%20Transition%20Period.pptx?d=wd0c7e73c4b2f4da68d421e94fc8fc928&csf=1&web=1&e=K4rcgQ |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | [11 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 09, 2025 | 2025-09-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1129 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 11. Technology | [12 empty] | API Issue | 1. Enhancement to delete The standard tables ESH_SR_LTXT and ESH_SR_TXT_OBJ are utilized to replicate long texts from the SAP Script tables STXH and STXL. 2. Enhancement is to create a Custom field in standard API in API_PURCHAEORDER_2, API_PURCHASECONTRACT_PROCESS_SRV VERSION 2 & API_PURCHASEREQUISITION_2 (OData v4) to capture Line item Amount in USD. Also need add new filed in API_PURCHAEORDER_2 for Incoterm Location ID in API | 1. Enhancement to delete The standard tables ESH_SR_LTXT and ESH_SR_TXT_OBJ are utilized to replicate long texts from the SAP Script tables STXH and STXL. After deleting all entries from ESH_SR_LTXT and ESH_SR_TXT_OBJ, running the report ESH_SR_LTXT_REPLICATE in Update Run mode will repopulate these tables. Which allow to capture custom Text Id in API_PURCHASECONTRACT_PROCESS_SRV version 2, API_PURCHASEORDER_PROCESS_SRV to create, update Custom Text id. 2. As discussed with SAP, to facilitate the conversion of local currency amounts into USD, SAP has recommended the use of the function module CONVERT_TO_LOCAL_CURRENCY. To meet the BAPP requirement for retrieving the line item USD amount details of Purchase Orders, Purchase Contracts, and Purchase Requisitions via the APIs API_PURCHASEORDER_2, API_PURCHASECONTRACT_PROCESS_SRV Version 2, and API_PURCHASEREQUISITION_2 (OData v4), it is necessary to introduce a custom field in these APIs. This custom field will capture the line-item amount in USD, in addition to the existing local currency value. Also need to add new filed Incoterm Location ID as it is not available in standard API_PURCHASEORDER_2 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR1129_PTP_IF_API%20Issue.pptx?d=w85ddb2cdff8d42d8b4c2c9fb99a65e03&csf=1&web=1&e=81T9s3 |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | PTPE1622, PTPE1621 |  | PTPE1622, PTPE1621 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-04 | o There are 2 parts to the request: Purchase order creation/change and contract creation/change – 2 API’s  For the first part, there was a standard SAP program that works for the custom text population; it will delete entries from all tables and re-populate.  For the second part, standard SAP needs to have a custom change to send to the Boundary apps. o This will solve the issues with 24 objects in FUT  Effort is low for both of them, and the work will be done for ITC1.  FS has started o AR: Align with Chris and Architects to ensure that the approach is valid - @K P, Murthy o AR: Send CR to Uzma for approval of tech and OSC/enhancement review - @K P, Murthy | [9 empty] | Other | Tower | 2025-09-04 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1130 | Approved | Presenter: Lilibeth | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [8 empty] | WIINGS | Material Master Purchasing View WINGS requirement for Conversion | Data of Spares Parts needs to be converted from WINGS to S/4 system for Material Master Data Purchasing View | Development is completed for original Object and now it will be reopened to include changes for Spare Parts Conversion |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1130.pptx?d=wd0490036e00c4a8591fe92ec2d515a6f&csf=1&web=1&e=9nUBRO | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [10 empty] | 123 |  |  | 0 | 123 | Data Migration | Yes | S4 | 1 | DATC1637 |  | DATC1637 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0072_IP | 1 | DATC0072_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | [10 empty] | Other | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1131 | Approved | Presenter: Lilibeth | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [8 empty] | WIINGS | Material Master Accounting and Costing View WINGS requirement for Conversion | Data of Spares Parts needs to be converted from WINGS to S/4 system for Material Master Data Accounting and Costing View | Development is completed for original Object and now it will be reopened to include changes for Spare Parts Conversion |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1131.pptx?d=w671fa5d0db1d4e4697775ddf33829999&csf=1&web=1&e=WkpXAg | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [10 empty] | 123 |  |  | 0 | 123 | Data Migration | Yes | S4 | 1 | DATC1638 |  | DATC1638 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0075_IP | 1 | DATC0075_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | [10 empty] | Other | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1132 | Approved | Presenter: Lilibeth | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [8 empty] | WIINGS | Material Master Plant and Storage Location View WINGS requirement for Conversion | Data of Spares Parts needs to be converted from WINGS to S/4 system for Material Master Data Plant and Storage Location View | Development is completed for original Object and now it will be reopened to include changes for Spare Parts Conversion |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1132.pptx?d=w88c1d199953341579fdf164c5b2a2f84&csf=1&web=1&e=K3taqM | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [10 empty] | 123 |  |  | 0 | 123 | Data Migration | Yes | S4 | 1 | DATC1639 |  | DATC1639 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0070_IP | 1 | DATC0070_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | [10 empty] | Other | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1133 | Approved | Presenter: Lilibeth | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [8 empty] | WIINGS | Material Master MRP View WINGS requirement for Conversion | Data of Spares Parts needs to be converted from WINGS to S/4 system for Material Master Data MRP View View | Development is completed for original Object and now it will be reopened to include changes for Spare Parts Conversion |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1133.pptx?d=w143274eef71a4308829a38f4b54f8ea3&csf=1&web=1&e=oHCKMG | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [10 empty] | 123 |  |  | 0 | 123 | Data Migration | Yes | S4 | 1 | DATC1640 |  | DATC1640 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0071_IP | 1 | DATC0071_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | [10 empty] | Other | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
R2 (Hypercare) | R2 Hypercare | INT-CR1134 | Approved |  | Other (Boundary Apps, Data Transformation) | R2 Hypercare | High | 04. OTC IF | 4.1 OTC IF - ALL |  | 04. OTC IF 17. B-App | luis.a.garza@intel.com | BApps — Kelly Gerber | OTC IF - Angela Laskowski |  |  |  |  | INC14868886 | Work In Progress | 36518 | Foundry Services Summary Database |  | R2 Hypercare - FSSD Fab POLP Enhancement Scope/Schedule | Manual DNs (not PGIed) will have specific SO-Lots pegged at the time of DN creation. FSSD Fab POLP dynamic lot pegging algorithm need to be enhanced to retain these SO-Lot combination and not use these SO and Lots during dynamic lot pegging.. Design Change – (a) DN based Fixed Pegging : Peg the SO and Lots based on DNs which have not been shipped; (b). Factory based Fixed Pegging : Peg the SO and Lots based on Demand Pegging Lot Attribute from factory; (c ). Look for lots in WH which have been pegged to SO in last run and peg the Lot to same SO. For remaining lots, run the dynamic lot pegging algorithm as per existing capability; | Once a lot is assigned to DN, the information is shared with EWM as well as warehouse team. FSSD need to consider this assignment as fixed pegging and should not reassign the lot to different SO. FSSD is currently considering DNs that have been PGIed. Enhancement needed in FSSD to consider the lot assignment done for DNs which have not been PGIed. FSSD pegging these assigned lots will lead to confusion and delay in the warehousing activities since the lot received on the DN for execution (picking/packing etc.) is different than lot FSSD reports are showing. | No | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/CR%20-%20FSSD%20Fab%20POLP%20-%20R2%20Hypercare.pptx?d=w28bccacd6bee4a33aa989402d4f87e6a&csf=1&web=1&e=ghJnLc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [12 empty] | 50 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-09 | o Lots are assigned and shared to EWM. FSSD needs to take that into consideration and treat it as fixed pegging; lot should not be re-assigned to a different sales order. o Issue was encountered in Hypercare because they had to manually create delivery notes.  The assigned lots were supposed to be pegged to the DN, but the lots were assigned to different sales orders. o There is no ECA effort as there is already a view.  It will be 50 hours of FSSD effort to consider the S4 data and enhance the logic so that correct data is sent for Dynamic lot pegging.  There are no changes on the S4 side; effort is just from the Boundary Apps team. | [9 empty] | Build | Tower | 2025-09-09 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-04 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  | No Objects |  | In Progress | No
| R2 Hypercare | INT-CR1135 | Cancelled |  | ERP | R2 Hypercare | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 13. Security | rea.m.meyer@intel.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | NA | NA | NA | Standalone | Work In Progress |  |  |  | Create a New version for Altera sub-consolidation | The original S4 GR design had US GAAP and Altera consolidations occurring in the same GR Version as the expectation was that the data required from ACDOCA and the tasks required in ACDOCU would be similar. This approach limited the duplication of information within ACDOCU. However, with the Altera deconsolidation from US GAAP this is no longer the case and we are unable to maintain both consolidations groups within the same version.​ | Altera divestiture and removal from US GAAP results after deal close | None. | No |  |  |  |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is a duplicate of CR1136 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1136 | Approved |  | ERP | R2 Hypercare | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | NA | NA | NA | Standalone | Delivered |  |  |  | Create a New version for Altera sub-consolidation | The original S4 GR design had US GAAP and Altera consolidations occurring in the same GR Version as the expectation was that the data required from ACDOCA and the tasks required in ACDOCU would be similar. This approach limited the duplication of information within ACDOCU. However, with the Altera deconsolidation from US GAAP this is no longer the case and we are unable to maintain both consolidations groups within the same version.​ | Altera divestiture and removal from US GAAP results after deal close​ |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1136/Re_%20R2%20CR%20for%20Altera%20sub-consolidation_.msg?csf=1&web=1&e=6Iimg9 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4B32F9F5-1AC0-4E23-8975-3B26FD516703%7D&file=INT-CR_R1%20New%20Version%20for%20Altera%20Sub-Consolidation.pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  | Medium |  | 2 |  |  | 40 |  |  |  |  | 35 | [5 empty] | 0 | 35 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-09 | o This is a change to a group reporting, and it is part of the impacts from Altera.  Original GR design had US GAAP and Altera consolidations occurring in the same GR version.  Now, tasks have to be broken out with the Altera deconsolidation from US GAAP.  An Altera-specific version is required. o This will be temporary for R2 Hypercare and straddle until Altera is onboarded as a customer. o AR: Include in the deck that this work is needed for the straddle between October to December until Altera is onboarded as a customer - @Bethune, Shane o AR: Include in the deck that the ingestion of this change request does not pose a risk to missing the R3 Build milestone - @Bethune, Shane o AR: Include a comment that the work will be split between Deloitte and Intel - @Bethune, Shane | [9 empty] | Other | Tower | 2025-09-09 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-05 | 0 | < 15 Days | kdey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1137 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Mehak Malhan | [11 empty] | Descope PR/PO workflow Custom Table maintenance PTPE0707 object from IP system. | As capital/equipment is only applicable for IF system, so we kindly request your approval to descope PR/PO workflow Custom Table maintenance PTPE0707 object from IP system. | As capital/equipment is only applicable for IF system, so we kindly request your approval to descope PR/PO workflow Custom Table maintenance PTPE0707 object from IP system. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1137/FW%20Descoping%20PTPE0707%20for%20IP%20system.msg?csf=1&web=1&e=kwX51r |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 117 |  |  |  |  | 0 | 117 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE0707 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-10 | [10 empty] | Other | Tower | 2025-09-10 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-05 | 0 | < 15 Days | mmalhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1138 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Custom enhancement to add the material group field in MIRO screen for Non-PO based invoice postings [Console 3099] | We need to create a custom enhancement to populate the material group field in standard MIRO screen while posting Non-PO based invoices. User will input the material group values manually in the material group field and same value will be populated in standard SAP table i.e. BSEG and ACDOCA. | In AS-IS, business has material field customization in MIRO screen. | NA | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | We don't need this CR now. We added this requirement with PTPE1606_IP and PTPE1606_IF [Custom enhancement to edit the posted accounting document for Payment Term, Baseline date, and Withholding tax fields]. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-05 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
| R2 Hypercare | INT-CR1139 | Cancelled |  | ERP | R2 Hypercare | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 13. Security | natashax.laramie@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | na | INC14866877 | na | INC14866877 | Work In Progress |  |  |  | Production security roles access request to MP3 and BP0 | Production security roles request | We need access to MP3 and BP0 transaction codes and tables for performing business as usual activities for the customer master data. | none | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT-CRXXXX%20Production%20Security%20Roles.pptx?d=w004119ada5f446ab90167bc3bea73645&csf=1&web=1&e=nb6Fag |  | 6. Build Security-Related Changes |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Being tracked in separate Hypercare log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1140 | Approved |  | ERP | R3 (Release 3) | Low | 09A. Master Data | 9A.5 Master Data - Finance |  | 13. Security | Lynn Asbury | [11 empty] | Cancel-Finance Master Data R3 Build SFUTs | Cancel 2 Finance Master Data build SFUTs as they are already in production with R1. ​ -BSPID-50769​ -BSPID-50788​ | Per Kitty, both roles were covered in R1 and are in production:​ FPR CORP - MDG - Company Code - Corporate Transaction Approver [ Task Role: Y_MM_MDG_FI_USMDSRCHZZ_XXXX_M3; App ID: USMD_SEARCH(/ITR/I1_COMPCODE_SEARCH)​ FPR CORP - MDG - Company Code - Corporate Transaction Approver [ Task Role: Y_MM_MDG_MD_MDGLAPRVER_XXXX_M3; App ID: USMD_EDITION_CREQUEST (USMD_EDITION_CREQUEST)​ | NA | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1140/EXT%20RE%20CR1140%20-%20Cancel%20Finance%20Master%20Data%20R3%20Build%20SFUTs%20-%20in%20Prod%20wR1.msg?csf=1&web=1&e=B1TwXV | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1140%20Cancel-Finance%20Master%20Data%20R3%20Build%20SFUTs.pptx?d=wa0586e99a3e64d82a836ae7ed2a40e89&csf=1&web=1&e=2vxbV0 |  | 9. Non-Build Security-related Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-10 | [10 empty] | Other | Tower | 2025-09-10 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-06 | 0 | < 15 Days | lynn.asbury@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1141 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Deepanshu Lnu | [11 empty] | need to cancel the PTPI0368_IP, PTPI0369_IP, PTPI0671_IP as this is not requires in IP system . | need to cancel the PTPI0368_IP, PTPI0369_IP, PTPI0671_IP as this is not requires in IP system . | VMI process is only applicable to IF , hence it should be cancelled in IP . |  |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1141&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&csf=1&web=1&e=Lm3V9O&CID=ebdc042b%2D3624%2D49b9%2D83fd%2D68ae0070ce48&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 390 |  |  |  |  | 0 | 390 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI0368_IP, PTPI0671_IP, PTPI0369_IP | N/A |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-08 | 0 | < 15 Days | deepanlnu@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1142 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 2.3 E2E Process Integration - Process Design |  | 04. OTC IF 07. FTS IF 10. Analytics | sunil.k.parida@intel.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma |  | N/A | N/A | N/A |  |  | 36518 | Foundry Services Summary Database |  | POLP straddle | Because of R3-R4 Straddle POLP( Sales order Lot pegging) data feed from Production scheduling tool ( FSCO and FFS) to ECA ..from ECA data will feed to IF S4 POLP custom table in S4 | In IF S4 because of cluster release Production order will not be created in IF S 4 for all the sites so in ECA we will stich with CIBR data to feed it to S4 POLP table .IF S4 Batch will be internal number range and actual Batch ID will store in supplier batch filed.during straddle MPL waybill will create the internal batch in IF S4 | Design/Development: October | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR1142_POLP%20Straddle%20(%20R3-R4).pptx?d=w07d7c209cb864b20ac8a81a9f9f2b9f2&csf=1&web=1&e=UIjLfu | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [9 empty] | 640 |  |  |  | 0 | 640 | N/A | Yes | ECA | 19 | ECAFTSIFV6961, ECAFTSIPV6962, ECAFTSIFV6963, ECAFTSIFV6182, ECAFTSIPV6183, ECAFTSIFV6185, ECAFTSIPV6184, ECAFTSIFV6249, ECAFTSIPV6250, ECAFTSIFV6245, ECAFTSIPV6246, ECAFTSIFV6251, ECAFTSIPV6252, ECAFTSIFV6247, ECAFTSIPV6248, ECAFTSIFV6363, ECAFTSIFV6405, ECAFTSIFV6432, ECAFTSIPR6431 |  |  | 0 |  | 0 | ECAFTSIFV6961, ECAFTSIPV6962, ECAFTSIFV6963, ECAFTSIFV6182, ECAFTSIPV6183, ECAFTSIFV6185, ECAFTSIPV6184, ECAFTSIFV6249, ECAFTSIPV6250, ECAFTSIFV6245, ECAFTSIPV6246, ECAFTSIFV6251, ECAFTSIPV6252, ECAFTSIFV6247, ECAFTSIPV6248, ECAFTSIFV6363, ECAFTSIFV6405, ECAFTSIFV6432, ECAFTSIPR6431 | 19 | 19 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-11 | o This CR is for the straddle period.  There is no work to be done in CIBR, and it will only require ECA work  No extra headcount o AR: Re-assess and align on trading something else (as 7B1 is critical) - @Clark, Vanessa M |  |  | 2025-10-03 | • Critical for R3/R4 straddle; enables order-to-cash process by linking production scheduling data to sales orders. • Two delivery options discussed: (1) Deliver in ITC2 (not preferred), (2) Pull into ITC1 by pushing some procurement activities to ITC2 and adding three contractors in Q1. • Direction is to avoid pushing to ITC3; plan is to source additional resources and finalize budget. • Decision: Approved, with follow-up needed on budget and resource sourcing. | [5 empty] | Other | CL/OSC | 2025-10-03 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1143 | Cancelled |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan |  | FPR - Aubrey Hinderlider | [9 empty] | Report to display the missing UserID in MDG, HR minimaster and SAP | Create a report in ECA to display the missing user details from MDG, HR Mini master and SAP user ID tables | It is required to identify the users created in MDG to have user ID created in HR Mini master and in SAP | No Impact to Existing Deliverables | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to be cancelled by Shiva Harikrishnan as it is addressed by another CR | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-08 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) |  | INT-CR1144 | Approved |  | ERP | R2 Hypercare | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Rea Meyer | [7 empty] | Delivered |  |  |  | Update the NonGAAP Sidecar logic | Update the NonGAAP Sidecar logic, manual upload template, and reporting to disaggregate the SnM and GnA adjustments on to separate line items and change the current Marketing and G&A (MG&A) line to a calculation of those two fields | User feedback highlighted a downstream need for this data to be disaggregated. If the upstream source (S4 GR) is not updated then users will have to manually disaggregate in SAC. This has the potential to cause disconnects as the full process should be owned by the External Reporting team. The Sidecar update will eliminate the need for the External Reporting team to manually calculate and add this into their Fiori upload template |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1144/Re_%20R2%20CR%20for%20Non-GAAP%20report_.msg?csf=1&web=1&e=cLuRSm | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1144%20-%20NonGAAP%20OpEx%20Update.pptx?d=w478b53a7a6204dcb9fc8c778ed7eb8f9&csf=1&web=1&e=y8wCnf |  | 1. Process Scope / Design Change |  |  | Low |  | 1 |  |  | 15 | [6 empty] | 15 |  |  |  | 0 | 15 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-16 | o This is an R1 near-real time reporting. o SnM and GnA needs to be separate line items | [9 empty] | Design | Tower | 2025-09-16 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-08 | 0 | < 15 Days | kdey@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1145 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 07. FTS IF 17. B-App | rudrsengupta@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | 594 | NA | NA |  |  | 32287 | FFS / APPS |  | Interface from Production Scheduling Apps for Material Staging | Interface from FFS->MARS and APPS->MARS to S4HANA for Lot level Material staging of Semi-Finished Materials for ATM and WLA stages. | Material Staging for the Bailed Material and SFGs for the ATM and WLA Stages | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR0xxx_FTS-IF_Interface%20from%20FFS%20%26%20APPS%20for%20Material%20Staging.pptx?d=w8e6b9c312d6a45239361cee0008c381e&csf=1&web=1&e=lfMuXl |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | FTSI1647, FTSI1646 | 3123, 3124 | FTSI1647, FTSI1646 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes |  | 2025-09-11 | o POR was FSCO, but it was changed to APPS due to an architectural change.  There will be other implications from the change, but this interface is required regardless o AR: Create a KDD to capture the architecture change – @Maxey, Stef |  |  | 2025-09-19 | • Two medium-complexity interfaces involving FFS Mars and Zeus applications connecting to S/4 HANA for material staging and production scheduling across multiple sites. • These interfaces are planned for ITC2, bypassing ITC1 due to complexity. • Clarifications were made that these interfaces do not use PDF for communication but rather bots, differentiating them from MES integration transactions. • These are regular interfaces and not enhancements, so they go into the standard interface bucket after approval. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-09-19 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R2 (Hypercare) | R2 Hypercare | INT-CR1146 | Approved |  | ERP | R2 Hypercare | Low | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | rodolfo.alarcon@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | INC14899379 | Delivered |  |  |  | Change in tme of Putaway Delay | Currently, for cross dock relevant products, there is delay of 1 hour in putaway process set in production system. Now this delay of 1 hour to be increased by 6 hours | ADNC and POLP job (that helps in Order Creation) runs at frequency of 4 hours, to accomdate this frequency, Putaway delay timing is increased when cross dock relevant products (Bodega Rock) is received in Warehouse | No impact on existing configuration | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-_FTS_EWM_R2_Change%20Request%20for%20Putaway%20Delay.pptx?d=w7188f40824df494b8b26605a8905ffb5&csf=1&web=1&e=fUXv6a |  | 3. Configuration Change |  | No |  | Low | 0 |  |  | 26 |  |  |  |  | 4 | [5 empty] | 0 | 4 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-09 | o This request is to bump up putaway to 6 hours so that it is synced up with cross-docking, which enables the use of EWM cross-docking capabilities.  This increase in delay will prevent normal putaway tasks from being triggered before outbound orders are available, allowing items to skip the rack and go straight to pick/pack/ship o Malaysia warehouse needs these changes by next Tuesday, and the other warehouses will be done by WW39. | [9 empty] | Other | Tower | 2025-09-09 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1147 | Approved |  | ERP | R3 (Release 3) | Low | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Pabbisetty Harshavardhan | [11 empty] | Descoping of PTPE1127_IP/IF: Enhancement of PO close interface from S4 to Ariba | Need to descope PTPE1127_IP/IF | PTPI1128_IP/IF using the standard interface of sending PO closure status information from S/4 to Ariba, will serve the business need and does not require to send closed for all actions using enhancement PTPE1127_IP/IF |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1147/FW%20Descoping%20of%20Enhancement%20PTPE1127_IPIF%20Interface%20to%20send%20PO%20closure%20status%20information%20from%20S4%20to%20Ariba(Enhancement).msg?csf=1&web=1&e=YMIxBY |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 117 |  |  |  |  | 0 | 117 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPE1127_IP, PTPE1127_IF |  |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-10 | [10 empty] | Other | Tower | 2025-09-10 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-09 | 0 | < 15 Days | pabharshavardhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1148 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | amitkumar55@deloitte.com |  | FPR - Aubrey Hinderlider |  | INT-CR1337 | [7 empty] | Cancellation of Object: FPRE0891_IF -Split from primary Cost centers to PCOS & R&D/OCOS | Cancellation of Object: FPRE0891_IF -Split from primary Cost centers to PCOS & R&D/OCOS | As per business decision, We need to use Xeus/Mars volume data for non-depreciation and non-burden allocation to PCOS/OCOS instead of MvT 101 and 501 quantities. Awaiting new RICEFW in CR1337 |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1148/Re_%20Cancellation%20CR%20__%20FPRE0891%20-%20Split%20from%20primary%20Cost%20centers%20to%20PCOS%20%26%20R%26D_OCOS.msg?csf=1&web=1&e=CCUKod |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0891_IF | Console 3150 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-29 | [10 empty] | Other | Tower | 2025-10-29 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-09 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1149 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Arif Ahmed | FPR — Sara Cooper | FPR - Aubrey Hinderlider | [9 empty] | Add P-unit report to scope of existing object FPRXV188 – Consolidated VAT report | P-unit report is used by Indirect Tax team to self-accrue use tax on finished goods that Intel US giveaway as samples to external US customers or use in internal processes (RND) within the US based on material standard cost. ​ Further analysis shows that one of the required data fields of the report, Material Standard Cost/unit, is not available in standard S/4 report. Hence, team is requesting to add the P-unit report as additional scope to an existing object FPRXV188 – Consolidated VAT report so the report can be custom built. | The required data fields of P-unit report, such as Material Standard Cost/unit and Total Billback Cost, are not available in standard S/4 reports or existing data sources. No out-of-the-box solution or Fiori app can fulfill these specific reporting needs, and the legacy ECC report cannot be replicated due to system and process changes. P-unit report needs to be custom built to mitigate the risk of non-compliance with US State and local Tax Authorities and disruption to critical tax reporting activities. |  | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1149%20-%20Add%20P-unit%20report%20to%20scope%20of%20existing%20object%20FPRXV188%20%E2%80%93%20Consolidated%20VAT%20report.pptx?d=w7e6d1f1f631d413bb31c921b4e05cb88&csf=1&web=1&e=1ZE0zo |  | 4. Change to Existing RICEFW / ECA/ Build Object | Manage Indirect Tax Reporting and Compliance |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed with Rafael that it is approved by Shane, so a Build CR will be created as a replacement and work will proceed | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-10 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1150 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics | eugene.celis@intel.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma |  | CR-1024;CR1075; | N/A | N/A |  |  |  |  | Anafi | Anafi Build Instruction UDF UI+S4 Table + Integration with ECA-FSCO/HANA; HANA to RTD Kitting | -S4 Universal Data Format Table and UI (transform customer specific Build Instruction to Universal Data Format for Downstream Apps)​ -Data from S4 to ECA, ECA to FSCO view and ECA to HANA by by ECA team​ -HANA (Transform ECA into 2 views for Assy BI and Finish BI) to RTD Kitting with XTO publication in HANA | Part of the Anafi capability CR | R3 ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR1150%20S4%20UDF_UI_ECA%20Integration_DSA.pptx?d=w47f7a6ac49dc4d39b513547dab4af88f&csf=1&web=1&e=lJP9L8 |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-11 | o Table will be prioritized first, and UI can follow. This will enable teams to start their development.  Approved OTC CR is already inclusive of the ECA and HANA work. o If there is a delta of a few weeks for the delivery of this change, then the pilot product will need to be extended. o This Anafi work is the highest priority and will be off the table as a trade off.  This work is already a part of R3, and it will be pulled forward to meet the testing time frame for Anafi |  |  | 2025-09-12 | • This Anafi work for FTS was missed in the previously approved CR to pull in R3 work to R2.5 and is now being added. • The Universal Data Format (UDF) UI and ECA integration for S4 is required to be pulled in, specifically for the Anafi build instruction process, due to high volume and manual workload concerns from the OTC team. There is concern regarding the OTC team constraints o AR: Eugene Celis to coordinate and prepare contingency plans in case the timeline cannot be met due to technical or resource risks. • The Anafi technical sizing for the coding effort is about 400 hours over seven weeks, but the total effort including functional and SS4 support requires incremental Deloitte spending in Q4'25, about 1.5 FTE functional, 1 FTE SS4. The overall timeline is compressed due to the Anafi pilot schedule. There is very high risk due to the compressed testing window and dependencies across multiple teams (OTC, ECA, HANA, factory automation, FTS). The team coordinating needs to ensure all aspects are included in the scope, schedule and tracked holistically. o AR: Uzma Ahmed schedule WW38 meeting with Mike Lange, Rick Antonellis, Paul Whitlock re: funding Anafi Q4'25 Deloitte incremental budget requirements from IAO IT budget. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-09-12 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1151 | Cancelled |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | deborah.whitely@intel.com | Security — Debbie Whitely | FPR - Aubrey Hinderlider |  | INT-CR1124 | NA | NA | [5 empty] | Sprint 17 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 17 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | Yes |  |  | NA |  | 1. Process Scope / Design Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR1124 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1152 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Material Master Intelligent Description Conversion | Intelligent Description for RAPP Material for IP and IF will be converted from Source and Loaded in MDG in characteristics "LEGACY_DESCRIPTION" | This is an additional requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1152.pptx?d=w50dc504325424e2a8630c9594aa47f7b&csf=1&web=1&e=aNtLa4 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-10 12:19 | 210 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1153 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Prabesh Acharya | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  |  | NA | NA | [5 empty] | Non federal labor charges to IP WBS for LE 199 employees | Uniquely identify labor charges by LE 199 employees when working on non federal projects | New requirement, design options to implement the solution need to be reviewed | R3 ITC2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1153%20-%20Non%20federal%20labor%20charges%20to%20IP%20WBS%20for%20LE%20199%20employees.pptx?d=w9cd21cd7137d4d8fbcd52e6977692e23&csf=1&web=1&e=h0yzTQ | Design / Build Gap | 1. Process Scope / Design Change |  | No |  |  | 0 | [13 empty] | 0 | 0 | Tech - S/4 | No | S4 | 0 | N/A | 3160 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRI1238 | 1 | FPRI1238 | 1 |  | 0 |  | 0 | N/A |  | 2025-10-24 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o This change is required to ensure cross charges are correct o POR for today is to move everything to Corp 100; nothing is done to the costs  All costs are put onto dummy entities, and it has no exposure o This change is driven by new information identified recently: audit exposure and overstatement on government charging o This change is to review high-level design and size the technical effort (ETA 10/3) with FPR and Boundary Apps  It won’t be finalized this year, and build will complete during Q2 o Design is mostly FPR and Boundary Apps o AR: Add topic to Open Design Tracker - @Acharya, Prabesh | [9 empty] | Design | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-10 12:48 | 0 | < 15 Days | manidgupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1154 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Class and Characteristics Master Data Long Description Conversion | Business request to migrate existing Material Class & Characteristic Long Description data from xEDM to MDG (Itego) and be able to maintain this long text description moving forward in MDG (Itego).​ | This is a new requirement |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2783FF47-9AF7-4EB2-B3F7-CFEE1F28DC02%7D&file=3097%20-%20Class%20and%20Characteristic%20Long%20Characteristic%20Description%20Conversion.pptx&wdLOR=c5BD1E5A8-4ED9-460B-981E-96F1A9D4ECB2&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-10 13:42 | 210 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1155 | Approved | Presenter: Nikhil Missing workaround for ITC1 | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Rudra Sengupta |  | FTS IF - Haritha Komma |  | CR1195 |  |  |  |  | 12630, 16134 | Prospal-Product Shipment Planning and Logistics, Global Master Production Control aka Synergy |  | An interface from Prospal/Synergy to create lot level STO in S/4 for the straddle solution from Non S/4 to S/4 sites | An interface from Prospal/Synergy to create lot level STO in S/4 for the straddle solution from Non S/4 to S/4 sites | New Requirement for Prospal Straddle and synergy lot level STO |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1155%20New%20Requirement%20for%20Prospal%20Straddle.pptx?d=w09782c6f5b4d4da5bf9523369e71dc44&csf=1&web=1&e=qXqy1V | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FTSI1680 | 3136 | FTSI1680 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-25 | o STO was going to be created manually during ITC1 |  |  | 2025-09-26 | • Nikhil Jain presented a CR related to the Prospal interface requiring creation of lot-level STOs for straddle solutions moving from non-S4 to S4 sites. • This change is driven by shipping task force requirements, shifting from bulk to lot-level STOs. • Development hours estimate is 40, and the functional design will be completed by the next sprint, but technical work will begin after Sprint 20. • The CR will miss ITC1 and intercept ITC2. Nikhil noted this is likely the last change request for the Prospal interface. • Decision: CR is approved | [5 empty] | Other | CL/OSC | 2025-09-26 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-10 13:47 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1156 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Deepak L Motwani | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | LOGE0627 + LOGE0690 - Multiple deliveries as an input | Logic change required for Program in S/4 to accept Multiple Sales Order/Delivery/HAWB number as an input. This would require to change the structure of the program created. | This is an additional requirement raised during the FUT review of object LOGE0627. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B703CEFF8-5E1A-4623-AB72-7DF40EE8CF79%7D&file=INT-CR1156_%20S4%20to%20accept%20Multiple%20Sales%20OrderDeliveryHAWB%20number%20.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High |  | 3 |  |  | 150 | [5 empty] | 150 |  |  |  |  | 0 | 150 | Tech - S/4 | No |  | 0 | N/A | 3173, 3176 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0627, LOGE0690 | 2 | LOGE0627, LOGE0690 | 2 |  | 0 |  | 0 | N/A |  | 2026-04-01 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | - After FUT, we came to know from the WOM team that there is a change to the output. - It is only the change that will be moved beyond 1/9/26. The base object functionality will be tested in ITC1. - There is boundary apps impact. | [9 empty] | Build | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-10 14:42 | 0 | < 15 Days | shadhir@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1157 | Approved | Presenter: Praveen | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Deepak L Motwani | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [6 empty] | 1887 | Channel Management |  | PRMP Role needs to be sent to CHM from S4 to create Channel Partner Role in CHM | The Channel Partner role PRMP needs to be sent to CHM if the ZK partner number is equal to the SP partner number (i.e., ZK = SP in S4). If the existing Channel Partner is deleted from the sold-to customer in S4, or if it is changed to a different Channel Partner, then the Channel Partner role PRMP must be removed from the customer in CRM. | A new requirement has been identified to transfer the PRMP role to CHM from S4. The Channel Partner role should be created in CHM when the ZK partner function (IP-Channel Partner) is assigned to the sold-to customer, and the ZK partner number is the same as the sold-to number. This is an existing enhancement in ECC for integration between ECC and CHM. The same functionality must be implemented in S/4HANA to ensure consistent handling of Channel Partner role (PRMP) data between S/4 and CHM. | No impact to S4 system | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1029-PRMP%20Role%20needs%20to%20be%20sent%20to%20CHM%20from%20S4%20to%20create%20Channel%20Partner%20Role%20in%20CHM%20%20.pptx?d=w75fc3608b7b0415688dc2b31b00e4ca1&csf=1&web=1&e=qumVYR | Missed Requirement | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 |  |  | 16 | [10 empty] | 0 | 0 | N/A | Yes | S4 | 1 | OTCE1703 | 3154 | OTCE1703 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-16 | o This is an existing functionality established in ECC and CHM, but this was missed out in the design workshops. o Channels do not exist in IF, so it’s only needed for IP. o AR: Need to include the design effort and path to close – @Muppala, Praveen Kumar o PRMP role is not an S4 role, so MDG needs to do a lot of developments. It will not be in the data for S4. o AR: Include comments on why this cannot be manually maintained in S4 - @Muppala, Praveen Kumar |  |  | 2025-10-17 | • The team discussed a requirement from the SAP Channel Management (CHM) application involving the transfer of customer master data from SAP S4 to CHM. • A specific flag, PRMP, needs to be added to the interface when the sold-to party and channel partner role are the same. • This flag enables CHM to create a partner function correctly. • The MDG team does not currently support this feature, so the change must be implemented in the SAP-to-CHM interface. • The discussion highlighted challenges in implementing this logic on the CHM side due to its discontinued status and limited capabilities, leading to the decision to introduce the enhancement in the SAP interface. • The team agreed to further explore alternatives, including the possibility of handling this logic on the inbound interface, but acknowledged the necessity of the change for end-to-end functionality • Decision - Need for solution is agreed on but will need to be further reviewed to identify new solution options. | [5 empty] | Other | CL/OSC | 2025-10-17 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-10 23:50 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1158 | Cancelled |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 17. B-App | Twinkle Shah |  | FPR - Aubrey Hinderlider | [9 empty] | BADI enhancement to define custom field to store Note To Payee information | BADI enhancement to define custom field to store Note To Payee information | Additional fields are required from Bank Statement (EBS) to process the Open Items for matching (for Matching rules in Blackline to be able to pick up Open Items to be matched). The additional fields are: Transaction description Extra information payment details name_address | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1158%20-%20%20BADI%20to%20store%20Note%20To%20Payee.pptx?d=w4c3de1b5ae1d48dda1011f88e969af4c&csf=1&web=1&e=qXCj6h |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is a duplicate of CR0849 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-11 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1159 | Approved | Presenter: Sekhar | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | New Enhancement for implementing user exits or business add in | To create a user exit (or) Business Add In to update Components and Operations against a Production Order. | Update for some of the fields in the components and operations against a production order is unable to process using Std. APIs/Std. BAPIs. Components and Operations updates are required for production order interface, conversion, and mass upload objects. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1159_FTS-IP%20Manufacturing%20%20New%20Enhancement%20CR%20content%20for%20implementing%20user%20exits%20or%20business%20add%20in.pptx?d=w7ca1abe9155f40f3a343da8802725904&csf=1&web=1&e=sWFHPL |  | 2. New RICEFW / ECA / Build Object | M-090-110, M-090-130 |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FTSE1642 | 3119 | FTSE1642 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o Standard API did not work for mass upload production orders for all engineering orders. o Testing will be done manually in ITC1, and it will be correct for ITC2. o AR: Add in risk to not testing in ITC1/MC1 - @Lingam, Sekhar | [9 empty] | Other | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-12 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1161 | Approved | Presenter: Prabesh, Naveen | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Twinkle Shah |  | FPR - Aubrey Hinderlider | [9 empty] | BADI Enhancement to change Order Type from Product cost Collector from IP & IF system to Internal Order in CFIN in R3 | BADI Enhancement to change Product cost Collector to Internal Order in CFIN from IP & IF system in R3 | Accounting transactions flowing from IP & IF system to CFIN containing PCC should get replicated as Internal order as Accounting transaction needs a Cost-object to post the transaction, otherwise it will get failed. Accounting Transactions will PCC pick Internal Order in CFIN to get posted | Transactions with PCC from IP & IF will get failed in CFIN and reporting will be disrupted between systems | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE4D9B4C4-418A-482C-BE8D-9E10815B1B3F%7D&file=PCC%20to%20IO%20Cost%20Obejct%20Mapping.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FPRE1711 | 3155, 3188 | FPRE1711 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0023 | 1 | FPRE0023 | 1 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-16 | o There are changes required from a substrate design for EMIB die that was recently approved. The product cost collector needs to be re-mapped. o The change is within S4 in the SLT layer. o We cannot test in ITC1 because there is no systematic solution. The manual workaround is make a postings. o AR: Include statement on workaround for ITC1 - @Negi, Naveen | [9 empty] | Other | Tower | 2025-10-16 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-12 | 0 | < 15 Days | sosil@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR1162 | Approved | Presenter: Shashank Kolhe, Brian Staab | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Shashank.kolhe@intel.com |  |  |  |  | SCP0593 | [6 empty] | SCP IP DP - Descope Audit Logging | Audit logging will not be available in BY CDP to support R3 deployment. This functionality will be removed from scope for R3. | APPROVED. Audit logging not available in CDP product or roadmap for R3 timeline. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/CR1162%20-%20Audit%20Logging%20Descope.pptx?d=w6570bd00ac4642fb86cdfb9d6d0b0856&csf=1&web=1&e=AKPC2f |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | Confirmed by Loni Adams that this was approved: APPROVED. Audit logging not available in CDP product or roadmap for R3 timeline. | [9 empty] | Design | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-12 | 0 | < 15 Days | brian.staab@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1163 | Approved | Presenter: Shashank Kolhe, Brian Staab | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Shashank.kolhe@intel.com |  |  |  |  | SCP0593 | [6 empty] | SCP IP DP - Descope Global Locking | Global Locking will not be available in BY CDP to support R3 deployment. This functionality will be removed from scope for R3. | APPROVED. Global Locking not available in CDP product or roadmap for R3 timeline. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/CR1163%20-%20Global%20Locking%20Descope.pptx?d=w048c22d6dd864d87aeb24850e9eee443&csf=1&web=1&e=UeXz9X |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | Confirmed by Loni Adams that this was approved: APPROVED. Global Locking not available in CDP product or roadmap for R3 timeline. | [9 empty] | Design | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-12 | 0 | < 15 Days | brian.staab@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1164 | Rejected | Presenter: Praveen Work with Vivek to see if we want to bring all ingestion in at once for R2.1 | ERP | R2.1 Feb 2026 | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Praveen Kumar Muppala | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Bulk Price upload by End Customer for Multi Sold to customer scenarios | Currently, price uploads using the Manage Prices – Sales Fiori app are enabled only for sold-to customers. In scenarios involving multiple sold-to customers (for example, when several sold-to accounts are linked to a single end customer), prices must be loaded separately for each sold-to customer rather than against a single end customer. | CBAs state that S4 now only allows NRE values to be uploaded under one Sold-To or one MM. This creates a problem for customers with multiple Sold-To accounts, as NRE can’t be split across their full account structure. | None | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1164-Bulk%20Price%20upload%20by%20Parent%20Customer%20for%20Multi%20Sold%20to%20customer%20scenarios%20%20.pptx?d=w8bcba454d59d47dd80f3936bd480dc6b&csf=1&web=1&e=XUNBXN |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 |  |  | 24 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-09-25 | [9 empty] | Confirmed Loni and Gabriel, Anthony Roman, etc. to not be required | Other | Not Assigned |  | Not Approved | 09, 2025 | 09, 2025 | 2025-09-13 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1165 | Approved |  | ERP | R3 (Release 3) | Low | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Shishir Kumar Dwivedi | [11 empty] | Cancellation of RICEFW object in S4 R3 IDM object tracker OTCC1225 Data conversion for Intel Federal – Clause Library | Data conversion for Intel Federal – Clause Library cancellation | It was determined by the business after the CLM integration was cancelled that there was no longer a need for this conversion. |  | No |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/CR Approval Emails/CR1165?csf=1&web=1&e=5yrH3x |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCC1225 | Intel Federal’s CLM (Icertis) will contain the DoD clause library, and Dassian provides a standard tool to upload this information into their Dassian tables. |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-15 | 0 | < 15 Days | balupm@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1166 | Cancelled |  | ERP | R2 Hypercare R2.3 Aug 2026 | High | 11. Technology | 11.3 Technology - Middleware |  | 04. OTC IF 11. Technology | Ambar Jain | [11 empty] | Request for the change of JOB scheduling time for OTCI0030/31/32 Autosys Jobs | Scheduling the AutoSys jobs with a 15-minute interval between the execution of interface OTCI0030/31/32. | OTC10031 & OTC10032 jobs were triggered simultaneously, both interfaces attempted to process the same files at the same time. This led to file conflicts between the two interfaces. Change is already completed as part of Incident INC14870533, it was high priority. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B96BEAC4D-ED42-48EA-B56D-EAA053DE3EC4%7D&file=INT-CR1166%20-%20Autosys%20Job%20Change%20for%20OTCI0030%20OTCI0031%20OTCI0032.pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Being tracked in separate Hypercare log | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-15 | 0 | < 15 Days | ambajain@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1167 | Approved | Presenter: Eugene | SCP | R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | Eugene.celis@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | Assign Lots to IF BY STR in PDH from Ship TF | This Change Request was from W19’25 Shipping Task Force Outcome. The Change request included work on S4 and affected shipping boundary apps but did not include PDH work. PDH team was aware of the design and included in the PDH planned deliverables but needed a Formal CR to include PDH work. | Part of the aligned Shipping TF design (Outcome from W19 F2F), together with Deloitte, IT Architects, Factory Automation, Logistics, Planning & Mfg reps. | Yes. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR1167%20Assign%20Lots%20to%20IF%20BY%20STR%20in%20PDH%20from%20Ship%20TF.pptx?d=wf84e7f98cd5745e99b79709503ccd948&csf=1&web=1&e=fEqsZ4 |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0253 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o No formal CR was submitted for the PDH work; a CR submitted previously only included S4 work and affected shipping Boundary Apps o AR: Add in a risk mitigation slide with a list of tasks required to perform the workaround for ITC1 - @Celis, Eugene | [9 empty] | Design | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1168 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR | Suresh Nagalingam Muniandi |  | FPR - Aubrey Hinderlider | [9 empty] | Split enhancement FPRE0285 into two as per Development team recommendation | Split enhancement FPRE0285 into two object as per development team recommendation. We will continue to use FPRE0285 for "Cash App rule engine enhancement during EBS load". Need to create new enhancement object for "enhancement to Cash App post EBS load". So, created new console id# 3106 for the second process "enhancement to Cash App post EBS load", And this enhancement aims to boost the efficiency of AR open item invoice clearing (AR Cash Application) and improve the accuracy of post EBS process to clear the AR open items which is not cleared during EBS load. As and when the payment advice is created, this custom program is triggered and used to match a payment advice to a payment on account (which is posted during EBS load) and clear the open items listed in the payment advice. This process is available in current ECC system and coding will be lift and shift from Intel’s ECC program and may need to make changes as required. | In the intake form of console id 565 (Object id FPRE0285), two process, 1. Cash App rule engine enhancement during EBS load as well as 2. enhancement to Cash App post EBS load, was included, presented and approved. Now as per development team recommendation, need to split those 2-process related program development into 2 different enhancement objects. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1168%20OR-140-140_Enhancement%20to%20Cash%20App%20Post%20EBS%20load%20v1.0.pptx?d=wca05fd06082141fe8200f838db198d3b&csf=1&web=1&e=acfOkb |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FPRE1705 | 3187 | FPRE1705 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-27 | - This request is to split an object into 2 due to tech complexity. - AR: Tag to R3 ITC1 and call out that there is 0 tech effort | [9 empty] | Other | Tower | 2025-10-27 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-16 | 0 | < 15 Days | sureshx.nagalingam.muniandi@intel.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1169 | Approved | Presenter: Satya / Joshua | ERP | R3 (Release 3) | Medium | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 13. Security | babu.jadam@intel.com | Infra/Tech/Middleware — Babu Jadam | E2E - Aishwarya Bhat |  | Late "birthright access' requirement identified to minimize access to SAP across IP, IF and corp. | 1183 | n/a | [5 empty] | IAO My workplace redesign: Architecture required to allow all Intel users access to the right SAP workflows | Introduce My Workspace landing page on Circuit. Build out front-end application tabs with seamless access to backend systems. Add access control intelligence and AI enabled request process. Change SAP user expirations from 4-month to 6-months and relocate the expiration and renewal functions from SAP to AGS, to standardize with Intel processes. Create end-user roles in AGS to enable approver roles in SAP. Pre-load roles with known approvers and manager/leadership approvers. Create end-user roles in AGS to enable cross-box approvers, allowing for selected users to be present with ability to approve in multiple SAP systems. TCM required to educate users on My Workspace landing page and system access. | Intel Information security policy requires only users with a need-to-know be present in enterprise systems. All Intel users have access to the existing Fiori Launchpad and can access applications like My Inbox, eCheck requests and non-SAP URLs when needed. This is possible because all Intel users on legacy SAP system are provided default "birthright" access to the SAP ECC and SRM systems. This can impact any RICEFW where an approval is needed and the complete scope is unknown. In the future, SAP users on S4 systems will not be granted any default user ID or authorization to S4 systems so default access will not be possible | no impact to existing deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/IAO%20My%20Workspace%20Redesign%20CR.pptx?d=w6fc4ee340d814cd5b272cc65a01096e6&csf=1&web=1&e=szUJsg | New Requirement / Scope | 1b. Solution Design | Security L3s | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3159 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-18 | Presented in Core Leadership, and it was decided that this CR will go directly to CR Meeting on Friday |  |  | 2025-09-19 | • Presented a redesign of the My Workspace landing page on Circuit to comply with Intel’s information security policies by eliminating birthright SAP access. • The redesign aims to provide a personalized launchpad showing only the applications users have access to, with options to request additional access via AGS. • The redesign includes two implementation options: an MVP costing approximately $50K and a more advanced AI-enabled version costing about $300K. • The MVP approach was favored to avoid high costs and complexity, with development planned across Q4'25 and Q1'26 and backend integration handled by Deloitte. • Decision: Approved the MVP option | [5 empty] | Other | CL/OSC | 2025-09-19 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1170 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | Vara Prasad Rutthala |  | PTP - Richard Taylor | [9 empty] | Enhancement to make PO price updates for HVM (OSAT) orders (Exclude Engineering and Rework orders) based on the service PIR price and SIFO PO with material contract with no goods receipt(GR) or partial GR completed. | This custom program will check all open HVM POs for which the goods receipt is not yet posted for the first PO line item. Then, it checks the corresponding service PIR associated with first PO line item of the HVM order If the PO unit price of the first line item of the HVM order is different from the corresponding service PIR price, this program calls a SAP standard BAPI to make PO price updates. | This custom program will check all open HVM POs for which the goods receipt is not yet posted for the first PO line item. Then, it checks the corresponding service PIR associated with first PO line item of the HVM order If the PO unit price of the first line item of the HVM order is different from the corresponding service PIR price, this program calls a SAP standard BAPI to make PO price updates. |  | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to be a duplicate of CR1213 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-16 | 0 | < 15 Days | vrutthala@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1171 | Approved |  | ERP | R3 (Release 3) | Low | 04. OTC IF | 4.12 OTC IF - TM | Yes | 04. OTC IF | Shameek Dhir | [11 empty] | Descope of RICEFW object # LOGE156_IF # TM - GTT: SAP S/4 Return Deliveries relevant for TM are not propagating to BN4L GTT under “Monitor Outbound Deliveries” as Returns are not applicable for Intel Foundry in R3. | Cancellation of RICEFW # LOGE156_IF # TM - GTT: SAP S/4 Return Deliveries relevant for TM are not propagating to BN4L GTT under “Monitor Outbound Deliveries” | The Intake form presented during the OSC was only applicable for OTC IP because returns are applicable for OTC IP tower only. Returns are not applicable for OTC IF tower. Hence, We need to cancel the object LOGE1567_IF. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1171/%5BEXT%5D%20RE_%20Cancellation%20of%20GTT%20RICEFW%20LOGE1567_IF%20%23%20%20CR1171.pdf?csf=1&web=1&e=01saCW |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1567_IF | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-08 | [10 empty] | Other | Tower | 2025-10-08 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-16 | 0 | < 15 Days | shadhir@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1172 | Cancelled |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 4.14 OTC IF - IF R2 FE Supply Planning |  | 07. FTS IF | mike.s.lenau@intel.com | Data & Analytics - Rebecca Verette | E2E - Aishwarya Bhat |  | CR1128 | N/A | N/A | [5 empty] | OTD Report Adjustment: Exclude Duplicate Lots During Transition Period | Closed: OTD (On-Time Delivery) Report (formerly POWER) to exclude duplicate lots during transition period. Code to be written and inserted into the OTD report to validate that lots that passed old commit point and afterwards new commit point post R2 transition will exclude duplicate lots. | Important to ensure actuals aren’t double counted in the transition period, allow accuracy for SP and MFG. | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1128%20for%20OTD%20Report%20Adjustment%20Exclude%20Duplicate%20Lots%20During%20Transition%20Period.pptx?d=w42b5e0cbf3d846eca65cd1f34cffc39c&csf=1&web=1&e=gvauNP |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it was not included in Upali's list of open CR's | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1173 | Cancelled | Presenter: JR Hoover Missing ITC2 and workaround, RICEFW and new FS/Dev/FUT dates | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 09A. Master Data 17. B-App | jhoover@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | Design changed no longer needing some data to be sent from EMS | N/A | N/A | [5 empty] | Update to EMS & Plant Maintenance interface | Remove few characteristics coming from EMS payload and master data as well. 1.FTSI1008 – API Update:?Update the FTSI1008 interface to support enhanced API functionality The characteristics to be removed from the EMS payload are : SUPPLIERQUALACTUALIZED, SUPPLIERQUALENDDATE, ASSETNUMBER and ETAGNUMBER 2.FTSM007 – Remove Characteristics:?Eliminate characteristics from FTSM007 The characteristics to be removed from the Master data(MDG) are : SUPPLIERQUALACTUALIZED, SUPPLIERQUALENDDATE. 3. FTSE0925 – Batch Process Update:?Revise the batch process logic in FTSE0925 to get asset ID and eTag # from that enhancement. | These changes help maintain data integrity and support evolving business requirements. Since these fields will not come from EMS, API needs an update ensuring the interface payload only has the fields that are required. Removing unnecessary characteristics from master data (FTSM007) simplifies data structures. Updating the batch process in FTSE0925 addresses performance bottlenecks and aligns processing logic with current business needs. Collectively, these updates will improve operational effectiveness, support scalability, and reduce long-term maintenance efforts. | Changes cannot be started by tech team until Sprint 21 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/6.%20Draft%20Deliverables/Decks/INT-CRXXXX%20-%20Removing%20Characteristics%20coming%20from%20EMS%20payload%20and%20master%20data%20.pptx?d=w3e237fa3855346e5960cd5c23e01391a&csf=1&web=1&e=d5D2JV |  | 1. Process Scope / Design Change | PE-060-290 PE-060-030 | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Hailey Weller to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1174 | Approved | Presenter: Nikhil Chug | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP 11. Technology 17. B-App | nikhil.chug@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | 71 |  | 1675 |  |  |  | 15170 | ISA-VS2012 US (MAPPS) |  | EMIB Design | Enable new capabilities to support EMIB die-on mylar wafers with the EMIB ide inventory stored in wafter form at IF Sort Site. Enable a pull-based process to generate Production Orders for IF to pull the mylar wafers from inventory at Sort and ship the EMIB die to Substrate Suppliers. | Recent feedback was the IF will store EMIB die on Mylar instead of Tape and Reel Die Prep before R3. Once the EMIB wafer is sawed the expiration clock of the die starts. Currently the expiration timeframes are close to 6 months but once EMIB2.0 comes into picture the expiration timeframes will be much lower - about 4 weeks and the EMIB2.0 die will need refrigeration. | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR1174%20-%20EMIB%20Design.pptx?d=w83f53fd137d74d118f1d778510b4fed3&csf=1&web=1&e=y0DEba |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 |  |  |  |  | 120 | 40 | [7 empty] | 160 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPSPPDH0149, SCPIPSPPDH0150 | 2 | 2 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - This is a must, and the teams have aligned to take on this work. - No commercial impacts. | [9 empty] | Design | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1175 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | nmaddi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1176 | Cancelled |  | ERP | R2 Hypercare | High | [20 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | pujagadeesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1177 | Cancelled |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | [15 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | pujagadeesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
| R2 Hypercare | INT-CR1178 | Cancelled |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | Implementing One-Time Confirmation for Picking Activity Completion | This is to facilitate the Picker to complete the RF Picking can collectively confirm the placing of placing of the HU in the same destination bin instead of duplicated verification of the same Destination Bin. | This will Make the Picking Process more efficient and effective as the picker can confirm Group of handling unit with the same destination Bin one after another | Needs extensive regression testing in RF scanner with various scenarios both existing and Potential scenarios | No |  |  | https://secure-web.cisco.com/1By5s-FvyrWh-299XRW29BseHTUJp-Hniszv-KuE2UhdX6HKmR_KEmCtQXnFnkjSvcVdUq0d4hJbjQNv-Px53VXebIBXH_fYRfF17ILYZjgPxft54-qb95-WRzMqPys9j8SmUvuz0Hxmyfc0fT5ju1KHVoPbk55VJM8X0JeVO00EsxxPPLht6KzxkJ5Mcd_c4AX-7bkE0eulPlHmub496TKITxJ_tyWWzJaYSPdqlQw1bbKyIhKI3eqE6jrfJSNopnzXdGHLQcw0aw9F0CdTguzpF4TAs-of8U4HExIIPGYABSkd5VAiLN_qjPDkSjQ9rErt8q0TdXKjkUxbwdPV7J-ZAC5C2Q6RIBz5WhRb5rFm47_WpIZLHRKydxUkvuAt0XJUBPr1gknSD4VoYQXNv5EWYo_azcyJkPTQNxJP34FH6LdL_rzgAbgWyoIw1L-foMBotY3bKTch8w_Wy5b6ZekXJYgMCK8KbbQZfCTfdbTGjR1NtWsKDPn9EVJi2Snx6fUXyMyjh3NQMzFWak0QkuQ/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F01.%2520PMO%2F05.%2520Scope%2520and%2520Change%2520Control%2FChange%2520Control%2FChange%2520Request%2520Decks%2FOTC%2FINT-CRXXXX_IF_Pick%2520Process%2520Improvement.pptx%3Fd%3Dw3a2c3ddf9df54b2e89a3c10972ecfad9%26csf%3D1%26web%3D1%26e%3D09fex1 |  | 3. Configuration Change |  | No |  | Low | 0 |  |  | 15 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Being tracked in separate Hypercare log | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| R3 ITC1* | INT-CR1179 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 11. Technology 17. B-App | Eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | WLA APPS Integration with other apps | This is to cover Integration of ERP/SCP with APPS (Advanced Packaging Production Scheduling) platform for Long Term and Straddle Designs starting R3. New POR for WLA changed from FSCO to APPS. Status quo for Front End + DP (FSCO); Assy/Test/Fin (FFS) New Interface/Ownership (slide#3) – Details PDH to APPS (IT owned) XEUS/DIS to S4 (Deloitte owned) APPS to XEUS/DIS (Factory Automation owned) | Tech Solution team aligned that for WLA, APPS could best support IF WLA mfg stage given the state of the existing APPS product availability in the site but with additional new features, including resource and timing to deploy. Shamin (SMDS) and Jeff (Factory Automation) both aligned to move forward with APPS. | Potential new interface may not meet ITC1, pending tech sizing across affected teams | No | Core |  | https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R5?csf=1&web=1&e=6Mrcfe |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-18 | 202 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1180 | Approved | Presenters: Parida, Sunil K sunil.k.parida@intel.com or Celis, Eugene eugene.celis@intel.com | SCP | R3 (Release 3) | High | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 02. E2E Process Integration 07. FTS IF 17. B-App | Eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | CR1167 | xxxx | 9999 |  |  | 12630 | Prospal-Product Shipment Planning and Logistics |  | WIP Inventory Straddle from non S4 plant | PDH Changes: Create Lot to STR mapping for all sites include non-S4 sites Send the mapping and relevant details to PROSPAL (from and to site / plant, batch / MES lot, UPI / MM, Shipping condition) Adjust the lot to STR mapping based on PROSPAL input, if any PROSPAL: Create Lot Level exception based on PDH input Allow to create LLE directly and send back to PDH FFS Changes: | Planning is implemented big-bang in R3. the site still on S4 will use legacy tool (PROSPAL) to ship the lots. Their schedule be based on BY plans and PDH Lot mapping | This was identified during the During detail design of straddle | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR1180_WIP%20Inventory%20-%20Straddle%20%20.pptx?d=w5ffad0487739462ebb78925d2f5e64ca&csf=1&web=1&e=rzYE5L |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 |  |  |  |  | 240 | [8 empty] | 240 | 0 | N/A | Yes | SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-02 | To be taken to the CR Meeting |  |  | 2025-10-03 | • Focused on integrating lot-to-STR mapping for non-S4 sites using Prospal and PDH. • The process will allow lot-level exception handling and shipment creation. • Engineering lots will be handled in a separate, upcoming CR. • Delivery is targeted for ITC2, with resource constraints acknowledged but mitigated by parallel workstreams. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-03 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1181 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | 1. Under PTPE1139_IP, PTPE1139_IF and PTPE1139_CFIN, We need to add invoice data and Payload ID [IR payload and INV payload] for invoice paid status interface, carbon copy integration interface, payment proposal, payment remittance and payment status interface. 2. We need to extend development of PTPE1139_CFIN object for Payment Proposal interface in CFIN system. | ->We need to send invoice date from SAP system to Ariba system for the below mentioned five interfaces- 1.Invoice paid status interface, 2.Carbon copy integration interface, 3.Payment proposal interface 4. payment remittance interface 5. Payment status interface. ->We need to send Payload ID [IR payload and INV payload] from SAP system to Ariba system for the below mentioned four interfaces- 1.Invoice paid status interface, 2.Payment proposal interface 3. payment remittance interface 4. Payment status interface. -> We need to extend development of PTPE1139_CFIN object for Payment Proposal interface in CFIN system. | Business requested these two additional fields after the development of these RICEFW object and we developed Payment Proposal from CFIN to Ariba Network. | N.A. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/2.%20Interfaces/E2Open%20Interfaces/PTPI0369_IF-IP%20Develop%20an%20interface%20to%20send%20inventory%20reports%20and%20MRP%20parameters%20from%20S4(IF)%20%26%20S4(IP)%20to%20suppliers/INT-CR1181_PTP_IP_IF_CFIN.pptx?d=w11a9adc99b82429aac1be2ddf06c6199&csf=1&web=1&e=xKFZcb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-18 | 202 | > 30 Days | suggupta@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 Q4'25 Anafi enablement | R2 Hypercare | INT-CR1183 | Approved | Presenter: Junior and Neetu | ERP | R2 Hypercare | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | LOGI0278 | N/A | N/A | INC14926445 | Delivered |  |  | Anafi | Ship Date Mapping on Labels | Map "Planned Goods Issue" date on Shipping and Carrier Labels from EWM to MPL.​ | Shipping Label and Carrier Label need to reflect Planned Goods Issue Date and not Confirmed Goods Issue Date to reflect correct data on label. | No Impact to the Existing deliveries | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0B720A6E-756C-4348-9536-5FFC329B1F27%7D&file=INT-CRXXXX_IF_Ship%20Date%20Mapping%20on%20Labels.pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  | No |  | Low | 0 |  |  | 5 |  |  |  |  | 10 | [5 empty] | 0 | 10 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o This change is to fix configuration for the customer to send the Planned Goods Issue date o Work needs to be done before the next shipment, which is next week  Having it incorrect on the label will not preclude us from doing the shipment. | [9 empty] | Other | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1184 | Approved | Presenter: John Heiney | SCP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.1 OTC IF - ALL |  | 04. OTC IF | john.p.heiney@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A |  |  |  |  | Anafi | Anafi Demand Data Flow | With Anafi separation, Anafi will be providing demand to Intel in the form of a forecast file. This file will have data at an aggregated level. During the R2 to R3 straddle, OneMPS requires demand at the MM/work-week level of detail to run the legacy process. This CR will add the capability in IF-PDH to ingest the demand file, map it to the Intel FG Items, disagg and pass the data to ECA for backend and to BY CDP for front-end. ECA will then send the back-end demand forecast to SPAN.​ | As Anafi separates and becomes an external Foundry customer, we need a method of ingesting the customer demand forecast and providing it to BY and legacy systems.​ | Design/Development: October​ ITC: November​ UAT/Go Live: December | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B88392030-210B-4363-B6A6-BF256BF86AD7%7D&file=CR_Anafi%20Demand.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cryapark%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA4MTUwMDcxNyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 |  |  |  |  | 240 | [8 empty] | 240 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | Approved to proceed with work | [9 empty] | Design | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1185 | Approved | Presenter: Deb and Junior | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 07. FTS IF 11. Technology | debradas@deloitte.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | 1142 | NA | NA | [5 empty] | Batch determination while creating outbound delivery where batch details will be directly picked up from new POLP table (ZTFTS_TRX_POLP ) | As POLP table is changed from ZTOTC_TRX_POLP to ZTFTS_TRX_POLP previous batch determination logic need to change. With batch already added in new POLP table (ZTFTS_TRX_POLP ) fields, same will be used for the batch determination while creating outbound delivery.​ All Order will be in POLP table and have corresponding MES Lot number. Based on MES lot number (MCHA-LICHA) fetch the SAP Internal Batch and create DN.​ Market Code and Order type validation is not applicable.​ Current logic of Batch as Mandatory don’t change​ Trans Qty will be used to create the DN and not the existing old logic | Identified with recent change of POLP table from ZTOTC_TRX_POLP to ZTFTS_TRX_POLP and If change not done the automatic DN creation with batch lot will not work​ | OTC IF | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B999E6F5A-8956-46B9-AB57-FB457700EA89%7D&file=INT-Build-CR0801%20%25u2013%20POLP%20Straddle.pptx&wdLOR=c9C97FCCA-6850-406E-8CB3-15C034AF1CF5&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 60 | [5 empty] | 45 |  |  |  |  | 0 | 45 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE400 | 1 | LOGE400 | 1 |  | 0 |  | 0 | N/A |  | 2026-03-31 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-18 | o These changes are related to CR1142 for POLP straddle. o There is a testing risk as the team will be manually creating DN’s for ITC1. o This CR will be prioritized once tech capacity frees up. | [9 empty] | Build | Tower | 2025-09-18 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1186 | Approved | Presenter: Rocco De Marino, Naren Mangtani, Ariana Gallardo, Scott Gerwig, David J Park Need to confirm | SCP | R3 (Release 3) | High | 07. FTS IF | 7.12 FTS IF - IF R3 FE Supply Planning & Adv Packaging |  | 07. FTS IF | rocco.p.demarino@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | R3 IF Timeline Revision to push-out non-ITC critical deliverables post-ww02 | 0748 | N/A | [5 empty] | R3 IF Timeline Revision to push-out non-ITC critical deliverables post-ww02 | PDH resource conflict between R2/3, resulting in push-outs of deliverables post-ww02. The post-ww02 deliverables were deemed not gating for ITC1 readiness. The team is requesting approval to modify the due dates for these specific deliverables (as opposed to recover ww02 timeline) | Ongoing resourcing conflicts between R2/3 | No. This is not a Design CR. It is a request to get approval to extend the dev complete timeline for non-ITC gating capabilties. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B63C6368B-B834-4F3D-95BB-E8FB7939178F%7D&file=CR1186%20-%20IF%20SP%20-%20Schedule%20Push%20out.pptx&wdLOR=c91B53D68-499A-4446-897C-65E463B5AE1B&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0116, SCPIFSPPDH0254, SCPIFSPPDH0249, SCPIFSPPDH0223, SCPIFSPPDH0239, SCPIFSPPDH0241, SCPIFSPPDH0250, SCPIFSPPDH0164, SCPIFSPPDH0165, SCPIFSPPDH0166, SCPIFSPPDH0208, SCPIFSPPDH0220, SCPIFSPPDH0240, SCPIFSPPDH0246, SCPIFSPPDH0197, SCPIFSPPDH0252, SCPIFSPPDH0221, SCPIFSPPDH0167, SCPIFSPPDH0276, SCPIFSPPDH0281 | 20 | 20 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o This CR is a formal documentation of the delayed objects that have been communicated for a whole. | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1187 | New |  | ERP | R2.2 May 2026 | Low | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 11. Technology | rsiddharth@deloitte.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  |  |  |  | INC14930703 |  |  |  |  | Change Descartes XML file upload path (MuleSoft Source) to JPO shared path - OTCI0030/31/32 | For IAO R2 release, Descartes is placing XML file at GTS legacy \\sapngpfd.fm.intel.con\fd\gts\dpl\IAO for GTS E4H file upload (zip version) and place an unzip version at \\sapngpfd.fm.intel.con\fd\gts\dpl\IAO for GTS legacy file upload. We need to have the file path change to \\sapjp0fd.intel.com\fd\510\inbox for GTS E4H (zip version). No changes on the unzip version till IAO R3 go live. |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1187_Change%20Descartes%20XML%20file%20upload%20path%20(MuleSoft%20Source)%20to%20JPO%20shared%20path%20-%20OTCI00303132.pptx?d=w00937004401d41ce8eb7ca530958494c&csf=1&web=1&e=oYHImV |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 2 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-19 | 201 | > 30 Days | arumr@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1188 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Material Master Data Construction and Cleansing Effort | Material Master Data Construction and Cleansing Effort | This is a new requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7DFC7CCB-DC64-4758-8B34-3E42518F3452%7D&file=INT-CR1188.pptx&wdLOR=c95348551-1644-4519-9597-1508180FFF90&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 |  | 50000 | [11 empty] | 0 | 0 | N/A | Yes | Conversion | 0 |  | 3168 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-06 | [10 empty] | Other | Tower | 2025-10-06 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-19 | 0 | < 15 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1191 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | suresavula@deloitte.com | [11 empty] | Changes Related to Object FPRE0877_IF | 1) IF WBS BLCK Status: Update BLCK status for restricting the actuals to the WBS based on the STP (Startup)Functional Area Sub Type Flip date. Previous logic was based on the RND Functional Area Sub Type Flip Date. 2)Due to recent changes in the OCOS Subtypes (Remove Ongoing and include Demo & One time event sub types), logic for OCOS subtypes sequence must be changed to RND->STP->MFY->EOL. Previous logic was RND->SUP->ONG->EOL 2a) : Flip date must be in the sequence: RND->STP->MFY->EOL 2b) : Flip date must not overlap with each other. 2c) : If Flip date is blank at any functional area subtype, program must exclude that functional area from the logic 2d) : If any functional area subtype WBS Element is not available in the project, program must exclude that functional area from the logic. 3) Duplicate L3 WBS elements: Search with Dotprocess/Stage+Plant+Co.code+FN_area, if there are more than 1 WBS then don't allow to create |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Suresh Avula to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-19 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1192 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Harshal Bornare |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS-IF object FTSI1014 | Request the cancellation of Object FTSI1014 - IMR - IMR - Interface from SAP ME to auto send Production orders confirmation to SAP S/4 after the completion of Manufacturing​ | As this requirement can be handled through SAP ME and MII configuration, this object is no longer required. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Interface/FTSI1014%20-%20Interface%20from%20SAP%20ME%20to%20S4%20for%20auto%20confirmation%20of%20production%20orders/EXT%20Re%20FTSI1014%20-%20needs%20to%20be%20cancelled.msg?csf=1&web=1&e=tB54OE |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1014 | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-29 | [10 empty] | Other | Tower | 2025-09-29 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-22 | 0 | < 15 Days | hbornare@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1193 | Approved | Presenter: Sekhar | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | To automate creation of Routing & Prod. Versions with reference to SPEED BoMs for IF | To automate creation of Routing & Prod. Versions with reference to SPEED BoMs for IF | In the current process alignment, FTS-IP Team had asked the business team to prepare input files manually to populate routing and production versions for materials. This approach was both time-consuming and susceptible to data entry errors. After business internal discussions, they decided to automate the creation of routing and production versions by leveraging SPEED BoMs, which were already created in the IP SAP S/4HANA system. This automation aims to improve data accuracy, reduce manual effort, and streamline the overall process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1193%20%E2%80%93To%20automate%20creation%20of%20Routing%20%26%20Prod.%20Versions%20with%20reference%20to%20SPEED%20BoMs%20for%20IF%20.pptx?d=w3dce4bcef5a64655a489427993c38b14&csf=1&web=1&e=h5WZzu |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes |  | 4 | FTSE1701, FTSE1653, FTSE1597, FTSE1586 | 3131 | FTSE1701, FTSE1653, FTSE1597, FTSE1586 | 4 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-25 | o AR: Add in the tradeoffs required to pull in this work - @Lingam, Sekhar @Arora, Nishant |  |  | 2025-10-03 | • The team is automating the creation of routings and production versions for Intel Foundry products in IPS4, using BOMs from Speed. • Previously, these files were created manually due to incomplete foundry design and lack of data in the IP world. Now, with the foundry design finalized, manual creation is recognized as too complex and time-consuming. • The automation will support both cutover and post go-live operations, and is required for ITC1 due to the large volume of materials and combinations that need testing. • To prioritize this automation for ITC1, two other already-approved enhancements (including mass upload of production orders) will be deferred to ITC2. These deferred items can be managed manually in the interim. • The automation will be implemented as a custom ABAP program in S4, reviewed and approved by SAP architects. • There are no concerns from the team about deferring the two objects, and the P1 risk associated with this automation will be downgraded once approved. • Decision: Approved • AR: Sekhar Lingam - Downgrade the P1 risk associated with the automation of routing and production version creation. • AR: Kumar Vytla and Sekhar Lingam - Clearly specify which two enhancements are being deferred from ITC1 to ITC2, and why, in the change request documentation. | [5 empty] | Other | Tower | 2025-09-25 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-22 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR1194 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | NA | NA | NA | [5 empty] | Sprint 18 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 18 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | No |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1194&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&csf=1&web=1&e=DjdIo9&CID=072c8397%2D8ca4%2D46e8%2Dae21%2D98c34905254d&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7 | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-08 | [10 empty] | Other | Tower | 2025-10-08 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1195 | Approved | Presenter: Mira Foley, Krishnamoorthy Gopal Need change dates and Sunil's approval. | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 10. Analytics | rawasthi@deloitte.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma |  | CR1155 | N/A | N/A | [5 empty] | ECA view to be created to support Straddle design | change required to support straddle design for scenarios when shipment is initiated from live to non-live plants in SAP. | non live plant inventory gets tracked in CIBR and this data to be shared to ECA which will be the source to feed the information to S4. | N/A | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1195-%20ECA%20view%20to%20be%20created%20to%20support%20Straddle%20design.pptx?d=w2a0471af22064a51837907096b34a491&csf=1&web=1&e=B67IH6 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [9 empty] | 80 |  |  |  | 0 | 80 | ECA | Yes | ECA | 1 | ECAFTSIFV6417 |  |  | 0 |  | 0 | ECAFTSIFV6417 | 1 | 1 |  | 0 |  | 0 | 0 | LOGI1555 | 1 | LOGI1555 | 1 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-25 | o There is no legacy process to close out ECC. This is needed for straddle design as GR’s will be done in new IAO design. o Supply planning requires this one.  Can manually test this in ITC1 as this is the current process for planners o AR: Connect with Dinesh on the implications - @Wuppalapati, Bharadwaj |  |  | 2025-09-26 | • The CR involves closing straddle STOs for legacy plants, complementing Prospal straddle CR1155. The ECA team will support the effort, and it’s aligned with ITC timelines and the build plan. • Roman Vorel asked how ECA would be used to close STOs. It was clarified they’ll use CIBR RVLT transactions to simulate receipt at the destination, then scrap the inventory to avoid double-counting in CIBR and S4 systems. • The functional specification for this work is already included in the build plan, and the timeline targets readiness for ITC2, with dates for TUT and testing already planned. • This CR is closely related to the Prospal straddle CR1155, as both address different aspects of the straddle process for legacy and S4 sites. • Decision: CR is approved | [5 empty] | Other | CL/OSC | 2025-09-26 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | Object Missing in OT |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1197 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Traceable and non-traceable values to be maintained in classification data. | The traceable and non-traceable materials are identified based on the value maintained in material master classification data | Change in existing design |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1197_Material%20Traceability%20attributes.pptx?d=w34d8c0b2e62448cd93c54e147f320a73&csf=1&web=1&e=m5Gnj6 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 20 | [7 empty] | 50 |  |  | 0 | 50 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0076_IP | 1 | DATC0076_IP | 1 |  | 0 |  | 0 | N/A |  | 2026-03-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-09 | o There is some impact to FTS IP because they will have some Boundary applications that will consume these fields o AR: Let Sunil Parida know which Boundary apps will be impacted - @Lejarde, Lilibeth | [9 empty] | Build | Tower | 2025-10-09 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-23 10:57 | 0 | < 15 Days | mghazi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1198 | Approved | Presenter: Sekhar | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP 17. B-App | Sekhar Lingam | [8 empty] | 12208, 59283 | E2open, PDF Sapience Manufacturing Hub Integration Platform - IP |  | Create Zero Lead Time Order for DLCP and Non-DLCP Scenarios to convert Sorted Wafers into Sorted Dies | Enhancement to create Zero Lead Time Order to convert Sorted Wafers into Sorted Dies to consume against Assembly order using DLCP & Non-DLCP scenarios. | External OSATs typically operate without distinct material master records for Sorted Wafers and Sorted Dies. In addition: There is no standard conversion factor from wafers to dies due to variability in die count per wafer. Materials with Dies as a unit of measure are not maintained in the system, making direct consumption against assembly orders infeasible. OSATs do not consume wafers against assembly orders and SAP S4 System may not support wafer tracking in decimals, which leads to challenges in accurate inventory and consumption reporting. As a result, there is a clear need to implement a solution that creates Zero Lead time order to convert from Sorted Wafers to Sorted Dies, This solution will: Converts Sorted Wafers into Dies prior to consumption. Enables die-level tracking and consumption against assembly orders. Aligns with OSAT operational practices and system capabilities. Improves inventory accuracy, traceability, and compliance with manufacturing and financial reports. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/Approval_%20FTS-IP%20New%20CR%20Intake%20Form%20for%20DLCP.pdf?csf=1&web=1&e=Ud9IQW | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1198%20%E2%80%93Create%20Zero%20Lead%20Time%20Order%20for%20DLCP%20and%20Non-DLCP%20Scenarios%20to%20convert%20Sorted%20Wafers%20into%20Sorted%20Dies.pptx?d=we0ad051346f64d3386aa149d3437150a&csf=1&web=1&e=yGuAit | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [12 empty] | 288 | 0 | 0 | N/A | Yes | S4 | 1 | FTSI1681 | 3148 | FTSI1681 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-02 | o Master Data has to add in die-prep items into the BOM because of this CR. o AR: Add in diagrams and statement that this is related to an open design topic that was just closed - @Katzorke, Matt |  |  | 2025-10-03 | • Addresses the need to manage inventory at the die level in SAP, requiring BOM changes and new conversion logic. • High effort required from the master data team; approval withheld pending a detailed impact assessment from Rebecca’s team. • Decision: Not approved; action required to clarify and document master data impacts. • AR: Matt Katzorke - Clarify and document master data impacts. | 2025-10-10 | • Discussed the need to introduce a non-zero lead time intermediate production order to convert wafers into die units between wafer sort and assembly. • This process requires new master data elements and production orders triggered automatically between systems (SMH to S4). • The solution is limited to wafer sort UPI for OSATS and is necessary for process compliance. • Master data impacts were reviewed and approved, with ITC2 handling the automated process and ITC1 managing manual orders for representative cases. The solution is expected to be integrated without major volume impact but is essential for subsequent assembly operations • Decision: Approved |  |  |  | Other | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-23 11:36 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1199 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [8 empty] | WIINGS | DATC0073_IP-Material Master Data Warehouse Management View Conversion additional requirement | 3 More attributes will be included in scope for Conversion of Material Master Data Warehouse Management View | Change in existing design |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1199.pptx?d=wf1fd8faa616e415c82269574011935ed&csf=1&web=1&e=w83noh |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [10 empty] | 50 |  |  | 0 | 50 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0073_IP | 1 | DATC0073_IP | 1 |  | 0 |  | 0 | N/A |  | 2026-02-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-06 | [10 empty] | Build | Tower | 2025-10-06 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-23 11:51 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1200 | Cancelled |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Supply Planning Data Conversion | Supply Planning Data Conversion | Support R3 golive | being assessed | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR0XXX%20-%20SP%20Data%20Conversion.pptx?d=w83e1a7fd0c2c4e8390fe6f0e2a2b4ccb&csf=1&web=1&e=hamg22 |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brian Staab to be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-23 18:43 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1201 | Cancelled |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | WLA RTF | WLA RTF - see form | R3 go live | tbd | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CRxxxx%20-%20WLA%20RTF.pptx?d=w68f40abbf66345a48419d7907afab1ba&csf=1&web=1&e=Rbapcx |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brian Staab to be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-23 19:02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1202 | New |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 01. PMO 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 10. Analytics 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | joaquim.guedes@intel.com | Data & Analytics - Rebecca Verette | E2E - Aishwarya Bhat |  | CR #1028 | RAID #1733 | NA | [5 empty] | Tariffs for Release 3 | Leverage new automation to extend the standard items to COF specific line items in planning and ERP systems where required - Allows data to be maintained on the standard item, but allows planning to commit supply to customer based on tariff requirements by preventing mixing along the mfg flow TCM required to educate users on My Workspace landing page and system access. | New tariff regimes require tracking the country of fabrication (COF) of silicon through the entire manufacturing flow (from wafer to packaged finished good) so that all shipments to customers have the correct Country of Origin identified on shipping documentation | There will be impact to existing work/deliverables. CR is being drafted to scope it out. Please refer to the updated CR for final details. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/Change%20ID_E2E_CR%20IAO%20Tariffs%20for%20R3.pptx?d=w44e7f119f46847e481f12502c16f195f&csf=1&web=1&e=SsNz9E |  | 1. Process Scope / Design Change |  | Yes |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-23 21:07 | 197 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1204 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | DATC0068_IP-Material Master Basic Data Conversion changes | 1. Change in extraction criteria and this is highlighted in blue. 2. Change in source of IFS FERT and DIEN Materials. 3. Change in transformation logic for HERS Materials. 4. Automation of Critical Materials extraction logic 5. Change in Transformation Logic of Placeholder items. | Change in existing design |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC1EC71B-5031-4CA9-BC4E-84D363CE6E55%7D&file=INT-CR1204.pptx&wdLOR=cF6D64F12-1AB1-45F4-B0C4-FF1F5342C2DB&action=edit&mobileredirect=true&previoussessionid=c9546729-8cd2-c2c8-d3e7-7b0c8e447e08 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 100 | [7 empty] | 301 |  |  | 0 | 301 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0078_IP | 1 | DATC0078_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-05 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-06 | [10 empty] | Build | Tower | 2025-10-06 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-24 09:33 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1205 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 11. Technology | Sindhuja Gangireddy | [10 empty] | Anafi | Change in logic to identify type of POLP while sending SO from S4 to ECC | Change in logic to identify type of POLP while sending SO from S4 to ECC | Change in existing design |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1205_OTC%20IF_POLP%20Identifier.pptx?d=w734352b0aa2e454aa11e76d44d7aab0c&csf=1&web=1&e=ICqmLn |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 12 | [5 empty] | 16 |  |  |  |  | 0 | 16 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0410 | 1 | OTCE0410 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | o Changes will be absorbed into the SOW. | [9 empty] | Build | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-24 10:00 | 0 | < 15 Days | sigangireddy@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1209 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Vinay Kumar Khandelwal | [6 empty] | INC14914054 | Open |  |  |  | Need AIF to have Customer name and filtering , there should be an F4 functionality like Standard in AIF as well | Need AIF to have Customer name and filtering , there should be an F4 functionality like Standard in AIF as well | This would be helpful for business for searching the SO's or PO's by name |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7Bf6961c62-89dc-47a0-b54a-301b0087c5e7%7D&action=edit&wdPreviousSession=9ac7b7f3-c91f-2977-a4d3-3850c8313d3d&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cvkumarkhandelwal%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA4MjgxNzkxMiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 14 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-24 13:00 | 196 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1210 | Approved | Presenter: Ananthakrishnan Padmanaban, Barry Scott, Sunil Parida | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 06. PTP 07. FTS IF 08. FTS IP 10. Analytics 17. B-App | alfie.him.yeong.tung@intel.com | FTS (SCP IF) — John Heiney | FTS IP - Loni Adams |  | NA | NA | NA |  |  | 13134 | SAP IBP Supply Management and Materials Requirements Tool |  | Type A (Substrates & Memory) Proactive inventory management capability for SMART IP and IF | Carry forward the proactive inventory management capability for AT/ATTD/OSAT in SMART SAP IBP for the Type A (Substrates and Memory) materials IP and IF inclusive, and the associated technical changes | BY does not have the capability to perform proactive inventory management as performed currently in SMART SAP IBP | High-confidence schedule to complete the build & unit testing by WW12’26 and make it available for ITC2, ensuring no impact to overall IAO-R3 timeline. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B653C0432-2D6B-4E36-B6F3-C78719456CCD%7D&file=Change%20ID_Tower_CR%20Deck_SMART-IP%20&%20IF%20Type%20A%20Proactive%20Inv%20Management.pptx=&action=edit&mobileredirect=true |  | 11. Boundary Apps-related Change |  | No |  | High | 0 |  |  |  | 880 | 1320 |  | 400 | [6 empty] | 2600 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 | ECAFTSIPV6702, ECAFTSIPV6705, ECAFTSIPV6706, ECAFTSIPV6707, ECAFTSIPV6708, ECAFTSIPV6709, ECAFTSIPV6704, ECAFTSIPV6703, ECAFTSIPV6710, ECAFTSIPV6711, ECAFTSIPV6712, ECAFTSIPV6713 | 12 | 12 |  | 0 | SCPIPSPPDH0132, SCPIPSPPDH0133, SCPIPSPPDH0134, SCPIPSPPDH0136, SCPIPSPPDH0138, SCPIPSPPDH0140, SCPIPSPPDH0141, SCPIPSPPDH0142, SCPIPSPPDH0143, SCPIPSPPDH0146, SCPIPSPPDH0147, SCPIPSPPDH0148, SCPIPSPPDH0162, SCPIPSPPDH0163 | 14 | 14 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-02 | To be taken through CR Meeting |  |  | 2025-10-03 | • Extends SMART’s detailed planning capabilities to all BOM part types, not just B-types, due to Blue Yonder’s limitations. • Requires new development for IP and extension for IF. • IAO incremental funding of $180K for 2026 is required, the budget will need to be scrubbed to fit this into the current budget envelope. • Decision: Approved, pending budget alignment and ECA confirmation. | [5 empty] | Other | CL/OSC | 2025-10-03 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-24 15:12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1211 | Approved | Presenter: Puttasandra Jagadeesh | ERP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | Junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  |  | New | N/A |  |  |  |  | Anafi | Anafi Label Changes | New customer (ANAFI) is requesting the inclusion of a new field (1P/OPN) in their custom label. | Today, 1P/OPN is not mapped from EWM to MPL on label XML's. This is a new request for customer (Anafi). | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBB198A05-C5BD-4E99-AB83-8D5580605A58%7D&file=INT-CR1211_IF_ANAFI%20Ship%20Label_OPN%20Field.pptx&action=edit&mobileredirect=true&CID=8F4ED969-D2C9-4CAE-8537-CF9BF4B4D403&wdLOR=c923E47B6-7098-4F08-8EFB-61BBB6677A87 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 15 | [5 empty] | 30 |  |  |  |  | 0 | 30 | N/A | No |  | 0 | N/A | 3142 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0278 | 1 | LOGI0278 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-09 |  |  |  | 2025-10-10 | • CR is for a small enhancement to map an unmapped material field from EWM to MPL on label XMLs for Anafi. • This change ensures label compliance for both outer and inner box labels and is scheduled for December 2025 deployment. • The effort is minimal and considered low risk • Decision: Approved | [5 empty] | Build | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-24 19:17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1212 | Cancelled |  | ERP | R4 (Release 4) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 03. FPR 04. OTC IF 07. FTS IF 09A. Master Data 09B. Data Migration 11. Technology 13. Security 15. Cutover 16. Testing 17. B-App | ravishwanathan@deloitte.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | Requirement of additional business resources for testing & support for Implementation of SIMS Processes for Release 4 | NA | NA | [5 empty] | SIMS process | Requirement of additional business resources for testing & support for Implementation of SIMS Processes for Release 4 | Additional resource required - 5 Core OTC (OM, BR, Return) – 3 FTE Logistics – 1 FTE GTS – 1 FTE Duration - 8 month From Nov 2026 (Start R4 ITC1) till July 2027 ( R4 Go-Live) Scope - This covers testing, cutover & deployment of below scenarios under SIMS Process :- Outbound SIMS :- SIMS to IF (S/4 Plant) internal sale SIMS to IP External Sale SIMS to IF (S/4 Plant) internal sale (Intra) SIMS to IF (ECC Plant) internal sale Returns SIMS :- 1A – Internal Sale (Return PO with Credit) 1B – Internal Sale (Return PO with replacement) FG/SFG 1C – Internal Return for Repair with stock from front office 1D - Internal Return for Repair Not ODM Induced (Invalid return) 1E – External Sale (Returns with Credit) 1F – External Sale (Returns with Exchange) 1G – External Return for Repair with stock from Front office * Additional Deloitte resource requirement will be estimated later | No risk identified on this change | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR1212-R4%20SIMS%20RICEFW%20Details.pptx?d=wce0664d675b8467ebb8c21949ef2a726&csf=1&web=1&e=BdIN9o |  | 1. Process Scope / Design Change |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Stacee that the team no longer needs this CR. Jill Matalon sent email on 4/2 that SIMS is already included in R4 Scope | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 11:36 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1213 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | srihk@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | New Enhancement required for to make PO price updates for HVM OSAT and SIFO orders for no GR done yet and partial GR posted | Enhancement to make PO price updates for open and partial GR’s (Exclude Engineering and Rework orders) . 1) HVM OSAT PO orders based on the service PIR price no goods receipt(GR) or partial GR completed 2) HVM SIFO PO with material contract with no goods receipt(GR) or partial GR completed. | Currently, Commodity Managers are updating the prices (~500/yr) before material ship out and allow Intel to achieve approx. USD 5.3 million cost savings(FY25). The cost savings are achieved largely from yield improvements at Sort and Test stages For Intel to achieve these savings, Intel CMs must continue to be able to update prices timely at material ship out. (price determination at ship out) therefore PO price update need to be automated when pricing changing in underlying document.Currently, Commodity Managers are updating the prices (~500/yr) before material ship out and allow Intel to achieve approx. USD 5.3 million cost savings(FY25). The cost savings are achieved largely from yield improvements at Sort and Test stages For Intel to achieve these savings, Intel CMs must continue to be able to update prices timely at material ship out. (price determination at ship out) therefore PO price update need to be automated when pricing changing in underlying document. | No risk for ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1170_Enhancement%20to%20make%20PO%20price%20updates%20for%20HVM%20OSAT%20and%20SIFO%20orders%20for%20no%20GR%20and%20partial%20GR%20posted%20%20-%20%20Read-Only.pptx?d=w3cc70a046f354732aae9e9153c63e9e2&csf=1&web=1&e=5vuW1e | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | PTPE1644 | 3121 | PTPE1644 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-09-25 | o Since this will come into ITC2, the workaround is to manually update prices for ITC1. |  |  | 2025-09-26 | • The CR is to enhance the purchase order price update process for HVM OSAT orders, addressing limitations in the standard MEI1 transaction that only works for material-based PIRs but not for service PIRs or text-based purchase orders. • The enhancement will implement a standard BAPI to automate price updates, replacing manual interventions currently performed by commodity managers. The volume is about 500 updates per year, with an estimated cost savings of $5.3 million. • This medium complexity enhancement is included within the current budget. It will skip ITC1 and enter at ITC2. This will proceed through the RICEFW intake and technical team architecture review process. • Discussions clarified that manual processing would continue during ITC1, and the automation will be tested independently. Business representatives confirmed the enhancement addresses existing manual workload without introducing new capabilities. The team expects a straightforward implementation using a standard BAPI rather than complex AI solutions. • Decision: CR is approved | [5 empty] | Other | CL/OSC | 2025-09-26 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-25 16:45 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1214 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | NAMAN JAIN |  | FPR - Aubrey Hinderlider | [9 empty] | Changes in COGS calculation and posting as per legal and group valuation. | According to the original design, the COGS (Cost of Goods Sold) calculation and posting for the FPRE0475 ( Unissued Return Credit not Accrual) were based on the transfer price (ZTPR). However, following the latest alignment, COGS calculation and posting should now be performed using the standard cost (VPRS). Currently, COGS calculation and posting occur only for legal valuation. Based on recent discussions, the business requires COGS to be posted for both legal (Cost) and group (Cost) valuations. We need to identify the logic to capture group valuation at the material and plant levels, so it can be used for posting the FPRE0475 ( Unissued Return Credit not Accrual). To accurately identify the COGS (Cost of Goods Sold) value for the KW00 condition in S/4HANA, it is necessary to include two additional field during the data extraction process and same will update in custom table (ZTFPR_RET_UICP). These columns should be based on the KW00 condition requirements. The relevant Group Valuation amount for each record can be obtained by referencing the PRCD_ELEMENT and CKMLPR tables within S/4HANA. | Requirement for Business to Recognize the COGS at group and legal valuation level by using standard cost. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1214%20%E2%80%93FPRE0475%20%20Changes%20in%20COGS%20calculation%20and%20posting%20as%20per%20legal%20and%20group%20valuation..pptx?d=w8dda182d408e4726ade4f07cfe6009ea&csf=1&web=1&e=oky7Fx |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 45 | 0 |  |  | 12 | [5 empty] | 45 |  |  |  |  | 0 | 45 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FPRE0475 | 1 | FPRE0475 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-02-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-16 | o This was identified during FUT, and it is a logic change. o We need to use a different condition type to do COGS changes. o In ITC1, we will be able to test for 1 currency. If not, we can do manual postings. | [9 empty] | Build | Tower | 2025-10-16 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-25 17:38 | 0 | < 15 Days | namanx.jain@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
R2 (Hypercare) | R2 Hypercare | INT-CR1229 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Vicki Perry |  |  |  | SCP-CR.004 | [7 empty] | Approved: IAO_SC_R2_2_IF_SPAN FSTP Integration | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/_layouts/15/Doc.aspx?sourcedoc=%7B18691D40-4B80-43B1-9B37-B3B4CC707571%7D&file=IAO_SC_R2_2_IF_SPAN_FSTP_Integration.pptx&action=edit&mobileredirect=true | [7 empty] | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-24 | Confirmed by Upali Dutta and Rocco to be approved and closed | [9 empty] | Build | Tower | 2025-11-24 | 11, 2025 | 11, 2025 | 09, 2025 | 2025-09-25 19:52 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1228 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Tushar/ Rob |  |  |  | SCP-CR.013 | [7 empty] | Approved: R2 Must Have Reports (Outside of BY)- P5 - Post WW5 | [8 empty] | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-01 | Confirmed by email from Upali to be approved | [9 empty] | Build | Tower | 2025-12-01 | 12, 2025 | 12, 2025 | 09, 2025 | 2025-09-25 19:52 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1232 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Mike Lenau |  |  |  | SCP-CR.087 | [7 empty] | Safety Stock |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 19:52 | 195 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1217 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Rob Cassalia |  |  |  | SCP-CR.117 | [7 empty] | Automation of Expedite Process |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 19:52 | 195 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1224 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  |  | Scott Palmer |  |  |  | SCP-CR.114 | [7 empty] | 11/25: Approved for R3, will run thru CRT process for pull-in to R2 (Jim G) Visibility of weekly consensus forecast snapshots full solution |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 19:52 | 195 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1233 | Cancelled |  | SCP | R2 Hypercare R2 Nov 2025 | Very High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 06. PTP 08. FTS IP 11. Technology | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | n/a | IAODTM-6915 (JIRA Ticket) | n/a | [5 empty] | IBP BY - RTF and PO consumption change | Explain the Issue: IF indicated in a call on 8/25 that we should consider RTF and POs as separate signals. The RTF does not include POs committed. If we have POs committed beyond NNSD, we need to account for this in the RTF load somehow or change logic in BY. Chug, Nikhil was on the call when we learned this from IF team. Mena, Marissa confirmed the external RTF includes POs committed beyond NNSD | current configuration does not support Go-Live business process. not a showstopper for Go-Live Planning Cycle, but a showstopper for HPC Planning Cycle #1 (ww47.0 IP BY IBP solve) | TBD | No |  |  | https://jira.devtools.intel.com/browse/IAODTM-6915 |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 19:53 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1234 | New |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  |  | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | [9 empty] | IP BY CDP Relative Time Fields for DP | In order to automate changing the Qtr / month / Year, need to bring in Relative Year, Relative Qtr, Realtive Month, Relative WW Fields to BY CDP (Already in ECA Demand) |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 20:07 | 195 | > 30 Days | anthony.romano@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1235 | Cancelled |  | SCP | R2 Hypercare | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [10 empty] | IP BY CDP - Realign/Move data due to Node expiration | Provide a way to configure / automate Moving Data from one leaf or mid-level node to another (e.g. Source FG to Target FG, Source MFI to Target MFI) in prep for Node Expiration | current process is 100% manual and not sustainable for all of R2. Prone to error |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni that this is not required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 20:14 | 0 | < 15 Days | anthony.romano@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1236 | Cancelled |  | SCP | R2 Hypercare | Very High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP 10. Analytics | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [10 empty] | Profit Center Adjustment to Gross Billings | Current system assignment of profit center to billings is incorrect | Billings data split by profit center has errors |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 20:20 | 0 | < 15 Days | anthony.romano@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1239 | Cancelled |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [10 empty] | Incorrect calculate measures in BY CDP | Certain measures have incorrect calculations | Data is incorrect confusing users |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 20:30 | 0 | < 15 Days | anthony.romano@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1238 | Cancelled |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [10 empty] | Modify Disag logic in BY CDP | Need to change the logic from prior CD pub to CD pub | Disag logic is using old data to calculate. |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 20:30 | 0 | < 15 Days | anthony.romano@intel.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1237 | Approved |  | SCP | R2 Hypercare | Very High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP 09B. Data Migration 11. Technology 12. Infrastructure 17. B-App | maida.buglino@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | INT-CR0634 (rejected due to short window to UAT), still needed, showstopper for ww47.0 HPC Cycle | n/a | N/A | [5 empty] | IP SP - Send Day 0, Day 3 Output Downstream (including external wafers, Mega CR Part 1) | BY IBP and PDH to Send Day 0 and Day 3 Planned output to Compass & OneMPS. This includes the constrained, flex-constrained and flagged for publish team scenario (default to Team A). The technical work is needed to support the existing business design during Release 2. | Compass and OneMPS are expecting the PRF for Day 0 of Solve week (Sunday), Day 3 of Solve week (EOD Wednesday), and Executive Week (Thursday) published planned output. R2 Front End (BY) and Back-End (OneMPS, COMPASS) planning processes need be kept ina synch for both 0-12 months. (OneMPS) and 13-24 months (COMPASS) planning horizons per design. This technical change supports the original design by ensuring BE processes start their process limited by the FE output, including the planner adjusted output. | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CR01237-%20Multiple%20Sends%20downstream%20+%20External%20send%20downstream.pptx?d=we7783462b7954fc394b0338c8fc5beb0&csf=1&web=1&e=kjphan |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | Approved during R2 SCP Hypercare Ingestion call | [9 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 09, 2025 | 2025-09-25 20:26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1240 | Cancelled |  | ERP | R2 Nov 2025 | Very High | 04. OTC IF | 3.10 FPR - Accounts Receivable & Collections |  | 04. OTC IF | Jason.carmichael@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR0573 | None | None | [5 empty] | PRF Invoice to SFTP | Add an output condition record to enable PDF formatted invoice output by customer to a configurable SFTP folder. | Identified as a gap during Customer Onboarding | None | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B663C5B23-4865-4B00-8A3E-C94667B9A0A0%7D&file=INT-CR0573%20Invoice%20PDF%20SFTP.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Low | 0 |  |  | 10 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is a duplicate of CR0573 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1241 | Cancelled |  | SCP | R2.2 May 2026 | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | amy.loomis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - Flattop Mountain - Automate Inventory Load | https://jira.devtools.intel.com/browse/IAODTM-6551 Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW10'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW10'26 | Will impact R2.3 | No |  |  | To be Provided later |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1242 | Cancelled |  | SCP | R2.1 Feb 2026 | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | stephanie.anderson@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - 0 Bin split logic in BOM MCP UI | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW10'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW10'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW10'26 | No |  |  | Will impact R2.3 |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1243 | Cancelled |  | SCP | R2.1 Feb 2026 | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | lexey.sbriglia@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - ITE forecast "ITE PRF is displayed in Capacity Corridor and in wafers in E2Open in the wrong path" | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 The ITE PRF is displayed in Capacity Corridor and in wafers in E2Open in the wrong path. The PRF is exchanged in PCs and in UPI granularity in E2Open per customer requirement. Need PDH solution to send PC and UPI granularity to the OSAT path in E2Open for this customer and future customers if necessary. | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Will Impact R2.2 | No |  |  | To be Provided later |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:34 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1244 | Approved |  | SCP | R2 Hypercare | Very High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 11. Technology 12. Infrastructure | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | n/a | n/a | n/a | [5 empty] | BY IBP - PR Edit Bundle | Ability to edit as follows: (PR Edit Bundle) Part 1) Wafer Type 1, Type 2, PRF Import Capability for Edits and Add Part 2) Edit/Override PR Type | data quality and cycle time support issue (not resourcing issue) | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CR1244-%20PR%20Edit%20Capability.pptx?d=w2c2cb36d71d54b51bdfc88583938363a&csf=1&web=1&e=JMc9qO |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [5 empty] | 40 | [7 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-03 | Approved offline with Kumar Vytla and Chad Smith | [8 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Other | Tower | 2026-02-03 | 02, 2026 | 02, 2026 | 09, 2025 | 2025-09-25 21:35 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1245 | Cancelled |  | SCP | R2 Dec 2025 | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | britta.davis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - Hide flex supply signals for external parts in OneMPS | https://jira.devtools.intel.com/browse/IAODTM-4722 Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Will Impact R2.2 | No |  |  | To be Provided later |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:37 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1246 | Cancelled |  | ERP | R2 Oct 2025 | Very High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR1073 | None | None | [5 empty] | Commercial Invoice Line Item Numbering | Commercial Invoices and Packing Lists with multiple batches to show the Line Item on the form as "10-X" | For customer consumption and OpenText messages, create unique identifier on the form per new line item when multiple batches or countries of origin are present in the form. | None | No |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1073_IF_R2_Commercial%20Invoice%20Line%20Item%20Numbering%E2%80%8B.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Low | 0 |  |  | 8 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Dilky Bruggeman that CR1246 was a duplicate of CR1073 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:40 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1247 | Cancelled |  | SCP | R2 Dec 2025 | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | jeffrey.maclaren@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - External RTF E2OPen Extension (10-24mo) | https://jira.devtools.intel.com/browse/IAODTM-6298 this was a design miss in testing. IT already committed to address for WW50.6 Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Will impact R2.2 | No |  |  | To be Provided later |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:42 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1248 | Cancelled |  | SCP | R2.1 Feb 2026 | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | rajbir.k.girn@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP SP - AT WIP Design to forward project (automated) | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Added to have visibility of it for CIP R2 releases, Details will be provided in the CR Template Sizing and Template expected WW05'26 | Will impact R2.2 | No |  |  | To be Provided later |  | 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Gabriel that SP Operations Team has made prioritizations and for now those are out of the ranking | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 21:48 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1249 | Cancelled |  | ERP | R2 Oct 2025 | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | matthew.nisenboym@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR1095 | None | None | [5 empty] | Pricing Report for NRE Discount | Generate an NRE Price Report that lists all sales orders where the ZNRE condition type is applied. For each customer, show the total NRE discount consumed to date and the remaining NRE discount balance, based on their agreed NRE allocation. | Currently, we do not have a report in place that allows us to check how much NRE discount has been offered to a customer, how much has been consumed, and what remains available for the customer's future consumption | N/A | No |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1095-Pricing%20Report%20for%20NRE%20Discount%20.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 |  |  | 16 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is a duplicate of CR1095 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 22:02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1250 | Cancelled |  | ERP | R2.1 Feb 2026 | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR1072 | N/A | N/A | [5 empty] | Wafer Die Export Invoice Forms Clean-up | Remove Wafer Quantity and Die Quantity fields from the Export Commercial Invoice and the End-Customer Invoice. | Align Export Commercial forms with a request from ITG to remove Wafer and Die fields from our forms. | Can be completed by start of ITCI | No |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1072_IF_Wafer%20Die%20CI%20Forms%20Clean-up.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is a duplicate of CR1072 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 22:11 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1251 | Cancelled |  | ERP | R2.1 Feb 2026 | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | CR1084 | N/A | N/A | [5 empty] | XML files Transfer from PRD Share drive to QA environment Share drive OTCI0030, OTCI0031, OTCI0032 | XML files transfer from PRD to QA shared drive for objects OTCI0030, OTCI0031 and OTCI0032 | As a part of RICEFW OTCI0030,31 and 32, the files procured from Descartes are placed in the share path \\sapjp0fd.intel.com\fd\510\GTS_Descartes. In order to keep the testing system up to date, the request is to have the same file copied to the QA environment so that it can be uploaded into the test system. This will help in keeping the xml files updated in the test system in sync with production system and will be used for any future testing. | Address Compliance Gap | No |  |  |  |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Ridhi that this needs to be cancelled as per GTS team | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 22:17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1252 | Cancelled |  | ERP | R2.3 Aug 2026 | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR0550 | N/A | N/A | [5 empty] | Implement new SFTP mapping for order creation and changes | Implement an update to the EDI SFTP mapping for order creation and changes to support a new customer PO file format. Creation and updates ( Change) will be sent separately but in the same format. The creation process will linearize quantities by the number of weeks in a month into separate order lines, utilizing the customer provided RDD. Additionally, it must capture the customer's customer PO in the sales order ‘s Ship-To Party Customer Reference field. Update the Backlog Report in ECA to include Customer’s final Ship To ID and Ship-To Party Customer Reference field. | The current SFTP EDI process does not support the customers file format. This is to be expected when onboarding a new customer using SFTP. | None known | No |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1072_IF_Wafer%20Die%20CI%20Forms%20Clean-up.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | Medium | 0 |  |  | 4 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is a duplicate of CR0550 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 22:25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1253 | Cancelled |  | SCP | R2 Dec 2025 R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP 09A. Master Data 11. Technology 12. Infrastructure 17. B-App | stephanie.anderson@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | WIP | https://jira.devtools.intel.com/browse/IAODTM-6711 | N/A | [5 empty] | IP SP - PDH BOM MCP flag Has Full Speed BOM "N" when it's valid | Snow Ridge MCP item (pairs with Cedar Fork) being flagged as not having a Full SPEED BOM when I see a valid Full BOM in SPEED. We would expect the Has Full SPEED BOM to be set to "Y" for this particular combination Die Code Name: SNOW RIDGE-24; Item (FG) : 99AM44; Comp Concat: 2000-214-517¦1¦2000-216-053¦1 | Data quality high risk. Aligned with PDH to HPC deployment during UAT 2 | TBD | No |  |  | https://jira.devtools.intel.com/browse/IAODTM-6711 |  | 3. Configuration Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-25 23:35 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1255 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Ashish Vinayak Patil |  | FTS IF - Haritha Komma | [9 empty] | Cancellation of FTS IF Object FTSI1566 | Request the cancellation of Object FTSI1566 - Interface from FFS to S4 to maintain POLP table. | Due to changes in straddle design, data from production scheduling feed (FSCO, FFS, Apps) will be ingested to ECA and then to S4 to maintain IF POLP table. (FSCO/FFS/Apps  ECA  S4). FTSI1566 will be cancelled, and FTSI1159 logic will be updated to pull FSCO/FFS/Apps data from a single source in ECA to S4. Unless the design changes after R5, this interface will remain the POR. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1255/EXT%20RE%20FTS-IF%20POLP%20Objects.msg?csf=1&web=1&e=Sds9x1 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1566 | FTSI1159 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-09-30 | [10 empty] | Other | Tower | 2025-09-30 | 09, 2025 | 09, 2025 | 09, 2025 | 2025-09-26 04:54 | 0 | < 15 Days | avinayakpatil@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1257 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 09B. Data Migration | Tanmaya H J |  | PTP - Richard Taylor | [9 empty] | PTPC0176_IP_IF_02_Purchase Order Conversion | 1.Extraction and Transformation of Ariba PO fields 2.To extract values from text field from ECC to load into your reference field at header level in S4 in EMS scenario 3.To extract values using FM- VC_I_GET_CONFIGURATION in ECC and load into text fields ( Handedness and CEID ) in EMS scenario 4.Extraction of PO with doc type ZIMR & ZSP for specific vendors and transforming single PO into 2 STO and loading into S4 system 5.Addition of 2 to 3 fields in all scenarios | 1. New scenario for IMR PO Conversion is added where WIINGS ZSP PO for specific vendor in ECC is converted into 2 intracompany STO 2. For creation of Ariba PR in Ariba System, PO fields are required rather than PR fields 3. For EMS PO, few fields from text needs to loaded into header and item text |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1F6F1DB3-BF32-4BC1-BE94-259C458B298F%7D&file=INT-CR1257.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 135 | 0 | [10 empty] | 135 |  |  | 0 | 135 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPC0176_IP, PTPC0176_IF | 2 | PTPC0176_IP, PTPC0176_IF | 2 |  | 0 |  | 0 | N/A |  | 2026-01-02 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-09 | o This CR encompasses enhancements to an existing RICEFW resulting from FUT and design changes. o This will be picked up in the next sprint 19 for development. | [9 empty] | Build | Tower | 2025-10-09 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-26 13:27 | 0 | < 15 Days | thj@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1256 | Cancelled |  | SCP | R2 Dec 2025 R2 Hypercare | Very High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 09B. Data Migration 11. Technology 12. Infrastructure 13. Security | alfred.j.schrems@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | WIP | n/a | N/A - ww40.5 | [5 empty] | BY IBP - Demand WIF Import capability | ability to import different demand scenarios into BY IBP for what-if purposes, in order to understand implications to the supply plan under different demand pictures | no demand what-if capability is available in BY IBP for further analysis of supply plan implications | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/Change%20ID_Tower_CR%20Deck_template%20-%20PO%20Edit%20Import%20Capability%20.pptx?d=w2c2cb36d71d54b51bdfc88583938363a&csf=1&web=1&e=v4clfE |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-26 13:08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1258 | Approved |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP 11. Technology 12. Infrastructure | amy.loomis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | WIP ww40.5 | n/a | N/A | [5 empty] | Demand - Demand Prioritization breakout into multiple time buckets | Demand - Demand Prioritization breakout into multiple time buckets | to enable and secure adequate supply support to demand prioritization across different time horizons | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CR1258%20Break%20out%20yr2%20priorities%20in%20multiple%20buckets.pptx?d=w948a9adc0e824efca7b5418647b7955a&csf=1&web=1&e=0jGH2C |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [5 empty] | 360 | [7 empty] | 360 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | Approved during the R2 SCP Hypercare call | [9 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 09, 2025 | 2025-09-26 13:30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1259 | Approved |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP | amy.loomis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | WIP ww40.5 | n/a | N/A | [5 empty] | IP SP - Add Safety Stock bands | add functionality to manage Safety Stock targets in ranges (bands) | this will have a direct impact on improving the prioritization of Safety Stock supply support plan | TBD | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CR1259%20SS%20Band%20v1.pptx?d=w88e8dcac316848978dd2d3dad98d6741&csf=1&web=1&e=94snn4 |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | Approved during the R2 SCP Hypercare call | [9 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 09, 2025 | 2025-09-26 13:34 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1260 | Cancelled |  | SCP | R2 Dec 2025 R2 Hypercare | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP 11. Technology 12. Infrastructure | amber.wespi@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | WIP ww40.5 | n/a | N/A | [5 empty] | BY IBP - Modeling Reticle Constraints | we have no way to model reticle constraints beyond PO month in BY with current design | need to make sure plan has all critical constraints modeled in order to ensure feasibility of the plan for the entire horizon | TBD | No |  |  | WIP ww40.5 |  | 3. Configuration Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this was not listed as open in Upali Dutta's email | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-26 13:37 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1261 | Approved | Presenter: Imran | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology | iathar@deloitte.ca | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA |  |  |  |  | WIINGS | Stock movement from vendor owned to intel owned | Develop a custom enhancement for the 3B13 and 2B2 PGI processes to verify whether the stock is vendor-owned. If so, automatically post an internal transaction to transfer ownership to Intel, ensuring completion of the receiving process. | This enhancement is needed to move the stock from vendor owned to intel owned | Ready | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR%20Stock%20movement%20from%20vendor%20owned%20to%20intel%20owned%20.pptx?d=wd7dffbca7f5c4054a36c6aed5d4f314c&csf=1&web=1&e=1labgy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  | 3710 | 8 | [5 empty] | 45 |  |  |  |  | 0 | 45 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1450 | 1 | LOGE1450 | 1 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | o Enhancement will check whether the stock is Intel-owned or not.  This is a conversion of vendor stock to Intel stock, and it is automatic. o This work is related to WIINGS, so there is a some dollar amount which Susan and Cari is funding. o This is done in ITC2 because the tech team cannot take it on. | [9 empty] | Build | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-26 14:25 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1263 | New |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP 10. Analytics | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [10 empty] | Demand Prioritization Dashboard enhancements | Update demand prioritization dashboard to retrieve and display POR data -BU Fin POR Qty, and BU Fin POR Amt, CD Margin and Wafer Cost data (this is not a new requirement. It's missed in R2) "The business needs the capability to analyze data segmented by capacity corridor from the SnOP Process. For instance, demand leaders should be able to review the prioritization distribution across capacity corridors to ensure that no single corridor is disproportionately weighted with High Priority classifications. Transform CD and POR data into wafer outs and present the results in the Dashboard. " Update Demand Prioritization Dashboard Refresh timings to reflect latest CD , POR KFs and demand prioritization data from data sources - profisee, ECA, PDH views/tables, etc. Prior snapshots/versions of data should be available for audit purposes. Use CD benchmark, Profisee (master data job) and PDH translation job as benchmarks to save versions. These snapshots do not necessarily need to appear on the dashboard. | In order to use dashboard need enhancements and correct design/development miss from R2. | [6 empty] | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-26 16:20 | 194 | > 30 Days | anthony.romano@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1264 | Cancelled |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Anthony Romano | FTS (SCP IP & OP) — Chad Smith | [24 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-26 16:26 | 0 | < 15 Days | anthony.romano@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1262 | Approved | Presenter: Imran Need to add in ITC1 workaround | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology | Karthikeyan P P | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | CR0700 | NA | NA |  |  |  |  | WIINGS | NSO forms to be updated with STO logic for few fields | NSO forms such as Packing list and Commercial Invoice, will be leveraged for STO as well. Based on alignment with Business there are few logics to be added in the existing object to leverage the existing NSO forms to print the CI and PL forms for STO Delivery as well. | In R2 OTC is using Enhancement to trigger the Performa Invoice once the packing status is completed for the Delivery. In STO there are some commodities where the Packing is not relevant and so lift and shift from OTC logic will not work. FTS will leverage the same logic and add additional logic for new Routine where Packing in not relevant for STO. By this approach, the R2 object will not be impacted | No Impact to existing deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B82813378-EF3C-4464-9BE2-77597367F5C7%7D&file=INT-CR0650%20%25u2013%20NSO%20forms%20to%20be%20updated%20with%20STO%20logic%20for%20few%20fields.pptx&wdLOR=c8FE5C7D1-F930-4106-A994-754A211A719E&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | High | 0 |  |  | 32 | [5 empty] | 218 |  |  |  |  | 0 | 218 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0349_IF, LOGF0359_IF, LOGF0349_IP, LOGF0359_IP, LOGE1450 | 5 | LOGF0349_IF, LOGF0359_IF, LOGF0349_IP, LOGF0359_IP, LOGE1450 | 5 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Leveraging NSO forms for all logistics processes - After trade feedback, they have asked for fields to be consolidated for IF and IP in order to be compliant. FS was created with base requirements. - Layout remains intact, but logic will change - No other team impacted | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-26 15:13 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1265 | Approved | Presenter: Imran | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology | iathar@deloitte.ca | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Supplier batch number instead of internal batch number | We currently share batch information via outbound PIP’s with our 3PL partners and receive it for inbound shipments using the standard IDOC segment, which captures the batch number. However, the business requires us to also provide the supplier batch number (CHAR > 15). To address this, we propose enhancing a IDOC segment LICHN or ATWRT Based on the character value it should fetch and pass it in CHARG in mulesoft. Similarly, vice versa should happen in inbound. | The Standard segment needs to be enhanced to capture this information | No Impact to existing deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR0737%20%E2%80%93%20Supplier%20batch%20information%20to%20be%20shared%20instead%20of%20internal%20batch%20number.pptx?d=w94791554cbf0474ebe3d564022bcf86b&csf=1&web=1&e=0erbhP |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 30 | [5 empty] | 76 |  |  |  |  | 0 | 76 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI1038, LOGI1043, LOGI1037, LOGI1053, LOGI1040, LOGI0237​, LOGI1041, LOGE1450 | 8 | LOGI1038, LOGI1043, LOGI1037, LOGI1053, LOGI1040, LOGI0237​, LOGI1041, LOGE1450 | 8 |  | 0 |  | 0 | N/A |  | 2026-04-17 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | o Team will add logic to refer to the supplier batch number instead of internal batch number. o Original plan was to send the internal SAP batch number, but then there was a switch in requirements.  Communication with supplier was a little late. These objects were done with development. o This impact is just on the S4 side, not the 3PL or OpenText.  Deloitte team will be manually change the numbers to run the E2E scenario.  ITC1 volume is okay to handle because we are not planning to test all 3PL suppliers. | [9 empty] | Build | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-26 16:50 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1266 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.8 PTP - QM |  | 06. PTP 09A. Master Data | anantjoshi@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor |  | PTPI1153 | NA | NA | [5 empty] | ILM to MDG - Deactivation Signal | We need to change the design for the Deactivation Signal that is coming from ILM and reaching MDG and S/4 | The Excursion created at ILM is intended to unique combination of Intel Part Number, Site and Supplier relation. But in SAP, Intel Part Number are activated per site and not with unique to supplier. So, if ILM wants to deactivates Inspection Type at Material Master with respect to single supplier, it is not possible if open Excursion is present already in the system. | No, we will try to get it ready by ITC1, if not definitely for ITC2. | No |  |  | Placeholder |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-26 18:45 | 194 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1267 | Approved | Presenter: Imran | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Manmohan Jha | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | LOGE0936 | NA | NA | [5 empty] | GR Processing for Consignment Pickup | The process begins with creating a consignment pick-up order in SAP to receive stock from the customer consignment hub. EDI signals facilitate seamless communication between SAP and the third-party logistics (3PL) warehouse management system (WMS), enabling automatic posting of inventory movements. This integration ensures that inventory transactions are accurately reflected in both systems, streamlining operations and reducing manual intervention. By leveraging EDI for real-time updates, the process enhances visibility and control over consignment inventory, supporting efficient stock management and timely reconciliation between SAP and the 3PL WMS.​ | LOGI0950 serves as an interface object within our system. To improve the consignment pickup process, we propose an enhancement to be incorporated into LOGE0936. This enhancement should trigger a transfer posting using movement type 309 prior to executing the goods receipt for consignment pickup. By implementing this change, we can ensure that inventory is correctly transferred and accounted for before the goods receipt is processed, thereby reducing errors and improving overall efficiency in inventory management. This proactive step will help streamline operations and support accurate tracking of consignment inventory movements. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-Build-CR0804%20%E2%80%93%20GR%20Processing%20for%20Consignment%20Pickup.pptx?d=w56f4bbb30b7d40b3863394a198f0d844&csf=1&web=1&e=kLmIUF |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 34 | [5 empty] | 36 |  |  |  |  | 0 | 36 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0950, LOGE0936 | 2 | LOGI0950, LOGE0936 | 2 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | o Related to the VMI consignment process, and the CR is to take care of the inbound process. | [9 empty] | Build | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-29 05:54 | 0 | < 15 Days | manmjha@deloitte.com |  | No | FUT Not Started | No Objects |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR1268 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: FTSI1140 and FTSI1142 | Cancellation of RICEFW Objects: FTSI1140 and FTSI1142 | SMH will handle the Splits and save the information until supplier sends the Merge signal. SMH will send the signal to update the Source and Target production orders by reducing and adding the Target Quantity. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/Approval_CR%20%23INT-CR1268%20Intake%20Forms%20(Cancellation%20of%20RICEFW%20Objects).pdf?csf=1&web=1&e=ywW1gl | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1268%20%E2%80%93%20Cancellation%20of%20RICEFW%20Objects%20FTSI1140%20and%20FTSI1142.pptx?d=w69787823a37e480da820ce64be0c0d8c&csf=1&web=1&e=MfrSH3 |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1140, FTSI1142 | FTSI1631, FTIS1619 |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-08 | [10 empty] | Other | Tower | 2025-10-08 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-29 06:51 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1269 | New | 4/7: Work with Adam | SCP | R4 (Release 4) | Medium | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration |  | 07. FTS IF 12. Infrastructure 17. B-App | eric.yamada@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | IP & IF demand aggregation/disaggregation of memory requirements in ECA Corp zone | This change request needs to be created for Memory – starting R4, where we need to have the IP & IF demand aggregation/disaggregation of memory requirements to occur in Corp ECA zone | For R3 – since there are no memory products that IF will plan, demand aggregation and disaggregation solution doesn’t need to occur in ECA Corp Zone o For IP products, the design will continue to be BY – IP -> PDH – IP -> E2Open/S4. There will be no IF instances for the same However, beyond R3, there could be potential memory requirements in IF – hence demand aggregation/disaggregation needs to occur in ECA Corp Zone | Business justification for this CR currently in progress. Entering this into the tool for CR visibility | No |  |  | TBD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 08:27 | 191 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No | Yes
|  | INT-CR1277 | Cancelled | [34 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 11:50 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1271 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Naved Naved | [11 empty] | Disposition button in Custom receiving screen LOGE1266 to call disposition logic to determine the disposition code for respective RMA. | Disposition button to be added in custom receiving screen to call disposition logic for static and dynamic disposition to determine the disposition code for respective RMA. | Given that batch job for static and dynamic disposition will run on specific schedules, Disposition button to be added in the custom receiving to call the same logic of static batch job for the respective RMA to determine the disposition code which will be updated in Disposition outcome table. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBEDAF4A9-E489-465E-BCAE-ACEB9449C3A3%7D&file=INT-CR1271_OTC%20IP%20%25u2013%20Disposition%20button%20on%20custom%20receiving%20screen.pptx&wdLOR=c3025A6C6-30B7-4E1A-A8E3-B8868F492127&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 16 | [5 empty] | 63 |  |  |  |  | 0 | 63 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1266 | 1 | LOGE1266 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-03-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | - This is a part of our receiving process, and it is to bring a disposition decision / button into the receiving screen - There is currently a break in the flow due to a delay in the process. The receiving line will have to pull the product off of the line and go back to run the disposition decision in the screen. - The ask is to add a button the pulls in the disposition decision into the receiving screen. This was discovered when the technical team looked at the execution of batching. - Background jobs will continue to take care of edge cases that could occur. - AR: Confirm with Keerti – @Tam, Anna @Woodburn, Christopher B @Jagadeesh, Puttasandra | [9 empty] | Build | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 09, 2025 | 2025-09-29 09:38 | 0 | < 15 Days | nanaved@deloitte.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR1272 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP | Vivek Prashant Potphode | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Descope OTCE1264 | Descope OTCE1264 - Enable Credit check on Milestone Completion Billing | Given the current timeline and the extensive scope as well as the complexity of the proposed system design options, the credit business team has carefully evaluated the operational feasibility and long-term implementation impact. While they recognize the value of automation, they believe that utilizing a manual process to assess credit risk for the milestone completion billing is more feasible and is the right approach at this point, particularly given that IFL Team has confirmed this billing accounts for only 20% of the milestone value. Build will be updated in INT-Build-CR1210 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE1264 | OTCE0235 |  | 1 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-02-18 | [10 empty] | Other | Tower | 2026-02-18 | 02, 2026 | 02, 2026 | 09, 2025 | 2025-09-29 09:51 | 0 | < 15 Days | vprashantpotphode@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1276 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP 11. Technology | Vivek Prashant Potphode | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | INT-CR1272; INT-Build-CR1210 | [7 empty] | OTCE0235 - Bypass Credit check for certain combinations of Order type & Item categories | Bypass Credit check when Contract type is ZDIF and Item category is ZD04 & ZD07 | Credit checks are expected to behave differently for the same Order types but different Item categories. Hence, need to enhance Routine under OVA8 which will bypass credit checks for certain combinations of Order types & Item categories |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B73032D16-E062-4672-B50F-E116274FC019%7D&file=INT-CR01276_CreditCheckStep_Milestone%20Contracts.pptx&wdLOR=c5B94157E-7C98-437A-A5CD-6B581B6208CF&action=edit&mobileredirect=true&CID=41E9C5F9-AD3B-498B-8EA6-749BCE5DE5B8 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Tech team confirmed to deliver by ITC1, and tech effort is 28 hours. Logged into Build CR Log under: INT-Build-CR1210 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 10:46 | 0 | < 15 Days | vprashantpotphode@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1274 | New |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 17. B-App | sujitkumar.kakodkar@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | 02314 | NA |  |  | 40617 | SAP IBP Consolidated Materials Planning |  | Stitching of IF Engineering S&OE & S& OP schedules from Engg SAP IBP for Materials Planning apps (SMART, CMP & MaPPS) | Currently Materials Planning for Engineering is based on stitched demand using PACE and S&OP SAP IBP signals. With PACE EOL plans, S&OE will now be planned using Engineering SAP IBP around Q3'26. | *CR is cancelled per Rajkumar R. With PACE EOL plans, Business requires integration of S&OP & S&OE for getting the entire time horizon for materials planning. Data granularity for both S&OP & S&OE are different and poses a challenge to stitch the 2 demand signals. This requires design closure, feasibility analysis and additional development to stitch to the 2 signals. | Assessment underway and estimation not complete, as Engineering planning timelines and design not closed. Entering this into the tool for CR visibility | No |  |  | TBD |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 10:10 | 191 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1275 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR | prashachauhan@deloitte.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | NA | No |  | NA | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR07XX%20-Derive%20FCS%20FTQ%20data%20by%20Capex%20WBS%20L2%20%26%20Mfr.%20Process%20Node%20CC%E2%80%8B%20-%20Cancellation%20.pptx?d=w2a2e627c38914fcb859856be6bc10f12&csf=1&web=1&e=HtoWV7 |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [11 empty] | Confirmed by Rafael that this is a duplicate of CR1478 | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 09, 2025 | 2025-09-29 10:40 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1278 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology | karthp@deloitte.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Supplier batch number instead of internal batch number | Supplier batch number instead of internal batch number | We currently share batch information via outbound PIP’s with our 3PL partners and receive it for inbound shipments using the standard IDOC segment, which captures the batch number. However, the business requires us to also provide the supplier batch number (CHAR > 15). To address this, we propose enhancing a IDOC segment LICHN or ATWRT Based on the character value it should fetch and pass it in CHARG in mulesoft. Similarly, vice versa should happen in inbound.The enhancement piece of determining the SAP batch number will be covered as part of LOGE1450. This change does not impact Opentext or 3PL’s. | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR0737%20%E2%80%93%20Supplier%20batch%20information%20to%20be%20shared%20instead%20of%20internal%20batch%20number.pptx?d=w94791554cbf0474ebe3d564022bcf86b&csf=1&web=1&e=Xr9e5o |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 |  |  | 30 | [10 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 12:09 | 191 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1280 | New |  | ERP | R2 Oct 2025 | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 11. Technology | R Prem Siddharth | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | NA | NA | INC14904166 |  |  |  |  | GTS Master Data data updated for Business Partners disappear from System | GTS Master Data data updated for Business Partners disappear from System | The IATA, SCAC, and EIN codes were originally assigned to Business Partners before the R2 go-live on August 11 (during PCO), but they were later removed when the MDG Auto replication occurred, which is now causing production issues like the inability to create Transactional documents. The issue in GTS is happening because data is being updated directly(Manually) there, which is a new requirement.Since MDG replicates data to multiple systems and only GTS needs this specific update, it makes more sense to implement the solution directly in GTS. This avoids unnecessary changes in MDG and prevents impact on other systems. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1280_GTS%20Master%20Data%20data%20updated%20for%20Business%20Partners%20disappear%20from%20System.pptx?d=w399b6db7e61d4fa283a87a4dcbcd0e6c&csf=1&web=1&e=hWFguy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-29 20:42 | 191 | > 30 Days | arumr@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1279 | Approved |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | IP IRES Integration | IP IRES Integration - more to come to assessment slides | for go live - see slides | tbd | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CRxxxx%20-%20IRES.pptx?d=wabd3b8ed46fa4f7aa966d107e24c2483&csf=1&web=1&e=Rr30TE |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 |  |  |  |  | 140 | [8 empty] | 140 | 0 | N/A | Yes | SCP | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPSPPDH0023 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-02 | Approved offline with Kumar Vytla | [9 empty] | Design | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-29 16:28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1281 | Approved | Presenter: Puttasandra Jagadeesh | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | Junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  |  | N/A | N/A |  |  |  |  | Tariff | EWM connection to DBAAS | To capture correct Country of Assembly and Country of Fabrication on FVR and AVR managed batches, EWM will need to connect directly to DBAAS to pull managed data. ​ | Keep Intel compliant to changing requirements around Country of Origin/Fabrication/Assembly rules. Expectation is that these new fields will be available for new Multiple CoA label and Multiple CoF and CoA label(s).​ | No Impact | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC093EE4C-D3F6-4C98-BADA-78D23164F737%7D&file=INT-CRXXXX_IF_EWM%20connection%20to%20DBAAS.pptx&action=edit&mobileredirect=true | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No | High | High | 3 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | LOGI1688 | 3137 | LOGI1688 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-16 | o This came in due to Tariffs. This requirement needs to establish a new interface to pull this data, feed through MPL, and then print it out on the label. o This is for legal compliance and is part of the core build. o AR: Include statement that there is no impact / technical work required for MPL side - @Ramireddi, Neetu @Jagadeesh, Puttasandra o AR: Add what FVR and AVR stands for - @Ramireddi, Neetu @Jagadeesh, Puttasandra o AR: Include statement that S4 team is taking care of the integration - @Ramireddi, Neetu @Jagadeesh, Puttasandra o This is an interim process because the long-term solution will be deployed post-R5.  If work is not done, then the label will not show anything and the shipment might stop. o IP has this capability. This is for Prospal design that is moving into S4, and they had trade rules that were missed. o AR: Add in statement about WIP inventory and label is for site-to-site movement for Intel. - @Ramireddi, Neetu @Jagadeesh, Puttasandra |  |  | 2025-10-31 | • CR for label printing compliance related to country of fabrication and assembly data pulled from the DBAS system. • This requirement aligns with existing ECC environment processes and addresses China tariff compliance. • The CR is considered straightforward and small, with approvals granted • Decision: Approved. | [5 empty] | Other | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-29 21:46 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | N/A | INT-CR1282 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Posina Chiranjeevi Kalesh | FTS (SCP IP & OP) — Chad Smith | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Cancellation of RICEFWID FTSI0480, FTSI0482 | These ID's were created to handle changes to the batch value wherein this turns either status to restricted or unrestricted. This whole functionality now will be handled separately with a new RICEFWID- FTSE1581, which will probably taking a look at one of the material characteristic value and determine if that needs to be set to restricted or unrestricted. | Business decision change | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1282%2FEXT%20Re%20MES%20Integration%20Meeting%20%2D%20RestrictedUnrestricted%20%2D%20Cancellation%20CR1282%20%2D%20Approval%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1282 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0480, FTSI0482 | FTSI0422, FTSE1581 |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-08 | [10 empty] | Other | Tower | 2025-10-08 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-30 01:57 | 0 | < 15 Days | posinax.chiranjeevi.kalesh@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1283 | Cancelled |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 06. PTP 08. FTS IP 17. B-App | karthic.v.thallikar@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | 02331 | NA |  |  | 40709 | ODM Materials Planning (Consigned, Turnkey , iDMI) |  | CSP Design & Development Timeline based based on Upstream SP PDH design closure for Planning Parameters | The CSP design is subject to revision due to its dependency on the upstream SP PDH design. Specifically, the ROO/ROR values and the datatype of planning parameters (static or time-phased) are expected to be finalized by SP PDH in Sprint 18. These inputs may necessitate changes to the current CSP design and involve additional effort/time for design and development | Cancelled. No need for CR.. The CSP design must align with the planning parameter definitions provided by BY ESP to SP PDH. Once the ROO/ROR and datatype specifications are received, the CSP design will be reassessed and updated accordingly. | Impact assessment is currently in progress, and effort estimation is not yet complete for any new changes coming in. This change request is being entered into the tool to ensure visibility and tracking. | No |  |  | TBD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni Adams; CANCELLED, not needed. The CSP design must align with the planning parameter definitions provided by BY ESP to SP PDH. Once the ROO/ROR and datatype specifications are received, the CSP design will be reassessed and updated accordingly. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 08:30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1284 | Cancelled |  | SCP | R4 (Release 4) | Medium | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 06. PTP 07. FTS IF 08. FTS IP 17. B-App | mauro.arias.mora@intel.com | FTS (SCP IF) — John Heiney | FTS IP - Loni Adams |  | NA | NA | NA |  |  | 40617 | SAP IBP Consolidated Materials Planning |  | Split LRP demand as IP and IF separately for CMP Passives Planning | CRP/DD/DDWOI demand signals from MAPPS were consumed by CMP to plan for Passive ( LSC/DSC). This signal needs to be split for to IP and IF and sent CMP IP/IF Planning areas separately. | *cancel CR per Rajkumar R. CRP/DD/DDWOI demand signals from MAPPS were consumed by CMP to plan for Passive ( LSC/DSC). In the initial design the LRP signals were classified as IF. But, with the BOM for IF and IP being different in the tactical horizon, the CRP/DD/DDWOI signals might need to be split based on IP and IF products. | Assessment underway and estimation not complete. Entering this into the tool for CR visibility | No |  |  | TBD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni Adams and Lisa Perigault to be cancelled on 11/7/25 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 09:44 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
|  | INT-CR1286 | Cancelled |  | ERP | R2 Oct 2025 | Low | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 11. Technology | R Prem Siddharth | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | NA | NA | [5 empty] | Update MuleSoft alert recipients for the OTCI0030/31/32 interfaces in the GTS PROD environments | Update MuleSoft alert recipients for the OTCI0030/31/32 interfaces in the GTS PROD environments | With the end of Hypercare for the R2 Release, support ownership for OTC GTS interfaces (OTCI0030, OTCI0031, OTCI0032) is shifting to the Operate team. Updating MuleSoft alert recipients from the Project team to the Operate team ensures timely incident response and aligns with the post-Hypercare support model. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1286_Update%20MuleSoft%20alert%20recipients%20for%20the%20OTCI00303132%20interfaces%20in%20the%20GTS%20PROD%20environments.pptx?d=w8fa49782fe75440d85659f4818b28ada&csf=1&web=1&e=g9icy1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as this is already an incident | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 13:47 | 0 | < 15 Days | arumr@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1287 | Approved |  | SCP | R2 Oct 2025 | Very High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 01. PMO 08. FTS IP 09B. Data Migration 12. Infrastructure | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | Cutover - Mark Mahony |  | n/a | n/a | n/a | [5 empty] | IP SCP R2 Additional Tech Solve ww42.3 in POC Plan | Team is requesting an additional IP BY IBP Tech Solve run in ww42.3, to address specific gaps that the first (POR) Tech Solve in ww41.0 will not be able to address, which includes: further validation of BOMs, validate sending data to ECA and the ability to run planning reports in a production environment | Current POC POR has a ww41.0 Tech Solve, which was recently reintegrated in the plan. Changes were made in the IP POC POR plan that did not follow the proper CR process (specifically the exclusion of the ww41 Tech Solve). While working on re-incorporating the ww41.0 Tech Solve, additional gaps and timing issues were encountered in the plan at the time, triggering the need for ww42.3. Adding the ww42.3 Tech Solve together with the ww41.0 will allow a more comprehensible validation of critical functionality in the prod environment that needs to be ready for Go-Live in ww43.0 | none | No |  |  | https://intel.sharepoint.com/:p:/r/sites/teamsintelspinnaker14669/Shared%20Documents/2.1%20Program%20Mgt%20Channel/CCB/Change%20Requests/Pending/IP%20SCP%20R2%20Additional%20Tech%20Solve%20ww42.3%20PCO%20Change%20ID_IP%20FTS_CR%20Deck_template.pptx?d=w4f2c0667b9e841b8b0249afb42595f7c&csf=1&web=1&e=L8n60q |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-10-02 | Confirmed by Stacee in email on 10/2 that CR was approved by Rick. Email copied below: All, I confirmed with Rick that CR1287, IP SCP R2 Additional Tech Solve ww42.3 in the POC Plan is fully approved and does not need to be presented at the Change Request Meeting. We will note that CR1287 was approved by email in the ww40.5 Change Request Meeting minutes for documentation purposes. If you have any questions or need further clarification, please contact Rick or me directly. Best regards, Stacee | [9 empty] | Other | Tower | 2025-10-02 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-30 15:54 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1288 | Approved |  | ERP | R3 (Release 3) | Very High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology | chgorantla@deloitte.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | Cash Management Data from Quantum for F110 payment run | Enhancement to create Cash Management relevant data from F110 Payment Run for Invoice based payments to be sent to Quantum | SAP has responded to OSS message # and confirmed that APM cannot generate a Memo Record for Invoice based Payments (F110). Hence need to create a Custom object to create Cash Management relevant data from F110 payment run and send it to Quantum which is critical for Cash Management |  | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/TREASURY%20NEW%20CR.pptx?d=w6091f8166d544846bba6c380c53ec8cb&csf=1&web=1&e=c9cbsT |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FPRE1706 | 3185 | FPRE1706 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-27 | - This is purely S4 and no other impact outside of S4 - Scenario will not be tested in ITC1 because of the volume. - No downstream or upstream impact - Shane has approved | [9 empty] | Other | Tower | 2025-10-27 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-30 16:20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1292 | Approved | ME21N, F0842, VA01, VA02 | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 06. PTP 11. Technology 13. Security | rodolfo.alarcon@intel.com | Inventory/Logistics/FTS — Stef Maxey | Security - Raj Valluri |  | Change was identified during localization build workshops and might require customization of multiple tcodes/apps | 02318 | N/A | [5 empty] | Log IF localization restriction on Storage Location | Additional requirements for localization was identified for logistics team during finalization/signoff. This might involve customization of apps/tcodes to utilize storage location field for security role restrictions | There are separate teams within logistics that need to be restricted by using storage location since they share same plant/Warehouse. | ITC2 for R3 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Logistics/CRXXXX%20-%20Security%20Role%20restrictions%20for%20Log%20IF.pptx?d=w0f982e16a7ae4a23ae1a509ddd529f95&csf=1&web=1&e=wpOHvm |  | 6. Build Security-Related Changes |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | Security | Yes | S4 | 2 | LOGE1691, LOGE1690 | 3170 | LOGE1691, LOGE1690 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-09 | o This is related to Security roles per the testing plan will be used in ITC2 and ITC3.  This CR is a request for security team to start engaging with specific functional teams at Deloitte to add more layers to existing logistics roles to be storage location and site-specific.  Validated by the team to be possible to restrict down to that level o There are 2 different groups of users that need to have different set of approvers. o It is at the warehouse-level for EWM. | [9 empty] | Build | Tower | 2025-10-09 | 10, 2025 | 10, 2025 | 09, 2025 | 2025-09-30 19:58 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | Complete |  | Complete | Yes
|  | INT-CR1294 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | lorinda.m.braun@intel.com |  |  |  | SCP-CR.169 | [7 empty] | When we add the aggregate_ds, the query is most likely performing complex joins across multiple large tables that result in a large intermediate result set before aggregation occurs since the list of views Jorge provided are not persistent views.- To create persistent views with the same access parameters to see if this helps with performance |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 21:31 | 190 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1296 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Alissa M Cramer |  |  |  | SCP-CR.171 | [7 empty] | [NEW] Swap Ratio Change - Change BY Logic to respect Capacity Maxes |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 21:31 | 190 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1297 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | greg.underhill@intel.com |  |  |  | SCP-CR.172 | [7 empty] | [NEW] Freeze Wafer Starts : Need ability to force specific wafer starts and associated outs (rather than making changes in SPAN) |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 21:31 | 190 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1298 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | kurien.p.cherian@intel.com |  |  |  | SCP-CR.173 | [7 empty] | [NEW] Email or clear indicator on PDH UI confirming Bump/Sort File has been uploaded |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 21:31 | 190 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1299 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Tracy Hendricks |  |  |  | SCP-CR.174 | [7 empty] | Approved: Within PDH UI: Need to calculate Default value for capacity corridors - today, looks at last week's capacity corridor, but if more supply was allocated in the prior week, use that value |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-01 | Confirmed by Rocco to be approved | [9 empty] | Build | Tower | 2025-12-01 | 12, 2025 | 12, 2025 | 09, 2025 | 2025-09-30 21:31 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1300 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | gianfranco.solimano@intel.com |  |  |  | SCP-CR.175 | [7 empty] | Upgrade data processing speed / Faster Data Retrieval from PDH (currently is XS, need Med or higher) |  |  |  | No |  |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 09, 2025 | 2025-09-30 21:31 | 190 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1301 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 06. PTP | 10.8 Analytics - PTP |  | 06. PTP 10. Analytics | yogesh.d.chaudhari@intel.com | Data & Analytics - Rebecca Verette | PTP - Richard Taylor | No | NA | 02122 | NA | [5 empty] | Adjustment to Report's Build Timelines | Request to revise & extend the delivery timeline for a subset of 3rd party reports due to dependencies on backend data consumption view availability, resource realignment, and delayed build planning. 81 3rd Party/SSBI Reports are at risk of missing the ITC 1 readiness milestone, 20 ready for ITC1, 61 will be ready for ITC2 | Data Dependency: Backend data consumption views required for SSBI/3rd party reporting were scheduled late in the build cycle, limiting time for report development. Resource Constraints: CPM actions impacted identified build owners; replacements require onboarding and domain ramp-up. Planning Delays: 61 reports remain unplanned due to pending ownership assignment and late availability of data view build dates (19th Sept). Effort estimation is expected to complete by 10th Oct, after which risk clarity will improve. | Delay in readiness of 81 reports & impact to ITC 1 readiness. Revised timelines and mitigation plan will be finalized post 10th Oct once effort estimates are complete. | Yes | Non-Core | GPO (Cari) Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR0xxx%20-%20Adjustment%20to%20Reporting%20Build%20Timelines%20(R3).pptx?d=wd7a49da8eefa4d6eb54685db52a78f6a&csf=1&web=1&e=cfgCjY |  | 13. Other Milestone Adjustments |  | No | Medium | High | 2 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 51 | ECAPTP6777, ECAPTP5092, ECAPTP5136, ECAPTP5137, ECAPTP5138, ECAPTP5149, ECAPTP5150, ECAPTP5151, ECAPTP5152, ECAPTP5154, ECAPTP5093, ECAPTP5094, ECAPTP5784, ECAPTP5764, ECAPTP5765, ECAPTP5769, ECAPTP5777, ECAPTP5779, ECAPTP5788, ECAPTP5789, ECAPTP5790, ECAPTP5799, ECAPTP5817, ECAPTP5837, ECAPTPV5257, ECAPTPV5261, ECAPTPV5270, ECAPTPR5759, ECAPTP5107, ECAPTP5108, ECAPTP5113, ECAPTP5114, ECAPTP5115, ECAPTP5116, ECAPTP5117, ECAPTP5118, ECAPTP5119, ECAPTP5120, ECAPTP5121, ECAPTP5122, ECAPTP5124, ECAPTP5125, ECAPTP5126, ECAPTP5127, ECAPTP5128, ECAPTP5129, ECAPTP5130, ECAPTP5806, ECAPTP5807, ECAPTP5808, ECAPTP5826 |  |  | 0 |  | 0 | ECAPTP6777, ECAPTP5092, ECAPTP5136, ECAPTP5137, ECAPTP5138, ECAPTP5149, ECAPTP5150, ECAPTP5151, ECAPTP5152, ECAPTP5154, ECAPTP5093, ECAPTP5094, ECAPTP5784, ECAPTP5764, ECAPTP5765, ECAPTP5769, ECAPTP5777, ECAPTP5779, ECAPTP5788, ECAPTP5789, ECAPTP5790, ECAPTP5799, ECAPTP5817, ECAPTP5837, ECAPTPV5257, ECAPTPV5261, ECAPTPV5270, ECAPTPR5759, ECAPTP5107, ECAPTP5108, ECAPTP5113, ECAPTP5114, ECAPTP5115, ECAPTP5116, ECAPTP5117, ECAPTP5118, ECAPTP5119, ECAPTP5120, ECAPTP5121, ECAPTP5122, ECAPTP5124, ECAPTP5125, ECAPTP5126, ECAPTP5127, ECAPTP5128, ECAPTP5129, ECAPTP5130, ECAPTP5806, ECAPTP5807, ECAPTP5808, ECAPTP5826 | 51 | 51 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o These reports sill miss the 1/9 milestone due to a decision to support Boundary Apps views first over Enterprise views. o The team will be able to test the data flowing into the view, but will not be able to test the reports. This decision was made back in June. | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-01 05:34 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1302 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 02. E2E Process Integration 17. B-App | priya.c@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | MO response to BY | To publish the MO response from Mapps to BY | *Cancel per Sunil Parida. This is for BY to get the accurate supply. See design open #189 | May not be completed by ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Change%20ID_Tower_CR%20Deck_MOResponse.pptx?d=w9b50d3a0cef042d0962e9b27023e4a94&csf=1&web=1&e=LXdlaq |  | 1. Process Scope / Design Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni and Sunil Parida that this is not required. | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-01 06:33 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1303 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Big 3 Master Data Recon Reports | Recon Reports are required to reconcile Big 3 Master Data (Material, Customer and Vendor) between MDG and S/4 Systems | This is a new requirement |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1303.pptx?d=w2051dcb3659c4327914db683bee4d399&csf=1&web=1&e=OlHkxU |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  | 3175 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-01 13:03 | 189 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1304 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Material Master Data-Derivation of Attributes | Derivation of Material Description, Material Group, Product Hierarchy, Intelligent Description and Profit Center during conversion | This is a new requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1304.pptx?d=w9e749ec531514aecabff87e6533e27a8&csf=1&web=1&e=XBhYhU |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-01 13:08 | 189 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1305 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Material Master Data Input File Based Conversion Automation (Group 9) | Automation of Input File Based Conversion (Group 9), business will provide only Reference Material and New attributes that are required for creation of Materials against Group 9 and all the attributes from all the views will be copied from Material Master Data | Automation in conversion process and less dependency on Business users |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1305.pptx?d=w7d5dd3c629e44c98a491af4d1e47bc13&csf=1&web=1&e=W2dsch |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [10 empty] | 385 |  |  | 0 | 385 | Data Migration |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC1237, DATC0213, DATC0075_IP, DATC0074_IP​, DATC0073, DATC0072, DATC0068_IP, DATC0069_IP, DATC0070_IP, DATC0071_IP, DATC0073, DATC0072, DATC0076_IP | 13 | DATC1237, DATC0213, DATC0075_IP, DATC0074_IP​, DATC0073, DATC0072, DATC0068_IP, DATC0069_IP, DATC0070_IP, DATC0071_IP, DATC0073, DATC0072, DATC0076_IP | 13 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-27 | - It is manually feasible to create the data for MC1; Deloitte Master Data team and Intel Master Data Team will be able to complete the work | [9 empty] | Build | Tower | 2025-10-27 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-01 14:38 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1306 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Material Master Data Construction and Cleansing Effort-2 | Automation and Cleaning for below mentioned activities 1) Extracts needed for Report# 21 generation​ 2) Item - PROC File Item ​ 3)Item – WLA UPI with Proc Identifier ​ PROC_STACK_SI_GROUPING for Stack SI products, rules are provided by biz team​ 4) Item – Placeholder Replacement MMID ​ 5) BODs script to move BOM from Placeholder IC to new replacement FG MMID​ 6) Item – List of New spare parts / construction materials without MMID today ​ 7) Data Cleansing ​ Inactivate FGS and applicable components based on zero demand, order, forecast etc.​ Reclassification of incorrectly classified ZCAP/ ZCU material types and applicable item classes | This is a new requirement |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1306.pptx?d=w7f673eefe68249a2826d707494de4753&csf=1&web=1&e=hMtoIQ |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-01 15:03 | 189 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1310 | Rejected | Presenter: Prabhakar Vemuri, Murthy | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | pvemuri@deloitte.com |  | PTP - Richard Taylor |  |  | N/A | [5 empty] | WIINGS | Develop a ECA Report for monitoring and error handling of the PM orders and the associated purchasing documents generated | Develop a ECA Report for monitoring and error handling of the PM orders and the associated purchasing documents generated. This is required to monitor the errors and status of various purchasing documents (e.g., return & repair purchase orders, STO documents, Warranty PRs etc.) generated through RICEFW objects PTPE0961, PTPE0962. | Users need visibility to PM orders and the associated purchasing documents generated from the PM work order. This ECA report can provide the visibility into whether documents are created successfully or if errors have occurred. Considering the huge volume of PM order items, this report can address the need for error handling for Purchasing documents generated through RICEFW objects PTPE0961, PTPE0962. | New RICEFW objects needs to be planned for Build and FUT | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEDDD9E87-02DA-4836-9ACA-B4DD14F3BE17%7D&file=INT_CR1310_WIINGS%20-%20ECA%20Report%20requirement%20for%20monitoring%20and%20error%20handling%20of%20the%20PM%20orders%20.pptx&wdLOR=cE22EE34C-4981-4FB3-9384-C6F3EF0AC9F7&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-10-16 | [9 empty] | Cancelled as Richard Taylor confirmed that CR1310 is captured in CR1320 | Other | Not Assigned |  | Not Approved | 10, 2025 | 10, 2025 | 2025-10-01 16:49 | 0 | < 15 Days | pvemuri@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1311 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | anantjoshi@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor |  | Added to change extraction crietera | NA | NA | [5 empty] | Changing Extraction criteria for AMPL | Changing Extraction criteria for AMPL | To Avoid redundant data to be extracted and to avoid heavy manual work in clean up in the source system. | Should be available for ITC2, we will try to get it ready for ITC1. | No |  |  | placeholder |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Anant to be cancelled | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-01 17:29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1312 | Cancelled |  | SCP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 07. FTS IF 08. FTS IP | alfie.him.yeong.tung@intel.com | FTS (SCP IP & OP) — Chad Smith | PTP - Richard Taylor |  | N/A | N/A | N/A | [5 empty] | Blue Yonder Supply/Inventory Data Element For Planning Solve | potential addition/change of supply data elements considered by BY for planning solve. | If BY missed some of the critical supply elements before running the planning solve, the solve results would not be accurate, we may under or over planned. | Impact of schedule is not known at this moment. | No |  |  | Not available yet |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Richard Taylor to no longer be needed. Alfie Tung has dispositioned as not needed. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-02 15:07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1313 | Cancelled |  | SCP | R3 (Release 3) | Very High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 07. FTS IF 08. FTS IP 11. Technology | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | During detail discussions with Intel Foundry that expand the need from just the IP CW Demand feed to 4 additional data needs. | 448 | No | [5 empty] | THIS CAN BE CANCELLED IP IRES Design | . ​Enable below 5 data feeds to IRES to provide IP CW demand prioritization to IF ATM factories. ​ Item Group configuration​ Test PROC/FG schedule (13 weeks)​ Bin splits (13 weeks)​ Active routes (AIP) (13 weeks)​ IP CW demand (13 weeks) | Sunil to talk to Winston on whether this is closed. Confirm if Open Design #69 is open. This is a must have. ATM cannot manufacture a single unit without the IRES signal. | PDH estimate – 3.5 weeks for base table and files to IF/IRES​ This can be absorbed into Build schedule with no impact to WW2 milestone. However this consumes remaining PDH capacity and additional CRs can not be absorbed – there are additional SP CRs in the pipeline. IRES is assumed to be the top priority. | No |  |  |  |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Brian Staab to be cancelled | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-02 15:57 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1314 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 10. Analytics | stef.maxey@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | IP SMH was brought in to scope late in overall timeline. | N/A | N/A |  |  | 41627, 59283 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF, PDF Sapience Manufacturing Hub Integration Platform - IP |  | IP SMH data to ECA | IP SMH data will need to move to ECA for long term data storage. | IP SMH will not be used for long term storage of data. | ITC2 will be soonest available. There is no risk to other dependencies. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR0%23%23%23%20-%20IP%20SMH%20data%20to%20ECA.pptx?d=w28d5037b6d5c4c5baaff667b3662ed2b&csf=1&web=1&e=jxfp94 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 12 | ECAFTSIFV6228, ECAFTSIFV6233, ECAFTSIFV6229, ECAFTSIFV6230, ECAFTSIFV6231, ECAFTSIFV6232, ECAFTSIFV6714, ECAFTSIFV6715, ECAFTSIFV6716, ECAFTSIFV6717, ECAFTSIFV6718, ECAFTSIFV6780 |  |  | 0 |  | 0 | ECAFTSIFV6228, ECAFTSIFV6233, ECAFTSIFV6229, ECAFTSIFV6230, ECAFTSIFV6231, ECAFTSIFV6232, ECAFTSIFV6714, ECAFTSIFV6715, ECAFTSIFV6716, ECAFTSIFV6717, ECAFTSIFV6718, ECAFTSIFV6780 | 12 | 12 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o FTS IF has submitted request for this functionality, so IP can re-use the work. o The API will not be ready for ITC1, and it is not critical for it.  Having historical data is not required for ITC1. | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-02 18:18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R2 Q4'25 Anafi enablement | R2 Anafi | INT-CR1315 | Approved |  | ERP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 11. Technology | Junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | NA | NA |  |  |  |  | Anafi | Commercial Invoice Changes for Virtual Shipment Anafi | To remain compliant to US Government audit regulations, Intel Foundry will need to generate a compliant Commercial Invoice for the virtual transactions used to bill clients per predetermined invoice points.​ | In WW39'25, ITG (Trade) confirmed that compliant commercial invoices would need to be generated and archived in EDDAR for audit purposes. | CR is part of Anafi Release. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B328A0CB4-24DF-41AC-BFBA-AAEDFBE08E6C%7D&file=INT-CRXXXX_IF_ANAFI%20Virtual%20Commercial%20Invoice%20Generation.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 |  |  | 50 | [7 empty] | 36 |  |  | 0 | 36 | N/A | No |  | 0 | N/A | 3139, 3140, 3141 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE341_IF​, LOGF345_IF​, LOGF347_IF​ | 3 | LOGE341_IF​, LOGF345_IF​, LOGF347_IF​ | 3 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-10-09 |  |  |  | 2025-10-10 | • Team discussed the need to generate commercial invoices for Anafi virtual shipments, which do not involve physical shipments but still require documentation for trade compliance and audits. • The change relaxes mandatory fields like carrier and tracking information to allow invoice generation without physical shipment data. • This affects three RICEFW objects, including billing documents and forms. • The go-live is targeted for December 28, 2025, aligning with Anafi’s Oracle ERP implementation. • Decision: Approved | [5 empty] | Build | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-02 20:06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1316 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.13 OTC IP – Returns (Logistics Management) | Yes | 05. OTC IP 11. Technology 13. Security | kimberly.moore@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | N/A | 1056 | N/A | [5 empty] | Exporter of Records requirement for OTC-IP Customer Returns | In case of Customer returns from specific countries like UK, JP etc, regional Intel Entity takes ownership of the returned products from the customer and then takes responsibility of exporting the returned products to the final Returns warehouse. Hence the regional Intel Entity is responsible for generation the CI/PL forms. For incorporating this change a custom program to be built to capture the transfer of ownership to Intel UK/JP and then shipment to final returns warehouse. Additionally changes to existing CI/PL RICEFs-LOGF1257 & LOGF1258 is required | Currently this transfer of ownership from Customer to Intel UK/JP is not being captured in the system, which is a trade compliance gap. Hence going forwared in IAO this gap has to addressed and transfer of ownership has to be captured in the system | Change to be implemented in ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BE7209B68-7DF8-4DB7-9337-8DB300F4D4DF%7D&file=INT-CR1316%25u2013%20Exporter%20of%20Records%20requirement%20for%20OTC-IP%20Customer%20Returns.pptx&wdLOR=c6F294735-EAC7-4162-9ADD-1E0D49C7E961&action=edit&mobileredirect=true&CID=C0C20197-2B3F-4D30-9A3F-EED7BE773ACA&previoussessionid=f7e612eb-1f2b-06e8-fb10-44390d184061&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTg1MjYuMjA2MDQiLCAiT1MiIDogIldpbmRvd3MiIH0%3D |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | High | 0 |  |  | 65 | [5 empty] | 36 |  |  | 30 |  | 0 | 36 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF1257​, LOGF1258​ | 2 | LOGF1257​, LOGF1258​ | 2 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - AR: Include statement about what is being closed in ITC1 vs ITC2 | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-03 07:27 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R2m (December 2025) | R2.1 ITC | INT-CR1317 | Approved |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Vinay Kumar Khandelwal | [6 empty] | INC14865835 |  |  |  |  | BODS job clearing the DN # in the ZTOTC_POLP_TRX | BODS job clearing the DN # in the ZTOTC_POLP_TRX | This could help the delivery information from being wiped out from custom table ZTOTC_POLP_TRX |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7Bc3ec37fc-64cc-46ca-b0fa-1dd1c6d53f55%7D&action=edit&wdPreviousSession=c4c604b4-e9bf-bd7a-5028-aea22ee316f4 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 14 | [5 empty] | 18 |  |  |  |  | 0 | 18 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0410 | 1 | OTCE0410 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-09 |  |  |  | 2025-10-10 | • Shishir Kumar Dwivedi reported a production issue where a batch job incorrectly blanks out delivery numbers in the POLP table on the S4 side, causing potential data inconsistencies and manual interventions. The fix requires minor functional and technical effort and is considered an operational priority. • The team agreed this should be handled through the operate pipeline with prioritization and capacity managed accordingly, avoiding unnecessary escalation to leadership unless capacity is exceeded. o The reason for bringing this request to today's CR Meeting is IM and email requests for status and next steps were unanswered and this CR is urgent. • The meeting concluded with discussions on the operational process for handling small change requests and defects through the operate team, ensuring capacity and prioritization are managed without impacting core project resources. • Decision: Approved • AR: Roman Vorel and Anand Jha to clarify and document the process, distinguishing between defect resolution and formal change requests to streamline approvals and delivery | [5 empty] | Build | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-03 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1318 | Approved | Presenter: Eugene Celis, Rudra Sengupta, Nikhil Jain | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 16. Testing 17. B-App | Eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | N/A | N/A | N/A |  |  | 4982 | IMO - NBS |  | R3 ITC2 - Intel Mask Operations (IMO) NBS System | IMO NBS System Development/FUT complete changed from Q4’25 to 3/31/26 . Requesting for Formal CR process. | Due to very constraint resource impact and competing IFS revenue project. Prioritization and Trade-off considered. | ITC1 will not be able to test IMO’s E2E scope. Adjacent IF biz and limited impact of missing ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR_1318%20IMO%20NBS%20Change%20Request.pptx?d=wcde34c08e463475182f79236c3c1ab08&csf=1&web=1&e=mHiAOU |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment S4 | 1 | FTSI1020 |  | FTSI1020 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-09 | o This CR is to get approval for IMO to be a part of the ITC1 Exceptions list. o Resources supporting development of IMO and IFS Revenue overlap, and teams have aligned to prioritize IFS Revenue.  This is supported by Automation team in the NBS.  IFS revenue project will complete by the end of this year. o If this does not go-live, then we will need to put together a business process. It is a non-core process with a workaround. |  |  | 2025-10-10 | • Reported a delay in the development of the IMO NBS system integration, which manages reticle ordering, acknowledgments, shipment readiness, and cost signals. • The system is complex and currently managed by a small operations automation team with limited resources. • The delay is due to resource constraints and competing priorities, particularly supporting a new customer. • The team discussed contingency plans, including manual processes and possibly delaying deployment to a later release (R5), while maintaining the current plan for R3. • The integration is critical for billing and inventory movement to S4, shifting from a cost-only model to a customer-billable revenue model. • Stakeholders emphasized the need for backup resources (1 GB) and risk mitigation to ensure delivery. • Decision: Approved • AR - Eugene Celis & Paul Whitlock to engage with NBS team to explore onboarding a green badge developer as backup. • AR - Eugene Celis & Paul Whitlock to establish backup plan for CR1318. • AR - Anand Jha to evaluate implications of manual workaround if R3 delivery fails for CR1318. | [5 empty] | Other | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1319 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 10. Analytics | mark.c.bargovan@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | Excess capacity for Deprecation and Non-Depreciation. | FPRE0883 – Excess capacity for Deprecation and Non-Depreciation. | Excess capacity is very essential for any business. This Excess capacity for both Depreciation and Non depreciation should be calculated in ECA and the data should be posted to ACDOCP and further imported into SAC. For this to happen, 3 RICEFWs for Excess Capacity for Depreciation and 3 RICEFWs for Non-Depreciation is needed. 3 RICEFWs – a. Excess capacity calculation for next 24 months. B. Identify tech node level cost centers and receiver tech node level WBS elements to transfer costs from PCOS to OCOS C. ECA to S4 Interface - Transfer PCOS costs to S4 for financial planning. | No | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB99BA92D-2AFA-40C4-9B17-3B2AC44E4205%7D&file=INT-CR1319%20Excess%20capacity%20related%20RICEFWs.pptx&wdLOR=cAB147DDF-4ACC-47E9-B5E5-0D39441782DB&action=edit&mobileredirect=true | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA S4 | 3 | FPRI1704, ECAFPRV6916, ECAFPRV6917 | 3186 | FPRI1704 | 1 |  | 0 | ECAFPRV6916, ECAFPRV6917 | 2 | 2 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-27 | - AR: Include details about the proper flow |  |  | 2025-10-28 | • CR11319 is focused on forecast excess capacity: • Purpose: carve out costs related to factory excess capacity for financial forecast. • Data flow: ECA → transform → S4 → SAC. • Includes 2 ECA views and 2 RISEFs for calculations and data transfer. • Team confirmed: o Quarterly process aligned with RPOR forecast. o Using Blue Yonder forecast data. • Roman Vorell questioned need for new interfaces vs. existing ones. Team confirmed new views and incremental interfaces required. • Time pressure noted: only 3.5 days left to complete pending items. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-28 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1320 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.9 PTP - Plant Maintenance |  | 06. PTP 07. FTS IF 10. Analytics | susan.strathman@intel.com | Data & Analytics - Rebecca Verette | PTP - Richard Taylor |  | CR1030 | NA | NA |  |  |  |  | WIINGS | 4 reports related to WIINGS to be added to the Deloitte ECA Object Tracker | 4 reports related to WIINGS to be added to the Deloitte ECA Object Tracker. Related to CR1030 | Support business requirements after WIINGS is being sunset | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B944BC626-87B3-422D-9CBD-128C13120652%7D&file=INT-CR1030.pptx&action=edit&mobileredirect=true | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 1 | PTPFR130 |  |  | 0 | PTPFR130 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-10-09 |  |  |  | 2025-10-10 | • This CR is a follow-up on change request 1030 regarding PTP reports. • The team reduced the initial 10 reports down to 5 key reports for approval, focusing on inventory item details, Fab Source Intelligence Center, and SLA metrics for order receipt and delivery. • These reports aim to consolidate and optimize reporting, eliminating redundancies. • The reports will be Deloitte-built and aligned with Cari Shim and other stakeholders. • The scope is confirmed as final unless new surprises arise, and there is consensus on moving forward with the plan. • Roman Vorel raised questions about naming conventions and report structure for future cockpit adoption, with Susan Strathman confirming alignment with existing aging reports and standardization efforts. The spares reporting remains out-of-the-box without new reports • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1321 | Rejected | Presenter: Kelly Gerber | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP 17. B-App | Jorge Erazo Cruz | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | B.Apps Source Addtl Funds Needed | This CR is for additional funds to retain IT resources (CWs) that are critical to support the IAO remediation, Mock Cutover, Testing cycles and Production for the multiple B.Apps. | Our internal capacity is insufficient to handle the volume and pace of work for upcoming test cycles, a direct result of 2025 CPM actions and 2026 budget reductions. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Boundary%20Applications/Change%20Control%20Tracking/CC%20Request%20Forms%20Submitted/Supply%20Chain%20MisCo/INT-CR1321_PTP_B%20Apps%20Source%20Addtl%20Funds%20(Sourcing)%20Final.pptx?d=w9d5bdcdeff4c41bab6d6fc1e0fa048c1&csf=1&web=1&e=TePaR0 |  | 14. Other Resource Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-10-09 | [9 empty] | Confirmed by Kelly to be cancelled | Other | Not Assigned |  | Not Approved | 10, 2025 | 10, 2025 | 2025-10-04 | 0 | < 15 Days | lisa.honeycutt@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1323 | Approved | Presenter: Chris Oltmann, Brian Staab | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.1 FTS IP - ALL |  | 05. OTC IP | haley.a.cooper@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Allocation Change Log | Allocation changes in BY OP | see form | see form | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Allocation%20and%20Order%20Promising/3.%20Execution%20Phase/CCB/INT-CR1323%20-%20Sales%20Order%20Escalation%20Process.pptx?d=w1ca18925d6b148db80768effba035805&csf=1&web=1&e=WfeVLz |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 |  |  |  |  | 80 | 80 | 16 | [6 empty] | 176 | 0 | N/A | Yes | ECA SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPAPOPPDH0045 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Shelly has approved, and team has aligned. - This is a build CR, and there is no commercial impact. | [9 empty] | Other | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1324 | Approved | Presenter: Lynn Asbury | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 09A. Master Data 17. B-App | Debbie Voon | BApps — Kelly Gerber | Data - Julie Fawdington |  | NA |  |  |  |  | 11140, 4092, 37423, 36578, 18676, 21841 | SPEED PDM (Next Generation SPEED), SPEED PDM (Legacy SPEED), Finished Good Items Update - Oracle Product Lifecycle Management Cloud, IntelOne, Oracle Product Lifecycle Management Cloud (Enterprise Instance), Item BOM Hub - IBDS |  | PDM Automations | Item/BOM data automations for enabling IP/IF collaboration, shop floor products creation, class/characteristics synchronization between SAP and SPEED, mass import, Engineering & HVM as well as Grow and Spawn Items. THE CHANGES IN THIS CR ARE ISOLATED WITHIN PDM SYSTEMS (SPEED/OCPLM) ONLY. | IAO leadership asked us to automate as much of the item/bom maintenance across the landscape as possible. Other CRs for MDG/S4’s are already approved for ITC2 and being built. This change is for the SPEED/OCPLM systems. These automations are required for a successful IAO program, otherwise the business teams will crater under the weight of data maintenance. The data volume is growing more than 3.5x from today’s numbers and those biz teams have significantly shrunk due to CPMs. | Change to be implemented in ITC2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1324%20-%20PDM%20Automations.pptx?d=wa8e3cd57ce9b4b659240d4d9a842346f&csf=1&web=1&e=gogP7q |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [12 empty] | 960 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-09 | o This CR is to document the Intel-only work that will be done by Rebecca’s team | [9 empty] | Other | Tower | 2025-10-09 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-07 | 0 | < 15 Days | lynn.asbury@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1328 | Cancelled | [5 empty] | 10.4 Analytics - OTC IF | [18 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-07 | 0 | < 15 Days | nmaddi@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1329 | New |  | ERP | R3 (Release 3) | Medium | 13. Security | 5.11 OTC IP - Order Management |  | 05. OTC IP 13. Security | olga.moskaleva-hughes@intel.com | Security — Debbie Whitely | Security - Raj Valluri | n/a | n/a | n/a | n/a | [5 empty] | Business roles change | rename role OTC IP Dpas Super User to OTC IP Assignment Priority Superuser. Delete role OTC IP Mass change scheduling agreements | Dpass field has been expanded for multiple functions so need access naming convention to be reflective accordingly. Scheduling agreements for automotive have been descoped so role OTC IP Mass change scheduling agreements not needed. | none | No |  |  |  |  | 6. Build Security-Related Changes |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-08 | 182 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1330 | Approved | Presenter: Praveen | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Manjunath M Meti | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Condition type ZCNP to be enabled with additional new combination when the new price is sent from IPAR | New Key combination to ZCNP condition – New Combinations are Sold To/Material Sold To/Product Hierarchy | This CR was identified during the business discussion |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B76B4473C-03A3-4F2D-A858-AB475E354E45%7D&file=INT-CR1330_OTC%20IP_CR%20Deck_Changes%20to%20Interfaces%20OTCI0081_%20Addition_of_Key_field.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 33 | [7 empty] | 65 |  |  | 0 | 65 | Data Migration Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0081, OTCC0717 | 2 | OTCI0081, OTCC0717 | 2 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-23 | o This is a legacy condition called non-exception price condition.  Boundary app found that they need a couple new sets of field combinations. o We can utilize ZCEP, but it will not go to Vistex.  So, they need to go back to the original combinations o AR: Need to add in what scenario cannot be tested. What can be not test because we cannot send to Vistex - @Muppala, Praveen Kumar |  |  | 2025-10-24 | • Discussion involves enabling price loading functionality at the “sold to” customer level for the ZCNP pricing condition type in SAP S4, in addition to the existing “end customer” level. • This change requires configuration updates and impacts two OTC objects (IE 008 and OTC 0717), with readiness targeted for ITC2. • The enhancement supports mass maintenance of pricing conditions, particularly for scenarios involving ODMs purchasing for end customers without disclosing pricing. • The work involves technical team changes and is fully managed by Deloitte. • Decision: Approved | [5 empty] | Build | CL/OSC | 2025-10-24 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-08 | 0 | < 15 Days | mmeti@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1331 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 11. Technology | 11.4 Technology - Boundary Apps |  | 04. OTC IF 05. OTC IP 06. PTP | sanjaykumar.b.morab@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | NA | To accomodate data separation requirement between IP\IF\CORP\ECC new portal for data retrieval is need to be introduced for IP. With this dedicated portal for IP, IF and Legacy(ECC) will run parallel. | RAID# 02022 | NA | [5 empty] | New EDDAR portal for IP data retrieval as part of IAO R3 | To accomodate data separation requirement between IP\IF\CORP\ECC new portal for data retrieval is need to be introduced for IP. With this dedicated portal for IP, IF and Legacy(ECC) will run parallel. | To accomodate data separation requirement between IP\IF\CORP\ECC new portal for data retrieval is need to be introduced for IP. With this dedicated portal for IP, IF and Legacy(ECC) will run parallel. | On track with R3 development. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/EDDAR_PORTAL_INT-CRXXXXX-Template.pptx?d=w2ea24eb19a2d46afaa302d101ab6cd77&csf=1&web=1&e=Zum9a3 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-08 | 182 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1332 | Approved | Presenter: Gilberto, Shashank, Anthony Romano, Chad Smith, Brian Staab | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | shashank.kolhe@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | na | na | na | na | [5 empty] | PDH UI for Node Discontinued | PDH UI for Node Discontinued - see form | APPROVED WW42 | delivered beyond WW2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1332%20-%20PDH%20UI%20for%20Node%20Discontinued.pptx?d=w9fd99828826e486d848cc441278715e5&csf=1&web=1&e=bIvWjd |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPDPPDH0046 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-16 | o Approved offline with Kumar o ITC1 will be a manual transaction | [9 empty] | Other | Tower | 2025-10-16 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1334 | Approved | Presenter: Srivatsan, Imran | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP | Pushpdev Rai | [8 empty] | 12208, 12842 | E2open, OpenText |  | Inventory Reconciliation between IP and IF | In IF-IP bailment for inventory sync, it required to have interface for inventory sync, cycle count and daily reconciliation for Inventory at Rest​ Console: 3125/3126/3127/3128/3129 | New RICEFWs required for 4C1 B2B PIPs for IF-E2Open-IP |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B48E7A224-2668-4156-8875-201B4B393D1F%7D&file=INT-Build-CR1334%20Inventory%20Reconciliation%20between%20IF%20and%20IP.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 5 | LOGI1679, LOGI1678, LOGI1677, LOGI1676, LOGE1686 |  | LOGI1679, LOGI1678, LOGI1677, LOGI1676, LOGE1686 | 5 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-09 | o This CR is a request for 5 new RICEFW’s. o The volume of work is 9300 lots. o AR: Update effort for the 5 objects along with high-level estimate of hours - @Nayak, Keerti o AR: Add in what we can re-use from OSAT RICEFW’s - @Santhanam, Srivatsan o It will be done in FSSD on the IFS side |  |  | 2025-10-10 | • CR is focusing on inventory reconciliation of bailment materials between IF and IP. • This involves syncing stock type changes, cycle counts, and inventory snapshots between IF’s EWM/3PL systems and IP’s systems to ensure alignment and accurate reporting. • Four new interfaces and enhancements are planned to support these transactions, including outbound and inbound signals and daily inventory snapshots. • The scope includes bailment materials in specific locations like staging areas but excludes manufacturing locations. • The volume since January 2025 includes about 9,300 lots across multiple locations. • The total estimated effort is 2,400 hours, covered within the 2025 budget and existing Deloitte agreements. • Decision: Approved pending confirmation of funding and CW hours available for OpenText and e2Open. • AR - Kevin Brown to confirm availability of OpenText budget for CR1334. • AR - Jose Vargas Lepiz to confirm availability of e2Open budget for CR1334. | [5 empty] | Other | CL/OSC | 2025-10-10 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-09 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1335 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-09 | 0 | < 15 Days | shumehrotra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1336 | Approved | Presenter: Sunil Parida | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 06. PTP 07. FTS IF 08. FTS IP 16. Testing | sunil.k.parida@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | Straddle Bailment | Bailed Material Straddle | INT-CR-1115 | NA |  |  |  |  | WIINGS | Bailed material straddle CR | Bailed material straddle architecture definition to handle IP & IFS bailment to IF sites which will be partly S4 and partly ECC until R5 | R3 design is defined for S4. IP is big bang, while IF is not. Hence many HVM locations will still be on ECC when R3 goes live. IP bailment of material to such locations need to be managed through ECC straddle design for non valuated material PO creation, GR at IF 3PL, STO between S4 and ECC sites and bailment return process. This will also have ‘conversion’ implications to revalue material in ECC to $0 and convert them into IP S4. And Some of the manual process need to be conducted | ITC1 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR1336-%20Bailment%20Straddle%20CR.pptx?d=w9bd882740cc347de8f2dffaf41fe50f7&csf=1&web=1&e=Z3bQ7m | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 |  | 50000 | [11 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-16 | o Manually tested in ITC1 |  |  | 2025-10-17 | • A comprehensive explanation was provided on the straddle scenarios between different system releases (R3 to R4, R4 to R5), covering interactions between IP, IF, and IFS sites. • The approach focuses on maintaining existing R3 design integrity while semi-automating processes to manage POs and goods receipt in ECC and ECA systems. • This includes manual PO creation and coordination with logistics teams and 3PL carriers across multiple global sites. • The ECA system plays a critical role in generating reports to aid buyers and 3PL warehouses in managing inventory receipts. • The team clarified that existing interfaces and data tables are leveraged to minimize disruption and avoid code changes in the B2B logic. • Discussions also covered headcount requirements for manual operations during the straddle period, with estimates of additional external and contract resources needed to support processes from January to November 2026, with a budget of approximately $900K. Budget discussions were acknowledged but deferred for senior leadership resolution. • Decision: Approved • AR - Roman Vorel to identify '26 budget available for CR1336 funding. | [5 empty] | Other | CL/OSC | 2025-10-17 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1337 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 07. FTS IF 10. Analytics | mark.c.bargovan@intel.com | FPR — Sara Cooper | FPR - Aubrey Hinderlider | Volume Data Source to Split Spending for Close | CR1190, CR1148 | n/a | n/a | [5 empty] | ECA: Sourcing XEUS/MARS Volume Data via ECA to S4 (IF) S4 :Non-Burden and Non- depreciation allocation based on the Xesus/Mars volumes | ECA: Changes for FTS ECA view from Xeus/Mars FPR ECA view which consolidates the data as per table below S4 development CR for posting volume details for allocation S4:Non-Burden and Non- depreciation: 1: Need to allocate non-burden and non-depreciation to PCOS and OCOS based on the Xesus/Mars volume 2: Identify the OCOS WBS based on the dotprocess/stage or with first 4 or 6 digits of the dot process & flip date with backward logic, Plant and PCOS ALLOCATION Check Box Replicate the MDG custom table-Dotprocess/stage details into IF for dotprocess/stage values selection at OCOS WBS element level | ECA: FTW indicated previous design relied on 101/501 txn data that will have insufficient attributes for use case of splitting spending and assigning to WBS. S4: Actual production and non-production volumes are stored in Xeus and MARS Front End (FE) and Back End (BE) operations. The data includes various lot types such as TD (Technology Development), ENG (Engineering), and PROD (Production). Therefore, an ECA view is required to consolidate these actual volumes by lot types, manufacturing dot process, plant and stage to enable the necessary PCOS/OCOS split for actual allocation process. | Potential impact to current ECA development work | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1337%20%26%20CR1190_FPRExxxx%20%20Actuals%20PCOS%20OCOS%20ECA%20View.pptx?d=w40c3fb52b40c4d39926446ba2a598c8b&csf=1&web=1&e=w98CMZ | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA S4 | 7 | FPRI1670, FPRI1669, FPRE1671_IP, FPRE1671_IF, DATI1712, ECAFPRV6918, ECAFTSIFV6864 | 3150 | FPRI1670, FPRI1669, FPRE1671_IP, FPRE1671_IF, DATI1712 | 5 |  | 0 | ECAFPRV6918, ECAFTSIFV6864 | 2 | 2 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-23 | o Data will be mapped in Excel and loaded to support ITC1 testing. This will allow for allocation to be tested. |  |  | 2025-10-24 | • This CR involves automating the import of XEUS volumes from multiple sources into SAP S4 and ECA for cost allocation purposes. • Volumes are categorized by “O cost” and “P cost” to allocate non-depreciation commodity and consulting costs from primary cost centers to product and other costs. • The automation includes creating views in ECA, importing data into S4, and performing calculation mappings. • The build will not be completed by ITC1 but manual loading will be done, with automation targeted for ITC2. • The work involves SAP and ECA systems only, with no middle-layer systems like OpenText involved. • The meeting discussed the complexity of data sources, the need for summarized data from XEUS and MARS systems, and the challenge that not all volume data (especially non-revenue and engineering volumes) is currently in S4. • This situation was recognized as a design issue or misunderstanding, requiring future strategic review to fully integrate all volumes into S4 for comprehensive ERP functionality. • AR: Suresh Avula to validate architecture with Devendra Srivastava • Decision: Approved once Devendra Srivastava has signed off on design. | [5 empty] | Other | CL/OSC | 2025-10-24 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1338 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 10. Analytics | dikotha@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA | NA | NA | [5 empty] | Separate flow is required for Inventory reserves CFIN execution | Separate flow is required for Inventory reserves CFIN execution and derivation of excess inventory/demand requires change | Demand reserves calculation in consolidated models (PAPM) identified as a design miss | ITC2 | Yes | Core | Approved on 11/06 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B04C5964E-EFF1-421E-BA15-C52307171626%7D&file=INT-CR1338%20%25u2013%20Separate%20flow%20is%20required%20for%20Inventory%20reserves%20CFIN%20execution%25u200b.pptx&action=edit&mobileredirect=true | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | Yes |  | High | 0 | [7 empty] | 330 |  | 160 |  |  | 0 | 0 | 490 | Configuration | Yes | ECA | 22 | ECAFPRV2216, ECAFPRV2215, ECAFPRV2217, ECAFPRV2218, ECAFPRV2219, ECAFPRV2220, ECAFPRV2221, ECAFPRV4636, ECAFPRV7025, ECAFPRV7026, ECAFPRV7027, ECAFPRV7028, ECAFPRV7029, ECAFPRV7030, ECAFPRV7031, ECAFPRV7032, ECAFPRV7034, ECAFPRV7036, ECAFPRV7033, ECAFPRV7035, ECAFPRV7037, ECAFPRV7038 |  |  | 0 |  | 0 | ECAFPRV2216, ECAFPRV2215, ECAFPRV2217, ECAFPRV2218, ECAFPRV2219, ECAFPRV2220, ECAFPRV2221, ECAFPRV4636, ECAFPRV7025, ECAFPRV7026, ECAFPRV7027, ECAFPRV7028, ECAFPRV7029, ECAFPRV7030, ECAFPRV7031, ECAFPRV7032, ECAFPRV7034, ECAFPRV7036, ECAFPRV7033, ECAFPRV7035, ECAFPRV7037, ECAFPRV7038 | 22 | 22 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - AR: Align with Liesl on ECA effort – Sunil Narayanan | [9 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT Not Started | Object Missing in OT | In Progress | In Progress | Yes
|  | INT-CR1339 | Rejected |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | Junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | NA | NA | NA | NA | [5 empty] | New Form- Loading Check List | An Adobe form titled "Loading Check List" will be created within the existing 3PV Fiori tile. A new Destination field button will be added to the 3PV Fiori tile, allowing users to enter this information before printing the form.​ Additional logic will be implemented to retrieve and populate the required field values on the new form. | - To have better Shipment Verification Clarity​. - To have specific roles signing​. - To have better Accountability and Traceability of products for each party.​ - To minimize errors as operation is familiar with existing loading list | No Impact | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_EWM_Loading%20Check%20List.pptx?d=w87f5eaea7f1a46c497df8f521c4831cc&csf=1&web=1&e=5MhW4o |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-10-30 | - This is only for S4 - AR: Help GLO team figure out whether to go through Operate or Tech – Chris Woodburn | [9 empty] | Other | Not Assigned |  | Not Approved | 10, 2025 | 10, 2025 | 2025-10-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1340 | Cancelled |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | virgil.caruz@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | 152 | na | na | na | [5 empty] | PRF/RTF Horizon and System Interfaces | PRF/RTF Horizon and System Interfaces - see form | *Cancel this per Brian | see form | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1340%20-%20PRF_RTF%20Horizon%20and%20System%20Interfaces.pptx?d=w5af77caa7c0a4dc886ac64e090afbe68&csf=1&web=1&e=ADoMoU |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1341 | Approved | Presenter: Aishwarya, Todd | ERP | R3 (Release 3) R4 (Release 4) R5 (Release 5) | Medium | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 01. PMO 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 10. Analytics 11. Technology 12. Infrastructure 13. Security 14. OCM 15. Cutover 16. Testing 17. B-App | talbot.smith@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat | N/A | Adjustment based on detailed schedule | N/A | N/A | [5 empty] | Go-Live Schedule Alignment | Adjust the R3, R4, R5 go-live schedules to align with a consistent approach, specifically go-live on the first day of the third week of the second fiscal month of the fiscal quarter. | Detailed review of schedule indicated that go-live dates were not consistent in terms of where they fell in the calendar. This led to a discussion and several meetings to align with Finance and Operations on an approach | R3 will be pulled in by one week | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR1341%20Go-Live%20Schedule%20Alignment.pptx?d=w99b2844e20e74028bc03cd99584d87d6&csf=1&web=1&e=h3TE74 |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-16 | o Aligned in Core Leadership, and no other impact | [9 empty] | Other | Tower | 2025-10-16 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1342 | Approved | Presenter: Richard, Cari, Susan | ERP | R3 (Release 3) | High | 06. PTP | 6.1 PTP - ALL |  | 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 15. Cutover 16. Testing | susan.strathman@intel.com | E2E/Architecture — Satya Vajjala | PTP - Richard Taylor | IMR Straddle Design R3-R4, R4-R5 | NA | NA | NA |  |  |  |  | WIINGS | Intel Module Repair (IMR) Straddle Design R3-R4, R4-R5 | R3 Design is defined for S4. IP is big bang, while IF is not. Hence IMR locations in CH, KM, VN will still be on ECC when R3 goes live. IMR orders from S4 sites to non-IAO sites and vice-versa will need to be managed through a straddle architecture. The request is for the E2E team to propose a straddle design for IMR. ww42.5 PMO approved CR, no build impact (per Ranju), now E2E to update process. | The volume of IMR transaction is very high requiring support during straddle. Total Rolling 12 months Shop Orders = 66,850 Number of system users = 165 | <Need Deloitte Input> This E2E design is owned by the E2E team. | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CRxxxx%20%E2%80%93%20IMR%20Straddle%20Architecture%20R3-R4,.pptx?d=wf91c1999ab8845dc83a36b548ae7f817&csf=1&web=1&e=Ear60W |  | 1. Process Scope / Design Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-16 | o This is a request for approval to move forward with design for IMR straddle o This is related to cross-site issues for repairs.  If Vietnam or Malaysia needs to send something to Chandler for repair, there is currently no solution to handle these scenarios. o AR: Include statement on why this topic was late to straddle - @Pancholi, Ranju |  |  | 2025-10-17 | CR1342 - IMR Straddle Design R3-R4, R4-R5 • Addressed the need for a change request to enable straddle design for IMR locations spread across different system releases (R3, R4, R5). • This involves process design rather than technical automation to support transactions between IAO and non-IAO sites. • The end-to-end team requires approval of the change request before proceeding with the process design. • The discussion clarified that this is a manual process with no immediate build activities, and it will be prioritized behind other technical builds. • The group agreed to approve the change request and incorporate the process design into testing scenarios to ensure smooth implementation. • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-10-17 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1343 | Approved | Presenter: Piyush, Prem | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 05. OTC IP 09B. Data Migration | Piyush Ashok Patil | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | NA | NA | [5 empty] | Transformation logic update is required to automatically classify the HALB products in the new E4H system as per FERT to HALB mapping | Transformation logic update is required to automatically classify the HALB products in the new E4H system as per FERT to HALB mapping | Enables Fully automated conversion functionality |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1343%20Transformation%20logic%20update%20for%20OTCC232_33%20to%20include%20HALB%20FERT%20materials.pptx?d=w53e24b9de6ee4bc79409b532268e2ff5&csf=1&web=1&e=iavrzh |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 5 | [7 empty] | 70 |  |  | 0 | 70 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC232, OTCC233 | 2 | OTCC232, OTCC233 | 2 |  | 0 |  | 0 | N/A | N/A | 2026-02-13 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o We have 2 conversion objects that need update on transformation logic to automate the manual process | [9 empty] | Build | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1344 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 17. B-App | Siddharth Asitkumar Desai | PTP — Kenneth Salazar | PTP - Richard Taylor | 00004 - IP/IF Rework Automation | NA |  | NA |  |  | 12208 | E2open |  | IP-IF Rework Automation | Changes required in Logistics Interfaces of Outbound & Inbound 4B2 for IF & IP to automate GR for STO to transfer Rework material from IP to IF for OSAT | In this Scenario, IP raises a STO to transfer the Material that needs to be reworked to IF. Return SO (RMA) will be created in IF w.r.t Original Invoice and Rework Material will be received against the Return Delivery of respective Return SO (RMA). 1. Once GR is posted against Return Delivery on physical receipt of Rework Material from IP, Changes require to trigger Outbound 4B2 needs w.r.t the respective GR Document from IF to IP via OpenText. STO & STO Line reference needs to be retrieved from Return SO and sent as part of the Outbound 4B2 along with unique interface name as an Identifier for the respective scenario. 2. Outbound 4B2 sent by IF, will be received in E2Open via OpenText and E2Open needs to trigger the Inbound 4B2 to IP. IP will receive the respective Inbound 4B2 and change require to post the Inbound Delivery against STO and GR against the respective Inbound Delivery of the STO. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR1344_PTP%20LE_Automate%20GR%20for%20STO%20to%20transfer%20Rework%20material%20from%20IP%20to%20IF.pptx?d=w36e4489898ce4291aaa375bff3bc0c87&csf=1&web=1&e=gHMYbe |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Neetu Ramireddi that this can be cancelled as the volumes are not significant | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-14 | 0 | < 15 Days | siddesai@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1345 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shivkulkarni@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | WIP IP Forms | NA | NA | NA | [5 empty] | WIP IP forms - STO | Logics & enhancement to update OTC R3 developed forms to be utilized in case of IP STO process. | STEF TO FOLLOW UP WITH NEETU. To utilizes the existing OTC R3 forms instead of developing new from the scratch | No impact | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B36FCEA9D-BF21-4052-8398-A9BBE34ABF7A%7D&file=INT-Build-%20CR%20Logics%20&%20Enhancement%20to%20update%20WIP%20IP%20forms%20-%20STO.pptx=&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Need program CR to be cancelled as this was a build CR and got approved by Jorge under CR number 948. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1346 | Approved | Presenter: Sekhar | ERP | R3 (Release 3) | Low | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Security Role Restrictions for MySamples, ALPS and OCTO BU | Additional restrictions by MRP Area for S4 IP security roles to meet business need. | Ready for WW44.4 CR meeting. RAID# MRP Transactions needs additional segregation by MRP area to align to distinct commodity- specific Business unit. Currently, Plant specific roles already exist as part of Plant localization. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5C16DE77-459B-49B6-B4D4-707A0F956231%7D&file=INT-CR1346%20-%20Security%20Role%20Restrictions%20for%20MySamples%2C%20ALPS%20and%20OCTO%20BU.pptx&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [11 empty] | 40 |  | 0 | 0 | N/A | No |  | 0 | N/A | 3174, 3178 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | This is the POR | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1347 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.6 FPR - Cost and Profitability Analysis |  | 03. FPR 10. Analytics | mark.c.bargovan@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | PCOS OCOS SPlit | NA | NA | NA | [5 empty] | Need to expose planned volumes & provide SKF (%) of planned TD volume from ECA to automate PCOS/OCOS spending split in SAC Foundry spending model. | Need to expose planned volumes & provide SKF (%) of planned TD volume from ECA to automate PCOS/OCOS spending split in SAC Foundry spending model. | PCOS/OCOS data for planned volumes are stored in different systems for Front End (FE) and Back End (BE) operations. The data includes various lot types such as TD (Technology Development), ENG (Engineering), and PROD (Production), which represent plans or forecasts from different boundary applications. Therefore, an ECA view is required to consolidate these planned volumes by lot types and provide the necessary PCOS/OCOS split for SAC reporting. | No. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/03.%20FPR/3%20Final%20Deliverables/03.%20RICEFW%20Documentation/Team%2006%20-%20Cost%20%26%20Profitability/Reports/INT-CR0XXX_FPRExxxx%20%20Forecast%20for%20PCOS%20OCOS%20ECA%20View.pptx?d=wf17c6ec073804d37a6e0bd1a59c93418&csf=1&web=1&e=SRejQ0 |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 1 | ECAFPRV6919 | 3151 |  | 0 |  | 0 | ECAFPRV6919 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-23 | Related to CR1337 |  |  | 2025-10-24 | • A related CR extends the volume data usage by sending it to SAC for financial forecasting to split costs between other cost of sales and product cost of sales. • The source data for forecasting differs from actuals and involves multiple prior sources, including SAP IBP and wafer start data. • The ECA view aggregates these data sources for SAC consumption. • Ongoing changes to source systems and data flows were noted, and the forum acknowledged the complexity of the planning horizon data integration. • The CR was supported as an extension of the previous volume automation work. • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-24 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1348 | Approved | Presenter: Sandeep | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP 10. Analytics | sandeep.sastry@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | 188 | na | na | na | [5 empty] | Push / Pull / Cancel Concept | Push / Pull / Cancel Concept - see form | see form | tbd | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1348%20-%20Push%20Pull%20Cancel.pptx?d=w144229b921a34733b20e41f020d1df79&csf=1&web=1&e=v5dErg |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 |  |  |  |  | 240 | 80 | 80 | [6 empty] | 400 | 0 | N/A | Yes | ECA S4 SCP | 5 | PTPI0473, ECAFTSIPV6939, SCPIPSPRF0035, SCPIPSPRF0037, SCPIPSPRF0041 |  | PTPI0473 | 1 |  | 0 | ECAFTSIPV6939 | 1 | 1 | SCPIPSPRF0035, SCPIPSPRF0037, SCPIPSPRF0041 | 3 | SCPIPSPPDH0014, SCPIPSPPDH0028, SCPIPSPPDH0101, SCPIPSPPDH0127, SCPIPSPPDH0128, SCPIPSPPDH0129, SCPIPSPPDH0131, SCPIPSPPDH0130, SCPIPSPPDH0149, SCPIPSPPDH0150 | 10 | 13 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Entire process will be tested in ITC2 as this is a new process - Interface is changing date and quantity on production order or purchase order - AR: See if Kim is okay with this – Done - AR: Follow up with Chad that he is okay with the process (PDH) and Vanessa/Sunil with ECA - Anna |  |  | 2025-11-06 | Per Stacee Mattrazzo, CR was approved offline | [5 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R2 (Hypercare) |  | INT-CR1349 | Approved |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP 10. Analytics | shashank.kolhe@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | na | na | na | na | [5 empty] | PC Billings | PC Billings - see form | see form | see form | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1349%20-%20PC%20Billings.pptx?d=w5b0ea51c1c7545f09e8643fb4b29b221&csf=1&web=1&e=xXFiKc |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | [6 empty] | 2025-11-06 | Per Stacee Mattrazzo, CR was approved offline | [5 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1350 | Cancelled |  | SCP | R2 Hypercare | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | anthony.romano@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | na | na | na | na | [5 empty] | SMA Calc/Disag Driver change | SMA Calc - see form | see form, expecting CR in Nov'25 | see form | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1350%20-%20SMA%20Calc.pptx?d=w55fae8c6a31147b9b3f8101ec2a5981c&csf=1&web=1&e=vS176n |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1351 | Cancelled |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | anthony.romano@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | na | na | na | na | [5 empty] | Cust PRF/RTF Automation (for constrained) | Cust PRF/RTF Automation (for constrained) - see form | *Cancel per Anthony Romano. | see form | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1351%20-%20Cust%20PRF_RTF%20Automation%20-%20constrained.pptx?d=w9a62b8a421b14d2ab12905ef8759e7c7&csf=1&web=1&e=dXb2ao |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R5 (Oct 2027) | R5 ITC1 | INT-CR1352 | Approved |  | ERP | R5 (Release 5) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Yousef Khan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | Add Poland, Romania, Turkey to SAF-T Configuration scope in R5; add Japan to VAT Return - DRC Configuration scope in R3 | Adding the below SAF-T reports in scope: Poland JPK V7M - monthly declaration Romania Standard Audit File - Taxation (SAF-T) Standard Audit File - Taxation (SAF-T) Fixed Assets Turkey - TBD Add Japan's VAT Return to DRC configuration scope (awaiting Vidhata's confirmation) | Implementing SAF-T automation allows Intel to efficiently comply with Polish and Romanian tax regulations by streamlining the digital submission of comprehensive accounting and tax data in a standardized format, as mandated by local authorities. Similar rationale applies to automating Japan's VAT Return generation. |  | Yes | Non-Core | AR: Include in R4/R5 scope list and discussions in January 2026 – Alpna | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B860916EE-02A5-4DDA-8630-0811C35A951C%7D&file=INT-CR1352%20-%20Add%20Poland%2C%20Romania%2C%20Turkey%20to%20SAF-T%20Configuration%20scope%20in%20R4R5%20and%20e-ledger%20for%20Turkey.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change | Manage Indirect Tax Reporting and Compliance |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Design | CL/OSC | 2026-04-02 | 04, 2026 | 04, 2026 | 10, 2025 | 2025-10-15 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1353 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Kolleru Venkatesh |  | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Cancellation of RICEFWID FTSI0687 | This whole functionality now will be handled in SMH using existing interface FTSI0422 SMH will perform the check to see if an SAP batch exists for the vendor batch (MES Lot). If no duplicates are found only then Create SAP batch API will be called by SMH. This requirement will be addressed in SMH (integration layer). | Business decision change | No Impact to Existing Deliverables | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Interface/FTSI0687%20-%20MES-SMH-S4%20Integration%20Lot%20RENAME%20Event/EXT%20RE%20MES%20Integration%20Meeting%20-%20RestrictedUnrestricted%20-%20Cancellation%20INT-CR1353%20-%20Approval.msg?csf=1&web=1&e=AZoHn3 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  | High | 0 | 3 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI0687 | FTSI0422 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-29 | [10 empty] | Other | Tower | 2025-10-29 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-15 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1354 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP | YASH DESHPANDE | PTP — Kenneth Salazar | PTP - Richard Taylor | “Purchasing services fiori tiles will be replaced with a Circuit page with the same tiles as purchasing services fiori used to have.” | CR1169 | NA | NA | [5 empty] | Descoping of RICEFW PTPI0817_IF/IP | To proceed with descoping of PTPI0817_IF/IP with alterative solution “Purchasing services fiori tiles will be replaced with a Circuit page with the same tiles as purchasing services fiori used to have.” Which is going to be processed through CR1169 | Intel Information security policy requires only users with a need-to-know be present in enterprise systems. All Intel users have access to the existing Fiori Launchpad and can access applications like My Inbox, eCheck requests and non-SAP URLs when needed. This is possible because all Intel users on legacy SAP system are provided default "birthright" access to the SAP ECC and SRM systems. This can impact any RICEFW where an approval is needed and the complete scope is unknown. In the future, SAP users on S4 systems will not be granted any default user ID or authorization to S4 systems so default access will not be possible |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 175 | > 30 Days | yswaddeshpande@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1356 | Approved | Presenter: Sekhar | ERP | R3 (Release 3) | High | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP 10. Analytics | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Change Request for Conversion of Intel Products Bailed Inventory from OSATs and IF | Change Request for Conversion of Intel Products Bailed Inventory from OSATs and IF | During the initial requirement gathering phase, the need to convert Intel Products' bailed inventory—particularly semi-finished goods—was overlooked. This requirement was initially deemed to be handled by the Logistics Team; however, their scope is limited to converting only finished goods inventory. As a result, the FTS-IP Team has taken ownership of this conversion requirement. This Change Request (CR) document is being created to initiate the authoring and development of a program that will enable the conversion of Intel Products' bailed inventory into the IP SAP S/4 system |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1356-%20Change%20Request%20for%20Conversion%20of%20Intel%20Products%20bailed%20inventory%20to%20IF%20and%20OSATs%20.pptx?d=w4cba93c02cc84d8698060955c319850e&csf=1&web=1&e=xvUeL0 | Missed Requirement | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | Conversion | 4 | FTSC1682, ECAFTSIFV6816, ECAFTSIFV6412, ECAFTSIFV4675 | 3149, 3167 | FTSC1682 | 1 |  | 0 | ECAFTSIFV6816, ECAFTSIFV6412, ECAFTSIFV4675 | 3 | 3 |  | 0 |  | 0 | 0 | ECAFTSIFV6412, ECAFTSIFV4675 | 2 |  | 0 | ECAFTSIFV6412, ECAFTSIFV4675 | 2 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o This is a CR highlighted in Core Leadership, and it will be needed to pull and convert bailed material before being loaded in SAP. o It will make it to MC1 | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1357 | Cancelled | [22 empty] | This requirement was initially deemed to be handled by the Logistics Team; however, their scope is limited to converting only finished goods inventory. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1358 | Cancelled | [22 empty] | As a result, the FTS-IP Team has taken ownership of this conversion requirement. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1355 | Cancelled | [22 empty] | This Change Request (CR) document is being created to initiate the authoring and development of a program that will enable the conversion of Intel Products' bailed inventory into the IP SAP S/4 system. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1359 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Shivkulkarni@Deloitte.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | WIP IP Forms - STO | Share folder Enhancement to upload output in WIP IP forms - STO | NA | NA | [5 empty] | INT-Build- Share folder Enhancement to upload output in WIP IP forms - STO | Enhancement to upload WIP IP STO forms to share folder when output trigger for communication with 3PL. | Stef to close with logistics, need design open created. Uploading WIP IP STO forms to a share folder upon output trigger ensures immediate, standardized access for 3PL partners, improving communication efficiency and traceability while reducing manual errors. | ITC 2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCB9D9895-F93C-4EB1-A402-3A9C3FFDDF1E%7D&file=INT-Build-%20Share%20folder%20Enhancement%20to%20upload%20output%20in%20WIP%20IP%20forms%20-%20STO%20.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Need program CR to be cancelled as this was a build CR and got approved by Jorge under CR number 947. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1362 | Approved | Presenter: Shilpa Waiting on ECA alignment | ERP | R3 (Release 3) | High | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration |  | 08. FTS IP 10. Analytics | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams |  | CR1356, CR1384 | [7 empty] | Change Request for Reporting Scrappage at OSAT and IF manufacturing locations for Semi Finished Goods | Change Request for Reporting Scrappage at OSAT and IF manufacturing locations for Semi Finished Goods | In alignment with current business processes, the FTS-IP Team is responsible for updating scrappage related to Work-in-Progress (WIP) inventory at the production order operation level. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1362-%20Change%20Request%20for%20Reporting%20of%20Scrappage%20at%20OSAT%20and%20IF%20Manufacturing%20locations%20for%20Semi%20Finished%20Inventory%20in%20IP%20SAP%20S4%20System%20.pptx?d=wc2949c9d99064eefa135ff5a11a03763&csf=1&web=1&e=PzsSxE |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [9 empty] | 350 |  |  |  | 0 | 350 | N/A | Yes | S4 | 4 | FTSI1693, FTSI1692, ECAFTSIFV5725, ECAFTSIPV7004 | 3177 | FTSI1693, FTSI1692 | 2 |  | 0 | ECAFTSIFV5725, ECAFTSIPV7004 | 2 | 2 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) |  |  | 2025-10-30 | - CR started as how we capture scrap - Scrapping is targeted for ITC1, and scrap reporting is targeted for ITC2 - Conversion team is okay, and the FS is fast-tracked - PIP comes through E2Open, but there is no change required - This will impact 7b1 work. This is a technical dependency. So, this is prioritized. - AR: Need to make sure that the team can mock up the 7b1 data – Shilpa - AR: Capture sentiment that data will be manually entered into PDF. No impact to Boundary Apps | [9 empty] | Other | Not Assigned |  | Not Approved | 10, 2025 | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1363 | Cancelled | [22 empty] | However, scrappage of inventory that is at rest (i.e., semi-finished goods held in inventory) has traditionally been outside the scope of FTS-IP responsibilities. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1364 | Cancelled | [22 empty] | To support a new business requirement, the FTS-IP Team is now authoring and developing an interface object to automate the reporting of scrappage occurring at OSAT and IF manufacturing locations for semi-finished goods in inventory. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1360 | Cancelled | [22 empty] | This enhancement will enable automated scrap reporting within the IP SAP S/4HANA system. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1361 | Cancelled | [22 empty] | The data exchange will be facilitated using PIP 7B1, which will transfer scrappage information from OSAT or IF suppliers to middleware systems. An API will then be used to transmit this data from the middleware to the IP SAP S/4HANA system. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-15 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2m (January 2026) | R2.2 ITC | INT-CR1365 | Approved |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | Junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | LOGF0334 | N/A | N/A | N/A | [5 empty] | 3PV Form Changes​ | Changes to 3 PV Form | Improve operational visibility and compliance tracking by enabling system printouts with key details (Truck No, Destination, Form ID) and implementing separate workflows for 3PV and Loading Checklist processes. Enhance security compliance.​ | No impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_3PV_Form_Changes.pptx?d=wd18bf5e96d2b4902a69932cbc7ab2be1&csf=1&web=1&e=B4E5cc |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 10 | [5 empty] | 18 |  |  |  |  | 0 | 18 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0337 | 1 | LOGF0337 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-04 | Uzma approved offline with Kim and Heather. We agree for ITC1 these are the preferred methods in order: 1. Ideally everything is automated, and the integration testing flows like a true integration test like the box in green I believe. 2. If a system cannot generate a 7B1 file(i.e. ECA in this case) we would like to get the structure of the file out to where we can manually input the data into that file, SMH picks it up and it flows like option 1(green box). @Srivastava, Devendra & @Heagney, Heather, can you confirm if this can be done or not. I foresee this as a need in the future as well 3. If we cannot do 1 or 2 then last resort is to use Postman to call the S4 APIs just to get us through testing the S4 capabilities and production data/documents for other teams to use. | [9 empty] | Build | Tower | 2025-11-04 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-15 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1366 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.3 OTC IF - Billing and Rebates |  | 04. OTC IF 13. Security | tracy.e.bowerman@intel.com | Security — Debbie Whitely | OTC IF - Angela Laskowski | Program team support role | N/A | N/A | N/A | INC14988103 |  |  |  |  | Allow OTC IF Order to Cash Display Only role have access to Billing Job Log ( V.22) & Sales Documents user Status List ( V.26) | Allow OTC IF Order to Cash Display Only role have access to V.22 Display Collective Runs and V.26 List Sales Documents by objetc status | adding both these transactions to the OTC IF Order to Cash Display Only role will allow PS/BA to troubleshoot and analyze issues related to billing and sales processes. | N/A | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-XXX_%20Add%20have%20access%20to%20Billing%20Job%20Log%20%26%20Sales%20Documents%20user%20Status%20List%20%20OTC%20IF%20Order%20to%20Cash%20Display%20Only%20role.pptx?d=wba00944aaf9d44bdaa1b84efa9483fdf&csf=1&web=1&e=OBApRi |  | 8. Non-Build Infrastructure-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 174 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1367 | Approved |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 07. FTS IF 10. Analytics | eric.yamada@intel.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma | Release 3 IF Reports | N/A | N/A | N/A | [5 empty] | R3 IF Additional Reports Requirements | Request to add 16 additional reports to ECA timeline for R3 | Reports identified post requirements gathering. All reports have been reconciled against other identified reports and consolidated to single reports covering all areas (Front end, WLA and Back End) . Current platforms Power and Vipre will be EOL these reports are required to replace existing reports from both systems. Report logic and data sources are changing as part of IAO business process changes in the R3 implementation – Related to RAID 1394​ | None | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/Intel%20Foundry%20R3%20Program%20Mgmt/Program%20Integration/Change%20Control/SCP-CR.1367-%20Release%20R3%20Reports%20CR.pptx?d=w4f450ea634764f58b7d40592ed7d0ad6&csf=1&web=1&e=2xZBoS |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | 35000 | [12 empty] | 0 | 0 | N/A | Yes | ECA | 14 | ECAFTSIFV6915, ECAFTSIFR6480, ECAFTSIFR6838, ECAFTSIFR6476, ECAFTSIFR5715, ECAFTSIFR6697, ECAFTSIFR6690, ECAFTSIFR6691, ECAFTSIFR6692, ECAFTSIFR6693, ECAFTSIFR6695, ECAFTSIFR6820, ECAFTSIFR6819, ECAFTSIFR6821 |  |  | 0 |  | 0 | ECAFTSIFV6915, ECAFTSIFR6480, ECAFTSIFR6838, ECAFTSIFR6476, ECAFTSIFR5715, ECAFTSIFR6697, ECAFTSIFR6690, ECAFTSIFR6691, ECAFTSIFR6692, ECAFTSIFR6693, ECAFTSIFR6695, ECAFTSIFR6820, ECAFTSIFR6819, ECAFTSIFR6821 | 14 | 14 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - Started as RAID for reports required in IF side. These were identified after requirements gathering ended and is driven by Vipre being EOL’ed recently. - New scope for IAO - AR: Add in that $35K is required for Q1 2026 - Commercial impact: $35K |  |  | 2025-10-31 | • Change request concerning Foundry ECA reporting for R3, consolidating 14 report requirements identified post-R3 requirements gathering from manufacturing, logistics, and other teams. • Twelve of these reports are new, with an estimated 25 weeks of work to be done after ITC1 and ready for testing in ITC2. • The business timing aligns with the testing phases, and the cost is within budget for Q1 2026. • Discussions clarified that this CR should have been tracked as an open design however it was not. It is related to closing a previous RAID item (1394). • Decision: Approved | [5 empty] | Other | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1368 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 13. Security | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Log Inv Manager Profile Enhancement | Today, Operations Managers do not have the ability to execute BCP receipts into S4/EWM when systems are down/not working | To provide Inventory Area Managers (Logistics Ops Managers) Secuity Profile access to critical transactions in S4 and EWM that allows them to quickly execute required transactions to process materials. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Log%20Inv%20Manager%20Profile%20Enhancement.pptx?d=w589b3f3ab8d84f4bbdef4d77a625388a&csf=1&web=1&e=gnR9Nc |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 174 | > 30 Days | suresavula@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1369 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | George Bakare | [11 empty] | FPRE0884_IP - CPA Budget Approval App- Attachment should be stored in SAP | FPRE0884_IP - CPA Budget Approval App- Attachment should be stored in SAP | Attachment should be displayed or downloaded in the app itself once request is Saved or Submitted. Attachment is to be stored in SAP server. ACMS is being replaced by DMS. |  | No |  |  |  |  | 1. Process Scope / Design Change | DC-050 |  | Medium | 26 | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled as this will be created in Build CR log | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 0 | < 15 Days | sandpendyala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1370 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | George Bakare | [11 empty] | FPRE0884_IF - CPA Budget Approval App- Attachment should be stored in SAP | FPRE0884_IF - CPA Budget Approval App- Attachment should be stored in SAP | Attachment should be displayed or downloaded in the app itself once request is Saved or Submitted. Attachment is to be stored in SAP server. ACMS is being replaced by DMS. |  | No |  |  |  |  | 1. Process Scope / Design Change | DC-050 |  | Medium | 15 | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled as this will be created in Build CR log | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 0 | < 15 Days | sandpendyala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1371 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | George Bakare | [11 empty] | FPRE0885 (IP) - Addition of Attachment column in the custom Fiori app WBS Creation/Update. | FPRE0885 (IP) - Addition of Attachment column in the custom Fiori app WBS Creation/Update. Additional column in the ALV Grid for attachment to be added. | ACMS is being replaced with DMS. |  | No |  |  |  |  | 1. Process Scope / Design Change | DC-050 |  | Medium | 30 | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled as this will be created in Build CR log | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 0 | < 15 Days | sandpendyala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1372 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | George Bakare | [11 empty] | FPRE1600 (IF) - Addition of Attachment column in the custom Fiori app WBS Creation/Update. | FPRE1600 (IF) - Addition of Attachment column in the custom Fiori app WBS Creation/Update. Additional column in the ALV Grid for attachment to be added. | ACMS is being replaced with DMS. |  | No |  |  |  |  | 1. Process Scope / Design Change | DC-050 |  | Medium | 17 | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled as this will be created in Build CR log | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 0 | < 15 Days | sandpendyala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1373 | New |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Kolleru Venkatesh |  | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | FTSE1634 Time Line need to change to R3 To Move the object FTSE1634 out from R2.5 to R3 |  | For Anafi there is no manual BI upload so we do not need to develop any UI to upload BI manually in Anafi 2.5 timeline | No Impact to Existing Deliverables | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/EXT%20RE%20FTSE1634%20to%20move%20to%20R3%20timeline.msg?csf=1&web=1&e=o9KkeE |  |  | 13. Other Milestone Adjustments |  |  | High | N/A | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-16 | 174 | > 30 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1375 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF 17. B-App | Pravin Sowale |  |  |  | 869 |  |  |  |  | 12015 | SiGaC (Site Gas and Chemical) | WIINGS | SiGaC Bapp Interface Readiness for ITC2 | SIGAC Boundary app related 2 interfaces – LOGI1084: Interface to SiGac for capturing the consumption of Chems and Gases against a cost center: Build is completed but Baap is not ready for FUT testing. New CR#869 for SIGAC interface – RICEFW Console #3070 |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/INT-CR1375%20-%20SiGaC%20Interface%20for%20ITC2.pptx?d=w165252e335734a40a017bde549930f25&csf=1&web=1&e=7gjplc |  | 13. Other Milestone Adjustments |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment S4 | 2 | LOGI1675, LOGI1084 |  | LOGI1675, LOGI1084 | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | Yes | No | 2025-10-27 | - There is a change in the SiGaC team structure, so there is a delay in the timeline to get the objects done. - The interface is all completed, but we are waiting for the SIGAC team to get the data, which will not come until December end. - AR: Need to add in how the change was identified and what the driver of the CR is - AR: Add in a tagging this is related to WIINGS scope - AR: Include timeline | [9 empty] | Other | CL/OSC |  | Missing Review Date for Approval Level | 10, 2025 | 10, 2025 | 2025-10-17 | 0 | < 15 Days | vgulhane@deloitte.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR1376 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-17 | 0 | < 15 Days | vgulhane@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1418 | Cancelled | [34 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1374 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-17 | 0 | < 15 Days | vgulhane@deloitte.com |  | No |  | No Objects |  | In Progress | No
R5 (Oct 2027) | R5 ITC1 | INT-CR1377 | Approved |  | ERP | R5 (Release 5) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | Eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | Multi Product Wafer (UOM Duplicate) | NA | NA | NA | [5 empty] | Multi Product Wafer (UOM Duplicate) | Multi Product Wafer (UOM Duplicate) | Multi Product Wafer (UOM Duplicate) | ITC2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR_1377%20Multi-Prod%20Wafer%20IP%20product.pptx?d=wce2d63c917114cef986747ce7ac5e015&csf=1&web=1&e=Skp5Ry |  | 0. Request for Investigation |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - AR: Need to go and explore other options |  |  | 2025-10-31 | • Scope is master data work for a handful of products (e.g., Willowpad, Wildcat) currently scheduled for ITC3. • Addressed challenges with multi-product wafer master data, currently planned for ITC3, which risks missing the ITC2 timeline. • Team plans to meet with the master data team to explore manual interventions or reduced automation to bring critical data into ITC2. • This approach aims to mitigate risks associated with late automation and maintain downstream boundary application testing. • Decision: Not Approved | 2025-11-23 | Approved by Uzma offline |  |  |  | Other | CL/OSC | 2025-11-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1378 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  |  |  |  | N.A. | [6 empty] | Cancel Objects: PTPE0471 [Review the auto reversal of payment documents, Reset clearing of invoice and payment documents & update funding request with zero balance - SAP S/4 HANA CFIN ](Descoping) | Removing object PTPE0471 [Review the auto reversal of payment documents, Reset clearing of invoice and payment documents & update funding request with zero balance - SAP S/4 HANA CFIN] from PTP- EP subteam. | We received confirmation from Treasury team to remove this from P2P side and all P2P relevant logics are added in RTR object. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/EXT%20RE%20Request%20for%20GPO%20approval%20related%20to%20descoping%20PTPE0471%20CR%20ID%20INT-CR1378.msg?csf=1&web=1&e=ppjVpA |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 10, 2025 | 2025-10-18 | 172 | > 30 Days | suggupta@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1379 | New | Presenter: Jason Carmichael | ERP | R3 (Release 3) | High | 03. FPR | 4.1 OTC IF - ALL |  | 03. FPR 04. OTC IF | stacey.ramsdell@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | Revenue by Stage | N/A | N/A | N/A | [5 empty] | Revenue by Stage and Percentage of Completion (POC) Rev​ | Design simplification for revenue by stage/POC rev rec custom program and report. See next slide for previous design and simplified design.​ - Recording revenue by stage in the GL: instead of different processes for bailed and non-bailed, will have a single process that occurs each time an invoice posts.​ - Instead of recording revenue by stage for bailment, we will do a quarter end accrual (auto-reversing) to record POC revenue​ Change for OTC is for revenue account determination. Will be updated in review and sign off with Deloitte. | Simplify design to enable all revenue billings to post as revenue, rather than unbilled receivable. Eliminated unbilled receivable recon challenges. | No | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR%23%23%23%23%20Revenue%20by%20Stage%20and%20POC%20Rev%20Rec.pptx?d=w94e0dd405ee54bf0812fb0cde3ccdef1&csf=1&web=1&e=dRjxR4 |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | No | 2025-10-23 | - AR: Add number of objects, object ID’s and dates | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-21 | 169 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1380 | Cancelled |  | SCP | R3.X (Post-R3) | Medium | 07. FTS IF | 7.13 FTS IF - IF BE Supply Planning |  | 07. FTS IF 08. FTS IP 10. Analytics | matt.katzorke@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | IAO00195 | New Design Change | NA | NA | [5 empty] | Approved: Model Memory as a Constrained Material for Back side Metallzation (BSM) | As per initial design memory supply was considered as unconstraint. However, the memory going through the Back side Metallization is constraint by resource capacity This change will include getting PRF-RTF interaction with IP and other external customers. Needs to validate the overall BOM structure and resource modeling for it include coupon die supply chain and BSM related constraint Due to common capacity at BSM, the overall demand prioritization logic to be finalized. Update Solution design documents on the IF IT side.. | The resource used for Backside metallization is shared for both memory and other FG and is a constraint resource. Hence it is critical to model the memory related products to get the effective resource availability and utilization. Since IF is providing service for the memory products, these should be available in CDP, and we need to have a PRF and RTF process associated with it | Initiated solutioning with all potentially impacted teams after which the schedule will be confirmed. Current approved CR's for IF/SP run beyond ITC1, so this will be queued up after those beyond ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Change%20ID_Memory%20as%20a%20Constrained%20Material.pptx?d=w4cb90574fbf84ccebc7e981d17d6b3c0&csf=1&web=1&e=TBzR26 |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is duplicated of CR1396 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1381 | Approved | Presenter: Chris Martin, JR Hoover | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP 07. FTS IF | christopher.j.martin@intel.com | PTP — Kenneth Salazar | PTP - Richard Taylor | Automate Warranty Financial Credit Posting | RICEFW 2516 | RICEFW 2516 | RICEFW 2516 |  |  |  |  | WIINGS | Automate Warranty Financial Credit Posting | Construct a program to automate the creation of a credit memos after Suppliers have approved warranty claims. Utilizes SAP “Create Invoice” BAPI to create credit memos. Credit memo will pass through ReadSoft for validation prior to payment. | Current design sends Supplier-validated claims to an email address for manual processing. The recipient of this email is expected to complete the creation of a credit memo (4mins/memo). With an existing BAPI in SAP and the volume of current warranty claims between 5,500 - 7,000 claims per month, automation is a requirement. | Target completion for ITC2. This is the final step in warranty workflow, so it will not interfere with warranty testing in ITC1. | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/INT-CR1381%20Automating%20Warranty%20Credit%20Memo%20Posting.pptx?d=wbdd2e638d7954e4faf3e41d561ba1f2d&csf=1&web=1&e=9QhyDz&xsdata=MDV8MDJ8YW5udGFtQGRlbG9pdHRlLmNvbXxjMmQyOTVhMWNlYTk0ZjQyYjBjODA4ZGUxMWE0OTQ3N3wzNmRhNDVmMWRkMmM0ZDFmYWYxMzVhYmU0NmI5OTkyMXwwfDB8NjM4OTY3NTk1NzI2NTgyMjk4fFVua25vd258VFdGcGJHWnNiM2Q4ZXlKRmJYQjBlVTFoY0draU9uUnlkV1VzSWxZaU9pSXdMakF1TURBd01DSXNJbEFpT2lKWGFXNHpNaUlzSWtGT0lqb2lUV0ZwYkNJc0lsZFVJam95ZlE9PXwwfHx8&sdata=b0FVNEFOOXBoQ1hwZG5EWlYwNW96aHFvc2NUMFg5ZU16SXB0by9YWWk5RT0%3d&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTg1MjYuMjA2MDQiLCAiT1MiIDogIldpbmRvd3MiIH0%3D&CT=1761171896399&OR=Outlook-Body&CID=27B4C36F-8E8E-44D9-8150-430300CFEBEF&wdLOR=c12B34BC0-DD77-41D8-8B17-08C0EB55C829 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No |  | Low | 0 | 70 | 25000 | [11 empty] | 0 | 0 | N/A | Yes | S4 | 1 | PTPE1687 | 3145 | PTPE1687 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | No | No | 2025-10-23 | o The 2 solutions were not viable ones, and the PM team decided to go with the manual process.  SCP team will write an email to the buyer to create a credit memo.  This is not a process today, and it will add 5600 hours per year. o This is not required for ITC1 as it will be tested at the end of a scenario. So, no subsequent steps. |  |  | 2025-10-24 | • CR is seeking approval to proceed with detailed design and refined development estimates for automating the credit memo process related to equipment spares warranty. • Currently, when equipment under warranty is repaired using spares, a manual process is used to create credit memos after supplier approval. • The proposed solution involves using an SAP BAPI to automate credit memo creation, integrating with existing workflows to ensure invoices are verified before posting. • The timeline targets ITC2 for completion, with ITC1 being preferable but not mandatory. • Concerns were raised about the timing of the request relative to a design freeze and resource availability. • The forum emphasized adherence to the design freeze deadline of October 31, and the need for impacted teams’ agreement before proceeding. • Funding and development complexity were also discussed, with the consensus being to proceed with detailed design if it can fit within existing priorities and resources without jeopardizing other work. • Decision: Approved for detailed design work if it does not impact other critical work and meets design freeze deadline of October 31. | 2025-10-31 | • Presented a CR for automating credit memo creation after supplier-approved warranty claims for equipment spare parts. • Volume is 5-7K transactions/month, $130M annual value. • The current manual process would require approximately three full-time employees and is prone to delays and errors. • The automated solution involves using SAP’s Miro BAPI to create credit memos and integrate with existing enable payment workflows. • The CR is categorized as a must-do enhancement, with no objections from the team, and is planned for ITC2. • Decision: Approved. |  |  |  | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1382 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | Kimberly Moore | [11 empty] | LOGE838_IP : One time location creation impacted due to std SAP recommendation + process change from sales force | LOGE838_IP : One time location creation impacted due to std SAP recommendation + process change from sales force | LOGE838_IP : One time location creation impacted due to std SAP recommendation + process change from sales force |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6F33C213-6394-4479-B587-6102DDB50DDC%7D&file=INT-CR1382_TM%20One%20Time%20Location%20Intel%20IAO%20Program%20for%20SAP.pptx&action=edit&mobileredirect=true&xsdata=MDV8MDJ8fDk0MTI1ODI3NGE4ZDQ2ZDIwZTk3MDhkZTEwYWE0Njg4fDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg5NjY1MjA2NDY5OTk4ODl8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKRFFTSTZJbFJsWVcxelgwRlVVRk5sY25acFkyVmZVMUJQVEU5R0lpd2lWaUk2SWpBdU1DNHdNREF3SWl3aVVDSTZJbGRwYmpNeUlpd2lRVTRpT2lKUGRHaGxjaUlzSWxkVUlqb3hNWDA9fDF8TDJOb1lYUnpMekU1T20xbFpYUnBibWRmV20xU2JGcEhUVE5aVkZGMFRYcG5lazFETURCT1YwVXlURlJvYkU1WFZYUlpla0pzV2tkV2FsbHRSWGxhVkd4cVFIUm9jbVZoWkM1Mk1pOXRaWE56WVdkbGN5OHhOell4TURVMU1qWTBNek0yfDQ3N2JlYjAwZmJkZDQ2NWJjNzNiMDhkZTEwYWE0Njg3fGQxZjc4YzAyZGNhMjQyOWQ4ZGQ0Zjg3YWJjN2RkM2U2&sdata=ZTBVSU4vZHdpbC9OY0hxdXd4Sjdxemt1a2NOWXMybFBiN0IybnpYL3dqOD0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cadshinde%40deloitte.ca |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0838_IP | 1 | LOGE0838_IP | 1 |  | 0 |  | 0 | N/A |  | 2025-12-08 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - This is agreed upon by the tech team to deliver in ITC1 - There is no external impacts | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-21 | 0 | < 15 Days | adshinde@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1383 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury |  |  |  | INT-CR1683 | [7 empty] | Replacing Alfresco with EDDAR for docking. | Docking functionality saves images for tracking the quality of the returns. These were supposed to be saved in Alfresco. But because of the recent decision on not wanting to use Alfresco, the alternative to be used is EDDAR. | Docking functionality saves images for tracking the quality of the returns. These were supposed to be saved in Alfresco. But because of the recent decision on not wanting to use Alfresco, the alternative to be used is EDDAR. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/CRs/INT-CR1383%20Replacing%20Alfresco%20with%20EDDAR%20for%20docking.pptx?d=w0d3f96d2e0074b169328389f9491cf1f&csf=1&web=1&e=39wFE0 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [8 empty] | 80 |  |  |  |  | 0 | 80 | Tech - S/4 | No |  | 0 | N/A | 3146 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE1265, LOGE1277 | 2 | LOGE1265, LOGE1277 | 2 |  | 0 |  | 0 | N/A | N/A | 2026-03-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-23 | o Earlier, docking did include EDDAR, so we had 3 objects created.  When there was a decision to replace EDDAR with Alfresco, the RICEFW that connects to EDDAR was descoped.  But now we need to bring back EDDAR because Alfresco did not work. o AR: Add in hours of effort if any changes to EDDAR is required. - @Julury, Surendra |  |  | 2025-10-24 | • A CR to replace Alfresco with EDDAR in the docking process for IP returns was presented. • Alfresco had integration issues and a KDD had been previously approved not to pursue Alfresco further. • The replacement requires changes to two enhancements and the creation of a new interface to connect with EDDAR. However, there was some confusion regarding whether application layer code changes were necessary, as some Deloitte personnel indicated no changes would be needed since the document store objects are logical and tool-agnostic. It was agreed to take this discussion offline to clarify. • AR: Surendra Julury - Take offline discussion to clarify application layer impact. • Decision: Approved. Team to discuss offline if code change is required. | [5 empty] | Other | CL/OSC | 2025-10-24 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-21 | 0 | < 15 Days | sjulury@deloitte.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC2 | INT-CR1384 | Approved | Presenter: Shilpa | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 03. FPR 10. Analytics 17. B-App | salingam@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | 00156 - FTS IP physical inventory reconciliation | NA | 02611 Inventory SCrapping | NA | [5 empty] | Inventory Reconciliation | Change Request for an ECA Report to facilitate Inventory Reconciliation between IP S4 and External OSATs & IF manufacturing locations​ | During IP/IF/OSAT inventory management discussions it is identified to have inventory sync between IP S4 and IF & External OSATs since the transaction volume is high. It is proposed to use 7B1 PIP for inventory sync, and daily reconciliation. The data flows from IF/External OSATs to ECA via IP PDF SMH. | Targeted for ITC2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B54985BA7-3942-41AE-8688-913DCBBF8F6B%7D&file=INT-CR1384_Inventory%20Reconciliation%20in%20IP.pptx&action=edit&mobileredirect=true | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [9 empty] | 720 |  |  | 80 | 0 | 720 | N/A | Yes | ECA | 7 | ECAFPRV6942, ECAFPRV6943, ECAFPRV6944, ECAFPRV6946, ECAFPRV7016, ECAFTSIFR6964, ECAFTSIFR6965 |  |  | 0 |  | 0 | ECAFPRV6942, ECAFPRV6943, ECAFPRV6944, ECAFPRV6946, ECAFPRV7016, ECAFTSIFR6964, ECAFTSIFR6965 | 7 | 7 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | o Purpose & Scope  The five-way reconciliation report is designed to compare inventory and financial data across five systems: IP S4, CIBR, ICOST, SAP ECC, and IF S4, especially during the transition phases of the IAO program.  It addresses straddle and post-go-live requirements, ensuring tight integration and identifying discrepancies between legacy and new systems. o Technical Complexity  Major challenge is translating and cross-mapping data between systems, as SAP uses storage locations and CIBR uses operation codes, requiring complex reference tables and transformations. Manual comparison is not feasible.  The report will highlight discrepancies but will not determine which system is correct; manual troubleshooting processes will be developed to resolve issues. o Delivery Plan  The report will be delivered in two phases: a three-way reconciliation for ITC2 and a full five-way reconciliation for ITC3, due to data availability and complexity.  Up to 10 views may be developed, with the exact number determined after further data analysis.  Functional specification will be delivered in a single phase by end of year, with technical specs split between ITC2 and ITC3. o Ownership & Next Steps  Intel is responsible for both functional and technical development, with Shilpa Chandra working on the functional spec. Manual business processes will be used to troubleshoot discrepancies identified by the report, with separate CRs for any transactional updates required.  The team emphasized the ongoing complexity and time required for reconciliation, even after initial report delivery, and the importance of early business team engagement.  Rebecca to schedule meetings every couple of weeks through the end of the year, shifting to weekly as the team moves into detailed work, to closely track progress and address any issues.  Vanessa and team to update the object tracker as views are finalized and to provide status updates at each checkpoint.  AR: Vanessa Clark to add notes to CR1384 that one functional specification will cover both ITC2 and ITC3, to be delivered by December’25. o Decision: Approved | [9 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-21 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
|  | INT-CR1385 | Cancelled |  | SCP | R3.X (Post-R3) | Medium | 07. FTS IF | 7.12 FTS IF - IF R3 FE Supply Planning & Adv Packaging |  | 07. FTS IF 08. FTS IP 10. Analytics | anil.sankarapillai@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | IAO00195 | New Design Change | NA | NA | [5 empty] | Approved: Model Memory as a Constrained Material for Back side Metallzation (BSM) | As per initial design memory supply was considered as unconstraint. However, the memory going through the Back side Metallization is constraint by resource capacity This change will include getting PRF-RTF interaction with IP and other external customers. Needs to validate the overall BOM structure and resource modeling for it include coupon die supply chain and BSM related constraint Due to common capacity at BSM, the overall demand prioritization logic to be finalized. Update Solution design documents on the IF IT side.. | The resource used for Backside metallization is shared for both memory and other FG and is a constraint resource. Hence it is critical to model the memory related products to get the effective resource availability and utilization. Since IF is providing service for the memory products, these should be available in CDP, and we need to have a PRF and RTF process associated with it | Initiated solutioning with all potentially impacted teams after which the schedule will be confirmed. Current approved CR's for IF/SP run beyond ITC1, so this will be queued up after those beyond ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4CB90574-FBF8-4CCE-BC7E-981D17D6B3C0%7D&file=Change%20ID_Memory%20as%20a%20Constrained%20Material.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as it is duplicated of CR1396 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1386 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | kimberly.moore@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Configure and activate new TM integration for Scrap to vendor in order to print Commercial Invoice and Pack list. Need to configure below: 1. FU type 2. FO type 3. Optimizer based planning and consolidation 4. Carrier selection/Tendering/Charge calculation/Settlement/Execution --.Out of scope | Configure and activate new TM integration for Scrap to vendor in order to print Commercial Invoice and Pack list. Need to configure below: 1. FU type 2. FO type 3. Optimizer based planning and consolidation 4. Carrier selection/Tendering/Charge calculation/Settlement/Execution --.Out of scope | A dummy freight order is required to print CI and PL. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB2981D28-0D18-4105-9064-9A6CDE76C180%7D&file=INT-CR1386_Returns-%20Scrap%20to%20Vendor.pptx&action=edit&mobileredirect=true | Design / Build Gap | 3. Configuration Change | R-220-020, R-220-030 |  |  |  | 0 | [7 empty] | 25 | [5 empty] | 0 | 25 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2026-01-23 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | - It is the functional team that is doing this configuration work - It is ITC2 because of capacity constraints. | [9 empty] | Other | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-22 | 0 | < 15 Days | adshinde@deloitte.ca |  | No | CR Complete | No Objects |  | Complete | Yes
| N/A | INT-CR1387 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Descope and change release of edFIT -DATC1551 and descope of DATE1611_IP and DATI1612_IP(2A1) | Descope and change release of edFIT -DATC1551 | edFIT has been planned for release R4 |  | Yes |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 10, 2025 | 2025-10-22 | 168 | > 30 Days | shrutisingh7@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1388 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | graeme.johnson@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | Changes to label under LOGF1056- Print Return Label (FTS IF EWM). | NA | NA | NA |  |  |  |  | WIINGS | Changes to label of LOGF1056- Print Return Label (FTS IF EWM). | Changes to label of LOGF1056- Print Return Label (FTS IF EWM). | New field of "Description" = Warehouse No to be added within the label | CR might be tested after ITC1 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD3ACE50F-98F8-4C50-AC01-4807F3946FA4%7D&file=INT-XXXX%20-%20FTS%20EWM%20Returns%20Label%20CR%20WW43%20Rev%200.pptx&wdLOR=c2BEBEF37-68C6-4F86-A269-4C1D24A4A99B&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | 44 | 4000 | [6 empty] | 44 |  |  |  |  | 0 | 44 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF1056 | 1 | LOGF1056 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-02-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o We need to add a field to a return label. Business is collecting parts that can go back to multiple warehouses, and this field will help the warehouse SME do that work.  Know the destination and know how to map it, and the return label has room for the information | [9 empty] | Build | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1390 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | [15 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-23 | 0 | < 15 Days | pramokulkarni@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1389 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-23 | 0 | < 15 Days | pramokulkarni@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1391 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Pramod Kulkarni | [11 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Pramod Kulkarni that it can be cancelled as the technical effort is less than 40 hours |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-23 | 0 | < 15 Days | pramokulkarni@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1392 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 02. E2E Process Integration 06. PTP 07. FTS IF | eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | IMO Straddle Design | NA | No | NA | [5 empty] | IMO Straddle Design | IMO Straddle Design | Straddle. IMO sending Plant (Oregon) is in R3 and Receiving Plant (Ireland) not | There will be no impact to ITC1 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/INT-CR0xxx_E2E_IMO_Straddle.pptx?d=w1a06c2240b114bf9928167d7af0751d2&csf=1&web=1&e=XjuNA2 | New Requirement / Scope | 1. Process Scope / Design Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-23 | o This CR is low effort because it is just documentation of the E2E flow.  GFM and Sri are aligned. o NBS is not impacted. The key changes are part of the interface. | [9 empty] | Design | Tower | 2025-10-23 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1393 | Cancelled |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.1 FTS IF - ALL |  | 02. E2E Process Integration 06. PTP 07. FTS IF | eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | IMO Straddle | NA | NA | NA | [5 empty] | IMO Straddle | IMO Straddle Design | IMO Manufacturing Plant (Oregon) will be in R3 whereas the Ireland receiving Plant will be post R3. | No , E2E flows required. | No | Core |  | https://app.smartsheet.com/b/form/13ea7582a9594d4dadf0c6cf67d29e93 |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This is a duplicate of CR1392 | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1395 | Approved | Presenter: Tse Pei Tan, Arnie Frilles | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 10. Analytics | Naman Parti | [11 empty] | Implement New Wafer True Up Yield Report and Descope of OTCE1249 | Descoping of Object OTCE1249:​ Following the latest alignment with the Intel IF and IP teams, the original assumptions underlying the functional requirements for yield reconciliation are no longer applicable. Consequently, we propose descoping the OTCE1249 enhancement, despite significant progress on FSD, build, and FUT. The relevant BI1 system code will be commented out accordingly.​ New Scope Addition:​ A new ECA report for manual yield reconciliation calculations is being introduced. This report aims to handle calculation for yield reconciliation process to improve both accuracy and operational efficiency. Business stakeholders will provide these requirements in a future communication as part of requirement gathering. | The rationale for this change is to realign build scope with updated business priorities and assumptions on the yield reconciliation process. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B25CAC48D-7205-4B9B-A346-7B1E02666FD5%7D&file=INT-Build-CR0-Descope%20of%20OTCE1249%20and%20Implement%20Automated%20Yield%20Reconciliation%20Report.pptx&wdLOR=cBE65BED1-AB0A-420F-9A1E-C7179B60B801&action=edit&mobileredirect=true | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  |  | High | 0 |  |  | 18 | [5 empty] | 130 | 40 |  |  |  | 0 | 170 | N/A | Yes | ECA | 2 | OTCFR106, ECAOTCIFR6865 |  |  | 0 | OTCFR106 | 1 | ECAOTCIFR6865 | 1 | 2 |  | 0 |  | 0 | 0 | ECAFTSIFV6405 | 1 |  | 0 | ECAFTSIFV6405 | 1 |  | 0 | OTCE1249 |  |  | 1 | 04. Tower/Horizontal Approved (end status) |  |  | 2025-10-30 | - Automated design didn’t work, so we will need a new ECA report to perform yield recon - This will be manually tested in ITC1 - No tradeoffs or impacts | [9 empty] | Other | Not Assigned |  | Not Approved | 10, 2025 | 10, 2025 | 2025-10-23 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1396 | Approved |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | karthic.v.thallikar@intel.com |  |  |  | SCP-CR.159 | [7 empty] | IF Memory – Model as a Constrained Material for BSM | As per initial design memory supply was considered as unconstraint. However, the memory going through the Back side Metallization is constraint by resource capacity​ This change will include getting PRF-RTF interaction with IP and other external customers.​ Needs to validate the overall BOM structure and resource modeling for it including coupon die supply chain and BSM related capacity constraints.​ Due to common capacity at BSM, the overall demand prioritization logic to be finalized.​ Update Solution design documents on the IF IT side.. | The resource used for Backside metallization is shared for both memory and other FG and is a constraint resource. Hence it is critical to model the memory related products to get the effective resource availability and utilization.​ Since IF is providing service for the memory products, these should be available in CDP, and we need to have a PRF and RTF process associated with it |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/Intel%20Foundry%20-%20SP-%20IT%20Documents/1.%20Program%20Management/Change%20Requests/Change%20ID_Memory%20as%20a%20Constrained%20Material.pptx?d=w9e8fc23b73904f278286e835aecc3752&csf=1&web=1&e=h3d4OI |  | 1a. Operations Design |  |  |  |  | 0 |  |  |  |  | 80 | 80 | 40 | [6 empty] | 200 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-11-13 |  |  |  | 2025-11-14 | • The CR is to incorporate backside metal constraints into memory processing, specifically for HBM. This involves updating the PRF RTF modeling to reflect capacity limitations due to backside metallization, which was previously modeled as unconstrained. The change is considered a minor extension of the existing design but requires adjustments in configuration and testing. • The memory design will now factor in backside metal capacity constraints within PRF RTF modeling, aligning with a prior agreement and IP’s approved portion of the change request. • Adjustments include feeding capacity data from systems, configuring the BOM structure, and ensuring the product BOM is modeled through the relevant line segment. Testing will confirm proper function with the new constraint. • The change does not affect the overall BOM but introduces ordering by pieces instead of wafers for certain processes, requiring configuration to handle this unit of measure difference. • Most application changes are estimated to take about one week, with user interface updates requiring two weeks. The BOM and MDG hierarchy need no additional effort. Testing and business process readiness are confirmed for upcoming intercept testing. • The new constraint will be applied starting with ITC 2 intercept, while ITC 1 will continue to model backside metal capacity as unconstrained. • Participants discussed risks of modeling many constraints, which could limit revenue by restricting orders and missing opportunities to push capacity boundaries. A balance between constrained and unconstrained modeling is necessary. • The backside metal constraint for HBM will be a separate capacity corridor from fab capacity on the IP side, with ongoing communication to accompany capacity signals. • Decision: Approved with acknowledgment of the challenges in managing multiple short-term constraints in manufacturing. | [5 empty] | Other | CL/OSC | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-24 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1397 | Approved |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  |  | Naren Mangtani |  |  |  | SCP-CR.160 | [7 empty] | IF 0 FFS Production Scheduling | Based on architectural reviews, Production Scheduling system for backend stages (Assy/test/Finish) and WLA changed to FFS and APPS respectively and bring some incremental requirements to PDH. | Strategic architectural decision by the TD and SMDS leadership to switch from FSCO to FFS and APPS as the scheduling systems for BE and WLA. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B10DA49BB-011F-4FA2-8344-A09C1AA879E1%7D&file=CR1397_FFS%20and%20APPS%20Prod%20Scheduling%20for%20IF%20SP-BE%20and%20WLA.pptx&wdLOR=c58E01B6C-66EE-46D3-80A1-982F94B1F118&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0247, SCPIFSPPDH0249, SCPIFSPPDH0250, SCPIFSPPDH0246, SCPIFSPPDH0190, SCPIFSPPDH0251, SCPIFSPPDH0257, SCPIFSPPDH0268 | 8 | 8 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-04 | - None of the objects being pushed out will impact ERP. It will impact MaPPS or Blue Yonder. - AR: Work with FTS IF to ensure that there is no ERP impact - @Vajjala, Satyadeep @Heiney, John P - AR: Add in the new build dates for all impacted objects - @Mangtani, Naren | [9 empty] | Other | Tower | 2025-12-04 | 12, 2025 | 12, 2025 | 10, 2025 | 2025-10-24 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1399 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-24 | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1400 | Cancelled |  | ERP | [22 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-24 | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1398 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Vivek Yadav | [11 empty] | New custom API needed to process GET and DELETE function for Document Info Record Object Link where boundary app EMS and CWB can perform GET and DELETE in S4 and Vice Versa. | As standard DMS API is not have functionality to GET and DELETE Object link in Document Info Record which is also confirmed by SAP by OSS 1152384/2025 also provided 2 BAPI which can be used to achieve required functionality . As business requirement is to perform GET and DELETE function for DIR document. | As discussed with SAP on OSS 1152384/2025 on Standard API is not having functionality to perform GET and DELETE document info record Object link via API_CV_ATTACHMENT_SRV and API_DMS_PROCES_SRV. As SAP has provided solution to use BAPI_DOCUMENT_GETOBJECTLINKS to perform GET function and BAPI_DOCUMENT_CHANGE2 for delete object Link. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR1398_PTP_DMS_Object_Link.pptx?d=w98e3bd6c8fc74f129dd0d1c407fffe00&csf=1&web=1&e=nBfAsm |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | PTPI1689 | 3147 | PTPI1689 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - SAP said that they don’t have this functionality - CWB – Commercial workbench; this is the tool that is used for sourcing - Cannot link or delete documents in a standard API | [9 empty] | Other | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-24 | 0 | < 15 Days | vivekyadav3@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1401 | Approved | Presenter: Neetu | ERP | R3 (Release 3) | High | 07. FTS IF | 7.1 FTS IF - ALL | Yes | 07. FTS IF | rodolfo.alarcon@intel.com | Inventory/Logistics/FTS — Stef Maxey |  | 00203 -Securing FOL WH Physical Space | [8 empty] | Securing FOL WH Physical Space | Design to have FOL WH Space aligned. Check if CR is required by W44'2, including straddle. Physical Space requirement by site per roll out strategy by Dec, securing physical space per site roll-out strategy (R3/R4/R5) |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA1B0F984-851F-4206-8662-00E361D9E204%7D&file=INT-CR1401%20FOL%20Storage%20Capacity%20by%20MFG%20stage%20by%20Site.pptx&wdLOR=c46AED731-D94C-4F2A-ABB6-1BF207F4D792&action=edit&mobileredirect=true | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  |  | 0 | [7 empty] | 28 | 107 |  |  |  |  | 0 | 135 | Tech - S/4 | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0677, FTSE0507, LOGI0667 | 3 | FTSI0677, FTSE0507, LOGI0667 | 3 |  | 0 |  | 0 | N/A |  | 2026-03-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - This will allow Production schedule to steer WIP to warehouse storage locations - This is not how wafer die material moves today - All stakeholders are involved - Option 1 is the long-term solution - Team needs another couple of weeks to close out decisions - We can test what we have configured for ITC1; STR data will not be available until ITC2. - Strong partnership needed from SCP - AR: Capture the testing impact within deck - AR: Include PDH configuration work that is required |  |  | 2025-10-30 | [6 empty] | Design | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-25 | 0 | < 15 Days | nramireddi@deloitte.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1402 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Mubashir Ghazi | Data & Analytics - Rebecca Verette | [10 empty] | Material Master data authorization segregation between IP and IF in MDG | Material master display access need to be restricted between IP and IF |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1402.pptx?d=w40cc4b05da264eb39e47a6f95e7897f0&csf=1&web=1&e=Ed3EiJ | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-27 | 163 | > 30 Days | mghazi@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1403 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | SIMS Straddle Commerical Invoice | To support SIMS straddle process, changes to the existing Commercial Invoice generation logic require amendment. | SIMS shipments from Jabil (supplier) require creating an Intel Foundry Commercial invoice to swap the Supplier commercial invoice (CI) and packing list (PL) to perform the Import Declaration with the ultimate transaction value (selling price from Foundry vs Jabil price) |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_SIMS%20Straddle%20Commerical%20Invoice%E2%80%8B.pptx?d=w9da2736f5348486b81ae855a668ff97b&csf=1&web=1&e=kDVggL |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 50 | [5 empty] | 63 |  |  |  |  | 0 | 63 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0342_IF​, LOGE0341_IF​, LOGF0345_IF​ | 3 | LOGF0342_IF​, LOGE0341_IF​, LOGF0345_IF​ | 3 |  | 0 |  | 0 | N/A |  | 2026-03-16 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - SIMS is straddling through R4, when it is going live. - Only S4 impact | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1404 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | CR-817 | [6 empty] | Tariff | Tariff and Trade Impacts ¦ Ship/iBox Labels | Trade requirement received to ensure Shipping Label(s) display multiple Co"X" with semicolon when multiple entries are present. | Tariff and trade requirement changes captured under CR-817 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Display%20Multiple%20CoX_Ship%20Label.pptx?d=wc09f6e8998574f22abe739014e8f0632&csf=1&web=1&e=7cpYi1 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-27 | 163 | > 30 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1405 | Cancelled |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | [8 empty] | Tariff | Display Multiple CoX on iBox Labels | Trade requirement received to ensure Product Label(s) on SST products display Country of Fabrication (CoF). | Tariff and trade requirement changes captured under CR-817 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Display%20Multiple%20CoX_iBox%20Label.pptx?d=we56611e89fac4be8ae7978989072751b&csf=1&web=1&e=Gtz0Ix |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Imme to be cancelled as this was consolidated with CR1404 | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1406 | Cancelled |  | ERP | R2 Hypercare | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | CR-817 | [6 empty] | Tariff | Display Multiple CoX on Export Documents | Trade requirement received to ensure multiple Co"X" are displayed on the Export Documents when multiple entries are present on a Delivery Note | Tariff and trade requirement changes captured under CR-817 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Display%20Multiple%20CoX_iBox%20Label%20-%20Copy.pptx?d=wa59dc76c4c3d4521840f1468973aa0f1&csf=1&web=1&e=SI0tng |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Being tracked in separate Hypercare log | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1407 | Approved |  | SCP | R3 (Release 3) R3.X (Post-R3) R4 (Release 4) | High | 07. FTS IF | 7.14 FTS IF - New Product Supply Planning Enablement |  | 07. FTS IF | sunil.k.parida@intel.com | E2E/Architecture — Satya Vajjala | FTS IF - Haritha Komma | 0119 | NA | NA | NA | [5 empty] | Revenue Engineering Excel to PDH data load as Straddle prior to SAP IBP | Rev Eng planning straddle architecture definition to handle IF & IFS Revenue Eng for R3-R5 | R3 design- IF does not have any Planning tool hence Business user will prepared the planned order schedule ,Transportation schedule,MO/PO output schedule in a template ,then upload into the IF PDH..IF PDH will make sure to send the appropriate eng master data and the schedule to send it to production scheduling like FSCO,APPS& FFS | TBD, under assessment | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR1407%20Eng%20planning%20starddle%20CR_.pptx?d=wc50f71e828e84fb99e505e8054672d45&csf=1&web=1&e=hHzAw9 |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 |  |  | 50000 |  | 360 | [8 empty] | 360 | 0 | N/A | Yes | SCP | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0259 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - Will create engineering product and sales order and then indicate what lot types are in there. - This has been reviewed with all stakeholders. - This is for ITC3. If we want to pull in, then we will need to add more resources for 1 quarter (Q1). - AR: Add in that the $50K is required for Q1 2026 - Commercial impact: $50K |  |  | 2025-10-31 | • Discussed the manual process planned for revenue engineering planning at the Intel Foundry site due to the absence of a planning tool in ITC1 and ITC2, with SAP IBP tentatively expected in ITC3. • Business users will manually prepare planned order schedules to be uploaded into PDH, which will send data to production scheduling and material planning systems. • The manual process requires about nine weeks of PDH effort, starting in WW12 and ending in WW21 (ITC3). • The team discussed the need for additional budget (50K) and developers to pull this work into ITC2. • Options include manual data uploads versus automation, with the manual upload being the current change request. • The end-state design aims to move revenue engineering capabilities into Blue Yonder by R5. • The manual process is considered an interim step to maintain production scheduling capabilities, as production scheduling requires integrated engineering and production sales orders to function correctly. • Failure to implement this could cause significant production scheduling issues. • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No | Yes
|  | INT-CR1408 | Cancelled |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | scomcpha1@publicisgroupe.net | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | 00206 - S&OP BY IBP scenario capability | N/A | N/A | N/A | [5 empty] | Additional “What If” Functionality for S&OP | Enhance the functionality in BY-IBP for S&OP and support additional “What If” scenario analysis and reviews​ | *cancel, duplicate; Current POR for BY-IBP for S&OP is limited functionality with limited scenarios per run and manage/analyze multiple scenarios to baseline, ability to manage Demand Aggregation/Disaggregation, and export POR and Capacity Corridors to source systems (BY-CDP, BY-ESP) and generate S&OP Report​ | No Impact | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CRxxxx%20-%20Additional%20%E2%80%9CWhat%20If%E2%80%9D%20Functionality%20for%20S%26OP%E2%80%8B.pptx?d=w4bcec87e614345fe97407d40fbb6c2c5&csf=1&web=1&e=MM4cmV |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1409 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 10. Analytics 17. B-App | leena.saxena@intel.com | BApps — Kelly Gerber | FPR - Aubrey Hinderlider | Annual Plan (Revenue/Target/remix) to support Regional SMG process and BU's | New business process to support Regional SMG users to submit Annual Plan Target | x | x |  |  | 20290 | EBP/IBP - Revenue Forecast |  | Annual Plan Target to support Regional SMG process | Build a template to support Annual revenue/targets and remix. The data needs to be saved by version and follow enterprise master data. This data will be used to track Annual product and margin targets for top 18 accounts | Intel’s Sales Leader requested to track Annual product and margin targets for top 18 accounts, BU amd Regions. Enabling enterprise capture of Annual targets is intended to drive systematized accountability and ensure focus on a. Ramp of key product families at scale, minimizing ramping product cost where possible b. Limit discounting of products to preserve product margins, i.e. ASP maximization c. Improve seller acumen on PM, including levers of influence | This is a new scope. We will start the build in Jan. We will complete the build and functional testing before ITC2 | Yes | Core | AR: - AR: Add in documentation on the IBP and Profisee plan (FS/Development) - Milind - AR: Send email to Uzma and Rebecca (CC Anna) for offline approval - Milind | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B05E91F99-722C-4448-A194-13576DE1AEDC%7D&file=Change%20ID_Tower_CR%20Deck_template_annual_plan.pptx&wdLOR=c55FA73A5-DFD4-49BD-8E7C-1DDD5E661530&action=edit&mobileredirect=true |  | 1b. Solution Design |  | No |  | High | 0 | [9 empty] | 480 |  |  | 480 | 0 | 480 | N/A | Yes | ECA | 1 | ECAFPRV6887 |  |  | 0 |  | 0 | ECAFPRV6887 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-11-06 |  |  |  | 2025-11-06 | Per Stacee Mattrazzo, this CR was approved in offline reporting CR Meeting on 11/6 | [5 empty] | Other | CL/OSC | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
|  | INT-CR1410 | Rejected |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 10. Analytics 17. B-App | leena.saxena@intel.com | BApps — Kelly Gerber | FPR - Aubrey Hinderlider | SAC IP Gross Margin Model | x | None | x | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No | Core | Millind asked to work this offline | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B73E76E7D-8CC2-42A6-B5C8-048757F87DBA%7D&file=Change%20ID_Tower_CR%20Deck_template_inventory_model_sellable_supply_GM_model.pptx&wdLOR=c12782AE7-92AC-4F42-8326-865DBC2F9447&action=edit&mobileredirect=true |  | 0. Request for Investigation |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | Yes | No | 2025-10-30 | - This is related to inventory modeling, and 4 major changes are requested - These are new requirements that came in now from P&L team - It is currently a manual process - AR: List out what will be delivered in ITC2 - Leena - AR: List out team members required to do the work and include timeline of when the design requirements can be finalized - Leena | [9 empty] | Other | CL/OSC |  | Missing Review Date for Approval Level | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1412 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | Sherry Y Green |  |  | New storage type for neutral packaging | [7 empty] | WIINGS | New storage type for neutral packaging | This change initiative will neutral packaging for GXO WH. sites, ensuring optimization of storage for GXO-Huffman warehouse. New storage type for neutral packaging for GXO WH. | Huffman warehouse needs the flexibility to store Non-Copper and Copper products in the same storage type for optimized storage to leverage neutral packaging. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B71C3A4C8-D644-4E29-834B-6258A8CBE5C5%7D&file=INT-CR1412_New%20storage%20type%20with%20neutral%20packaging%20for%20GXO%20WH.pptx&wdLOR=c366B1317-DC0C-402D-A70B-A10A5D170A1A&action=edit&mobileredirect=true | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  |  | 0 | 60 | 4200 | [5 empty] | 60 | [5 empty] | 0 | 60 | Configuration | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  | 2025-12-12 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Commercial Impact: $4200 - This is needed now because there are Copper/Heavy Metal rules. Need to make sure that the copper is not sent to the wrong storage. - LTD has been reducing some of the restrictions to make use of the full warehouse. - This effort is for only 1 warehouse (Huffman), and this will be repeated for other warehouses | [9 empty] | Design | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | rshankarshastry@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1411 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Low | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 10. Analytics 17. B-App | leena.saxena@intel.com | BApps — Kelly Gerber | FPR - Aubrey Hinderlider | none | none | none | none |  |  | 20290 | EBP/IBP - Revenue Forecast |  | Update Planning Model- Forecast Measures; stitching of BU Fin POR Qty/Amt w Rev Net | Rev Net Qty/Amt (Revenue Actuals) and Revenue POR are finance owned ROO. It's needed as data source for upstream ingestion into Reporting. Data Calc/Stitch: Upon Ingestion, Rev Net Qty/Amt (Revenue Actuals) are then stitched to Revenue POR to show full Revenue forecast for that current year for Reporting. | Creation of a stitching of BU Fin POR Qty/Amt to Net Rev Amt and Qty | none | Yes | Non-Core | AR: - AR: Get Chad’s team involved for PDH IP effort analysis | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4C78E9ED-6FB9-4148-BC30-3AB5946DDC7B%7D&file=Change%20ID_Tower_CR%20Deck_template_stitching%20of%20BU%20Fin%20POR%20Qty%20and%20Amt%20w%20Rev%20Net.pptx&wdLOR=c152C7193-6C86-47FA-B2D3-7CEEB8639D4E&action=edit&mobileredirect=true | New Requirement / Scope | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [9 empty] | 240 |  |  | 0 | 0 | 240 | N/A | Yes | ECA | 1 | ECAFPRV6888 |  |  | 0 |  | 0 | ECAFPRV6888 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - AR: Get Chad’s team involved for PDH IP effort analysis |  |  | 2025-11-06 | Per Stacee Mattrazzo, this CR was approved in offline reporting CR Meeting on 11/6 | [5 empty] | Design | CL/OSC | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1413 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | vijasharma@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor | PTPE0727_IP and PTPE0727_IF Source List Mass Upload Utility Changes Required | During the FUT of the object the issue were identified that the Function Module used in the custom object has certain limitations to handle the change scenario. Therefore it is aligned to only keep the CREATE operation for this object. | N/A | N/A | [5 empty] | Source List mass upload utility change required in the build logic - Include additional validations and remove the UPDATE operation | Issue Details - Currently we are using a custom function module to create and modify source list entries. However, this approach requires implementation of all standard SAP validations from scratch, as the selected function module does not natively provide these checks—unlike typical SAP mass upload utilities. Change description - Develop mass creation for Source List records via Excel upload. Handle changes manually. Core creation logic is already in place; only few additional validations need to be added to complete FUT. | This approach requires implementation of all standard SAP validations from scratch, as the selected function module does not natively provide these checks—unlike typical SAP mass upload utilities. | No major impact on current go-live plans. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Change%20Request%20Decks/INT_CRXXX_Changes%20required%20to%20add%20validations%20and%20remove%20UPDATE%20operation%20for%20Source%20list%20mass%20upload%20utility.pptx?d=wba29b13dafea439e8589c00129a57677&csf=1&web=1&e=2fPPzZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 16 | [5 empty] | 120 |  |  |  |  | 0 | 120 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPE0727_IP, PTPE0727_IF | 2 | PTPE0727_IP, PTPE0727_IF | 2 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Data is entered into the Excel and then uploaded manually to create source lists - None of the function modules are working to validate the source list upload - Therefore, this request is for a programmatic way for validation - There is no impact to ITC1 in terms of loading (will be through BODS) - AR: Add in sentence that there will be no impact to cutover activities and will be manually done. The validations will be tested in ITC2 | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1414 | New |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | vijasharma@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor | N/A | N/A | N/A | N/A | [5 empty] | Layout changes required for Mass upload utility objects for PTP to have unique layout across all utility objects | 1. We need the layout changes required for all the PTP mass upload utilities regarding the “Test Mode” drop down. We need to revert to checkbox option for test mode instead of dropdown. We have total 6 mass uploads, making 12 RICEFW objects for IP and IF, below are the object details – Source list – PTPE0727_IP and PTPE0727_IF Quota Arrangement – PTPE0745_IP and PTPE0745_IF Purchase Order – PTPE0200_IP and PTPE0200_IF Purchase Requisition – PTPE0202_IP and PTPE0202_IF Info Records – PTPE0744_IP and PTPE0744_IF Contracts – PTPE0743_IP and PTPE0743_IF 2. The Purchase order mass utility output fields also needs to be aligned with other mass upload utility objects. | Currently the Test Mode button is made as Drop Down option. If user does not select anything, then the record is loaded with blank value which is incorrect. This checkbox was changed to dropdown earlier to support multiple selection in the initial screen. Therefore, this needs to be reverted back to checkbox option only. | The Functionality is working, but the layout changes might not be ready by ITC1 if the CR is not delivered and tested earlier. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Change%20Request%20Decks/INT_CRXXX_Layout%20Changes%20Required%20for%20PTP%20Mass%20Upload%20Utility%20Objects.pptx?d=wf77df38429104a0c867548d32c40d667&csf=1&web=1&e=cimj5J |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 162 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1415 | New |  | ERP | R3 (Release 3) | Very High | 10. Analytics | 10.1 Analytics - ALL |  | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP | thienne.johnson@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | Technical challenge in ILM IP & IF data segregation | ILM needs to build ~6 months of data with IP/IF segregation in order to segregate historical data. | N/A | N/A | [5 empty] | Logistics CPLG Dashboard related analytics objects will miss ITC1/2/3 due to source data dependency on ILM | Currently ILM team doesn’t have a way to segregate IP and IF data. They are deploying a change in Production to start identifying IP and IF data. They need ~6 months of data with this change to segregate historical data, so ILM data won’t be landed in ECA until ~Jun’26. | Non availability of source data | Below objects will miss ITC1, ITC2 & ITC3 which will provide very less opportunity for thorough testing: 1. ECAFTSIPV4807 (ECA View) - CPLG Quality Dashboard - IP 2. ECAFTSIFV4806 (ECA View) - CPLG Quality Dashboard – IF 3. ECAFTSIF5075 (3rd Party Report) - RPT#FTSIP147-CPLG Quality Dashboard - IF 4. ECAFTSIP5076 (3rd Party Report) - RPT#FTSIP147-CPLG Quality Dashboard - IP | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-AnalyticsILMExceptions.pptx?d=w3339a6bd043e4b139717e25e5283c5ee&csf=1&web=1&e=MXDDvj |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 162 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1416 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Print Separate CI for Brexit and Intercompany | Requirement is to have separate forms printed for Brexit and Inter Company scenarios along with End Customer Ci | A separate logic and form are required for Brexit /Intercompany shipments. For example, the price per unit and the total value of the shipment are not needed for a Brexit invoice, it will be blank. In case of Intercompany it should print Transfer price instead of End Customer Price. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20LE/INT-CR1416%20%E2%80%93%20OTC_LE%20Brexit%20%20InterCompany%20CI.pptx?d=w636a978de18d49d79253d9189dcfbe76&csf=1&web=1&e=H3QfRD |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 |  |  | 30 | [5 empty] | 36 |  |  |  |  | 0 | 36 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0345_IP​, LOGE0341_IP​ | 2 | LOGF0345_IP​, LOGE0341_IP​ | 2 |  | 0 |  | 0 |  |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Partial functionality will be tested in ITC1 - This is a corner case for testing | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | kpitroda@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1417 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | pvemuri@deloitte.com | PTP — Kenneth Salazar | PTP - Richard Taylor | Factory Spares Return for external and IMR repair and return to supplier for serialized materials and generic materials | N/A | N/A | N/A |  |  |  |  | WIINGS | Changes required in existing objects PTPE0961 to include serialization decision and copper repair loop | With PTPE0961 custom program we are creating return documents for supplier repair and quench reasons from PM work order. There are changes required in this object because of recent finalization on - 1. Using serial numbers for spare parts returns to include serial numbers on PR and PO documents 2. Cu and Non-Cu repair loop process 3. Capture PM order reference in custom text fields in PR and PO documents The details of the changes are captured in the PPT document. | The requested enhancements arise from functional gaps and business alignment post-initial testing. Capturing full traceability of serial numbers and correct PM references is crucial | No major impact on current go-live plans. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Change%20Request%20Decks/INT_CR1413_Changes%20for%20PTPE0961%20and%20PTPE0962%20objects.pptx?d=wbee2d1b3ab1f4779a9c7642fb4b1a842&csf=1&web=1&e=lnRtOx |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | 16 | 5300 | [6 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPE0961 | 1 | PTPE0961 | 1 |  | 0 |  | 0 | N/A |  | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Commercial Impact: $5.3K - Team would have found this in ITC1 - Serial numbers will be updated manually. It will be a part of the purchase order. - AR: Add in what will be done in ITC1 manually | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC2 | INT-CR1419 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 11. Technology 17. B-App | Imran Athar | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | N/A | N/A | N/A | N/A |  |  | 12842 | OpenText |  | ASN 3B2 interface for IF owned EMIB shipments | Interface to send Advanced Shipment Notification to substrate suppliers for EMIB shipments owned by Intel Foundry | Intel is manufacturing and bailing EMIB materials to substrate suppliers to incorporate into advanced substrates. Substrate supplier need to receive advanced shipping notification (3B2 ) via B2B channel to enable physical receipt of EMIB shipments and track inventory accurately For IP owned EMIB materials, advanced shipment notification will be generated from sales order placed by IP. For Anafi & other IFS customers who are NOT providing substrates as bailed materials, IF needs to manage EMIB shipment and have visibility of EMIB inventory at substrate supplier site Shipment of EMIB to substrate supplier will be managed via stock transfer orders (STO) in S4 IF. Upon issue of outbound shipment from IF STO, S4 needs to trigger advanced shipment notification with details of EMIB lots to Open Text which will send ASN to substrate supplier in required B2B format | Tentatively set for ITC2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR1419%20-%20ASN%203B2%20Interface%20for%20IF%20owned%20EMIB%20shipments.pptx |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 30 | [5 empty] | 90 |  |  |  |  | 0 | 90 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI1040, LOGE1450 | 2 | LOGI1040, LOGE1450 | 2 |  | 0 |  | 0 |  |  | 2026-05-15 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-11-06 |  |  |  | 2025-11-07 | [6 empty] | Build | CL/OSC | 2025-11-07 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | rodolfo.alarcon@intel.com |  | No | Dev Not Started | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1420 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | shashank.kolhe@intel.com | FTS (SCP IP & OP) — Chad Smith | OTC IP - Teresa McNicol/Jon Benoist | na | na | na | na | [5 empty] | IP Demand Objects Pushed beyond Build Milestone | IP Demand Objects Pushed beyond Build Milestone - see form | see form | see form | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1420%20-%20IP%20Demand%20Objects%20pushed%20beyond%20WW2.pptx?d=wd11fa962c1ef43b78c92efb70fc97ebe&csf=1&web=1&e=63RhBg |  | 13. Other Milestone Adjustments |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPDPPDH0047 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-13 | - This is approved from Kumar Vytla, Chad Smith, and Roman - It is to push out the development of 5 objects. There is no other cost. | [9 empty] | Other | Tower | 2025-11-13 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1421 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns | Yes | 05. OTC IP | Pramod Kalli Srinivas | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Payload Split in Outbound Interface from S4 to SFDC | Payload Split in Outbound Interface from S4 to SFDC | While sending the data to SFDC from S4 if data file is more than 10 MB then middleware cannot receive that file. In this case we need to split the payload. When splitting the payload each RMA will be sent separately in different payloads and number of lines which will be on payload should be configurable along with Split ID. Current API is synchronous API and when we go with the payload split functionality then API will be Asynchronous and to receive the response from SFDC we will require new API because based on the response we are updating custom table in S4 system. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1421%20-%20Payload%20Split%20in%20Outbound%20Interface%20from%20S4%20to%20SFDC..pptx?d=w39a4abf562244a2cb90beecef589e031&csf=1&web=1&e=saJUAb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 12 | [5 empty] | 45 |  |  |  |  | 0 | 45 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0291 | 1 | OTCI0291 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-08 | • This is a change to the interface OTCI0291 as payloads over 10mb cannot be sent by the middleware. Therefore, payloads will be split. • There will be a line-level trigger to make sure that each split is less than 10mb. | [9 empty] | Build | Tower | 2026-01-08 | 01, 2026 | 01, 2026 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1423 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1424 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1425 | Cancelled | [22 empty] | For new API to receive the response from SFDC we will be required new RICEFW. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-28 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1422 | Approved |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF | eric.yamada@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | NA | NA | NA | NA | [5 empty] | Approved: Align SI POR Sort Schedule to CMAD Orders | Change the definition of the SI POR schedule for the Sort Stage to be equal to CMAD Orders + RTF instead of the current design of Sched Receipts + Planned Orders | The current SI POR reflects the latest projections from our Production Scheduling applications rather than the current order commits within the Fab WIP horizon. Fab Planning and Manufacturing teams do not want the projected outs to be automatically passed to OneMPS for Back-End Planning and want to hold to the commit schedules even if the projections are showing potential delays or pull-ins. | None | No | Core |  | https://intel-my.sharepoint.com/:p:/p/john_p_heiney/EfGwl7kzXMhFiIX1W5qdf30BK0LfxZY9K1wBKeu1xXxz8g?e=NCuJcr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-04 | Confirmed by Rocco to be approved and implemented | [9 empty] | Build | Tower | 2025-11-04 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1426 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP |  | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | Spit program 1 into 2 to allow system to generate table entries as per the rules defiled in FS. ( Called out during TUT) Filter Criteria for Program 2. Filter Criteria for Program 3 ( Called out during TUT) Table maintenance active for all 5 tables based on authorization. | Spit program 1 into 2 to allow system to generate table entries as per the rules defiled in FS. ( Called out during TUT) Filter Criteria for Program 2. Filter Criteria for Program 3 ( Called out during TUT) Table maintenance active for all 5 tables based on authorization. | Spit program 1 into 2 to allow system to generate table entries as per the rules defiled in FS. ( Called out during TUT) Filter Criteria for Program 2. Filter Criteria for Program 3 ( Called out during TUT) Table maintenance active for all 5 tables based on authorization. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 161 | > 30 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1427 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP 10. Analytics 13. Security | scomcpha1@publicisgroupe.net | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams | NA | NA | NA | NA | [5 empty] | Additional Functionality for S&OP | Enhance the functionality in BY-IBP for S&OP and support additional “What If” scenario analysis and reviews | *approved by Kumar; Current POR for BY-IBP for S&OP is limited functionality with limited scenarios per run and manage/analyze multiple scenarios to baseline, ability to manage Demand Aggregation/Disaggregation, and export POR and Capacity Corridors to source systems (BY-CDP, BY-ESP) and generate S&OP Report | None | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR1427-Additional_Functionality_for_SnOP.pptx?d=wd7498530c34a4285b0b6ffea3a11c23d&csf=1&web=1&e=rZDYPA |  | 1b. Solution Design |  |  | High |  | 3 |  |  | 360 |  | 400 | [8 empty] | 400 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPSPPDH0165 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-18 | • Kumar Vytla approved offline |  |  | 2026-02-06 | Approved to be exception | [5 empty] | Other | Tower | 2025-12-18 | 12, 2025 | 12, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | jon.benoist@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1428 | Approved |  | SCP | R3 (Release 3) | High | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration |  | 02. E2E Process Integration 07. FTS IF 17. B-App | Eugene.celis@intel.com | E2E/Architecture — Satya Vajjala | FTS IF - Haritha Komma | Shipment Transformation Straddle WTF Open | CR1180 | NA | NA |  |  | 32329 | #NO MATCH |  | Shipping Straddle WTF Open for Non-S/4 to S/4 Site | Build data feed from IF PDH to Xeus and batch jobs to update the C4, e-test, Sort destination in MES, to enable the sites not on S4 to ship using PROSPAL. This requires additional work on TD ATA, IF PDH. | FSCO, APPS and FFS are scheduling all sites in R3. However, manufacturing sites that are not being deployed to S4 in R3 won't be ready for this change as per the current roll out plan. During straddle, solution is needed for sites that are not on S4, to enable them execute production in alignment with the schedules from FSCO, APPS and FFFS. | Testing intercept will be Mid-ITC2 or ITC3, since TD can only start design in WW05 2026 and cannot commit to ITC2 at this time. They have estimated ~ 1 Quarter development to build the solution. Manual process is the risk mitigation alternative till the time TD ATA is ready with the solution. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRXXX%20-%20Shipping%20straddle%20Non%20S4%20to%20S4%20site.pptx?d=wddfcf61e15574c9993abd2c41884956f&csf=1&web=1&e=B2CkVy |  | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - This is a manual process and got push back to see what can be automated - Need help from Core Leadership to drive this commitment - TD design cannot start design until WW5 - AR: Add in the manual process – Bharath P - AR: Add in sentence that POR is manual process and there was pushback - AR: Add in sentence that data will be collected by Planning team and Eugene (FTS IF) |  |  | 2025-10-31 | • Explained a design gap regarding shipment scheduling for non-S4 to S4 sites. • The original straddle design required changes to TD systems to assign shipment destinations per lot, which TD would not support due to risks and scale. • The interim solution involves manual updating of attributes by MPC based on detailed scheduling reports, with TD proposing a smaller development effort to automate this process in work week five, estimated to take one quarter. • The manual process is the current (POR) until data justifies automation. Factory sign-off on the manual process is still pending, Paul Whitlock is helping with this. • PDH and ECA teams require approval for 8 and 4 weeks of work respectively, regardless of automation. PDH and ECA work must finish by ITC2. • The team agreed to collect data on the manual process’s impact before approving automation, with manual processing as POR for now . • Mike Lange emphasized that nothing should be pushed to ITC3; all work must fit into ITC2, and teams must find ways to deliver within this timeline. • Decision: Approved. | [5 empty] | Other | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1430 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1429 | Rejected |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.12 FPR - ALL |  | 03. FPR 10. Analytics 12. Infrastructure 17. B-App | chris.wilcox@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | Escalating issues with original design that will cause performance issues downstream | NA | NA | [5 empty] | ECA Mega Tables | Many of the developed ECA views are being created way too large. There are over 20 tables that the DARC team is consuming that have over 100 columns and a couple that have 400-500. The desire is to have optimal table structure and not large flat tables. | Large tables cause a variety of issues: performance, development, and governance. These large tables are not even yet populated with production data and there is a high suspicion that run times will be long and cause several time outs. Development is difficult as there are duplicate columns and missing items making location the right data extremely difficult. And governing large tables are tough as we cannot see who is consuming what data and therefore no idea of what is being consumed. | Redesigning table structure would R3 ITC1 at risk. There are downstream impacts to reporting and other systems that would need to be redirected once nee tables land. However this would have some efficiencies in our development. Also, there is still a lot of work to do with these tables as dozens of columns are missing thus leaving an opportunity to go back in and land these fields in ECA and land optimal table structure at the same time. | Yes | Core | Approved in core meeting, waiting for status change | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/CR_ECA%20Mega%20Tables.pptx?d=wec6f8704b97c4fdab38b0c89a4b7678a&csf=1&web=1&e=qkk5fE |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A | No | ECA | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 16. Cancelled by Requestor Tower | Yes | No | 2025-10-30 | - AR: Need timeline of when this will be closed & get effort estimate - AR: Log as design open |  |  | 2025-11-03 | • CR is for performance issues with ECA tables used by the FPR Dark team for Power BI reports. • Some ECA tables are extremely large (close to 500 tables), causing performance problems. • The DARC team may be using foundation data incorrectly. Analysis is needed to confirm correct views and suggest improvements. With an estimated effort of 2–3 days by ECA developers. • The consensus is this is not a formal CR; it’s a build/testing issue discovered during development. • Decision: Approved. Team is to proceed with analysis without tracking as a CR unless necessary in the future. |  |  |  |  | Flipped to cancelled as per Rebecca Verette, Vanessa Clark, and Sunil Narayanan that the work will not be tracked through CR. teams will work together to better understand design and use the data. Teams will make adjustments if needed. | Design | CL/OSC | 2025-11-03 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1433 | Approved |  | ERP | R3 (Release 3) | Very High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 17. B-App | Jose Vargas Lepiz | PTP — Kenneth Salazar | PTP - Richard Taylor | [6 empty] | 12208 | E2open |  | E2Open change for STO & PO Linkage capability shift from ITC1 to ITC2 | Multiple STOs linkage to single PO with partial receives capability not possible to deliver by E2O as agreed design. Change requires customization by E2O with impact to schedule | Multiple STOs linkage to single PO with partial receives was a confirmed capability with signed off design. E2O realized during Build/FUT it was not possible to address requirement via standard product design, this requiring product customization. This change is in process of being approved by E2O Leadership but requires longer product development times from E2O Product Team pushing committed timelines for ITC1 |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1433%20-E2Open%20design%20change%20for%20STO%20%26%20PO%20Linkage%20capability.pptx?d=wfd471b13d706401bb2d103f5e6f710f1&csf=1&web=1&e=U7aYXH | Design / Build Gap | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | PTPI0144 | 1 | PTPI0144 | 1 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - STO linkage capability in E2Open was not possible based on original assumptions during design - We need to change standard product design |  |  | 2025-10-31 | • Reviewed challenges with meeting ITC1 and ITC2 commitments related to E2Open, particularly concerning multiple STOs linked to one PO and build instruction models. • The team analyzed and reprioritized deliverables, splitting some functionalities between ITC1 and ITC2 and planning manual testing for certain boundary applications. • Concerns were raised about previous missed commitments and ensuring better resource allocation and micromanagement to avoid future delays. • The team emphasized tight control and weekly progress reporting with E2Open to mitigate risks . • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1434 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | GL balance Recon Report_R3_IF/IP/CFIN | 1. Require separate GL balance recon report to effectively tie out & identify the discrepancy in balances between IP/CFIN and IF/CFIN by GL activity and by period end balance – FI report | Users need reconciliation reports modified to incorporate additional filters, improve performance and usability, making them more efficient and user-friendly |  | Yes | Core | Reviewed on 11/14, waiting to be updated? | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR1434_%20New%20GL%20balance%20report.pptx?d=we2c6c17fb3954b3d9d4dd7d641df744b&csf=1&web=1&e=znbco7 |  | 2. New RICEFW / ECA / Build Object |  |  | High | 0 | 3 | 420 | 29400 | [11 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-14 | • The remaining CRs are for FPR reconciliation reports, which have evolved from earlier releases to accommodate more source systems and updated logic. The reports aim to verify the completeness and accuracy of transactions moving between source systems (AIA, IP, ECC) and the target system (CFIN), providing summary statistics and detailed unmatched item reports with key attributes for investigation. • There are five main reconciliation reports covering balance reports, trial balance updates using new mapping tables, and line item comparisons for financial and management accounting postings. These reports are complex and require significant development and testing effort, recognized as one of the longest and most resource-intensive tasks from previous releases. The team emphasized the need to start development early to allow for iterative logic refinement and testing, targeting ITC 3 for comprehensive testing with stable data. • The estimated cost for completing all five reconciliation reports is approximately $105K covering both Deloitte Analytics and SAP functional team efforts. The reports are highly complex and require close collaboration between analytics and tower teams. Budget constraints were acknowledged, but internal absorption was deemed challenging due to the complexity. The team plans to finalize the functional design specification by mid-December to allow sufficient development and testing time before ITC 3 begins around late April. • A key technical decision under consideration is moving away from Power BI as the interface for these reconciliation reports, as it has proven ineffective for the required audit and reconciliation activities. The team aims to finalize the front-end tool choice by EOW WW47 in consultation with Deloitte and internal analytics teams to streamline development and improve usability. • Manual workarounds are planned for ITC 1 and 2 phases, with formal reconciliation testing deferred to ITC 3 when the system stabilizes and data volumes are sufficient to reduce false positives. This approach is informed by lessons learned from previous releases where early testing generated many false unmatched items due to unstable data and incomplete logic. The current state compares S4 to S4 data, which should be less complex than earlier ECC to S4 comparisons. • The meeting concludes with confirmations on alignment between analytics and tower teams regarding timelines, budget, and technical approaches. It is noted that while many reporting tasks could be handled internally, the reconciliation reports’ complexity justifies external support. Other reporting efforts, such as the supply chain five-way reconciliation, are planned for internal delivery to manage costs effectively. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1435 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | GL Trial Balance report functionality and output display with new PC mapping table changes | 1. Ensure that the report is not using PBI but generates only excel based output 2. Use static table for P0, Fixed table for past periods and Variable table for current period 3. Ensure that report output has balances for both ECC and S4 eventhough it is not matched 4. Manually build the report initial period balance till Go-live period 5. Use the new PC mapping table to instead of cfin mapping table for PC | 1. The output has both summary and detailed view 2. The report runs only for S4 company codes 3. The report doesnt display the balances directly posted in S4 |  | Yes | Core | Reviewed on 11/14, waiting to be updated? | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR1435_Trial%20Balance%20update%20CR%20with%20new%20PC%20mapping%20table.pptx?d=w7a59eceb79d1498b9b7fbbcef848a24b&csf=1&web=1&e=c299bb |  | 2. New RICEFW / ECA / Build Object |  |  | Very High |  | 4 | 245 | 17150 | 70 | [6 empty] | 175 |  |  |  | 0 | 175 | N/A | Yes | ECA | 1 | FPRXR126 |  |  | 0 | FPRXR126 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-14 | • The remaining CRs are for FPR reconciliation reports, which have evolved from earlier releases to accommodate more source systems and updated logic. The reports aim to verify the completeness and accuracy of transactions moving between source systems (AIA, IP, ECC) and the target system (CFIN), providing summary statistics and detailed unmatched item reports with key attributes for investigation. • There are five main reconciliation reports covering balance reports, trial balance updates using new mapping tables, and line item comparisons for financial and management accounting postings. These reports are complex and require significant development and testing effort, recognized as one of the longest and most resource-intensive tasks from previous releases. The team emphasized the need to start development early to allow for iterative logic refinement and testing, targeting ITC 3 for comprehensive testing with stable data. • The estimated cost for completing all five reconciliation reports is approximately $105K covering both Deloitte Analytics and SAP functional team efforts. The reports are highly complex and require close collaboration between analytics and tower teams. Budget constraints were acknowledged, but internal absorption was deemed challenging due to the complexity. The team plans to finalize the functional design specification by mid-December to allow sufficient development and testing time before ITC 3 begins around late April. • A key technical decision under consideration is moving away from Power BI as the interface for these reconciliation reports, as it has proven ineffective for the required audit and reconciliation activities. The team aims to finalize the front-end tool choice by EOW WW47 in consultation with Deloitte and internal analytics teams to streamline development and improve usability. • Manual workarounds are planned for ITC 1 and 2 phases, with formal reconciliation testing deferred to ITC 3 when the system stabilizes and data volumes are sufficient to reduce false positives. This approach is informed by lessons learned from previous releases where early testing generated many false unmatched items due to unstable data and incomplete logic. The current state compares S4 to S4 data, which should be less complex than earlier ECC to S4 comparisons. • The meeting concludes with confirmations on alignment between analytics and tower teams regarding timelines, budget, and technical approaches. It is noted that while many reporting tasks could be handled internally, the reconciliation reports’ complexity justifies external support. Other reporting efforts, such as the supply chain five-way reconciliation, are planned for internal delivery to manage costs effectively. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1436 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | [10 empty] | Fine tune FICO recon report with new PC mapping table | Incorporate the new PC mapping table with valid from and valid to date instead of the standard CFIN mapping table for PC to generate the FI recon reports | The existing FI recon reports use the mapping table for GL and PC using CFIN mapping table. This does not have the time based valid from and valid to date . Therefore, when the report is run for the past data, the data is matched with current mapping table for PC and the results are mismatched. To overcome this short coming, a new custom table for PC with valid from and valid to is created. The report has to check the new table for PC instead of standard PC mapping table and check the records posting date within the valid to and valid from date to determine the mismatch records. This change is to be implemented for all the FI recon reports |  | Yes | Core | Reviewed on 11/14, waiting to be updated? | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR1436_%20Incorporate%20the%20new%20PC%20mapping%20table%20with%20valid%20from%20and%20valid%20to%20date%20instead%20of%20the%20standard%20CFIN%20mapping%20table%20for%20PC%20to%20generate%20the%20FI%20recon%20reports.pptx?d=wc98572ba23f042e9bb06a4c42f9c25e6&csf=1&web=1&e=rXiMlJ |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | 140 | 9800 | [11 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-14 | • The remaining CRs are for FPR reconciliation reports, which have evolved from earlier releases to accommodate more source systems and updated logic. The reports aim to verify the completeness and accuracy of transactions moving between source systems (AIA, IP, ECC) and the target system (CFIN), providing summary statistics and detailed unmatched item reports with key attributes for investigation. • There are five main reconciliation reports covering balance reports, trial balance updates using new mapping tables, and line item comparisons for financial and management accounting postings. These reports are complex and require significant development and testing effort, recognized as one of the longest and most resource-intensive tasks from previous releases. The team emphasized the need to start development early to allow for iterative logic refinement and testing, targeting ITC 3 for comprehensive testing with stable data. • The estimated cost for completing all five reconciliation reports is approximately $105K covering both Deloitte Analytics and SAP functional team efforts. The reports are highly complex and require close collaboration between analytics and tower teams. Budget constraints were acknowledged, but internal absorption was deemed challenging due to the complexity. The team plans to finalize the functional design specification by mid-December to allow sufficient development and testing time before ITC 3 begins around late April. • A key technical decision under consideration is moving away from Power BI as the interface for these reconciliation reports, as it has proven ineffective for the required audit and reconciliation activities. The team aims to finalize the front-end tool choice by EOW WW47 in consultation with Deloitte and internal analytics teams to streamline development and improve usability. • Manual workarounds are planned for ITC 1 and 2 phases, with formal reconciliation testing deferred to ITC 3 when the system stabilizes and data volumes are sufficient to reduce false positives. This approach is informed by lessons learned from previous releases where early testing generated many false unmatched items due to unstable data and incomplete logic. The current state compares S4 to S4 data, which should be less complex than earlier ECC to S4 comparisons. • The meeting concludes with confirmations on alignment between analytics and tower teams regarding timelines, budget, and technical approaches. It is noted that while many reporting tasks could be handled internally, the reconciliation reports’ complexity justifies external support. Other reporting efforts, such as the supply chain five-way reconciliation, are planned for internal delivery to manage costs effectively. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1438 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Change Request for Change Quantity Event for 7B1​ | Change Request for allowing the Production order confirmation qquantity adjustments in IP S4 based on IF 7B1 event​ | *canceled, not needed; IF OSAT will have quantity increase and decreases for reasons other than scrap. Unit level traceability (ULT) in the factory reconciles units between the lot and the MES system. If ULT finds discrepancies, lot quantities are adjusted in MES systems (+/-). This is common for DIE (pieces)​ IF ECA needs to have the ability to gather quantity increases/decreases and send “Change Quantity” message in 7B1​ IP SMH will receive quantity increases/decreases in 7B1 and need to send the same to IP SAP in order to keep quantities in synch between IF OSAT and IP SAP |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1438%20-%20Change%20Request%20for%20Change%20Quantity%20Event%20for%207B1.pptx?d=w13b8696a267349339a04b3db7c7e21bb&csf=1&web=1&e=YUh7dy |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1437 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | New ECA FI recon report between IP/CFIN and IF/CFIN | Create a new FI recon report for recon purpose between IP/CFIN and IF/CFIN like the recon report between ECC and S4 | The new FI recon reports between IP/CFIN and IF/CFIN should have all the functionalities like that of the existing recon report between ECC and S4 incorporating the new PC mapping table with valid to and valid from date |  | Yes | Core | Reviewed on 11/14, waiting to be updated? | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR1437_%20New%20FI%20Recon%20report%20for%20IP_S4%20and%20IF_S4.pptx?d=wfedff3048e2d48759f61e04244957b30&csf=1&web=1&e=c6vmp6 |  | 2. New RICEFW / ECA / Build Object |  |  | Very High |  | 4 | 350 | 24500 | 100 | [6 empty] | 250 |  |  |  | 0 | 250 | N/A | Yes | ECA | 1 | FPRXR127 |  |  | 0 | FPRXR127 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-14 | • The remaining CRs are for FPR reconciliation reports, which have evolved from earlier releases to accommodate more source systems and updated logic. The reports aim to verify the completeness and accuracy of transactions moving between source systems (AIA, IP, ECC) and the target system (CFIN), providing summary statistics and detailed unmatched item reports with key attributes for investigation. • There are five main reconciliation reports covering balance reports, trial balance updates using new mapping tables, and line item comparisons for financial and management accounting postings. These reports are complex and require significant development and testing effort, recognized as one of the longest and most resource-intensive tasks from previous releases. The team emphasized the need to start development early to allow for iterative logic refinement and testing, targeting ITC 3 for comprehensive testing with stable data. • The estimated cost for completing all five reconciliation reports is approximately $105K covering both Deloitte Analytics and SAP functional team efforts. The reports are highly complex and require close collaboration between analytics and tower teams. Budget constraints were acknowledged, but internal absorption was deemed challenging due to the complexity. The team plans to finalize the functional design specification by mid-December to allow sufficient development and testing time before ITC 3 begins around late April. • A key technical decision under consideration is moving away from Power BI as the interface for these reconciliation reports, as it has proven ineffective for the required audit and reconciliation activities. The team aims to finalize the front-end tool choice by EOW WW47 in consultation with Deloitte and internal analytics teams to streamline development and improve usability. • Manual workarounds are planned for ITC 1 and 2 phases, with formal reconciliation testing deferred to ITC 3 when the system stabilizes and data volumes are sufficient to reduce false positives. This approach is informed by lessons learned from previous releases where early testing generated many false unmatched items due to unstable data and incomplete logic. The current state compares S4 to S4 data, which should be less complex than earlier ECC to S4 comparisons. • The meeting concludes with confirmations on alignment between analytics and tower teams regarding timelines, budget, and technical approaches. It is noted that while many reporting tasks could be handled internally, the reconciliation reports’ complexity justifies external support. Other reporting efforts, such as the supply chain five-way reconciliation, are planned for internal delivery to manage costs effectively. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1439 | Cancelled |  | ERP | R3 (Release 3) | Very High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Naveen Negi | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  |  | NA | NA | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1439%20-%20IHC%20Clearing%20Open%20Items%20Intake%20form.pptx?d=w51755ce9b18f402885a0908df2e4a2c1&csf=1&web=1&e=BG6WGx |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael that this is no longer needed | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 0 | < 15 Days | bopalanisamy@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1441 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 11. Technology | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | Upload the BODS converted consumption data into S4 | Create a new upload program in IP and IF to support BODS converted S4 consumption data | The ECC PAT data requires to be transformed to support S4 PAT consumption data. Based on the data available in legacy system , three different transformation rule is to be used to convert the data in S4 required format. The approach is mentioned below . The existing PAT data from ECC will be provided to BODs teams The S4 PO converted PO data will be provided to BODs team BODS team to use the ECC PAT data and estimate the % required to convert the total commit value in S4 in the proportion The S4 file is used to identify the commit data and the % from ECC is used to estimate the consumption amount data by BODS BODS generates the data across multiple years based on the ECC file and % calculated and generates the input file to be loaded Use the new S4 program to upload the BODS file to upload the consumption data |  | Yes | Non-Core | Approved on 11/6 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT%20CR1441%20-%20Upload%20the%20BODS%20converted%20consumption%20data%20into%20S4.pptx?d=wd2ee242a48814fb38c6b8a6d5877d738&csf=1&web=1&e=NPnAnr |  | 2. New RICEFW / ECA / Build Object |  |  | High |  | 3 | [13 empty] | 0 | 0 | N/A | Yes | Conversion S4 | 2 | FPRC1724_IP, FPRC1724_IF | 3190 | FPRC1724_IP, FPRC1724_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - POR was to have a 1:1 mapping and manual upload, but this CR was triggered by a change to the conversion approach of PTP PO’s. - AR: Confirm complexity of enhancement – Keerti Nayak, Chris Woodburn | [9 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR1443 | Rejected |  | ERP | R4 (Release 4) R5 (Release 5) R5+ (Post Release 5) | High | 06. PTP | 6.8 PTP - QM |  | 06. PTP 11. Technology | Anant Joshi | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | To implement IQC Solution for IM(3PL) and EWM Locations | 04/02 [RT] Was approve 3/27 CR Review, RT to follow-up with Stacee | This is required for IQC process in QM |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBE86E535-4020-48DD-B9E2-879A0CE3E7E1%7D&file=INT-CR1443_PTP_QM_IF.pptx&wdLOR=c12E8C078-BC03-4F06-AF3F-BF1F77E37211&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 0 |  | 3171 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2025-10-30 | - This automation will help with the traceability issue. Can be done manually, but team does not want to go through this route as there is no process today in Foundry. - Related to the bailment requirement - Once this is turned on, it will be done for every batch |  |  | 2025-10-31 | • Scope: Industry standard request for incoming quality check on customer-owned materials; requires usage decision across two storage locations. • Challenge: SAP QM only applies usage decision to one location; risk of traceability loss. • Action: Develop custom program to synchronize usage decision across locations; EWM team to review alternatives and confirm technical feasibility. • Presented a CR related to the bailment process for customer-owned materials, aiming to perform non-destructive IQC. • The process requires moving a portion of material to a separate storage location within SAP to maintain traceability and quality standards without destroying the material. • The CR involves custom programming to apply usage decisions consistently across two storage locations, as standard SAP QM functionality only supports decisions at one location. • Discussions highlighted challenges with standard EWM capabilities and batch management, with the need to maintain traceability between split batches and inspection lots. • Decision: Not approved. The team agreed to take this issue back to EWM experts for further analysis to determine if standard functionality can be leveraged or if custom development is necessary. | [5 empty] | Other | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | nnagapushpa@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1442 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | New ECA CO recon report between IP/CFIN and IF/CFIN | Create a new COrecon report for recon purpose between IP/CFIN and IF/CFIN like the recon report between ECC and S4 | The new CO recon reports between IP/CFIN and IF/CFIN should have all the functionalities like that of the existing recon report between ECC and S4 incorporating the new PC mapping table with valid to and valid from date |  | Yes | Core | Reviewed on 11/14, waiting to be updated? | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-%20CR1442_%20New%20CO%20Recon%20report%20for%20IP_CFIN%20and%20IF_CFIN.pptx?d=w9011d423026147f881844d8c199a795a&csf=1&web=1&e=YhwhTn |  | 2. New RICEFW / ECA / Build Object |  |  | Very High |  | 4 | 315 | 22050 | 90 | [6 empty] | 225 |  |  |  | 0 | 225 | N/A | Yes | ECA | 1 | FPRXR128 |  |  | 0 | FPRXR128 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-14 | • The remaining CRs are for FPR reconciliation reports, which have evolved from earlier releases to accommodate more source systems and updated logic. The reports aim to verify the completeness and accuracy of transactions moving between source systems (AIA, IP, ECC) and the target system (CFIN), providing summary statistics and detailed unmatched item reports with key attributes for investigation. • There are five main reconciliation reports covering balance reports, trial balance updates using new mapping tables, and line item comparisons for financial and management accounting postings. These reports are complex and require significant development and testing effort, recognized as one of the longest and most resource-intensive tasks from previous releases. The team emphasized the need to start development early to allow for iterative logic refinement and testing, targeting ITC 3 for comprehensive testing with stable data. • The estimated cost for completing all five reconciliation reports is approximately $105K covering both Deloitte Analytics and SAP functional team efforts. The reports are highly complex and require close collaboration between analytics and tower teams. Budget constraints were acknowledged, but internal absorption was deemed challenging due to the complexity. The team plans to finalize the functional design specification by mid-December to allow sufficient development and testing time before ITC 3 begins around late April. • A key technical decision under consideration is moving away from Power BI as the interface for these reconciliation reports, as it has proven ineffective for the required audit and reconciliation activities. The team aims to finalize the front-end tool choice by EOW WW47 in consultation with Deloitte and internal analytics teams to streamline development and improve usability. • Manual workarounds are planned for ITC 1 and 2 phases, with formal reconciliation testing deferred to ITC 3 when the system stabilizes and data volumes are sufficient to reduce false positives. This approach is informed by lessons learned from previous releases where early testing generated many false unmatched items due to unstable data and incomplete logic. The current state compares S4 to S4 data, which should be less complex than earlier ECC to S4 comparisons. • The meeting concludes with confirmations on alignment between analytics and tower teams regarding timelines, budget, and technical approaches. It is noted that while many reporting tasks could be handled internally, the reconciliation reports’ complexity justifies external support. Other reporting efforts, such as the supply chain five-way reconciliation, are planned for internal delivery to manage costs effectively. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-14 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1444 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 17. B-App | Shiva Shankar Harikrishnan | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  |  | NA | NA |  |  | 12245 | Workday |  | Interface to transfer the Denodo workday details to FD share path in excel format to be processed by S4 program | Workday will send undivided file containing data for both IP and IF in a secured path. Denodo will use this file and split the file between IP and IF and further divide as Create/change and Close file for IP and IF respectively. Mulesoft to pick the details from Denodo and transform to excel format and store the file in FD file path for IP and IF | Interface to be developed to transfer the files from Denodo to FS share path in excel format |  | Yes | Core | Approved on 11/06 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1444%20-%20Interface%20to%20transfer%20the%20Denodo%20workday%20details%20to%20FD%20share%20path%20in%20excel%20format%20to%20be%20processed%20by%20S4%20program%20.pptx?d=w9175933ce5be414683dac642ab73d00b&csf=1&web=1&e=eeV1pc |  | 2. New RICEFW / ECA / Build Object |  |  | Medium |  | 2 | [12 empty] | 100 | 0 | 0 | N/A | Yes | Boundary Apps | 2 | FPRI1725_IP, FPRI1725_IF | 3200 | FPRI1725_IP, FPRI1725_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - We have identified interface coming in from Workday, but there is a challenge to split the file. The architecture team recommended Denodo, which is an integration team in Asia - No extra work from Workday required, but there might be testing impacts | [9 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-29 | 0 | < 15 Days | sharikrishnan@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1445 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | saikat.hazra@intel.com | PTP — Kenneth Salazar | PTP - Richard Taylor | ALPS PR interface | N/A | N/A | N/A | [5 empty] | Interface to trigger Purchase Requisition from ALPS to S/4 | ALPS requires the implementation of a similar automated interface for Purchase Requisition (PR) creation from ALPS to S/4 | ALPS requires the implementation of a similar automated interface for Purchase Requisition (PR) creation from ALPS to S/4 |  | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled per Prabhakar Vemuri | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 0 | < 15 Days | pvemuri@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1446 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR | Prabesh Acharya | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | Not ready since the other CR in FS build being rejected. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9F320883-C95C-4B45-ACD8-7F9AC0BE089B%7D&file=INT-CR1446%20-%20Non%20federal%20PCOS%20labor%20charges%20for%20LE%20199%20employees.pptx&wdOB=560185C8A0B14093A537B92244BB40D9&action=edit&mobileredirect=true | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-29 | 0 | < 15 Days | manidipax.gupta@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1448 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 02. E2E Process Integration 07. FTS IF 17. B-App | Eugene.celis@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | NA | NA | NA | NA |  |  | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF |  | Interplant shipping of non-revenue lots (TD Lots) needs to have GR into S/4 | Interplant shipping of non-revenue lots (TD Lots) needs to have GR into S/4 (issue was identified during the L4 design review for TD lots ingestion into S4. it was discovered that there is no reliable operation to suggest the lot is ready for shipment), this is critical to ship TD lots across sites | - The Non-Revenue lots also need to be shipped between manufacturing locations and need to have GR to ingest lots into S4, STO created and then shipped using the STO - These lots don’t get production orders in S4. However, SMH can send the transaction for these lots to S4. In S4, a check will be performed to see whether these lots were being requested to be shipped. If "Yes", then the ingestion of inventory and shipment will start. Otherwise, the data is discarded - In addition to the above, lot attributes will be also captured to help with the COO etc. for CI for the shipment. Site code for Fab, WLA and Assembly, Country Code for these sites. If lot is mixed from multiple Fabs then Fab Site code should be FVR and Fab Country for WIP should be either IE or US (To be decided by Trade Biz) and for Finish lots update based on MPL Waybill - This Change Request (CR) document is being created to cover the changes in SMH and S4 to support this process. - Update all required batch characteristics values in in Batch | Total 15 days development time (low complexity). (Intel Design – 2 days, PDF Design – 2 days, Development – 7 days, QA – 4 days) | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5A00A778-CDC0-4E65-B331-3C2AC1DB0B90%7D&file=INT-CR1304%20-Change%20Request%20For%20interplant%20shipment%20of%20TD%20lots.pptx&wdLOR=c91F59385-4D28-4448-90FC-16D9BBB59886&action=edit&mobileredirect=true |  | 1b. Solution Design |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 160 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1449 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Very High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 09A. Master Data 12. Infrastructure | joey.huang@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | Master Data | N/A | N/A | N/A |  |  | 7440, 9008 | ICOST - Integrated Cost of Sales tool, ICOST Forecast - Integrated Cost of Sales Forecast Tool |  | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | P0 Risk under analysis, CR not ready until be addressed. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/SPEED%20Straddle%20BOM%20%26%20PMD.pptx?d=w4a6ce93df5174cfb89c811c684246a60&csf=1&web=1&e=XEk4K4 |  | 11. Boundary Apps-related Change |  | Maybe | Very High | Very High | 4 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1450 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Very High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 09A. Master Data 12. Infrastructure 16. Testing 17. B-App | joey.huang@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | Master Data | N/A | N/A | N/A |  |  | 7440, 9008 | ICOST - Integrated Cost of Sales tool, ICOST Forecast - Integrated Cost of Sales Forecast Tool |  | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | P0 Risk under analysis, CR not ready until be addressed. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4323f2cb-fc9e-4b98-b46c-889206562ea4%7D&action=edit&wdPreviousSession=99c29a73-6c0a-7f56-e403-f29a92b91b5f |  | 11. Boundary Apps-related Change |  | No | High | High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 0 | < 15 Days | tatyanna.k.ariel@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1451 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 17. B-App | jerry.brown@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | Spending Data | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | P0 Risk under analysis, CR not ready until be addressed. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Supplier%20Spending%20Source.pptx?d=wca70a531af3b4b4281f60c431c9e0ab2&csf=1&web=1&e=YntxmA |  | 11. Boundary Apps-related Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1452 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 17. B-App | jerry.brown@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | Spending Data | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | P0 Risk under analysis, CR not ready until be addressed. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/Direct%20Material%20Spending%20Source.pptx?d=w8984b750e6db4f1992dd5c8c69c61248&csf=1&web=1&e=UM3lJ1 |  | 11. Boundary Apps-related Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1453 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Very High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 10. Analytics 17. B-App | jerry.brown@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | DLCP Reserves Design at R3 | N/A | N/A | N/A |  |  | 7440 | ICOST - Integrated Cost of Sales tool |  | FPR ICOST - DLCP Reserves Design at R3 | Current DLCP Reserves input source is OneMPS for reporting and an interface. This source is planned for EoL at R3. | ICOST will continue to process DLCP Reserves and requires this data for the system to run. Decision is needed regarding the R3 DLCP reserve data sources design. | Unknown as a new input source has not been defined/provided by SCP SDA/OneMPS. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR1453%20-%20DLCP%20Reserves%20Design%20at%20R3.pptx?d=we5cb5017a35a425b9d8c1dcb30fe28b1&csf=1&web=1&e=IeKsow |  | 0. Request for Investigation |  | Maybe |  | Very High | 0 | [6 empty] | 240 | [5 empty] | 40 | 240 | 0 | N/A | Yes | ECA | 1 | ECAFTSIPV6940 |  |  | 0 |  | 0 | ECAFTSIPV6940 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - In R3, OneMPS PRF2-based solve data will be completely EOL’ed, and the team needs a DLCP source - There was a temporary fix in R2, but they need a fix for R3 - Team knew about it, but they couldn’t work through it due to the R2 go-live - AR: Log as design open - AR: Align with Chad Smith & IT SCP Team - AR: Need to add in how much time BY and other teams need to spend to get the design fleshed out |  |  | 2025-11-03 | • Topic: DLCP input data for reserves program (carry-over from R2). NPS source data has changed and/or is missing. The solution for R2 was manual input. • For R3 there is a need for long-term DLCP input data for reserves calculation. • Current challenge is data previously sourced from OneMPS is gone; BY may hold it but the team needs confirmation. • The team emphasized this is critical for reserves (~hundreds of millions monthly). • Current design assumptions are unclear; the stated effort estimate (3 months) was questioned—may be less if data exists. • Rebecca Verette and Uzma Ahmed flagged this as design work, not a typical CR and requires full IT analysis. • Risk: Build ends in 6 weeks; unclear scope and integrations (PDH, BY, ICOS). • ICOST remains system of record until post-R5; BY/SAP RP will take over later. • Team agreed to timebox analysis and involve Chad Smith for effort scoping. • Needs to be added to design tracker and to engage all IT teams for detailed design and cost assessment. • John Sharkey requested Spinnaker team involvement for reporting alignment. • Decision: Not approved. Team needs to return to CR Meeting once they have worked through standard CR process to scope effort, cost, impacts, and timeline of requirements. • AR : Chad Smith to lead effort scoping effort, cost, impacts, and timeline by EO WW45. Include Joey Huang and relevant IT teams (ECA, PDH, BY, integrations). | 2025-11-07 | • CR is requesting a change in the EOL data feed from OneMPS to BY to support inventory reserves for DLCP. This data is critical for monthly close processes and auditor documentation. • The CR involves producing a report and interface for automated processing with an effort estimate of 40 hours from ICOST and six weeks from ECA. • It was clarified that this CR applies only to IP, not IF. • The report will continue beyond the system’s end of transaction date to support final close and archival. • The CR was supported and approved with understanding of its integration into a broader design open scheduled for December 19, 2025, which will consolidate related CRs • Decision: Approved |  |  |  | Other | CL/OSC | 2025-11-07 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1454 | Approved | Presenter: Chandra Elancheran | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Sangepu Lakshmi Padmaja | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | INT-CR1481 | [7 empty] | Order Change Confirmation conditions change (ZBA2, ZBA4, Z3A7) for Orders with Blocks or Status Holds ​ | pecification (FS) includes a rule that prevents order confirmation when an order is blocked. This CR proposes modifying that rule to allow the confirmation process to proceed even during blocks or status holds.​ ​ ZBA2- Order Confirmation Print Output​ ZBA4 –Order Confirmation Email Output​ Z3A7 – Significant Order change Output​ ​ Note: Z3A7 triggers for intel-initiated order changes and for customer-driven (due to inbound 3A8R), trigger 3A8C be triggered. These two triggers are mutually exclusive and cannot occur at the same time.​ ​ | Allowing order confirmation to be triggered even when blocks or status holds are applied ensures timely communication with customers and business stakeholders. The current restriction causes unnecessary delays in updating order status, which can lead to confusion and impact customer satisfaction. By revising this rule, the process becomes more agile and aligned with business needs, helping to maintain efficient order processing and transparency. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/NT-Build-CR0892-Trigger%20of%20significant%20Order%20Change%20Confirmation(ZBA2,%20ZBA4,%20Z3A7)%20for%20Orders%20with%20Blocks%20or%20Status%20Holds%20%E2%80%8B.pptx?d=w6bc95e491cb2434bb055c548f13be301&csf=1&web=1&e=rnGYPk |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 28 | 0 |  |  | 25 | [5 empty] | 28 |  |  |  |  | 0 | 28 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0191 | 1 | OTCE0191 | 1 |  | 0 |  | 0 | N/A |  | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-10-30 | - Might have to change rules for order change confirmations | [9 empty] | Build | Tower | 2025-10-30 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-30 | 0 | < 15 Days | celancheran@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1456 | New |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 04. OTC IF 05. OTC IP 08. FTS IP | meenakshi lawrence | OTC — Kevin Brown | [9 empty] | Tariff | Tariff - Legal Needs for Country Of Origin (COO) | COO determination rule changes for WLCSP, MCP and MST products at UPI Assy and UPI Test; Shipping Label Changes for EMEA countries as per new trade rules; Communicating relevant indicators to 3PL’s via RNet PIPs for printing of COO in Labels as per changes in rules. see page 3 in link to change request deck for more details. | Trade Legal compliance need |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1456_OTC_R3_Country%20Of%20Origin%20COO.pptx?d=w6fc51728b1c3465a93fa66e23698f60d&csf=1&web=1&e=3VgRO1 |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-30 | 160 | > 30 Days | meenakshi.lawrence@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1459 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 03. FPR 06. PTP 09A. Master Data | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri | NA | NA | NA | NA | [5 empty] | Sprint 19 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 19 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | No | Core | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=u2AlAJ&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTg1MjYuMjA2NjAiLCAiT1MiIDogIldpbmRvd3MiIH0%3D&CID=ed8bdfa1%2D503f%2Da000%2De87b%2Dd8fc6798c3f4&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1459 |  |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1461 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  |  | eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | [9 empty] | Pre Laser Mark- Manufacturing Re-config (Re-test lots at Finish that have completed Test) | IP needs IF to support PLM Manufacturing reconfig where tested material at Finish Stage (pre-Laser Mark) to be put on inventory staging hold point per candidate lots that meets the IP Post Test Program. Candidate lots need to go back for re-test. This is applicable mostly to server products with CPLD programmable die (i.e. SPR MCC, GNR) | Millions in ROI to avoid scrap by re-purposing tested and fused item to a different spec controlled by IP’s test program |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR1461%20PLM%20MFG%20ReConfig.pptx?d=wd6fc01264a184292a0a60ce9d224830c&csf=1&web=1&e=SsAhLA | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - This should have been part of the rework order. - Need to check with each of the tower GPO’s that they are okay with the assumptions |  |  | 2025-10-31 | • Described a manufacturing reconfiguration process where certain products failing tests require inventory to be held post-test and potentially rerouted through additional manual workarounds. • Four major changes were outlined: o Build instruction model (UI/BI alerts and data storage) postponed, with a minor SAP interface change confirmed by Deloitte. o Box and CPU ITC testing split between ITC1 (POPR and PO) and ITC2 (PR and GR), to better fit supplier capacity. o Change requests (FUT revisions) prioritized: 11 for ITC1, 8 for ITC2, with manual testing for boundary apps via flat file. o STO-PO linkage moved to ITC2, specifically for OSAT, matching previously defined scope. • The late emergence of this requirement has led to unresolved design opens, requiring approximately two additional weeks to finalize a manual process. • The team acknowledged the complexity and the need for cross-tower alignment to ensure feasible manual solutions while minimizing automation dependencies. • Mike Lange stressed the need for close vendor management and treating vendor delays as internal risks, with ongoing weekly calls and micromanagement until completion. • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-10-31 | 10, 2025 | 10, 2025 | 10, 2025 | 2025-10-30 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1463 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 09A. Master Data 10. Analytics 17. B-App | sunil.parida@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | 135 | n/a | n/a | n/a |  |  | 237 | Corporate Inventory Business Repository ODS( Operations Data Store) |  | Batch Attribute update for Straddle | For IF sites not going live at R3, need batch attribute to populate in IF S/4 when shipping materials from IF to OSAT (using 3B2 B2B messages). For IF sites live on S/4 at R3, IF PDF SMH will update the batch attribute in IF S/4. | All sites must be able to report batch attributes in IF S/4 to communicate to OSAT. For IF sites not live on IF S/4 at R3, will need ECA to send batch attributes via BODS/Mulesoft to IF S/4 custom table in order to issue 3B2 message to OSAT. | Sizing needs to be finalized by WW45.5 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20SCP/Batch%20Atrribute%20starddle%20CR.pptx?d=w8e64948067c94ecfbf9bdbd5228887f4&csf=1&web=1&e=jEJMgd |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 |  |  | 40 |  | 240 |  | 440 |  | 135 | 32 |  |  | 1 | 680 | 167 | Tech - Middleware Tech - S/4 | Yes | ECA S4 SCP | 2 | LOGI1718, ECAFTSIFV7005 | 3194 | LOGI1718 | 1 |  | 0 | ECAFTSIFV7005 | 1 | 1 |  | 0 |  | 0 | 0 | LOGI0612_IF, LOGI0155_IP | 2 | LOGI0612_IF, LOGI0155_IP | 2 |  | 0 |  | 0 | N/A |  | 2026-03-13 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-10-30 | - This is required for IF to send to IP OSAT’s due to Straddle - There will be sites that have not gone live yet, but IP is going big bang. So, it needs to provide this information - There is some CIBR logic that needs to change |  |  | 2025-11-07 | • Team outlined the need to send batch attributes from IF to IP for genealogy and traceability, especially during the straddle period involving multiple S4 plans. • This requires cross-functional work among ECA, S4 IF SMH, and IP SMH teams, with estimates including seven weeks for ECA, 135 hours for the new ECA interface, 40 hours for S4 functional work, and 32 hours for master data mapping. • Highlighted that approval is needed for placing IP data in the IF data zone; without approval, a new corporate zone setup would increase the timeline to 10-11 weeks but still feasible for ITC2. • The group agreed to approve the work conditionally, pending further review of the exception request • AR: Vanessa Clark sync w/Rebecca Verette and E2E Team re: CR1463 exception request to put IP data in the IF zone, alternatively update estimates if approval is not granted. • Decision: Approved conditionally, pending further review of the exception request with team | [5 empty] | Other | CL/OSC | 2025-11-07 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FS Overdue | Object Missing in OT | In Progress | In Progress | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1464 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 10. Analytics | 10.1 Analytics - ALL |  | 10. Analytics | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | N/A | N/A | N/A | N/A |  |  | 353, 1649, 6012, 36518, 33583, 41245, 41592, 57580, 41808 | #INVALID OPERATION |  | Analytics Exceptions for ITC2 - There are ~30+ Analytics (ECA) views & reports that won't be ready until ITC2 | Analytics Exceptions for ITC2 - There are ~30+ Analytics (ECA) views & reports that won't be ready until ITC2 | Requirements were received late and other CR's impacted the delivery of 30+ views & reports, pushing them to ITC2 | There are ~30+ Analytics (ECA) views & reports that won't be ready until ITC2 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-AnalyticsITC1Exceptions.pptx?d=wa0943e10c2dc40658b283d17ad4c3ec0&csf=1&web=1&e=Jh8so4 |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | ECA | 46 | OTCPCV003, ECAOTCIPV6827, ECAOTCIPR6845, ECAFPRV5872, ECAPTPR2406, ECAPTPR2408, ECAPTPR2409, ECAPTPR2412, ECAPTPR2382, ECAPTPR2383, ECAPTPR2384, ECAPTPR2385, ECAPTPR2387, ECAPTPR4755, ECAFTSIFV6818, ECAOTCIPV6502, ECAOTCIPR6828, ECAOTCIPR6829, ECAOTCIPR6830, ECAOTCIPR6831, ECAFTSIF4839, ECAFTSIP4840, ECAPTP5018, ECAFTSIF5075, ECAFTSIP5076, ECAOTCIP6808, ECAOTCIPR6809, ECAFTSIFR5716, ECAFTSIFR5717, ECAFTSIFR5719, ECAFTSIFR5720, ECAFTSIFR6694, ECAFTSIFR6696, ECAOTCIPR6835, ECAOTCIPR6832, ECAOTCIPR6833, ECAOTCIPR6836, ECAOTCIPR6834, ECAOTCIPR6837, ECAFTSIFR6959, ECAFTSIFR6957, ECAFTSIFR6955, ECAFTSIFR6953, ECAFTSIFR6951, ECAFTSIFR6950, ECAFPRR876 |  |  | 0 | OTCPCV003 | 1 | ECAOTCIPV6827, ECAOTCIPR6845, ECAFPRV5872, ECAPTPR2406, ECAPTPR2408, ECAPTPR2409, ECAPTPR2412, ECAPTPR2382, ECAPTPR2383, ECAPTPR2384, ECAPTPR2385, ECAPTPR2387, ECAPTPR4755, ECAFTSIFV6818, ECAOTCIPV6502, ECAOTCIPR6828, ECAOTCIPR6829, ECAOTCIPR6830, ECAOTCIPR6831, ECAFTSIF4839, ECAFTSIP4840, ECAPTP5018, ECAFTSIF5075, ECAFTSIP5076, ECAOTCIP6808, ECAOTCIPR6809, ECAFTSIFR5716, ECAFTSIFR5717, ECAFTSIFR5719, ECAFTSIFR5720, ECAFTSIFR6694, ECAFTSIFR6696, ECAOTCIPR6835, ECAOTCIPR6832, ECAOTCIPR6833, ECAOTCIPR6836, ECAOTCIPR6834, ECAOTCIPR6837, ECAFTSIFR6959, ECAFTSIFR6957, ECAFTSIFR6955, ECAFTSIFR6953, ECAFTSIFR6951, ECAFTSIFR6950, ECAFPRR876 | 45 | 46 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - Aligned with business and boundary apps leads - AR: Gather all testing impacts from Boundary Apps – Lopa Chaudry - This does not include the SCP reports |  |  | 2025-11-14 | • CR is for ECD view related to ITC1, with updates indicating that delivery is now planned for ITC 3. • The ECD fix, initially deferred from the go-live release, is tied to R2 and R3 releases. • The R2 release involves development and QA structures becoming available soon, with production readiness targeted for week 13 for locations including Ireland and New Mexico. UAT testing is planned to start around WW13, with hopes for mid-ITC 2 delivery but final sign-off required first. • The R3 release will rewire the data source from SPAN to ECA, necessitating regression testing at ITC 3, with approval from the FSSD owner for this timeline. • Development differences between R2 and R3 mainly concern the data source, with R2 pulling from SPAN and R3 from ECA. • The team decided to maintain a single code base to avoid redundant testing and reintegration efforts. • Coordination with boundary application teams confirmed that testing can proceed without the ECD data set until ITC 3 without causing showstoppers. • Clarifications were made that the ECD data represents the estimated completion date for all manufacturing lots, not just quality lots, and is intended for external foundry customers to track lot completion across manufacturing stages. • This data does not feed back into internal systems and primarily serves as a visibility tool for customers rather than impacting transaction processing • Decision: Approved | [5 empty] | Other | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1465 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.1 FTS IF - ALL |  | 02. E2E Process Integration 07. FTS IF | sunil.k.parida@intel.com | E2E/Architecture — Satya Vajjala | FTS IF - Haritha Komma | Newly Identified Design Open; will add soon | NA | NA | NA | [5 empty] | IMO Shipping End state design | Intel Mask Operations end state design | IMO Oregon shipping to Ireland--- > IMO need to ship to the other site like IR and OCT so need a separate Shipping and storage location in IF S4 and EWM need new storage type. That would be feasible to ship the reticles from IMO to OR and OCT | Will intercept ITC2; low risk. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/INT-CR0xxx_E2E_IMO_.pptx?d=w8c146ab50f284de481879c1753347be1&csf=1&web=1&e=RI9Lpv | New Requirement / Scope | 1. Process Scope / Design Change |  | No |  | Low | 0 | [7 empty] | 38 | [5 empty] | 0 | 38 | Configuration | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A | 2026-03-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2025-11-06 |  |  |  | 2025-11-07 | • Presented CR 1465, which involves configuring the IMO end-to-end design to reflect lab as an EWM location instead of an IM location. • This change is necessary because pick, pack, labeling, and handling activities cannot occur at an IM location. • The CR requests 38 hours of effort to update the STO configuration, including shipping point and storage location setup to separate IMO from other storage logs. • This change does not introduce new tasks but corrects the design representation to align with existing workflows and has been reviewed with technical teams. • The request was acknowledged as straightforward and approved without reservations • Decision: Approved | [5 empty] | Design | CL/OSC | 2025-11-07 | 11, 2025 | 11, 2025 | 10, 2025 | 2025-10-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1466 | Cancelled | [20 empty] | SIMs Segregation and reclassification in conversion | SIMs Segregation and reclassification in conversion |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-31 | 0 | < 15 Days | shrutisingh7@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1467 | New |  | ERP | R2.1 Feb 2026 | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP 07. FTS IF 08. FTS IP | junior.milan@intel.com | FTS (ERP) — Stef Maxey | OTC IF - Angela Laskowski |  | CR-1456 | [7 empty] | Tariff and Trade Impacts ¦ Co"X" Determination for WLCSP and MCP Products | Identify WLCSP or WL-CSP products for orders with Ship To's into the US to apply correct Co"X" in appropriate S4 rule table. Identify MCP products for orders with Ship To's into the US to correctly apply correct Co"X" in S4 in appropriate S4 rule table. | Tariff and trade requirement changes captured under CR-1456 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Tariff%20and%20Trade%20Impacts_CoX%20Determination%20for%20Products.pptx?d=w28e469a21e4f4cb88d8fc474310375eb&csf=1&web=1&e=KVlYdP | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-31 | 159 | > 30 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1468 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-31 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1469 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP | JEAN-MARC LENC | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | CRXXXX- CAAS API to split the Entity Name into SAP format | Enhancement to convert the name information sent by B-Apps into SAP format | The Interface OTCI1187 is designed based on the standard SAP structure of the name fields ( Name 1,2,3 and 4 with 40 character length each ) for customers and vendors. But the Boundary Apps ( Profisee, Reltio and Webquote )consuming this interface doesn’t have such a limitation and they have one whole name. Due to this constraint, to have the BP created in GTS with the full name we need to have a split logic enabled at Mulesoft or at S4 level so that the full name from B Apps is split and transformed into the 4 name field options we have in SAP. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6D2494D4-3ABB-4E7F-B2B8-8FE762868EEA%7D&file=INT-CRXXXX%20CAAS%20API%20to%20split%20the%20Entity%20Name%20from%20B%20App%20into%20SAP%20format.pptx&action=edit&mobileredirect=true&previoussessionid=d7f35331-8932-f93c-7455-e888b133e249 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 10, 2025 | 2025-10-31 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1470 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 04. OTC IF 05. OTC IP | sukhwinder.ranu@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR1470-%20Change%20Ownership%20of%20AR%20reports%20from%20OTC%20to%20FPR.pptx?d=w76451169da664884a2a7939b2592e889&csf=1&web=1&e=07VN7j |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2025 | 2025-11-03 | 0 | < 15 Days | rahulranjan3@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1471 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | [11 empty] | Cancellation of RICEFW Objects: FTSE1627 - Enhancement to capture Quality lot hold information | Cancellation of RICEFW Objects: FTSE1627 - Enhancement to capture Quality lot hold information | This functionality will be implemented directly within ECD, and the associated information will be stored in an ECD-related table. Per Ron’s confirmation, there is no need to store this information in the FTS IP custom table. |  | Yes |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Cancellation%20Requests/Descope%20_%20FTSE1627%20-%20Enhancement%20to%20capture%20Quality%20lot%20hold%20information.pdf?csf=1&web=1&e=Xusot3 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1471%E2%80%93%20Cancellation%20of%20RICEFW%20Objects%20FTSE1627.pptx?d=w6e1f392d032b4814b0ce80610f1e2d91&csf=1&web=1&e=cAeRMs |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE1627 | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | [10 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-03 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1472 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP 08. FTS IP | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | CR-1456 | [6 empty] | Tariff | Tariff and Trade Impacts ¦ 3B12R for 3PL Shipping Label | Compliance needs to send the indicator in 3B12R for EMEA shipments to 3PL to suppress COF for EMEA Countries for IP | Tariff and trade requirement changes captured under CR-1456 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-XXXX_IP_Tariff%20and%20Trade%20Impacts_3B12R%20for%203PL%20Shipping%20Label.pptx?d=w6558bfe7e83f4622befb0d9e4723b762&csf=1&web=1&e=jM5ngr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 35 | [5 empty] | 90 |  |  |  |  | 0 | 90 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0418, LOGE0611 | 2 | LOGI0418, LOGE0611 | 2 |  | 0 |  | 0 | N/A | N/A | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 |  |  |  | 2026-01-30 | [6 empty] | Build | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 11, 2025 | 2025-11-03 | 0 | < 15 Days | imme.sandweg@intel.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR1473 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | NJAIN42@deloitte.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | None | INT-CR1150 | None | None | [5 empty] | Cancellation of FTSE1634 (Build Instruction Manual UI) | The functionality to upload the Build Instruction data to the UDF table and create the Sales order along with it is covered by the OTC object- FS-O-020-010-OTCE1106_Enhancement to support Inbound interface and manual upload to create the sales order via Build Instructions .docx Design including one global template which will is expected to be filled by the CBA before uploaded to UDF tables via custom fiori UI. Since the functionality is alredy covered by the OTC object the current object# FTSE1634 will be CANCELLED. | The functionality to upload the Build Instruction data to the UDF table and create the Sales order along with it is covered by the OTC object- FS-O-020-010-OTCE1106_Enhancement to support Inbound interface and manual upload to create the sales order via Build Instructions .docx | None | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/03.%20Final%20Deliverables/Build/IF_RICEFW/Enhancements/FTSE1634-%20Anafi_Build%20Instructions%20to%20UDF/EXT%20RE%20Cancellation%20of%20FTSE1634%20Fiori%20UI%20to%20upload%20BI.msg?csf=1&web=1&e=MeHTve | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE1634 | OTCE1106 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | [10 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1474 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | [11 empty] | Cancellation of Returns Conversion Object - OTCC0637 | As per the latest business alignment, the conversion process will be part of any of the existing RICEFW ID's and hence the Returns Conversion object has been proposed to be descoped. | As per the latest business alignment, the conversion process will be part of any of the existing RICEFW ID's and hence the Returns Conversion object has been proposed to be descoped. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/EXT%20RE%20Request%20Approval%20for%20Descope%20of%20RICFEW%20ID%20OTCC0637.msg?csf=1&web=1&e=mhuaco | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1474%E2%80%93%20Cancellation%20of%20RICEFW%20Object%20ID%20OTCC0637.pptx?d=wd402fd5706444374b245ebce09461449&csf=1&web=1&e=WlKxxL |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCC0637 | OTCI0294 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-04 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | No Objects |  | In Progress | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1475 | Approved |  | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Nikhil Jain | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | No | [8 empty] | Readjust Dates for R4 Objects | Currently the R4 objects are showing under R3 Release. Required to correct the object Release and plan the build and FUTs accordingly. | R4 objects flagged under Release 3 | No | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1475/EXT%20RE%20CR1475%20to%20adjust%20FTS%20IF%20objects%20from%20R3%20to%20R4.msg?csf=1&web=1&e=HsZS3K | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1475_FTS-IF_Readjust%20dates%20for%20R4%20objects.pptx?d=w5bf66ad8a24a4337bb249abb271e2469&csf=1&web=1&e=hfTGvi |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 9 | FTSI1654, FTSI1652, FTSI1651, FTSI1578, FTSI1431, FTSI1321, FTSI1318, FTSE1577, FTSE1119 |  | FTSI1654, FTSI1652, FTSI1651, FTSI1578, FTSI1431, FTSI1321, FTSI1318, FTSE1577, FTSE1119 | 9 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-25 | Approved offline with Uzma, Stef, and Shamin | [9 empty] | Other | Tower | 2025-11-25 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-04 | 0 | < 15 Days | njain42@deloitte.com |  | No |  | In Progress |  | In Progress | No
R2 (Aug 2025) | R2 Anafi | INT-CR1476 | Approved |  | SCP | R2 Q4 '25 Anafi enablement | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 11. Technology | tracy.a.hendricks@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | unsure what to put here, but it is required to fill it out | new VP has different expectation of the process and we do not want to commit supply to one customer and then take it away to commit it to another customer. | unsure what to put here, but it is required to fill it out | unsure what to put here, but it is required to fill it out | [5 empty] | IFS needs an "Unallocated Partition" to hold capacity and prevent it from being utilized by BY ESP. | IFS needs an "Unallocated Partition" where it is possible to hold capacity and prevent it from being consumed from either the common or IFS partition, while decisions are being made on which customers to allocate the capacity to. | Deepak requested this Change Request. The business use case that drove this requirement coming out of Nov Cycle and will be the driver in the future, is the 10nm increase in capacity at about 117k wafers over the horizon. We were ready to allocate the 2026 improvements but not the 2027 improvements. However, there is no way in BY today to prevent this capacity from being consumed based on our constrained situation. Then with the data transfer to customers, IFS Customers would see that they were allocated the capacity which would give an incorrect picture of their supply if next month IF then redistribute the capacity to other customers. | unsure what to put here, but it is required to fill it out | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR_XXX_IF%20FTS_IF%20Unallocated%20Partition%20Creation.pptx?d=w2d1341501b4a42f7b7c197f4a39ef919&csf=1&web=1&e=RVBfAK |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | Medium | 0 |  |  |  |  | 80 | 40 | [7 empty] | 120 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 140 objects | 1 |  | 0 |  | 0 | 140 objects | 1 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | - There is no impact to deploying by WW50 | [9 empty] | Build | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1477 | Approved |  | ERP | R3 (Release 3) | Low | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 06. PTP 07. FTS IF | Ramadas Sridhar |  | FTS IF - Haritha Komma |  | INT-CR1381 | N/A | N/A | [5 empty] | Cancel Object: FTSE0987 | Develop a program that automatically creates credit memos after suppliers approve warranty claims. The program should use the SAP MIRO BAPI to generate the credit memos, which will then be validated in ReadSoft before being posted to the AP sub-ledger and applied as a payment deduction for the supplier. | The PTP & FPR teams want to eliminate the manual process for creating credit memos. Previously, an email was sent to the Purchasing Group, and someone had to create the credit memo manually. To reduce resource burden, the business would like to move forward with a fully automated approach: once a warranty claim is updated in E2Open, a credit memo will be created automatically using the BAPI. | No Impact | No |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1477%2FEXT%20Re%20Approval%20for%20Object%20Cancellation%20FTSE0987%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FCR1477 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSE0987 | FTSE1687 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | [10 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1478 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR | maheshx.reddy.dwarampudi@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | Cancel Object FPRE0882_IP | S/4 RICEFW was created for IP to process the FTQ based drivers and transform them to be used for allocation. There are no FTQ based Drivers in IP and hence this RICEFW is not needed. This development was never picked up. This CR is to record the cancellation of this tracking serial# of FPRE0882_IP. This is to allow development team descope above mentioned RICEFW. | S/4 RICEFW was created for IP to process the FTQ based drivers and transform them to be used for allocation. There are no FTQ based Drivers in IP and hence this RICEFW is not needed. This development was never picked up. This CR is to record the cancellation of this tracking serial# of FPRE0882_IP. This is to allow development team descope above mentioned RICEFW. | No Impact | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1478/Re_%20FPRE0882_IP%20object%20Cancellation%20for%20FP%26A_.msg?csf=1&web=1&e=zn2jr4 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE0882_IP | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-19 | [10 empty] | Other | Tower | 2025-11-19 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | prashachauhan@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1479 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  | 07. FTS IF 10. Analytics | Eric Yamada | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  |  | N/A | N/A | CHG117277398 | Open |  |  |  | R2 Demand Netting for Non PO Products | Request to calculate correct netting of demand for non PO products | Forecast provided to Supply planning for non PO items does not account for actual sort outs from previous week production | No Impact | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared Documents/Intel Foundry R3 Program Mgmt/Program Integration/Change Control/SCP-CR.xxxx Demand Netting for Non PO Products.pptx?d=w2490f3e9c6664d51841baf368c417760&csf=1&web=1&e=xeIRKh |  | 1a. Operations Design |  | Yes |  | Low | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-04 | - This change is for all of the EMIB die. - This is for cases when we over or under deliver, we are not netting the demand. o This should not have an impact to IT unless we have a shortage. - This is a design gap. When we decided to not have orders for certain products, we didn’t go through all of the scenarios or implications of the decision. - The options are to create a process to identify the correct items/products that don’t have orders on them. o There is PDH work to do the calculation to send the correct information onto F&E and supply planning. o This will require an additional SPAN interface to PDH o We also need some process (straddle) that will cover from now until the long-term changes are live. - We have to go forward with this. The workaround is in CDP and manual. o This will go away with R3 as all products will have orders by then. | [9 empty] | Other | Tower | 2025-11-04 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1481 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology | Sangepu Lakshmi Padmaja | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | INT-CR1454 | [7 empty] | Prioritization & Readiness plan for Custom conversion tool(OTCE0719) & to pull in CR 1454 into ITC1 | The custom conversion tool (OTCE0719), designated for use by the Mergers & Acquisitions team, is classified as a high-complexity RICEF object. The IP team is aligned that, given this tool’s nature as a conversion solution, critical objects related to order management can be prioritized above it. Both technical unit testing and functional unit testing will require comprehensive testing and validation efforts to ensure quality and accuracy. Additionally, the delivery of Change Request CR-1454 will be brought forward into ITC1, recognizing its importance as a key object for external partner readiness testing. | Based on the feedback from development team, this effort will span multiple sprints as the work consists of both front-end Fiori development (involving multiple screens) and substantial backend programming. Given its conversion nature, the IP team agrees that critical order management objects can be prioritized above this Delivery of CR-1454 is being advanced to ITC1 to support external partner readiness testing. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B14FB0B58-EE47-4E7C-A303-ECA7D8F59465%7D&file=NT-Build-CR1481-Prioritization%20and%20Readiness%20Plan%20for%20Custom%20Conversion%20Tool%20(OTCE0719).pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment S4 | 1 | OTCE0719 |  | OTCE0719 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-13 | - This is for swapping 2 development objects - OTCE0719 will take more than 1 sprint, so they decided to swap it out with OTCE0191 as it was more critical. - It was aligned with order management team, and they were okay because it is OM automation. - Tech team is okay to make this swap - Shelly and Kevin are aligned. | [9 empty] | Other | Tower | 2025-11-13 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | celancheran@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1482 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | Rose Pham | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA | [7 empty] | Cancellation of ITT objects | Cancellation of Build Sprint activities 5.1 and 5.2 for ITT objects below: FPRE1510_CFIN FPRE1511_CFIN FPRE1512_CFIN FPRE1513_CFIN FPRE1514_CFIN 5.1 Conduct & document FUT 5.2 Approve FUT document | The below ITT objects are in scope for FUT in R3 S19. ISM number creation and PO number creation are both needed to create scenarios for FUT purpose. We received confirmation from ISM and PTP team that PO and ISM are not created in CFIN instance. Hence, the build sprint activities related to these objects in CFIN need to be cancelled (no FUT is performed in CFIN). FPRE1510_CFIN FPRE1511_CFIN FPRE1512_CFIN FPRE1513_CFIN FPRR1514_CFIN 5.1 Conduct & document FUT 5.2 Approve FUT document | No | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1482/Approval_%20INT-CR1482%20Cancellation%20of%20Build%20Sprint%20activities%205_1%20and%205_2%20(FUT)%20for%20ITT%20objects.msg?csf=1&web=1&e=9gtdmO | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1482%20Cancellation%20of%20Build%20Sprint%20activities%205.1%20and%205.2%20(FUT)%20for%20ITT%20objects.pptx?d=w3414df9b23cf405aa94dd000d31434d8&csf=1&web=1&e=yQtzy1 |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRE1510_CFIN, FPRE1511_CFIN, FPRE1512_CFIN | N/A |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1483 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1484 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1485 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1486 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1487 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1488 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Sindhuja Gangireddy | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Wild card search functionality for WOM users (OTCI0085) | To incorporate Wild card search functionality for WOM users and send response from S4 accordingly in order status tab | To incorporate Wild card search functionality for WOM users and send response from S4 accordingly in order status tab |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1488_OTC%20IP_CR%20Deck_OTCI0085_Wild%20Card%20Search.pptx?d=w0aec0ed825d44a43a9498bdd451d0e48&csf=1&web=1&e=zOx7j5 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 18 | [5 empty] | 30 |  |  |  |  | 0 | 30 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI0085 | 1 | OTCI0085 | 1 |  | 0 |  | 0 |  |  | 2026-04-17 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - This CR is to add 6 fields that were originally considered not required. - This will impact 6 test cases. Base functionality will be tested in ITC1. - This is the existing capability today | [9 empty] | Build | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-05 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1490 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | [9 empty] | DOM/ Incoming Bridge die- Customer Lot number Change | DOM/ Incoming Bridge die- Customer Lot number Change | *Cancelled; Die on Mylar(wafer Map) file is shared with Substrate supplier triggered from Mfg Systems and supplier sends back Incoming bridge die information to Intel. After R3, these file shares should reference the IP “customer Lot number” instead of Intel Lot number from Mfg. Change request is for TD automation to generate DOM file with IP customer lot number and when Substrate supplier sends back the customer Lot number in the Incoming Bridge dies, it has to be translated back to IF lot numbers for Mfg use |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1490%20_DOM%20Incoming%20Bridge%20die-%20Customer%20Lot%20number%20Change.pptx?d=w1a4aec377b2842648b83a70d9bb2e285&csf=1&web=1&e=hkdEMN |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Loni to not be required | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-05 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1491 | New |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Bapuji Reddy | PTP — Kenneth Salazar | PTP - Richard Taylor |  | N.A. | [7 empty] | Additional Enhancement for PTPI0470 [Payment Proposal after invoice posted from SAP S/4 HANA CFIN to Ariba] Custom Payment Proposal Status Update for Ariba Integration | Currently, when we trigger a payment remittance cancellation interface, the payment proposal status in SAP changes to "Cancelled." This is an SAP bug. According to Intel’s requirements, the status should show as "Scheduled" instead, so that suppliers understand that Intel will make the payment in the future, not that it’s been permanently cancelled. The "Cancelled" status gives suppliers the wrong information to Supplier. To fix this, we need a custom solution for the payment proposal so that the correct status ("Scheduled") is sent to Payment proposal tab in ARIBA. | Right now, when we cancel a payment, SAP shows the status as "Cancelled." This makes suppliers think the payment won’t happen at all, but often, we just plan to pay them later. If we show the status as "Scheduled," suppliers will know we still plan to pay them. This will help avoid confusion and keep communication clear. | Yes | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1491_PTP_CFIN.pptx?d=w0f4c2fafd435494d84a532930838b6b4&csf=1&web=1&e=ixEtGQ |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  | 3184 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-06 | 153 | > 30 Days | suggupta@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1492 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 09B. Data Migration | Imran Athar | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Logic change for Batch master conversion (LOGC0972_IF and LOGC0972_IP) from SAP ECC | Logic change for Batch master conversion (LOGC0972_IF and LOGC0972_IP) from SAP ECC and Manual File | 1.Extraction criteria changed (Extract batch master details based up the open stock inventory) for Batch conversion from ECC to S4.​ 2. Plant and Sloc. X-Ref logic change (Applicable for Open Inventory and Batch Master)​ 3.Extraction, Preload & post load file to be split as per the commodity as the business owner are different for different commodities.​ 4. Change in the Layout of Preload file.​ 5. Extraction of Customer Warranty Batches (Batch Stock = 0) from ECC based upon Material list provided by Intel Business and upload into the S/4. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD63715D0-79AC-4E50-B60B-2B0DC20EAD84%7D&file=CR1492%20Logic%20change%20for%20Batch%20master%20conversion%20(LOGC0972_IF%20and%20LOGC0972_IP)%20from%20SAP%20ECC.pptx&wdLOR=c928F1961-D08B-44F9-931D-5A378004B11E&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 46 | [7 empty] | 129 |  |  | 0 | 129 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGC0972_IF, LOGC0972_IP | 2 | LOGC0972_IF, LOGC0972_IP | 2 |  | 0 |  | 0 | N/A |  | 2025-12-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-06 | - Team is aligned to make changes before MC1 - Will need 10 more days past the December due date to submit the data for cross-reference; that is the only timeline that the Logistics team will break | [9 empty] | Build | Tower | 2025-11-06 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-06 | 0 | < 15 Days | suggupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1493 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | 3.10 FPR - Accounts Receivable & Collections |  | 03. FPR 04. OTC IF 05. OTC IP 10. Analytics | sukhwinder.ranu@intel.com |  | FPR - Aubrey Hinderlider | [9 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/CR1493-%20Addition%20of%20new%20%20fields%20to%20the%20existing%20Batch%20%26%20NRT%20Reports.pptx?d=w430bd56542354867aec177b573e513ff&csf=1&web=1&e=OG5uG8 | [5 empty] | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-06 | 0 | < 15 Days | rahulranjan3@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1494 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | chgorantla@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | 1499 | NA | NA | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | NA | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/N%20rate.pptx?d=wc1494d6aab7e45528f637023752e91ca&csf=1&web=1&e=pYbMYw |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael that this is covered in the FS Build CR Log | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1495 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP | anand.sharma@intel.com | BApps — Kelly Gerber | Testing - Guna Vishwanathan |  | Testing schedule change | NA | NA |  |  | 23736 | SAP ECC Vistex Rebate and Accruals |  | Vistex Request for splitting ITC1 Test Case Execution between ITC1 & ITC2 | CR describes the changes to ITC Testing Approach for Vistex Rebate Automation. Vistex Rebate Automation team has 2200 Test Cases with following plan for ITC Testing ITC1 50% Test Cases: Execute 1,100 test cases focusing on core application functionality. This initial cycle will help us identify and resolve critical defects while accounting for data availability constraints and the expected volume of issues in early testing phases. ITC2: 60% Test Cases Execute remaining 1100 test cases and additional 300 test cases from ITC1, achieving 100% test coverage. Building on lessons learned from ITC1, we will complete remaining test cases plus additional coverage from the previous cycle. ITC3 : 100% Intercept - execute all 2200 test cases with the benefit of an additional week & accumulated testing experience, ensuring complete app coverage. | Test cases need to be strategically split between ITC1 and ITC2 cycles to address environmental, timing, data constraints as listed below 1. Customer Hierarchy Limitations - Not all rebate customers and customer hierarchies may be available in ITC1 and ITC2 environments. Due to these limitations, customer hierarchy test cases will be split between ITC1 and ITC2 based on data availability. 2. Product Hierarchy Constraints - Incomplete product master data and hierarchies in ITC1 and ITC2 environments restrict rebate testing scenarios. Product hierarchy test cases will be distributed across ITC1 and ITC2 cycles, focusing on available critical combinations in ITC1 and corner cases in ITC2. 3. Extended Test Cycle Duration – Many test cases require extended execution time due to batch job dependencies in Vistex and across upstream and downstream system. To manage these timing constraints, long-running test cases will be split between ITC1 and ITC2 cycles. IQR and MyDeals System Dependencies - Deal propagation test cases dependent on IQR and MyDeals systems will be segmented across ITC1 and ITC2 cycles due to batch job timing requirements.. Vistex Internal Batch Processing Constraints - Vistex Object Test Case completion require Batch Jobs Completion which introduces delay in Vistex Specific test cases. Test cases requiring GRASP and Consumption batch jobs will be split between ITC1 and ITC2 to manage processing delays. ITC1 will cover 90% of system functionality. corner and edge test cases will be executed in ITC2. OTC and CFIN Integration and Batch Job Dependencies - Batch jobs across boundaries such as OTC, CFIN run on a specific cadence. This will delay our test case completion in areas where financial posting is needed. Accrual and payment posting test cases will be split across ITC1 and ITC2 cycles due to the sequential nature of Vistex, OTC, and CFIN batch job dependencies. 4. Data Set Reusability Limitations - User driven UI test cases require complex data preparation and once a test case is executed same data can’t be re-used. Consumption-related test cases will be carefully distributed across ITC1 and ITC2 cycles to preserve data integrity and avoid conflicts. 5. High Volume of Expected Issues in ITC1 - Functional testing completed in DI0 with very limited dataset, we are expecting high volume of issues in ITC1. This will prohibit us from testing at full capacity | None. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/CR%20-%20Vistex_Rebates%20B_App%20_ITC%20Split%20Test%20Cases%20Change%20Request.pptx?d=w0075ef16d2674fc89c48b69f984aac62&csf=1&web=1&e=rXXBE5 |  | 13. Other Milestone Adjustments |  | No |  | High | 0 | [12 empty] | 0 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-13 | - This can be tested with all of the invoices within ECC, and Vistex will be able to run testing off of this. | [9 empty] | Other | Tower | 2025-11-13 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1496 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Manjunath M Meti | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Creation of entries in order sim input tables ZTOTC_ORD_SIM_W and ZTOTC_ORD_SIM_D table upon creation of ZSDP condition records from conversion ​ | Creation of entries in order sim input tables ZTOTC_ORD_SIM_W and ZTOTC_ORD_SIM_D table upon creation of ZSDP condition records from conversion | Order sim input tables ZTOTC_ORD_SIM_W and ZTOTC_ORD_SIM_D, which will be the data feed for Order Sim Program and prices are simulated and captured in table ZTOTC_ORDERSIM. This data will be further Utilized by PIP 2A1 price catalogue, ECA and for creation of CHM condition records |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Praveen to be cancelled |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-06 | 0 | < 15 Days | mmeti@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1497 | New |  | ERP | R3 (Release 3) |  | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Abhishek Hingne | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | ECD IP Legacy Table Migration |  | This CR is required for the Legacy Table Migration of As-Is ECD IP data which consists of MRB and material based information to upload in S4.Upload function need to be implemented for S4 ECD IP proposed tables. This alignment came after the object FS is approved |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/FTS_LE%20INT-INT-CR1497%20ECD%20IP%20Conversion%20Finished%20Good%20from%20ECC%20to%20S4.pptx?d=w51eb631058334cfc986d908409a6661d&csf=1&web=1&e=GD2DbD |  | 1b. Solution Design |  |  | Medium | High | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-07 | 152 | > 30 Days | ahingne@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1498 | Approved |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Abhishek Hingne | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma | [9 empty] | COO determination logic for WIP-IF inventory | To incorporate COO determination logic for WIP-IF inventory and to be printed on CI, PL forms | This CR is required to accommodate determining COO for WIP-IF inventory and print the same on CI, PL forms. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9AD13E4A-92FB-4A4E-AD04-E05A3EA45339%7D&file=INT-1498%20%25u2013COO%20Determination%20Logic%20for%20WIP-IF%20Inventory.pptx&wdLOR=cDF34CDE9-2AA3-473F-9AD9-99865798A377&action=edit&mobileredirect=true&CID=1F2FC09A-DB58-4922-A321-580D70DA9328 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | High | 2 |  |  | 66 | [5 empty] | 234 |  |  |  |  | 0 | 234 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0842_IF, LOGI0842_IP, LOGF1523​, LOGF1524, LOGF1525, LOGF0350_IF, LOGF0350_IP, LOGF0349_IF, LOGF0349_IP, LOGF0342_IF​ | 10 | LOGI0842_IF, LOGI0842_IP, LOGF1523​, LOGF1524, LOGF1525, LOGF0350_IF, LOGF0350_IP, LOGF0349_IF, LOGF0349_IP, LOGF0342_IF​ | 10 |  | 0 |  | 0 | N/A | N/A | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-11 | - Trade finalized logic for COO determination to apply a correction and meet legal requirements. - Existing DBAAS object can be utilized and updated with a routine. DBAAS currently has an SLA of 45 minutes for a batch. - If 45 minutes pass and DBAAS is blank, then transaction will be failed. Else, it will pull that value. - COO will be manually populated in the STO or S/4 delivery document in ITC1. It will be automated in ITC2. - COO will not be a required field. - AR: Make sure that Trade is aligned with this logic - @Athar, Imran | [9 empty] | Build | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-10 | 0 | < 15 Days | ahingne@deloitte.com |  | No | FUT Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1499 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | chgorantla@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | 1494 | NA | NA | [5 empty] | N rates tickers coming as null or zero for around 270 tickers​ | We are using ZTMDG_CONSTANTS table for storing the values. Now, this is required only for local bank rate and we will remove spot rates from identifiers as no interpretation is required for them. | N rates tickers coming as null or zero for around 270 tickers | NA | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/N%20rate2.pptx?d=waa0777bf99a3466386b32ed8e993a667&csf=1&web=1&e=oNh1G8 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | This is a copy of CR1494 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1500 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF | Kolleru Venkatesh | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | No | [8 empty] | Cancellation of FTSI1684-Interface from FFS to S/4 to maintain POLP table | Cancellation of FTSI1684-Interface from FFS to S/4 to maintain POLP table | Since the functionality is already covered by the Other FTS object FTSI1159 the current object# FTSI1684 will be CANCELLED. The data will be published by all the production scheduling applications ( FSCO,FFS,APPS) to one ECA view. This is from where S4 reads the data and update custom PLPO table | No | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/_EXT_%20RE_%20Cancellation%20of%20FTSI1684-Interface%20from%20FFS%20to%20S_4%20to%20maintain%20POLP%20table.msg?csf=1&web=1&e=uzlu9T |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FTSI1684 | FTSI1159 |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-12 | [10 empty] | Other | Tower | 2025-11-12 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1501 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1502 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1503 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-10 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1504 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP | jean-marc.lenc@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | NA | 2321 | NA | [5 empty] | Exception CR for pushing E2E FUT for 3 NL Broker interface objects beyond Sprint 21. | Exception CR for pushing E2E FUT for 3 NL Broker interface objects beyond Sprint 21. | In the to-be IAO design, we will have three interfaces connecting GTS E4H to Expeditor for import Customs Declaration filing (OTCI1423, OTCI1648 and OTCI1649 ). While the ERP side build is expected to be complete by the current sprint, we have got a confirmation from Expeditor that their build will be complete by Jan 2026. Hence the FUT of the above mentioned objects cannot be completed by Sprint 21 time-frame. | ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B96413D0C-1596-4489-A765-795C890E4AFA%7D&file=INT-CRXXXX%20CAAS%20API%20to%20split%20the%20Entity%20Name%20from%20B%20App%20into%20SAP%20format.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  | No |  | NA | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as the RICEFW's will be completed to intercept later weeks of ITC1. | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1505 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.3 OTC IP - Billing and Rebates |  | 05. OTC IP | Eina Gupta | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | INT-Build-CR0950 | [7 empty] | Custom Requirement Routine to automatically trigger ZZIV Output only for Intercompany Billing document | Custom Requirement Routine to automatically trigger ZZIV Output which calls the standard program to trigger IC Credit and Debit Memo only when the billing document Selling LE is different than Supplying LE | As per requirement, IC Credit and Debit should get triggered without any IC CMR/DMR whenever a credit or debit memo is created where Selling LE is different than Supplying LE. However, as per standard functionality, to trigger IC Billing for non-delivery scenarios, Program RVIVAUFT needs to be executed via ZZIV Output from Credit/Debit. (OSS 63459). A custom requirement routine is required to trigger the ZZIV output only if Selling LE is different than Supplying LE, otherwise system will always trigger this output without any check. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B539BBDED-D18E-475D-9E5F-58106CD8D721%7D&file=INT-Build-CR0950-IP_Custom%20Routine%20for%20IC%20Credit_Debit.pptx&action=edit&mobileredirect=true | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | Low | 2 |  |  | 12 | [6 empty] | 27 |  |  |  | 0 | 27 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE1605 | 1 | OTCE1605 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-03-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-13 | - There is no check if the planned order is different than the sales order. - We didn’t do this before because the ask was to check with SAP to see if there was standard solution. But the check is not there. - This is not required for the PO/SO model - SO1 will trigger purchase order to create SO2. This is 2DN. It is not used internally - This will be tested manually in ITC1 - This was discovered during testing | [9 empty] | Build | Tower | 2025-11-13 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-11 | 0 | < 15 Days | eigupta@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1506 | Cancelled |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Praveen Kumar Muppala | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Intrastat Reporting-Sales consignment WIA Invoice setup for Fill up orders(ZKB) | INTRASTAT is an EU-wide system used to collect data on the movement of goods between EU member states. Businesses registered for VAT and exceeding a certain threshold must report these transactions monthly | The business moving goods across EU borders, even if it’s just to place them at a consignment location, must file an INTRASTAT report |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRxxxx-Intrastat%20Reporting-Sales%20consignment%20WIA%20Invoice%20setup%20for%20Fill%20up%20orders(ZKB).pptx?d=w464a0f7274674383bf1ea280a4cdc34c&csf=1&web=1&e=b0No83 | New Requirement / Scope | [5 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-13 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1507 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 13. Security | 13.2 Security - Cyber/ App Security |  | 03. FPR 04. OTC IF 13. Security | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri | NA | NA | NA | NA | [5 empty] | Operate - Updating IT Support Roles based on Firefighter Usage | Based on an analysis of the initial weeks of Firefighter ID usage, it has been evaluated whether any access currently used through Firefighter IDs can be transitioned to IT support access. This is to reduce reliance on Firefighter access | Reduce firefighter usage | 2//28/2026 | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/Approvals/INT-CR1507%20EXT%20RE%20CR%20Approval%20for%20Updating%20IT%20Support%20Roles.msg?csf=1&web=1&e=JaaoLQ | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6f1d3d96-ca6a-4be7-962a-12ff47f8d0e3%7D&action=edit&wdPreviousSession=20ea4fd4-221c-5979-6cfd-ab87baff888a | New Requirement / Scope | 1a. Operations Design |  | No | Low | Low | 1 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-13 | 146 | > 30 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1508 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor | [9 empty] | Cancel Objects: PTPI1425_IP and PTPI1425_IF | Descoping of PTPI1425_IP and PTPI1425_IF | In these two RICEFW we captured logic for creating RFC in IP/IF calling from CFIN to send original values from CFIN to ARIBA network. We have an enhancement object PTPE1139_IP and IF, In this we have already created RFC and covered all our ARIBA interfaces to send original values. We need to descope PTPI1425_IP and PTPI1425_IF. | N.A | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub%20Team%20-%20Enable%20Payment/Mails%20for%20Approval/RICEFW%27s%20Descope%20Approval%20Mail/EXT%20RE%20Request%20for%20GPO%20alignment%20related%20to%20Descoping%20PTPI1425_IP%20%20IF%20CR%20ID%20INT-CR1508.msg?csf=1&web=1&e=4K4W62 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Medium | 0 | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | PTPI1425_IP, PTPI1425_IF | PTPE1139_IP, PTPE1139_IF |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-19 | [10 empty] | Other | Tower | 2025-11-19 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-14 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1509 | Cancelled |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR 04. OTC IF | Praveen Kumar Muppala |  | OTC IF - Angela Laskowski | [9 empty] | Calculation of condition ZDCV – Pass through Revenue. |  | During Mfg by Stages Previous Product will pass through to next stage. And at every stage we need to break up the Intercompany Invoice for Value add and Pass through cost. We have ZPRS – Cost (Total cost in selling plant) , ZVAL- for Value added in selling plant, We need to Create this condition ZDCV which is the Diff of ZPRS –ZVAL to derive Pass through Cost. For this we need a minor Routine in SD to calcualte this formula in condition record. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1509-%20Pass%20Through%20Revenue%20for%20IF%20IC.pptx?d=w4402e0606b274568bc2e73dcf819a8d6&csf=1&web=1&e=dMuX4g |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as technical effort is less than 40 hours | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-17 | 0 | < 15 Days | pmuppala@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 UAT1 | INT-CR1511 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 17. B-App | Lopa Chaudhry | BApps — Kelly Gerber | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A |  |  | 5159 | ADP Payroll GAR |  | New IF Entities IN/TW/JP & Testing Strategy for HR – ADP Payroll BApp | 3 New IF LEs are being set up for R3 Go Live Q2’27 - India, Taiwan, and Japan which will be legally incorporated in Q3’26. Definition of testing strategy to serve both S4 and HR BApp – ADP Payroll (vendor app). Note: ADP integrates with Workday for the payroll files and S4 integrates with Workday. ITC cycles: Workday will provide payroll files to S/4 for testing. UAT cycles: ADP will engage in e2e testing for new legal entities. ADP does not participate in e2e testing until LEs are legally created | Intel's Chief Tax Officer, Clara Wong, requests not to incorporate entities until 6 months prior to Go Live due to financial reporting requirements. Entities are not expected to be operational until R3 and incorporating entities more than a year in advance of operationalization is not recommended. | Low risk for R3 – e2e testing will occur in UAT for ADP Payroll. Typical schedule for all new LE setup in Workday and payroll is 3 months, allowing 6 months due to IAO | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Boundary%20Apps/INT-CR0%23%23%23%20-%20LERBappsFPRIFINTWJPADPpayroll.pptx?d=wa9dec0ee10da4c218a79df6010199430&csf=1&web=1&e=7E7fCX |  | 11. Boundary Apps-related Change |  | No | Low | Low | 1 | [12 empty] | 1 | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Other | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 11, 2025 | 2025-11-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1512 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 09A. Master Data 17. B-App | mauricio.mata.villaobos@intel.com | BApps — Kelly Gerber | Data - Julie Fawdington |  | CMAP added as late scope due to SPEED BOM changes. CMAP build will intersect ITC2 instead ITC1 | 0257 |  |  |  | 12153 | Compliance Map (CMAP) |  | CMAP (Compliance Map) BApp Request to Intercept ITC2 | CMAP was identified late in WW41 as a BApp due to SPEED BOM Change impacts, build will complete in Q1 and intercept ITC2. CMAP is a SPEED Core Connect App, but not a Tower Critical App. | As part of the IAO R3 Release, SPEED items have been separated into IP and IF categories. CMAP needs to implement compliance rollup logic to handle separate IP/IF BOMs and role-based security controls to limit access. Design was finalized in collaboration with the SPEED team in WW44. CMAP has a Vendor dependency for build, which will not start until WW02, and hence will not be able to intercept integrated testing until ITC2. | Build cannot start until Jan'26 due to Vendor dependency hence will intercept ITC2 testing. There is a low risk associated with skipping ITC1. Comprehensive and robust testing will be conducted in subsequent cycles to ensure all requirements are thoroughly validated. Please note, this change is not included in E2E testing & CMAP is not a Tower Critical App | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4DF647FC-A7CC-4738-8B44-2F3C5C3A907B%7D&file=INT-CR1512%20-%20BApp%20-%20CMAP%20BApp%20Intersect%20ITC2.pptx&wdLOR=cF0A1D5C7-EAA7-47A6-A582-0470276D852D&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [12 empty] | 240 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | - CMAP is not a tower-critical app. - CMAP needs to be brought in to support the SPEED BOM changes. This will be new scope / boundary app, and an external vendor is involved with the development. - It is clear how testing needs to be done, and it is not a part of the E2E testing. - AR: Include detailed project plan into the deck - @Mata Villalobos, Mauricio | [9 empty] | Other | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1513 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Chandrakanth Elancheran | [11 empty] | Enhancement OTCE1302, Listing and Exclusion custom fields and catalog append will be descoped. | The R3 IP enhancement OTCE1302 is being removed from scope following discussions with the Intel IP GTS and OM teams. This decision was made because the listing and exclusion functionality is primarily utilized by GTS, and after reviewing legacy transaction volumes in the S4 system, the Intel team decided not to move forward with the enhancement. Specifically, they opted not to add the custom partner function to the listing field catalog or use it in the condition table for condition record maintenance. | The R3 IP enhancement OTCE1302 is being removed from scope following discussions with the Intel IP GTS and OM teams. This decision was made because the listing and exclusion functionality is primarily utilized by GTS, and after reviewing legacy transaction volumes in the S4 system, the Intel team decided not to move forward with the enhancement. Specifically, they opted not to add the custom partner function to the listing field catalog or use it in the condition table for condition record maintenance. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1513/FW%20CR1513-Enhancement%20OTCE1302%20Listing%20and%20Exclusion%20custom%20fields%20and%20catalog%20append%20will%20be%20descoped..msg?csf=1&web=1&e=aUY4hb | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2D0FA1BC-455C-42DC-ACFD-E6FDE6BDDC10%7D&file=INT%20Build%20CR0608_Descope%20object%20OTCE1302%20based%20on%20the%20alignment%20with%20Intel%20IP%20GTS%20&%20OM%20team.pptx=&action=edit&mobileredirect=true |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE1302 | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-19 | [10 empty] | Other | Tower | 2025-11-19 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-18 | 0 | < 15 Days | plakshmipadmaja@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1516 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP | Aditya Shinde | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | Cancel Call ahead reports : objects LOGE0854_IP LOGE0855_IP LOGR0856_IP | Cancel Call ahead reports : objects LOGE0854_IP, LOGE0855_IP, LOGR0856_IP | Rationale for IP capital cancelations: Original understanding was that all equipment procurement would be treated the same. Current understanding is that this does not actually span IF and IP. IP capital procurement is limited in scope and volume and will be handled via Ariba and exception/manual processes for shipment tracking and carrier call ahead. |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1516/CR%20INT-CR1516%20%20Cancel%20LOGE0854_IPLOGE0855_IPLOGR0856_IP.msg?csf=1&web=1&e=yRz5K9 |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE0854_IP, LOGE0855_IP, LOGR0856_IP | Manual Call Ahead Process |  | 3 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-18 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1517 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-18 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1518 | Cancelled | [21 empty] | LOGR0856_IP |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-18 | 0 | < 15 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1519 | New |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | marissa.mena@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | CHG117268605 (Service Now), JIRA (IAODTM-7063) | n/a | n/a | [5 empty] | SP CR External Wafer PRF - need to add Schedule Receipts + PRF in E2Open | need to Stitch schedule receipts + override lot sized qty to generate the external PRF to E2OPen for External vendors, similar to what is done for internal | From UAT, for external Suppliers, PRF is not getting stitched together with Schedule Receipts, (this is different than Internal PRF), resulting in the need to manually override the external PRF in BY to account for the missing Sched Receipts. Applies to products where Schedule Receipts are placed for dates beyond the current PO month. For situations where IP ordered ahead and those schedule receipts need to be stitched with the PRF to show the complete signal | Solution identified by PDH team ( POC Anil M.). Effort is considered low. 2 weeks max. | No | Core |  | https://jira.devtools.intel.com/browse/IAODTM-7063 |  | 3. Configuration Change |  | Yes |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 140 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1520 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Nov2025 Label Enhancements | Four (4) new label elements have been requested by new Customer (West) and Operations. Bundling together to make one request | Customer requirement request(s). |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_Nov2025%20Label%20Enhancements.pptx?d=wa83cfa99beb64578b6bfe14fd5006212&csf=1&web=1&e=0o1yGC | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 140 | > 30 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1521 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 10.1 Analytics - ALL |  | 03. FPR 06. PTP 10. Analytics 17. B-App | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  | 42901, 14474, 36739 | Resource Optimization Support Engine, DFSC CCAA (Component Cost & Analytics) ESCA (Equipment Should Cost Analytics), Project Insights Tracking Tool |  | MBEW data redesign causing deliverable delays | MBEW data redesign causing deliverable delays. The S4 views won't be completed until S21, thus preventing several objects from completing TUT and FUT for start of ITC1. | MBEW data redesign causing deliverable delays. The S4 views won't be completed until S21, thus preventing several objects from completing TUT and FUT for start of ITC1, so an exception has to be filed for the impacted objects. | There are several objects that will delivery by ITC2 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-MBEW.pptx?d=w7494088e8cec4efd9dbe11d04df3882f&csf=1&web=1&e=4079mE |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | ECA N/A - Milestone Adjustment | 5 | ECAFPRV884, ECAFPRV885, ECAPTPR4756, ECAPTPV6142, ECAPTPV6393 |  |  | 0 |  | 0 | ECAFPRV884, ECAFPRV885, ECAPTPR4756, ECAPTPV6142, ECAPTPV6393 | 5 | 5 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | - This request is to include 2 ECA objects in ITC2 due to late requirements from WIINGS to source a certain table from ECA. - Impacted boundary apps are not critical - Build is continuing, but the data won’t be flowing - AR: Add in a plan for when the ECA reports can be completed - @Singh, Indra | [9 empty] | Other | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1522 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 10.1 Analytics - ALL |  | 03. FPR 10. Analytics 17. B-App | chris.wilcox@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  | 18973 | Finance Analytics Environment SSAS |  | FPR 3rd Party (DARC) Report Exceptions | FPR 3rd Party (DARC) Report Exceptions | There are FPR 3rd Party (DARC) Report that are not going to be delivered by ITC1, so this CR is a request to delivery some reports past ITC1. | There are FPR 3rd Party (DARC) Report that are not going to be delivered by ITC1, so this CR is a request to delivery some reports past ITC1. | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-FPR-3rdPartyReport-Exceptions.pptx?d=w18270ffa59a645d5920583db0e13da38&csf=1&web=1&e=BUCJKf |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | ECA N/A - Milestone Adjustment | 100 | FPRXV408, FPRXV468, FPRXV470, FPRXV471, FPRXV472, FPRXV478, FPRXV479, FPRXV467, FPRXV487, FPRXV488, FPRXV489, FPRXV490, FPRXV491, ECAFPRV2216, ECAFPRV2215, ECAFPRV2217, ECAFPRV2218, ECAFPRV2219, ECAFPRV2220, ECAFPRV2221, ECAFPRV2358, ECAFPRV4636, ECAFPRV7025, ECAFPRV7026, ECAFPRV7027, ECAFPRV7028, ECAFPRV7029, ECAFPRV7030, ECAFPRV7031, ECAFPRV7032, ECAFPRV7034, ECAFPRV7036, ECAFPRV7033, ECAFPRV7035, ECAFPRV7037, ECAFPRV7038, ECAFPR5992, ECAFPR5994, ECAFPR5996, ECAFPR5997, ECAFPR5999, ECAFPR6000, ECAFPR6002, ECAFPR6004, ECAFPR6007, ECAFPR6009, ECAFPR6013, ECAFPR6014, ECAFPR6016, ECAFPR6021, ECAFPR6023, ECAFPR6024, ECAFPR6025, ECAFPR6037, ECAFPR6038, ECAFPR6046, ECAFPR6048, ECAFPR6054, ECAFPR6065, ECAFPR6076, ECAFPR6079, ECAFPR6081, ECAFPR6082, ECAFPR6083, ECAFPR6084, ECAFPR6085, ECAFPR6086, ECAFPR6089, ECAFPR6091, ECAFPR6093, ECAFPR6095, ECAFPR6096, ECAFPR6100, ECAFPR6101, ECAFPR6102, ECAFPR6103, ECAFPR6104, ECAFPR6107, ECAFPR6108, ECAFPR6109, ECAFPR6110, ECAFPR6167, ECAFPR6200, ECAFPR6202, ECAFPR6203, ECAFPR6728, ECAFPR6729, ECAFPR6776, ECAFPR6814, ECAFPR7008, ECAFPR7009, ECAFPR7010, ECAFPR7011, ECAFPR7012, ECAFPR7013, ECAFPR7014, ECAFPR7015, ECAFPR7059, ECAFPR7060, ECAFPRR876 |  |  | 0 | FPRXV408, FPRXV468, FPRXV470, FPRXV471, FPRXV472, FPRXV478, FPRXV479, FPRXV467, FPRXV487, FPRXV488, FPRXV489, FPRXV490, FPRXV491 | 13 | ECAFPRV2216, ECAFPRV2215, ECAFPRV2217, ECAFPRV2218, ECAFPRV2219, ECAFPRV2220, ECAFPRV2221, ECAFPRV2358, ECAFPRV4636, ECAFPRV7025, ECAFPRV7026, ECAFPRV7027, ECAFPRV7028, ECAFPRV7029, ECAFPRV7030, ECAFPRV7031, ECAFPRV7032, ECAFPRV7034, ECAFPRV7036, ECAFPRV7033, ECAFPRV7035, ECAFPRV7037, ECAFPRV7038, ECAFPR5992, ECAFPR5994, ECAFPR5996, ECAFPR5997, ECAFPR5999, ECAFPR6000, ECAFPR6002, ECAFPR6004, ECAFPR6007, ECAFPR6009, ECAFPR6013, ECAFPR6014, ECAFPR6016, ECAFPR6021, ECAFPR6023, ECAFPR6024, ECAFPR6025, ECAFPR6037, ECAFPR6038, ECAFPR6046, ECAFPR6048, ECAFPR6054, ECAFPR6065, ECAFPR6076, ECAFPR6079, ECAFPR6081, ECAFPR6082, ECAFPR6083, ECAFPR6084, ECAFPR6085, ECAFPR6086, ECAFPR6089, ECAFPR6091, ECAFPR6093, ECAFPR6095, ECAFPR6096, ECAFPR6100, ECAFPR6101, ECAFPR6102, ECAFPR6103, ECAFPR6104, ECAFPR6107, ECAFPR6108, ECAFPR6109, ECAFPR6110, ECAFPR6167, ECAFPR6200, ECAFPR6202, ECAFPR6203, ECAFPR6728, ECAFPR6729, ECAFPR6776, ECAFPR6814, ECAFPR7008, ECAFPR7009, ECAFPR7010, ECAFPR7011, ECAFPR7012, ECAFPR7013, ECAFPR7014, ECAFPR7015, ECAFPR7059, ECAFPR7060, ECAFPRR876 | 87 | 100 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | • Shane Bethune presented the FPR DARC change request, noting that reporting is behind and an exception is needed for 77 reports: 36 targeted for ITC2 and 41 for ITC3. The plan is conservative to avoid multiple exception requests. • Uzma Ahmed asked if this plan makes the business delivery feasible, given the backlog and current roadmap. Shane confirmed this is the high-confidence, feasible plan. • Sunil and Karthik discussed the need for more rigor and integrated planning across multiple teams, Deloitte, Intel APT, DARC, etc., with a focus on clear handoffs and expectations. • Shane emphasized the importance of an E2E process flow and clear expectations at handoff points, noting that turnover and unclear responsibilities have caused delays. Rebecca Verette agreed and will broker a conversation with Adam White, DARC team owner to align on expectations. • Rebecca identified three main issues: change in ownership expectations, differing quality standards, and the technical approach to mapping new data structures to legacy FAE. The team will explore whether rebuilding reports to new structures would be faster. • The group agreed to shift technical leadership of daily meetings to Karthik and team, with Rebecca’s team supporting, and to update the object tracker and MRC slide to reflect the new plan. • Uzma and Rebecca agreed to reset the current Sprint and update trackers to the new plan, as the previous Sprint was not feasible. • Decision: Approved | [9 empty] | Other | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1523 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Adding new CR Types for IF/IP in Reference master data for Sales org and Shipping conditions | There are new CR Type configs required.​ 1. Sales Organization - As per the original design, there was requirement of segregation. Later, during the design session we had with Intel Federal team we had miscommunication that no segregation was required all together for the object and following internal CRs were created for making the update.​ INT-Build-CR0599​ INT-Build-CR0600​ INT-Build-CR0601​ INT-Build-CR0602​ Post further discussion during build code review calls, it was realized that segregation is required for IF/IP as per original design. As per the mail - RE: Alignment on IF/IP segregation for Sales Organization, Distribution Channel and Division. Criteria to segregate is based on creating separate CR Types and security roles for IP/IF.​ 2. Shipping Conditions - As per recent design changes, the requirement was to add reason code-based routing.( Refer mail - RE: Signavio flow for Shipping Conditions 7/16 reply and Internal CR - INT-Build-CR0605 and changes already implemented ). But new requirements came to NOT have segregation at all as per the mail Re: Signavio flow for Shipping Conditions - 8/22 reply.​ 3. Requirement to add new role especially for Shipping Condition Requestor. This role should be restricted for only shipping condition creation and should not be shared with any other object. (Refer mail - SFUT - App access to create a record_Shipping Conditions 9/11 Reply)​ | The decision is required to properly segregate IF/IP based on CR types | This change will miss R3 ITC1, and picked in ITC2. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-Build-CR0697%20%E2%80%93%20Change%20Request%20for%20segregation.pptx?d=wea9dbbfd34bd4d4a94f2b72f64197894&csf=1&web=1&e=rU62R3 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | Low | 0 | [7 empty] | 32 |  |  |  | 32 |  | 0 | 32 | Configuration Security | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATW0591​, DATE1044​ | 2 | DATW0591​, DATE1044​ | 2 |  | 0 |  | 0 | N/A | N/A | 2026-04-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | - There was a gap in the reference data process for IF and IP separation; sales org and shipping condition information is needed. - The work will be a mix of configuration and security role setup. - Workflow won’t be tested because it is not available. | [9 empty] | Build | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-19 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1524 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 10. Analytics | 10.5 Analytics - OTC IP |  | 10. Analytics | john.chung@intel.com | Data & Analytics - Rebecca Verette | OTC IP - Teresa McNicol/Jon Benoist |  | Legal Trade and Government Affairs Analytics was recently identified as a boundary app and was updated to the tracker, by when design of R3 had completed. | n/a | n/a | [5 empty] | Include MD-Commodity fields for Legal Compliance | Include [v_cmdt_grp], [Commodity_additional_comment_text] and [commodity_keyword_txt] back into S4 build in order to consume into Commodity Detail view, in order to continue deriving commodity risk transformations needed for PO Anomaly and Compliance Risk Intelligence System. | 1. IAO is following industry best practices in terms of commodity, Intel along with Deloitte needed to identify fields that needed to be dropped and no longer be able to maintain, as per business process. 2. [v_cmdt_grp], [Commodity_additional_comment_text] and [commodity_keyword_txt] values were taken off from the Source and cannot be re-included at this phase of the program. Legal will be impacted since these fields are relevant for legal compliance metrics and will require additional exploration, forcing team to re-engineer the CRIS dashboard as well as the PO Anomaly Detection ML model to work without these data features during Q1’26, to make it for ITC2. The original compliance scope of the tool will be limited to the remaining data that doesn’t properly derive compliance risk. Limiting the PO Anomaly Detection ML model and CRIS to data restrictions can be an issue when explaining to regulatory bodies in the event a corruption event unfolds. CRIS and PO Anomaly leverage data features not necessarily following industry best practice. | Current effort is unknown. Will require enabling fields currently available in legacy, that were dropped from S4. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/INT-CRXXXXX-%2041216-%20Legal%20Trade%20and%20Government%20Affairs%20Analytics.pptx?d=wf23f20191dfd4a75b7585dc34c51a7b2&csf=1&web=1&e=xxNlie |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 140 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1527 | Cancelled | [34 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 0 | < 15 Days | venkvenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1526 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 0 | < 15 Days | venkvenkatesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1528 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | Venkat Venkatesh | [11 empty] | Cancellation of RICEFWS - DATE1643_IP, DATE1643_IF & DATE1643_CFIN as the BADI is working as expected from MDG. | BADI written in the outbound IDOC is working as expected with respect to Action Delimition and Generic Company Code and Cost Center. | Implementation of this BADI in downstream system is no more required as the code implemented in the outbound BADI is working as expected with respect to Actions Delimitation and defaulting Gen company codes and Cost Centers in the downstream systems. |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 11, 2025 | 2025-11-19 | 140 | > 30 Days | venkvenkatesh@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1529 | Cancelled |  | ERP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 11. Technology | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | 3B2 ASN changes for Anafi Customer Lot | 3B2 ASN logic to be enhanced to pull 2 new fields (ANAFI Customer Lot and ANAFI Customer SFGI) from Sales Order and pass to customer via IDoc. | New Customer (ANAFI) has requested that two new fields (ANAFI Customer Lot and ANAFI Customer SFGI) are returned to them when the 3B2 ASN is triggered. | CR part of Anafi release | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFD2CB4D8-A986-4691-84B1-0D5CE5B02B1E%7D&file=INT-CRXXXX_IF_ANAFI%203B2%20ASN%20Enhancements.pptx&wdLOR=c0D3B0EAC-865D-4828-983E-A890834E9F6C&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1530 | Approved |  | ERP | R2.X (Between Release 2 & 3) | High | 10. Analytics | 10.3 Analytics - FPR |  | 10. Analytics | rea.m.meyer@intel.com | [11 empty] | Remap transaction type for 10Q consolidated report | Source system for the consolidated GL balances included in the FAA production reports was not redirected to Group Reporting and therefore the update needs to be made. | The transaction type data fed from legacy systems (ECC & consolidation- BCS) until Sep’2025. With BCS EOL as end of Aug’25, the data flow was interrupted causing issue. It was highlighted that the new 10Q reports continued to point to BCS (instead of Group Reporting), issue would have been caught in test if the reports had pointed to Group Reporting |  | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B120F8107-BD9B-4BA4-9D0A-1DB696AA5531%7D&file=CRXXXX_FPR_R1-R2_10Q%20consolidated_remap%20transactions%20type.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTkwMjkuMjAyNDQiLCAiT1MiIDogIldpbmRvd3MiIH0%3D&CID=673960DF-2D45-4020-B176-618FA218EC33&wdLOR=c0B092CC0-B2A7-49B5-8591-17CDFCB0B138 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-02 | Approved by Shane for R2.X; email approval attached in row comments | [9 empty] | Build | Tower | 2025-12-02 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-20 | 0 | < 15 Days | opeerzada@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1531 | Approved |  | SCP | R3 (Release 3) | Very High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP 10. Analytics 15. Cutover 16. Testing | pradnya.patil@intel.com | Data & Analytics - Rebecca Verette | FTS IP - Loni Adams |  | NA | RAID ID 01417 and 02091 | NA | [5 empty] | R3 Reporting ITC Deliverables | R3 Reporting requirements with detailed func spec delivery was delayed and did not meet the program timeline for design complete. Requesting a CR to adjust the build plan per this detailed ask | Business submitted data categories/key figure related requirements based on R2 approach.. We pivoted to submit reporting requirements per guidelines. This required reengagement from Spinnaker to help drive func specs as the capabilities | Documented in the template | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Change%20ID_Tower_CR%20Deck_R3%20Reporting.pptx?d=we673ac09493147aa8259238c24d18bbc&csf=1&web=1&e=0iToBk |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Very High | 0 |  |  |  |  | 240 | 480 | 920 | [6 empty] | 1640 | 0 | N/A | Yes | ECA | 38 | ECAFTSIPR6868, ECAFTSIPR6870, ECAFTSIPR6871, ECAFTSIPR6872, ECAFTSIPR6873, ECAFTSIPV6978, ECAFTSIPV6979, ECAFTSIPV6973, ECAFTSIPV6974, ECAFTSIPV6975, ECAFTSIPV6976, ECAFTSIPV6977, ECAFTSIPV6869, ECAFTSIPV6874, ECAFTSIPV6875, ECAFTSIPV6876, ECAFTSIPV6877, ECAFTSIPV6878, ECAFTSIPV6879, ECAFTSIPV6880, ECAFTSIPV6881, ECAFTSIPV6882, ECAFTSIPV6883, ECAFTSIPV6884, ECAFTSIPV6885, ECAFTSIPV6886, ECAFTSIPV6940, ECAFTSIPV6971, ECAFTSIPV6972, ECAFTSIPV7082, ECAFTSIPV6685, ECAFTSIPV6686, ECAFTSIPV6673, ECAFTSIP6668, ECAFTSIP6688, ECAFTSIPV6689, ECAFTSIPV6664, ECAFTSIPV6667 |  |  | 0 |  | 0 | ECAFTSIPR6868, ECAFTSIPR6870, ECAFTSIPR6871, ECAFTSIPR6872, ECAFTSIPR6873, ECAFTSIPV6978, ECAFTSIPV6979, ECAFTSIPV6973, ECAFTSIPV6974, ECAFTSIPV6975, ECAFTSIPV6976, ECAFTSIPV6977, ECAFTSIPV6869, ECAFTSIPV6874, ECAFTSIPV6875, ECAFTSIPV6876, ECAFTSIPV6877, ECAFTSIPV6878, ECAFTSIPV6879, ECAFTSIPV6880, ECAFTSIPV6881, ECAFTSIPV6882, ECAFTSIPV6883, ECAFTSIPV6884, ECAFTSIPV6885, ECAFTSIPV6886, ECAFTSIPV6940, ECAFTSIPV6971, ECAFTSIPV6972, ECAFTSIPV7082, ECAFTSIPV6685, ECAFTSIPV6686, ECAFTSIPV6673, ECAFTSIP6668, ECAFTSIP6688, ECAFTSIPV6689, ECAFTSIPV6664, ECAFTSIPV6667 | 38 | 38 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-11-20 | • Pradnya Patil explained that 3 reporting requirements were delayed, and the design phase is now closed; the request has been submitted to IT. The delay was due to not meeting the original PMO timeline, prompting the need for a CR. • The business submitted reporting requirements, working closely with IT to ensure functional specs are as complete as possible. Some mockups and details remain open and will be closed in the next 2 weeks with Spinnaker. • The scope includes 28 reports, reduced from 29, covering IBP, ESP, and ERP reports. The report removed was an ERP report. The business wants prioritized delivery: some reports will be delivered for ITC2 and the rest for ITC3, with testing as reports are delivered. • UAT is a few months away; if new data needs arise, a new CR will be created. SNOP requirements are included, and the current Excel-based SVD and SNOP schema will be replaced in R3. • Sunil Narayanan provided effort estimates: 23 weeks for ECA, plus PDH effort for data from Blue Yonder PDH. 5 reports are planned for ITC2, 14 for ITC3. The SCP report was merged based on feedback. No additional cost is expected. • Uzma Ahmed clarified that true S4 reports, and Fiori app deliveries are not part of this CR; only ECA reports sourced from ERP or Blue Yonder are included. • Rebecca Verette and Uzma confirmed support for the CR from the data side. Mike Lange had no concerns, having discussed the topic previously. • Decision: Approved. | [9 empty] | Other | Tower | 2025-11-20 | 11, 2025 | 11, 2025 | 11, 2025 | 2025-11-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | Complete | Complete | No
R3 (Feb 2027) | N/A | INT-CR1532 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 09A. Master Data | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | NA | NA | NA |  | Open |  |  |  | Sprint 20 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 20 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | No | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/Approvals/RE%20Removal%20of%20Security%20Roles%20-%20Vendor%20Master.msg?csf=1&web=1&e=g9RZoW | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1535 | New |  | ERP | R2 Q4 '25 Anafi enablement | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Keith Wu | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Customer Lot Number on Sales Order Header and Item via ERO | Anafi will send the customer lot information via ERO signal. This customer lot information at header and bin information at line item needs to be updated on Sales Order. "Your reference" field in VBKD table will be used to update the lot information at both header and item. This information also needs to be updated in the UDF table as-is. | This customer lot information isneeded by downstream manufacturing and logistics system |  | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF8316FF0-0C8D-4A72-9A41-5C8CCB4A5D47%7D&file=Anafi%20-%20CR%20DECK%20(1).pptx&wdLOR=cCE21577D-1C86-489A-AD65-F3EBAD4976D3&action=edit&mobileredirect=true | New Requirement / Scope |  | O-020-100 |  | Medium |  | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-20 | 139 | > 30 Days | shisdwivedi@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1537 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | CR-817 | N/A | N/A |  |  |  |  | Tariff | Display Multiple CoX on Export Documents | Trade requirement received to ensure multiple Co"X" are displayed on the Export Documents when multiple entries are present on a Delivery Note | Tariff and trade requirement changes captured under CR-817 | No Impact to Existing Deliverables | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1537_IP_Display%20Multiple%20CoX%20on%20Export%20Documents.pptx?d=wab670fa566c044ad8dfbd768455286ae&csf=1&web=1&e=A1nYId |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 20 | [5 empty] | 18 |  |  |  |  | 0 | 18 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0353_ IP, LOGF1149_ IP, LOGF0342_IP, LOGF0345_IP, LOGF0344_IP, LOGF0343_ IP | 6 | LOGF0353_ IP, LOGF1149_ IP, LOGF0342_IP, LOGF0345_IP, LOGF0344_IP, LOGF0343_ IP | 6 |  | 0 |  | 0 | N/A | N/A | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-18 | • There was a request from the Tariff team to display the origin in CI and forms. There might be multiple countries displayed, so the team is asking for a semicolon to separate them • Minor cosmetic change, so technical work is low. Functional effort is to capture the work to re-do the FUT. | [9 empty] | Build | Tower | 2025-12-18 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1538 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP | jean-marc.lenc@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [6 empty] | 35207, 35248, 37052, 9168, 1649 | Consumption Data Management, Reltio Connected Customer Data for Salesforce, Salesforce - Enterprise Sales Cloud org (SELA1), Enterprise registration and profile management, Webquote |  | CAAS API to smart split the Address information into SAP format | Enhancement to convert the Address information ( Street Data ) sent by B-Apps into SAP format | The Interface OTCI1187 is designed with the Street field as 60 character ( Based on standard SAP structure ) for customers and vendors. But the Boundary Apps ( Profisee, Reltio and Web quote )consuming this interface has street length of more than 60 characters. Due to this constraint, to have the BP created in GTS with the full street information available in B Apps we need to have a split logic enabled at Mulesoft so that the street information from B Apps is split and transformed into the Street 1,2,3 and 4 field options we have in SAP. ??In the legacy setup, the smart split logic is enabled at the SAP end in he point-point interfaces with B Apps. With IAO, we have one standardized interface which will be used by all the B Apps for creating business partners in GTS. Hence this logic must be implemented to capture the entire street information by leveraging the existing SAP structure. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR1538%20-%20CAAS%20API%20to%20smart%20split%20the%20Address%20information%20into%20SAP%20format.pptx?d=wec0623a1b223447aa99663049e56a61c&csf=1&web=1&e=SO1OJE |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 20 | [5 empty] | 30 |  |  |  | 50 | 0 | 30 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  | OTCI1187 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCI1187 | 1 | OTCI1187 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-02-09 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-04 | - In Boundary Apps, the street data is different than what is in SAP and has more than 60 characters. - Boundary Apps cannot split on their end, so we will have to make changes in S4. - It is a small build CR | [9 empty] | Build | Tower | 2025-12-04 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-21 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1539 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP | jean-marc.lenc@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [6 empty] | 35207, 35248, 37052, 9168, 1649 | Consumption Data Management, Reltio Connected Customer Data for Salesforce, Salesforce - Enterprise Sales Cloud org (SELA1), Enterprise registration and profile management, Webquote |  | Making postal Code Optional for all Countries in GTS E4H | Convert the postal code from Mandatory for certain countries (129 countries) to optional for all countries (254 countries ). | In the current setup, the baseline configs in GTS system are synced up from MDG system which includes the countries and the relevant configs for it. As a part of interface OTCI1187, B Apps will be creating business partners directly in GTS and for certain B Apps they don’t have postal code information available in their current dataset. Due to this there is a possibility that the B Apps will not be able to create the business partners in GTS for those countries in which the postal code is mandatory thereby leading to potential issue in the B App / downstream systems due to non availability of compliance data. ?In the Legacy system, the postal code config is setup as optional for all countries. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0BB3A635-87AC-469F-BAF1-509C6EFC4DCE%7D&file=CR1539%20-%20Making%20Postal%20Code%20Optional%20for%20all%20countries%20in%20GTS..pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  |  |  |  | 0 |  |  | 60 | [9 empty] | 60 | 0 | 0 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  | 2026-02-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-04 | - This will be configuration work by the GTS functional team - Even in the US, postal code will be optional. - There are other validations to make sure that special characters or extra spaces throws an error message. | [9 empty] | Other | Tower | 2025-12-04 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-21 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1540 | New |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF | noreen.j.pedersen@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | FSCO Post-Fab WIP Projection Design Change Capturing Constraints in Frozen Horizon | WIP Projection does not reflect correct supply statement from the CBS factories, sending wrong frozen period schedules (capacity infeasible) to BY, therefore creating incorrect statement of supply across horizon. It projects an overstated number especially for wafers that have sitting inventory, BOH and WIP and have not run thru or passed thru real capacity constraint models and prevalent on 1001 TSMC wafers. FSCO not deployed yet for this site/stage (NM bump and sort). | Given that BY's output will be incorrect, Planning will need to manually override in SPAN weekly post BY publication until a solution is determined. | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR-FSCO%20WIP%20Projection-PostFab_WW472025.pptx?d=wd727afe9d5f34214b3b8fabbcf1994ec&csf=1&web=1&e=szLQLR |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-22 | 137 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1541 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 11, 2025 | 2025-11-22 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1542 | Approved |  | ERP | R3 (Release 3) |  | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Twinkle Shah | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | FPR- Cancellation of Object FPRI0378_CFIN-GL Interface - SAP API CFIN | FPR- Cancellation of Object FPRI0378_CFIN-GL Interface - SAP API CFIN | There is no business use case to post directly into CFIN via API | No | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1542/Re_%20RICEFW%20Cancellation%20-%20FPRI0378_CFIN.msg?csf=1&web=1&e=kMZ9fb | This is a cancellation request |  | 5. Cancel RICEFW / ECA / Build Object |  |  | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0378_CFIN | MJE processes by using Standard Fiori App (Verify General Journal Entry) |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-17 | [10 empty] | Other | Tower | 2025-12-17 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-25 | 0 | < 15 Days | shubhambpatil@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1543 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | Kolleru Venkatesh | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | No | [8 empty] | Payload Change for 8 prospal Interfaces | Paylaod change for Prospal Interfaces (FTSI1317,FTSI1318,FTSI1319,FTSI1320,FTSI1321,FTSI1323, FTSI0677,FTSI0830) Logic for FTSi0677 in Die inventory scneario This is needed for ITC1 | The XML payload structure which was initially defined needs to be updated to support the new structure IMConnect (MFG API Gateway) is adopting for Workstream/ShipServer/ULT communications to trigger WIP lots shipment. This will also ensure that the S/4 payload structure is forward compatible with ATMES migration. | YES | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/Approval%20Emails/EXT%20Re%20Req%20for%20CR%20Approval%20to%20Update%20XML%20Payload%20Structure%20for%20WIP%20Inventory%20Movement%20API%20Interfaces.msg?csf=1&web=1&e=rxnipk | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1543_FTS_IF_Request%20and%20Response%20Payload%20Change%20for%20prospal%20Interfaces.pptx?d=w2fc82d7e93604c679c328c315afe4a50&csf=1&web=1&e=kvau5A |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High |  | 3 |  |  | 16 | [5 empty] | 84 |  |  |  |  | 0 | 84 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI1317, FTSI1318, FTSI1319, FTSI1320, FTSI1321, FTSI1323, FTSI0677, FTSI0830, FTSE1325 | 9 | FTSI1317, FTSI1318, FTSI1319, FTSI1320, FTSI1321, FTSI1323, FTSI0677, FTSI0830, FTSE1325 | 9 |  | 0 |  | 0 |  |  | 2026-02-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-18 | • Technical changes were identified during TUT for payload for 8 different API’s into Shipserver. • Older versions of Shipservers were used as the payload signature. There was an update after the TS was written. So, the payloads were no longer compatible. • No business functionality or requirements need to be changed. Purely technical work to make API calls compatible with IM gateway. | [9 empty] | Build | Tower | 2025-12-18 | 12, 2025 | 12, 2025 | 11, 2025 | 2025-11-26 | 0 | < 15 Days | kollevenkatesh@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1544 | Cancelled |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.7 PTP - Enable Payments |  | 06. PTP | Sugandh Gupta |  | PTP - Richard Taylor |  |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC022D7D0-A697-4F84-98AF-50014EF80641%7D&file=KDD_S4%20Capital%20Downpayment.pptx&wdLOR=c4663747E-A79F-43F6-BF04-26238DC60DAA&action=edit&mobileredirect=true | [5 empty] | Console 3189 Custom program for automation of Downpayment Process S4 IP and IF | Implement enhancement using the standard SAP BAPI "BAPI_ACC_DOCUMENT_POST"in the PO save routine so that when the Down Payment Indicator is activated and the PO is saved, the system automatically collects the necessary purchase order data and calls the appropriate standard SAP BAPI to generate a down payment request, equivalent to executing transaction F-47. This process ensures the down payment request is created without manual intervention | Custom enhancement to automate the creation of down payment requests for ZCAP Purchase order types, equivalent to executing transaction F-47. | No | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/Change%20Request%20-%20New%20Objects/INT-CR1544_PTP_IP_IF.pptx?d=w7d132e51eef3461287df617d14e90c3c&csf=1&web=1&e=tAaazY |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  | 3189 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael to be cancelled as the business decided not to move forward with it | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-01 | 0 | < 15 Days | suggupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1545 | New |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP | Aditya Shinde | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | Update file format from Comma Delimited to Pipe delimited for object LOGE0750_IF/IP | Update file format from Comma Delimited to Pipe delimited for object LOGE)750_IF/IP | comma delimiter causes an issue when used as name separator within a cell leading to distortion of columns and database field values. In order to avoid this issues, it was recommended to go change the separator to Pipe rather than comma. |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-01 | 128 | > 30 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1547 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP 11. Technology | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA |  |  | 11565 | My Samples ( Future of Samples) |  | Special Instruction Printing in CI | Logic to print CI needs to be modified based on the new logic. | Per legal guidance, need to apply distinct special instructions for sample shipments—one for free-of-charge (FOC) orders and another for loan-fee samples.​ ​ | It will be delivered in ITC2. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/CR - OTC IP Logistics/INT-CRXXXX_IP_Item Level Special Instruction for CI .pptx?d=wd9981a6038bf44e1bb77f258c321dbe5&csf=1&web=1&e=lbrBY6&xsdata=MDV8MDJ8ZGVicmFkYXNAZGVsb2l0dGUuY29tfGQxMmZkZTI3ZTk5ZTRmOThiNjQ1MDhkZTMxMTY1MmMxfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2MzkwMDIxNjk0NjgwNTUzMDV8VW5rbm93bnxUV0ZwYkdac2IzZDhleUpGYlhCMGVVMWhjR2tpT25SeWRXVXNJbFlpT2lJd0xqQXVNREF3TUNJc0lsQWlPaUpYYVc0ek1pSXNJa0ZPSWpvaVRXRnBiQ0lzSWxkVUlqb3lmUT09fDB8fHw%3d&sdata=dm9rYjNmRjlSVWNkYW83OEMyLzNKZU51OGhrS0tJWVhlMlBYTXBkM3NEbz0%3d |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | Medium | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | S4 | 1 | LOGE1713 | 3193 | LOGE1713 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-18 | • This new enhancement will be to push item-level shipping instructions and commercial invoice instructions into the CI and PL. • This was identified during MySample orders testing. • This text needs to be added and stored at the line-item level. This is a legal requirement to have special instructions for different order types. • The as-is process today has the special instructions at the header-level. But in SAP, it is needed at the line-item level as it is the more efficient method. • TUT and FUT can be done together. | [9 empty] | Other | Tower | 2025-12-18 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1548 | Approved |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | Sherry Y Green | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA |  |  |  |  | WIINGS | – Wrapper program for Inbound interface from KPI to SAP | A custom wrapper program should be developed to handle multiple inbound interface structures from Kommand Autostore (Bapp) to SAP EWM. This wrapper will process all three planned interfaces for the GXO Huffman Warehouse—Pick Confirmation, Putaway Confirmation, and Inventory Adjustments—through a single endpoint, despite their differing data structures. | Inventory Adjustments has different structure compared Warehouse task confirmation, even though the operations in the host system—SAP EWM—are distinct and handled separately. We need to have the wrapper program to handle any new interface addition for the Inbound to SAP EWM from Kommand AS | ITC1 Readiness | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/INT-CR1548-%20Wrapper%20program%20for%20Inbound%20interface.pptx?d=wa5a4e36928f4494bbc7d9a313d45c04a&csf=1&web=1&e=DPQp3m | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  | Low | Medium | 1 | 63 | 4400 | [6 empty] | 63 |  |  |  |  | 0 | 63 | Tech - Middleware Tech - S/4 | Yes | S4 | 1 | LOGI1708 | 3192 | LOGI1708 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI1626, LOGI1594, LOGI1593 | 3 | LOGI1626, LOGI1594, LOGI1593 | 3 |  | 0 |  | 0 |  |  | 2026-02-20 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-04 | - During KPI integration testing, the team realized that they cannot perform the 3 step process to capture the specific worker information if inventory is removed or adjusted. - The recommended solution was to create a wrapper program to drive the required workflows. - AR: Work with tech team to define tradeoffs - @Ramireddi, Neetu @Mohan, Vasanth @Strathman, Susan | [9 empty] | Other | Tower | 2025-12-04 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-02 | 0 | < 15 Days | rshankarshastry@deloitte.com |  | No | CR Complete | Complete |  | Complete | Yes
|  | INT-CR1549 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes |  | Junior Milan |  |  |  | INT-CR0772 | RAID#2596 | [6 empty] | Milestone change for CR 772 | Customer ASN (LOGI0612_IF) needs to incorporate additional attributes required by IP as a customer. However some of the additional attributes is not yet freezed hence delay in meeting ITC1 timelines. It will be ready in ITC2. In ITC1, Inbound Delivery and GR will be done manually. | Post R3 release, IP will be treated as external customer to IF. IP requires Advanced Shipping notification to be sent when sales order is complete. The signal is critical for IP to close purchase order, allow payment and track inventory in-transit. IP needs specific attributes such as: secondary lot number, manufacturing dates, countries of diffusion/WLA/assembly, etc to be included into ASN to keep IP inventory records up to date. | ready in ITC2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA749C3C3-91D0-4D8C-9286-33073AB16B17%7D&file=INT-CR1549-Customer%20ASN%20Milestone%20Adjustment.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High | 80 | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-02 | 127 | > 30 Days | preetiwari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1550 | New | 4/7: Followed up with Sekhar/Venkata | ERP | R5 (Release 5) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 05. OTC IP 06. PTP 08. FTS IP 09A. Master Data 13. Security 15. Cutover 16. Testing | Shilpa Chandra | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Sub Bailment of materials by customer | Bailment of materials and products by customers to Intel Products. | New Requirement: Introduction of customer bailment process similar to Intel Foundry IFS | Required for R4 | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-02 | 127 | > 30 Days | akindore@deloitte.com |  | No |  | No Objects |  | N/A | No | Yes
|  | INT-CR1551 | New | 4/7: Work with Adam | SCP | R5 (Release 5) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 07. FTS IF 08. FTS IP 15. Cutover 16. Testing 17. B-App | Shilpa Chandra | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Engineering Planning | Engineering Planning; Automation of procurement proposals (PR, STR and Production Orders) from planning system BY for engineering related orders | New Requirement: Introduction of formal planning process in upstream planning engine BY for engineering related products and Integrating with ERP and other boundary Apps. | Required for R4 | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-02 | 127 | > 30 Days | akindore@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1552 | New | 4/7: Followed up with Sekhar/Venkata | ERP | R5 (Release 5) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 05. OTC IP 06. PTP 08. FTS IP 11. Technology 15. Cutover 16. Testing 17. B-App | Kim Holloway | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | B2B Design Standardization - Landscape Design (OSATs and SMH) | B2B Design: Standardization of PIP messages like 7B1 between ERP and OSATs including Intel Foundry | New Requirement: Standardization of PIP messages like 7B1 between ERP and External OSATs, and ensuring consistent communication design for both External OSATs and Intel Foundry. | Required for R5 | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-02 | 127 | > 30 Days | akindore@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1553 | Approved |  | ERP | R3 (Release 3) |  | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP 11. Technology | Pramod Kalli Srinivas | [11 empty] | Inbound Interface to Update Original Flag Interface from SFDC to S4. | Inbound Interface to Update Original Flag Interface from SFDC to S4. | Current API is synchronous API and when we go with the payload split functionality then API will be Asynchronous because SFDC will send the response once they processed all the data for RMA and to receive the response from SFDC we will require new API because based on the response we are updating original flag indicator which is in custom table in S4 system. For new API to receive the response from SFDC we will be required new RICEFW. Also, Once data shared with SFDC original flag needs to be updated as I - Interim. This values needs to be added in Original Flag values. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC84EB217-32E5-4308-A252-0BA64BB5901A%7D&file=INT-CR1553%20-%20Inbound%20Interface%20to%20Update%20Original%20Flag%20Interface%20from%20SFDC%20to%20S4.pptx&wdLOR=cA94CF074-E33D-4DA9-AAA6-D4E3AB0F711D&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | OTCI1720 | 3197 | OTCI1720 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-08 | • This request is for a new inbound interface into S4. • Related to CR1421. Once all of the split payloads are sent to Salesforce, a new inbound interface will bring the results back to S4. | [9 empty] | Other | Tower | 2026-01-08 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-02 | 0 | < 15 Days | sbharathalkude@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1555 | New |  | SCP | R3 (Release 3) |  | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  | 07. FTS IF | Jim Gwin | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Cycle over Cycle for S&OE (Weekly Forecast) | Request to capture and display S&OE published consensus forecast and Final Customer Forecast within CDP weekly | As part of R2, Relevant metrics for customer forecast and consensus forecast are stored into PDH and EC for use in demand planninc accuracy calculations and metrics for reporting. The consensus forecast extract accounts for planner and executive overrides, but they are not identified independently. This request adds the storage of the overrides independently so that data can be compared and evaluated in the future more accurately | Already committed for R3; requested to be pulled into R2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared Documents/Intel Foundry R3 Program Mgmt/Program Integration/Change Control/SCP-CR.xxx2 Capture Weekly forecast within CDP.pptx?d=w72ae510b29c94d5bbaa6d8204f7218fe&csf=1&web=1&e=ZphmSQ |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-02 | 127 | > 30 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1554 | Approved |  | SCP | R3 (Release 3) |  | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  | 07. FTS IF | Jim Gwin | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Store Planner & Executive Override | Request to store planner override and executive override to PDH and ECA for use in Demand Planning Accuracy and BIAS metric calculations | As part of R2, Relevant metrics for customer forecast and consensus forecast are stored into PDH and EC for use in demand planning accuracy calculations and metrics for reporting. The consensus forecast extract accounts for planner and executive overrides, but they are not identified independently. This request adds the storage of the overrides independently so that data can be compared and evaluated in the future more accurately | Needed for Release 3 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/Intel%20Foundry%20R3%20Program%20Mgmt/Program%20Integration/Change%20Control/SCP-CR.1554%20Store%20Planner%20and%20Executive%20Overrides.pptx?d=waa99a994ec5249a79c7342c8d303d4c0&csf=1&web=1&e=Nbf6io |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-11 | - There are 2 metrics that were intended to be part of the requirements but were missed during the R2 testing cycle. - PDH team included work in R3, but CDP and ECA did not. The 2 teams are confirmed to be able to deliver the extra work with no impacts to schedule / deliverables. - Final consensus forecast will be stored, and executive and manual override metrics will be tracked  forecast value add - AR: Add in objects and schedule details into the Slide 3 template - @Jim Gwin | [9 empty] | Build | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-02 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects | Complete | Complete | No
|  | INT-CR1558 | New |  | ERP | R5+ (Post Release 5) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 07. FTS IF 08. FTS IP 11. Technology 12. Infrastructure 15. Cutover 16. Testing 17. B-App | Shilpa Chandra | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Lot Geneology | Interfacing ERP system with Quality and Lot Geneology systems for Traceability in place CATTS/TCA landscape | Interfacing ERP system with Quality and Lot Geneology systems for Traceability in place CATTS/TCA landscape | Needed for R5. | No | Core |  |  |  | 11. Boundary Apps-related Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-03 | 126 | > 30 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1559 | New |  | SCP | R5+ (Post Release 5) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 07. FTS IF 08. FTS IP 15. Cutover 16. Testing 17. B-App | Shilpa Chandra | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Centralized materials planning (MAPPS EOL) | Centralize all materials planning including Substrates in BY (MAPPS EOL) | Centralize all materials planning including Substrates in BY (MAPPS EOL) |  | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-03 | 126 | > 30 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No | Yes
|  | INT-CR1560 | New |  | ERP | R5+ (Post Release 5) | Medium | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 07. FTS IF 08. FTS IP 15. Cutover 16. Testing 17. B-App | joaquim.guedes@intel.com | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Improve TPT for boxed CPU process | Improve TPT for boxed CPU process | Improve TPT for boxed CPU process |  | No |  |  |  |  | 1b. Solution Design |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-03 | 126 | > 30 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No | Yes
|  | INT-CR1561 | Cancelled | Anna to confirm with Lilibeth that it is not a duplicate of CR1028 | ERP | R5 (Release 5) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 02. E2E Process Integration 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 13. Security 15. Cutover 16. Testing 17. B-App | joaquim.guedes@intel.com | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | [7 empty] | Tariffs | Enhancing planning and execution processes to mitigate tariff impacts while considering COA, COF etc. | Enhancing planning and execution processes to mitigate tariff impacts while considering COA, COF etc. |  | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that there is not need to create a new CR to capture BApps effort for Tariffs. It can be combined with CR1028 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-03 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1568 | Cancelled |  | ERP | [22 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-04 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1562 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) R5 (Release 5) | High | 07. FTS IF | 7.1 FTS IF - ALL |  | 08. FTS IP | matt.katzorke@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | 02433 | 02433 | 02433 | [5 empty] | Build Instructions for WLA (Component Level) R4/R5 | CBS needs to provide Build Instructions for WLA. Need to provide component level instruction details by IP FTS. | Detail Designs found the gap | R4 /R5 CR | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1562_FTS-IF_Build%20InstructionGrouping.pptx?d=w18b09de49214400d86d13bf0422aada3&csf=1&web=1&e=0bH9dI |  | 1b. Solution Design |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-04 | 125 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1563 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP 09B. Data Migration | Akshay Awasthi | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Additional logic for Credit Case Conversion in case of HLP (reference RICEFW OTCC0803) | Additional logic for Credit case conversion (in case of HLP) - Check the Account Group in KNA1 table, if it is ZSPY then look at the search term field- If Search term field – is ‘IF HLP’ then there should be two credit cases created, one on Credit Segment 0000-Main Segment, and another on IFCC- IF Credit Segment. If Search term field – is ‘IP HLP’ then there should be two credit cases created, one on Credit Segment 0000-Main Segment, and another on IPCC- IP Credit Segment. If Search term field – is ‘Shared HLP’ then there should be three credit cases created, one on Credit Segment 0000-Main Segment, second on IFCC- IF Credit Segment and third on IPCC- IP Credit Segment. | For HLP in current system (ECC) there is only one credit segment(WWCC), however in CFIN each HLP will have a minimum of 2 and maximum 3 credit segments. (IF, IP and Main) As per current credit case conversion design, each HLP would have converted only one credit case on the Main segment. During FUT review for BP credit segment conversion a concern was raised that, for shared HLP the rule set is to split the credit limit as 50-50 amongst IP and IF segment. Practically the split might vary from customer to customer (eg 70-30, 40-60,etc). Creating a credit case on each segment would allow business to adjust this credit limit and will also help in keeping a better audit trail for limit assigned to each segment on BP. | MC2/ ITC2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1563%20-%20Open%20Credit%20case%20conversion%20additional%20logic.pptx?d=wcfd91df6b2784689aa0234e5d3cc9adb&csf=1&web=1&e=XjgHXU |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Low | 0 | [8 empty] | 38 |  |  |  |  | 0 | 38 | Data Migration | No |  | 0 | N/A |  | OTCC0803 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCC0803 | 1 | OTCC0803 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-04 | - For high-level payers, additional logic is needed as there is no 1:1 mapping in CFIN for HLP and credit segment. - Manual work will be done to validate and adjust values in the recon file during MC1 prior to loading in S4. | [9 empty] | Build | Tower | 2025-12-04 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-04 | 0 | < 15 Days | aksawasthi@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1569 | Cancelled |  | ERP | R3 (Release 3) | High | 06. PTP | 6.3 PTP - EWM | Yes | 06. PTP 07. FTS IF 17. B-App | susan.strathman@intel.com | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | WIINGs ITC1 Conversion where less than 100% | EWM: Bins and Inventory conversion templates will be less than 100% of total Data PM: Equipment Master Template will contain a sample set of data for sub-entity due to lack of single SOR for Sub-entity data in MARS/Xeus ECM: A sample set of BOM data will be supplied for Parts Clean BOMs as the data was not clean enough for initial load | EWM: WIINGs to SAP migration from 1:Many to 1:1 is a physical warehouse task requiring new bins/separators to be ordered and inventory to be physically moved. OR and AZ are in process and will be complete in time for ITC2. The Aloha stockroom migration planned for January from xx to yy has been pushed out a couple of times. Estimate is 6 wks once it begins – monitoring for ITC2. PM: Establishing a clean list of sub-entities for conversion in time for ITC2 while we continue define R/R and system of record on going. ECM: Clean up required, scrubbed boms expected by end of December. | Expect most of the data (with exception of Aloha whse move) to be complete by ITC2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1569%20for%20WIINGS%20Data%20ITC1.pptx?d=wc2acede366c44a08a87f5e082ef07eb2&csf=1&web=1&e=8SmJTX |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Cancelled as MC1 data is not expected to be fully complete | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-04 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1570 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | Rose Pham | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [6 empty] | 64229, 64228 | Readsoft - Process Director Accounts Payable IP, Readsoft - Process Director Accounts Payable IF |  | Intel BRF+ - Create Function Modules in S/4HANA | To support BRF+ configuration, we need to create the following function modules and related components in S/4HANA: ​ ​ YFI_WHT_DA_CTRL - Function Group - Center point for the Withholding Tax Automation ​ YFI_WHT_AMNT_TRANSLATE - Function Module - Translate the amount from foreign currency to local currency ​ YFI_WHT_GET_MDM_MATKL_PARAM - Function Module - Get Material group code ​ YFI_WHT_REGEX_MATCH - Function Module - BRF Regular Expression Matching ​ YFI_WHT_GET_DATA - Function Module - Information source type modules ​ YFI_WHT_BRF_COMM - Custom Table - BRF Communication Structure ​ YFI_WHT_GET_DELIVERY_ADDR - Function Module - Get the Address details for Ship-to country ​ REEXC_WHTAX_TYPE_FI_VEND - SAP Table? - FI Withholding Tax Type Vendor Master Record (LFBW) ​ YMDMT_MATL_GROUP (renamed ZTITR_MATL_GROUP) - Custom Table - Material group data from MDM interface | "To support BRF+ configuration, we need to create the following function modules and related components in S/4HANA: YFI_WHT_DA_CTRL - Function Group - Center point for the Withholding Tax Automation YFI_WHT_AMNT_TRANSLATE - Function Module - Translate the amount from foreign currency to local currency YFI_WHT_GET_MDM_MATKL_PARAM - Function Module - Get Material group code YFI_WHT_REGEX_MATCH - Function Module - BRF Regular Expression Matching YFI_WHT_GET_DATA - Function Module - Information source type modules YFI_WHT_BRF_COMM - Custom Table - BRF Communication Structure YFI_WHT_GET_DELIVERY_ADDR - Function Module - Get the Address details for Ship-to country REEXC_WHTAX_TYPE_FI_VEND - SAP Table? - FI Withholding Tax Type Vendor Master Record (LFBW) YMDMT_MATL_GROUP (renamed ZTITR_MATL_GROUP) - Custom Table - Material group data from MDM interface" |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1570_Intel%20BRF%20-%20Create%20Function%20Modules%20in%20S-4HANA.pptx?d=wac9c3ac36acc44a494c7d82a20ae1c2b&csf=1&web=1&e=c6sVFh |  | 2. New RICEFW / ECA / Build Object |  | No | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 4 | FPRE1723_IP, FPRE1723_IF, FPRE1722_IP, FPRE1722_IF | 3199 | FPRE1723_IP, FPRE1723_IF, FPRE1722_IP, FPRE1722_IF | 4 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-18 | • This is a legal requirement related to withholding tax. • The original design was to use standard function modules. When it was being done in SAP, the function module turned out to be customized according to the scenarios. • FPR owns the function modules, but it is the ReadSoft team who consumes the data to do the withholding tax. Withholding tax is FPR function, but ReadSoft is PTP app. • This process cannot be done manually. • Function modules can be tested as soon as one of them is developed. Therefore, TS/TUT and FUT can be done in parallel. | [9 empty] | Other | Tower | 2025-12-18 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-06 | 0 | < 15 Days | ropham@deloitte.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1571 | Rejected |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF 11. Technology 17. B-App | sri.harisha.sai.kasturi@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | [8 empty] | WIINGS | Automate creation of the Repair PM Order for IMR | Automate creation of the Repair PM Order at IMR whenever:​ Factory technician completes Step 1 return in SIMOM​, Or EWM receives the faulty part at WH​ This removes the need for IMR to manually trigger PM order creation.​ | In the As-Is process, when a repair PO is created by a factory (IF), the system auto-creates shop orders in SAP ME.IMR materials coordinator validates PO against Shop order and confirm receipt. ​ The new E2E design introduces a manual “Create Repair Order” step in SIMOM/SAP PM for IMR, triggered every time a faulty part is sent from a factory site. This would trigger an interface to SAP ME for shop order creation.​ IMR would now need to perform significant manual data entry, which they have no bandwidth to support order volume(Avg. 100’s per week per lab for US labs and 10X more for Kulim labs – see back-up for summary table) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1571%20-%20Automation%20of%20repair%20order%20creation%20for%20IMR.pptx?d=w47ec0963687e4cd0aa1638771401711a&csf=1&web=1&e=ODoxym |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2026-01-22 |  |  |  | 2026-01-23 | • Description: Automate creation of the Repair PM Order at IMR whenever: Factory technician completes Step 1 return in SIMOM, Or EWM receives the faulty part at WH This removes the need for IMR to manually trigger PM order creation. • Rationale: In the As-Is process, when a repair PO is created by a factory (IF), the system auto-creates shop orders in SAP ME.IMR materials coordinator validates PO against Shop order and confirm receipt. The new E2E design introduces a manual “Create Repair Order” step in SIMOM/SAP PM for IMR, triggered every time a faulty part is sent from a factory site. This would trigger an interface to SAP ME for shop order creation. IMR would now need to perform significant manual data entry, which they have no bandwidth to support order volume(Avg. 100’s per week per lab for US labs and 10X more for Kulim labs – see back-up for summary table) • Impact: Not provided in CR Log • Discussion - o Context: Automate creation of PM repair orders when factory technicians initiate returns; currently duplicate manual entry at IMR creates data quality risk. o Constraints: Proposed FUT 3/16 is late against sprint timelines; program capacity tight. Manual fallback possible but high volume (hundreds/week) and quality concerns. No boundary app changes (existing SAPME interface). o Debate: Value acknowledged; timing risk flagged; suggestions included R4, post go live/hypercare, or if build finishes in Sprint 22–23 then allow FUT alongside ITC1 as a managed risk. • AR - Cari Shim - Align with leadership on a small window policy (if any) for late pre go live automations vs. hypercare track. • AR - Anand Jha - Review plan to allow FUT concurrent with ITC1 (if build completes in Sprint 22/23) and define guardrails. • AR - Susan Stratham - Quantify data quality risks and operational impact (US labs & Kulim) if IMR automation is deferred; propose R3 manual + hypercare automation option. • AR - Paul Whitlock - Partner with MDG leads to determine who owns material master maintenance post go live (org/roles), given automation timing. • Decision - Not approved - Treat as late if needed; explore alternate timing (post go live/hypercare) or completing build now with FUT concurrent with ITC1 if safe. Team to take offline to size options. | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-06 | 0 | < 15 Days | hweller@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1572 | New |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Naved Naved | [11 empty] | Delta Indicator update to restrict the duplicate records to be sent to SF | Introduction of Delta Indicator at the GR subline level and original flag indicator at the OTC CRT and Item level table which will enable to the returns order batch job to pick only RMAs where there is any update to sublines | Returns Order Status Interface Batch job should send only those RMAs to Salesforce that are either new or have been updated. RMAs with sublines without any changes should not be sent to SF, which will help prevent duplicate entries, optimize the payload size, and improve overall system efficiency. To fulfill this requirement, the EWM team will implement a Delta Indicator at the EWM Subline level. This indicator will enable the Returns Order batch job to identify and select only the new or updated RMAs to be sent to Salesforce. Original Flag indicator also needs to be updated in S4 tables: ZTOTC_RETURN_CRT and ZTOTC_RETURN_ITM once any changes happens during the Inbound process. This process starts after user click on confirm button. Impacted FS: LOGI1261 - Resolution received from SF will update the Delta Indicator at subline level, so they get eligible to be picked by Returns Order batch job in next run to update SF LOGE1314-Returns order Status Interface object to pick the RMA sublines for which CMR is generated and change the status to “Credited” at the EWM subline level LOGE1298- Returns order Status Interface object to pick the Unexpected RMA sublines for which the price details are fetched from SF LOGE1266 - In case of GR reversal and Inventory adjustments, when sublines are updated, status needs to be sent to SF. LOGE1311- In case of Virtual warehouse, subline status once updated, status needs to be sent to SF. LOGI1300- In case of CQNR interface, subline status once updated, status needs to be sent to SF. |  | No | Core |  | https://amedeloitte-my.sharepoint.com/personal/nanaved_deloitte_com/Documents/INT-BUILD-Delta%20Indicator.pptx?web=1 | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High | 145 | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-08 | 121 | > 30 Days | prasshinde@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1574 | Rejected |  | ERP | R3 (Release 3) |  | 06. PTP | 6.1 PTP - ALL |  | 06. PTP 11. Technology | Prabhakar Vemuri | PTP — Kenneth Salazar | [10 empty] | PTPI0817_IF ¦ Purchasing Services Fiori Catalog - Dynamic URL's | The current requirement is to maintain different URLs for the FIORI tile depending on the environment—for example, the URL for a single FIORI tile will vary between the Dev, QA, and PRD systems. Additionally, several more URLs that need to be incorporated alongside the existing development. | Fiori tiles will be created as part of a Fiori catalog that link to several internal and external purchasing and payment tools for Indirect procurement. This tile will serve as a single-entry point for all shoppers, especially given that these tools are available to the entire Intel employee population. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7b180BF301-EE49-4E0B-B49C-4C28C04A6264%7d&file=INT-CR1574.pptx&wdLOR=cCADD1F8A-5FC8-46CB-8B86-72EAD1E6A305&action=edit&mobileredirect=true&xsdata=MDV8MDJ8YW5udGFtQGRlbG9pdHRlLmNvbXxjNGI0NjI5ODU4N2E0ZTM2OTMxNDA4ZGUzODJhMmE3ZHwzNmRhNDVmMWRkMmM0ZDFmYWYxMzVhYmU0NmI5OTkyMXwwfDB8NjM5MDA5OTUxMTA2MzQxMjc2fFVua25vd258VFdGcGJHWnNiM2Q4ZXlKRmJYQjBlVTFoY0draU9uUnlkV1VzSWxZaU9pSXdMakF1TURBd01DSXNJbEFpT2lKWGFXNHpNaUlzSWtGT0lqb2lUV0ZwYkNJc0lsZFVJam95ZlE9PXwwfHx8&sdata=Q0xwZ0dDeFlxem1pQzVjb3A4ZDdEZlY0b1FTaHp5ZEZGTlpkajMvS1NFcz0%3d |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | High | High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 07. OSC/CL rejected - no further analysis (end status) | No | No | 2025-12-11 | - This change is related to purchasing services and to enable dynamic URL’s so that user experience will remain consistent. - AR: Team to work with architects to re-design SAP page for consistent design - @Vargas Lepiz, Jose @Shim, Cari H | [9 empty] | Build | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-08 | 0 | < 15 Days | yswaddeshpande@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1573 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-08 | 0 | < 15 Days | preetiwari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1575 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data 09B. Data Migration | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | Extension of Material Master Data and BOMs to Manufacturing Plants | As per the current design Material Master Data is only getting extended to Warehouse Plants and in order to support the conversion of BOM extension to Manufacturing Location is also required | This is an additional requirement |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1575.pptx?d=we385efac053a48d5ad1bb2e7771b4287&csf=1&web=1&e=rGJQgr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 40 | [7 empty] | 70 |  |  | 0 | 70 | Data Migration | No |  | 0 | N/A |  | DATC0213, DATC0075_IP, DATC0070_IP | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0070_IP, DATC0071_IP​, DATC0072_IP, DATC0075_IP, DATC0213, DATC1237_IF | 6 | DATC0070_IP, DATC0071_IP​, DATC0072_IP, DATC0075_IP, DATC0213, DATC1237_IF | 6 |  | 0 |  | 0 | N/A | N/A | 2026-04-10 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-11 | - There are some manufacturing plants that do not exist in ECC. - This change is to automate extension of Material Master Data and BOM to SPEED manufacturing plants. - Mock Cutover steps can be re-sequenced to build a buffer for these objects. | [9 empty] | Build | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-08 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
|  | INT-CR1577 | Cancelled |  | ERP | R2.X (Between Release 2 & 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 11. Technology 13. Security | gary.nilsen@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/Approvals/EXT%20RE%20INT-CR1577%20-%20New%20FPR%20CR%20for%20Operate%20R12.msg?csf=1&web=1&e=LeP9F1 | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/13.%20Security/01%20SAP%20Application%20Security/05.%20Security%20Champions/FPR/R3%20Change%20Request%20Info/Change%20Request%20-%20FPR%20Security%20-%20December%202025%20R1-R2%20Role%20Changes.pptx?d=w292da24833a24f8398bc24b203a315ef&csf=1&web=1&e=R961vP | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-08 | 0 | < 15 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1578 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 10. Analytics | adam.m.grudzien@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | INT-Build-CR1088 | N/A | N/A | [5 empty] | Add new attributes to ECA GLAP view to supporting FPnA & Legal analytical reporting | Addition of new attributes are requested to GLAP view in ECA. The GLAP view in ECA was designed to support GLAP report in DARC Hermes Additional attributes to same GLAP report are requested to support reporting capability in FPnA and Legal IT areas. In legacy environment, the reporting to FPnA and Legal IT are support via HANA query being pulled into DARC reporting (for FPnA) and Legal IT Analytic dashboard. | The GLAP view was built supporting GLAP report. Downstream reporting requirements were identified later for which this CR has been created. | This CR will be for ITC3 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC278F790-6525-4438-A82F-B3B87B53BCC1%7D&file=INT-Build-CR1088%20Add%20attributes%20to%20GLAP%20view.pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 | [9 empty] | 65 |  |  |  | 0 | 65 | ECA | No | ECA | 0 | N/A |  |  | 0 | FPRXV164 | 1 | ECAFPRV7064, ECAFPRV7075 | 2 | 3 |  | 0 |  | 0 | 0 | FPRXV164 | 1 |  | 0 | FPRXV164 | 1 |  | 0 |  |  | 2026-05-29 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 | Straight to Reporting CR Meeting |  |  | 2026-01-23 | • Description: Addition of new attributes are requested to GLAP view in ECA. The GLAP view in ECA was designed to support GLAP report in DARC Hermes. Additional attributes to same GLAP report are requested to support reporting capability in FPnA and Legal IT areas. In legacy environment, the reporting to FPnA and Legal IT are support via HANA query being pulled into DARC reporting (for FPnA) and Legal IT Analytic dashboard. • Rational: The GLAP view was built supporting GLAP report. Downstream reporting requirements were identified later for which this CR has been created. • Impact to Schedule: This CR will be for ITC3 • Discussion: o These reports are evolutions of previous reconciliation reports from earlier releases (R1 and R2) but now include more source systems and require logic rebuilding. A key change is moving away from Power BI as the interface due to its ineffectiveness for this use case. o The reports aim to verify completeness and accuracy of transactions between source systems (AIA, IP, ECC) and CFIN and include summary and detailed unmatched transaction reports for research and resolution. o There are five main reconciliation reports planned, covering balance and line item comparisons for financial and management accounting postings. o These reports are complex and require early development to allow for iterative logic refinement and testing. o The effort is estimated at approximately $105,000, involving both Deloitte Analytics and SAP functional teams. o Testing is scheduled for ITC3 when sufficient data is available, with manual workarounds employed in ITC1 and ITC2 . o The complexity is mitigated somewhat by comparing S4 to S4 data rather than ECC to S4, reducing mapping and logic challenges. o The team aims to finalize specifications by mid-December to allow adequate development and testing time before ITC3, which is expected to start around late April 2026. o Discussions are ongoing regarding the front-end tool to replace Power BI, with a decision expected within a week. • Decision: Approved | [5 empty] | Build | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No | Dev Not Started | No Objects |  | In Progress | Yes
R2 (Hypercare) | R2 Hypercare | INT-CR1579 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 09A. Master Data | Lexey.Sbriglia@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | E2E benchmarks and impact not looked at in this detail and impact was assumed low. | N/A | N/A | [5 empty] | Add Master Data Snapshot | Deploy supplementary PDH-to-BY IBP master data snapshot on Monday morning at 5:00 AM PST during Inputs week, ensuring data availability before business hours to support timely file generation by Supply Chain Optimization Engineers for all BY IBP input processes. | This new enhancement addresses critical misalignment in product configurations between front-end and back-end supply planning systems. The current gap necessitated 300+ manual solver adjustments in the previous cycle to reconcile product setup and BOM discrepancies across platforms. These manual adjustments and product set up errors are part of the cause to missed benchmarks and the risk creating a decrease in forecast reliability. | TBD, IT still working on the assessment and tech estimation. Asked to fill this out already. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/Change%20ID_IP-FTS_CR%20Deck_AddMasterDataSnapshot.pptx?d=wafa4faf2e5584662ab15626238c600c6&csf=1&web=1&e=pYAIQt |  | 3. Configuration Change |  | Yes |  | Medium | 0 |  |  |  |  | 120 | 120 | [7 empty] | 240 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-16 | This gives the team another week to get the safety stock together. PDH and BY are aligned, and OneMPS is reviewing. | [9 empty] | Other | Tower | 2025-12-16 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1580 | New |  | SCP | R3 (Release 3) | High | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  | 07. FTS IF | Scott Palmer | FTS (SCP IF) — John Heiney |  |  |  | 3214 | [6 empty] | IF/DP Scenario Planning rework based on feedback from user demo. | IF/DP Scenario Planning rework based on feedback from user demo. | Based on user feedback from Scenario Planning demo for FUT, one feature will need design and development change. This is critical for the functionality to work and Scenario Planning itself is a core capability. The rework is expected through 01/16, but with no impact to MC1 and ITC1. | Yes - WW3 | No | Core |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-09 | 120 | > 30 Days | naren.mangtani@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1583 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting |  | 03. FPR | Pramod Kulkarni | [11 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/RAR_INT-CR1583%20FPRE0697%20Assign%20Additional%20Dimension%20for%20RAR%20Postings.pptx?d=wf39c3cbda1244156859efe0976ff0fff&csf=1&web=1&e=9EH8Rb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Rafael and Pramod to be cancelled as it is no longer needed. | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-09 | 0 | < 15 Days | ppranavyogesh@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1581 | New |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP | randall.paniagua.espinoza@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | To update design for the NSO fiori app based on the business scope variation | To implement design and layout updates for the upcoming NSO Fiori release in line with the latest requirements, including updating validation logic for ship reason based on the business process used for NSO delivery creation; enhancing sales organization determination logic; refining shipping condition determination logic for VMF shipments; and updating business process labels. | Since inception, scope of NSO has changed considerably thus to be in sync with the business process requirement these changes need to be incorporated. The proposed changes are required for smooth functioning of the NSO Fiori app. | NA | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1581-%20Frontend%20design%20changes%20for%20NSO%20Fiori%20app.pptx?d=wc324ca2cacd64fa58b519b55b6dd2d34&csf=1&web=1&e=b5ObXw |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-09 | 120 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1585 | Cancelled |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.8 OTC IP - EWM | Yes |  | Naved Naved |  | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Original flag indicator at the OTC CRT and Item level table which will enable to the returns order batch job to pick only RMAs where there is any update to sublines | Returns Order Status Interface Batch job should send only those RMAs to Salesforce that are either new or have been updated. RMAs with sublines without any changes should not be sent to SF, which will help prevent duplicate entries, optimize the payload size, and improve overall system efficiency. To fulfill this requirement, the EWM team will implement a Delta Indicator at the EWM Subline level. This indicator will enable the Returns Order batch job to identify and select only the new or updated RMAs to be sent to Salesforce. Original Flag indicator also needs to be updated in S4 tables: ZTOTC_RETURN_CRT and ZTOTC_RETURN_ITM once any changes happens during the Inbound process. |  |  | Yes | Core |  |  | Missed Requirement |  |  |  | High | High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Surendra to be cancelled |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-09 | 0 | < 15 Days | prasshinde@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1584 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 08. FTS IP | Abhishek Hingne | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | COO determination logic for IP inventory | To incorporate COO determination logic for IP inventory and to be printed on CI, PL forms | *Approved 1/5/26; This CR is required to accommodate determining COO for IP inventory and print the same on CI, PL forms. |  | No |  | x | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-1584%20%E2%80%93COO%20Determination%20Logic%20for%20IP%20Inventory.pptx?d=w95c5232acdff4db79bfad3aa57b30626&csf=1&web=1&e=AvXLT3 | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | High | 2 | [8 empty] | 268 |  |  |  |  | 0 | 268 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0842, LOGF0342, LOGF0344​, LOGF0345​, LOGF0353, LOGF1149, LOGF0350, LOGF0349 | 8 | LOGI0842, LOGF0342, LOGF0344​, LOGF0345​, LOGF0353, LOGF1149, LOGF0350, LOGF0349 | 8 |  | 0 |  | 0 | N/A | N/A | 2026-04-03 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • This CR is related to the COO logic, and it is coming because of the new tax requirement coming from the trade team. • Before the break, a CR was submitted to update the logic for the IF side; this is the logic for the IP side. • Trade was able to figure out the final requirements in November. There are certain commodities that were IP-specific, and they had different requirements. • The existing logic will be copied into the STO. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-09 | 0 | < 15 Days | ahingne@deloitte.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1586 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP 11. Technology 12. Infrastructure |  | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | INT-CR1142 | [7 empty] | Objects to be pushed to ITC2 due to POLP Straddle ECA Views | Due to approved CR1142, ECA views for POLP Straddle will not be complete until ITC2. Impacted S4 RICEFW's will need to be pushed accordingly. | Due to approved CR1142, ECA views for POLP Straddle will not be complete until ITC2. Impacted S4 RICEFW's will need to be pushed accordingly. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Logistics/CR1586%20-%20POLP%20Straddle%20ECA%20View%20Impacted%20RICEFW%27s.pptx?d=wafeb970e8cb340afbf7c42b6b9d0039f&csf=1&web=1&e=ojNXDi |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 3 | LOGI1555, LOGI1584, FTSI1573 |  | LOGI1555, LOGI1584, FTSI1573 | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI1584, LOGI1555, FTSI1573 | 3 | FTSI1584, LOGI1555, FTSI1573 | 3 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-11 | - There’s no change to these objects - All 3 objects are HLTA-completed | [9 empty] | Other | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-10 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1587 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 10. Analytics | 10.5 Analytics - OTC IP |  | 10. Analytics | roseann.m.irwin@intel.com | Data & Analytics - Rebecca Verette | OTC IP - Teresa McNicol/Jon Benoist |  | Legal Trade and Government Affairs Analytics was recently identified as a boundary app and was updated to the tracker, by when design of R3 had completed. | n/a | n/a |  |  | 41216 | Legal Trade and Government Affairs Analytics |  | Include IF- Sales CRM/ FPR GLAP/worker_expense/PTP fields to Legal ECA | Unable to close gap on pending attributes needed for LTG views currently consuming from EDW, IF Sales CRM and ECC/HANA views. 29 attributes from GLAP pending in Dev1 . INT-CR1578 in place to work on this. View will not be available before ITC3. attributes from IF Sales CRM not available in Dev1. Business approval process in progress. 2 Worker data objects requiring original PIA where owners were impacted by CPM. 7 attributes from [cp_workforce.worker_dsa_analytic.expense] continue in progress of enabling within final view for Legal consumption. +100 attributes from EDW procurement missing and not able to map during Build /FUT. | Legal actively uses the Compliance Risk Intelligence System, Matter Spending as well as downstream consumption from Last Day Office tool to ensure process is monitored once triggered. | FPR GLAP data will not be available before ITC3. As for other data we are expecting by early ITC2. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8D815ED3-4808-4A4A-A7B6-C92433DA3737%7D&file=INT-CR1587-%2041216-%20Legal%20Trade%20Government%20Affairs_Exception.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | High | 0 | [9 empty] | 320 |  |  | 1 | 0 | 320 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | ECAMDV1830 | 1 |  | 0 | ECAMDV1830 | 1 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 | Straight to Reporting CR Meeting |  |  | 2026-01-23 | • Description: Unable to close gap on pending attributes needed for LTG views currently consuming from EDW, IF Sales CRM and ECC/HANA views. 29 attributes from GLAP pending in Dev1 . INT-CR1578 in place to work on this. View will not be available before ITC3. Attributes from IF Sales CRM not available in Dev1. Business approval process in progress. 2 Worker data objects requiring original PIA where owners were impacted by CPM. 7 attributes from [cp_workforce.worker_dsa_analytic.expense] continue in progress of enabling within final view for Legal consumption. +100 attributes from EDW procurement missing and not able to map during Build /FUT. • Rational: Legal actively uses the Compliance Risk Intelligence System, Matter Spending as well as downstream consumption from Last Day Office tool to ensure process is monitored once triggered. • Impact to Schedule: FPR GLAP data will not be available before ITC3. As for other data we are expecting by early ITC2. • Discussion: o This change request (CR0383) was initially flagged for a post-release update and is now planned for delivery in ITC3. o The work involves completing R2 development and QA structures, with production readiness expected after week 13 for locations including Ireland and New Mexico. o UAT is planned to start around WW13, targeting delivery by mid ITC2 if possible, but officially set for ITC3 due to rewiring data sources from SPAN in R2 to ECA in R3. o Regression testing will be conducted in ITC 3, with alignment from the FSSD owner on this timeline. o Anand Jha inquired about the development differences between R2 and R3, with clarification that the primary difference is the source system for data (SPAN vs. ECA). o It was explained that maintaining separate codebases would be inefficient, and boundary applications have agreed to the ITC3 timeline for testing purposes. o The estimated completion date is mainly for customer visibility, not impacting transaction processing, and relates to all manufacturing stages for foundry customers. • AR - Vanessa Clark - Reconfirm with FSCO that production will be ready after WW13 for Ireland and New Mexico. • AR - Sunil Narayanan - Confirm alignment with B-Apps that the R3 testing timeline (ITC3) is acceptable and does not disrupt their testing. • Decision: Approved | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-10 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1588 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Vinay Kumar Khandelwal | [11 empty] | There is a requirement to have Invoice date populated along with Invoice number in the SFTP folder | There is a requirement to have Invoice date populated along with Invoice number in the SFTP folder | This change was identified after CR0573 implementation as this is a new requirement from business side to have Invoice date populated along with the invoice number , as to business to have invoice date along with Invoice number will be more convenient |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B23f58fa5-fa20-40f4-8cde-d65e7fa30338%7D&action=edit&wdPreviousSession=f4c557a8-ad07-b0bf-7735-3d28de0efb3c |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-10 | 119 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1589 | New |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.5 PTP - TM | Yes | 06. PTP | Aditya Shinde | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | ITC1 PTP exception: LOGE0769_IF/IP and LOGE0752_I/IP |  |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-10 | 119 | > 30 Days | adshinde@deloitte.ca |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1590 | Approved |  | SCP | R3 (Release 3) | Low | 07. FTS IF | 7.13 FTS IF - IF BE Supply Planning |  | 07. FTS IF | Radhika Ramasubban | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | [6 empty] | 13284 | ISA-VS2008 Asia (ATMPS CR and DPCR) |  | INT-CR1590–Change Request for ATCR to use PDH Site Split Rule Parameter | Add ATMPSCR function to split PRF/CD from VF to by site by using PDH site split rule parameter for VF sharing products | Currently planning use ATMPS CR to split VF level request into site level and publish such to ATM IE. Post IAO R3, request is still at VF level and BY ESP will be capacity related information like capacity envelope from ATMPS CR, and site split rule from PDH, and run solver to generate site level response (RTF). There’s no step of splitting request into site level in future request/response process. However, IE need site level request to guide them in generating capacity envelope for sharing product. | 4wks development, can only start after completing existing task for ITC#1. Target for ITC#2 | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/Intel%20Foundry%20BE%20Supply%20Planning/Design/CR%20ATCR%20PDH%20WW48.pptx?d=wa45be94c4c134ad886d9954eff31074d&csf=1&web=1&e=jFz3Lb |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [12 empty] | 80 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0269 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-11 | - This is a request for site-split demand visibility - There is a total of 5 weeks of work - AR: Need a plan from Shamin’s team & confirmation from his team - @Tan, Bee Ling - AR: Need to add in objects needed and timeline - @Mangtani, Naren | [9 empty] | Build | Tower | 2025-12-11 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-11 | 0 | < 15 Days | rocco.p.demarino@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1591 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | LOGF0355_IF, LOGF0356_IF | N/A | N/A | [5 empty] | Changes in Consolidated bailment CI for wafer/die and FG | - Inclusion of bailment price column in LOGF0355_IF AND LOGF0356_IF form layout. - CR 1072 removal of wafer/die qty columns. This is applicable only to wafer/die FORMS. - New trade data logic shared by Diego to be implemented. This is applicable to both LOGF0355 and LOGF356. | Needed for trade compliance | To be part of ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Logistics/INT-CR1591_IF_Changes%20in%20Consolidated%20bailment%20CI%20for%20wafer%20or%20die%20and%20FG.pptx?d=w44c2a7eb9d2e491296f5eda50f320fbf&csf=1&web=1&e=iMOW10 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 25 | [5 empty] | 27 |  |  |  |  | 0 | 27 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGF0355_IF, LOGF0356_IF | 2 | LOGF0355_IF, LOGF0356_IF | 2 |  | 0 |  | 0 | N/A | N/A | 2026-04-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 |  |  |  | 2026-01-30 | Approved in Core Leadership CR Meeting | [5 empty] | Build | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-11 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1592 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 13. Security | 13.2 Security - Cyber/ App Security |  | 09A. Master Data 13. Security 14. OCM | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri | NA | NA | NA | NA | [5 empty] | Updating MDG Firefighter IDs (New Config FFIDs and Access) | 1. Update shared config FFIDs for MDG team with sub-team specific FFIDs. The new FFIDs will maintain the same roles but have distinct owners and controllers by sub team, which will increase accountability and expedite log closure.​ 2. Add access to MDG reference data FFIDs | The MDG team requests replacing shared config firefighter IDs (e.g., FFC_MDGXXX*) in production with sub-team-specific FFIDs. The new FFIDs will maintain the same roles but have distinct owners and controllers by sub team, which will increase accountability and expedite log closure., which is an audit control | 2//28/2026 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Security%20%26%20Controls/INT-CR1592%C2%A0Operate%20-%20Updating%20MDG%20Firefighter%20IDs%20(New%20Config%20FFIDs%20and%20Access)%E2%80%8B.pptx?d=wae3ef1e80bc04e7783048fd736fe981f&csf=1&web=1&e=NA99k8 |  |  |  |  | Low |  | 1 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-11 | 118 | > 30 Days | nlaramie@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1593 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | britta.davis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Incorrect frozen weeks for external Fab product | This request seeks to include ordering month into frozen period as was originally designed for external hybrid products | In order to understand supply accurately, SPAN was designed to consider ordering month as frozen. During development phase, a change was made (frozen period excludes ordering month), resulting in inaccurate capture of understated supply. | Will be documented | No | Core |  | https://intel-my.sharepoint.com/:p:/r/personal/wen_qi_tan_intel_com/Documents/Desktop/IAO/CR%20for%20INC15092112%20%E2%80%93%20Incorrect%20frozen%20Weeks%20for%20external%20Fab%20product.pptx?d=we1978953761a4583a0b2e07525c7f439&csf=1&web=1&e=e2AvSs |  | 1. Process Scope / Design Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2025-12-16 | For external factory products, the ordering month for the frozen period needs to be included in PDH in SPAN. The ordering month was not frozen, and, as a result, supply schedules are not visible. If more supply is needed, an order will have to be manually adjusted, which is a huge risk for ordering supply. | [9 empty] | Design | Tower | 2025-12-16 | 12, 2025 | 12, 2025 | 12, 2025 | 2025-12-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1594 | Approved |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 10.1 Analytics - ALL |  | 03. FPR 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 10. Analytics | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | INT-CR1706 | N/A | N/A |  |  | 25513 | GMT Reporting Portal |  | Analytics Exceptions for ITC2/ITC3 | Analytics Exceptions for ITC2, in addition to objects/apps included in CR1464 | Delays related to late requirements, design opens, S4 dependencies | There will be various non-critical Analytics objects that will miss ITC1, but will be delivered for ITC2 or ITC3 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-CommodityCostObjectException.pptx?d=w1b4f608310e64222a2873d2493904a58&csf=1&web=1&e=UoK2RG |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | ECA N/A - Milestone Adjustment | 94 | FPRXR110, FPRXR111, FPRXR112, FPRXR113, FPRXR114, FPRXR115, FPRXR116, FPRXR117, FPRXR118, FPRXR119, FPRXR120, FPRXV511, FPRXV512, FPRXV513, OTCFCV026, OTCFCV027, OTCFCV028, OTCPCV048, OTCPCV049, OTCPCV050, FPRXV518, FPRXV519, FPRXV520, FPRXV521, FPRXV522, FPRXV523, FPRXV524, FPRXV525, FPRXV526, FPRXV527, FPRXV528, FPRXV529, FPRXV530, FPRXV531, FPRXV532, FPRXV533, FPRXV534, FPRXV535, FPRXV536, FPRXV537, FPRXV538, FPRXV539, FPRXV540, FPRXV541, FPRXV542, FPRXV543, FPRXV544, FPRXV545, FPRXV546, FPRXV547, FPRXV548, FPRXV549, FPRXR129, FPRXV550, FPRXV551, FPRXV552, FPRXV553, FPRXV554, FPRXV555, FPRXV556, FPRXV557, FPRXV558, FPRXV559, FPRXV560, ECAFPRV878, ECAFPRV888, ECAFPRV2194, ECAFPRV2205, ECAFPRV2358, ECAFPRV6863, ECAFPRV7017, ECAFPRV7018, ECAFPRV7019, ECAFPRV7020, ECAPTPV5503, ECAPTPV5504, ECAPTPV5505, ECAPTPV5506, ECAPTPV5507, ECAPTPV5508, ECAPTPV5509, ECAPTPV6509, ECAFTSIPV2257, ECAFTSIPV2261, ECAFTSIPV2269, ECAFTSIPV2268, ECAFTSIPV6448, ECAFPR6055, ECAFPR6147, ECAFPR6166, ECAOTCIFR2364, ECAOTCIFR2373, ECAOTCIFR2375, ECAOTCIFR2371 |  |  | 0 | FPRXR110, FPRXR111, FPRXR112, FPRXR113, FPRXR114, FPRXR115, FPRXR116, FPRXR117, FPRXR118, FPRXR119, FPRXR120, FPRXV511, FPRXV512, FPRXV513, OTCFCV026, OTCFCV027, OTCFCV028, OTCPCV048, OTCPCV049, OTCPCV050, FPRXV518, FPRXV519, FPRXV520, FPRXV521, FPRXV522, FPRXV523, FPRXV524, FPRXV525, FPRXV526, FPRXV527, FPRXV528, FPRXV529, FPRXV530, FPRXV531, FPRXV532, FPRXV533, FPRXV534, FPRXV535, FPRXV536, FPRXV537, FPRXV538, FPRXV539, FPRXV540, FPRXV541, FPRXV542, FPRXV543, FPRXV544, FPRXV545, FPRXV546, FPRXV547, FPRXV548, FPRXV549, FPRXR129, FPRXV550, FPRXV551, FPRXV552, FPRXV553, FPRXV554, FPRXV555, FPRXV556, FPRXV557, FPRXV558, FPRXV559, FPRXV560 | 64 | ECAFPRV878, ECAFPRV888, ECAFPRV2194, ECAFPRV2205, ECAFPRV2358, ECAFPRV6863, ECAFPRV7017, ECAFPRV7018, ECAFPRV7019, ECAFPRV7020, ECAPTPV5503, ECAPTPV5504, ECAPTPV5505, ECAPTPV5506, ECAPTPV5507, ECAPTPV5508, ECAPTPV5509, ECAPTPV6509, ECAFTSIPV2257, ECAFTSIPV2261, ECAFTSIPV2269, ECAFTSIPV2268, ECAFTSIPV6448, ECAFPR6055, ECAFPR6147, ECAFPR6166, ECAOTCIFR2364, ECAOTCIFR2373, ECAOTCIFR2375, ECAOTCIFR2371 | 30 | 94 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | [6 empty] | Other | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 12, 2025 | 2025-12-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
|  | INT-CR1595 | Rejected |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 07. FTS IF 09A. Master Data | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | HAZMAT Enhancement, UI & Conversion move to ITC2/MC2 | Object Date Changes; Activities in R3 Sprint 20 & 21 Build Plan will be delayed, as objects will be moved to ITC2/MC2. of R4 and will re-include in future Sprint Build plans, for the following: DATE1613 – HAZMAT UI: Date Change from R3 in ITC1 to ITC2; will be completed by 27th Feb 2026. FTSE1360 - Custom Fiori UI - : Date Change from R3 in ITC 1 and move to ITC2 DATC1617 – HAZMAT Profile Conversion- : Date Change from R3 in ITC 1 and move to ITC2. | These enhancement (screen) and conversion needed to move to ITC2/MC2. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1595%20%E2%80%93%20HAZMAT%20Enhancement,%20UI%20%26%20Conversion%20move%20to%20ITC2,MC2.pptx?d=w01d27c66f8c84af4a4a09590e5889245&csf=1&web=1&e=GCJrNa |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower |  |  | 2025-12-18 | [10 empty] | Other | Not Assigned |  | Not Approved | 12, 2025 | 12, 2025 | 2025-12-16 | 0 | < 15 Days | pbhalawat@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1596 | Approved |  | ERP | R3 (Release 3) R3 Backlog | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 09A. Master Data 15. Cutover 16. Testing | chgorantla@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | New requirement | NA | NA | [5 empty] | Cashpool Change Project for S4 | Cashpool Change Project for S4 | A new cash pool will be established in Ireland to replace the existing offshore cash pool in the Netherlands. It is anticipated that the same entities currently participating in the existing pool will transition to the new pool. | Guidance is not to miss UAT1 and intercept ITC3 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAF25D658-B3F6-40D1-95FB-1FF0F36C0CE6%7D&file=INT-CR1596_FPR_Treasury.pptx&action=edit&mobileredirect=true&CID=A816CE2E-18EF-4DCC-8741-0A5BA8E041A0&wdLOR=cF1A762C6-35AA-4884-BC0E-E10364D4CFF8 | New Requirement / Scope | 3. Configuration Change |  | Maybe |  | High | 0 | 540 | 91800 | [5 empty] | 540 | [5 empty] | 0 | 540 | Configuration | No | S4 | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A | 2026-06-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-15 | • There will be a cash pool change from Netherlands to Ireland. This decision was made during Q4 for risk avoidance. • There will be around 540 hours of additional configuration work. • There will be impacts to treasury boundary apps, but it is only related to ECC. Current S4 will not be impacted. • The changes will be made in ECC first • This work will require a whole new structure to be created. • AR: Ask Kjell to see who is paying for it in ECC and how many hours he is estimating. |  |  | 2026-01-16 | [6 empty] | Other | CL/OSC | 2026-01-16 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT Not Started | No Objects |  | In Progress | Yes
|  | INT-CR1597 | Cancelled | [6 empty] | Yes | [27 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-17 | 0 | < 15 Days | manmjha@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1598 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 10. Analytics | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | NPI Inputs Process Improvements | Expand DPW parameter in table SUPPLY_CHAIN.SPAN_ANALYSIS.MANUFACTURING_PARAMETER_ITEM_LOCATION_WORKWEEK to include 2 year horizon. Have that additional data flow through BOM Traversal Report. (Rashmi/Atharva) and then through SCOE data load process Develop reporting with SOAR team (Gabe) to source and map parameters for additional NPI products. Have these be reference reports for Jeffrey/Mo data load process with HVM products (BU data loads benchmark) Continue fully manual process for remaining parameters and new items (“fresh” PCRFs/BOM creation as they likely won’t have mapping in Compass tables) | Didn’t know that fab planning as part of R2 would be updated DPW in source systems for 2 years Nov and Dec cycles highlight data quality risk around NPI product management (missing DPW, DLCP, yield, etc.) – highly manual process resulting multiple resolve and poor wafer forecast | Will be documened if exist | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/NPI%20Inputs.pptx?d=wc22b8f38c94b40399db8dfc3b150cb41&csf=1&web=1&e=gXztTI |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 |  |  |  |  | 90 | 32 | [7 empty] | 122 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-20 | [10 empty] | Design | Tower | 2026-01-20 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1599 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP 10. Analytics | stephanie.anderson@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | BY MP Updates to Support 24 month BOM | We have identified two gaps related to the dependent demand signal that BY IBP receives from BY MP. These are: The horizon length The 24-month Placeholder BOM setup. We need: The full 118-week horizon of demand from BY CDP to flow through BY MP to calculate dependent demand The 24-month Placeholder BOM setups to successfully be loaded into BY MP | Currently entire products are missing from the demand signal sent to BY IBP because: Demand falls outside the current BY MP 104-week horizon or Their Placeholder setup & BOM Status does not allow BY MP to accept their BOMs. | Will be docummented | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CR1599%20%E2%80%93%20BY%20MP%20Updates%20to%20Support%2024%20month%20BOM.pptx?d=w65043395356245d8a24cb1b016946912&csf=1&web=1&e=Dg2UPK&xsdata=MDV8MDJ8YW5udGFtQGRlbG9pdHRlLmNvbXxmZmExODEwMDI1YWI0YjJiNDgyMTA4ZGU2OGZkMjE4YnwzNmRhNDVmMWRkMmM0ZDFmYWYxMzVhYmU0NmI5OTkyMXwwfDB8NjM5MDYzNjMzNzM4NTYxMTI5fFVua25vd258VFdGcGJHWnNiM2Q4ZXlKRmJYQjBlVTFoY0draU9uUnlkV1VzSWxZaU9pSXdMakF1TURBd01DSXNJbEFpT2lKWGFXNHpNaUlzSWtGT0lqb2lUV0ZwYkNJc0lsZFVJam95ZlE9PXwwfHx8&sdata=RUpkT1BrSHJoVHdDWU45QXZYTi9sbUY3bk43SXJEWjk3R1VUdy80L01wdz0%3d&CT=1772061895599&OR=Outlook-Body&CID=25A26EA6-55CA-4F6A-897D-7F08AF46D859&wdLOR=cB2193491-E83A-4D7F-9FD4-09440F239A6A |  | 0. Request for Investigation |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-09 | Approved offline by Kumar Vytla and Chad Smith to perform the sizing. | [9 empty] | Other | Tower | 2026-02-09 | 02, 2026 | 02, 2026 | 12, 2025 | 2025-12-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1600 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR | mark.c.bargovan@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | FPRI1704_IP | NA | NA | [5 empty] | Object Cancellation - FPRI1704_IP | Need to Cancel below Object as its not needed to IP system. FPRI1704_IP - Automated Tool MUP Excess Capacity calculation and associated PCOS/OCOS Split for the forecast. | Need to Cancel below Object as its not needed to IP system and specific to IF system only. FPRI1704_IP - Automated Tool MUP Excess Capacity calculation and associated PCOS/OCOS Split for the forecast. | No Impact as this request is for object cancellation. | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1600/RE_%20Confirmation%20-%20Intel%20IDM%202_0%20Change%20Request%20Form_Object%20Cancellation%20FPRI1704_IP.msg?csf=1&web=1&e=rSIBUY | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI1704_IP |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-01-28 | [10 empty] | Other | Tower | 2026-01-28 | 01, 2026 | 01, 2026 | 12, 2025 | 2025-12-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1601 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.4 FPR - Intercompany |  | 03. FPR 13. Security | Swati Ashok Jogi |  | FPR - Aubrey Hinderlider | [9 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B838EE862-4F46-4AC3-B2E6-C6DCD4974100%7D&file=INT_Build_CR1601_Security%20Roles%20Required.pptx&action=edit&mobileredirect=true |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-18 | 0 | < 15 Days | karansingh94@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1602 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF |  |  | 04. OTC IF | Vinay Kumar Khandelwal | [6 empty] | INC15147844 | Open |  |  |  | Return Authorization form Email ID Change | Return Authorization form Email ID Change | Returns authorization form are being sent on the sold-to party email as per current design but IF returns business want to get it on CBA’s mail ID.​ To achieve this, need to maintain CBA mail ID as fix value to send the authorization form.​ ​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF8BCCA12-DB74-4363-8119-A8FF2ADE25D0%7D&file=Return%20Authorization%20form%20Email%20ID%20Change.pptx&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-18 | 111 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1603 | New |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF 17. B-App | rodolfo.alarcon@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | 2684_R3_Interface between ECD and S4/EWM | No | NA | [5 empty] | Changes in Integration at Middleware Mulesoft from R2 to R3 (Objects LOGI0520) | Changes to Integration at Middleware level Integration between ECD <-> Mulesoft <-> EWM System requires update at Mulesoft level to transition from R2 to R3 It shall optimize the setup by removing integration with ECA for Product check, changes in timeout duration and eliminate payload transformation requirement between ECD to EWM. Change to Code at Technical level In R3, Status "Open TO" shall permit blocking of Products in Warehouse before Goods Issue , perform archival of historical data from ECD custom table ( greater than 6 months). | Changes at Mulesoft in R3 is required meet R3 design as ECC and ECD integration setups are no longer required after R3 Go Live. It shall remove integration with ECC,ECA and all transformation logic for payload sent/received from ECD. This process will enable ECD to check inventory status and Block product within EWM warehouse before goods issue. R2 Objects with dependencies : LOGI0520 R3 Objects with dependencies, LOGI1601 | This Change will be completed by sprint 23. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/CRXXXX_FTS%20IF_EWM_Change%20request%20for%20IF%20ECD%20Integration%20with%20EWM.pptx?d=w088de742edbd47558eadabb1ba501fce&csf=1&web=1&e=eFUdBi |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-19 | 110 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1604 | Approved |  | ERP | R3 (Release 3) |  | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | Rishav Kumar | PTP — Kenneth Salazar | PTP - Richard Taylor |  |  |  | NA |  | Open |  |  | WIINGS | CR for new object creation (Enhancement) | Enhancement to automate OBD creation of Repair /Rework Subcon PO | Need to create new RICEFW for the implementation of this enhancement |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4C0E00F3-1BDF-4B83-A46E-6312D7D581EC%7D&file=CR1604_PTP%20LE_Automate%20Outbound%20delivery%20creation%20for%20Repair%20Rework%20Subcon%20PO.pptx&action=edit&mobileredirect=true |  | 1. Process Scope / Design Change 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 | 80 | 15120 | 80 | [5 empty] | 136 |  |  |  |  | 0 | 136 | N/A | Yes | S4 | 1 | LOGE1728 | 3204 | LOGE1728 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-19 |  |  |  | 2026-02-20 | [6 empty] | Other | CL/OSC | 2026-02-20 | 02, 2026 | 02, 2026 | 12, 2025 | 2025-12-22 | 0 | < 15 Days | rishavkumar4@deloitte.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR1605 | New |  | ERP | R3 (Release 3) |  | 06. PTP |  |  | 06. PTP | Rishav Kumar | PTP — Kenneth Salazar | PTP - Richard Taylor |  |  |  | NA |  | Open |  |  |  | Changes required in Logistics Workflow in the distribution process once the GR is reversed with Movement type 110 and 108 then no need to trigger the workflow again for same Purchase Order IP to IF | As part of IP-IF Distribution Process, When Goods is arrived at warehouse location the Goods receipt is processed with movement type 107 and workflow is trigrred to notify the respective recipient, A delivery agent will deliver the goods to recipient and confirm the workflow. Once these is any issue found the goods need to be returned and GR need to be posted with movement type 108 and 110. Post the reversal the business ask is there is no requirement to trigger the workflow again with respect to same PO since the workflow is already triggered previously. | Changes required in Logistics Workflow in the distribution process once the GR is reversed with Movement type 110 and 108 then no need to trigger the workflow again for same Purchase Order IP to IF |  | No | Core |  |  |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 12, 2025 | 2025-12-22 | 107 | > 30 Days | rishavkumar4@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1606 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Very High | 02. E2E Process Integration | 2.2 E2E Process Integration - Solution Architecture |  | 02. E2E Process Integration 10. Analytics 17. B-App | tsering.d.zingkha@intel.com | BApps — Kelly Gerber | Biz Continuity - Aishwarya Bhat |  | Need to pull in IFS report development by ECA team due to VIPRE EOL in April 2026. | N/A | N/A | [5 empty] | Pull in IFS report development by April 2026 due to VIPRE EOL. | Need to pull in IFS report development by ECA team due to VIPRE EOL in April 2026. Currently the reports are bundled with R3 and are projected to be released in Q1 2027. | IFS needs these tactical Planning reports by April 2026 for KTBR reasons. This is when VIPRE is scheduled to EOL. IFS is continually adding more products and the reports are critically required by Planning teams. | Currently, the Planning reports are scheduled to be delivered with R3 in Q1 2027. Due to VIPRE EOL in April 2026, we need the reports developed and released before that. IT teams support of this CR could affect existing timeline of other deliverables depending on developer resources, etc. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/CR1606%20-%20Pull%20In%20Request%20for%20IFS%20Reports.pptx?d=wfeae03486f1e483cafd52b5e37bb3746&csf=1&web=1&e=PSBz0v |  | 11. Boundary Apps-related Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-01 | 97 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1609 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.3 OTC IP - Billing and Rebates |  | 05. OTC IP 11. Technology 17. B-App | kevin.m.johns@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | N/A | N/A | N/A | [5 empty] | Intel Federal Output Type SF1443 | Create the government form 1443 utilizing the print program to ensure that the correct document due to BRF+ not being turned on for Billing output. Dassian print program will be leveraged to generate Government forms.​ Form will contain details of name, address, customer sold to name & number, Customer payment details, sequential voucher number, ACR no. etc. | This is a government requirement form for progress payment. Form output to leverage Dassian print program to get required data.​ Form generation of Invoice as per DMR[SO] | this change can be supported for ITC2 | Yes | Core |  | https://intel.sharepoint.com/:p:/s/dassianandintelfederalsystems/IQAmbOKinvffRI_GTxBdmjaGATB2iSSTnZQZf_lkBNztAUg?email=erica.nash.wills%40intel.com&e=2g53E7 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [8 empty] | 180 |  |  |  |  | 0 | 180 | N/A | Yes | S4 | 1 | OTCF1714 | 3196 | OTCF1714 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-15 | • 1 of the 3 forms for government regulations were missed when the FS was created, so this CR is coming in to create it. • We cannot turn on BRF+ for this because there are other parts of billing that it is not compatible with. SAP did not build out BRF+ for certain capabilities that they need. |  |  | 2026-01-16 | [6 empty] | Other | CL/OSC | 2026-01-16 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Complete |  | Complete | No
|  | INT-CR1610 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.8 Master Data – HR Mini Master |  | 09A. Master Data | Venkat Venkatesh |  |  |  | NA | NA | NA | [5 empty] | Creation of 2 New Security Roles for HRMM transactions for IFED and Non-IFED | IFL HR mini master role (IP system – Intended for business and IT). It includes display access to TCs: PA20, PO13D, PP01_DISP, PP02,PO13 and PPOSE, and backend tables: PA0000, PA0001, PA0002, PA0006, PA0007, PA0008, PA0041, PA0105 & PA0315.​ PTP/FPR HR mini master access (IP/IF/CFIN - Intended for business and IT): Role covers PA20 excluding IT0008. Access to view backend tables: PA0000, PA0001, PA0002, PA0006, PA0041 & PA0105.​ | These 2 new roles are needed to grant Display access to HR infotypes and Tables. |  | No |  |  |  |  | 6. Build Security-Related Changes |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-06 | 92 | > 30 Days | venkvenkatesh@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1611 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 16. Testing | akpa@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | No impact | No | Core | Draft Change for FPRE0880 that was originally created as a placeholder for DMEE updates relevant to APAC | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/Change%20ID_Tower_CR%20Deck_template.pptx?d=wbb01159c67fb4305af3ade301e24acb5&csf=1&web=1&e=Jwzdpb |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1612 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 04. OTC IF 05. OTC IP 09A. Master Data | Sahil Syal | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [6 empty] | 16892, 41477 | #INVALID OPERATION |  | Automated update to DC Sales Status and other Item Sales Data fields | Requirement is to update following Item Sales Data field values from PCDM (PCN Tool) into MDG system: ​ Product visibility Sales Text (this covers PCN#, Sales Discontinuance date, Last Product Discontinuance Order Date, Last Product Discontinuance Ship Date, Last Product Return Date) Sales status​ | Currently these attributes are maintained in PCDM and are interfaced into SPEED, which then sends the data into legacy SAP ECC. Since the Sales Data is being removed from SPEED as part of IAO R3 design, we need a new interface between PCDM and Translator to get these updated into SAP MDG. | R3 ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1612_Master%20Data_Derivation%20of%20DC%20Sales%20Status.pptx?d=wd069fb3578604c2385ed00e905d27ecd&csf=1&web=1&e=B2WmLF | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | Medium | 2 | [10 empty] | 120 |  | 160 | 0 | 120 | Tech - MDG | Yes | S4 | 1 | DATI1727 | 3203 | DATI1727 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATI0943 | 1 | DATI0943 | 1 |  | 0 |  | 0 |  |  | 2026-05-22 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | [6 empty] | Build | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | FS In Progress | In Progress |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1614 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | anthony.romano@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Net Constrained VMI & LAFI Fcst | Introduce two new demand types: Net Constraint VMI Forecast and Net Constraint LAFI Forecast. | *Conditionally Approved 1/5/26; This supports a valid use case where a constrained demand plan is entered for the VMI/LAFI fulfillment channels. | tbd | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20PXT%20CCB%20-%20Net%20Constarint%20VMI%20%26%20LAFI%20Fcst.pptx?d=w36c62cd3c3bc4a8f9352a65fa796b551&csf=1&web=1&e=11CgA4 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 |  |  |  |  | 120 | 80 | [7 empty] | 200 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | SCPIPAPOPBY0024 | 1 |  | 0 |  | 0 | SCPIPAPOPBY0024 | 1 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • A fourth layer of logic is needed to adjust demand calculations. Otherwise, larger customers will be prioritized more than smaller customers. • AR: Get confirmation from PDH team that they are onboard to deliver by timeline. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects | Complete | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1617 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.4 OTC IP - Returns |  | 05. OTC IP | Pramod Kalli Srinivas | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Outbound Interface changes to send data from S4 to SF | Changed and updated fields needs to be share with SF. TM fields will be shared with SF once freight order is created or any changes made in carrier details. Also, to share the updated events with SF custom table and custom program will be required to check the for the change field values and share with the SF. | Changed and updated fields needs to be share with SF. TM fields will be shared with SF once freight order is created or any changes made in carrier details. Also, to share the updated events with SF custom table and custom program will be required to check the for the change field values and share with the SF. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Change%20Request/CR%20Forms/INT-CR1617%20-%20Outbound%20Interface%20changes%20to%20send%20data%20from%20S4%20to%20SF.pptx?d=web849e4dbd4c4b7a94b709ed2bb17307&csf=1&web=1&e=bh4hds | Design / Build Gap | 2. New RICEFW / ECA / Build Object |  |  |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | OTCI1721 | 3198 | OTCI1721 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-08 | • Need to have visibility at every stage of the transfer process. • Freight details to be sent back to S4 | [9 empty] | Other | Tower | 2026-01-08 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | pkallisrinivas@deloitte.com |  | No |  | Complete |  | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1615 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | anthony.romano@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Net Constrained Dmd Calc | Use Const CD Ovrd Qty to calculated Net Constraint Dmd instead of Constrained Dmd Fcst Qty Publish. | *Approved 1/5/26; Use Const CD Ovrd Qty to calculated Net Constraint Dmd instead of Constrained Dmd Fcst Qty Publish. | tbd | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20PXT%20CCB%20-%20Net%20Constraint%20Dmd%20Calc.pptx?d=wd37988edbdc34919a69b408cb188ed3e&csf=1&web=1&e=4jrIjf |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 |  |  |  |  | 80 | [8 empty] | 80 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | SCPIPAPOPBY0037, SCPIPAPOPPDH0025, SCPIPAPOPRF0025 | 3 |  | 0 |  | 0 | SCPIPAPOPBY0037, SCPIPAPOPPDH0025, SCPIPAPOPRF0025 | 3 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • This change request are enhancements to the current design. • Demoes will be done in conjunction with FUT. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects | Complete | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1616 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | anthony.romano@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | CD Upper & Lower Case | Enable CD Upper & Lower Case forest netting for BY-IBP and BY-ESP consumption. | *Approved 1/5/26; Unable to send CD Upper & Lower Case driven demand signal to BY-IBP and BY-ESP | tbd | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IAO%20PXT%20CCB%20-%20CD%20Upper%20%26%20Lower%20case.pptx?d=wd27f58fc9cf14b4ebe39b1ee832d53ff&csf=1&web=1&e=k2f7OU |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 |  |  |  |  | 145 | [8 empty] | 145 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPAPOPPDH0046 | 1 | 1 | SCPIPAPOPBY0037, SCPIPAPOPPDH0025, SCPIPAPOPRF0025 | 3 |  | 0 |  | 0 | SCPIPAPOPBY0037, SCPIPAPOPPDH0025, SCPIPAPOPRF0025 | 3 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • All 3 signals are gross signals and need to be maintained. • When original design was planned, there was no downstream process in place to consume the signals. • No process design changes are required. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1618 | Approved |  | ERP | R3 (Release 3) | Medium | 14. OCM | 14.1 OCM - ALL |  | 14. OCM | Laura Winterton |  | Change Mgmt - Cindie Blackmer |  | N/A | N/A | N/A | [5 empty] | OCM R3 Build Deliverables | Realign ERP SOW change management R3 Build deliverables to align with new IAO R3 Change Management POR . | We have aligned on a centralized change management POR across all programs (ERP, SCP, and B-Apps) and need to ensure that contractual dates align with CM POR. | None | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OCM/INT-CR01618_OCM_R3%20Build%20Deliverables.pptx?d=wf2d5c6fc490542d99302cadc4cda23e1&csf=1&web=1&e=Ahv8mU |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-09 | Approved by Richard Antonellis offline | [9 empty] | Other | Tower | 2026-01-09 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-08 | 0 | < 15 Days | likent@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1621 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | Elizabeth White | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | FNE run for OneMPS Tech Solve | Request to add one additional FNE solve that feeds into the OneMPS Tech Solve, which runs once per month. FNE Inputs: Month-begin CD Qty Pub Month-begin Billing Gross Adj Qty The run will occur at midnight on Wednesday/Thursday during the CD Publish week. The exact dates for each month should follow the Demand Publish Calendar. | To support OneMPS Tech Solve on Thursday of the CD publish week. | tbd | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP%20DP%20CRxxxx%20-%20FNE%20run%20for%20OneMPS%20TechSolve.pptx?d=wc2d0d99cafad47c5b7e0e55a67866842&csf=1&web=1&e=k4bPxp |  | 1b. Solution Design |  | Maybe |  | Medium | 0 |  |  |  |  | 80 | 40 | 40 | [6 empty] | 160 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-22 | • This request is to add one additional FNE solve that feeds not the OneMPS Tech Solve. • Work can be performed concurrently; total of 280 hours / 2 weeks. • AR: Update deck with detailed timeline once resourcers are finalized. | [9 empty] | Other | Tower | 2026-01-22 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1622 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 10. Analytics | devendra.srivastava@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | 2706 | N/A | [5 empty] | Integration of ICS data to SMH via ECA instead of direct connect | SMH requires item, operation and baseline flow data from ICS In order to generate reference operation sets which are sent to SAP. SMH was originally planning to get data directly from SMH, but this change would have ECA pull data from ICS and SMH pull data from ECA. The change will not impact the data quality or latency. | A) There was an earlier plan for getting the data from ICS directly to SMH but there are additional security overheads involved (TLS implementation on ICS would not allow us to meet the requested build timeframe) B) through ECA it will be much more shareable for future DSA consumption C) ECA was already pulling some of the related data so this will further enrich the data footprint supported in ECA D) Simplify architecture for IF SMH since all other master data is being pulled from ECA, this would eliminate a system connection. | No impact to schedule, will intercept MC1. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRXXXXX-ICS%20Data%20to%20IF%20SMH%20from%20ECA.pptx?d=wa6ce0b30785f47d59f738bc23ccfefc6&csf=1&web=1&e=Atr1eT |  | 2. New RICEFW / ECA / Build Object |  | No |  | Low | 0 | [6 empty] | 80 | [5 empty] | 0 | 80 | 0 | N/A | Yes | ECA | 5 | ECAFTSIFV7041, ECAFTSIFV7042, ECAFTSIFV7043, ECAFTSIFV7044, ECAFTSIFV7045 |  |  | 0 |  | 0 | ECAFTSIFV7041, ECAFTSIFV7042, ECAFTSIFV7043, ECAFTSIFV7044, ECAFTSIFV7045 | 5 | 5 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 | Straight to Core Leadership |  |  | 2026-01-30 | Approved in Core Leadership CR Meeting | [5 empty] | Other | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | Complete | Complete | No
|  | INT-CR1623 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Soumik Sil | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1623%20-%20Update%20incurrent%20FA%20derivation%20logic.pptx?d=w2cf95981cc5542ffa6a6a00f6f9bfe74&csf=1&web=1&e=JstyD7 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-09 | 0 | < 15 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1624 | New |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data | Lilibeth Lejarde | [11 empty] | Descope and change release of Automate External BOM - DATE1616_IF | Descope and change release of Automate External BOM - DATE1616_IF | Automate External BOM - DATE1616_IF has been planned for release R4 |  | No |  |  |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 01, 2026 | 2026-01-12 | 86 | > 30 Days | nagirreddy@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1625 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.11 FTS IF - IF Demand Planning |  | 07. FTS IF | Scott Palmer | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | [9 empty] | PRF Load Reschedule - Thursday instead of Friday | Change batch schedule to load PRF into IF CDP on Thursday instead of Friday - gives the team significantly more time to review the latest demand data and address issues internally or with IP (2 business days instead of one and adds weekend days if necessary) |  |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1625%20%E2%80%93%20PRF%20Load%20Reschedule.pptx?d=w1ff39c5d4a0b47609bb55b393d0b2772&csf=1&web=1&e=ndNbo4 |  | 3. Configuration Change |  | No |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-06 | Confirmed in email from Stacee that the CR was approved; Eric Yamada replied and confirmed that it was approved offline. | [9 empty] | Other | Tower | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-13 | 0 | < 15 Days | naren.mangtani@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1626 | Approved |  | ERP | R3 (Release 3) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 04. OTC IF 06. PTP | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | NA | NA | NA | [5 empty] | Sprint 21 SFUT- Descoped Items | Descoped Apps/T codes received for Sprint 21 SFUT. | Tower Teams requested to cancel the apps/T codes which are no longer in scope. | NA | No | Core | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=PbBWPf&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTk0MjYuMjAyNjAiLCAiT1MiIDogIldpbmRvd3MiIH0%3D&CID=b0d1f3a1%2D103b%2Db000%2D965b%2D63a5f2e293c0&cidOR=SPO&FolderCTID=0x012000D4E40463F60529498CAD8638059098C7&id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F01%2E%20PMO%2F05%2E%20Scope%20and%20Change%20Control%2FChange%20Control%2FCR%20Approval%20Emails%2FINT%2DCR1626 | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-18 | [10 empty] | Other | Tower | 2026-02-18 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1627 | Cancelled |  | ERP | R3 (Release 3) | Very High | [20 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-13 | 0 | < 15 Days | vprashantpotphode@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1628 | Approved |  | ERP | R3 (Release 3) | Very High | 04. OTC IF | 4.6 OTC IF - Credit and Collections |  | 04. OTC IF | Linda Y Nguyen | [11 empty] | Credit Dashboard Additional requirements | Credit Dashboard Additional requirements OTCE1625 1) Have additional Payer Tab for Within Horizon Values 2) Have additional column for Confirmed Quantity in Sales order Within & Outside Horizon Tabs 3) Separate out the Billing & Receivables bucket for 500 & 200 Categories | Business needs to see Within Horizon values for Payer screen Also Confirmed quantity will help Business to understand line item details Receivables need to be segregated incase the Billed document is not invoiced immediately |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/OTC/INT-CR1628 IF Credit and Collections - Credit Release Dashboard.pptx?d=w9b2733673b7e4ec886b2d90f01bac40f&csf=1&web=1&e=GhxyGr |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | High | 0 |  |  | 48 | [5 empty] | 87 |  |  |  |  | 0 | 87 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE1625 | 1 | OTCE1625 | 1 |  | 0 |  | 0 |  |  | 2026-04-17 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-13 | 0 | < 15 Days | vprashantpotphode@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1629 | Approved |  | ERP | R3 (Release 3) | Medium | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 03. FPR 07. FTS IF | talbot.smith@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat |  | NA | 3216 | NA |  |  | 4982 | IMO - NBS |  | IMO Non-Revenue Design | Masks produced by IMO will follow two paths: some are invoiced to a customer (in current scope), while others are expensed by Intel Foundry (gap). Currently Mask Point of Sale (MPOS) is used for this along with manual intervention. | Current S/4 design accommodates Revenue generating Masks for billing to external IF customers. Non-Revenue masks were part of the original design and E2E flows, but somehow this requirement was lost. Need to be added as an additional use case to expense non-revenue masks (those where Intel Foundry bears the cost) on receipt at the destination fab. | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR1629_P2P_Tester%20Front%20Office%20Marketplace%20Enablement.pptx?d=we8ebb26c135b46458660bb1fab2e3c4d&csf=1&web=1&e=nPu5eV | Missed Requirement | 1a. Operations Design |  | Yes |  | Medium | 0 |  |  | 8 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • When the process for IMO was designed, there were 2 paths for determining masks. The E2E flows covered both, but the version of it getting expensed to Foundry was lost. So, this is an ask for a discussions to re-do the flow back in. • System customization is not expected to come out of it. The assumption is to use standard functionality. • No need to change anything on the NBS interface. It might tweak the way that the STO gets created. • No other confirmation will be needed because it is entirely in S4. • This is needed for R3 as there are fabs in scope. | [9 empty] | Other | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects | Complete | Complete | No
|  | INT-CR1630 | Cancelled |  | ERP | [22 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1631 | Cancelled |  | ERP | R3 (Release 3) |  | 03. FPR | [19 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1632 | Cancelled |  |  |  | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | [16 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1633 | Cancelled |  | ERP | R3 (Release 3) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1634 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration |  | 07. FTS IF | rudrsengupta@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | PROC Items Planned Order Creation, Implicit ENH | PROC Items Planned Order Creation, Implicit ENH | Standard BAPI do not support the creation of Planned Orders for the PROC Items | No Impact- Target to complete in Sprint#22 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1634_FTS-IF_PROCItem_PlannedOrd_ImplicitENH.pptx?d=w3e4e24b22ce240cfb246071cf4584dcc&csf=1&web=1&e=fLpekx | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 8 | [5 empty] | 32 |  |  |  |  | 0 | 32 | Tech - S/4 | No | S4 | 0 | N/A | 3195 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI0311 | 1 | FTSI0311 | 1 |  | 0 |  | 0 | N/A | N/A | 2026-03-06 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • This is related to PROC items. • During testing, the team found out that the standard BAPI does not support creation of Planned Orders. SAP OSS note was raised, but it was not resolved. • SAP counterpart confirmed that this was a gap, and this enhancement will not be affected by any upgrades that might occur in the future. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1635 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration |  | 07. FTS IF 11. Technology 17. B-App | rudrsengupta@deloitte.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Payload Structure change for 2 SGP Interfaces | Payload Structure change for 2 SGP Interfaces | The XML payload structure, which was initially defined, needs to be updated to support the new structure IMConnect (MFG API Gateway) by adapting for SGP-Starts Game Planner communications to trigger Reservation creation for Raw Si. These are technical changes to payload headers etc. without any change to business functionality or business requirements and are not initiated by the business FTSI1157 and FTSI1602 | None been identified at this time | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1635_FTS-IF_Payload%20Changes%20to%20SGP%20related%20Interface%20Objects.pptx?d=w6161385162df45ccb6b6abb24c4182cd&csf=1&web=1&e=LSdchS |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 2 | [5 empty] | 56 |  |  |  |  | 0 | 56 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSI1157, FTSI1602 | 2 | FTSI1157, FTSI1602 | 2 |  | 0 |  | 0 |  |  | 2026-02-27 | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-15 | • These changes are related to the Prospal interfaces changes regarding payload • The full analysis will be complete on whether there will be any more impacts. | [9 empty] | Build | Tower | 2026-01-15 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR1637 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | snavasthi@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA |  |  |  |  | NA | #INVALID VALUE |  | Cancellation of object: FPRI1065_IF - connection will be required to MDG to get Capital approvers and to ISM to create a shipping memo. | We have an object interface (object ID: FPRI1065_IP & IF) to establish a connection between the MDG and S/4 systems and pull the capital approver from an MDG custom table (based on cost center) for the WBS Transfer tool. Later, we learned this capability is already built and available for the fixed asset objects (FPRI0323 and FPRW0325). We will leverage the same existing capability for the WBS Transfer tool as well. | We have an object interface (object ID: FPRI1065_IP & IF) to establish a connection between the MDG and S/4 systems and pull the capital approver from an MDG custom table (based on cost center) for the WBS Transfer tool. Later, we learned this capability is already built and available for the fixed asset objects (FPRI0323 and FPRW0325). We will leverage the same existing capability for the WBS Transfer tool as well. | NA | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1636%20and%20CR1637/RE_%20Approval%20__%20Cancellation%20of%20object%20__%20FPRI1065_IF%20%26%20IP%20-%20Connection%20will%20be%20required%20to%20MDG%20.msg?csf=1&web=1&e=RY5DbO |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI1065_IF, FPRI1065_IP | FPRI0323_IF, FPRW0325_IF |  | 2 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-28 | [10 empty] | Other | Tower | 2026-01-28 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1636 | Rejected |  | ERP | R3 (Release 3) | High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 11. Technology | snavasthi@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA |  |  |  |  | NA | #INVALID VALUE |  | Cancellation of object: FPRI1065_IP - connection will be required to MDG to get Capital approvers and to ISM to create a shipping memo. | We have an object interface (object ID: FPRI1065_IP & IF) to establish a connection between the MDG and S/4 systems and pull the capital approver from an MDG custom table (based on cost center) for the WBS Transfer tool. Later, we learned this capability is already built and available for the fixed asset objects (FPRI0323 and FPRW0325). We will leverage the same existing capability for the WBS Transfer tool as well. | We have an object interface (object ID: FPRI1065_IP & IF) to establish a connection between the MDG and S/4 systems and pull the capital approver from an MDG custom table (based on cost center) for the WBS Transfer tool. Later, we learned this capability is already built and available for the fixed asset objects (FPRI0323 and FPRW0325). We will leverage the same existing capability for the WBS Transfer tool as well. | NA | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1636%20and%20CR1637/RE_%20Approval%20__%20Cancellation%20of%20object%20__%20FPRI1065_IF%20%26%20IP%20-%20Connection%20will%20be%20required%20to%20MDG%20.msg?csf=1&web=1&e=RY5DbO |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI1065_IF, FPRI1065_IP | FPRI0323_IF, FPRW0325_IF |  | 2 | 07. OSC/CL rejected - no further analysis (end status) | No | No | 2026-01-28 |  |  |  | 2026-02-13 | This decision was reversed during the Core Leadership meeting | [5 empty] | Other | Tower | 2026-01-28 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-14 | 0 | < 15 Days | amitkumar55@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1638 | Approved |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 02. E2E Process Integration 03. FPR 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 14. OCM 17. B-App | sunil.k.parida@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat |  | NA | NA | NA | [5 empty] | Bailed vs Turnkey for Substrates/EMIB Master CR | Move to a model where IP plans for all substrates, but purchases them as turnkey materials from IF, Substrates and all substrate components (e.g., EMIB/bridge die, LSC & DTC) are included in this scope Substrates would appear in both IP and IF BY models and Master Data Both BY models will calculate substrate dependent requirements IP will be able to prioritize substrate capacity based on demand priorities IF will execute manufacturing Orders and Purchase Orders leveraging MAPPS via S4 IP will pay for the substrates (including service fee) as part of the FG price | IF requested that all substrates with EMIB be managed as turn-key (i.e., IF would manage the substrate and EMIB planning and procurement, and IP would pay for the substrates as part of the Finished Good price. Additionally, there is no desire at leadership level to initiate any organizational changes to move substrate procurement from current IF team to IP. IAO CL decision made to move to a model where IP plans for all substrates, but purchases them as turnkey materials from IF | None | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/Master%20CR%20for%20Substartes_EMIB_Non%20EMIB.pptx?d=w5d9f0ffa442b47138d6192343b9f80df&csf=1&web=1&e=Dc13xe | New Requirement / Scope | 1b. Solution Design |  | Yes |  | High | 0 |  |  | 40 |  |  | 20 | [7 empty] | 20 | 0 | N/A | Yes | ECA | 24 | ECAFTSIPV6336, ECAFTSIPV6340, ECAFTSIFV6342, ECAFTSIFV6343, ECAFTSIFV6344, ECAFTSIFV6355, ECAFTSIFV6353, ECAFTSIPV6346, ECAFTSIFV6348, ECAFTSIPV6345, ECAFTSIFV6354, ECAFTSIPV6350, ECAFTSIFV6347, ECAFTSIPV6356, ECAFTSIFV6351, ECAFTSIFV6349, ECAFTSIFV6357, ECAFTSIPV6352, ECAFTSIPV6390, ECAFTSIFV6391, ECAFTSIFV7023, ECAFTSIFV7024, ECAFTSIFV7021, ECAFTSIFV7022 |  |  | 0 |  | 0 | ECAFTSIPV6336, ECAFTSIPV6340, ECAFTSIFV6342, ECAFTSIFV6343, ECAFTSIFV6344, ECAFTSIFV6355, ECAFTSIFV6353, ECAFTSIPV6346, ECAFTSIFV6348, ECAFTSIPV6345, ECAFTSIFV6354, ECAFTSIPV6350, ECAFTSIFV6347, ECAFTSIPV6356, ECAFTSIFV6351, ECAFTSIFV6349, ECAFTSIFV6357, ECAFTSIPV6352, ECAFTSIPV6390, ECAFTSIFV6391, ECAFTSIFV7023, ECAFTSIFV7024, ECAFTSIFV7021, ECAFTSIFV7022 | 24 | 24 |  | 0 | SCPIPSPPDH0135, SCPIPSPPDH0137, SCPIPSPPDH0139, SCPIPSPPDH0144, SCPIPSPPDH0145, SCPIFSPPDH0270, SCPIFSPPDH0271, SCPIFSPPDH0272, SCPIFSPPDH0273, SCPIFSPPDH0274, SCPIFSPPDH0275, SCPIFSPPDH0277, SCPIFSPPDH0278, SCPIFSPPDH0279, SCPIFSPPDH0280, SCPIPSPPDH0152, SCPIPSPPDH0153, SCPIPSPPDH0154, SCPIPSPPDH0155, SCPIPSPPDH0156, SCPIPSPPDH0157, SCPIPSPPDH0158, SCPIPSPPDH0160, SCPIPSPPDH0161, SCPIPSPPDH0164, SCPIFSPPDH0283 | 26 | 26 | FTSI1573 | 1 | FTSI1573 | 1 |  | 0 |  | 0 | FTSI1584 | FTSI1573 |  | 1 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-23 |  |  |  | 2026-01-23 | Approved in Core Leadership | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
|  | INT-CR1639 | New |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.1 E2E Process Integration - ALL |  | 02. E2E Process Integration 03. FPR 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data | eugene.celis@intel.com | E2E/Architecture — Satya Vajjala | E2E - Aishwarya Bhat |  | CR-1102 | NA | NA | [5 empty] | TD Substrates Factory Business Model Change Request | From prior CR1102 – TD Substrates moving from 100% TD Non-REV to a mix of REV and Non-REV to support overall substrates shortages, introducing bailment process where supplier becomes a customer and different new scenarios. E2E flows were compiled and reviewed with X-tower teams. Previous CR requires Master Data Tech Sizing into ITC3/MC3 while others into ITC2. New Proposal contains MVP for CR and manual process where possible to get back into ITC1 intercept with the new timeline | New Business Model to support worldwide shortage to bring new Substrates technology to support IFS and IP future packaging needs. | None | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/INT-CRxxxx%20R3_TD%20Substrates%20Factory%20Change%20Request.pptx?d=w130c5927e61c4abf852d593411ea6971&csf=1&web=1&e=sYRj4i | New Requirement / Scope | 1a. Operations Design |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 1 | ECAFTSIPV6337 |  |  | 0 |  | 0 | ECAFTSIPV6337 | 1 | 1 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-15 | 83 | > 30 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | N/A | No
|  | INT-CR1640 | Cancelled |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 03. FPR 10. Analytics 17. B-App | Russell T Kaleekal | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | 00156 - FTS IP physical inventory reconciliation | CR-1384 | 02611 Inventory SCrapping | NA | [5 empty] | Inventory Reconciliation Testing Extension | 3/16: Request to close. This was created under the misunderstanding that we required a CR to test outside of ITC1, but such is not the case and CR1384 will remain the CR driving the changes. Change Request for a Report to facilitate Inventory (Unit) Reconciliation between IP S/4, CIBR, iCOST, IF S/4, ECC, and External OSATs & IF manufacturing locations, testing the first capability (3-Way Reconciliation) in ITC1, and second and final capability (5-Way Reconciliation) in ITC2. | Rationale for Requested Extension: - IT Resources are tied up in other higher priority CRs - Data dependencies will not be met until ITC2 | Targeted for ITC2 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1640_Inventory%20Reconciliation%20in%20IP%20Testing%20Extension.pptx?d=wb8d8fd90070b474383754a38c634b11c&csf=1&web=1&e=E5lTYR |  |  |  | No |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Jon Benoist to not be required for the team |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-16 | 0 | < 15 Days | jon.benoist@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1641 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | sathpanda@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | FPRI0696_CFIN ¦ RICEFW Cancellation | we plan to cancel the RICEFW object FPRI0696_CFIN, which supports the ReadSoft Process Director integration with Central Finance (CFIN). This cancellation is proposed because ReadSoft will not be installed in the CFIN instances; it will be used only in the IP and IF instances. | we plan to cancel the RICEFW object FPRI0696_CFIN, which supports the ReadSoft Process Director integration with Central Finance (CFIN). This cancellation is proposed because ReadSoft will not be installed in the CFIN instances; it will be used only in the IP and IF instances. | NA | Yes | Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1641/RE_FW_%20%20%20FPRI0696_CFIN%20_%20RICEFW%20Cancellation.msg?csf=1&web=1&e=ZKMIUF | NA |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI0696_CFIN |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-28 | [10 empty] | Other | Tower | 2026-01-28 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1642 | Approved |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF | R Prem Siddharth | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | 3290 | 3290 | [5 empty] | Descope Request for OTCE0642_IF | Descope request for Object: OTCE0642_IF due to non-availability of any transactions from Ireland to another EU region. | As per confirmation from business team(s) the Intrastat consolidation enhancement is not required as there is no scope for any transactional movement within EU in IF. ( Solution Decision #3290 )​ |  | No |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F17%2E%20International%20Trade%2F4%20Working%20Documents%2FChange%20Request%2FCR%20OTCE0642%5FIF%2FRE%20FW%20%20%20IAO%20%2D%20LE101%20Irish%20VAT%20registration%20ID%20%20R3%20confirmation%2Emsg&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F17%2E%20International%20Trade%2F4%20Working%20Documents%2FChange%20Request%2FCR%20OTCE0642%5FIF | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/CR1642%20-%20Descope%20Request%20for%20Object%20OTCE0642_IF.pptx?d=wed95a47c0c9b4327aa18210eaa979b0a&csf=1&web=1&e=RXZs8Z |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | OTCE0642_I |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-04 | [10 empty] | Other | Tower | 2026-02-04 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-16 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1644 | Cancelled | [22 empty] | ​ |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-16 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1645 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-16 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  | No Objects |  | In Progress | No
| N/A | INT-CR1643 | New |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | FTSI1584_EMIB ¦ RICEFW Cancellation | Cancellation of RICEFW Objects: FTSI1584 - Interface to post inventory in SAP S/4HANA from ECA via MuleSoft (EMIB) | RICEFW object FTSI1584 - Interface to post inventory in SAP S/4HANA from ECA via MuleSoft (EMIB) is no longer relevant for FTS-IP as Turnkey ordering process will be introduced for EMIB to place the orders on IF. Hence FTS-IP will be descoping this object. |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1643_Cancellation%20of%20RICEFW%20Objects%20FTSI1584.pptx?d=wa77f541bbb2745c199d85e0ba902eadd&csf=1&web=1&e=MUQGmq |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 01, 2026 | 2026-01-16 | 82 | > 30 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1646 | Approved |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 10. Analytics | jennifer.k.della-santina@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | n/a | n/a | n/a | [5 empty] | SPAN Horizon Needs To Be Current Qtr + 8 | Parameter UIs in SPAN (Fab Sort Parameters, Manufacturing Process Parameters) need to be longer to match the solve horizon in Blue Yonder, current qtr + 8. | Parameter horizon needs to match BY solve horizon. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/INT-CR1646%20SPAN%20horizon%20extension.pptx?d=w214329658f3946eb845c320ef7beb681&csf=1&web=1&e=A3nl3O |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [5 empty] | 100 | [7 empty] | 100 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-09 | [10 empty] | Build | Tower | 2026-03-09 | 03, 2026 | 03, 2026 | 01, 2026 | 2026-01-17 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1647 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 10. Analytics | 3.14 FPR - Boundary Apps |  | 03. FPR 10. Analytics | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  | 7440 | ICOST - Integrated Cost of Sales tool |  | New iCost view needed for R3-R5 straddle | A new ending-on-hand view that is needed in ECA for iCost to use during the R3-R5 straddle. | A new ending-on-hand view that is needed in ECA for iCost to use during the R3-R5 straddle. | Late build completion, but still deliver in time for ITC1 starting WW19 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-iCostViewException.pptx?d=w7f0ccdd0debd4b37a205bdd58474dd88&csf=1&web=1&e=kSAbFq |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [9 empty] | 320 |  |  | 40 | 0 | 320 | N/A | Yes | ECA | 2 | ECAFPRV6947, ECAFPR7006 |  |  | 0 |  | 0 | ECAFPRV6947, ECAFPR7006 | 2 | 2 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 | Straight to Core Leadership |  |  | 2026-01-30 | Approved in Core Leadership CR Meeting | [5 empty] | Other | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1648 | Approved |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 6.1 PTP - ALL |  | 06. PTP 10. Analytics | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  |  |  | WIINGS | PTP reports delayed until ITC2 | There are various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 | There are various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 | None - There are just various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B667839A4-C616-4851-B872-77D7B062CC6F%7D&file=INT-CR1648-PTPReportsException.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA N/A - Milestone Adjustment | 72 | FTSFV017, FTSFV045, PTPFR116, PTPFR117, PTPFR118, PTPFR119, PTPFR121, PTPFR124, PTPFR125, PTPFR126, PTPFR127, PTPV080, PTPFR128, PTPFR129, FTSFV016, FTSFV021, FTSFV028, FTSFV047, ECAPTP5133, ECAPTP5135, ECAPTP5144, ECAPTP5155, ECAPTP5096, ECAPTP5097, ECAPTP5593, ECAPTP5773, ECAPTP5828, ECAPTP6211, ECAPTP6778, ECAFTSIFV7046, ECAFTSIFV7051, ECAFTSIFV7047, ECAFTSIFV7048, ECAFTSIFV7049, ECAFTSIFV7050, ECAFTSIFV7052, ECAFTSIFV7053, ECAPTP5134, ECAPTP5154, ECAPTP5813, ECAPTP5820, ECAPTP6388, ECAPTP5761, ECAPTP5762, ECAPTP5763, ECAPTP5804, ECAPTP5805, ECAPTP5829, ECAPTP5836, ECAPTP5837, ECAFTSIFR6960, ECAFTSIFR6958, ECAFTSIFR6956, ECAFTSIFR6954, ECAFTSIFR6952, ECAFTSIFR6948, ECAPTPR5760, ECAPTPR5783, ECAPTPR5787, ECAPTPR5818, ECAPTPR7104, ECAPTPR7105, ECAPTPR7106, ECAPTPR7107, ECAPTP5109, ECAPTP5110, ECAPTP5111, ECAPTP5112, ECAPTP5123, ECAPTP5132, ECAPTP5754, ECAPTP6212 |  |  | 0 | FTSFV017, FTSFV045, PTPFR116, PTPFR117, PTPFR118, PTPFR119, PTPFR121, PTPFR124, PTPFR125, PTPFR126, PTPFR127, PTPV080, PTPFR128, PTPFR129, FTSFV016, FTSFV021, FTSFV028, FTSFV047 | 18 | ECAPTP5133, ECAPTP5135, ECAPTP5144, ECAPTP5155, ECAPTP5096, ECAPTP5097, ECAPTP5593, ECAPTP5773, ECAPTP5828, ECAPTP6211, ECAPTP6778, ECAFTSIFV7046, ECAFTSIFV7051, ECAFTSIFV7047, ECAFTSIFV7048, ECAFTSIFV7049, ECAFTSIFV7050, ECAFTSIFV7052, ECAFTSIFV7053, ECAPTP5134, ECAPTP5154, ECAPTP5813, ECAPTP5820, ECAPTP6388, ECAPTP5761, ECAPTP5762, ECAPTP5763, ECAPTP5804, ECAPTP5805, ECAPTP5829, ECAPTP5836, ECAPTP5837, ECAFTSIFR6960, ECAFTSIFR6958, ECAFTSIFR6956, ECAFTSIFR6954, ECAFTSIFR6952, ECAFTSIFR6948, ECAPTPR5760, ECAPTPR5783, ECAPTPR5787, ECAPTPR5818, ECAPTPR7104, ECAPTPR7105, ECAPTPR7106, ECAPTPR7107, ECAPTP5109, ECAPTP5110, ECAPTP5111, ECAPTP5112, ECAPTP5123, ECAPTP5132, ECAPTP5754, ECAPTP6212 | 54 | 72 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 | Straight to Reporting CR Meeting |  |  | 2026-01-23 | • Description: There are various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 • Rational: There are various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 • Impact to Schedule: None - There are just various PTP reporting objects that are delayed and won’t be ready for testing until ITC2 • Discussion: o Questions about cost management revealed that these reconciliation reports require specific support from Deloitte’s Tower and Analytics teams due to their complexity. o While some reporting tasks are handled internally, these particular reports are budgeted under Deloitte contracts. o The team is mindful of budget constraints and strives to balance internal resources and external spend effectively. o Other reconciliation reports, such as the supply chain five-way reconciliation, are planned to be delivered internally to manage costs. • Decision: Approved | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1649 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 06. PTP | 6.1 PTP - ALL |  | 02. E2E Process Integration 06. PTP 16. Testing 17. B-App | russell.a.hensley@intel.com | PTP — Kenneth Salazar | PTP - Richard Taylor |  | LE Merge Schedule Change | NA | NA | [5 empty] | External supplier engagement strategy post LE Merge timeline change | Maintain external supplier engagement strategy post LE Merge decision for pilot supplier testing starting in ITC2  1) OSAT, SiFO and 2) Fab Spares ALL other business domains have pilot suppliers starting in ITC1. | With the push of ITC1 timeline start for the LE Merge – Intel Dev/Test: All exceptions for capabilities to be developed and tested in ITC2 have been eliminated. All objects and interfaces are scheduled to be completed by the beginning of the new ITC1 start date. External supplier engagement – business domain specific supplier engagement strategies have been developed and implemented focused on managing program risk (timing and efficiency) and supplier relationships. Background: Suppliers are already engaged in supplier owned Dev/FUT with Intel B2B teams including connectivity testing (achieves >80% confidence in external partner connection before ITC with supplier. OSAT, SiFO  allow pilot suppliers to engage in either ITC1 or ITC2 per alignment between business, B2B team, and supplier Intel has pushed suppliers hard to meet the original ITC timelines. Timeline change creates frustration, tradeoffs, and additional costs for suppliers. Depending upon how suppliers IT is organized will drive different risk decisions: 1) PUSHOUT (new ITC2): maintaining code for 9-12months (i.e. the code developed for IAO will be excluded and even purged from the test environment) and regression testing more work and cost VS 2) MAINTIAN (new ITC1): easier to not have to extend or reallocate resources. Focus on minimizing the risk to program in partnership with supplier. Net result is expected to be equal to the existing approved plan assessed as low risk OR potentially better if some suppliers agree to move earlier Fab Spares  H2M engagement for R3. No change from ITC2 for pilot suppliers. ITC1 is needed to for debugging and stabilizing new capabilities before engaging the suppliers for ITC. ITC1 testing will conducted emulating supplier responses through E2Open. Engaging suppliers in ITC1 increases workload to manage communication and timing of issues, fixes, and retesting for already constrained testing teams Pilot suppliers will continue to be engaged before and during ITC1 for E2Open account onboarding and process training. (engagements are currently ongoing | Maintains as-is strategy with OSAT/SiFO and Fab Spares | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR%20-%20External%20supplier%20engagement%20strategy%20post%20LE%20Merge%20timeline%20change.pptx?d=w8c1385ef0514457bbf043f1c40e4ec23&csf=1&web=1&e=8DVcyY |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [12 empty] | 1 | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 | Skipped Ingestion |  |  | 2026-01-23 | • Description: Maintain external supplier engagement strategy post LE Merge decision for pilot supplier testing starting in ITC2 1) OSAT, SiFO and 2) Fab Spares ALL other business domains have pilot suppliers starting in ITC1. • Rationale: With the push of ITC1 timeline start for the LE Merge Intel Dev/Test: All exceptions for capabilities to be developed and tested in ITC2 have been eliminated. All objects and interfaces are scheduled to be completed by the beginning of the new ITC1 start date. External supplier engagement – business domain specific supplier engagement strategies have been developed and implemented focused on managing program risk (timing and efficiency) and supplier relationships. Background: Suppliers are already engaged in supplier owned Dev/FUT with Intel B2B teams including connectivity testing (achieves >80% confidence in external partner connection before ITC with supplier. OSAT, SiFO à allow pilot suppliers to engage in either ITC1 or ITC2 per alignment between business, B2B team, and supplier Intel has pushed suppliers hard to meet the original ITC timelines. Timeline change creates frustration, tradeoffs, and additional costs for suppliers. Depending upon how suppliers IT is organized will drive different risk decisions: 1) PUSHOUT (new ITC2): maintaining code for 9-12months (i.e. the code developed for IAO will be excluded and even purged from the test environment) and regression testing more work and cost VS 2) MAINTIAN (new ITC1): easier to not have to extend or reallocate resources. Focus on minimizing the risk to program in partnership with supplier. Net result is expected to be equal to the existing approved plan assessed as low risk OR potentially better if some suppliers agree to move earlier Fab Spares à H2M engagement for R3. No change from ITC2 for pilot suppliers. ITC1 is needed to for debugging and stabilizing new capabilities before engaging the suppliers for ITC. ITC1 testing will conducted emulating supplier responses through E2Open. Engaging suppliers in ITC1 increases workload to manage communication and timing of issues, fixes, and retesting for already constrained testing teams Pilot suppliers will continue to be engaged before and during ITC1 for E2Open account onboarding and process training. (engagements are currently ongoing • Impact: Maintains as-is strategy with OSAT/SiFO and Fab Spares • Discussion: o Context: Due to the LE merge timeline shift, proposal to keep supplier onboarding in ITC2 (vs. collapsing to ITC1) for OSAT/SiFO and Fab Spares. Other domains (ODM, Box, CPO, ATDM, Substrates) will still engage suppliers in ITC1. o Rationale: Stabilize capabilities in ITC1 via emulation/string testing and avoid rework/relationship strain with suppliers already developing; align with OTC approach of engaging externals in ITC2. o Emulation in ITC1; real supplier onboarding in ITC2. Consider “left shift” opportunities where feasible. o Fab Spares initially H2M via E to Open for R3; lower risk. o Internal pre ITC1 stabilization/testing may be expanded if it does not result in risk to replans. • AR - Cari Shim - Assess feasibility of additional internal pre ITC1 stabilization/testing without risking replans; revert with recommendation. • AR - Jose Vargas Lepiz - Evaluate how far pre test emulation can be extended given S4 constraints; advise where it adds value vs. risk. • Decision: Approved - Proceed with supplier engagement in ITC2 for OSAT, SiFO & Fab Spares; craft external comms immediately. Continue evaluating internal pre ITC1 testing options. | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects | Complete | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1650 | Approved |  | ERP | R3 (Release 3) | Very High | 05. OTC IP | 5.6 OTC IP - Credit and Collections |  | 05. OTC IP | sukhwinder.ranu@intel.com | [11 empty] | Credit Dashboard Additional requirements | Credit Dashboard Additional requirements OTCE0021 1) Have additional Payer Tab for Within Horizon Values 2) Have additional column for Confirmed Quantity in Sales order Within & Outside Horizon Tabs 3) Separate out the Billing & Receivables bucket for 500 & 200 Categories | Business needs to see Within Horizon values for Payer screen Also Confirmed quantity will help Business to understand line item details Receivables need to be segregated incase the Billed document is not invoiced immediately |  | Yes | Core |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 45 | [5 empty] | 41 |  |  |  |  | 0 | 41 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | OTCE0021 | 1 | OTCE0021 | 1 |  | 0 |  | 0 |  |  | 2026-04-10 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-20 | 0 | < 15 Days | vprashantpotphode@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1651 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP | manjunath.shastry@intel.com |  |  |  | LOGE0797_IP LOGE0797_IF | NA | NA | [5 empty] | Send ZPRE alerts using Batch jobs to ensure inflight matrix is checked before sending the pre-alert ​ | Pre alert Processing through batch Jobs | Send ZPRE alerts using Batch jobs to ensure inflight matrix is checked before sending the pre-alert |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1AC9C576-E24D-4D62-BEBE-8E5A9D040A3A%7D&file=INT-CR1651_Pre-alert%20(ZPRE).pptx&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | Medium | 0 |  |  | 27 | [5 empty] | 40 |  |  |  |  | 0 | 40 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGE0797_IP​, LOGE0797_IF | 2 | LOGE0797_IP​, LOGE0797_IF | 2 |  | 0 |  | 0 |  |  | 2026-03-30 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-20 | 0 | < 15 Days | preetiwari@deloitte.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
|  | INT-CR1653 | Rejected |  | ERP | R3 (Release 3) |  | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | Imran Athar |  | FTS IF - Haritha Komma | [9 empty] | Extension of FUT for LOGI0155 beyond 23A dues to delays and dependency on completion of the object for ECA. FUT Dates - 4/17 - 4/31 | Extension of FUT for LOGI0155 beyond 23A dues to delays and dependency on completion of the object for ECA. FUT Dates - 4/17 - 4/31 | Delays and dependency on completion of the object for ECA |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/INT-CR-1653/INT-CR1653_FTS_IF_Extension%20of%20FUT%20for%20LOGI1555.pptx?d=wa0f73751f95e4a4cb727b3040dcd6de2&csf=1&web=1&e=5kOzI4 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2026-01-22 | Straight to CR Meeting |  |  | 2026-01-23 | • Description: Extension of FUT for LOGI0155 beyond 23A dues to delays and dependency on completion of the object for ECA. FUT Dates - 4/17 - 4/31 • Rationale: Delays and dependency on completion of the object for ECA • Impact: Not provided in CR Log • Discussion - o Context: ECA view timeline moved (~4/17 ready; middleware to ~4/30), pushing S4 testing earliest to 5/1; request to move S4 FUT accordingly. o Importance: Considered core (close STOS in S4 IF for bailment); recommendation to reprioritize non core/reporting to fit this within ITC1 where possible. • AR - Anand Jha - Work with ECA/S4 teams to reprioritize so FUTLOGI1555 testing impact is minimized and ITC1 coverage for core flows is preserved. • Decision - Not Approved - attempt to reprioritize to protect ITC1 scope despite ECA slip; align across teams on a workable plan. | [6 empty] | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-21 | 0 | < 15 Days | aditiwari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1654 | Rejected |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) |  | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 17. B-App | Kelly Gerber |  | FTS IF - Haritha Komma | [6 empty] | 12015, 18863, 15173, 31776 | SiGaC (Site Gas and Chemical), I-CHEM - Chemical Management System, TRIRIGA, Parts Lifetime - PLT |  | Facilities apps have resource constraints, will be complete after Sprint 23. Impacted B-Apps : SiGaC, I-CHEM, TRIRIGA Interface objects : S/4 LOG1084, ECAFTSIFV765, ECAFTSIFV817, ECAFTSIFV815, LOG1675 | Facilities apps have resource constraints, will be complete after Sprint 23. SiGaC (Site Gas and Chemical management): 4/30/26 I-CHEM (Chemical management and EHS): 3/31/26 Trirega (Space and Real Estate Management): 4/20/26 SiGaC S/4 interfaces and ECA Views can be tested in WW06 (2/6/26) S/4 LOG1084, ECAFTSIFV765, ECAFTSIFV817, ECAFTSIFV815 SiGaC S/4 interface with open defects, test plan TBD S/4 LOG1675 | Factory Automation has been communicating this at PXT for ~2 months. Further pull-in not possible so we are requested this CR | Schedule extension to 4/30 (beyond Sprint 23) Will test in ITC1 for all apps and interfaces | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Boundary%20Applications/Change%20Control%20Tracking/CC%20Request%20Forms%20Submitted/Mfg.%20Integration%20MisCo/CR%20Facilities%20Date%20Change%201_21_26.pptx?d=wa27467f0e4414720ae2db43efdeded2f&csf=1&web=1&e=xeo5Uo |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 11. OSC/CL Rejected (end status) |  |  | 2026-01-29 |  |  |  | 2026-01-30 | CR1654 - Not Approved. Alignment discussion to be held with Roman Vorel, Rebecca Verrette and Stef Maxey. Approval can be provided following the discussion. | [5 empty] | Other | Not Assigned |  | Not Approved | 01, 2026 | 01, 2026 | 2026-01-22 | 0 | < 15 Days | yashuvyas@deloitte.ca |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1655 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 09A. Master Data 17. B-App | lynn.asbury@intel.com | BApps — Kelly Gerber | Data - Julie Fawdington |  | CR1303 | 01895 | NA |  |  | 9360 | SAP Information Steward |  | Update to 9360 -SAP Information Steward for Big 3 Replication Reconciliation Reports | Reconciliation Reports are required to reconcile Material, Customer and Vendor Master Data between MDG and S/4 Systems post replication | CR is required because as per the standard Conversion Object Recon Report efforts are not included. To validate if all the data have been successfully replicated to downstream SAP systems these recon reports would be required. These will be utilized for cutover post replication validation purpose by PS / IT. Additionally, we will continue to use these reports in Production to ensure all data continues to replicate and any issues are mitigated before they result in an MI. | No impact to existing deliverables. | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CRXXXX%20SAP%20InfoSteward%20Replication%20Recon%20Reports.pptx?d=wece81163c5274744ac9a66c92075f40d&csf=1&web=1&e=w5bNvx |  | 11. Boundary Apps-related Change |  | No |  | Medium | 0 | [8 empty] | 1 |  |  |  | 20 | 0 | 1 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-06 | Flipped to approved according to email from Stacee: Hi Anna, I had a 1:1 today with Lynn Asbury and received additional information for Non-LE CR1655. Lynn, cc’d requested that we remove CR1655 from the ww05.5 Change Request Meeting because it requires less than 40 hours of work and doesn't require Core Leadership review for the effort, schedule impact, or any exception requests. The good news is that Candi Linnell already approved this CR last week. The work to add 5 new recon reports fits within the team's planned activities for Sprint 22/23 and aligns with MC1 and ITC1 timing. Lynn is making some minor edits to clarify these details in the documentation for CR1655. Could you please update the status for CR1655 to "Approved" in the CR Log? Thank you. Regards, Stacee | [9 empty] | Other | Tower | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1657 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 12. Infrastructure | rudrsengupta@deloitte.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | CR1142 | NA | NA | [5 empty] | Adjust timeline for two FTS objects impacted by BApp | Adjust timeline for two objects impacted by BApp | Required views will not be ready by the BApp Team | Potentially missing FUT in Sprint 23 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1657_FTS-IF_Adjust%20timeline%20for%20two%20objects%20impacted%20by%20BApp.pptx?d=w19a27109316348fd998a657e2b41197c&csf=1&web=1&e=6EYM77 |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-22 | 76 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1656 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 07. FTS IF 11. Technology | rudrsengupta@deloitte.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Expand Material staging design for FFS/APPS | Expand Material staging design from Lot level to Material + Lot-level for WLA and Backend stages. | Recent discussions with Production scheduling Team (FFS/APPS) discovered that Material staging should not only be based at the Lot level but also it can be at Material Level. The current design only target to replenish the Lot from warehouse to FOL. | Technology Team for making changes to existing objects. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1656_FTS-IF_MaterialStaging_DesignChange.pptx?d=w595ed7fce0004ffba80e9637d68aee70&csf=1&web=1&e=12qsgl |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [8 empty] | 60 |  |  |  |  | 0 | 60 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | FTSE1456, FTSE0507, FTSI1455, FTSI1646, FTSI1647 | 5 | FTSE1456, FTSE0507, FTSI1455, FTSI1646, FTSI1647 | 5 |  | 0 |  | 0 | N/A | N/A | 2026-03-20 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 | Taken straight to CR Meeting |  |  | 2026-01-23 | • Description: Expand Material staging design from Lot level to Material + Lot-level for WLA and Backend stages. • Rationale: Recent discussions with Production scheduling Team (FFS/APPS) discovered that Material staging should not only be based at the Lot level but also it can be at Material Level. The current design only target to replenish the Lot from warehouse to FOL. • Impact: Technology Team for making changes to existing objects. • Discussion - o Context: Original design: Production scheduling (FSCO) provides lot numbers to stage. New ask from FFS/APPS: provide material & qty (no lot), have S4 do batch determination if BI lacks lots. o Concerns: Potential scope increase and risk of recreating site specific RTD kitting logic inside S4; 60 hour estimate challenged as under scoped; requires cross tool alignment (FSCO commitment was “always send lot”). • AR - Rudra Sengupta - Arrange a formal design review (Stef Maxey/Eugene Celis + TD Automation + Shamin Shirodkar/FSCO) to confirm lot number commitment vs. S4 batch determination, and re estimate scope (beyond 60 hrs. if needed). • Decision - Not Approved - Do not proceed until full review with the right SMEs. Re evaluate scope/ownership; avoid “fast tracking” without approvals. | 2026-01-30 | Approved offline with Uzma and aligned with Stef, Roman, Mike |  |  |  | Build | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-22 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1658 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | llejarde@deloitte.com | [11 empty] | Objects in Sprint 23 to be tracked as late for DATE1615,DATE1616_IF,DATE1616_IP,DATI1618_IF,DATI1618_IP | Object completion Sprint to be changes to S24 as Build will be completed in S23 for Automate the PROC material master creation process based on business rules and Automate External BOM | Today’s process is incredibly manual, and user needs to perform multiple steps in SPEED system to trigger this followed by additional steps in SAP system. Additionally, current process doesn't synchronize post-BOM extension updates from SPEED to SAP ECC and to avoid manual intervention |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB253211D-8055-4CD7-A85E-D8136203738D%7D&file=CR1658_MDG_CR%20Object%20Completion%20Sprint%20to%20change%20to%20S24.pptx&action=edit&mobileredirect=true |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-22 |  |  |  | 2026-01-23 | • Description: Object completion Sprint to be changed to S24 as Build will be completed in S23 for Automate the PROC material master creation process based on business rules and Automate External BOM • Rationale: Today’s process is incredibly manual, and user needs to perform multiple steps in SPEED system to trigger this followed by additional steps in SAP system. Additionally, current process doesn't synchronize post-BOM extension updates from SPEED to SAP ECC and to avoid manual intervention • Impact: Not provided in CR Log • Discussion - o A set of automation enhancements for Item/BOM/PDM/MDG data creation and maintenance had previously been approved for ITC2. o These automations were purposely scheduled last in the build plan because they do not impact tower dependencies and priority was given to foundational CRs (e.g., EMIB). o Workstreams involved include Speed, OCPLM, IBDS, and the Translator. o Specs are being completed in Sprint 22. o Build planned for Sprint 23. o Unit testing (FUT) would fall beyond Sprint 23, effectively becoming what the team called “Sprint 24.” o These automations are not needed for: Pre cutover, Data conversion, Any ITC blocking scenario o They still meet the new ITC1 start date even if delivered later. o Business may need additional headcount if automation is not available, especially to maintain proc materials manually. o Without automation, risks include lower data quality, difficulty meeting conversion thresholds, and increased manual workload o Current Build Reality: Two thirds of the work will be complete by end of Sprint 23. Only unit testing remains, needing “a little more time.” Delivering slightly late will make the program "look behind," but is id considered low risk. • Decision - Approved - Work can proceed, but must be tracked as late, not recast into a new sprint and delivered without affecting ITC1 readiness. | [5 empty] | Other | CL/OSC | 2026-01-23 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-22 | 0 | < 15 Days | shrutisingh7@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1659 | New |  | ERP | R3 (Release 3) | Very High | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP | lilibethx.lejarde@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR | Risk-Issue | KDD | [5 empty] | Custom API for MDG to S4 and S4 to MDG | In order to replicate the MPV capability in SPEED, there are item extensions to plants and BOM traversal needed in order to create / automate the External BOM. It cannot be self contained in either MDG or S4 by itself | Without this bi directional Interfaces the capability for Automation of External BOM cannot be completely delivered. | This FS will need to be drafted and approved so that it can be tested along with the DATE1616 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1659_Interface%20for_MDG%20S4%20API%20for%20External_BOM_Automation.pptx?d=w5fce6f77b5bc4b5a9e7f97f121e76e40&csf=1&web=1&e=FcLAoW |  | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-22 | 76 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1660 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | pique@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | n/a | n/a | n/a | [5 empty] | Intel BRF+ - Create Additional Function Modules in S/4HANA | To support BRF+ configuration, we need to create the following two function modules and related components in S/4HANA: ​ | 1) YFI_WHT_DA_CONTROLLER Used as main module handling the communication, BRF invocation and generic validation 2) YFI_WHT_PASS_RESULTS Used as Results passing module | n/a | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-Build-CRXXXX_%20Intel%20BRF%20Effort%20Estimate%20for%20Creating%20Function%20Modules%20in%20S4HANA_2.pptx?d=wef68b0008afe418488baa2dc07a574ab&csf=1&web=1&e=8o86hN |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Pingyi that the details are captured in CR1570 | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-23 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1661 | New |  | ERP | R3 (Release 3) | Low | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 08. FTS IP | Tanmaya HJ | PTP — Kenneth Salazar | PTP - Richard Taylor | Exception approval Requested for Demand Change Request(DCR) Object ID PTPI473 Build to be pushed beyond Sprint 23 as it has dependency on PDH Layer readiness which will be developed by March 1st Week | CR 1348 | [7 empty] | Exceptional approval requested for delay in Build - Object ID PTPI0473 (DCR interface from BY to S4) | For Object ID PTPI0473 - Demand Change Request, development in the PDH layer will only be completed by March 1st week which is essential and must have for Functional Unit Testing to be initiated. The object being complex has to tested End to End with all Integrations and Testing will be pushed beyond Sprint 23. | As data needs to be sent from BY to S4 through PDH to perform change/create Document in S4. Hence, this FUT needs to be put on Hold till the development is completed in PDH layer (Estimated Timeline March 1st week) | Yes Build to be pushed beyond S23 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Sub-team%20-%20Procurement/3.%20Conversions/Purchase%20Order%20Conversion/INT-CR1661.pptx?d=wa8965874cda44f16aa8d6413ecf7949d&csf=1&web=1&e=uL4r70 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-23 | 75 | > 30 Days | thj@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1662 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP 11. Technology 17. B-App | Rishav Kumar | PTP — Kenneth Salazar | PTP - Richard Taylor | [9 empty] | Receive Goods receipt signal from ECC to S4 via ECA | Change required in Logistics Interface for 4B2 Goods receipt signal coming from ECC | A new object need to be designed for this Interface: For the transmission of goods receipt signal from ECC to S4: ECC will send data to ECA and Mulesoft will get the data from ECA and transfer it to S4. The Interface is defined for transaction between ECA o Mulesoft and Mulesoft to S4 |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR1662_PTP%20LE_GR%20replication%20for%20Memory%20for%20Straddle%20Sites%20from%20ECC%20to%20S4%20IP%20via%20ECA.pptx?d=we1df05c4681649f7a83f8dcb8ba50c35&csf=1&web=1&e=HiBnk9 | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  | No | Medium |  | 2 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | LOGI1726 | 3202 | LOGI1726 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | Design was intact, but there was a change in the architecture between ECA/S4/Denodo. | [5 empty] | Other | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-23 | 0 | < 15 Days | rishavkumar4@deloitte.com |  | No |  | In Progress |  | In Progress | No
R2.1MR (Feb 2026) | R2.1 ITC | INT-CR1663 | Approved |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF | R Prem Siddharth | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Update of PGA Codes to Agency codes mapping | Additional PGA configuration mappings for the remaining 11 agency codes in GTS E4H | The PGA authority code assignment to the tariff number was not functioning when classifying the Products with the HS_US tariff numbers. And therefore, PGA records functionality was not working. Through SAP OSS 1308188/2025 SAP suggested to complete the authority code mapping for the 11 agency codes. (FDA agency code mapping is already present, and the 11 agency codes mapping was missing) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B048E96B9-4AE2-4F79-A891-7A2F392CDEFE%7D&file=CR1663_Update%25u00a0of%25u00a0PGA%20Codes%20to%20Agency%20Codes%20mapping_GTSE4H.pptx&action=edit&mobileredirect=true |  | 3. Configuration Change |  | No | Low |  | 1 | [7 empty] | 15 | [5 empty] | 0 | 15 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-30 | Approved by Babu Jadam offline | [9 empty] | Other | Tower | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-23 | 0 | < 15 Days | arumr@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1664 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | lilibethx.lejarde@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR | Risk/Issue | KDD | [5 empty] | PROC BOM Enhancement for DiePrep-2-DiePrep and UNBW | Change in the BOM Structure of Multiple DiePrep-2-DiePrep and UNBW for IP and IF | To update the PROC BOM structure in the existing RICEFW ID DATE0926_IP and DATE0926_IF as per new requirement for both IP and IF, as well as Material Master to generate correct PROC Identifier | this is a enhancement to an existing complex object. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CRxxx_Change%20BOM%20PROC%20for%20DiePrep2DiePrep%20and%20UNBW.pptx?d=w330c211fa86d48ae921b1485c1ba2078&csf=1&web=1&e=ZdhuiT |  | 1b. Solution Design |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-24 | 74 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1665 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 10. Analytics 11. Technology | Prabesh Acharya | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core | Decided to use INT-Build-CR1022 & INT-Build-CR1023 instead of this one. | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1665%20%20(IP)%20ECA%20Report%20for%20reclassing%20LE100%20posting%20to%20individual%20WBS%20and%20original%20home%20cost%20center.pptx?d=w74d29a5bd94a4539a2f311c36fe9b343&csf=1&web=1&e=ODxibr | New Requirement / Scope | 2. New RICEFW / ECA / Build Object | DC-050 |  | High | Very High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-27 | 0 | < 15 Days | manidgupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1666 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 10. Analytics 11. Technology | Prabesh Acharya | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1666%20%20(IF)%20ECA%20Report%20for%20reclassing%20LE101%20posting%20to%20individual%20WBS%20and%20original%20home%20cost%20center.pptx?d=wcc48357afa0e4020b120a558834c66cb&csf=1&web=1&e=Ie67LA | New Requirement / Scope | 2. New RICEFW / ECA / Build Object | DC-050 |  | High | Very High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-27 | 0 | < 15 Days | manidgupta@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1667 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Sahil Syal | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Master Data Asynchronous Response SPEED/ECM to PLM to MDG to S4 | Requirement is to check material master extension is done in S4 systems before sending Asynchronous response to PLM translator from MDG system during SPEED Extend, ECM Create & ECM Change Scenarios. | Data Consistency | R3 ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7049B0A4-81A4-40DB-9DE5-CF90728EB825%7D&file=INT-CR1667_Master%20Data_Asynchronous%20Response%20to%20PLM%20translator.pptx&action=edit&mobileredirect=true | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | 70 | 2 |  |  | 40 | [5 empty] | 70 |  |  |  |  | 0 | 70 | Tech - MDG | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATI0943​, DATI0944​ | 2 | DATI0943​, DATI0944​ | 2 |  | 0 |  | 0 |  |  | 2026-04-09 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-27 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | FUT In Progress | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1668 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data | rausingh@deloitte.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Reltio Name change | Due to BVD EOLD, Reltio plan to remove all ‘LEGAL’ names sourced from BvD in Reltio by December. These names have been used in S4 MDG for SBR & DQM processes. 1.Newname type “AI PREFERRED BUSINESS NAME” should be mapped from Reltio to MDG in both Search Before Create(DATI0391) and DQM Interface(DATI0657) RICEFW. 2.InDQMReport and Custom Table(ZMDG_CUSTMAST) additional column should be add to accommodate the new name type. Additionally, when any of the Reltio names does not match with MDG Name, Legal name will be updated when Admin creates a CR. This logic need to be changed. | Without this change both Search before create and DQM interface will not have Legal and it will have impact on data sync between MDG and Reltio | R3 ITC1 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/2%20Customer%20Master/Change%20Request%20and%20Efforts/INT-CR1668_R3_MDG_New_Name_in_Reltio.pptx?d=w2bb4db3b78934674ad066b590cd6cb90&csf=1&web=1&e=suPw6F | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | 60 | 2 |  |  | 10 | [5 empty] | 26 |  | 34 |  |  | 0 | 60 | Tech - MDG Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATI0391_IP, DATI0657_IP, DATR0390_IP, DATI0391_IF, DATI0657_IF, DATR0390_IF | 6 | DATI0391_IP, DATI0657_IP, DATR0390_IP, DATI0391_IF, DATI0657_IF, DATR0390_IF | 6 |  | 0 |  | 0 | N/A | N/A | 2026-03-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 |  |  |  | 2026-01-30 | Approved for design discussions and exploration | [5 empty] | Build | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-27 | 0 | < 15 Days | bharathkumr@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1669 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | P2P Requirement for multi-line purchase orders | Requirement for multi-line purchase orders | missing requirement for moduslink | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1669%20Requirement%20for%20Multi%20Line%20PO.pptx?d=w6f014d6e888d45929d9ffad2f0e94e21&csf=1&web=1&e=aJsC0G |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPSPPDH0166 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-28 | 70 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1670 | Approved |  | SCP | R3 (Release 3) | High | 05. OTC IP | 5.14 OTC IP - IP Allocation Planning & Order Promise |  | 05. OTC IP | kevin.chan@spinnakersca.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Constraint VMI/LAFI Calc - Rev2 | Added missing requirements / design for original CR1614. | High, allow VMI and LAFI signals to be segregated into two buckets, constraint vs net (above constraint), and prioritized separately. If we do not align VMI/LAFI with CD process, we will prioritize ALL VMI/LAFI dmd over other customer constrained demand. This violates our prioritization rules. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Allocation%20and%20Order%20Promising/3.%20Execution%20Phase/CCB/IP%20DP%20CR1614B%20-%20Net%20Constarint%20VMI%20%20LAFI%20Fcst%20(004).pptx?d=wad9c943d896d457897fa5cc2ecff0fa5&csf=1&web=1&e=greINV |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [5 empty] | 10 | [7 empty] | 10 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | SCPIPAPOPBY0024 | 1 |  | 0 |  | 0 | SCPIPAPOPBY0024 | 1 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | [6 empty] | Design | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects | Complete | Complete | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1671 | Approved |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.3 E2E Process Integration - Process Design |  | 02. E2E Process Integration 04. OTC IF 16. Testing | craig.eastwood@intel.com | OTC — Kevin Brown | E2E - Aishwarya Bhat |  | n/a | RAID # 3112 | n/a | [5 empty] | Commercial Invoice - automation of cumulative value | Automation is needed to track the incremental value of a customer order passing through the IF Factory Network in multiple locations, including any bailed materials. Current design would require OTC-IF to manually track and accumulate Customs/Trade value at each location, and manually populate the Commercial Invoice prior to goods moving to the next location. | Lack of automation would significantly slow IF's ability to ship goods from one location to another within the Foundry Factory Network - a manual process would not be scalable. | TBD - start with an investigative CR | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/Draft%20CR/CR_Commercial%20Invoice%20Automation_OTC-IF.pptx?d=w720a02dbf22447b3afc053003d018cef&csf=1&web=1&e=WtRN3e | Missed Requirement | 0. Request for Investigation |  | Maybe |  | High | 0 |  |  | 80 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-01-29 |  |  |  | 2026-01-30 | Approved for design discussions and exploration | [5 empty] | Other | CL/OSC | 2026-01-30 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1672 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | shashank.kolhe@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Demand Flags in BY CDP for R2 and AI/ML program​ | BY CDP is unable to allow users to filter out nodes (intersections of Product/Customer/PC) that have been expired / or not valid from their Planning Views.​ As a result, we need to bring in attributes that enable users to ensure they’re forecasting the correct list of products.​ Customers Forecasters are seeing products they should not show customers in BY CDP Planning Views​ CD Planners are seeing products that they should no longer be forecasting in BY CDP Planning Views | Improve Data Integrity and Governance​ Enable Customer Forecasters to provide appropriate product visibility to Customers​ Ensure Consensus Demand data integrity by providing ability to filter for only active products​ Assignment node: For Intelligent Fcst (AI/ML) project, these flags are requisite for node assignments (node effective dates) logic and models learning. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CRxxxx%20-%20Demand%20Flags%20in%20BY%20CDP%20R2.pptx?d=w9fdf2f49331344859b61e2810233cc95&csf=1&web=1&e=Whn0li |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 |  |  |  |  | 280 | 200 | [7 empty] | 480 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | N/A | N/A |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-01-27 | • This request is to bring in demand flags to forecast demand. In addition, CD planners would be able to filter better in CDP using the flags. • Work to start WW7 and complete WW12. | [9 empty] | Design | Tower | 2026-01-27 | 01, 2026 | 01, 2026 | 01, 2026 | 2026-01-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1673 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | rodolfo.alarcon@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | Automatic Creation and Update of the EWM Warehouse Product | Implement an automated creation and update of the EWM Warehouse Product (product master warehouse view) when a new material is created/extended, so the required EWM warehouse-level fields (e.g., PACI and Section Indicator) are populated and the product is immediately usable in warehouse processes without manual maintenance in /SCWM/MAT1. | Currently, new materials created in the system do not automatically generate the EWM Warehouse Product view, leading to manual follow-up steps and occasional missing mandatory indicators. | N/A | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B5BFF9564-4E46-4DC5-A4C4-232A003352DA%7D&file=INT-CRXXXX-Automatic%20Warehouse%20Product%20Extension%20in%20EWM.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-28 | 70 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1675 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 05. OTC IP | 5.1 OTC IP - ALL |  | 05. OTC IP 10. Analytics | shawn.mccarthy@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | N/A | N/A | N/A | [5 empty] | Implement New OTC IP Reports | Build new Semantic models to support below 3rd party reports: Finished Goods Material Report Customer Master Report BY Error Log Report RDD OTIF Report | New reports to be developed based on user engagement and BOBJ Reports disposition | views and 3rd party reports will be delivered in ITC2 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/IP%20OTC%20New%203rd%20Party%20Reporting%20Requirements.pptx?d=wab49feac13554ccc9339f8088505fc6e&csf=1&web=1&e=ejSnAm |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [9 empty] | 72 |  |  | 0 | 0 | 72 | N/A | Yes | ECA | 7 | ECAOTCIP7067, ECAOTCIP7068, ECAOTCIP7070, ECAOTCIP7071, ECAOTCIPR7072, ECAOTCIP6969, ECAOTCIP6970 |  |  | 0 |  | 0 | ECAOTCIP7067, ECAOTCIP7068, ECAOTCIP7070, ECAOTCIP7071, ECAOTCIPR7072, ECAOTCIP6969, ECAOTCIP6970 | 7 | 7 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | Approved in Core Leadership | [5 empty] | Other | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | Complete | Complete | No
R3 (Feb 2027) | N/A | INT-CR1676 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.12 OTC IP - TM | Yes | 05. OTC IP | manjunath.shastry@intel.com | [11 empty] | Descope/Cancel:LOGE1131_IP | Cancel/descope LOGE1131. Original Design: custom development to set TM FO status to "In-Execution" after S/4 PGI. FUT review finding: Intel IT advised sending TM FO to GTT once HAWB is received from 3PL is critical. DLT POC result: standard program /SCMTMS/TOR_FO_PROC_BATCH can set status to "Ready for Transportation Execution", which automatically sends the FO to GTT. Use standard functionality-- No custom program needed. | Standard functionality will be leveraged and no custom program needed. TM Standard program /SCMTMS/TOR_FO_PROC_BATCH will be scheduled to run to update the status of TM FO – Batch job Automatic TM functional team have subsequent 3PL object LOGE1130 for which the FS and additional FUT testing/test cases will be managed & added |  | Yes |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1676/EXT%20RE%20Cancellation%20of%20TM%20RICEFW%20-%20LOGE1131%20(%20INT-CR1676).msg?csf=1&web=1&e=UFgUde |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [8 empty] | 130 |  |  |  |  | 0 | 130 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGE1131 | TM Standard program /SCMTMS/TOR_FO_PROC_BATCH will be scheduled to run to update the status of TM FO – Batch job Automatic; TM functional team have subsequent 3PL object LOGE1130 for which the FS and additional FUT testing/test cases will be managed & added |  | 1 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-02-04 | [10 empty] | Other | Tower | 2026-02-04 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-29 | 0 | < 15 Days | gakumaresan@deloitte.ca |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1677 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | niamh.b.doyle@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | 03405 | 03405 | [5 empty] | EWM Passthrough ID design for GFM Factory Order & Returns | Current proposed design to manage Passthroughs in EWM is not workable for Warehouse operations, risk to safety, quality & delays to Factory. | Original Design needs to be revisited. | R3 ITC2 pending Deloitte inputs on design solution and effort estimation. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR_Passthrough%20ID%20design%20risk%20to%20support%20Factory%20Order%20%26%20Returns.pptx?d=wea347032077249309c1c75e37cab9f4d&csf=1&web=1&e=J8XMII |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-29 | 69 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R2 (Hypercare) | R2 Hypercare | INT-CR1678 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Take or Pay Firm Planning | Need to model Take or Pay supplier agreements in the solve vs. current process of post-solve edits. We have supplier contracts and executive strategy that require us to meet minimum requirements on certain corridors (decision has been made to “take” not “pay”). In some cases, we need the flexibility to select which products to put those additional wafers on across a certain horizon (usually modeled for ~1yr horizon). | Account for and analyze inventory impact of min requirements during Supply Week so we can size impacts to financials, supply chain, etc. ​ Decrement/Adjust year 2 requirements based on year 1 volumes by product ​ These edits and threshold quantities are aligned on prior to Supply Week | Schedule will be provided | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/Change%20Request%20-%20Take%20or%20Pay.pptx?d=wad9b9012f34e4e169888fcb366e6539a&csf=1&web=1&e=s21IEJ |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [5 empty] | 80 | [7 empty] | 80 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-03 | Approved offline with Kumar Vytla and Chad Smith | [9 empty] | Design | Tower | 2026-02-03 | 02, 2026 | 02, 2026 | 01, 2026 | 2026-01-30 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1679 | New |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | stephanie.anderson@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Sustainable Demand Edits | We need a method by which FE Planners (or SuperUsers) can edit demand after it is published (CD Pub) from BY CDP downstream into BY IBP (CD for Solvers) to align with manual adjustments that can be made directly in OneMPS and Compass. These edits must be available to us to intercept post-demand publish changes that are driven by late-breaking customer requests, supply planning optimization requirements, and BOM/Item setup or configuration issues. | There have been demand edits required in each cycle post-R2 Go Live and the current SCOUT SQL insert process has a single point of failure making it unsustainable. | will be documented | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CRXYZ%20Sustainable%20Demand%20Edits.pptx?d=w2a64ec009f80479e944c99f0168a0b9d&csf=1&web=1&e=RNsNIX |  | 1. Process Scope / Design Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-30 | 68 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1680 | New |  | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 04. OTC IF 07. FTS IF 17. B-App | rodolfo.alarcon@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | 2684_R3_Interface between ECD and S4/EWM | No | NA |  |  | 8785 | Excursion Containment Disposition |  | Changes in Integration at Middleware Mulesoft from R2 to R3 for object LOGI0519 | Changes to Integration at Middleware level Integration between ECD <-> Mulesoft <-> EWM System requires update at Mulesoft level to transition from R2 to R3 It shall optimize the setup by removing integration with ECA for Product check, changes in timeout duration and eliminate payload transformation requirement between ECD to EWM. Change to Code at Technical level In R3, Status "Open TO" shall permit blocking of Products in Warehouse before Goods Issue , perform archival of historical data from ECD custom table ( greater than 6 months). | Changes at Mulesoft in R3 is required meet R3 design as ECC and ECD integration setups are no longer required after R3 Go Live. It shall remove integration with ECC,ECA and all transformation logic for payload sent/received from ECD. This process will enable ECD to check inventory status and Block product within EWM warehouse before goods issue. R2 Objects with dependencies : LOGI0519 R3 Objects with dependencies, LOGI1601 | This Change will be completed by sprint 23. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/CR-1680_FTS%20IF_EWM_Change%20request%20for%20IF%20ECD%20Integration%20with%20EWM.pptx?d=w176f4ba5bcd8439ab476f2b868d54cec&csf=1&web=1&e=WVrPij |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-30 | 68 | > 30 Days | rhingmire@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1681 | Cancelled |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.12 OTC IP - TM | Yes | 04. OTC IF 05. OTC IP 06. PTP | Shameek Dhir | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Update Freight order status to In execution in case of events received from EWM and 3PL process. | EWM # Currently, the system only processes events where Info Source equals A, P, or S. However, events originating from EWM are received with Info Source = "W".​ As a proposed solution, we need to extend the existing program logic to also accept Info Source = "W". This change will allow EWM-generated events flowing through EWM → TM to be recognized and propagated to GTT, enabling the events to update the corresponding GTT shipment.​ 3PL # Need to check the Info source value coming in case of 3PL | Required to track the shipments that are routed by customer (CRF) |  | Yes | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Shameek Dhir to be GPO rejected |  | Not Assigned |  | Not Approved | #INVALID OPERATION | 01, 2026 | 2026-01-31 | 0 | < 15 Days | shadhir@deloitte.ca |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1682 | Approved |  | ERP | R3 (Release 3) | Very High | 03. FPR | 3.11 FPR - Project Accounting |  | 03. FPR 13. Security 16. Testing | kevin.m.johns@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | this was identified during the FUT phase of the timekeeping app | N/A | N/A |  |  |  |  | Federal | Federal Timekeeping Mobile Application | Develop a Mobile timekeeping applications that enables the user to enter time, approve time, assign delegates from registered mobile devices | Intel Federal Requirement: Accurate/daily time reporting is a Federal audit requirement. Mobile timekeeping provides increased application availability and allows them to enter time with increased accuracy. Fiori Based mobile device is not user friendly. Column names are misaligned with the data entry fields. Screen is not rendered to be read on a phone | 800 Hours New RICEFW -Timesheet Mobile UI 350 Hours New RICEFW -Mobile UI 350 Hours General Function Hours – (100) Scheduled for ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1682%20-%20Federal%20Timekeeping%20Mobile%20Application.pptx?d=w320ff50eda8d45c88c44e8859366dfed&csf=1&web=1&e=F5ZK8P |  | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [8 empty] | 350 |  |  |  |  | 0 | 350 | N/A | No |  | 0 | N/A | 3210 | FPRE1741 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-03-11 | Confirmed to be approved by Uzma and Stacee | [9 empty] | Other | Tower | 2026-03-11 | 03, 2026 | 03, 2026 | 01, 2026 | 2026-01-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1683 | Approved |  | ERP | R3 (Release 3) | Low | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury |  |  |  | INT-CR1383 | [7 empty] | Cancellation of the RICEFW LOGI1715 | LOGI1715 needs to be deleted. This is the object originally intended for connecting SAP EWM and EDDAR via an API call. But in the recent workshop discussions with Naidu and Pari, Intel has agreed to keep data upto 180 days in SAP shared drive and EDDAR would keep them for 10 years. But an interface call is not needed anymore as the business will check data only upto 180 days from SAP. Anything older than that, business login directly to EDDAR. | LOGI1715 needs to be deleted. This is the object originally intended for connecting SAP EWM and EDDAR via an API call. But in the recent workshop discussions with Naidu and Pari, Intel has agreed to keep data upto 180 days in SAP shared drive and EDDAR would keep them for 10 years. But an interface call is not needed anymore as the business will check data only upto 180 days from SAP. Anything older than that, business login directly to EDDAR. |  | No |  | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1683/Re%20EXT%20RE%20EXT%20FW%20EWM-Alfresco%20-%20RICEF%20LOG1411%20.msg?csf=1&web=1&e=UNERmm |  |  | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | LOGI1715 |  |  | 1 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-02-04 | [10 empty] | Other | Tower | 2026-02-04 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-01 | 0 | < 15 Days | sjulury@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1684 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | Naveen Negi | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | Non-GAAP P&L – QTD & YTD Reports | Develop two new Fiori reports to support the Non-GAAP P&L – QTD & YTD comparatives. | Build two new reports to support the Non-GAAP Profit & Loss (P&L)​ 1. Quarter-to-date (QTD) report : ​ Balances with comparisons to prior quarter and prior year (same quarter)​ Show variance and % change for each comparison​ 2. Year-to-date (YTD) report​ Balances with comparison to prior year (YTD)​ Show variance and % change​ | No Impact to Existing Deliverables | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFF3CB1C0-AD23-4F1B-8393-C43A5BE9F63D%7D&file=CR%20for%20NON-GAAP%20P&L%20%25u2013%20QTD%20=&%20YTD%20Reports.pptx=&wdLOR=c738C9AE2-5339-4351-BDC5-4DEA89F0F28F&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-02 | 65 | > 30 Days | poojaagrawal4@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1685 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Material Master Basic Data Conversion Transformation Logic Changes | Below below mentioned changes are required in Material Master Basic Data" 1) HERS Materials 2) HALB Make Materials 3) Number Range for Spare Parts 4) UPIs with both Internal and External Locations 5) Material Freight Group Derivation | Additional Requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4BE0BC1E-9FBD-4CB5-8A30-1922945508D9%7D&file=INT-CR1685.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-02 | 65 | > 30 Days | mshabaz@deloitte.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1686 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.1 OTC IP - ALL |  | 08. FTS IP 11. Technology 13. Security 16. Testing | sonia.azar@intel.com | OTC — Kevin Brown | E2E - Aishwarya Bhat |  | NA | NA | NA |  |  |  |  | Tariff | Integrate Intel BOT to Auto Generate DN with Batch Assigned for Intel Corporation S4 | Enable capability using BOT to auto generate DN for Intel Corporation S4 with Batch ID that meets customer COO requirement assigned | Currently, BOT to auto generate DN in ECC has been deployed. Production validation is underway. Similar BOT needs to be retrofitted for Intel Corporation SAP - S4 | OTC IP Team will be able to provide estimate by March 20th; 2 wks after Sprint 23. We will know then if intercept to ITC1 is feasible or not. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/E2E%20Arch/01.%20E2E%20Architecture/04.%20FTF,%20Workshops,%20Meeting%20Content/Tariffs%20PRT/R3%20Tariffs/Auto_DN_with%20BOT%20for%20Intel%20Corp%20S4.pptx?d=wf2951753d57044f4835c00f813d1c68b&csf=1&web=1&e=HuBW5g | Design / Build Gap | 0. Request for Investigation |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A | 3214 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | Approved in Core Leadership | [5 empty] | Other | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1687 | Approved |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | Inventory/Logistics/FTS — Stef Maxey | OTC IP - Teresa McNicol/Jon Benoist |  | N/A | N/A | N/A | [5 empty] | Additional Fields for Manifest Report | More additional fields are required for Outbound and Inbound Manifest Report Planned Shipment Start Date :- New fields into report output (Outbound Manifest report) Planned Shipment Start Time :- New fields into report output (Outbound Manifest report) W/H Cut off time :- New fields into report output (Outbound Manifest report) 1st Leg MAWB :- New fields into report output (Outbound Manifest report) 2nd FO Status (FO fixed status) : New fields into report selection screen and output screen. (Outbound Manifest report) Gross Amount (Transfer Price – 1st Leg) :- Logic change: Currently the price is fetched for ZTPR condition type in intercompany SO but as per the Trade team this need to be Resale price minus Transfer Price. (Outbound and inbound Manifest report) Country of Origin : - Logic change: Currently report showing the country of origin as per CI form but the country of origin is has to be shown with COO+BatchQTY similar to the ECC report. (Inbound Manifest report) | Those are existing fields in the current manifest report, but we removed them during design with the assumption that XD doesn’t need them anymore. However, due to the complexity of shipment planning in AMS XD, those fields are crucial for consolidating and transporting the 2nd-leg shipment, so we need to add them back to the report. Points 1 and 2: AMS XD needs these fields to plan the 2nd leg to ensure no delays or missed shipments. Point 3: DSV uses this as the key communication indicator for their warehouse to proceed with loading on time and balance resources. Point 6: As per the trade team guidelines. Point 7: As per the ECC report. | No Impact | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/INT-CR1687_IP_inbound_Outbound%20Manifest%20Report.pptx?d=w36067f9dcac7411ebd72ed909165a5a1&csf=1&web=1&e=glsXJS |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 |  |  | 40 | [5 empty] | 63 |  |  |  |  | 0 | 63 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGR1173​, LOGR1172​ | 2 | LOGR1173​, LOGR1172​ | 2 |  | 0 |  | 0 |  |  | 2026-03-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-03 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
|  | INT-CR1688 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | Medium | 01. PMO | 1.2 PMO - Boundary Systems PMO |  | 01. PMO 07. FTS IF 17. B-App | Lisa Honeycutt | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | n/a | 03332 | [6 empty] | ATMES and Enterprise IT Migration - Request to continue discovery phase and assess IAO impact. | ATMES and Enterprise IT Migration - Request to continue discovery phase and assess IAO impact. |  |  | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by the team that as of 2/4/26, they are no longer going forward with this | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-04 | 0 | < 15 Days | lisa.honeycutt@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1689 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | graeme.johnson@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A |  |  |  |  | WIINGS | ATTD/SPTD SLOC Remapping & EWM Storage type Remapping | Consolidating and segregating ATTD/SPTD storage location structure based on new mapping requirements through deletion & rename of legacy storage locations, creation of new ATTD/SPTD specific storage locations, and comprehensive EWM configuration updates. | Current storage location structure lacks proper ATTD/SPTD segregation and clear security classification for Revenue and Non-Revenue material. The new mapping addresses stakeholder requirements for business unit separation for Material Planning, Procurement and Budgeting ​ Allow shared storage locations where operationally justified (IDM/DM sharing GS01/GS02). Legacy storage locations require consolidation to eliminate redundant configurations and align with current operational structure. | R3 ITC1 - Config Change Only | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/EWM/R3-EWM%20BUILD/R3-EWM%20Build%20Plan/Configuration%20Values/Test%20Data%20readiness%20for%20ITC1/CRs%20for%20WH%20%26%20Logistic/CR_Enterprise%20Structure%20ATTD%20%26%20SPTD.pptx?d=w56d55b29f41b48e0b9ed9a32a3a0c5c4&csf=1&web=1&e=06wGZ1 |  | 3. Configuration Change |  | No |  | Medium | 0 | 184 | 14000 | [5 empty] | 184 | [5 empty] | 0 | 184 | Configuration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  | 2026-03-27 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Other | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1690 | Approved |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 4.16 OTC IF - IF R3 FE Supply Planning & Adv Packaging |  | 07. FTS IF | Naren Mangtani | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | N/A | N/A | [6 empty] | S4/PDH - PO Deletions in S4 for Frozen Horizon | Deletions of PO within the Frozen Horizon period in PDH and then sending to S4 was not covered during the design and specs done by all teams. |  | R3 ITC1 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/FTS/R3/CR1690 --S4 Planned Order Deletions.pptx?d=w7bfe537500e0491bae7d7d60ef1c072b&csf=1&web=1&e=xISWuG&xsdata=MDV8MDJ8YW5udGFtQGRlbG9pdHRlLmNvbXxiODQwNGY2ZjAwNGQ0NGYyMDM3MDA4ZGU2ZTVjZWJiOHwzNmRhNDVmMWRkMmM0ZDFmYWYxMzVhYmU0NmI5OTkyMXwwfDB8NjM5MDY5NTQyOTQ1NTYzNTQ4fFVua25vd258VFdGcGJHWnNiM2Q4ZXlKRmJYQjBlVTFoY0draU9uUnlkV1VzSWxZaU9pSXdMakF1TURBd01DSXNJbEFpT2lKWGFXNHpNaUlzSWtGT0lqb2lUV0ZwYkNJc0lsZFVJam95ZlE9PXwwfHx8&sdata=VjZoQ1k3eGJmallFZFlFL3RQQjZkMm8zQ0k1T3hkVWUzQ2Z1Ui8zUVRLRT0%3d | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  |  | 200 |  |  |  | 28 |  |  |  |  | 200 | 28 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIFSPPDH0282 | 1 | 1 | FTSI0311, SCPIFSPPDH0282 | 2 | FTSI0311 | 1 |  | 0 | SCPIFSPPDH0282 | 1 |  |  | 2026-04-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-19 |  |  |  | 2026-02-20 | [6 empty] | Build | CL/OSC | 2026-02-20 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-05 | 0 | < 15 Days | naren.mangtani@intel.com |  | No | Dev Overdue | No Objects |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC1 | INT-CR1691 | Approved |  | ERP | R3 (Release 3) | Very High | 11. Technology | 11.3 Technology - Middleware |  | 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 11. Technology 12. Infrastructure 13. Security 15. Cutover 16. Testing 17. B-App | babu.jadam@intel.com | Infra/Tech/Middleware — Babu Jadam | Tech & Dev - John Camarillo |  | None | 03185 | None | [5 empty] | Setup legacy middleware (PI/PO) for boundary app straddle. | Implement new SAP Process Integration / Process Orchestration (PI/PO) work to repoint ~200 interfaces from SAP Enterprise Central Component (ECC) Production Support FC0 (QA) to ECC Mock environments FM1/FM2 to support IAO R3–R5 boundary application straddle testing and readiness for ITC1 (Integration Test Cycle 1). | Core Leadership decided (12/17) that all R3 straddle testing will use FM1/FM2 (not FC0) except by explicit exception approval, to ensure a consistent 2026 Path-to-Production and production-like test conditions for IAO. This change addresses current constraints where legacy middleware for straddle testing is not set up, creating issues for boundary apps attempting to connect to both FC0 and FM1. FM1/FM2 will be used for ITC1/2/3 and UAT1 (User Acceptance Test 1); FB0 (Bench) for UAT2; FC0 (QA) for UAT3. | Work planned early Feb 2026 through Apr 2026 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Technology/CR1691_Technology_Setup%20legacy%20middleware%20PIPO%20for%20boundary%20app%20straddle.pptx?d=we2a121e0ac7b49e2a3de15ed44a89f16&csf=1&web=1&e=DhYynq |  | 1b. Solution Design |  | No |  | Very High | 0 |  | 175000 | [10 empty] | 2500 | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Other | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-05 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1692 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com |  | OTC IF - Angela Laskowski |  | N/A | [7 empty] | Enable Pallet Label Print Capability | New Product (Square Hill) is requesting the use of Pallet Label printing functionality in EWM and MPL. | New product requires the activation of a system capability in EWM/MPL. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_R2%20Operate_Enable%20Pallet%20Label%20Print.pptx?d=w01ee3d3bb91d4e4e86b9b1e6740b9318&csf=1&web=1&e=JyhBb9 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-05 | 62 | > 30 Days | imme.sandweg@intel.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1693 | New |  | ERP | R2.X (Between Release 2 & 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Vinay Kumar Khandelwal | [11 empty] | Changing width of company name field in various forms | Changing width of company name field in various forms | Since the description of Sales organization SG01 is changed , the adjustment of the name needs to be done in all the forms where applicable |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1693%E2%80%93%20Changing%20width%20of%20company%20name%20field%20in%20various%20forms%20.pptx?d=wd4cf390c944546ab8a7c1c0eafec77f9&csf=1&web=1&e=YLstq2 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-05 | 62 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1694 | New |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | pooja2@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | FPRE0929 | NA | NA | [5 empty] | Cancellation of Fiori UI for Counterparty Maintenance and User Exit to trigger replication to CFIN | Cancellation of Fiori UI for Counterparty Maintenance and User Exit to trigger replication to CFIN | Initially we planned to achieve this functionality in MDG system but later changed to move to CFIN directly and now it can be handled in a standard way. No need of custom object. | NA | No | Core | NA | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/0929.pptx?d=w17fd7dc2e95b485b8f0f7e018d9c2f86&csf=1&web=1&e=Aa2flk |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | No | [12 empty] | Other | Tower |  | Missing Review Date for Approval Level | #INVALID OPERATION | 02, 2026 | 2026-02-05 | 62 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1695 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-05 | 0 | < 15 Days | karthp@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1696 | Approved |  | ERP | R3 (Release 3) | High | 11. Technology | 11.3 Technology - Middleware |  | 11. Technology | ravindra.b.neralakatte@intel.com | Infra/Tech/Middleware — Babu Jadam | Tech & Dev - John Camarillo |  | This is a Tech change to integration due to Redis version update by DBAAS team | NA | NA | [5 empty] | DBaaS – REDIS upgrade impact change | Modify MuleSoft APIs to replace Redis-based functionality with an alternative mechanism, prompted by the Redis 7.x → 8.x upgrade and related to connector compatibility considerations. | Redis is being upgraded from 7.x to 8.x, introducing major-version compatibility considerations for dependent components. The MuleSoft APIs will be updated to eliminate the Redis dependency (replacing it with an alternative mechanism for Autosys based watermark functionality and JWT validation package). Redis 7.x will be no longer supported on new DBaaS platform and Redis 8.x compatible mule connector will take significant time to roll out. | Redis 7.X will not be available after Fed 28. R2, R3 interfaces dependent on Redis will need this configuration change by Feb 27 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/2%20Middleware/CR/CR%20XXX%20-%20DBaaS%20%20REDIS%20upgrade%20impact%20change.pptx?d=wdc23d1a625804f69b122577903d25d21&csf=1&web=1&e=69Cccp |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low -per Object | 0 | [8 empty] | 429 |  |  |  |  | 0 | 429 | Tech - Middleware | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 94 API's and RICEFW's | 1 | 94 API's and RICEFW's | 1 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-05 |  |  |  | 2026-02-06 | [6 empty] | Build | CL/OSC | 2026-02-06 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | N/A | INT-CR1697 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 10. Analytics | prashachauhan@deloitte.com |  |  |  | NA | NA | NA | NA |  |  |  |  | "FPR - Cancellation CR for RICEFW - - FPRI1717 "To import EMS-Source Capacity Free Date (CFD) from ECA to S4 | CR to be cancelled as CFD data is being fetched directly from ECA using Denodo API. | There is no need for this RICEFW to fetch data from ECA to S4 as S4 will be fetching the data directly from ECA using Denodo API. | No impact. | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1697/RE_%20_Cancellation%20Request_%20FPRI1717%20-%20To%20import%20EMS-Source%20Capacity%20Free%20Date%20(CFD)%20from%20ECA%20to%20.msg?csf=1&web=1&e=pGNvfI | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/Cancellation%20CR1697%20%E2%80%93%20FPRI1717%20-To%20import%20EMS-Source%20Capacity%20Free%20Date%20(CFD)%20from%20ECA%20to%20S4.pptx?d=w7d8588a7b6e74485b44b0056daa72a04&csf=1&web=1&e=Fi61Tp | Missed Requirement | 5. Cancel RICEFW / ECA / Build Object |  |  |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 | FPRI1717 | N/A |  | 1 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-25 | [10 empty] | Other | Tower | 2026-02-25 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-06 | 0 | < 15 Days | hatewari@deloitte.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1698 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | Mubashir Ghazi | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Material Master Classification Data additional requirement | Below below mentioned changes are required in Material Master Classification Data 1) Transformation Logic for characteristic "manufacturing Device Name" 2) FERT to HALB Classification Data Changes | Additional Requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD2162D01-A88F-4749-A5EC-19A17E2BC463%7D&file=INT-CR1698.pptx&wdLOR=cC36B28B3-371D-4DC6-BB2F-AD40D3A8929F&action=edit&mobileredirect=true | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [9 empty] | 120 |  |  |  | 0 | 120 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | DATC0076_IP | 1 | DATC0076_IP | 1 |  | 0 |  | 0 |  |  | 2026-03-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-19 |  |  |  | 2026-02-20 | [6 empty] | Build | CL/OSC | 2026-02-20 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-06 | 0 | < 15 Days | mshabaz@deloitte.com |  | No | CR Complete | No Objects |  | Complete | Yes
R3 (Feb 2027) | R3 ITC1* | INT-CR1699 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | ekaterina.potapova@intel.com | FTS (ERP) — Stef Maxey | PTP - Richard Taylor |  | N/a | N/a | N/a | [5 empty] | Enable receiving process for IF FG shipments to selected IP FG warehouses ​ | Additional changes are required in OpenText & IP S4 LOGI0956 interface to enable receiving process for IF shipments in IP Finished Goods 3PL warehouses that do not have capabilities to accept externally manufactured finished goods as of now | Only limited IP FG warehouses (HKA8, MYG6) are enabled for receiving FG shipments from external manufacturers (ODMs, OSATs) using ASN 3B2 signal with order reference number. Other FG warehouses (VN, CD) do not have such capability enabled. Without this CR, this will required intensive analysis and changes on 3PL WMS system for multiple sites not having V11 and will impact R3 Timelines Manual Receiving is not possible due to the high vol receiving or 2000 boxes per day, the recommendation is to follow ‘factory receiving’ process in the impacted 3PLs which requires a special format of ASN 3B2 to be sent to 3PL and a special format of ‘goods receipt’ signal to be generated back to S4 | N/a | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B69BC6154-DFA0-4BD3-99A9-D769D015809E%7D&file=CR%20WH%20Receipt.pptx&action=edit&mobileredirect=true | Missed Requirement | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [8 empty] | 50 |  |  |  |  | 0 | 50 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | LOGI0956 | 1 | LOGI0956 | 1 |  | 0 |  | 0 |  |  | 2026-05-08 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | Try to bring in by a week. 3PL should be optimized in the long-term; this should be marked as an optimization opportunity | [5 empty] | Build | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FUT Not Started | No Objects |  | In Progress | Yes
|  | INT-CR1701 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-10 | 0 | < 15 Days | jose.vargas.lepiz@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1702 | Approved |  | ERP | R3 (Release 3) | Very High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | iathar@deloitte.ca | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A |  |  | 11807 | Factory Communications | WIINGS | Activating the Text and message functionality to Factory Users through factory Comm application | The Technician requires a text message update on their mobile in case the parts are PGI'ed from the EWM location or returned from the factory location to the EWM location. To activate the text functionality the only way to communicate is through the interface from S/4 to FC. FC primarily retains the User config and owns the capability to generate the text messages. | Today the technicians have the capability to receive the text messages on their mobile in case their shipment request is partially fulfilled or rejected by the warehouse operator. | No Impact on Schedule | Yes | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared Documents/General/Implementation/16. Logistics (LE+TM+EWM)/CR/CR1702 Interface to trigger the Text message on Mobile to Maintinance technicians via FC.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | 280 | 19600 | [10 empty] | 1 | 0 | 0 | N/A | Yes | S4 | 1 | LOGI1738 | 3206 | LOGI1738 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-26 |  |  |  | 2026-02-27 | [6 empty] | Other | CL/OSC | 2026-02-27 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-11 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR1703 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-11 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1704 | Approved |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 10. Analytics | Naren Mangtani | FTS (SCP IF) — John Heiney | [10 empty] | 100% xRB Pegging/Accounting | Once lots/wfrs are marked as 100% MRB they should not be pegged or considered commit material all the way till sort commit | Current State: Causes schedule/actuals accounting between Fab/Bump and Sort, as lots w/ 100% projected xRB loss are counted as actuals fr Fab/Bump, but not Sort. Consistency needed for all xRB flagged material, in order to drive proper factory schedule execution & accounting Desired result - Once lots/wfrs are marked as 100% MRB they should not be pegged or considered commit material all the way till end of sort. All systems should match, across all segments too (SPAN, PDH, BY, FSCO, Xeta, POWER). These lots should also not get counted as actuals and net properly |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1704%20%E2%80%93%20100%25%20xRB%20Pegging%20Accounting.pptx?d=wb787f5eb7bb645469cc7ae294805e3c2&csf=1&web=1&e=aZMTjN |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  |  |  | 40 |  | 320 | [6 empty] | 360 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-24 | [10 empty] | Build | Tower | 2026-02-24 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-11 | 0 | < 15 Days | naren.mangtani@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1705 | Approved |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 10. Analytics 13. Security 15. Cutover 16. Testing | joseph.t.chen@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | INT-CR1427 | N/A | N/A | [5 empty] | What-if Demand Prioritization UI | Create 4 separate PDH UIs/views to enable Demand Prioritization What-If analysis for BY-IBP solves. Each UI has the ability to be re-initialized with production, and create a separate demand-ranking procedure that consumes the what-if versions of demand tiering and customer tiering, both provided as new output from the SP-PDH team. | Enable What-If runs in BY-IBP to use different demand prioritization rules and strategies. | Expected to complete early ITC1 (ww20) | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/INT-CR1705_Demand_Prioritization_What-If_UI.pptx?d=w8e127101025c459f84563bbdf2ebbbb6&csf=1&web=1&e=HPCHNk | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 |  |  |  |  | 180 | [8 empty] | 180 | 0 | N/A | Yes | SCP | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 | SCPIPSPPDH0169 | 1 | 1 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | - Connect with Shelly on requirements - Dave Stutzneggar - Schedule meeting with Dave, Shelly, and all to walk through prioritization | [5 empty] | Other | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-12 | 0 | < 15 Days | jon.benoist@intel.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1711 | Approved |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | Yes | 11. Technology | Jorge Sanchez | FTS (ERP) — Stef Maxey |  |  | INT-Build CR1194, CR1336, CR1638 | N/A | N/A | [5 empty] | To update mapping sheet based on business requirement for Bailment Straddle | To update mapping sheet based on business requirement for Bailment Straddle. | The change was identified based on the business requirement and is part of the Straddle architecture definition (CR-1336). |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/03.%20Final%20Deliverables/Build/IP_RICEFW/Internal%20CR%20Deck/INT-%20Build%20CR1194-%20To%20update%20mapping%20sheet%20based%20on%20business%20requirement%20for%20Bailment%20Straddle%20%20.pptx?d=wc3f342295c6a4811915439a5126b5fef&csf=1&web=1&e=a2l0JP |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | LOGI1584 |  | LOGI1584 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-13 | 0 | < 15 Days | anntam@deloitte.com |  | No |  | In Progress |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1706 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Low | 10. Analytics | 10.1 Analytics - ALL |  | 03. FPR 04. OTC IF 07. FTS IF 10. Analytics | vanessa.m.clark@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | INT-CR1594 | N/A | N/A |  |  | 12842, 12208, 59283 | OpenText, E2open, PDF Sapience Manufacturing Hub Integration Platform - IP |  | Analytics ITC2 Exceptions | This CR is to identify all the Analytics deliverables that will be delivered for ITC2 due to various inter-tower design delays, upstream data delivery delays and delayed requirements. | This CR is to identify all the Analytics deliverables that will be delivered for ITC2 due to various inter-tower design delays, upstream data delivery delays and delayed requirements. | 23 analytics object will be delayed to ITC2 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR1594-AnalyticsITC2Exceptions.pptx?d=wfb625ac4ae1f40188891d99e7e582374&csf=1&web=1&e=CQnmsF |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [12 empty] | 0 | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment | 23 | OTCFCV003, ECAOTCIF5086, ECAFTSIFR5715, ECAFTSIFR5720, ECAFTSIFR6697, ECAFTSIFV5725, ECAFTSIFV6228, ECAFTSIFV6233, ECAFTSIFV6229, ECAFTSIFV6230, ECAFTSIFV6231, ECAFTSIFV6232, ECAFTSIFR6696, ECAFTSIFV6714, ECAFTSIFV6715, ECAFTSIFV6716, ECAFTSIFV6717, ECAFTSIFV6718, ECAFTSIFV6780, ECAFPR6055, ECAFPR6147, ECAFPR6166, ECAFTSIFR7085 |  |  | 0 | OTCFCV003 | 1 | ECAOTCIF5086, ECAFTSIFR5715, ECAFTSIFR5720, ECAFTSIFR6697, ECAFTSIFV5725, ECAFTSIFV6228, ECAFTSIFV6233, ECAFTSIFV6229, ECAFTSIFV6230, ECAFTSIFV6231, ECAFTSIFV6232, ECAFTSIFR6696, ECAFTSIFV6714, ECAFTSIFV6715, ECAFTSIFV6716, ECAFTSIFV6717, ECAFTSIFV6718, ECAFTSIFV6780, ECAFPR6055, ECAFPR6147, ECAFPR6166, ECAFTSIFR7085 | 22 | 23 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-12 |  |  |  | 2026-02-13 | [6 empty] | Other | CL/OSC | 2026-02-13 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | Object Missing in OT | In Progress | In Progress | No
|  | INT-CR1707 | New |  | ERP | R3 (Release 3) | Medium | 04. OTC IF | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 04. OTC IF | stacey.ramsdell@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | Partner Owned Equipment Descope | Eliminate all IIF OTC design related to partner owned equipment (POE), including the following: - Update OTC for Capitol Finance Analyst role to not requestable in AGS - All order reason codes related to partner owned equipment | Design is no longer needed. There is only one customer following this process today and the process is too complicated to transition from post contract management (PCM) ownership into SAP due to escrow accounts and billing requirements. Additionally, operations do not expect additional contracts containing partner owned equipment. | None | No | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1707%20Descope%20Partner%20Owned%20Equipment.pptx?web=1 |  | 1. Process Scope / Design Change 1b. Solution Design |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-12 | 55 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1708 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF 08. FTS IP | thienne.johnson@Intel.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | Holistic IF Inventory Reporting | Need holistic IF inventory reporting from S4 for GLO use cases | Few kinds of materials (e.g. Direct Materials for backend sites (managed by 3 PL) and certain types of Indirect Materials) are not recorded in EWM in IF and they are managed only in S4. | There is no impact to R3 ECA deliverables and this will participate in ITC1, although this report may not be ready by WW10 (program timeline) | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Logistics/INT-CRXXXXX-S4Inventory.pptx?d=w726dbe81c96f4fe9b94527c6e738de9d&csf=1&web=1&e=Z6rInG |  | 2. New RICEFW / ECA / Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-12 | 55 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1709 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Release Process in ESP / PDH | Release Process in ESP / PDH | Release Process in ESP / PDH | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CRxxxx%20-%20Release%20Process%20in%20ESP_PDH.pptx?d=wd5667a93fd41482997e65b38ca61b2cc&csf=1&web=1&e=81cSvU |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-12 | 55 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1710 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 13.1 Security - ALL |  | 04. OTC IF | my.mcglothlin@intel.com | Security — Debbie Whitely | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | Add Product and Material Transaction to OTC IF Profile | Add the 2 native Fiori apps: Product List Manage Product Master Data Display Only To the following OTC business user roles: OTC IF CBA Business Manager OTC IF Business Analyst/Program Manager OTC IF Customer Business Analyst OTC IF Pricing Manager OTC IF Rebate Analyst | Needed a list in Excel of the available service MMIDs (DIENs) that are available to bill customers | N/A | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/INT-CR1710%20-%20Add%20Product%20and%20Material%20Transaction%20to%20OTC%20IF%20Profile.pptx?d=wc613acad189548fdb2883eceee400a47&csf=1&web=1&e=lbRYrt |  | 6. Build Security-Related Changes |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-13 | 54 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1712 | Approved |  | ERP | R3 (Release 3) | Medium | 06. PTP | 6.6 PTP - GTS |  | 04. OTC IF 05. OTC IP | Archith Mahindra | PTP — Kenneth Salazar | PTP - Richard Taylor |  | CR0610 | [7 empty] | Fair Market Value in Purchase Orders​ | Availability of Fair Market Value in all $0 purchase orders in S4 systems. | Trade requirement is to have Fair Market Value in all $0 cross-border transactions. Hence for all scenarios like FOC, Warranty Claim / Return, Subcon Repair/Rework we will need to have the fair market price of the goods used in the Purchase order so that the actual value of the good gets sent to GTS, ECA reports, Customs tracker and CI forms. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBEE11045-1300-4C24-90EA-FC5003ED49A5%7D&file=INT-CRXXXX%20PTP__GTS_PO%20Fair%20Market%20Value.pptx&action=edit&mobileredirect=true |  | 0. Request for Investigation |  |  |  |  | 0 |  |  | 80 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-19 |  |  |  | 2026-02-20 | Do the investigative work in 1 week | [5 empty] | Other | CL/OSC | 2026-02-20 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-14 | 0 | < 15 Days | amahindra@deloitte.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1713 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | sheryl.r.haile@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Add DmdWk.3 (Wed) Prelim Solve using Current Cycle Draft CD ​ | Additional Prelim Solve on Wednesday of Inputs Week | Current Thursday Prelim solve has been very successful in finding issues and ahead of Sunday solve, reducing risk of resolve in Supply Week. ​ Current Thursday Prelim solve presents some issues with mismatched current cycle master data and prior month demand – planners spent hours root causing issues that weren’t truly issues but rather a symptom of current MD vs. old CD ​ Currently Thursday Prelim solves only allows team Friday to check and fix ahead of Sunday solve. Wednesday solve allows for a cycle of validation for implemented fixes. | No Impact | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/Wed%20Prelim%20Solve.pptx?d=wab13b06dad40491fa19b6334a1c98420&csf=1&web=1&e=lbaxJJ |  | 1. Process Scope / Design Change |  | Maybe |  | Low | 0 | [5 empty] | 32 | [7 empty] | 32 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-17 | Kumar approved offline | [9 empty] | Design | Tower | 2026-02-17 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1714 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | stephanie.anderson@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Ethernet Dependent Demand for Reporting | We would like PDH to publish the Ethernet Dependent Demand Upload back to ECA making it available for use by planning in their reporting | Ethernet Division Planning has no visibility into the direct vs. dependent segments of their demand. Unlike WiFi & GPU whose DD signal comes from BY MP and is represented as Dependent Demand in BY IBP, Ethernet’s demand is just totaled into one bucket. | No Impact | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CRXYZ%20Ethernet%20Dependent%20Demand%20for%20Reporting.pptx?d=wc95eab8d74934dcca76cc7afda5c7dcc&csf=1&web=1&e=7pUcdA |  | 1. Process Scope / Design Change |  | Maybe |  | Low | 0 | [6 empty] | 40 | [6 empty] | 40 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-02-17 | Kumar approved offline | [9 empty] | Design | Tower | 2026-02-17 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-14 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1715 | Approved |  | ERP | R3 (Release 3) | Very High | 09A. Master Data | 9A.2 Master Data - BOM |  | 02. E2E Process Integration 07. FTS IF 08. FTS IP 09A. Master Data 09B. Data Migration 11. Technology 13. Security 14. OCM 15. Cutover 16. Testing | lilibethx.lejarde@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | INT- CR1013 | RAID | KDD | [5 empty] | Elaboration for Automation of External BOM (DATE1616) | Implement External BOM Extension functionality in MDG , S4 and related SPEED migration with Error Reprocessing Logic | Today’s process is incredibly manual, and user needs to perform multiple steps in SPEED system to trigger this followed by additional steps in SAP system. . Additionally, current process doesn't synchronize post-BOM extension updates from SPEED to SAP ECC. This needs a Elaborate symphony of multiple WRICEF objects | This automation process will not impact the Item/BOM master data conversion in MC1, and hence there are no impacts to any other towers for their dependencies on Item/BOM master data for ITC1 testing. This will be assessed in December when all the priority development is done (looking at ITC2). However due to multiple objects and their orchestration involved, it will be significant effort and coordination | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1715_Elaboration%20for%20External_BOM_Automation.pptx?d=w3e30321b05274758a2ca267d3d123615&csf=1&web=1&e=CydZv3 | Design / Build Gap | 11. Boundary Apps-related Change 1b. Solution Design 2. New RICEFW / ECA / Build Object 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | Very High | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 20 | DATE1737_IP, DATE1737_IF, DATE1736_IP, DATE1736_IF, DATE1735_IP, DATE1735_IF, DATE1734_IP, DATE1734_IF, DATE1733_IP, DATE1733_IF, DATE1732_IP, DATE1732_IF, DATE1731_IP, DATE1731_IF, DATE1730_IP, DATE1730_IF, DATE1729_IP, DATE1729_IF, DATE1616_IP, DATE1616_IF | 3205 | DATE1737_IP, DATE1737_IF, DATE1736_IP, DATE1736_IF, DATE1735_IP, DATE1735_IF, DATE1734_IP, DATE1734_IF, DATE1733_IP, DATE1733_IF, DATE1732_IP, DATE1732_IF, DATE1731_IP, DATE1731_IF, DATE1730_IP, DATE1730_IF, DATE1729_IP, DATE1729_IF, DATE1616_IP, DATE1616_IF | 20 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-19 |  |  |  | 2026-02-20 | [6 empty] | Other | CL/OSC | 2026-02-20 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-16 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | In Progress |  | In Progress | No
|  | INT-CR1716 | Cancelled |  | ERP | [22 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-17 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1717 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting | [14 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | A build CR has been created | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/3201_FPR_DC-050-680-Interface%20for%20importing%20the%20Headcount%20details%20by%20Person%23%20and%20WBS%20element%20combination%20from%20HAT%20to%20S4%20for%20burden%20allocation.pptx?d=w706eddde055946afaae4515e677e866a&csf=1&web=1&e=1dOHxD | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-680 |  | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-17 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1718 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1719 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1720 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1721 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1722 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1723 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1724 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1725 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1726 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1727 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1728 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | winston.ho@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | PDH Memory Planning in BY ESP | 1. PDH logic change to support BY input data at VF level of granularity 2. Add capability in PDH to systematically disaggregate the Memory PRF to Supplier level and further down Supplier Plant level as needed per user provided % split. The received RTF will need to be aggregated back to VF. | BY ESP/IBP need to plan memory at the VF level instead of Assembly/Finish/ODM and business requirement to generate the memory PRF by supplier/supplier plant and aggregating the RTF. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-%20CR1728%20%20Memory%20planning%20capability%20in%20PDH.pptx?d=w12720221c04542e1b77feac37c932732&csf=1&web=1&e=bgJrRl |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-18 | 49 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1729 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR0918_MDG_Material Master_CR Enhancement to create PROC material.pptx INT_CR1013_Extenal_BOM_Automation.pptx | NA | NA | [5 empty] | 5 RICEFW on Master Data Automations to be moved to ITC2 | 5 RICEFW on Master Data Automations to be moved to ITC2 | These 5 objects are confined to Master Data and do not directly impact other towers We prioritized FUTs and CRs that affect core business processes to protect critical outcomes New requirements and clarifications were introduced for these objects, increasing the required build and FUT effort. Potential CR for new scope | This will be for ITC2 | No | Core |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-19 | 48 | > 30 Days | web-form@smartsheet.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1730 | Cancelled |  | ERP | R3 (Release 3) | High | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 11. Technology | hgore@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | We need it for R3 ITC1. | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-20 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1731 | New |  | ERP | R5+ (Post Release 5) | High | 06. PTP | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | [12 empty] | Standardize 3B2 for 3PLs | Enable 3PL IP FG warehouses (VN, CD) to receive FG Shipments from external manufacturers using ASN 3B2 V11 signal with order reference number. Currently only limited IP FG warehouses (HKA8, MYG6) are enabled | Standardization of process and signals. Reference CR #1699 |  | No |  |  |  |  | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-20 | 47 | > 30 Days | againda@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1732 | New |  | ERP | R3 (Release 3) | Medium | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Change Request to Use Confirmation/Material Document Numbers for Reversal and Cancellation | Change Request to Use Confirmation/Material Document Numbers for Reversal and Cancellation | The business would like to use as confirmation numbers or material document numbers to reverse confirmations or cancel material documents, instead of relying on the confirmation text or material document header text as previously agreed design. | Targeted for ITC2 | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-20 | 47 | > 30 Days | vchaudhari@deloitte.com |  | No |  | No Objects |  | N/A | No
|  | INT-CR1733 | Cancelled |  |  | R1 (Release 1) R1 Hypercare R2 (Release 2) R2 Hypercare R2 Q4 '25 Anafi enablement R2.X (Between Release 2 & 3) R3 (Release 3) R3 Backlog R3.X (Post-R3) R4 (Release 4) R5 (Release 5) R5+ (Post Release 5) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-21 | 0 | < 15 Days | elizabeth.perigault@intel.com |  | No |  | No Objects |  | In Progress | No
|  | INT-CR1734 | New |  | ERP | R2 Hypercare | High | 04. OTC IF | 4.8 OTC IF - EWM | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | INT-CR0550 | NA | NA | [5 empty] | Copy Text Information From Delivery line Item To Shipping Label | Copy new text information (End Customer PO) from Outbound delivery line item to shipping labels. | Customer requirement request(s). | NA | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX.pptx?d=w39c47839e4284fc088684f01cc2da576&csf=1&web=1&e=5SGEzd |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-23 | 44 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1735 | Approved |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | joseph.t.chen@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | 2DN enhancement: Forecast cannot be tied to a xdock location | BY-CDP: Both nodes and billing/backlog will be created at the xDock in accordance with the 2DN design. Ensure the final CD Qty Pub is NOT assigned to an xDock location. Ensure billing and backlog loaded at the xDock are visible to demand planners during forecast entry. Option 1: Enhance the disaggregation logic to exclude all disaggregation drivers at the xDock location (e.g., backlog, customer/sales forecast, statistical forecast). Option 2: Expire all nodes associated with the xDock location, while keeping measures loaded at the xDock visible to demand planners during forecast entry. | Demand follows revenue, and revenue is generated only from SO1 (xDock → Customer). SO2 (CW → xDock) is excluded from the transactional data feed to avoid double counting. As a result, nodes are created at the xDock and forecasts are disaggregated to the xDock. However, all downstream systems (FNE, ESP, OP) expect forecasts to be associated with a CW location. The ask is to identify a solution in CDP that ensures forecasts remain associated only with the CW location. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP%20DP%20CR1735%20-%202DN%20Forecast%20not%20assigned%20at%20xDock.pptx?d=w9bf475dc825d4781bf3a6c57615a451a&csf=1&web=1&e=D0BuMw |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 |  |  |  | 40 | 40 | [8 empty] | 80 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Design | CL/OSC | 2026-03-27 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-24 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1737 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | OTC — Kevin Brown | [10 empty] | Purging Docking files older than 180 days | Docking process saves images on the file system in EWM system. They need to get deleted on an ongoing basis. Any file that is older than 180 days need to get deleted to maintain the File system's performance. | Docking process saves images on the file system in EWM system. They need to get deleted on an ongoing basis. Any file that is older than 180 days need to get deleted to maintain the File system's performance. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/CRs/INT-CR1737%20Purging%20Docking%20files%20older%20than%20180%20days.pptx?d=we7873ae41b644c29b840af17c2b0811e&csf=1&web=1&e=mEd5cr | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 54 |  |  |  |  | 0 | 54 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | LOGE1277 | 1 | [6 empty] | 2026-05-18 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-05 |  |  |  | 2026-03-06 | [6 empty] | Build | CL/OSC | 2026-03-06 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-24 | 0 | < 15 Days | sjulury@deloitte.com |  | No | Dev Not Started |  |  | In Progress | Yes
|  | INT-CR1736 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.8 FTS IP - IP R2 Supply Planning |  | 08. FTS IP | joseph.t.chen@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | DemandProductGrp feed | ​To enable demand-mix what-if scenario planning in BY-IBP, it is essential that both S&OP and Demand stakeholders operate with a consistent demand product hierarchy and common terminology. Currently, CDP (Demand) leverages a localized demand product hierarchy, where Level 3 DemandProductGrp is dynamically generated within DP-PDH. The request is to integrate DemandProductGrp from DP-PDH into SP-PDH and subsequently into IBP, where it will be modeled as a product attribute within BY-IBP (D360) to support aligned planning and scenario analysis. select distinct ITEM_ID, DMD_PROD_CD, DMD_PROD_GRP, DMD_PROD_GRP_ACTIVE from SUPPLY_CHAIN.PDH_COMMON_XFRM.V_BRD_ITEM_CORE_PIT where DMD_PROD_GRP_ACTIVE = 'Y'; | Medium, to allow S&OP to perform demand-mix what-if in BY-IBP. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/IP%20SP%20CR1736%20-%20DemandProductGroup%20feed.pptx?d=w3309ad86ed8b495a828cb8f4a7a35d31&csf=1&web=1&e=sooRqu |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-24 | 43 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1738 | Rejected |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 02. E2E Process Integration 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 09A. Master Data 10. Analytics 11. Technology 14. OCM 16. Testing 17. B-App 18. SCP | Shishir Kumar Dwivedi | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Enabling multiple shipment per SO line item | This change request covers two key business requirements: Enabling multiple shipments per line item esp. for IP as customer Business process change to ensure CMIR records are updated without complete delivery indicator and over/under delivery tolerance is updated as per customer needs Interface to PDH change to include complete confirmation regardless of SO complete delivery indicator Ensure R3 batch processes correct sequencing/timing to support E2E fulfillment process Updating Sales Orders after Delivery creation based on R3 POLP table Refer new POLP table in R3 instead of Market Code to determine items relevant for POLP Ensure the quantity update on Sales Order happens only after Final Delivery is created for give line item, Quantity is determined based on all deliveries created per line item Enable quantity update on SO for over delivery scenario after final delivery creation |  |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEFEBF370-3945-46D7-95D3-A3624441AD8C%7D&file=OTC%20-%20Enabling%20Multiple%20Shipments%20Per%20SO%20Line%20Item%20-%20Draft.pptx&wdLOR=c89A39E88-AE24-4B43-94B5-3E6D8E602F5E&action=edit&mobileredirect=true | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2026-03-05 |  |  |  | 2026-03-06 | CR1738 Not Approved. ARs required for CR resubmission: End to End Impact Review (IP/IF/Planning), Fully Identify and Tie Out B-App Impacts, Update and Finalize the Effort Estimate, Confirm IP Readiness for Partial Receipts and Netting Logic, Validate Cross Team Alignment. | [5 empty] | Build | CL/OSC | 2026-03-06 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-24 | 0 | < 15 Days | shisdwivedi@deloitte.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1739 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP 11. Technology 12. Infrastructure | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | [5 empty] | Open |  |  |  | Change Request for change in design architecture requirement for Reporting Scrap of Semi Finished Goods at IF manufacturing location interface FTSI1693​ | Change Request for change in design architecture requirement for Reporting Scrap of Semi Finished Goods at IF manufacturing location interface FTSI1693​ FTSI1693:​ As per the current approach, there is an issue where data filtered to IP-owned inventory is sent from IF ECA to IP ECA, and the same data is duplicated when moving from IF FTS Inventory to IP FTS Inventory .​ To support the business requirement for accurate scrap reporting in IP S/4, the new design approach will eliminate middleware and post scrap using the SFT route. In this design, the ECA team will place files in a shared folder, and an SAP program will read the files from the shared folder via SFT and post scrap in the IP S/4 system.​ ​ The data exchange will be facilitated using ​​ IF straddle locations- CIBRIF ECA(reuse); IF ECA to Shared folder :SFT  I IP S4( New)​ ​ For error handling via this interface send consolidated error record file to PDL as an attachment. ​ After posting records in IP S/4, store the successful record files in the shared folder.​ | Change Request for change in design architecture requirement for Reporting Scrap of Semi Finished Goods at IF manufacturing location interface FTSI1693​ FTSI1693:​ As per the current approach, there is an issue where data filtered to IP-owned inventory is sent from IF ECA to IP ECA, and the same data is duplicated when moving from IF FTS Inventory to IP FTS Inventory .​ To support the business requirement for accurate scrap reporting in IP S/4, the new design approach will eliminate middleware and post scrap using the SFT route. In this design, the ECA team will place files in a shared folder, and an SAP program will read the files from the shared folder via SFT and post scrap in the IP S/4 system.​ ​ The data exchange will be facilitated using ​​ IF straddle locations- CIBRIF ECA(reuse); IF ECA to Shared folder :SFT  I IP S4( New)​ ​ For error handling via this interface send consolidated error record file to PDL as an attachment. ​ After posting records in IP S/4, store the successful record files in the shared folder.​ |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/03.%20Final%20Deliverables/Build/IP_RICEFW/Internal%20CR%20Deck/XXXX%20-%20Change%20Request%20for%20change%20in%20design%20architecture%20requirement%20for%20Reporting%20Scrap%20of%20Semi%20Finished%20Goods%20at%20IF%20manufacturing%20location%20interface..pptx?d=wf716c0c2ee18480d9d8f61ee095b0230&csf=1&web=1&e=YhQqXN | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 85 | 0 |  |  | 5 | [5 empty] | 80 |  |  |  |  | 0 | 80 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | FTSI1693 | 1 | [6 empty] | 2026-06-12 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-05 |  |  |  | 2026-03-06 | [6 empty] | Build | CL/OSC | 2026-03-06 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-24 | 0 | < 15 Days | akindore@deloitte.com |  | No | Dev Not Started |  |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR1740 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.2 FPR - Tax |  | 03. FPR | tafunk@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | INT-CR1570 | NA | NA | NA |  | NA | #INVALID VALUE |  | RICEFW Cancellation request for FPRE1722_CFIN and FPRE1723_CFIN | we plan to cancel the RICEFW object FPRE1722_CFIN and FPRE1723_CFIN, which supports the BRF+ integration with Central Finance (CFIN). The reason for this cancellation is that BRF+ functional modules will not be needed in the CFIN instances—it will be used only in the IP and IF instances. | The reason for this cancellation is that BRF+ functional modules will not be needed in the CFIN instances—it will be used only in the IP and IF instances. | No impact. | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1740/FW_%20FPRE1722_CFIN%20and%20FPRE1723_CFIN%20_%20RICEFW%20Cancellation.msg?csf=1&web=1&e=a01ONj | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/_EXT_%20RE_%20FPRE1722_CFIN%20and%20FPRE1723_CFIN%20_%20RICEFW%20Cancellation.msg?csf=1&web=1&e=cY0fVj | Missed Requirement | 5. Cancel RICEFW / ECA / Build Object |  | No | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A |  |  | 0 |  |  |  |  | FPRE1722_CFIN, FPRE1723_CFIN | N/A |  | 2 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-04 | [10 empty] | Other | Tower | 2026-03-04 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1741 | Approved |  | ERP | R3 (Release 3) |  | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 06. PTP 11. Technology 18. SCP | sunil.k.parida@intel.com | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Sub or Double Bailment for IP for R3 | Sub or Double Bailment for IP for R3 | As sub bailment process is implementing in ECC by virtue of that it will be part of R3 Scope for IP |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR1741%20-%20Double%20Bailment%20MMG400_R3%20Design.pptx?d=w61ca71c3a2c9426bb69337ee5a93369e&csf=1&web=1&e=yOgFTn |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [8 empty] | 40 | 160 |  |  |  | 0 | 200 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | LOGI0156, LOGE0952, LOGI0267 | 3 | [6 empty] | 2026-05-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-26 |  |  |  | 2026-02-27 | [6 empty] | Build | CL/OSC | 2026-02-27 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-25 | 0 | < 15 Days | anntam@deloitte.com |  | No | FS Overdue |  |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC2 | INT-CR1742 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 Backlog | Medium | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 08. FTS IP 15. Cutover 16. Testing | devendra.srivastava@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | 3163, 3600, 3601 & 3605 | N/A |  |  | 59283, 41627 | #NO MATCH |  | Post Sprint 23 Efforts for PDF SMH IF and IP | Build phase efforts and associated risks that the IP PDF SMH & IF PDF SMH project team will be doing after the end of Sprint 23 (March 6) | IF PDF SMH will have post Sprint 23 build related activities due to low priority development (1 orchestration for retention data to ECA), functional unit testing and upcoming application release testing IP PDF SMH will have post Sprint 23 build related activities due to functional unit testing and upcoming application release testing | No IAO schedule changes only IF PDF SMH & IP PDF SMH project schedule impacts (extension of build phase) | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1742%20Post%20Sprint%2023%20Efforts%20for%20PDF%20SMH%20IF%20and%20IP.pptx?d=w02a792cb78844d839c8d7af5befa3188&csf=1&web=1&e=546tg6 |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-02-26 |  |  |  | 2026-02-27 | [6 empty] | Other | CL/OSC | 2026-02-27 | 02, 2026 | 02, 2026 | 02, 2026 | 2026-02-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R2 (Hypercare) | R2 Hypercare | INT-CR1743 | Approved |  | SCP | R2 Hypercare | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | jeffrey.maclaren@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Eff Date Import | Source the Eff/Disc dates in the Production method table externally to BY to prevent date management directly in BY UIs | Drive data governance upfront for the Eff/Disc dates, versus using the BY Prelim solve to validate the data​ Efficiency of data management by persisting the data externally to prevent master data changes from overriding the data in BY | Required after WW12 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/TEAMSIntelSpinnakerServices17053-A001/Shared%20Documents/2.1%20Business%20Design/Business%20Readiness%20Opens/Change%20Requests/INT-CRxxxx%20-%20Eff%20Date%20Import.pptx?d=wf2d2ecdf9de74f8aba283cf415aaf156&csf=1&web=1&e=Uli3wY |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [5 empty] | 40 | [7 empty] | 40 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-09 | • CR1743: Approved, option 1. o CR Title: Eff Date Import o Change Description: Source the Eff/Disc dates in the Productionmethod table externally to BY to prevent date management directly in BY UIs.  Option 1: Create an import UI in BY IBP for IBP Production method FE for Eff Date and Disc Date fields, requires manual (excel) Data Governance (most flexible with multiple updates). | [9 empty] | Design | Tower | 2026-03-09 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1744 | Approved |  | ERP | R4 (Release 4) | High | 03. FPR | 3.14 FPR - Boundary Apps |  | 03. FPR 13. Security 17. B-App | kevin.m.johns@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | INT-CR1682 | N/A | N/A |  |  |  |  | Federal | R4 Federal Timekeeping Mobile Applications | create 3 additional capabilities for Intel Federal mobile timekeeping supporting Timesheet Entry, Manage Delegates and Report + Get Help | Intel Federal Requirement: Accurate/daily time reporting is a Federal audit requirement. Mobile timekeeping provides increased application availability and allows them to enter time with increased accuracy. Fiori Based mobile device is not user friendly. Column names are misaligned with the data entry fields. Screen is not rendered to be read on a phone Design was based on Deloitte Internal timekeeping app and in their process, they created an independent mobile app Team spent weeks trying to correct the current design and make it usable | No impact to schedule | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CRxxxx%20-%20R4%20Federal%20Timekeeping%20Mobile%20Applications.pptx?d=w851a03771c984ee5b85fab6b4b580571&csf=1&web=1&e=nHiEen |  | 1b. Solution Design 2. New RICEFW / ECA / Build Object 6. Build Security-Related Changes |  | No |  | High | 0 | [8 empty] | 610 |  |  |  |  | 0 | 610 | Tech - Boundary App | Yes | S4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | FPRE1560​, FPRE1562​ | 2 | [6 empty] | 2026-10-02 | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-11 | Confirmed by Uzma and Stacee to be approved offline | [9 empty] | Other | Tower | 2026-03-11 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FS Not Started |  |  | In Progress | Yes | Yes
|  | INT-CR1745 | New |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.13 OTC IP – Returns (Logistics Management) | Yes | 05. OTC IP 11. Technology 13. Security | kimberly.moore@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | N/A | [7 empty] | R3 IP Returns ¦ COO determination for CI/PL outbound | In case of customer returns, after the receiving and disposition is completed for the returned material, the requirement was to generate Commercial invoice and packing list forms. Country of Origin information was previously required to be printed referencing the EWM tables but now the requirement is to change the logic and print it based on information available in S4 | Initially the requirement was to give the user the flexibility to perform receiving in EWM for materials where batch details were unknown by assigning a dummy batch to it and hence manually enter the Country of origin information for such items. Now, trade has raised concerns and proposed to remove any manual intervention for such items. For such items, the COO information should come out of the latest batch manufactured for that item. | Change to be implemented in ITC2 | No | Core |  |  |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 41 | > 30 Days | brthigpen@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1746 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1747 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1748 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1749 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1750 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1751 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1752 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1753 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1754 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-26 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1755 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1756 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1757 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1758 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1759 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1760 | Cancelled | [34 empty] | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | No | [13 empty] | Tower |  |  |  | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1761 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1762 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1763 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1764 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | brthigpen@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1765 | New | Ready: Wednesday | ERP | R3 Backlog R3.X (Post-R3) R4 (Release 4) R5 (Release 5) R5+ (Post Release 5) | Medium | 02. E2E Process Integration | 2.4 E2E Process Integration - Cross Functional Topics |  | 02. E2E Process Integration 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 09A. Master Data | craig.eastwood@intel.com | Data & Analytics - Rebecca Verette | E2E - Aishwarya Bhat |  | n/a | n/a | n/a | [5 empty] | Intel Federal equipment procurement and management | Intel Federal’s business is expanding due to increased demands from the US Govt. Intel Federal needs to be able to place orders on Intel Foundry to purchase, assemble and manage various tooling/M&E on their behalf. | The current IAO design for this is manual, and with increased business demand, would likely be cumbersome for Intel Federal to manage. This is an Investigational CR to determine whether Intel Federal can leverage the existing PO/SO and WBS element process (LE-199 on the IP instance placing orders on LE-101 on the IF instance) and then having IF install and manage the finished tool/M&E as part of the Partner-Owned Equipment (POE) process. | New business requirement. Intel Federal understands that functionality may not be available by R3, unless existing PO/SO and POE (Partner-Owned Equipment) processes can be leveraged. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/E2E/CR_Intel%20Federal%20Equipment%20Ordering_link%20to%20IF_POE%20process.pptx?d=wfb4e63926a6145979e394cbcddb4ea47&csf=1&web=1&e=lkiDJH |  | 0. Request for Investigation |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 40 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1766 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting | [14 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | A build CR has been created | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1766%20%E2%80%93Interface%20for%20Importing%20the%20Xesus,%20Mars%20volume%20details%20from%20ECA%20into%20S4%20file%20path.pptx?d=w7a028788f9574bd0a59a662325b463b5&csf=1&web=1&e=uQEk2s | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-680 |  | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1767 | Cancelled |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.11 FPR - Project Accounting | [14 empty] | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | CR to be cancelled, no longer needed. | A build CR has been created | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1767%20%E2%80%93%20Consume%20HAT%20details%20and%20Xesus,%20Mars%20volume%20details%20from%20S4%20file%20path.pptx?d=wb2c1b3c25df9403982a6bd460679c89c&csf=1&web=1&e=7XKRIu | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object | DC-050-680 |  | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION | 02, 2026 | 2026-02-27 | 0 | < 15 Days | suresavula@deloitte.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1770 | Approved |  |  | R3 (Release 3) | High | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 04. OTC IF 05. OTC IP 09A. Master Data | andrew.t.austin@intel.com |  | Data - Julie Fawdington | [9 empty] | MDG weight program enhancement for IF HALB | Enhance existing MDG weight program to use IP FERT material weight to update the IF HALB materials | Due to separation of IF/IP, the movement of a finished product from IF to IP must be arms length, including the recording of weight of shipment. Current BP does not include weighing of shipment between IF to IP FG Warehouse to minimized the waste in processing and avoid the need of processing lanes. Even though IF to IP handoff occurs by pushing a cage across the warehouse from IF factory dock to IP receiving, certain country specific requirements for actual weight to be captured. Current MDG weight program enhancement will only provide updated weights for MM’s that are actively being weighed at shipment. Without enforcing weighing of IF “test” or “finish” shipments, the |  |  |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CRxxxx_MDG%20MM%20weight%20program%20enhancement%20for%20IF%20HALB.pptx?d=w7b20b3be485c474ab99bb02762ac7ca5&csf=1&web=1&e=prqZQU | Design / Build Gap | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 18 | [5 empty] | 36 |  |  |  |  | 0 | 36 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | DATI0508 | 1 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-12 |  |  |  | 2026-03-13 | [6 empty] | Build | CL/OSC | 2026-03-13 | 03, 2026 | 03, 2026 | 02, 2026 | 2026-02-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1769 | Cancelled | [22 empty] | Current BP does not include weighing of shipment between IF to IP FG Warehouse to minimized the waste in processing and avoid the need of processing lanes. | [11 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-02-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1771 | Cancelled | [22 empty] | Current MDG weight program enhancement will only provide updated weights for MM’s that are actively being weighed at shipment. Without enforcing weighing of IF “test” or “finish” shipments, the |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-02-27 | 0 | < 15 Days | imme.sandweg@intel.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC3 | INT-CR1772 | Approved |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 07. FTS IF | elena.kaufman@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | Noted as part of R2 Hypercare | n/a | n/a | [5 empty] | Time Phased Capacity Upside modeling | Enhance the PRF calculation by enabling BY ESP to model wafer capacity upside in a way that generates a more gradual profile of die availability. This is needed in the ESP_BEUNCON scenario used to generate BE PRF signals, but would modulate capacity on the Fab stage. | Provide a more reasonable & realistic forecast to Intel Foundry and our other OSAT partners. | pending IT feedback | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/IP%20SP%20CR1772%20-%20Time%20Phased%20Capacity%20Upside%20modeling.pptx?d=wb0e85d9fcf0f4ed0ad538b98492fafc2&csf=1&web=1&e=NAolVt |  | 1. Process Scope / Design Change |  | No |  | Medium | 0 |  |  | 40 |  |  | 160 | [7 empty] | 160 | 0 | N/A | No |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Design | CL/OSC | 2026-03-27 |  |  |  | 2026-02-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1773 | Approved |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | NA | 03541 | NA | [5 empty] | 2DN: Customs déclaration création before GR in 2DN process | Import declaration must be created in GTS before the GR is done in S4 for the IBD’s in 2DN process. ( Only valid for NL location ) | GTS E4H will be creating and filing the import declarations to the NL customs authorities by referring the open IBD documents which are importing materials into NL. The Current design for the 2DN process is to have the IBD created and GR done in a single program thereby marking the IBD as complete before the declaration is created in GTS. Since there are no open IBD documents, the declaration are not getting created via the automation program. ​ | No Impact | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B03A7270F-15BC-4DCB-9470-F2A34C667FC4%7D&file=INT-CRXXXX%20LOG__GTS_Customs%20declaration%20creation%20before%20GR%20in%202DN%20process.pptx&wdLOR=c4853B34F-B7CD-443B-90EB-D0AC24CE2DBB&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 80 | [5 empty] | 50 |  |  |  |  | 0 | 50 | Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | LOGE1114​, LOGE1147​, OTCE1420, OTCE1421​, OTCE1505​ | 5 | [6 empty] | 2026-05-22 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-05 |  |  |  | 2026-03-06 | [6 empty] | Build | CL/OSC | 2026-03-06 |  |  |  | 2026-02-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No | Dev Not Started |  |  | In Progress | Yes
R3 (Feb 2027) | N/A | INT-CR1774 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 09B. Data Migration | shivax.shankar.harikrishnan@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | NA | NA | NA | NA |  | NA | #INVALID VALUE |  | RICEFW Cancellation request for RICEFW FPRE1716 IP and IF | Cancellation of RICEFW FPRE1716(IP,IF) | The conversion logic in FPRE1716 will be merged with FPRC1724. Hence the RICFEW FPRE1716 will be redundant. Hence requested for cancellation. | No impact. | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1774/GPO%20approval_%20PAT%20Conversion%20object_%20Request%20for%20be%20cancelled.msg?csf=1&web=1&e=rz5pPj | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/New/EXT%20RE%20PAT%20Conversion%20object_%20Request%20for%20approval.msg?csf=1&web=1&e=dn6F8A | Missed Requirement | 5. Cancel RICEFW / ECA / Build Object |  | No | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  | PTPE0471 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A |  |  | 0 |  |  |  |  | FPRE1716_IP, FPRE1716_IF | FPRC1724_IP, FPRC1724_IF |  | 2 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-04 | [10 empty] | Other | Tower | 2026-03-04 |  |  |  | 2026-03-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | N/A | INT-CR1775 | Approved |  | ERP | R3 (Release 3) | Low | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR 10. Analytics | shivax.shankar.harikrishnan@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | NA | CR1434 | NA | NA | NA |  | NA | #INVALID VALUE |  | Cancellation of CR1434 New GL balance recon report_R3 | Cancellation of CR1434 New GL balance recon report_R3 | The recon report for GL trial balance will be developed based on R1 scope. In R3, the balances will be different across all the three S4 instances. Hence, the R3 Trial balance report is not required. | No impact | Yes | Non-Core | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/CR1775/IT-GPO_%20FI%20Recon%20report%20for%20R3_Request%20for%20approval.msg?csf=1&web=1&e=GBQkWv | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/CR%20Approval%20Emails/New/EXT%20RE%20FI%20Recon%20report%20for%20R3_Request%20for%20approval.msg?csf=1&web=1&e=4C0XMO | Missed Requirement | 5. Cancel RICEFW / ECA / Build Object |  | No | Low | 0 | 1 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A |  |  | 0 | [7 empty] | 0 | 04. Tower/Horizontal Approved (end status) | No |  | 2026-03-04 | [10 empty] | Other | Tower | 2026-03-04 |  |  |  | 2026-03-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1776 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP 11. Technology 17. B-App | Chandrakanth Elancheran | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | 2DN Vendor assignment in PDH & Delivering plant determination in SO2 | Existing Vendors representing component warehouses (CWs) are configured in a way that prevents the Logistics 2DN wrapper program to process inbound delivery & GR at the Cross-dock plant. Setup an additional vendors (with plant code maintained in Search term 2 filed) in MDG per CW. Have the PDH assign these 2DN vendors when processing transfer requests for CW -> Cross dock movement orders, rather than the existing vendor associated to the CW. Supplying plant determination For SO2 | Currently, the vendors representing CWs are configured with their source plant configured in the standard field (WERKS). This works for standard STO’s. 2DN scenarios (specifically the Logistics 2DN wrapper program) requires vendors to be treated as external vendors (with no plant vendor maintained) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/DRAFT_CRXXXX%20PDH%202DN%20VendorID%20assignment.pptx?d=wc0096d6af8de4cb1a8798b64b4e8e28e&csf=1&web=1&e=0HnK5O |  | 13. Other Milestone Adjustments |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  | Not Approved | #INVALID OPERATION |  | 2026-03-03 | 36 | > 30 Days | celancheran@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1777 | New |  | ERP | R3 (Release 3) | Medium | 10. Analytics | 5.11 OTC IP - Order Management |  | 05. OTC IP | Nupur Kumari | [11 empty] | Creation of the view "consignment_sales_order_fulfilment_planning_log" till Snowflake layer in IP DEV1 | This data set is required to determine the SOURCE location of the supply that is fulfilling the XDOC in support of a 2DN SO. This is essential attribute for every Vehicle Load Line data set that is generated by PDH as input to BY ESP during subsequent solve runs. | Change was identified during recent sprint when PDH team started VLL design and development. Current ECA mapping to enable VLL in PDH turned out to be incorrect and this required detailed design discussions b/w PDH, S4 and ECA teams to arrive at the data gaps and to be solution approach |  | No |  |  |  |  | 1. Process Scope / Design Change |  |  |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 1 | OTCPCV051 |  |  | 0 | OTCPCV051 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-03 | 36 | > 30 Days | njalaliheravi@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1778 | New |  | ERP | R3 (Release 3) | High | 05. OTC IP | 5.11 OTC IP - Order Management |  | 05. OTC IP | Chandrakanth Elancheran | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Update to the M&A Custom conversion utility tool (OTCE0719) | Based on the feedback from development team, this effort will span multiple sprints as the work consists of both front-end Fiori development (involving multiple screens) and substantial backend programming. The below list of functionalities are to be achieved in OTCE0719 Mass external SO upload/conversion based on the template Internal open sale orders conversion –This includes Identifying the open orders in the existing system (in a specific sales organization as an example) & creating an upload file as a result, which then can be uploaded to create orders under a different sales organization – This is based on a Merger/Acquisition. Mass Order cancellation(mainly to support the above internal order conversion process, once the open orders are converted into target Sales Org, the open orders in source sale org has to be rejected) Flexibility in translation data – the translation data (XREF’s) can be maintainable, so that this tool can be used across multiple Mergers & Acquisitions over time. Reconciliation reports to review pre & post data (with colored differentiation on the results) Summary screens for the results (for the executions in foreground) | Feedback from development team on the custom conversion object’s (OTCE0719) complexity in developing all the requirements(listed above) as part of the object. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX-M%26A%20Custom%20Conversion%20Utility%20Tool(OTCE0719).pptx?d=w1c867bd616aa48c5ba44e95dcfd8df8c&csf=1&web=1&e=J01KJd |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  | Not Approved | #INVALID OPERATION |  | 2026-03-03 | 36 | > 30 Days | celancheran@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1779 | New |  | ERP | R3 (Release 3) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR | sureshx.avula@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | 1) Need to create new custom table to maintain legacy WBS, Opex WBS, Asset...etc. 2) Hence user will maintain the data with frontend, need Fiori app.3) Additional logic to be added to existing Object FPRE0883 | NA | NA | [5 empty] | Static custom table in S/4 to enable Legacy (not converted) WBS MD for DPN calculation​ | Business Requirement: Create static table in S/4 and add: 1. Legacy WBS element, 2. CEID, 3. OpEx WBS L1, 4. ECC Asset Number, 5. ECC Sub-Asset Number, 6. AMIC eligible (Y/N), 7. S/4 Asset Number, 8. S/4 Sub-Asset Number, ​ S/4 AssetECC AssetECC WBS​ Update S/4 logic (RICEFW 0883, 1650) to get legacy data from static table when Capital WBS element not found in the Asset.​ 1) Asset master, Opex L1 WBS elements should be available in S4.​ 2) Actual depreciation posted with point 1 asset number in S4.​ S4 Changes: 1) Need to create new custom table to maintain legacy WBS, Opex WBS, Asset...etc. 2) Hence user will maintain the data with frontend, need Fiori app.3) Additional logic to be added to existing Object FPRE0883 | Today in ECC, 640K active assets are linked to 104K Capital WBS elements that are or will closed before the R3 go-live in May 2027. Because closed WBS elements will not be converted, the associated assets in S/4 will lack the originating WBS master data. ​ Two key S/4 capabilities depend on data fields that exist only in Capital WBS master data: CEID, OpEx WBS Level 1. These fields are required for: 1). Depreciation disaggregation from Primary → Secondary Cost Centers 2). OCOS/PCOS split logic in S/4 and downstream SAC models. (RICEFW 0883, 1650), ​ Without the WBS data in S/4, depreciation posted to these assets cannot be allocated correctly, resulting in: 1). No Primary-to-Secondary cost center split, 2). No OCOS flow into Spending and Capital models.​ | ~640K ($78b) current assets may be impacted by not having WBS related data flowing into the S/4 Depreciation calculation logic. | No | Core | Open Discussion still in progress, requested to keep it as Draft until aldo, mark and the rest align on this | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/Change%20ID_FPR_CR%20Deck_template%20-%20Static%20custom%20table%20in%20S4%20to%20enable%20Legacy%20WBS%20MD%20for%20DPN%20calculation.pptx?d=w55840aaebba64f11be74588036894464&csf=1&web=1&e=KX7A4e |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-03-04 | 35 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1780 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 08. FTS IP 10. Analytics 17. B-App | stephanie.anderson@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | none | none | none | [5 empty] | Historical supply planning data migration | This is needed to migrate the historical supply planning data from AIR to ECA to support future ML/AI/deep analysis projects. | AIR SQL license will expire in 2029, and all data feeds will be shut off at R3 go live. To support ML/AI/Deep Analytics projects, this data needs to be migrated and hosted on our next gen platform (ECA). | TBD | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-AIRData.pptx?d=w052043815463401d9c9f1383f416243f&csf=1&web=1&e=Z3zzla |  | 11. Boundary Apps-related Change 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-04 | 35 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1781 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | Piyush Ashok Patil | PTP — Mike Nayab | PTP - Richard Taylor | Need to capture GTS Fair Market Value for PO types such as Free Goods, Bailment, Warranty Return and Subcontracting (Repair/Rework) Orders | [5 empty] | 42860 | #NO MATCH |  | Fair Market value Determination using custom code/logic during the replication of the Purchase Order (PO) in GTS | To achieve this, leverage the existimg custom code/logic developed under OTCE1668 IF/IP that accurately computes the fair market value during the replication of the Purchase Order (PO) in GTS.​ Tech team needs to build wrapper program to re-use the logic to pass the FMV to Bapp(s) e.g: Cutoms Tracker.​ ECA reports much be enhanced to include fields for Fair Market Value, ensuring accurate and comprehensive reporting.​ The Commercial Invoice form must be configured to populate the Fair Market Value field, supporting compliance and trade requirement. | This change is required to determine Fair Market value during the replication of the Purchase Order (PO) in GTS | No major impact on current go-live plans. | No | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared Documents/General/Implementation/06. PTP/3 Final Deliverables/2. Build/Change Request Decks/INT-CR1781 - Fair Market value Determination using custom code logic during the replication of PO in GTS.pptx?web=1&xsdata=MDV8MDJ8YW5udGFtQGRlbG9pdHRlLmNvbXw2MTI5YWRlNmFlNDU0NjMyMTI2YTA4ZGU3YmQ1MTdlMHwzNmRhNDVmMWRkMmM0ZDFmYWYxMzVhYmU0NmI5OTkyMXwwfDB8NjM5MDg0MzUyNTQ5MDgyOTk5fFVua25vd258VFdGcGJHWnNiM2Q4ZXlKRmJYQjBlVTFoY0draU9uUnlkV1VzSWxZaU9pSXdMakF1TURBd01DSXNJbEFpT2lKWGFXNHpNaUlzSWtGT0lqb2lUV0ZwYkNJc0lsZFVJam95ZlE9PXwwfHx8&sdata=eXJYQzNaQkVweUlRb2hpMFYydUVHcWljRU9vNjJHUHJzOXZwTGc3QnhMbz0%3d |  | 1b. Solution Design 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 |  |  | 200 | [5 empty] | 216 |  |  |  |  | 0 | 216 | Tech - S/4 | Yes | S4 | 1 | PTPE1740 | 3212 | PTPE1740 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | PTPI1137_IP, PTPI1137_IF, PTPE1465_IP, PTPE1465_IF, OTCE1668_IF, OTCE1668_IP, LOGF0353, LOGF0344, LOGF1524, LOGF1525, LOGF0359 | 11 | OTCFV011, OTCPV031, OTCFV017 | [5 empty] | 2026-06-05 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-05 |  |  |  | 2026-03-06 | [6 empty] | Other | CL/OSC | 2026-03-06 |  |  |  | 2026-03-04 | 0 | < 15 Days | pvemuri@deloitte.com |  | No | FS Overdue |  |  | In Progress | Yes
|  | INT-CR1782 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Medium | 03. FPR | 10.1 Analytics - ALL |  | 03. FPR 10. Analytics 17. B-App | jorge.calderon.calvo@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A |  |  | 9008 | #NO MATCH |  | iCost Forecast needs IP Wafer Starts views for the R3-R5 straddle | iCost needs additional Wafer Starts views for the R3-R5 straddle | iCost needs additional Wafer Starts views for the R3-R5 straddle | iCost can't build/test Wafer Starts and Parameters until ITC2 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-iCostWaferStartsData.pptx?d=wb0bcaf3712d44f49bf98a4dbb96fb096&csf=1&web=1&e=Gpmp93 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 3 | ECAFPRV884, ECAFPRV2205, ECAFPRV2271 |  |  | 0 |  | 0 | ECAFPRV884, ECAFPRV2205, ECAFPRV2271 | 3 | 3 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-04 | 35 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1783 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 07. FTS IF 08. FTS IP | R3 (Release 3) | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Zero Qty Co-Product Definition for IP Production Orders & Build Instructions | Zero Qty Co-Product Definition for IP Production Orders & Build Instructions | Issue: IP will order PROC’s and COPO’s with expected tolerances as a result of the process / stage being ordered. The result from an order may include COPO’s that were not ordered / desired, however, IP will get inventory on the items as closure of the order. IP must have a process to receive the non-desired / unexpected COPO’s. Example: 1. IP Orders 1000 Wafers with 10,000 Die units, IF creates matching Sales Order. 2. Result of production process ends with 6 different COPO’s instead of 5 that were ordered. SAP will need to be able to receive the 6th COPO but without it being on the Production Order and IF Sales Order the GR cannot occur. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Management/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/Build%20Instructions/INT-Build-CR1783.pptx?d=w38b0a41972a8402090b8b0840edf4be2&csf=1&web=1&e=IOvBui | New Requirement / Scope | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-05 | 34 | > 30 Days | daklnu@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1786 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-05 | 0 | < 15 Days | daklnu@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1784 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-05 | 0 | < 15 Days | daklnu@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1785 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-05 | 0 | < 15 Days | daklnu@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1789 | New |  | ERP | R2.X (Between Release 2 & 3) | High | 03. FPR | 3.1 FPR – GL Close & Consolidate |  | 03. FPR | vivekx.sahni@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider | [9 empty] | New Tasks at Consolidation Level | Update an existing task and create 6. | For management reporting process to differentiate the type of transaction. Also, will help identifiy outages easily. | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1789%C2%A0%E2%80%93%20Creation%20of%20new%20tasks%20at%20Consolidation%20level.pptx?d=w96bcde2100eb45b89a2afc8fac47b522&csf=1&web=1&e=h2Yzyf | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-05 | 34 | > 30 Days | cesarx.gonzalez.martinez@intel.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1790 | Approved |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) R4 (Release 4) R5 (Release 5) | Medium | 13. Security | 13.2 Security - Cyber/ App Security |  | 13. Security | deborah.whitely@intel.com | Security — Debbie Whitely | Security - Raj Valluri |  | NA | NA | NA | [5 empty] | $0 CR to update the milestone dates in Non-ERP SOW | This $0 change request updates the milestone dates in the Non-ERP SOW to reflect the revised timelines for R4 and R5 related to the LE Merge and to align with the original SOW’s design support date. | The current milestones are based on the prior IAO timelines and need to be updated to align with the revised timelines. | NA | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6E6E173E-531B-4276-8C8F-5E7B852A3BA0%7D&file=INT-CR0604%20-%20Change%20Order%20to%20Non-ERP%20Security%20and%20Controls%20SOW1.pptx&action=edit&mobileredirect=true&previoussessionid=222e7567-add3-1595-332d-8eb80f2d1217 |  | 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 04. Tower/Horizontal Approved (end status) | No | No | 2026-03-10 | Confirmed to be approved offline by Debbie Whitely and Uzma Ahmed | [9 empty] | Other | Tower | 2026-03-10 |  |  |  | 2026-03-06 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1791 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 08. FTS IP 09A. Master Data 10. Analytics 15. Cutover | isaac.utter@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  |  | 03578 | [6 empty] | HBI Manufacturing Flow Changes | HBI Process Flow changing that will generate change to align with physical flow and invoice point. There are three factors 1. OTC needs to invoice for the item that is inventoried a. In this case it is the XX DP item 2. When there is an inventory audit, it is good for the items in SAP to match what is on the factory floor 3. IP BY needs top die inventory broken out by DLCP | HBI changes impacted multiple towers |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1A373758-5279-4E01-864B-36D62D9CFDC9%7D&file=CR1791%20-%20HBI%20Manufacturing%20Flow%20Changed.pptx&wdLOR=cF14076D3-4EF0-48FC-AB52-0A358A99C52F&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-06 | 33 | > 30 Days | haritha.komma@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1793 | Cancelled |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | [16 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-07 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1792 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | amy.loomis@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | Original design was to utilize BY native capabilities to manage the plan. Concerns about BY system availability due to potentially long solves has caused us to reconsider old design. | No Raid | N/A | [5 empty] | Plan Approval in PDH (instead of BY UDT) | Move the Plan Approval process from BY UDTs to PDH UI. | The plan that is sent to suppliers will be more accurate resulting in less re-planning reduced waste/inventory resulting from misaligned production to demand. Also allows for more labor flexibility as planning work will not be restricted to specific time windows. | Need IT feedback here. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/IP%20SP%20CRxxxxx%20-%20Plan%20Approval%20in%20PDH%20(vs.%20BY%20UDT).pptx?d=w70374e32749a4ae6b3f2e22293f37ad6&csf=1&web=1&e=JIKV5e |  | 1b. Solution Design |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-07 | 32 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1794 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | [12 empty] | Credit memo requests & Debit Memo requests are incorrectly triggering "Net Value" errors in the Incompletion Log, even when the net value is zero. This issue causes unnecessary error flags and disrupts the processing of valid credit memos & debit Memos. | Credit memo requests & Debit Memo requests are incorrectly triggering "Net Value" errors in the Incompletion Log, even when the net value is zero. This issue causes unnecessary error flags and disrupts the processing of valid credit memos & debit Memos. | This is needed to process the Credit memo & Debit Memo when the net value is zero. This solution will process the credit memo requests 7 debit memo requests with out any errors when the net value is zero Currently, due to the zero net value the program is not allowing the CMR’s to process as its showing as incompletion log. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX-%20Zerovalue%20on%20a%20CMR%20or%20DMR%20should%20not%20put%20order%20on%20incompletion%20.pptx?d=wf9772c13f6544d00b11b11ba0b50a4bb&csf=1&web=1&e=9FKPva | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-07 | 32 | > 30 Days | vkumarkhandelwal@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1795 | Cancelled | [24 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-07 | 0 | < 15 Days | vkumarkhandelwal@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1796 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | Solomon.Levinrad@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | N/A | N/A | N/A | [5 empty] | Scripting_U_Item_Planning_Type | The current design makes users manually select values for ITEM. U_Item_Planning_Type. However, this is not only a very cumbersome process when populating master data for R3, especially when the team is going through multiple iterations of data creation for testing and validation, but also carries the risk of users entering wrong value for the field or accidentally leaving this field blank. As a result, the team came up with logic to determine values for ITEM. U_Item_Planning_Type. We would like to change this to a scripted field for data completeness and validity on top of reducing users’ manual workload. | By making ITEM. U_Item_Planning_Type a scripted field instead of manual entry field, improvements we expect are: - Reduce manual labor work from selecting U_Item_Planning_Type from all items in the table - Reduce risks of selecting incorrect values - Reduce risks of accidentally leaving the field blank and affect downstream tables | Need IT team's feedback | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRxxxx-Scripting_U_Item_Planning_Type.pptx?d=wda0f2e8908614548b30ebd273af5a93f&csf=1&web=1&e=xV0To3 |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-07 | 32 | > 30 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1797 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP 18. SCP | Solomon.levinrad@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | n/a | n/a | n/a | [5 empty] | Ability to load planning demand to drive QRV builds | Add capability for planners to maintain planning demand to drive QRV builds. | To enable release of new products there is always a need to initiate a Quality, Validation, and Reliability (QRV) build through the supply network. This demand needs to be highly prioritized and may eventually be sellable but cannot safely be assumed immediately so. To align with as-is process where QRV is planned as production up to the ATM location we need ability to maintain this QRV dieprep or stacked dieprep demand in a system and for BY to treat it as incremental demand with a high priority. This is not a new business requirement and was originally captured in ISCPP-2960 | IP PDH SP: Backend Build 1 week and UI Build 2 weeks. Required by final UAT cycle | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR-%20Ability%20to%20load%20planning%20demand%20to%20support%20QRV.pptx?d=w8080a37fbe1b424dace50e7c41200fe3&csf=1&web=1&e=YSqOtT |  | 1b. Solution Design |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-09 | 30 | Not New | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1798 | Approved |  | ERP | R3 (Release 3) | High | 06. PTP | 6.2 PTP - Procurement |  | 06. PTP 11. Technology | murthykp@deloitte.com | PTP — Mike Nayab | PTP - Richard Taylor |  | N/A | N/A | KDD59 - PM080-050 PO Close | [5 empty] | New Enhancement requirement to read production order changes and automate text purchase order updates for OSAT business | As part of OSAT business process a text purchase order is created for production order to support the invoicing. But with huge volume of production orders and changes, significant manual effort would be required to manually change purchase orders (close, change qty, change delivery dates). The proposed enhancement will enable delivery completion indicator to be set automatically for the text purchase order once the production order status is set as DLV or TECO. | 1. With this custom program scheduled as background job, the production orders and text purchase orders would be in sync and Text PO will reflect the correct picture 2. This would remove the manual intervention by business to modify text purchase orders. | Planned to be developed before ITC2 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B10B91D74-66FB-4219-ACD3-3E913C1BF002%7D&file=INT-CR1798%20New%20Enhancement%20required%20to%20read%20production%20order%20status%20and%20changes%20and%20automate%20text%20PO%20%20closure%20for%20OSAT%20process%20(1).pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cbareddy%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNjAyMDEwMTEyMCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 |  |  | 50 | [5 empty] | 60 |  |  |  |  | 0 | 60 |  | Yes | S4 | 1 | PTPE1742 |  | PTPE1742 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | PTPE0958_IP | 1 | [6 empty] | 2026-05-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 |  |  |  | 2026-03-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FS Overdue |  |  | In Progress | Yes
|  | INT-CR1799 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | Low | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 17. B-App | symon.k.thelappillil@intel.com | Data & Analytics - Rebecca Verette | OTC IP - Teresa McNicol/Jon Benoist |  | New request made from Price Team | - | - | [5 empty] | Price Data Source Update | Price team landed Price Information for Standard Disti Price, Recommended Customer Price and List Price on ECA/Snowflake. They asked Boundary App to use this source instead of DBaaS and Denodo. | Price team requested this logic change. | Change can be completed in time for ITC1. We will take an Exception if not delivered in time. | No | Non-Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Olga Moskaleva-Hughes to not be required | Other | Not Assigned |  |  |  |  | 2026-03-09 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1800 | New |  | SCP | R3 (Release 3) | Low | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | deepikax.c.mohan@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | MP Object Descope | MP objects descoped based on LE changes | MP objects descoped based on LE changes | none | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/CRxxx%20-%20CR%20template%20for%20SP%20descope.pptx?d=wa165322ab187495e807f342a751d7ef7&csf=1&web=1&e=2Yv9Q8 |  | 1. Process Scope / Design Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-09 | 30 | Not New | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1801 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 1.2 PMO - Boundary Systems PMO |  | 17. B-App | Arjun Puri | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | 3703, 3515 |  |  |  | 31937, 31939, 31906​, 31935,​ 31936​, 21691​, 32287 | #NO MATCH |  | FUT Data Availability for Factory Automation Apps​ | Available Planning data is not sufficient for complete testing of Factory Automation Apps. Data for these kitting apps requires full end-to-end integration between PDH, Blue Yonder, FFS/MARS, with matching data in each system and a BY solve​ ​ App List: ​ 31937 Tape and Reel Die Inventory Kitting​ 31939 BAICOM Kitting​ 31906​ Assembly Die Inventory Kitting​​ 31935​ Reel Shipping Queue (Kitting) ​​ 31936​ Die-to-wafer-kitting​​ 21691​ Manufacturing Kitting Control​ 32287 FFS / APPS​ ​ ​ | Connected data is not available in development environments.​ Purpose of this CR is to highlight that FUT was not done as completely as desired on FA apps, which will increase our risk of defects in ITC cycles​ impacting SCP, Manufacturing , B-Apps Kitting apps (listed in CR)​ | none | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9ACCA8C5-686A-4B62-B757-F70D739B8A77%7D&file=CR%20FUT%20Data%20Avail%203_10_26.pptx&wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&action=edit&mobileredirect=true |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  |  |  | Low | 0 |  | 0 | [11 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-11 | 28 | 15-29 Days | elizmurphy@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1802 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 07. FTS IF 08. FTS IP | R3 (Release 3) | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Automate UDF Table Updates for Revised BI Sales Order Changes (Including Material Type Validation)​ | The change enables automated UDF table updates for all revised BI-Sales Order changes (including Ship-To, RDD, quantity, and cancellations), excludes manual CBA updates, and adds validation to replace rejected FERT entries with HALB in the UDF table.​ Automated UDF table updates via the revised Build instructions (BI): Update the revised BI so all fields available in the revised BI are included in the automated updates to the UDF table.​ Exclude manual Sales Order changes from automation: Manual changes made by the CBA should not trigger or be included in the automated UDF table updates.​ Ship-to updates flow to UDF: Ship-to updates on the Sales Order (SO) performed via 1126 should flow through to the UDF table.​ Sales Order updates ( via BI interface) flow to UDF: The following SO updates performed via the revised BI should flow through to the UDF table:​ Requested Delivery Date (RDD) changes​ Quantity (Qty) changes​ Cancellations ( Rejection )​ Adding a line (unexpected CoPo)​ UDF material validation (FERT → HALB handling): Validation step to check FERT material rejection in the UDF table and ensure the rejected FERT entry is replaced with HALB material, as applicable.​ Anafi specific fields to be updated as Lot Type, Customer lot number, Delivery Priority, Special instructions, PO number, Item number, Required Quantity, Special Instructions. | Ensure the UDF table consistently reflects system-driven updates from the revised BI and SO transactions, while avoiding unintended overrides from manual CBA adjustments.​ Improve downstream reliability by ensuring key SO changes (Ship-to, RDD, Qty, cancellations) are synchronized and traceable.​ Reduce data exceptions by adding a clear validation rule for FERT rejection and HALB substitution in the UDF table. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Order%20Managment/FS_Ready%20for%20Review/Order%20Management/O-020%20Capture%20Orders/Build%20Instructions/INT-CR1802-Automate%20UDF%20Table%20Updates%20for%20Revised%20BI%20Sales%20Order%20Changes%20(Including%20Material%20Type%20Valid.pptx?d=w30a827e9a8ad405584ffd5c53c5972eb&csf=1&web=1&e=dPsdJt | New Requirement / Scope | 0. Request for Investigation 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  | 40 | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-11 | 28 | 15-29 Days | plakshmipadmaja@deloitte.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1803 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Change Request to Develop a utility for mass change of production orders via load file in SAP S4 system | Change Request to Develop a utility for mass change of production orders via load file in SAP S4 system | This CR is associated to create new RICEFW for mass change of production orders via load file in SAP S4 system. Business requires an SAP S4 HANA enhancement to support mass updates of production orders using a user-uploaded template (Excel/CSV). Today, users must update production orders manually, which is time-consuming and increases the likelihood of data entry errors. especially when large volumes of orders require changes to key fields such as quantities and dates. The proposed functionality will enable users to download a standardized, filter-based template of eligible production orders, make controlled updates offline, and upload the file via a dedicated SAP program. The program will validate the file for completeness and accuracy, process only valid records, and automatically apply updates in SAP with appropriate error handling and traceability, improving efficiency, consistency, and data quality. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1803%C2%A0-%20Change%20Request%20to%20Develop%20a%20utility%20for%20mass%20change%20of%20production%20orders%20via%20load%20file%20in%20SAP%20S4%20system.pptx?d=w71fa2735cc8d4423b3e3a59959a2fb3e&csf=1&web=1&e=yg60hv | New Requirement / Scope | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FTSE1739 | 3207 | FTSE1739 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-12 |  |  |  | 2026-03-13 | [6 empty] | Other | CL/OSC | 2026-03-13 |  |  |  | 2026-03-11 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC1* | INT-CR1804 | Approved |  | ERP | R3 (Release 3) | High | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | shira.koerbel@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | New RICEFW ID for Cash Concentration for Cross-Currency Current Accounts | Generation of a new RICEFW ID for “Cash concentration functionality for cross-currency current accounts – IHC relevant.” | FPRE0880 was originally created as a placeholder for DMEE updates relevant to APAC, but it was then changed to "Cash concentration functionality for cross-currency current accounts - IHC relevant.“ Thus, the purpose of this CR is to generate a new RICEFW ID for "Cash concentration functionality for cross-currency current accounts - IHC relevant." | N/A | Yes | Core | Created to replace FPRE0880 with a new RICEFW ID | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1804%20Intel%20Cash%20Concentration%20for%20Cross%20Currency%20Current%20Accounts.pptx?d=w293212c327e64f5caba7e2192dc9a0d5&csf=1&web=1&e=hYBN5Q |  | 2. New RICEFW / ECA / Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | FPRE0880 | 3208 | FPRE0880 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 |  |  |  | 2026-03-12 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1805 | Approved |  | ERP | R3 (Release 3) | Medium | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | tiffany.sorrell@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | Increase the DARC reports that need to be delivered in ITC2 | Increase the DARC reports that need to be delivered in ITC2 | Due to complexities encountered during the development and FUT of views and reports, there are DARC reports that need to be delivered in ITC2. | Delayed reporting delivery to ITC2 | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXXXX-FPR-DARCReportingExceptions_Mar%2726.pptx?d=w2280500893c54379ba4128f8099fab48&csf=1&web=1&e=iuLOax |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | ECA N/A - Milestone Adjustment | 15 | ECAFPR6015, ECAFPR5964, ECAFPR5996, ECAFPR6081, ECAFPR6082, ECAFPR6083, ECAFPR6084, ECAFPR6085, ECAFPR6093, ECAFPR6108, ECAFPR6109, ECAFPR6110, ECAFPR6776, ECAFPR6814, ECAFPR7060 |  |  | 0 |  | 0 | ECAFPR6015, ECAFPR5964, ECAFPR5996, ECAFPR6081, ECAFPR6082, ECAFPR6083, ECAFPR6084, ECAFPR6085, ECAFPR6093, ECAFPR6108, ECAFPR6109, ECAFPR6110, ECAFPR6776, ECAFPR6814, ECAFPR7060 | 15 | 15 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-12 |  |  |  | 2026-03-13 | [6 empty] | Other | CL/OSC | 2026-03-13 |  |  |  | 2026-03-13 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1806 | New |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 07. FTS IF 10. Analytics 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | [9 empty] | DMD POR Schedule Redesign | Change BlueYonder Si POR to be used for manufacturing commit, where changes outside the frozen horizon are established using parameter-feasible calculation (MPS-based format) Demand POR schedule will continue to be generated for reference (back-projection of CMAD Orders and RTS), but with zero frozen horizon. It will reflect a pure customer order signal which could be earlier or later than the POR Schedule | Mfg schedules, based on Demand, drove unstable schedules outside the frozen period, resulting in excess manual over-rides and confusion to stakeholders |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1806%20-%20DMD%20Schedule%20Redesign.pptx?d=w9a0243e75eee499fbf28ec425477a108&csf=1&web=1&e=CLMevl | Design / Build Gap | 1b. Solution Design 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-13 | 26 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC3 | INT-CR1807 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | PROC Item changes | HERS part creation for newly created UPI parts | Additional Requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1807%20-%20PROC%20Item%20changes.pptx?d=w1ac39ed193f44debac038e60580ad062&csf=1&web=1&e=uBkQqu |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 28 | [5 empty] | 81 |  |  |  |  | 0 | 81 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | DATC0068_IP, DATC0072 | 2 | [6 empty] | 2026-07-24 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Build | CL/OSC | 2026-03-27 |  |  |  | 2026-03-13 | 0 | < 15 Days | mghazi@deloitte.com |  | No | FS Not Started |  |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC2 | INT-CR1808 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Conversion Basic data changes (UPI, UOM, Co-Product Indicator) | 1. UoM conversion for Spares ?Business requested to get Unit of Measure from file based Instead of retrieving from HANA DB as UOMs are incorrect. 2. Co-Product Indicator to be set for items ( Finish , Test, STACK(WLA), Die-Prep class ) | Additional Requirement |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1808%20-%20Conversion%20Basic%20data%20changes%20(UPI,%20UOM,%20Co-Product%20Indicator).pptx?d=wa177d4c75d97483d963aac3f019ace24&csf=1&web=1&e=Lp30DL |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 22 | [5 empty] | 117 |  |  |  |  | 0 | 117 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | DATC0068_IP​, DATC0071_IP | 2 | [6 empty] | 2026-07-17 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Build | CL/OSC | 2026-03-27 |  |  |  | 2026-03-13 | 0 | < 15 Days | mghazi@deloitte.com |  | No | FS Not Started |  |  | In Progress | Yes
R3 (Feb 2027) | R3 ITC3 | INT-CR1809 | Approved |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Conversion Classification assignment (STACK_COMBO & STACK_SILICON) | Two new item classes (STACK_COMBO & STACK_SILICON) require item assignment setup?BUMP and DIE PREP need reclassification during conversion |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1809%20-%20Conversion%20Classification%20assignment%20(STACK_COMBO%20%26%20STACK_SILICON).pptx?d=w0f89561fad2d48f38b913b00f502d4e8&csf=1&web=1&e=pie4qq |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 32 | [5 empty] | 72 |  |  |  |  | 0 | 72 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | DATC0076_IP | 1 | [6 empty] | 2026-06-19 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Build | CL/OSC | 2026-03-27 |  |  |  | 2026-03-13 | 0 | < 15 Days | mghazi@deloitte.com |  | No | FS Not Started |  |  | In Progress | Yes
|  | INT-CR1810 | New |  | ERP | R3 (Release 3) | High | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | Inability to create materials manually in case of critical incidents | Create material master in MDG directly for all material types in case of emergency |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1810%20-%20Inability%20to%20create%20materials%20manually%20in%20case%20of%20critical%20incidents.pptx?d=w1ee7298a09b74c3a84ec4bb8e8e896ce&csf=1&web=1&e=UyNl6g | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-13 | 26 | 15-29 Days | mghazi@deloitte.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1811 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | [12 empty] | Create Group BOM (DATC0552 & DATC0553) | Create the Group Bill of Materials (BOM) as a prerequisite to creating the External BOM. The Group BOM will serve as the BOM template for all External BOMs, except OSAT and MySample BOMs. | The Group Bill of Materials (BOM) must be created first because it serves as the standardized template and foundational structure required to generate consistent External BOMs. Establishing the Group BOM up front improves alignment and reuse, reduces manual rework and variability across External BOM creation, and helps ensure downstream accuracy—while OSAT and MySample BOMs will be created same as internal BOMs. | External BOMs functionality will not work if Group BOMs are missing. These BOMs will be required for ITC2. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1811%20-%20Create%20Group%20BOM.pptx?d=w4219d77f63ec46bf8ba17deb555e8626&csf=1&web=1&e=ln5mNb |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 2 | DATC1744_IP, DATC1744_IF | 3215 | DATC1744_IP, DATC1744_IF | 2 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Other | CL/OSC | 2026-03-27 |  |  |  | 2026-03-13 | 0 | < 15 Days | nagirreddy@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1812 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP 10. Analytics | xinting.luk@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | N/A | N/A | N/A | [5 empty] | PRF_Includes_Week+Day | In the current design, UDT_PUBLISHED_PRF captures information sent to vendors by WorkWeek. However, in case of sending multiple PRFs within the week, there is no capability to identify the different versions. Therefore, the reporting team requested to add “day of the week” to increase granularity of Published PRF. In addition, a “Final PRF” column is also requested added to the table to let users differentiate which is the latest publish within the same week. | By including “Publish_WWD” and “Final_PRF” columns in the table, users can: Differentiate different PRF versions that were sent to vendors within the same week Identify which is the latest PRF that the team should look at Identify whether the RTF is a response to the latest PRF sent out | Need IT team's feedback | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRXXXX-PRF_Includes_Week+Day.pptx?d=wa43b2f2acc3f40978b074b8fb35af3d3&csf=1&web=1&e=2ROLDC |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1813 | New |  | ERP | R3 (Release 3) | High | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 10. Analytics 18. SCP | Joey.Huang@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | The need was identified, but the ECA view built does not meet the Finance requirements. | N/A | N/A | [5 empty] | BY IF WIF solve data for Product Costing | BY IF What-If solve output is needed at the detailed plant and operation level for Costing forecast What-if scenarios. | Detailed level solve for WIF scenarios is needed to calculate Standard cost WIF scenarios. | Change would be delivered by ITC2. | No | Core | Drafted |  |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1814 | New |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | [10 empty] | Exception Products prioritization | Exception Products - Not getting prioritized equally along with the IP orders (CHG117608092 | Blue Yonder is not maintaining existing schedules & commits for External Die (1001,1002, etc.) Finance / S&OE is now asking Factory Planning why 1001 schedules are changing outside the frozen horizon. This is likely due to 1001 not having POs and the fact that 1001 schedules in Blue Yonder are not actually treated as a commit. How can we configure Blue Yonder to respect existing 1001 schedules/commits? How can we clearly communicate to Finance and Management that Blue Yonder is driving a reduction in schedules? |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1814%20-%20Exception%20Products.pptx?d=w954e2c1128f24d10acc208b56d71040a&csf=1&web=1&e=8AYd9n | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1815 | New |  | SCP | R2 Hypercare | High | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | [10 empty] | RTF Edits/BY override | Override RTF in BY | IF Leadership is making decisions where supply is moved from one customer to another customer and we currently do not have a mechanism to execute these decisions in BY. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1815%20%E2%80%93%20Override%20RTF%20in%20BY.pptx?d=w694afd790f0449ef9fea28408d27e7ca&csf=1&web=1&e=BcuBun | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1816 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | [10 empty] | Single Order Confirmation Date | Single Order Confirmation (no splits) | Orders/wafers split across multiple ww's, outside of 25wfr increments |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R2/CR1816%20%E2%80%93%20Single%20Order%20Confirmation%20Date.pptx?d=wd32e4c1d72854ca0a1119043dbfb0dd2&csf=1&web=1&e=d3mclp | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1818 | New |  | SCP | R2 Hypercare | Medium | 07. FTS IF | 7.10 FTS IF - IF R2 FE Supply Planning |  | 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | [10 empty] | Order Linearization |  |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-14 | 25 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1819 | New |  | ERP | R2 (Release 2) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data | Khetan B | FTS (ERP) — Stef Maxey | Data - Julie Fawdington | [9 empty] | Customer Master data - Partner Functions validations | When a user adds a partner function for a customer during Create, Change, or Extension processing, the system must validate the partner function being added against Central Order Block and Sales Area Order Block status to the customer. If either order block applies to the customer (per the relevant master data), the system must prevent adding the partner function and display an error message. | If users are allowed to add previously blocked Partner Functions (e.g., Sold-to/Ship-to/Bill-to/Payer, Contact Person, or custom partner roles) the system will start accepting relationship data that it previously prevented, few impacts may be as below, Orders may route to different plants/ship points or deliver to the wrong address if Ship-to is changed/added; ATP and shipping instructions can change. Billing & AR: Bill-to/Payer changes can redirect invoices, dunning, and cash application; can create disputes, revenue delays, or misapplied payments. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-Build-CR0XXX%20%E2%80%93CM-MDG%E2%80%93FS_DATE0313_IF%20%E2%80%93%20Partner%20Functions%20Validations%20Addition..pptx?d=w530ffbf906f94b5ba62a6a0f2ac4e14f&csf=1&web=1&e=OrcXj2 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-16 | 23 | 15-29 Days | khetanx.b@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1820 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF 07. FTS IF 08. FTS IP | R3 (Release 3) | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | IDOC Enhancement for Production Order HOLD Release and Cancellation | The SAP S/4 IP to IF interface (OTCI1162) to create SO from BI Production Orders needs to be enhanced to automatically create, update, hold, and cancel Production Orders via IDocs. | Purpose: Close the FUT gap in OTCI1162 by enabling fully automated HOLD, RELEASE, and CANCELLATION processing for Production Orders via IDOCs, reducing manual interventions and preventing status mismatches between IP and IF SAP systems. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9E3A1356-034E-4F0D-82BE-320362753699%7D&file=INT-CR1820-IDOC%20Enhancement%20for%20Production%20Order%20HOLD%20Release%20and%20Cancellation.pptx&action=edit&mobileredirect=true&CID=C2908441-5E6B-417D-A3C3-5F9018E022DB&wdLOR=cC9AB183A-D770-4E3D-87E1-77962A27EA87 | New Requirement / Scope | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-16 | 23 | 15-29 Days | plakshmipadmaja@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1821 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 03. FPR 08. FTS IP 10. Analytics 18. SCP | elena.kaufman@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | Missed requirement | n/a | n/a | [5 empty] | Edit and Publish Single Operating Plan - Draft/Final | 1. Run fully constrained plan in IBP and hold in BY memory for comparison to WIF scenarios. 2. Allow users to designate which IBP WIF scenario is the Single Operating Plan when it’s ready for consumption by downstream applications. 3. Provide capability to edit the output of IBP WIF scenarios used to generate the Single Operating Plan. Edit granularity should be at site, stage, item, month, quantity. Additional detail normally required for PR/PRF creation are not necessary. | Setting the operating plan involves generating multiple views of our demand & supply plans for executive review and decision-making. These plans are all variations of a constrained plan. There is no single view that is pre-determined to be the one that will become our strategy going forward. Once a decision has been made, we must flag this scenario for downstream consumers as the official operating plan. We will have a DRAFT version that comes out of the Supply Review and a FINAL version out of the Executive Review. Both DRAFT and FINAL are “published” designations that downstream systems can consume and must include all manual changes that Planning chooses to incorporate. Planning cannot always efficiently generate the desired result through input data. Output overrides in an external layer allows planning to feed changes into reporting for a cohesive look, rather than adding footnotes for items we cannot quickly get into a scenario. (Min loading, strategic purchases, quick updates) | TBD | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CRxxxxx%20-IP%20SnOP%20Edit%20and%20Publish%20Single%20Operating%20Plan.pptx?d=wb0d54b097bc64244a57d39778eb1e485&csf=1&web=1&e=kSGye4 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-03-16 | 23 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1822 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.9 FTS IP - IP Demand Planning |  | 08. FTS IP | kattia.brenes.ramirez@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | IP Test Cases beyond ITC1 | Communication of IP DP test cases finishing after ITC1 milestone due to extended MC1/ITC1 tasks - ECA FUT in ITC1 + historical billing transformations delaying ability for publish CD from CDP per plan. | Communication of testing plan for ITC1 | delays contained to DP. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Demand%20Planning/3.%20Execution/CCB/INT-CR1822%20-%20IP%20Test%20Cases%20beyond%20ITC1.pptx?d=w659676b637f64d8da38d9423f44005ef&csf=1&web=1&e=lzfKIv |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-16 | 23 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1823 | New |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR 11. Technology 16. Testing | shrpillai@deloitte.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | NA | NA | NA | [5 empty] | Company Code–Specific Withholding Tax Setup​ | Withholding Tax Setup Customization at company code level | Following the new Ireland cash pool changes, business has identified 11 countries that currently participate in both the US cash pool and the Irish cash pool. The standard functionality supports maintaining withholding tax percentages at the participant country level only. However, some participants require different withholding percentages depending on the bank area. Hence, there is a business need to maintain multiple withholding rates for the same participant country. This requires maintaining the withholding percentage at the company code level. | It will be for ITC2 | Yes | Core | Approved and submitted for PMO approval | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/Change%20ID_Tower_CR%20Deck_template%20(1).pptx?d=w9dc1f515678144c7a976eaf910190c81&csf=1&web=1&e=mFPiff |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  | 3216 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-17 | 22 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1824 | Rejected |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 3.7 FPR - Product Costing and Inventory Valuation |  | 10. Analytics 18. SCP | Naren Mangtani | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma | [9 empty] | What-If scenario output to calculate What-If costing Finance impacts. | Need BY IF POR solve output with Sequence number as a unique identifier, and BY IF What-If scenario output to calculate What-If costing Finance impacts. | BY IF solve is sent to S4 IF to update Activity Quantity for Rate calculations to set Standard Cost in S4-IF for both POR and What-if scenarios for business. |  | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR1824%20-%20What%20If%20Scenarios%20for%20Costing.pptx?d=w2afe7ac0722c48d2a64f741561e5b31f&csf=1&web=1&e=1AYzwf |  | 1b. Solution Design |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Other | CL/OSC | 2026-03-27 |  |  |  | 2026-03-18 | 0 | < 15 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC1 | INT-CR1825 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.6 Master Data - Material |  | 09A. Master Data | candice.s.linnell@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR0918_MDG_Material Master_CR Enhancement to create PROC material.pptx INT_CR1013_Extenal_BOM_Automation.pptx | NA | NA | [5 empty] | 5 RICEFW on Master Data Automations to be moved to ITC2 | Exception to move 3 PROC Automations to Sprint OB1 | We prioritized FUTs and CRs that affect core business processes to protect critical outcomes These 3 objects are confined to Master Data and do not directly impact other towers | Still be in ITC1 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1825_Object%20Completion%20to%20change%20to%20Sprint%20OB1.pptx?d=we351bec36e054012ab505b481bb2dff0&csf=1&web=1&e=LDqNm5 |  | 13. Other Milestone Adjustments |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | Yes | N/A - Milestone Adjustment S4 | 3 | DATI1618_IP, DATI1618_IF, DATE1615 |  | DATI1618_IP, DATI1618_IF, DATE1615 | 3 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 |  |  |  | 2026-03-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1826 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | patrick.matthews@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Inventory Holding Point Capacity | Inventory holding points needs to be able to have a capacity associated with it in case there are storage limitations For example, between Test and Finish for 2-Step FACT products. Holding inventory at SFGI to prevent unnecessary fusing may have storage limitations that other inventory points may not. Can apply to all inventory locations, but suppliers may have limited storage options for holding inventory for customers. Inventory holding point between Test and Finish was brought up as the main point that will have storage limitations. Currently this is a process that is followed by the planning org for products using the 2-Step FACT process & Lunar Lake | Initially this will impact all products with 2nd assembly for memory attach (LNL, Nova Lake) & 2 Step-FACT products Study conducted by SVR Divisional Planning Team (Mitzi C) | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1826%20-%20Inventory%20Holding%20Point%20Capacity.pptx?d=wf0fb163dce9e40de8ed750d0416fc883&csf=1&web=1&e=70aLSs |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-18 | 21 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1827 | Approved |  | ERP | R4 (Release 4) | Medium | 09A. Master Data | 9A.2 Master Data - BOM |  | 07. FTS IF 08. FTS IP 09A. Master Data | llejarde@deloitte.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR | RAID | KDD | [5 empty] | Simulation mode need to be added to PROC BOM Enhancement program (DATE0926) | The PROC BOM creation is a custom enhancement to create a new pseudo BOM with Co-products for each material stage. This change will stop short of the actual PROC BOM creation and allow users to preview the results of the enhancement prior to committing the decision | The Inability to validate the actual results of PROC BOM Create /Update program may result in wrong PROC BOM update/create | Minimal | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/CR1827_Simulation_of_PROC_BOM.pptx?d=w03b3b9e562a240f2af6e51d85b07c578&csf=1&web=1&e=Rx7ING |  | 2. New RICEFW / ECA / Build Object |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1828 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | elena.kaufman@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | Extend Demand Prioritization Planning horizon | Extend planning horizon in the listed application to ensure both IBP solves against 9 qtrs worth of prioritized demand signals. SP-PDH – Update the time translation logic in the Demand Tiering scripts to incorporate T12 to capture the 9th qtr. BY-IBP – Extend the Demand Ranking UI to include T12 buckets to capture the 9th qtr. | Enable IBP constraint solve to compute a 2-year wafer-outs plan for financial planning. | tbd | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1828%20-%20Extend%20FNE%20%26%20Demand%20Priority%20horizon.pptx?d=w949349fe58a14edc94ff79f86761631f&csf=1&web=1&e=vY18I3 |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-18 | 21 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1829 | Approved |  | ERP | R3 (Release 3) R4 (Release 4) | High | 06. PTP | 6.2 PTP - Procurement |  | 04. OTC IF 06. PTP | chin.chai.ng@intel.com | PTP — Mike Nayab | PTP - Richard Taylor |  | This is the new business model or initiative aligned by Navid/Dave/Phil/Jasleen | N/A | N/A. | [5 empty] | Tester Front Office Marketplace Enablement | The Tester Front Office (TFO) currently supports a customer‑specific test tooling business using a centralized ordering and catalog model. The proposed system changes enable: A centralized marketplace (“storefront”) for customer‑specific tester collaterals Standardized order intake through IFS True‑cost catalog pricing (hardware + labor/support) captured at time of order Elimination of downstream bill‑backs and manual accounting corrections Alignment with Foundry‑grade financial and operational requirements The system needs to enable for customer’s order through Intel Foundry / Tester Front Office and place order to the parts/tool supplier, deliver and bill to customer based on the Intel’s catalogue price (with the true cost / mark-up). | This is not a greenfield build. It is a targeted extension of an existing, proven capability, designed to simplify the business, reduce financial friction, and enable scalable growth beyond the current >$300M baseline. Without these changes, scaling this business will require increasing reliance on manual bill‑backs and accounting workarounds—an approach that is unsustainable for the Foundry operating model. As we expand this business to additional tester collaterals (e.g., sockets, TIUs, DKMs, probe‑adjacent tooling), continuing to rely on bill‑backs will: Increase financial complexity and audit risk Obscure true product cost Create friction with Foundry customers and finance Constrain growth of a material revenue stream | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/CR1829_P2P_Tester%20Front%20Office%20Marketplace%20Enablement.pptx?d=we8ebb26c135b46458660bb1fab2e3c4d&csf=1&web=1&e=cIexSb |  | 0. Request for Investigation |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 |  |  |  | 2026-03-18 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No | Yes
R3 (Feb 2027) | R3 ITC2 | INT-CR1830 | Approved |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.5 FTS IP - Manufacturing |  | 08. FTS IP | Sekhar Lingam | Inventory/Logistics/FTS — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Change Requirement to introduce AIF Monitoring Tool to validate and process the production order creation and update scenarios in the IP S/4 HANA System. | Change Requirement to introduce AIF Monitoring Tool to validate and process the production order creation and update scenarios in the IP S/4 HANA System. | This change introduces the AIF Monitoring Tool for object FTSI0209 in the IP S/4HANA system to centralize validation, processing, monitoring, and reprocessing of production order creation and update scenarios. It enables end to end visibility of successful and failed records within AIF, improving control and operational efficiency. The change also removes the existing logic that activates production orders with a deletion indicator on errors and instead sends CRTD status production orders to BODS and IP PDH as the source system. Overall, the enhancement aligns the integration design with business requirements while strengthening error handling and traceability. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/08.%20FTS%20-%20Intel%20Products/CR%20Intake%20Forms/INT-CR1830%C2%A0-Change%20Requirement%20to%20introduce%20AIF%20Monitoring%20Tool%20to%20validate%20and%20process%20the%20production%20order%20creation%20and%20update%20scenarios%20in%20the%20IP%20S4%20HANA%20System..pptx?d=w10b53b316de94114b55d467b84d4fe2f&csf=1&web=1&e=zQpKpe | New Requirement / Scope | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 |  |  | 5 |  | 40 |  |  |  | 135 |  | 25 |  |  | 40 | 160 | Tech - Middleware Tech - S/4 | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | FTSI0209 | 1 | [6 empty] | 2026-06-03 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Build | CL/OSC | 2026-03-27 |  |  |  | 2026-03-18 | 0 | < 15 Days | vchaudhari@deloitte.com |  | No | FS Not Started |  |  | In Progress | Yes
R4 (Jul 2027) | N/A | INT-CR1831 | Approved |  | ERP | R4 (Release 4) | High | 06. PTP | 6.8 PTP - QM |  | 06. PTP | anantjoshi@deloitte.com | [10 empty] | WIINGS | Change requirement for IQC Assessment | To assess logical process and map with physical process by running different POC’s at S/4 & EWM systems related to IQC for Customer Bailed Materials Once POC is complete, will generalize it for regular incoming quality enabled materials. | A new process to be established for IQC for Customer Bailed Materials and generalize it for regular incoming quality enabled materials. This investigative CR is for performing POC at S/4 and EWM systems and come up with solution. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/2.%20Build/Change%20Request%20Decks/INT-CR1831%20-%20IQC%20Solution%20Assessment.pptx?d=w5de4faef9b954062adc0314eead7dfcf&csf=1&web=1&e=K8evGO | New Requirement / Scope | 0. Request for Investigation |  |  |  |  | 0 |  |  | 138 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Other | CL/OSC | 2026-03-27 |  |  |  | 2026-03-18 | 0 | < 15 Days | nnagapushpa@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1832 | New |  | ERP | R3 (Release 3) | High | 03. FPR | 3.2 FPR - Tax |  | 03. FPR 10. Analytics | gabriela.hernandez@intel.com | Data & Analytics - Rebecca Verette | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | Tax Capital Spending Report Required fields | FSD for report ECAFPR6076 “CAPEX Forecasting Report” did not include all required fields requested in user story: IDM-USID-1913-FPR (for Property tax use) and IDM-USID-5010-FPR (for Ireland grant use). We need to incorporate the fields as shown below: company_code, location, project_definition, project_name, project_type, capital_wbs_descry, category, scope_type, program, process_node, BU_hierarchy_group, system_code, eval_code, GAAP_useful_life, depreciation_start _date | Tax team requires those fields to forecast property tax and IR grants. Not having those fields in the report will not allow for Tax team to properly forecast Capital spends subject to tax and grants. | Not needed for ITC1 | No | Non-Core | Matt Advice that this is not ready to go to GPO review | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CRXXXXX-Tax%20Capital%20Spending%20reports%20required%20fields.pptx?d=w730d20035db0451db529da64e7773002&csf=1&web=1&e=9dHgjZ |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-03-19 | 20 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1833 | New |  | ERP | R2.X (Between Release 2 & 3) | Medium | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | New Product Identification Flag in EWM | Operations will require a new field in EWM which will show New Products (NPI) received for added steps in outbound processing | Operations is moving towards automating shipment weights during the pack process. "Seed" weights for New Products needed to ensure first shipment compliance and future shipment automation. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_New%20Product%20Flag%20Id%20EWM.pptx?d=wac373264b70244a1b6908a5c839343c2&csf=1&web=1&e=6tbSNX |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-03-19 | 20 | 15-29 Days | imme.sandweg@intel.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1834 | Approved |  | ERP | R3 (Release 3) | Medium | 09A. Master Data | 9A.1 Master Data - ALL |  | 09A. Master Data | llejarde@deloitte.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR | RAID | KDD | [5 empty] | Material Human Readable Description Derivation and Direct Update on the Existing Materials | Standalone program has to be created to derive Material Human Readable Description. This is required to update the existing Materials which are created but for which Description has to updated according to latest business rules. | This is required to update the correct Material Description according to latest set of business rules otherwise it can lead to inconsistent data across the systems. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR1834_Material%20Human%20Readable%20Description%20Derivation%20and%20Direct%20Update%20on%20the%20Existing%20Materials.pptx?d=w36bb40e6726940f9a28f444ae7bf813e&csf=1&web=1&e=nVczaV |  | 2. New RICEFW / ECA / Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 1 | DATC1743 | 3213 | DATC1743 | 1 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-19 |  |  |  | 2026-03-20 | [6 empty] | Other | CL/OSC | 2026-03-20 |  |  |  | 2026-03-19 | 0 | < 15 Days | ssyal@deloitte.com |  | No |  |  |  | In Progress | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1835 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | susan.strathman@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | NA | 3444 | NA |  |  | 63174 | #NO MATCH | WIINGS | ITC2 Exception for Kommand Autostore Serialization | This change request is to approve ITC2 testing exception for Kommand Autostore Test Cases that are relevant for serialization. | Kommand Autostore FUT testing identified 2 defects which require KPI (Software Intergrator) to support. KPI has identified fixes and will incorporate into R10 production system by 5/3. This will miss ITC1 cut off for FUT approval. 1. Serial Number array not being sent in the payload during ReplenResult & PickResult is not seeing them 2. SortBarPositionID did not appear in payload in the hierarchy expected per spec | Low/Medium: All non-serialized test cases will be executed for Kommand in ITC1, all non-Kommand serialized test cases have a path forward in ITC1 for testing using functionality in SAP to create SAP generated Serial #. Team has reviewed all subsequent steps post the two defects and is confident no other roadblocks post these steps, and given timing of delivery at the beginning of ITC1, time for FUT work through and approval in time for ITC2. | No | Non-Core |  | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/IQArQSOCmut9T5qQmBFlrKTNAfp0eEq6Z8n5q6k-pA0JXbY?email=susan.strathman%40intel.com&e=FgmoMo |  | 12. Other Deliverable Changes (OCM, BPM, BCP, Testing, Cutover, Etc.) 13. Other Milestone Adjustments |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-20 | 19 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1836 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.4 OTC IF - Returns | Yes | 04. OTC IF | [12 empty] | Enable certain fields to be updated without additional workflow approval | RMA Workflow - Enable certain fields to be updated without additional workflow approval | Currently workflow is being triggered when making any change in the sales order. Need to enable certain fields that can be updated without triggering any additional workflow.Fields to be updated without additional workflow - COD Upload, Header text (any comment),Line-item text (any comment),Customer PO Reference, Output re issuance (Auth Letter) |  | Yes |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/25.%20Operate%20R1-R2%20(%20Artifacts%20)/Release%202/OTC/INT-CR1836-%C2%A0Enable%20certain%20fields%20to%20be%20updated%20without%20additional%20workflow%20approval.pptx?d=w2fd71a2cf71c4c0fbe62d62712849645&csf=1&web=1&e=9YysQs | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-20 | 19 | 15-29 Days | anirudhx.sharma@intel.com |  | No |  |  |  | N/A | No
R5 (Oct 2027) | N/A | INT-CR1837 | Approved |  | ERP | R5 (Release 5) | Medium | 05. OTC IP | 5.1 OTC IP - ALL |  | 17. B-App | Shelly Lafree | OTC — Kevin Brown | [7 empty] | 11565 | My Samples ( Future of Samples) |  | Global Samples Transformation (Finished Goods) | Decommission the legacy "My Samples" application and modernize the entire Samples Order-to-Cash (OTC) process by migrating it to Standard SAP S/4HANA capabilities | The legacy "My Samples" tool acts as a fragmented silo, creating operational risk and blocking the organization’s strategic roadmap. To support global growth and supply chain modernization, the business must migrate to S/4HANA to address five critical gaps: |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B399755D9-A498-4D61-B39D-976DCF82E87B%7D&file=INT-Build-CR1261%25u2013Global%20Samples%20Transformation_S4%20HANA%20Migration.pptx&wdLOR=cA9211A17-D64D-4A2E-9B9C-14B733338F1E&action=edit&mobileredirect=true | New Requirement / Scope | 0. Request for Investigation |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-20 | 0 | < 15 Days | anirudhx.sharma@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1838 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.1 FTS IP - ALL |  | 08. FTS IP 10. Analytics | pradnya.patil@intel.com | Data & Analytics - Rebecca Verette | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | R3 Reports and Data Fields | Updated list of additional fields needed to be landed and available for consumption for 72 new 3rd party reports for SMP & S&OP Reporting Capabilities | Business is asking for additional fields beyond what was previously submitted to be consumable in ECA. Additionally based on further analysis the biz is asking for 72 biz reports to support UAT and go live business operations developed by CPC Analytics. | Will land in ITC2, ITC3 deliverables | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/Change%20ID_FTS_CR_Deck_R3_Reports_and_Fields.pptx?d=we547077c8f014652bf0b83eef54f22d3&csf=1&web=1&e=dcsnwR |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-21 | 18 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1839 | New |  |  | R3 (Release 3) |  | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data | lakshmix.nagireddy@intel.com | [11 empty] | BOM status change when there is a change in existing BOM | DATI1501 & DATI0927 already exist, however, we’ve received a new client requirement to update the BOM status change when there is a change in BOM. | DATI1501 & DATI0927 already exist, however, we’ve received a new client requirement to update the BOM status change when there is a change in BOM. | ITC2 | No |  |  |  | New Requirement / Scope |  |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-23 | 16 | 15-29 Days | ssunilbabu@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1840 | New |  | SCP | R3 (Release 3) | High | 07. FTS IF | 7.12 FTS IF - IF R3 FE Supply Planning & Adv Packaging |  | 07. FTS IF | Naren Mangtani | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | CR1690 | NA | NA | [5 empty] | Capture and update Planned Orders (PO) Changes | Capture and update changes to Planned Orders (PO) during the Frozen Horizon period due to Pull-In’s/Push Out’s |  | ITC2 | No | Core | [7 empty] | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-23 | 16 | 15-29 Days | naren.mangtani@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1841 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | Solomon.Levinrad@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | N/A | N/A | N/A | [5 empty] | Cal_ProdYield PDH UI | In the current design, users manually manage Output_YieldQty for all Output_Items in Cal_ProdYield UI. This CR covers multiple issues with the prod yield table First raised by IT - The CAL_Name might sometimes exceed the 50-character limit This will cause ProdYield calendars to fallout and not make it to BY Second raised by R2 SC modeller - Prod yield needs line items with PROC as input and output in order to correctly plan orders with PROC's Third raised by business team - The granularity we maintain the parameters that make up prod yield (UOM, Good outs, Coproduct) are managed separately and the ability to maintain them as separate data elements in PDH is needed. In current design if input item is wafer and output items are dies, users have to enter exact number of dies considering both DPW and yield and coproduct split. Therefore, we re-designed the Cal_ProdYield to resolve all the issues above | By re-designing the Cal_ProdYield UI, we can: - Avoid the issue of having CAL_Name exceed the 50-character limit - Allow BY to calculate intended order quantity correctly - Maintain production yield components at correct granularity – a cleaner and easier approach | Need IT team's feedback | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRXXXX-Cal_ProdYield_PDH_UI.pptx?d=w7f108f40165e48ed868c6c3d955be782&csf=1&web=1&e=ypGp7b |  | 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-24 | 15 | 15-29 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1842 | Cancelled |  | ERP | R5 (Release 5) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 04. OTC IF 05. OTC IP 09A. Master Data | Sean Tillman | Data & Analytics - Rebecca Verette | [10 empty] | Automate GTS Sanctions | Automate the manual sanctions from GTS for both supplier and Customer on MDG | Currently this process is manual so looking to automate the process |  | No | Core | [8 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Nisha Kadakia in comment that this CR is cancelled |  | Not Assigned |  |  |  |  | 2026-03-25 | 0 | < 15 Days | nisha.kadakia@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1843 | New | Ready: Wednesday | ERP | R4 (Release 4) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data | Sean Tillman | Data & Analytics - Rebecca Verette | [10 empty] | DQM Report | Redesign DQM report to include MDG changes along with Reltio | Currently the report only compares Reltio changes with MDG, enhancing the report to compare MDG data with Reltio as well |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/BP/CR1843%20MD%20DQM%20report%20to%20accept%20MDG%20changes.pptx?d=w0f048e277e1f4973a9b618fe803120c1&csf=1&web=1&e=mRUxce |  | 1a. Operations Design 1b. Solution Design |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-25 | 14 | < 15 Days | nisha.kadakia@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1844 | New | Ready: Wednesday | ERP | R5 (Release 5) | Medium | 09A. Master Data | 9A.4 Master Data - Vendor |  | 06. PTP 09A. Master Data | Sean Tillman | Data & Analytics - Rebecca Verette | [10 empty] | Ariba Attributes updates | Automate the update of Ariba specific attributes at vendor master level in MDG from Ariba | Currently the process is manual and need to automate this process |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/BP/CR%201844%20%E2%80%93%20Ariba%20Attributes%20updates.pptx?d=wfb33c7d1b6584c549547c5772c532ee3&csf=1&web=1&e=Kb9slE |  | 1a. Operations Design 1b. Solution Design |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-25 | 14 | < 15 Days | nisha.kadakia@intel.com |  | No |  |  |  | N/A | No
R5 (Oct 2027) | R5 ITC1 | INT-CR1845 | Approved |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.7 Master Data - Reference |  | 17. B-App | Sughajit.ray@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA |  |  | 10772 | #NO MATCH |  | Virtual Locations: Migration from Legacy MDG to HR Systems | Virtual Locations are used by Workday and Fieldglass applications only. This data is not considered Enterprise Master Data. The HR systems would need to determine how and where to manage virtual locations within the HR ecosystem. | Required to EOL legacy MDG. | No | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Reference/CR1845%20-%20Virtual%20Locations.pptx?d=we89a25e877bd4899b7d5125efd422b1a&csf=1&web=1&e=velO0g |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1846 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | Solomon.Levinrad@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | N/A | N/A | N/A | [5 empty] | ProdMethod NNSD Data Source Change | In the current design, business sets ProductionMethod.U_ORIG_NONEWSUPPLYDATE value in Biz_Param_Control UI (This is outlined in Case 2 in the spec). If users would like to override the original value, they can do so in the ProductionMethod UI. However, because users can also manage Production Duration for each of the manufacturing stage in the ProductionStep UI, not only it is cumbersome for users to manage similar information at separate places, but also it creates risks for duplicating information. Therefore, after further discussion, we decided to change the data source for ProductionMethod.U_ORIG_NONEWSUPPLYDATE to be sum of Production Duration maintained in the ProductionStep UI. Users can still override the value in ProductionMethod UI, but they no longer need to maintain NNSD value in the Biz_Param_Control UI. Case 2 outlined in Biz_Param_Control spec will not be needed anymore, users will use Export_Control table instead of Case 2 to define start day of the week. | By changing the data source for ProductionMethod.U_ORIG_NONEWSUPPLYDATE : - Users don’t have to maintain similar information at separate UIs - New design reduces risk for duplicated information | Need IT team's feedback | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CRXXXX-ProdMethod_NNSD_Data_Source_Change.pptx?d=w5d5cdf0c7b6a4801937c0c3f54801374&csf=1&web=1&e=IKSsYu |  | 1b. Solution Design |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-25 | 14 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1847 | Approved |  | ERP | R3 (Release 3) | High | 02. E2E Process Integration | 2.4 E2E Process Integration - Cross Functional Topics |  | 02. E2E Process Integration 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data 13. Security 17. B-App | Jorge Sanchez | [11 empty] | Malaysia IAO IF/IP Legal Entity design | This is investigation CR for new Legal entity requirement for Malaysia IAO IF/IP |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDBE85E96-A33B-4DC3-9066-D0DB9D5D12D6%7D&file=INT-CR0000%20Malaysia%20New%20LE%20for%20Products%20Business%20Logistics.pptx&action=edit&mobileredirect=true |  | 0. Request for Investigation |  |  |  |  | 0 |  |  | 120 | [10 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Other | CL/OSC | 2026-03-27 |  |  |  | 2026-03-25 | 0 | < 15 Days | nramireddi@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1848 | New |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration |  | 04. OTC IF 07. FTS IF 10. Analytics | satheesh.s.kumar@intel.com | Data & Analytics - Rebecca Verette | FTS IF - Haritha Komma |  | identified this data gap during FUT | 3704 | NA | [5 empty] | ASN with MLC Information for ATFX, NGWITS, SFI | ASN information required by ATFX, NGWITS,SFI,SHIPSERVER to create Lot and below process. This information is required at MLC codes level; Currently these External suppliers are having only Supplier ID ; IFA have no method to find out the supplier ID and MLC associations. determination of CoA & CoF and communicate the same back to ERP during the traceability (b) to support ULT traceability requirement (c) to identify the folders in which customers / Outsource manufacturers will be sharing the electronic data (like wafer map, eTest data, etc., ) *ECC will provide a consolidated view of all the ASN/IBDN information for all sites and IP + IFS scenarios; Including the MLC code requirement for SHIP FROM and FAB SITE code. | with out this view, ATFX, NGWITS, SFI will NOT be able to create Lot in MES. Hence this view is required | will not be able to intercept in ITC-1 and will be part of ITC-2 onwards. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCF03A914-CCCB-49A4-9A2A-82190CE7B714%7D&file=INT-CRXXXX-ASN_MLC_Requriment%20from%20ATFX%2C%20NGWITS%2C%20SFI.pptx&wdLOR=c48EF9495-D87E-406D-9DF1-4DF86028DE7F&action=edit&mobileredirect=true |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 1 | FTSFV050 |  |  | 0 | FTSFV050 | 1 |  | 0 | 1 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-25 | 14 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1849 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 06. PTP 09A. Master Data 17. B-App | Sean Tillman | Data & Analytics - Rebecca Verette | [10 empty] | Supplier Hierarchy | Remove supplier hierarchy from sCheck & Reltio and consolidate in MDG, EOL sCheck. | Required to EOL Custom APP( #8586). |  | No | Core |  |  |  | 1a. Operations Design 1b. Solution Design |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Chris Birely to no longer be required | Other | Not Assigned |  |  |  |  | 2026-03-25 | 0 | < 15 Days | nisha.kadakia@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1850 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.10 Master Data - Boundary Apps |  | 06. PTP 09A. Master Data 17. B-App | Sean Tillman | Data & Analytics - Rebecca Verette | [10 empty] | Preferred Supplier | Move preferred supplier attributes maintenance to Ariba & EOL this custom App | Required to EOL Custom APP( #12464). |  | No | Core | [8 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Chris Birely to no longer be required |  | Not Assigned |  |  |  |  | 2026-03-25 | 0 | < 15 Days | nisha.kadakia@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1851 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.7 Master Data - Reference |  | 17. B-App | viswakanth.ankireddi@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | IT Service move to ServiceNow | IT Service move to ServiceNow | Required to EOL legacy MDG (include CS Tax Codes) | No | No | Non-Core |  | TBD |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1852 | Approved |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data | subhajit.ray@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Move MLOC to new MDG | Move MLOC to new MDG as interim until new PLMs remove the need for it | Required to EOL legacy MDG (lift and shift) | No | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Reference/CR1852%20-Manufacturing%20Location%20Code.pptx?d=w90def3108ef4432f9badd609f65bd83b&csf=1&web=1&e=a6J7ts |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-25 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1853 | New |  | SCP | R3 (Release 3) | High | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 03. FPR 08. FTS IP 18. SCP | elena.kaufman@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | Missed requirement | n/a | n/a | [5 empty] | Edit and Publish Single Operating Plan - Editable | This is Part 2 of CR1821 | This is Part 2 of CR1821 | TBD | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1853%20-IP%20SnOP%20Edit%20and%20Publish%20Single%20Operating%20Plan%20-%20Editable.pptx?d=w1df48e12fb864834a00d22cc6c9150ff&csf=1&web=1&e=eUmqH6 |  |  |  | Yes |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-26 | 13 | < 15 Days | brian.staab@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1854 | New |  | ERP | R5+ (Post Release 5) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 06. PTP 07. FTS IF 09A. Master Data | karen.e.ramirez@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | Originally identified in 2023 and intentionally deferred, this item was revisited during R5 roadmap scope reviews and confirmed as a capability gap, with Capital and Construction inventory still supported by the legacy NIT system rather than SAP S/4HANA, resulting in leadership direction to submit a Change Request for evaluation | - | - | [5 empty] | IM S4 for Capital and Construction Inventory | -Implement an SAP S/4HANA Inventory Management (IM) solution to support Capital Equipment, Capital Supporting Items, and Construction Inventory, replacing the legacy boundary application NIT. -This change enables system‑of‑record inventory management in S/4 for materials currently managed in NIT, including integrated receiving, inventory tracking, movements, adjustments, and financial posting—without deploying a full Warehouse Management (WMS/EWM) solution. -The scope aligns with the IAO R4/R5 roadmap and focuses on standard SAP IM capabilities to improve control, visibility, and governance. | -NIT is end‑of‑life and unsupported, having gone live in 1998 with no viable modernization path, creating growing operational, financial, and compliance risk. -Current NIT‑based processes rely heavily on manual workarounds, duplicate postings, and offline controls, resulting in data integrity issues and limited auditability. -Implementing SAP IM provides a right‑sized, lower‑complexity solution that retires NIT while delivering standardized inventory control and financial integration within S/4HANA. | Request to explore adding this scope as part of R5 or Post R5, not impacting current schedule, but requires additional resources | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA589BC6C-9CC6-4A54-B661-067D4EB9DBC2%7D&file=CR1854_Logistics%20FTS%20IF_CR%20Deck_%20IM%20S4%20for%20Capital%20and%20Construction%20Inventory.pptx&wdLOR=c5E98044B-F22C-4274-8EB6-889D2569DF88&action=edit&mobileredirect=true |  | 0. Request for Investigation 1. Process Scope / Design Change |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-26 | 13 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | R3 ITC2 | INT-CR1855 | Approved |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | susan.strathman@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | 03761 | NA |  |  |  |  | WIINGS | EWM Serialized Part Conversion Enablement​ | This change request is to enable serialized item conversion change to BODS functionality for spares​ | Require BODs team to support Object ## for serialized parts conversion. At one point team was planning not to complete Serialized template for ITC1 expecting to complete in ITC2, consequence was not understood that BODs design required and that in making that decision our manual upload template would fail.​ | Low impact | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2581D68A-65FA-4D19-A1D2-61CE05525186%7D&file=EWM%20Serialized%20Part%20Conversion%20Enablement.pptx&wdLOR=cB1C44368-8D52-4660-800F-44F41FC657C4&action=edit&mobileredirect=true |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | 66 | 4620 | 12 | [7 empty] | 54 |  |  | 0 | 54 | Data Migration | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  | LOGC0971, LOGC0970 | 2 | [6 empty] | 2026-06-06 | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Build | CL/OSC | 2026-03-27 |  |  |  | 2026-03-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No | FS In Progress |  |  | In Progress | Yes
|  | INT-CR1856 | Cancelled |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Koyel Boral | [15 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-26 | 0 | < 15 Days | kboral@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1857 | Cancelled |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | KOYEL BORAL | [15 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-26 | 0 | < 15 Days | kboral@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1858 | New | Leadership Approval; Thursday | ERP | R5 (Release 5) | Medium | 05. OTC IP | 5.9 OTC IP - GTS |  | 03. FPR 04. OTC IF 05. OTC IP | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | Bank/Payment Screening Functionality​ | Bank master data from MDG and payment from the CFIN system will be screened in SAP GTS for Sanctioned Party List matches. Any potential hits will automatically block the associated BP or payment transaction until Compliance review is done to confirm or release the block in accordance with Intel policy.​ | Performing Sanctioned Party List screening on bank master data and payment transactions prevents processing financial transactions involving sanctioned parties. The current, weekly, manual process is Inadequate to provide continuous coverage for all compliance risks and exposes Intel to regulatory violations, substantial fines and penalties, and transaction blocks, freezes, or other enforcement actions. Specific gaps with the current manual process are: * Point in time screening only – banks screened once but not automatically rescreened when Sanctioned Party lists are updated * No coverage for updates to existing banks – weekly reports captures newly created bank records but not updates to existing banks * No system integrated or transaction level control – screening is performed outside of GTS and not integrated with the payment process for transaction blocking if needed The integration of Bank MD and CFIN payment txns with SAP GTS E4H for SPL screening would close all these gaps. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1858%20-%20Bank_Payment%20Screening%20Functionality.pptx?d=w0ec62205b2c347afaebdda12a20dbc39&csf=1&web=1&e=rxl50h |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-26 | 13 | < 15 Days | rsiddharth@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1859 | Rejected |  | ERP | R4 (Release 4) | Medium | 05. OTC IP |  |  |  | Shelly Lafree | OTC — Kevin Brown | [9 empty] | Tariff | Unit-Level Tracking Data In B2B ASN | Implement a scalable capability to transmit unit‑level (serialized) tracking data via B2B to customers as part of ASN and/or API integrations. The initiative addresses current limitations where serial data is handled outside of SAP S/4 and relies on manual, customer‑specific, and non‑scalable solutions that frequently fail due to data inconsistency and quality issues.​ | Intel requires an efficient, automated process to transmit comprehensive unit-level data to customers, including: Country of Assembly (CoA), Country of Fabrication (CoF), Country of Origin (COO), Date codes, Warranty information, Firmware details, Batch information​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc2.aspx?action=edit&sourcedoc=%7B026036f8-74a3-47ef-871a-b6abb628c6d8%7D&wdOrigin=TEAMS-MAGLEV.null_ns.rwc&wdExp=TEAMS-TREATMENT&wdhostclicktime=1774539465857&web=1&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTk3MjUuMjAxNzAiLCAiT1MiIDogIldpbmRvd3MiIH0%3D&CID=745D4410-D523-4878-9369-DA1F6A193730&wdLOR=c92146090-6FDE-48CB-B0FE-2BB5B0855EFE | New Requirement / Scope | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 11. OSC/CL Rejected (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Design | CL/OSC | 2026-04-02 |  |  |  | 2026-03-26 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  |  |  | N/A | No
R3 (Feb 2027) | N/A | INT-CR1860 | Approved |  | SCP | R3 (Release 3) | High | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | Yes | 07. FTS IF | christopher.j.martin@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | 03779 | NA | [5 empty] | Chem 3PL PIP Enhancements to Support FTZ | Enhance the OpenText 3B12 and 2A1 PIPs exchanged with Chem 3PLs (RinChem & Linde) to support chain-of-custody for Chemical deliveries and Free Trade Zone (FTZ) zone-to-zone (Z2Z) movement reporting to US Customs and Border Patrol (CBP)​ | 2A1: the current 2A1 payload does not contain information that can be used to convert Purchasing UoM, Base UoM, to a Volume/weight UoM. This is a problem for materials that are received in a Purchasing UoM (Ex: Case) and then distributed/consumed in a Base UoM (Ex: Bottle). The absence of this data creates problems in Consignment settlement, FTZ zone-to-zone transfers, and 3PL fee schedules that are based upon weight of material moved.​ ​ 3B12: Chemical 3PLs currently deliver directly to a storage location on Intel’s campus. This process avoids a hand-off of material to the onsite 3PL, which may not be capable of handling hazardous materials and would incur additional handling charges. In SAP, this direct-delivery requires the Chem 3PL to see the S.Loc on a Stock Transfer Order (STO), which is currently not included within the 3B12. Adding the Storage Location to the 3B12 enables the 3PL to deliver material directly to the storage location without needing to hand the material off to the local onsite 3PL.​ | It is required for R3 and will be intercepted at ITC2. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1860%20-%20Chem%203PL%20PIP%20Enhancement%20to%20support%20FTZ.pptx?d=we9203eee3468437293a2e3f8b041265d&csf=1&web=1&e=PoSqb8 |  | 0. Request for Investigation |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-03-26 |  |  |  | 2026-03-27 | [6 empty] | Other | CL/OSC | 2026-03-27 |  |  |  | 2026-03-26 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1861 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5+ (Post Release 5) | High | 09A. Master Data | 9A.9 Master Data – PDM |  | 17. B-App 18. SCP | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Product Design Project in Speed for ERP /Planning Hierarchies | Product Design Project in Speed for ERP /Planning Hierarchies | Ability to tie the product design project in SPEED to the part numbers in ERP/Planning Hierarchies. | None | No | Core |  | TBD |  | 0. Request for Investigation |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1862 | Cancelled |  | ERP | R5 (Release 5) | Medium | 05. OTC IP | 5.9 OTC IP - GTS |  | 05. OTC IP | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | CAAS Error Management​ | CAAS Error Management to fulfill boundary apps requirements. | Sending all error emails to a single, broad distribution list creates alert fatigue by notifying users about issues outside their boundary app. Over time, users may ignore notifications, including those relevant to their own interfaces. Segregating notifications by system ID and boundary-app user group ensures the right users receive the right error notifications. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA7B16872-DA55-4132-8823-8C6A414D6558%7D&file=INT-CRXXXX%20-%20CAAS%20Error%20Management-%20INTERNAL%20COPY_DONOTEDIT.pptx&action=edit&mobileredirect=true | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Piyush and Prem that the CR was rejected by GPO |  | Not Assigned |  |  |  |  | 2026-03-27 | 0 | < 15 Days | rsiddharth@deloitte.com |  | No |  |  |  | In Progress | No
|  | INT-CR1863 | New | Leadership Approval; Thursday | ERP | R4 (Release 4) | Medium | 05. OTC IP | 5.9 OTC IP - GTS |  | 04. OTC IF 05. OTC IP | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist | [9 empty] | New Export Control Legal Regulations for Vietnam and China ​ | New export-control legal regulations must be configured in GTS for Vietnam and China, including the underlying regulation content, numbering schemes, license-determination strategy, and the required license types to ensure compliant exports from both countries. | All exports from Vietnam or China must have the applicable export licenses assigned to the transaction. Accordingly, sales orders and outbound deliveries in S/4 will be checked in GTS to ensure the required licenses are determined and applied in line with local export-control laws and regulations. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1863%20-%20New%20Export%20Control%20Legal%20Regulations%20for%20Vietnam%20and%20China.pptx?d=wf5850db882c74863a1a24dd07964c62d&csf=1&web=1&e=k1icC1 |  | 1. Process Scope / Design Change |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-27 | 12 | < 15 Days | rsiddharth@deloitte.com |  | No |  |  |  | N/A | No
R4 (Jul 2027) | R4 ITC1 | INT-CR1864 | Approved |  | ERP | R4 (Release 4) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data 10. Analytics | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | PSI BOM: Move Interface from EMS to PLM Translator | PSI BOM: Move Interface from EMS to PLM Translator and possible IBM, MDG, S4, ECA changes | This is connecting EMS to Translator as another source. This is an interim design until they can move this to Windchill. Needed to EOL eDFIT in R4 (eDFIT already approved for R4) | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1864%20-%20PSI%20BOM%20from%20EMS%20to%20S4%20via%20PLM%20Translator.pptx?d=wf4aa136859da4e9597942e2c2a71077d&csf=1&web=1&e=K9kI76 |  | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A | Yes | S4 | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-27 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1865 | New | 4/7: Chris Birely confirmed that he is working with teams to get decks | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data 17. B-App | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Quality Attributes. Automate manual updates to ROH, HALB and ERSA MMs | Quality Attributes. Automate manual updates to ROH, HALB and ERSA MMs for quality. Manual process put in place at R3 (coming from SPEED ILM) | Volume will be too much to manage and would like to automate at R5. See if volume justifies automation or wait to automate when PLM replaces ILM | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1865%20-%20Quality%20Attributes%20Automation.pptx?d=wf2d41619eaf34c41be10f4df93a3e416&csf=1&web=1&e=uc2zBw |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-27 | 12 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1866 | New | 4/7: Chris Birely confirmed that he is working with teams to get decks | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Alternate Preferred BOM | To avoid CR for R3, biz is creating a ticket to get Team to add component changes to alternate preferred BOMs for PTP (missed capability on ECC). Will EOL custom report Intel built w/ this design | Came in too late for R3. Needs automation to avoid human errors Should be in the PLM in the future | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1866%20-%20Alternate%20Preferred%20BOM.pptx?d=w43cf1c37693b48d780f204f2953cd3c8&csf=1&web=1&e=6GaUox |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-27 | 12 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1867 | New | 4/7: Chris Birely confirmed that he is working with teams to get decks | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data 17. B-App | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Biz Automations: Sales Status, IP to IF, IF to IP | Biz Automations: 1. Sales Status Automation 2. More IP to IF and IF to IP Automations | Business not staffed to support volume | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1867%20-%20Business%20Automations.pptx?d=w92a2983ee85943e8b8a76e92efe16ef9&csf=1&web=1&e=kEqePh |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-27 | 12 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1868 | New | 4/7: Chris Birely confirmed that he is working with teams to get decks | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | Medium | 09A. Master Data | 9A.3 Master Data - Customer |  | 09A. Master Data 17. B-App | viswakanth.ankireddi@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | External Payer Bank Details | External Payer Bank Details. Custom program to lock down in MDG | Need investigation first | None | No | Non-Core |  |  |  | 0. Request for Investigation |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-27 | 12 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
R4 (Jul 2027) | N/A | INT-CR1869 | Approved |  | ERP | R4 (Release 4) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 09A. Master Data 17. B-App | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | CR1199 | NA | NA | [5 empty] | Material Master Data Warehouse Management View Automation | 3 new attributes for automation of Material master Data Warehouse management View​ Handling Indicator, MARA-HNDLCODE​ Warehouse Storage Condition, MARA-WHSTC​ Relevant for Hazardous Substances, MARA-HAZMAT​ | Too resource intensive for manual entry. | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1869%20-%20EWM%20Parameters%20Update%20Automation.pptx?d=w959ff44f029540c1842ac939cbd553ec&csf=1&web=1&e=37quhS |  | 0. Request for Investigation |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 10. OSC/CL Approved (end status) | Yes | No | 2026-04-02 |  |  |  | 2026-04-02 | [6 empty] | Other | CL/OSC | 2026-04-02 |  |  |  | 2026-03-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1870 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R3 (Release 3) | High | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation |  | 03. FPR 10. Analytics 18. SCP | james.deforrest@intel.com | Data & Analytics - Rebecca Verette | FPR - Aubrey Hinderlider |  | Part of an finance | none | none | [5 empty] | Demand Data in ECA | Request SAC inventory model data be available in ECA and Snowflake view for dashboard visualization | SAC is not able to support creating visualizations needed for inventory dashboards. Data from the model needs to be exported into an ECA environment in order to create the necessary dashboards to support the business process. | No forecasted impact to schedule | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CR1870-SAC%20Inventory%20Model.pptx?d=w5abcdd49200e434699d493b9016b53ed&csf=1&web=1&e=gmR8Ae |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by James Deforrest that the work is not for IAO and can be cancelled | Build | Not Assigned |  |  |  |  | 2026-03-28 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1871 | New |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 04. OTC IF 07. FTS IF 08. FTS IP | sunil.k.parida@intel.com | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | [9 empty] | Delivery status complete for final IP shipment Order | As part of detailed design and FUT activities, a gap was identified in the mechanism for IP to determine the final shipment for a build instruction, which is necessary to complete the production order in IP S/4. As part of POLP design, POLP will capture whether all the LOTs are complete or not for that sales order /sales order line. OTC logistics will create the Auto DN by reading the POLP Lot once all the LOTs are complete. Auto DN will create the Delivery Note. Once all Delivery Notes complete for that sales order, sales order line, sales order status will be updated as Delivery Complete( DLV); if not status will reman as partial delivery. OTC Logistics need to enhance the current logic to put the Delivery Status Indicator in the 3B2 IDOC segment. Once the Delivery note Pick Pack and PGI, IDOC will populate the indicator in segment; that segment will map to 3b2 Mapping. 3B2 outbound from IF S/4 to IP S/4 will carry the indicator in the payload. OpenText will need to pass this information via a change in the current object. IP SMH will receive the 3B2 outbound in IP SMH which will read the indicator to pass to the IP S/4. IP S/4 will receive the indicator and update the production order as delivery complete. | This needs to change, else IP will not know when to close the production order for that build instruction |  | No |  |  | TBD | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-30 | 9 | < 15 Days | jon.benoist@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1872 | New | Ready: Wednesday | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 06. PTP | 10.8 Analytics - PTP |  | 06. PTP 10. Analytics | Ambika Balasubramaniyan | Data & Analytics - Rebecca Verette | PTP - Richard Taylor |  | NA | NA | NA | [5 empty] | R4 Reporting Scope for PTP | Request approval to confirm and baseline the Release 4 (R4) reporting scope for the Procure-to-Pay (PTP) domain. This change formally establishes the list of reports required to be delivered as part of R4, enabling downstream planning, estimation, and other milestone planning. | R4 release scope approval | No negative impact as such as there are completely new reports/requests. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/R4%20Reporting%20Scope%20for%20PTP.pptx?d=w34da7eb159df4afb83c9c566508ea376&csf=1&web=1&e=12lRuG |  | 2. New RICEFW / ECA / Build Object |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 3 | ECAFTSIPV7118, ECAFTSIPV7121, ECAFTSIPV7122 |  |  | 0 |  | 0 | ECAFTSIPV7118, ECAFTSIPV7121, ECAFTSIPV7122 | 3 | 3 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1876 | Cancelled |  | ERP | R4 (Release 4) R5 (Release 5) | [21 empty] | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [14 empty] | Not Assigned |  |  |  |  | 2026-03-31 | 0 | < 15 Days | lopa.chaudhry@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1873 | New | Potentially Ready: has deck but need changes | ERP | R5 (Release 5) | Medium | 06. PTP | 6.2 PTP - Procurement |  | 08. FTS IP | krishna.subramanian@intel.com | PTP — Mike Nayab | PTP - Richard Taylor |  | timing of STO for OSAT originally was shortly before request date. Supplier are not able to implement, therefore we change the STO timing to order release date. | na | na | [5 empty] | DCR full automation for STO to SiFO / OSAT | current DCR automation stop at Text PO. Enhance to check for existing STO and then update STO request date / qty accordingly. If existing STO update failed, send notification for error resolution. 04/01 [RT] Link to supporting doc added, needs additional data. | Previously this scope was pushed from R3 by FTS-IP Karthic/Sekhar (Deloitte) All SiFO/OSAT shipments are impacted, if not implemented all STOs will need manual updates to ensure PO and STO stay in sync - this is a high risk of misalignment between demand signals, STO dates, and quantities, increasing the likelihood of incorrect supply execution, missed delivery commitments, and reactive exception handling. ​ | No Impact to Existing Deliverables | Yes | Non-Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/INT-CR1873_PTP_DCR%20full%20automation%20for%20STO%20to%20SiFO-OSAT.pptx?web=1 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1874 | Cancelled | Ready; effort estimate | ERP | R4 (Release 4) R5 (Release 5) | High | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | New Export Control Legal Regulations for Vietnam and China | New export-control legal regulations must be configured in GTS for Vietnam and China, including the underlying regulation content, numbering schemes, license-determination strategy, and the required license types to ensure compliant exports from both countries. | All exports from Vietnam or China must have the applicable export licenses assigned to the transaction. Accordingly, sales orders and outbound deliveries in S/4 will be checked in GTS to ensure the required licenses are determined and applied in line with local export-control laws and regulations. | N/A | No | Core |  |  |  | 3. Configuration Change |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to be a duplicate of CR1863 | Other | Not Assigned |  |  |  |  | 2026-03-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1875 | Cancelled | Ready; effort estimate | ERP | R5 (Release 5) | Medium | 04. OTC IF | 4.9 OTC IF - GTS |  | 04. OTC IF 05. OTC IP | mariana.campos.guilcrits@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | Bank/Payment Screening Functionality | Bank master data from MDG and payment from the CFIN system will be screened in SAP GTS for Sanctioned Party List matches. Any potential hits will automatically block the associated BP or payment transaction until Compliance review is done to confirm or release the block in accordance with Intel policy. | Performing Sanctioned Party List screening on bank master data and payment transactions helps prevent processing financial transactions involving sanctioned parties. Inadequate screening increases exposure to regulatory violations, substantial fines and penalties, and transaction blocks, freezes, or other enforcement actions. | N/A | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object 3. Configuration Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed to be a duplicate of CR1858 | Other | Not Assigned |  |  |  |  | 2026-03-31 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1878 | New | Potentially Ready: has deck but need updates | ERP | R4 (Release 4) R5 (Release 5) | High | 03. FPR | 3.8 FPR - Financial Planning & Analysis |  | 03. FPR 08. FTS IP 17. B-App | Jason Rollman | BApps — Kelly Gerber | FPR - Aubrey Hinderlider | [9 empty] | Revenue Forecasting Transformation | Transition revenue forecasting from SAP IBP to a future‑ready, enterprise‑aligned SAP Analytics Cloud (SAC) architecture, by migrating all revenue planning processes currently executed in SAP IBP—including POR and RevOpt for IP and IF, BU Finance and Regional forecasts, and Rebate Forecasting and Accruals—while continuing integration with SAP IBP, Blue Yonder, and ECA as core upstream and downstream systems. | Support real‑time margin scenarios and submissions required for timely business decisions. Optimize future SAP IBP license footprint and costs through revenue forecast re-platforming | R4/R5 | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1878_FPR_CF_Rev%20Forecasting.pptx?d=w8e0cf0de6086496e92af7ae855fbf13a&csf=1&web=1&e=HuoSf3 |  | 1. Process Scope / Design Change |  |  | High | High | 3 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | lopa.chaudhry@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1877 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF | yuliya.gula@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Master Warranty Update or Edit Reusable Object | Develop a program to update an existing Master Warranty with new Plant, Entity, and Item values. Use Batch Data Communication (BDC) to update item details and use the function module BAPI_OBJCL_CHANGE to update characteristic details such as Plant and Entity.​ | The functional specification (FS) was signed off in August ’25, and the solution was written and tested to create Master Warranties for each contract in a single run. Any subsequent characteristic updates are intended to be handled manually, and item updates will be completed either manually or via the auto-roll function. During the FUT review, it was identified that a program is needed to update new values in an existing Master Warranty. Developing a reusable template and bulk upload capability reduces manual entry, minimizes errors and rework, enables efficient onboarding of additional sites and machines, and allows for streamlined bulk updates to contract details such as expiration dates.​ | Medium | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4F956D92-0E2A-4E69-A65C-3B727551294D%7D&file=INT-CRXXXX%20-%20Master%20Warranty%20Update%20or%20Edit%20Reusable%20Object.pptx&action=edit&mobileredirect=true&previoussessionid=6f5acaab-bcfe-789a-a9cc-28310d1b3e37 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1879 | New |  | ERP | R2 (Release 2) | Low | 09A. Master Data | 9A.1 Master Data - ALL |  | 09A. Master Data | Khetan B | Data & Analytics - Rebecca Verette | Data - Julie Fawdington | [9 empty] | IDOC MONITORING PROGRAM | •When the program is scheduled as a background job, it gathers failed IDOCs details and sends the emails to the relevant stakeholders with error details. | •Business users have to login to system to monitor for IDOCs Inbound errors and still have manually download information for further actions •Team needs spend significant amount of time in resolving the issue to reduce business impact when failure of data for Inbound IDOCs •Quick response to IDOC failures, there by reducing the business impact. •Reduces the time taken for team to generate the error IDOC information and reprocess them |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-Build-CRXXX%20%E2%80%93IDOC-MONITORING-PROGRAM-%20Copy.pptx?d=w8a2f75408d8446dfa853601ee77b3ab0&csf=1&web=1&e=EiFxOl | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | khetanx.b@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1880 | New |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | NA | NA | NA | NA | [5 empty] | Design for Linkville/Connorville | Link-/Connorsville use DLCP in the middle of class test to segregate industrial and commercial use of product. Class test continues with different spec, MMID and price for the variants. When we use a PROC item for first class test execution than the natural distribution is covered by co-products. Second class test order with different price per variant (MMID) used for shipment to FG WH. ​ | WIP tracking by production order will require manual adjustments during class test operation. Email communication from supplier requesting adjustments on orders – prolonged manufacturing cycle time. No visibility of product variants till end of process. ​ |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR1880-Design_for_LinkvilleConnorville.pptx?d=w7826dbc083f24308912511d927266f73&csf=1&web=1&e=NYHeui | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-03-31 | 8 | < 15 Days | khetanx.b@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1881 | New | 4/7: Followed up with JR/Laura/Ramadas | ERP | R4 (Release 4) |  | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF | Laura Marshall | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | [9 empty] | TPTD | BDL/SDL, formerly TPTD, was taken out of scope, in August 2024, for SAP PM. Along with it there were 26 L3s that were descoped along with potential config changes and incremental FS to account for teams using SAP PM in ECC today. | BDL/SDL are currently utilizing SAP ME. SAP ME will EOL 2030. Need to weigh the Pros/Cons of implementing SAP PM vs. Legacy SAP ME. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R4/INT-CR1881-%20TPTD.pptx?d=wb1fdc0580b7647ceb0c3fa3ff4b110f8&csf=1&web=1&e=PgDwAb | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | hweller@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1882 | New | 4/7: Followed up with JR/Laura/Ramadas | ERP | R4 (Release 4) |  | 07. FTS IF | 7.9 FTS IF - Plant Maintenance |  | 07. FTS IF | Laura Marshall | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma | [9 empty] | Regulatory Compliance Requirements for Malaysia/Chengdu/Vietnam | To investigate connections to IAO for a new boundary app to address E2E Duty Free Asset Management to enable sites functioning in Duty Free Zones to meet local regulatory obligations. ​ | Intel Malaysia through an IA Audit finding conducted a deep dive to determine systemic gaps and build predictable E2E systems for managing Duty Free Assets (which per customs definition consists of machinery and equipment, manufacturing aids, cleanroom and spares) different from Finance Asset Management. Intel Malaysia through trade facilitation enjoys significant tax exemptions to operate in 4 Legal Entities and across multiple customs zones, each with different requirements to meet.) Current systems to manage this is highly disintegrated, does not comprehend essential data and information to meet the requirements for duty free asset management across the asset lifecycles which often include reusing, harvesting and movement of goods across the LE and custom zones.. Traceability and reconciliation is broken given the complexity and scale of operations. The team has now developed an E2E framework to manage this and gotten the value decision approval from management to go build this new system which we believe would constitute a boundary app that integrates trade requirements with supply chain data and operations management. It will cover all Intel Foundry and Intel Product groups that reside in the zones. Recent alignment with Trade suggests that given Malaysia’s complexity and years of operating in Duty Free Zone, there is an opportunity to build & pilot this in Malaysia and scale this to other sites that will be required to operate in Duty Free Zones i.e. Vietnam, Costa Rica, Ohio and Arizona. |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R4/INT-CR1882%20-%20regulatory%20Compliance%20Requirements%20for%20Malaysia%20Chengdu%20Vietnam.pptx?d=w6a7f3053fc2f4274865e4bc1d9b18a75&csf=1&web=1&e=wBSn7X | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | hweller@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1883 | New | Potentially Ready: has deck, pending Deloitte estimates | ERP | R4 (Release 4) | High | 09A. Master Data | 9A.2 Master Data - BOM |  | 03. FPR 17. B-App 18. SCP | jayant.kashikar@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Order Point Removal | Order Point on UPI Design Change for R4/R5 | TBD | None | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/R4-R5%20MD%20CRs/Item-BOM/INT-CR1883%20-%20Order%20Point%20Removal.pptx?d=w5ec2a1ade0c54cc3a18a9c21a3b03cff&csf=1&web=1&e=VhvrpB |  | 1a. Operations Design 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1884 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 09A. Master Data | michael.hallock@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | CR1841 | N/A | N/A | [5 empty] | PROC Creation for single-die wafers | Expand logic for when to create a PROC to include single-die wafers | The current Master Data management design will create a proc only in the case of multiple possible output parts (i.e., co-products). However, the use of procs as a modeling tool within BY has expanded beyond this use case. PROCs and the related modeling structure (BY’s Production Yield table) are also used to capture UOM transitions (e.g., wafer to Die) and the impact of good die per wafer. Without PROC's single-die wafers are unplannable with current design | Need team's feedback | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/IP%20SP%20CRxxxxx%20-%20Proc%20Items%20for%20single-die%20wafers.pptx?d=w212d9bdf11874ab081c4e997957319d8&csf=1&web=1&e=SwojSf |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1885 | New | 4/6: Kelly to work with teams to get deck | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | Low | 07. FTS IF | 7.2 FTS IF - Business |  | 17. B-App | eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Inclusion of IHS (Lids, Preform, Stiffener), and Interposer for material feasibility assessment | TBD: Reviewed.Eugene C. to Pre-Approve. Exploring in progress.Inclusion of IHS (Lids, Preform, Stiffener), and Interposer for material feasibility assessment | TBD: Eugene C. to Pre-Approve. Inclusion of IHS (Lids, Preform, Stiffener), and Interposer for material feasibility assessment | R4 | No | Non-Core |  |  |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1886 | New | 4/6: Kelly to work with teams to get deck | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Exclusion of Direct Materials with Block (S status in SAP) status in SAP Storage Location (RMx, ENx, KBx) as available supply in FFS material feasibility assessment. | TBD:Reviwed.Eugene C. to PRE APPROVE. Exploring alternate options. Sunil P. & Anil U. Exclusion of Direct Materials with Block (S status in SAP) status in SAP Storage Location (RMx, ENx, KBx) as available supply in FFS material feasibility assessment. | R4 | R4 | No | Non-Core |  |  |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1887 | New | 4/7: Followed up with Kelly | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 17. B-App | eugene.celis@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | CMP:DTC Yield automation from ICS/E2OPEN | Eugene C. pre-approved. Requested by R,RajKumar. DTC Yield automation from ICS/E2OPEN | CMP: DTC Yield automation from ICS/E2OPEN | R4 | No | Non-Core |  |  |  | 11. Boundary Apps-related Change |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1888 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly Moore | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | R4C Data Archival Strategy Implementation | Implement a data archiving strategy for R4C | Estimate cost of $51K/yr ( $6k per 10GB) will be required as data archival needs grow | R5 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Change%20Request/CR%20Forms/INT-CR1888%20-%20R4C%20Data%20Archival.pptx?d=w5f0ea0f31de84cdab4c75346efb996fe&csf=1&web=1&e=lHnsWY |  | 11. Boundary Apps-related Change |  |  |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | kimberly.moore@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1889 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | Raised post Design solution as a part of R4CT UAT | NA | NA | [5 empty] | Validation Result - CATTS record for NPHF | BAG/Inconclusive record: Instead of reflecting NPHF(as it is locating the latest records in CATTS), system should have the validation result reflecting other purchases within the CATTS Box Report as positive purchaser for INCONCLUSIVE state ULT. | This impacts Returns ability to correctly assign entitlement during customer returns - purchase history is not accurately being determined in all cases | No impact - requested for R4/R5 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1889%20-%20NPHF%20Logic%20Update.pptx?d=wfeca7a51b26e40368095156bd64ebfc4&csf=1&web=1&e=TDsXMV |  | 11. Boundary Apps-related Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1890 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) R5 (Release 5) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly Moore | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | Raised post Design solution as a part of R4CT UAT | NA | NA | [5 empty] | Entitlement validations for PO History using CPN | To look up CPN at the BAG level instead of CMF level in R4C | Customer needs to be able to choose CPN and should be coming from transaction data rather than Master Data | No impact - requested for R4/R5 | No | Core | [8 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO |  | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | kimberly.moore@intel.com |  | No |  |  |  | In Progress | No
|  | INT-CR1891 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | Pull SN associated batches from SNTRAX | Batch is associated to SN in SNTRAX for certain products – these batches are needed for country of origin determination . Now we only get from CATTS, but needed from both SNTRAX and CATTS to correctly select the correct COO. | Compliance with COO requirements | No Impact to Existing Deliverables | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1891_%20Pull%20SN%20associated%20Batches%20from%20SNTRAX.pptx?d=we8b2e04804434b04a2d5681be1708846&csf=1&web=1&e=XC29eg |  | 11. Boundary Apps-related Change |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1892 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | Entitlement validations for PO History using CPN | Customer to be able to look up CPN at the BAG level instead of CMF level in Salesforce to ensure accurate entitlement | If CPN is not tied to correct BAG, entitlement details are incorrect and customer is credited incorrectly. | None - R4/R5 | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1892_%20Entitlement_Validations_PO_History.pptx?d=w2c449bf6f7ef4071951a90f6065158ac&csf=1&web=1&e=8yEFjX |  | 11. Boundary Apps-related Change |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1893 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) R5 (Release 5) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | PLACEHOLDER - Enhancements to Case Auto Closure rules and the overrides by agents | Details to follow | Accurate capture of auto-closed RMA cases | None | No | Non-Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1894 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | Medium | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | Entitlement & Scanning Log Archival | Enable archiving for receiving data stored in table to prevent performance issues due to very large line item searches | PRvent performance issues in Receiving process | None | Yes | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1894%20-%20Entitlement%20%26%20Scanning%20Log%20Archival.pptx?d=w55fcc80a764a456a8522bce164301c92&csf=1&web=1&e=aWZhS5 |  | 11. Boundary Apps-related Change |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1895 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5 (Release 5) | Medium | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | RMA Case Mgmt - Holiday Calendar | Establish maintenance screen allowing users to select country holidays for customer pick-ups, data to be uploaded via Excel | Previous holiday calendar solution no longer exists with R3 - need a way to manage customer pick-ups in consideration of holidays | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Change%20Request/CR%20Forms/INT-CR1895%20-%20Holiday%20Calendar.pptx?d=w3d390af47ea4457cad0c239acd81bb8d&csf=1&web=1&e=wUccNi |  | 11. Boundary Apps-related Change |  | Yes |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1896 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R5+ (Post Release 5) | Medium | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | Warranty cancellation Interface enhancement - Switch to source system | Call is from R4C(downstream system) in current design, architecture design should call from SAP since source system for credit issue– | Incorrect architecture design and if called from R4C additional cost associated w/ API calls | None | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Change%20Request/CR%20Forms/INT-CR1896_Warranty_Cancellation_Interface_Enhancement.pptx?d=w175b090d9d4d45a5b746719c6ee2559c&csf=1&web=1&e=nfnGzS |  | 11. Boundary Apps-related Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Kelly Gerber that these are related to returns and can be handled outside of IAO | Other | Not Assigned |  |  |  |  | 2026-04-01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1897 | New | 4/7: Kelly followed up with team | Other (Boundary Apps, Data Transformation) | R4 (Release 4) R5 (Release 5) | High | 05. OTC IP | 5.15 OTC IP - Boundary Apps |  | 05. OTC IP 17. B-App | Kimberly.Moore@intel.com | BApps — Kelly Gerber | OTC IP - Teresa McNicol/Jon Benoist |  | NA | NA | NA | [5 empty] | Addition of OSAT Data in CATTS | • Current state of ULT data (a past decision defined a hybrid OSAT flow, likely originated from TD/CPG alignment but no clear current owner/documented E2E business process): o Intel manufactured parts - > CATTS o OSAT manufactured parts -> TD Filer only (as backup, retained for 7 years) • This historical decision prevents ICS/ Warranty teams from validating OSAT parts returned by customers, resulting in potential false OOW cases | Gap in ULT data that leads to false OOW designation - customer returns incorrectly rejected. | None | No | Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | Very High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1898 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | niamh.b.doyle@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | EWM Labels | Labels do not have all the necessary fields to support the warehouse operator and support BCP | Change request is to update EWM labels to support BIZ operations between Warehouse & Factory & labels meet 2D data matrix ANSI standards​ | Medium | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCA5CFDFA-319F-47E1-86D1-FFDC96458BFE%7D&file=CR-1898%20EWM%20Labels%20&%20Documents%20updates.pptx=&wdLOR=cDDF62556-6CB9-4FD1-A96B-B116E6743C4B&action=edit&mobileredirect=true |  | 0. Request for Investigation |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1899 | New |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 10.1 Analytics - ALL |  | 07. FTS IF 10. Analytics | sunil.k.parida@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | R3 Cutover for Production Orders | During Cut over IP is going to create the production order using current SPAN schedule also it will generate the build instruction send it to IF IF will create the Sales order . For cut over generate a Report that sequence lots in order that they will get to order point ,then assign the LOTS to sales order using FIFO. This report will be using the Prod scheduling FSCO/YETA /FFS and CIBR data .Using that Report then load these data into the POLP table in IF S4..That would help Sales order to be pegged to Lot .if any LOT is not able to assigned to the sales order and sales order line item Report will capture as a fall out reports that would help business user to analyze and manually take the action to assign the sales order These data will be uploaded manually in POLP table Finance will use these data to upload the WIP values per production order per cost component structure using the KB15 N conversion of WIP values to IF S4 | To Support R3 Cut over | Intercept MC2 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/CR_CutOver.pptx?d=wfd75fa4d3a14401790daf2b3a480e039&csf=1&web=1&e=L4Zca6 |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-01 | 7 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1900 | Cancelled |  | ERP | R4 (Release 4) | High | 06. PTP | 6.9 PTP - Plant Maintenance |  | 06. PTP 07. FTS IF 17. B-App | ranju.pancholi@intel.com | PTP — Mike Nayab | PTP - Richard Taylor |  | CR#1018 | n/a | n/a | [5 empty] | ECM Copper Repair Process | Enable foundational process for repairable copper parts *04/06 [RT+SS+RP] CR to be cancelled* | ECM and Plant Maintenance | No, R4 scope | No | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR-1018%20-%20Cu%20Repair%20loop%20-%20500%20to%206.pptx?web=1 |  | 0. Request for Investigation 1. Process Scope / Design Change 11. Boundary Apps-related Change |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed in comment from Richard Taylor that this is cancelled from R4/R5 scope | Other | Not Assigned |  |  |  |  | 2026-04-02 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1901 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.8 OTC IP - EWM | Yes | 05. OTC IP | Surendra Julury | [11 empty] | Automatic Storage type determination based on disposition status in custom receiving screen and update the bin information in GR custom table as well as SAQ screen after disposition confirmation. | Enhance the custom Receiving (GR) screen by adding a new column to display Disposition Status at the subline level. Determine the storage type and bin based on the disposition status assigned to the subline: Awaiting Dynamic Disposition: Users must manually determine and enter BIN_NUMBER using an appropriate bin in the GR-ZONE. Awaiting Manual Disposition: Users must manually determine and enter BIN_NUMBER using an appropriate bin in the GR-ZONE. | Based on the disposition status determined from the batch job, Storage bin to be determined and to be updated in custom table on Save in custom receiving screen. Bin should be used in SAQ screen to update and create the warehouse task when the disposition is determined for the Awaiting dynamic disposition and Awaiting Manual disposition Status |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/CRs/INT-CR1901_Bin%20and%20Disposition%20status%20CR.pptx?d=w68f119d17037489ea60baebe544b60e4&csf=1&web=1&e=hcIpua |  | 4. Change to Existing RICEFW / ECA/ Build Object |  |  |  |  | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-02 | 6 | < 15 Days | nanaved@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1905 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | CDD will not get change/update in IF order for 3PL Move feed | As per the current design , whenever ATP related changes are made in Sales order order confirmation gets restored if ATP iterim block(19) is not available in SO. In case of Build instruction scenario ,change in ship to party will happen and item cateogery gets flipped from ZVIR to ZCOP and since this is ATP relevant change , confirmation is removed from the SOLI. Requirement is to keep SOLI confirmed when ship to party is changed and item catogery is flipped from ZVIR to ZCOP. | System will remove CDD in IF order for 3PL Move feed i.e when ship to code and Item category ZVIR to ZCOP flip in the IF order. |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CR1905_CDD%20will%20not%20get%20change%20or%20update%20in%20IF%20order%20for%203PL%20Move%20feed.pptx?d=wd418067d993143b8b9e0ca501aa9d65f&csf=1&web=1&e=WVDF4j | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-04-02 | 6 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1906 | In Progress |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.11 OTC IF - Order Management |  | 04. OTC IF | Taposh Ganguli | OTC — Kevin Brown | OTC IF - Angela Laskowski | [9 empty] | Determining the delivering plant in the Sales order |  |  |  | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/Plant%20Determination%20in%20IF%20SO/INT-CR1906(Investigation%20CR)-%20Determine%20Delivery%20plant%20in%20IF%20Sales%20Orders.pptx?d=w8b0d1dc5f6c44c449fbe35dbafc8200d&csf=1&web=1&e=GagimW | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | [15 empty] | Not Assigned |  |  |  |  | 2026-04-02 | 0 | < 15 Days | kgajananchaporkar@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1907 | New |  | SCP | R3 (Release 3) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 06. PTP 07. FTS IF | sunil.k.parida@intel.com | FTS (SCP IF) — John Heiney | FTS IF - Haritha Komma |  | none | none | none | [5 empty] | IHS Capacity | Distribute the IHS Supplier provided capacity from Monthly capacity to weekly capacity after netting for POs issued in a month, and offsetting by Lead Time. before presenting the capacity to BY-IF | BY-IF weekly solve expects supplier IHS capacity on weekly basis and Dock out weeks. However supplier provides on a monthly basis and production starts week. This CR is translate supplier provided capacity to a format that is required by BY-IF | ITC3 | No | Core |  |  |  | 1b. Solution Design |  | Maybe |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-02 | 6 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1908 | New |  | ERP | R3 (Release 3) | Low | 09A. Master Data | 9A.7 Master Data - Reference |  | 09A. Master Data | lynn.asbury@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | NA | NA | NA | [5 empty] | Descope-MDCE0012- Sales Org Association – Custom Itego Object | Descope-MDCE0012- Sales Org Association – Custom Itego Object | The Sales Org Association object is no longer required. Its original design has been fully replaced by the following Itego custom objects, which were delivered by Intel IT and are already in place for testing and cutover: MDCE0023 (R3): Sales Organization – Extended Itego data model and UI to govern assignment to Sales Regions MDCE0022 (R3): Sales Region – Custom Itego object to govern Sales Regions | None | No | Non-Core | tbd | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/INT-CR%20Descope%20Sales%20Org%20Association%20MDCE0012%20Object.pptx?d=w9b60faa711b347a7bb2cc33e2aca38bc&csf=1&web=1&e=tajLrm |  | 5. Cancel RICEFW / ECA / Build Object |  | No |  | 0 | 0 | [13 empty] | 0 | 0 | N/A | No |  | 0 | N/A |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | N/A |  |  | 0 | [7 empty] | 0 | 00. Identified | No | [12 empty] | Other | Tower |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1909 | New |  | ERP | R1 (Release 1) R2 (Release 2) R2 Q4 '25 Anafi enablement R2.X (Between Release 2 & 3) R3 (Release 3) | High | 11. Technology | 11.3 Technology - Middleware |  | 11. Technology | ravindra.b.neralakatte@intel.com | Infra/Tech/Middleware — Babu Jadam | Tech & Dev - John Camarillo |  | Change was identified because the DBaaS classic Platform is nearing end-of-life. | N/A | N/A | [5 empty] | DBaaS upgrade impact change | Update MuleSoft APIs (2 Apps) and related configuration parameters to incorporate the new DBaaS connection details, enabling connectivity to the new DBaaS instances. | DBaaS Classic is nearing end-of-life and will be replaced by the new DBaaS platform. All MuleSoft APIs and related configurations will be updated to connect to the new DBaaS instances, since DBaaS Classic will no longer be supported. This will not impact the business process flow and limited to technical functionality. | Implementation for the change is expected to be completed by: R1+R2+R2.5: End of May 2026 in Production R3: 24th April 2026 (before ITC1 starts) till QA. | No | Non-Core |  |  |  | 3. Configuration Change 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1910 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 08. FTS IP | eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | Extension of Build Instructions functionality to Assembly | N/A | N/A | [5 empty] | IP_IF Integration: Build Instructions for Assy | 1.) IP_IF: Substrates Vendor specific build instructions from IP. Currently not existing IFS requirement. IP does not have Build Instruction for Assy that specifies substrates but IF ATD has highlighted there are cases that only a specific substrates vendor can be used (sharing part# for different vendor) particularly in REV ENG. The CR will require IP to send this as part of Build Instruction via B2B, need to add in the UDF table and its mapping, need FFS logic to consume substrates specific in Build Instruction, need FFS to provide substrates vendor specific back to S4 interface. And S4 interface to WH. Potential Short-Term Mitigation plan: this can be part of manual/special instruction until this can be automated (but can’t be for long term). Release – TBD pending IP’s. (Matt can confirm this with IP NPP team but this is what ATD Chandler informed us) | IP_IF: Substrates Vendor specific build instructions from IP. Currently not existing IFS requirement. IP does not have Build Instruction for Assy that specifies substrates but IF ATD has highlighted there are cases that only a specific substrates vendor can be used (sharing part# for different vendor) particularly in REV ENG. | R4 | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1911 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 08. FTS IP | eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | Extension of Scrap functionality to remnant | N/A | N/A | [5 empty] | IP_IF Integration: K Lot Management | IP_IF: K lot management (small remnant unit that could have been scrapped but saving unit for potential recovery which adds more TPT and capacity due to additional re-test – this is pre-SFGI material and not part of the mfg reconfig at PLM). This is to support both IP and ANAFI part of IDM1.0 into IDM2.0. Target R4 unless manual process can’t be aligned for R3. | Optimization:small remnant unit that could have been scrapped but saving unit for potential recovery | R4 | No | Core |  |  |  | 1b. Solution Design |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1912 | New | 4/7: Followed up with Eugene/team | ERP | R3 (Release 3) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 04. OTC IF 07. FTS IF | eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | IFS: Extension of Ship Instructions functionality | N/A | N/A | [5 empty] | IFS:Anafi:Automate ship instructions from Build Instruction into STR and PDH | IF Only: different IFS customer requirement where customer ship instruction is part of the Build Instruction. Compared to IP design, the Customer ship instruction is a different file/B2B with Build Instruction. CR change description: need solution to automate the ship instruction (From and To location) from Build Instruction into STR and PDH. Once in Planning Datahub it will pass STR to STO and PDH ship instruction to RSQ. Pre-requisite: IFS customer to add FROM location to To Location for SHIP To. | Compared to IP design, the Customer ship instruction is a different file/B2B with Build Instruction | R4 | No | Core |  |  |  | 1b. Solution Design |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1913 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 04. OTC IF 07. FTS IF | eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | Extension of Auto DN Closure functionality | N/A | N/A | [5 empty] | Auto DN Closure needs Kitting information | IF Only: POLP table prior to Auto DN processing: potential corner case where Auto DN checks and that there are no Lot with SOLI in WIP, and all are in Warehouse, and could close the SOLI. But it lacks information that Kitting has not completed releasing all lots intended for the Sales Order. CR description: production scheduling sends indicator if there are no additional lots planned to be release for that Planned Order/SOLI to PDH for IF BY. Need to send this data to S4 for Auto DN to check prior to triggering AUTO DN closure | Auto DN lacks information that Kitting has not completed releasing all lots intended for the Sales Order. | R4 | No | Core |  |  |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1914 | New |  | ERP | R3 (Release 3) | Low | 07. FTS IF | 7.4 FTS IF - EWM | Yes | 07. FTS IF | poh.mun.leong@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | N/A | N/A | N/A | [5 empty] | FTS IF_EWM_Change request for ECD Supplier Batch and SAP Batch Numbers | Change request to modify the existing EWM response to ECD Inventory Status and Hold/Release requests. ​For Inventory Status and Hold/Release response from EWM should be based on Supplier Lot/Batch information instead of the SAP Batch Number.​To enable this, logic changes are required within EWM for the existing objects -LOGI0520 – Inventory Status, LOGI0519 – Hold/Release, LOGI1601 – Custom Table Update | During Internal batch discussions ((RAID 01442) it was assumed that ECD could manage using the SAP internal batch number. However, ECD team has confirmed that the SAP batch number will not be available on their application screen, and ECD will require lot/supplier batch information in the Inventory Snapshot from EWM and will initiate Quan hold/release based on the lot/supplier batch information . Therefore, the current mapping does not support the actual operational process and must be revised. | No Impact to existing deliverable | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR-XXXX%20FTS-EWM-ECD-IF%20Supplier%20Batch%20and%20SAP%20Batch%20Numbers.pptx?d=wa920c45fd3114183a639d995df040a92&csf=1&web=1&e=TaEuw7 |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No | Medium | Medium | 2 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  | 3 |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1915 | New | Ready: Wednesday | ERP | R5 (Release 5) | High | 06. PTP | 7.2 FTS IF - Business |  | 03. FPR 06. PTP 07. FTS IF 09A. Master Data | krishna.subramanian@intel.com | E2E/Architecture — Satya Vajjala | FTS IF - Haritha Komma |  | CR#1101 | n/a | n/a |  |  | 36978 | #NO MATCH |  | *NEW* SDL IF Factory Operation & Organization [Replacement for CR#1101 - however moved from FTS-IF Eugene to PTP Krishna and removed BDL scope] | SDL (Boards & Systems Development) underwent some organizational changes. W33 MRC approved that both will be supported using IF Applications. | Most development will be for R5 intercept, except for SAP ME which Factory automation will need to prioritize for R3 development with resource constraint. | R5 ITC1 | Yes | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/CR_1915_R5_SDL%20Change%20Request.pptx?web=1 |  | 0. Request for Investigation |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-03 | 5 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1916 | New |  | ERP | R3 (Release 3) | High | 11. Technology | 11.2 Technology - ABAP |  | 03. FPR 04. OTC IF 05. OTC IP 06. PTP 07. FTS IF 08. FTS IP 09A. Master Data | christopher.b.woodburn@intel.com | Infra/Tech/Middleware — Babu Jadam | Tech & Dev - John Camarillo |  | this is to identify if AIF needs to be present based on business design | 3577 | 3577 | [5 empty] | AIF refactoring discussion with Tower leads | Discussion with tower leads to validate if AIF is needed for interfaces. | To make better use of existing reprocess mechanisms | Parallel work during ITC1 | No | Core |  |  |  | 0. Request for Investigation |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-04 | 4 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1917 | New |  | ERP | R3 (Release 3) | High | 08. FTS IP | 8.2 FTS IP - Business |  | 08. FTS IP | Sekhar Lingam | FTS (ERP) — Stef Maxey | FTS IP - Loni Adams | NA | NA | NA | NA | [5 empty] | Delivery Tolerances Maintained in Material Master | Under-delivery and over-delivery tolerances are required for HVM, with different tolerances required (UNL over-delivery and ≤99.9% under-delivery) for Engineering and PROC/co-Products. Will require RECEFW update, Reference Material population at time of MM creation, and on-going Master Data governance process. |  |  | No |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/R3/INT-CR1917_Delivery_Tolerances_Maintenance_in_MM.pptx?d=w623651c6fb2d49eb87f238b3ea2acdd3&csf=1&web=1&e=tQbHd7 | [6 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-04-06 | 2 | < 15 Days | jon.benoist@intel.com |  | No |  |  |  | N/A | No
|  | INT-CR1918 | New | Potentially Ready: has deck, need updates | ERP | R4 (Release 4) R5 (Release 5) | Medium | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | carolyn.g.chiafulio@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | FPR R4 & R5 ECA Views & 3rd Party Reports | R4/R5 FPR Reports needed | R4/R5 FPR Reports needed | TBD | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRxxxx-FPR%20R4%26R5.pptx?d=w91cdf1bbfd294df5b43f24e4bb04f931&csf=1&web=1&e=FTgJvr |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1919 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF | sri.harisha.sai.kasturi@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | 03831 | NA | [5 empty] | Bailment Scrap | Implement a standardized, scalable solution to trace warehouse scrap material (PN/Lot/Qty) into barrels (handling units) at the time of scrapping. This includes capturing traceability data in SAP S/4 + EWM, supporting both offsite and onsite crushing scenarios, ensuring accurate reporting for customer COD, trade compliance, and internal asset recovery. | Current warehouse scrap processes are largely manual and vary significantly across sites, limiting scalability and increasing risk of errors. A unified, system-driven approach using barrel IDs as handling units enables: Accurate mapping of lots to barrels for customer COD. Compliance with trade and government reporting requirements. Standardization across US, APAC, Ireland, and future Chandler operations. Reduction in manual reconciliation, emails, and human errors. | R4 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR_1919_IF_FTS_CR%20Bailment%20Scrap%20Tracing.pptx?d=w46b52aa7461c45349178888fab30389a&csf=1&web=1&e=QSTMDi |  | 2. New RICEFW / ECA / Build Object |  | Maybe |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1920 | New |  | Other (Boundary Apps, Data Transformation) | R5+ (Post Release 5) | High | 07. FTS IF | 7.15 FTS IF - Boundary Apps |  | 07. FTS IF 17. B-App | ananthakrishnan.padmanaban@intel.com | BApps — Kelly Gerber | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | SMART R4 Scope | 1. SMART - ATTD indirect materials enablement in SDA 2. SMART - ATM Multiple Warehouse Plant design integration for Direct and Indirect materials SDA 3. SMART (Supply Management and Materials Requirements Tool) - ION QTG data integration from new data source <Place holder> | Run/Grow Changes need to reflect for IAO Upstream Design changes for R4 Upstream data source changes for R4 | TBD | No | Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1921 | New |  | ERP | R3 (Release 3) | High | 07. FTS IF | 7.2 FTS IF - Business |  | 07. FTS IF 10. Analytics | sunil.k.parida@intel.com | Inventory/Logistics/FTS — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Update the SLED date for all the product and calculate the Seal date and update in batch attribute | R3-R4 straddle design- CIBR to ECA to IF S4 to update in batch attribute1:Seal Date = Obtained by processing CIBR Lot Attribute 9001/0001 and converted into SealWorkWeek IF S4: this need custom.2:Shelf Life Date = Seal Date of the Lot IF S4 + Shelf Life in Weeks maintained IF S4 R5 – End state: XEUS/MARS to IF SMH to IF S4 Using the Operation ID ,SMH will read the data it to IFS4 to update the seal date in Batch attribute Shelf Life Date = Seal Date of the Lot IF S4 + Shelf Life in Weeks maintained IF S4 | Change is part of our detail discussion with Business ops team | R3 - ITC2 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FTS/CR_1921_SLED%20IF%20FTS_straddle_%20end%20state%20CR.pptx?d=w9a534ce2eb514c7bbcbd8099ca917a9e&csf=1&web=1&e=VwH6pY |  | 1b. Solution Design 2. New RICEFW / ECA / Build Object |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1922 | New |  | Other (Boundary Apps, Data Transformation) | R5+ (Post Release 5) | High | 08. FTS IP | 8.12 FTS IP - Boundary Apps |  | 08. FTS IP 17. B-App | ananthakrishnan.padmanaban@intel.com | BApps — Kelly Gerber | FTS IP - Loni Adams |  | NA | NA | NA | [5 empty] | Goal State transformation to BY | Transform all CSP planning capabilities present in SAP IBP to BY | Align to Goal State Enterprise Landscape | TBD | No | Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1923 | New |  | ERP | R3 (Release 3) | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF 17. B-App | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | N/A | N/A | N/A | [5 empty] | 3B2 ASN Fixed Fields_IF to IP | Required fields in 3B2 ASN were found to be missing for IF to IP Virtual Shipments during FUT review. Virtual Shipments do not pass thru Transportation Management <TM>, which will require logic to add missing values to 3B2 ASN before sending 3B2 ASN for Virtual Shipments to IP. | Required fields for IP system to properly process the Virtual Shipment 3B2 ASN, needed to trigger downstream processes. | Planned to intercept ITC1 | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_3B2%20ASN%20Fixed%20Fields_IF%20to%20IP.pptx?d=w7ef7e577f9d946488fca133d3c4dc8af&csf=1&web=1&e=GYku3k |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1924 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | Chad.smith@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | 1705 | na | na | [5 empty] | Milestone change for CR1705 (What-if Demand Prioritization UI ) | CR to change build complete milestone for CR1705 | schedule change | na | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/intelspinnakerdeloitteiao/Shared%20Documents/IP%20Supply%20and%20Materials%20Planning/3%20Development,%20Build_Test/CCB/INT-CR1924%20Milestone%20Change%20for%20CR1427_1705.pptx?d=w81272f61c49b46caa7e2798bb44d672b&csf=1&web=1&e=6a7KtO |  | 13. Other Milestone Adjustments |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1925 | Cancelled |  | Other (Boundary Apps, Data Transformation) | R4 (Release 4) | High | 06. PTP | 6.10 PTP - Boundary Apps |  | 06. PTP 17. B-App 18. SCP | anitha.somasundaram@intel.com | BApps — Kelly Gerber | PTP - Richard Taylor |  | NA | NA | NA | [5 empty] | OSAT PRF Auto-publication Control in e2open | The HVM PRF for OSAT is published by planners in BY which is directly pushed to PDH and then to e2open. The ask is for SLMs to have the option in e2open to configure the setting to auto publish the PRF to Supplier per vendor and stage. If Auto-Publication is turned On, PRF is directly published to supplier. If Auto-Publication is turned Off, once PRF is available in e2open, SLM must trigger the publication to supplier. | To Enable release point in E2Open for SLMs before PRF is published to suppliers. This will ensure only the SLM to trigger PRF only to supplier per Vendor and stage. | TBD | No | Non-Core |  |  |  | 11. Boundary Apps-related Change |  | No |  | High | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 16. Cancelled by Requestor Tower | [12 empty] | Confirmed by Amrutaunshu Nerurkar to be cancelled. | Other | Not Assigned |  |  |  |  | 2026-04-07 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | In Progress | No
|  | INT-CR1926 | New |  | ERP | R2.X (Between Release 2 & 3) | Low | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | Improvement to existing troubleshooting process by Ops. | No RAID | No KDD | [5 empty] | SMQ2 Access Cleanup Request | To streamline Operations common PPF error troubleshooting and resolution timelines, provide SMQ2 queue clear/execute permissions to Ops Manager role (Inv. Area Manager) and remove transaction access from Warehouse Operator and Ground Controller roles. | Real-time resolution of some PPF locking issues thru the SMQ2 queue. Avoids opening of urgent P1/2 ticket and FFID assignment to clear queue to get product moving thru the system. | No impact to schedule. This is a CR for Operate (R2). | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-CRXXXX_IF_SMQ2%20Access%20Cleanup%20Request.pptx?d=wbd9ddfa29d9442e9b147c8ae6afcc43a&csf=1&web=1&e=NE58Tv |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1927 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 05. OTC IP 08. FTS IP | Solomon.levinrad@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | n/a | n/a | n/a | [5 empty] | Automate post-Si sourcing lane creation | Implement logic to automate post-Si sourcing lane creation | Currently sourcing lanes are automatically derived and generated for Si to OSAT based on BOM in PDH. However, there is no automated logic for Post-Si sourcing lanes which will require significant manual work and offline scripting for upload to ensure proper supply planning network is being modeled. | TBD | No | Core |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/SCP/CR-xxx%20automate%20post-Si%20sourcing%20lane%20creation.pptx?web=1 |  | 1b. Solution Design |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-07 | 1 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1928 | New |  | ERP | R3 (Release 3) | Medium | 03. FPR | 10.3 Analytics - FPR |  | 03. FPR 10. Analytics | carolyn.g.chiafulio@intel.com | Data & Analytics - Rebecca Verette | Data - Julie Fawdington |  | N/A | N/A | N/A | [5 empty] | FPR R3 Report Updates | FPR R3 Report Updates | FPR R3 Report Updates | Deliver reports by ITC3 | No | Non-Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Analytics/INT-CRXXX-FPR-ReportUpdates.pptx?d=w69815464841741309d94d9864f2619ff&csf=1&web=1&e=lyWFPC |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1929 | New |  | SCP | R3 (Release 3) | Medium | 08. FTS IP | 8.10 FTS IP - IP R3 Supply & Material Planning |  | 08. FTS IP | michael.hallock@intel.com | FTS (SCP IP & OP) — Chad Smith | FTS IP - Loni Adams |  | na | na | na | [5 empty] | PROC Creation for single-die wafers | Expand logic for when to create a PROC to include single-die wafers | The current Master Data management design will create a proc only in the case of multiple possible output parts (i.e., co-products). However, the use of procs as a modeling tool within BY has expanded beyond this use case. PROCs and the related modeling structure (BY’s Production Yield table) are also used to capture UOM transitions (e.g., wafer to Die) and the impact of good die per wafer. | na | No | Core |  | tbd |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1930 | New | 4/7: Followed up with Eugene/team | ERP | R4 (Release 4) | Medium | 07. FTS IF | 7.2 FTS IF - Business |  | 02. E2E Process Integration | Eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | Pelican ATM startUp (From R5 to R4 scope) and adding Assembly Test stage | Pelican ATM startUp (From R5 to R4 scope) and adding Assembly Test stage | Need for R4. Pelican ATM startUp (From R5 to R4 scope) and adding Assembly Test stage | R4 | No | Core |  |  |  | 3. Configuration Change 7. Non-Build Data Conversion Changes |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1931 | New |  | ERP | R4 (Release 4) R5 (Release 5) | Medium | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration |  | 07. FTS IF | Eugene.celis@intel.com | FTS (ERP) — Stef Maxey | FTS IF - Haritha Komma |  | NA | NA | NA | [5 empty] | capture the substrate inventory undergoing preprocessing at the site. Currently this inventory is not captured . | capture the substrate inventory undergoing preprocessing at the site. Currently this inventory is not captured and not sure what is the source of this inventory too. | capture the substrate inventory undergoing preprocessing at the site. Currently this inventory is not captured and not sure what is the source of this inventory too. | R4/R5 | No | Core |  |  |  | 1b. Solution Design |  | Yes |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1932 | New |  | ERP | R3 (Release 3) | Medium | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | Yes | 05. OTC IP | manjunath.shastry@intel.com | OTC — Kevin Brown | OTC IP - Teresa McNicol/Jon Benoist |  | NA | [7 empty] | 1. Archive CI forms & PL on sharepoint for EDDAR. 2. Trade requirement to populate TW, CN for China shipments based on certain parametrs. | 1. Archive CI forms & PL on sharepoint for EDDAR. 2. Display Taiwan, China with comma on CI/PL for ALL China shipments and Ship To country has to be configurable. 3. Display TW, CN on IPLA for ALL China shipments and Ship To country has to be configurable. 4. Display TW, CN on Export CI/Sales Invoice/Consolidated CI for shipment from CN |  |  | No | [9 empty] | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [14 empty] | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | kpitroda@deloitte.com |  | No |  |  |  | N/A | No
|  | INT-CR1933 | New |  | ERP | R2 Q4 '25 Anafi enablement | High | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | Yes | 04. OTC IF | junior.milan@intel.com | OTC — Kevin Brown | OTC IF - Angela Laskowski |  | NA | INC15411123 | NA | [5 empty] | POLP Virtual Shipment Update | New POLP logic to consider SPLT transaction type in ZTOTC_TRX_POLP table for virtual materials relevant for PATPOLP. Changes cannot be implemented upstream; ECC is unable to modify the transaction type being shared to S4 to work with the existing SHLT logic. | Current POLP lot pegging logic checks for SHLT transaction type to identify lots for automatic DN creation. Virtual materials (item category ZVIR) relevant for PATPOLP require DN creation at SPLT transaction type stage. | Short-term solution requires manually workaround during Anafi Hypercare for impacted orders. | No | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/OTC/INT-Build-CRXXXX%20%E2%80%93%20POLP%20Virtual%20Shipment%20Update.pptx?d=w54e9ea63393e4c069fdf0862fb36489b&csf=1&web=1&e=y4xNsq |  | 4. Change to Existing RICEFW / ECA/ Build Object |  | No |  | Low | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Build | Not Assigned |  |  |  |  | 2026-04-08 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1934 | New |  | ERP | R4 (Release 4) | Medium | 02. E2E Process Integration | 6.4 PTP - Logistics Management Inbound | Yes | 06. PTP | vishal.jain@Intel.com | PTP — Mike Nayab | PTP - Richard Taylor |  | Not Applicable | Not Applicable | Not Applicable | [5 empty] | IFS Customer - Good Receipt - 4B2 - Direct Signal to Customer for the Bailed Inventory | Bailed Material - Customer need to receive the material in their ERP system like intel need to receive the material once 3PL receive the material on behalf of the Intel. The Customer/Customer Supplier will send the 3B2 for the Shipments. Once intel receives the material in Intel Warehouse ( 3PL/IM/EWM) we need to send the signal back to customer that intel has received the material. This will trigger Good Receipt in the Customer System and Intel can then receive the Production Order. | Foundry Standard Services Model- Customer Expect the 4B2 signal directly send to them once intel receives the Bailed Inventory | Not Applicable | No | Core |  |  |  | 1. Process Scope / Design Change |  | Maybe |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 | TBD |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Design | Not Assigned |  |  |  |  | 2026-04-08 18:01 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No
|  | INT-CR1935 | New |  | ERP | R3 (Release 3) | Medium | 03. FPR | 3.9 FPR - Treasury and Cash Management |  | 03. FPR | shivani.luthra@intel.com | FPR — Sara Cooper, Bharath Paturi, Nidhi Wadhwani | FPR - Aubrey Hinderlider |  | N/A | N/A | N/A | [5 empty] | Convert incoming MT199 (bank acknowledgement for pre-advice files) to pain.002 format​ | Convert incoming MT199 (bank acknowledgement for pre-advice files) to pain.002 format, for allowing the status update in SAP dashboards. | For all the pre-advice instructions - MT210s sent to the banks, the bank sends acknowledgements in MT199 format for these MT210s which is not compatible with SAP Advanced payment management (APM) system. SAP can only process acknowledgements in pain.002 format. Bank is sending files in MT199 format since SAP will be transmitting the files MT210 – payment pre-advice format. As a workaround there is a need to convert the MT199 format to SAP compatible format (pain.002). ​ | The goal is to reflect the status of the MT210 pre-advice acknowledgements in SAP Advanced payment management module. The volume of MT210/MT199 is 1400 in a year. | Yes | Core |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDFFBD27C-96A1-456A-96D1-4097BCB7F74B%7D&file=INT-1263.pptx&action=edit&mobileredirect=true |  | 2. New RICEFW / ECA / Build Object |  | No |  | Medium | 0 | [13 empty] | 0 | 0 | N/A |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | [7 empty] | 0 | 00. Identified | [13 empty] | Other | Not Assigned |  |  |  |  | 2026-04-08 18:04 | 0 | < 15 Days | web-form@smartsheet.com |  | No |  |  |  | N/A | No

## Comments
Row 4 | @dawn.l.kahane@intel.com - entered in CR tracker. ID CR0015. | Alpna Gainda | 03/16/24 6:52 PM
Row 26 | From the review with Mike in ERP huddle, Karthik/Sunil to put the overall estimate for NRT/RT reporting including infrastructure. Uzma to help schedule for an offline OSC in WW34 | Alpna Gainda | 08/15/24 1:12 PM
Row 26 | a,b,c,d are all done | Alpna Gainda | 08/15/24 1:11 PM
Row 26 | a. Update Change Request deck with scope of backend work (ingestion tables, data models etc.)– Sunil Narayanan/Neha Mehta/Karthik Subramanian b. Discuss best way to represent $0 CO – Anand Jha/Uzma Ahmed c. Bring CR details to ERP Huddle with Mike – Alpna Gainda DONE d. Check with Rebecca Verette to see if she is available on Thursday, 8/15 from 12PM-1PM PST for ERP Huddle – Sunil Narayanan Done | Alpna Gainda | 08/15/24 1:10 PM
Row 37 | This one is going to be moved out to next week | Miranda White | 08/22/24 3:38 PM
Row 42 | 10/16: After confirmation from Jesse and no objections from Prabesh, change record can go to PMO CCB prior decide if OSC review is needed. | Rafael A Quesada Alfaro | 10/16/24 8:31 AM
Row 44 | @debradas@deloitte.com , need you to work on estimates and revised dates for the form impacted with this request. Need to go to OSC next week. | Ruben David Alvarez Carroz | 09/12/24 4:10 PM
Row 52 | CR has been approved, new dates are attached | Leah Orzechowski | 10/24/24 7:24 AM
Row 53 | 09/26: We got the Technical effort hours be more than 13.5hrs ( Including the development and TUT/Tech. docs) from Isha Prabhakar. | Prasadu Bathini | 09/26/24 4:09 AM
Row 69 | approved to be cancelled during the Leadership DSU on 04/01/2025, Biz approval has been attached for reference as well. | Rafael A Quesada Alfaro | 04/01/25 12:32 PM
Row 70 | approved to be cancelled during the Leadership DSU on 04/01/2025, Biz approval has been attached for reference as well. | Rafael A Quesada Alfaro | 04/01/25 12:32 PM
Row 77 | This should be an internal CR and should be cancelled. This would be an internal CR and should be cancelled. | Vijayadeep Jillela | 01/17/25 5:28 AM
Row 80 | This should be an internal CR and should be cancelled. This would be an internal CR and should be cancelled. | Vijayadeep Jillela | 01/17/25 5:30 AM
Row 86 | @pranjayadav@deloitte.com @ray.m.oneill@intel.com - this looks like it can go into the FS Build Change tracker instead. since the time estimate is so low it wont need PMO or OSC review? please let me know | Brianne Ramirez | 10/15/24 4:48 PM
Row 198 | This should be an internal CR and should be cancelled. This would be an internal CR and should be cancelled. | Vijayadeep Jillela | 01/17/25 5:26 AM
Row 199 | This would be an internal CR and should be cancelled. This would be an internal CR and should be cancelled. | Vijayadeep Jillela | 01/17/25 5:26 AM
Row 200 | This would be an internal CR and should be cancelled. | Vijayadeep Jillela | 01/17/25 5:24 AM
Row 201 | @junior.milan@intel.com Please check the information I have submitted | Imme Sandweg | 01/15/25 4:48 AM
Row 207 | @anntam@deloitte.com this CR is no longer needed. | Lynn Asbury | 03/12/25 2:39 PM
Row 250 | "On further discussion with Kitty from business team, she is aligned to have “New Cost Center” field on Fiori app “Manage Cost Center” only. Per our discussion today morning, this will not require any new CR. " | Rafael A Quesada Alfaro | 02/27/25 8:58 AM
Row 250 | Needs to be Cancelled in SmartSheets | Rafael A Quesada Alfaro | 02/27/25 8:58 AM
Row 251 | Offline approval Requested to Uzma by GPO | Rafael A Quesada Alfaro | 02/27/25 8:59 AM
Row 272 | attached approval mail. | Kolleru Venkatesh | 02/21/25 3:44 AM
Row 278 | Approved on WW09.2 during the DSU leadership Waiting offline approval | Rafael A Quesada Alfaro | 02/27/25 9:00 AM
Row 279 | Approved on WW09.2 during the DSU leadership Waiting offline approval | Rafael A Quesada Alfaro | 02/27/25 9:01 AM
Row 294 | Attaching business alignment | Kritarth Joshi | 02/26/25 2:18 PM
Row 311 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 311 | Cancellation approval received from Anson. Email attached. | Kaushik Mhatre | 03/07/25 2:25 AM
Row 316 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 317 | @tasarvani@deloitte.com / @ankitax.vijay.rathod@intel.com Could you please check and update the hours for this CR. | Harshavardhan Harshavardhan | 03/04/25 5:25 AM
Row 331 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 332 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 333 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 337 | confirmed via chat that we have the alignments from all the teams DARC/APT, we are good to go and he sent a note to Shane - marked it ready for PMO Approval | Rafael A Quesada Alfaro | 04/16/25 8:28 AM
Row 337 | GM @kritajoshi@deloitte.com, we would like to follow on the AR for this CR to see when we could have a second round of review. pls advice! | Rafael A Quesada Alfaro | 04/16/25 7:59 AM
Row 337 | To proceed we will need to have a explicit confirmation of the work that will be transfer from DLT to Intel, and DARC agreement to proceed | Rafael A Quesada Alfaro | 04/10/25 12:41 PM
Row 337 | Rafael it is still in progress.. I am getting the latest comments from different sub-towers and will notify you when we are ready. | Kritarth Joshi | 03/17/25 2:45 PM
| Please provide and update details when be ready for review let me know. | Rafael A Quesada Alfaro | 03/21/25 9:32 AM
Row 337 | Dear @kritajoshi@deloitte.com, Please add more details for this request like the Object IDs, we reviewed and rejected this CR until that information has been added. | Rafael A Quesada Alfaro | 03/17/25 1:30 PM
Row 337 | This will need to be reviewed with the Scrum Lead since there is a lack of data for take a decision. | Rafael A Quesada Alfaro | 03/17/25 1:10 PM
Row 344 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 344 | We will need the ECA object from Hari to be added into the rationale field | Rafael A Quesada Alfaro | 03/17/25 1:14 PM
Row 345 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:31 PM
Row 345 | We will need the ECA object from Hari to be added into the rationale field. | Rafael A Quesada Alfaro | 03/17/25 1:14 PM
Row 349 | Hi Anna, We got an approval mail from Process Steward / GPO (Lafree, Shelly ) for the cancellation object : OTCI0615 (cancellation CR: CR0427) Could you please help us to get approval. Shelly approval mail attached FYI | Ramesh U | 04/04/25 5:35 AM
Row 350 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 351 | Uzma approved on 3/14/2025, waiting to be updated in SS. | Rafael A Quesada Alfaro | 03/17/25 8:27 AM
Row 351 | Hi @anntam@deloitte.com , we just reviewed and approved this CR to go to the CBB call. | Rafael A Quesada Alfaro | 03/13/25 12:36 PM
Row 352 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 353 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 353 | ask Hari to include the ECA object into the rationale. | Rafael A Quesada Alfaro | 03/17/25 1:19 PM
Row 354 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 356 | Hi @anntam@deloitte.com , We already have this CR ready for CBB review or offline approval process. | Rafael A Quesada Alfaro | 03/17/25 12:40 PM
Row 357 | Hi @anntam@deloitte.com , We already have this CR ready for CBB review or offline approval process. | Rafael A Quesada Alfaro | 03/17/25 12:41 PM
Row 358 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 359 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 364 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 365 | Reviewed with Leadership, agreed to be cancelled on 03/17. | Rafael A Quesada Alfaro | 03/17/25 1:32 PM
Row 369 | Approved on Leadership call to be cancelled | Rafael A Quesada Alfaro | 03/21/25 2:46 PM
Row 373 | Approved on Leadership call to be cancelled | Rafael A Quesada Alfaro | 03/21/25 2:46 PM
Row 377 | Approved on Leadership call to be cancelled | Rafael A Quesada Alfaro | 03/21/25 2:46 PM
Row 381 | This CR is ready | Rafael A Quesada Alfaro | 03/20/25 12:52 PM
Row 385 | @rafael.a.quesada.alfaro@intel.com Thank you! I will add to teh agenda | Anna Tam | 04/01/25 1:30 PM
Row 385 | Updates has been made, ready to check before be added into the CBB agenda. | Rafael A Quesada Alfaro | 04/01/25 10:21 AM
Row 385 | Hi @navnegi@deloitte.com please do the slides cleanup to have it ready for the presentation next Thursday. | Rafael A Quesada Alfaro | 03/28/25 11:01 AM
Row 385 | Good morning @anntam@deloitte.com , I would like to let you know that this CR is ready to be added to the CBB agenda for 4/3 if time permits. | Rafael A Quesada Alfaro | 03/28/25 11:00 AM
Row 394 | Good morning @anntam@deloitte.com , I would like to let you know that this CR is ready to be added to the CBB agenda for 4/3 if time permits. | Rafael A Quesada Alfaro | 04/01/25 12:27 PM
Row 394 | to be review on Leadership | Rafael A Quesada Alfaro | 04/01/25 10:21 AM
Row 394 | Not ready yet to be presented! | Rafael A Quesada Alfaro | 03/31/25 12:10 PM
Row 396 | Good afternoon @anntam@deloitte.com, we just finish the review of this CR and is ready to be added for a CBB review or offline approval process. | Rafael A Quesada Alfaro | 03/27/25 12:26 PM
Row 402 | approved to be cancelled during the Leadership DSU on 04/01/2025, Biz approval has been attached for reference as well. | Rafael A Quesada Alfaro | 04/01/25 12:33 PM
Row 402 | Reviewed and Approved during the DSU on 4/1/2025. | Rafael A Quesada Alfaro | 04/01/25 12:16 PM
Row 403 | approved to be cancelled during the Leadership DSU on 04/01/2025, Biz approval has been attached for reference as well. | Rafael A Quesada Alfaro | 04/01/25 12:33 PM
Row 403 | Reviewed and Approved during the DSU on 4/1/2025. | Rafael A Quesada Alfaro | 04/01/25 12:16 PM
Row 404 | approved to be cancelled during the Leadership DSU on 04/01/2025, Biz approval has been attached for reference as well. | Rafael A Quesada Alfaro | 04/01/25 12:33 PM
Row 404 | Reviewed and Approved during the DSU on 4/1/2025. | Rafael A Quesada Alfaro | 04/01/25 12:16 PM
Row 414 | Approved for cancellation. | Rafael A Quesada Alfaro | 04/02/25 12:28 PM
Row 416 | Good Afternoon @anntam@deloitte.com , we have this CR already reviewed and status will be change as ready for review. | Rafael A Quesada Alfaro | 04/02/25 12:36 PM
Row 420 | 04/14: CR has been reviewed and Discussed in the Leadership DSU. GPO agreed to proceed with this Change record. | Rafael A Quesada Alfaro | 04/14/25 12:48 PM
Row 420 | 04/10: FA No Shown, moved to friday | Rafael A Quesada Alfaro | 04/10/25 1:11 PM
Row 420 | requestor sub team changed from team 11 to team 5. as per George confirmation | Rafael A Quesada Alfaro | 04/09/25 11:56 AM
Row 425 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com Please help us to Cancel this duplicated CR. | Rafael A Quesada Alfaro | 04/10/25 12:35 PM
Row 425 | This CR is duplicated with INT-CR0411. and must be cancelled to proceed with the other one raised by Kritarth. | Rafael A Quesada Alfaro | 04/10/25 12:32 PM
Row 429 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com we review, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/10/25 1:07 PM
Row 431 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com we review, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/10/25 1:07 PM
Row 432 | 04/10: Hi @bcoffey@deloitte.com , @anntam@deloitte.com we review, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/10/25 12:51 PM
Row 432 | 04/40: Reviewed and approved in the Leadership DSU to proceed with the cancellation | Rafael A Quesada Alfaro | 04/10/25 12:49 PM
Row 434 | RICEFW ID OTCM026_IP | Atir Rajput | 04/15/25 1:10 AM
Row 436 | 04/14: CR has been reviewed and Discussed in the Leadership DSU. GPO agreed to proceed with this Change record. | Rafael A Quesada Alfaro | 04/14/25 12:51 PM
Row 436 | 04/10: FA No Shown, moved to friday | Rafael A Quesada Alfaro | 04/10/25 1:11 PM
Row 437 | 04/14: CR has been reviewed and Discussed in the Leadership DSU. This CR must wait until a complementary Change to present both together. CR is on ice until then | Rafael A Quesada Alfaro | 04/14/25 12:59 PM
Row 437 | 04/10: FA No Shown, moved to friday | Rafael A Quesada Alfaro | 04/10/25 1:11 PM
Row 441 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com we review, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/14/25 12:18 PM
Row 441 | 04/14: CR has been reviewed and Discussed in the Leadership DSU. GPO agreed to proceed with this Change record. | Rafael A Quesada Alfaro | 04/14/25 12:18 PM
Row 441 | Good afternoon mpuvvala@deloitte.com could you please attached the disposition for this CR, Prabesh said that this will be covered in the Leadership call tomorrow, but the PPT is not available for review. | Rafael A Quesada Alfaro | 04/10/25 1:13 PM
Row 448 | Business confirmation has been provided. this will be offline shared with GPO to get approval for object cancellation. | Rafael A Quesada Alfaro | 04/16/25 2:32 PM
Row 448 | 04/14: Tax team asked for more time before defend this case. | Rafael A Quesada Alfaro | 04/16/25 7:27 AM
Row 449 | Hi Rafael, yes! I will mark as Cancelled | Anna Tam | 05/08/25 1:32 PM
Row 449 | Good Morning @anntam@deloitte.com, Could you please help us to mark this as cancel? I got confirmation from Candice that this should be cancelled and no longer presented. proof has been attached. | Rafael A Quesada Alfaro | 05/07/25 9:05 AM
Row 449 | From Candice: We need a few more days on this. Give us until next week, please. I’m hopeful we can enhance an already approved enhancement and depending on where Deloitte is at in Build, it may not be a large amount of work/rework. | Rafael A Quesada Alfaro | 04/23/25 8:54 AM
Row 449 | 04/23: Rachel Goulding said that this is already aligned, GPO approved and Candi from MD approved, so this is ready for CBB. | Rafael A Quesada Alfaro | 04/23/25 8:52 AM
Row 449 | 04/14: CR has been reviewed and Discussed in the Leadership DSU. A deeper discussion about Biz and IT is needed to align the scenarios, MM for proper derivation, and other scenarios. then we can have a second review before marking it as ready. | Rafael A Quesada Alfaro | 04/14/25 12:45 PM
Row 451 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com FPR reviewed this case late last week, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/22/25 10:31 AM
Row 451 | Kalyan told me that this CR was reviewed by GPO while i was out of office therefore this CR can be marked as ready. | Rafael A Quesada Alfaro | 04/22/25 10:31 AM
Row 456 | Hi @bcoffey@deloitte.com , @anntam@deloitte.com we review, and this CR is now ready for review, please help us to add it to the agenda for CBB review. | Rafael A Quesada Alfaro | 04/15/25 12:25 PM
Row 456 | 04/15: Reviewed on the DSU and approved to move forward. | Rafael A Quesada Alfaro | 04/15/25 12:25 PM
Row 464 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 1:03 PM
Row 465 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 1:03 PM
Row 470 | Requested to be cancelled | Rafael A Quesada Alfaro | 05/14/25 10:17 AM
Row 479 | Waiting for @Sadarangani, Aarti, who is working on providing a walkthrough to Sunil today, post that we will mark it ready for PMO. | Rafael A Quesada Alfaro | 04/28/25 12:11 PM
Row 481 | RICEFW OTCC0652 | Atir Rajput | 04/23/25 6:16 AM
Row 486 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 492 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 1:03 PM
Row 493 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 1:03 PM
Row 494 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 1:03 PM
Row 501 | • INT-CR0599: Intel Federal Timekeeping – Will need to go to CR Meeting | Rafael A Quesada Alfaro | 05/07/25 7:40 AM
Row 503 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 12:57 PM
Row 503 | 05/06: Waiting for final confirmation that these views/reports can be descope without future risks since are unconsolidated reports. | Rafael A Quesada Alfaro | 05/06/25 12:22 PM
Row 506 | Requested to be cancelled | Rafael A Quesada Alfaro | 05/14/25 10:18 AM
Row 508 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 508 | Team has been request the GPO approval | Rafael A Quesada Alfaro | 05/07/25 7:48 AM
Row 509 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 509 | Team has been requested the GPO approval | Rafael A Quesada Alfaro | 05/07/25 7:49 AM
Row 517 | @rafael.a.quesada.alfaro@intel.com Hey Rafael, I looked through the deck, and it seems like it will be logic change. Will it only be functional work with no technical work involved? | Anna Tam | 05/08/25 1:35 PM
| Should be only Functional side, since will be the changes in signavio, however, i asked the CR owner to confirm | Rafael A Quesada Alfaro | 05/08/25 1:40 PM
Row 517 | Good afternoon @anntam@deloitte.com this CR has been reviewed in the FPR DSU and GPO approved to proceed. | Rafael A Quesada Alfaro | 05/08/25 1:15 PM
Row 517 | Cr has been moved back to not ready until GPO sign off been added by the team as discussed by chat, please check attached file. | Rafael A Quesada Alfaro | 05/07/25 7:39 AM
Row 517 | Shane's approval is missing, I advised Murali than approval is required prior to sent this to Change record review call with PMO. | Rafael A Quesada Alfaro | 05/07/25 7:37 AM
Row 518 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 12:57 PM
Row 518 | 05/06: Waiting for final confirmation that these views/reports can be descope without future risks since are unconsolidated reports. | Rafael A Quesada Alfaro | 05/06/25 12:22 PM
Row 519 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 12:57 PM
Row 519 | 05/06: Waiting for final confirmation that these views/reports can be descope without future risks since are unconsolidated reports. | Rafael A Quesada Alfaro | 05/06/25 12:22 PM
Row 527 | Hi Anna, the attached deck is added also under request review Deck column. | Rafael A Quesada Alfaro | 05/08/25 1:39 PM
Row 527 | @rafael.a.quesada.alfaro@intel.com Can you please help to tag the deck? | Anna Tam | 05/08/25 1:35 PM
Row 527 | Good afternoon @anntam@deloitte.com this CR has been reviewed in the FPR DSU and approved to proceed. | Rafael A Quesada Alfaro | 05/08/25 12:50 PM
Row 527 | To be presented in the DSU on 05/08 | Rafael A Quesada Alfaro | 05/07/25 11:48 AM
Row 530 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 530 | Team has been submitted the GPO approval | Rafael A Quesada Alfaro | 05/07/25 7:48 AM
Row 540 | @neetux.ramireddi@intel.com ; @junior.milan@intel.com Neetu, please provide the effort information | Imme Sandweg | 05/06/25 8:55 AM
Row 541 | @debradas@deloitte.com ; @junior.milan@intel.com Deb, please provide effort information | Imme Sandweg | 05/06/25 9:00 AM
| Tech= 10 Hours. Functional: 8 Hours | Debranjan Das | 05/06/25 9:11 AM
Row 545 | Requested to be cancelled | Rafael A Quesada Alfaro | 05/14/25 10:18 AM
Row 545 | email sent to Shane for Object cancellation request. | Rafael A Quesada Alfaro | 05/08/25 8:00 AM
Row 546 | Intel approval in progress, may be tied to design changes. | Leah Orzechowski | 10/03/25 12:18 PM
Row 550 | Item has been approved by GPO: Angela. | Rafael A Quesada Alfaro | 05/13/25 12:42 PM
Row 550 | Requested to be presented on Monday 12 instead. | Rafael A Quesada Alfaro | 05/08/25 12:28 PM
Row 550 | To be presented in DSU on 5/8/25 by Suresh and Ricardo | Rafael A Quesada Alfaro | 05/07/25 11:33 AM
Row 552 | Approved by GPO, email attached and saved into SP | Rafael A Quesada Alfaro | 05/08/25 12:53 PM
Row 553 | @rafael.a.quesada.alfaro@intel.com Hey Rafa, I saw that CR0652 is a duplicate of CR0710. So, I am cancelling CR0652 and taking CR0710 to Uzma. | Anna Tam | 05/21/25 1:38 PM
| Hi Anna, Yesterday Hari and myself detected the same scenario, but decided to keep the 0652 since that one have the GPO approval, and at the same time we removed the entry for 0710, since 0652 is rejected can we bring back from the trashcan this other entry that removed or revert the rejection of 0652 and have it that approved instead of 0710? | Rafael A Quesada Alfaro | 05/22/25 7:39 AM
Row 553 | Approved offline by Joey. | Rafael A Quesada Alfaro | 05/19/25 12:59 PM
Row 553 | Team needs more time to figure it out for this object. | Rafael A Quesada Alfaro | 05/16/25 10:59 AM
Row 553 | @hgore@deloitte.com please work with the process steward to know if this CR still needed or not, if yes, them please follow the new process shared with you via email. | Rafael A Quesada Alfaro | 05/13/25 1:56 PM
Row 553 | Request the team to initiate the approval process | Rafael A Quesada Alfaro | 05/08/25 1:07 PM
Row 559 | GPo approve | Rafael A Quesada Alfaro | 05/13/25 8:02 AM
Row 560 | GPO | Rafael A Quesada Alfaro | 05/13/25 8:03 AM
Row 561 | GPO Sign only | Rafael A Quesada Alfaro | 05/13/25 8:03 AM
Row 585 | Good Afternoon @anntam@deloitte.com , We have this CR that is ready to be collected for the next available session of CRs review | Rafael A Quesada Alfaro | 06/26/25 1:20 PM
Row 585 | Reviewed in the DSU, we need the hours added to be fully ready for CR CBB review. asked to complete and we will check tomorrow (06/25) | Rafael A Quesada Alfaro | 06/24/25 12:47 PM
Row 589 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 590 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 591 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 592 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 593 | Approved by GPO | Rafael A Quesada Alfaro | 05/14/25 12:37 PM
Row 600 | Good afternoon @anntam@deloitte.com This CR is now ready to be collected for CBB agenda. | Rafael A Quesada Alfaro | 05/22/25 2:55 PM
Row 601 | This CR needs to be Cancelled. NRT equivalent report will be in scope and priority will be R5, instead of R3. | Rafael A Quesada Alfaro | 06/02/25 12:23 PM
Row 601 | Approved, email has been stored as requested. but CR has been reverted to not ready as requested by It lead. | Rafael A Quesada Alfaro | 05/16/25 12:50 PM
Row 602 | This CR needs to be Cancelled. NRT equivalent report will be in scope and priority will be R5, instead of R3. | Rafael A Quesada Alfaro | 06/02/25 12:23 PM
Row 602 | Approved, email has been stored as requested. but CR has been reverted to not ready as requested by It lead. | Rafael A Quesada Alfaro | 05/16/25 12:50 PM
Row 603 | This CR needs to be Cancelled. NRT equivalent report will be in scope and priority will be R5, instead of R3. | Rafael A Quesada Alfaro | 06/02/25 12:23 PM
Row 603 | Approved, email has been stored as requested. but CR has been reverted to not ready as requested by It lead. | Rafael A Quesada Alfaro | 05/16/25 12:50 PM
Row 604 | This CR needs to be Cancelled. NRT equivalent report will be in scope and priority will be R5, instead of R3. | Rafael A Quesada Alfaro | 06/02/25 12:23 PM
Row 604 | Approved, email has been stored as requested. but CR has been reverted to not ready as requested by It lead. | Rafael A Quesada Alfaro | 05/16/25 12:50 PM
Row 605 | This CR needs to be Cancelled. NRT equivalent report will be in scope and priority will be R5, instead of R3. | Rafael A Quesada Alfaro | 06/02/25 12:23 PM
Row 605 | Approved, email has been stored as requested. but CR has been reverted to not ready as requested by It lead. | Rafael A Quesada Alfaro | 05/16/25 12:50 PM
Row 606 | Change record is ready to be reviewed on Tuesday 27th. Anna already informed and we will be added into the agenda. | Rafael A Quesada Alfaro | 05/23/25 10:34 AM
Row 621 | Hi anna this CR 0723 has been approved by GPO to be cancelled, changing the status to ready to be collected in next meeting | Rafael A Quesada Alfaro | 05/22/25 10:34 AM
Row 629 | Hi @anntam@deloitte.com this CR is ready to be collected, approval has been attached (saved in SP) | Rafael A Quesada Alfaro | 06/02/25 12:49 PM
Row 629 | To be reviewed on 5/30 with GPO. offline email sent to ask for approval. | Rafael A Quesada Alfaro | 05/29/25 12:38 PM
Row 642 | GM @anntam@deloitte.com, This CR is ready to be collected, Shane's approval attached. | Rafael A Quesada Alfaro | 06/02/25 12:29 PM
Row 642 | To be reviewed on 5/30 with GPO. offline email sent to ask for approval. | Rafael A Quesada Alfaro | 05/29/25 12:38 PM
Row 646 | nitin.patil@intel.com | Abhay Tibrewal | 05/30/25 12:39 AM
Row 663 | Hi @anntam@deloitte.com , this CR is ready to be collected for an object descoping process. approval has been added in the corresponding SP folder. | Rafael A Quesada Alfaro | 06/10/25 10:06 AM
Row 663 | Email sent to Cr requestor to fill out the necessary template for CR. | Rafael A Quesada Alfaro | 06/09/25 1:30 PM
Row 665 | @vinayprabhu@deloitte.com, @ravishwanathan@deloitte.com, @celancheran@deloitte.com. This CR was approved in June 2025. Please update this line item. | Teresa Mcnicol | 10/21/25 12:27 PM
Row 667 | cancelled. DT is working to cancel in the tracker | Olga Moskaleva-Hughes | 11/02/25 1:18 PM
Row 685 | @GM Anna, We have this CR that is ready to be collected for the next available session of CRs review. According with Prabesh this is only functional effort of 40 hour to change documents in signavio and PAPM. | Rafael A Quesada Alfaro | 06/18/25 12:33 PM
Row 686 | @anntam@deloitte.com the CR still appearing as new instead of approved. Could you pls check one more time? | Rafael A Quesada Alfaro | 10/15/25 3:25 PM
Row 686 | Hi @anntam@deloitte.com This CR has been corrected and is ready for review., | Rafael A Quesada Alfaro | 10/02/25 1:24 PM
Row 686 | @rafael.a.quesada.alfaro@intel.com I am putting this CR back to "No" because we need the dates of when the changes to the FS, development, and FUT will be ready | Anna Tam | 09/24/25 2:54 PM
| I have confirmed with Kritarth that the report development should be completed by S20 (12/5/2025) and FUT will be ready the last week of December. Please let us know if there is anything else needed to move forward with the CR. | Rose Pham | 09/26/25 2:11 PM
| Hi Rose, Please follow this guide to validate all the mandatory data has been entered in the power point, we will not get the CR approved by PMO without this completed. https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/_layouts/15/Doc.aspx?sourcedoc=%7B7B1C7FAC-3807-405D-A58D-28AB1CF90CB2%7D&file=Obj%20Descoping%20process%20vs%20ERP%20Changes.pptx&wdLOR=c8B2CB7C2-45BF-4D98-A440-446333276C7E&action=edit&mobileredirect=true | Rafael A Quesada Alfaro | 09/26/25 3:47 PM
| Hi Rafa - I have added the Build object effort details with specific dates. Please let me know if it's sufficient. | Rose Pham | 09/26/25 3:54 PM
| Thanks Rose, case sent to PMO core team for review and to be added into their CBB CR review process. | Rafael A Quesada Alfaro | 09/29/25 10:31 AM
Row 686 | Shane Verbally approve the CR, waiting CBB addition | Rafael A Quesada Alfaro | 09/23/25 2:37 PM
Row 686 | Email sent to ask for an update about this case. | Rafael A Quesada Alfaro | 08/20/25 10:45 AM
Row 692 | Hi @anntam@deloitte.com, Can you help us to reject this CR, after few deeper discussions with DLT team we decided to don't ask to bring back the cancelled ECA views mentioned in this CR. | Rafael A Quesada Alfaro | 06/18/25 12:35 PM
Row 692 | CR must be rejected since has been decided on 06/18 that is no longer needed to bring back all the cancelled objects requested in the disposition. | Rafael A Quesada Alfaro | 06/18/25 12:24 PM
Row 694 | Hi @anntam@deloitte.com, This CR is ready to be collected for CBB review. | Rafael A Quesada Alfaro | 06/16/25 12:15 PM
Row 700 | @siddesai@deloitte.com @vaibgupta@deloitte.com | Vaibhav G Gupta | 06/11/25 6:16 AM
Row 709 | RICEFW object approved by LOG GPO. DT team to update in the tracker as approved | Olga Moskaleva-Hughes | 11/02/25 1:27 PM
Row 715 | Hi @anntam@deloitte.com, Please note that this Cancellation CR is ready to be collected. pls help us to process it. | Rafael A Quesada Alfaro | 06/26/25 8:05 AM
Row 715 | Hi @anntam@deloitte.com, Please note that this Cancellation CR is ready to be collected. pls help us to process it. | Rafael A Quesada Alfaro | 06/13/25 7:30 AM
Row 718 | GM @anntam@deloitte.com , we need your help to reject this CR too, Christine Spoke with the Deloitte analytics team and we do not want to restate the Fixed Asset objects we will add them to the intel ECA Smartsheet | Rafael A Quesada Alfaro | 06/23/25 9:41 AM
Row 718 | Waiting Anna response about how to proceed with this request. | Rafael A Quesada Alfaro | 06/18/25 12:49 PM
Row 721 | @sjulury@deloitte.com , @ravishwanathan@deloitte.com . This CR was approved in July by OSC. Please update the line item | Teresa Mcnicol | 10/21/25 12:30 PM
Row 743 | @sshettyk@deloitte.com - this CR has been cancelled due to alternative solution. Please update in the tracker ASAP | Olga Moskaleva-Hughes | 10/22/25 1:08 PM
Row 744 | this CR was approved. @pramodx.kalli.srinivas@intel.com update in the tracker | Olga Moskaleva-Hughes | 11/02/25 1:29 PM
Row 753 | GM @anntam@deloitte.com , We have this CR that is ready to be collected for the next available session of CRs review. | Rafael A Quesada Alfaro | 07/23/25 9:51 AM
Row 753 | CR has been approved by GPO and it is ready for CBB. | Rafael A Quesada Alfaro | 07/23/25 9:50 AM
Row 753 | Chandra confirmed that CR has been already reviewed and approved by Shane and Prabesh during Treasury leadership call. | Rafael A Quesada Alfaro | 07/17/25 11:22 AM
Row 762 | GM @anntam@deloitte.com , We have this CR that is ready to be collected for the next available session of CRs review. | Rafael A Quesada Alfaro | 07/07/25 12:29 PM
Row 762 | To be reviewed on July 7th during the Leadership DSU to get GPO approval before going to PMO | Rafael A Quesada Alfaro | 06/30/25 9:32 AM
Row 777 | S4 Tech efforts spent for IOR, HLTA | Jeson Noronha | 08/14/25 10:02 PM
Row 789 | @rafael.a.quesada.alfaro@intel.com @pramokulkarni@deloitte.com I am flipping this back to "No" because it is missing dates on when the changes to the FS, development, and FUT will be completed. | Anna Tam | 09/24/25 2:52 PM
| Hi @annax.tam@intel.com , This is the design CR to analyze requirements and impact and risk, I asked Pramod to help to rephrase the CR to avoid this confusion. waiting him to execute the correction in the PPT. | Rafael A Quesada Alfaro | 09/24/25 3:24 PM
Row 789 | Cr waiting to be taken by PMO team and added into the CBB agenda. Hi @anntam@deloitte.com, case has been reviewed; and Pramod is finalizing the PPT so can be added into the next available session for CBB review. | Rafael A Quesada Alfaro | 09/22/25 1:28 PM
Row 789 | Pramod said: Case reviewed last week and agreed with Shane to be presented in the CBB call. | Rafael A Quesada Alfaro | 09/22/25 1:26 PM
Row 789 | waiting Pramod to align and ask to reject this CR. | Rafael A Quesada Alfaro | 08/20/25 10:44 AM
Row 789 | This is a Design Change Request (CR). I will first align and discuss internally with Mani and Prabesh. Once this is complete, we will proceed to create the Build CR. No action is required at this time. | Rafael A Quesada Alfaro | 08/20/25 10:44 AM
Row 797 | Hi @anntam@deloitte.com, Please note that this Cancellation CR is ready to be collected. pls help us to process it. | Rafael A Quesada Alfaro | 07/15/25 2:24 PM
Row 797 | Waiting Doug to send the email template for descoping Items. | Rafael A Quesada Alfaro | 07/15/25 7:56 AM
Row 806 | CR scheduled for 08/21 | Rafael A Quesada Alfaro | 08/21/25 9:21 AM
Row 806 | CR approved by Prabesh during the DSU on 07/17. Shane will be requested to sign off prior be sent to CBB. | Rafael A Quesada Alfaro | 07/17/25 12:32 PM
Row 813 | 10/30 : CR #INT-CR0940 is duplicate of #INT-CR1078. Hence CR #INT-CR0940 can be cancelled. #INT-CR1078 is already approved. | Vaibhav Pravin Chaudhari | 10/30/25 4:23 AM
Row 817 | CR tagged for be cancelled, no longer needed. Email sent to PMO to request dropping this item. | Rafael A Quesada Alfaro | 09/22/25 2:46 PM
Row 821 | @rafael.a.quesada.alfaro@intel.com This CR is still showing as to be delivered by ITC1. Did the tech team confirm this? They have told me that they do not have capacity for ITC1 | Anna Tam | 11/05/25 11:53 AM
| Hi Anna, This CR was aligned with Tech team by @sharikrishnan@deloitte.com, when i asked that question the response was that Dev team commit with the dates added into the CR. | Rafael A Quesada Alfaro | 11/05/25 11:59 AM
Row 821 | Hi @anntam@deloitte.com , This CR is ready for PMO review. | Rafael A Quesada Alfaro | 10/28/25 9:04 AM
Row 821 | Deck still incomplete, waiting completion | Rafael A Quesada Alfaro | 10/23/25 12:35 PM
| Deck has been completed, and is ready for PMO | Rafael A Quesada Alfaro | 10/28/25 9:04 AM
Row 821 | Hi @prashachauhan@deloitte.com @sharikrishnan@deloitte.com Pls check this case that been in draft and work to have it completed to be presented into the leadership to be submitted | Rafael A Quesada Alfaro | 10/15/25 3:39 PM
Row 821 | Cr has been presented to the Leadership, few corrections are needed, CR will not be sent for PMO approval until address this ARs | Rafael A Quesada Alfaro | 07/28/25 12:39 PM
Row 827 | @shadhir@deloitte.ca , @ravishwanathan@deloitte.com . This CR was approved by OSC already, please update line item accordinly | Teresa Mcnicol | 10/22/25 9:39 AM
Row 829 | Good afternoon @anntam@deloitte.com , We have this R1 CR that is ready to be defended. | Rafael A Quesada Alfaro | 07/31/25 1:00 PM
Row 829 | Case not ready yet. under review. not ETA | Rafael A Quesada Alfaro | 07/24/25 10:37 AM
Row 830 | Good afternoon, @anntam@deloitte.com , this descoping Change is ready for be collected. | Rafael A Quesada Alfaro | 08/19/25 1:32 PM
Row 830 | A follow up email has been sent to GPO for approval prior CR submission. | Rafael A Quesada Alfaro | 08/19/25 9:07 AM
Row 836 | Object Cancellation has been approved by GPO of Team 7. | Rafael A Quesada Alfaro | 10/13/25 11:46 AM
Row 836 | CR created but not presented yet to GPO for approval | Rafael A Quesada Alfaro | 09/18/25 7:55 AM
Row 837 | Good afternoon @anntam@deloitte.com , We have this CR that is ready to be collected for the next available session of CRs review. | Rafael A Quesada Alfaro | 07/24/25 1:09 PM
Row 849 | This has been approved to go to Ingestion call on WW30.3 during FPR Leadership call. | Rafael A Quesada Alfaro | 07/23/25 11:55 AM
Row 855 | Good afternoon @anntam@deloitte.com , We have this CR that is ready to be collected for the next available session of CRs review. | Rafael A Quesada Alfaro | 07/24/25 1:10 PM
Row 859 | Hi @anntam@deloitte.com, Please note that this Cancellation CR is ready to be collected. pls help us to process it. | Rafael A Quesada Alfaro | 08/07/25 12:20 PM
Row 877 | Approved, waiting to be changed in SS | Rafael A Quesada Alfaro | 08/20/25 10:15 AM
Row 895 | this CR was closed/rejected by GPO in August. @celancheran@deloitte.com - are you able to update tracker? | Olga Moskaleva-Hughes | 10/27/25 1:16 PM
Row 898 | Email: https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/10.%20Analytics/00%20Admin/1%20Meeting%20Minutes%20and%20Recordings/PTP/Approvals/_EXT_%20RE_%20_APPROVAL%20REQUESTED_%20-%2012%20WIINGS%20Reports%20-%20CR_1030.msg?csf=1&web=1&e=T9FZPg | Sheila Nguyen | 10/06/25 2:37 PM
Row 900 | This CR is merged with INT-CR1090. This can be canceled. | Venkat Venkatesh | 10/08/25 4:54 AM
Row 908 | Hello PMO, we need to cancel this CR as we have now an approved business process | Lilibeth Lejarde | 03/11/26 8:44 AM
Row 911 | Build CR 688 is created for the same because the effort is less than 40 hours. Build CR 688 is approved. Hence canceling CR 1046 in this tracker. | Surendra Julury | 10/10/25 8:25 AM
Row 915 | Raised an Internal CR # INT-Build-CR0717. this CR will be not applicable. | Lakshmi Narasimha Reddy Nagireddy | 08/28/25 2:27 AM
Row 920 | CBB passed on 08/14, Will need to go to CR Meeting. waiting to be scheduled to this other meeting. | Rafael A Quesada Alfaro | 08/21/25 9:21 AM
Row 924 | Hi @annax.tam@intel.com @anntam@deloitte.com this CR is ready to be collected since object has been approved for cancellation. | Rafael A Quesada Alfaro | 01/09/26 11:08 AM
Row 924 | Follow up with GPO in progress. | Rafael A Quesada Alfaro | 08/19/25 9:15 AM
Row 932 | Hi @annax.tam@intel.com , We have this urgent Sap Security role needed for R2 MEC, could you help us to expedite the approval? | Rafael A Quesada Alfaro | 08/14/25 10:46 AM
Row 965 | Changed the scope to design change. | Vijay Sharma | 08/28/25 9:23 AM
Row 973 | @rafael.a.quesada.alfaro@intel.com I cancelled CR0983 recently because Hari Gore confirmed that it is no longer required. However, in this CR1111, the description said that CR0983 was to create a new object to replace FPRR1492. Can you please help to confirm whether descoping FPRR1492 is still required because the replacement object was cancelled? I just wanted to make sure before I go to Uzma | Anna Tam | 09/24/25 2:56 PM
| I'm asking Hari about this discrepancy and request confusion. | Rafael A Quesada Alfaro | 09/24/25 3:04 PM
| Hi @anntam@deloitte.com , Hari confirmation attached, CR number in the rationale has been updated as well. HI Rafa, Instead of CR 983 we used CR 1009 for COGS split and this 1009 is approved, hence Cancellation of CR 1111 is valid. Only Rational of CR 1111 need to be updated as “New CR 1009” instead of “New CR 983”. Regards, Hari Gore | Rafael A Quesada Alfaro | 09/25/25 2:46 PM
Row 973 | GM @anntam@deloitte.com this Request for an object cancellation is ready to be collected | Rafael A Quesada Alfaro | 09/17/25 8:31 AM
Row 991 | @mshabaz@deloitte.com Reverting back to "No" as it is not ready for pmo review. It is missing information on whether the changes will be completed by ITC1 or not | Anna Tam | 09/24/25 2:49 PM
Row 992 | @mshabaz@deloitte.com Reverting back to "No" as it is not ready for pmo review. It is missing information on whether the changes will be completed by ITC1 or not | Anna Tam | 09/24/25 2:48 PM
Row 993 | @mshabaz@deloitte.com Reverting back to "No" as it is not ready for pmo review. It is missing information on whether the changes will be completed by ITC1 or not | Anna Tam | 09/24/25 2:48 PM
Row 994 | @mshabaz@deloitte.com Reverting back to "No" as it is not ready for pmo review. It is missing information on whether the changes will be completed by ITC1 or not | Anna Tam | 09/24/25 2:48 PM
Row 996 | CR entry is no longer needed since is a duplication of 1136. Email sent to PO to request the entry cancellation in smartsheet. | Rafael A Quesada Alfaro | 09/22/25 2:48 PM
Row 1010 | Hi @anntam@deloitte.com This CR is ready for review., | Rafael A Quesada Alfaro | 10/02/25 1:24 PM
Row 1013 | @mshabaz@deloitte.com Marking this CR as not ready because it is missing a deck | Anna Tam | 09/24/25 2:46 PM
Row 1021 | Hi @anntam@deloitte.com, could you help us to change the status of this to approve? It been presented last Thursday but the status didn't change. | Rafael A Quesada Alfaro | 10/23/25 10:12 AM
Row 1021 | @rafael.a.quesada.alfaro@intel.com Tech team said that they will not be able to complete this enhancement by ITC2. Therefore, before we bring this CR into the Ingestion, we need the deck to be updated with any workarounds that we can use for ITC1 testing. | Anna Tam | 10/01/25 3:30 PM
| Hi @anntam@deloitte.com Deck has been updated to reflect the available WorkArounds for this while been completed during ITC1 testing. I will change the status back to ready for PMO review. | Rafael A Quesada Alfaro | 10/03/25 1:54 PM
| @rafael.a.quesada.alfaro@intel.com @anntam@deloitte.com - Kindly confirm the CR approval status? CC: @kdey@deloitte.com @navnegi@deloitte.com | Naveen Negi | 10/13/25 1:04 PM
Row 1021 | Hi @anntam@deloitte.com This Case has been approved to go to CBB review. | Rafael A Quesada Alfaro | 09/25/25 2:40 PM
Row 1021 | CR been reviewed on the DSU today. | Rafael A Quesada Alfaro | 09/25/25 12:42 PM
Row 1028 | Hey Rafael, I am changing it back to not ready as we need the a CR slide to be filled out. Also, we need to get confirmation from the tech team whether the new RICEFW can be tested in ITC1 or not | Anna Tam | 09/24/25 2:44 PM
| Hi Anna, This has been corrected by the team and deloitte said that can start working on this as soon as be approved, we need to split one RIcefw into two. | Rafael A Quesada Alfaro | 10/15/25 3:16 PM
Row 1028 | CR presented and approved by GPO to split a ricefw. | Rafael A Quesada Alfaro | 09/22/25 2:56 PM
Row 1033 | @jhoover@deloitte.com Please update the effort section and add in an estimated / actual date to the schedule section. | Brie Thigpen | 02/11/26 9:12 AM
Row 1066 | hi @anntam@deloitte.com new dates added by Pramod, based on Vasanth information. | Rafael A Quesada Alfaro | 10/16/25 11:55 AM
Row 1066 | Hi @anntam@deloitte.com This CR has been reviewed and is ready to be collected for CBB Review. | Rafael A Quesada Alfaro | 10/02/25 12:44 PM
Row 1111 | @annax.tam@intel.com - can you please update to approved. this CR was approved by GPO and low tech hours, ITC1 so does not need to go to ingestion. | Olga Moskaleva-Hughes | 11/24/25 8:11 PM
Row 1111 | Approved by OTC IP GPO. does not need to go to Ingestion | Olga Moskaleva-Hughes | 11/24/25 3:17 PM
Row 1113 | This item is duplicated with CR1478 | Rafael A Quesada Alfaro | 11/13/25 12:41 PM
Row 1123 | Hi @anntam@deloitte.com pending Items completed. Chandra will reserve few mins with you to validate that all his pending actions being already addressed | Rafael A Quesada Alfaro | 10/22/25 11:41 AM
Row 1123 | Hi @anntam@deloitte.com pending Items completed. | Rafael A Quesada Alfaro | 10/16/25 11:54 AM
Row 1123 | @chgorantla@deloitte.com This CR is not Ready, Deck is not completed and be rejected by PMO, pls follow the guide that i shared multiple times and be sure that all fields are filled in before submit the CR to avoid delays on this apprvoal process. | Rafael A Quesada Alfaro | 10/13/25 1:11 PM
| Please take into consideration that last day to submit a Design CR will be 10/17 after that date will have additional process or could even be rejected by PMO team. | Rafael A Quesada Alfaro | 10/15/25 3:42 PM
Row 1143 | was approved in ingestion meeting. Needs to be closed on the tracker @debradas@deloitte.com please help to update | Olga Moskaleva-Hughes | 11/02/25 1:38 PM
Row 1146 | Hi @anntam@deloitte.com this CR is ready for CBB meeting | Rafael A Quesada Alfaro | 10/15/25 5:09 PM
Row 1146 | Waiting some checks ijn the effort before being sent to PMO queue for revision. | Rafael A Quesada Alfaro | 10/14/25 1:16 PM
| Corrections in place, Waiting GPO sign off | Rafael A Quesada Alfaro | 10/15/25 3:34 PM
Row 1159 | @anntam@deloitte.com This CR is ready for be taking into the ingestion call | Rafael A Quesada Alfaro | 10/10/25 3:04 PM
Row 1160 | @dikotha@deloitte.com Flipping back to "No" in "Ready for PMO Review" because it is still missing PDH tech estimate | Anna Tam | 11/05/25 11:55 AM
Row 1169 | Hi @anntam@deloitte.com this CR is ready for CR ingestion meeting | Rafael A Quesada Alfaro | 10/15/25 5:10 PM
Row 1169 | Correction complete, sending this via email to GPO for approval. | Rafael A Quesada Alfaro | 10/15/25 9:16 AM
Row 1169 | Waiting some corrections before be sent to PMO queue for revision. | Rafael A Quesada Alfaro | 10/14/25 12:42 PM
Row 1174 | Good morning @annax.tam@intel.com @anntam@deloitte.com this CR has been reviewed with Prabesh and approved by Shane to go to CBB, so this is not a request for new RICEFW but for more time to work on R5. | Rafael A Quesada Alfaro | 10/22/25 12:06 PM
Row 1191 | To be deleted, Build CR created. | Rafael A Quesada Alfaro | 10/17/25 9:48 AM
Row 1192 | To be deleted, Build CR created. | Rafael A Quesada Alfaro | 10/17/25 9:49 AM
Row 1193 | To be deleted, Build CR created. | Rafael A Quesada Alfaro | 10/17/25 9:49 AM
Row 1194 | To be deleted, Build CR created. | Rafael A Quesada Alfaro | 10/17/25 9:49 AM
Row 1205 | approved in Ingestion meeting. @adityax.shinde@intel.com help update in the tracker | Olga Moskaleva-Hughes | 11/02/25 1:41 PM
Row 1214 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed. | Rafael A Quesada Alfaro | 10/23/25 9:39 AM
Row 1227 | This request needs to be cancelled, it has been consolidated with INT-CR1404 | Imme Sandweg | 10/28/25 10:07 AM
Row 1231 | comeback after Chad check all the information and need to go back to ingestion call. | Rafael A Quesada Alfaro | 10/31/25 8:38 AM
Row 1232 | @rafael.a.quesada.alfaro@intel.com Will this be ready for tomorrow's CR ingestion? | Anna Tam | 11/12/25 5:09 AM
| Hi Anna, Milind is handling this Change offline in the email thread with Alpna and Uzma where we been added. so this cannot need to be added in the agenda, they are working it via email and he requested more time to provide to them the pending information. | Rafael A Quesada Alfaro | 11/12/25 8:57 AM
Row 1232 | comeback after Chad check all the information and need to go back to ingestion call. | Rafael A Quesada Alfaro | 10/31/25 8:38 AM
Row 1234 | comeback after Chad check all the information and need to go back to ingestion call. | Rafael A Quesada Alfaro | 10/31/25 8:38 AM
Row 1238 | has been approved in Ingestion meeting 10/30. tracker needs to be updated | Olga Moskaleva-Hughes | 11/02/25 1:43 PM
Row 1242 | @pkallisrinivas@deloitte.com Reverted back to "No" in "Ready for PMO review" as the tech effort is still pending | Anna Tam | 11/05/25 11:48 AM
Row 1251 | Approved in core meeting, waiting for status change | Rafael A Quesada Alfaro | 11/04/25 9:29 AM
Row 1251 | Need approval from core leadership, Analysis done by ECA team members and finally Dates. | Rafael A Quesada Alfaro | 10/31/25 8:31 AM
Row 1258 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed. | Rafael A Quesada Alfaro | 11/06/25 7:24 AM
Row 1258 | Harikrishnan, Shiva Shankar (External) 9:22 AM INT-CR1439 IHC Open Items clearing 2. New RICEFW / ECA / Build This was cancelled | Rafael A Quesada Alfaro | 11/06/25 7:23 AM
Row 1258 | This CR is not ready. | Rafael A Quesada Alfaro | 10/30/25 1:48 PM
Row 1270 | Approved in core meeting, waiting for status change | Rafael A Quesada Alfaro | 11/04/25 9:28 AM
Row 1270 | On 10/31: the CR was not approved; they asked Joey to add the CR details as open Desing line under this: https://app.smartsheet.com/sheets/PXWcc756Wgg2fQ3v4wcgRCm4vJ5R7fFhHf9QH6W1?view=grid It will work and added there and as soon as design be completed and dates provided, it will be approved even after the due date of Oct 31. | Rafael A Quesada Alfaro | 10/31/25 8:29 AM
Row 1271 | approved in ingestion meeting 10/30 | Olga Moskaleva-Hughes | 11/02/25 1:51 PM
Row 1271 | has been approved in ingestion meeting 10/30. tracker needs to be updated | Olga Moskaleva-Hughes | 11/02/25 12:18 PM
Row 1272 | per Trade team CR is cancelled. DT please update tracker | Olga Moskaleva-Hughes | 11/25/25 10:28 AM
Row 1281 | @annax.tam@intel.com can you please help to update tracker. this CR has been approved by OTC IP GPO and does not need to go to Ingestion | Olga Moskaleva-Hughes | 11/24/25 8:26 PM
Row 1281 | approved by OTC IP GPO. does not need to go to Ingestion. ITC1, low tech hours. | Olga Moskaleva-Hughes | 11/07/25 9:20 AM
Row 1282 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed. | Rafael A Quesada Alfaro | 11/07/25 11:08 AM
Row 1286 | waiting on email approval to be sent to Uzma | Olga Moskaleva-Hughes | 11/17/25 1:36 PM
Row 1290 | Hi @anntam@deloitte.com This Cancellation is ready to be taken. | Rafael A Quesada Alfaro | 11/13/25 12:40 PM
Row 1292 | has been approved in ingestion. please update | Olga Moskaleva-Hughes | 11/14/25 3:32 PM
Row 1293 | Hi Anna, This request for Cancellation is ready to be collected. | Rafael A Quesada Alfaro | 11/06/25 3:28 PM
Row 1303 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed. | Rafael A Quesada Alfaro | 11/07/25 11:09 AM
Row 1304 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed since was duplicated with a CR under FS build CR page. | Rafael A Quesada Alfaro | 11/20/25 9:41 AM
Row 1305 | approved in Ingestion. please update statuce | Olga Moskaleva-Hughes | 11/14/25 3:31 PM
Row 1306 | CR is cancelled and no longer needed. DT to cancel in tracker. | Olga Moskaleva-Hughes | 11/17/25 2:27 PM
Row 1315 | has been approved in ingestion meeting. please update the statuce | Olga Moskaleva-Hughes | 11/14/25 3:30 PM
Row 1316 | @annax.tam@intel.com - this CR has been approved by OTC IP GPO. because of low tech hours and it is ITC1, it does not need to go to ingestion. Please switch to approved. | Olga Moskaleva-Hughes | 12/12/25 2:22 PM
Row 1322 | CR INT-BUILD-608, duplicate for Program Change Log. | Olga Moskaleva-Hughes | 11/24/25 2:55 PM
Row 1335 | This CR has been cancelled. Confirmed by Ryan Rych on Dec 10 2025. | Imme Sandweg | 12/11/25 8:53 AM
Row 1336 | Hi @annax.tam@intel.com @anntam@deloitte.com , We have this defect for R2, can we add it to be presented and approved? | Rafael A Quesada Alfaro | 12/02/25 12:23 PM
| attached is Shane's approval. | Rafael A Quesada Alfaro | 12/02/25 12:23 PM
Row 1345 | Hi @anntam@deloitte.com, this Cancellation request has been approved by GPO and is ready to be collected | Rafael A Quesada Alfaro | 12/02/25 1:15 PM
Row 1347 | @suggupta@deloitte.com Please update the effort with estimated hours and schedule with estimated/actual date, and include the name of approver for Testing and Technology | Brie Thigpen | 01/27/26 12:52 PM
| @briex.arie.thigpen@intel.com As per latest alignment with business, this change is not required. We requested @anntam@deloitte.com to mark this CR cancel. | Sugandh Gupta | 02/02/26 4:10 AM
Row 1366 | Approved to go to CBB meeting | Rafael A Quesada Alfaro | 12/09/25 11:48 AM
Row 1368 | not approved by GPO. rejected, needs to be cancelled. Put on CIP list. @pramodx.kalli.srinivas@intel.com - please cancel in the tracker. | Olga Moskaleva-Hughes | 12/15/25 9:37 PM
Row 1373 | @rafael.a.quesada.alfaro@intel.com Hi Rafael, did you have any luck on getting the dates of when the changes will be completed? Just need the table filled out with the new dates | Anna Tam | 01/28/26 2:11 PM
| I sent an email to @maheshreddy@deloitte.com so he can follow up on the missing dates. | Rafael A Quesada Alfaro | 01/28/26 2:22 PM
Row 1373 | Hi @anntam@deloitte.com, This CR is ready to be collected for CBB call next Thursday. | Rafael A Quesada Alfaro | 12/08/25 1:16 PM
Row 1376 | Dear @anntam@deloitte.com could you please disregards this Change record; It's an CR no longer needed, as confirmed by Pramod, so we need to discard this CR from the ready list. | Rafael A Quesada Alfaro | 12/10/25 12:13 PM
Row 1390 | Prabesh confirmed that this will going to CBB on 01/08 instead of 01/15 | Rafael A Quesada Alfaro | 01/08/26 12:38 PM
Row 1394 | Hi @annax.tam@intel.com @anntam@deloitte.com this CR is ready to be collected since object has been approved for cancellation. | Rafael A Quesada Alfaro | 01/09/26 11:08 AM
Row 1403 | This CR must be cancel as duplication of CR1804 | Rafael A Quesada Alfaro | 03/19/26 12:43 PM
Row 1403 | Also, now that we are nearing the end of build, we will need the tech team to provide high-level dates of when the RICEFW will get completed | Anna Tam | 01/28/26 2:10 PM
| I sent an email to @maheshreddy@deloitte.com so he can follow up on the missing dates. | Rafael A Quesada Alfaro | 01/28/26 2:22 PM
Row 1403 | @rafael.a.quesada.alfaro@intel.com Hi Rafa, is FPRE0879 the new RICEWF that is needed? Or is a separate new RICEFW required? | Anna Tam | 01/28/26 2:09 PM
Row 1403 | On hold until Monday January 19 | Rafael A Quesada Alfaro | 01/15/26 1:59 PM
Row 1404 | @ssyal@deloitte.com Please update the schedule with an actual / estimated date and an explanation of what the manual workaround for ITC1 is. | Brie Thigpen | 02/11/26 9:18 AM
Row 1425 | Hi @anntam@deloitte.com, this CR for an object descoping is ready to be processed. | Rafael A Quesada Alfaro | 01/27/26 12:49 PM
Row 1426 | Hi @anntam@deloitte.com, this CR for an object descoping is ready to be processed. | Rafael A Quesada Alfaro | 01/27/26 12:51 PM
Row 1430 | Good morning @anntam@deloitte.com this CR for object descoping has been approved and is ready to be collected. | Rafael A Quesada Alfaro | 01/22/26 8:53 AM
Row 1440 | @shrideshpande@deloitte.ca @ravishwanathan@deloitte.com Please update schedule with estimated/actual date. | Brie Thigpen | 01/27/26 1:03 PM
Row 1441 | @iathar@deloitte.ca Please update effort and name of approver for Logistics & Warehouse | Brie Thigpen | 01/27/26 1:06 PM
Row 1449 | @murthykp@deloitte.com @rtol@deloitte.com Please update effort and schedule | Brie Thigpen | 01/27/26 1:08 PM
Row 1455 | @ssyal@deloitte.com Please update schedule with estimated/ actual date and fill in impact table | Brie Thigpen | 01/27/26 1:09 PM
Row 1456 | @bharathkumr@deloitte.com Please fill in schedule and include the name of the approver for Master data | Brie Thigpen | 01/27/26 1:10 PM
Row 1484 | Hi @anntam@deloitte.com, this Cancellation request has been approved by GPO | Rafael A Quesada Alfaro | 02/06/26 10:58 AM
Row 1503 | 02/24/26: During DSU we agreed to keep this CR open as placeholder for the rethink solution, while CR requester analyze with BODS team, this will be tag as Draft item not ready for review. | Rafael A Quesada Alfaro | 02/24/26 12:45 PM
Row 1526 | Dear @anntam@deloitte.com , This CR for an object cancelation is ready to be collected and presented to Uzma, could you please help us with this request? | Rafael A Quesada Alfaro | 02/27/26 7:22 AM
Row 1559 | Hi @annax.tam@intel.com, @anntam@deloitte.com This Cancellation request is ready for be processed. | Rafael A Quesada Alfaro | 03/03/26 10:36 AM
Row 1560 | Dear @anntam@deloitte.com This Cancellation request is ready. | Rafael A Quesada Alfaro | 03/03/26 7:44 AM
Row 1564 | 03.17: will be repurpose for a new scope, until then will be park as draft Change | Rafael A Quesada Alfaro | 03/17/26 1:43 PM
Row 1614 | according with Matt this is not ready yet. | Rafael A Quesada Alfaro | 03/19/26 8:08 AM
Row 1624 | This is cancelled | Nisha Kadakia | 04/01/26 4:26 PM
Row 1678 | not approved by GPO | Olga Moskaleva-Hughes | 04/06/26 11:32 AM
Row 1679 | not approved by GPO | Olga Moskaleva-Hughes | 04/06/26 11:30 AM
Sheet | @rafael.a.quesada.alfaro@intel.com We do need this CR. We are waiting for requirements finalization from Kathleen and Mark. | Suresh Avula | 10/15/25 7:41 PM
Sheet | . | Rafael A Quesada Alfaro | 04/22/25 11:57 AM