## S4 _R3_ Intel IDM Object Tracke
Scope | Release Name | Console ID | Object ID | Object Type | Business Unit | Description | Tower Name | Sub-Tower Name | Object Status | Need OSC approval? (Y/N) | OSC Approval Planned Date (Maintained by PMO) | OSC Approval Status (Maintained by PMO) | RICEFW Intake Form Link | Statutory Requirement | Go live Critical | Related Object ID | GPO Approval Submission Date | GPO Approver Email | GPO Approval Status | OSC Approval Submission Date (Maintained by PMO) | Std. vs Non-Std. (Maintained by PMO) | Interim State | FS Responsible Team | Middleware Responsible Team | S/4 DEV Responsible Team | Technical Complexity | B-App Misco | Boundary App Involved? | Boundary App. IAPM ID | Boundary Application Name | Source System | Target System | Middleware | Initial FS Planned Start Date | Initial FS Planned End Date (incl. approval) | FS Plan Finish Date | FS % Complete | FS Rev/Actual End Date | Initial HLT Planned Start Date | Initial HLT Planned End Date (incl. approval) | HLT Plan Finish Date | HLT % Complete | HLT Rev/Actual End Date | Initial S/4 TDD Planned Start Date | Initial S/4 TDD Planned End Date (incl. approval) | S/4 TDD Plan Finish Date | S/4 TDD % Complete | S/4 TDD Rev/Actual End Date | Initial S/4 Build & TUT Planned Start Date | S/4 Build & TUT Planned End Date (incl. approval) | S/4 Build & TUT Plan Finish Date | S/4 Build & TUT % Complete | S/4 Build & TUT Rev/Actual End Date | Initial MW TDD Planned Start Date | Initial MW TDD Planned End Date (incl. approval) | MW TDD Plan Finish Date | MW TDD % Complete | MW TDD Rev/Actual End Date | Initial MW Build & TUT Planned Start Date | MW Build & TUT Planned End Date (incl. approval) | MW Build & TUT Plan Finish Date | MW Build & TUT % Complete | MW Build & TUT Rev/Actual End Date | Initial BA Build & TUT Planned Start Date | BA Build & TUT Planned End Date (incl. approval) | BA Build & TUT Plan Finish Date | BA Build & TUT % Complete | BA Build & TUT Rev/Actual End Date | S/4 & MW_Build & TUT Rev/Actual End Date | Final Build Planned Date | Relevant for S4 FUT? (Yes/No) | 5.0 S4 FUT Plan Finish Date | 5.1 Conduct FUT Plan Finish Date | 5.2 Approve FUT Plan Finish Date | 5.0 S4 FUT % Complete | 5.1 Conduct FUT % Complete | 5.2 Approve FUT % Complete | 28.1 Conduct MC FUT % Complete | 28.2 Approve MC FUT % Complete | 5.0 S4 FUT Status | 5.1 Conduct FUT Status | 5.2 Approve FUT Status | 28.1 Conduct MC FUT Status | 28.2 Approve MC FUT Status | Initial FUT Planned Start Date | Initial FUT Planned End Date (incl. approval) | FUT Plan Finish Date | FUT Date Discrepancy ? | FUT % Complete | FUT Rev/Actual End Date | R3 Replan Sprint/Week | Object Completion Sprint | S4 & MW Initial Planned End Date | Final Build Initial Planned End Date | Max Build Date (Temp) | Created By | Created | Modified By | Modified | Object Status Value | GPO/OSC Approval Date | Development System | Original Object | Original Object Complexity | Medium Equivalent | Effort Equivalent | Object ID # | Change Request ID | ITC Cycle | Approved Exception ITC | ITC Mapping Rationale | Rev-Trac ID | Fiori application type | Interface – Approach / Clean Core adherence | FS Actual End Date (Automated) | FS Actual End Date | FS Rev End Date(Calc only) | FS Build End Date (Calc only) | HLT Actual End Date (Automated) | HLT Actual End Date | HLT Rev End Date(Calc only) | HLT Build End Date (Calc only) | S/4 TDD Actual End Date (Automated) | S/4 TDD Actual End Date | S/4 TDD Rev End Date(Calc only) | S/4 TDD Build End Date (Calc only) | S/4 Build & TUT Build End Date (Calc Only) | MW TDD Actual End Date (Automated) | MW TDD Rev End Date(Calc only) | MW TDD Build End Date (Calc only) | MW TDD Actual End Date | MW Build & TUT Actual End Date (Automated) | MW Build & TUT Rev End Date(Calc only) | MW Build & TUT Build End Date (Calc only) | MW Build & TUT Actual End Date | BA Build & TUT Actual End Date (Automated) | BA Build & TUT Rev End Date(Calc only) | BA Build & TUT Build End Date(Calc only) | BA Build & TUT Actual End Date | S/4 & MW_Build & TUT Actual End Date | Final Build Actual End Date | S4 FUT Actual End Date (Automated) | FUT Actual End Date (Automated) | FUT Actual End Date | FUT Rev End Date(Calc only) | FUT Build End Date(Calc only) | Initial BA TDD Planned End Date (incl. approval) | BA TDD Plan Finish Date | BA TDD % Complete | BA TDD Rev/Actual End Date | BA Critical App Family | FS Base Line Date | S4 Base Line Date | MW Base Line Date | BA Base Line Date | FUT Base Line Date | TM/GTS | WIINGS/Federal Tag | WIINGS Only Tag | Logistics Objects (Yes/No) (DO NOT DELETE) | External Partner Mapping | ROW ID | HLT Actual End Date | S/4 Build & TUT Build End Date | WIINGS Tag | Boundary App Responsible Team | Technical Effort (hours) | RAID | Category | FUT On Track/ Off Track | FUT Dependency | FUT Delay Comments | Final Build Planned End Date | Final Build Planned Date > Initial FUT Planned Sta | Towers + Logistics (PMO USE) | Sub-Scope | RAID Created Date | RAID Assigned To | FUT PMO Comments | Next Steps (PMO Use Only) | IT Lead Review Category | Review Group | FUT Delay Reason Category | FUT Category | Final Build Sprint | S/4 Build & TUT Actual End Date (Automated) | S/4 Build & TUT Rev End Date (Calc Only) | S/4 Build & TUT Actual End Date | S4 - LE Merge Impact (Yes/No) | S4 - LE Merge Change Description | MW - LE Merge Impact (Yes/No) | MW - LE Merge Change Description | Conversions - LE Merge Impact (Yes/No) | Conversions - LE Merge Change Description | LE Merge Regression Test Initial Start Date | LE Merge Regression Test Initial End Date | BApps - LE Merge Impact (Yes/No) | BApps - LE Merge Change Description | BApps - LE Merge BA RT Planned Start Date | BApps - LE Merge BA RT Planned End Date | BApps - LE Merge BA RT Rev/Act End Date | BApps -LE Merge BA RT Actual % Complete | Overall - LE Merge Impact (Yes/No) | 29.2 LE Merge Plan Finish Date | 29.1 LE Merge RT Plan End Date | LE Merge Rev/Actual End Date | LE Merge Regression Test % Completion | LE Merge RT 29.2 Status | LE Merge RT 29.1 Completion % | LE Merge RT 29.1 Status | LE Merge Actual End Date (Automated) | WIINGS Classification
01. IAO ERP | 03.R3 | 794 | PTPW0367_IP | 06.Workflow | 01.IP - Intel Product | Workflow for Email Functionality and Notification to PO approver(IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/794_PTP_PM-070-070-0006_Workflow%20for%20Email%20Functionality%20and%20Notification%20to%20PO%20approver(IF%20and%20IP).pptx?d=w54368ebc22de43b4830d4a7b860a28e9&csf=1&web=1&e=CmnTht | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-12-13 | 100% | 2024-12-10 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-18 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-06-18 05:17 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 2 | 2.1 | 0367 |  | R3 ITC1 | [6 empty] | 2024-12-10 | 2025-05-16 | 2024-12-10 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-04-24 |  |  |  | 0 | 08. Not Applicable | 1642 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 FUT shared for approval on 12/23. Awaiting approval from Intel 12/19- WIP 12/17- Will be sent on 18th 12/12 : ETA to be send for approval by tomorrow 12/11 PO Workflow FUT in Progress 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-10-08 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-23 | Yes | HR master change with plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 794 | PTPW0367_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow for Email Functionality and Notification to PO approver(IF) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/794_PTP_PM-070-070-0006_Workflow%20for%20Email%20Functionality%20and%20Notification%20to%20PO%20approver(IF%20and%20IP).pptx?d=w54368ebc22de43b4830d4a7b860a28e9&csf=1&web=1&e=CmnTht | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-12-13 | 100% | 2024-12-10 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-18 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPW0367_IP | 02.High | 1 | 1.05 | 0367 |  | R3 ITC1 | [6 empty] | 2024-12-10 | 2025-05-16 | 2024-12-10 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-04-24 |  | WIINGS |  | 0 | 08. Not Applicable | 1641 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 FUT shared for approval on 12/23. Awaiting approval from Intel 12/19- WIP 12/17- Will be sent on 18th 12/12 : ETA to be send for approval by tomorrow 12/11 PO Workflow FUT in Progress 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-10-08 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 792 | PTPW0366_IP | 06.Workflow | 01.IP - Intel Product | Workflow to trigger PO approvals in S4_IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/792_PTP_PM-070-070-0005_Workflow%20to%20trigger%20PO%20approvals%20in%20S4_IF%20and%20IP.pptx?d=w40fee8a6028540999dbeeeabec1b3f7c&csf=1&web=1&e=5KpU5k | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-12-27 | 100% | 2025-01-10 | 2025-07-14 | 2025-07-18 | 2025-08-21 | 100% | 2025-08-13 | 2025-08-18 | 2025-08-22 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-18 05:17 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 |  | 01.S4 |  |  | 1 | 1.05 | 0366 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-05-16 | 2025-01-10 |  | 2025-08-13 | 2025-08-21 | 2025-08-13 |  | 2025-09-05 | 2025-09-05 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-04-24 |  |  |  | 0 | 08. Not Applicable | 2358 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-05 | Yes | HR master change with plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 792 | PTPW0366_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow to trigger PO approvals in S4_IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/792_PTP_PM-070-070-0005_Workflow%20to%20trigger%20PO%20approvals%20in%20S4_IF%20and%20IP.pptx?d=w40fee8a6028540999dbeeeabec1b3f7c&csf=1&web=1&e=5KpU5k | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-12-27 | 100% | 2025-01-10 | 2025-07-14 | 2025-07-18 | 2025-08-21 | 100% | 2025-08-13 | 2025-08-18 | 2025-08-22 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPW0366_IP | 03.Medium | 0.5 | 0.525 | 0366 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-05-16 | 2025-01-10 |  | 2025-08-13 | 2025-08-21 | 2025-08-13 |  | 2025-09-05 | 2025-09-05 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-04-24 |  | WIINGS |  | 0 | 08. Not Applicable | 2357 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 779 | PTPW0363_IP | 06.Workflow | 01.IP - Intel Product | Workflow for Email Functionality and Notification to PR approver - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/779_PTP_PM-070-070-0002_Workflow%20for%20Email%20Functionality%20and%20Notification%20to%20PR%20approver(IF%20and%20IP).pptx?d=w86a756fae54f4a01a2c8c974d1ce73f4&csf=1&web=1&e=irQood | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-09-06 | 100% | 2024-11-26 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-18 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-06-18 05:17 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 2 | 2.1 | 0363 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-05-16 | 2024-11-26 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-09-06 | 2025-02-21 |  |  | 2025-04-03 |  |  |  | 0 | 08. Not Applicable | 2654 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 1/5 100% approved. Smartsheet to be updated 12/19- Send for approval awaiting 12/17- Waiting approval 12/12 : FUT submitted for approval. Awaiting approval 12/10 FUT in Progress. To be submitted for approval by 12/10 12/3 FUT in progress. ETA 12/5 11/18 Custom Enhancement for Rejection Email being Analyzed. Design discussion in Progress 11/14 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. Also impacted by defect 4094 being worked by tech Team FUT Completion on Track. Approval is planned for S20 | 2025-10-03 | N | 06. PTP |  |  |  |  | Defect 3565 (ETA 1124) ETA 1205 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-23 | Yes | HR master change with plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 779 | PTPW0363_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow for Email Functionality and Notification to PR approver - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/779_PTP_PM-070-070-0002_Workflow%20for%20Email%20Functionality%20and%20Notification%20to%20PR%20approver(IF%20and%20IP).pptx?d=w86a756fae54f4a01a2c8c974d1ce73f4&csf=1&web=1&e=irQood | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-09-06 | 100% | 2024-11-26 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-18 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPW0363_IP | 02.High | 1 | 1.05 | 0363 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-05-16 | 2024-11-26 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-09-06 | 2025-02-21 |  |  | 2025-04-03 |  | WIINGS |  | 0 | 08. Not Applicable | 2653 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 1/5 100% approved. Smartsheet to be updated 12/19- Send for approval awaiting 12/17- Waiting approval 12/12 : FUT submitted for approval. Awaiting approval 12/10 FUT in Progress. To be submitted for approval by 12/10 12/3 FUT in progress. ETA 12/5 11/18 Custom Enhancement for Rejection Email being Analyzed. Design discussion in Progress 11/14 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. Also impacted by defect 4094 being worked by tech Team FUT Completion on Track. Approval is planned for S20 | 2025-10-03 | N | 06. PTP |  |  |  |  | Defect 3565 (Fixed) ETA 1205 4867 (logic required), 4870 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 777 | PTPW0362_IP | 06.Workflow | 01.IP - Intel Product | Workflow to Trigger PR approvals in S/4 – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/777_PTP_PM-070-070-0001_Workflow%20to%20trigger%20PR%20approvals%20in%20S4_IF%20and%20IP.pptx?d=w97e014e04de648c78d1ec712a0ecab18&csf=1&web=1&e=FATApd | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-09-06 | 100% | 2024-11-26 | 2025-06-09 | 2025-06-13 | 2025-01-17 | 100% | 2025-01-07 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | No |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-18 05:17 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 1 | 1.05 | 0362 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-05-16 | 2024-11-26 |  | 2025-01-07 | 2025-06-13 | 2025-01-07 |  | 2025-08-29 | 2025-09-12 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-09-06 | 2025-02-21 |  |  | 2025-04-03 |  |  |  | 0 | 08. Not Applicable | 2652 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-29 | Yes | HR master change with plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-02-14 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 777 | PTPW0362_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow to Trigger PR approvals in S/4 – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/777_PTP_PM-070-070-0001_Workflow%20to%20trigger%20PR%20approvals%20in%20S4_IF%20and%20IP.pptx?d=w97e014e04de648c78d1ec712a0ecab18&csf=1&web=1&e=FATApd | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-21 | 2025-05-16 | 2024-09-06 | 100% | 2024-11-26 | 2025-06-09 | 2025-06-13 | 2025-01-17 | 100% | 2025-01-07 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | No |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPW0362_IP | 03.Medium | 0.5 | 0.525 | 0362 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-05-16 | 2024-11-26 |  | 2025-01-07 | 2025-06-13 | 2025-01-07 |  | 2025-08-29 | 2025-09-12 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2024-09-06 | 2025-02-21 |  |  | 2025-04-03 |  | WIINGS |  | 0 | 08. Not Applicable | 2651 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 3025 | PTPR1530_IP | 01.Report | 01.IP - Intel Product | Develop a custom report in SAP S/4 HANA for auto PR to PO conversion failures instead in ECA – IP/IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3025-PM-080-050_Develop%20a%20custom%20report%20in%20SAP%20S4%20for%20auto%20PR%20to%20PO%20conversion%20failures%20%E2%80%93%20IP%20and%20IF.pptx?d=w22c987c47f3e4609ac3990762b785a0c&csf=1&web=1&e=L8h8dZ | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-09 | 2025-08-09 | 100% | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-18 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-28 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-07-12 10:06 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 0.85 | 1530 |  | R3 ITC1 | [6 empty] | 2025-08-08 | 2025-08-09 | 2025-08-08 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | [5 empty] | 2025-08-09 | 2025-10-03 |  |  | 2025-11-05 |  |  |  | 0 |  | 3145 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/25 Submitted for approval. ETA to receive approval is 11/26 11/18 Defect 4633 created for review comments. Resolution in Progress 11/14 Awaiting approval. FUT Approval ETA is 11/14 11/11 - Defect 4047 is created post sent for approval 11/4 Submitted for approval on 11/4 10/27 FUT defect resolved. FUT in Progress. ETA to submit for approval 10/29 10/22 - FUT in progress. Defect 3802 is created | 2025-10-03 | N | 06. PTP |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3025 | PTPR1530_IF | 01.Report | 02.IF - Intel Foundry | Develop a custom report in SAP S/4 HANA for auto PR to PO conversion failures instead in ECA – IP/IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3025-PM-080-050_Develop%20a%20custom%20report%20in%20SAP%20S4%20for%20auto%20PR%20to%20PO%20conversion%20failures%20%E2%80%93%20IP%20and%20IF.pptx?d=w22c987c47f3e4609ac3990762b785a0c&csf=1&web=1&e=L8h8dZ | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-09 | 2025-08-09 | 100% | 2025-08-08 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-18 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-28 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-07-12 10:06 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-07-24 | 01.S4 | PTPR1530_IP | 03.Medium | 0.2 | 0.17 | 1530 |  | R3 ITC1 | [6 empty] | 2025-08-08 | 2025-08-09 | 2025-08-08 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | [5 empty] | 2025-08-09 | 2025-10-03 |  |  | 2025-11-05 |  |  |  | 0 |  | 3146 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/25 Submitted for approval. ETA to receive approval is 11/26 11/18 Defect 4633 created for review comments. Resolution in Progress 11/14 Awaiting approval. FUT Approval ETA is 11/14 11/11 - Defect 4047 is created post sent for approval 11/4 Submitted for approval on 11/4 10/27 FUT defect resolved. FUT in Progress. ETA to submit for approval 10/29 10/22 - FUT in progress. Defect 3802 is created | 2025-10-03 | N | 06. PTP |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | PTPM0008 | 12.Manual Conversion | 02.IF - Intel Foundry | Quality Info record upload [T-Code - QI01] | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N | [8 empty] | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-05 | 100% | 2025-08-20 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-05-20 | 2025-06-16 |  | 0% | 2025-06-16 | [15 empty] | 2025-06-16 | 2025-06-16 | Yes | [6 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-05-20 | 2025-06-16 | 2025-06-11 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | anntam@deloitte.com | 2025-02-07 15:57 | jenoronha@deloitte.com | 2026-03-04 09:32 | 10 | 2025-05-20 | 01.S4 |  |  |  | 0 | 0008 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 | [25 empty] | 2025-07-31 | 2025-07-31 | 2025-07-31 | [5 empty] | 2025-05-16 | 2025-06-16 |  |  | 2025-06-16 |  |  |  | 0 |  | 2261 | [9 empty] | 25/7 - Reminder sent to Jose to mark this as 100% | 2025-06-16 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-06-16 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | PTPM0007 | 12.Manual Conversion | 02.IF - Intel Foundry | Inspection Plan upload [T-Code - QP01] | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N | [8 empty] | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-05 | 100% | 2025-08-20 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-05-20 | 2025-06-16 |  | 0% | 2025-06-16 | [15 empty] | 2025-06-16 | 2025-06-16 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-05-20 | 2025-06-16 | 2025-06-11 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | anntam@deloitte.com | 2025-02-07 15:57 | jenoronha@deloitte.com | 2026-03-04 09:32 | 10 | 2025-05-20 | 01.S4 |  |  |  | 0 | 0007 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 | [25 empty] | 2025-07-31 | 2025-07-31 | 2025-07-31 | [5 empty] | 2025-05-16 | 2025-06-16 |  |  | 2025-06-16 |  |  |  | 0 |  | 2260 | [9 empty] | 25/7 - Reminder sent to Jose to mark this as 100% | 2025-06-16 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-06-16 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | PTPM0006 | 12.Manual Conversion | 02.IF - Intel Foundry | Master Inspection Characteristics upload [T-Code - QS21] | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N | [8 empty] | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | N/A | [6 empty] | NA | 2025-03-24 | 2025-03-28 | 2025-05-05 | 100% | 2025-08-20 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-03-31 | 2025-04-18 |  | 0% | 2025-04-18 | [15 empty] | 2025-04-18 | 2025-04-18 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-03-31 | 2025-04-18 | 2025-06-11 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | anntam@deloitte.com | 2025-02-07 15:57 | jenoronha@deloitte.com | 2026-03-04 09:32 | 10 | 2025-05-20 | 01.S4 |  |  |  | 0 | 0006 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 | [25 empty] | 2025-07-31 | 2025-07-31 | 2025-07-31 | [5 empty] | 2025-03-28 | 2025-04-18 |  |  | 2025-04-18 |  |  |  | 0 |  | 2262 | [9 empty] | 25/7 - Reminder sent to Jose to mark this as 100% | 2025-04-18 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3147 | PTPI1689 | 02.Interface | 02.IF - Intel Foundry | New custom API needed to process GET and DELETE function for Document Info Record Object Link where boundary app CWB can perform GET and DELETE in S4. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3147_R3_PTP_IF_Custom%20API%20to%20GET%20and%20DELETE%20DIR%20Object%20Link.pptx?d=w36a8396de1e54aea90d35842da6695ed&csf=1&web=1&e=laxLyO | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 22233 | Commercial Workbench |  |  | Apigee | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-16 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-22 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-23 | 2025-12-15 | 2026-01-31 | 2026-01-31 | 100% | 2026-02-13 | 2026-03-09 | 2026-03-09 |  |  | 2026-01-23 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-29 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-11-05 05:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1.45 | 1689 | INT-CR1398 | R3 ITC1 | [6 empty] | 2025-12-16 | 2026-01-07 | 2025-12-16 |  | 2025-12-22 | 2026-01-07 | 2025-12-22 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-14 | 2026-02-14 |  | 2026-01-07 |  | 2026-01-07 |  | 2026-01-07 | 2025-12-23 | 2025-12-23 |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-03-09 | 2026-03-09 |  |  | 2026-01-29 | 2026-01-30 | 2026-01-29 | [5 empty] | 2026-01-07 | 2026-02-20 | 2026-01-07 |  | 2026-01-30 |  |  |  | 0 |  | 3372 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 1/20 Review comments received from Intel where segregation of API is needed. Fix in progress with Technical Team/ ETA 1/23 1/13 FUT completed and shared with Intel for approval. ETA for approval 1/16 1/9 - Build is still in progress. 1/5 Waiting for development to be completed. Planned in S22 for FUT 12/19 Waiting for tech to complete 12/17- FS completed tech to complete 12/12 : FS completed in sprint 21 | 2026-02-20 | Y | 06. PTP |  |  |  | TBD 1209:FS submitted. Nishant to confirm dev. actvitities. 5.1 and 5.2 to be added in S21. | FS already complete. To be added in S21 plan. |  |  | Defects | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-20 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2934 | PTPI1657 | 02.Interface | 05.CFIN | Interface to send Invoice PAID Status from CFIN to IP | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N | 2025-05-05 |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CFC07E3-39DA-4751-86BA-DB6A987A9F61%7D&file=PM-150-020%20Enhacement%20to%20Update%20Invoice%20PAID%20Status%20from%20CFIN%20to%20IF%20&%20IP%20ARIBA%20Standard%20Tables%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-08 | 2025-08-08 | 100% | 2025-10-06 | 2025-09-12 | 2025-09-19 | 2025-10-15 | 100% | 2025-11-13 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-13 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-11-14 | 2025-11-28 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-04 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jenoronha@deloitte.com | 2025-06-12 04:42 | cell-link@smartsheet.com | 2026-03-09 08:15 | 10 | 2025-05-05 | 01.S4 |  |  | 1 | 1.45 | 1657 |  | R3 ITC1 | [6 empty] | 2025-10-06 | 2025-10-06 | 2025-10-06 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | [5 empty] | 2025-08-08 | 2025-10-24 |  |  | 2025-12-04 |  |  |  | 0 |  | 3102 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/25 FUT completed and shared for approval 11/24 FUT in Progress. Expedited. To be shared for approval by 11/25 11/18 FUT in Progress. Planned to be submitted for approval by 11/28 11/12 - FUT in Progress. | 2025-10-24 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3019 | PTPI1533 | 02.Interface | 02.IF - Intel Foundry | Pay@accept – Inbound Interface to fetch the values from FCE ODS to SAP S/4 HANA IF | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3019-PM-150-170-0013-PTP-IF%20Pay@Accept%20-%20Interface%20to%20fetch%20the%20MRCL%20and%20Sup%20Qual%20End%20date.pptx?d=wf9273fadc2eb4fca9aa71e087f2241d8&csf=1&web=1&e=KRqjH8 | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management |  |  | APIGEE | 2025-08-18 | 2025-09-08 | 2025-09-08 | 100% | 2025-09-08 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-15 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-15 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-14 | 2025-08-11 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2025-10-15 | 2025-10-15 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-14 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-07-12 10:06 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1.45 | 1533 |  | R3 ITC1 | [6 empty] | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2025-09-30 | 2025-10-08 | 2025-09-30 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-11-07 | 2025-10-14 | 2025-10-14 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-10-15 | 2025-10-15 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-09-08 | 2025-09-26 | 2025-10-08 |  | 2025-11-05 |  |  |  | 0 |  | 3151 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 Submitted for approval 10/27: FUT is in progress. | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-15 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2993 | PTPI1529_IP | 02.Interface | 01.IP - Intel Product | An interface to retrieve the list of approvers from a custom MDG table(MDG system) when a PR/PO creation or change workflow is triggered in S/4HANA.​ | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B75CB195C-F03B-4B0F-AB21-3F1C5A6C60FF%7D&file=2993_PTP_Interface%20to%20call%20custom%20costcentre%20MDG%20table%20for%20fetching%20approvers%20list%20during%20PR&PO%20crreation.change%20workflow%20trigeering.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-09 | 2025-08-09 | 100% | 2025-10-03 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-17 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-17 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 0.5 | 0.725 | 1529 | INT-CR0742 | R3 ITC1 | [6 empty] | 2025-10-03 | 2025-10-03 | 2025-10-03 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-08-09 | 2025-10-24 |  |  | 2025-12-03 |  |  |  | 0 |  | 3143 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 12/3 FUT approved. Awaiting Jose to mark as 100% 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-10-24 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | Yes | Workflow object if plants are getting changed, needs to retest with MDG | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2993 | PTPI1529_IF | 02.Interface | 02.IF - Intel Foundry | An interface to retrieve the list of approvers from a custom MDG table(MDG system) when a PR/PO creation or change workflow is triggered in S/4HANA.​ | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B75CB195C-F03B-4B0F-AB21-3F1C5A6C60FF%7D&file=2993_PTP_Interface%20to%20call%20custom%20costcentre%20MDG%20table%20for%20fetching%20approvers%20list%20during%20PR&PO%20crreation.change%20workflow%20trigeering.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-09 | 2025-08-09 | 100% | 2025-08-29 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-29 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-29 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 | PTPI1529_IP | 04.Low | 0.15 | 0.2175 | 1529 | INT-CR0742 | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-08-09 | 2025-09-26 |  |  | 2025-12-03 |  |  |  | 0 |  | 3144 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 12/3 FUT approved. Awaiting Jose to mark as 100% 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-26 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2964 | PTPI1458 | 02.Interface | 02.IF - Intel Foundry | Develop an interface between PEGA and S/4 HANA system to transmit MSL information – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2964-PM-070-060-0001_MSL%20Interface%20between%20PEGA%20and%20SAP%20S4_IF.pptx?d=w947a2f8c06984caca76f7ac369b9db60&csf=1&web=1&e=vbgRw8 | 01.Yes | 01.Yes |  | 2025-05-19 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 20386 | Pega Manage My Supply Line GFM |  |  | MULESOFT | 2025-06-18 | 2025-07-18 | 2025-07-08 | 100% | 2025-07-21 | 2025-07-28 | 2025-08-01 | 2025-08-13 | 100% | 2025-08-11 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-08-20 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-08-20 | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-12 | 2025-09-15 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-06 | 2025-09-12 | 2026-01-06 |  | 2025-11-21 | 2025-12-03 | 2025-12-12 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-12 | 2025-12-12 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-05-17 02:08 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-03 | 01.S4 |  |  | 1 | 1.45 | 1458 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-08-20 | 2025-09-05 | 2025-08-20 | 2025-08-20 |  | 2025-08-15 |  | 2025-08-13 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2026-01-09 | 2026-01-06 | 2026-01-06 | 2025-09-12 | 2026-01-06 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 |  |  |  |  | WIINGS | 2025-07-18 | 2025-08-13 | 2025-08-15 |  | 2025-12-12 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 3029 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 12/19- Defect fixed will be again send today for approval 12/12 : Send for approval 12/10 Awaiting approval. Walkthrough planned on 12/11 12/3 FUT submitted for approval on 12/2 11/24 FUT in Progress. 90% completed. Targeted to be shared for approval by 11/26 11/12 FUT Initiated. In Progress | 2026-01-09 | Y | 06. PTP |  |  |  | 1217: Submitted for approval 11/24 FUT in Progress. 90% completed. |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-09-05 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2938 | PTPI1428_IP | 02.Interface | 01.IP - Intel Product | Setting Up Inbound Interface from SPT tool/GTT(Global Trade and Tax) system to S/4 IF and IP Systems | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B23F5A0BC-A8AF-49AC-AF8F-CD6052CD0AE8%7D&file=PM-150-170%20PTP-%20Setting%20Up%20Inbound%20Interface%20from%20GTT%20system%20to%20S4%20IF%20and%20IP%20Systems.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 42860 | Customs Tracker |  | S/4 | APIGEE | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-11 | 2025-06-30 | 2025-07-04 | 2025-07-18 | 100% | 2025-07-21 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-09 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-09 | 2025-06-16 | 2025-07-16 | 2025-07-18 | 100% | 2025-07-18 | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-04 | 2025-08-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-15 | 2025-08-09 | 2025-09-15 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-09-15 | 2025-09-15 | jonsanders@deloitte.com | 2025-04-23 10:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-05-05 | 01.S4 |  |  | 0.5 | 0.725 | 1428 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-09 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-08-09 | 2025-09-15 |  |  | 2025-10-22 | 2025-11-05 | 2025-10-22 |  |  |  |  | Trade Apps | 2025-06-11 | 2025-08-08 | 2025-07-16 |  | 2025-11-05 |  |  |  | 0 |  | 2981 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 10/22 : FUT approved. Jose to mark it as 100% 10/17; FUT is completed and FUT document is shared for approval. | 2025-09-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-09 | 2025-08-09 | Yes | SPT interface regression testing | No |  | No |  |  |  | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2938 | PTPI1428_IF | 02.Interface | 02.IF - Intel Foundry | Setting Up Inbound Interface from SPT tool/GTT(Global Trade and Tax) system to S/4 IF and IP Systems | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B23F5A0BC-A8AF-49AC-AF8F-CD6052CD0AE8%7D&file=PM-150-170%20PTP-%20Setting%20Up%20Inbound%20Interface%20from%20GTT%20system%20to%20S4%20IF%20and%20IP%20Systems.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 42860 | Customs Tracker |  | S/4 | APIGEE | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-11 | 2025-06-30 | 2025-07-04 | 2025-07-18 | 100% | 2025-07-21 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-12 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-12 | 2025-06-16 | 2025-07-16 | 2025-07-18 | 100% | 2025-07-18 | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-04 | 2025-08-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-15 | 2025-08-12 | 2025-09-15 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-09-15 | 2025-09-15 | jonsanders@deloitte.com | 2025-04-23 10:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-05-05 | 01.S4 | PTPI1428_IP | 04.Low | 0.15 | 0.2175 | 1428 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-08-12 | 2025-09-15 |  |  | 2025-10-22 | 2025-11-05 | 2025-10-22 |  |  |  |  | Trade Apps | 2025-06-11 | 2025-08-08 | 2025-07-16 |  | 2025-11-05 |  |  |  | 0 |  | 2982 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 10/22 : FUT approved. Jose to mark it as 100% 10/17; FUT is completed and FUT document is shared for approval. | 2025-09-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-12 | 2025-08-12 | No | Custom Tracker interface need to retest. | No | Regression test only | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2304 | PTPI1331_IP | 02.Interface | 01.IP - Intel Product | Ariba POs Goods Receipts to be sent from WIINGS to S/4 for R4 sites | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/RICEFW_Interface_S4_WIINGS_PO%20details.pptx?d=w4d96d28562964599b0190bb96eb1f87c&csf=1&web=1&e=E6Q4QY | 02.No | 01.Yes |  | 2024-10-16 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 10821 | Wiings on the Web (WOW) - WIINGS (Angular) | WIINGS | S/4 | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-20 | 2025-08-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-08 | 2025-08-22 | 2025-06-11 | 100% | 2025-06-11 | 2025-09-01 | 2025-09-26 | 2025-05-23 | 100% | 2025-05-20 | 2025-01-29 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-05-24 | 2025-07-30 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-03-27 05:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-27 | 01.S4 |  |  | 1 | 1.45 | 1331 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-20 | 2025-07-18 | 2025-05-20 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 |  | 2025-08-22 |  | 2025-06-11 |  | 2025-09-26 | 2025-05-20 | 2025-05-20 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-24 | 2025-07-30 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | WIINGS | 2025-05-16 | 2025-08-15 | 2025-08-22 |  | 2025-10-08 |  |  |  | 0 | 01.1 Supplier -Capital | 2839 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/18 FUT Completed. Shared for approval on 11/18 11/14 FUT completed. Waiting for B-app to update the screenshots. ETA 11/14 11/11 - Dependent object is ready. FUT to being in S20. 11/4: Object PTPI0735 was not ready when the plan was made , we will picking PTPI1131 with PTPI0735 once in sprint 20 10/10 Had dependency on WIINGS readiness. Its ready now. Object planned in Sprint 19 10/10 Had dependency on WIINGS readiness. Its ready now. Object planned in Sprint 19 | 2025-09-26 | Y | 06. PTP |  |  |  | 1027: WIINGS issue? Current Status: FUT cannot be performed Issue: Dependent object PTPI0735 was not ready when the plan was made. Next Steps: Post build is completed for PTPI0735, FUT for both objects PTPI1131 & PTPI0735 will be picked in Sprint 20. Help Needed: | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-05-24 | Yes | Mapping changes for plant | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2304 | PTPI1331_IF | 02.Interface | 02.IF - Intel Foundry | Ariba POs Goods Receipts to be sent from WIINGS to S/4 for R4 sites | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/RICEFW_Interface_S4_WIINGS_PO%20details.pptx?d=w4d96d28562964599b0190bb96eb1f87c&csf=1&web=1&e=E6Q4QY | 02.No | 01.Yes |  | 2024-10-16 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 10821 | Wiings on the Web (WOW) - WIINGS (Angular) | WIINGS | S/4 | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-20 | 2025-08-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-08 | 2025-08-22 | 2025-06-11 | 100% | 2025-06-11 | 2025-09-01 | 2025-09-26 | 2025-05-23 | 100% | 2025-05-20 | 2025-01-29 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-05-24 | 2025-07-30 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-03-27 05:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-27 | 01.S4 | PTPI1331_IP | 03.Medium | 0.3 | 0.435 | 1331 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-20 | 2025-07-18 | 2025-05-20 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 |  | 2025-08-22 |  | 2025-06-11 |  | 2025-09-26 | 2025-05-20 | 2025-05-20 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-24 | 2025-07-30 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | WIINGS | 2025-05-16 | 2025-08-15 | 2025-08-22 |  | 2025-10-08 |  |  |  | 0 | 01.1 Supplier -Capital | 2838 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/18 FUT Completed. Shared for approval on 11/18 11/14 FUT completed. Waiting for B-app to update the screenshots. ETA 11/14 11/11 - Dependent object is ready. FUT to being in S20. 11/4: Object PTPI0735 was not ready when the plan was made , we will picking PTPI1131 with PTPI0735 once in sprint 20 10/10 Had dependency on WIINGS readiness. Its ready now. Object planned in Sprint 19 10/10 Had dependency on WIINGS readiness. Its ready now. Object planned in Sprint 19 | 2025-09-26 | Y | 06. PTP |  |  |  | 1027: WIINGS issue? Current Status: FUT cannot be performed Issue: Dependent object PTPI0735 was not ready when the plan was made. Next Steps: Post build is completed for PTPI0735, FUT for both objects PTPI1131 & PTPI0735 will be picked in Sprint 20. Help Needed: | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2093 | PTPI1329_IP | 02.Interface | 01.IP - Intel Product | FSD to change Purchase Order information from B2B Staging DB ePO from S4 IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PTP%20B-App%20RICEFW%20Requests/PM-080-060-1010_SPS_Intel_Web_PO_PTP.pptx?d=w7c22917b10d142069ddfe36d41c70810&csf=1&web=1&e=Oc2MRe | 02.No | 01.Yes |  | 2025-03-28 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 829; 24834 | Intel WebSuite - Web PO; B2B Staging Database | S/4 | Stagging DB | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-22 | 2025-07-11 | 100% | 2025-07-11 | 2025-09-01 | 2025-09-26 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-02 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-03-25 01:22 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-04-03 | 01.S4 |  |  | 1 | 1.45 | 1329 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 |  | 2025-07-11 |  | 2025-09-26 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-08-15 | 2025-08-22 |  | 2025-12-03 |  |  |  | 0 |  | 2030 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-15 | 2025-07-21 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-05 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2093 | PTPI1329_IF | 02.Interface | 02.IF - Intel Foundry | FSD to change Purchase Order information from B2B Staging DB ePO from S4 IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PTP%20B-App%20RICEFW%20Requests/PM-080-060-1010_SPS_Intel_Web_PO_PTP.pptx?d=w7c22917b10d142069ddfe36d41c70810&csf=1&web=1&e=Oc2MRe | 02.No | 01.Yes |  | 2025-03-28 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 829; 24834 | Intel WebSuite - Web PO; B2B Staging Database | S/4 | Stagging DB | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-22 | 2025-07-11 | 100% | 2025-07-11 | 2025-09-01 | 2025-09-26 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-02 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-03-25 01:22 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-04-03 | 01.S4 | PTPI1329_IP | 03.Medium | 0.3 | 0.435 | 1329 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 |  | 2025-07-11 |  | 2025-09-26 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-08-15 | 2025-08-22 |  | 2025-12-03 |  |  |  | 0 |  | 2031 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 585 | PTPI1308_IP | 02.Interface | 01.IP - Intel Product | FSD to publish SAP Contracts pricing condition details to Web Contract - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0003_Publish_SAP_Contract_Details_To_WebContracts_Intel_Products.pptx?d=wc0df8a85ce4546ebb2a13c279fbae455&csf=1&web=1&e=WeZCzf | 02.No | 01.Yes | PTPE1135_IP | 2025-03-04 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-09 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-09 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-08-27 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-03-04 02:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-06 | 01.S4 |  |  | 1 | 1.45 | 1308 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-07-18 | 2025-07-18 |  | 2025-11-05 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2409 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix |  | 2025-10-10 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-02-27 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 586 | PTPI1308_IF | 02.Interface | 02.IF - Intel Foundry | FSD to publish SAP Contracts pricing condition details to Web Contract - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0004_Publish_SAP_Contract_Details_To_WebContracts_Intel_Foundary.pptx?d=w89e7c55a60b242579464073c735ed53c&csf=1&web=1&e=UF1hLE | 02.No | 01.Yes | PTPE1135_IF | 2025-03-04 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-02 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-08-27 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-03-04 02:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-06 | 01.S4 | PTPI0211_IP | 03.Medium | 0.3 | 0.435 | 1308 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-07-18 | 2025-07-18 |  | 2025-11-05 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2412 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100% | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 585 | PTPI1307_IP | 02.Interface | 01.IP - Intel Product | FSD to publish SAP Contracts changes details to Web Contract - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0003_Publish_SAP_Contract_Details_To_WebContracts_Intel_Products.pptx?d=wc0df8a85ce4546ebb2a13c279fbae455&csf=1&web=1&e=WeZCzf | 02.No | 01.Yes | PTPE1135_IP | 2025-03-04 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-09 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-09 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-09-22 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-03-04 02:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-06 | 01.S4 |  |  | 1 | 1.45 | 1307 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-07-18 | 2025-07-18 |  | 2025-11-05 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2411 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100% | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 586 | PTPI1307_IF | 02.Interface | 02.IF - Intel Foundry | FSD to publish SAP Contracts changes details to Web Contract - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0004_Publish_SAP_Contract_Details_To_WebContracts_Intel_Foundary.pptx?d=w89e7c55a60b242579464073c735ed53c&csf=1&web=1&e=UF1hLE | 02.No | 01.Yes | PTPE1135_IF | 2025-03-04 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-02 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-09-22 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-03-04 02:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-06 | 01.S4 | PTPI0211_IP | 03.Medium | 0.3 | 0.435 | 1307 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-05-16 | 2025-07-18 | 2025-07-18 |  | 2025-11-05 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2414 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100% | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2781 | PTPI1171 | 02.Interface | 02.IF - Intel Foundry | Get Material details from IF to METs/SOM | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2781_PTP_Mets_SOM_Get%20Material%20Master%20details%20from%20IF%20to%20Mets_SOM.pptx?d=w1aac40e3e21149e1b67fc023704ae42b&csf=1&web=1&e=w5C43E | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management | S/4 | METs/SOM | APIGEE | 2025-05-01 | 2025-05-30 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-08 | 2025-07-21 | 2025-10-08 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1171 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-08 | 2025-10-08 | 2025-07-21 | 2025-10-08 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | [5 empty] | 2025-05-30 | 2025-07-18 | 2025-06-27 | S4 |  |  |  |  | 0 |  | 1812 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2780 | PTPI1170 | 02.Interface | 02.IF - Intel Foundry | Get Source List details from IF to METs/SOM | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2780_PM-090-060-0014_PTP_METs_SOM_Get%20OA%20determination%20by%20material%20from%20IF%20to%20METs_SOM.pptx?d=w30335147f3784699a8e34ab2c5ed3a79&csf=1&web=1&e=QoUymV | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management | METs/SOM | S/4 | APIGEE | 2025-05-01 | 2025-05-30 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-08 | 2025-07-21 | 2025-10-08 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 2 | 2.9 | 1170 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-08 | 2025-10-08 | 2025-07-21 | 2025-10-08 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | [5 empty] | 2025-05-30 | 2025-07-18 | 2025-06-27 | S4 |  |  |  |  | 0 |  | 1811 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2779 | PTPI1169 | 02.Interface | 02.IF - Intel Foundry | Read Outline Agreement (OA) from IF in METs/SOM app. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2779_PM-090-040-PTP_METs_SOM_Maintain%20Outline%20Agreement%20in%20IF%20from%20METs_SOM.pptx?d=w103422df110f4019a726d30fd5f90405&csf=1&web=1&e=ddzZIk | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management | S/4 | METs/SOM | APIGEE | 2025-05-01 | 2025-05-30 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-08 | 2025-07-21 | 2025-10-08 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 2 | 2.9 | 1169 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-08 | 2025-10-08 | 2025-07-21 | 2025-10-08 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | [5 empty] | 2025-05-30 | 2025-07-18 | 2025-06-27 | S4 |  |  |  |  | 0 |  | 1810 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2778 | PTPI1168 | 02.Interface | 02.IF - Intel Foundry | Get PO details from IF to METs/SOM | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2778_PM-080-070-0010_PTP_METs_SOM_Get%20PO%20details%20from%20IF%20to%20METs_SOM.pptx?d=w7bc36ea6e103485a835fc8476eebbc6a&csf=1&web=1&e=V24rAB | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management | S/4 | METs/SOM | APIGEE | 2025-05-01 | 2025-05-30 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-08 | 2025-07-21 | 2025-10-08 | Yes | 2025-07-15 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1168 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-08 | 2025-10-08 | 2025-07-21 | 2025-10-08 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | [5 empty] | 2025-05-30 | 2025-07-18 | 2025-06-27 | S4 |  |  |  |  | 0 |  | 1809 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2777 | PTPI1167 | 02.Interface | 02.IF - Intel Foundry | Maintain PR in IF from METs/SOM | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2777_PM-070-080-0012_PTP_METs_SOM_Maintain%20PR%20in%20IF%20from%20METs_SOM.pptx?d=wbdcf440101ae47719fe9727436af7eae&csf=1&web=1&e=tFenyG | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 25285 | FCE Operational Data Services - METS Smart Order Management | METs/SOM | S/4 | APIGEE | 2025-05-01 | 2025-05-30 | 2025-05-12 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-08 | 2025-07-21 | 2025-10-08 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1167 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-08 | 2025-10-08 | 2025-07-21 | 2025-10-08 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | [5 empty] | 2025-05-30 | 2025-07-18 | 2025-06-27 | S4 |  |  |  |  | 0 |  | 1808 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2757 | PTPI1154 | 02.Interface | 02.IF - Intel Foundry | ILM to SAP S4 Interface – Assigning Material to Inspection Plan | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2757_RICEFW_Interface%20from%20ILM%20to%20SAP%20S4%20-Assigning%20material%20to%20Inspection%20Plan.pptx?d=w95545f2aa646490db9351f296a45ffef&csf=1&web=1&e=txmyyO |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 25998 | ILM FOAM | ILM | S/4 | NA | 2025-03-21 | 2025-04-18 | 2025-04-15 | 100% | 2025-04-19 | 2025-05-11 | 2025-05-16 | 2025-09-26 | 100% | 2025-09-17 | 2025-08-04 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | 2025-08-04 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | [10 empty] | 2025-08-18 | 2025-11-25 | 2025-11-25 | 100% | 2025-11-24 | 2025-09-03 | 2025-11-24 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-11-25 | 2025-11-25 | pgaroo@deloitte.com | 2025-01-20 06:30 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-24 | 01.S4 |  |  | 1 | 1.45 | 1154 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-19 | 2025-04-19 |  | 2025-09-17 | 2025-09-26 | 2025-09-17 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | [9 empty] | 2025-11-25 | 2025-11-24 | 2025-11-24 | 2025-09-03 | 2025-11-24 |  |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 |  |  | WIINGS |  | 0 |  | 2048 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24 FUT submitted for approval. Awaiting approval from Intel 11/18 FUT in Progress. 2/12 scenarios completed. ETA 11/18 and walkthrough planned on 11/24 11/12 - FUT in Progress. | 2025-11-25 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2756 | PTPI1153 | 02.Interface | 02.IF - Intel Foundry | Interface from ILM to SAP S/4 - Create/Modify Quality Info records | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2756_RICEFW_Interface%20from%20ILM%20to%20SAP%20S4%20-%20Create_Modify_Quality%20Info_Record_IF.pptx?d=w302dedca41de4af28452989a0c9a9599&csf=1&web=1&e=HAMBpK |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 25998 | ILM FOAM | ILM | S/4 | NA | 2025-03-21 | 2025-04-18 | 2025-04-15 | 100% | 2025-04-19 | 2025-05-11 | 2025-05-16 | 2025-09-26 | 100% | 2025-09-17 | 2025-08-04 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | 2025-08-04 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | [10 empty] | 2025-08-18 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-24 | 2025-09-03 | 2025-11-24 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-01-20 06:30 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-24 | 01.S4 |  |  | 1 | 1.45 | 1153 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-19 | 2025-04-19 |  | 2025-09-17 | 2025-09-26 | 2025-09-17 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | [9 empty] | 2025-11-28 | 2025-11-24 | 2025-11-24 | 2025-09-03 | 2025-11-24 |  |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 |  |  | WIINGS |  | 0 |  | 2047 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24 FUT submitted for approval. Awaiting approval from Intel 11/18 FUT in Progress. 2/12 scenarios completed. ETA 11/18 and walkthrough planned on 11/24 11/12 - FUT in Progress. | 2025-11-28 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2767 | PTPI1152 | 02.Interface | 02.IF - Intel Foundry | Develop an interface to create PO/STO from IRIS Non-Standard Request to S/4 Hana | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2767-LI-200-020-0004_PTP_Interface%20from%20IRIS%20to%20S4%20to%20create%20PR%20and%20STR%20from%20non-standard%20request%20created%20in%20IRIS_IF_IP.pptx?d=wff12c44d234049deaf1fcf27d3192af9&csf=1&web=1&e=Ad7Iid |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 17940 | Integrated Repair System | IRIS | S/4 | APIGEE | 2025-02-25 | 2025-03-30 | 2025-03-20 | 100% | 2025-03-20 | 2025-04-14 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-09-08 | 2025-09-12 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | 2025-07-21 | 2025-08-15 | 2025-05-16 | 100% | 2025-05-16 | 2025-06-02 | 2025-06-27 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-04 | 2025-08-13 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-27 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2025-01-20 06:30 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-24 | 01.S4 |  |  | 0.5 | 0.725 | 1152 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-30 | 2025-03-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 |  | 2025-08-15 |  | 2025-05-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-04 | 2025-08-13 |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 |  |  |  |  | WIINGS | 2025-03-30 | 2025-05-16 | 2025-08-15 |  | 2025-11-05 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 2313 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/17- Waiting approval 12/12 ETA is today to send for approval 12/10 AWaiting approval 12/3 Feedbacks Received from Intel. Fix in Progress 11/18 B-app making logic change at their side. ETA for making necessary changes and approval is 11/21 11/14 Awaiting approval. FUT Approval ETA is 11/21 11/11 - IRIS team to update screenshots. Sent for approval 11/3 IRIS team suggested review comments. Deloitte is making necessary changes. Will spill over to next week. ETA 11/4 10/27 - Defect resolved by Tech. FUT is in progress | 2025-08-13 | N | 06. PTP |  |  |  | 1217: Submitted for approval Current Status: FUT Submitted for approval Issue : Approval taking longer Next Steps: FUT Review in progress Help needed: N/A |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2759 | PTPI1138 | 02.Interface | 01.IP - Intel Product | This interface is required to trigger split account assigned Purchase Requisition from My samples to S4 to accommodate engineering builds for Intel Products . | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2759_PTP_PM-080-100_RICEFW_Interface%20Interface%20to%20trigger%20split%20account%20assigned%20Purchase%20Requisition%20from%20My%20samples%20to%20S4.pptx?d=wbe52e9c3681d4d6ca4be0c71713cefb5&csf=1&web=1&e=0pOdN9 |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 11565 | My Samples ( Future of Samples) | MySamples | S/4 | APIGEE | 2025-03-03 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-21 | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-07-25 | 2025-06-02 | 2025-06-13 | 2025-05-30 | 100% | 2025-08-12 | 2025-06-02 | 2025-06-13 | 2025-05-30 | 100% | 2025-08-12 | 2025-04-21 | 2025-05-16 | 2025-06-06 | 100% | 2025-06-06 | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-08-04 | 2025-10-01 | 2025-11-14 | 2025-11-14 | 100% | 2025-12-26 | 2025-08-12 | 2025-12-26 |  |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-11-14 | 2025-11-14 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 |  |  | 1 | 1.45 | 1138 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-28 | 2025-03-21 |  | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-06-06 |  | 2025-06-06 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-08-12 | 2025-12-26 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | SMG Apps | 2025-03-28 | 2025-06-13 | 2025-05-16 | S4 |  |  |  |  | 0 | 08. Not Applicable | 2049 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/10 Awaiting approval on MySamples 12/3 Awaiting approval 11/25 FUT completed and shared for approval 11/24 FUT in Progress. Roadblocked for G/account - FPR. ETA 11/28 11/18 FUT in Progress. Planned to be submitted for approval by 11/28 11/12 - FUT in Progress. | 2025-11-14 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-08-12 | 2025-08-12 | Yes | If Plants are changes it needs to be retested | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2747 | PTPI1137_IP | 02.Interface | 01.IP - Intel Product | Interface between S4 to Boundary Apps (Customs Tracker and PEGA-ISMQ) for real time data on Purchase Order details from both S4 IF & IP system | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2747_PTP_PM_080_050_S4%20interface%20for%20PO%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w086b4c1d5abc47fc87ea0bf7e3bcf6c2&csf=1&web=1&e=ULwyFO |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 42860 | Customs Tracker | ILM | S/4 | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-18 | 100% | 2025-03-21 | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-09 | 2025-05-26 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-05 | 2025-05-26 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-05 | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-06-06 | 2025-06-16 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-11 | 2025-05-01 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2025-06-11 | 2025-09-30 | No | 2025-07-31 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 |  |  | 2 | 2.9 | 1137 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-28 | 2025-03-21 |  | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-06-05 | 2025-06-13 | 2025-06-05 | 2025-06-05 |  | 2025-06-13 |  | 2025-06-06 |  | 2025-07-18 | 2025-06-11 | 2025-06-11 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-06-11 | 2025-09-30 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 |  |  |  |  | Trade Apps | 2025-03-28 | 2025-06-13 | 2025-06-13 | MW |  |  |  |  | 0 |  | 1654 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-09-30 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-06-13 | 2025-06-05 | Yes | If Plants are changes it needs to be retested | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2747 | PTPI1137_IF | 02.Interface | 02.IF - Intel Foundry | Interface between S4 to Boundary Apps (Customs Tracker and PEGA-ISMQ) for real time data on Purchase Order details from both S4 IF & IP system | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2747_PTP_PM_080_050_S4%20interface%20for%20PO%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w086b4c1d5abc47fc87ea0bf7e3bcf6c2&csf=1&web=1&e=ULwyFO |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 42860 | Customs Tracker | S/4 | Boundary Apps (Customs Tracker and PEGA-ISMQ | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-18 | 100% | 2025-03-21 | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-10 | 2025-06-02 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-11 | 2025-06-02 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-11 | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-06-06 | 2025-06-16 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-03 | 2025-05-01 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2025-06-11 | 2025-09-30 | No | 2025-07-31 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 | PTPI1137_IP | 02.High | 0.6 | 0.87 | 1137 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-28 | 2025-03-21 |  | 2025-06-10 | 2025-06-10 | 2025-06-10 |  | 2025-06-11 | 2025-06-13 | 2025-06-11 | 2025-06-11 |  | 2025-06-13 |  | 2025-06-06 |  | 2025-07-18 | 2025-06-03 | 2025-06-03 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-06-11 | 2025-09-30 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 |  |  |  |  | Trade Apps | 2025-03-28 | 2025-06-13 | 2025-06-13 | S4 |  |  |  |  | 0 |  | 1653 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-09-30 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-06-13 | 2025-06-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2736 | PTPI1134 | 02.Interface | 02.IF - Intel Foundry | Inbound Interface from E2Open to IF – Intel Foundry in S/4 to bring shipping details and create STO applicable for Bailment Process. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2736_PTP_Inbound%20Interface%20from%20E2open%20to%20IF%20for%20STO%20Creation%20%5B3A13%20Signal%5D.pptx?d=wdf62e6b89dab454db848245d165083da&csf=1&web=1&e=s3F2SB |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | E2Open | S/4 | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-20 | 2025-04-14 | 2025-04-18 | 2025-07-18 | 100% | 2025-07-21 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-06-12 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-06-12 | 2025-05-09 | 2025-05-23 | 2025-07-18 | 100% | 2025-07-18 | 2025-06-02 | 2025-06-27 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-29 | 2025-07-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-07-21 | 2025-07-21 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-27 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1134 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-28 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-21 | 2025-07-21 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | B2B - OpenText | 2025-03-28 | 2025-06-13 | 2025-06-13 | MW |  |  |  |  | 0 |  | 2064 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 11/25 Impacted by defect 4956. Resolution in Progress 11/18 Defect 4657 created for Review comments. Resolution in Progress 11/14 Awaiting approval. FUT Approval ETA is 11/21 11/11 - Sent for approval 11/4 defects Resolved. Testing in Progress. ETA to share for approval by 11/5 10/27 Blocked by FUT defect 3864. | 2025-07-18 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-06-12 | 2025-06-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2735 | PTPI1128_IP | 02.Interface | 01.IP - Intel Product | Interface to send Ariba PO closure status information from S4 to Ariba | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB128D5E5-EA1D-44C9-BDA3-09BD8CECB129%7D&file=2735_PTP_PM-080-100_RICEFW_Interface%20to%20send%20PO%20closure%20status%20information%20from%20S4%20to%20Ariba.pptx&action=edit&mobileredirect=true |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 19569; 15206 | SAP Ariba Cloud; SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-03-03 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-15 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-06-09 | 2025-06-13 | 2025-06-11 | 100% | 2025-09-23 | 2025-06-09 | 2025-06-13 | 2025-06-11 | 100% | 2025-09-23 | [10 empty] | 2025-08-01 | 2025-08-25 | 2025-08-25 | 100% | 2025-08-25 | 2025-09-23 | 2025-09-23 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-08-25 | 2025-08-25 | jonsanders@deloitte.com | 2025-01-16 12:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-22 | 01.S4 |  |  | 1 | 1.45 | 1128 |  | R3 ITC1 | [6 empty] | 2025-03-15 | 2025-03-28 | 2025-03-15 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [9 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-23 | 2025-09-23 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 |  |  |  |  | Ariba | 2025-03-28 | 2025-06-13 | 2025-07-18 | S4 |  |  |  |  | 0 |  | 2061 | [7 empty] | 5. Not Dispositioned |  |  | 2025-08-25 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2735 | PTPI1128_IF | 02.Interface | 02.IF - Intel Foundry | Interface to send Ariba PO closure status information from S4 to Ariba | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB128D5E5-EA1D-44C9-BDA3-09BD8CECB129%7D&file=2735_PTP_PM-080-100_RICEFW_Interface%20to%20send%20PO%20closure%20status%20information%20from%20S4%20to%20Ariba.pptx&action=edit&mobileredirect=true |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 19569; 15206 | SAP Ariba Cloud; SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-03-03 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-15 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-06-09 | 2025-06-13 | 2025-06-11 | 100% | 2025-09-23 | 2025-06-09 | 2025-06-13 | 2025-06-11 | 100% | 2025-09-23 | [10 empty] | 2025-08-01 | 2025-08-25 | 2025-08-25 | 100% | 2025-08-25 | 2025-09-23 | 2025-09-23 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-08-25 | 2025-08-25 | jonsanders@deloitte.com | 2025-01-16 12:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-22 | 01.S4 | PTPI1128_IP | 03.Medium | 0.3 | 0.435 | 1128 |  | R3 ITC1 | [6 empty] | 2025-03-15 | 2025-03-28 | 2025-03-15 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [9 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-23 | 2025-09-23 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 |  |  |  |  | Ariba | 2025-03-28 | 2025-06-13 | 2025-07-18 | S4 |  |  |  |  | 0 |  | 2060 | [7 empty] | 5. Not Dispositioned |  |  | 2025-08-25 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2613 | PTPI1032 | 02.Interface | 02.IF - Intel Foundry | MQCS data pull Interface | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2613_RICEFW_QI-130-010_Interface_Pull%20MQCS%20Inteface%20data%20to%20SAP%20S4_%20IF.pptx?d=we0b18e9e75f34dfc958cd8f481f209f5&csf=1&web=1&e=JAD18A | 02.No | 01.Yes |  | 2024-12-18 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 1086 | Materials Quality Certification System | MQCS | S/4 | MULESOFT | 2025-03-17 | 2025-04-25 | 2025-04-15 | 100% | 2025-04-19 | 2025-06-27 | 2025-07-04 | 2025-11-05 | 100% | 2025-10-28 | 2025-08-01 | 2025-08-08 | 2025-08-08 | 100% | 2025-09-03 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-09-03 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-06 | 2025-07-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-11-06 | 2025-11-07 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1.45 | 1032 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-25 | 2025-04-19 |  | 2025-10-28 | 2025-11-05 | 2025-10-28 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-11-07 | 2025-11-06 | 2025-11-06 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-06 | 2025-11-07 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2025-04-25 | 2025-08-15 | 2025-08-15 | MW | 2025-11-26 |  | WIINGS |  | 0 |  | 1496 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change | 11/18 Issue with the FUT. Discussions with Business in Place of adding an enhancement 11/4 - Middleware is completing the TUT and will provide end points accordingly 10/22 - MW Build is in progress. Will receive a date today. | 2025-11-07 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | CR/Design change | Complete | R3 Build & UT Sprint 19 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 1761 | PTPI0825 | 02.Interface | 02.IF - Intel Foundry | Get Purchase Group details from IF to CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/TBD-Deloitte-0024_PTP_CWB_Get%20Purchase%20Group%20details%20from%20IF%20to%20CWB.pptx?d=w96dd7bf1a5644be9910867a04cad0b44&csf=1&web=1&e=MOXUOz | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 22233 | Commercial Workbench | S/4 | CWB | MULESOFT | 2024-11-18 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-28 | 2025-03-07 | 2025-02-28 | 100% | 2025-02-03 | 2025-02-28 | 2025-03-07 | 2025-02-28 | 100% | 2025-02-03 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-04 | 2025-10-17 | 2025-10-17 | 100% | 2025-09-11 | 2025-03-28 | 2025-09-11 |  |  | 2025-03-10 | 2025-03-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-03 | 2025-03-17 | 2025-03-17 | N | 100% | 2025-03-11 | Not Applicable | R3 Build & UT Sprint 11 | 2025-04-18 | 2025-10-17 | 2025-10-17 | pgaroo@deloitte.com | 2024-10-25 10:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 0.5 | 0.725 | 0825 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-03 | 2025-03-07 | 2025-02-03 | 2025-02-03 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-18 | 2025-03-28 | 2025-03-28 |  | 2025-10-17 | 2025-09-11 | 2025-09-11 | 2025-03-28 | 2025-09-11 |  |  | 2025-03-11 | 2025-03-17 | 2025-03-11 | [5 empty] | 2024-12-13 | 2025-03-07 | 2025-01-24 | MW | 2025-08-01 |  |  |  | 0 | 08. Not Applicable | 2134 | [10 empty] | 2025-10-17 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-03-07 | 2025-02-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1845 | PTPI0823 | 02.Interface | 02.IF - Intel Foundry | Get Purchase Req Details from IF to CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-070-080-0006_PTP_CWB_Get%20PR%20details%20from%20IF%20to%20CWB.pptx?d=we015b197e20f4d4797e1f4f4ca66a3b7&csf=1&web=1&e=oyYq9c | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 22233 | Commercial Workbench | S/4 | CWB | APIGEE | 2024-11-18 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-28 | 2025-03-07 | 2025-02-28 | 100% | 2025-02-10 | 2025-02-28 | 2025-03-07 | 2025-02-28 | 100% | 2025-02-10 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-05-03 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-03-19 | 2025-05-16 |  |  | 2025-03-10 | 2025-03-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-03-17 | N | 100% | 2025-03-11 | Not Applicable | R3 Build & UT Sprint 11 | 2025-03-21 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-10-25 10:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0823 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-10 | 2025-03-07 | 2025-02-10 | 2025-02-10 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-03-19 | 2025-05-16 |  |  | 2025-03-11 | 2025-04-18 | 2025-03-11 | [5 empty] | 2024-12-13 | 2025-03-07 | 2025-01-24 | MW | 2025-08-01 |  |  |  | 0 | 08. Not Applicable | 2162 | [10 empty] | 2025-05-16 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-03-07 | 2025-02-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1877 | PTPI0822_IP | 02.Interface | 01.IP - Intel Product | Ariba Invoice Integration through (CIG - Cloud Integration Gateway (Currently – Managed Gateway for Spend & Network – Buyer)] | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0001%20PTP%20Invoice%20Integration%20through%20CIG.pptx?d=wf15d7d19062e4f45bf8b38a9b3aa023d&csf=1&web=1&e=jKFlyk | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | SAP Ariba Network | S/4 | NA | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-11-28 | 100% | 2025-11-21 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2026-01-09 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2026-01-09 | [10 empty] | 2025-10-28 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2026-01-09 | 2026-01-09 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-08 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-10-25 10:21 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0822 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-02-19 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2026-01-09 | 2026-01-09 |  |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  |  |  |  | Ariba | 2025-03-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1689 | [7 empty] | 1. On Track | 14. B-App Under Test | 11/4 Facing Readsoft Issue at Tax side. ETA 11/4 10/27: FUT is in progress. 10/17: FUT is in progress. 10/10: End to End FUT is planned in Sprint 19. Needs to update date in Object tracker. 9/29: Needs to update dates for this FUT. Team will plan this FUT in Sprint 19. | 2025-11-07 | Y | 06. PTP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2026-01-09 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes | 2026-03-13 | 2026-03-04 | 2026-02-26 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1877 | PTPI0822_IF | 02.Interface | 02.IF - Intel Foundry | Ariba Invoice Integration through (CIG - Cloud Integration Gateway (Currently – Managed Gateway for Spend & Network – Buyer)] | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0001%20PTP%20Invoice%20Integration%20through%20CIG.pptx?d=wf15d7d19062e4f45bf8b38a9b3aa023d&csf=1&web=1&e=jKFlyk | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | SAP Ariba Network | S/4 | NA | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-11-28 | 100% | 2025-11-21 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2026-01-09 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2026-01-09 | [10 empty] | 2025-10-28 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2026-01-09 | 2026-01-09 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-08 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-10-25 10:21 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 | 2024-11-01 | 01.S4 | PTPI0822_IP | 03.Medium | 0.3 | 0.435 | 0822 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-03-21 | 2025-02-19 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2026-01-09 | 2026-01-09 |  |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  |  |  |  | Ariba | 2025-03-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1688 | [7 empty] | 1. On Track | 14. B-App Under Test | 11/4 Facing Readsoft Issue at Tax side. ETA 11/4 10/27: FUT is in progress. 10/17: FUT is in progress. 10/10: End to End FUT is planned in Sprint 19. Needs to update date in Object tracker. 9/29: Needs to update dates for this FUT. Team will plan this FUT in Sprint 19. | 2025-11-07 | Y | 06. PTP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2026-01-09 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 1878 | PTPI0821_IP | 02.Interface | 01.IP - Intel Product | Invoice Status Update from SAP S/4 to Ariba Network through CIG - Cloud Integration Gateway (Currently – Managed Gateway for Spend& Network – Buyer) | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0002%20PTP%20Invoice%20Status%20update%20through%20CIG.pptx?d=w379d1652c4524bc69a508c483ae3a8c4&csf=1&web=1&e=H4Caou | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-02-24 | 2025-03-21 | 2025-03-15 | 100% | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-11-13 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-11-13 | [10 empty] | 2025-10-25 | 2025-11-14 | 2025-11-14 | 100% | 2025-11-14 | 2025-11-13 | 2025-11-14 |  | 2025-11-14 | 2025-11-28 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-18 | 2025-11-14 | 2025-11-14 | pgaroo@deloitte.com | 2024-10-25 10:21 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0821 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [9 empty] | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-13 | 2025-11-14 |  |  | 2025-11-26 | 2025-12-05 | 2025-11-26 |  |  |  |  | Ariba | 2025-03-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1691 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24 Awaiting approval from Intel (Andrea) 11/18 Reminder Dropped for approval 11/12 Submitted for approval. Approval Expected by 11/14 | 2025-11-14 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1878 | PTPI0821_IF | 02.Interface | 02.IF - Intel Foundry | Invoice Status Update from SAP S/4 to Ariba Network through CIG - Cloud Integration Gateway (Currently – Managed Gateway for Spend& Network – Buyer) | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0002%20PTP%20Invoice%20Status%20update%20through%20CIG.pptx?d=w379d1652c4524bc69a508c483ae3a8c4&csf=1&web=1&e=H4Caou | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-02-24 | 2025-03-21 | 2025-03-15 | 100% | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-11 | 2025-04-18 | 2025-05-15 | 100% | 2025-11-13 | 2025-04-11 | 2025-04-18 | 2025-05-15 | 100% | 2025-11-13 | [10 empty] | 2025-10-25 | 2025-11-14 | 2025-11-14 | 100% | 2025-11-14 | 2025-11-13 | 2025-11-14 |  | 2025-11-14 | 2025-11-28 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-18 | 2025-11-14 | 2025-11-14 | pgaroo@deloitte.com | 2024-10-25 10:21 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 | 2024-11-01 | 01.S4 | PTPI0821_IP | 03.Medium | 0.3 | 0.435 | 0821 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [9 empty] | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-13 | 2025-11-14 |  |  | 2025-11-26 | 2025-12-05 | 2025-11-26 |  |  |  |  | Ariba | 2025-03-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1690 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24 Awaiting approval from Intel (Andrea) 11/18 Reminder Dropped for approval 11/12 Submitted for approval. Approval Expected by 11/14 | 2025-11-14 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 1882 | PTPI0820_IP | 02.Interface | 01.IP - Intel Product | Carbon Copy Invoice Integration from SAP S/4 to Ariba Network | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0006%20PTP%20Carbon%20Copy%20Invoice%20Integration.pptx?d=w217b3f88361d40a7b9b8a051667651f1&csf=1&web=1&e=iA9K59 | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-03-24 | 2025-04-18 | 2025-03-21 | 100% | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2026-01-07 | 100% | 2025-12-18 | 2025-05-02 | 2025-05-16 | 2025-08-13 | 100% | 2025-10-02 | 2025-05-02 | 2025-05-16 | 2025-08-13 | 100% | 2025-10-02 | [10 empty] | 2025-10-28 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-10-02 | 2025-11-07 |  | 2025-08-29 | 2025-09-08 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-04-01 02:19 | 10 | 2024-11-19 | 01.S4 |  |  | 1 | 1.45 | 0820 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-04-18 | 2025-03-19 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-10-02 | 2025-11-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | Ariba | 2025-04-18 | 2025-05-16 | 2025-05-16 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1693 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 FUT submitted for approval on 11/3. 10/27: FUT is reviewed with Business and Intel IT on 10/24. Call is scheduled for open related to Bill to address on 10/27. 10/17: FUT is dependent upon PTPE1422_IP and IF. Once defect is resolved for PTPE1422_IP and IF, we will able to perform this FUT. 10/10: Team is targeting to close this FUT by Sprint 19 along with approval planned in sprint 19. This object is dependent upon Bill to address mapping to Standard IDOC [PTPE1422_IP & IF]. 9/29: Due to ReadSoft implementation, we are not able to route Ariba invoices to ReadSoft and also, we are unable to post CC invoice in S4 system. Checking with ReadSoft Team. This FUT approval is planned for Sprint 19. | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-02 | 2025-10-02 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-05 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1882 | PTPI0820_IF | 02.Interface | 02.IF - Intel Foundry | Carbon Copy Invoice Integration from SAP S/4 to Ariba Network | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-030-0006%20PTP%20Carbon%20Copy%20Invoice%20Integration.pptx?d=w217b3f88361d40a7b9b8a051667651f1&csf=1&web=1&e=iA9K59 | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2025-03-24 | 2025-04-18 | 2025-03-21 | 100% | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2026-01-07 | 100% | 2025-12-18 | 2025-05-09 | 2025-05-16 | 2025-08-13 | 100% | 2025-10-02 | 2025-05-09 | 2025-05-16 | 2025-08-13 | 100% | 2025-10-02 | [10 empty] | 2025-10-28 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-10-02 | 2025-11-07 |  | 2025-08-29 | 2025-09-08 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-04-01 02:19 | 10 | 2024-11-01 | 01.S4 | PTPI0820_IP | 03.Medium | 0.3 | 0.435 | 0820 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-04-18 | 2025-03-19 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-10-02 | 2025-11-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | Ariba | 2025-04-18 | 2025-05-16 | 2025-05-16 | S4 | 2025-08-22 |  |  |  | 0 | 08. Not Applicable | 1692 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 FUT submitted for approval on 11/3. 10/27: FUT is reviewed with Business and Intel IT on 10/24. Call is scheduled for open related to Bill to address on 10/27. 10/17: FUT is dependent upon PTPE1422_IP and IF. Once defect is resolved for PTPE1422_IP and IF, we will able to perform this FUT. 10/10: Team is targeting to close this FUT by Sprint 19 along with approval planned in sprint 19. This object is dependent upon Bill to address mapping to Standard IDOC [PTPE1422_IP & IF]. 9/29: Due to ReadSoft implementation, we are not able to route Ariba invoices to ReadSoft and also, we are unable to post CC invoice in S4 system. Checking with ReadSoft Team. This FUT approval is planned for Sprint 19. | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2091 | PTPI0819_IP | 02.Interface | 01.IP - Intel Product | Intel B2B – XML (3C7) Notify of Self Billing Invoice – Interface to send notification of Self-Billing Invoice (3C7) data to Supplier from EDW | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-000-000-0000_B2B_Intel_XML_Invoice_SelfBilling_PTP%20-%20Copy.pptx?d=weda53852991340da897e7048d5772a9b&csf=1&web=1&e=I4ObRS | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-11-25 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-16 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-17 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-26 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-26 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-21 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-08-26 | 2025-08-26 |  | 2025-09-19 | 2025-09-26 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-16 | 2025-10-08 | 2025-10-09 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0819 |  | R3 ITC1 | [6 empty] | 2024-12-16 | 2024-12-16 | 2024-12-16 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-08-26 | 2025-08-26 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | B2B - OpenText | 2024-12-13 | 2025-03-21 | 2025-01-24 | S4 | 2025-06-20 |  |  |  | 0 |  | 1898 | [9 empty] | We need to replan this FUT in Sprint 17 as development is still in progress. In forecasted plan- we included this FUT for Sprint 17. | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | Yes | We need to check Payload transfer to Stagging DB [Company Code data] | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2091 | PTPI0819_IF | 02.Interface | 02.IF - Intel Foundry | Intel B2B – XML (3C7) Notify of Self Billing Invoice – Interface to send notification of Self-Billing Invoice (3C7) data to Supplier from EDW | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-000-000-0000_B2B_Intel_XML_Invoice_SelfBilling_PTP%20-%20Copy.pptx?d=weda53852991340da897e7048d5772a9b&csf=1&web=1&e=I4ObRS | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-11-25 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-16 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-17 | 2025-03-14 | 2025-03-21 | 2025-05-02 | 100% | 2025-09-12 | 2025-03-14 | 2025-03-21 | 2025-05-02 | 100% | 2025-09-12 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-05-23 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-09-12 | 2025-09-12 |  | 2025-09-19 | 2025-09-26 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-16 | 2025-10-08 | 2025-10-09 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 | PTPI0819_IP | 03.Medium | 0.3 | 0.435 | 0819 |  | R3 ITC1 | [6 empty] | 2024-12-16 | 2024-12-16 | 2024-12-16 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-09-12 | 2025-09-12 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | B2B - OpenText | 2024-12-13 | 2025-03-21 | 2025-01-24 | S4 | 2025-06-20 |  |  |  | 0 |  | 1897 | [9 empty] | We need to replan this FUT in Sprint 17 as development is still in progress. In forecasted plan- we included this FUT for Sprint 17. | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2466 | PTPI0817_IP | 02.Interface | 01.IP - Intel Product | Purchasing Services Fiori Catalog | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_FIORI_Purchasing_Services_Catalog.pptx?d=wff8012658ccc4ce2a3024adf0ba06137&csf=1&web=1&e=naTutB | 01.Yes | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 02.No | NA | NA | S/4 | Shopping@Intel | NA | 2025-02-24 | 2025-03-21 | 2025-03-18 | 100% | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-10-02 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 03:49 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-19 | 01.S4 |  |  | 1 | 1.45 | 0817 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-21 | 2025-03-11 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2025-03-21 | 2025-04-18 | 2025-03-21 |  | 2025-07-31 |  |  |  | 0 | 08. Not Applicable | 1884 | [7 empty] | 1. On Track | 8. Blocked by CR/Design change | 12/10 New CR created for additional logics to be added. CR approval in Progress. 11/18 To be Cancelled 11/11 - CR1354 created for cancellation 10/22 - CR1354 created for cancellation | 2025-04-18 | N | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2466 | PTPI0817_IF | 02.Interface | 02.IF - Intel Foundry | Purchasing Services Fiori Catalog | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_FIORI_Purchasing_Services_Catalog.pptx?d=wff8012658ccc4ce2a3024adf0ba06137&csf=1&web=1&e=naTutB | 01.Yes | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 02.No | NA | NA | S/4 | Shopping@Intel | NA | 2025-02-24 | 2025-03-21 | 2025-03-18 | 100% | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2025-10-02 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 03:49 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-01 | 01.S4 | PTPI0817_IP | 03.Medium | 0.3 | 0.435 | 0817 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-21 | 2025-03-11 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2025-03-21 | 2025-04-18 | 2025-03-21 |  | 2025-07-31 |  |  |  | 0 | 08. Not Applicable | 1883 | [7 empty] | 1. On Track | 8. Blocked by CR/Design change | 12/10 New CR created for additional logics to be added. CR approval in Progress. 11/18 To be Cancelled 11/11 - CR1354 created for cancellation 10/22 - CR1354 created for cancellation | 2025-04-18 | N | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2093 | PTPI0816_IP | 02.Interface | 01.IP - Intel Product | Intel WebSuite - Web PO – Interface to display Purchase Order information from B2B Staging DB ePO from S4 IF/IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PTP%20B-App%20RICEFW%20Requests/PM-080-060-1010_SPS_Intel_Web_PO_PTP.pptx?d=w7c22917b10d142069ddfe36d41c70810&csf=1&web=1&e=Oc2MRe | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 829; 24834 | Intel WebSuite - Web PO; B2B Staging Database | Stagging DB | S/4 | MULESOFT | 2025-04-01 | 2025-04-30 | 2025-04-15 | 100% | 2025-04-15 | 2025-07-18 | 2025-07-25 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-29 | 2025-08-29 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-29 | 2025-08-29 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-02 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes | 2025-09-22 | 2025-11-24 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0816 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-30 |  |  | 2025-07-21 | 2025-07-25 | 2025-07-21 |  | 2025-07-21 | 2025-08-29 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 |  | 2025-07-11 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  |  |  |  | B2B - Intel WebSuite | 2025-04-30 | 2025-08-29 | 2025-08-15 | S4 | 2025-09-04 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 1549 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-12-05 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-29 | 2025-07-21 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-03 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2093 | PTPI0816_IF | 02.Interface | 02.IF - Intel Foundry | Intel WebSuite - Web PO – Interface to display Purchase Order information from B2B Staging DB ePO from S4 IF/IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PTP%20B-App%20RICEFW%20Requests/PM-080-060-1010_SPS_Intel_Web_PO_PTP.pptx?d=w7c22917b10d142069ddfe36d41c70810&csf=1&web=1&e=Oc2MRe | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 829; 24834 | Intel WebSuite - Web PO; B2B Staging Database | Stagging DB | S/4 | MULESOFT | 2025-04-01 | 2025-04-30 | 2025-04-15 | 100% | 2025-04-15 | 2025-07-18 | 2025-07-25 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-02 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes | 2025-09-22 | 2025-11-24 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 03:49 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-11-01 | 01.S4 | PTPI0816_IP | 03.Medium | 0.3 | 0.435 | 0816 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-30 |  |  | 2025-07-21 | 2025-07-25 | 2025-07-21 |  | 2025-07-21 | 2025-08-29 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 |  | 2025-07-11 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  |  |  |  | B2B - Intel WebSuite | 2025-04-30 | 2025-08-29 | 2025-08-15 | S4 | 2025-10-17 |  | WIINGS |  | 0 | 01.10 Suppliers - WebSuite | 1548 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-12-05 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-29 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2097 | PTPI0812_IP | 02.Interface | 01.IP - Intel Product | Intel WebSuite - Web Forecast – Interface to display Purchase Order information from B2B Staging DB ePO from S4 and Blue Yonder (S4 ECC and S4 SCM) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-099-SPS_Intel_WebForecast_PTP%20-%20Copy.pptx?d=w50e32ea5cc73434a8510336f7a84d6bd&csf=1&web=1&e=UtYyGn | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 1638; 24834 | Intel WebSuite - Web Forecast; B2B Staging Database | Intel WebSuite Web Contract | S/4 | MULESOFT | 2025-03-17 | 2025-04-18 | 2025-04-15 | 100% | 2025-04-15 | 2025-07-04 | 2025-07-11 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes | 2025-09-22 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0812 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 |  | 2025-07-11 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 |  |  |  |  | B2B - Intel WebSuite | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 | 2025-10-03 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 1553 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 11/11 - Smartsheet update pending 11/4 FUT submitted for approval on 10/31. Awaiting approval 10/27 FUT in progress as we have initiated FUT for 816 as well ahead in this S19 10/22 - Dependency with 816. | 2025-11-07 | Y | 06. PTP |  |  |  | 5.1 Complete. Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-15 | 2025-07-21 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2097 | PTPI0812_IF | 02.Interface | 02.IF - Intel Foundry | Intel WebSuite - Web Forecast – Interface to display Purchase Order information from B2B Staging DB ePO from S4 and Blue Yonder (S4 ECC and S4 SCM) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-099-SPS_Intel_WebForecast_PTP%20-%20Copy.pptx?d=w50e32ea5cc73434a8510336f7a84d6bd&csf=1&web=1&e=UtYyGn | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 1638; 24834 | Intel WebSuite - Web Forecast; B2B Staging Database | Intel WebSuite Web Contract | S/4 | MULESOFT | 2025-03-17 | 2025-04-18 | 2025-04-15 | 100% | 2025-04-15 | 2025-07-04 | 2025-07-11 | 2025-07-04 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-10-31 | 2025-07-21 | 2025-10-31 | Yes | 2025-09-22 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 03:49 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-11-01 | 01.S4 | PTPI0812_IP | 03.Medium | 0.3 | 0.435 | 0812 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 |  | 2025-07-11 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-07 | 2025-10-31 | 2025-10-31 | 2025-07-21 | 2025-10-31 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 |  |  |  |  | B2B - Intel WebSuite | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 | 2025-10-03 |  | WIINGS |  | 0 | 01.10 Suppliers - WebSuite | 1552 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 11/11 - Smartsheet update pending 11/4 FUT submitted for approval on 10/31. Awaiting approval 10/27 FUT in progress as we have initiated FUT for 816 as well ahead in this S19 10/22 - Dependency with 816. | 2025-11-07 | Y | 06. PTP |  |  |  | 5.1 Complete. Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2304 | PTPI0735_IP | 02.Interface | 01.IP - Intel Product | Ariba/Capital PO details to be retrieved from SAP S/4 at the time of receiving in WIINGS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/RICEFW_Interface_S4_WIINGS_PO%20details.pptx?d=w4d96d28562964599b0190bb96eb1f87c&csf=1&web=1&e=E6Q4QY | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 10821 | Wiings on the Web (WOW) - WIINGS (Angular) | WIINGS | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-02-28 | 2025-03-07 | 2025-04-18 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-04 | 2025-03-07 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-04 | 2025-02-24 | 2025-03-21 | 2025-05-16 | 100% | 2025-05-16 | 2025-03-24 | 2025-04-18 | 2025-05-09 | 100% | 2025-08-04 | 2025-01-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-12-05 | 2025-08-04 | 2025-12-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1.45 | 0735 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-04 | 2025-04-04 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-08-04 | 2025-12-05 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | WIINGS | 2025-02-21 | 2025-03-21 | 2025-03-21 | MW | 2025-07-04 |  |  |  | 0 | 01.1 Supplier -Capital | 2119 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/10 Awaiting screenshots from B-app WIINGS for IT to provide approval 12/3 FUT submitted for approval on 12/2 11/24 FUT in Progress. Awaiting WIINGS confirmation. Planned to be submitted for approval by 11/28 11/12 - FUT in Progress. | 2025-11-07 | N | 06. PTP |  |  |  |  | ETA - 1203 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-04-04 | 2025-04-04 | Yes | Mapping changes for plant | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2304 | PTPI0735_IF | 02.Interface | 02.IF - Intel Foundry | Ariba/Capital PO details to be retrieved from SAP S/4 at the time of receiving in WIINGS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/RICEFW_Interface_S4_WIINGS_PO%20details.pptx?d=w4d96d28562964599b0190bb96eb1f87c&csf=1&web=1&e=E6Q4QY | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 10821 | Wiings on the Web (WOW) - WIINGS (Angular) | WIINGS | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-02-28 | 2025-03-07 | 2025-04-18 | 100% | 2025-08-04 | 2025-03-14 | 2025-03-21 | 2025-04-02 | 100% | 2025-04-02 | 2025-03-14 | 2025-03-21 | 2025-04-02 | 100% | 2025-04-02 | 2025-02-24 | 2025-03-21 | 2025-05-16 | 100% | 2025-05-16 | 2025-03-24 | 2025-04-18 | 2025-05-09 | 100% | 2025-08-04 | 2025-01-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-12-05 | 2025-08-04 | 2025-12-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-17 | 01.S4 | PTPI0735_IP | 03.Medium | 0.3 | 0.435 | 0735 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-02 | 2025-04-02 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-08-04 | 2025-12-05 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | WIINGS | 2025-02-21 | 2025-03-21 | 2025-03-21 | MW | 2025-07-04 |  |  |  | 0 | 01.1 Supplier -Capital | 2118 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/10 Awaiting screenshots from B-app WIINGS for IT to provide approval 12/3 FUT submitted for approval on 12/2 11/24 FUT in Progress. Awaiting WIINGS confirmation. Planned to be submitted for approval by 11/28 11/12 - FUT in Progress. | 2025-11-07 | N | 06. PTP |  |  |  |  | ETA - 1203 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-04-02 | 2025-04-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2246 | PTPI0710_IP | 02.Interface | 01.IP - Intel Product | S4 Manual Invoice Release Blocking functionality requires connection with GTT – Custom Tracker (.NET in-House Solution) | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-020-0001%20PTP%20Invoice%20Manual%20Release%20Integration%20through%20GTT%20Solution.pptx?d=wc4c2d495da1747f2a4e10efed3e328d4&csf=1&web=1&e=KM0Dhr&isSPOFile=1 | 02.No | 01.Yes |  | 2024-10-09 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 10451; 42860 | SAP ECC - Accounts Payable; Customs Tracker | S/4 | GTT (Custom Tracker) | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-04-04 | 2025-04-11 | 2025-09-26 | 100% | 2025-09-16 | 2025-05-02 | 2025-05-16 | 2025-08-08 | 100% | 2025-09-10 | 2025-06-09 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-10 | [10 empty] | 2025-08-08 | 2025-08-25 | 2025-08-25 | 100% | 2025-08-25 | 2025-09-10 | 2025-09-10 |  | 2025-09-19 | 2025-09-26 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-03 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-08-25 | 2025-08-25 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-10 | 01.S4 |  |  | 1 | 1.45 | 0710 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | [9 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-10 | 2025-09-10 |  |  | 2025-10-03 | 2025-10-09 | 2025-10-03 |  |  |  |  | Trade Apps | 2025-02-21 | 2025-05-16 | 2025-05-16 | S4 | 2025-09-19 |  |  |  | 0 | 08. Not Applicable | 2295 | [10 empty] | 2025-08-25 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2246 | PTPI0710_IF | 02.Interface | 02.IF - Intel Foundry | S4 Manual Invoice Release Blocking functionality requires connection with GTT – Custom Tracker (.NET in-House Solution) | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-020-0001%20PTP%20Invoice%20Manual%20Release%20Integration%20through%20GTT%20Solution.pptx?d=wc4c2d495da1747f2a4e10efed3e328d4&csf=1&web=1&e=KM0Dhr&isSPOFile=1 | 02.No | 01.Yes |  | 2024-10-09 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 10451; 42860 | SAP ECC - Accounts Payable; Customs Tracker | S/4 | GTT (Custom Tracker) | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-04-04 | 2025-04-11 | 2025-09-26 | 100% | 2025-09-16 | 2025-05-09 | 2025-05-16 | 2025-08-08 | 100% | 2025-09-10 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-10 | [10 empty] | 2025-08-08 | 2025-08-25 | 2025-08-25 | 100% | 2025-08-25 | 2025-09-10 | 2025-09-10 |  | 2025-09-19 | 2025-09-26 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-03 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-08-25 | 2025-08-25 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-10 | 01.S4 | PTPI0710_IP | 03.Medium | 0.3 | 0.435 | 0710 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | [9 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-09-10 | 2025-09-10 |  |  | 2025-10-03 | 2025-10-09 | 2025-10-03 |  |  |  |  | Trade Apps | 2025-02-21 | 2025-05-16 | 2025-05-16 | S4 | 2025-09-19 |  |  |  | 0 | 08. Not Applicable | 2294 | [10 empty] | 2025-08-25 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2282 | PTPI0709_IP | 02.Interface | 01.IP - Intel Product | Ariba Asset Settlement Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Interface_Ariba_Asset_Settlement.pptx?d=w536d3552c128402c8670e7dac10ca4e3&csf=1&web=1&e=uqXwnX | 01.Yes | 01.Yes | PTPE0730_IP | 2024-10-09 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | Shopping@Intel | S/4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-03-07 | 2025-03-14 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-11 | 2025-04-18 | 2025-06-11 | 100% | 2025-12-02 | 2025-04-11 | 2025-04-18 | 2025-06-11 | 100% | 2025-12-02 | [10 empty] | 2025-10-01 | 2025-11-07 | 2025-11-07 | 100% | 2026-01-05 | 2025-12-02 | 2026-01-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-10 | 01.S4 |  |  | 1 | 1.45 | 0709 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | [9 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-02 | 2026-01-05 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 |  |  |  |  | Ariba | 2025-02-21 | 2025-04-18 | 2025-06-27 | S4 | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 2445 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/19- Send for approval awaiting issues were there 12/17- Waiting approval sent on 12th 12/12 : Will be send by tomorrow 12/11 Response received from Ariba. Resolution in progress with Tech Team 12/3 Awaiting SAP Inputs on Ariba Internal Error. ETA 12/4 11/24 Impacted by defect 4883 11/18 Defect with FPR and Tech Team 2208 awaiting resolution | 2025-11-07 | N | 06. PTP |  |  |  | 1216:FUT completed and sent for approval Current Status: SR# for Ariba issue to be escalated SAP Ariba SR #1433805/2025. SR got a response from Ariba Issue: FUT is now completed. Asset interface is failing to update the PR in Ariba, giving an internal error Next Steps: FUT Awaiting approval. Help needed: NA | 1125: SR# for Ariba issue to be escalated FPRE0783_IF Defect 2208 and 4716, 4614 (Keerti to priortize fix) | 5. Review Closed | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-02 | 2025-12-02 | Yes | Mapping changes for plant | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-06 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2282 | PTPI0709_IF | 02.Interface | 02.IF - Intel Foundry | Ariba Asset Settlement Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Interface_Ariba_Asset_Settlement.pptx?d=w536d3552c128402c8670e7dac10ca4e3&csf=1&web=1&e=uqXwnX | 01.Yes | 01.Yes | PTPE0730_IF | 2024-10-09 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15205 | Shopping@Intel | Shopping@Intel | S/4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-03-07 | 2025-03-14 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-11 | 2025-04-18 | 2025-06-11 | 100% | 2025-12-02 | 2025-04-11 | 2025-04-18 | 2025-06-11 | 100% | 2025-12-02 | [10 empty] | 2025-10-01 | 2025-11-07 | 2025-11-07 | 100% | 2026-01-05 | 2025-12-02 | 2026-01-05 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-10 | 01.S4 | PTPI0709_IP | 03.Medium | 0.3 | 0.435 | 0709 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | [9 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-02 | 2026-01-05 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 |  |  |  |  | Ariba | 2025-02-21 | 2025-04-18 | 2025-06-27 | S4 | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 2444 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/19- Send for approval awaiting issues were there 12/17- Waiting approval sent on 12th 12/12 : Will be send by tomorrow 12/11 Response received from Ariba. Resolution in progress with Tech Team 12/3 Awaiting SAP Inputs on Ariba Internal Error. ETA 12/4 11/24 Impacted by defect 4883 11/18 Defect with FPR and Tech Team 2208 awaiting resolution | 2025-11-07 | N | 06. PTP |  |  |  | 1216:FUT completed and sent for approval Current Status: SR# for Ariba issue to be escalated SAP Ariba SR #1433805/2025. SR got a response from Ariba Issue: FUT is now completed. Asset interface is failing to update the PR in Ariba, giving an internal error Next Steps: FUT Awaiting approval. Help needed: NA | 1125: SR# for Ariba issue to be escalated FPRE0783_IF Defect 2208 and 4716, 4614 (Keerti to priortize fix) | 5. Review Closed | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-02 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1664 | PTPI0692_IP | 02.Interface | 01.IP - Intel Product | Custom program to send configurations from S4 system to Illumis | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2025-01-02 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-17 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-09-23 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-09-23 | 2025-09-23 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-10-04 08:37 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0692 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2025-01-24 | 2024-12-17 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-23 | 2025-09-23 |  |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-05-02 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1758 | [9 empty] | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1664 | PTPI0692_IF | 02.Interface | 02.IF - Intel Foundry | Custom program to send configurations from S4 system to Illumis | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2025-01-02 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-17 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-28 | 2025-03-07 | 2025-05-02 | 100% | 2025-08-04 | 2025-02-28 | 2025-03-07 | 2025-05-02 | 100% | 2025-08-04 | 2025-11-03 | 2025-11-07 | 2026-01-07 | 100% | 2026-01-07 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-09-23 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-09-23 | 2025-09-23 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-10-04 08:39 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 | PTPI0692_IP | 03.Medium | 0.3 | 0.435 | 0692 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2025-01-24 | 2024-12-17 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2026-01-07 |  | 2026-01-07 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-23 | 2025-09-23 |  |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-05-02 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1757 | [7 empty] | 5. Not Dispositioned |  | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1664 | PTPI0691_IP | 02.Interface | 01.IP - Intel Product | Custom program to send the supplier master data from S4 system to Illumis. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2025-01-02 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-17 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-10-07 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-10-07 | 2025-10-07 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-10-04 08:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0691 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2025-01-24 | 2024-12-17 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-10-07 | 2025-10-07 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-05-02 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1760 | [9 empty] | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | Yes | Illumis Interface testing | Yes |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1664 | PTPI0691_IF | 02.Interface | 02.IF - Intel Foundry | Custom program to send the supplier master data from S4 system to Illumis. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2025-01-02 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-17 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-28 | 2025-03-07 | 2025-05-02 | 100% | 2025-08-04 | 2025-02-28 | 2025-03-07 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-10-07 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-10-07 | 2025-10-07 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-10-04 08:34 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 | PTPI0691_IP | 03.Medium | 0.3 | 0.435 | 0691 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2025-01-24 | 2024-12-17 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-10-07 | 2025-10-07 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-05-02 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1759 | [9 empty] | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1664 | PTPI0685 | 02.Interface | 05.CFIN | Custom program to send the Transactions (Invoices) from IF system to Illumis | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2025-01-02 | 2025-01-24 | 2025-08-08 | 100% | 2025-08-19 | 2025-01-24 | 2025-01-31 | 2025-09-26 | 100% | 2025-09-16 | 2025-02-28 | 2025-03-07 | 2025-08-08 | 100% | 2025-08-01 | 2025-02-28 | 2025-03-07 | 2025-08-08 | 100% | 2025-08-01 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-11-08 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-11-08 | 2025-11-08 |  | 2025-12-20 | 2026-01-03 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-10-04 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0685 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-01 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-11-08 | 2025-11-08 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-08-25 |  | 2026-01-09 |  |  |  | 0 | 08. Not Applicable | 1755 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/5 Defect ID 5981 created and assigned to tech Team. ETA to complete FUT is 1/6 and FUT walkthrough on 1/7 for getting approval. 12/19: FUT is in progress. ETA: 12/22 12/17: FUT is in progress. 12/12: FUT is in progress. 10/10 :Initially for sending the Transactions (Invoices) from IP and IF system to Illumis, we created PTPI0685_IP and PTPI0685_IF. But right place for this development is CFIN system. PTP- EP team want to rename one existing object into CFIN object and the other one to be cancelled. Functionality and requirement from business standpoint remain the same. So team planned CFIN FS approval in Sprint 16. We will plan FUT in Sprint 21 after development. | 2025-09-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-08 | 2025-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2111 | PTPI0671 | 02.Interface | 02.IF - Intel Foundry | Interface to automatically create VMI PO & IB delivery in S/4 (IF and IP) via approved Interface PTPI0368 and send the response to E2Open​ | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2111_PM-080-210-0005_PTP_RICEFW_Interface%20to%20send%20the%20response%20for%20PTPI0368(VMI%20PO%20and%20IBD%20creation).pptx?d=w3b299d3222ff46c68d29e04cb5883162&csf=1&web=1&e=2Pu90Z | 01.Yes | 01.Yes |  | 2024-09-25 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-12-16 | 2025-01-24 | 2024-11-15 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-06-11 | 100% | 2025-06-11 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-10 | 2025-09-08 | 2025-09-08 | 100% | 2025-09-23 | 2025-08-04 | 2025-09-23 |  | 2025-07-15 | 2025-09-25 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-10 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-30 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-09-08 | 2025-09-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-10-02 | 01.S4 |  |  | 2 | 2.9 | 0671 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-11 |  | 2025-06-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-08-04 | 2025-09-23 |  |  | 2025-09-30 | 2025-10-08 | 2025-09-30 |  |  |  |  | B2B - E2open | 2025-01-24 | 2025-04-18 | 2025-03-21 |  | 2025-10-08 |  | WIINGS |  | 0 | 01.4 Suppliers that engage with E2Open | 2781 | [10 empty] | 2025-09-08 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 1981 | PTPI0568 | 02.Interface | 02.IF - Intel Foundry | Maintain Purchasing Info Record in IF from Pega PSI | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040_PTP_Pega%20PSI_Get%20Purchasing%20Info%20Record%20details%20from%20IF%20to%20Pega%20PSI.pptx?d=w8c594a8b9eaa4558a5bea77625c15be8&csf=1&web=1&e=mCOZyo | 02.No | 01.Yes |  | 2024-08-26 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 17296 | Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI | PEGA PSI | S/4 | APIGEE | 2024-09-13 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-11-01 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2024-12-20 | 100% | 2024-12-18 | 2025-01-27 | 2025-02-21 | 2024-12-20 | 100% | 2024-12-18 | 2024-12-16 | 2025-01-18 | 2024-10-25 | 100% | 2024-10-25 | 2024-12-16 | 2025-01-24 | 2024-12-27 | 100% | 2024-12-06 | 2025-06-02 | 2025-12-05 | 2025-12-05 | 100% | 2025-12-05 | 2024-12-18 | 2025-12-05 |  | 2025-07-15 | 2024-11-29 | 2024-12-06 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2024-12-06 | 2024-12-09 | 2024-12-06 | N | 100% | 2024-12-09 | Not Applicable | R3 Build & UT Sprint 8 | 2025-02-21 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-28 | 01.S4 |  |  | 1 | 1.45 | 0568 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-18 | 2025-02-21 | 2024-12-18 | 2024-12-18 |  | 2025-01-18 |  | 2024-10-25 |  | 2025-01-24 | 2024-12-06 | 2024-12-06 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2024-12-18 | 2025-12-05 |  |  | 2024-12-09 | 2024-12-09 | 2024-12-09 | [5 empty] | 2024-10-17 | 2025-02-21 | 2025-01-18 | S4 | 2024-12-09 |  |  |  | 0 | 08. Not Applicable | 1926 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-02-21 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1983 | PTPI0567 | 02.Interface | 02.IF - Intel Foundry | Get Material Master details from IF to Pega PSI | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-050_PTP_Pega%20PSI_Get%20Material%20Master%20details%20from%20IF%20to%20Pega%20PSI.pptx?web=1 | 02.No | 01.Yes |  | 2024-08-26 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 17296 | Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI | S/4 | PEGA PSI | APIGEE | 2024-09-13 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-10-25 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-11-08 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2024-10-18 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-11-29 | 2024-12-27 | 2024-12-27 | 100% | 2024-12-06 | 2025-11-01 | 2026-03-06 | 2026-03-06 | 100% | 2026-03-06 | 2024-12-06 | 2026-03-06 |  | 2025-07-15 | 2024-11-29 | 2024-12-06 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2024-12-06 | 2024-12-09 | 2024-12-06 | N | 100% | 2024-12-09 | Not Applicable | R3 Build & UT Sprint 8 | 2024-12-27 | 2026-03-06 | 2026-03-06 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-28 | 01.S4 |  |  | 2 | 2.9 | 0567 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-12-27 | 2024-12-06 | 2024-12-06 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2024-12-06 | 2026-03-06 |  |  | 2024-12-09 | 2024-12-09 | 2024-12-09 | [5 empty] | 2024-10-17 | 2024-11-15 | 2024-10-25 | MW | 2024-12-09 |  |  |  | 0 | 08. Not Applicable | 1927 | [7 empty] | 5. Not Dispositioned |  |  | 2026-03-06 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 23 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1984 | PTPI0566 | 02.Interface | 02.IF - Intel Foundry | Maintain Outline Agreement in IF from Pega PSI | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040_PTP_Pega%20PSI_Maintain%20Outline%20Agreement%20in%20IF%20from%20Pega%20PSI.pptx?web=1 | 02.No | 01.Yes |  | 2024-08-26 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 17296 | Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI | PEGA PSI | S/4 | APIGEE | 2024-09-13 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-11-22 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-06 | 2025-01-27 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-08-01 | 2025-12-05 | 2025-12-05 | 100% | 2025-12-05 | 2025-04-11 | 2025-12-05 |  | 2025-07-15 | 2024-11-29 | 2024-12-06 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2024-12-06 | 2024-12-09 | 2024-12-06 | N | 100% | 2024-12-09 | Not Applicable | R3 Build & UT Sprint 8 | 2025-04-18 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-28 | 01.S4 |  |  | 1 | 1.45 | 0566 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-29 | 2024-11-26 |  | 2025-01-07 | 2025-02-21 | 2025-01-07 | 2025-01-07 |  | 2024-12-06 |  | 2024-12-06 |  | 2025-04-18 | 2025-04-11 | 2025-04-11 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-04-11 | 2025-12-05 |  |  | 2024-12-09 | 2024-12-09 | 2024-12-09 | [5 empty] | 2024-10-17 | 2025-02-21 | 2024-12-06 | MW | 2024-12-09 |  |  |  | 0 | 08. Not Applicable | 1928 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-02-21 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1967 | PTPI0559_IP | 02.Interface | 01.IP - Intel Product | All Validation of Chemical purchases on non MRP PR by using integration between ICHEM and S4 IP and IF. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1967-PM-070-020-PTP_S4_ICHEM_interface.pptx?d=w4d8af2910a244149915a269ddfd4f99d&csf=1&web=1&e=s0iV9K | 01.Yes | 01.Yes | PTPE0558_IP | 2024-08-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 18863 | I-CHEM - Chemical Management System | ICHEM | S/4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-22 | 100% | 2024-12-18 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-03-27 | 100% | 2025-04-21 | 2025-02-21 | 2025-03-07 | 2025-03-27 | 100% | 2025-04-19 | [10 empty] | 2025-02-24 | 2025-04-15 | 2025-04-15 | 100% | 2026-02-06 | 2025-04-19 | 2026-02-06 | No | 2025-08-27 | 2025-09-10 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-07 | 2025-04-15 | 2025-04-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-28 | 01.S4 |  |  | 1 | 1.45 | 0559 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-19 | [9 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2025-04-19 | 2026-02-06 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-01-31 | S4 | 2025-09-04 |  |  |  | 0 | 08. Not Applicable | 1921 | [10 empty] | 2025-04-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 22 |  | 2025-04-19 | 2025-04-19 | Yes | PLant changes needs to checking with the custom table changes | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1967 | PTPI0559_IF | 02.Interface | 02.IF - Intel Foundry | All Validation of Chemical purchases on non MRP PR by using integration between ICHEM and S4 IP and IF. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1967-PM-070-020-PTP_S4_ICHEM_interface.pptx?d=w4d8af2910a244149915a269ddfd4f99d&csf=1&web=1&e=s0iV9K | 01.Yes | 01.Yes | PTPE0558_IF | 2024-08-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Manufacturing Integration | 01.Yes | 18863 | I-CHEM - Chemical Management System | ICHEM | S/4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-22 | 100% | 2024-12-18 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-28 | 2025-03-07 | 2025-03-27 | 100% | 2025-03-27 | 2025-02-28 | 2025-03-07 | 2025-03-27 | 100% | 2025-03-27 | [10 empty] | 2025-02-24 | 2025-04-15 | 2025-04-15 | 100% | 2026-02-06 | 2025-03-27 | 2026-02-06 | No | 2025-08-27 | 2025-09-10 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-07 | 2025-04-15 | 2025-04-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-23 | 01.S4 | PTPI0559_IP | 03.Medium | 0.3 | 0.435 | 0559 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-03-27 | 2025-03-27 | [11 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2025-03-27 | 2026-02-06 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-01-24 | 2025-03-07 | 2025-01-31 | S4 | 2025-09-04 |  |  |  | 0 | 08. Not Applicable | 1920 | [10 empty] | 2025-04-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 22 |  | 2025-03-27 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1856 | PTPI0494 | 02.Interface | 02.IF - Intel Foundry | Maintain PO in IF from CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM_080-080_PTP_CWB_Maintain%20PO%20in%20IF%20from%20CWB.pptx?d=wd7512320478947f6a5cc0cb5e19e138f&csf=1&web=1&e=2K9X1w | 02.No | 01.Yes |  | 2024-07-31 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | CWB | S/4 | APIGEE | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-11 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | 2024-10-11 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-22 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-29 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2024-12-20 | 2025-05-05 | 2025-10-24 | 2025-10-24 | 100% | 2025-09-11 | 2024-12-20 | 2025-09-11 | No | 2025-06-03 | 2025-10-01 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-18 | Not Applicable | R3 Build & UT Sprint 18 | 2025-01-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2024-07-30 06:33 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 01.S4 |  |  | 4 | 5.8 | 0494 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-29 |  | 2024-11-29 |  | 2025-01-24 | 2024-12-20 | 2024-12-20 |  | 2025-10-24 | 2025-09-11 | 2025-09-11 | 2024-12-20 | 2025-09-11 |  |  | 2025-09-18 | 2025-10-08 | 2025-09-18 | [5 empty] | 2024-09-20 | 2024-11-08 | 2024-11-29 | MW | 2025-03-17 |  |  |  | 0 | 08. Not Applicable | 2169 | [10 empty] | 2025-10-24 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1807 | PTPI0473 | 02.Interface | 05.CFIN | Demand Change - Automatic update of PR/PO/STR/STO/Scheduling agreement and Production Order in S/4 based on input signal from planning engine (IP) | 06. PTP | 6.2 PTP - Procurement | 09. FUT Overdue | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-070-010-0002_PTP_RICEFW_DCR_IP%20Auto%20update%20PR_PO_STR_STO_SA.pptx?d=wa31ca1856dbf402cb0b7f8969119c42a&csf=1&web=1&e=W6eZjd | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved | 2024-08-01 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 02.No | NA | NA | NA | NA | Mulesoft | 2024-10-21 | 2025-02-07 | 2025-02-14 | 100% | 2025-02-21 | 2025-09-12 | 2025-09-19 | 2026-02-27 | 100% | 2026-03-12 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2026-04-07 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2026-04-07 | 2026-02-23 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | 2026-02-23 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-06 | [5 empty] | 2026-04-07 | 2026-04-07 | Yes | 2025-12-24 | 2026-03-04 | 2026-03-27 | 90% | 70% | 0% |  |  | 02. In Progress | 02. In Progress | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-03-27 | N | 35% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | pgaroo@deloitte.com | 2024-07-22 10:39 | cell-link@smartsheet.com | 2026-04-06 23:25 | 9 |  | 01.S4 |  |  | 2 | 2.9 | 0473 | INT-CR1348 | R3 ITC2 | R3 ITC2 | [5 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 |  | 2026-02-27 |  | 2026-02-27 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 |  |  |  |  | 2026-04-07 | 2026-04-07 |  |  |  | 2026-03-27 | [6 empty] | 2025-02-07 | 2025-10-24 | 2026-02-27 |  | 2026-03-06 |  |  |  | 0 | 01.2 Supplier - OSAT | 1533 | [7 empty] | 3. Off Track | 17. FUT In progress | 4/3 80% FUT is complete. OSAT test cases are pending to be tested with PDH. ETA 4/7 3/30 70% FUT is complete. OSAT test cases are pending to be tested with PDH. ETA 3/31 3/27- Testing in progress, Defect 8534 working with BODS team. 3/23 FUT in Progress. 50% Completed. ETA to accomplish is 3/31 3/12 FUT in Progress. As it involves multiple commodities, ETA to complete FUT is 3/27. 3/5 Build in Progress by Dev Team and PDH Team. We have started parallel TUT and FUT to expedite. 2/25: PDH build is expected to completed by 03/06. S4 FUT is completed. E2E FUT to begin from 03/10 | 2026-02-27 | Y | 06. PTP |  |  |  | 03/24: E2E FUT in progress. ETA for completion is 03/31 Current status:. E2E FUT in progress. ETA for completion is 03/31 Issue: E2E FUT on HOLD due to BA build incompletion Next steps: Complete E2E FUT as PDH Build is completed Help needed: Complete E2E FUT ETA: 03/31 |  | 2. Risk | Approved Exception (ITC2) | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-04-07 | 2026-04-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1795 | PTPI0470 | 02.Interface | 05.CFIN | Payment Proposal after invoice posted from SAP S/4 HANA CFIN to Ariba | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1795-PM-150-130-0001-PTP%20Payment%20Proposal%20after%20invoice%20posted%20from%20SAP%20S4%20HANA%20IP%20IF%20to%20Ariba.pptx?d=wa18a19c2586342a4878ce78228f73177&csf=1&web=1&e=gDg9Bh | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292 | SAP Ariba Network; SAP Ariba Invoicing | S/4 | SAP Ariba Network | NA | 2024-09-23 | 2025-01-24 | 2025-11-05 | 100% | 2025-10-14 | 2025-09-12 | 2025-09-19 | 2025-11-20 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [10 empty] | 2025-11-10 | 2025-12-05 | 2025-12-05 | 100% | 2025-12-05 | 2025-11-28 | 2025-12-05 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-06 04:14 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0470 |  | R3 ITC1 | [6 empty] | 2025-10-14 | 2025-11-05 | 2025-10-14 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [9 empty] | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-12-05 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | Ariba | 2025-01-24 | 2025-12-05 |  |  | 2025-11-05 |  |  |  | 0 | 01. Supplier - All | 3217 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/25 Submitted for approval IMP 11/18 New Enhancement needed because of change in business requirement. CR creation in Progress 11/11 - Design is changed during FUT Review. Needs new object development 11/4 Approved by IT. Pending Business approval 10/27: FUT is in progress. 10/17: FUT is in progress. | 2025-12-05 | Y | 06. PTP |  |  |  | Submitted for approval | Defect 4572 (ETA 1123) ETA 1204 | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-19 | 2026-04-10 | 2026-04-10 | 75% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1799 | PTPI0469 | 02.Interface | 05.CFIN | Payment Remittance after payment posted from CFIN to IP/IF and from IP/IF to Ariba | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1799-PM-150-130-0005-PTP%20Payment%20Remittance%20after%20payment%20posted%20from%20CFIN%20to%20IPIF%20and%20from%20IPIF%20to%20Ariba.pptx?d=wc45596c72ab44da497bc50a4803a77a9&csf=1&web=1&e=SCBmjB | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292 | SAP Ariba Network; SAP Ariba Invoicing | S/4 | SAP Ariba Network | NA | 2024-08-26 | 2025-01-24 | 2024-09-13 | 100% | 2025-01-24 | 2025-02-16 | 2025-02-21 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-21 | 2025-05-16 | 2025-04-25 | 100% | 2025-10-02 | 2025-04-21 | 2025-05-16 | 2025-04-25 | 100% | 2025-10-02 | [10 empty] | 2025-10-13 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-10-02 | 2025-11-07 |  | 2025-08-29 | 2025-09-08 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-17 | 2025-11-14 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-07-22 10:39 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0469 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-01-24 | 2025-01-24 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-10-02 | 2025-11-07 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  |  |  |  | Ariba | 2025-01-24 | 2025-05-16 | 2025-01-16 | S4 | 2024-12-19 |  |  |  | 0 | 01. Supplier - All | 2662 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 12/3 FUT in progress. Planned to be submitted by 12/5 11/24 FUT in Progress. 80% complete. To be shared for approval by 11/25 11/18 FUT in Progress. ETA to submit for approval by 11/28 11/12 - FUT in Progress. Defect#4506 under Fix by Tech Team | 2025-11-07 | Y | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-02 | 2025-10-02 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes | 2026-03-13 | 2026-03-04 | 2026-02-26 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1805 | PTPI0468 | 02.Interface | 01.IP - Intel Product | Payment Status after payment is cancelled / Void from CFIN to IP / IF and From IP / IF to Ariba | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1805-PM-150-130-0009-PTP%20Payment%20Status%20after%20payment%20is%20cancelled%20Void%20from%20CFIN%20to%20IP%20IF%20and%20From%20IP%20IF%20to%20Ariba.pptx?d=w8f0d3a8a465e4cb0bfbaca5be1d3e060&csf=1&web=1&e=7VqaLI | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 15206; 18292 | SAP Ariba Network; SAP Ariba Invoicing | S/4 | SAP Ariba Network | NA | 2024-08-26 | 2025-01-24 | 2024-09-20 | 100% | 2025-01-24 | 2025-03-07 | 2025-03-14 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-12-02 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-12-02 | [10 empty] | 2025-10-13 | 2026-02-06 | 2026-02-06 | 100% | 2026-02-20 | 2025-12-02 | 2026-02-20 |  | 2025-08-29 | 2025-09-08 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-17 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-04-18 | 2026-02-06 | 2026-02-06 | pgaroo@deloitte.com | 2024-07-22 10:39 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0468 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-01-24 | 2025-01-24 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-02 | [9 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2025-12-02 | 2026-02-20 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 |  |  |  |  | Ariba | 2025-01-24 | 2025-04-18 | 2025-05-30 | S4 | 2024-12-26 |  |  |  | 0 | 01. Supplier - All | 2665 | [7 empty] | 1. On Track | 17. FUT In progress | 1/9 - Feedback received post FUT Review. Working on this to get it moved back to awaiting approval 1/5 Test Data issue awaiting Treasury Team support. ETA 1/6 12/17: Defect 5556 is created. 12/12: FUT is in progress. | 2026-02-06 | Y | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 23 |  | 2025-12-02 | 2025-12-02 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 75% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-03 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1840 | PTPI0467 | 02.Interface | 02.IF - Intel Foundry | Maintain Outline Agreement in IF from EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-TBD_PTP_EMS_Maintain%20Outline%20Agreement%20in%20IF%20from%20EMS.pptx?web=1 | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | EMS | S/4 | APIGEE | 2024-08-26 | 2024-08-26 | 2024-08-26 | 100% | 2024-11-26 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-10-04 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-07-01 | 2025-07-15 | 2025-07-15 | 100% | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-10-08 | 2024-10-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-10-17 | N | 100% | 2024-11-08 | Not Applicable | R3 Build & UT Sprint 7 | 2024-10-25 | 2025-07-15 | 2025-07-15 | pgaroo@deloitte.com | 2024-07-22 10:39 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0467 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-07 | 2024-10-11 | 2024-10-07 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-11-08 | 2025-07-29 | 2024-11-08 | [5 empty] | 2024-08-26 | 2024-10-11 | 2024-10-25 | S4 | 2024-10-17 |  |  |  | 0 | 08. Not Applicable | 2160 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-07-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1833 | PTPI0466_IP | 02.Interface | 01.IP - Intel Product | Payment Remittance after payment posted from CFIN to IP/IF for Readsoft | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1833-PM-150-130-0007-PTP%20Payment%20Remittance%20after%20payment%20posted%20from%20CFIN%20to%20IPIF%20for%20Readsoft.pptx?d=w8d48d942c6c8448e8921ea9e3d92e28a&csf=1&web=1&e=caShv7 | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 6878; 64229 | Readsoft - WorkCycle; Readsoft - Process Director Accounts Payable IP | S/4 | Readsoft | NA | 2025-01-27 | 2025-02-21 | 2024-10-11 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-08-13 | 100% | 2025-08-09 | 2025-04-04 | 2025-04-18 | 2025-07-04 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-07-04 | 100% | 2025-07-21 | [10 empty] | 2025-10-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-07-21 | 2025-11-07 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-07-22 10:39 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0466 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-07-21 | 2025-11-07 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  |  |  |  | Readsoft | 2025-01-24 | 2025-04-18 | 2025-05-16 | S4 | 2025-01-24 |  |  |  | 0 | 08. Not Applicable | 2154 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/10 Awaiting approval 11/25 Submitted FUT for approval. Andrea (Business) has come up with New design. Discussion in Progress. This will be delayed. 11/18 Delayed due to Readsoft not being Ready in terms of Payment Terms. ETA 11/28 by Readsoft Team 11/14 Delayed due to Readsoft not being Ready in terms of Payment Terms 11/11- Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 11/4 - Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 10/27: Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 10/17: FUT is dependent upon ReadSoft Payment Readiness. ETA for ReadSoft is 3 Nov. 10/10: Dependency on Read Soft Development. Replanned this FUT in Sprint 19. | 2025-11-07 | Y | 06. PTP |  |  |  | Submitted for approval | 1125: New requirement being discussed. CR might be required. FUT Complete ETA 1125 for Approval | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 80% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 1833 | PTPI0466_IF | 02.Interface | 02.IF - Intel Foundry | Payment Remittance after payment posted from CFIN to IP/IF for Readsoft | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1833-PM-150-130-0007-PTP%20Payment%20Remittance%20after%20payment%20posted%20from%20CFIN%20to%20IPIF%20for%20Readsoft.pptx?d=w8d48d942c6c8448e8921ea9e3d92e28a&csf=1&web=1&e=caShv7 | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 6878; 64228 | Readsoft - WorkCycle; Readsoft - Process Director Accounts Payable IF | S/4 | Readsoft | NA | 2025-01-27 | 2025-02-21 | 2024-10-11 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-08-13 | 100% | 2025-08-09 | 2025-04-11 | 2025-04-18 | 2025-07-04 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-18 | 2025-07-04 | 100% | 2025-07-21 | [10 empty] | 2025-10-29 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-07-21 | 2025-11-07 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-07-22 10:39 | cell-link@smartsheet.com | 2026-04-06 17:13 | 10 |  | 01.S4 | PTPI0466_IP | 03.Medium | 0.3 | 0.435 | 0466 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-07-21 | 2025-11-07 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  |  |  |  | Readsoft | 2025-01-24 | 2025-04-18 | 2025-05-16 | S4 | 2025-01-10 |  |  |  | 0 | 08. Not Applicable | 2153 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/10 Awaiting approval 11/25 Submitted FUT for approval. Andrea (Business) has come up with New design. Discussion in Progress. This will be delayed. 11/18 Delayed due to Readsoft not being Ready in terms of Payment Terms. ETA 11/28 by Readsoft Team 11/14 Delayed due to Readsoft not being Ready in terms of Payment Terms 11/11- Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 11/4 - Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 10/27: Blocked due to ReadSoft Readiness. RAID is open [RAID ID: 2421] 10/17: FUT is dependent upon ReadSoft Payment Readiness. ETA for ReadSoft is 3 Nov. 10/10: Dependency on Read Soft Development. Replanned this FUT in Sprint 19. | 2025-11-07 | Y | 06. PTP |  |  |  | Submitted for approval | 1125: New requirement being discussed. CR might be required. FUT Complete ETA 1125 for Approval | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-09 | 2026-04-10 | 2026-04-10 | 80% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 1777 | PTPI0463_IP | 02.Interface | 01.IP - Intel Product | GR Carbon Copy (Posted in S4) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/LI_120_100_8881_PTP_Procurement_Carbon_Copy_GR.pptx?d=wd1291850ccc14a3e8baea86726cbce3f&csf=1&web=1&e=W4ddoG | 01.Yes | 01.Yes | PTPE0731_IP | 2024-07-19 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2024-08-07 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-17 | 2025-03-21 | 2025-09-26 | 100% | 2025-09-16 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | [10 empty] | 2025-08-23 | 2025-09-02 | 2025-09-02 | 100% | 2025-08-30 | 2025-06-11 | 2025-08-30 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-09-02 | 2025-09-02 | pgaroo@deloitte.com | 2024-07-19 07:03 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0463 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-06-11 | 2025-06-13 | [11 empty] | 2025-09-02 | 2025-08-30 | 2025-08-30 | 2025-06-11 | 2025-08-30 |  |  | 2025-09-09 | 2025-09-12 | 2025-09-09 |  |  |  |  | Ariba | 2024-09-20 | 2025-06-13 |  | S4 | 2025-07-01 |  |  |  | 0 | 08. Not Applicable | 2657 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-09-02 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-06-13 | 2025-06-11 | Yes | Mapping table changes | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-06 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1777 | PTPI0463_IF | 02.Interface | 02.IF - Intel Foundry | GR Carbon Copy (Posted in S4) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/LI_120_100_8881_PTP_Procurement_Carbon_Copy_GR.pptx?d=wd1291850ccc14a3e8baea86726cbce3f&csf=1&web=1&e=W4ddoG | 01.Yes | 01.Yes | PTPE0731_IF | 2024-07-19 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206 | SAP Ariba Network | S/4 | SAP Ariba Network | NA | 2024-08-07 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-17 | 2025-03-21 | 2025-09-26 | 100% | 2025-09-17 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-01 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-01 | [10 empty] | 2025-08-23 | 2025-09-02 | 2025-09-02 | 100% | 2025-08-30 | 2025-08-01 | 2025-08-30 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-09-02 | 2025-09-02 | jenoronha@deloitte.com | 2024-08-14 02:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0463_IP | 02.High | 0.6 | 0.87 | 0463 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-09-17 | 2025-09-26 | 2025-09-17 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | [9 empty] | 2025-09-02 | 2025-08-30 | 2025-08-30 | 2025-08-01 | 2025-08-30 |  |  | 2025-09-09 | 2025-09-12 | 2025-09-09 |  |  |  |  | Ariba | 2024-09-20 | 2025-06-13 |  | S4 | 2025-07-01 |  |  |  | 0 | 08. Not Applicable | 2656 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-02 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-01 | 2025-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1764 | PTPI0452 | 02.Interface | 02.IF - Intel Foundry | Get Material Master alternate UOM details from IF to CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-050-9013_PTP_CWB_Get%20Material%20Master%20alternate%20UOM%20details%20from%20IF%20to%20CWB.pptx?d=w9db708d6a62a419fa415fc3422d0aef4&csf=1&web=1&e=AEwz6s | 02.No | 01.Yes |  | 2024-07-18 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | S/4 | CWB | APIGEE | 2024-10-21 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-12 | 2024-08-16 | 2024-08-23 | 2025-02-21 | 100% | 2025-02-07 | 2024-08-16 | 2024-09-13 | 2025-02-28 | 100% | 2025-03-18 | 2024-08-16 | 2024-09-13 | 2025-02-28 | 100% | 2025-03-18 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-03 | 2025-05-14 | 2025-05-14 | 100% | 2025-05-14 | 2025-08-04 | 2025-08-04 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-09 | 2024-09-20 | 2024-09-20 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-05-14 | 2025-05-14 | pgaroo@deloitte.com | 2024-07-18 00:20 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0452 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-08-12 | 2024-08-12 | 2024-08-12 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-08-09 | 2024-09-13 | 2025-01-24 | MW | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 2135 | [9 empty] | 8/11 - Will check with Jose to mark it as 100% 25/7 - Checking with Sean on the UOM issue ETA 8/6 -Wed | 2025-05-14 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-03-18 | 2025-03-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1760 | PTPI0449 | 02.Interface | 02.IF - Intel Foundry | Maintain Outline Agreement in IF from CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0002_PTP_CWB_Maintain%20Outline%20Agreement%20in%20IF%20from%20CWB.pptx?web=1 | 02.No | 01.Yes |  | 2024-07-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | CWB | S/4 | APIGEE | 2024-07-26 | 2024-08-19 | 2024-08-19 | 100% | 2024-08-13 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-05-05 | 2025-10-24 | 2025-10-24 | 100% | 2025-09-23 | 2024-11-26 | 2025-09-23 |  |  | 2024-11-01 | 2024-11-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-28 | 2024-12-20 | 2024-11-08 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-25 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2024-07-16 03:28 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 4 | 5.8 | 0449 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-08-13 | 2024-08-19 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-10-24 | 2025-09-23 | 2025-09-23 | 2024-11-26 | 2025-09-23 |  |  | 2024-11-26 | 2024-12-20 | 2024-11-26 | [5 empty] | 2024-08-19 | 2024-10-25 | 2024-10-25 | S4 | 2024-12-20 |  |  |  | 0 | 08. Not Applicable | 2133 | [10 empty] | 2025-10-24 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1765 | PTPI0448 | 02.Interface | 02.IF - Intel Foundry | Maintain Purchasing Info Record in IF from CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-9012_PTP_CWB_Maintain%20Purchasing%20Info%20Record%20in%20IF%20from%20CWB.pptx?d=w669c8ccffa2a4fc0ab7ec59c94124e57&csf=1&web=1&e=R8rhVh | 02.No | 01.Yes |  | 2024-07-16 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | CWB | S/4 | APIGEE | 2024-07-26 | 2024-08-19 | 2024-08-19 | 100% | 2024-08-12 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-05-03 | 2026-01-31 | 2026-01-31 | 100% | 2026-02-06 | 2024-11-26 | 2026-02-06 |  |  | 2024-11-01 | 2024-11-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-28 | 2024-12-20 | 2024-11-08 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-25 | 2026-01-31 | 2026-01-31 | pgaroo@deloitte.com | 2024-07-16 03:28 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0448 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-08-12 | 2024-08-19 | 2024-08-12 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2024-11-26 | 2026-02-06 |  |  | 2024-11-26 | 2024-12-20 | 2024-11-26 | [5 empty] | 2024-08-19 | 2024-10-04 | 2024-10-25 | MW | 2024-12-20 |  |  |  | 0 | 08. Not Applicable | 2136 | [7 empty] | 5. Not Dispositioned |  |  | 2026-01-31 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 22 |  | 2024-10-04 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 816 | PTPI0388_IP | 02.Interface | 01.IP - Intel Product | Custom program to send the Purchase order from SAP S4 system to Illumis | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-06-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2024-09-30 | 2024-10-04 | 2024-10-04 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-14 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-02-14 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-10-08 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-10-08 | 2025-10-08 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-06-19 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0388 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2024-10-04 | 2025-03-07 | 2025-04-04 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1651 | [9 empty] | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | Yes | Illumis Interface testing | Yes |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 816 | PTPI0388_IF | 02.Interface | 02.IF - Intel Foundry | Custom program to send the Purchase order from SAP S4 system to Illumis | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/816_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IF.pptx?d=w4fa4be9a57cb4378be663114b287a58a&csf=1&web=1&e=xzeb8K | 02.No | 01.Yes |  | 2024-06-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 23042 | Accounts Payable Recoveries (APR) | S/4 | Accounts Payable Recovery Tool | SFT | 2024-09-30 | 2024-10-04 | 2024-10-04 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-02-21 | 2025-03-07 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-10-08 | 2025-05-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-10-08 | 2025-10-08 |  | 2025-08-12 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-06-19 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0388_IP | 02.High | 0.6 | 0.87 | 0388 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2024-10-04 | 2025-03-07 | 2025-04-04 | MW | 2025-05-22 |  |  |  | 0 | 08. Not Applicable | 1650 | [9 empty] | EP team planned S4 FUT in Sprint 16. Post B-app is ready. E2E FUT will be initiated. | 2025-09-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 814 | PTPI0386 | 02.Interface | 02.IF - Intel Foundry | Maintain Document Info Record in IF from CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/186_PM-080-050-0021_PTP_EMS_Create%20Document%20Info%20Record%20in%20IF%20from%20EMS.pptx?d=we1aaaeefeedd4d5a892b9bd87641fb59&csf=1&web=1&e=V4yWEG | 02.No | 01.Yes |  | 2024-06-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | CWB | S/4 | APIGEE | 2025-03-24 | 2025-04-10 | 2025-04-15 | 100% | 2025-04-15 | 2025-04-25 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-25 | 2025-05-16 | 2025-08-08 | 100% | 2025-09-09 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-09 | 2025-04-21 | 2025-05-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-10-29 | 2026-01-31 | 2026-01-31 | 100% | 2026-01-23 | 2025-11-05 | 2026-01-23 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2026-01-31 | 2026-01-31 | pgaroo@deloitte.com | 2024-06-19 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0386 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-15 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-11-07 | 2025-11-05 | 2025-11-05 |  | 2026-01-31 | 2026-01-23 | 2026-01-23 | 2025-11-05 | 2026-01-23 |  |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | MW | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 1649 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24 Awaiting approval from Intel 11/18 FUT submitted for approval 11/12 - FUT in Progress. | 2026-01-31 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-09-09 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 186 | PTPI0384 | 02.Interface | 02.IF - Intel Foundry | Create Document Info Record in IF from EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/186_PM-080-050-0021_PTP_EMS_Create%20Document%20Info%20Record%20in%20IF%20from%20EMS.pptx?d=we1aaaeefeedd4d5a892b9bd87641fb59&csf=1&web=1&e=NGoiJa | 02.No | 01.Yes |  | 2024-06-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | Equipment Management System | S/4 | APIGEE | 2025-03-24 | 2025-04-10 | 2025-04-15 | 100% | 2025-04-15 | 2025-05-12 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-25 | 2025-05-16 | 2025-08-08 | 100% | 2025-09-09 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-09 | 2025-04-21 | 2025-05-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2026-01-15 | 2026-01-30 | 2026-01-30 | 100% | 2026-01-30 | 2025-11-05 | 2026-01-30 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2026-01-30 | 2026-01-30 | pgaroo@deloitte.com | 2024-06-19 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0384 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2025-04-15 | 2025-04-15 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-11-07 | 2025-11-05 | 2025-11-05 |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2025-11-05 | 2026-01-30 |  |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | MW | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 2709 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24 Awaiting approval from Intel 11/18 FUT submitted for approval 11/12 - FUT in Progress. | 2026-01-30 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-09-09 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 824 | PTPI0382 | 02.Interface | 02.IF - Intel Foundry | Get OA determination by material from IF to CWB | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-060-0010_PTP_CWB_Get%20OA%20determination%20by%20material%20from%20IF%20to%20CWB%20-%20Copy.pptx?d=w8c60d39528ec409eb75766137697cce3&csf=1&web=1&e=aodaj3 | 02.No | 01.Yes |  | 2024-06-20 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 22233 | Commercial Workbench | Commercial Workbench | S/4 | APIGEE | 2024-07-08 | 2024-07-29 | 2024-07-29 | 100% | 2024-07-24 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-22 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-24 | 2025-05-03 | 2025-10-24 | 2025-10-24 | 100% | 2025-09-24 | 2024-11-26 | 2025-09-24 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-09 | 2024-09-20 | 2024-09-20 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2024-06-19 08:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0382 |  | R3 ITC1 | [6 empty] | 2024-07-24 | 2024-07-29 | 2024-07-24 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-09-24 | 2024-09-24 |  | 2025-10-24 | 2025-09-24 | 2025-09-24 | 2024-11-26 | 2025-09-24 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-07-29 | 2024-09-13 | 2024-10-04 | S4 | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 2050 | [10 empty] | 2025-10-24 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 184 | PTPI0370 | 02.Interface | 02.IF - Intel Foundry | Get OA determination by material from IF to EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/184_PM-090-060-0014_PTP_EMS_Get%20OA%20determination%20by%20material%20from%20IF%20to%20EMS.pptx?d=w3bcf453025424ad9a0f79e0ccca655a6&csf=1&web=1&e=R2kDXJ | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System | S/4 | Equipment Management System | APIGEE | 2024-07-08 | 2024-07-29 | 2024-07-29 | 100% | 2024-07-24 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-22 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-24 | 2025-07-01 | 2025-07-15 | 2025-07-15 | 100% | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-09-20 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-15 | 2025-07-15 | pgaroo@deloitte.com | 2024-06-18 05:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0370 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-07-24 | 2024-07-29 | 2024-07-24 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-09-24 | 2024-09-24 |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-11-26 | 2025-07-29 | 2024-11-26 | [5 empty] | 2024-07-29 | 2024-09-13 | 2024-10-04 | S4 | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 2708 | [10 empty] | 2025-07-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 706 | PTPI0369 | 02.Interface | 02.IF - Intel Foundry | Develop an interface to send inventory reports and MRP parameters from S4(IF) & S4(IP) to suppliers. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-07-08 | 2024-08-09 | 2024-08-09 | 100% | 2024-09-05 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 100% | 2024-09-26 | 2025-01-27 | 2025-12-05 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-12-05 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2024-12-19 | 2024-11-25 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-01-07 | 2025-03-28 | Yes | 2025-07-28 | 2025-08-13 | 2025-08-29 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0369 | INT-CR0408 | R3 ITC1 | [6 empty] | 2024-09-05 | 2024-09-05 | 2024-09-05 |  | 2024-09-26 | 2024-10-18 | 2024-09-26 |  | 2025-01-07 | 2025-12-05 | 2025-01-07 | 2025-01-07 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-01-24 | 2024-12-19 | 2024-12-19 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-01-07 | 2025-03-28 |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 |  |  |  |  | B2B - E2open | 2024-08-09 | 2025-12-05 | 2025-01-24 |  | 2025-08-29 |  | WIINGS |  | 0 | 01.4 Suppliers that engage with E2Open | 2585 | [9 empty] | 10/10: Object is completed and approved. It was renamed to PTPI0369 | 2025-12-05 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 12 |  | 2025-12-05 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 698 | PTPI0368 | 02.Interface | 02.IF - Intel Foundry | Automatic creation of Discrete PO & IB delivery when supplier initiates shipment and send details to S/4 (IF) & S/4 ( IP). | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/LI-100-040-0001_PTP_RICEFW%20Intake%20Form.pptx?d=wc6c13cc52b7842149e706aecc9cae1fa&csf=1&web=1&e=WisfNP | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | E2open | S/4 | MULESOFT | 2024-07-08 | 2024-08-09 | 2024-08-09 | 100% | 2024-09-03 | 2024-11-08 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2024-11-15 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-22 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2024-12-19 | 2025-06-10 | 2025-09-08 | 2025-09-08 | 100% | 2025-09-23 | 2025-01-07 | 2025-09-23 |  | 2025-07-15 | 2025-09-25 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-12 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-30 | Not Applicable | R3 Build & UT Sprint 18 | 2025-02-21 | 2025-09-08 | 2025-09-08 | pgaroo@deloitte.com | 2024-06-18 05:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0368 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-09-03 | 2024-09-03 | 2024-09-03 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-02-21 | 2025-01-07 | 2025-01-07 |  | 2024-11-22 |  | 2024-11-22 |  | 2025-01-24 | 2024-12-19 | 2024-12-19 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-01-07 | 2025-09-23 |  |  | 2025-09-30 | 2025-10-08 | 2025-09-30 |  |  |  |  | B2B - E2open | 2024-08-09 | 2025-02-21 | 2024-11-22 |  | 2025-10-08 |  | WIINGS |  | 0 | 01.4 Suppliers that engage with E2Open | 2573 | [10 empty] | 2025-09-08 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-02-21 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 657 | PTPI0272 | 02.Interface | 02.IF - Intel Foundry | Get Material Master details from IF to EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/TBD-Deloitte-0044_PTP_EMS_Get%20Material%20Master%20details%20from%20IF%20to%20EMS%20-%20Copy.pptx?d=w034e8e2b15d14168b3488c10281fd964&csf=1&web=1&e=t0DkLL | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | S/4 | EMS | APIGEE | 2024-06-24 | 2024-07-16 | 2024-07-16 | 100% | 2024-07-17 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-12 | 2024-08-30 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-08-09 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2025-07-01 | 2025-07-15 | 2025-07-15 | 100% | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-09-20 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-15 | 2025-07-15 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0272 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-07-17 | 2024-07-17 | 2024-07-17 |  | 2024-08-12 | 2024-08-16 | 2024-08-12 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2024-11-26 | 2025-07-15 |  |  | 2024-11-26 | 2025-07-29 | 2024-11-26 | [5 empty] | 2024-07-16 | 2024-09-06 | 2024-10-04 | S4 | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 1937 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-07-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 655 | PTPI0271 | 02.Interface | 02.IF - Intel Foundry | Get Material Master details from IF to SIRFIS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PTP%20B-App%20RICEFW%20Requests/TBD-Deloitte-0042_PTP_SIRFIS_Get%20Material%20Master%20details%20from%20IF%20to%20SIRFIS.pptx?d=w7f22b8e0f7b947ac9c76a5afa9ffc115&csf=1&web=1&e=7vehof | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | S/4 | SIRFIS | APIGEE | 2024-06-24 | 2024-07-16 | 2024-07-16 | 100% | 2024-07-18 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-12 | 2024-08-30 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-08-09 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2025-06-25 | 2025-07-22 | 2025-07-22 | 100% | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-09 | 2024-09-20 | 2024-09-20 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-22 | 2025-07-22 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0271 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-12 | 2024-08-16 | 2024-08-12 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-07-16 | 2024-09-06 | 2024-10-04 | S4 | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 1936 | [10 empty] | 2025-07-22 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 640 | PTPI0269_IP | 02.Interface | 01.IP - Intel Product | Supplier Onboarding Data - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B020DEFF3-62FF-46CE-AD7C-887CCE30E819%7D&file=PM-080-060-0012_PTP_Ariba%20Supplier%20Onboarding%20Data_Intel%20Factory%20-%20Copy%20-%20Copy.pptx&wdLOR=c135B4353-D9E8-472D-ADAA-00FA1117FA5C&action=edit&mobileredirect=true | 02.No | 01.Yes | PTPE0726_IP | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | Shopping@Intel | S/4 | NA | 2024-07-22 | 2024-08-19 | 2024-08-19 | 100% | 2024-09-18 | 2024-12-16 | 2025-01-07 | 2025-08-13 | 100% | 2025-08-11 | 2025-02-10 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-02-10 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | [10 empty] | 2025-07-11 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-21 | 2025-07-21 | 2025-07-21 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0269_CFIN | 03.Medium | 0.3 | 0.435 | 0269 |  | R3 ITC1 | [6 empty] | 2024-09-18 | 2024-09-18 | 2024-09-18 |  | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-24 | 2025-10-08 | 2025-09-24 |  |  |  |  | Ariba | 2024-08-19 | 2025-04-18 | 2025-01-10 | S4 | 2025-07-31 |  |  |  | 0 | 01. Supplier - All | 1833 | [10 empty] | 2025-07-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | Yes | Mapping table changes | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 640 | PTPI0269_IF | 02.Interface | 01.IP - Intel Product | Supplier Onboarding Data - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B020DEFF3-62FF-46CE-AD7C-887CCE30E819%7D&file=PM-080-060-0012_PTP_Ariba%20Supplier%20Onboarding%20Data_Intel%20Factory%20-%20Copy%20-%20Copy.pptx&wdLOR=c135B4353-D9E8-472D-ADAA-00FA1117FA5C&action=edit&mobileredirect=true | 02.No | 01.Yes | PTPE0726_IF | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15205 | Shopping@Intel | Shopping@Intel | S/4 | NA | 2024-07-22 | 2024-08-19 | 2024-08-19 | 100% | 2024-09-18 | 2024-12-16 | 2025-01-07 | 2025-08-13 | 100% | 2025-08-11 | 2025-02-10 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-02-10 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | [10 empty] | 2025-07-11 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-21 | 2025-07-21 | 2025-07-21 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-07-21 | 2025-07-21 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0269_CFIN | 03.Medium | 0.3 | 0.435 | 0269 |  | R3 ITC1 | [6 empty] | 2024-09-18 | 2024-09-18 | 2024-09-18 |  | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-24 | 2025-10-08 | 2025-09-24 |  |  |  |  | Ariba | 2024-08-19 | 2025-04-18 | 2025-01-10 | S4 | 2025-07-31 |  |  |  | 0 | 01. Supplier - All | 1832 | [10 empty] | 2025-07-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 640 | PTPI0269_CFIN | 02.Interface | 05.CFIN | Supplier Onboarding Data - CFIN | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B020DEFF3-62FF-46CE-AD7C-887CCE30E819%7D&file=PM-080-060-0012_PTP_Ariba%20Supplier%20Onboarding%20Data_Intel%20Factory%20-%20Copy%20-%20Copy.pptx&wdLOR=c135B4353-D9E8-472D-ADAA-00FA1117FA5C&action=edit&mobileredirect=true | 02.No | 01.Yes | PTPE0726_IP | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | Shopping@Intel | S/4 | NA | 2024-08-18 | 2024-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-08 | 2025-09-05 | 100% | 2025-10-07 | 2025-09-29 | 2025-10-08 | 2025-09-05 | 100% | 2025-10-07 | [10 empty] | 2025-09-15 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2025-10-07 | 2025-11-07 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-07-22 09:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0269 |  | R3 ITC1 | [6 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-09-12 | 2025-09-19 | 2025-09-12 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [9 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-10-07 | 2025-11-07 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 |  |  |  |  | Ariba | 2024-09-10 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 | 01. Supplier - All | 3180 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/27 FUT Completed and submitted for approval 10/22 - FUT in progress 10/10 Will be picked up for FUT once dev is complete. | 2025-11-07 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 174 | PTPI0266 | 02.Interface | 02.IF - Intel Foundry | Get PO details from IF to EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/174_PM-080-070-0010_PTP_EMS_Get%20PO%20details%20from%20IF%20to%20EMS.pptx?d=wf2012555d97d4253a67bd5b9c3f648d7&csf=1&web=1&e=PLUyIL | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | S/4 | EMS | APIGEE | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-21 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-16 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-08-02 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 100% | 2024-10-02 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-30 | 2025-09-25 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-07 | 2024-11-26 | 2025-11-07 |  |  | 2024-09-06 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-09-13 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0266 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-08-16 | 2024-08-16 | 2024-08-16 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-02 |  | 2024-10-02 |  | 2024-10-04 | 2024-09-30 | 2024-09-30 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2024-11-26 | 2025-11-07 |  |  | 2024-11-26 | 2025-07-29 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 | 2024-10-02 | S4 | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 2705 | [10 empty] | 2025-11-07 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 170 | PTPI0263 | 02.Interface | 02.IF - Intel Foundry | Maintain PR in IF from EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/170_PM-070-080-0012_PTP_EMS_Maintain%20PR%20in%20IF%20from%20EMS.pptx?d=wc755fa317ecc457cbe3f31975c30ff7b&csf=1&web=1&e=BZw2Dg | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | EMS | S/4 | APIGEE | 2024-06-24 | 2024-07-16 | 2024-07-16 | 100% | 2024-07-18 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-08-30 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-08-09 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-24 | 2025-09-15 | 2025-11-30 | 2025-11-30 | 100% | 2025-11-30 | 2024-11-26 | 2025-11-30 |  |  | 2024-09-06 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-09-13 | N | 100% | 2024-12-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-10-04 | 2025-11-30 | 2025-11-30 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0263 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-09-24 | 2024-09-24 |  | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2024-11-26 | 2025-11-30 |  |  | 2024-12-20 | 2025-07-29 | 2024-12-20 | [5 empty] | 2024-07-16 | 2024-09-06 | 2024-10-04 | S4 | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1491 | [7 empty] | 5. Not Dispositioned |  |  | 2025-11-30 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 168 | PTPI0262 | 02.Interface | 02.IF - Intel Foundry | Get PR details from IF to EMS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/168_PM-070-080-0010_PTP_EMS_Get%20PR%20details%20from%20IF%20to%20EMS.pptx?d=wcc36531302fb43a48626d6b58f4f2c5f&csf=1&web=1&e=Yr6tHI | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System | S/4 | EMS | APIGEE | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-21 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-13 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-08-02 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 100% | 2024-10-02 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2025-09-15 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-22 | 2024-11-26 | 2025-09-22 |  |  | 2024-09-06 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-16 | 2025-07-29 | 2024-09-13 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0262 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-08-13 | 2024-08-16 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-02 |  | 2024-10-02 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-09-30 | 2025-09-22 | 2025-09-22 | 2024-11-26 | 2025-09-22 |  |  | 2024-11-26 | 2025-07-29 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 | 2024-10-02 | S4 | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1490 | [10 empty] | 2025-09-30 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 166 | PTPI0261 | 02.Interface | 02.IF - Intel Foundry | Get PR details from IF to SIRFIS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/166_PM-070-080-0008_PTP_SIRFIS_Get%20PR%20details%20from%20IF%20to%20SIRFIS.pptx?d=w9a03ce6e3c49434e9421cd4d280cbd1f&csf=1&web=1&e=Ja5EuE | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | S/4 | SIRFIS | APIGEE | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-13 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-08-02 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-25 | 2024-10-02 | 2024-10-02 | 100% | 2024-10-02 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2025-05-03 | 2025-07-22 | 2025-07-22 | 100% | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-09-06 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-13 | 2024-09-13 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-22 | 2025-07-22 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0261 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-08-13 | 2024-08-16 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-02 |  | 2024-10-02 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 | 2024-10-02 | S4 | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1489 | [10 empty] | 2025-07-22 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 585 | PTPI0211_IP | 02.Interface | 01.IP - Intel Product | Outbound interface to publish SAP Contracts details to Web Contract - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0003_Publish_SAP_Contract_Details_To_WebContracts_Intel_Products.pptx?d=wc0df8a85ce4546ebb2a13c279fbae455&csf=1&web=1&e=WeZCzf | 02.No | 01.Yes | PTPE1135_IP | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2024-08-05 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-31 | 2025-06-06 | 2025-06-13 | 2025-03-21 | 100% | 2025-03-14 | 2025-05-09 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-09 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-06-16 | 2025-07-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-21 | 2025-08-15 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-08-27 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-05-15 06:11 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0211 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-14 | 2025-06-13 | 2025-03-14 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 |  | 2025-04-18 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-01-24 | 2025-07-18 | 2025-07-18 | S4 | 2025-08-29 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2410 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100% | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | Yes | Plant changes staging Db need to be revalidated | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 586 | PTPI0211_IF | 02.Interface | 02.IF - Intel Foundry | Outbound interface to publish SAP Contracts details to Web Contract - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-090-040-0004_Publish_SAP_Contract_Details_To_WebContracts_Intel_Foundary.pptx?d=w89e7c55a60b242579464073c735ed53c&csf=1&web=1&e=UF1hLE | 02.No | 01.Yes | PTPE1135_IF | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 10546; 24834 | Intel WebSuite - Web Contract; B2B Staging Database | S/4 | WebContract | MULESOFT | 2024-08-05 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-31 | 2025-06-06 | 2025-06-13 | 2025-03-21 | 100% | 2025-03-14 | 2025-05-02 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-02 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-06-16 | 2025-07-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-21 | 2025-08-15 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-29 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-08-04 | 2025-10-10 | Yes | 2025-08-27 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2024-05-14 02:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0211_IP | 03.Medium | 0.3 | 0.435 | 0211 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-14 | 2025-06-13 | 2025-03-14 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 |  | 2025-04-18 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-08-04 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  |  |  |  | B2B - Intel WebSuite | 2025-01-24 | 2025-07-18 | 2025-07-18 | S4 | 2025-08-29 |  |  |  | 0 | 01.10 Suppliers - WebSuite | 2413 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100% | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 197 | PTPI0144_IP | 02.Interface | 01.IP - Intel Product | Interface from E2Open to S4 to publish supplier commits against Purchase Order | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/197_PM-080-070_0003_PTP_E2Open_Receive_Commit_against_PO_3A7_Intel%20Products.pptx?d=w4630dcac581e46dd89fa29f47515e68f&csf=1&web=1&e=xJLJef | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-06-10 | 2024-06-28 | 2024-06-28 | 100% | 2024-08-09 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-05 | 2024-12-02 | 2025-08-04 | 2025-08-04 | 100% | 2025-08-04 | 2025-03-05 | 2025-08-04 | Yes | 2025-08-27 | 2025-09-25 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-10 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-02-21 | 2025-08-04 | 2025-08-04 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0144 | INT-CR0168 | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-01-07 | 2025-02-21 | 2025-01-07 | 2025-01-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-05 | 2025-03-05 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-03-05 | 2025-08-04 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | B2B - E2open | 2024-06-28 | 2025-02-21 | 2025-01-24 | MW | 2025-04-09 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1462 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/10 Defect 3575 under Fix by technical Team. ETA 10/13 10/10 Defect 3575 under Fix by technical Team. ETA 10/13. | 2025-08-04 | N | 06. PTP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-02-21 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 198 | PTPI0144_IF | 02.Interface | 02.IF - Intel Foundry | Interface from E2Open to S4 to publish supplier commits against Purchase Order | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/198_PM-080-070_0004_PTP_E2Open_Receive_Commit_against_PO_3A7_Intel%20Foundry.pptx?d=w4d7b75e4be0d40769d5346ba7c90ae1c&csf=1&web=1&e=HjYBs9 | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-06-10 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-20 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-05 | 2024-12-02 | 2025-08-04 | 2025-08-04 | 100% | 2025-08-04 | 2025-03-05 | 2025-08-04 | Yes | 2025-08-27 | 2025-09-25 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-10 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-02-21 | 2025-08-04 | 2025-08-04 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0144_IP | 02.High | 0.6 | 0.87 | 0144 | INT-CR0168 | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-08-20 | 2024-08-23 | 2024-08-20 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-01-07 | 2025-02-21 | 2025-01-07 | 2025-01-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-05 | 2025-03-05 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-03-05 | 2025-08-04 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-07 |  |  |  |  | B2B - E2open | 2024-08-23 | 2025-02-21 | 2025-01-24 | MW | 2025-04-09 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1463 | [10 empty] | 2025-08-04 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-02-21 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 193 | PTPI0140_IP | 02.Interface | 01.IP - Intel Product | Interface from S4 to E2Open to send SA delivery schedule lines | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/193_PM-080-060-0007_PTP_E2Open_Send%20SA%20Delivery%20Schedule%20Lines_3A4_3A8_Intel%20Products.pptx?d=wa63ea19871c84755b96699f19a5ce1cb&csf=1&web=1&e=yEsCOh | 02.No | 01.Yes | PTPE0918 PTPE0606 PTPE0259 | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-05-30 | 2024-06-14 | 2024-06-14 | 100% | 2024-07-12 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-19 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2025-03-17 | 2025-03-21 | 2024-10-25 | 100% | 2024-11-26 | 2025-01-24 | 2025-07-24 | 2025-07-24 | 100% | 2025-07-24 | 2024-11-26 | 2025-07-24 | Yes | 2025-07-28 | 2024-11-01 | 2024-11-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-09-05 | 2024-11-08 | N | 100% | 2025-09-16 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-07-24 | 2025-07-24 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0140 |  | R3 ITC1 |  |  |  |  | 04. Enhanced IDOC |  | 2024-07-12 | 2024-07-12 | 2024-07-12 |  | 2024-08-19 | 2024-08-19 | 2024-08-19 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2025-03-21 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2024-11-26 | 2025-07-24 |  |  | 2025-09-16 | 2025-09-16 | 2025-09-16 |  |  |  |  | B2B - E2open | 2024-06-14 | 2024-09-13 | 2024-10-25 | S4 | 2025-04-09 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 2350 | [7 empty] | 3. Off Track | 25. Requirement Change | 9/12- Sent for approval 9/12- Sent for approval 9/10 FUT Completed. Submitted for approval. B-app screenshots are pending to be attached. 9/8 -PTPI0140_IP and IF is currently in progress but there is a CR in place. Its currently being developed and ETA is today. 25/7 - B2B was not ready and the decision to test the E2E came later after scheduling it. | 2025-07-24 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | Yes | Custom table entries change | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 194 | PTPI0140_IF | 02.Interface | 02.IF - Intel Foundry | Interface from S4 to E2Open to send SA delivery schedule lines | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/194_PM-080-060-0008_PTP_E2Open_Send%20SA%20Delivery%20Schedule%20Lines_3A4_3A8_Intel%20Foundry.pptx?d=w6da0c14464414a80929c3ebd5e2b2359&csf=1&web=1&e=Swq59M | 02.No | 01.Yes | PTPE0918 PTPE0606 PTPE0259 | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-05-30 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-10-25 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-08 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-15 | 2025-03-17 | 2025-03-21 | 2024-11-15 | 100% | 2024-11-26 | 2025-01-24 | 2025-07-24 | 2025-07-24 | 100% | 2025-07-24 | 2024-11-26 | 2025-07-24 | Yes | 2025-07-28 | 2024-11-01 | 2024-11-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-09-05 | 2024-11-08 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-07-24 | 2025-07-24 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0140_IP | 02.High | 0.6 | 0.87 | 0140 |  | R3 ITC1 |  |  |  |  | 04. Enhanced IDOC |  | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-15 |  | 2024-11-15 |  | 2025-03-21 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2024-11-26 | 2025-07-24 |  |  | 2025-09-03 | 2025-09-05 | 2025-09-03 |  |  |  |  | B2B - E2open | 2024-08-23 | 2024-09-13 | 2024-11-15 | S4 | 2025-04-09 |  |  |  | 0 |  | 2797 | [9 empty] | 9/19 9/12- Sent for approval 9/10 FUT Completed. Submitted for approval. B-app screenshots are pending to be attached. 9/8 -PTPI0140_IP and IF is currently in progress but there is a CR in place. Its currently being developed and ETA is today. 25/7 - B2B was not ready and the decision to test the E2E came later after scheduling it. | 2025-07-24 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 192 | PTPI0138 | 02.Interface | 02.IF - Intel Foundry | Interface from S4 to OpenText to send new purchase orders & purchase order changes | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/192_PM-080-060-0006_PTP_OpenText_Send_PO_New_Update_3A4R_3A8R_Intel%20Foundry.pptx?d=wb2388eb78e5c4b539b2753a62da6074c&csf=1&web=1&e=GrUfnP | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | GXS (Open text) | MULESOFT | 2024-05-30 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-08-26 | 2024-09-06 | 2025-02-21 | 100% | 2025-02-05 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2025-04-21 | 2025-05-16 | 2024-10-25 | 100% | 2024-11-26 | 2024-08-26 | 2025-04-20 | 2025-04-20 | 100% | 2025-04-20 | 2024-11-26 | 2025-04-20 | Yes | 2025-08-12 | 2025-09-19 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-04-23 04:10 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0138 | INT-CR0168 | R3 ITC1 |  |  |  |  | 04. Enhanced IDOC |  | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2025-05-16 | 2024-11-26 | 2024-11-26 |  | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2024-11-26 | 2025-04-20 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  |  |  |  | B2B - OpenText | 2024-08-23 | 2024-11-01 | 2024-10-25 |  | 2025-09-26 |  | WIINGS |  | 0 | 04.7 Logistics - GFM | 2347 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/16 EP: Update FUT Revised End date & ETA for approval. Awaiting approval from Intel. 10/3- 13 hours CR raised and dropped mail to Jose for approval. | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 189 | PTPI0136_IP | 02.Interface | 01.IP - Intel Product | Interface from S4 to E2open to send new purchase orders, purchase order changes & schedule agreement headers | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/189-PM-080-060-0003_PTP_E2Open_Send_PO_SA%20Request_3A4_3A8_Intel%20Products.pptx?d=w5aad77feea66421f840ad9532eb239ba&csf=1&web=1&e=GHEb87 | 02.No | 01.Yes | PTPE0606, PTPE0259, PTPE0543 | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-05-30 | 2024-06-14 | 2024-06-14 | 100% | 2024-07-12 | 2024-06-17 | 2024-09-06 | 2025-02-21 | 100% | 2025-02-05 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | 2024-11-15 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-22 | 2025-04-21 | 2025-05-16 | 2024-11-22 | 100% | 2024-11-14 | 2025-06-25 | 2025-11-10 | 2025-11-10 | 100% | 2026-01-05 | 2024-11-14 | 2026-01-05 | Yes |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-11-10 | 2025-11-10 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0136 | INT-CR0168 | R3 ITC1 |  |  |  |  | 04. Enhanced IDOC |  | 2024-07-12 | 2024-07-12 | 2024-07-12 |  | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2024-11-01 | 2024-11-01 |  |  |  | 2024-11-22 |  | 2024-11-22 |  | 2025-05-16 | 2024-11-14 | 2024-11-14 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2024-11-14 | 2026-01-05 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  |  |  |  | B2B - E2open | 2024-06-14 | 2024-11-01 | 2024-11-22 | MW | 2025-04-04 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 2712 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/22 - Awaiting for B-App screenshots and Jose to mark 100% 10/10 More Test cases are being performed along with CR0868 - Implementation in Progress. ETA 10/14 10/3- More test cases to be added as suggested by business 9/29 - Submitted for approval 9/19 This will be spilled over as CR and E2open readiness - 1 test case left 9/12- THis will be spilled over as CR and E2open readiness" 10/10 More Test cases are being performed along with CR0868 - Implementation in Progress. ETA 10/14 10/3- More test cases to be added as suggested by business 9/29 - Submitted for approval 9/19 This will be spilled over as CR and E2open readiness - 1 test case left 9/12- THis will be spilled over as CR and E2open readiness | 2025-11-10 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 21 |  | 2024-11-01 | 2024-11-01 | Yes | Custom table entries change | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 190 | PTPI0136_IF | 02.Interface | 02.IF - Intel Foundry | Interface from S4 to E2open to send new purchase orders, purchase order changes & schedule agreement headers | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/190-PM-080-060-0004_PTP_E2Open_Send_PO_SA%20Request_3A4_3A8_Intel%20Foundry.pptx?d=wf8fab8d1caf645c6831ddf6c851c6b5e&csf=1&web=1&e=6GFpxf | 02.No | 01.Yes | PTPE0606, PTPE0259, PTPE0543 | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-05-30 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-08-26 | 2024-09-06 | 2025-02-21 | 100% | 2025-02-05 | 2024-12-16 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-18 | 2024-12-16 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-18 | 2024-11-15 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-22 | 2025-04-21 | 2025-05-16 | 2024-11-22 | 100% | 2024-11-14 | 2025-06-25 | 2025-11-10 | 2025-11-10 | 100% | 2026-01-05 | 2024-12-18 | 2026-01-05 | Yes |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-11-10 | 2025-11-10 | pgaroo@deloitte.com | 2024-04-23 04:10 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPI0136_IP | 02.High | 0.6 | 0.87 | 0136 | INT-CR0168 | R3 ITC1 |  |  |  |  | 04. Enhanced IDOC |  | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2024-12-18 | 2025-01-24 | 2024-12-18 | 2024-12-18 |  | 2024-11-22 |  | 2024-11-22 |  | 2025-05-16 | 2024-11-14 | 2024-11-14 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2024-12-18 | 2026-01-05 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  |  |  |  | B2B - E2open | 2024-08-23 | 2025-01-24 | 2024-11-22 | S4 | 2025-04-04 |  | WIINGS |  | 0 | 01.4 Suppliers that engage with E2Open | 2714 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/24 - This is approved and marked as 100% from FUT side. 10/22 - Awaiting for B-App screenshots and Jose to mark 100% 10/10 More Test cases are being performed along with CR0868 - Implementation in Progress. ETA 10/14 10/3- More test cases to be added as suggested by business 9/29 - Submitted for approval 9/19 This will be spilled over as CR and E2open readiness - 1 test case left 9/12- THis will be spilled over as CR and E2open readiness" 10/10 More Test cases are being performed along with CR0868 - Implementation in Progress. ETA 10/14 10/3- More test cases to be added as suggested by business 9/29 - Submitted for approval 9/19 This will be spilled over as CR and E2open readiness - 1 test case left 9/12- THis will be spilled over as CR and E2open readiness | 2025-11-10 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 21 |  | 2025-01-24 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 187 | PTPI0134_IP | 02.Interface | 01.IP - Intel Product | Interface from S4 to E2Open for SIMS Master Data & supply demand elements | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/187_PM-080-060_0001_PTP_E2Open_SIMS_Master_data_and%20SDE_Intel%20Products.pptx?d=we46c30f7079b4f73a8a7585ba228ebff&csf=1&web=1&e=YK36UK | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-06-10 | 2024-06-28 | 2024-06-28 | 100% | 2024-08-07 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 100% | 2024-09-26 | 2024-12-16 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-18 | 2024-12-16 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-18 | 2024-11-15 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-22 | 2024-10-25 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-22 | 2024-11-11 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-14 | 2024-12-18 | 2025-02-14 | Yes | 2025-07-28 | 2025-07-18 | 2025-08-29 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-24 | 2025-02-14 | 2025-02-14 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0134 |  | R3 ITC1 | [6 empty] | 2024-08-07 | 2024-08-07 | 2024-08-07 |  | 2024-09-26 | 2024-10-18 | 2024-09-26 |  | 2024-12-18 | 2025-01-24 | 2024-12-18 | 2024-12-18 |  | 2024-11-22 |  | 2024-11-22 |  | 2024-11-22 | 2024-11-22 | 2024-11-22 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2024-12-18 | 2025-02-14 |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 |  |  |  |  | B2B - E2open | 2024-06-28 | 2025-01-24 | 2024-11-22 | S4 | 2025-04-03 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 2710 | [7 empty] | 1. On Track | 3. Awaiting Approval | FUT Complete. Awaiting E2O to test in touchless mode and attach screenshots to the FUT document. Then it would be routed for approval. | 2025-02-14 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-24 | 2024-12-18 | Yes | Custom table entries change | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 188 | PTPI0134_IF | 02.Interface | 02.IF - Intel Foundry | Interface from S4 to E2Open for SIMS Master Data & supply demand elements | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/188_PM-080-060-0002_PTP_E2Open_SIMS_Master_data_and%20SDE_Intel%20Foundry.pptx?d=w4c6664cc245c41859412d681040adae7&csf=1&web=1&e=iSPq2v | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-06-10 | 2024-08-23 | 2024-08-23 | 100% | 2024-09-03 | 2024-10-11 | 2024-10-18 | 2024-10-18 | 100% | 2024-09-26 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-02-21 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2024-12-19 | 2024-11-11 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-14 | 2025-01-07 | 2025-02-14 | Yes | 2025-07-28 | 2025-07-18 | 2025-08-29 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0134_IP | 02.High | 0.6 | 0.87 | 0134 |  | R3 ITC1 | [6 empty] | 2024-09-03 | 2024-09-03 | 2024-09-03 |  | 2024-09-26 | 2024-10-18 | 2024-09-26 |  | 2025-01-07 | 2025-02-21 | 2025-01-07 | 2025-01-07 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-01-24 | 2024-12-19 | 2024-12-19 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-01-07 | 2025-02-14 |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 |  |  |  |  | B2B - E2open | 2024-08-23 | 2025-02-21 | 2025-01-24 | S4 | 2025-04-03 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 2711 | [9 empty] | FUT Complete. Awaiting E2O to test in touchless mode and attach screenshots to the FUT document. Then it would be routed for approval. | 2025-02-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 182 | PTPI0133 | 02.Interface | 02.IF - Intel Foundry | Get OA determination by material from IF to SIRFIS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/182_PM-090-060-0012_PTP_SIRFIS_Get%20OA%20determination%20by%20material%20from%20IF%20to%20SIRFIS.pptx?d=w78062827865c4b2c9fc4980c3f5bf1ef&csf=1&web=1&e=HQB7XJ | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | SIRFIS | S/4 | APIGEE | 2024-07-22 | 2024-06-26 | 2024-06-26 | 100% | 2024-07-24 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-22 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-04 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-24 | 2025-05-03 | 2025-07-22 | 2025-07-22 | 100% | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-09-13 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-20 | 2024-09-20 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-22 | 2025-07-22 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0133 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-07-24 | 2024-07-24 | 2024-07-24 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-04 |  | 2024-10-04 |  | 2024-10-04 | 2024-09-24 | 2024-09-24 |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-26 | 2024-09-13 | 2024-10-04 | S4 | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 2707 | [10 empty] | 2025-07-22 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 180 | PTPI0131 | 02.Interface | 02.IF - Intel Foundry | Get Outline Agreement data from IF to SIRFIS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/180_PM-090-060-0008_PTP_SIRFIS_Get%20Outline%20Agreement%20data%20from%20IF%20to%20SIRFIS.pptx?d=w0b412a2396e840acbb1b90b1d054845c&csf=1&web=1&e=0zoBmx | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | SIRFIS | S/4 | APIGEE | 2024-07-22 | 2024-08-19 | 2024-08-19 | 100% | 2024-08-13 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-27 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-05-03 | 2025-07-22 | 2025-07-22 | 100% | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-10-08 | 2024-10-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-30 | 2024-10-17 | 2024-10-17 | N | 100% | 2024-12-06 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-25 | 2025-07-22 | 2025-07-22 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0131 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-08-13 | 2024-08-19 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | [5 empty] | 2024-08-19 | 2024-10-04 | 2024-10-25 | MW | 2024-10-17 |  |  |  | 0 | 08. Not Applicable | 2706 | [10 empty] | 2025-07-22 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-10-04 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 472 | PTPI0111_IP | 02.Interface | 01.IP - Intel Product | PO change (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-100-0007_PTP_Ariba%20PO%20change%20%20(Custom%20logic)_Intel%20Products.pptx?d=w828d9258f61641cb90f455817191adc0&csf=1&web=1&e=5qMDxc | 02.No | 01.Yes | PTPE0656_IP | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-05-31 | 2024-06-17 | 2024-06-17 | 100% | 2024-06-19 | 2024-07-12 | 2024-07-19 | 2024-07-19 | 100% | 2024-06-28 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2024-11-26 | 2025-08-26 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-13 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-22 01:01 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0111 |  | R3 ITC1 | [6 empty] | 2024-06-19 | 2024-06-19 | 2024-06-19 |  | 2024-06-28 | 2024-07-19 | 2024-06-28 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2024-11-26 | 2025-08-26 |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 |  |  |  |  | Ariba | 2024-06-17 | 2024-09-13 | 2025-01-10 | S4 | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 1957 | [7 empty] | 5. Not Dispositioned |  | 9/1- Send for approval | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-11-26 | 2024-11-26 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 473 | PTPI0111_IF | 02.Interface | 02.IF - Intel Foundry | PO change (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-100-0008_PTP_Ariba%20PO%20change%20%20(Custom%20logic)_Intel%20Factory.pptx?d=wdf73389f69e748b6a56d62b2b6ad60fe&csf=1&web=1&e=hvcCDK | 02.No | 01.Yes | PTPE0656_IF | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-05-31 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-12-16 | 2025-01-07 | 2025-09-26 | 100% | 2024-06-28 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2024-10-01 | 2025-08-26 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2024-10-04 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-22 01:01 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0111_IP | 03.Medium | 0.3 | 0.435 | 0111 |  | R3 ITC1 | [6 empty] | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2024-06-28 | 2025-09-26 | 2024-06-28 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 | 2024-10-01 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2024-10-01 | 2025-08-26 |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 |  |  |  |  | Ariba | 2024-08-23 | 2024-10-04 | 2025-01-10 | S4 | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 1958 | [7 empty] | 5. Not Dispositioned |  | 9/1- Send for approval | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-10-04 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 172 | PTPI0110 | 02.Interface | 02.IF - Intel Foundry | Get PO details from IF to SIRFIS | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/172_PM-080-070-0008_PTP_SIRFIS_Get%20PO%20details%20from%20IF%20to%20SIRFIS.pptx?d=w488df4724ec94a49afcd3adea3cf1124&csf=1&web=1&e=bqXCdy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | SIRFIS | S/4 | APIGEE | 2024-06-06 | 2024-06-19 | 2024-06-19 | 100% | 2024-06-18 | 2024-07-12 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-19 | 2024-08-23 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-08-02 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-20 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-09-30 | 2025-05-07 | 2025-07-22 | 2025-07-22 | 100% | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-09-06 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-13 | 2024-09-13 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2025-07-22 | 2025-07-22 | pgaroo@deloitte.com | 2024-04-22 01:01 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0110 |  | R3 ITC1 |  |  |  |  | 01. Standard API |  | 2024-06-18 | 2024-06-19 | 2024-06-18 |  | 2024-07-19 | 2024-07-19 | 2024-07-19 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-09-27 |  | 2024-09-27 |  | 2024-10-04 | 2024-09-30 | 2024-09-30 |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2024-11-26 | 2025-07-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-19 | 2024-08-30 | 2024-09-27 | S4 | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1492 | [10 empty] | 2025-07-22 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 476 | PTPI0107_IP | 02.Interface | 01.IP - Intel Product | PO Cancel | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-110-0001_PTP_Ariba%20PO%20cancel_Intel%20Products.pptx?d=we41373389a9d498fa0f33d72a4025046&csf=1&web=1&e=wlQXAb | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-06-03 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-10-07 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-10-07 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2025-10-07 | 2025-10-07 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-22 01:01 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0107 |  | R3 ITC1 | [6 empty] | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-10-07 | 2025-10-07 |  |  | 2025-09-10 | 2025-09-12 | 2025-09-10 |  |  |  |  | Ariba | 2024-08-23 | 2025-05-16 |  | S4 | 2025-06-03 |  |  |  | 0 | 08. Not Applicable | 1961 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-05 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 477 | PTPI0107_IF | 02.Interface | 02.IF - Intel Foundry | PO Cancel | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-110-0002_PTP_Ariba%20PO%20cancel_Intel%20Factory.pptx?d=wc1541981e8b14d288de3a09395ad7da3&csf=1&web=1&e=e7p4m8 | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-06-03 | 2024-06-26 | 2024-06-26 | 100% | 2024-06-19 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-10-07 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-10-07 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2025-10-07 | 2025-10-07 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0107_IP | 03.Medium | 0.3 | 0.435 | 0107 |  | R3 ITC1 | [6 empty] | 2024-06-19 | 2024-06-26 | 2024-06-19 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-10-07 | 2025-10-07 |  |  | 2025-09-04 | 2025-09-12 | 2025-09-04 |  |  |  |  | Ariba | 2024-06-26 | 2025-06-13 |  | S4 | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 1962 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 466 | PTPI0103_IP | 02.Interface | 01.IP - Intel Product | PO create (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-050-0005_PTP_Ariba%20PO%20Create_Intel%20Products.pptx?d=w08a16c424a224c06be1d7d94625ec837&csf=1&web=1&e=1fNXNe | 02.No | 01.Yes | PTPE0656_IP | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-05-31 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-08-26 | 2024-08-30 | 2025-09-26 | 100% | 2025-09-18 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2024-09-26 | 2025-08-26 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-27 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-22 01:01 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0103 |  | R3 ITC1 | [6 empty] | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2025-09-18 | 2025-09-26 | 2025-09-18 |  | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-26 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2024-09-26 | 2025-08-26 |  |  | 2025-08-21 | 2025-08-27 | 2025-08-21 |  |  |  |  | Ariba | 2024-08-23 | 2024-09-27 | 2025-01-07 | S4 | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 2384 | [7 empty] | 5. Not Dispositioned |  |  | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-09-27 | 2024-09-26 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 467 | PTPI0103_IF | 02.Interface | 02.IF - Intel Foundry | PO create (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-050-0006_PTP_Ariba%20PO%20Create_Intel%20Factory.pptx?d=wd1c8ec50e801478192ab18825d2c05a8&csf=1&web=1&e=CY8e0i | 02.No | 01.Yes | PTPE0656_IF | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15205 | Shopping@Intel | SAP Ariba Network | S/4 | NA | 2024-05-31 | 2024-06-17 | 2024-06-17 | 100% | 2024-06-18 | 2024-07-05 | 2024-07-12 | 2024-07-12 | 100% | 2024-06-28 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | [10 empty] | 2025-02-01 | 2025-08-26 | 2025-08-26 | 100% | 2025-08-26 | 2024-09-26 | 2025-08-26 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-27 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0103_IP | 03.Medium | 0.3 | 0.435 | 0103 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-06-28 | 2024-07-12 | 2024-06-28 |  | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-26 | [9 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2024-09-26 | 2025-08-26 |  |  | 2025-08-21 | 2025-08-27 | 2025-08-21 |  |  |  |  | Ariba | 2024-06-17 | 2024-09-27 | 2025-01-10 | S4 | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 2386 | [7 empty] | 5. Not Dispositioned |  |  | 2025-08-26 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-09-27 | 2024-09-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 465 | PTPI0100_IP | 02.Interface | 01.IP - Intel Product | PR Cancel | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0026_PTP_Ariba%20PR%20Cancel_Intel%20Products.pdf?csf=1&web=1&e=XOVhDw | 02.No | 01.Yes |  | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-06-24 | 2024-07-25 | 2024-07-25 | 100% | 2024-07-24 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-04-07 | 2025-04-18 | 2025-06-11 | 100% | 2025-09-29 | 2025-04-07 | 2025-04-18 | 2025-06-11 | 100% | 2025-09-29 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-09-29 | 2025-09-29 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0100 |  | R3 ITC1 | [6 empty] | 2024-07-24 | 2024-07-25 | 2024-07-24 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-09-29 | 2025-09-29 |  |  | 2025-09-04 | 2025-09-12 | 2025-09-04 |  |  |  |  | Ariba | 2024-07-25 | 2025-04-18 |  | S4 | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1779 | [7 empty] | 5. Not Dispositioned |  |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-29 | 2025-09-29 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 464 | PTPI0100_IF | 02.Interface | 02.IF - Intel Foundry | PR Cancel | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0025_PTP_Ariba%20PR%20Cancel_Intel%20Factory.pdf?csf=1&web=1&e=IGmwhI | 02.No | 01.Yes |  | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-06-24 | 2024-07-25 | 2024-07-25 | 100% | 2024-07-19 | 2025-03-17 | 2025-03-21 | 2025-11-28 | 100% | 2025-11-21 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-10-07 | 2025-06-02 | 2025-06-13 | 2025-06-11 | 100% | 2025-10-07 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-10-07 | 2025-10-07 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0100_IP | 03.Medium | 0.3 | 0.435 | 0100 |  | R3 ITC1 | [6 empty] | 2024-07-19 | 2024-07-25 | 2024-07-19 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-10-07 | 2025-10-07 |  |  | 2025-09-04 | 2025-09-12 | 2025-09-04 |  |  |  |  | Ariba | 2024-07-25 | 2025-06-13 |  | S4 | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2834 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 463 | PTPI0098_IP | 02.Interface | 01.IP - Intel Product | PR change (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0024_PTP_Ariba%20PR%20Change_Intel%20Products.pdf?csf=1&web=1&e=GI7F56 | 02.No | 01.Yes | PTPE0472_IP | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-05-27 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-12 | 2024-12-16 | 2025-01-07 | 2025-09-26 | 100% | 2025-09-17 | 2024-08-16 | 2024-09-13 | 2025-02-28 | 100% | 2025-02-09 | 2024-08-16 | 2024-09-13 | 2025-02-28 | 100% | 2025-02-09 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2025-02-09 | 2025-06-30 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-13 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0098 |  | R3 ITC1 | [6 empty] | 2024-08-12 | 2024-08-23 | 2024-08-12 |  | 2025-09-17 | 2025-09-26 | 2025-09-17 |  | 2025-02-09 | 2025-02-28 | 2025-02-09 | 2025-02-09 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-02-09 | 2025-06-30 |  |  | 2025-08-21 | 2025-08-27 | 2025-08-21 |  |  |  |  | Ariba | 2024-08-23 | 2024-09-13 | 2025-01-10 | S4 | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2833 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-02-28 | 2025-02-09 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 462 | PTPI0098_IF | 02.Interface | 02.IF - Intel Foundry | PR change (Custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0023_PTP_Ariba%20PR%20Change_Intel%20Fatcrory.pdf?csf=1&web=1&e=Yza1Rx | 02.No | 01.Yes | PTPE0472_IF | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-06-07 | 2024-06-26 | 2024-06-26 | 100% | 2024-06-19 | 2024-09-13 | 2024-09-20 | 2024-09-20 | 100% | 2024-08-13 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2024-09-26 | 2025-06-30 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-27 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0098_IP | 03.Medium | 0.3 | 0.435 | 0098 |  | R3 ITC1 | [6 empty] | 2024-06-19 | 2024-06-26 | 2024-06-19 |  | 2024-08-13 | 2024-09-20 | 2024-08-13 |  | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-26 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2024-09-26 | 2025-06-30 |  |  | 2025-08-21 | 2025-08-27 | 2025-08-21 |  |  |  |  | Ariba | 2024-06-26 | 2024-09-27 | 2025-01-10 | S4 | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2832 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-09-27 | 2024-09-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 461 | PTPI0096_IP | 02.Interface | 01.IP - Intel Product | PR creation (budget check, custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0022_PTP_Ariba%20PR%20Creation%20Budget_Intel%20Products.pdf?csf=1&web=1&e=8XHvv6 | 02.No | 01.Yes | PTPE0472_IP | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-04-29 | 2024-11-20 | 2024-05-24 | 100% | 2024-05-22 | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 2024-06-14 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2024-09-26 | 2025-06-30 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-27 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0096 |  | R3 ITC1 | [6 empty] | 2024-05-22 | 2024-11-20 | 2024-05-22 |  | 2024-06-14 | 2024-06-14 | 2024-06-14 |  | 2024-09-26 | 2024-09-27 | 2024-09-26 | 2024-09-26 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2024-09-26 | 2025-06-30 |  |  | 2025-08-27 | 2025-08-27 | [5 empty] | Ariba | 2024-11-20 | 2024-09-27 | 2025-01-10 | S4 | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2831 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-09-27 | 2024-09-26 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 460 | PTPI0096_IF | 02.Interface | 02.IF - Intel Foundry | PR creation (budget check, custom logic) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0021_PTP_Ariba%20PR%20Creation%20Budget_Intel%20Foundry.pdf?csf=1&web=1&e=5PTash | 02.No | 01.Yes | PTPE0472_IF | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | SAP Ariba Network | S/4 | NA | 2024-04-29 | 2024-11-20 | 2024-05-24 | 100% | 2024-05-22 | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 2024-06-14 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-16 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [10 empty] | 2025-02-01 | 2025-06-30 | 2025-06-30 | 100% | 2025-06-30 | 2024-11-26 | 2025-06-30 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2024-09-13 | 2025-06-30 | 2025-06-30 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0096_IP | 03.Medium | 0.3 | 0.435 | 0096 |  | R3 ITC1 | [6 empty] | 2024-05-22 | 2024-11-20 | 2024-05-22 |  | 2024-06-14 | 2024-06-14 | 2024-06-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [9 empty] | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2024-11-26 | 2025-06-30 |  |  | 2025-08-18 | 2025-08-27 | 2025-08-18 |  |  |  |  | Ariba | 2024-11-20 | 2024-09-13 | 2025-01-10 | S4 | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2830 | [7 empty] | 5. Not Dispositioned |  |  | 2025-06-30 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 459 | PTPI0094_IP | 02.Interface | 01.IP - Intel Product | validate and enrich (PR - master data and custom code) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0020_PTP_Ariba%20Validate%20and%20Enrich_Intel%20Products.pdf?csf=1&web=1&e=yXjHUs | 02.No | 01.Yes |  | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | S/4 | SAP Ariba Network | MULESOFT | 2024-05-27 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 2024-06-14 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-19 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-19 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-11-22 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-10 | 2025-07-21 | 2025-08-18 | 2025-08-18 | 100% | 2025-08-18 | 2024-12-10 | 2025-08-18 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2025-08-18 | 2025-08-18 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0094 | INT-CR0721 | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-06-14 | 2024-06-14 | 2024-06-14 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-12-20 | 2024-12-10 | 2024-12-10 |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2024-12-10 | 2025-08-18 |  |  | 2025-08-27 | 2025-08-27 | [5 empty] | Ariba | 2024-05-24 | 2024-09-27 | 2024-10-25 | MW | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2829 | [10 empty] | 2025-08-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2024-10-19 | 2024-10-19 | Yes | ZTPTP_GR_MAP, ZTPTP_BILLID, ZTPTP_ARIBA_CURR & ZTPTP_ARIBA_FEP contains LE/Plant details, entries to be maintained for required LE | Yes | Regression testing only | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 458 | PTPI0094_IF | 02.Interface | 02.IF - Intel Foundry | validate and enrich (PR - master data and custom code) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-070-080-0019_PTP_Ariba%20Validate%20and%20Enrich_Intel%20Foundry.pptx?d=w2cf8e1a833e340369ba406ab58cc06d6&csf=1&web=1&e=nuLY3z | 02.No | 01.Yes |  | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | S/4 | SAP Ariba Network | MULESOFT | 2024-05-27 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-06-07 | 2024-06-14 | 2024-06-14 | 100% | 2024-11-26 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-19 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-19 | 2024-12-16 | 2024-01-24 | 2024-10-25 | 100% | 2024-10-25 | 2024-11-22 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-10 | 2025-07-21 | 2025-08-17 | 2025-08-17 | 100% | 2025-08-17 | 2024-12-10 | 2025-08-17 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2025-08-17 | 2025-08-17 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0094_IP | 03.Medium | 0.3 | 0.435 | 0094 | INT-CR0721 | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-12-20 | 2024-12-10 | 2024-12-10 |  | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2024-12-10 | 2025-08-17 |  |  | 2025-08-18 | 2025-08-27 | 2025-08-18 |  |  |  |  | Ariba | 2024-05-24 | 2024-09-27 | 2024-01-24 | MW | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2826 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix |  | 2025-08-17 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2024-10-19 | 2024-10-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 457 | PTPI0092_IP | 02.Interface | 01.IP - Intel Product | Transfer of Ownership (change Ariba PR/PO) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0018_PTP_Ariba%20Transfer%20of%20Ownership_Intel%20Products.pdf?csf=1&web=1&e=0bI4SX | 02.No | 01.Yes | PTPE0729_IP | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | S/4 | SAP Ariba Network | APIGEE | 2024-07-01 | 2024-12-20 | 2024-07-25 | 100% | 2024-12-20 | 2025-02-07 | 2025-02-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-21 | 2025-04-04 | 2025-04-11 | 100% | 2025-04-14 | 2025-05-15 | 2025-10-11 | 2025-10-11 | 100% | 2025-09-15 | 2025-08-04 | 2025-09-15 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-04 | 2025-10-11 | 2025-10-11 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0092 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-04-14 | 2025-04-14 | 2025-04-14 |  | 2025-10-11 | 2025-09-15 | 2025-09-15 | 2025-08-04 | 2025-09-15 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | Ariba | 2024-12-20 | 2025-03-21 | 2025-05-30 | S4 | 2025-06-03 |  |  |  | 0 | 08. Not Applicable | 2777 | [7 empty] | 3. Off Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/25 Awaiting Intel approval - Luis and Jorge 11/18 Issue with Security authorization. Fix in Progress 11/14 - Defect 4598. Tech team ETA is 11/14. FUT Completion is 11/19 11/11 : RAID 3039 raised for Luis to check on ARIBA side - Ariba is not sending the payload to APIGEE, webservice task is in error 11/11 - MW Team is still working on the CR Changes. ETA is 11/11 11/3 Blocked by INT-Build-CR1016 being worked by M/W Team. ETA 11/6 10/27 Blocked by Design Change. Limitation on Ariba capability to segregate data into IP and IF. Re-Design in discussion with Intel Process Stewards and SAP Team. *Roadblocked* Object 10/22 - Limitation of Segregation of IP and IF data | 2025-10-11 | N | 06. PTP |  |  |  | Submitted for approval | Note to Jose | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 456 | PTPI0092_IF | 02.Interface | 02.IF - Intel Foundry | Transfer of Ownership (change Ariba PR/PO) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-070-080-0017_PTP_Ariba%20Transfer%20of%20Ownership_Intel%20Foundry.pdf?csf=1&web=1&e=2UUooy | 02.No | 01.Yes | PTPE0729_IF | 2024-04-21 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 15206; 18292; 16048; 19569; 13370 | SAP Ariba Network; SAP Ariba Invoicing; SAP Ariba Mobile; SAP Ariba Cloud; SAP Ariba Procurement Content Marketplace | S/4 | SAP Ariba Network | APIGEE | 2024-07-01 | 2024-12-20 | 2024-07-25 | 100% | 2024-12-20 | 2025-02-07 | 2025-02-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-21 | 2025-04-04 | 2025-04-11 | 100% | 2025-04-14 | 2025-05-15 | 2025-10-11 | 2025-10-11 | 100% | 2025-09-15 | 2025-08-04 | 2025-09-15 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-04 | 2025-10-11 | 2025-10-11 | jenoronha@deloitte.com | 2024-04-21 00:41 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | PTPI0092_IP | 03.Medium | 0.3 | 0.435 | 0092 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-04-14 | 2025-04-14 | 2025-04-14 |  | 2025-10-11 | 2025-09-15 | 2025-09-15 | 2025-08-04 | 2025-09-15 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | Ariba | 2024-12-20 | 2025-03-21 | 2025-05-30 | S4 | 2025-06-03 |  |  |  | 0 | 08. Not Applicable | 2776 | [7 empty] | 3. Off Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/25 Awaiting Intel approval - Luis and Jorge 11/18 Issue with Security authorization. Fix in Progress 11/14 - Defect 4598. Tech team ETA is 11/14. FUT Completion is 11/19 11/11 : RAID 3039 raised for Luis to check on ARIBA side - Ariba is not sending the payload to APIGEE, webservice task is in error 11/11 - MW Team is still working on the CR Changes. ETA is 11/11 11/3 Blocked by INT-Build-CR1016 being worked by M/W Team. ETA 11/6 10/27 Blocked by Design Change. Limitation on Ariba capability to segregate data into IP and IF. Re-Design in discussion with Intel Process Stewards and SAP Team. *Roadblocked* Object 10/22 - Limitation of Segregation of IP and IF data | 2025-10-11 | N | 06. PTP |  |  |  | Submitted for approval | Note to Jose | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 85 | PTPI0018 | 02.Interface | 02.IF - Intel Foundry | SAP S4 IF Boundary App Interface for updating Requested Dock Date (RDD) for Capital Supporting Item ​ | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-080-010-0005_PTP_RICEFW%20SAP%20S4%20IP%20Boundary%20App%20Interface%20for%20updating%20Requested%20Dock%20Date%20(RDD)%20for%20Capital%20Supporting%20Item%E2%80%8B.pdf?csf=1&web=1&e=29u0kV | 02.No | 01.Yes | PTPE0826 | 2024-03-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | S/4 | SIRFIS | APIGEE | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-06-05 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 100% | 2024-06-24 | 2024-07-26 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-02 | 2024-07-05 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-02 | 2024-05-31 | 2024-06-07 | 2024-06-07 | 100% | 2024-06-07 | 2024-06-14 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-09 | 2025-08-27 | 2025-11-21 | 2025-11-21 | 100% | 2025-11-21 | 2024-08-02 | 2025-11-21 |  |  | 2024-08-09 | 2024-08-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-05 | 2024-08-16 | 2024-08-16 | N | 100% | 2024-12-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-08-02 | 2025-11-21 | 2025-11-21 | pgaroo@deloitte.com | 2024-03-22 00:13 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0018 |  | R3 ITC1 | [6 empty] | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 |  | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2024-06-07 |  | 2024-06-07 |  | 2024-07-12 | 2024-07-09 | 2024-07-09 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2024-08-02 | 2025-11-21 |  |  | 2024-12-20 | 2024-12-20 | 2024-12-20 | [5 empty] | 2024-05-24 | 2024-08-02 | 2024-06-07 | S4 | 2024-08-16 |  |  |  | 0 | 08. Not Applicable | 1481 | [7 empty] | 4. Completed | 17. FUT In progress |  | 2025-11-21 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2024-08-02 | 2024-08-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 86 | PTPI0017 | 02.Interface | 02.IF - Intel Foundry | SAP S4 IF Boundary App Interface for updating POChange/PODeliveryDates - PO SDD, STD for equipment. Synchronous interface (outbound /inbound from SAP)​ | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-080-010-0006_PTP_RICEFW%20SAP%20S4%20IP%20Boundary%20App%20Interface%20for%20updating%20POChange%20PODeliveryDates%20-%20PO%20SDD%20STD%20for%20equipment.%20Synchronous%20interface%20(outbound_inbound%20from%20SAP)%E2%80%8B.pdf?csf=1&web=1&e=ZRb3LQ | 02.No | 01.Yes | PTPE0826 | 2024-03-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 100 | Supplier-Intel Resource, Forecast, Install System | S/4 | SIRFIS | APIGEE | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-06-05 | 2024-05-24 | 2024-05-31 | 2024-05-31 | 100% | 2024-06-24 | 2024-07-26 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-02 | 2024-07-05 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-02 | 2024-05-31 | 2024-06-07 | 2024-06-07 | 100% | 2024-06-07 | 2024-06-14 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-09 | 2025-08-27 | 2025-11-21 | 2025-11-21 | 100% | 2025-11-21 | 2024-08-02 | 2025-11-21 |  |  | 2024-08-09 | 2024-08-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-05 | 2024-08-16 | 2024-08-16 | N | 100% | 2024-12-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-08-02 | 2025-11-21 | 2025-11-21 | pgaroo@deloitte.com | 2024-03-22 00:13 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 2 | 2.9 | 0017 |  | R3 ITC1 | [6 empty] | 2024-06-05 | 2024-06-05 | 2024-06-05 |  | 2024-06-24 | 2024-06-24 | 2024-06-24 |  | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2024-06-07 |  | 2024-06-07 |  | 2024-07-12 | 2024-07-09 | 2024-07-09 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2024-08-02 | 2025-11-21 |  |  | 2024-12-20 | 2024-12-20 | 2024-12-20 | [5 empty] | 2024-05-24 | 2024-08-02 | 2024-06-07 |  | 2024-08-16 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 1482 | [7 empty] | 4. Completed |  |  | 2025-11-21 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2024-08-02 | 2024-08-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2658 | PTPF1384 | 05.Form | 02.IF - Intel Foundry | Exception Notification – Label printing functionality – IF only | 06. PTP | 6.8 PTP - QM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5FAC8D5B-C294-4EC8-935B-B6E2D036E1C1%7D&file=2658_RICEFW_L-040-080_Notification%20Exception%20-%20Label%20printing%20functionality_IF.pptx&wdLOR=cA3CB1082-6B84-4739-AB2E-E83CC51BA2D4&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-06-04 | 2025-06-06 | 2025-07-25 | 100% | 2025-07-24 | 2025-06-09 | 2025-06-20 | 2025-08-08 | 100% | 2025-07-24 | 2025-06-09 | 2025-06-20 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 | Yes |  | 2025-09-02 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-20 | 2025-06-20 | 2025-06-20 | pgaroo@deloitte.com | 2025-04-08 08:07 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-05 | 01.S4 |  |  | 1 | 0.69 | 1384 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-12 | [6 empty] | 2025-05-16 | 2025-06-20 |  |  | 2025-09-12 |  |  |  | 0 |  | 2884 | [9 empty] | 25/7 - Will be taken in next sprint 17 and tracker to be updated | 2025-06-20 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 41 | PTPF0014_IP | 05.Form | 01.IP - Intel Product | PO Output Form Customization - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PM-080-010-0001_PTP_RICEFW%20PO%20Output%20Form%20Customization%20-%20IP.pdf?csf=1&web=1&e=TWPcoh | 02.No | 01.Yes |  | 2024-03-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-05-27 | 2024-05-27 | 2024-05-31 | 100% | 2024-05-31 | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-24 | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-24 | [15 empty] | 2024-06-24 | 2024-06-24 |  |  | 2025-05-07 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-13 | 2025-03-25 | 2024-09-13 | N | 100% | 2025-02-21 | Not Applicable | R3 Build & UT Sprint 10 | 2024-06-21 | 2024-06-21 | 2024-06-21 | pgaroo@deloitte.com | 2024-03-22 00:13 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0014 | INT-CR0288 | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-05-31 | 2024-05-31 |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-06-24 | [12 empty] | 2024-06-24 | 2024-06-24 |  |  | 2025-02-21 | 2025-03-25 | 2025-02-21 | [5 empty] | 2024-05-24 | 2024-06-21 |  |  | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1435 | [10 empty] | 2024-06-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 3 |  | 2024-06-24 | 2024-06-24 | Yes | Custom table entries change | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 40 | PTPF0014_IF | 05.Form | 02.IF - Intel Foundry | PO Output Form Customization - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29%2FPM%2D080%2D010%2D0001%5FPTP%5FRICEFW%20PO%20Output%20Form%20Customization%20%2D%20IF%2Epdf&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29 | 02.No | 01.Yes |  | 2024-03-28 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-05-27 | 2024-05-27 | 2024-05-31 | 100% | 2024-05-31 | 2024-06-03 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-06-03 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 |  |  | 2025-05-07 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-13 | 2025-03-25 | 2024-09-13 | N | 100% | 2025-02-21 | Not Applicable | R3 Build & UT Sprint 10 | 2024-08-16 | 2024-08-16 | 2024-08-16 | jenoronha@deloitte.com | 2024-03-19 05:25 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | PTPF0014_IP | 02.High | 0.4 | 0.276 | 0014 |  | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-05-31 | 2024-05-31 |  |  | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2025-02-21 | 2025-03-25 | 2025-02-21 | [5 empty] | 2024-05-24 | 2024-08-16 |  |  | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 1433 | [10 empty] | 2024-08-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-16 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3029 | PTPE1700 | 04.Enhancement | 01.IP - Intel Product | Enhancement required in the purchase order (change only) to validate if the users add only service line items | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBCCE8C9D-2EE6-4652-94A4-EB60DCB8BC50%7D&file=3029_CR0856_ENG%20HVM%20Rework%20Process_Enhancement%20for%20restriction%20of%20Material%20ID%20addition%20during%20PO%20Change_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-18 | 2024-09-10 | 2025-09-10 | 100% | 2025-09-29 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 |  |  | 2025-12-16 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1700 | INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | [5 empty] | 2024-09-10 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3149 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/5 Awaiting approval from Intel on FUT Results. 12/19- Send for approval awaiting 12/17 - Will be send for approval till tomorrow 12/12 : Defect 5512 raised | 2025-12-05 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3028 | PTPE1699 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required in the purchase requisition (change only) to validate if the users add only service line items | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD3B779C9-655A-47C0-BCB2-D0C81303609A%7D&file=3028_CR0856_ENG%20HVM%20Rework%20Process_%20Enhancement%20for%20restriction%20of%20Material%20IDs%20addition%20during%20PR%20Change_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-18 | 2024-09-10 | 2025-09-10 | 100% | 2025-09-04 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-11-28 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-12-16 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1699 | INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-04 | 2025-09-10 | 2025-09-04 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | [5 empty] | 2024-09-10 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3148 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/5 Awaiting approval from Intel on FUT Results. 12/19- Send for approval awaiting 12/17 - Will be send for approval till tomorrow 12/12 : Defect 5512 raised | 2025-12-05 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3145 | PTPE1687 | 04.Enhancement | 02.IF - Intel Foundry | Automate Warranty Credit Memo Posting | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/INT-CR1381%20Automating%20Warranty%20Credit%20Memo%20Posting.pptx?web=1 | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2026-01-12 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-02 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-11-05 05:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 1687 | INT-CR1381 | R3 ITC1 | [6 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-02 | 2026-03-04 | 2026-03-02 | [5 empty] | 2025-12-03 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3371 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/26: FUT is reviewed with business and submitted for approval. 2/16: FUT is in progress. | 2026-01-09 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2933 | PTPE1656 | 04.Enhancement | 05.CFIN | Enhancement to Update Invoice PAID Status from CFIN to IF & IP ARIBA Standard Tables | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CFC07E3-39DA-4751-86BA-DB6A987A9F61%7D&file=PM-150-020%20Enhacement%20to%20Update%20Invoice%20PAID%20Status%20from%20CFIN%20to%20IF%20&%20IP%20ARIBA%20Standard%20Tables%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-08 | 2025-08-08 | 100% | 2025-10-07 | 2025-09-19 | 2025-09-26 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-08-29 | 2025-09-08 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-12-04 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-06-12 04:42 | cell-link@smartsheet.com | 2026-03-09 08:15 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1656 |  | R3 ITC1 | [6 empty] | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-04 | 2025-12-03 | [5 empty] | 2025-08-08 | 2025-12-05 |  |  | 2025-12-04 |  |  |  | 0 |  | 3103 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/25 FUT completed and shared for approval 11/24 FUT in Progress. Expedited. To be shared for approval by 11/25 11/18 FUT in Progress. Planned to be submitted for approval by 11/28 11/12 - FUT in Progress. | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3121 | PTPE1644 | 04.Enhancement | 01.IP - Intel Product | New Enhancement required for to make PO price updates for HVM OSAT and SIFO orders for no GR and partial GR posted. | 06. PTP | 6.2 PTP - Procurement | 09. FUT Overdue | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3121-PTP_PM-080-050_Enhancement%20to%20make%20PO%20price%20update%20for%20HVM%20OSAT%26SIFO%20%20for%20no%20GR%20and%20partial%20_IP.pptx?d=w91a4d04908bb4bd9b61440d3dd619479&csf=1&web=1&e=HOwOxc | 02.No | 01.Yes |  | 2025-10-23 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2026-01-14 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-17 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-04-07 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-04-07 | [15 empty] | 2026-04-07 | 2026-04-07 |  |  | 2026-03-25 | 2026-03-27 |  | 100% | 60% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 80% | 2026-03-27 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | cell-link@smartsheet.com | 2026-04-06 14:43 | 9 | 2025-10-23 | 01.S4 |  |  | 2 | 2 | 1644 | INT-CR1213 | R3 ITC1 | [6 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | [12 empty] | 2026-04-07 | 2026-04-07 |  |  |  | 2026-03-27 | [6 empty] | 2025-12-03 | 2026-02-06 |  |  | 2026-03-04 |  |  |  | 0 |  | 3303 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 4/3 Review comments incorporated and re-shared for approval business approval is Awaiting approval. ETA 4/7 3/30 Review comments incorporated and re-shared for approval. AWaiting approval. ETA 3/31 3/27 - Review comments in progress 3/23 FUT is shared for approval. Review comments received which have been updated. 3/20- Send for approval 3/12 Awaiting Build completion from Tech Team. 3/5 Development not complete. Awaiting Tech Team to complete. 2/16 - Awaiting Tech team to confirm once the build is completed. 2/18 - Awaiting Tech team to confirm once the build is completed. | 2026-02-06 | N | 06. PTP |  |  |  | 03/23: Submitted for Approval. ETA 03/27 | FS already complete. To be added in S21 plan. |  | On track for S23+ | Awaiting approval | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-04-07 | 2026-04-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3096 | PTPE1628_IP | 04.Enhancement | 01.IP - Intel Product | INT-CR0941-Develop a custom enhancement in SAP S/4 for Subcon PO BOM comparison and automatic changes based on Product BOM changes – IP and IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3096-PM-110-010_PTP_Subcon%20PO%20BOM%20comparison%20and%20re-explode%20as%20per%20Product%20BOM%20change%E2%80%8B_IF_IP.pptx?d=w960991bc70e2414ea28b0cdcbfa7ea1f&csf=1&web=1&e=n8v3bw | 02.No | 01.Yes |  | 2025-10-23 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-17 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | [15 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-03-25 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-07 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | cell-link@smartsheet.com | 2026-04-06 13:56 | 10 | 2025-10-23 | 01.S4 |  |  | 0.5 | 0.5 | 1628 | INT-CR0941 | R3 ITC1 | [6 empty] | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | [12 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | [5 empty] | 2025-12-03 | 2026-02-06 |  |  | 2026-03-04 |  |  |  | 0 |  | 3305 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 4/3 Review comments incorporated and re-shared for approval. IT approval done. 3/30 Review comments incorporated and re-shared for approval. AWaiting approval. ETA 3/31 3/27 - Review comments in progress 3/23 FUT is shared for approval. Review comments received which have been updated. 3/20- Send for approval 3/12 Awaiting Build completion from Tech Team. 3/5 Development not complete. Awaiting Tech Team to complete. 2/16 - Awaiting Tech team to confirm once the build is completed. 2/18 - Awaiting Tech team to confirm once the build is completed. | 2026-02-06 | N | 06. PTP |  |  |  | 03/23: Submitted for Approval. ETA 03/27 | FS already complete. To be added in S21 plan. |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-05 | No | If plants are getting changed, needs to retest | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3096 | PTPE1628_IF | 04.Enhancement | 02.IF - Intel Foundry | INT-CR0941-Develop a custom enhancement in SAP S/4 for Subcon PO BOM comparison and automatic changes based on Product BOM changes – IP and IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3096-PM-110-010_PTP_Subcon%20PO%20BOM%20comparison%20and%20re-explode%20as%20per%20Product%20BOM%20change%E2%80%8B_IF_IP.pptx?d=w960991bc70e2414ea28b0cdcbfa7ea1f&csf=1&web=1&e=n8v3bw | 02.No | 01.Yes |  | 2025-10-23 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-17 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | [15 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-03-25 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-07 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | cell-link@smartsheet.com | 2026-04-06 13:56 | 10 | 2025-10-23 | 01.S4 | PTPE1628_IP | 04.Low | 0.1 | 0.1 | 1628 | INT-CR0941 | R3 ITC1 | [6 empty] | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | [12 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-04-07 | 2026-04-07 | 2026-04-07 | [5 empty] | 2025-12-03 | 2026-02-06 |  |  | 2026-03-04 |  |  |  | 0 |  | 3307 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 4/3 Review comments incorporated and re-shared for approval. IT approval done. 3/30 Review comments incorporated and re-shared for approval. AWaiting approval. ETA 3/31 3/27 - Review comments in progress 3/23 FUT is shared for approval. Review comments received which have been updated. 3/20- Send for approval 3/12 Awaiting Build completion from Tech Team. 3/5 Development not complete. Awaiting Tech Team to complete. 2/16 - Awaiting Tech team to confirm once the build is completed. 2/18 - Awaiting Tech team to confirm once the build is completed. | 2026-02-06 | N | 06. PTP |  |  |  | 03/23: Submitted for Approval. ETA 03/27 | FS already complete. To be added in S21 plan. |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3103 | PTPE1622 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to update Purchase document amount into USD when BAPP pull data form S4 via API’s GET function for Purchase order, Purchase requisition and Purchase Contract | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3103_R3_PTP_IF_Enhancement%20to%20update%20document%20price%20into%20USD.pptx?d=wfd1465d663f2476e8744aa31fb001718&csf=1&web=1&e=yjUAQH | 02.No | 01.Yes |  | 2025-09-10 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-01 | 2025-10-01 | 100% | 2025-09-26 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-09 22:29 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-10 | 01.S4 |  |  | 1 | 1 | 1622 | INT-CR1129 | R3 ITC1 | [6 empty] | 2025-09-26 | 2025-10-01 | 2025-09-26 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | [5 empty] | 2025-10-01 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3282 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/25 Conditional approval Received with one open item that business needs to confirm to IT. 11/18 FUT completed and submitted for approval. ETA 11/21 for approval 11/12 - FUT in Progress. | 2025-12-05 | Y | 06. PTP |  |  |  |  | Note to Jose |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3102 | PTPE1621 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to deleting all entries from ESH_SR_LTXT and ESH_SR_TXT_OBJ, running the report ESH_SR_LTXT_REPLICATE in Update Run mode will repopulate these tables | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3102_R3_PTP_IF_Enhancement%20to%20run%20report%20for%20ESH_SR_LTXT_REPLICATE.pptx?d=w5df6aac69b8a4922a79b2498980c8c85&csf=1&web=1&e=dcxwOl | 02.No | 01.Yes |  | 2025-09-10 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-01 | 2025-10-01 | 100% | 2025-09-24 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-09 22:29 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-10 | 01.S4 |  |  | 0.5 | 0.5 | 1621 | INT-CR1129 | R3 ITC1 | [6 empty] | 2025-09-24 | 2025-10-01 | 2025-09-24 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-24 | 2025-12-03 | 2025-11-24 | [5 empty] | 2025-10-01 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3281 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 11/18 FUT completed and approved. Jose to mark as 100% 11/12 - FUT in Progress. | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3063 | PTPE1606_IP | 04.Enhancement | 01.IP - Intel Product | Custom enhancement to edit the posted accounting document for Payment Term, Baseline date, and Withholding tax fields. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-170%20PTP%20Custom%20enhancement%20to%20edit%20the%20posted%20accounting%20document%20for%20Payment%20Term%20Baseline%20date%20and%20Withholding%20tax%20fields%20in%20IP%20%26%20IF.pptx?d=wafd9ff290e714d69a8b4680296c69026&csf=1&web=1&e=Mkkgfl | 02.No | 01.Yes |  | 2025-09-24 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-11-14 | 2025-11-28 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-24 | 01.S4 | PTPE1606_CFIN | 03.Medium | 0.2 | 0.2 | 1606 | INT-CR1007 | R3 ITC1 | [6 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | [5 empty] | 2025-10-03 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3274 | [7 empty] | 4. Completed | 7. FUT Defect Retesting | 12/3 FUT in Progress. Planned to be submitted by 12/5 11/24 Issue with CFIN replication. Discussion in Progress 11/18 FUT Defect Retesting. ETA 11/19 11/12 - FUT in Progress. Defect#4488 under Fix by Tech Team | 2025-12-05 | Y | 06. PTP |  |  |  | FUT in Progress. Roadblock removed. Current Status: The existing functionality of this object does meet the requirement. Needs a design change Issue: Current functionality will not help. Needs design change. Next Steps: CR to be created and get the estimates from Tech for the changes. Help needed: Object to get ITC1 exception for the CR build and FUT completion. Will be ready for ITC2. | OSS message SAP Note# 1414705/2025 | 3. Watch item | 3 | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3063 | PTPE1606_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom enhancement to edit the posted accounting document for Payment Term, Baseline date, and Withholding tax fields. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-170%20PTP%20Custom%20enhancement%20to%20edit%20the%20posted%20accounting%20document%20for%20Payment%20Term%20Baseline%20date%20and%20Withholding%20tax%20fields%20in%20IP%20%26%20IF.pptx?d=wafd9ff290e714d69a8b4680296c69026&csf=1&web=1&e=Mkkgfl | 02.No | 01.Yes |  | 2025-09-24 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-11-14 | 2025-11-28 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-24 | 01.S4 | PTPE1606_CFIN | 03.Medium | 0.2 | 0.2 | 1606 | INT-CR1007 | R3 ITC1 | [6 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | [5 empty] | 2025-10-03 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3276 | [7 empty] | 4. Completed | 7. FUT Defect Retesting | 12/3 FUT in Progress. Planned to be submitted by 12/5 11/24 Issue with CFIN replication. Discussion in Progress 11/18 FUT Defect Retesting. ETA 11/19 11/12 - FUT in Progress. Defect#4488 under Fix by Tech Team | 2025-12-05 | Y | 06. PTP |  |  |  | FUT in Progress. Roadblock removed. Current Status: The existing functionality of this object does meet the requirement. Needs a design change Issue: Current functionality will not help. Needs design change. Next Steps: CR to be created and get the estimates from Tech for the changes. Help needed: Object to get ITC1 exception for the CR build and FUT completion. Will be ready for ITC2. | OSS message SAP Note# 1414705/2025 | 3. Watch item | 3 | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3063 | PTPE1606_CFIN | 04.Enhancement | 05.CFIN | Custom enhancement to edit the posted accounting document for Payment Term, Baseline date, and Withholding tax fields. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-170%20PTP%20Custom%20enhancement%20to%20edit%20the%20posted%20accounting%20document%20for%20Payment%20Term%20Baseline%20date%20and%20Withholding%20tax%20fields%20in%20IP%20%26%20IF.pptx?d=wafd9ff290e714d69a8b4680296c69026&csf=1&web=1&e=Mkkgfl | 02.No | 01.Yes |  | 2025-09-24 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-12 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-11 | 2025-10-17 | 2025-10-24 | 2025-12-11 | 100% | 2025-12-18 | 2025-11-17 | 2025-12-05 | 2025-12-19 | 100% | 2025-12-18 | 2025-11-17 | 2025-12-05 | 2025-12-19 | 100% | 2025-12-18 | [15 empty] | 2025-12-18 | 2025-12-18 |  | 2025-12-20 | 2026-01-03 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2026-01-07 | N | 100% | 2025-12-12 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-11-14 00:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-24 | 01.S4 |  |  | 1 | 1 | 1606 | INT-CR1007 | R3 ITC1 | [6 empty] | 2025-12-11 | 2026-01-07 | 2025-12-11 |  | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 2025-12-18 | 2025-12-19 | 2025-12-18 | 2025-12-18 | [12 empty] | 2025-12-18 | 2025-12-18 |  |  | 2025-12-12 | 2026-01-07 | 2025-12-12 | [5 empty] | 2026-01-07 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3384 | [7 empty] | 1. On Track | 1. Approved no action | 12/11: FUT is approved and marked 100%. | 2025-12-05 | Y | 06. PTP |  |  |  |  | FS already complete. To be added in S21 plan. |  |  |  | Complete | R3 Build & UT Sprint 21 |  | 2025-12-19 | 2025-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3045 | PTPE1603 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Auto block the Expired Batches in IM Locations | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_PTP_QM_3045_RICEFW%20for%20Auto%20block%20of%20expired%20batches.pptx?d=w8194b16ad82e4aa4abaf28a64e9219a6&csf=1&web=1&e=HLwfoa | 02.No | 01.Yes |  |  |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-01 | 2025-10-01 | 100% | 2025-10-02 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-11-28 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-12-16 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1603 | INT-CR0928 | R3 ITC1 | [6 empty] | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-12-24 | 2026-01-09 | 2025-12-24 | [5 empty] | 2025-10-01 | 2025-12-05 |  |  | 2026-01-09 |  | WIINGS |  | 0 |  | 3268 | [7 empty] | 4. Completed | 1. Approved no action | 12/19- Received approval. Awaiting to mark it as 100% by Jose. 12/17- Waiting approval 12/12 FUT in Progress. To be submitted for approval by 12/17 | 2025-12-05 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 3029 | PTPE1532 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required in the purchase order (change only) to validate if the users add only service line items | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBCCE8C9D-2EE6-4652-94A4-EB60DCB8BC50%7D&file=3029_CR0856_ENG%20HVM%20Rework%20Process_Enhancement%20for%20restriction%20of%20Material%20ID%20addition%20during%20PO%20Change_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-18 | 2024-09-10 | 2025-09-10 | 100% | 2025-09-29 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-11-28 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-12-16 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1532 | INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | [5 empty] | 2024-09-10 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3150 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/5 Awaiting approval from Intel on FUT Results. 12/19- Send for approval awaiting 12/17 - Will be send for approval till tomorrow 12/12 : Defect 5512 raised | 2025-12-05 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3028 | PTPE1531 | 04.Enhancement | 01.IP - Intel Product | Enhancement required in the purchase requisition (change only) to validate if the users add only service line items | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD3B779C9-655A-47C0-BCB2-D0C81303609A%7D&file=3028_CR0856_ENG%20HVM%20Rework%20Process_%20Enhancement%20for%20restriction%20of%20Material%20IDs%20addition%20during%20PR%20Change_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-18 | 2024-09-10 | 2025-09-10 | 100% | 2025-09-04 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-11-28 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-12-16 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1531 | INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-04 | 2025-09-10 | 2025-09-04 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-08 | 2026-01-09 | 2026-01-08 | [5 empty] | 2024-09-10 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3147 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/5 Awaiting approval from Intel on FUT Results. 12/19- Send for approval awaiting 12/17 - Will be send for approval till tomorrow 12/12 : Defect 5512 raised | 2025-12-05 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2989 | PTPE1495_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to Web suite_IF _IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2989-PTP_PM-080-060-_Enhancement%20required%20for%20ORDERS05%20IDOC%20applicable%20for%20PO%20outbound%20from%20S4%20to%20Web%20suite_IF%20_IP.pptx?d=w976b41374c3b462cb37997acf54a7b03&csf=1&web=1&e=XHFphw |  |  |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-30 | 2025-08-09 | 100% | 2025-08-21 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-06-09 06:12 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1495 | INT-CR0735 | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-07-30 | 2025-10-31 |  |  | 2025-12-03 |  |  |  | 0 |  | 3092 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-10-31 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2989 | PTPE1495_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to Web suite_IF _IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2989-PTP_PM-080-060-_Enhancement%20required%20for%20ORDERS05%20IDOC%20applicable%20for%20PO%20outbound%20from%20S4%20to%20Web%20suite_IF%20_IP.pptx?d=w976b41374c3b462cb37997acf54a7b03&csf=1&web=1&e=XHFphw |  |  |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-30 | 2025-08-09 | 100% | 2025-08-21 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-06-09 06:12 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-07-24 | 01.S4 | PTPE1495_IP | 03.Medium | 0.2 | 0.2 | 1495 | INT-CR0735 | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-07-30 | 2025-10-31 |  |  | 2025-12-03 |  |  |  | 0 |  | 3093 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/3 Awaiting approval 11/24 FUT submitted for approval. Awaiting approval 11/18 - FUT in Progress with Web suite integration. ETA 11/21 | 2025-10-31 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2971 | PTPE1494_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for Web suite relevant DSL. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2971-PTP_PM-080-060-0004_Enhancement%20required%20during%20GR%20applicable%20for%20DSL%20output%20type%20LPET%20from%20S4%20to%20Websuite%20_IF%20_IP%20(1).pptx?d=wfaff24440b164a85a080ee821d7880fc&csf=1&web=1&e=R4aLy7 |  |  |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-30 | 2025-08-09 | 100% | 2025-08-05 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-15 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-06-09 06:12 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-07-24 | 01.S4 |  |  | 1 | 1 | 1494 |  | R3 ITC1 | [6 empty] | 2025-08-05 | 2025-08-09 | 2025-08-05 |  | 2025-09-15 | 2025-09-16 | 2025-09-15 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-07-30 | 2025-10-08 |  |  | 2025-10-09 |  |  |  | 0 |  | 3090 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2025-10-08 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2971 | PTPE1494_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for Web suite relevant DSL. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2971-PTP_PM-080-060-0004_Enhancement%20required%20during%20GR%20applicable%20for%20DSL%20output%20type%20LPET%20from%20S4%20to%20Websuite%20_IF%20_IP%20(1).pptx?d=wfaff24440b164a85a080ee821d7880fc&csf=1&web=1&e=R4aLy7 |  |  |  | 2025-07-23 | cari.h.shim@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-30 | 2025-08-09 | 100% | 2025-08-05 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-18 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-11 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-11 | [15 empty] | 2025-10-11 | 2025-10-11 |  |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-06-09 06:12 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-07-24 | 01.S4 | PTPE1494_IP | 03.Medium | 0.2 | 0.2 | 1494 |  | R3 ITC1 | [6 empty] | 2025-08-05 | 2025-08-09 | 2025-08-05 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [12 empty] | 2025-10-11 | 2025-10-11 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-07-30 | 2025-10-08 |  |  | 2025-10-09 |  |  |  | 0 |  | 3091 | [8 empty] | 5. Object to be Cancelled |  | 2025-10-08 | Y | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 18 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2919 | PTPE1465_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to Get Purchase order details like Payee, Supnam, Purchase group description, Purchase organization description, payment term description, material description, and material group description from IF & IP system to Customs tracker. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2919_PTP_Enhancement%20required%20to%20send%20description%20of%20multiple%20fields%20from%20IF%20and%20IP%20system%20to%20Customs%20Tracker%20_IF%26IP.pptx?d=w4986ff6176af437599761e209313a25a&csf=1&web=1&e=3g2UKL | 01.Yes | 01.Yes |  | 2025-05-26 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-18 | 2025-07-08 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 1465 | INT-CR0754 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 |  | 2025-09-23 | 2025-10-10 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 | [5 empty] | 2025-07-18 | 2025-10-10 |  |  | 2025-11-05 |  |  |  | 0 |  | 3049 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2919 | PTPE1465_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Get Purchase order details like Payee, Supnam, Purchase group description, Purchase organization description, payment term description, material description, and material group description from IF & IP system to Customs tracker. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2919_PTP_Enhancement%20required%20to%20send%20description%20of%20multiple%20fields%20from%20IF%20and%20IP%20system%20to%20Customs%20Tracker%20_IF%26IP.pptx?d=w4986ff6176af437599761e209313a25a&csf=1&web=1&e=3g2UKL | 01.Yes | 01.Yes |  | 2025-05-26 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-18 | 2025-07-08 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 | PTPE1465_IP | 03.Medium | 0.2 | 0.2 | 1465 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 |  | 2025-09-23 | 2025-10-10 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 | [5 empty] | 2025-07-18 | 2025-10-10 |  |  | 2025-11-05 |  |  |  | 0 |  | 3051 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22 - Waiting for B-App screenshots. Will be sent for approval | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2931 | PTPE1452_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to create AMPL (Approved manufacturer part list ) in S/4 using existing HERS records in S4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B25EB006C-016E-444D-A854-54EFCD6E8FCC%7D&file=XXXX-PTP-XXX_Enhancement%20to%20create%20AMPL%20record%20in%20S4%20using%20HERS%20record%20_IF%20_IP.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-26 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-18 | 2025-07-08 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-14 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-04 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-04 | [15 empty] | 2025-09-04 | 2025-09-04 |  |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-17 02:08 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 01.S4 |  |  | 2 | 2 | 1452 | INT-CR0545 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-09-19 | 2025-08-14 |  | 2025-09-04 | 2025-10-10 | 2025-09-04 | 2025-09-04 | [12 empty] | 2025-09-04 | 2025-09-04 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | [5 empty] | 2025-07-18 | 2025-10-10 |  |  | 2025-10-09 |  |  |  | 0 | 08. Not Applicable | 3022 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2931 | PTPE1452_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to create AMPL (Approved manufacturer part list ) in S/4 using existing HERS records in S4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B25EB006C-016E-444D-A854-54EFCD6E8FCC%7D&file=XXXX-PTP-XXX_Enhancement%20to%20create%20AMPL%20record%20in%20S4%20using%20HERS%20record%20_IF%20_IP.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-26 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-18 | 2025-07-18 | 2025-07-08 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-14 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-17 02:08 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 01.S4 | PTPE1452_IP | 02.High | 0.4 | 0.4 | 1452 | INT-CR0545 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-09-19 | 2025-08-14 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | [5 empty] | 2025-07-18 | 2025-10-10 |  |  | 2025-10-09 |  |  |  | 0 | 08. Not Applicable | 3023 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2932 | PTPE1440_IP | 04.Enhancement | 01.IP - Intel Product | Custom program to generate a PDF printout of SAP self-billing invoices (ERS/Consignments), archives it to EDDAR. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2868357F-BB83-41B5-AB28-343AC2BE8850%7D&file=PM-150-030%20PTP%20PDF%20printout%20of%20SAP%20self-billing%20invoices%20(ERS%20&%20Consignment)%20IP-IF%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-29 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-15 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2025-04-29 04:16 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1440 | INT-CR0614 | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-09-15 | 2025-09-17 | 2025-09-15 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-06-11 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 |  | 3002 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 Submitted for approval 10/27: EDDAR configuration call is scheduled on 10/27. FUT is in progress. 10/17: Defect 3595 is created for Bill to address logic. As per latest update defect is resolved, team is working on retesting. | 2025-10-08 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2932 | PTPE1440_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom program to generate a PDF printout of SAP self-billing invoices (ERS/Consignments), archives it to EDDAR. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2868357F-BB83-41B5-AB28-343AC2BE8850%7D&file=PM-150-030%20PTP%20PDF%20printout%20of%20SAP%20self-billing%20invoices%20(ERS%20&%20Consignment)%20IP-IF%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-29 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-18 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2025-04-29 04:16 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 | PTPE1440_IP | 03.Medium | 0.2 | 0.2 | 1440 | INT-CR0614 | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-06-11 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 |  | 3003 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 Submitted for approval 10/27: EDDAR configuration call is scheduled on 10/27. FUT is in progress. 10/17: Defect 3595 is created for Bill to address logic. As per latest update defect is resolved, team is working on retesting. | 2025-10-08 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2911 | PTPE1437_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement required to populate custom logic for BLAORD (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B313E3C83-9093-40F5-8376-FF55A71978C5%7D&file=2911_PTP_PM-090-040_Enhancement%20required%20to%20populate%20custom%20logic%20for%20BLAORD_IF%20_IP.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cjenoronha%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAzMTMyMTAxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-04-29 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-07-28 | 2025-08-01 | 2025-07-25 | 100% | 2025-07-24 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  | 2025-08-27 | 2025-10-08 | 2025-10-22 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-18 | 2025-10-22 | 2025-10-22 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2025-04-25 05:59 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-03 | 01.S4 |  |  | 1 | 1 | 1437 | INT-CR0540 | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | [5 empty] | 2025-06-11 | 2025-08-13 |  |  | 2025-10-22 |  |  |  | 0 |  | 2996 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/24 - FUT approved. Jose to mark 100% | 2025-08-13 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2911 | PTPE1437_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required to populate custom logic for BLAORD (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B313E3C83-9093-40F5-8376-FF55A71978C5%7D&file=2911_PTP_PM-090-040_Enhancement%20required%20to%20populate%20custom%20logic%20for%20BLAORD_IF%20_IP.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cjenoronha%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAzMTMyMTAxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-04-29 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-07-28 | 2025-08-01 | 2025-07-25 | 100% | 2025-07-24 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  | 2025-08-27 | 2025-10-08 | 2025-10-22 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-18 | 2025-10-22 | 2025-10-22 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2025-04-25 05:59 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 | PTPE1437_IP | 03.Medium | 0.2 | 0.2 | 1437 | INT-CR0540 | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | [5 empty] | 2025-06-11 | 2025-08-13 |  |  | 2025-10-22 |  |  |  | 0 |  | 2997 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/24 - FUT approved. Jose to mark 100% | 2025-08-13 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2910 | PTPE1436_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement required to populate custom logic for BLAOCH (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 99. Rejected/Cancelled/On Hold | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2922AAAD-DD20-4784-891B-CE6C9DBE2C5C%7D&file=2910_PTP_PM-090-040_Enhancement%20required%20to%20populate%20custom%20logic%20for%20BLAOCH_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-29 | cari.h.shim@intel.com | 04.Cancelled |  | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-09-15 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | [14 empty] | 2025-10-13 | 2025-11-05 |  | Y | 0% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2026-01-09 | 2026-01-09 | 2026-01-09 | pgaroo@deloitte.com | 2025-04-25 05:59 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1436 | INT-CR2911 | #INVALID VALUE | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  |  | 2025-09-19 |  |  |  | 2026-01-09 | [19 empty] | 2025-11-05 | [6 empty] | 2025-06-11 | 2026-01-09 |  |  | 2025-11-05 |  |  |  | 0 |  | 2994 | [10 empty] | 2026-01-09 | Y | 06. PTP | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2910 | PTPE1436_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required to populate custom logic for BLAOCH (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 99. Rejected/Cancelled/On Hold | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2922AAAD-DD20-4784-891B-CE6C9DBE2C5C%7D&file=2910_PTP_PM-090-040_Enhancement%20required%20to%20populate%20custom%20logic%20for%20BLAOCH_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-29 | cari.h.shim@intel.com | 04.Cancelled |  | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-09-15 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | [14 empty] | 2025-10-13 | 2025-11-05 |  | Y | 0% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2026-01-09 | 2026-01-09 | 2026-01-09 | pgaroo@deloitte.com | 2025-04-25 05:59 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 | 2025-05-06 | 01.S4 | PTPE1436_IP | 03.Medium | 0.2 | 0.2 | 1436 | INT-CR2910 | #INVALID VALUE | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  |  | 2025-09-19 |  |  |  | 2026-01-09 | [19 empty] | 2025-11-05 | [6 empty] | 2025-06-11 | 2026-01-09 |  |  | 2025-11-05 |  |  |  | 0 |  | 2995 | [10 empty] | 2026-01-09 | Y | 06. PTP | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2926 | PTPE1424_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement for I-chem PR creation from Ariba until R5 go-live | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BA6BA1695-9EFE-43E9-9B06-3CAFCF4CFD19%7D&file=2926_PM-070-020-PTP_Enhancement%20for%20I-chem%20PR%20creation%20from%20Ariba%20until%20R5%20go-live.pptx&wdLOR=c367DBF25-2EF3-4B79-B549-ADF6566F072C&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-10 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-10 | [15 empty] | 2025-09-10 | 2025-09-10 | No |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-04-18 05:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1424 | INT-CR0612 | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  | 2025-08-05 | 2025-09-19 | 2025-08-05 |  | 2025-09-10 | 2025-10-10 | 2025-09-10 | 2025-09-10 | [12 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | [5 empty] | 2025-06-11 | 2025-10-10 |  |  | 2025-10-09 |  |  |  | 0 |  | 2978 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2926 | PTPE1424_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for I-chem PR creation from Ariba until R5 go-live | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BA6BA1695-9EFE-43E9-9B06-3CAFCF4CFD19%7D&file=2926_PM-070-020-PTP_Enhancement%20for%20I-chem%20PR%20creation%20from%20Ariba%20until%20R5%20go-live.pptx&wdLOR=c367DBF25-2EF3-4B79-B549-ADF6566F072C&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-06 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-10 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-10 | [15 empty] | 2025-09-10 | 2025-09-10 | No |  | 2025-10-03 | 2025-10-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-04-18 05:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 | PTPE1424_IP | 03.Medium | 0.2 | 0.2 | 1424 | INT-CR0612 | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-11 | 2025-06-06 |  | 2025-08-05 | 2025-09-19 | 2025-08-05 |  | 2025-09-10 | 2025-10-10 | 2025-09-10 | 2025-09-10 | [12 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-08 | [5 empty] | 2025-06-11 | 2025-10-10 |  |  | 2025-10-09 |  |  |  | 0 |  | 2957 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2933 | PTPE1422_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to Update Invoice PAID Status from CFIN to IF & IP ARIBA Standard Tables | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CFC07E3-39DA-4751-86BA-DB6A987A9F61%7D&file=PM-150-020%20Enhacement%20to%20Update%20Invoice%20PAID%20Status%20from%20CFIN%20to%20IF%20&%20IP%20ARIBA%20Standard%20Tables%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-09-19 | 2025-09-26 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-08-29 | 2025-09-08 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-12 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-04-18 05:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1422 | INT-CR0615 | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | [5 empty] | 2025-05-16 | 2025-12-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 2974 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11 - Submitted for approval. IT approval received. Business approval is pending 11/4 FUT in Progress. On Track for S19 10/27: We are facing ReadSoft Tax dump error. TR team is working for this. 10/17: Defect 3595 and 3803 is created and defect is not fixed yet. | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | Yes | ARIBA end to end invoicing need to retest. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2933 | PTPE1422_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Update Invoice PAID Status from CFIN to IF & IP ARIBA Standard Tables | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CFC07E3-39DA-4751-86BA-DB6A987A9F61%7D&file=PM-150-020%20Enhacement%20to%20Update%20Invoice%20PAID%20Status%20from%20CFIN%20to%20IF%20&%20IP%20ARIBA%20Standard%20Tables%20.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-09-19 | 2025-09-26 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  | 2025-08-29 | 2025-09-08 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-12 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-04-18 05:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-05-06 | 01.S4 | PTPE1422_IP | 03.Medium | 0.2 | 0.2 | 1422 | INT-CR0615 | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | [5 empty] | 2025-05-16 | 2025-12-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 2975 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11 - Submitted for approval. IT approval received. Business approval is pending 11/4 FUT in Progress. On Track for S19 10/27: We are facing ReadSoft Tax dump error. TR team is working for this. 10/17: Defect 3595 and 3803 is created and defect is not fixed yet. | 2025-12-05 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2670 | PTPE1343 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required to maintain the list of approved suppliers for copper material repair in a custom table - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2670-PM-080-050-0009_PTP_Custom%20table%20requirement%20to%20maintain%20approved%20suppliers%20list%20for%20copper%20material%20repairs%20S4-IF.pptx?d=w9ec7f5ef62ed4a7ba680166aa346e877&csf=1&web=1&e=0w1WLj | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-19 | 100% | 2025-03-11 | 2025-07-04 | 2025-07-11 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2024-12-19 08:23 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-21 | 01.S4 |  |  | 1 | 1 | 1343 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-29 | 2025-03-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-03-29 | 2025-08-15 |  |  | 2025-08-13 |  | WIINGS Only | TRUE | 0 |  | 2667 | [10 empty] | 2025-08-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2808 | PTPE1195_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to auto close Purchase Orders based on policy criteria , executed at a designated frequency . | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://secure-web.cisco.com/1bkPEKLDc3bkzp_cLeUrfS3OcK25NEZBdNEcfb10JaUpXQfGTPgBKg6ZSSQ-0yUDlRk4Ru3cZ4coVqZ-su-K6rtoFKn3jJ9o29sGV4P0GcK9ZNVFCkTTsqQ2OZ8ON_1SGiua7M37J1FIrw6d_KFTo2UoeYTwOw-WMksEP4Urd3AGSC_FkXkDabzn2hQY5cRiU9WbXlZ6EHVUu3od09kxYFY5tBI6yvtPs1mUoSuXUMwJc_BxBGIt5F2z82VJ4V_hrdPge8VcWOecYXk6hYOUkJN25fc0PVlBwzgGs47iS2pbV2Tl0H1Nn4jzdWTVHEkxH4UcE1VQJTIkzDGpKLNhqLZhgVuZqQbcFvNIaVJZ8q210u0aX56qg6GdU-nJPl-MQiRlfXDo1qEs3WvZHHVsxSK4V5n_AJgjgN3Qzi4trsNWoB0TQqbiTxyTtMexkOnF2VyLXlYdeGnaa8BcPDza-A93sk4w9yw1mzPA8CUVLMXvrh1MD3bFCqhtyP46_RifdWuHWeGqvrSjaHPIm6mVi3g/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2F_layouts%2F15%2FDoc.aspx%3Fsourcedoc%3D%257B78995484-D5C1-4046-8D4B-7B37C4160B61%257D%26file%3D2808-PTP_PM-070-070_0007_Enhancement%2520required%2520to%2520auto%2520close%2520PO%2520based%2520on%2520policy_IP_IF.pptx%26action%3Dedit%26mobileredirect%3Dtrue | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-02 | 2025-05-30 | 2025-05-14 | 100% | 2025-08-04 | 2025-06-16 | 2025-06-20 | 2025-06-20 | 100% | 2025-10-02 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-01-29 09:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1 | 1195 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | [5 empty] | 2025-05-30 | 2025-07-18 |  |  | 2025-11-05 |  |  |  | 0 |  | 1729 | [7 empty] | 1. On Track | 17. FUT In progress | 10/27 FUT in progress. Targeted to be shared for approval by 10/29 10/10 Object FUT Planned in Sprint 19 10/10 FUT Planned in sprint 19 as TUT Got approved in sprint 18. Re-Plan object tracker as per Sprint 19 dates | 2025-07-18 | N | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2808 | PTPE1195_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to auto close Purchase Orders based on policy criteria , executed at a designated frequency . | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://secure-web.cisco.com/1bkPEKLDc3bkzp_cLeUrfS3OcK25NEZBdNEcfb10JaUpXQfGTPgBKg6ZSSQ-0yUDlRk4Ru3cZ4coVqZ-su-K6rtoFKn3jJ9o29sGV4P0GcK9ZNVFCkTTsqQ2OZ8ON_1SGiua7M37J1FIrw6d_KFTo2UoeYTwOw-WMksEP4Urd3AGSC_FkXkDabzn2hQY5cRiU9WbXlZ6EHVUu3od09kxYFY5tBI6yvtPs1mUoSuXUMwJc_BxBGIt5F2z82VJ4V_hrdPge8VcWOecYXk6hYOUkJN25fc0PVlBwzgGs47iS2pbV2Tl0H1Nn4jzdWTVHEkxH4UcE1VQJTIkzDGpKLNhqLZhgVuZqQbcFvNIaVJZ8q210u0aX56qg6GdU-nJPl-MQiRlfXDo1qEs3WvZHHVsxSK4V5n_AJgjgN3Qzi4trsNWoB0TQqbiTxyTtMexkOnF2VyLXlYdeGnaa8BcPDza-A93sk4w9yw1mzPA8CUVLMXvrh1MD3bFCqhtyP46_RifdWuHWeGqvrSjaHPIm6mVi3g/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2F_layouts%2F15%2FDoc.aspx%3Fsourcedoc%3D%257B78995484-D5C1-4046-8D4B-7B37C4160B61%257D%26file%3D2808-PTP_PM-070-070_0007_Enhancement%2520required%2520to%2520auto%2520close%2520PO%2520based%2520on%2520policy_IP_IF.pptx%26action%3Dedit%26mobileredirect%3Dtrue | 02.No | 01.Yes |  | 2025-01-29 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-02 | 2025-05-30 | 2025-05-14 | 100% | 2025-08-04 | 2025-06-16 | 2025-06-20 | 2025-06-20 | 100% | 2025-10-02 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-01-29 09:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-04 | 01.S4 | PTPE1195_IP | 03.Medium | 0.2 | 0.2 | 1195 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | [5 empty] | 2025-05-30 | 2025-07-18 |  |  | 2025-11-05 |  |  |  | 0 |  | 1728 | [7 empty] | 1. On Track | 17. FUT In progress | 10/27 FUT in progress. Targeted to be shared for approval by 10/29 10/10 Object FUT Planned in Sprint 19 10/10 FUT Planned in sprint 19 as TUT Got approved in sprint 18. Re-Plan object tracker as per Sprint 19 dates | 2025-07-18 | N | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2760 | PTPE1139_IP | 04.Enhancement | 01.IP - Intel Product | Custom Enhancements for Payment Proposal, payment remittance, payment status, carbon copy invoice [ERP] and invoice status after invoice Posted in SAP IP, IF and CFIN to Ariba Network. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-130-0001%20PTP%20Custom%20Enhancement%20for%20Payment%20Proposal%20after%20invoice%20posted%20from%20IP%20%26%20IF%20to%20Ariba%20IP-IF%20-%20Copy%20(2).pptx?d=w7a17bc687dbf4c26b74d66f50e7722cd&csf=1&web=1&e=12b4Jz |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-07-28 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-20 | [15 empty] | 2025-09-20 | 2025-09-20 |  | 2026-02-06 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-19 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-20 06:30 | cell-link@smartsheet.com | 2026-02-19 07:12 | 10 | 2025-01-23 | 01.S4 | PTPE1139_CFIN | 03.Medium | 0.2 | 0.2 | 1139 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-28 | 2025-08-22 | 2025-07-28 |  | 2025-09-20 | 2025-10-10 | 2025-09-20 | 2025-09-20 | [12 empty] | 2025-09-20 | 2025-09-20 |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | [5 empty] | 2025-05-30 | 2025-10-10 | [6 empty] | 0 | 08. Not Applicable | 2311 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/16: Awaiting approval from Andrea and Jorge [Intel IT] 2/10 Additional scenarios are requested by Intel to be tested during FUT walkthrough call. It requires changes from SAP Ariba side. We have raised the issue to SAP Ariba team and waiting for their response. 2/3 - Ariba Issue encountered and changes are required at Ariba end. Once it is done, they can resume testing. 2/2 FUT in progress. To be completed by 2/2 and shared for approval by 2/3 post Review 1/30 FUT in Progress. Targeted to be completed by 1/2 1/27: Update is mentioned below: 1. Payment remittance interface : It is working fine we started FUT for this. 2. Invoice status interface: code is completed, while we were testing this interface we identified there is one CIG mapping is pending due to that invoices are failing in CIG. @Maddi, PhanidharX is working on this from Intel and given ETA is today. 3. Carbon copy interface: development is completed and testing is in progress. 4. Payment proposal interface: after implementing this enhancement the standard program got effected and sending duplicate values to ARIBA network @Adhikari, Akankshya@Ayyavaraiah, Ayyavaraiah Yadav C is debugging the standard program to identify the root cause. 5. Payment remittance cancelation interface: Original values are not getting populated in the program @Ayyavaraiah, Ayyavaraiah Yadav C is checking. 1/20 Issues faced in Readsoft for FUT. Analysis and Resolution by Readsoft is in progress. ETA for FUT completion is 1/23 1/13 CR Completion in Progress. Test data issue with Readsoft - To be Resolved by 1/14 1/5 Dev for Internal CR to be completed by End of this week. FUT Completion will be pushed to Next week. ETA 1/16 ETA 1/12/17: Development team is working on development for internal CR mentioned. 12/12: Object is blocked due to pending development for internal CR: INT-Build-CR1058 and CR1013. | 2025-10-10 | N | 06. PTP |  |  |  | 02/17: FUT approval ETA EOD 0218 Current status: Awaiting Approval Issue: N/a Next steps: Awaiting approval Help needed: N/a ETA: 0218 | Week 2 Target | 3. Watch item |  | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2760 | PTPE1139_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Enhancements for Payment Proposal, payment remittance, payment status, carbon copy invoice [ERP] and invoice status after invoice Posted in SAP IP, IF and CFIN to Ariba Network. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-130-0001%20PTP%20Custom%20Enhancement%20for%20Payment%20Proposal%20after%20invoice%20posted%20from%20IP%20%26%20IF%20to%20Ariba%20IP-IF%20-%20Copy%20(2).pptx?d=w7a17bc687dbf4c26b74d66f50e7722cd&csf=1&web=1&e=12b4Jz |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-07-28 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-20 | [15 empty] | 2025-09-20 | 2025-09-20 |  | 2026-02-06 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-19 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-20 06:30 | cell-link@smartsheet.com | 2026-02-19 07:12 | 10 | 2025-01-23 | 01.S4 | PTPE1139_CFIN | 03.Medium | 0.2 | 0.2 | 1139 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-28 | 2025-08-22 | 2025-07-28 |  | 2025-09-20 | 2025-10-10 | 2025-09-20 | 2025-09-20 | [12 empty] | 2025-09-20 | 2025-09-20 |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | [5 empty] | 2025-05-30 | 2025-10-10 | [6 empty] | 0 | 08. Not Applicable | 2310 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/16: Awaiting approval from Andrea and Jorge [Intel IT] 2/10 Additional scenarios are requested by Intel to be tested during FUT walkthrough call. It requires changes from SAP Ariba side. We have raised the issue to SAP Ariba team and waiting for their response. 2/3 - Ariba Issue encountered and changes are required at Ariba end. Once it is done, they can resume testing. 2/2 FUT in progress. To be completed by 2/2 and shared for approval by 2/3 post Review 1/30 FUT in Progress. Targeted to be completed by 1/2 1/27: Update is mentioned below: 1. Payment remittance interface : It is working fine we started FUT for this. 2. Invoice status interface: code is completed, while we were testing this interface we identified there is one CIG mapping is pending due to that invoices are failing in CIG. @Maddi, PhanidharX is working on this from Intel and given ETA is today. 3. Carbon copy interface: development is completed and testing is in progress. 4. Payment proposal interface: after implementing this enhancement the standard program got effected and sending duplicate values to ARIBA network @Adhikari, Akankshya@Ayyavaraiah, Ayyavaraiah Yadav C is debugging the standard program to identify the root cause. 5. Payment remittance cancelation interface: Original values are not getting populated in the program @Ayyavaraiah, Ayyavaraiah Yadav C is checking. 1/20 Issues faced in Readsoft for FUT. Analysis and Resolution by Readsoft is in progress. ETA for FUT completion is 1/23 1/13 CR Completion in Progress. Test data issue with Readsoft - To be Resolved by 1/14 1/5 Dev for Internal CR to be completed by End of this week. FUT Completion will be pushed to Next week. ETA 1/16 ETA 1/12/17: Development team is working on development for internal CR mentioned. 12/12: Object is blocked due to pending development for internal CR: INT-Build-CR1058 and CR1013. | 2025-10-10 | N | 06. PTP |  |  |  | 02/17: FUT approval ETA EOD 0218 Current status: Awaiting Approval Issue: N/a Next steps: Awaiting approval Help needed: N/a ETA: 0218 | Week 2 Target | 3. Watch item |  | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2760 | PTPE1139_CFIN | 04.Enhancement | 05.CFIN | Custom Enhancements for Payment Proposal, payment remittance, payment status, carbon copy invoice [ERP] and invoice status after invoice Posted in SAP IP, IF and CFIN to Ariba Network. | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-130-0001%20PTP%20Custom%20Enhancement%20for%20Payment%20Proposal%20after%20invoice%20posted%20from%20IP%20%26%20IF%20to%20Ariba%20IP-IF%20-%20Copy%20(2).pptx?d=w7a17bc687dbf4c26b74d66f50e7722cd&csf=1&web=1&e=12b4Jz |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-07-28 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  | 2026-02-06 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-19 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-20 06:30 | cell-link@smartsheet.com | 2026-02-19 07:12 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1139 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-28 | 2025-08-22 | 2025-07-28 |  | 2025-10-07 | 2025-10-10 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | [5 empty] | 2025-05-30 | 2025-10-10 | [6 empty] | 0 | 08. Not Applicable | 2312 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/16: Awaiting approval from Andrea and Jorge [Intel IT] 2/10 Additional scenarios are requested by Intel to be tested during FUT walkthrough call. It requires changes from SAP Ariba side. We have raised the issue to SAP Ariba team and waiting for their response. 2/3 - Ariba Issue encountered and changes are required at Ariba end. Once it is done, they can resume testing. 2/2 FUT in progress. To be completed by 2/2 and shared for approval by 2/3 post Review 1/30 FUT in Progress. Targeted to be completed by 1/2 1/27: Update is mentioned below: 1. Payment remittance interface : It is working fine we started FUT for this. 2. Invoice status interface: code is completed, while we were testing this interface we identified there is one CIG mapping is pending due to that invoices are failing in CIG. @Maddi, PhanidharX is working on this from Intel and given ETA is today. 3. Carbon copy interface: development is completed and testing is in progress. 4. Payment proposal interface: after implementing this enhancement the standard program got effected and sending duplicate values to ARIBA network @Adhikari, Akankshya@Ayyavaraiah, Ayyavaraiah Yadav C is debugging the standard program to identify the root cause. 5. Payment remittance cancelation interface: Original values are not getting populated in the program @Ayyavaraiah, Ayyavaraiah Yadav C is checking. 1/20 Issues faced in Readsoft for FUT. Analysis and Resolution by Readsoft is in progress. ETA for FUT completion is 1/23 1/13 CR Completion in Progress. Test data issue with Readsoft - To be Resolved by 1/14 1/5 Dev for Internal CR to be completed by End of this week. FUT Completion will be pushed to Next week. ETA 1/16 ETA 1/12/17: Development team is working on development for internal CR mentioned. 12/12: Object is blocked due to pending development for internal CR: INT-Build-CR1058 and CR1013. | 2025-10-10 | N | 06. PTP |  |  |  | 02/17: FUT approval ETA EOD 0218 Current status: Awaiting Approval Issue: N/a Next steps: Awaiting approval Help needed: N/a ETA: 0218 | Week 2 Target | 3. Watch item |  | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2740 | PTPE1135_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement required while triggering the COND_A idoc for contracts (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1681_PTP_PM-090-040_Enhancement%20required%20while%20triggering%20the%20COND_A%20idoc%20for%20Contracts%20_IF%20_IP.pptx?d=wf3785e2225584da4a6d2584bd505df77&csf=1&web=1&e=bVVyr2 |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-17 | 100% | 2025-03-11 | 2025-05-19 | 2025-05-20 | 2025-05-20 | 100% | 2025-05-21 | 2025-05-12 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-21 | 2025-05-12 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-21 | [15 empty] | 2025-05-21 | 2025-05-21 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2025-01-20 06:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1135 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-28 | 2025-03-11 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 |  | 2025-05-21 | 2025-05-30 | 2025-05-21 | 2025-05-21 | [12 empty] | 2025-05-21 | 2025-05-21 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-03-28 | 2025-05-16 | [6 empty] | 0 |  | 2067 | [9 empty] | 9/12- Approved by Soon , Rafa has to approve 9/10 FUT Completed and Submitted for approval. 9/5 - CR raised and approved, waiting tech ETA 9/1- POC in progress ETA given by tech 9/1 8/25 - SAP passed feedback working on POC. 8/18 - With SAP BD64 Filter issue | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2740 | PTPE1135_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required while triggering the COND_A idoc for contracts (PTPI0211_IP_IF). | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1681_PTP_PM-090-040_Enhancement%20required%20while%20triggering%20the%20COND_A%20idoc%20for%20Contracts%20_IF%20_IP.pptx?d=wf3785e2225584da4a6d2584bd505df77&csf=1&web=1&e=bVVyr2 |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-17 | 100% | 2025-03-11 | 2025-05-19 | 2025-05-20 | 2025-05-20 | 100% | 2025-05-21 | 2025-05-05 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-21 | 2025-05-05 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-21 | [15 empty] | 2025-05-21 | 2025-05-21 | Yes | 2025-07-15 | 2025-08-06 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2025-01-20 06:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 | PTPE1135_IP | 03.Medium | 0.2 | 0.2 | 1135 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-28 | 2025-03-11 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 |  | 2025-05-21 | 2025-05-30 | 2025-05-21 | 2025-05-21 | [12 empty] | 2025-05-21 | 2025-05-21 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-03-28 | 2025-05-16 | [6 empty] | 0 |  | 2066 | [9 empty] | 9/12- Approved by Soon , Rafa has to approve 9/10 FUT Completed and Submitted for approval. 9/5 - CR raised and approved, waiting tech ETA 9/1- POC in progress ETA given by tech 9/1 8/25 - SAP passed feedback working on POC. 8/18 - With SAP BD64 Filter issue | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2678 | PTPE1133 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Get Purchase group email address details from IF system to CWB. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2678-PTP_Enhancement%20required%20to%20send%20Purchase%20Group%20Email%20address%20from%20IF%20system%20to%20CWB%20_IF.pptx?d=wf28d22599de24c92823071b50b7b7b5b&csf=1&web=1&e=HO4zIC |  |  |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-17 | 100% | 2025-02-27 | 2025-05-19 | 2025-05-20 | 2025-05-20 | 100% | 2025-06-06 | 2025-05-12 | 2025-05-16 | 2025-05-30 | 100% | 2025-06-10 | 2025-05-12 | 2025-05-16 | 2025-05-30 | 100% | 2025-06-10 | [15 empty] | 2025-06-10 | 2025-06-10 |  |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-08 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2025-01-20 06:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 0.5 | 0.5 | 1133 |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-03-28 | 2025-02-27 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | [12 empty] | 2025-06-10 | 2025-06-10 |  |  | 2025-08-08 | 2025-08-13 | 2025-08-08 | [5 empty] | 2025-03-28 | 2025-05-16 | [6 empty] | 0 |  | 2672 | [10 empty] | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-10 | 2025-06-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2628 | PTPE1120 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required to automatically create and change subcon purchase requisitions based on customer sales order for SIMS – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2628-PM-080-050-0007_PTP_Auto%20create%20subcon%20PO%20based%20on%20customer%20sales%20order_IF.pptx?d=wb93ddfcb44104ed499dca2ffbf3ec6cc&csf=1&web=1&e=XxVqq3 | 02.No | 01.Yes |  | 2025-01-21 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-01 | 2025-05-30 | 2025-04-15 | 100% | 2025-04-15 | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-01 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-01 | 2025-09-30 | 2025-10-10 | 2025-08-13 | 100% | 2025-08-01 | [15 empty] | 2025-08-01 | 2025-08-01 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 0.5 | 0.5 | 1120 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-05-30 |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 |  | 2025-08-01 | 2025-08-13 | 2025-08-01 | 2025-08-01 | [12 empty] | 2025-08-01 | 2025-08-01 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-05-30 | 2025-10-10 | [6 empty] | 0 |  | 1948 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2737 | PTPE1107 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required to automatically create and change subcon purchase orders (PO) based on customer sales order for SIMS – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEF063EF3-A524-40C3-8636-BFE801F16156%7D&file=2737-PM-080-050-0008_PTP_Auto%20update%20subcon%20PO%20based%20on%20customer%20sales%20order%20changes_IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-20 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-02 | 2025-05-30 | 2025-05-14 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-07-18 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-15 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-15 | [15 empty] | 2025-08-15 | 2025-08-15 | Yes |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1107 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 | 2025-09-19 | 2025-07-18 |  | 2025-08-15 | 2025-10-10 | 2025-08-15 | 2025-08-15 | [12 empty] | 2025-08-15 | 2025-08-15 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | [5 empty] | 2025-05-30 | 2025-09-12 | [6 empty] | 0 |  | 2065 | [10 empty] | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2658 | PTPE1099 | 04.Enhancement | 02.IF - Intel Foundry | Exception Notification – Label printing functionality – IF only | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5FAC8D5B-C294-4EC8-935B-B6E2D036E1C1%7D&file=2658_RICEFW_L-040-080_Notification%20Exception%20-%20Label%20printing%20functionality_IF.pptx&wdLOR=cA3CB1082-6B84-4739-AB2E-E83CC51BA2D4&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-16 | cari.h.shim@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-04-28 | 2025-05-23 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-08 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-29 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-29 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-09-02 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2025-01-08 06:55 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-16 | 01.S4 |  |  | 1 | 1 | 1099 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-10 | 2025-09-12 | [6 empty] | 2025-05-07 | 2025-09-12 |  |  |  |  | WIINGS |  | 0 |  | 1842 | [10 empty] | 2025-09-12 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2562 | PTPE1050_IP | 04.Enhancement | 01.IP - Intel Product | BADI Enhancement for PR PO Approval Workflow | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B3CA51DC2-A80B-40FE-9A85-4E9437B2846A%7D&file=Console%20ID_PTP_RICEFW%20Intake%20Form_v2.0.pptx%20PR%20PO%20BADI%20enhancement.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | cari.h.shim@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-06-16 | 2025-07-04 | 2025-08-01 | 100% | 2025-08-26 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-26 | 2025-07-14 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-26 | [15 empty] | 2025-08-26 | 2025-08-26 | Yes |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1050 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | [12 empty] | 2025-08-26 | 2025-08-26 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-10-24 |  |  |  | 0 |  | 2618 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-07-18 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | Yes | Workflow is the mainly dependent on plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-02-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2562 | PTPE1050_IF | 04.Enhancement | 02.IF - Intel Foundry | BADI Enhancement for PR PO Approval Workflow | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B3CA51DC2-A80B-40FE-9A85-4E9437B2846A%7D&file=Console%20ID_PTP_RICEFW%20Intake%20Form_v2.0.pptx%20PR%20PO%20BADI%20enhancement.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-18 | Cari H Shim | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-18 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | Yes |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-16 | 01.S4 | PTPE1050_IP | 03.Medium | 0.2 | 0.2 | 1050 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-08-18 | 2025-09-19 | 2025-08-18 |  | 2025-09-05 | 2025-10-10 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-30 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 0 |  | 2617 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/5 Clarifications/Review comments addressed by Deloitte. Awaiting Sean's approval on FUT 12/19- Send for approval awaiting 12/17- Waiting approval sent 12/12 : FUT submitted for approval. Awaiting approval 12/11 FUT submitted for approval. Awaiting approval 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-10-10 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2561 | PTPE1049_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to create custom field on Purchase Order Header Table to store Approved Value from Workflow | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BBCAECDDE-DCF9-485A-B558-7A440DDB3096%7D&file=XXXX-PTP_PM-XXX-XXX-XXXX_Enhancement%20required%20to%20create%20Z%20feild%20_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | cari.h.shim@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-03-17 | 100% | 2025-03-11 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-08 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-08 | [15 empty] | 2025-09-08 | 2025-09-08 | Yes |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1049 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-28 | 2025-03-11 |  | 2025-08-12 | 2025-08-22 | 2025-08-12 |  | 2025-09-08 | 2025-09-12 | 2025-09-08 | 2025-09-08 | [12 empty] | 2025-09-08 | 2025-09-08 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-10-10 |  |  |  | 0 |  | 1467 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/12 : Send for approval 12/11 FUT in progress. To be submitted by 12/11 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-08 | Yes | Workflow is the mainly dependent on plant need to be retested | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-02-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2561 | PTPE1049_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to create custom field on Purchase Order Header Table to store Approved Value from Workflow | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BBCAECDDE-DCF9-485A-B558-7A440DDB3096%7D&file=XXXX-PTP_PM-XXX-XXX-XXXX_Enhancement%20required%20to%20create%20Z%20feild%20_IF%20_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | cari.h.shim@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-03-17 | 100% | 2025-03-11 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-08 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-08 | [15 empty] | 2025-09-08 | 2025-09-08 | Yes |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 | PTPE1049_IP | 03.Medium | 0.2 | 0.2 | 1049 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-28 | 2025-03-11 |  | 2025-08-12 | 2025-08-22 | 2025-08-12 |  | 2025-09-08 | 2025-09-12 | 2025-09-08 | 2025-09-08 | [12 empty] | 2025-09-08 | 2025-09-08 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-10-10 |  |  |  | 0 |  | 1466 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/12 : Send for approval 12/11 FUT in progress. To be submitted by 12/11 12/3 No Roadblocks. FUT in Progress 11/24 for Logic update defect 3565 is under Fix by Technical Team. FUT on Hold. ETA 12/4 for FUT completion 11/18 Custom Enhancement being proposed for Rejection Email Design. Discussions in Progress for the CR and design change 11/11 - Alternative technical feasibility is being explored. ETA from tech team is 11/12 11/4 SAP OSS Note Raised 1251984/2025. Defect 3565 also created to track the progress. FUT Completion on Track. Approval is planned for S20 | 2025-09-12 | N | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2671 | PTPE1036 | 04.Enhancement | 02.IF - Intel Foundry | Batch update Program | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B75DC8B7E-9C54-4AC1-934F-36E0A08E033C%7D&file=2671_RICEFW_QI-130-060_Batch%20update%20program_IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-17 | 2025-04-18 | 2025-04-15 | 100% | 2025-04-19 | 2025-07-04 | 2025-07-11 | 2025-06-20 | 100% | 2025-09-03 | 2025-08-01 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | 2025-08-01 | 2025-08-15 | 2025-07-11 | 100% | 2025-09-03 | [15 empty] | 2025-09-03 | 2025-09-03 | Yes |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-11 | 01.S4 |  |  | 1 | 1 | 1036 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-19 | 2025-04-19 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | [12 empty] | 2025-09-03 | 2025-09-03 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-28 |  | WIINGS |  | 0 |  | 2668 | [10 empty] | 2025-08-15 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2615 | PTPE1033 | 04.Enhancement | 02.IF - Intel Foundry | UD Enhancement | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2615_RICEFW_QI-130_010_Enhancement%20at%20the%20time%20of%20Usage%20Decision%20to%20check%20MQCS%20Disposition%20status_IF.pptx?d=w188146326245467ba188ab8dd011d8ef&csf=1&web=1&e=5fP54y | 02.No | 01.Yes |  | 2024-12-20 | cari.h.shim@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-31 | 2025-05-02 | 2025-05-14 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-08-01 | 100% | 2025-09-03 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-03 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-03 | [15 empty] | 2025-09-03 | 2025-09-03 | Yes |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-11 | 01.S4 |  |  | 1 | 1 | 1033 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | [12 empty] | 2025-09-03 | 2025-09-03 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-11-07 |  | WIINGS Only | TRUE | 0 |  | 1498 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 11/4 - Queues are stuck due to auth issue - In Progress with EWM Team 10/28 Issues identified and pending actions by EWM Team. 70% FUT Completed 10/22- Testing in Progress, defect 2853 raised 10/16- Previous defects closed; 3770 raised resolution in progress 10/14- blocked due to defects# 3630, 3631, 3654, 3658 ETA 10/16 10/13- In Progress" 10/22 - 9/16 test scenarios are completed. 3800 defect is open. | 2025-08-15 | N | 06. PTP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2571 | PTPE1031 | 04.Enhancement | 02.IF - Intel Foundry | Send email notification with details of task for Quality notification – IF only | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2571_RICEFW_QI-130-110_Send%20email%20notification%20with%20details%20of%20task%20for%20Quality%20notification_IF.pptx?d=wf82cf738338a49d797538b06b385e02f&csf=1&web=1&e=UUcQdP | 02.No | 01.Yes |  | 2024-12-18 | cari.h.shim@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-07 | 2025-02-20 | 100% | 2024-12-18 | 2025-05-09 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-19 | 2025-10-10 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-09-02 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-11 | 01.S4 |  |  | 1 | 1 | 1031 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-03-07 | 2024-12-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | [5 empty] | 2025-03-07 | 2025-06-13 |  |  | 2025-10-24 |  | WIINGS Only | TRUE | 0 |  | 2321 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2570 | PTPE1030 | 04.Enhancement | 02.IF - Intel Foundry | Creation of Return PO from Action box within Notification – IF only | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2570_RICEFW_QI-130-110_Creation%20of%20Return%20PO%20from%20Action%20box%20within%20Notification_IF.pptx?d=w446a7bf1828d4ae3b8ac377a1756626a&csf=1&web=1&e=cm2WkB | 02.No | 01.Yes |  | 2024-12-18 | cari.h.shim@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-03-14 | 2025-02-20 | 100% | 2025-02-19 | 2025-06-06 | 2025-06-13 | 2025-05-20 | 100% | 2025-08-13 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-08-13 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-08-13 | [15 empty] | 2025-08-13 | 2025-08-13 | Yes |  | 2025-08-12 | 2025-08-22 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-13 | 2025-08-22 | 2025-08-22 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-11 | 01.S4 |  |  | 1 | 1 | 1030 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-03-14 | 2025-02-19 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | [12 empty] | 2025-08-13 | 2025-08-13 |  |  | 2025-08-18 | 2025-08-22 | 2025-08-18 | [5 empty] | 2025-03-14 | 2025-07-18 |  |  | 2025-10-24 |  | WIINGS |  | 0 |  | 2320 | [9 empty] | 8/18: FUT is completed in Sprint 16 and marked as completed by Jose on 8/13 | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2567 | PTPE1029 | 04.Enhancement | 02.IF - Intel Foundry | Creation of Notification as a follow up action with rejection codes – IF only | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2567_RICEFW_QI-130-110_Creation%20of%20Notification%20as%20a%20follow%20up%20action%20with%20rejection%20codes_IF.pptx?d=w8d719e77af3a49abbfda9fe470dc324e&csf=1&web=1&e=L2YINb | 02.No | 01.Yes |  | 2024-12-18 | Cari H Shim | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-03-14 | 2025-02-20 | 100% | 2025-02-20 | 2025-09-29 | 2025-10-03 | 2025-06-20 | 100% | 2025-09-03 | 2025-09-19 | 2025-07-11 | 2025-07-11 | 100% | 2025-09-03 | 2025-06-04 | 2025-06-13 | 2025-07-11 | 100% | 2025-09-03 | [15 empty] | 2025-09-03 | 2025-09-03 | Yes |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-11 | 01.S4 |  |  | 2 | 2 | 1029 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-03-14 | 2025-02-20 |  | 2025-09-03 | 2025-10-03 | 2025-09-03 |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | [12 empty] | 2025-09-03 | 2025-09-03 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | [5 empty] | 2025-03-14 | 2025-10-10 |  |  | 2025-10-24 |  | WIINGS |  | 0 |  | 2623 | [9 empty] | 9/12: This object is considered as part of sprint 18 FUT plan. Will start FUT from Monday. 9/5: TUT Approval is received. This object is not part of Sprint 17 FUT. It will be added to Sprint 18 FUT plan, 8/29: Awaiting TUT approval. This object is not planned in Sprint 17. Once TUT Approval is completed, It will be picked up for Sprint 18 FUT testing. 8/25: Awaiting TUT approval. This object is not planned in Sprint 17. Once TUT Approval is completed, It will be picked up for Sprint 18 FUT testing. 8/22: Developer confirmed today that review comments from Intel are addressed for this object. Awaiting TUT approval. 8/18: TUT is not approved. It is not planned to pick up for testing in sprint 17 as TUT is not completed. | 2025-06-13 | N | 06. PTP | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 17 |  | 2025-09-03 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2569 | PTPE1009 | 04.Enhancement | 02.IF - Intel Foundry | Returns to 3PL | 06. PTP | 6.2 PTP - Procurement | 99. Rejected/Cancelled/On Hold | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 04.Cancelled | 2024-12-19 | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 |  | 0% | 2025-04-18 | 2025-09-24 | 2025-10-01 |  | 0% | 2025-10-01 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | Yes | [13 empty] | 2025-11-10 | 2025-11-28 |  | Y | 0% | 2025-11-28 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-09 | 2026-01-09 | 2026-01-09 | vasamohan@deloitte.com | 2024-12-16 13:18 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 | 2025-01-06 | 01.S4 |  |  | 0.5 | 0.5 | 1009 | INT-CR2569 | #INVALID VALUE | [7 empty] | 2025-04-18 |  |  |  | 2025-10-01 |  |  |  | 2026-01-09 | [19 empty] | 2025-11-28 | [6 empty] | 2025-04-18 | 2026-01-09 |  |  | 2025-11-28 |  |  |  | 0 |  | 2319 | [10 empty] | 2026-01-09 | Y | 06. PTP | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2503 | PTPE0977 | 04.Enhancement | 02.IF - Intel Foundry | Develop app/transaction to Automate the stock from ‘Unrestricted/Blocked to Quality’ (with or without Inspection Lot Creation) | 06. PTP | 6.8 PTP - QM | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B12DA5139-4F94-4DCF-9B72-690265A1EBF0%7D&file=2503_QI-130-020_RICEFW_App%20to%20move%20stock%20from%20Unrestricted%20or%20Blocked%20to%20QI%20Stock.pptx&wdLOR=cA0CF97F7-32C0-4347-9C23-6F6FC215BE0C&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | cari.h.shim@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-11 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 100% | 2025-08-25 | 2025-07-04 | 2025-07-18 | 2025-07-11 | 100% | 2025-08-25 | 2025-07-04 | 2025-07-18 | 2025-07-11 | 100% | 2025-08-25 | [15 empty] | 2025-08-25 | 2025-08-25 | Yes |  | 2025-08-12 | 2025-08-22 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-28 | 2025-08-22 | 2025-08-22 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-12-06 07:21 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-18 | 01.S4 |  |  | 1 | 1 | 0977 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-28 | 2025-03-11 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | [12 empty] | 2025-08-25 | 2025-08-25 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  |  |  | WIINGS |  | 0 |  | 2500 | [10 empty] | 2025-07-18 | N | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-08-25 | 2025-08-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2506 | PTPE0962 | 04.Enhancement | 01.IP - Intel Product | Enhancement required to automatically create return purchase orders based on PM order GR status – IP & IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2506-PM-080-050-0005_PTP_Auto%20create%20return%20POs%20based%20on%20return%20reason%20and%20PM%20order%20GR%20status_IF_IP.pptx?d=w2206286b0ed14151bf2870eb5773aafc&csf=1&web=1&e=d66TsU | 02.No | 01.Yes |  | 2025-01-10 | Cari H Shim | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-03 | 2025-04-30 | 2025-04-07 | 100% | 2025-03-26 | 2025-08-01 | 2025-08-08 | 2025-06-17 | 100% | 2025-07-21 | 2025-08-29 | 2025-09-12 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-29 | 2025-09-12 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-09-19 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-11-12 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-26 00:26 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-16 | 01.S4 |  |  | 1 | 1 | 0962 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-04-30 | 2025-03-26 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | [5 empty] | 2025-04-30 | 2025-09-12 |  |  | 2025-09-26 |  | WIINGS Only | TRUE | 0 |  | 2122 | [7 empty] | 1. On Track | 1. Approved no action | 11/12 approved and smartsheet updated on 11/12 11/4 Awaiting approval 10/24 - Awaiting approval. Review comments from Pavan are addressed. 10/10 FUT Submitted for approval on 10/10 10/3 - Defect resolution in progress ETA today 9/29- Defect 3394 fix in progress | 2025-09-12 | Y | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2505 | PTPE0961 | 04.Enhancement | 01.IP - Intel Product | Enhancement required to automatically create rework or repair and replacement purchase requisitions based on PM order GR status – IP & IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2505-PM-080-050-0006_PTP_Auto%20create%20repair%20or%C2%A0rework%20PRs%20based%20on%C2%A0reason%20code%20and%20PM%20order%20GR%20status_IF.pptx?d=wec053115bdb149baab50c479ed170444&csf=1&web=1&e=6spysa | 02.No | 01.Yes |  | 2025-01-10 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-03 | 2025-04-30 | 2025-04-07 | 100% | 2025-03-26 | 2025-08-01 | 2025-08-08 | 2025-05-20 | 100% | 2025-06-12 | 2025-08-29 | 2025-09-12 | 2025-05-30 | 100% | 2025-05-30 | 2025-08-29 | 2025-09-12 | 2025-05-30 | 100% | 2025-05-30 | [15 empty] | 2025-05-30 | 2025-05-30 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-26 00:26 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-16 | 01.S4 |  |  | 1 | 1 | 0961 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-04-30 | 2025-03-26 |  | 2025-06-12 | 2025-08-08 | 2025-06-12 |  | 2025-05-30 | 2025-09-12 | [14 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-04-30 | 2025-09-12 |  |  | 2025-09-26 |  | WIINGS Only | TRUE | 0 |  | 2121 | [9 empty] | 9/12 Working on defect. 9/10 FUT Completed and Submitted for approval 9/8- Send for approval , 1 issue checking 9/5 - Defect raised to tech 9/1- Send for approval 8/25- Defect resolution in progress. 8/18- Defect resolution in progress | 2025-09-12 | Y | 06. PTP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 14 |  | 2025-09-12 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2528 | PTPE0958_IP | 04.Enhancement | 01.IP - Intel Product | Activating the Final Invoice Indicator at PO Level SAP S/4 HANA - IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2528-PM-150-050-0002-S4%20IP-%20Activating%20the%20Final%20invoice%20Indicator%20at%20the%20PO%20level%20.pptx?d=w7a04a4ef6aad4f62941fd73619b8fc75&csf=1&web=1&e=ihRWRm | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-03 | 2025-04-18 | 2025-01-24 | 100% | 2025-01-24 | 2025-06-09 | 2025-06-13 | 2025-06-20 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 |  | 2025-12-20 | 2026-01-03 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:14 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1 | 0958 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-04-18 | 2025-01-24 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2026-02-04 | 2026-02-04 | [6 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-10-10 |  |  |  | 0 |  | 2810 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/16: Awaiting approval from Andrea and Jorge [Intel IT] /2/10 As per intel's Feedback, additional scenarios are to be tested and additional changes are requested. Team is working with Tech team on the changes. 2/2 Awaiting Intel approval 1/29: FUT submitted for approval. New comment received from Intel Team. Meeting is scheduled to discuss open comment for today 1/29. 1/20 FUT completed. Walkthrough planned on 1/20 with Intel IT. Expected ETA for approval 1/27 1/13 Requirement Change after FUT completion. To be discussed in Ariba Build Call. Design change anticipated which will impact FS and Code change 1/9 - Internal Build 5463 is created. ETA is 1/9 EOD 1/5 Defects Resolved. FUT in Progress. Targeted to be completed by 1/7 12/17: Development team is working on development for internal CR mentioned. 12/12: Object is blocked due to pending development for internal CR: INT-Build-CR1057. | 2025-07-18 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | Yes | Need to check as this will be on plant level | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2527 | PTPE0958_IF | 04.Enhancement | 02.IF - Intel Foundry | Activating the Final Invoice Indicator at PO Level - SAP S/4 HANA - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2527-PM-150-050-0002-S4%20IF-%20Activating%20the%20Final%20invoice%20Indicator%20at%20the%20PO%20level.pptx?d=w91e5686403684227b3488ec437d33b93&csf=1&web=1&e=aBZoI2 | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-03 | 2025-04-18 | 2025-01-24 | 100% | 2025-01-24 | 2025-06-09 | 2025-06-13 | 2025-06-20 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 |  | 2025-12-20 | 2026-01-03 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:14 | cell-link@smartsheet.com | 2026-02-17 22:37 | 10 | 2024-12-20 | 01.S4 | PTPE0958_IP | 03.Medium | 0.2 | 0.2 | 0958 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-04-18 | 2025-01-24 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2026-02-04 | 2026-02-04 | [6 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-21 |  |  |  | 0 |  | 2809 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/16: Awaiting approval from Andrea and Jorge [Intel IT] 2/10 As per intel's Feedback, additional scenarios are to be tested and additional changes are requested. Team is working with Tech team on the changes. 2/2 Awaiting Intel approval 1/29: FUT submitted for approval. New comment received from Intel Team. Meeting is scheduled to discuss open comment for today 1/29. 1/20 FUT completed. Walkthrough planned on 1/20 with Intel IT. Expected ETA for approval 1/27 1/13 Requirement Change after FUT completion. To be discussed in Ariba Build Call. Design change anticipated which will impact FS and Code change 1/9 - Internal Build 5463 is created. ETA is 1/9 EOD 1/5 Defects Resolved. FUT in Progress. Targeted to be completed by 1/7 12/17: Development team is working on development for internal CR mentioned. 12/12: Object is blocked due to pending development for internal CR: INT-Build-CR1057. | 2025-07-18 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2504 | PTPE0941_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to capture material price from receiving plant in Intercompany STO. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-040_Enhancement%20to%20capture%20material%20price%20from%20receiving%20plant%20in%20Intercompany%20STO_IF%20_IP.pptx?d=wc0d6cbf9640a4bdbbaa0221eaaceb26d&csf=1&web=1&e=aXCynG | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-02-20 | 100% | 2025-02-20 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-26 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-06-12 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-06-12 | [15 empty] | 2025-06-12 | 2025-06-12 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1 | 0941 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-03-28 | 2025-02-20 |  | 2025-05-26 | 2025-07-11 | 2025-05-26 |  | 2025-06-12 | 2025-08-15 | 2025-06-12 | 2025-06-12 | [12 empty] | 2025-06-12 | 2025-06-12 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-09-26 |  |  |  | 0 |  | 2502 | [10 empty] | 2025-08-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-06-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2504 | PTPE0941_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to capture material price from receiving plant in Intercompany STO. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-040_Enhancement%20to%20capture%20material%20price%20from%20receiving%20plant%20in%20Intercompany%20STO_IF%20_IP.pptx?d=wc0d6cbf9640a4bdbbaa0221eaaceb26d&csf=1&web=1&e=aXCynG | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-02-20 | 100% | 2025-02-20 | 2025-06-06 | 2025-06-13 | 2025-05-20 | 100% | 2025-05-26 | 2025-07-11 | 2025-07-18 | 2025-05-30 | 100% | 2025-06-12 | 2025-07-11 | 2025-07-18 | 2025-05-30 | 100% | 2025-06-12 | [15 empty] | 2025-06-12 | 2025-06-12 | Yes |  | 2025-08-06 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:23 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 | PTPE0941_IP | 03.Medium | 0.2 | 0.2 | 0941 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-03-28 | 2025-02-20 |  | 2025-05-26 | 2025-06-13 | 2025-05-26 |  | 2025-06-12 | 2025-07-18 | 2025-06-12 | 2025-06-12 | [12 empty] | 2025-06-12 | 2025-06-12 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-09-26 |  | WIINGS |  | 0 |  | 2501 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-06-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 1875 | PTPE0919_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for E2Open relevant DSL. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1875-PTP_PM-080-060-0004_Enhancement%20required%20during%20GR%20applicable%20for%20DSL%20output%20type%20LPET%20from%20S4%20to%20E2O%20_IF%20_IP.pptx?d=wdb2a20b3897b4846a87b88a3e040d170&csf=1&web=1&e=1yaXwX | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-02-20 | 100% | 2025-02-07 | 2025-06-06 | 2025-06-13 | 2025-04-29 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes | 2025-06-03 | 2025-10-01 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 0919 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-03-28 | 2025-02-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-26 | 2025-10-08 | 2025-09-26 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-01-17 |  |  |  | 0 |  | 1687 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Custom table changes | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1875 | PTPE0919_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to trigger Output type which will generate IDOC once GR or GR reversal done for E2Open relevant DSL. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1875-PTP_PM-080-060-0004_Enhancement%20required%20during%20GR%20applicable%20for%20DSL%20output%20type%20LPET%20from%20S4%20to%20E2O%20_IF%20_IP.pptx?d=wdb2a20b3897b4846a87b88a3e040d170&csf=1&web=1&e=1yaXwX | 02.No | 01.Yes |  | 2024-12-19 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-28 | 2025-02-20 | 100% | 2025-02-07 | 2025-06-06 | 2025-06-13 | 2025-04-29 | 100% | 2025-08-04 | 2025-07-11 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-11 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes | 2025-06-03 | 2025-10-01 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 | PTPE0919_IP | 03.Medium | 0.2 | 0.2 | 0919 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-03-28 | 2025-02-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-26 | 2025-10-08 | 2025-09-26 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-01-17 |  |  |  | 0 |  | 1686 | [10 empty] | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2243 | PTPE0826 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required for FS-PTPI0017_IF, PTPI0018 to update the EKPO-VSART Field | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA2B4AD18-766A-4210-831E-7F02D459BBF9%7D&file=2243_Enhancement%20required%20for%20FS-PTPI0017_IF%2C%20PTPI0018%20%20to%20update%20the%20EKPO-VSART%20field.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | cari.h.shim@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | 100 | Supplier-Intel Resource, Forecast, Install System |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-10 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-26 | 2025-04-04 | 2025-04-18 | 2025-03-25 | 100% | 2025-04-10 | 2025-04-04 | 2025-04-18 | 2025-03-25 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes | 2025-06-03 | 2025-09-03 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1 | 0826 |  | R3 ITC1 | [6 empty] | 2024-12-10 | 2024-12-13 | 2024-12-10 |  | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | 2025-04-10 | 2025-04-18 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 2292 | [10 empty] | 2025-04-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1618 | PTPE0790_IP | 04.Enhancement | 04.GTS | Enhancement to enrich or remove transactions from Intrastat arrival declarations in IP S/4Hana system | 06. PTP | 6.6 PTP - GTS | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4E7CD4CD-A28D-46DA-83F6-161B90C60CD6%7D&file=1618_GTS_RICEFW%20-%20Intake%20Form_Intrastat%20-%20Collect%20Purchase%20Related%20Information%20(IP).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-23 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-10-23 09:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0790 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-09-12 | GTS |  |  | 0 | 08. Not Applicable | 1741 | [7 empty] | 4. Completed | 17. FUT In progress | 10/10: Awaiting test data from PTP for Receipt 11/18: Documentation Complete. Internal Review in-progress 12/04: On Track | 2025-11-05 | Y | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1616 | PTPE0790_IF | 04.Enhancement | 04.GTS | Enhancement to enrich or remove transactions from Intrastat arrival declarations in IF S/4Hana system | 06. PTP | 6.6 PTP - GTS | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7FAC9EDA-52E3-46D9-87E7-BF8C5CA3B4EA%7D&file=1616_GTS_RICEFW%20-%20Intake%20Form_Intrastat%20-%20Collect%20Purchase%20Related%20Information%20(IF).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-23 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-10-23 09:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 | PTPE0790_IP | 03.Medium | 0.2 | 0.2 | 0790 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-09-12 | GTS |  |  | 0 | 08. Not Applicable | 1740 | [7 empty] | 4. Completed | 17. FUT In progress | 10/10: Awaiting test data from PTP for Receipt 11/18: Documentation Complete. Internal Review in-progress 12/04: On Track | 2025-11-05 | Y | 06. PTP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0745_IP | 04.Enhancement | 01.IP - Intel Product | Quota Arrangement Mass Upload Tool Functionality IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-05-20 | 100% | 2025-05-26 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-30 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-30 | [15 empty] | 2025-05-30 | 2025-05-30 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-22 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 2 | 2 | 0745 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-02-21 | 2025-01-17 |  | 2025-05-26 | 2025-05-26 | 2025-05-26 |  | 2025-05-30 | 2025-05-30 | [14 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | [5 empty] | 2025-02-21 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2463 | [7 empty] | 1. On Track | 3. Awaiting Approval | 9/19- Sent for approval, waiting for feedback 9/12 - Sent for approval 9/10 Road block - QA Validations to be added. To reach out to SAP 9/5- 1 issue left tech is working 9/1- 1 Defect 2457 open 8/25- Feedback shared by Pavan defect resolution in progress. 8/18 - Sent for approval | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0745_IF | 04.Enhancement | 02.IF - Intel Foundry | Quota Arrangement Mass Upload Tool Functionality IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-22 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0745_IP | 02.High | 0.4 | 0.4 | 0745 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-02-21 | 2025-01-17 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | [5 empty] | 2025-02-21 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2462 | [9 empty] | 9/19- Sent for approval, waiting for feedback 9/12 - Sent for approval 9/10 Road block - QA Validations to be added. To reach out to SAP 9/5- 1 issue left tech is working 9/1- 1 Defect 2457 open 8/25- Feedback shared by Pavan defect resolution in progress. 8/18 - Sent for approval | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0744_IP | 04.Enhancement | 01.IP - Intel Product | PIR Mass Upload Tool Functionality IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-19 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-14 | 2025-08-13 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 | 2024-10-17 | 01.S4 |  |  | 2 | 2 | 0744 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2465 | [9 empty] | 8/18- Working with tech for defect resolution | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | Yes | Plant changes will need to be checked | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2229 | PTPE0744_IF | 04.Enhancement | 02.IF - Intel Foundry | PIR Mass Upload Tool Functionality IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-19 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-14 | 2025-08-13 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0744_IP | 02.High | 0.4 | 0.4 | 0744 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2464 | [9 empty] | 8/18- Working with tech for defect resolution | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0743_IP | 04.Enhancement | 01.IP - Intel Product | OA Mass Upload Tool Functionality IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-17 | 2025-01-24 | 2025-01-22 | 100% | 2025-01-17 | 2025-08-01 | 2025-08-08 | 2025-05-20 | 100% | 2025-05-26 | 2025-05-30 | 2025-09-12 | 2025-05-30 | 100% | 2025-05-30 | 2025-05-30 | 2025-09-12 | 2025-05-30 | 100% | 2025-05-30 | [15 empty] | 2025-05-30 | 2025-05-30 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 2 | 2 | 0743 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-24 | 2025-01-17 |  | 2025-05-26 | 2025-08-08 | 2025-05-26 |  | 2025-05-30 | 2025-09-12 | [14 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2467 | [9 empty] | 9/1- Issues CR to be raised 8/25- Sent for approval. 8/18- Working with tech for defect resolution | 2025-09-12 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-09-12 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0743_IF | 04.Enhancement | 02.IF - Intel Foundry | OA Mass Upload Tool Functionality IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-16 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-17 | 2025-01-24 | 2025-01-22 | 100% | 2025-01-17 | 2025-08-01 | 2025-08-08 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-06 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-06 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-10-17 | 01.S4 | PTPE0743_IP | 02.High | 0.4 | 0.4 | 0743 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-24 | 2025-01-17 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-06-06 |  | WIINGS |  | 0 | 08. Not Applicable | 2466 | [9 empty] | 9/1- Issues CR to be raised 8/25- Sent for approval. 8/18- Working with tech for defect resolution | 2025-09-12 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2352 | PTPE0733_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to validate the user that creates/edits the PO cannot make themselves the PO recipient | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2B46BF2B-E079-45BF-BCF1-80E4CB642A34%7D&file=PTP_S4_Enhancement_Recipient_PO.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-21 | 2025-05-02 | 2025-05-09 | 2025-04-01 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-04-11 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-03 | 2025-06-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-06-03 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0733 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-07-04 | 2025-06-11 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2290 | [10 empty] | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2352 | PTPE0733_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to validate the user that creates/edits the PO cannot make themselves the PO recipient | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2B46BF2B-E079-45BF-BCF1-80E4CB642A34%7D&file=PTP_S4_Enhancement_Recipient_PO.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-21 | 2025-05-02 | 2025-05-09 | 2025-04-01 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-04-11 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-10-17 | 01.S4 | PTPE0733_IP | 03.Medium | 0.2 | 0.2 | 0733 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-07-04 | 2025-06-11 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-20 |  | WIINGS |  | 0 | 08. Not Applicable | 2289 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2319 | PTPE0732 | 04.Enhancement | 02.IF - Intel Foundry | Pay@Accept Custom Program to release the invoice - SAP S/4 HANA IP and IF | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2319-PM-150-170-0011-PTP-IP-Pay@Accept%20-%20Release%20the%20Block%20functionality.pptx?d=w8e591da97c24445ab576ed0a42d58bc6&csf=1&web=1&e=H5VLa4 | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-04 | 2025-03-21 | 2024-10-04 | 100% | 2024-11-26 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-06-02 | 2025-05-09 | 2025-05-16 | 2025-08-29 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-08-29 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  | 2025-10-17 | 2025-11-01 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0732 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-03-21 | 2024-11-26 |  | 2025-06-02 | 2025-08-22 | 2025-06-02 |  | 2025-08-04 | 2025-08-29 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-03-21 | 2025-05-16 |  |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 2567 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4 FUT submitted for approval. 10/27: FUT is in progress. 10/17: FUT is in progress. We planned this FUT for approval in Sprint 19. 10/10: Team planned this FUT in Sprint 19. Dependency on Interface PTPI1533. Need to replan in object tracker. | 2025-05-16 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-29 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2289 | PTPE0731_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement on Goods Receipts created from S4 (IF-IP) to Ariba Network | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2289_PTP_LI-120-100_RICEFW_Enhancement%20on%20Goods%20Receipts%20created%20from%20S4%20(IF-IP)%20to%20Ariba%20Network.pptx?d=w349d487caa0041eb891de0a135e43bf4&csf=1&web=1&e=on8q5u&xsdata=MDV8MDJ8fDdlZTJjNmQ2ZmY0ZjRhZmU4ZDFjMDhkY2U4ZTk3ZmNmfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg2NDEzMzY3NDk4ODE1NjR8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPakEyTURSaU1EWmpMV0UzTm1NdE5EazVOQzFoWlRreExUTTFPRE16TlRWaU5qTTFZMTh4WWpjNU5tRmhOQzAxWWpRd0xUUXhPV1V0WW1aak55MHlOMll6TnpSbVpqYzRNekJBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN5T0RVek5qZzNOREkwTmc9PXw2MWU3ODkwYzg3Yjc0ZjdlOGQxYzA4ZGNlOGU5N2ZjZnw1Y2MwNDE1MGQzMzg0M2E3YjUwMWM4NjI2OTVkNDkxNw%3D%3D&sdata=WE1TOUIxTTQ3YitjZTE3cjM5S3RicENLQ0RTME81d2U1VG1qNkk0eUlzVT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cbabanerjee%40deloitte.com | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-14 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-03-26 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-21 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-19 | [15 empty] | 2025-04-19 | 2025-04-19 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0731 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-03-14 | 2025-01-17 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-04-21 | 2025-05-16 | 2025-04-21 | 2025-04-19 | [12 empty] | 2025-04-19 | 2025-04-19 |  |  | 2025-09-09 | 2025-09-12 | 2025-09-09 | [5 empty] | 2025-03-14 | 2025-05-16 |  |  | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 2455 | [10 empty] | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2289 | PTPE0731_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement on Goods Receipts created from S4 (IF-IP) to Ariba Network | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2289_PTP_LI-120-100_RICEFW_Enhancement%20on%20Goods%20Receipts%20created%20from%20S4%20(IF-IP)%20to%20Ariba%20Network.pptx?d=w349d487caa0041eb891de0a135e43bf4&csf=1&web=1&e=on8q5u&xsdata=MDV8MDJ8fDdlZTJjNmQ2ZmY0ZjRhZmU4ZDFjMDhkY2U4ZTk3ZmNmfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg2NDEzMzY3NDk4ODE1NjR8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPakEyTURSaU1EWmpMV0UzTm1NdE5EazVOQzFoWlRreExUTTFPRE16TlRWaU5qTTFZMTh4WWpjNU5tRmhOQzAxWWpRd0xUUXhPV1V0WW1aak55MHlOMll6TnpSbVpqYzRNekJBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN5T0RVek5qZzNOREkwTmc9PXw2MWU3ODkwYzg3Yjc0ZjdlOGQxYzA4ZGNlOGU5N2ZjZnw1Y2MwNDE1MGQzMzg0M2E3YjUwMWM4NjI2OTVkNDkxNw%3D%3D&sdata=WE1TOUIxTTQ3YitjZTE3cjM5S3RicENLQ0RTME81d2U1VG1qNkk0eUlzVT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cbabanerjee%40deloitte.com | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-14 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-03-26 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0731_IP | 03.Medium | 0.2 | 0.2 | 0731 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-03-14 | 2025-01-17 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-04-10 | 2025-05-16 | [14 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-09-09 | 2025-09-12 | 2025-09-09 | [5 empty] | 2025-03-14 | 2025-05-16 |  |  | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 2454 | [10 empty] | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2283 | PTPE0730_IP | 04.Enhancement | 01.IP - Intel Product | PR and PO interface enhancements to support Ariba Asset Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Enhancement_Ariba_Asset_Settlement.pptx?d=w20645d639a31463b9aa936c3f7ab9919&csf=1&web=1&e=Iirk9v | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-10-02 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-10-02 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0730 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2447 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/19- Send for approval awaiting issues were there 12/17- Waiting approval sent on 12th 12/12 : Will be send by tomorrow 12/11 Response received from Ariba. Resolution in progress with Tech Team 12/3 Awaiting SAP Inputs on Ariba Internal Error. ETA 12/4 11/24 Impacted by defect 4883 11/18 Defect with FPR and Tech Team 2208 awaiting resolution | 2025-06-13 | N | 06. PTP |  |  |  | 1216:FUT completed and sent for approval Current Status: SR# for Ariba issue to be escalated SAP Ariba SR #1433805/2025. SR got a response from Ariba Issue: FUT is now completed. Asset interface is failing to update the PR in Ariba, giving an internal error Next Steps: FUT Awaiting approval. Help needed: NA | 1125: SR# for Ariba issue to be escalated FPRE0783_IF Defect 2208 and 4716, 4614 (Keerti to priortize fix) | 5. Review Closed | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2283 | PTPE0730_IF | 04.Enhancement | 02.IF - Intel Foundry | PR and PO interface enhancements to support Ariba Asset Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Enhancement_Ariba_Asset_Settlement.pptx?d=w20645d639a31463b9aa936c3f7ab9919&csf=1&web=1&e=Iirk9v | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-14 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-22 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-10-02 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-10-02 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 | No |  | 2025-11-24 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0730_IP | 03.Medium | 0.2 | 0.2 | 0730 |  | R3 ITC1 | [6 empty] | 2025-02-22 | 2025-02-22 | 2025-02-22 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2446 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/19- Send for approval awaiting issues were there 12/17- Waiting approval sent on 12th 12/12 : Will be send by tomorrow 12/11 Response received from Ariba. Resolution in progress with Tech Team 12/3 Awaiting SAP Inputs on Ariba Internal Error. ETA 12/4 11/24 Impacted by defect 4883 11/18 Defect with FPR and Tech Team 2208 awaiting resolution | 2025-06-13 | N | 06. PTP |  |  |  | 1216:FUT completed and sent for approval Current Status: SR# for Ariba issue to be escalated SAP Ariba SR #1433805/2025. SR got a response from Ariba Issue: FUT is now completed. Asset interface is failing to update the PR in Ariba, giving an internal error Next Steps: FUT Awaiting approval. Help needed: NA | 1125: SR# for Ariba issue to be escalated FPRE0783_IF Defect 2208 and 4716, 4614 (Keerti to priortize fix) | 5. Review Closed | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2280 | PTPE0729_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement - Transfer of ownership Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Enhancement_Transfer_Ownership.pptx?d=waef30f31b53b4981ab093038efa0693f&csf=1&web=1&e=KUbum9 | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-06 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-03-26 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-04 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-04 | [15 empty] | 2025-04-04 | 2025-04-04 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0729 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-04-04 | 2025-05-16 | [14 empty] | 2025-04-04 | 2025-04-04 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 2443 | [7 empty] | 3. Off Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/25 FUT completed and shared for approval on 11/22 11/18 Issue with Security authorization. Fix in Progress 11/14 - Defect 4598. Tech team ETA is 11/14. FUT Completion is 11/19 11/11 : RAID 3039 raised for Luis to check on ARIBA side - Ariba is not sending the payload to APIGEE, webservice task is in error 11/11 - MW Team is still working on the CR Changes. ETA is 11/11 11/3 Blocked by INT-Build-CR1016 being worked by M/W Team. ETA 11/6 10/27 Blocked by Design Change. Limitation on Ariba capability to segregate data into IP and IF. Re-Design in discussion with Intel Process Stewards and SAP Team. *Roadblocked* Object 10/22 - Limitation of Segregation of IP and IF data | 2025-05-16 | N | 06. PTP |  |  |  | Submitted for approval |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2280 | PTPE0729_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement - Transfer of ownership Interface | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP_S4_Enhancement_Transfer_Ownership.pptx?d=waef30f31b53b4981ab093038efa0693f&csf=1&web=1&e=KUbum9 | 01.Yes | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-06 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-03-26 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-05-05 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-05-05 | [15 empty] | 2025-05-05 | 2025-05-05 | No |  | 2025-10-28 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0729_IP | 03.Medium | 0.2 | 0.2 | 0729 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-05-05 | 2025-05-16 | 2025-05-05 | 2025-05-05 | [12 empty] | 2025-05-05 | 2025-05-05 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 2442 | [7 empty] | 3. Off Track | 2. Smartsheet Hygiene(5.2) | 12/3 Waiting for Jose to mark as 100% 11/25 FUT completed and shared for approval on 11/22 11/18 Issue with Security authorization. Fix in Progress 11/14 - Defect 4598. Tech team ETA is 11/14. FUT Completion is 11/19 11/11 : RAID 3039 raised for Luis to check on ARIBA side - Ariba is not sending the payload to APIGEE, webservice task is in error 11/11 - MW Team is still working on the CR Changes. ETA is 11/11 11/3 Blocked by INT-Build-CR1016 being worked by M/W Team. ETA 11/6 10/27 Blocked by Design Change. Limitation on Ariba capability to segregate data into IP and IF. Re-Design in discussion with Intel Process Stewards and SAP Team. *Roadblocked* Object 10/22 - Limitation of Segregation of IP and IF data | 2025-05-16 | N | 06. PTP |  |  |  | Submitted for approval |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 13 |  | 2025-05-16 | 2025-05-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0727_IP | 04.Enhancement | 01.IP - Intel Product | Source List Data Mass Upload Tool Functionality IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-17 | 2025-01-24 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 2 | 2 | 0727 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-24 | 2025-01-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-01-24 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2461 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100%. 10/10 Validation CR draft created. Proposal shared with Intel IT to Validate and confirm. 10/3 to be discussed with tech and proposal to bsuiness 9/29 - Source list to be discussed -proposal change to be discussed 9/19- Working with tech 9/12 9/10 Road blocked. POC Requested for SAP Recommendation 9/10 Road blocked. POC Requested for SAP Recommendation 9/5 - Working wit tech on recommendation provided by SAP 9/1 - SAP note raised to check BDC issues. 8/25 - Reviewed from Pavan and shared feedback, check internally 8/18- Feedback to be accommodated. 8/11 - Sent for approval waiting for business review 8/4 FUT shared for approval. Feedbacks Incorporated. Awaiting Final approval from Intel | 2025-05-16 | N | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2229 | PTPE0727_IF | 04.Enhancement | 02.IF - Intel Foundry | Source List Data Mass Upload Tool Functionality IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B231BE8E7-ABEE-4BB7-8AFC-F4596D6FDE1A%7D&file=2229_PTP_PM-040-140_RICEFW_Source%20List%20Data%20Mass%20Upload%20Tool%20Functionality%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-17 | 2025-01-24 | 2025-01-22 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-10-17 | 01.S4 | PTPE0727_IP | 02.High | 0.4 | 0.4 | 0727 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-24 | 2025-01-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-01-24 | 2025-05-16 |  |  | 2025-06-06 |  | WIINGS |  | 0 | 08. Not Applicable | 2460 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 10/22 - FUT approved. Jose to mark 100%. 10/10 Validation CR draft created. Proposal shared with Intel IT to Validate and confirm. 10/3 to be discussed with tech and proposal to business 9/29 - Source list to be discussed -proposal change to be discussed 9/19- Working with tech 9/12 9/10 Road blocked. POC Requested for SAP Recommendation 9/10 Road blocked. POC Requested for SAP Recommendation 9/5 - Working wit tech on recommendation provided by SAP 9/1 - SAP note raised to check BDC issues. 8/25 - Reviewed from Pavan and shared feedback, check internally 8/18- Feedback to be accommodated. 8/11 - Sent for approval waiting for business review 8/4 FUT shared for approval. Feedbacks Incorporated. Awaiting Final approval from Intel | 2025-05-16 | N | 06. PTP | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2200 | PTPE0726_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to validate enabled supplier details to trigger Ariba relevant interfaces (IF-IP-CFIN) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1C65295D-52DF-4F84-B9FC-515CAAEE46CD%7D&file=2200_PTP_PM-080-060_RICEFW_Enhancement%20to%20populate%20Ariba%20Network%20Vendor%20table%20with%20supplier%20entries%20in%20S4%20(IF-IP-CFIN).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-17 | 2025-07-04 | 2025-07-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0726_CFIN | 03.Medium | 0.2 | 0.2 | 0726 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-28 | 2025-03-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-07-01 |  |  |  | 0 | 08. Not Applicable | 2553 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis | 2025-08-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2200 | PTPE0726_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to validate enabled supplier details to trigger Ariba relevant interfaces (IF-IP-CFIN) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1C65295D-52DF-4F84-B9FC-515CAAEE46CD%7D&file=2200_PTP_PM-080-060_RICEFW_Enhancement%20to%20populate%20Ariba%20Network%20Vendor%20table%20with%20supplier%20entries%20in%20S4%20(IF-IP-CFIN).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-17 | 2025-07-04 | 2025-07-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 | PTPE0726_CFIN | 03.Medium | 0.2 | 0.2 | 0726 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-28 | 2025-03-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-07-01 |  |  |  | 0 | 08. Not Applicable | 2552 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis | 2025-08-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2200 | PTPE0726_CFIN | 04.Enhancement | 05.CFIN | Enhancement to validate enabled supplier details to trigger Ariba relevant interfaces (IF-IP-CFIN) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1C65295D-52DF-4F84-B9FC-515CAAEE46CD%7D&file=2200_PTP_PM-080-060_RICEFW_Enhancement%20to%20populate%20Ariba%20Network%20Vendor%20table%20with%20supplier%20entries%20in%20S4%20(IF-IP-CFIN).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Cari H Shim | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-28 | 2025-03-20 | 100% | 2025-03-17 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0726 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-28 | 2025-03-17 |  | 2025-05-24 | 2025-07-11 | 2025-05-24 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-03-28 | 2025-08-15 |  |  | 2025-07-01 |  |  |  | 0 | 08. Not Applicable | 2551 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis 10/10 FUT Submitted for approval on 10/8. Awaiting approval from Jorge and Luis | 2025-08-15 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2081 | PTPE0707 | 04.Enhancement | 02.IF - Intel Foundry | PR workflow Custom Table enhancement | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/3%20Final%20Deliverables/1.%20Design/D.%20RICEFW%20List/PM-070-070-Perform%20Requisition%20Approval%20Process/2081_PTP_070_070_Workflow%20Custom%20Table%20Enhancement%20IP%20IF.pptx?d=w4d1edce69c264afb8b6f82b67a9d6fd6&csf=1&web=1&e=7MilW4 | 02.No | 01.Yes |  | 2024-10-09 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-03-24 | 2025-04-18 | 2024-12-11 | 100% | 2024-11-26 | 2025-05-12 | 2025-05-16 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | 2025-06-09 | 2025-06-13 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 | Yes |  | 2025-07-04 | 2025-07-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-15 | 2025-07-15 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-22 06:47 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0707 |  | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-11-26 | 2025-04-18 | 2024-11-26 |  | 2025-01-07 | 2025-05-16 | 2025-01-07 |  | 2025-01-30 | 2025-01-31 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-08-15 |  | WIINGS |  | 0 | 08. Not Applicable | 2084 | [9 empty] | 9/5 - This is approved by Intel 9/1- Defect 2595 and 2624 open 8/25- 8/18 : CR in progress 8/18 : CR in progress | 2025-06-13 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-06-13 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2236 | PTPE0706_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to Post Goods Receipt for the converted Ariba Purchase Orders in S/4 post PO migration. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2236_Enhancement%20required%20after%20PO%20migration%20to%20post%20GRN%20for%20Ariba%20PO%20in%20S4%20_IF%20_IP.pptx?d=w51cc4b6ca7154f7dabb797e4be1581f5&csf=1&web=1&e=NK10RT | 02.No | 01.Yes |  | 2024-10-09 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-14 | 2025-03-19 | 100% | 2025-03-11 | 2025-06-06 | 2025-06-13 | 2025-04-01 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-07-04 | 2025-07-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-19 | 2025-08-10 | 2025-07-15 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-24 | 01.S4 |  |  | 2 | 2 | 0706 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-19 | 2025-03-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-31 | 2025-08-10 | 2025-07-31 | [5 empty] | 2025-03-14 | 2025-07-18 |  |  | 2025-08-10 |  |  |  | 0 | 08. Not Applicable | 2472 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change |  | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2236 | PTPE0706_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Post Goods Receipt for the converted Ariba Purchase Orders in S/4 post PO migration. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2236_Enhancement%20required%20after%20PO%20migration%20to%20post%20GRN%20for%20Ariba%20PO%20in%20S4%20_IF%20_IP.pptx?d=w51cc4b6ca7154f7dabb797e4be1581f5&csf=1&web=1&e=NK10RT | 02.No | 01.Yes |  | 2024-10-09 | Cari H Shim | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-07 | 2025-03-14 | 2025-03-19 | 100% | 2025-03-11 | 2025-06-06 | 2025-06-13 | 2025-04-01 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-07-04 | 2025-07-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-19 | 2025-08-10 | 2025-07-15 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jenoronha@deloitte.com | 2025-02-28 08:47 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-24 | 01.S4 | PTPE0706_IP | 02.High | 0.4 | 0.4 | 0706 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-19 | 2025-03-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-31 | 2025-08-10 | 2025-07-31 | [5 empty] | 2025-03-14 | 2025-07-18 |  |  | 2025-08-10 |  |  |  | 0 | 08. Not Applicable | 2471 | [10 empty] | 2025-07-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1772 | PTPE0656_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement on Purchase Orders Created or Changed from Ariba to S4 (IF-IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B26A1683B-EBFD-43A6-B2EE-1333BC4EFE0C%7D&file=1772_PTP_PM-080-010_RICEFW_Enhancement%20for%20Custom%20logics%20on%20Purchase%20Orders%20Created%20or%20Changed%20from%20Ariba%20to%20S4%20(IF-IP).pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-09-18 | Cari H Shim | 01.Approved | 2024-10-03 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-07 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-03-07 | 2025-03-14 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-18 14:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0656 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-27 | 2025-08-27 | [6 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1999 | [10 empty] | 2025-04-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1772 | PTPE0656_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement on Purchase Orders Created or Changed from Ariba to S4 (IF-IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B26A1683B-EBFD-43A6-B2EE-1333BC4EFE0C%7D&file=1772_PTP_PM-080-010_RICEFW_Enhancement%20for%20Custom%20logics%20on%20Purchase%20Orders%20Created%20or%20Changed%20from%20Ariba%20to%20S4%20(IF-IP).pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-09-18 | Cari H Shim | 01.Approved | 2024-10-03 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-07 | 2024-12-13 | 2024-12-11 | 100% | 2024-12-09 | 2025-03-07 | 2025-03-14 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-18 14:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 | PTPE0656_IP | 03.Medium | 0.2 | 0.2 | 0656 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-13 | 2024-12-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-27 | 2025-08-27 | [6 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1998 | [10 empty] | 2025-04-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1890 | PTPE0606_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to create idoc extension for payload header info to send data to E2Open via MuleSoft | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7036CB54-C946-4E85-B2A5-9693EF107B7F%7D&file=1890-PTP_PM-080-060-0004_Enhancement%20required%20to%20create%20idoc%20extension%20for%20payload%20header%20information%20S4%20to%20E2O_OpenText%20_IF%20_IP.pptx&wdOB=D6869A7EAAC243E183149207EA333564&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-04 | Cari H Shim | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-08 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-08 | [15 empty] | 2025-01-08 | 2025-01-08 | Yes |  | 2025-08-13 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-09-10 | 2025-02-20 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-31 | 2025-01-31 | 2025-01-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 |  |  | 2 | 2 | 0606 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-08 | [12 empty] | 2025-01-08 | 2025-01-08 |  |  | 2025-08-21 | 2025-09-10 | 2025-08-21 | [5 empty] | 2024-10-17 | 2025-01-31 |  |  | 2025-05-23 |  |  |  | 0 |  | 2326 | [9 empty] | 25/7 - Scheduled for closure in upcoming sprint as this is E2O and require to be close with PTPI0136 | 2025-01-31 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-31 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1890 | PTPE0606_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to create idoc extension for payload header info to send data to E2Open via MuleSoft | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7036CB54-C946-4E85-B2A5-9693EF107B7F%7D&file=1890-PTP_PM-080-060-0004_Enhancement%20required%20to%20create%20idoc%20extension%20for%20payload%20header%20information%20S4%20to%20E2O_OpenText%20_IF%20_IP.pptx&wdOB=D6869A7EAAC243E183149207EA333564&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-04 | Cari H Shim | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 | Yes |  | 2025-08-13 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-09-10 | 2025-02-20 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-31 | 2025-01-31 | 2025-01-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 | PTPE0606_IP | 02.High | 0.4 | 0.4 | 0606 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-30 | 2025-01-31 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-08-21 | 2025-09-10 | 2025-08-21 | [5 empty] | 2024-10-17 | 2025-01-31 |  |  | 2025-05-23 |  |  |  | 0 |  | 2325 | [9 empty] | 25/7 - Scheduled for closure in upcoming sprint as this is E2O and require to be close with PTPI0136 | 2025-01-31 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1966 | PTPE0558_IP | 04.Enhancement | 01.IP - Intel Product | Enhancements for chemical purchases on non MRP PR’s. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1966-PM-070-020-PTP_S4_ICHEM_enhancement.pptx?d=w53b6e35dd36c4144a2b99434cad812b1&csf=1&web=1&e=60HLnB | 01.Yes | 01.Yes |  | 2024-08-20 | Cari H Shim | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-07 | 2025-02-14 | 2024-12-27 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-02-28 | 100% | 2025-03-01 | 2025-05-02 | 2025-05-16 | 2025-03-07 | 100% | 2025-03-07 | 2025-05-02 | 2025-05-16 | 2025-03-07 | 100% | 2025-03-07 | [15 empty] | 2025-03-07 | 2025-03-07 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-23 | 01.S4 |  |  | 1 | 1 | 0558 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-02-14 | 2024-12-18 |  | 2025-03-01 | 2025-04-11 | 2025-03-01 |  | 2025-03-07 | 2025-05-16 | [14 empty] | 2025-03-07 | 2025-03-07 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-02-14 | 2025-05-16 |  |  | 2025-09-04 |  |  |  | 0 | 08. Not Applicable | 1919 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-05-16 | 2025-03-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1966 | PTPE0558_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancements for chemical purchases on non MRP PR’s. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1966-PM-070-020-PTP_S4_ICHEM_enhancement.pptx?d=w53b6e35dd36c4144a2b99434cad812b1&csf=1&web=1&e=60HLnB | 01.Yes | 01.Yes |  | 2024-08-20 | Cari H Shim | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-07 | 2025-02-14 | 2024-12-27 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-02-28 | 100% | 2025-03-01 | 2025-05-09 | 2025-05-16 | 2025-03-07 | 100% | 2025-05-21 | 2025-05-09 | 2025-05-16 | 2025-03-07 | 100% | 2025-05-21 | [15 empty] | 2025-05-21 | 2025-05-21 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-23 | 01.S4 | PTPE0558_IP | 03.Medium | 0.2 | 0.2 | 0558 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-02-14 | 2024-12-18 |  | 2025-03-01 | 2025-04-11 | 2025-03-01 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | [12 empty] | 2025-05-21 | 2025-05-21 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-02-14 | 2025-05-16 |  |  | 2025-09-04 |  |  |  | 0 | 08. Not Applicable | 1918 | [7 empty] | 1. On Track | 20. Connection Issue |  | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-21 | 2025-05-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1847 | PTPE0543_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to E2O _IF _IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1847-PTP_PM-080-060-0004_Enhancement%20required%20for%20ORDERS05%20IDOC%20applicable%20for%20PO%20outbound%20from%20S4%20to%20E2O%20_IF%20_IP.pptx?d=w17c30f36d038444ba6e457115c18a9b4&csf=1&web=1&e=aNdxRb | 02.No | 01.Yes |  | 2024-08-23 | Cari H Shim | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-18 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-17 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 | Yes |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-08-14 10:19 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 | 2024-08-30 | 01.S4 |  |  | 1 | 1 | 0543 | INT-CR0288 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2024-10-17 | 2024-12-20 |  |  | 2025-03-17 |  |  |  | 0 |  | 2165 | [10 empty] | 2024-12-20 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | Yes | Custom table changes | No |  | No |  | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1847 | PTPE0543_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required for ORDERS05 IDOC applicable for PO outbound from S4 to E2O _IF _IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1847-PTP_PM-080-060-0004_Enhancement%20required%20for%20ORDERS05%20IDOC%20applicable%20for%20PO%20outbound%20from%20S4%20to%20E2O%20_IF%20_IP.pptx?d=w17c30f36d038444ba6e457115c18a9b4&csf=1&web=1&e=aNdxRb | 02.No | 01.Yes |  | 2024-08-23 | Cari H Shim | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-18 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-17 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 | Yes |  | 2025-10-01 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2024-12-20 | 2024-12-20 | 2024-12-20 | jenoronha@deloitte.com | 2024-09-04 05:24 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-04 | 01.S4 | PTPE0543_IP | 03.Medium | 0.2 | 0.2 | 0543 | INT-CR0288 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2024-10-17 | 2024-12-20 |  |  | 2025-03-17 |  |  |  | 0 |  | 2163 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2024-12-20 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1727 | PTPE0472_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to map correct plant and user ID’s for Ariba PR replication in S4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B010CE7FC-5DF6-4D54-8BA6-0686B4C02631%7D&file=890_PTP_RICEFW_Enhancement%20for%20adding%20Hazmat%20flag%2C%20IPN%20and%20EHS%20fields%20on%20table(EBAN)%20for%20Purchase%20Requisitions%20from%20Ariba%20to%20S4%20(IF-IP).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | pgaroo@deloitte.com | 2024-07-22 10:39 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-22 | 01.S4 |  |  | 1 | 1 | 0472 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-08-18 | 2025-08-27 | 2025-08-18 | [5 empty] | 2024-10-17 | 2025-01-17 |  |  | 2025-01-31 |  |  |  | 0 |  | 2188 | [10 empty] | 2025-01-17 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1727 | PTPE0472_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to map correct plant and user ID’s for Ariba PR replication in S4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B010CE7FC-5DF6-4D54-8BA6-0686B4C02631%7D&file=890_PTP_RICEFW_Enhancement%20for%20adding%20Hazmat%20flag%2C%20IPN%20and%20EHS%20fields%20on%20table(EBAN)%20for%20Purchase%20Requisitions%20from%20Ariba%20to%20S4%20(IF-IP).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | No |  | 2025-08-13 | 2025-08-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-27 | 2025-08-27 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | jenoronha@deloitte.com | 2024-08-19 01:10 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-22 | 01.S4 | PTPE0472_IP | 03.Medium | 0.2 | 0.2 | 0472 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-08-18 | 2025-08-27 | 2025-08-18 | [5 empty] | 2024-10-17 | 2025-01-17 |  |  | 2025-01-31 |  |  |  | 0 |  | 2187 | [10 empty] | 2025-01-17 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1774 | PTPE0471 | 04.Enhancement | 01.IP - Intel Product | Review the auto reversal of payment documents, Reset clearing of invoice and payment documents & update funding request with zero balance - SAP S/4 HANA CFIN | 06. PTP | 6.7 PTP - Enable Payments | 99. Rejected/Cancelled/On Hold | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-150-150-0001-PTP-CFIN-Auto%20Reversal%20and%20reset%20clearing%20or%20invoice%20and%20payment%20document.pptx?d=wde63d35210c7431d908d86ef8cb3bad8&csf=1&web=1&e=3TY4L9 | 02.No | 01.Yes |  | 2024-07-28 | Cari H Shim | 04.Cancelled | 2024-08-01 | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-10-21 |  | 0% | 2024-10-21 | 2025-09-12 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | [14 empty] | 2025-09-15 | 2025-10-10 |  | Y | 0% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2026-01-09 | 2026-01-09 | 2026-01-09 | pgaroo@deloitte.com | 2024-07-22 10:39 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 |  | 01.S4 |  |  | 2 | 2 | 0471 | INT-CR1774 | N/A | [7 empty] | 2024-10-21 |  |  |  | 2025-09-19 |  |  |  | 2026-01-09 | [19 empty] | 2025-10-10 | [6 empty] | 2024-10-21 | 2025-05-16 |  |  | 2025-01-29 |  |  |  | 0 | 08. Not Applicable | 2655 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | FSD under draft with Treasury Team. | 2026-01-09 | Y | 06. PTP | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 752 | PTPE0371_IP | 04.Enhancement | 01.IP - Intel Product | Standard BTE for Manage Supplier Line items to add the PO and Supplier name - SAP S/4 HANA IP | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/752-PM-150-170-0007-PTP-IP-Manage%20Supplier%20Line%20items%20with%20PO.pptx?d=w4eba32aae2024cf4b7f60354f23c3a84&csf=1&web=1&e=A5n430 | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-23 | 2024-08-12 | 2024-08-12 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2024-09-06 | 2024-09-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-10 | 2025-02-21 | 2024-09-06 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-18 06:01 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | PTPE0371_CFIN | 03.Medium | 0.2 | 0.2 | 0371 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | [5 empty] | 2024-08-09 | 2024-12-20 |  |  | 2024-09-06 |  |  |  | 0 | 08. Not Applicable | 2380 | [9 empty] | 9/01:CR approval is in progress. 8/25: CR 1044 is in progress. 8/18: INT-CR1044 is in progress for extending object in FBL1H report. 8/11 - business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. 8/4 - EP team completed this FUT and reviewed with business. Originally this enhancement is done in FBL1N report but business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. | 2024-12-20 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 753 | PTPE0371_IF | 04.Enhancement | 02.IF - Intel Foundry | Standard BTE for Manage Supplier Line items to add the PO and Supplier name - SAP S/4 HANA IF | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/752-PM-150-170-0007-PTP-IP-Manage%20Supplier%20Line%20items%20with%20PO.pptx?d=w4eba32aae2024cf4b7f60354f23c3a84&csf=1&web=1&e=A5n430 | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-23 | 2024-08-12 | 2024-08-12 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2024-09-06 | 2024-09-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-10 | 2025-02-21 | 2024-09-06 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-18 06:01 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | PTPE0371_CFIN | 03.Medium | 0.2 | 0.2 | 0371 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | [5 empty] | 2024-08-09 | 2024-12-20 |  |  | 2024-09-06 |  |  |  | 0 | 08. Not Applicable | 2527 | [9 empty] | 9/01:CR approval is in progress. 8/25: CR 1044 is in progress. 8/18: INT-CR1044 is in progress for extending object in FBL1H report. 8/11 - business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. 8/4 - EP team completed this FUT and reviewed with business. Originally this enhancement is done in FBL1N report but business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. | 2024-12-20 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 752 | PTPE0371_CFIN | 04.Enhancement | 05.CFIN | Standard BTE for Manage Supplier Line items to add the PO and Supplier name - SAP S/4 HANA CFIN | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/11. Technology/RICEFW/10 RICEFW Inbox/752-PM-150-170-0007-PTP-IP, CFIN-Manage Supplier Line items with PO.pptx?d=w4eba32aae2024cf4b7f60354f23c3a84&csf=1&web=1&e=iDY6ag | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-06-16 | 2025-07-10 | 2025-07-10 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-17 | 2025-09-05 | 2025-10-03 | 2025-09-18 | 100% | 2025-09-17 | 2025-09-05 | 2025-10-03 | 2025-09-18 | 100% | 2025-09-17 | [15 empty] | 2025-09-17 | 2025-09-17 |  | 2025-09-19 | 2025-09-26 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-09-17 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-06-03 02:48 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0371 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-09-17 | 2025-10-03 | 2025-09-17 | 2025-09-17 | [12 empty] | 2025-09-17 | 2025-09-17 |  |  | 2025-09-17 | 2025-10-09 | 2025-09-17 | [5 empty] | 2025-07-10 | 2025-10-03 |  |  | 2025-10-09 |  |  |  | 0 | 08. Not Applicable | 3078 | [10 empty] | 2025-10-03 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 783 | PTPE0365 | 04.Enhancement | 01.IP - Intel Product | Enhancement for populating DPAS data on Purchase Requisition (IF and IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/783_PTP_PM-070-070-0004_Enhancement%20to%20Populate%20DPAS%20details%20on%20PR%20(IF%20and%20IP).pptx?d=w3f2db12eb3814401a951b773ed2216a7&csf=1&web=1&e=eyERs1 | 02.No | 01.Yes |  | 2024-06-18 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2025-01-24 | 2024-09-20 | 100% | 2025-03-03 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | Yes | 2025-07-15 | 2025-07-04 | 2025-07-15 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-15 | 2025-07-15 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-06-18 05:17 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 0365 | INT-CR0297 | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-03 | 2025-03-03 |  | 2025-05-24 | 2025-07-11 | 2025-05-24 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-07-15 |  |  |  | 0 | 08. Not Applicable | 2354 | [9 empty] | 8/11 - Approved have asked Jose to mark as 100% | 2025-08-15 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 670 | PTPE0318_IP | 04.Enhancement | 01.IP - Intel Product | Custom program to block the vendor invoice based on the different business scenarios - SAP S/4 HANA IP | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/670-PM-150-170-0003-PTP-IP-Vendor%20Invoice%20-%20Block%20functionality.pptx?d=wdcee0cb9eb854dd3a34f402c3b925ba0&csf=1&web=1&e=fms8cs | 02.No | 01.Yes |  | 2024-06-11 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-22 | 2024-08-16 | 100% | 2024-11-08 | 2025-03-07 | 2025-03-14 | 2025-03-25 | 100% | 2025-03-26 | 2025-04-11 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-21 | 2025-04-11 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-17 | [15 empty] | 2025-04-17 | 2025-04-17 |  |  | 2024-09-20 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2024-09-20 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-06-11 10:18 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0318 |  | R3 ITC1 | [6 empty] | 2024-11-08 | 2024-11-08 | 2024-11-08 |  | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-17 | [12 empty] | 2025-04-17 | 2025-04-17 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-08-16 | 2025-04-18 |  |  | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 1942 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 1/9 - Defect created. ETA to fix is 1/9. Approval will be spilled over next week 1/5 Awaiting approval from Intel IT 12/17: Waiting for approval from Andrea and Jorge Intel IT. Submitted for approval on 12/12. 12/12: Submitted for approval on 12/12. 12/3 FUT in Progress. ETA 12/5 11/25 Blocked by Security issue/defect where authorization is not working. 11/18 FUT initiated for S20. FUT completion by 12/03 11/11 - E2E FUT to begin in S20. Readsoft is ready. 11/4 - Configuration is completed from ReadSoft. FUT in progress. Will be closed in S20. 10/22 - ReadSoft Readiness dependency. Most likely will be ready by next week 10/10: ReadSoft Readiness dependency. P1 RAID [ ID: 02421] is open on Karla for ReadSoft. 9/29: ReadSoft system integration is not completed and team is dependent upon ReadSoft readiness. 9/19: Same status, team is waiting for ReadSoft readiness. 9/10 ReadSoft will be ready by Sept End. This FUT is pushed to sprint 19 9/8 - We are dependent on the Read soft system to complete the E2E FUT 9/01: FUT for 2 blocks are completed, FUT is in progress for other blocks. 8/25: Defect is resolved, team is working to close FUT and revised ETA is 9/10/2025. 8/18: Defect 2165 is raised for Tech-ABAP team. Facing issue with Block functionality for PTPE0318_IP 8/11 - We have resolved the MIRO dump error and working on further steps in the FUT This FUT is in progress. | 2025-04-18 | N | 06. PTP |  |  |  | 0107: FUT completed and awaiting approval Current Status: Configuration is completed from ReadSoft. FUT in progress. Issue: Readsoft App readiness is delayed from August and is now 11/7. Next Steps: FUT Review in progress Help needed: N/A | ETA 1126 | 5. Review Closed |  | Defects | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 671 | PTPE0318_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom program to block the vendor invoice based on the different business scenarios - SAP S/4 HANA IF | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-06-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/671-PM-150-170-0004-PTP-IF-Vendor%20Invoice%20-%20Block%20functionality.pptx?d=w271c2c6692fa4a18856bbdc919b659e8&csf=1&web=1&e=FnyWTe | 02.No | 01.Yes |  | 2024-06-11 | Cari H Shim | 01.Approved | 2024-06-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-22 | 2024-08-16 | 100% | 2024-11-08 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-26 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-21 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-17 | [15 empty] | 2025-04-17 | 2025-04-17 |  |  | 2024-09-20 | 2024-09-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2024-09-20 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-06-11 10:18 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | PTPE0318_IP | 04.Low | 0.1 | 0.1 | 0318 |  | R3 ITC1 | [6 empty] | 2024-11-08 | 2024-11-08 | 2024-11-08 |  | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-17 | [12 empty] | 2025-04-17 | 2025-04-17 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-08-16 | 2025-04-18 |  |  | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 1943 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 1/9 - Defect created. ETA to fix is 1/9. Approval will be spilled over next week 1/5 Awaiting approval from Intel IT 12/17: Waiting for approval from Andrea and Jorge Intel IT. Submitted for approval on 12/12. 12/12: Submitted for approval on 12/12. 12/3 FUT in Progress. ETA 12/5 11/25 Blocked by Security issue/defect where authorization is not working. 11/18 FUT initiated for S20. FUT completion by 12/03 11/11 - E2E FUT to begin in S20. Readsoft is ready. 11/4 - Configuration is completed from ReadSoft. FUT in progress. Will be closed in S20. 10/22 - ReadSoft Readiness dependency. Most likely will be ready by next week 10/10: ReadSoft Readiness dependency. P1 RAID [ ID: 02421] is open on Karla for ReadSoft. 9/29: ReadSoft system integration is not completed and team is dependent upon ReadSoft readiness. 9/19: Same status, team is waiting for ReadSoft readiness. 9/10 ReadSoft will be ready by Sept End. This FUT is pushed to sprint 19 9/8 - We are dependent on the Read soft system to complete the E2E FUT 9/01: FUT for 2 blocks are completed, FUT is in progress for other blocks. 8/25: Defect is resolved, team is working to close FUT and revised ETA is 9/10/2025. 8/18: Defect 2165 is raised for Tech-ABAP team. Facing issue with Block functionality for PTPE0318_IP 8/11 - We have resolved the MIRO dump error and working on further steps in the FUT This FUT is in progress. | 2025-04-18 | N | 06. PTP |  |  |  | 0107: FUT completed and awaiting approval Current Status: Configuration is completed from ReadSoft. FUT in progress. Issue: Readsoft App readiness is delayed from August and is now 11/7. Next Steps: FUT Review in progress Help needed: N/A | ETA 1126 | 5. Review Closed |  | Defects | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 624 | PTPE0259_IP | 04.Enhancement | 01.IP - Intel Product | Develop a routing logic to send Purchase Order to the Boundary apps from S/4 HANA System (IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/624_PM-080-060_0001_PTP_Routing%20Logic%20to%20Transmit%20Order%20to%20Supplier_v1.0_IP.pptx?d=w1957dffe207e49149388a728be44b29f&csf=1&web=1&e=jLuftl | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-15 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-22 | 2024-08-05 | 2024-08-05 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-16 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | [15 empty] | 2024-10-01 | 2024-10-01 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-06-11 | N | 100% | 2025-05-22 | Not Applicable | R3 Build & UT Sprint 14 | 2024-10-04 | 2024-10-04 | 2024-10-04 | pgaroo@deloitte.com | 2024-05-23 23:15 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 0259 | INT-CR0288 | R3 ITC1 | [6 empty] | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 | 2024-10-01 | [12 empty] | 2024-10-01 | 2024-10-01 |  |  | 2025-05-22 | 2025-06-11 | 2025-05-22 | [5 empty] | 2024-08-02 | 2024-10-04 |  |  | 2025-03-21 |  |  |  | 0 |  | 1592 | [10 empty] | 2024-10-04 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-04 | 2024-10-01 | No | Changes on custom will be tested with interfaces | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 625 | PTPE0259_IF | 04.Enhancement | 02.IF - Intel Foundry | Develop a routing logic to send Purchase Order to the Boundary apps from S/4 HANA System (IF) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/625_PM-080-060_0002_PTP_Routing%20Logic%20to%20Transmit%20Order%20to%20Supplier_v1.0_IF.pptx?d=w82ea746ae64446d68b84f4776601faf9&csf=1&web=1&e=mTDxMK | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-15 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-22 | 2024-08-12 | 2024-08-12 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-16 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | [15 empty] | 2024-10-01 | 2024-10-01 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-06-11 | N | 100% | 2025-05-22 | Not Applicable | R3 Build & UT Sprint 14 | 2024-10-04 | 2024-10-04 | 2024-10-04 | pgaroo@deloitte.com | 2024-05-23 23:15 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPE0259_IP | 03.Medium | 0.2 | 0.2 | 0259 | INT-CR0288 | R3 ITC1 | [6 empty] | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 | 2024-10-01 | [12 empty] | 2024-10-01 | 2024-10-01 |  |  | 2025-05-22 | 2025-06-11 | 2025-05-22 | [5 empty] | 2024-08-09 | 2024-10-04 |  |  | 2025-03-21 |  | WIINGS |  | 0 |  | 1594 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2024-10-04 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-04 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 606 | PTPE0241_IP | 04.Enhancement | 01.IP - Intel Product | Payment Term Mass change functionality in FBL1N Vendor Line item report | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/606-PM-150-170-0001-PTP-IP-Payment%20Term%20Mass%20Change.pptx?d=wd0ce35a00c4b4300bae32d943b27eec8&csf=1&web=1&e=AQPbY2 | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-23 | 2024-09-23 | 2024-09-23 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-21 | 2024-10-07 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-21 | [15 empty] | 2024-11-21 | 2024-11-21 |  |  | 2024-09-13 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2024-09-13 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-05-21 03:17 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0241 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-21 | 2024-11-22 | 2024-11-21 | 2024-11-21 | [12 empty] | 2024-11-21 | 2024-11-21 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2024-08-02 | 2024-11-22 |  |  | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 2305 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/25 11/25: Recieved approval from Andrea, Intel IT. Waiting for approval from Jorge. 11/18 FUT initiated for S20. FUT completion by 12/03 11/11 - Dependent object is ready. FUT to being in S20. 11/4: This object is dependent upon development of PTPE1606_IP & IF. Dev of PTPE1606_IP & IF is planned in Sprint 20.10/10: Dependent upon PTPE1606_IP and IF. Dev of PTPE1606 is planned in Sprint 19. 9/29: Awaiting approval for PTPE1606_IP & IF and this object FUT is dependent upon development of PTPE1606_IP & IF. 9/19: PTPE1606_IP & IF [Dependent Object] FSD is drafted and shared with business for approval. 9/10: PTPE0241 is dependent on the PTPE1606 development, PTPE1606 is planned for FSD draft on Sprint 18. 9/01: FUT is in progress ETA: 9/15 8/25: CR 1038 is in progress. 8/11 - Josh confirmed to develop this in FBL1H report, Need to work on CR to adding the development in FBL1H report as well 8/4 - Team completed FUT and reviewed with business. But business raised some design change and EP team completed POC on design change and prepared one RICEFW for supporting this enhancement. | 2024-11-22 | N | 06. PTP |  |  |  | Submitted for approval | Defect 4615 ETA 1205 | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 8 |  | 2024-11-22 | 2024-11-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 606 | PTPE0241_IF | 04.Enhancement | 02.IF - Intel Foundry | Payment Term Mass change functionality in FBL1N Vendor Line item report | 06. PTP | 6.7 PTP - Enable Payments | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/607-PM-150-170-0002-PTP-IF-Payment%20Term%20Mass%20Change.pptx?d=w9f23d8c45d3a413b841d216c9fa24124&csf=1&web=1&e=3kiszG | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-23 | 2024-09-23 | 2024-09-23 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-21 | 2024-10-07 | 2024-11-22 | 2024-11-22 | 100% | 2024-11-21 | [15 empty] | 2024-11-21 | 2024-11-21 |  |  | 2024-09-13 | 2024-09-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2024-09-13 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-05-21 03:17 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | PTPE0241_IP | 03.Medium | 0.2 | 0.2 | 0241 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-21 | 2024-11-22 | 2024-11-21 | 2024-11-21 | [12 empty] | 2024-11-21 | 2024-11-21 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2024-08-02 | 2024-11-22 |  |  | 2024-09-13 |  |  |  | 0 | 08. Not Applicable | 2304 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/25 11/25: Recieved approval from Andrea, Intel IT. Waiting for approval from Jorge. 11/18 FUT initiated for S20. FUT completion by 12/03 11/11 - Dependent object is ready. FUT to being in S20. 11/4: This object is dependent upon development of PTPE1606_IP & IF. Dev of PTPE1606_IP & IF is planned in Sprint 20.10/10: Dependent upon PTPE1606_IP and IF. Dev of PTPE1606 is planned in Sprint 19. 9/29: Awaiting approval for PTPE1606_IP & IF and this object FUT is dependent upon development of PTPE1606_IP & IF. 9/19: PTPE1606_IP & IF [Dependent Object] FSD is drafted and shared with business for approval. 9/10: PTPE0241 is dependent on the PTPE1606 development, PTPE1606 is planned for FSD draft on Sprint 18. 9/01: FUT is in progress ETA: 9/15 8/25: CR 1038 is in progress. 8/11 - Josh confirmed to develop this in FBL1H report, Need to work on CR to adding the development in FBL1H report as well 8/4 - Team completed FUT and reviewed with business. But business raised some design change and EP team completed POC on design change and prepared one RICEFW for supporting this enhancement. | 2024-11-22 | N | 06. PTP |  |  |  | Submitted for approval | Defect 4615 ETA 1205 | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 8 |  | 2024-11-22 | 2024-11-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 333 | PTPE0202_IP | 04.Enhancement | 01.IP - Intel Product | Develop a change utility for mass PR creation and change of purchase requisitions – IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/333_PM-070-050_0002_PTP_RICEFW%20Intake%20Form_v1.0_IP.pptx?d=w9917044df8134e5c9fce3574c133310b&csf=1&web=1&e=aQKKTO | 02.No | 01.Yes |  | 2024-05-14 | Cari H Shim | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-08-23 | 2024-12-20 | 2024-10-17 | 100% | 2025-01-10 | 2025-04-04 | 2025-04-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-07-04 | 2025-07-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-07-15 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-13 23:48 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 2 | 2 | 0202 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-05-07 |  |  |  | 0 | 08. Not Applicable | 2083 | [9 empty] | 8/11 - New Defects found working with tech 8/4 FUT Delayed. Defects to be Fixed by Tech Team. | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Custom table changes | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 332 | PTPE0202_IF | 04.Enhancement | 02.IF - Intel Foundry | Develop a change utility for mass PR creation and change of purchase requisitions – IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/332_PM-070-050_0001_PTP_RICEFW%20Intake%20Form_v1.0_IF.pptx?d=w0d90d995324f4d06891246225409fdae&csf=1&web=1&e=obBfFl | 02.No | 01.Yes |  | 2024-05-14 | Cari H Shim | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-08-22 | 2024-12-20 | 2024-10-17 | 100% | 2025-01-10 | 2025-04-04 | 2025-04-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-07-04 | 2025-07-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-07-15 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-13 23:48 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPE0202_IP | 02.High | 0.4 | 0.4 | 0202 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-05-07 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 2082 | [9 empty] | 8/11 - New Defects found working with tech 8/4 FUT Delayed. Defects to be Fixed by Tech Team. | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 501 | PTPE0200_IP | 04.Enhancement | 01.IP - Intel Product | PO Mass Change - Upload Tool Functionality (IP) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/501_PM-080-100-0002_PTP_IP_PO%20Mass%20Change%20Upload%20Tool.pptx?d=we23bc81833504b0eb3c63bb2de29f868&csf=1&web=1&e=Z7UCZ0 | 02.No | 01.Yes |  | 2024-05-14 | Cari H Shim | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-07-26 | 2024-12-20 | 2024-12-11 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-03-26 | 2025-05-02 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-07 | 2025-05-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-05-14 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-13 23:48 | cell-link@smartsheet.com | 2026-03-10 08:49 | 10 |  | 01.S4 |  |  | 2 | 2 | 0200 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2391 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 25/7 - Sent reminder to Jose to mark as 100% | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Plant changes need to be retested as Plant is main component | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 500 | PTPE0200_IF | 04.Enhancement | 02.IF - Intel Foundry | PO Mass Change - Upload Tool Functionality (IF) | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/500_PM-080-100-0001_PTP_IF_PO%20Mass%20Change%20Upload%20Tool.pptx?d=we5da9d67565f49ffa72c02dbe8d480f0&csf=1&web=1&e=dqvIh8 | 02.No | 01.Yes |  | 2024-05-14 | Cari H Shim | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-25 | 2024-12-20 | 2024-12-11 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-03-26 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-05-07 | 2025-05-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-05-14 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-13 23:48 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPE0200_IP | 02.High | 0.4 | 0.4 | 0200 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-26 | 2025-04-11 | 2025-03-26 |  | 2025-04-10 | 2025-05-16 | [14 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-04-18 |  | WIINGS |  | 0 | 08. Not Applicable | 2390 | [7 empty] | 1. On Track | 9. Blocked by B-App Readiness | 25/7 - Sent reminder to Jose to mark as 100% | 2025-05-16 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 328 | PTPE0090_IP | 04.Enhancement | 01.IP - Intel Product | Attachment need to copy from PR to PO automatically | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/328_PM-070-080-0002_Attachment%20need%20to%20copy%20from%20PR%20to%20PO%20automatically.pdf?csf=1&web=1&e=Mj5VWa | 02.No | 01.Yes |  | 2024-04-19 | Cari H Shim | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-05-27 | 2024-05-27 | 2024-05-30 | 100% | 2024-05-30 | 2024-05-31 | 2024-06-19 | 2024-06-19 | 100% | 2024-06-21 | 2024-05-31 | 2024-06-19 | 2024-06-19 | 100% | 2024-06-21 | [15 empty] | 2024-06-21 | 2024-06-21 |  |  | 2024-07-05 | 2024-07-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-06-24 | 2024-07-12 | 2024-07-12 | N | 100% | 2024-07-12 | Not Applicable | R3 Build & UT Sprint 3 | 2024-06-19 | 2024-06-19 | 2024-06-19 | jenoronha@deloitte.com | 2024-04-19 09:02 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0090 |  | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-05-30 | 2024-05-30 |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 | [12 empty] | 2024-06-21 | 2024-06-21 |  |  | 2024-07-12 | 2024-07-12 | [6 empty] | 2024-05-24 | 2024-06-19 |  |  | 2024-07-12 |  |  |  | 0 | 08. Not Applicable | 2092 | [10 empty] | 2024-06-19 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 2 |  | 2024-06-21 | 2024-06-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 327 | PTPE0090_IF | 04.Enhancement | 02.IF - Intel Foundry | Attachment need to copy from PR to PO automatically | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/327_PM-070-080-0001_Attachment%20need%20to%20copy%20from%20PR%20to%20PO%20automatically.pdf?csf=1&web=1&e=fuzIom | 02.No | 01.Yes |  | 2024-04-19 | Cari H Shim | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-04-29 | 2024-05-24 | 2024-05-24 | 100% | 2024-05-23 | 2024-05-27 | 2024-05-27 | 2024-05-31 | 100% | 2024-05-31 | 2024-06-03 | 2024-07-12 | 2024-07-12 | 100% | 2024-06-28 | 2024-06-03 | 2024-07-12 | 2024-07-12 | 100% | 2024-06-28 | [15 empty] | 2024-06-28 | 2024-06-28 |  |  | 2024-08-09 | 2024-08-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-05 | 2024-08-16 | 2024-08-16 | N | 100% | 2024-08-13 | Not Applicable | R3 Build & UT Sprint 4 | 2024-07-12 | 2024-07-12 | 2024-07-12 | jenoronha@deloitte.com | 2024-04-19 09:02 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | PTPE0090_IP | 03.Medium | 0.2 | 0.2 | 0090 |  | R3 ITC1 | [6 empty] | 2024-05-23 | 2024-05-24 | 2024-05-23 |  | 2024-05-31 | 2024-05-31 |  |  | 2024-06-28 | 2024-07-12 | 2024-06-28 | 2024-06-28 | [12 empty] | 2024-06-28 | 2024-06-28 |  |  | 2024-08-13 | 2024-08-16 | 2024-08-13 | [5 empty] | 2024-05-24 | 2024-07-12 |  |  | 2024-08-16 |  |  |  | 0 | 08. Not Applicable | 2091 | [10 empty] | 2024-07-12 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 3 |  | 2024-07-12 | 2024-06-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2379 | PTPC0808_IP | 03.Conversion | 01.IP - Intel Product | 2379_Master Data Migration from ECC to S/4 to bring Approved Manufacturer Part List - APML applicable for Procurement Process. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B451831BE-2462-4094-887A-D9C8088738B1%7D&file=2379_PTP_Data%20Conversion%20from%20ECC%20to%20S4%20for%20APML.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | 4092; 11140 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED) |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-07 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-03 | 2025-03-07 | 2025-07-29 | 100% | 2025-07-24 | 2025-09-22 | 2025-10-10 | 2025-08-08 | 100% | 2025-08-08 | [15 empty] | 2025-08-08 | 2025-08-08 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-26 | Not Applicable | R3 Build & UT Sprint 17 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0808 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-24 | 2025-07-29 | 2025-07-24 | 2025-08-08 | [12 empty] | 2025-08-08 | 2025-08-08 |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | [5 empty] | 2025-02-21 | 2025-03-07 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1861 | [9 empty] | 8/25 - Approved asked Jose to mark 8/18- Scheduled to be sent tomorrow | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-08 | No |  | No |  | No | Regression Testing |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2379 | PTPC0808_IF | 03.Conversion | 02.IF - Intel Foundry | 2379_Master Data Migration from ECC to S/4 to bring Approved Manufacturer Part List - APML applicable for Procurement Process. | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B451831BE-2462-4094-887A-D9C8088738B1%7D&file=2379_PTP_Data%20Conversion%20from%20ECC%20to%20S4%20for%20APML.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No | 4092; 11140 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED) |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-20 | 100% | 2025-02-07 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-03 | 2025-03-07 | 2025-07-29 | 100% | 2025-07-24 | 2025-09-22 | 2025-10-10 | 2025-08-08 | 100% | 2025-08-08 | [15 empty] | 2025-08-08 | 2025-08-08 | Yes |  | 2025-08-05 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-26 | Not Applicable | R3 Build & UT Sprint 17 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-13 | 01.S4 | PTPC0808_IP | 03.Medium | 0.3 | 0.435 | 0808 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-24 | 2025-07-29 | 2025-07-24 | 2025-08-08 | [12 empty] | 2025-08-08 | 2025-08-08 |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | [5 empty] | 2025-02-21 | 2025-03-07 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1860 | [9 empty] | 8/25 - Approved asked Jose to mark 8/18- Scheduled to be sent tomorrow | 2025-10-10 | Y | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2069 | PTPC0633 | 03.Conversion | 02.IF - Intel Foundry | Purchase Requisition Conversion from ECC to S/4 - IF | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8D4C6E05-0AD5-444D-9CDF-F39C461DF5AF%7D&file=XXXX_PTP_Conversion%20Open%20Purchase%20Requisitions%20to%20S4_IF%20and%20IP.pptx&wdLOR=cAEECE2B7-7357-4B21-909A-2CF1A9720EF7&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-13 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-02-24 | 2025-02-24 | 2025-03-28 | 100% | 2025-03-28 | 2025-03-03 | 2025-04-18 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-03 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-18 | 01.S4 |  |  | 2 | 2.9 | 0633 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-06-13 | 2025-06-11 | [5 empty] | 2024-10-17 | 2025-04-18 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2512 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-04-18 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1860 | PTPC0537_IP | 03.Conversion | 01.IP - Intel Product | Purchasing Info Records Migration from ECC to S/4 – IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1860_PTP_Conversion%20PIR%20to%20S4_IF%20and%20IP.pptx?d=w13a42c654b6242399a73e2f2d1820d91&csf=1&web=1&e=eWVCcH | 02.No | 01.Yes |  | 2024-07-31 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-09-09 | 2024-09-20 | 2025-08-22 | 100% | 2025-08-21 | 2024-10-21 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | [15 empty] | 2025-01-24 | 2025-01-24 | Yes |  | 2025-02-14 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-13 | 2025-02-20 | N | 100% | 2025-02-20 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-07-30 06:31 | cell-link@smartsheet.com | 2026-03-16 07:27 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1.45 | 0537 | INT-CR0365 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-01-24 | [12 empty] | 2025-01-24 | 2025-01-24 |  |  | 2025-02-20 | 2025-03-13 | [6 empty] | 2024-09-20 | 2024-09-20 |  |  | 2025-03-13 |  |  |  | 0 | 08. Not Applicable | 2175 | [10 empty] | 2025-01-24 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-24 | Yes | Conversion main component is plant needs to be retested | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1860 | PTPC0537_IF | 03.Conversion | 02.IF - Intel Foundry | Purchasing Info Records Migration from ECC to S/4 – IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1860_PTP_Conversion%20PIR%20to%20S4_IF%20and%20IP.pptx?d=w13a42c654b6242399a73e2f2d1820d91&csf=1&web=1&e=eWVCcH | 02.No | 01.Yes |  | 2024-07-31 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-09-09 | 2024-09-13 | 2025-08-22 | 100% | 2025-08-21 | 2024-10-21 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | [15 empty] | 2025-01-24 | 2025-01-24 | Yes |  | 2025-02-14 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-13 | 2025-02-20 | N | 100% | 2025-02-20 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-07-30 06:31 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-08-12 | 01.S4 | PTPC0537_IP | 03.Medium | 0.3 | 0.435 | 0537 | INT-CR0365 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-01-24 | [12 empty] | 2025-01-24 | 2025-01-24 |  |  | 2025-02-20 | 2025-03-13 | [6 empty] | 2024-09-20 | 2024-09-13 |  |  | 2025-03-13 |  | WIINGS |  | 0 | 08. Not Applicable | 2174 | [10 empty] | 2025-01-24 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 1859 | PTPC0536_IP | 03.Conversion | 01.IP - Intel Product | Source List Migration from ECC to S/4 – IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1859_PTP_Conversion%20Source%20List%20to%20S4_IF%20and%20IP.pptx?d=w2b13b75b88dc4f1b9dcb1862943d1a77&csf=1&web=1&e=Hp4rnI | 02.No | 01.Yes |  | 2024-07-31 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-09-09 | 2024-09-13 | 2025-08-22 | 100% | 2025-08-21 | 2024-10-21 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-22 | [15 empty] | 2025-01-22 | 2025-01-22 |  |  | 2025-12-24 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-13 | 2025-02-20 | N | 100% | 2025-02-20 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-07-30 06:33 | cell-link@smartsheet.com | 2026-03-10 08:58 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1.45 | 0536 | INT-CR0413 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-01-22 | [12 empty] | 2025-01-22 | 2025-01-22 |  |  | 2025-02-20 | 2025-03-13 | [6 empty] | 2024-09-20 | 2024-09-13 |  |  | 2025-03-13 |  |  |  | 0 | 08. Not Applicable | 2173 | [7 empty] | 4. Completed |  |  | 2025-01-24 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-22 | Yes | Conversion main component is plant needs to be retested | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1859 | PTPC0536_IF | 03.Conversion | 02.IF - Intel Foundry | Source List Migration from ECC to S/4 – IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1859_PTP_Conversion%20Source%20List%20to%20S4_IF%20and%20IP.pptx?d=w2b13b75b88dc4f1b9dcb1862943d1a77&csf=1&web=1&e=Hp4rnI | 02.No | 01.Yes |  | 2024-07-31 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-09-09 | 2024-09-20 | 2025-08-22 | 100% | 2025-08-21 | 2024-10-21 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-22 | [15 empty] | 2025-01-22 | 2025-01-22 |  |  | 2025-12-24 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-13 | 2025-02-20 | N | 100% | 2025-02-20 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-07-30 06:33 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-08-12 | 01.S4 | PTPC0536_IP | 03.Medium | 0.3 | 0.435 | 0536 | INT-CR0413 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-01-22 | [12 empty] | 2025-01-22 | 2025-01-22 |  |  | 2025-02-20 | 2025-03-13 | [6 empty] | 2024-09-20 | 2024-09-20 |  |  | 2025-03-13 |  | WIINGS |  | 0 | 08. Not Applicable | 2172 | [7 empty] | 4. Completed |  |  | 2025-01-24 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 1883 | PTPC0509_IP | 03.Conversion | 01.IP - Intel Product | Open Contracts Migration from ECC to S/4 - IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1883_PTP_Conversion%20Open%20Contracts%20to%20S4_IF%20and%20IP.pptx?d=w2ec00e6b47bc4f00a41bf9d94d5f3d4b&csf=1&web=1&e=zmOB9c | 02.No | 01.Yes |  | 2024-08-08 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-21 | 2024-11-25 | 2024-11-04 | 100% | 2024-11-26 | 2024-12-16 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-11 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-11 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2024-08-12 | 01.S4 |  |  | 4 | 5.8 | 0509 | INT-CR0367 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-10-17 | 2024-11-25 |  |  | 2025-04-29 |  |  |  | 0 | 08. Not Applicable | 1695 | [7 empty] | 1. On Track | 3. Awaiting Approval | 8/11- checking internally on some design items and working with BODS 8/4 Awaiting Sean's approval. Feedbacks from Sean are incorporated | 2025-03-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Conversion main component is plant needs to be retested | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1883 | PTPC0509_IF | 03.Conversion | 02.IF - Intel Foundry | Open Contracts Migration from ECC to S/4 - IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1883_PTP_Conversion%20Open%20Contracts%20to%20S4_IF%20and%20IP.pptx?d=w2ec00e6b47bc4f00a41bf9d94d5f3d4b&csf=1&web=1&e=zmOB9c | 02.No | 01.Yes |  | 2024-08-08 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2024-09-20 | 2024-10-17 | 2024-10-17 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-21 | 2024-11-25 | 2025-08-22 | 100% | 2025-08-21 | 2024-12-16 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-11 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-11 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-08-12 | 01.S4 | PTPC0509_IP | 01.Very High | 1.2 | 1.74 | 0509 | INT-CR0367 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-08-22 | 2025-08-21 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-10-17 | 2024-11-25 |  |  | 2025-04-29 |  |  |  | 0 | 08. Not Applicable | 1694 | [7 empty] | 1. On Track | 3. Awaiting Approval | 8/4 - Approval Awaited from Sean Wilson (Intel). Feedbacks Incorporated. | 2025-03-21 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1907 | PTPC0504_IP | 03.Conversion | 01.IP - Intel Product | Quota Arrangement Migration from ECC to S/4 - IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/11. Technology/RICEFW/10 RICEFW Inbox/1907_PTP_Conversion Quota Arrangement_IF and IP.pptx?d=w44da7b4171fe45f5a2b3743c8a7f5a59&csf=1&web=1&e=bc4lkk | 02.No | 01.Yes |  | 2024-08-02 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-04 | 2024-11-04 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-11 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-03 | 2024-11-25 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 | Yes |  | 2025-02-14 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-02-20 | N | 100% | 2025-03-03 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-31 | 2025-01-31 | 2025-01-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1.45 | 0504 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-03-03 | 2025-03-21 | 2025-03-03 | [5 empty] | 2024-09-20 | 2024-10-04 |  |  | 2025-04-29 |  |  |  | 0 | 08. Not Applicable | 1706 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-01-31 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-30 | No |  | No |  | No | Regression Testing |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1907 | PTPC0504_IF | 03.Conversion | 02.IF - Intel Foundry | Quota Arrangement Migration from ECC to S/4 - IF and IP | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/11. Technology/RICEFW/10 RICEFW Inbox/1907_PTP_Conversion Quota Arrangement_IF and IP.pptx?d=w44da7b4171fe45f5a2b3743c8a7f5a59&csf=1&web=1&e=bc4lkk | 02.No | 01.Yes |  | 2024-08-02 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-04 | 2024-11-04 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-11 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-03 | 2024-11-25 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-29 | [15 empty] | 2025-01-29 | 2025-01-29 | Yes |  | 2025-02-14 | 2025-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-02-20 | N | 100% | 2025-03-03 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-31 | 2025-01-31 | 2025-01-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-08-12 | 01.S4 | PTPC0504_IP | 03.Medium | 0.3 | 0.435 | 0504 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2025-01-29 | [12 empty] | 2025-01-29 | 2025-01-29 |  |  | 2025-03-03 | 2025-03-21 | 2025-03-03 | [5 empty] | 2024-09-20 | 2024-10-04 |  |  | 2025-04-29 |  |  |  | 0 | 08. Not Applicable | 1705 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-01-31 | N | 06. PTP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 331 | PTPC0176_IP | 03.Conversion | 01.IP - Intel Product | Open PO conversion from Legacy to SAP S/4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/331_PM-080-050-0002_PTP_Open%20PO%20conversion%20from%20Legacy%20to%20SAP%20S4.pptx?d=w9ad20ea018da48949eb2c5b390eaaaee&csf=1&web=1&e=6daWFP | 02.No | 01.Yes |  | 2024-05-01 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | ECC | ECC | S4 | NA | 2024-08-19 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-15 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-18 | 2024-11-22 | 2024-11-29 | 100% | 2024-12-05 | 2024-12-16 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-07-11 | 2025-08-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-08-08 | 2025-08-08 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-04-30 03:30 | cell-link@smartsheet.com | 2026-03-12 22:32 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0176 |  | R3 ITC1 | [6 empty] | 2024-11-15 | 2024-11-15 | 2024-11-15 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2024-09-20 | 2024-11-22 |  |  | 2025-03-07 |  | Federal |  | 0 | 01. Supplier - All | 2094 | [7 empty] | 1. On Track | 1. Approved no action | 9/10 Awaiting approval from Jorge for Ichem Ariba POs. Multiple Reminders shared 9/5 - Awaiting approval from 1 comodity 9/1 - Sent for approval ETA next week 8/25 - Sent for approval 8/18 - It is send for approval in pieces and is in progress ETC- Sprint 17 8/11- This is a big Conversion with lot of defects/CR will be spilled to next sprint, we are trying to cover in phases. 25/7 - This is scheduled for sprint 16 approval. Presently, FUT in Progress and team is working on it. | 2025-03-21 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Plant changes will impact this main component for conversion | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-24 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 331 | PTPC0176_IF | 03.Conversion | 02.IF - Intel Foundry | Open PO conversion from Legacy to SAP S/4 | 06. PTP | 6.2 PTP - Procurement | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/330_PM-080-050-0001_PTP_Open%20PO%20conversion%20from%20Legacy%20to%20SAP%20S4.pptx?d=wf8c1d2293feb4344badde1bb49297fb5&csf=1&web=1&e=iZjVPs | 02.No | 01.Yes |  | 2024-05-01 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | ECC | ECC | S4 | NA | 2024-08-19 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-15 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-18 | 2024-11-22 | 2024-11-29 | 100% | 2024-12-05 | 2024-12-16 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-11 | 2025-08-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-08-08 | 2025-08-08 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-04-30 03:30 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | PTPC0176_IP | 02.High | 0.6 | 0.87 | 0176 |  | R3 ITC1 | [6 empty] | 2024-11-15 | 2024-11-15 | 2024-11-15 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-12-05 | 2024-12-05 | 2024-12-05 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2024-09-20 | 2024-11-22 |  |  | 2025-03-07 |  | WIINGS |  | 0 | 01. Supplier - All | 2093 |  |  | WIINGS |  |  |  |  | 1. On Track | 1. Approved no action | 9/10 Awaiting approval from Jorge for Ichem Ariba POs. Multiple Reminders shared 9/5 - Awaiting approval from 1 comodity 9/1 - Sent for approval ETA next week 8/25 - Sent for approval 8/18 - It is send for approval in pieces and is in progress ETC- Sprint 17 8/11- This is a big Conversion with lot of defects/CR will be spilled to next sprint, we are trying to cover in phases. 25/7 - This is scheduled for sprint 16 approval. Presently, FUT in Progress and team is working on it. | 2025-03-21 | N | 06. PTP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 3153 | OTCW1683 | 06.Workflow | 01.IP - Intel Product | Additional WRICEF for Credit Limit Request Workflow | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC78D9157-F820-43B1-A8EE-E7C95DBAE8E6%7D&file=INT-CR1065%20for%20CLR%20-%20Additional%20RICEFW%20for%20Credit%20Limit%20Request%20workflow.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Canntam%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA5MTExNjAxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2025-12-12 | 2025-12-12 | 100% | 2025-12-15 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-05 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-02-05 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-02-05 | [15 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-26 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-07 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-11-04 04:16 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 1.05 | 1683 | INT-CR1065 | R3 ITC1 | [6 empty] | 2025-12-15 | 2025-12-15 | 2025-12-15 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-05 | [12 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | [5 empty] | 2025-12-12 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3356 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/24:Sent for intel approval 2/19: Defect 7126 fixed (Email functionality) and re-testing is in progress. ETA - 2/20 to send for approval 2/17: Defect 7126 fixed and re-testing is in progress 2/12:defect 7126 needs to fix (2 email issues) 2/9:defect 7126 needs to fix (2 email issues) 1/14 : Build in progress.Approval task is in sprint 23. FUT execution comes under sprint 22 from Mid of S22 12/16 : FUT is planned in Sprint 22.Incorrect plan | 2026-01-09 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-05 | 2026-02-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2066 | OTCW0638 | 06.Workflow | 05.CFIN | Dispute Write-off Workflow | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2066_OTC_RICEFW_Dispute%20Write-off%20Workflow.pptx?d=wf80c2013c54b44d992667baa693f3c80&csf=1&web=1&e=ukg9Ht | 02.No | 01.Yes |  | 2024-09-11 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-08-08 | 100% | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-28 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 03:49 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-17 | 01.S4 |  |  | 1 | 1.05 | 0638 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 2506 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 1/8: 2 defect :5241 and 5998 need to fix by Tech team 1/6:5988 , 5982,5241 Defect fixes ETA 1/7 EOD 01/05: defect 5971, 5972 . 5241 to be fixed.. 12/23: Defect 4718 to be fixed by Tech team., 5881 fixed and ready for re-testing. 12/18: Object Sent for approval. Waiting for the feedback 12/16: Object Sent for approval. Waiting for the feedback 12/11:Defects fixed -REOPENed. Minor issues open. Expected to be fixed 12/12 first half. Target to send to approval by 12/12 12/9:Defects 4718,5241 addressed -Retest in progress .5127 reopened to be fixed 12/8:Defect 4718 reopened .ETA 12/9 12/4: 5127 - ABAP dump in Fiori - Manage dispute case app upon validation check. 4718:For the 'waiting your approval' email is being sent only to the new processor, it should aslo have last change user, coordinator, and any previous processor in 'CC'. 12/3:defect 4718,5126 fixed. 5127 in progress ETA 12/3 EOD 12/2:Defects 5126, 5127 - Yet to be picked by Tech team .ETA to pick 12/3 11/28:Defect 4718 in progress. ETA 11/28 EOD 11/25: Defect 4718 still open . ETA Revised to 11/26 11/21 : Defect 4718,4783 ETA 11/21 | 2025-11-05 | N | 04. OTC IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2568 | OTCR0967 | 01.Report | 01.IP - Intel Product | Developing a report for the 2DN model where we can view the E2E flow in one report. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2568_IP_%20Developing%20a%20report%20for%20the%202DN%20model%20where%20we%20can%20view%20the%20E2E%20flow%20in%20one%20report.pptx?d=w7054260467ec44cd93f183b8c1969144&csf=1&web=1&e=Ra6Aiv | 02.No | 01.Yes |  | 2024-12-02 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-08-18 | 2025-09-12 | 2025-09-19 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-11-26 00:26 | cell-link@smartsheet.com | 2026-03-17 21:08 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 0.85 | 0967 |  | R3 ITC1 | [6 empty] | 2025-08-18 | 2025-08-18 | 2025-08-18 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-05-23 | 2025-07-18 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2624 | [7 empty] | 1. On Track | 1. Approved no action | 2/24;Awaiting Intel approval 2/19:Object sent for approval.Review and Approval is in progress by Intel Team 2/17:Working with MX Fiori tech team on Options. USI Tech have shared the analysis already Defect 7261 2/12: FUT sent for approval 2/5: Defect 6960 ETA 2/6 Action on Tech Team (Mani) Defect 6765 Sorting issue Action on Fiori team ETA 2/6 2/3: 6765 defect needs to fix. Tech team need Fiori support to fix. 1/29: FUT Sent for approval 1/27: New defect 6598 - to be fixed. Developer was OOO on 1/27 and this will be picked only on 1/28 1/22:Defect fix under retest 1/20:Defect 6450 under fix. ETA 1/22 1/14: defect 6225 to be fixed by MX Tech team. regular call setup with MX tech team for the fix 1/8: ,MX team support required to fix a defect 5351 1/6:Defect 5351 under retest 01/05: Defect 5351 .ETA 06/01 12/23: Defect 5351 - MX Team working on ETA 12/23 12/11: Defect 5351 - MX Team working on ETA TBD 12/9:Defect 5351 In progress .ETA 12/10 12/8:Defect 5351 .ETA 12/9 EOD 12/4:Defect 4861 issues are only partially fixed. Still with tech team 12/2:Defect 4861 issues are only partially fixed. Still with tech team ,ETA 12/3 11/28:Defect 4861 Fix in progress 11/25: Defect 4861 in progress 11/21:FUT Defect under retest.ETA For FUT Completion 11/28 11/17: Defect 4495 | 2025-12-05 | N | 05. OTC IP |  |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | Yes | Custom Table entries to be updates as Sales Area and Customer are fetched based on the CW (LE102) plant​ | No |  | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 |  | OTCM028_IP | 12.Manual Conversion | 01.IP - Intel Product | Open Quantity Contract | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | ECC | S4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-11 | 100% | 2025-08-20 | 2024-12-02 | 2024-12-02 |  | 0% | 2024-12-02 |  |  |  | 0% |  | 2025-01-27 | 2025-02-21 |  | 0% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-01-27 | 2025-02-21 | 2025-02-28 | N | 100% | 2025-04-04 | Not Applicable | R3 Build & UT Sprint 12 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 028_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2024-12-02 | [22 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 | [5 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2199 | [10 empty] | 2025-02-21 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3198 | OTCI1721 | 02.Interface | 02.IF - Intel Foundry | Outbound Interface changes to send data from S4 to SF | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEB849E4D-BD4C-4B7A-94B7-09ED2BB17307%7D&file=INT-CR1617%20-%20Outbound%20Interface%20changes%20to%20send%20data%20from%20S4%20to%20SF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Jill Matalon | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 01.Yes | 36446 | Return For Credit |  |  | MULESOFT | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-17 | 2026-02-18 | 2026-02-25 | 100% | 2026-02-25 | 2026-02-19 | 2026-02-24 | 2026-03-04 | 100% | 2026-03-09 | 2026-01-29 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-09 | 2026-03-31 |  | 2026-02-20 | 2026-03-25 | 2026-03-25 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-25 | N | 100% | 2026-03-19 |  | R3 Build & UT Sprint 23+ | 2026-02-24 | 2026-03-31 | 2026-03-31 | jenoronha@deloitte.com | 2026-01-27 09:47 | cell-link@smartsheet.com | 2026-04-01 02:17 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1721 | INT-CR1617 | R3 ITC1 | [6 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-02 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | 2026-03-19 | 2026-03-25 | 2026-03-19 |  |  |  |  | Return for Credit | 2026-02-06 | 2026-02-20 | 2026-02-18 |  | 2026-03-04 |  |  |  | 0 |  | 3421 | [7 empty] | 3. Off Track | 17. FUT In progress | 3/13: Awaiting for Intel walktrhough+BAPP Testing 3/11:TM Scenarios completed -OTC FUT In progress 3/6: Collaborative test with TM in progress 7962,8026 Defects worked upon by TM 2/27- FUT started from 2/27 . FUT In progress 2/19: Awaiting Development completion. Tech team shared ETA - 2/24 2/10: Awaiting Development completion | 2026-03-31 | Y | 05. OTC IP |  |  |  | 03/11: FUT in progress. ETA is 03/20 Current status: FUT in progress. ETA is 03/20 Issue: FUT delayed Next steps: Expedite FUT completion. Help needed: N/A FUT ETA: 03/20 |  | 3. Watch item | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-02 | 2026-03-09 | No |  | No |  | No |  |  |  | Yes |  | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 3197 | OTCI1720 | 02.Interface | 01.IP - Intel Product | Inbound Interface to Update Original Flag Interface from SFDC to S4. | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC84EB217-32E5-4308-A252-0BA64BB5901A%7D&file=INT-CR1553%20-%20Inbound%20Interface%20to%20Update%20Original%20Flag%20Interface%20from%20SFDC%20to%20S4.pptx&wdLOR=cA94CF074-E33D-4DA9-AAA6-D4E3AB0F711D&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 01.Yes | 36446 | Return For Credit |  |  | MULESOFT | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-12 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 100% | 2026-02-18 | 2026-02-19 | 2026-02-24 | 2026-02-24 | 100% | 2026-03-09 | 2026-01-29 | 2026-03-31 | 2026-03-31 | 100% | 2026-03-31 | 2026-03-09 | 2026-03-31 |  | 2026-02-20 | 2026-03-27 | 2026-03-27 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-20 |  | R3 Build & UT Sprint 23+ | 2026-02-24 | 2026-03-31 | 2026-03-31 | jenoronha@deloitte.com | 2026-01-27 09:47 | cell-link@smartsheet.com | 2026-04-01 02:17 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1720 | INT-CR1553 | R3 ITC1 | [6 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-02 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-09 | 2026-03-31 | 2026-03-09 |  | 2026-03-20 | 2026-03-27 | 2026-03-20 |  |  |  |  | Return for Credit | 2026-02-06 | 2026-02-20 | 2026-02-18 |  | 2026-03-04 |  |  |  | 0 |  | 3420 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 20/3: sent for FUT approval, walkthrough done today. awaiting intel approval 3/13:BAPP testing under progress. Issues at BAPP Side 3/6:Defect 8047 under retest 2/19: Awaiting Development completion. Tech team shared ETA - 2/27 2/10: Awaiting Development completion | 2026-03-31 | Y | 05. OTC IP |  |  |  | 03/11: FUT in progress. ETA is 03/20 Current status: FUT in progress. ETA is 03/20 Issue: FUT delayed Next steps: Expedite FUT completion. Help needed: N/A FUT ETA: 03/20 |  | 3. Watch item | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-02 | 2026-03-09 | No |  | No |  | No |  |  |  | Yes |  | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2952 | OTCI1649 | 02.Interface | 01.IP - Intel Product | Service Interface and Enhancement of the outbound proxy sent to NL brokers - Final Tax Assessment | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1420 | 2025-05-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 02.No | NA | NA |  |  | MULESOFT | 2025-06-30 | 2025-08-04 | 2025-11-05 | 100% | 2025-10-15 | 2025-08-15 | 2025-08-22 | 2025-12-03 | 100% | 2025-12-01 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-01-29 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | [5 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-28 04:11 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-05-29 | 01.S4 |  |  | 2 | 2.9 | 1649 |  | R3 ITC1 | [6 empty] | 2025-10-15 | 2025-11-05 | 2025-10-15 |  | 2025-12-01 | 2025-12-03 | 2025-12-01 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-03 | 2025-12-01 | 2025-12-01 |  |  |  |  | 2026-01-29 | 2026-01-29 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-08-04 | 2025-12-05 | 2025-12-03 |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3314 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 2/27: E2E FUT with external partner is in progress 2/18 - Expeditor B-App Build ETA is 2/20. Post that, E2E FUT will be started | 2025-12-05 | N | 05. OTC IP |  |  |  | 1217: OSS Resolved. Awaiting for Expeditor B-App Readiness. ETA from B-App is 1/9/26 Current Status: TUT in progress Issue: Issue resolved Next Steps: TUT and FUT in progress in parallel Help needed: N/A |  | 5. Review Closed | 1 | BA Readiness | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2952 | OTCI1648 | 02.Interface | 01.IP - Intel Product | Service Interface and Enhancement of the outbound proxy sent to NL brokers - Declaration Notifications | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1420 | 2025-05-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 02.No | NA | NA |  |  | MULESOFT | 2025-06-30 | 2025-08-04 | 2025-11-05 | 100% | 2025-10-15 | 2025-08-15 | 2025-08-22 | 2025-12-03 | 100% | 2025-12-01 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-01-29 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | [5 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-28 04:11 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-05-29 | 01.S4 |  |  | 2 | 2.9 | 1648 |  | R3 ITC1 | [6 empty] | 2025-10-15 | 2025-11-05 | 2025-10-15 |  | 2025-12-01 | 2025-12-03 | 2025-12-01 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-03 | 2025-12-01 | 2025-12-01 |  |  |  |  | 2026-01-29 | 2026-01-29 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-08-04 | 2025-12-05 | 2025-12-03 |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3315 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 2/27: E2E FUT with external partner is in progress 2/18 - Expeditor B-App Build ETA is 2/20. Post that, E2E FUT will be started | 2025-12-05 | N | 05. OTC IP |  |  |  | 1217: OSS Resolved. Awaiting for Expeditor B-App Readiness. ETA from B-App is 1/9/26 Current Status: TUT in progress Issue: Issue resolved Next Steps: TUT and FUT in progress in parallel Help needed: N/A |  | 5. Review Closed | 1 | BA Readiness | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3076 | OTCI1598 | 02.Interface | 01.IP - Intel Product | An outbound Interface to Read the EEPM and DECODER Matrix from S4 to OL | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID%20%233076_OTC%20IP%20%20An%20interface%20to%20Read%20the%20EEPM%20and%20DECODER%20Matrix.pptx?d=wd232fc9dc3dd455b86bd7d8979c6428d&csf=1&web=1&e=yNemcZ | 02.No | 01.Yes |  | 2025-08-13 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 01.Yes | 39609 | Entitlement Orchestration Service |  |  | APIGEE | 2025-08-18 | 2025-09-05 | 2025-09-05 | 100% | 2025-09-19 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-11-06 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-12-31 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-12-31 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-11-10 | 2025-10-27 | 2026-03-06 | 2026-03-06 | 100% | 2026-03-27 | 2025-12-31 | 2026-03-27 |  | 2025-11-14 | 2025-11-26 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-08 | Sprint 22 Week 2 | R3 Build & UT Sprint 21 | 2025-12-03 | 2026-03-06 | 2026-03-06 | jenoronha@deloitte.com | 2025-08-11 01:04 | cell-link@smartsheet.com | 2026-03-27 00:42 | 10 | 2025-08-14 | 01.S4 |  |  | 2 | 2.9 | 1598 | INT-CR0906 | R3 ITC1 | [6 empty] | 2025-09-19 | 2025-09-19 | 2025-09-19 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-03 | 2025-11-10 | 2025-11-10 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2025-12-31 | 2026-03-27 |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 |  |  |  |  | Return for Credit | 2025-09-05 | 2025-10-24 | 2025-11-07 |  | 2025-12-05 |  |  |  | 0 |  | 3248 | [7 empty] | 4. Completed | 1. Approved no action | 1/8: Received approval 1/6:awaiting final approval 01/05: All opens closed. Awaiting final approval 12/23;Awaiting Intel approval 12/18:BAPP Test in progress. S4 Test completed 12/18: defect fixed and re-testing is in progress. defects are fixed and S4 FUT completed Currently integration testing going on. 12/19 - ETA Send for approval 12/16: Defect 5677- ETA - 12/16. Effort estimation : 4 hrs 12/11:Defect 5333 under fix .ETA 12/11 EOD 12/9:Defect 5333, 5311 yet to be fixed. Has to be fixed 12/10 first half 12/8:Defect 5333 fix Under Progress 12/4:Defect fixed and re-testing is in proress 12/2:Defect 4827 open . Authorization and ABAP issues. ETA To solve is 12/2 EOD. 11/28:Blocked with defect 4827 11/25: Defect 4827 - Under fix 11/21:Defect 4529 under fix 11/17:Defect 4529 | 2026-03-06 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | Not Dispositioned | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3034 | OTCI1568 | 02.Interface | 01.IP - Intel Product | Inbound Interface from WOM to S4 HANA to send Shipment and tracking information | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B880AA05A-7E2A-47C7-81FE-B1ECBF96EE2A%7D&file=Console%20ID_3034_shipment%20%20Information%20and%20the%20tracking%20details.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-07-29 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 31717 | SAP Commerce Cloud |  |  | MULESOFT | 2025-08-18 | 2025-08-29 | 2025-08-22 | 100% | 2025-08-19 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-03 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-16 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-11 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-20 | 2025-10-24 | 2025-10-08 | 100% | 2025-10-10 | 2025-10-01 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-31 | 2025-10-11 | 2025-10-31 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-24 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-07-24 03:57 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-08-01 | 01.S4 |  |  | 1 | 1.45 | 1568 | INT-CR0743 | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-29 | 2025-08-19 |  | 2025-09-03 | 2025-09-26 | 2025-09-03 |  | 2025-09-16 | 2025-10-03 | 2025-09-16 | 2025-10-11 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-10-24 | 2025-10-10 | 2025-10-10 |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-11 | 2025-10-31 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2025-08-29 | 2025-09-26 | 2025-10-24 |  | 2025-11-05 |  |  |  | 0 |  | 3197 | [7 empty] | 1. On Track | 1. Approved no action | 12/19:Received approval from Luis 12/18::Awaiting approvals 12/16::Awaiting approvals 12/11:Awaiting approvals 12/9:awaiting approval 12/8:awaiting approval 12/4:Defect 5177 closed. Good to start FUT testing 12/3:defect 5177 12/2:Issues encountered at BAPP Side .Dependency with BAPP for completion of testing 11/28: BAPP Will be ready for testing only by 12/1.Awaiting to start testing with BAPP 11/25:Awaiting BAPP to start the testing. ETA for completion is 11/27 11/21:All defects resolved. BAPP test planned on 11/24 11/17:MW Defect 4625 11/14: BAPP Aligned to test with single delivery. BAPP Testing in progress ETA 11/19 11/11:GTT Readiness impacting the FUT of BAPP. 11/6: This will be published for approval by 11/11. 11/4:FUT In progress 10/23 - FUT in progress | 2025-10-31 | Y | 05. OTC IP |  |  |  | Current Status: Retesting in progress Issue: GTT Readiness impacting the FUT of BAPP. Next Steps: Help needed:N/A E2E FUT ETA: 11/12 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2996 | OTCI1498 | 02.Interface | 01.IP - Intel Product | Inbound Interface from WOM to S4 HANA to send Customer Hierarchy | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2996_IP_OTC_Inbound%20Interface%20from%20WOM%20to%20S4%20HANA%20to%20%20send%20Customer%20Hierarchy.pptx?d=w0cd128f61cec4c2e8f91e524280eef5d&csf=1&web=1&e=9NjLTR | 02.No | 01.Yes |  | 2025-06-10 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud |  |  | MULESOFT | 2025-06-16 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-11 | 2025-08-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-11 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-11 | 2025-09-01 | 2025-09-10 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-15 | 2025-10-08 | 2025-08-13 | 100% | 2025-08-04 | 2025-09-17 | 2025-11-07 | 2025-11-07 | 100% | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-08-22 | 2025-09-01 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-06-09 06:12 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-11 | 01.S4 |  |  | 1 | 1.45 | 1498 | INT-CR0547 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-13 | 2025-07-21 |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | 2025-09-11 |  | 2025-09-10 |  | 2025-07-16 |  | 2025-10-08 | 2025-08-04 | 2025-08-04 |  | 2025-11-07 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | [5 empty] | 2025-06-27 | 2025-09-12 | 2025-09-10 |  | 2025-09-10 |  |  |  | 0 |  | 3084 | [9 empty] | 9/29: FUT sent for approval. All the open points are closed, awaiting final approval from Intel. | 2025-11-07 | Y | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2952 | OTCI1423 | 02.Interface | 01.IP - Intel Product | Service Interface and Enhancement of the outbound proxy sent to NL brokers - Declaration Request | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1420 | 2025-05-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 02.No | NA | NA |  |  | MULESOFT | 2025-06-30 | 2025-08-04 | 2025-07-16 | 100% | 2025-08-19 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-10-09 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-11-21 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-11-21 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-10 | [5 empty] | 2025-11-21 | 2025-11-21 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-05-01 11:33 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-05-29 | 01.S4 |  |  | 2 | 2.9 | 1423 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 |  |  |  |  | 2025-11-21 | 2025-11-21 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-08-04 | 2025-09-26 | 2025-10-08 |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3007 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 2/27: E2E FUT with external partner is in progress 2/18 - Expeditor B-App Build ETA is 2/20. Post that, E2E FUT will be started | 2025-11-07 | N | 05. OTC IP |  |  |  | 1217: TUT+FUT approach is in progress Current Status: TUT Complete Issue: One defect fix in progress Next Steps: . E2E FUT to start Help needed: N/A E2E FUT ETA - 1/9/26 |  |  | 1 | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-11-21 | 2025-11-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2841 | OTCI1259 | 02.Interface | 01.IP - Intel Product | Outbound interface from S4 HANA to WOM to send the product information | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD35DF2AF-F27F-42DD-AF06-BA2518A7FE97%7D&file=Console%20ID_2841_IP%20Inbound%20Interface%20from%20WOM%20to%20S4%20HANA%20to%20fetch%20required%20Product%20information%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | E-Commerce Cloud | APIGEE | 2025-05-05 | 2025-06-27 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-14 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-11 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | 2025-08-08 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-09 | 2025-09-08 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-01 | 2025-09-12 | 2025-10-01 |  | 2025-10-08 | 2025-10-24 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-02-17 06:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-28 | 01.S4 |  |  | 0.5 | 0.725 | 1259 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-08-22 |  | 2025-08-13 |  | 2025-09-12 | 2025-09-09 | 2025-09-09 |  | 2025-10-24 | 2025-10-01 | 2025-10-01 | 2025-09-12 | 2025-10-01 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-06-27 | 2025-09-12 | 2025-08-22 |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 1996 | [7 empty] | 4. Completed | 1. Approved no action | 12/4: 3877 -Closing opens today. sent for approval - 12/4 - ETA 12/2:Defect 3877 - which was working earlier -Not working at present. Defect reOpened. ETA 12/2 EOD 11/28: Awaiting Intel approval11/25:Awaiting Intel approval 11/21:FUT in progress. Target to send for BAPP Testing is 11/22 11/17:Tech and MW defects - 4644, 4623 11/14 - Defect 4257. MW ETA is TBD. MW Changes not impacting core functionality .Hence not blocker. BAPP Test planned to start on 11/17 and ETA 11/20 11/11 - Defect 3795. ETA is 11/11 11/6:3795/3877/4257 Defects deprioritized as per tech availability (Sandra 's defect reassignments ).Hence at Risk 11/4:defect 3795 10/30 - 3795 and 3877 under fix 10/23 - 3795 and 3877 defects | 2025-10-24 | Y | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2728 | OTCI1192 | 02.Interface | 04.GTS | Interface for BP Status query in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1109 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 25490; 9168; 1649; 11357 | Reltio; Enterprise registration and profile management; Webquote; Profisee - Business Reference Data Management | GTS | MULESOFT | APIGEE | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-11 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-17 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-17 | 2025-08-18 | 2025-09-12 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-08 | 2025-08-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-21 | 2025-09-17 | 2025-11-21 |  |  | 2025-10-08 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1192 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-08-13 | 2025-08-15 | 2025-08-13 |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-09-12 |  | 2025-08-13 |  | 2025-09-12 | 2025-09-08 | 2025-09-08 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-09-17 | 2025-11-21 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2025-06-13 | 2025-09-12 | 2025-09-12 | S4 |  | GTS |  |  | 0 | 08. Not Applicable | 2683 | [7 empty] | 4. Completed | 17. FUT In progress | 12/15: E2E FUT documents are reviewed internally. ETA 12/19 12/04: Documenting FUT. ETA for completion 12/10.; 11/18: Awaiting confirmation from B Apps for FUT Readiness. Standalone FUT documentation in progress | 2025-11-07 | Y | 05. OTC IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-09-17 | 2025-09-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2727 | OTCI1191 | 02.Interface | 04.GTS | Interface for Transactional status query in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1109 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 17492; 37510 | IRC2 Entitlement Management as-a Service; PEGA Integrated Shipping Memo Questionnaires | GTS | MULESOFT | APIGEE | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-15 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-15 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-15 | 2025-08-18 | 2025-09-12 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-08 | 2025-10-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-19 | 2025-09-15 | 2025-11-19 |  |  | 2025-10-08 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1191 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-08-14 | 2025-08-22 | 2025-08-14 |  | 2025-09-15 | 2025-09-26 | 2025-09-15 | 2025-09-15 |  | 2025-09-12 |  | 2025-08-13 |  | 2025-09-12 | 2025-09-08 | 2025-09-08 |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-09-15 | 2025-11-19 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  |  |  |  | Trade Apps | 2025-06-13 | 2025-09-26 | 2025-09-12 | S4 |  | GTS |  |  | 0 | 08. Not Applicable | 2682 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/04: Awaiting approval | 2025-11-07 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-09-26 | 2025-09-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2725 | OTCI1190 | 02.Interface | 04.GTS | Interface for Product Create/ Change in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1110 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 17492 | IRC2 Entitlement Management as-a Service | MULESOFT | GTS | APIGEE | 2025-03-24 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-07-18 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-31 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-31 | 2025-08-08 | 2025-08-22 | 2025-07-18 | 100% | 2025-07-18 | 2025-08-25 | 2025-09-19 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-28 | 2025-07-31 | 2025-11-28 |  |  | 2025-10-08 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-19 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 2 | 2.9 | 1190 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-31 | 2025-08-15 | 2025-07-31 | 2025-07-31 |  | 2025-08-22 |  | 2025-07-18 |  | 2025-09-19 | 2025-07-29 | 2025-07-29 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-07-31 | 2025-11-28 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-16 | 2025-08-15 | 2025-08-22 | S4 |  | GTS |  |  | 0 | 08. Not Applicable | 2681 | [7 empty] | 2. At Risk | 17. FUT In progress | 12/17 - Pending Internal Review. Will be sent for approval by 12/19 12/15: E2E FUT documents are reviewed internally. ETA 12/19 12/04: Awaiting B App readiness; 11/18: Awaiting confirmation from B Apps for FUT Readiness. Standalone FUT documentation in progress | 2025-11-07 | Y | 05. OTC IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-08-15 | 2025-07-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2724 | OTCI1189 | 02.Interface | 04.GTS | Interface for Product Classification Query in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1110 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 42860; 25189; 37510 | Customs Tracker; PEGA Global Trade Request; PEGA Integrated Shipping Memo Questionnaires | MULESOFT | GTS | APIGEE | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-11 | 2025-08-15 | 2025-07-18 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | 2025-09-01 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-18 | 2025-09-12 | 2025-07-18 | 100% | 2025-07-18 | 2025-09-15 | 2025-09-30 | 2025-08-13 | 100% | 2025-07-29 | 2025-09-29 | 2025-11-30 | 2025-11-30 | 100% | 2025-11-10 | 2025-07-29 | 2025-11-10 |  |  | 2025-10-08 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-30 | 2025-11-30 | 2025-11-30 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1189 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 |  | 2025-07-24 | 2025-09-12 | 2025-07-24 | 2025-07-24 |  | 2025-09-12 |  | 2025-07-18 |  | 2025-09-30 | 2025-07-29 | 2025-07-29 |  | 2025-11-30 | 2025-11-10 | 2025-11-10 | 2025-07-29 | 2025-11-10 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  |  |  |  | Trade Apps | 2025-06-13 | 2025-09-12 | 2025-09-12 | MW |  | GTS |  |  | 0 | 08. Not Applicable | 2680 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/04: FUT documentation sent out. Awaiting approval; 11/18 : E2E FUT complete, Documentation in-progress. ETA for completion is 11/20. | 2025-11-30 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-09-12 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2722 | OTCI1188 | 02.Interface | 04.GTS | Interface for Transactional Create/ Change in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1110 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 17492 | IRC2 Entitlement Management as-a Service | MULESOFT | GTS | APIGEE | 2025-03-24 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-14 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | 2025-08-08 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-17 | 2025-08-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-11-28 | 2025-09-17 | 2025-11-28 |  |  | 2025-10-08 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-23 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-12 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1188 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2025-08-22 |  | 2025-08-13 |  | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-09-17 | 2025-11-28 |  |  | 2026-01-23 | 2026-02-04 | 2026-01-23 | [5 empty] | 2025-05-16 | 2025-09-12 | 2025-08-22 | MW |  | GTS |  |  | 0 | 08. Not Applicable | 2679 | [7 empty] | 2. At Risk | 9. Blocked by B-App Readiness | 12/17 - Yet to pick up the E2E FUT. Working session planned for 12/18 12/15: E2E FUT documents are reviewed internally. ETA 12/19 12/04: Awaiting B App Readiness 11/18: Awaiting confirmation from B Apps for FUT Readiness. Standalone FUT documentation in progress | 2025-11-07 | Y | 05. OTC IP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-09-13 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2721 | OTCI1187 | 02.Interface | 04.GTS | Interface for BP Create/ Change in GTS - CAAS | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE229812-C2E4-486B-A968-64E1B9B43007%7D&file=Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCE1110 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 25490; 9168; 1649; 11357 | Reltio; Enterprise registration and profile management; Webquote; Profisee - Business Reference Data Management | MULESOFT | GTS | MULESOFT | 2025-03-24 | 2025-05-16 | 2025-05-14 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-08-08 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-17 | 2025-08-01 | 2025-11-17 | 2025-11-17 | 100% | 2025-11-25 | 2025-12-31 | 2025-12-31 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-26 | 2025-11-17 | 2025-11-17 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 2 | 2.9 | 1187 | INT-CR1538 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-14 | 2025-08-22 | 2025-08-14 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-08-22 |  | 2025-08-13 |  | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-12-31 | 2025-12-31 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2025-05-16 | 2025-09-26 | 2025-08-22 | S4 |  | GTS |  |  | 0 | 08. Not Applicable | 2678 | [7 empty] | 4. Completed | 17. FUT In progress | 11/17 - Will be sent for approval by 12/19 12/15: E2E FUT documents are reviewed internally. ETA 12/19 12/04: Documenting FUT. ETA for completion 12/10 11/18: Awaiting confirmation from B Apps for FUT Readiness. Standalone FUT documentation in progress | 2025-11-17 | Y | 05. OTC IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2594 | OTCI1180 | 02.Interface | 01.IP - Intel Product | EMS_Inbound Interface for Capturing Hardware SO and Line-Item Details into service sales order Text at Item Level and from OL (Orchestration layer) to S4 to remove the billing block | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID_2594_EMS_Inbound%20Interface%20for%20capturing%20hardware%20SO%20and%20Line-Item%20details%20into%20service%20sales%20order%20text%20at%20item%20level.pptx?d=wd69cca5b60e841758f4abb275999ec1d&csf=1&web=1&e=sh8El4 | 02.No | 01.Yes | OTCE1115 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 44876 | Entitlement Hub (SAP EMS, Internal Portal) | OL | S/4 | APIGEE | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-06-16 | 2025-07-18 | 2025-07-18 | 100% | 2025-07-21 | 2025-06-20 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-06-20 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-06-20 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-22 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-28 | 2025-07-29 | 2025-11-28 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-11-28 | 2025-11-28 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1180 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-08-13 | 2025-07-29 | 2025-07-29 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-07-29 | 2025-11-28 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 |  |  |  |  | Return for Credit | 2025-06-13 | 2025-07-18 | 2025-07-18 | MW |  |  |  |  | 0 | 08. Not Applicable | 1565 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/17: Awaiting Final Approval 11/14 - Sent for approval (no defects). FUT approval by 11/19 11/11 - Sent for approval 11/6:Delay observed by one day for BAPP Test. 10/30 - E2E FUT In progress 10/23 - S4 testing is completed. BA to get ready by 10/27 | 2025-11-28 | Y | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA 1119 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2590 | OTCI1179 | 02.Interface | 01.IP - Intel Product | EMS_Outbound interface to OL (Orchestration layer) for activation key generation of service warranty order and to send the validation result as part of call made from EH portal to S4 for validating the hardware and service warranty orders. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID_2590_EMS_Outbound%20interface%20to%20OL%20(Orchestration%20layer)%20upon%20service%20order%20create%20for%20activation%20key%20generation.pptx?d=w6881db91a6fb4e9fa6d0e11dc48e0f8d&csf=1&web=1&e=z9Cqy5 | 02.No | 01.Yes | OTCE1115 | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 44876 | Entitlement Hub (SAP EMS, Internal Portal) | S/4 | OL | APIGEE | 2025-06-16 | 2025-07-11 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-18 | 2025-08-22 | 2026-01-07 | 100% | 2025-12-18 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-02 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-18 | 2025-08-15 | 2025-09-30 | 100% | 2025-10-08 | 2025-08-18 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-28 | 2025-10-08 | 2025-11-28 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-11-28 | 2025-11-28 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1179 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-10-08 | 2025-11-28 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  |  | Return for Credit | 2025-07-11 | 2025-09-12 | 2025-09-10 | MW |  |  |  |  | 0 | 08. Not Applicable | 1562 | [7 empty] | 4. Completed | 1. Approved no action | 12/8:approved 12/4: Sent for approval.Opens in progress - ETA - 12/4 12/2:Awaiting intel approval 11/28-Sent for approval 11/28:Defect 5071 in fix. ETA 11/28 11/25:Defect 4960 under fix11/21: Defect 4667 under fix. ETA 11/22 11/17:Defects 4514, 4655 11/14 - Defects 4086 & 4514. FUT ETA is 11/21 11/11 - Defect 4086. ETA is TBD 11/4:defect 4086 10/30: BAPP Testing started . Issue identified -defect 4086 10/23 - S4 testing is completed. BA to get ready by 10/27 | 2025-11-28 | Y | 05. OTC IP |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1512 | OTCI1178 | 02.Interface | 01.IP - Intel Product | Interface from Sales Force (SF) to S4 to read the business rules | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B74756471-E309-4942-B733-779D53A986C6%7D&file=Return%20Console_IP_R-190-010_Interface%20from%20SF%20to%20read%20the%20business%20rules.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 36446 | Return For Credit | SF | S/4 | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-16 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-16 | 2025-03-28 | 2025-04-25 | 2025-08-08 | 100% | 2025-08-25 | 2025-03-28 | 2025-04-25 | 2025-08-08 | 100% | 2025-08-25 | 2025-06-20 | 2025-07-15 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-28 | 2025-09-30 | 2025-09-30 | 100% | 2025-10-07 | 2025-04-28 | 2025-12-21 | 2025-12-21 | 100% | 2026-01-05 | 2025-10-07 | 2026-01-05 |  | 2025-09-05 | 2025-09-26 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-30 | 2025-12-21 | 2025-12-21 | jonsanders@deloitte.com | 2025-01-23 15:43 | cell-link@smartsheet.com | 2026-04-01 01:51 | 10 | 2025-02-19 | 01.S4 |  |  | 1 | 1.45 | 1178 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 |  |  |  |  | Return for Credit | 2025-03-21 | 2025-04-25 | 2025-07-15 | MW |  |  |  |  | 0 |  | 2333 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30:Defect 4051 under fix 10/23 - Defect 3703. ETA is 10/23 10/17: defect 3703 10/10: Awaiting Intel approval on this | 2025-12-21 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-08-25 | 2025-08-25 | No |  | No |  | No |  |  |  | Yes |  | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2719 | OTCI1162 | 02.Interface | 02.IF - Intel Foundry | Inbound interface to change the sales order via Build Instructions | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B802677C8-F4E4-4791-AE61-1E1E7159DFC6%7D&file=IF_POSO_Console%20ID%202719_Inbound%20interface%20to%20change%20the%20sales%20order%20via%20Build%20Instructions.pptx&action=edit&mobileredirect=true&CID=0C8C320D-52C2-4FA3-9422-A95FE1DD3713&wdLOR=cCB3F38BD-5685-4A08-8EDF-2BBD7E3F1C91 | 02.No | 01.Yes |  | 2025-01-29 | Jill Matalon | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-28 | 2025-05-19 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-21 | 2025-04-21 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-21 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-09 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-11 | 2025-10-20 | 2025-10-24 | 2025-10-08 | 100% | 2025-09-17 | 2025-05-02 | 2025-05-23 | 2025-05-23 | 100% | 2025-05-23 | 2025-09-17 | 2025-09-17 |  | 2025-08-29 | 2026-03-25 | 2026-03-25 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-25 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-24 | 2025-10-24 | 2025-10-24 | jonsanders@deloitte.com | 2025-01-23 15:43 | cell-link@smartsheet.com | 2026-03-26 21:59 | 10 | 2025-01-29 | 01.S4 |  |  | 1 | 1.45 | 1162 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-10-24 | 2025-09-17 | 2025-09-17 |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-09-17 | 2025-09-17 |  |  | 2026-03-20 | 2026-03-25 | 2026-03-20 |  |  |  |  | B2B - OpenText | 2025-03-21 | 2025-05-16 | 2025-07-11 | MW |  |  |  |  | 0 | 02. IF Customers | 2676 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 3/20: sent for approval 3/13:FUT Defect under retest 3/6:New defect 8084 to be fixed 2/27:Defects 7718(AIF Issues) , 7578 - For the change Payload readiness -Also tracked in RAID 3621 2/25:7718 - No error Log in AIF For create scenarios , 7578 - Change Payload not ready from FTS 2/24:7652 Defect open with tech on Line item (POSEX Issues) 2/19: 7221, 6645 - both defect has been fixed and re-testing is in progress. Dependent object OTCE1106 defect to be closed for send for approval process. 2/17: Defect 7221 to be fixed by MW. Fix is in progress 2/12: Below 2 defects to be fixed. 6645 - Tech issue (Reopened) - BAPI issue. ( BAPI is not triggered return order's) 7221 - Build instruction information not reached to S4. there is no IDOC triggered from IP to IF. (IDOC reached till Open text. from OT to S4 not yet received. Tech fix required) ETA - 2/13 2/10: OTC Defect fixed : 6254. howe every testing not yet started due to E2E Scenario issue - FTS --->IDOC --->Payload flow not working . IDOC for FTS not triggered . FTS Defect 7087 impacting OTC. 1/14::CR 856 Still to be delivered. ETA TBD 1/6:CR 856 Still to be delivered. ETA TBD 01/05: CR will be delivered. 12/23: CR will be delivered on 12/24. Testing can be started only post 12/24 12/8: Dependent on FTS CR -Which is delayed -Not met 11/28 given ETA. FUT cannot be tested untill INT-CR0582 of FTSI0268 is completed 12/2: Dependent on FTS CR -Which is delayed -Not met 11/28 given ETA. FUT cannot be tested untill INT-CR0582 of FTSI0268 is completed 11/25: OTC FUT Blocked due to a CR dependency for FTS. CR Development ETA is 11/28 11/25: OTC FUT Blocked due to a CR dependency for FTS. CR Development ETA is 11/28 11/21:Blocked with FTS CR. ETA 11/28 11/17: Blocked due to Dev CR. FTS team have a CR which dev ETA -11/28 11/14 - Still looking for additional from FTS IP team. ETA is 11/21 11/6:Delayed FTS Support on this 11/4:Still dependent with FTS 10/30: This is blocked due to FTS development. RAID 2846 | 2025-10-24 | N | 04. OTC IF | [6 empty] | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | Yes | DUNS4 for Plant from IP Build Instructions Payload to determine Ship-to Party in IF Sales Order - Master Data Impact CR-856 OSAT Plant sent from IP, IF Determined Plant from ZPARAMS in IF - ZPARAMS Impact | Yes | Regression Testing Only | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-27 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2575 | OTCI1161 | 02.Interface | 02.IF - Intel Foundry | Inbound interface from BY-PDH to S4 to update CMAD in IF sales orders | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2575_IF_%20Inbound%20interface%20from%20BY-PDH%20to%20S4%20for%20order%20promising.pptx?d=w8fb29f87d8994b93b7453bd7d635d600&csf=1&web=1&e=maJPVn | 02.No | 01.Yes | OTCE1123 | 2025-01-30 | Jill Matalon | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 05. N/A | 03.Medium |  | 02.No | NA | NA | BY | S/4 | BODS | 2025-04-21 | 2025-06-27 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-29 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-01 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-01 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-06 | 2025-10-08 | 2025-10-24 | 100% | 2025-10-24 | [5 empty] | 2025-12-01 | 2025-12-01 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | jonsanders@deloitte.com | 2025-01-23 15:43 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-01-30 | 03.Mulesoft |  |  | 1 | 1.45 | 1161 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-10-24 | 2025-10-24 | 2025-10-24 |  |  |  |  | 2025-12-01 | 2025-12-01 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-06-27 | 2025-11-28 | 2025-08-13 | [5 empty] | 0 | 08. Not Applicable | 2323 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4:Sent for approval 10/30 - FUT In progress. ETA is 11/05 10/22 - FUT In progress. | 2025-11-28 | Y | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-01 | 2025-12-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2535 | OTCI1126 | 02.Interface | 02.IF - Intel Foundry | Inbound interface to create and change sales order via Subcon, STO & SIMS PO | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_POSO_Console%20ID%202535_Inbound%20interface%20to%20create%20the%20sales%20order%20via%20Build%20Instructions.pptx?d=w9088719be6f54ffe9324ebf48cb3222e&csf=1&web=1&e=NxXGWs |  |  |  | 2025-01-21 | Jill Matalon | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  |  | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-06-02 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-21 | 2025-06-02 | 2025-06-13 | 2025-07-11 | 100% | 2025-09-02 | 2025-06-02 | 2025-06-13 | 2025-07-11 | 100% | 2025-09-02 | 2025-05-19 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-11 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-02 | 2025-06-26 | 2025-06-26 | 100% | 2025-06-26 | 2025-09-02 | 2025-09-02 |  | 2025-09-19 | 2026-01-23 | 2026-01-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-23 | Sprint 22 Week 2 | R3 Build & UT Sprint 23 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-01-16 12:46 | cell-link@smartsheet.com | 2026-04-03 02:50 | 10 | 2025-01-21 | 01.S4 |  |  | 2 | 2.9 | 1126 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-09-02 | 2025-09-02 |  | 2026-02-23 | 2026-02-23 | 2026-02-20 | 2026-02-20 |  |  |  |  | B2B - OpenText | 2025-04-04 | 2025-06-13 | 2025-06-13 | S4 |  |  |  |  | 0 | 02. IF Customers | 1669 | [7 empty] | 4. Completed | 3. Awaiting Approval | 2/19: Object sent for approval.Luis approval is pending now. 2/17: Object sent for approval.Luis approval is pending now. 2/12: 2 new defect's identified in Bapp testing - 7187 and 7238-needs to be fixed. Working sessions set up on 2/13 6 scenario pending from Bapp testing out of 32 to complete FUT 7187 - AIF error message has not been updated correctly while doing changes ,Ex: Status Hold changes not captured in ALF error log (how ever, it works in client gatway) 7238 - AIF error message has not updated correctly while doing changes. Ex; Multiple changes are performed in sales order line item "10 - but in AIF error log, it showing other line items - 10,2030.. 2/10: No opens. Bapp testing is in progress.BAPP Experienced Queue issues on 2/10. 2/5: Defect 7008 fix in progress ETA 2/6, Action on Tech Team (Satya) 2/3: All the opens are closed. defect -6804, 6768 closed) Official Confirmation sent to Bapp team to start Testing(Soo chin from Open text) 2/2: 11 jira tickets are assigned back to b app team . 11 were from defect 6642 Team identified new defect "6804 - AIF reprocessing" today. It has to be fixed before Bapp team start E2E FUT . 1/29: defect 6642 to be fixed (AIF error message display issue in S4). 6/9 JIRA issues fixed - have to fixed by EOD and MY team have to work on testing .Critical for BAPP Testing 1/22:All S4 defects fixed. BAPP Testing in progress .ETA 1/23 1/20:Defect 6452 under retest 1/14: defect 6022 and 6180 to be fixed by Tech team. 1/8: : defect 6022 to be fixed. 5418 - re-testing is inprogress - ETA Today 1/6:Defect 5418,5613 fixed-under retest. ETA To close 1/7 EOD 01/05: defect 5418 to be fixed. 12/24:Defect 5418 still Open .ETA TBD 12/23:Defect 5418,5613 Still Open.ETA 12/23. 12/16: Defect 5418 (AIF error message needs to be replicated), 5613(rder create and change is not working ) to be fixed by Tech team. ETA - 12/16 12/11:Defect 5418,5447 - ETA 12/11 EOD 12/9:Defect 5047 still under fix 12/8: Defect 5047 -ETA 12/9 EOD 12/4: Defect 5047 -already fixed issues are recurring .Reopened defect. ETA 12/3 EOD 12/2:Defect 5047 -already fixed issues are recurring .Reopened defect. ETA 12/3 EOD 11/28:FUT in progress. ETA to send for approval 11/28 11/21:FUT In progress. ETA 11/24 11/17:Defect 4586 11/14 - Defect 4513 and 4477. ETA from tech team is 11/14. FUT can be closed by 11/19 11/11:Ongoing issues are resolved. FUT in progress. 10/30 - Defect 4095. 10/23 - Awaiting working payload from PTP Team. 10/17:IP-IF process. Dependency on BAPP/Procurement MW development dependency 8/25: New S4 Build end date 09/10/25 in OTC-IF Deloitte lead (Taposh G) | 2025-07-18 | N | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-02 | 2025-09-02 | Yes | DUNS4 for Plant from IP Build Instructions Payload to determine Ship-to Party in IF Sales Order - Master Data Impact | Yes | Regression Testing Only | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-04-03 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2353 | OTCI0876 | 02.Interface | 01.IP - Intel Product | Inbound interface to S4 HANA from PDH system to get dampened and Non Dampened orders and update Non-Dampened orders with new CMAD and Dampened orders in custom table | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFC27AE8C-3063-437F-969A-19F9ED63C151%7D&file=Console%20ID_2353_IP_%20Inbound%20interface%20to%20S4%20HANA%20from%20PDH%20system.pptx&action=edit&mobileredirect=true&CID=EBB213CA-3AC7-4933-904B-EC51C53103A4&wdLOR=cAB2822E1-9B3E-4AAA-9882-8A66B7384A7C | 02.No | 01.Yes |  | 2024-11-06 | Shelly.Lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | PDH | S/4 | BODS | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | 2025-07-21 | 2025-08-15 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-20 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-23 | [5 empty] | 2025-10-23 | 2025-10-23 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-14 | 01.S4 |  |  | 1 | 1.45 | 0876 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-24 | 2025-10-23 | 2025-10-23 |  |  |  |  | 2025-10-23 | 2025-10-23 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | [5 empty] | 2025-05-02 | 2025-08-29 | 2025-08-15 |  | 2025-10-31 |  |  |  | 0 | 08. Not Applicable | 2475 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/11 - Sent for approval 11/4:sent for approval 10/30 - FUT in progress. ETA is 11/05 | 2025-10-24 | Y | 05. OTC IP |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-09-13 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2255 | OTCI0716 | 02.Interface | 01.IP - Intel Product | PIP 2A1 Interface to Distribute | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_2255_IP_2A1%20Interface%20to%20distribute.pptx?d=w5716877daaa64e02a71e76ea0d698f7e&csf=1&web=1&e=MkIWNJ | 02.No | 01.Yes | OTCE0715 | 2024-10-11 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-02-10 | 2025-04-04 | 2025-04-04 | 100% | 2025-04-05 | 2025-05-12 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-26 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-20 | 2025-05-26 | 2025-06-13 | 2025-08-08 | 100% | 2025-09-20 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-16 | 2025-06-16 | 2025-06-27 | 2025-08-13 | 100% | 2025-07-29 | 2025-06-23 | 2025-07-07 | 2025-07-07 | 100% | 2025-07-07 | 2025-09-20 | 2025-09-20 |  | 2025-10-21 | 2025-10-28 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-06-27 | 2025-07-07 | 2025-07-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-11 | 01.S4 |  |  | 1 | 1.45 | 0716 |  | R3 ITC1 | [6 empty] | 2025-04-05 | 2025-04-05 | 2025-04-05 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-08-13 | 2025-07-29 | 2025-07-29 |  | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-09-20 | 2025-09-20 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 |  |  |  |  | B2B - OpenText | 2025-05-02 | 2025-08-29 | 2025-08-15 | S4 | 2025-11-14 |  |  |  | 0 | 03. IP Customers | 1501 | [7 empty] | 4. Completed | 1. Approved no action | 1/9: Approval received from Luis today 1/8:Defect 6307 -ETA 1/7 EOD.1 /6:Defect 6307 -ETA 1/7 EOD. 01/05: FUT sent for approval. Walkthrough completed. opens are in progress (defect 5959) 12/24:Awaiting approval 12/23: defect 5888, 5878 fixed and ready for re-testing 12/18: defect 5297 to be fixed. ETA - 12/18 12/16: as requested by tech team, new defect 5688 is created for 716 & 715 - ETA - 12/17 12/11:Defect 5427 in fix. ETA 12/11 12/8:Defect 5297 ETA 12/8 EOD 12/4: Defect fixed and Re-testing is in progress 12/2:FUT Defect 5129 Under fix 11/28:Defect 3917 fixed-test in progress 11/25:Defect 3917 -Initial fix is done . Currently Functional is working on clarifications asked by technical team .This will be moved back to tech on 11/26 11/21;Defect 3917 -MW Issues persists ETA TBD 11/17:Defect 3917 -At present Sorting RFC issues 11/14 - Defect 3917. ETA from tech is 11/17. FUT completion by 11/24 11/13 EP: Provide revised FUT due date 11/11 - RFC Destination needs to be setup for Open Text 11/6:Due to defect prioritization within available tech team - This defect was deprioritized. Will not be able to close FUT in S19 11/4:defect 3917 is deprioritized due to other defects. Untill this is fixed cannot test FUT. 10/30 : Defect 3917 - defect fix in progress. ETA is 10/31 10/23 - FUT & TUT in progress | 2025-07-07 | N | 05. OTC IP |  |  |  |  | ETA 1205 Defect 3917 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-20 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2106 | OTCI0711 | 02.Interface | 01.IP - Intel Product | IP - Inbound Interface from CSAR to SAP | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/O-020-080%20Billing%20Revenue-Process%20Customer%20Invoice%20CSAR%20Inbound%20Interface.pptx?d=w2b35e6944b824de2ba410d7f65cf435f&csf=1&web=1&e=sefLsK | 01.Yes | 01.Yes |  | 2024-10-09 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 316 | Customer Service Adjustment Request | CSAR | S/4 | NA | 2025-01-27 | 2025-03-14 | 2025-03-14 | 100% | 2025-03-26 | 2025-05-02 | 2025-05-09 | 2026-01-07 | 100% | 2025-12-18 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-12-31 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-12-31 | [10 empty] | 2025-08-18 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-12-31 | 2025-12-31 |  | 2025-10-08 | 2025-10-24 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-11 | 01.S4 |  |  | 2 | 2.9 | 0711 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [9 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-12-31 | 2025-12-31 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2025-03-14 | 2025-06-13 | 2025-06-13 | S4 | 2025-10-31 |  |  |  | 0 | 08. Not Applicable | 2275 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 11/17:Defect 4634 11/14 - Sent for approval on 11/13 (no defects). FUT Approval ETA is 11/18 11/11 - Defect 3543. | 2025-09-12 | N | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No | BAPP Config only, CSAR is not creating any transactional data for AM01 as of now, regression testing only may be required | No |  | No |  | 2026-02-16 | 2026-03-20 | No | BAPP Config |  |  |  |  | No
01. IAO ERP | 03.R3 | 1737 | OTCI0682 | 02.Interface | 01.IP - Intel Product | Inbound Interface for Receiving PO details from B2B Customer | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Receiving%20PO%20details%20from%20B2B%20Customer.pptx?d=wfd2cd2bbed744bc6b4d02ca346c060de&csf=1&web=1&e=1C0wXs | 02.No | 01.Yes |  | 2024-10-03 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2024-10-28 | 2025-01-10 | 2025-01-10 | 100% | 2024-12-13 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-08-20 | 2025-03-07 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-04 | 2025-03-07 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-04 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-05-05 | 2025-04-25 | 2025-05-22 | 2025-05-22 | 100% | 2025-05-22 | 2025-05-05 | 2025-05-22 |  | 2025-06-06 | 2025-08-01 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-05-22 | 2025-05-22 | pgaroo@deloitte.com | 2024-10-03 06:54 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-11 | 01.S4 |  |  | 1 | 1.45 | 0682 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-10 | 2024-12-13 |  | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | 2025-03-04 | 2025-03-21 | 2025-03-04 | 2025-03-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-05 | 2025-05-22 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  |  |  |  | B2B - OpenText | 2025-01-10 | 2025-03-21 | 2025-02-21 | MW | 2025-07-11 |  |  |  | 0 | 03. IP Customers | 2192 | [7 empty] | 1. On Track | 17. FUT In progress | 8/18: FUT sent for approval | 2025-05-22 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-03-21 | 2025-03-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2166 | OTCI0661 | 02.Interface | 01.IP - Intel Product | Inbound KL Order Creation from ALPS to S/4 | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%202166_Inbound%20KL%20Order%20Creation%20from%20ALPS%20to%20S4.pptx?d=w10b900c18c18426aafdbe2fd3637f833&csf=1&web=1&e=KY4VYd | 02.No | 01.Yes |  | 2024-09-22 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 36978 | ALPS (Intel Product Validation Labs Planning) | ALPS (Intel Product Validation Labs Planning) | S/4 | MULESOFT | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-21 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-06 | 100% | 2025-06-06 | 2025-08-01 | 2025-08-15 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-21 | 2025-08-15 | 2025-07-18 | 100% | 2025-07-18 | 2025-08-18 | 2025-09-12 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-21 | 2025-11-13 | 2025-11-13 | 100% | 2025-11-28 | 2025-07-21 | 2025-11-28 |  | 2025-09-02 | 2025-10-24 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-11-13 | 2025-11-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 01.S4 |  |  | 1 | 1.45 | 0661 |  | R3 ITC1 | [6 empty] | 2025-04-21 | 2025-04-21 | 2025-04-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-06 | 2025-08-15 |  |  |  | 2025-08-15 |  | 2025-07-18 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-07-21 | 2025-11-28 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | MW | 2026-02-13 |  |  |  | 0 | 08. Not Applicable | 1601 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting intel approval .No Opens 11/28:Awaiting Intel approval 11/25:Awaiting Intel approval. Opens are closed 11/21:Awaiting approval.ETA 11/21 11/17:Awaiting approval 11/14 - Awaiting approval (no defects). FUT Approval ETA is 11/19 11/11 - Awaiting approval 11/4:awaiting approval 10/30: defect 4041 under fix 10/23 - FUT feedback in progress. ETA to reshare is 10/24 | 2025-11-13 | Y | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA 1119. Additional CR to be requested. |  |  |  | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-08-15 | 2025-06-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1887 | OTCI0565 | 02.Interface | 01.IP - Intel Product | Outbound Interface development for Invoice data from S4 to CHM | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-170-090%20close%20claim.pptx?d=wf922d01157e84386aa88ab1c9114f519&csf=1&web=1&e=Kbe1c3 | 01.Yes | 01.Yes |  | 2024-08-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 1887 | Channel Management | S/4 | CHM | NA | 2024-09-23 | 2024-11-22 | 2024-12-06 | 100% | 2024-12-09 | 2025-01-24 | 2025-01-31 | 2026-01-07 | 100% | 2025-12-18 | 2025-02-21 | 2025-03-07 | 2025-06-11 | 100% | 2025-10-02 | 2025-02-21 | 2025-03-07 | 2025-06-11 | 100% | 2025-10-02 | [10 empty] | 2025-06-16 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-11 | 2025-10-02 | 2025-10-02 |  | 2025-08-01 | 2025-08-13 | 2025-09-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-08-20 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-07 | 2025-07-11 | 2025-07-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-28 | 01.S4 |  |  | 1 | 1.45 | 0565 |  | R3 ITC1 |  |  |  |  | 02. Standard IDOC |  | 2024-12-09 | 2024-12-09 | 2024-12-09 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [9 empty] | 2025-07-11 | 2025-07-11 | 2025-07-11 | 2025-10-02 | 2025-10-02 |  |  | 2025-08-20 | 2025-09-05 | 2025-08-20 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2024-11-22 | 2025-03-07 | 2025-03-21 | S4 | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 1696 | [7 empty] | 5. Not Dispositioned |  |  | 2025-07-11 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No | BAPP Config only, CHM is not creating any transactional data for AM01/AM10 even now, so regression testing not required | No |  | No |  | 2026-02-16 | 2026-03-20 | No | BAPP Config |  |  |  |  | No
01. IAO ERP | 03.R3 | 1676 | OTCI0540 | 02.Interface | 01.IP - Intel Product | Inbound Interface from WOM to S4 HANA to fetch the list of order Acknowledgements/confirmations for a particular customer. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CF8D569-435A-4929-969B-CBBD7FEB9E28%7D&file=Console%20ID_831_IP_%20Interface%20from%20WOM%20to%20S4%20to%20fetch%20list%20of%20all%20e-Acks%20for%20a%20particular%20customer%20.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-08-20 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | WOM | S/4 | MULESOFT | 2025-01-27 | 2025-04-04 | 2025-04-04 | 100% | 2025-04-07 | 2025-06-06 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-20 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-06-16 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-21 | 2025-08-15 | 2025-06-11 | 100% | 2025-06-11 | 2025-07-28 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-02 | 2025-06-11 | 2025-09-02 |  | 2025-09-02 | 2025-10-08 | 2025-10-31 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-08-14 08:27 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-22 | 01.S4 |  |  | 1 | 1.45 | 0540 |  | R3 ITC1 | [6 empty] | 2025-04-07 | 2025-04-07 | 2025-04-07 |  | 2025-05-20 | 2025-06-13 | 2025-05-20 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 |  | 2025-07-18 |  | 2025-06-06 |  | 2025-08-15 | 2025-06-11 | 2025-06-11 |  | 2025-09-12 | 2025-09-02 | 2025-09-02 | 2025-06-11 | 2025-09-02 |  |  | 2025-10-30 | 2025-10-31 | 2025-10-30 | [5 empty] | 2025-04-04 | 2025-07-18 | 2025-07-18 | MW | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2525 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/23 - Awaiting approval | 2025-09-12 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1849 | OTCI0488 | 02.Interface | 01.IP - Intel Product | Interface development direction inbound for Credit or Debit Memo Requests creation through CHM (Channel Management) | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%201849_Interface%20development%20direction%20inbound%20for%20Credit%20or%20Debit%20Memo%20Requests%20creation%20through%20CHM.pptx?d=wefd42da0215c47acaec086e76cb9c71e&csf=1&web=1&e=ICT8o4 | 02.No | 01.Yes |  | 2024-07-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 1887 | Channel Management | CHM | S/4 | NA | 2024-09-02 | 2024-10-11 | 2024-10-25 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-11-28 | 100% | 2025-11-21 | 2025-02-21 | 2025-03-07 | 2025-06-11 | 100% | 2025-10-02 | 2025-02-21 | 2025-03-07 | 2025-06-11 | 100% | 2025-10-02 | [10 empty] | 2025-09-01 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-15 | 2025-10-02 | 2025-10-02 |  | 2025-09-01 | 2025-09-10 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-07 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2024-07-26 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-09 | 01.S4 |  |  | 1 | 1.45 | 0488 |  | R3 ITC1 |  |  |  |  | 02. Standard IDOC |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-11-21 | 2025-11-28 | 2025-11-21 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [9 empty] | 2025-09-26 | 2025-09-15 | 2025-09-15 | 2025-10-02 | 2025-10-02 |  |  | 2025-09-15 | 2025-09-26 | 2025-09-15 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2024-10-11 | 2025-03-07 | 2025-03-21 | S4 | 2025-10-31 |  |  |  | 0 | 08. Not Applicable | 2168 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-09-26 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No | BAPP Config only, CHM is not creating any transactional data for AM01/AM10 even now, so regression testing not required | No |  | No |  | 2026-02-16 | 2026-03-20 | No | BAPP Config |  |  |  |  | No
01. IAO ERP | 03.R3 | 1575 | OTCI0442 | 02.Interface | 02.IF - Intel Foundry | IF: Interface requirement from SAC to S4 | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF%20Console%20ID_748_IF_Interface%20requirement%20from%20SAC%20to%20S4.pptx?d=w2b08ca1ba1ec490c8524b99212334776&csf=1&web=1&e=bnniAA | 02.No | 01.Yes |  | 2024-07-12 | Jill Matalon | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | SAC | S/4 | BODS | 2024-08-12 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-08-08 | 100% | 2025-08-04 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-07 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | [5 empty] | 2025-03-21 | 2025-03-21 |  | 2025-07-16 | 2025-11-26 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | vasamohan@deloitte.com | 2024-07-12 09:41 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0442 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-03-07 | 2025-03-07 |  |  |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 |  | 2025-03-21 |  |  |  |  | 2025-03-21 | 2025-03-21 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2024-09-13 | 2025-02-21 | 2025-01-24 |  | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 1737 | [7 empty] | 4. Completed | 1. Approved no action | 12/11:Approved No action 12/9:Opens closed.Awaiting approval 12/8:Opens closed.Awaiting approval 12/3:sent for Intel approval 12/2:FUT Defects 5096 , 5142 under fix. 12/3 ETA To send for approval after defect closure 11/28:FUT Defect 5019 and 5096 in progress .ETA 11/28 11/25 : Defects closed .FUT in Progress. On track 11/21:FUT Defect 4645 under retest. ETA FOR FUT -11/24 11/17:After BODS Changes -FUT started FUT Defect 4645 identified. 11/14: BAPP Changes completed. BODS Development in progress. If FUT could not be started by 11/17 - Risk of completion | 2025-03-21 | N | 04. OTC IF |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-03-07 | 2025-03-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1569 | OTCI0439 | 02.Interface | 01.IP - Intel Product | Enable PIP 3A6 – transmit order status to the B2B customer (outbound interface) | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_Console%20ID%20741_Enable%20PIP%203A6%20%E2%80%93%20transmit%20sales%20order%20status%20to%20B2B%20customers.pptx?d=wecc39bddc3ce4192b8553206990a6d7d&csf=1&web=1&e=XMM5dx | 02.No | 01.Yes |  | 2024-07-09 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-10-07 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-05 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-07 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-09 | 2025-02-07 | 2025-02-21 | 2025-02-28 | 100% | 2025-03-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-01-27 | 2025-04-28 | 2025-04-28 | 100% | 2025-04-28 | 2025-03-19 | 2025-04-28 |  | 2025-06-06 | 2025-06-27 | 2025-07-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-27 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-04-28 | 2025-04-28 | pgaroo@deloitte.com | 2024-07-09 00:12 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0439 |  | R3 ITC1 | [6 empty] | 2024-12-05 | 2024-12-06 | 2024-12-05 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-02-09 | 2025-02-28 | 2025-02-09 | 2025-03-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-03-19 | 2025-04-28 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  |  |  | B2B - OpenText | 2024-12-06 | 2025-02-21 | 2025-01-24 | MW | 2025-06-27 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1731 | [10 empty] | 2025-04-28 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-03-07 | 2025-03-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1570 | OTCI0438 | 02.Interface | 01.IP - Intel Product | Enable PIP 3A7 – transmit significant sales order changes to the B2B customers (outbound interface) | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_Console%20ID%20742_Enable%20PIP%203A7%20%E2%80%93%20transmit%20significant%20sales%20order%20changes%20to%20the%20B2B%20customers.pptx?d=wa4d7d5f63ea04b47b85e298db6e092cd&csf=1&web=1&e=pPUdP3 | 02.No | 01.Yes |  | 2024-07-09 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-10-07 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-05 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-07 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-09 | 2025-02-07 | 2025-02-21 | 2025-02-28 | 100% | 2025-03-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-01-27 | 2025-04-28 | 2025-04-28 | 100% | 2025-04-28 | 2025-03-19 | 2025-04-28 |  | 2025-06-06 | 2025-06-27 | 2025-07-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-27 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-04-28 | 2025-04-28 | pgaroo@deloitte.com | 2024-07-09 00:12 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0438 |  | R3 ITC1 | [6 empty] | 2024-12-05 | 2024-12-06 | 2024-12-05 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-02-09 | 2025-02-28 | 2025-02-09 | 2025-03-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-03-19 | 2025-04-28 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  |  |  | B2B - OpenText | 2024-12-06 | 2025-02-21 | 2025-01-24 | MW | 2025-06-27 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1732 | [10 empty] | 2025-04-28 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-03-07 | 2025-03-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1719 | OTCI0435 | 02.Interface | 01.IP - Intel Product | Inbound interface from IRC2 (Intel Registration Center) B-app to S4 against order create | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B230F9CB7-B8E7-4AF9-A958-7187E1E78600%7D&file=IP_Console%20ID%201719_Inbound%20interface%20from%20IRC2%20(Intel%20Registration%20Center)%20B-app%20to%20S4%20against%20order%20create.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes | OTCE0524 | 2024-12-06 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 17492 | IRC2 Entitlement Management as-a Service | IRC2 | S/4 | MULESOFT | 2024-09-09 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-17 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-01-30 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-26 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-26 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-05-21 | 2025-05-15 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-05-21 | 2025-06-13 |  |  | 2025-05-02 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-14 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-12-02 01:33 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0435 |  | R3 ITC1 | [6 empty] | 2024-10-17 | 2024-10-17 | 2024-10-17 |  | 2025-01-30 | 2025-02-21 | 2025-01-30 |  | 2025-02-26 | 2025-03-21 | 2025-02-26 | 2025-02-26 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-05-21 | 2025-06-13 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-11 | 2025-03-21 | 2025-01-24 | MW | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1806 | [7 empty] | 3. Off Track | 25. Requirement Change | Completed. | 2025-06-13 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-03-21 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1716 | OTCI0426 | 02.Interface | 01.IP - Intel Product | Outbound interface to IRC2 (Intel registration center) B-app upon order create | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDF89E403-4DA1-4356-8417-9EBDB966B498%7D&file=IP_Console%20ID%201716_Outbound%20interface%20to%20IRC2%20(Intel%20Registration%20Center)%20upon%20order%20create.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes | OTCE0489 | 2024-06-28 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 17492 | IRC2 Entitlement Management as-a Service | S/4 | IRC2 | MULESOFT | 2024-09-09 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-17 | 2024-12-16 | 2025-01-10 | 2025-02-21 | 100% | 2025-02-19 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-17 | 2024-12-16 | 2025-01-16 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-05-21 | 2025-05-15 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-05-21 | 2025-06-13 |  | 2025-06-11 | 2025-06-27 | 2025-07-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-02 | 2025-07-11 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-06-28 04:56 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0426 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-10-17 | 2024-10-17 | 2024-10-17 |  | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-02-17 | 2025-03-21 | 2025-02-17 | 2025-02-17 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-05-21 | 2025-06-13 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-10-11 | 2025-03-21 | 2025-01-16 | MW | 2025-07-11 |  |  |  | 0 | 08. Not Applicable | 1804 | [10 empty] | 2025-06-13 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-03-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1391 | OTCI0417 | 02.Interface | 01.IP - Intel Product | Interface to Maintain Customer Part numbers in CMIR in S4 through WOM | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF8333DE7-7D73-4729-ACA6-DD0B8EEEA198%7D&file=Console%20ID_562_IP_OTC_Interface%20to%20Maintain%20Customer%20part%20numbers%20in%20S4%20through%20WOM.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-08-12 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-02-21 | 100% | 2025-02-05 | 2025-01-27 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-21 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-10 | 2025-04-28 | 2025-06-12 | 2025-06-12 | 100% | 2025-06-12 | 2025-04-10 | 2025-06-12 |  | 2025-07-04 | 2025-07-16 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-06-12 | 2025-06-12 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0417 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2025-02-21 | 2025-03-21 |  |  |  | 2025-03-21 |  | 2025-02-21 |  | 2025-05-16 | 2025-04-10 | 2025-04-10 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-04-10 | 2025-06-12 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2024-09-13 | 2025-03-21 | 2025-03-21 | MW | 2025-10-24 |  |  |  | 0 | 08. Not Applicable | 2486 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/17:Awiating approval ,No opens 11/14 - Awaiting approval (no open defects). FUT approval by 11/17 11/11:Addressing Intel Opens. Will resent EOD 11/6:Defect 4021 if fixed - Can close approval Open | 2025-06-12 | N | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA 1119 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-03-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1527 | OTCI0414 | 02.Interface | 01.IP - Intel Product | Order create 4B3 - Consignment Issue | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_697_IP_Order%20create%204B3%20-%20Consignment%20Issue.pptx?d=w200523f96fb147e3a94e36ec77708d0f&csf=1&web=1&e=KLLxGf | 02.No | 01.Yes | OTCE0443 | 2024-06-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2024-08-12 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-29 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-02 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-05-16 | 100% | 2025-05-16 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-05 | 2025-01-27 | 2025-04-28 | 2025-04-28 | 100% | 2025-04-28 | 2025-03-05 | 2025-04-28 |  | 2025-06-27 | 2025-07-16 | 2025-08-01 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-01 | 2025-08-01 | N | 100% | 2025-09-01 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-04-28 | 2025-04-28 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0414 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-05-16 |  | 2025-05-16 |  | 2025-03-21 | 2025-03-05 | 2025-03-05 |  | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-03-05 | 2025-04-28 |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 |  |  |  |  | B2B - OpenText | 2024-09-13 | 2025-01-31 | 2025-01-24 | MW | 2025-07-25 |  |  |  | 0 | 03. IP Customers | 2038 | [9 empty] | 9/1: FUT sent for approval | 2025-04-28 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1580 | OTCI0413 | 02.Interface | 01.IP - Intel Product | WOM users should be able to verify/simulate orders details before submitting the order from WOM for S4 (IP)​ and receive the verify response from S4 HANA. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_750_IP_Enable%20WOM-Order%20Verification%20%26%20Simulation.pptx?d=w501fe30988e241289f2d9601fc708c75&csf=1&web=1&e=N8GZjM | 02.No | 01.Yes |  | 2024-06-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | WOM | S/4 | MULESOFT | 2024-07-29 | 2024-09-06 | 2024-09-06 | 100% | 2025-01-17 | 2025-05-02 | 2025-05-09 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-02 | 2025-06-13 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-02 | 2025-06-13 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-25 | 100% | 2025-08-04 | 2025-05-26 | 2025-06-24 | 2025-06-24 | 100% | 2025-06-24 | 2025-08-04 | 2025-08-04 |  | 2025-08-08 | 2025-09-05 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-06-24 | 2025-06-24 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0413 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2025-01-17 | 2025-01-17 | 2025-01-17 |  | 2025-03-21 | 2025-05-09 | 2025-03-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-08-04 | 2025-08-04 |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | [5 empty] | 2024-09-06 | 2025-06-13 | 2025-05-16 | S4 | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 1738 | [7 empty] | 4. Completed | 1. Approved no action | 01/05: FUT approved 12/23: defect 5536 fixed and ready for re-testing 2/18 : Defect 5697, 5744 to be fixed and retesting is in progress. Bapp testing planned tomorrow 12/16:5697 - ETA 12/17 Defect 5652 with Tech team. ETA - 12/16. PO line item and Ship to PO line item not populated correctly in Bulk order 12/11:Defect 5204 reopened ETA 12/12 12/8:BAPP have issues in UI-Hence testing is blocked. WOM team working on the same. ETA 12/9 EOD 12/3:BAPP Testing completed. FUT on track to send for approval 12/4 12/2: A common issue is raised today impacting all interface responses. Multiple OTC interfaces impacted . Defect being created.Due to this BAPP testing is not performed today which was planned .ETA to fix this is 12/2 EOD 11/28: Unable to retest defect fixes as BAPP Side UI is encountered with i ssues. ETA for retest with BAPP 12/2 11/25: Unable to retest defect fixes as BAPP Side UI is encountered with issues. Issues to resolve the same is 11/26 Note: Defect 4333 fixes were reopened on 11/21 and as of 11/25 all fixes are completed 11/21:4333 defect was fixed. But in retesting reopened.ETA to re fix - 11/21 EOD 11/17:Defect 4333 , MW Defect 4560 ,4580 11/14 - Defect 4333 and MW Defect 4324. ETA from Tech & MW is 11/14. FUT completion is 11/19 11/11: Defect 4324(Tech), 4333 (Tech).ETA 11/11 11/4:defect 2999 -MW in fix 10/30:Defect retest of 2999 with MW Team in progress 10/23 - Defect 2833 is WIP. ETA is 10/23 10/17: defect 2833 and 2999 10/10:At risk for completion due to defects 2833(Tech),2999(MW) 10/6: 2833 fixed. Re-testing is in progress | 2025-06-24 | N | 05. OTC IP |  |  |  |  | ETA 1126 Defect 4333 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 572 | OTCI0298 | 02.Interface | 01.IP - Intel Product | Enable capture of changes on the Return Request from Salesforce into relevant Return Order in S/4 | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Interface%20from%20SF%20to%20S4%20Order%20Change.pptx?d=w91b28e8e48614b0296d6cddf75d2bc48&csf=1&web=1&e=sFuqn6 | 02.No | 01.Yes | OTCE0575 | 2024-06-07 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 36446 | Return For Credit | SalesForce | S/4 | MULESOFT | 2024-09-23 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2024-12-16 | 2025-07-15 | 2025-09-10 | 100% | 2025-09-10 | 2025-02-24 | 2025-09-30 | 2025-09-30 | 100% | 2025-10-07 | 2025-04-21 | 2025-12-21 | 2025-12-21 | 100% | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2025-03-21 | 2025-04-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-04-04 | 2025-04-04 | N | 100% | 2025-11-27 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-30 | 2025-12-21 | 2025-12-21 | pgaroo@deloitte.com | 2024-06-07 06:50 | cell-link@smartsheet.com | 2026-04-01 15:16 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0298 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2025-11-27 | 2025-11-27 | 2025-11-27 |  |  |  |  | Return for Credit | 2024-11-01 | 2025-02-21 | 2025-01-24 | MW | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 2052 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/25:Awaiting approval 11/21:FUT Sent for approval 11/17: FUT sent for approval 11/14 - 2 Defects (4494 (ETA is 11/14), 4256 - Requires SAP OSS Note Implementation). FUT ETA is 11/26 11/11:Defect 4256, 4400 under fix. Expected ETA 11/12 EOD 11/6:Defect Under Fix 4256 11/4:FUT In progress -Will send for approval 11/4 | 2025-12-21 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-02-21 | 2025-02-17 | Yes | BAPP Config for new Sales Area, Plants | Yes | Regression Testing Only | No |  | 2026-02-16 | 2026-03-20 | Yes | BAPP Config | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 144 | OTCI0296 | 02.Interface | 01.IP - Intel Product | Enable EDI : Billing Output Generation | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1FE52019-9860-49FE-8686-386FAACCE9ED%7D&file=Billing_Console_IPG-BR-130-210_EDI.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-04 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-07-29 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-01-27 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-05-16 | 100% | 2025-05-16 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-06 | 2025-01-27 | 2025-04-23 | 2025-04-23 | 100% | 2025-04-23 | 2025-03-06 | 2025-04-23 |  | 2025-07-11 | 2025-08-01 | 2025-08-01 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-28 | 2025-08-01 | 2025-08-01 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-04-23 | 2025-04-23 | pgaroo@deloitte.com | 2024-06-04 07:05 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 1 | 1.45 | 0296 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-05-16 |  | 2025-05-16 |  | 2025-03-21 | 2025-03-06 | 2025-03-06 |  | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-03-06 | 2025-04-23 |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 |  |  |  |  | B2B - OpenText | 2024-09-13 | 2025-01-31 | 2025-01-24 | MW | 2025-08-01 |  |  |  | 0 | 03. IP Customers | 1486 | [9 empty] | 8/25: Sent for approval | 2025-04-23 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 571 | OTCI0294 | 02.Interface | 01.IP - Intel Product | Inbound interface between Sales Force and S4 needed to create Return Order for Intel Products | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Interface%20from%20SF%20to%20S4%20Order%20Create.pptx?d=w6cb957ad8c244abf8111dc1197e50f4a&csf=1&web=1&e=dCsi47 | 02.No | 01.Yes | OTCE0575 | 2024-06-05 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 36446 | Return For Credit | SalesForce | S/4 | MULESOFT | 2024-08-12 | 2024-09-06 | 2024-09-06 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-08-20 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-09 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-09 | 2024-12-16 | 2025-07-15 | 2025-09-10 | 100% | 2025-09-10 | 2025-02-24 | 2025-09-30 | 2025-09-30 | 100% | 2025-10-07 | 2025-04-21 | 2025-12-21 | 2025-12-21 | 100% | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2025-03-21 | 2025-04-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-04-04 | 2025-04-04 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-30 | 2025-12-21 | 2025-12-21 | pgaroo@deloitte.com | 2024-06-04 07:05 | cell-link@smartsheet.com | 2026-04-01 15:16 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0294 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | 2025-02-09 | 2025-02-21 | 2025-02-09 | 2025-02-09 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | Return for Credit | 2024-09-06 | 2025-02-21 | 2025-01-24 | MW | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 2051 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4:awaiting approval 10/23 - Sent for approval 10/17: Defects 3488, 3615 10/10:Blocked by BAPP Defects and also S4 Defect 3488 10/6: New defect : 3488 identified. Pending with Tech team11/4: | 2025-12-21 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-02-21 | 2025-02-09 | Yes | BAPP Config for new Sales Area, Plants | Yes | Regression Testing Only | No |  | 2026-02-16 | 2026-03-20 | Yes | BAPP Config | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 622 | OTCI0291 | 02.Interface | 01.IP - Intel Product | Outbound Interface from S4 to Salesforce to update the Return Order status in Salesforce | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Interface%20from%20S4%20to%20SF%20for%20Order%20Status.pptx?d=w95fb7dad2cfb47d8959f0442563037b5&csf=1&web=1&e=MowAcx | 02.No | 01.Yes |  | 2024-06-05 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 36446 | Return For Credit | S/4 | SalesForce | MULESOFT | 2024-08-12 | 2025-02-07 | 2025-03-14 | 100% | 2025-03-14 | 2025-08-18 | 2025-08-22 | 2026-01-07 | 100% | 2025-12-18 | 2025-04-04 | 2025-04-18 | 2025-09-05 | 100% | 2025-09-23 | 2025-04-04 | 2025-04-18 | 2025-09-05 | 100% | 2025-09-23 | 2025-03-24 | 2025-07-17 | 2025-09-10 | 100% | 2025-09-10 | 2025-04-21 | 2025-09-30 | 2025-09-30 | 100% | 2025-10-07 | 2025-05-19 | 2025-12-21 | 2025-12-21 | 100% | 2026-01-05 | 2025-10-07 | 2026-01-05 |  | 2025-10-03 | 2025-10-10 | 2025-10-31 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-10-31 | 2025-10-31 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-30 | 2025-12-21 | 2025-12-21 | pgaroo@deloitte.com | 2024-06-04 07:05 | cell-link@smartsheet.com | 2026-04-01 01:51 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0291 |  | R3 ITC1 | [6 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-10-07 | 2026-01-05 |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 |  |  |  |  | Return for Credit | 2025-02-07 | 2025-04-18 | 2025-04-18 | MW | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 1591 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/6:Awaiting final approval 01/05: All opens closed. Awaiting final approval 12/24:All opens closed. Awaiting final approval 12/23:Defect 5846 ETA 12/23. Defect and All the FUT opens are closed. Walkthrough call will be scheduled on 5th Jan as no was available on 22nd Dec. Kim suggested to have it on 5th Jan. 12/18: Defects fixed-resent for approval 12/11;Defect 3765, 4590 Reoepned .ETA TBD 12/9:Awaiting approval 12/8:Awaiting approval 12/4: Defect: 4789 fixed. FUT is in progress 12/3:4590 Fixed 4789 in fix ETA 12/3 EOD 12/2:Defect 4590 , 4789 under fix. The fixes done are not working 11/28:Defects 4590, 4789,4905,3765 in progress 11/25:FUT Defects 4590, 4789, 4905 11/21:FUT defects 4590,4763,4789 11/17:Defect 3765, 4590 11/14 - Defect 3765. ETA is 11/14. FUT ETA is 11/21 11/11 - Defect 3765. ETA is 11/4:Fix 3765 in progress 10/30 : Defect 3765 fix in progress 10/22: defect 3765 | 2025-12-21 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | Yes |  | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 156 | OTCI0258 | 02.Interface | 01.IP - Intel Product | Enable EDI 855 – Order Acknowledgment to B2B customer | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_Console%20ID%20154_Enable%20EDI%20855.pptx?d=wde399b6b04164eb5b80c647a06e40b66&csf=1&web=1&e=lWPpMR | 02.No | 01.Yes |  | 2024-05-24 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-06-24 | 2024-08-09 | 2024-08-09 | 100% | 2024-07-26 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2025-02-24 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-04 | 2025-02-24 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-04 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-08-19 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-04 | 2025-04-11 |  |  | 2024-10-25 | 2025-01-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-01 | 2025-07-25 | 2025-01-10 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-03-21 | 2025-04-11 | 2025-04-11 | pgaroo@deloitte.com | 2024-05-23 23:15 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 | OTCI0276 | 03.Medium | 0.3 | 0.435 | 0258 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-26 | 2024-08-09 | 2024-07-26 |  | 2024-08-23 | 2024-08-23 |  |  | 2025-03-04 | 2025-03-21 | 2025-03-04 | 2025-03-04 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-03-04 | 2025-04-11 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 |  |  |  |  | B2B - OpenText | 2024-08-09 | 2025-03-21 | 2024-10-25 | S4 | 2025-01-10 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1487 | [7 empty] | 1. On Track | 17. FUT In progress | 1/8: Defect 6099 to be fixed by MW. 1/6:all defects fixed and retested. FUT Resumed. sending for approval by 1/8 01/05: defect 4971 with tech team 12/23:4971 Under fix 12/22:4971 Under fix 12/18: defect 4971 in retesting with BAPP 12/11:Defect 4971 -ETA 12/12 EOD 12/9:Defect 4971 - 11 issues pending . ETA 12/10 EOD 12/8:Defect 4971 -ETA 12/8 To send FUT for approval 12/2:Defect 3968, 4971 in progress. ETA 12/4 11/28:Defect 3968, 4971 in progress. ETA 12/4 11/25: Defect 3968 in progress . ETA - 12/4 11/21:Defect 3968n.ETA To fix is 11/28 11/17:Defect 3968 11/14 - Defect 3968. Tech ETA is 11/18. FUT completion by 11/21 11/13 EP: Provide update on Defect 3968 & FUT end date 11/11:Defect 3968 under fix. ETA 11/12 11/06 EP: Provide ETA for Defect 3968 fix / FUT completion 11/6:Defect needed Nitesh help. Which a delay seen in between | 2025-04-11 | N | 05. OTC IP |  |  |  |  | Defect 3968. Complex object. CR67. Ravi/Shripad to deep dive and align on strategy to close. |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 12 |  | 2025-03-21 | 2025-03-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 157 | OTCI0257 | 02.Interface | 01.IP - Intel Product | Enable EDI 865 – Order change acknowledgment to B2B customer | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_Console%20ID%20155_Enable%20EDI%20865.pptx?d=w788575f086e8404c9eb44a80e082223b&csf=1&web=1&e=lvywSu | 02.No | 01.Yes |  | 2024-05-24 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-07-15 | 2024-08-09 | 2024-08-09 | 100% | 2024-07-26 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2025-02-24 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-04 | 2025-02-24 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-04 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-08-19 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-04 | 2025-04-11 |  |  | 2024-11-01 | 2025-01-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-28 | 2025-08-08 | 2025-01-10 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-03-21 | 2025-04-11 | 2025-04-11 | pgaroo@deloitte.com | 2024-05-23 23:15 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 | OTCI0275 | 03.Medium | 0.3 | 0.435 | 0257 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-26 | 2024-08-09 | 2024-07-26 |  | 2024-08-23 | 2024-08-23 |  |  | 2025-03-04 | 2025-03-21 | 2025-03-04 | 2025-03-04 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-03-04 | 2025-04-11 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 |  |  |  |  | B2B - OpenText | 2024-08-09 | 2025-03-21 | 2024-10-25 | S4 | 2025-01-10 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1488 | [7 empty] | 4. Completed | 1. Approved no action | 1/8: Awaiting approval 1/6: Awaiting approval 01/05: Sent for approval 12/23: Sent for approval 12/18: Sent for approval 12/16:Defect 5476 ETA 12/16 EOD 12/11:awaiting intel approval 12/9:Sent for approval 12/8:Defect 4971 -ETA 12/8 To send FUT for approval 12/2:Defect 3968, 4971 in progress. ETA 12/4 11/28:Defect 3968, 4971 in progress. ETA 12/411/25: Defect 3968 in progress . ETA - 12/4 11/21:Defect 3968n.ETA To fix is 11/28 11/17:Defect 3968 11/14 - Defect 3968. Tech ETA is 11/18. FUT completion by 11/21 11/13 EP: Provide update on Defect 4377 & FUT end date 11/11:Defect 4377, 3968 ETA 11/12 11/06 EP: Provide ETA for Defect 3968 fix / FUT completion 11/6:Defect needed Nitesh help. Which a delay seen in between | 2025-04-11 | N | 05. OTC IP |  |  |  |  | Defect 3968. Complex object. CR67. Ravi/Shripad to deep dive and align on strategy to close. |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-03-21 | 2025-03-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 138 | OTCI0085 | 02.Interface | 01.IP - Intel Product | Outbound Interface from S4HANA to WOM to Share order confirmation data | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console%20ID_138_IPG_Outbound_Interface%20to%20support%20WOM%20Dashboard%20where%20customer%20can%20efficiently%20manage%20and%20track%20their%20submitted%20orders_.pdf?csf=1&web=1&e=WQBc0q | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-07-11 | 2024-08-07 | 2024-08-07 | 100% | 2024-08-01 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-07 | 2025-01-27 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-03-07 | 2025-05-28 | 2025-05-28 | 100% | 2025-05-28 | 2025-03-21 | 2025-05-28 |  |  | 2025-05-09 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-21 | Not Applicable | R3 Build & UT Sprint 20 | 2025-02-21 | 2025-05-28 | 2025-05-28 | pgaroo@deloitte.com | 2024-04-19 04:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 2 | 2.9 | 0085 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-08-01 | 2024-08-07 | 2024-08-01 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | 2025-03-21 | 2025-05-28 |  |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | [5 empty] | 2024-08-07 | 2025-01-31 | 2025-01-24 | MW | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2000 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/17 - Intel Feedback in progress. No open defects. FUT Approval by 11/19 11/11:FUT Defect 4218 under MW 11/4:BAPP Test in progress 10/24:3878 Defect fix in progress ETA 10/30 EOD 10/23 - S4 testing in progress. B-App testing is next week. 10/17: Defect 3786 10/10:FUT Defect 3449 Under fix 9/12 :Defect:2763 : This is a minor change - Amar to Prioritize this today as this is one of the "On track List" | 2025-05-28 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 132 | OTCI0082 | 02.Interface | 01.IP - Intel Product | Interface between MyDeals and S4 needed for pricing feeds | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console%20ID_132_IP_MyDeals%20to%20S4%20interface.pdf?csf=1&web=1&e=WfNS4b | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 14464 | My Deals | MyDeals | S/4 | MULESOFT | 2024-06-11 | 2024-07-11 | 2024-07-11 | 100% | 2024-07-26 | 2024-10-25 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-01-31 | 100% | 2025-01-08 | 2024-11-18 | 2024-12-13 | 2025-01-31 | 100% | 2025-01-08 | 2024-11-22 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-29 | 2024-11-18 | 2024-12-13 | 2024-12-20 | 100% | 2025-01-17 | 2025-04-07 | 2025-07-15 | 2025-07-15 | 100% | 2025-07-15 | 2025-01-17 | 2025-07-15 |  |  | 2025-02-21 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-13 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-13 | 2025-07-15 | 2025-07-15 | pgaroo@deloitte.com | 2024-04-19 04:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 2 | 2.9 | 0082 | INT-CR0126 | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-08 |  | 2024-11-29 |  | 2024-11-29 |  | 2025-01-17 | 2025-01-17 | 2025-01-17 |  | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-01-17 | 2025-07-15 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2024-07-11 | 2024-12-13 | 2024-11-29 | MW | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 2793 | [9 empty] | 9/1: FUT sent for approval | 2025-07-15 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-01-31 | 2025-01-08 | Yes | ZPARAMS entries for the new Sales Org | Yes | Regression Testing Only | No |  | 2026-02-09 | 2026-03-06 | Yes | BAPP Config | 2026-02-09 | 2026-03-09 | 2026-03-09 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 131 | OTCI0081 | 02.Interface | 01.IP - Intel Product | Interface between IPAR and S4 needed for pricing feeds | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console%20ID_131_IP_Interface%20between%20IPAR%20and%20S4%20needed%20for%20pricing%20records%20for%20Intel%20Products.pdf?csf=1&web=1&e=a5LCUO | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 353 | Intel Price Administration and Reporting | IPAR | S/4 | MULESOFT | 2024-06-11 | 2024-07-11 | 2024-07-11 | 100% | 2024-07-22 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-09-20 | 2024-12-16 | 2025-01-24 | 2024-11-01 | 100% | 2024-11-01 | 2024-12-16 | 2025-01-24 | 2024-11-01 | 100% | 2024-11-01 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-10-18 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2025-04-23 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2024-11-26 | 2025-05-09 |  |  | 2025-02-21 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-13 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-24 | 2025-05-09 | 2025-05-09 | pgaroo@deloitte.com | 2024-04-19 04:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0081 | INT-CR0126 | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-09-20 | 2024-09-20 | 2024-09-20 |  | 2024-11-01 | 2025-01-24 |  |  |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2024-11-26 | 2025-05-09 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  |  |  |  | Vistex/Rebates & Customer Agreements | 2024-07-11 | 2025-01-24 | 2024-10-25 | MW | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 2792 | [7 empty] | 1. On Track | 3. Awaiting Approval | 9/12: Approved | 2025-05-09 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 13 |  | 2025-01-24 | 2024-11-01 | Yes | ZPARAMS entries for the new Sales Org | Yes | Regression Testing Only | No |  | 2026-02-09 | 2026-03-06 | No | BAPP Config |  |  |  |  | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 125 | OTCI0061 | 02.Interface | 01.IP - Intel Product | Enable WOM - Order Change | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20WOM%20-%20Order%20Change.pdf?csf=1&web=1&e=AKEA7E | 02.No | 01.Yes | OTCE0443 | 2024-04-10 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | Commerce Cloud | S/4 | MULESOFT | 2024-05-20 | 2024-06-15 | 2024-06-11 | 100% | 2024-06-21 | 2024-06-17 | 2024-06-21 | 2025-02-21 | 100% | 2025-02-17 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-09-20 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-16 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-30 | 2024-10-19 | 2025-05-30 |  |  | 2025-02-21 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-30 | 2025-03-21 | 2025-03-14 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2024-10-11 | 2025-05-30 | 2025-05-30 | jenoronha@deloitte.com | 2024-04-09 11:07 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 4 | 5.8 | 0061 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-09-27 |  | 2024-09-27 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2024-10-19 | 2025-05-30 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-06-15 | 2024-10-11 | 2024-09-27 | S4 | 2025-11-21 |  |  |  | 0 | 08. Not Applicable | 1530 | [7 empty] | 4. Completed | 1. Approved no action | 1/8: Defect 6097 need to fix. 01/05: Sent for Intel approval 1/6:Open defects fixed. Awaiting approval 12/23:Sent for Intel approval 12/24:Defect 5908 .ETA 12/24 12/22:Sent for Intel approval 12/18 : Defect 5697, 5744 to be fixed and retesting is in progress. Bapp testing planned tomorrow 12/16:5697 - ETA 12/17 Defect 5652 with Tech team. ETA - 12/16. PO line item and Ship to PO line item not populated correctly in Bulk order 12/11:Defect 5204 reopened ETA 12/12 12/8:BAPP have issues in UI-Hence testing is blocked. WOM team working on the same. ETA 12/9 EOD 12/3:BAPP Testing completed. FUT on track to send for approval 12/4 12/2: A common issue is raised today impacting all interface responses. Multiple OTC interfaces impacted . Defect being created.Due to this BAPP testing is not performed today which was planned .ETA to fix this is 12/2 EOD 11/28: Unable to retest defect fixes as BAPP Side UI is encountered with i ssues. ETA for retest with BAPP 12/2 11/25: Unable to retest defect fixes as BAPP Side UI is encountered with issues. Issues to resolve the same is 11/26 Note: Defect 4333 fixes were reopened on 11/21 and as of 11/25 all fixes are completed 11/21:4333 defect was fixed. But in retesting reopened.ETA to re fix - 11/21 EOD 11/17:Defect 4333 , MW Defect 4560 ,4580 11/14 - Defect 4333 and MW Defect 4324. ETA from Tech & MW is 11/14. FUT completion is 11/19 11/11: Defect 4324(Tech), 4333 (Tech).ETA 11/11 11/4:defect 2999 -MW in fix 10/30:Defect retest of 2999 with MW Team in progress 10/23 - Defect 2833 is WIP. ETA is 10/23 10/17: defect 2833 and 2999 10/10:At risk for completion due to defects 2833(Tech),2999(MW) 10/6: 2833 fixed. Re-testing is in progress | 2025-05-30 | Y | 05. OTC IP |  |  |  |  | ETA 1126 Defect 4333 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2024-10-19 | 2024-10-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 126 | OTCI0060 | 02.Interface | 01.IP - Intel Product | Enable EDI - Order Change | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20EDI%20-%20Order%20Change.pdf?csf=1&web=1&e=Pz2YiS | 02.No | 01.Yes | OTCE0443 | 2024-04-10 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2024-05-20 | 2024-06-12 | 2024-06-12 | 100% | 2024-06-21 | 2024-06-21 | 2024-06-28 | 2024-06-28 | 100% | 2024-06-26 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-09-20 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2024-08-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-01 | 2024-07-01 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-11 | 2024-10-19 | 2025-04-11 |  |  | 2024-10-25 | 2025-02-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-28 | 2025-08-08 | 2025-02-14 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2024-10-11 | 2025-04-11 | 2025-04-11 | jenoronha@deloitte.com | 2024-04-09 11:07 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 2 | 2.9 | 0060 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-06-26 | 2024-06-28 | 2024-06-26 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-09-27 |  | 2024-09-27 |  | 2024-10-01 | 2024-10-01 | 2024-10-01 |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2024-10-19 | 2025-04-11 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  |  |  |  | B2B - OpenText | 2024-06-12 | 2024-10-11 | 2024-09-27 | S4 | 2025-11-07 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1531 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/23 - Defect 3684 with performance issue. 10/17: defect 3684 10/16 EP: Defect 3508 Update & Update FUT Revised End date | 2025-04-11 | N | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 12 |  | 2024-10-19 | 2024-10-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 128 | OTCI0058 | 02.Interface | 01.IP - Intel Product | Enable MySamples - Sample Order Change | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20MySamples%20-%20Sample%20Order%20Change.pdf?csf=1&web=1&e=u3gdh8 | 02.No | 01.Yes | OTCE0443 | 2024-04-10 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 11565 | My Samples ( Future of Samples) | MySamples | S/4 | MULESOFT | 2024-06-10 | 2024-07-11 | 2024-07-11 | 100% | 2024-07-18 | 2024-08-09 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-22 | 2024-10-04 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-09-13 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-19 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-03-03 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2024-11-26 | 2025-03-21 |  |  | 2024-10-18 | 2024-10-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-07 | 2024-10-25 | 2024-10-25 | N | 100% | 2024-11-15 | Not Applicable | R3 Build & UT Sprint 7 | 2024-10-25 | 2025-03-21 | 2025-03-21 | jenoronha@deloitte.com | 2024-04-09 11:07 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0058 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2024-11-26 | 2025-03-21 |  |  | 2024-11-15 | 2024-11-15 | 2024-11-15 |  |  |  |  | SMG Apps | 2024-07-11 | 2024-10-11 | 2024-10-25 | MW | 2024-10-25 |  |  |  | 0 | 08. Not Applicable | 2790 | [10 empty] | 2025-03-21 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2024-10-19 | 2024-10-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 98 | OTCI0040 | 02.Interface | 01.IP - Intel Product | Enable MySamples - Sample Order Create | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20MySamples%20-%20Sample%20Order%20Create.pdf?csf=1&web=1&e=eW498D | 02.No | 01.Yes | OTCE0443 | 2024-04-05 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 11565 | My Samples ( Future of Samples) | MySamples | S/4 | MULESOFT | 2024-06-10 | 2024-07-11 | 2024-07-11 | 100% | 2024-07-18 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-22 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-19 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-19 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-09-27 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-02-03 | 2025-03-14 | 2025-03-14 | 100% | 2025-03-14 | 2024-11-26 | 2025-03-14 |  |  | 2025-03-21 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-04-11 | 2025-04-11 | N | 100% | 2025-04-21 | Not Applicable | R3 Build & UT Sprint 13 | 2024-10-25 | 2025-03-14 | 2025-03-14 | pgaroo@deloitte.com | 2024-04-05 06:53 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0040 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 |  | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2024-11-26 | 2025-03-14 |  |  | 2025-04-21 | 2025-04-21 | 2025-04-21 |  |  |  |  | SMG Apps | 2024-07-11 | 2024-10-04 | 2024-10-25 | MW | 2026-02-06 |  |  |  | 0 |  | 1526 | [10 empty] | 2025-03-14 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2024-10-19 | 2024-10-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 29 | OTCI0038 | 02.Interface | 01.IP - Intel Product | Enable EDI - Order Create | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20EDI%20-%20Order%20Create.pdf?csf=1&web=1&e=q54Eom | 01.Yes | 01.Yes | OTCE0441 | 2024-04-05 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2024-05-06 | 2024-06-12 | 2024-06-12 | 100% | 2024-06-21 | 2024-11-22 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-27 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2024-11-29 | 100% | 2024-11-29 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-14 | 2025-01-07 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-11 | 2025-02-14 | 2025-04-11 |  | 2025-08-22 | 2025-09-05 | 2025-10-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-03 | 2025-10-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-02-21 | 2025-04-11 | 2025-04-11 | pgaroo@deloitte.com | 2024-04-02 03:11 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 2 | 2.9 | 0038 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-11-27 | 2024-11-29 | 2024-11-27 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-01-24 |  | 2024-11-29 |  | 2025-02-21 | 2025-02-14 | 2025-02-14 |  | 2025-04-11 | 2025-04-11 | 2025-04-11 | 2025-02-14 | 2025-04-11 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  |  | B2B - OpenText | 2024-06-12 | 2025-01-31 | 2025-01-24 | MW | 2025-10-03 |  |  |  | 0 | 03.5 Both IF and IP Customers | 1431 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/4: defect re-opened. 4972 12/2:Issues are addressed FUT Sent for approval on 12/2 11/28:Defect 4972 fix in progress. ETA 11/26 EOD 11/25: The retest of Defect 3684 completed. An open from OTCE0641 was added in this FUT for dropship scenario. The BAPP Testing for the same is in progress. ETA 11/26 11/21: Defect 3684 addressed. Now testing a scenario Business mentioned (which as asked as part of OTCE0641) 11/17 - Defect 3684. ETA from Tech is 11/18. FUT completion ETA is 11/20 11/13 EP: Provide revised FUT due date 11/11:3684 Cause identified. Fix in Progress ETA 11/13 11/6:Delayed defect fix due to Prioritization | 2025-04-11 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 25 | OTCI0037 | 02.Interface | 01.IP - Intel Product | Enable WOM - Order Create | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20WOM%20-%20Order%20Create.pdf?csf=1&web=1&e=q9hz20 | 02.No | 01.Yes | OTCE0443 | 2024-04-05 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | Commerce Cloud | S/4 | MULESOFT | 2024-05-06 | 2024-05-21 | 2024-05-21 | 100% | 2024-06-21 | 2024-06-12 | 2024-06-19 | 2024-06-19 | 100% | 2024-06-19 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-05 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-05 | 2024-09-20 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2024-09-06 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-16 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-30 | 2024-10-05 | 2025-05-30 |  |  | 2024-10-18 | 2024-12-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-07 | 2024-11-01 | 2024-12-06 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2024-10-04 | 2025-05-30 | 2025-05-30 | pgaroo@deloitte.com | 2024-04-02 03:08 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-18 | 01.S4 |  |  | 4 | 5.8 | 0037 |  | R3 ITC1 |  |  |  |  | 05. Fully custom API |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-06-19 | 2024-06-19 |  |  | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 |  | 2024-09-27 |  | 2024-09-27 |  | 2024-10-04 | 2024-10-01 | 2024-10-01 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2024-10-05 | 2025-05-30 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2024-05-21 | 2024-10-04 | 2024-09-27 | S4 | 2024-11-01 |  |  |  | 0 | 08. Not Applicable | 1428 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/19:Awaiting Intel approval, one scenario validation from UI is pending. WOM Planned to test it on Monday 12/22 and close it 12/18: 12/11:awaiting intel approval 12/16: 12/11:awaiting intel approval 12/11:awaiting intel approval 12/9:Awaiting Intel approval 12/4:12/8:Awaiting approval 12/3:BAPP Testing completed. FUT on track to send for approval 12/4 12/2: A common issue is raised today impacting all interface responses. Multiple OTC interfaces impacted . Defect being created.Due to this BAPP testing is not performed today which was planned .ETA to fix this is 12/2 EOD 11/28: Unable to retest defect fixes as BAPP Side UI is encountered with i ssues. ETA for retest with BAPP 12/2 11/25: Unable to retest defect fixes as BAPP Side UI is encountered with issues. Issues to resolve the same is 11/26 Note: Defect 4333 fixes were reopened on 11/21 and as of 11/25 all fixes are completed 11/21:4333 defect was fixed on 11/20. But in retesting reopened.ETA to re fix - 11/21 EOD 11/17:Defect 4333 , MW Defect 4560 ,4580 11/14 - Defect 4333 and MW Defect 4324. ETA from Tech & MW is 11/14. FUT completion is 11/19 11/11: Defect 4324(Tech), 4333 (Tech).ETA 11/11 11/4:defect 2999 -MW in fix 10/30: Defect retest of 2999 and Defect fix for 3989 10/23 - Defect 2833 is WIP. ETA is 10/23 10/17: Defect 2833 2999 10/10:At risk for completion due to defects 2833(Tech),2999(MW) 10/10:At risk for completion due to defects 2833(Tech),2999(MW) 10/6: 2833 fixed. Re-testing is in progress | 2025-05-30 | Y | 05. OTC IP |  |  |  |  | ETA 1126 Defect 4333 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2024-10-05 | 2024-10-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3196 | OTCF1714 | 05.Form | 01.IP - Intel Product | Intel Federal Form for Progress Pay (Output type SF1443) | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30206200-EE34-4D25-BEC3-6D5D6036FF06%7D&file=BR-130-060%20Billing%20Revenue%20IFL%20Form%20for%20Progress%20Pay.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-25 | N | 100% | 2026-03-20 |  | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2026-01-27 01:26 | abvasu@deloitte.com | 2026-03-20 05:35 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 1714 | INT-CR1609 | R3 ITC1 | [6 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-25 | 2026-03-20 | [5 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-04 |  |  |  | 0 |  | 3412 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 3/13:FUT under approval 3/11:FUT Sent for approval 3/6:FUT In progress 2/19: Awaiting Development completion - Tech ETA - 2/27 2/12: Awaiting Development completion 2/10: Awaiting Development completion | 2026-02-27 | Y | 05. OTC IP |  |  |  | 03/11: Awaiting Approval Current status: FUT completed. Awaiting Approval Issue: FUT delayed Next steps: N/A Help needed: N/A FUT ETA: 03/13 |  | 3. Watch item | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3098 | OTCF1629 | 05.Form | 01.IP - Intel Product | Returns Credit Memo Output item level consolidation | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_3098_OTC_RICEFW%20Intake%20Form_Returns%20Credit%20Memo%20Output%C2%A0item%20level%20consolidation.pptx?d=we1f2f2bef24f4c34bd0a272f1dfa2700&csf=1&web=1&e=WeRG3p | 02.No | 01.Yes |  | 2025-11-04 | Shelly Lafree | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-10-31 | 2025-10-31 | 100% | 2025-11-11 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 |  |  | 2025-12-19 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-30 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-28 03:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-04 | 01.S4 |  |  | 1 | 0.69 | 1629 | INT-CR0300 | R3 ITC1 | [6 empty] | 2025-11-11 | 2025-11-11 | 2025-11-11 |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | [5 empty] | 2025-10-31 | 2025-12-05 |  |  | 2026-01-30 |  |  |  | 0 |  | 3308 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/29:Awaiting approval 1/27:Awaiting approval 1/22:Awaiting approval 1/20:sent for approval 1/14: Defect "6246, 6259 " to be fixed by Tech team 1/8:Defect 6122 - Due to MX developer unavailability -Re assigned USI developer .ETA 1/13 1/6:Defect 5396 - Due to MX developer unavailability -Re assigned USI developer .ETA 1/13 01/05: Defect 5396 .ETA TBD. Impacting the customer Forms as well 12/24:Defect 5396 .ETA TBD. Impacting the customer Forms as well 12/23:Defect 5396 .ETA TBD.MX Team help needed 12/18:Defect 5396 .ETA TBD.MX Team help needed | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2105 | OTCF0681_IP | 05.Form | 01.IP - Intel Product | Form development for Intercompany Invoice. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/BR-130-150%20Billing%20Revenue-Process%20Customer%20Invoice%20INTERCOMPANY.pptx?d=w0953b19a0a744d2d92463fe4b405f177&csf=1&web=1&e=RKhhLP | 01.Yes | 01.Yes |  | 2024-09-30 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-10-21 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2025-02-14 | 100% | 2025-02-09 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | [15 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-06-27 | 2025-06-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-30 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2024-10-04 | 01.S4 |  |  | 2 | 1.38 | 0681 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-09 | 2024-12-09 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-03-08 | 2025-03-08 | 2025-03-08 | 2025-03-08 | [12 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-06 | 2025-02-21 |  |  | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 2274 | [10 empty] | 2025-02-21 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-08 | 2025-03-08 | Yes | BAPP Config to add LE 100 | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2105 | OTCF0681_IF | 05.Form | 02.IF - Intel Foundry | Form development for Intercompany Invoice. | 04. OTC IF | 4.3 OTC IF - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/BR-130-150%20Billing%20Revenue-Process%20Customer%20Invoice%20INTERCOMPANY.pptx?d=w0953b19a0a744d2d92463fe4b405f177&csf=1&web=1&e=RKhhLP | 01.Yes | 01.Yes |  | 2024-09-30 | Jill Matalon | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-10-21 | 2024-11-22 | 2024-11-22 | 100% | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2025-02-14 | 100% | 2025-02-09 | 2025-02-14 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | 2025-02-14 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | [15 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-05-16 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-30 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-07 | 01.S4 | OTCF0681_IP | 02.High | 0.4 | 0.276 | 0681 |  | R3 ITC1 | [6 empty] | 2024-12-09 | 2024-12-09 | 2024-12-09 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-03-08 | 2025-03-08 | 2025-03-08 | 2025-03-08 | [12 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-11-22 | 2025-02-21 |  |  | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 2273 | [10 empty] | 2025-02-21 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-08 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2161 | OTCF0680 | 05.Form | 01.IP - Intel Product | Process IFL Customer Invoice | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/BR-130-150%20Billing%20Revenue%20IFL%20Cost%20Invoice%20Form.pptx?d=w3195dff37d5f4bd69eb0c80dbd1322eb&csf=1&web=1&e=Fye3V1 | 01.Yes | 01.Yes |  | 2024-09-30 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-19 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 0.69 | 0680 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-17 |  | Federal |  | 0 | 08. Not Applicable | 1600 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 12/4: 4519 defect fixing required. 12/2:Dassian POC is back on 12/1 and testing is resumed .FUT In progress ETA 12/5 11/28: The form should be validated by Dassian team for the fixes performed. Dassian unavailable till 12/1 11/25: The form should be validated by Dassian team for the fixes performed. Dassian unavailable till 12/1 11/21: Dassian support needed with 4519 test.To be followed up in US hours 11/17:Defect 4519 | 2025-11-05 | N | 05. OTC IP |  |  |  | Current Status: IFL Form testing needs Dassian support. Team is waiting from last week. Beth Workin left the project and her replacement Tanis Glascock is out of office this week. Issue : IFL Form needs Dassian Resource support for testing. Next Steps: Team is awaiting for resource availability Help needed: Need help to accelerate the testing and FUT closure |  | 1. Emerging risk | 3 | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1700 | OTCF0460_IP | 05.Form | 01.IP - Intel Product | Form Development for Invoice list. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Billings%20and%20Rebates/Filled%20RICEFW%20Template/Billing_Console_BR-130-010_process%20invoice%20list.pptx?d=wc71cd67681834abd9458b78f63d36b19&csf=1&web=1&e=4OOkmc | 01.Yes | 01.Yes |  | 2024-07-19 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-02 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2024-11-29 | 2024-12-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-25 | 2024-12-06 | 2024-12-06 | N | 100% | 2025-01-10 | Not Applicable | R3 Build & UT Sprint 9 | 2025-01-17 | 2025-01-17 | 2025-01-17 | pgaroo@deloitte.com | 2024-07-19 07:03 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0460 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-01-10 | 2025-01-10 | 2025-01-10 | [5 empty] | 2024-09-13 | 2025-01-17 |  |  | 2024-12-06 |  |  |  | 0 | 08. Not Applicable | 1794 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-01-17 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1148 | OTCF0460_IF | 05.Form | 02.IF - Intel Foundry | Form Development for Invoice list. | 04. OTC IF | 4.3 OTC IF - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Billings%20and%20Rebates/Filled%20RICEFW%20Template/Billing_Console_BR-130-010_process%20invoice%20list.pptx?d=wc71cd67681834abd9458b78f63d36b19&csf=1&web=1&e=4OOkmc | 01.Yes | 01.Yes |  | 2024-07-19 | Jill Matalon | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2024-12-13 | 2025-01-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-03 | 2025-01-10 | 2025-01-10 | N | 100% | 2025-02-28 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | pgaroo@deloitte.com | 2024-07-19 07:31 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | OTCF0460_IP | 03.Medium | 0.2 | 0.138 | 0460 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | [5 empty] | 2024-09-13 | 2025-01-17 |  |  | 2025-01-10 |  |  |  | 0 | 08. Not Applicable | 1569 | [10 empty] | 2025-01-17 | Y | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1643 | OTCF0431 | 05.Form | 05.CFIN | Generate Custom Late Payment Interest Charge Output Form | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/811_OTC_RICEFW%20Interest%20Charge%20Form%20Customization.pptx?d=w9f0ee832344f413a8ea4cc3def0678b4&csf=1&web=1&e=Ib9jFR | 02.No | 01.Yes |  | 2024-06-28 | Jill Matalon | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-03-24 | 2025-04-18 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-02 | 2024-10-04 | 100% | 2024-10-01 | 2025-04-07 | 2025-03-14 | 2025-01-31 | 100% | 2025-01-30 | 2025-04-07 | 2025-03-14 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-04-11 | 2025-05-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-17 | 2025-04-18 | 2025-05-09 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-14 | 2025-03-14 | 2025-03-14 | pgaroo@deloitte.com | 2024-06-28 04:56 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0431 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-04-18 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-01-30 | 2025-03-14 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-04-18 | 2025-03-14 |  |  | 2025-04-18 |  |  |  | 0 |  | 1744 | [10 empty] | 2025-03-14 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-03-14 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 616 | OTCF0290 | 05.Form | 02.IF - Intel Foundry | Dunning output form customization | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/616_OTC_RICEFW%20Dunning%20Form%20Customization.pptx?d=w314790f25adb406db31422f4c1252721&csf=1&web=1&e=ucqhLO | 02.No | 01.Yes |  | 2024-06-05 | Jason Carmichael | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-18 | 2024-07-18 | 100% | 2024-07-25 | 2024-07-19 | 2024-07-19 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-30 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-03-05 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-17 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-03-28 | Not Applicable | R3 Build & UT Sprint 12 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-04 07:05 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0290 |  | R3 ITC1 | [6 empty] | 2024-07-25 | 2024-07-25 | 2024-07-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-30 | 2025-01-31 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | [5 empty] | 2024-07-18 | 2024-12-20 |  |  | 2025-03-21 |  |  |  | 0 | 02. IF Customers | 1589 | [10 empty] | 2024-12-20 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 613 | OTCF0054_IP | 05.Form | 01.IP - Intel Product | Customer Billing output (Invoice/ Credit/ Debit/ Proforma Invoice) | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_EMAIL_TEMPLATE.pptx?d=w64d9e919ff4a43739c4e1b8a54657cd3&csf=1&web=1&e=Q1mMcc | 01.Yes | 01.Yes |  | 2024-06-07 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | [15 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-02-14 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-07 07:36 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | OTCF0054_IF | 02.High | 0.4 | 0.276 | 0054 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | [12 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-08-30 | 2024-12-20 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 1588 | [9 empty] | 8/11 : FUT sent for apprval | 2024-12-20 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2024-12-20 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 612 | OTCF0046_IP | 05.Form | 01.IP - Intel Product | Send/Transmit Invoice | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-040_INVOICE_FORM.pptx?d=w49e60ff4a0d04685b6291bee59bcd836&csf=1&web=1&e=HLMHKJ | 02.No | 01.Yes |  | 2024-06-07 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-12 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-18 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-18 | [15 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-01-17 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-06 | 2025-01-31 | 2025-01-24 | N | 100% | 2025-01-31 | Not Applicable | R3 Build & UT Sprint 10 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-07 07:36 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | OTCF0046_IF | 03.Medium | 0.2 | 0.138 | 0046 |  | R3 ITC1 | [6 empty] | 2024-08-12 | 2024-08-16 | 2024-08-12 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | [12 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | [5 empty] | 2024-08-16 | 2024-11-22 |  |  | 2025-01-31 |  |  |  | 0 | 08. Not Applicable | 1587 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness |  | 2024-11-22 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2024-12-20 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 23 | OTCF0004_IP | 05.Form | 01.IP - Intel Product | Order acknowledgment and confirmation to the customer | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Order%20Acknowledgement%20%26%20confirmation.pdf?csf=1&web=1&e=piiDAz | 01.Yes | 01.Yes |  | 2024-04-10 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-05-06 | 2024-06-10 | 2024-06-10 | 100% | 2024-06-12 | 2024-06-11 | 2024-06-11 | 2024-06-17 | 100% | 2024-06-19 | 2024-06-18 | 2024-07-18 | 2024-07-18 | 100% | 2024-07-26 | 2024-06-18 | 2024-07-18 | 2024-07-18 | 100% | 2024-07-26 | [15 empty] | 2024-07-26 | 2024-07-26 |  |  | 2024-08-02 | 2024-08-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-07-29 | 2024-08-16 | 2024-08-16 | N | 100% | 2024-08-22 | Not Applicable | R3 Build & UT Sprint 4 | 2024-07-18 | 2024-07-18 | 2024-07-18 | jenoronha@deloitte.com | 2024-04-09 11:53 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | OTCF0004_IF | 02.High | 0.4 | 0.276 | 0004 |  | R3 ITC1 | [6 empty] | 2024-06-12 | 2024-06-12 | 2024-06-12 |  | 2024-06-19 | 2024-06-19 | 2024-06-19 |  | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | [12 empty] | 2024-07-26 | 2024-07-26 |  |  | 2024-08-22 | 2024-08-22 | 2024-08-22 | [5 empty] | 2024-06-10 | 2024-07-18 |  |  | 2024-08-16 |  |  |  | 0 | 08. Not Applicable | 1427 | [10 empty] | 2024-07-18 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 3 |  | 2024-07-26 | 2024-07-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3041 | OTCE1710 | 04.Enhancement | 01.IP - Intel Product | Addition of Custom Fiori Tile/Dashboard - MRB,Pending,NPR,Freight Determination Matrix | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID%20%233041%20-%20RICEFW%20Intake%20Form.pptx?d=wc3b3a89ed9c54b00998a238a1668ffc2&csf=1&web=1&e=8lt5va | 02.No | 01.Yes |  | 2025-08-13 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-05 | 2025-12-15 | 100% | 2025-12-11 | 2025-10-22 | 2025-10-29 | 2026-02-04 | 100% | 2026-02-17 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-17 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-17 | [15 empty] | 2026-03-17 | 2026-03-17 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-26 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-26 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-12-08 05:07 | cell-link@smartsheet.com | 2026-03-26 09:49 | 10 | 2025-09-02 | 01.S4 |  |  | 4 | 4 | 1710 |  | R3 ITC1 | [5 empty] | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-11 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-03-17 | 2026-03-17 | 2026-03-27 | 2026-03-17 | 2026-03-17 | [12 empty] | 2026-03-17 | 2026-03-17 |  |  | 2026-03-26 | 2026-03-27 | 2026-03-26 | [5 empty] | 2025-09-05 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3396 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 20/3: FUT open defects are yet to be fixed by tech team - Defect no: 7458, 7673 and 8495 3/13: FUT under defect fix 3/11:defect 7867,7673,7958 3/6:Defect 7867 2/27:FUT - Sent for approval 2/24:FUT Defects Under fix 7144 7395 7482 7485 7624 7343 7481 7297 2/19: Team majorly focus on OTCE1585 and OTCE1709- Planning to take this object after fixing OTCE1585 and OTCE1709. Defect: 7144 - Fiori 7343-ABAP - ETA - 2/17 7395-ABAP- NPR - 2/17 7297-Fiori - NPR 7396-ABAP 2/17: Below 4 defect needs to fix 7144 - Fiori 7343-ABAP - ETA - 2/17 7395-ABAP- NPR - 2/17 7297-Fiori - NPR 7396-ABAP 2/12: Build is partially completed and testing available scenarios. we have identified issue - defect 7144 - pending with Tech team. 2/9: TUT+FUT Testing .defect 7144 | 2025-12-05 | N | 05. OTC IP |  |  |  | 03/23: FUT in progress. Defects closed. ETA 03/27 Current status: FUT in progress Issue: FUT delayed. Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 3. Watch item | On track for S23+ | Defects | Complete | R3 Build & UT Sprint 23+ | 2026-03-17 | 2026-03-27 | 2026-03-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3041 | OTCE1709 | 04.Enhancement | 01.IP - Intel Product | Addition of Custom Fiori Tile/Dashboard - Case routing,Required field,Return Location,Inco term | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID%20%233041%20-%20RICEFW%20Intake%20Form.pptx?d=wc3b3a89ed9c54b00998a238a1668ffc2&csf=1&web=1&e=8lt5va | 02.No | 01.Yes |  | 2025-08-13 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-05 | 2025-12-15 | 100% | 2025-12-11 | 2025-10-22 | 2025-10-29 | 2026-02-04 | 100% | 2026-02-05 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-29 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-29 | [15 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-01-23 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-27 | N | 100% | 2026-03-26 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-12-08 05:07 | cell-link@smartsheet.com | 2026-03-28 21:33 | 10 | 2025-09-02 | 01.S4 |  |  | 4 | 4 | 1709 |  | R3 ITC1 | [5 empty] | 2025-12-11 | 2025-12-11 | 2025-12-15 | 2025-12-11 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-03-29 | 2026-03-29 | 2026-03-29 | 2026-03-29 | [12 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-03-26 | 2026-03-27 | 2026-03-26 | [5 empty] | 2025-09-05 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3397 | [7 empty] | 2. At Risk | 7. FUT Defect Retesting | 20/3: will be shared for approval today, currently FUT open fixes being closed by tech team. No active defect. working sessions with tech.. 3/13: FUT under defect fix 3/11:7673,7958,7548 ETA 3/11 3/6:7996, 7684 2/24:Defects 7607,7624 2/19:7255 Is open with tech 7245 defect with Tech team 7111 - Fixed and retesting is in progress 2/17:Re-testing failed and 7244,7245,7111 - defect assign back to Tech team 2/12: Reopened defect 7111-Fiori(Rohit) to be fixed. ABAP Fix needed on 7245,7255 2/10: Defect 6898 -ABAP(Ibad) -ETA - 2/10; Defect 6917,7111-Fiori(Rohit) -ETA - 2/10 2/5: Defect 6898 Fix in progress ETA 2/6 Action on tech team (Ibad) Defect 6917 Fix in progress ETA 2/6 Action on Fiori team 2/3: 6898 - Tech -Upload function not working 6917 - Fiori - Upload function not working Action on both Tech and Fiori 2/2: Build completed and handed over to Functional team to start FUT. 1/29:Build still in progress. Build ETA 1/30 1/27: 1/23:Build still in progress. Build ETA 1/30 1/23:Build still in progress. Build ETA 1/30 1/20:Build and TUT not completed. ETA 1/22.RAID 3384 1/14: Dev TUT not yet completed. how ever, parallel FUT is in progress 12/16 : FUT is planned in Sprint 22.Incorrect plan | 2025-12-05 | N | 05. OTC IP |  |  |  | 03/23: FUT in progress. Defects closed. ETA 03/27 Current status: FUT in progress Issue: FUT delayed. Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 | Week 3 Target | 3. Watch item | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-29 | 2026-03-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3154 | OTCE1703 | 04.Enhancement | 01.IP - Intel Product | PRMP Role needs to be sent to CHM from S4 to create Channel Partner Role in CHM | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3154_IP%20PRMP%20Role%20needs%20to%20be%20sent%20to%20CHM%20from%20S4%20to%20create%20Channel%20Partner%20Role%20in%20CHM.pptx?d=wf1cfc4e3a991465d92a3a00e66b9ce02&csf=1&web=1&e=ZhFYYP | 02.No | 01.Yes |  | 2025-11-22 | Shelly Lafree | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-18 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-17 | 2026-01-19 | 2026-02-04 | 2026-02-04 | 100% | 2026-03-05 | 2026-01-19 | 2026-02-04 | 2026-02-04 | 100% | 2026-03-05 | [15 empty] | 2026-03-05 | 2026-03-05 |  |  | 2026-02-20 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-19 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-04 | 2026-02-04 | 2026-02-04 | jenoronha@deloitte.com | 2025-11-22 01:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 2 | 2 | 1703 | INT-CR1157 | R3 ITC1 | [5 empty] | 2025-12-18 | 2025-12-18 | 2026-01-07 | 2025-12-18 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | [12 empty] | 2026-03-05 | 2026-03-05 |  |  | 2026-02-19 | 2026-03-04 | 2026-02-19 | [5 empty] | 2026-01-07 | 2026-02-04 |  |  | 2026-03-04 |  |  |  | 0 |  | 3390 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/17: No opens, FUT sent for approval 2/12: Build is partially completed and testing available scenarios. we have identified issue - defect 7169 - CHM team is going to update that field in their system. ETA is Monday once it is done. 2/10: Build is partially completed and testing available scenarios. Change scenario and a scenario related a currently valid indicator is not working .Defect 7169 also raised for tracking 2/9: Tech team confirmed its sent for intel approval -Hence please start testing like TUT+FUT. How ever, object not delivered officially. | 2026-02-04 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-03-05 | 2026-03-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 81 | OTCE1698 | 04.Enhancement | 04.GTS | Additional material attributes for transfer from MDG to GTS to support product classification | 04. OTC IF | 4.9 OTC IF - GTS | 10. Object Complete | Y | 2024-04-16 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/81_OTC_RICEFW%20Intake%20Form_v1.0.pdf?csf=1&web=1&e=9zPsZi | 01.Yes | 01.Yes |  | 2025-03-25 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-10-13 | 2025-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-07 | 2025-02-07 | 100% | 2025-03-14 | 2025-01-20 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-14 | 2025-01-20 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-14 | [15 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-03-21 | 2025-03-21 | jenoronha@deloitte.com | 2025-11-12 21:14 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 02.MDG |  |  | 1 | 1 | 1698 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-11-15 | 2024-11-26 |  | 2025-03-14 | 2025-03-14 | 2025-03-14 |  | 2025-03-14 | 2025-03-21 | 2025-03-14 | 2025-03-14 | [12 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-11-15 | 2025-03-21 |  |  | 2025-12-03 | GTS |  |  | 0 |  | 3383 | [9 empty] | 11/18: On Track - FUT documentation complete. Internal Review in Progress. ETA for completion is 11/18. | 2025-03-21 | N | 04. OTC IF |  |  |  |  | FS and FUT complete. |  |  |  | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-03-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3143 | OTCE1668_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to transfer Customs value from S4 to GTS for Sales orders and delivery documents | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3143%20-OTC_GTS_%20Data%20Enrichment%20to%20include%20Customs%20Value%20during%20transfer%20of%20SO%20and%20DN%20from%20S4%20to%20GTS.pptx?d=wea634b923f0747bda1846625c3a987d7&csf=1&web=1&e=vQjToh | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-16 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-25 | 2026-03-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-25 | N | 100% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 01:53 | cell-link@smartsheet.com | 2026-03-23 10:14 | 10 |  | 01.S4 |  |  | 1 | 1 | 1668 | INT-CR0610 | R3 ITC1 | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-23 | 2026-03-25 | 2026-03-23 | [5 empty] | 2026-01-07 | 2026-02-06 |  |  | 2026-03-06 | GTS |  |  | 0 |  | 3347 | [7 empty] | 1. On Track | 17. FUT In progress | 03/13: Awaiting Defect Resolution 3/11: FUT with BAPP In progress 2/27: Test data for TUT and FUT creation is in progress mails sent to OTC and Logistics for coordination | 2026-02-06 | N | 05. OTC IP |  |  |  | 03/11: Build in progress. ETA is 03/13. Current status: Build is in progress and TUT+FUT will be followed post Build Issue: FUT delayed. Next steps: Expedite Build completion Help needed: N/A FUT ETA: 03/27 |  | 3. Watch item | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3143 | OTCE1668_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to transfer Customs value from S4 to GTS for Sales orders and delivery documents | 04. OTC IF | 4.9 OTC IF - GTS | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3143%20-OTC_GTS_%20Data%20Enrichment%20to%20include%20Customs%20Value%20during%20transfer%20of%20SO%20and%20DN%20from%20S4%20to%20GTS.pptx?d=wea634b923f0747bda1846625c3a987d7&csf=1&web=1&e=vQjToh | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-16 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-27 | N | 100% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 01:53 | cell-link@smartsheet.com | 2026-03-23 10:14 | 10 |  | 01.S4 | OTCE1668_IP | 03.Medium | 0.2 | 0.2 | 1668 | INT-CR0610 | R3 ITC1 | [5 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-23 | 2026-03-27 | 2026-03-23 | [5 empty] | 2026-01-07 | 2026-02-06 |  |  | 2026-03-06 | GTS |  |  | 0 |  | 3348 | [7 empty] | 1. On Track | 17. FUT In progress | 03/13: Awaiting Defect Resolution02/27: Test data for TUT and FUT creation is in progress mails sent to OTC and Logistics for coordination | 2026-02-06 | N | 04. OTC IF |  |  |  | 03/11: Build in progress. ETA is 03/13. Current status: Build is in progress and TUT+FUT will be followed post Build Issue: FUT delayed. Next steps: Expedite Build completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2066 | OTCE1662 | 04.Enhancement | 05.CFIN | BADI Enhancement for Dispute Write off (workflow Trigger) | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2066_OTC_RICEFW_Dispute%20Write-off%20Workflow.pptx?d=wf80c2013c54b44d992667baa693f3c80&csf=1&web=1&e=ukg9Ht | 02.No | 01.Yes |  | 2024-09-11 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-11-13 | 100% | 2025-12-08 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-17 05:02 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-17 | 01.S4 |  |  | 1 | 1 | 1662 |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-11-14 | 2025-11-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 | 08. Not Applicable | 3331 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 1/8: 2 defect :5241 and 5998 need to fix by Tech team 1/6:5988 , 5982,5241 Defect fixes ETA 1/7 EOD 01/05: defect 5971, 5972 . 5241 to be fixed.. 12/23: Defect 4718 to be fixed by Tech team., 5881 fixed and ready for re-testing. 12/18: Object Sent for approval. Waiting for the feedback 12/16: Object Sent for approval. Waiting for the feedback 12/11:Defects fixed -REOPENed. Minor issues open. Expected to be fixed 12/12 first half. Target to send to approval by 12/12 12/9:Defects 4718,5241 addressed -Retest in progress .5127 reopened to be fixed 12/8:Defect 4718 reopened .ETA 12/9 12/4: 5127 - ABAP dump in Fiori - Manage dispute case app upon validation check. 4718:For the 'waiting your approval' email is being sent only to the new processor, it should aslo have last change user, coordinator, and any previous processor in 'CC'. 12/3:defect 4718,5126 fixed. 5127 in progress ETA 12/3 EOD 12/2:Defects 5126, 5127 - Yet to be picked by Tech team .ETA to pick 12/3 11/28:Defect 4718 in progress. ETA 11/28 EOD 11/25: Defect 4718 still open . ETA Revised to 11/26 11/21 : Defect 4718,4783 ETA 11/21 | 2025-12-05 | Y | 04. OTC IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2066 | OTCE1658 | 04.Enhancement | 05.CFIN | Dispute Write-off Enhancement | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2066_OTC_RICEFW_Dispute%20Write-off%20Workflow.pptx?d=wf80c2013c54b44d992667baa693f3c80&csf=1&web=1&e=ukg9Ht | 02.No | 01.Yes |  | 2024-09-11 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-11-13 | 100% | 2025-11-14 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-28 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-15 07:37 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-17 | 01.S4 |  |  | 0.5 | 0.5 | 1658 |  | R3 ITC1 | [6 empty] | 2025-11-14 | 2025-11-14 | 2025-11-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 3326 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 1/8: 2 defect :5241 and 5998 need to fix by Tech team 1/6:5988 , 5982,5241 Defect fixes ETA 1/7 EOD 01/05: defect 5971, 5972 . 5241 to be fixed.. 12/23: Defect 4718 to be fixed by Tech team., 5881 fixed and ready for re-testing. 12/18: Object Sent for approval. Waiting for the feedback 12/16: Object Sent for approval. Waiting for the feedback 12/11:Defects fixed -REOPENed. Minor issues open. Expected to be fixed 12/12 first half. Target to send to approval by 12/12 12/9:Defects 4718,5241 addressed -Retest in progress .5127 reopened to be fixed 12/8:Defect 4718 reopened .ETA 12/9 12/4: 5127 - ABAP dump in Fiori - Manage dispute case app upon validation check. 4718:For the 'waiting your approval' email is being sent only to the new processor, it should aslo have last change user, coordinator, and any previous processor in 'CC'. 12/3:defect 4718,5126 fixed. 5127 in progress ETA 12/3 EOD 12/2:Defects 5126, 5127 - Yet to be picked by Tech team .ETA to pick 12/3 11/28:Defect 4718 in progress. ETA 11/28 EOD 11/25: Defect 4718 still open . ETA Revised to 11/26 11/21 : Defect 4718,4783 ETA 11/21 | 2025-12-05 | Y | 04. OTC IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2782 | OTCE1655 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to AIF capabilities on access and notifications | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%202782_Enhancement%20to%20AIF%20capabilities%20on%20access%20and%20notifications.pptx?d=w51f7d113fbb34fe3b2c4272ba425f0b3&csf=1&web=1&e=50xgVq | 02.No | 01.Yes |  | 2025-02-03 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-05 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 1 | 1 | 1655 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2026-01-23 |  |  |  | 0 | 08. Not Applicable | 1813 | [7 empty] | 1. On Track | 1. Approved no action | 2/5 Awaiting FUT approval 2/3: Awaiting FUT Approval 2/2: Awaiting FUT Approval 1/29: Awaiting FUT Approval 1/22:Defect 6387 fixed. Under retest .ETA 1/23 To resend for approvals 1/20:Defect 6254 ETA 1/21 1/14: Defect 5940 and 6254 to be fixed by Tech team. 1/8::Defect 5940 ,5572 for AIF implementation of IDOC . ETA 1/8 1/6:Defect 5940 ,5572 for AIF implementation of IDOC . ETA 1/8 01/05: Object sent for approval and walkthrough done. Opens are in-progress. (defect 5940) 12/24:Addressing Opens raised 12/23: Sent for approval. 12/16: Defect 5063 to be fixed. Tech to create auth profile, token creation for 3A6 & 3A7 RFC. 12/11:Defect 5338 - Fix In Progress ETA 12/11 12/9:Defect 5338 opened ETA 12/10 EOD 12/8:Defect 4627 ETA 12/9 EOD 12/4: Defect 4627 with Tech team 12/2: Defect 4627 under fix by tech ETA 12/3 . Defect 5063 -current action on BAsis on RFC 11/28:Defect 4627 , 5063 in progress ETA 11/28 11/25:FUT Defect 4627 .Revised ETA Given from tech : 11/26 11/21:Defect 4627 under fix ETA 11/22 11/17: Defect 4627 | 2025-11-05 | N | 04. OTC IF |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 28 | OTCE1625 | 04.Enhancement | 02.IF - Intel Foundry | Credit hold release dashboard at line-item level | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29%2FCM%2D050%2D020%5FOTC%5FRICEFW%20Intake%20Form%5FV1%2E0%2Epdf&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0&q=credit%20hold&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29&parentview=7 | 02.No | 01.Yes |  | 2024-03-26 | Jill Matalon | 01.Approved | 2024-03-26 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  | NA | NA | NA | NA | 2024-06-04 | 2024-07-12 | 2024-07-12 | 100% | 2024-08-16 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-13 | 2025-02-07 | 2025-02-21 | 2025-09-05 | 100% | 2026-03-13 | 2025-02-07 | 2025-02-21 | 2025-09-05 | 100% | 2026-03-13 | [15 empty] | 2026-03-13 | 2026-03-13 |  |  | 2025-10-03 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-07 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-02-21 | 2025-02-21 | 2025-02-21 | vasamohan@deloitte.com | 2024-03-22 16:09 | cell-link@smartsheet.com | 2026-03-12 23:25 | 10 |  | 01.S4 |  |  | 4 | 4 | 1625 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-16 | 2024-08-16 | 2024-08-16 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [12 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | [5 empty] | 2024-07-12 | 2025-02-21 |  |  | 2026-02-04 |  |  |  | 0 | 08. Not Applicable | 1429 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/5: 4 defects but nothing blocking approval, we will get conditional approval by 2/6 2/3: Defect 6667 is moving on a CR discussion . Business alignment pending. Working towards Conditional approval. Action on credit and collections team to discuss with Business 2/2: 6667 - Tech will be checking on the backend complexity from the additional filter. remaining all the opens are closed as of now. 1/29: 6646 The Release/check and Hold buttons - Fiori support 6667 - 6667 Filter issues )- Fiori . Also Fiori+ Tech alignment needed 6652 - Tech support (PPDM issue)- CR 1/30 6668 - Fiori support (But not critical on sign off) 1/27: 6647 fixed and closed defects 6646 and 6652,6667,6668- ETA 1/28 On track 1/20:PPDP defects under fix 5686, 6295 1/14: defect 5686, 5975, 6241, 6242 to be fixed by Tech team. Plan is to send for approval on or before 16/01 1/8: defect 5975 and 5686, 6087 to be fixed 1/6: Defects : ETA 1/9 To close all defects 5686,5975, 01/05: defect 5686 to be fixed 12/24:Defect 5756 in progress. ETA 12/24 12/23: Defect 5756, 5853 with Tech team 12/18:Defect 5676,5664 - ETA TBD 5696,5686 - Fixed and re-testing is in progress. 12/11: Credit dashboard fixes will hand over as per eta is this week 12/12 . 12/9:Credit dashboard Issues .ETA To receive for testing 12/12 12/2:Credit dashboard under defects. 11/28:Credit dashboard defects fix in progress 11/25:Credit dashboard Issues 11/21: The dashboard under redesign ETA 11/28 11/17- Tech team + Fiori Team is currently working on fixes. ETA is 11/28. FUT to follow post fixes (12/05) 11/11 - Multiple defects. Re-design of Fiori app. FUT on hold 11/6:Major Issue on custom fiori screen . 3401/4105/4106 Defects WIP 11/4:Defects 3401, 4105,4015, 4106 10/30 : Defect 3401, 3480 Under fix 10/17 Defects 3480, 3401,3515,3202 | 2025-02-21 | N | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-13 | 2026-03-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3061 | OTCE1605 | 04.Enhancement | 01.IP - Intel Product | Custom Routine for VAS Billing with Hardware | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-060_Custom%20Copy%20Control%20Routine.pptx?d=w3ad27aad045749759cfeaa0e256985cd&csf=1&web=1&e=EfBDRb | 02.No | 01.Yes |  | 2025-10-14 | Shelly Lafree | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-23 | 2025-10-10 | 2025-10-17 | 2025-11-11 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-14 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-14 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-03 | 2025-11-21 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-14 | 01.S4 |  |  | 1 | 1 | 1605 | INT-CR0954 | R3 ITC1 | [6 empty] | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-09-26 | 2025-12-05 |  |  | 2025-11-21 |  |  |  | 0 |  | 3273 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/2:Awaiting Approval -No Opens 11/28:Awaiting Intel approval 11/25: Awaiting Intel approval 11/21: FUT sent for approval. ETA to receive approval 11/25 11/17 : FUT in Progress | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3041 | OTCE1585 | 04.Enhancement | 01.IP - Intel Product | Addition of Custom Fiori Tile/Dashboard - EEPM,Decoder,Approval Matrix | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID%20%233041%20-%20RICEFW%20Intake%20Form.pptx?d=wc3b3a89ed9c54b00998a238a1668ffc2&csf=1&web=1&e=8lt5va | 02.No | 01.Yes |  | 2025-08-13 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-05 | 2025-09-05 | 100% | 2025-10-10 | 2025-10-22 | 2025-10-29 | 2025-11-20 | 100% | 2026-03-05 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-29 | 2025-11-10 | 2025-12-05 | 2026-03-27 | 100% | 2026-03-29 | [15 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-01-23 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-27 | N | 100% | 2026-03-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | cell-link@smartsheet.com | 2026-03-28 21:33 | 10 | 2025-09-02 | 01.S4 |  |  | 4 | 4 | 1585 |  | R3 ITC1 | [6 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-29 | 2026-03-29 | 2026-03-29 | 2026-03-29 | [12 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-03-20 | 2026-03-27 | 2026-03-20 | [5 empty] | 2025-09-05 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3237 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 20/3: 1585 - conditional approval received from Intel biz. awaiting Luis's final approval 3/13: FUT under defect fix 3/11:Defects 7673,7958,8170,7548 ETA 3/12 3/6:7673, 7958 2/27 - Defects 7673, 7548 In progress by tech(FUT Review ) 2/25-7548,7673,7254 Defects under fix 2/24:Sent for approval.Addressing Opens 2/19: 7254-Fixed Under retest. 7483 Fixed 7433 Fixed 7111 Fixed 2/17: Re-testing failed - 7254, 7111,7433 With tech team 2/12: defect 7054 - fixed-under retest. New defect 7254 to be fixed. ETA 2/13 2/10: Defect 7054-ETA 10-Feb Defect 6634-09-Feb 2/5: Defect 6634 FIORI issue WIP Action on Rohit ETA 2/6 2/3: 6634 - Fiori defect needs to fix. 2/2: defect 6551 - Tech team 6634 - New defect - Fiori- Defect needs to fix 1/29: 6551- Tech team 6634-Fiori to be fixed 1/27: Defect 6551 to be fixed. 1/22: Build still in progress . ETA 1/23 EOD 1/20:Build and TUT not completed. ETA 1/22.RAID 3384 1/14: TUT not yet completed. how ever, parallel FUT is in progress. 12/16 : FUT is planned in Sprint 22.Incorrect plan | 2025-12-05 | N | 05. OTC IP |  |  |  | 03/11 - Defect fixes in progress post sent for approval Current state: Defect fixes ongoing. Issue: FUT delayed. R4C BApps final testing is impacted. (OTCI1598). Next steps: Expedite defect fixing and resend it for approval. Help needed: N/A FUT ETA : 03/27 | Week 3 Target | 3. Watch item | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-29 | 2026-03-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3000 | OTCE1558 | 04.Enhancement | 02.IF - Intel Foundry | Business users want the capability to have CMIR updated for the specific Materials which will go under FERT To HALB Conversion during R3 Cutover, this activity will be specific for IF system, CMIR to be deleted automatically for materials which will undergo FERT to HALB Conversion and new records to be created for new Material code | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B08ACA71E-C08E-4A24-8AFF-319A5BC70D30%7D&file=Console%20ID_3000_IF_CMIR%20record%20conversion%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-17 | 2025-10-04 | 100% | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-10 | 01.S4 |  |  | 1 | 1 | 1558 | INT-CR0806 | R3 ITC1 | [6 empty] | 2025-10-10 | 2025-10-17 | 2025-10-10 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | [5 empty] | 2025-10-17 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 |  | 3186 | [7 empty] | 4. Completed | 1. Approved no action | 12/18: FUT updated with Reviewed and Approvals from Intel 12/18: FUT sent for approval. Walkthrough completed 12/11: FUT sent for approval 12/9:Defect 5355 ETA 12/9 EOD 12/8:Defect 5095 ETA 12/8 EOD 12/4: defect 5095 fix in progress. 12/2: Defect 5095 fix In progress. ETA 12/3 EOD 11/28:FUT defect retesting . Sending for approval 11/28 EOD 11/25: Defect 4964 is open . ETA 11/26 11/21: Defect 4781 under retest. ETA For FUT completion 11/22 11/17: FUT defect Under fix 4597 | 2025-12-05 | Y | 04. OTC IF |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2994 | OTCE1557 | 04.Enhancement | 02.IF - Intel Foundry | Business users want the capability to have sales order updated for the specific Materials which will go under FERT To HALB Conversion during R3 Cutover, this activity will be specific for IF system, orders to be updated automatically. | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2994_IF_Sales%20order%20conversion%20.pptx?d=w3affbd7c8bd04414a4b8e02c7258af75&csf=1&web=1&e=C9X1oR | 02.No | 01.Yes |  | 2025-08-13 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-07 | 2025-10-04 | 100% | 2025-11-04 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-01-30 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-26 | Sprint 22 Week 3 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-10 | 01.S4 |  |  | 2 | 2 | 1557 | INT-CR0806 | R3 ITC1 | [6 empty] | 2025-11-04 | 2025-11-04 | 2025-11-04 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | [5 empty] | 2025-10-07 | 2025-12-05 |  |  | 2026-01-30 |  |  |  | 0 |  | 3207 | [7 empty] | 4. Completed | 3. Awaiting Approval | 2/24:Awaiting approval 2/19:Object sent for approval.Review and Approval is in progress by Intel Team 2/17: Defect 7340 And Defect 7369 - fixed. Re-testing is in progress. 2/12: defect 6305 ,6391- Fixed and re-testing is in progress.. - ETA - 2/13 2/10:Sent for approval 2/5: Defect 6391 Fixed retesting in progress Action on functional team (nisa) Defect 6151 fix in progress ETA 2/6, Action on tech team (Tanmayee) 2/3: Tech defect : 6391 - ETA 2/3 Tech defect 6151 - ETA 2/5 Fiori defect -6305 -ETA 2/4/2025 Defect fixed and Closed - 6746 by Functional Team 2/2: ALM Defects 6391 & 6305 (Re-testing failed) has been updated with open issues. ALM Defect 6151 : ETA has been provided for 2/02/2026 6746- Tech fix required 1/29: 6305 6151,6391 defect with Tech team. need to fix.Developer OOO and not much progressed on 1/29.Need ETA 1/27: :Defect under fix 6305,6151 .,6391 ETA TBD 1/22:Defect under fix 6305,6151 .,6391 ETA TBD 1/20:Defects under fix 6095 6305 6151 6390 6391 1/14: defect 5449(Re-opened), 5922, 6095 (New) to be fixed by Tech team 1/8: MX Tech team support required, defect in fix - Fiori : 5922,5945, ABAP: 5449,5549.ETA TBD 1/6:Tech defect in fix - Fiori : 5922,5945, ABAP: 5449,5549.ETA TBD 01/05: defect to be fixed by Tech team 5449-Reopened 5945 12/24: Defect 5922 open.ETA TBD.Resumed back end testing 12/23:Defect 5549,5449 with MX Tech team. ETA - TBD 12/18: Defect 5549,5449 with MX Tech team. ETA - TBD Incorrect Data in Extraction report | 2025-12-05 | N | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2954 | OTCE1505 | 04.Enhancement | 01.IP - Intel Product | Automated Import declaration creation | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-05-27 | Shelly Lafree | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-08 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-04 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-05-01 11:33 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 1505 |  | R3 ITC1 | [6 empty] | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3006 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 2/27: FUT approval requesting Mail sent to Intel Business and IT 2/18 - Awaiting Approval | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2953 | OTCE1421 | 04.Enhancement | 01.IP - Intel Product | Data Enhancement for NL Import Broker | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-05-27 | Shelly Lafree | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-08-19 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-04 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2025-05-01 11:33 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 1421 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3005 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27: FUT approval requesting Mail sent to Intel Business and IT 2/18 - Awaiting Approval | 2025-11-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2955 | OTCE1420 | 04.Enhancement | 01.IP - Intel Product | NL Broker delivery filtration and Import worklist creatio | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2FECC65E-A7A3-4EBA-824F-B097A4FE061E%7D&file=IP_Console%20IDs%202952-2955%20Broker%20Integration%20WRICEFWs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | OTCI1423 | 2025-05-27 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-09 | 2025-07-11 | 2025-07-16 | 100% | 2025-09-08 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-04 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-05-01 11:33 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 1420 |  | R3 ITC1 | [6 empty] | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | [5 empty] | 2025-07-11 | 2025-12-05 |  |  | 2026-03-04 | GTS |  |  | 0 | 05. Trade | 3004 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 2/27: FUT approval requesting Mail sent to Intel Business and IT 2/18 - Awaiting Approval | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2837 | OTCE1248 | 04.Enhancement | 01.IP - Intel Product | IFL Enhancements Add custom fields to enable Dassian flow down | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2059CB24-4709-4E7C-9B3D-1B989FA47B24%7D&file=IFL_Enhancement%20for%20Add%20custom%20fields%20to%20enable%20Dassian%20flow%20down.pptx&action=edit&mobileredirect=true |  |  |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 03.Dassian |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-09 | 2025-05-09 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-06-17 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-02-07 07:16 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 0.5 | 0.5 | 1248 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-18 | 2025-09-05 | 2025-08-18 | [5 empty] | 2025-05-09 | 2025-08-15 |  |  | 2025-09-05 |  | Federal |  | 0 | 08. Not Applicable | 1514 | [10 empty] | 2025-08-15 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2714 | OTCE1200 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to transfer fields from Sales Orders to Purchase Requisition during Sales Order creation and change. | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0C2B5C81-4391-436B-AB4F-A6042A01CE38%7D&file=Console%20ID_2712_IF_Enhancement%20to%20transfer%20fields%20from%20Sales%20Orders%20to%20Purchase%20Requisition%20during%20Sales%20Order%20creation%20and%20change.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-30 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 |  |  | 1 | 1 | 1200 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-02 | 2025-12-05 | 2025-12-02 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 2743 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/2: All Opens closed. Awaiting Approval 11/28:Awaiting approval -Closing Opens .ETA to close Opens 11/28 11/25:In Approval - Addressing opens - ETA To address opens 11/25 EOD 11/21:FUT sent for approval. ETA to receive approval 11/28 11/17:FUT In progress 11/14: FUT In progress | 2025-12-05 | Y | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2675 | OTCE1199 | 04.Enhancement | 01.IP - Intel Product | Enhancement to determine PO number based on SoldTo & MMID maintained in a BRF+ table. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAAD7C8EF-0F9D-4078-AF25-57B94B427AC5%7D&file=IP_Console%20ID%202675_Enhancement%20to%20determine%20PO%20number%20based%20on%20SoldTo%20and%20ShipTo%20updated%20in%20BRFPLUS.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cspingili%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDExMDExNTcyMiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-02-03 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-13 | 01.S4 |  |  | 1 | 1 | 1199 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 2671 | [7 empty] | 4. Completed | 1. Approved no action | 12/11: FUT sent for approval after closing defects and Open 12/9:Defect fix 5276 under retest 12/8:Defect 5276 fixes not working expected. US MX team to pick this on 12/8US morning. ETA 12/9 EOD 12/4: New defect 5276 created. 12/2: Awaiting approval -Addressing Opens 11/28:Awaiting Approval . Closing open comments 11/25:Awaiting Intel approval And addressing opens -ETA 11/26 EOD 11/21: FUT sent for approval. ETA to receive approval 11/25 11/17: Defect 4632 | 2025-11-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2782 | OTCE1198 | 04.Enhancement | 01.IP - Intel Product | Enhancement to AIF capabilities on access and notifications | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%202782_Enhancement%20to%20AIF%20capabilities%20on%20access%20and%20notifications.pptx?d=w51f7d113fbb34fe3b2c4272ba425f0b3&csf=1&web=1&e=50xgVq | 02.No | 01.Yes |  | 2025-02-03 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-16 | 2025-06-27 | 100% | 2025-08-11 | 2025-10-17 | 2025-10-24 | 2025-10-17 | 100% | 2026-01-31 | 2025-10-31 | 2025-11-28 | 2025-11-21 | 100% | 2026-02-07 | 2025-10-31 | 2025-11-28 | 2025-11-21 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 2 | 2 | 1198 |  | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-11 | 2025-08-11 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-07-16 | 2025-11-28 |  |  | 2026-02-04 |  |  |  | 0 | 08. Not Applicable | 1814 | [7 empty] | 4. Completed | 1. Approved no action | 2/3: Defect 6820 Fixed. 6327 Fixed. Re-testing is in progress. WOM,2DN, Mysample - all interface testing completed and sent for approval. B2B testing is in progress. Action on Mathew -OTC Functional team 2/2: 6815 defect needs to fix 1/29: 6684 - WIP ETA 1/29 6798 - WIP ETA 1/30 to be fixed by Tech team 1/27: 6480 -ZKB Creation issue fixed and closed. New defect 6660 for ZKB auto creation 1/22:Defect 6480 under fix -ETA 1/23 EOD 1/20:As per meeting alignment with Intel -Separate name space is needed. We will be fixing this under a new defect 14/1: 1) defect "6222 - to be fixed by Tech team 2) 6092 - Retesting" 1/8: 6092-IRC2 defect to be closed. 1/6:defects fixed .Under retest 01/05: Defect 5961 with Tech team 12/23: All the defects closed. FUT is in progress 12/22:5532, 5794 ETA 12/23 12/18: Defect 5532 still Under fix .ETA 12/18. defect 4928 - re-testing failed defect will be assigned to Tech team once RFC client credential extend to tech team.. 12/16: Defect 4928 still Under fix .ETA 12/17 12/11:Defect 4928 still Under fix .ETA 12/12 12/8:Defect 4928 in progress . ETA 12/10 12/4: 4928 fix in progress - ETA 12/4 12/2:Defect 4928 in fix for IRC2, EMS. The WOM , B2B can be tested only after current ongoing interface issues on Defect 4962 and 3968 are addressed 11/28:Defect 4928 under fix 11/25:Defect 4928 under fix 11/21:IRC2 -Defect 4689 created. At present fixed. Retesting defect. ETA For overall FUT completion 11/28 11/17 : FUT in progress.Multiple Interfaces Involved | 2025-11-28 | N | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2720 | OTCE1124 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to support Inbound interface to change the ship to party record at the sales order | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_POSO_Console%20ID%202720_Enhancement%20to%20support%20Inbound%20interface%20to%20change%20the%20ship%20to%20party%20at%20the%20sales%20order.pptx?d=w9a7a1efc297d42e7b5fabd7c1b1b21a6&csf=1&web=1&e=RJfIiu | 02.No | 01.Yes |  | 2025-01-21 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-12 | 2025-05-16 | 2025-08-01 | 100% | 2025-09-23 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-23 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-09-01 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-20 | Sprint 22 Week 2 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-01-16 12:46 | cell-link@smartsheet.com | 2026-02-20 07:26 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1124 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | [5 empty] | 2025-03-28 | 2025-06-13 | [6 empty] | 0 | 02. IF Customers | 2677 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 2/19: Object sent for approval.Luis approval is pending now. 2/17: Object sent for approval. dependent object 1126 also sent for approval.Luis approval is pending now. 2/12: seent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 2/3:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 2/2::Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 1/27::Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 1/22:1/20:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 1/20:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 1/14:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 1/8::Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 01/06:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 01/05:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 12/23:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 12/11:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 12/9:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 12/8:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 12/2:Sent for Intel Approval . Approval On Hold.But this will be approved with OTCI1126 Only 11/28: Sent for Intel Approval . But this will be approved with OTCI1126 Only 11/25: Sent for Intel Approval . But this will be approved with OTCI1126 Only 11/21:Sent for approval. But as per Intel this will be approved together with OTCI1126 11/17:Sent for approval. But as per Intel this will be approved together with OTCI1126 11/11:Sent for approval. But as per Intel this will be approved together with OTCI1126 11/6;Approval delayed as Business looking for approval after OTCI1126 only 11/4:Awaiting approval 10/30: Defect 3842 fixed and awaiting approval | 2025-06-13 | N | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2711 | OTCE1123 | 04.Enhancement | 02.IF - Intel Foundry | Determine Confirmed Delivery date in sales orders at schedule line level based on CMAD received from Blue yonder | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5A7BF17B-D79E-4014-A9CB-F88D50EA89DF%7D&file=Console%20ID_2711_IF_Determine%20CDD%20in%20sales%20order%20at%20schedule%20line%20level%20based%20on%20CMAD%20recieved%20from%20BY.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-21 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-23 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2026-01-31 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2026-04-06 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2026-04-06 | [15 empty] | 2026-04-06 | 2026-04-06 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2025-01-16 12:46 | cell-link@smartsheet.com | 2026-04-06 07:17 | 10 | 2025-01-23 | 01.S4 |  |  | 2 | 2 | 1123 |  | R3 ITC1 | [6 empty] | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | [12 empty] | 2026-04-06 | 2026-04-06 |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | [5 empty] | 2025-06-13 | 2025-10-10 | [6 empty] | 0 |  | 2510 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/23: Approved by business 12/18: During the walkthrough, business requested to have the attachment in the email have .xlsx extension 12/18:awaiting approval 12/16: Defect 4850 to be fixed. ETA - 12/17.This defect is getting delayed considerably. 12/11: Defect 4850 - ETA TBD Yet to get from Tech team as the pending fix is taking more time than expected 12/9:Defect 4850 - ETA 12/9 EOD 12/8:Defect 4850 - ETA 12/9 EOD 12/4: Defect 4850 with Tech team - ETA 12/4 12/2:Defect 4850 Still in progress. Considering complexity -Overall ETA To close FUT 12/4 11/28:Defect 4850 fix in progress .ETA 11/28 11/25 :Defect 4850 -Fix in progress 11/21: TUT+FUT in parallel 11/17: FUT In progress 11/14: Parallel TUT+FUT in progress as object Build in progress | 2025-11-05 | N | 04. OTC IF |  |  |  |  | E |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-04-06 | 2026-04-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2679 | OTCE1122 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for IMR to update the Repair Sales Order post Repair work order is complete | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/IF_Returns/Filled%20RICEFW%20Templates/Return%20Console_IP_R-190-010_IMR%20Sales%20Order%20update.pptx?d=w37e5c64a3ecf4d9dbe59c391d1412e6e&csf=1&web=1&e=sMlzdU | 02.No | 01.Yes |  | 2025-01-21 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-18 | 2025-04-14 | 2025-04-18 | 2025-04-22 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  | 2025-05-30 | 2025-12-24 | 2025-06-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 1122 |  | R3 ITC1 | [6 empty] | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-02-21 | 2025-04-18 | [6 empty] | 0 | 08. Not Applicable | 2673 | [7 empty] | 4. Completed |  |  | 2025-05-16 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2592 | OTCE1115 | 04.Enhancement | 01.IP - Intel Product | EMS_Enhancement for S4 validation of hardware and service warranty orders linked via EH portal, to check eligible service warranty orders for the outbound interface to OL (orchestration layer) for activation key generation, to remove the billing block post activation key generation | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID_2592_EMS_Enhancement%20for%20S4%20validation%20of%20hardware%20and%20warranty%20orders%20linked%20via%20EH%20portal.pptx?d=wce0696a696ca4ec79112a620f2f6f2e9&csf=1&web=1&e=AV38lu | 02.No | 01.Yes |  | 2025-01-21 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2026-01-06 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-01-06 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 2 | 2 | 1115 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | [5 empty] | 2025-02-28 | 2025-05-16 | [6 empty] | 0 | 08. Not Applicable | 1564 | [7 empty] | 4. Completed | 1. Approved no action | 12/9:Approved 12/8:Awaiting approval 12/4: Sent for approval.Opens in progress - ETA - 12/4 12/2:Awaiting intel approval 11/28-Sent for approval 11/28:Defect 5071 in fix. ETA 11/28 11/25:Defect 4960 under fix11/21: Defect 4667 under fix. ETA 11/22 11/17:Defects 4514, 4655 11/14 - Defects 4086 & 4514. FUT ETA is 11/21 11/11 - Defect 4086. ETA is TBD 11/4:defect 4086 10/30: BAPP Testing started . Issue identified -defect 4086 10/23 - S4 testing is completed. BA to get ready by 10/27 | 2025-10-08 | N | 05. OTC IP |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2697 | OTCE1112 | 04.Enhancement | 01.IP - Intel Product | Enhancement to restrict ‘plant code’ changes in sale orders in change mode for CBA’s | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%20_Enhancement%20to%20restrict%20plant%20code%20changes%20for%20CBA%27s.pptx?d=w03ff3f3398d7461f885362f92356d0d5&csf=1&web=1&e=2QfoLr | 02.No | 01.Yes | OTCI0964 | 2025-01-21 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-29 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-09-01 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 0.5 | 0.5 | 1112 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-13 | 2025-09-19 | 2025-09-13 |  | 2025-09-29 | 2025-10-10 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-07-04 | 2025-11-07 | [6 empty] | 0 | 08. Not Applicable | 1524 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 9/12: FUT sent for approval | 2025-10-10 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2729 | OTCE1110 | 04.Enhancement | 04.GTS | Enhancement to determine the correct source system for integrating B-App data with GTS ( Both master and Transactional Data ) and to capture the compliance status changes of the business partners | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx?d=wde229812c2e4486ba96864e1b9b43007&csf=1&web=1&e=MZRZNb | 02.No | 01.Yes |  | 2025-01-21 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-28 | 100% | 2025-08-04 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-12-31 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-12-31 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-31 | 01.S4 |  |  | 2 | 2 | 1110 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-07-04 | 2025-11-07 |  |  |  | GTS |  |  | 0 | 08. Not Applicable | 2674 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 12/04: Defect Retesting in progress. | 2025-10-08 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2730 | OTCE1109 | 04.Enhancement | 04.GTS | Enhancement to capture the changes in the compliance status of the transactional documents and transfer it to the B-App | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID%202721%20to%202730%20CR0026_Tower_RICEFW%20Intake%20Form_v2.0.pptx?d=wde229812c2e4486ba96864e1b9b43007&csf=1&web=1&e=MZRZNb |  |  |  | 2025-01-21 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-07-07 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-30 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-30 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-30 | [15 empty] | 2025-10-30 | 2025-10-30 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-31 | 01.S4 |  |  | 2 | 2 | 1109 |  | R3 ITC1 | [6 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | [12 empty] | 2025-10-30 | 2025-10-30 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-07-04 | 2025-11-07 |  |  |  | GTS |  |  | 0 | 08. Not Applicable | 2056 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/15: Awaiting approval. | 2025-10-08 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-30 | 2025-10-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2752 | OTCE1108 | 04.Enhancement | 01.IP - Intel Product | 2DN_Enhancement to create KB order from staging table & to update staging table with the KB order number | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID_2752_Enhancement%20to%20create%20KB%20order%20from%20staging%20table%20%26%20to%20update%20staging%20table%20with%20the%20KB%20order%20number.pptx?d=w532a6cb210be4b75a2ae0ef7dc3519f4&csf=1&web=1&e=nisMaP |  |  |  | 2025-01-21 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1108 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-04-25 | 2025-09-12 | [6 empty] | 0 | 08. Not Applicable | 2046 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting approval 11/28:Awaiting Intel Approval 11/25:Awaiting Intel approval 11/21: FUT sent for approval. ETA to receive approval 11/25 11/17: FUT sent for approval | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2536 | OTCE1106 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to support Inbound interface and manual upload to create the sales order via Build Instructions | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_POSO_Console%20ID%202536_Enhancement%20to%20support%20Inbound%20interface%20to%20create%20the%20sales%20order%20via%20Build%20Instructions.pptx?d=w24c9a34772ed42b3ab0a9d706c366c0b&csf=1&web=1&e=7Dqn5N | 02.No | 01.Yes |  | 2025-01-22 | Jill Matalon | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-02-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-03-13 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-03-13 | [15 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-02-20 | 2026-03-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-25 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-01-16 12:46 | cell-link@smartsheet.com | 2026-03-26 21:59 | 10 | 2025-01-23 | 01.S4 |  |  | 2 | 2 | 1106 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [12 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-03-20 | 2026-03-25 | 2026-03-20 | [5 empty] | 2025-06-13 | 2025-10-10 | [6 empty] | 0 | 02. IF Customers | 1670 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: sent for approval. Dependent object 1126 also sent for approval. 3/6; sent for approval 2/27: Defect 7131 -ETA 2/27 EOD 2/25:7131 - Under fix 2/24:Dependency on 7652 Defect 2/19: 7215 fixed and retesting is in progress (Unwanted errors in AIF are removed and Changes are now commiting after reprocessing ) * 7131 - issue in Fiori app- 'Import Build Instructions' . Tech fix is in progress. 2/17: Defect 7215 and 6945, 7131 - To be fixed by Tech team - ETA - 2/18 2/12: Defect 7215 defect to be fixed and Fiori app development 7131 To be completed by 2/13 2/10: Fiori App development not completed . Defect 7131. Reassigned to Nikhil from 2/10. Primary ETA 2/13 6945 Satya-Retest Depends on 7087- WIP 6645- WIP 2/10 Fixed and retesting is in progress 7131 - Fiori Issue 1/14: In Build - Identified that this have a dependency with development of OTCI1162(CR 856 -Revised ETA not received) Meantime checking fiori app testing side of the same 1/6:In Build - Identified that this have a dependency with development of OTCI1162(CR 856 -Revised ETA not received) Meantime checking fiori app testing side of the same 01/05:In Build - Identified that this have a dependency with development of OTCI1162. Meantime checking fiori app testing side of the same 12/24:In Build - Identified that this have a dependency with development of OTCI1162. Meantime checking fiori app testing side of the same 12/23:Received confirmation from tech to start Build 12/18: Tech Build still not completed. ETA TBD | 2025-12-05 | N | 04. OTC IF | [6 empty] | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-13 | 2026-03-13 | Yes | OSAT Plant sent from IP, IF Determined Plant from ZPARAMS in IF - ZPARAMS Impact | No |  | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-27 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2170 | OTCE1098 | 04.Enhancement | 01.IP - Intel Product | BOT to extract input and validate mandatory fields and transform the data into structured format. BOT to log into SAP SE16N and EDDAR to input customer details | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_JPY%20Intel%20XDock%20BOT_Interface.pptx?d=w65380a09bbb24c5a963e0c0b29362e2d&csf=1&web=1&e=l1WpJP | 01.Yes | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-10 | 2025-06-02 | 2025-06-06 | 2026-01-07 | 100% | 2025-12-11 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  | 2025-12-03 | 2025-12-19 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 1 | 1 | 1098 |  | R3 ITC1 | [6 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-12-11 | 2026-01-07 | 2025-12-11 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-12-19 | 2026-01-09 | 2025-12-19 | [5 empty] | 2025-07-11 | 2025-09-12 | [6 empty] | 0 | 08. Not Applicable | 2749 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/18: FUT sent for approval. Walkthrough completed. waiting for approval | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2170 | OTCE1097 | 04.Enhancement | 01.IP - Intel Product | BOT to manage ad hoc execution schedules, create an audit trail and capture evidence of its activities, support scalability through a multi-bot architecture, generate digital insights for each execution, and trigger exception notifications to both business and technical teams. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_JPY%20Intel%20XDock%20BOT_Interface.pptx?d=w65380a09bbb24c5a963e0c0b29362e2d&csf=1&web=1&e=l1WpJP | 01.Yes | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-10 | 2025-06-02 | 2025-06-06 | 2026-01-07 | 100% | 2025-12-11 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  | 2025-12-03 | 2025-12-16 | 2025-12-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-23 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 0.5 | 0.5 | 1097 |  | R3 ITC1 | [6 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-12-11 | 2026-01-07 | 2025-12-11 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-12-19 | 2026-01-09 | 2025-12-19 | [5 empty] | 2025-07-11 | 2025-09-12 | [6 empty] | 0 | 08. Not Applicable | 2750 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/18: FUT sent for approval. Walkthrough completed. waiting for approval | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2169 | OTCE1096 | 04.Enhancement | 01.IP - Intel Product | BOT to orchestrate triggers for its execution, create an audit trail and capture evidence of its activities, support scalability through a multi-bot architecture, generate digital insights for each execution, and trigger exception notifications to both business and technical teams. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_O-020-080_Reference_Bulk_Creation_Credit_Debit.pptx?d=w3664c498df4f4f19bc8f77a94e89026b&csf=1&web=1&e=cQwc6A | 02.No | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-01 | 2025-09-05 | 2025-11-05 | 100% | 2025-11-05 | 2025-10-06 | 2025-11-07 | 2026-01-07 | 100% | 2025-12-11 | 2025-10-06 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 2 | 2 | 1096 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-05 | 2025-11-05 |  |  | 2025-12-11 | 2026-01-07 | 2025-12-11 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-07-11 | 2025-11-07 | [6 empty] | 0 | 08. Not Applicable | 2746 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting approvals. Closing The opens raised by Intel . ETA To close opens 12/2 EOD 11/28:Awaiting Intel approval 11/25:FUT Sent for approval 11/21: Parallel testing with BOT+ABAP in progress.ETA to complete overall testing 11/25 11/17: BOT Dev IN progress-Parallel FUT we are doing | 2025-11-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2169 | OTCE1095 | 04.Enhancement | 01.IP - Intel Product | BOT to manage queue functionality for human approval of the first document of either a Credit Memo Request (CMR) or Debit Memo Request (DMR). | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_O-020-080_Reference_Bulk_Creation_Credit_Debit.pptx?d=w3664c498df4f4f19bc8f77a94e89026b&csf=1&web=1&e=cQwc6A | 02.No | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-01 | 2025-09-05 | 2025-11-05 | 100% | 2025-11-05 | 2025-10-06 | 2025-11-07 | 2026-01-07 | 100% | 2025-12-11 | 2025-10-06 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 4 | 4 | 1095 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-05 | 2025-11-05 |  |  | 2025-12-11 | 2026-01-07 | 2025-12-11 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-06-13 | 2025-11-07 | [6 empty] | 0 | 08. Not Applicable | 2745 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting approvals. Closing The opens raised by Intel . ETA To close opens 12/2 EOD 11/28:Awaiting Intel approval 11/25:FUT Sent for approval 11/21: Parallel testing with BOT+ABAP in progress.ETA to complete overall testing 11/25 11/17: BOT Dev IN progress-Parallel FUT we are doing | 2025-11-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2169 | OTCE1094 | 04.Enhancement | 01.IP - Intel Product | BOT to identify the type of request and open the corresponding Order Type in the system | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_O-020-080_Reference_Bulk_Creation_Credit_Debit.pptx?d=w3664c498df4f4f19bc8f77a94e89026b&csf=1&web=1&e=cQwc6A | 02.No | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-01 | 2025-09-05 | 2025-11-05 | 100% | 2025-11-05 | 2025-10-06 | 2025-11-07 | 2026-01-07 | 100% | 2025-12-11 | 2025-10-06 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 1 | 1 | 1094 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-05 | 2025-11-05 |  |  | 2025-12-11 | 2026-01-07 | 2025-12-11 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-06-13 | 2025-11-07 | [6 empty] | 0 | 08. Not Applicable | 2747 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting approvals. Closing The opens raised by Intel . ETA To close opens 12/2 EOD 11/28:Awaiting Intel approval11/25:FUT Sent for approval 11/21: Parallel testing with BOT+ABAP in progress.ETA to complete overall testing 11/25 11/17: BOT Dev IN progress-Parallel FUT we are doing | 2025-11-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1769 | OTCE1093 | 04.Enhancement | 01.IP - Intel Product | BOT to manage its execution schedule, create an audit trail and capture evidence of its activities, support scalability through a multi-bot architecture, generate digital insights for each execution, and trigger exception notifications to both business and technical teams. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_PRC%20Invoice%20compilation%20BOT_Interface.pptx?d=wce3cc77d48a843e1bb3ccd7f722e6352&csf=1&web=1&e=ag9pKs | 01.Yes | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-14 | 2025-03-14 | 100% | 2025-04-09 | 2025-03-31 | 2025-04-04 | 2025-06-20 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 1 | 1 | 1093 |  | R3 ITC1 | [6 empty] | 2025-04-09 | 2025-04-09 | 2025-04-09 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2025-06-13 | 2025-06-13 | [6 empty] | 0 | 08. Not Applicable | 2138 | [9 empty] | 9/22: S4 FUT submitted to Intel for Review as of now (Conditional approval. Note: ETA for EDDAR Readiness is WW44, post which changes will be required in UiPath Program also. Risk 2022 has been raised. | 2025-06-13 | N | 05. OTC IP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 19 |  | 2025-10-15 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1769 | OTCE1092 | 04.Enhancement | 01.IP - Intel Product | BOT for extracting input data from email validating mandatory fields and transforming invoice numbers into a structured data table format. BOT to log into SAP FBL5N to input customer details. | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_PRC%20Invoice%20compilation%20BOT_Interface.pptx?d=wce3cc77d48a843e1bb3ccd7f722e6352&csf=1&web=1&e=ag9pKs | 01.Yes | 01.Yes |  | 2025-01-28 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-14 | 2025-03-14 | 100% | 2025-04-09 | 2025-03-31 | 2025-04-04 | 2025-06-20 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2025-01-07 07:44 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-28 | 04.S4 BOT |  |  | 2 | 2 | 1092 |  | R3 ITC1 | [6 empty] | 2025-04-09 | 2025-04-09 | 2025-04-09 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2025-06-13 | 2025-06-13 | [6 empty] | 0 | 08. Not Applicable | 2139 | [9 empty] | 9/22: S4 FUT submitted to Intel for Review as of now (Conditional approval. Note: ETA for EDDAR Readiness is WW44, post which changes will be required in UiPath Program also. Risk 2022 has been raised. | 2025-06-13 | N | 05. OTC IP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 19 |  | 2025-10-15 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2674 | OTCE1028 | 04.Enhancement | 01.IP - Intel Product | Determine Confirmed Delivery date in sales orders at schedule line level based on CMAD received from Blue yonder | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBB084305-9EBD-4BFC-801F-823C86737FFE%7D&file=Console%20ID_2674_IP_Determine%20CDD%20in%20sales%20order%20at%20schedule%20line%20level%20based%20on%20CMAD%20recieved%20from%20BY-PDH.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-18 | shelly.lafree@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1028 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | [5 empty] | 2025-07-11 | 2025-10-10 |  |  | 2025-11-28 |  |  |  | 0 | 08. Not Applicable | 2670 | [7 empty] | 4. Completed | 1. Approved no action | 12/16: Approved by Luis 12/16: Object sent for approval 12/11; Defect fix is done 12/9:Defect Yet to be picked due to other priority defects 12/8:Defect 5201 under fix .ETA 12/9 EOD 12/4: New defect 5201 12/2:Awaiting approval 11/28-Sent for approval 11/28:FUT in progress after fixing defects. 11/25: FUT Defect 4881 under fix 11/21: Defect 4768 under fix. ETA to fix 11/21 EOD 11/17 : FUT in Progress | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2598 | OTCE1027 | 04.Enhancement | 01.IP - Intel Product | Enhancement for Sold To and ShipTo determination for SO2 & KB order sales orders for SO PO Process flows. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B50A69E93-8563-483F-A486-8BDB22570F2E%7D&file=IP_Console%20ID%202598_Enhancement%20to%20determine%20SoldTo%20and%20ShipTo%20Determination.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cspingili%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2024-12-18 | shelly.lafree@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-10-16 | 100% | 2025-11-13 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-03-12 20:20 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1027 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-11-28 |  |  |  | 0 | 08. Not Applicable | 1761 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/25:FUT awaiting approval .No Opens 11/21:FUT awaiting approval. ETA to get approval 11/25 11/17: Defect 4611 | 2025-11-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | Yes | Custom Table entries to be updates as Sales Area and Customer are fetched based on the CW (LE102) plant​ | No |  | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2597 | OTCE1026 | 04.Enhancement | 01.IP - Intel Product | Enhancement for copying Data / referencing from SO1 to SO2 for SO PO 2DN model. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2220C602-9AD1-4EBD-A31B-00ECB0591F13%7D&file=IP_Console%20ID%202597_Enhancement%20to%20determine%20copy%20SO1%20to%20SO2.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cspingili%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMjAwMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2024-12-18 | shelly.lafree@intel.com | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-13 | Sprint 22 Week 3 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-03-12 20:20 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1026 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-11-28 |  |  |  | 0 | 08. Not Applicable | 1566 | [7 empty] | 1. On Track | 1. Approved no action | 2/13-Approved. 2/12: FUT sent for approval 2/5: Defect 6885 fixed , retesting in progress Action on functional team (Srinivas) 2/3:6885 - Defect under fix ETA 2/3 EOD . Issue in hold replication 2/2: one scenario testing is in progress. Planning to re-send for approval today EOD. no opens 1/29: 6720 fix in progress -Change Log issues 1/27: defect 6633 in retest ETA - 1/28 (Text issue - SO1 to SO2 line item).Testing blocked due to DI0 Downtime on 1/27 1/22:Sent for approval 1/20:Defect 6307 under fix eta 1/21 1/14: defect 6307 under fix 1/8: Defect 5965 - Tech team alignment needed on feasibility. ETA - Today EOD 1/6:Defect 5965 fixed.retesting 01/05: defect 5965 to be fixed 12/24:Defect 5928 with tech . ETA 12/24 12/23::defect 5158 fixed and ready for re-testing 12/16:defect 5158 to be fixed. When we create manually it is working the line item is fetching correctly but from PO its not working. PO: 7400005251 12/11;Defect 5158 - ETA To fix the same 12/12 12/9:Defect 5078 fixed. 5158 Fix in progress ETA 12/10 EOD 12/8:Defects 5078 , 5158 ETA 12/9 EOD 12/4: defect 5078 and 5158 to be fixed. 12/2:Defect 5078 under fix.ETA 12/3 EOD 11/28: Awaiting Intel approval 11/25:Awaiting approval 11/21;Awaiting approval 11/17:FUT Awaiting approval 11/14 - Defect fixed. FUT Retest and documentation in progress. ETA to publish for approval by 11/14. 11/11:FUT Defect 4379 11/4:defect 3872 10/30 - defect 3872 under fix 10/23 - Defect retest | 2025-11-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | Yes | Custom Table entries to be updates as Sales Area and Customer are fetched based on the CW (LE102) plant​ | No |  | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2345 | OTCE1013 | 04.Enhancement | 02.IF - Intel Foundry | SIMS Enhancement to determine the order type based on the Material Characteristic | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_SIMS_Console%20ID%202345_Enhancement%20to%20Determine%20the%20order%20type%20based%20on%20the%20Material%20Characteristic.pptx?d=w53c9fda021e74af8bc9131c6437b6c96&csf=1&web=1&e=taUOU1 | 02.No | 01.Yes |  | 2024-12-18 | Jill Matalon | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-03 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-03 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-03 | [15 empty] | 2025-09-03 | 2025-09-03 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-03 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 0.5 | 0.5 | 1013 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-03 | 2025-10-17 | 2025-09-03 |  | 2025-09-03 | 2025-11-07 | 2025-09-03 | 2025-09-03 | [12 empty] | 2025-09-03 | 2025-09-03 |  |  | 2025-10-03 | 2025-10-08 | 2025-10-03 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-17 |  |  |  | 0 | 08. Not Applicable | 2286 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-11-07 | Y | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2572 | OTCE0975 | 04.Enhancement | 01.IP - Intel Product | Implementation of an enhancement to restrict deletion of the material line item after a sales order1 is created in 2DN process | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2574_IP_%20Implementation%20of%20an%20enhancement%20to%20restrict%20deletion%20of%20the%20material%20line%20item%20after%20a%20sales%20order1%20is%20created%20in%202DN%20process.pptx?d=w5ef3b56c82ec4e28ae410408b56157c5&csf=1&web=1&e=xFOPSV | 02.No | 01.Yes |  | 2024-12-10 | shelly.lafree@intel.com | 01.Approved | 2024-12-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-16 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-12-06 07:21 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 0.5 | 0.5 | 0975 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | [5 empty] | 2025-05-23 | 2025-09-12 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2322 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 1/14: FUT sent for approval. all the opens are closed. 1/8:Defect 5867,5963 awaiting fix. ETA 1/8 EOD 1/6:Defect 5867,5963 awaiting fix. ETA 1/8 EOD 01/05: defect defect 5867 5963 need to fix 12/23: Defect 5867 to be fixed by Tech team. 12/22:Defect 5860 12/18: defect 5626 to be fixed by Tech team. ETA - 12/18. (Added the reason for rejection in SO1 it's not reflecting in SO2. 2. Via the super user ID, will have the authority to modify SO1 ) 12/11:Awaiting approvals.Addressing Opens 12/9:FUT Sent for approval.Addressing opens 12/8:FUT Sent for approval 12/4: Defect with 5183 Amar. due to the reason, it is blocking 37 scenario's - 12/2:New FUT Defect 5089 under fix eta 12/2 EOD 11/28:Defect 4729 retest in progress. ETA to rest complete 11/28 11/25:Defect 4729 - is open .ETA To fix 11/26 11/21:Defect 4729 under fix. ETA to fix is 11/21 EOD 11/17 : FUT in Progress | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2538 | OTCE0974 | 04.Enhancement | 02.IF - Intel Foundry | Screen enhancement to populate the assignment priority at SO line item | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IF_POSO_Console%20ID%202538_Screen%20enhancement%20to%20populate%20the%20assignment%20priority%20at%20SO%20line%20item.pptx?d=wb604529f6dfa4ee9a34ee38252f8e282&csf=1&web=1&e=VzSPjf | 02.No | 01.Yes |  | 2024-12-11 | Jill Matalon | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-12-06 07:21 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 0.5 | 0.5 | 0974 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-19 | 2025-09-09 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-11-14 |  |  |  | 0 | 08. Not Applicable | 1672 | [9 empty] | FUT sent for approval | 2025-10-10 | Y | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2564 | OTCE0966 | 04.Enhancement | 01.IP - Intel Product | Implementation of an enhancement to add DNI(Do not improve) flag to SO1 after creation of SO1 within 2DN cross-dock model | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-12-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF3E175B3-FE86-4E0D-B406-91482CBEEE20%7D&file=Console%20ID_2564_IP_%20Implementation%20of%20an%20enhancement%20to%20replicate%20sales%20order%20blocks%20and%20holds%20from%20SO1%20to%20SO2%20within%202DN%20cross-dock%20model.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-03 | shelly.lafree@intel.com | 01.Approved | 2024-12-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-11-26 00:26 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-19 | 01.S4 |  |  | 0.5 | 0.5 | 0966 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | [5 empty] | 2025-06-20 | 2025-10-10 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 2620 | [7 empty] | 4. Completed | 1. Approved no action | 11/28: Awaiting Intel approval 11/25: Awaiting Intel approval 11/21:Sent for approval -But defect opened 4795 11/17: Sent for approval -Addressing Opens 11/14 - Awaiting approval (no defects). 11/11 - Sent for approval 11/6: Awaiting 3794 fix to complete FUT 11/4:defect 3974 10/30: Defect 3974 under fix | 2025-10-08 | N | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA 1118 |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2563 | OTCE0965 | 04.Enhancement | 01.IP - Intel Product | Implementation of an enhancement to replicate sales order blocks and holds from SO1 to SO2 within 2DN cross-dock model | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-12-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA85F3145-BCF1-4E32-8237-94F3131C8EA4%7D&file=Console%20ID_2563_IP_%20Implementation%20of%20an%20enhancement%20to%20replicate%20sales%20order%20blocks%20and%20holds%20from%20SO1%20to%20SO2%20within%202DN%20cross-dock%20model.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-03 | shelly.lafree@intel.com | 01.Approved | 2024-12-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-27 | 100% | 2025-08-19 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-19 | Sprint 22 Week 2 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-11-26 00:26 | cell-link@smartsheet.com | 2026-02-19 06:56 | 10 | 2024-12-19 | 01.S4 |  |  | 1 | 1 | 0965 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | [5 empty] | 2025-04-25 | 2025-09-12 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2619 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/17-Opens are closed and object sent for approval 2/13-sent for approval 2/12:Defects fixed-Under retest 2/10:Defects fixed-Under retest 2/10: Defect #6885 fix in progress , tech ETA 02/10 2/5: Defect 6885 fixed , retesting in progress Action on functional team (Srinivas) 2/3: Defect 6885 - Issues with Hold updates happening on wrong line items Defect :6635-> Status Hold issue - not yet fixed by tech team (it works previously) 2/2: Delivery and billing block(change log) issue still with Tech team 1/29: defect 6635 - ETA - 1/29- Change log not working 1/27: defect 6635 - ETA - 1/27 1/22:Sent for approval 1/20:Defect 6470 ETA To send for approval 1/21 1/14: defect 5649 Under retest 1/8:Defect 5649 to be fixed. retesting failed and assign back to Tech team 1/6:Defect 5649 fixed-Under Retest. ETA 1/7 01/05: Defect 5649 in Fix. ETA TBD . Defect fix is delayed and reassigned to another developer at present 12/24:Defect 5649 in Fix. ETA TBD . Defect fix is delayed and reassigned to another developer at present 12/23:Defect 5649 in Fix. ETA 12/23 12/18: defect 5649 to be fixed - ETA 12/18 the application Job is getting failed here. Need to check with basis team as the code is working fine. When In SO1, we have changed Delivery block header and saved. It is not reflecting in SO2 | 2025-11-05 | N | 05. OTC IP |  |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2357 | OTCE0844 | 04.Enhancement | 01.IP - Intel Product | Enhancement to create Fiori report which will expose custom table data (Non dampened and dampened orders) sent from PDH system to S4 HANA | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE054535B-6AA5-4517-BE61-EEEA2B3815BA%7D&file=Console%20ID_2357_IP_%20Enhancement%20to%20create%20Fiori%20Report%20which%20will%20expose%20custom%20table(Dampened%20and%20Non%20Dampened%20Order)%20data%20as%20Fiori.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-01 | Shelly Lafree | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1 | 0844 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-26 | 2025-12-03 | 2025-11-26 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2025-12-03 |  |  |  | 0 | 08. Not Applicable | 2479 | [7 empty] | 4. Completed | 1. Approved no action | 11/28:FUT is approved. 11/25:All Opens are closed .Awaiting Intel approval .ETA To receive approval 11/28 11/21: Sent for Approval. ETA to get approval 11/28 | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2334 | OTCE0795 | 04.Enhancement | 01.IP - Intel Product | Custom Z table(DH) creation & updates to the outbound order acknowledgements | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2334_IP_OTC_DH%20table%20creation%20%26%20outbound%20interface%20updates.pptx?d=wbe4d0295d3d2494f98a2d8872fbb5d39&csf=1&web=1&e=xwtTtJ | 02.No | 01.Yes |  | 2024-10-28 | Shelly Lafree | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-13 | 100% | 2025-03-21 | 2025-08-01 | 2025-08-08 | 2025-04-29 | 100% | 2025-08-04 | 2025-08-29 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-29 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-13 | 2025-08-22 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-22 | 2025-08-22 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0795 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-05-23 | 2025-09-12 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 1974 | [7 empty] | 1. On Track | 3. Awaiting Approval | 9/8: FUT sent for approval | 2025-09-12 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1769 | OTCE0794 | 04.Enhancement | 01.IP - Intel Product | BOT for compilation of invoices in scheduled mode using pre-defined template | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_PRC%20Invoice%20compilation%20BOT_Interface.pptx?d=wce3cc77d48a843e1bb3ccd7f722e6352&csf=1&web=1&e=ag9pKs | 01.Yes | 01.Yes |  | 2024-10-28 | Shelly Lafree | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-14 | 2025-03-14 | 100% | 2025-04-09 | 2025-03-31 | 2025-04-04 | 2025-06-20 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | 2025-04-14 | 2025-06-13 | 2025-07-16 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-10-23 09:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 04.S4 BOT |  |  | 1 | 1 | 0794 |  | R3 ITC1 | [6 empty] | 2025-04-09 | 2025-04-09 | 2025-04-09 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2025-03-14 | 2025-06-13 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2137 | [9 empty] | 9/22: S4 FUT submitted to Intel for Review as of now (Conditional approval. Note: ETA for EDDAR Readiness is WW44, post which changes will be required in UiPath Program also. Risk 2022 has been raised. | 2025-06-13 | N | 05. OTC IP | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 19 |  | 2025-10-15 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2241 | OTCE0742 | 04.Enhancement | 01.IP - Intel Product | Create CHM condition records(ZADC & ZSDC) from Order SIM output | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID__IP_Create%20CHM%20condition%20records(ZADC%20%26%20ZSDC)%20from%20Order%20SIM%20output.pptx?d=wf96a2b50c7f347bf9a4a3349e85ecb3a&csf=1&web=1&e=rNfTxa | 02.No | 01.Yes |  | 2024-10-16 | Sarah A Miller | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-24 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-10-31 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-12-03 | 2025-11-21 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2024-10-23 | 01.S4 |  |  | 2 | 2 | 0742 |  | R3 ITC1 | [6 empty] | 2025-04-24 | 2025-04-24 | 2025-04-24 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-25 | 2025-08-15 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2474 | [7 empty] | 4. Completed | 1. Approved no action | 1/8: Approval received from Luis today 1/8: All defects closed Awaiting approval. ETA - Today EOD 1/6:All defects closed Awaiting approval 01/05: defect Defect 5935 5942 need to fixed. 12/23: defects and opens closed . Working with Intel in review of the same 12/16: defect 5460 fix is in progress. ETA - 12/16 12/11: 5460 Defect fixed.retest in progress 12/9:Opens addressed awaiting approval 12/2:Awaiting approval. 11/28:FUT in progress. ETA to send for approval 11/28 11/25: S4 Testing completed FUT in progress with CHM team. ETA 11/26 EOD To send for approval 11/21:Defect 4386 under fix(Defect reopened) 11/17: Defect 4452 fixed.Retest in progress 11/11 - Defect 4386. ETA is 11/12 11/6: FUT Defect 4115 under fix 11/4: FUT Defect 4115 under fix | 2025-10-31 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | Yes | ZPARAMS entries for the new Sales Org | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2240 | OTCE0741 | 04.Enhancement | 01.IP - Intel Product | Enhancement to standard SAP report V_NLN to generate prices for Order SIM by material selection | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_IP_Order%20Sim%20Enhancement.pptx?d=wdbf335ff838d4b22a38b0fcab196daf4&csf=1&web=1&e=pVhAdq | 02.No | 01.Yes |  | 2024-10-16 | Sarah A Miller | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-04-04 | 2025-04-04 | 100% | 2025-04-15 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2026-01-29 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2026-01-29 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-22 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2024-10-23 | 01.S4 |  |  | 2 | 2 | 0741 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-15 | 2025-04-15 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-11-22 | 2025-11-22 | 2025-11-22 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2473 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/21:Awaiting approval ETA 11/21 11/17:All defects closed awaiting final approval 11/14 - Defect 4521. ETA from tech is 11/14. Resend for approval by 11/17 11/11 - Sent for approval. 11/6:New Defect Logged 11/4:addressing opens in approval 10/30 - FUT under approval 10/23 - FUT in progress. | 2025-10-03 | N | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA 1119 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | Yes | ZPARAMS entries for the new Sales Org | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2065 | OTCE0737 | 04.Enhancement | 01.IP - Intel Product | Implement Standard BADI to activate Credit Limit Request Workflow | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2065_OTC_RICEFW_Implement%20Standard%20BADI%20to%20activate%20Credit%20Limit%20Request%20Workflow.pptx?d=w94d0b6076856407ca6f7a93a744ee693&csf=1&web=1&e=1HWmd7 | 02.No | 01.Yes |  | 2024-10-15 | Sarah A Miller | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-02-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-07 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-10-23 | 01.S4 |  |  | 0.5 | 0.5 | 0737 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | [5 empty] | 2025-06-20 | 2025-10-10 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 2505 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27: FUT sent after opens addressed 2/26: Defect 7693 -Minor fix ETA 2/25 2/19: FUT is in progress. ETA - 2/20 to send for approval 2/17:Standard BADI with custom enhancement has not been working. Observation - 10 validation are works out of 11. 7068 defect needs to be aligned with Business.Functional team(Nilesh) is working with Businesses in accelerating their response 2/12:Standard BADI with custom enhancement has not been working. Observation - 10 validation are works out of 11. 7068 defect needs to be aligned with Business.Functional team(Nilesh) is working with Businesses in accelerating their response 2/10: 7068 defect to be fixed. 2/5 All open issues are closed FUT in progress. 2/3: All the opens are closed. defect 6714 fixed. Re-testing is in progress. 2/2:Defect 6714 pending fix. 1/29: Defect 6714 pending fix. 1/27: Only 50% of FUT can be performed as remaining is dependent on OTCW1683 which is still under BUild 1/22: Only 50% of FUT can be performed as remaining is dependent on OTCW1683 which is still under BUild 1/14 : Build in progress.Approval task is in sprint 23. FUT execution comes under sprint 22 from Mid of S22 12/16 : FUT is planned in Sprint 22.Incorrect plan | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2169 | OTCE0721 | 04.Enhancement | 01.IP - Intel Product | BOT Enhancement to Bulk Create Credit/Debit | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_O-020-080_Reference_Bulk_Creation_Credit_Debit.pptx?d=w3664c498df4f4f19bc8f77a94e89026b&csf=1&web=1&e=cQwc6A | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-01 | 2025-09-05 | 2025-11-05 | 100% | 2025-11-05 | 2025-10-06 | 2025-11-07 | 2026-01-07 | 100% | 2025-12-11 | 2025-10-06 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0721 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-05 | 2025-11-05 |  |  | 2025-12-11 | 2026-01-07 | 2025-12-11 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-04-25 | 2025-11-07 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2748 | [7 empty] | 4. Completed | 1. Approved no action | 12/2:Awaiting approvals. Closing The opens raised by Intel . ETA To close opens 12/2 EOD 11/28:Awaiting Intel approval 11/25:FUT Sent for approval 11/21: Parallel testing with BOT+ABAP in progress.ETA to complete overall testing 11/25 11/17: BOT Dev IN progress-Parallel FUT we are doing | 2025-11-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2170 | OTCE0720 | 04.Enhancement | 01.IP - Intel Product | BOT for compilation of invoices in ad-hoc mode to the customer request via e-mail | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-210_JPY%20Intel%20XDock%20BOT_Interface.pptx?d=w65380a09bbb24c5a963e0c0b29362e2d&csf=1&web=1&e=l1WpJP | 01.Yes | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-10 | 2025-06-02 | 2025-06-06 | 2026-01-07 | 100% | 2025-12-11 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  | 2025-12-03 | 2025-12-19 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2024-10-24 | 04.S4 BOT |  |  | 4 | 4 | 0720 |  | R3 ITC1 | [6 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-12-11 | 2026-01-07 | 2025-12-11 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-12-19 | 2026-01-09 | 2025-12-19 | [5 empty] | 2025-03-28 | 2025-09-12 |  |  | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 2751 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/18: FUT sent for approval. Walkthrough completed. waiting for approval | 2025-12-05 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | Yes | UiPath Config to be updated for AdHoc BOT | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2218 | OTCE0719 | 04.Enhancement | 01.IP - Intel Product | Utility program for open sales order conversion for IP OM team, that will be used during mergers & acquisitions. | 05. OTC IP | 5.11 OTC IP - Order Management | 06. Dev In Progress | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD2E8A6F3-E0E6-4015-935B-D5E266AE589B%7D&file=Console%20ID_2218_OTC_IF_RICEFW%20Intake%20Form_Sales%20order%20conversion_0924.pptx&action=edit&mobileredirect=true&CID=CEA4B264-0B6F-495A-9B04-A758A1E31ABD&wdLOR=cA63E2E01-4640-4332-8444-3DCA5AD224F3 | 02.No | 02.No |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-06-20 | 100% | 2025-08-28 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2026-02-17 | 2025-10-31 | 2025-11-05 | 2026-03-31 | 99% | 2026-03-31 | 2025-10-31 | 2025-11-05 | 2026-03-31 | 96% | 2026-03-31 | [15 empty] | 2026-03-31 | 2026-03-31 |  |  | 2026-02-20 | 2026-03-31 |  | 100% | 98% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-31 | N | 99% | 2026-03-31 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | divyad4@deloitte.com | 2026-04-03 00:35 | 6 | 2024-10-17 | 01.S4 |  |  | 4 | 4 | 0719 | INT-CR1481 | R3 ITC1 | [6 empty] | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  |  | 2026-03-31 | [19 empty] | 2026-03-31 | [6 empty] | 2025-05-23 | 2025-09-12 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 1617 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 4/3:Defect 8856 identified in review. Fix in progress 27/3: FUT sent for approval. Walkthrough completed. Waiting for intel reviews and Approval 20/3: Defect 8443 to be fixed. 3/13:FUT In progress 3/11:FUT In progress from 3/9 3/6:Dev ETA 3/6 2/19: Still Dev In Progress... 2/12: Still Dev In Progress... 2/10:Still Dev In Progress... | 2025-11-05 | N | 05. OTC IP |  |  |  | 03/23: FUT in progress. Defects closed. ETA 03/31 Current status: FUT in progress Issue: FUT delayed. Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/31 |  | 3. Watch item | On track for S23+ | Defects | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-03-31 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2242 | OTCE0718 | 04.Enhancement | 01.IP - Intel Product | Pricing routines for Order SIM price calculations | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_IP_Pricing%20routines%20for%20Order%20SIM%20price%20calcuations.pptx?d=w9c2d093fd7dd4ec4953ea701bc69a6e7&csf=1&web=1&e=23C3Xc | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-05 | 2025-05-30 | 2025-06-06 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-29 | 2025-07-11 | 2025-07-11 | 100% | 2025-09-09 | 2025-08-29 | 2025-09-12 | 2025-07-11 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-09-01 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-23 | 01.S4 |  |  | 1 | 1 | 0718 |  | R3 ITC1 | [6 empty] | 2025-04-05 | 2025-04-11 | 2025-04-05 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-23 | 2025-09-12 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2291 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2025-09-12 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2256 | OTCE0715 | 04.Enhancement | 01.IP - Intel Product | PIP 2A1 Interface: Custom Program to update Price catalogue | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Condole%20ID_2256_%20PIP%202A1%20Interface%20Custom%20Program%20to%20update%20Price%20catalogue.pptx?d=w5ae504ead53748e28e2886f86cab9a77&csf=1&web=1&e=IquEbr | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-20 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-20 | [15 empty] | 2025-09-20 | 2025-09-20 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-23 | 01.S4 |  |  | 1 | 1 | 0715 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | [12 empty] | 2025-09-20 | 2025-09-20 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-06-20 | 2025-10-10 |  |  | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 1502 | [7 empty] | 4. Completed | 1. Approved no action | 1/9: Approval received from Luis today 1/8:Defect 6307 -ETA 1/7 EOD.1 /6:Defect 6307 -ETA 1/7 EOD. 01/05: FUT sent for approval. Walkthrough completed. opens are in progress (defect 5959) 12/24:Awaiting approval 12/23: defect 5888, 5878 fixed and ready for re-testing 12/18: defect 5297 to be fixed. ETA - 12/18 12/16: as requested by tech team, new defect 5688 is created for 716 & 715 - ETA - 12/17 12/11:Defect 5427 in fix. ETA 12/11 12/8:Defect 5297 ETA 12/8 EOD 12/4: Defect fixed and Re-testing is in progress 12/2:FUT Defect 5129 Under fix 11/28:Defect 3917 fixed-test in progress 11/25:Defect 3917 -Initial fix is done . Currently Functional is working on clarifications asked by technical team .This will be moved back to tech on 11/26 11/21;Defect 3917 -MW Issues persists ETA TBD 11/17:Defect 3917 -At present Sorting RFC issues 11/14 - Defect 3917. ETA from tech is 11/17. FUT completion by 11/24 11/13 EP: Provide revised FUT due date 11/11 - RFC Destination needs to be setup for Open Text 11/6:Due to defect prioritization within available tech team - This defect was deprioritized. Will not be able to close FUT in S19 11/4:defect 3917 is deprioritized due to other defects. Untill this is fixed cannot test FUT. 10/30 : Defect 3917 - defect fix in progress. ETA is 10/31 10/23 - FUT & TUT in progress | 2025-09-12 | N | 05. OTC IP |  |  |  |  | ETA 1205 Defect 3917 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-20 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2264 | OTCE0714 | 04.Enhancement | 01.IP - Intel Product | Requirement is to Update CPN when there is a change in MMID of SOLI MMID triggered by Blue Yonder as part of Product Substitution | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B705F42BB-3480-403F-973D-174B8C900D89%7D&file=Console%20ID_2264_IP_%20Update%20CPN%20when%20there%20is%20a%20change%20in%20MMID%20of%20SOLI%20MMID%20triggered%20by%20Blue%20Yonder%20as%20part%20of%20Product%20Substitution%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-11 | Sarah A Miller | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-08-01 | 100% | 2025-08-09 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-09 | [15 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-09-05 | 2025-10-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-10-03 | 2025-10-03 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-23 | 01.S4 |  |  | 1 | 1 | 0714 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 |  | 2025-08-09 | 2025-08-15 | 2025-08-09 | 2025-08-09 | [12 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | [5 empty] | 2025-04-25 | 2025-08-15 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 1511 | [9 empty] | 10/6: FUT sent for approval | 2025-08-15 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2305 | OTCE0713 | 04.Enhancement | 01.IP - Intel Product | IP End customer CI :Custom Validations to be accommodated for Price masking condition | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_2305_IP_End%20customer%20CI%20Custom%20Validations%20to%20be%20accommodated%20for%20Price%20masking%20condition.pptx?d=w236f21b98d2e4027ac484cb1bb3b4bb2&csf=1&web=1&e=ttyafH | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0713 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-04-25 | 2025-09-12 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2120 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/2:All Opens closed. Awaiting approval 11/28:Awaiting Intel approval 11/25:Defect 4969 fix in progress.ETA 11/26 11/21: FUT awaiting approval. ETA 11/25 11/17 : FUT in Progress | 2025-12-05 | Y | 05. OTC IP |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2339 | OTCE0712 | 04.Enhancement | 01.IP - Intel Product | Sold to party & Ship to party customer codes determination based on DUNS & DUNS4 numbers | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_IP_OTC_Sold%20to%20%26%20Ship%20to%20determination%20from%20DUNS%20%26%20DUNS4%20%20.pptx?d=w3ac22bee30754d9ab684ff992d6ed5b8&csf=1&web=1&e=aRhAKL | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved | 2024-10-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-29 | 2025-09-05 | 2025-04-29 | 100% | 2025-08-04 | 2025-09-26 | 2025-10-10 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-26 | 2025-10-10 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-08 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-10-29 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-17 | 01.S4 |  |  | 1 | 1 | 0712 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-04 | 2025-09-05 | 2025-08-04 |  | 2025-08-04 | 2025-10-10 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | [5 empty] | 2025-06-20 | 2025-10-10 |  |  | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 2285 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 10/23 - Defect 3747 to be picked 10/17: defect 3747 10/6: Sent for approval | 2025-10-10 | Y | 05. OTC IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1793 | OTCE0683 | 04.Enhancement | 01.IP - Intel Product | Enhancement request for adding End customer partner in Pricing Catalogue and user exit for enabling End Customer based pricing in Sales Order | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-11 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_1793_IP_Enhancement%20request%20for%20adding%20End%20customer%20partner%20in%20Pricing%20Catlogue%20and%20user%20exit%20for%20enabling%20in%20Sales%20Order.pptx?d=wfdde329b2fd44abfabc64c3e085892be&csf=1&web=1&e=aZroFg | 02.No | 01.Yes |  | 2024-10-03 | Shelly Lafree | 01.Approved | 2024-10-11 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-10-28 | 2024-12-06 | 2024-12-06 | 100% | 2024-11-20 | 2024-11-27 | 2024-12-04 | 2025-01-17 | 100% | 2025-01-18 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-03-07 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-19 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-10-03 06:54 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0683 |  | R3 ITC1 | [6 empty] | 2024-11-20 | 2024-12-06 | 2024-11-20 |  | 2025-01-18 | 2025-01-18 | 2025-01-18 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-03-19 | 2025-03-21 | 2025-03-19 | [5 empty] | 2024-12-06 | 2025-02-21 |  |  | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 2659 | [10 empty] | 2025-02-21 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1974 | OTCE0659 | 04.Enhancement | 02.IF - Intel Foundry | IF : Apply a Delivery Block Hold for Items with Multiple Schedule lines (MSL) which have price differences identified | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_1974_IF_Apply%20a%20Delivery%20Block%20Hold%20for%20Items%20with%20%20Multiple%20Schedule%20lines%20(MSL)%20having%20price%20differences%20identified.pptx?d=wd35bb2bad8ac42ccbc04522c815a2b95&csf=1&web=1&e=T7Qep9 | 02.No | 02.No |  | 2024-09-22 | Jill Matalon | 01.Approved | 2024-10-03 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-04 | 2025-01-09 | 2025-01-09 | 100% | 2024-12-18 | 2024-12-25 | 2025-01-01 | 2025-02-14 | 100% | 2025-02-15 | 2025-02-07 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-21 | 2025-02-07 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-21 | [15 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-03-07 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-20 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0659 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-09 | 2024-12-18 |  | 2025-02-15 | 2025-02-15 | 2025-02-15 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | [12 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-03-20 | 2025-03-21 | 2025-03-20 | [5 empty] | 2025-01-09 | 2025-02-21 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 1925 | [10 empty] | 2025-02-21 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-03-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2070 | OTCE0658 | 04.Enhancement | 01.IP - Intel Product | IP-Intel Federal To capture DPAS Rating from Dassian table on Sales Order and screen enhancement | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDA4558EB-9A39-4FE0-ABAC-32F98CFE1BE0%7D&file=IP%20Intel%20Federal%20Console%20ID-2070-Capture%20DPAS%20Rating%20from%20Dassian%20table%20and%20update%20in%20condition%20group5%20field%20at%20SOLI%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Stacey Carter | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-07 | 2025-05-02 | 2025-05-09 | 2025-04-29 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-16 | 2025-08-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-23 | 2025-08-08 | 2025-08-08 | N | 100% | 2025-08-01 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-23 | 01.S4 |  |  | 0.5 | 0.5 | 0658 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-21 | 2025-03-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-05-16 |  | Federal |  | 0 | 08. Not Applicable | 2514 | [10 empty] | 2025-06-13 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2040 | OTCE0654 | 04.Enhancement | 01.IP - Intel Product | Enhancement for idoc validation and creation of custom basic type, segment for Outgoing invoice EDI | 05. OTC IP | 5.3 OTC IP - Billing and Rebates | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing%20Console%20_BR-130-040_Enhacement%20for%20idoc%20validations%20and%20custom%20segments.pptx?d=w2ffb2f90f1c44df28f5c0c83916e6ccb&csf=1&web=1&e=kLvuK6 | 01.Yes | 01.Yes |  | 2024-09-18 | Shelly Lafree | 01.Approved | 2024-10-03 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-10-21 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-14 | 2024-12-20 | 2024-12-27 | 2025-02-14 | 100% | 2025-02-09 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-21 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | [15 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-27 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0654 |  | R3 ITC1 | [6 empty] | 2024-12-14 | 2024-12-14 | 2024-12-14 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-08 | [12 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | [5 empty] | 2024-12-06 | 2025-02-21 |  |  | 2025-03-21 |  |  |  | 0 | 03. IP Customers | 2015 | [9 empty] | 8/25: Sent for approval | 2025-02-21 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-08 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2115 | OTCE0651_IP | 04.Enhancement | 04.GTS | Enrich the delivery data transfer data from S/4 IP to GTS with the 'new' vs 'used indicator | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2024-10-02 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/17.%20International%20Trade/4%20Working%20Documents/RICEF%20Intake/GTS_RICEFW%20Intake%20Form_V2.0_%20%27New%27%20vs%20%27Used%27%20Indicator%20-%20IP.pptx?d=w795224c12f7d49489a21114bab68a567&csf=1&web=1&e=7iarlC | 01.Yes | 01.Yes |  | 2024-09-18 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-12 | 2025-07-04 | 2025-07-16 | 100% | 2025-07-25 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-10-17 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-17 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-16 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-03 | 01.S4 |  |  | 1 | 1 | 0651 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-10-17 | 2025-10-24 | 2025-10-17 |  | 2025-10-17 | 2025-10-24 | 2025-10-17 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-08-15 | GTS |  |  | 0 | 08. Not Applicable | 2788 | [7 empty] | 4. Completed | 17. FUT In progress | 12/17 - Pending review 12/15: FUT documents are internally reviewed. ETA 12/16 12/04: FUT Documentation to be completed. ETA 12/04 11/18:OnTrack - FUT documentation in Progress. ETA for completion is 11/28 | 2025-10-24 | Y | 05. OTC IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2114 | OTCE0651_IF | 04.Enhancement | 04.GTS | Enrich the delivery data transfer data from S/4 IF to GTS with the 'new' vs 'used indicator | 04. OTC IF | 4.9 OTC IF - GTS | 10. Object Complete | Y | 2024-10-02 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/17.%20International%20Trade/4%20Working%20Documents/RICEF%20Intake/GTS_RICEFW%20Intake%20Form_V2.0_%20%27New%27%20vs%20%27Used%27%20Indicator%20-%20IF.pptx?d=w03c5dd31b0474ff89b1dad534adea45d&csf=1&web=1&e=bh6lj2 | 01.Yes | 01.Yes |  | 2024-09-18 | Jill Matalon | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-12 | 2025-07-04 | 2025-07-16 | 100% | 2025-07-25 | 2025-10-17 | 2025-10-24 | 2025-10-14 | 100% | 2025-10-17 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-17 | 2025-10-31 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-16 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-03 | 01.S4 | OTCE0651_IP | 03.Medium | 0.2 | 0.2 | 0651 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-10-17 | 2025-10-24 | 2025-10-17 |  | 2025-10-17 | 2025-10-24 | 2025-10-17 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-08-15 | GTS |  |  | 0 | 08. Not Applicable | 2787 | [7 empty] | 4. Completed | 17. FUT In progress | 12/17 - FUT Documentation is completed. Internal review in progress. Will be sent for approval by 12/19 12/04: FUT documentation in progress. 11/18 : TUT approval in Progress | 2025-10-24 | Y | 04. OTC IF | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2116 | OTCE0650 | 04.Enhancement | 04.GTS | Enhancement for Legal Control Exception Scenarios | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2024-10-02 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/17.%20International%20Trade/4%20Working%20Documents/RICEF%20Intake/GTS_RICEFW%20Intake%20Form_V2.0_%20Legal%20Control%20Exception%20Scenarios.pptx?d=w3f9079a543ca44909ed4c2b2668eec97&csf=1&web=1&e=Xcd0MA | 01.Yes | 01.Yes |  | 2024-09-23 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-23 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-03 | 01.S4 |  |  | 1 | 1 | 0650 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-18 |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-01-23 | 2026-02-04 | 2026-01-23 | [5 empty] | 2025-04-18 | 2025-10-31 |  |  | 2026-02-04 | GTS |  |  | 0 | 08. Not Applicable | 2716 | [7 empty] | 1. On Track | 17. FUT In progress | 12/15: FUT documents are internally reviewed. ETA 12/16 8/25 - FUT Dates to be adjusted. Revised TUT date is 9/12 11/18: FUT defect 12/04: FUT documentation in progress. ETA 12/05 | 2025-10-31 | Y | 05. OTC IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1620 | OTCE0642 | 04.Enhancement | 04.GTS | Enrich Intrastat dispatch declaration with missing transactions and missing data fields in IP S/4Hana system | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2024-10-02 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC0B3639F-FEB0-416A-9FBF-B5D8DF202A40%7D&file=1620_GTS_RICEFW%20-%20Intake%20Form_Intrastat%20-%20Collect%20Sales%20Related%20Information%20(IP).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-19 | 100% | 2025-03-17 | 2025-06-06 | 2025-06-13 | 2025-04-22 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-23 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-07-18 | 2025-07-18 | 2025-07-18 | vasamohan@deloitte.com | 2024-09-11 12:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-03 | 01.S4 |  |  | 1 | 1 | 0642 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-21 | 2025-03-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2026-01-23 | 2026-02-04 | 2026-01-23 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2026-02-04 | GTS |  |  | 0 | 08. Not Applicable | 1743 | [7 empty] | 3. Off Track | 23. Data Dependency | 12/17 - Pending config from OTC and awaiting test data. 12/15: Awaiting test data from OTC for Dispatch, OTC CR is pending approval | 2025-07-18 | N | 05. OTC IP | [7 empty] | Data Dependency | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2074 | OTCE0641 | 04.Enhancement | 01.IP - Intel Product | Enhancement to determine transportation zone based on country key and region for drop ship scenario | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7EC3D05D-B32A-4BC0-9799-1C3D8BE4D78F%7D&file=IP_Console%20ID%202074_Determine%20transportation%20zone%20based%20on%20country%20key%20and%20region%20for%20drop%20ship%20scenario%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-07-18 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-11 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-01 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 0.5 | 0.5 | 0641 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-07-18 | 2025-03-28 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-05-23 |  |  |  | 0 | 08. Not Applicable | 2075 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/17: One open is being addressed 11/14 - Defect 4288 ETA from tech is 11/14. FUT Completion by 11/17 11/11:Defect 4288 under fix .ETA TBD 11/4:Awaiting approval 10/30-FUT Resent for approval 10/17: defect 3754 10/10:FUT sent for approval -Review -New defect created 3555 10/6: Sent for approval | 2025-09-12 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2072 | OTCE0640 | 04.Enhancement | 01.IP - Intel Product | Enhancement to support inbound interface 4B3 consignment issue | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF6FE189F-53E3-46D0-9941-6F9698F68613%7D&file=IP_Console%20ID%202072_Enhancement%20to%20support%20inbound%20interface%20for%204B3%20consignmentr%20issue.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-28 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-08-01 | 100% | 2025-07-31 | 2025-07-04 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-31 | 2025-07-04 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-31 | [15 empty] | 2025-07-31 | 2025-07-31 |  |  | 2025-09-01 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0640 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-31 | 2025-08-01 | 2025-07-31 |  | 2025-07-31 | 2025-08-15 | 2025-07-31 | 2025-07-31 | [12 empty] | 2025-07-31 | 2025-07-31 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2025-02-28 | 2025-08-15 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2073 | [9 empty] | 9/22: FUT sent for approval | 2025-08-15 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2064 | OTCE0614_IP | 04.Enhancement | 01.IP - Intel Product | Implement Standard Credit/Collection BADI | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2064_OTC_RICEFW_Implement%20Standard%20Credit%26Collection%20BADI.pptx?d=w975edd25b190497b82bcbd8488841762&csf=1&web=1&e=zNPfgw | 02.No | 01.Yes |  | 2024-09-09 | Shelly Lafree | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-15 | 2025-06-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-11 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-11 | 2025-07-18 | 2025-04-18 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-01 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0614 | INT-CR0149 | R3 ITC1 | [6 empty] | 2025-03-15 | 2025-03-15 | 2025-03-15 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2504 | [9 empty] | 9/12: FUT sent for approval | 2025-07-18 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2064 | OTCE0614_IF | 04.Enhancement | 01.IP - Intel Product | Implement Standard Credit/Collection BADI | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2064_OTC_RICEFW_Implement%20Standard%20Credit%26Collection%20BADI.pptx?d=w975edd25b190497b82bcbd8488841762&csf=1&web=1&e=zNPfgw | 02.No | 01.Yes |  | 2024-09-11 | Jill Matalon | 01.Approved | 2024-10-03 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-22 | 2025-08-29 | 2025-09-05 | 2025-08-13 | 100% | 2025-08-09 | 2025-10-03 | 2025-10-10 | 2025-08-13 | 100% | 2025-08-09 | 2025-10-03 | 2025-10-10 | 2025-04-18 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-01 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-10-04 | 01.S4 | OTCE0614_IP | 03.Medium | 0.2 | 0.2 | 0614 | INT-CR0149 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-08-09 | 2025-09-05 | 2025-08-09 |  | 2025-08-09 | 2025-10-10 | 2025-08-09 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2025-06-20 | 2025-10-10 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 2503 | [9 empty] | 9/22: FUT sent for approval | 2025-10-10 | Y | 04. OTC IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-10-10 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1963 | OTCE0579 | 04.Enhancement | 01.IP - Intel Product | Enhancement to extend standard table which will record fixed plant and fixed material indicator selected in Order promiser adapter screen for a sales order line item | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B850A266E-476B-4A6D-80E5-FE6D82FD8648%7D&file=Console%20ID_1963_IP_%20Creation%20of%20Custom%20table%20which%20will%20record%20Fixed%20plant%20and%20fixed%20material%20fields%20selected%20in%20order%20promiser%20screen%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-27 | Shelly Lafree | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 02.Intel | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-04 | 2025-01-10 | 2025-01-10 | 100% | 2025-01-17 | 2025-04-04 | 2025-04-11 | 2025-09-21 | 100% | 2025-09-16 | 2025-05-02 | 2025-05-16 | 2025-09-29 | 100% | 2025-09-16 | 2025-05-02 | 2025-05-16 | 2025-10-04 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-08-13 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-30 | 01.S4 |  |  | 1 | 1 | 0579 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-17 | 2025-01-17 |  | 2025-09-16 | 2025-09-21 | 2025-09-16 |  | 2025-09-16 | 2025-09-29 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 1916 | [9 empty] | 9/8: FUT sent for approval | 2025-05-16 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-04 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1962 | OTCE0578 | 04.Enhancement | 01.IP - Intel Product | Enhancement to create custom table which will log Blue Yonder Order promiser errors and all other communications from S4 to BY and BY to S4.​ | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA2D8456B-18B1-4099-A953-3082058AD6E2%7D&file=Console%20ID_1962_IP_%20Creation%20of%20Custom%20table%20which%20will%20log%20BY%20errors%20and%20other%20communications%20to%20BY%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-27 | Shelly Lafree | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 02.Intel | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-02 | 2025-01-31 | 2025-02-14 | 100% | 2025-02-14 | 2025-10-24 | 2025-10-31 | 2025-11-20 | 100% | 2025-11-26 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-26 | [15 empty] | 2025-11-26 | 2025-11-26 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-30 | 01.S4 |  |  | 1 | 1 | 0578 |  | R3 ITC1 | [6 empty] | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-26 | 2025-11-26 | [12 empty] | 2025-11-26 | 2025-11-26 |  |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | [5 empty] | 2025-01-31 | 2025-06-13 |  |  | 2025-07-04 |  |  |  | 0 | 08. Not Applicable | 2396 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/4: Awaiting approval 10/30 - Awaiting approval 10/23 - Awaiting approval | 2025-12-05 | Y | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1961 | OTCE0577 | 04.Enhancement | 01.IP - Intel Product | List of fields that needs to be mapped to Order promiser Adaptor for order confirmation | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5C7E48C3-01D6-4B86-ADA1-043710124F8A%7D&file=Console%20ID_1961_IP_%20List%20of%20S4%20fields%20that%20needs%20to%20be%20mapped%20into%20order%20promiser%20Adaptor.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-27 | Shelly Lafree | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 02.Intel | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-04 | 2025-01-10 | 2025-01-10 | 100% | 2025-01-15 | 2025-04-04 | 2025-04-11 | 2025-09-21 | 100% | 2025-09-16 | 2025-05-02 | 2025-05-16 | 2025-09-29 | 100% | 2025-09-16 | 2025-05-02 | 2025-05-16 | 2025-10-04 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-08-13 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-30 | 01.S4 |  |  | 1 | 1 | 0577 |  | R3 ITC1 | [6 empty] | 2025-01-15 | 2025-01-15 | 2025-01-15 |  | 2025-09-16 | 2025-09-21 | 2025-09-16 |  | 2025-09-16 | 2025-09-29 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-08-22 | 2025-09-05 | 2025-08-22 | [5 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2341 | [10 empty] | 2025-05-16 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-04 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1738 | OTCE0576 | 04.Enhancement | 01.IP - Intel Product | Enhancement to update the B2B PO number at the return Order | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Enhancement%20to%20update%20the%20B2B%20PO%20number%20at%20the%20return%20Order.pptx?d=we615caec63924b25bbb59f0b493e6302&csf=1&web=1&e=No9JLj | 02.No | 01.Yes |  | 2024-08-27 | Shelly Lafree | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-10-28 | 2024-12-06 | 2024-12-06 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-05-02 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-28 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-08-27 08:04 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 0.5 | 0.5 | 0576 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2024-12-13 | 2024-12-13 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | [5 empty] | 2024-12-06 | 2025-04-18 |  |  | 2025-04-04 |  |  |  | 0 |  | 2193 | [9 empty] | 8/18: FUT sent for approval | 2025-04-18 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1453 | OTCE0575 | 04.Enhancement | 01.IP - Intel Product | Enhancement to create custom table and field and determining actions on return Order in S4 | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Enhancement%20to%20add%20custom%20field%20and%20determining%20actions%20on%20return%20Order%20in%20S4.pptx?d=w576879508e0442cfae16fc30ad33119f&csf=1&web=1&e=ypVr6Z | 02.No | 01.Yes |  | 2024-08-27 | Shelly Lafree | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-03-21 | 2025-04-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-04-04 | 2025-04-04 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-08-27 08:04 | cell-link@smartsheet.com | 2026-03-18 08:56 | 10 | 2024-09-03 | 01.S4 |  |  | 1 | 1 | 0575 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2024-10-25 | 2025-01-31 |  |  | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 2489 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 9/12: FUT sent for approval | 2025-01-31 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZPARAMS entries for the new Plants | No |  | No |  | 2026-02-16 | 2026-03-20 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1721 | OTCE0524 | 04.Enhancement | 01.IP - Intel Product | Enhancement to support inbound interface from IRC2 (Intel Registration Center) B-app to S4 | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B32600765-FFFF-40C8-BB96-ACAAEA727A59%7D&file=IP_Console%20ID%201721_Enhancement%20to%20support%20Inbound%20interface%20from%20IRC2%20(Intel%20Registration%20Center)%20B-app%20to%20S4.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-08-09 | Shelly Lafree | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-18 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-18 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-18 | [15 empty] | 2025-02-18 | 2025-02-18 |  |  | 2025-03-14 | 2025-04-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-03 | 2025-04-04 | 2025-04-04 | N | 100% | 2025-04-14 | Not Applicable | R3 Build & UT Sprint 12 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-08-09 07:52 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-10 | 01.S4 |  |  | 0.5 | 0.5 | 0524 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-18 | 2025-01-18 | 2025-01-18 |  | 2025-02-18 | 2025-02-21 | 2025-02-18 | 2025-02-18 | [12 empty] | 2025-02-18 | 2025-02-18 |  |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | [5 empty] | 2024-10-25 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 1807 | [10 empty] | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1715 | OTCE0523 | 04.Enhancement | 01.IP - Intel Product | Enhancement to put user status hold on IRC2 (Intel Registration Center) relevant orders | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B07BB1598-646B-4EEF-8057-85124B9DCE59%7D&file=IP_Console%20ID%201715_Enhancement%20to%20put%20user%20status%20hold%20on%20IRC2%20(Intel%20Registration%20Center)%20orders.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-08-09 | Shelly Lafree | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-25 | 2024-10-25 | 100% | 2025-01-17 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-09 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-13 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-02-07 | 2025-02-07 | 2025-02-07 | pgaroo@deloitte.com | 2024-08-09 07:52 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-10 | 01.S4 |  |  | 0.5 | 0.5 | 0523 |  | R3 ITC1 | [6 empty] | 2025-01-17 | 2025-01-17 | 2025-01-17 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-02-09 | 2025-02-21 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2024-10-25 | 2025-02-07 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 1803 | [7 empty] | 2. At Risk | 17. FUT In progress | 9/12: FUT sent for approval | 2025-02-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1714 | OTCE0522 | 04.Enhancement | 01.IP - Intel Product | Enhancement to put billing block at the line-item level for IRC2 (Intel Registration Center) relevant orders | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9EAE5595-F107-40D1-8171-83EA915527AE%7D&file=IP_Console%20ID%201714_Enhancement%20to%20put%20billing%20block%20on%20IRC2%20(Intel%20Registration%20Center)%20orders.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-08-09 | Shelly Lafree | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-24 | 2024-10-25 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-09 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-11 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-08-09 07:52 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-10 | 01.S4 |  |  | 0.5 | 0.5 | 0522 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-09 | 2025-02-21 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-21 | 2025-08-29 | 2025-08-21 | [5 empty] | 2024-10-24 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 1802 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1718 | OTCE0489 | 04.Enhancement | 01.IP - Intel Product | Enhancement to support outbound interface from S4 to IRC2 (Intel registration center) B-app | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B176A4F0C-CCF7-4188-9819-F2B838E5E20C%7D&file=IP_Console%20ID%201718_Enhancement%20to%20support%20outbound%20interface%20from%20S4%20to%20IRC2%20(Intel%20Registration%20Center).pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2024-07-26 | Shelly Lafree | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-16 | 2024-09-16 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-11 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-11 | [15 empty] | 2025-02-11 | 2025-02-11 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-07-26 07:50 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-10 | 01.S4 |  |  | 1 | 1 | 0489 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-11 | 2025-02-21 | 2025-02-11 | 2025-02-11 | [12 empty] | 2025-02-11 | 2025-02-11 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2024-09-16 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 1805 | [10 empty] | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1680 | OTCE0486 | 04.Enhancement | 02.IF - Intel Foundry | Price Swamp: For Order Repricing | 04. OTC IF | 4.11 OTC IF - Order Management | 10. Object Complete | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID%20834__IF_Price%20Swamp%20program%20for%20order%20repricing.pptx?d=wfa4aa18cb1f9454fa97c4f31dc80b814&csf=1&web=1&e=l7nDVg | 02.No | 01.Yes |  | 2024-07-26 | Jill Matalon | 01.Approved | 2024-08-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-18 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-09 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-03-14 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-27 | 2025-04-18 | 2025-04-11 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-07-26 07:50 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0486 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-18 | 2025-01-18 | 2025-01-18 |  | 2025-02-09 | 2025-02-21 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-09-13 | 2025-01-31 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2526 | [10 empty] | 2025-01-31 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1734 | OTCE0444 | 04.Enhancement | 01.IP - Intel Product | Credit/Debit Memo Approval Workflow | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Billing%20%26%20Revenue/B%26R%20Filled%20RICEFW%20Template/Billing_Console_BR-130-020_credit%20debit%20memo%20approval%20workflow.pptx?d=w5b6b2b61983c40d7a9e2ab2904ff2714&csf=1&web=1&e=peZnxQ | 02.No | 01.Yes |  | 2024-07-12 | Shelly Lafree | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2024-11-29 | 2024-12-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-25 | 2024-12-06 | 2024-12-06 | N | 100% | 2025-01-31 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-17 | 2025-01-17 | 2025-01-17 | vasamohan@deloitte.com | 2024-07-12 10:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0444 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | [5 empty] | 2024-09-13 | 2025-01-17 |  |  | 2024-12-06 |  |  |  | 0 | 08. Not Applicable | 2191 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-01-17 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1701 | OTCE0443 | 04.Enhancement | 01.IP - Intel Product | Enhancement to include the API custom field, S4 custom fields and append to the S4 standard tables, order header and item | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/IP_Console%20ID%20838_Enhancement%20to%20include%20the%20API%20custom%20field,%20S4%20custom%20fields%20and%20append%20to%20the%20S4%20standard%20tables,%20order%20header%20and%20item.pptx?d=w4ba5ce6286524158a53802ad44df061b&csf=1&web=1&e=X6ggrj | 02.No | 01.Yes |  | 2024-07-12 | Shelly Lafree | 01.Approved | 2024-07-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-05 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-21 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-02-07 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-07 | 2025-02-21 | N | 100% | 2025-02-25 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | vasamohan@deloitte.com | 2024-07-12 10:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0443 |  | R3 ITC1 | [6 empty] | 2024-08-21 | 2024-08-21 | 2024-08-21 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-02-25 | 2025-02-25 | 2025-02-25 | [5 empty] | 2024-08-16 | 2025-01-17 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 1795 | [10 empty] | 2025-01-17 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1130 | OTCE0440 | 04.Enhancement | 01.IP - Intel Product | Implement NCNR (non-cancellable / non reschedule) and NCNRR (non-cancellable non-returnable) validation for the order create and changes​ | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE8FF7419-2BBC-427F-8317-30FBFF581E16%7D&file=Console_ID_140_Implement%20NCNR%20(non%20cancellable%20non%20reschedule)%20check%20validation%20for%20the%20order%20change.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-09 | Shelly Lafree | 01.Approved | 2024-07-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-20 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-18 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-03-07 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-07-09 00:12 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0440 |  | R3 ITC1 | [6 empty] | 2024-08-20 | 2024-08-20 | 2024-08-20 |  | 2025-01-18 | 2025-01-18 | 2025-01-18 |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | [12 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-08-16 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 1522 | [10 empty] | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 143 | OTCE0406 | 04.Enhancement | 01.IP - Intel Product | Implement a warning and hold for the sales order line item having material with Characteristic maintained as Q-SPEC | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console_ID_143_IP_Material%20characteristic%20Spec%20Code=Q.pptx?d=wd1b7cb8baa354647a71f15f85d8c39b3&csf=1&web=1&e=QJQkzX | 02.No | 01.Yes |  | 2024-06-21 | Shelly Lafree | 01.Approved | 2024-07-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-12 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-02 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | 2024-10-07 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | [15 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-01-24 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-13 | 2025-02-07 | 2025-02-21 | N | 100% | 2025-02-21 | Not Applicable | R3 Build & UT Sprint 10 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 0406 | INT-CR0494 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | [12 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-02-21 | 2025-02-21 | [6 empty] | 2024-08-30 | 2024-12-20 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 2002 | [10 empty] | 2024-12-20 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2024-12-20 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 617 | OTCE0404 | 04.Enhancement | 01.IP - Intel Product | Enhancement to capture business rules for entitlement and Warranty of return orders | 05. OTC IP | 5.4 OTC IP - Returns | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/Return%20Console_IP_R-190-010_Enhancement%20for%20Business%20Rules.pptx?d=we17e4f02925a48e5bc34e1126e251256&csf=1&web=1&e=f5veSf | 02.No | 01.Yes |  | 2024-06-21 | Shelly Lafree | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-17 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-03-21 | 2025-04-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-04-04 | 2025-04-04 | N | 100% | 2025-04-04 | Not Applicable | R3 Build & UT Sprint 12 | 2025-02-07 | 2025-02-07 | 2025-02-07 | pgaroo@deloitte.com | 2024-06-21 03:27 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0404 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-04-04 | 2025-04-04 | [6 empty] | 2024-08-30 | 2025-02-07 |  |  | 2024-12-13 |  |  |  | 0 | 08. Not Applicable | 1590 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-02-07 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 792 | OTCE0398_IP | 04.Enhancement | 04.GTS | Enhance data transfer from SAP S4/HANA to SAP GTS for Customs Declaration Creation using Proforma Invoice - IP | 05. OTC IP | 5.9 OTC IP - GTS | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/GTS_RICEFW%20Intake%20Form_V2.0_%20792_SD0C%20BADI%20Enrichment.pptx?d=w1012e8a14f5345d799b9663c247eeb9c&csf=1&web=1&e=nj9e1W | 02.No | 01.Yes |  | 2024-06-21 | Shelly Lafree | 01.Approved | 2024-06-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-22 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-11-05 | 2025-12-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-09 | 2025-12-19 | N | 100% | 2025-12-15 | Not Applicable | R3 Build & UT Sprint 21 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-21 03:27 | cell-link@smartsheet.com | 2026-02-27 01:55 | 10 |  | 01.S4 | OTCE0398_IF | 03.Medium | 0.2 | 0.2 | 0398 |  | R3 ITC1 | [6 empty] | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 | [12 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-12-15 | 2026-01-09 | 2025-12-15 | [5 empty] | 2024-08-16 | 2025-01-31 |  |  | 2025-10-10 | GTS |  |  | 0 | 08. Not Applicable | 2359 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No | Retest the new company code for US export declaration | No |  | No |  | 2026-03-30 | 2026-04-03 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 522 | OTCE0235 | 04.Enhancement | 02.IF - Intel Foundry | Credit and Collections - Credit Check Step Configuration | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/522_OTC_RICEFW%20CFIN%20Credit%20Check%20Rule%20Configuration.pptx?d=w473f0602096c41289cf003287a2bbbc0&csf=1&web=1&e=Hq22Dx | 02.No | 01.Yes |  | 2024-05-21 | Jill Matalon | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-25 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-25 | 2024-07-22 | 2024-07-22 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-07 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-05-16 | 2025-06-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-01 | 2025-05-30 | 2025-06-06 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-05-17 09:21 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0235 |  | R3 ITC1 | [6 empty] | 2024-07-25 | 2024-07-25 | 2024-07-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-07-19 | 2024-12-20 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 1675 | [10 empty] | 2024-12-20 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 556 | OTCE0234 | 04.Enhancement | 02.IF - Intel Foundry | Implement mapping between customer’s risk class and credit check steps | 04. OTC IF | 4.6 OTC IF - Credit and Collections | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/556_OTC_RICEFW%20CFIN%20Credit%20Risk%20Class%20Mapping.pptx?d=we68a588013a643cb82daa5d719fd410c&csf=1&web=1&e=EKR8mh | 02.No | 01.Yes |  | 2024-05-21 | Jill Matalon | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-25 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-26 | 2024-07-22 | 2024-07-22 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | 2024-09-16 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-18 | [15 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-01-24 | 2025-02-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-13 | 2025-02-14 | 2025-02-14 | N | 100% | 2025-02-22 | Not Applicable | R3 Build & UT Sprint 10 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-05-17 09:21 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0234 |  | R3 ITC1 | [6 empty] | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | [12 empty] | 2024-12-18 | 2024-12-18 |  |  | 2025-02-22 | 2025-02-22 | 2025-02-22 | [5 empty] | 2024-07-19 | 2024-12-20 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 1683 | [10 empty] | 2024-12-20 | N | 04. OTC IF | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2024-12-20 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 335 | OTCE0191 | 04.Enhancement | 01.IP - Intel Product | Generate Order e-Ack’s in sales order to customer in accordance with specific business rules. | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-05-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC5D4A8CC-948F-423E-AEA3-F2B6D7951499%7D&file=Console%20ID_335_IP_Generate%20Order%20e-Ack%E2%80%99s%20in%20sales%20order%20to%20customer%20in%20accordance%20with%20specific%20business%20rules.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-05-06 | Shelly Lafree | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-25 | 2024-07-17 | 2024-07-17 | 100% | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-30 | 100% | 2024-08-30 | 2024-08-19 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-05 | 2024-08-19 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-05 | [15 empty] | 2024-10-05 | 2024-10-05 |  |  | 2024-11-01 | 2024-11-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-21 | 2024-11-08 | 2024-11-08 | N | 100% | 2025-01-24 | Not Applicable | R3 Build & UT Sprint 9 | 2024-10-04 | 2024-10-04 | 2024-10-04 | pgaroo@deloitte.com | 2024-05-06 10:15 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0191 |  | R3 ITC1 | [6 empty] | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-30 | 2024-08-30 |  |  | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | [12 empty] | 2024-10-05 | 2024-10-05 |  |  | 2025-01-24 | 2025-01-24 | 2025-01-24 | [5 empty] | 2024-07-17 | 2024-10-04 |  |  | 2024-11-08 |  |  |  | 0 | 08. Not Applicable | 2606 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2024-10-04 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-05 | 2024-10-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 325 | OTCE0088 | 04.Enhancement | 01.IP - Intel Product | Determine sale orders to trigger availability check with BY | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console%20ID_325_IP_%20determine%20sale%20orders%20to%20trigger%20availability%20check%20with%20BY%E2%80%99.pdf?csf=1&web=1&e=wht2YW | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-25 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-23 | 100% | 2024-08-22 | 2024-08-26 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | 2024-08-26 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | [15 empty] | 2024-11-01 | 2024-11-01 |  |  | 2025-02-14 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-03 | 2025-03-14 | 2025-03-14 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-11-01 | 2024-11-01 | 2024-11-01 | pgaroo@deloitte.com | 2024-04-19 04:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0088 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-08-22 | 2024-08-23 | 2024-08-22 |  | 2024-11-01 | 2024-11-01 | [14 empty] | 2024-11-01 | 2024-11-01 |  |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | [5 empty] | 2024-07-19 | 2024-11-01 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 2090 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change |  | 2024-11-01 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 7 |  | 2024-11-01 | 2024-11-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 301 | OTCE0087 | 04.Enhancement | 01.IP - Intel Product | Implement sales order cancellation control on order changes through B2B & WOM | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console_ID_301_IPG_Implement%20sales%20order%20cancellation%20control%C2%A0on%20order%20changes%20through%20B2B%20%26%20WOM.pdf?csf=1&web=1&e=yWg6cQ | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-18 | 2024-08-01 | 2024-08-01 | 100% | 2024-08-01 | 2024-08-02 | 2024-08-02 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | 2024-09-16 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | [15 empty] | 2025-01-03 | 2025-01-03 |  |  | 2025-03-21 | 2025-03-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-03 | 2025-03-28 | 2025-03-28 | N | 100% | 2025-03-28 | Not Applicable | R3 Build & UT Sprint 12 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-04-19 04:42 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0087 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-03 | 2025-01-10 | 2025-01-03 | 2025-01-03 | [12 empty] | 2025-01-03 | 2025-01-03 |  |  | 2025-03-28 | 2025-03-28 | [6 empty] | 2024-08-01 | 2024-12-20 |  |  | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 2824 | [10 empty] | 2024-12-20 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-10 | 2025-01-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 139 | OTCE0086 | 04.Enhancement | 01.IP - Intel Product | Implement Minimum order quantity (MOQ) and Delivery unit increment check validation for order creation and change | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD349357E-5D2F-461D-949A-5730C1681B3F%7D&file=Console_ID_139_IPG_Implement%20Requested%20delivery%20date%20(RDD)%20in%20the%20past%2C%20Minimum%20order%20quantity%20(MOQ)%20and%20Delivery%20unit%20increment%20check%20for%20order%20creation%20and%20change.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-25 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | [15 empty] | 2025-01-08 | 2025-01-08 |  |  | 2024-12-06 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-02 | 2025-01-24 | 2025-01-24 | N | 100% | 2025-02-07 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-04-19 04:42 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0086 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-01-08 | 2025-01-24 | 2025-01-08 | 2025-01-08 | [12 empty] | 2025-01-08 | 2025-01-08 |  |  | 2025-02-07 | 2025-02-07 | 2025-02-07 | [5 empty] | 2024-07-19 | 2025-01-24 |  |  | 2025-01-24 |  |  |  | 0 | 08. Not Applicable | 2001 | [10 empty] | 2025-01-24 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 134 | OTCE0084 | 04.Enhancement | 01.IP - Intel Product | Notification when Multiple Schedule lines are created | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/O-IP-040-0005_OTC_Notification%20when%20Multiple%20Schedule%20lines%20are%20created.pptx?d=wf36bbd256aad45549db3f5c92ce7591d&csf=1&web=1&e=zDUk61 | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-20 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-02-14 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-28 | 2025-03-14 | N | 100% | 2025-03-07 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | pgaroo@deloitte.com | 2024-04-19 04:42 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-10 | 01.S4 |  |  | 1 | 1 | 0084 |  | R3 ITC1 | [6 empty] | 2024-08-20 | 2024-08-20 | 2024-08-20 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-03-07 | 2025-03-14 | 2025-03-07 | [5 empty] | 2024-08-16 | 2025-01-17 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 2795 | [10 empty] | 2025-01-17 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 133 | OTCE0083 | 04.Enhancement | 01.IP - Intel Product | Price Swamp program for order repricing | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-06-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/O-IP-040-0004_OTC_Price%20Swamp%20program%20for%20order%20repricing.pptx?d=w974bccd1607b4fc58dd8917ba6feb42a&csf=1&web=1&e=QAfCK0 | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-05 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-08 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-18 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-03-21 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-27 | 2025-04-18 | 2025-04-11 | N | 100% | 2025-04-11 | Not Applicable | R3 Build & UT Sprint 12 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-04-19 04:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0083 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 |  | 2025-01-18 | 2025-01-18 | 2025-01-18 |  | 2025-01-30 | 2025-01-31 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-04-11 | 2025-04-18 | [6 empty] | 2024-08-02 | 2025-01-31 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2794 | [10 empty] | 2025-01-31 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 130 | OTCE0080 | 04.Enhancement | 01.IP - Intel Product | IP: Pricing Date determination based on RGID and CGID | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/O-040-0002_OTC_IP_Pricing%20Date%20Calculation%20based%20on%20RGID%20and%20CGID.pptx?d=w5714ce6072b1499988c6880c4b6cc799&csf=1&web=1&e=XJc4kS | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-26 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-18 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-18 | [15 empty] | 2024-12-18 | 2024-12-18 |  |  | 2024-11-01 | 2024-12-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-04 | 2024-12-11 | 2024-12-11 | N | 100% | 2024-12-12 | Not Applicable | R3 Build & UT Sprint 8 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-04-19 04:42 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-08 | 01.S4 |  |  | 1 | 1 | 0080 |  | R3 ITC1 | [6 empty] | 2024-08-05 | 2024-08-05 | 2024-08-05 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-12-18 | 2024-12-20 | 2024-12-18 | 2024-12-18 | [12 empty] | 2024-12-18 | 2024-12-18 |  |  | 2024-12-12 | 2024-12-12 | 2024-12-12 | [5 empty] | 2024-08-02 | 2024-11-22 |  |  | 2024-12-11 |  |  |  | 0 | 08. Not Applicable | 2791 | [10 empty] | 2024-11-22 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2024-12-20 | 2024-12-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 21 | OTCE0079 | 04.Enhancement | 01.IP - Intel Product | Implement duplicate PO check validations for order create and change | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console_ID_21_IPG_Implement%20duplicate%20PO%20check%20validations%20for%20order%C2%A0create%20and%20change.pdf?csf=1&web=1&e=lcVsMv | 02.No | 01.Yes |  | 2024-04-19 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-04 | 2024-07-08 | 2024-07-08 | 100% | 2024-06-28 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | [15 empty] | 2025-01-08 | 2025-01-08 |  |  | 2024-12-06 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-02 | 2025-01-24 | 2025-01-24 | N | 100% | 2025-02-07 | Not Applicable | R3 Build & UT Sprint 10 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-04-19 04:42 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0079 |  | R3 ITC1 | [6 empty] | 2024-06-28 | 2024-07-08 | 2024-06-28 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-01-08 | 2025-01-24 | 2025-01-08 | 2025-01-08 | [12 empty] | 2025-01-08 | 2025-01-08 |  |  | 2025-02-07 | 2025-02-07 | 2025-02-07 | [5 empty] | 2024-07-08 | 2025-01-24 |  |  | 2025-01-24 |  |  |  | 0 | 08. Not Applicable | 1425 | [10 empty] | 2025-01-24 | Y | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 28 | OTCE0021 | 04.Enhancement | 01.IP - Intel Product | Credit hold release dashboard at line-item level | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | Y | 2024-04-23 | 01. Approved | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29&viewid=c4c37517%2D41b5%2D478f%2D8da3%2Dc109204256a0 | 02.No | 01.Yes |  | 2024-03-26 | Shelly Lafree | 01.Approved | 2024-04-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  | NA | NA | NA | NA | 2024-05-24 | 2024-07-19 | 2024-07-19 | 100% | 2024-08-23 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2026-01-31 | 2025-01-31 | 2025-02-21 | 2025-09-05 | 100% | 2026-03-13 | 2025-01-31 | 2025-02-21 | 2025-09-05 | 100% | 2026-03-13 | [15 empty] | 2026-03-13 | 2026-03-13 |  |  | 2025-10-03 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-07 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-02-21 | 2025-02-21 | 2025-02-21 | vasamohan@deloitte.com | 2024-03-22 16:09 | cell-link@smartsheet.com | 2026-03-12 23:25 | 10 |  | 01.S4 |  |  | 4 | 4 | 0021 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [12 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | [5 empty] | 2024-07-19 | 2025-02-21 |  |  | 2026-02-04 |  |  |  | 0 | 08. Not Applicable | 1430 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/5: 4 defects but nothing blocking approval, we will get conditional approval by 2/6 2/3: Defect 6667 is moving on a CR discussion . Business alignment pending. Working towards Conditional approval. Action on credit and collections team to discuss with Business 2/2: 6667 - Tech will be checking on the backend complexity from the additional filter. remaining all the opens are closed as of now. 1/29: 6646 The Release/check and Hold buttons - Fiori support 6667 - 6667 Filter issues )- Fiori . Also Fiori+ Tech alignment needed 6652 - Tech support (PPDM issue)- CR 1/30 6668 - Fiori support (But not critical on sign off) 1/27: 6647 fixed and closed defects 6646 and 6652,6667,6668- ETA 1/28 On track 1/20:PPDP defects under fix 5686, 6295 1/14: defect 5686, 5975, 6241, 6242 to be fixed by Tech team. Plan is to send for approval on or before 16/01 1/8: defect 5975 and 5686, 6087 to be fixed 1/6: Defects : ETA 1/9 To close all defects 5686,5975, 01/05: defect 5686 to be fixed 12/24:Defect 5756 in progress. ETA 12/24 12/23: Defect 5756, 5853 with Tech team 12/18:Defect 5676,5664 - ETA TBD 5696,5686 - Fixed and re-testing is in progress. 12/11: Credit dashboard fixes will hand over as per eta is this week 12/12 . 12/9:Credit dashboard Issues .ETA To receive for testing 12/12 12/2:Credit dashboard under defects. 11/28:Credit dashboard defects fix in progress 11/25:Credit dashboard Issues 11/21: The dashboard under redesign ETA 11/28 11/17- Tech team + Fiori Team is currently working on fixes. ETA is 11/28. FUT to follow post fixes (12/05) 11/11 - Multiple defects. Re-design of Fiori app. FUT on hold 11/6:Major Issue on custom fiori screen . 3401/4105/4106 Defects WIP 11/4:Defects 3401, 4105,4015, 4106 10/30 : Defect 3401, 3480 Under fix 10/17 Defects 3480, 3401,3515,3202 | 2025-02-21 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-13 | 2026-03-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 22 | OTCE0002_IP | 04.Enhancement | 01.IP - Intel Product | Populate Incoterms and Shipping conditions from Ship to party | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | Y | 2024-04-16 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/Console%20ID_22_IPG_Ship%20to%20drives%20the%20incoterm%20%26%20SC.pdf?csf=1&web=1&e=ZN74Bn | 02.No | 01.Yes |  | 2024-04-15 | Shelly Lafree | 01.Approved | 2024-04-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-04 | 2024-07-08 | 2024-07-08 | 100% | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2024-08-14 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-08-02 | 2024-08-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-03 | 2024-08-09 | 2024-08-09 | N | 100% | 2024-08-14 | Not Applicable | R3 Build & UT Sprint 4 | 2024-09-02 | 2024-09-02 | 2024-09-02 | pgaroo@deloitte.com | 2024-04-15 00:41 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | OTCE0002_IF | 04.Low | 0.1 | 0.1 | 0002 |  | R3 ITC1 | [6 empty] | 2024-07-09 | 2024-07-09 | 2024-07-09 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-08-14 | 2024-08-14 | 2024-08-14 | [5 empty] | 2024-07-08 | 2024-09-02 |  |  | 2024-08-09 |  |  |  | 0 | 08. Not Applicable | 1426 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2024-09-02 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | OTCC1341 | 03.Conversion | 01.IP - Intel Product | Payer Profile Data Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/OTC/INT-CR0397_OTC_Create automation program for Payer Segment Data.pptx?d=w50a2c7e142604a7fab0c23b1dbeb514b&csf=1&web=1&e=oDJn29 | 02.No | 01.Yes |  | 2025-04-01 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-19 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-20 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-23 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-04-01 12:01 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-04-02 | 01.S4 |  |  | 1 | 1.45 | 1341 | INT-CR0396 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | [5 empty] | 2025-05-02 | 2025-07-18 |  |  | 2025-09-10 |  |  |  | 0 |  | 2850 | [9 empty] | 9/22: FUT sent for approval | 2025-07-18 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | OTCC1340 | 03.Conversion | 01.IP - Intel Product | Payer Segment Data Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/OTC/INT-CR0396_OTC_Create automation program for Payer Profile Data.pptx?d=wfdbd5d18492445f58ca57fe34821fb66&csf=1&web=1&e=yBUnxU | 02.No | 01.Yes |  | 2025-04-01 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-19 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-20 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-04-01 12:01 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-04-02 | 01.S4 |  |  | 1 | 1.45 | 1340 | INT-CR0397 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | [5 empty] | 2025-05-02 | 2025-07-18 |  |  | 2025-09-10 |  |  |  | 0 |  | 2849 | [7 empty] | 1. On Track | 3. Awaiting Approval | 9/22: FUT sent for approval | 2025-07-18 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | OTCC1339 | 03.Conversion | 01.IP - Intel Product | Payer Relationship Data Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/01. PMO/05. Scope and Change Control/Change Control/Change Request Decks/OTC/INT-CR0395_OTC_Create automation program for Payer Relationship data conversion.pptx?d=w9792cf541bbd4e8f94f46a1820b0aa01&csf=1&web=1&e=Bkpe4k | 02.No | 01.Yes |  | 2025-04-01 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-30 | 2025-06-06 | 100% | 2025-06-06 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-18 | 2025-10-13 | 2025-10-17 | 2025-10-23 | 100% | 2025-10-14 | 2025-10-20 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-11-05 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-21 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2025-04-01 12:01 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-04-02 | 01.S4 |  |  | 1 | 1.45 | 1339 | INT-CR0395 | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-06 | 2025-06-06 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-14 | 2025-10-23 | 2025-10-14 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-03 |  |  |  | 0 |  | 2848 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/2:Awaiting Intel approval 11/28:awaiting approval 11/25: Addressing Opens as part of Intel Review . Good to close all opens by 11/26 11/21:Addressing opens as part of FUT Review. ETA to resend for approval 11/24. 11/11 - Sent for approval 11/6:FUT will be sent for approval 11/6 | 2025-11-07 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2823 | OTCC1232 | 03.Conversion | 01.IP - Intel Product | Intel Federal Data conversion for Contract ITD costs | 05. OTC IP | 5.1 OTC IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/Intel%20Federal/WRICEF_Intake%20forms/IFL_conversion%20for%20Contract%20ITD%20costs.pptx?d=wb34d7e8207f3416483024f7eb9de5d9a&csf=1&web=1&e=Bw4yos | 02.No | 02.No |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 03.Dassian |  | 03.Dassian | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-18 | 2025-04-30 | 2025-08-13 | 100% | 2025-07-25 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-10-01 | 2025-10-27 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-20 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-27 | 2025-10-27 | 2025-10-27 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1232 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2025-04-30 | 2025-10-27 |  |  | 2026-01-30 |  | Federal |  | 0 |  | 1457 | [7 empty] | 1. On Track | 16. Intel Owned | 10/30 - Federal are Intel owned objects | 2025-10-27 | N | 05. OTC IP |  |  |  | Need updates from Keith/Kevin |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2822 | OTCC1231 | 03.Conversion | 01.IP - Intel Product | Intel Federal Data conversion for Bill Plans | 05. OTC IP | 5.1 OTC IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/Intel%20Federal/WRICEF_Intake%20forms/IFL_conversion%20for%20Bill%20Plans.pptx?d=wc68c320aedc840f88b27b47389e898d0&csf=1&web=1&e=Ep86vE | 02.No | 02.No |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 03.Dassian |  | 03.Dassian | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-18 | 2025-04-30 | 2025-08-13 | 100% | 2025-07-25 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-07-28 | 2025-08-08 | 2025-08-13 | 100% | 2025-07-25 | 2025-10-01 | 2025-10-27 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-20 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-27 | 2025-10-27 | 2025-10-27 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1231 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2025-04-30 | 2025-10-27 |  |  | 2026-01-30 |  | Federal |  | 0 |  | 1456 | [7 empty] | 1. On Track | 16. Intel Owned | 10/30 - Federal are Intel owned objects | 2025-10-27 | N | 05. OTC IP |  |  |  | Need updates from Keith/Kevin |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2815 | OTCC1229 | 03.Conversion | 01.IP - Intel Product | Data conversion of open Federal Contracts from ECC to Dassian S4. | 05. OTC IP | 5.1 OTC IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/Intel%20Federal/WRICEF_Intake%20forms/OTC%20IFL%20Conversion%20RICEFWS/Intel%20Federal%20Data%20Conversion%20-%20Contracts%20RICEFW.pptx?d=w970dc59b2f4e4735a8dae4f1130dbe68&csf=1&web=1&e=3YpR1L | 02.No | 02.No |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 03.Dassian |  | 03.Dassian | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-18 | 2025-04-30 | 2025-08-13 | 100% | 2025-07-25 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-07-28 | 2025-08-08 | 2025-08-13 | 100% | 2025-07-25 | 2025-10-01 | 2025-10-27 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-20 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-27 | 2025-10-27 | 2025-10-27 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1229 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2025-04-30 | 2025-10-27 |  |  | 2026-01-30 |  | Federal |  | 0 |  | 2388 | [7 empty] | 1. On Track | 16. Intel Owned | 10/30 - Federal are Intel owned objects | 2025-10-27 | N | 05. OTC IP |  |  |  | Need updates from Keith/Kevin |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2814 | OTCC1228 | 03.Conversion | 01.IP - Intel Product | Data conversion for Federal Contracts - Contract Fees/Retention/Incentive Fee Formulas | 05. OTC IP | 5.1 OTC IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/Intel%20Federal/WRICEF_Intake%20forms/OTC%20IFL%20Conversion%20RICEFWS/Intel%20Federal%20Data%20Conversion%20-%20ContractRetentionIncentive%20Fees%20RICEFW.pptx?d=w9993221215a1470d8c1b374831a86dfe&csf=1&web=1&e=JivHDo | 02.No | 02.No |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 03.Dassian |  | 03.Dassian | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-18 | 2025-04-30 | 2025-08-13 | 100% | 2025-07-25 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-10-01 | 2025-10-27 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-20 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-27 | 2025-10-27 | 2025-10-27 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1228 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2025-04-30 | 2025-10-27 |  |  | 2026-01-30 |  | Federal |  | 0 |  | 2387 | [7 empty] | 1. On Track | 16. Intel Owned | 10/30 - Federal are Intel owned objects | 2025-10-27 | N | 05. OTC IP |  |  |  | Need updates from Keith/Kevin |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2813 | OTCC1227 | 03.Conversion | 01.IP - Intel Product | Data conversion for Intel Federal Contract WBS Assignments | 05. OTC IP | 5.1 OTC IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/Intel%20Federal/WRICEF_Intake%20forms/OTC%20IFL%20Conversion%20RICEFWS/Intel%20Federal%20Data%20Conversion%20-%20Contract%20WBS%20Assignment%20RICEFW.pptx?d=wc89a9ffd580049e891e1743a5ae0cca6&csf=1&web=1&e=n8we1U | 02.No | 02.No |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 03.Dassian |  | 03.Dassian | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-18 | 2025-04-30 | 2025-08-13 | 100% | 2025-07-25 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-10-01 | 2025-10-27 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-27 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-27 | 2025-10-27 | 2025-10-27 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1227 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [13 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-11-05 | 2025-11-07 | [6 empty] | 2025-04-30 | 2025-10-27 |  |  | 2025-11-07 |  | Federal |  | 0 |  | 2789 | [7 empty] | 4. Completed |  |  | 2025-10-27 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2258 | OTCC0803 | 03.Conversion | 05.CFIN | Open Credit Case Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2258_OTC_RICEFW_Open%20Credit%20Case%20Conversion.pptx?d=w835c54382d95448882f134e8a83e5aa6&csf=1&web=1&e=2KqMBT | 02.No | 01.Yes |  | 2024-11-08 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-16 | 2025-10-13 | 2025-10-14 | 2025-10-14 | 100% | 2025-10-13 | 2025-10-13 | 2025-10-17 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-20 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-12 | [15 empty] | 2025-11-12 | 2025-11-12 |  |  | 2025-11-19 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-07 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-11-14 | 01.S4 |  |  | 2 | 2.9 | 0803 | INT-CR1563 | R3 ITC1 | [6 empty] | 2025-06-16 | 2025-07-18 | 2025-06-16 |  | 2025-10-13 | 2025-10-14 | 2025-10-13 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-11-12 | [12 empty] | 2025-11-12 | 2025-11-12 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | [5 empty] | 2025-05-02 | 2025-07-01 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 1504 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/9:awaiting approval 12/8:Awaiting intel approval . addressing Intel Opens 12/2: Awaiting Intel approval. Review started 12/1 after disconnect 11/28:FUT sent for approval 11/25: FUT In progress. Targeting to send for approval 11/26 11/21:FUT in progress. ETA to complete 11/24 11/17 : FUT in Progress | 2025-11-07 | N | 05. OTC IP |  |  |  |  | 11/26 - End of week target to send for approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-12 | 2025-11-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2338 | OTCC0802 | 03.Conversion | 01.IP - Intel Product | Custom Z table(DH) DH tables data conversion from ECC to S4 for IP | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_2338_IP_OTC_DH%20table%20conversion.pptx?d=w9e4dc1516f2149c6adfb0085e94661bb&csf=1&web=1&e=CJ6QlN | 02.No | 01.Yes |  | 2024-10-30 | Shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-16 | 2025-05-23 | 2025-05-23 | 100% | 2025-06-11 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-28 | 2025-08-05 | 2025-07-29 | 100% | 2025-08-01 | 2025-08-13 | 2025-09-13 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-13 | 2025-09-13 | 2025-09-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2024-10-30 | 01.S4 |  |  | 2 | 2.9 | 0802 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-05 | 2025-08-01 | [13 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-05-23 | 2025-08-05 |  |  | 2025-10-24 |  |  |  | 0 | 08. Not Applicable | 2404 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/4:awaiting approval 10/30: Addressing Opens in approvals 10/17: FUT sent for approval | 2025-09-13 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-13 | 2025-08-29 | Yes | XREF Table need to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2244 | OTCC0717 | 03.Conversion | 01.IP - Intel Product | Pricing Condition records conversion | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Order%20Management/Ready%20for%20review_IP/Console%20ID_2244_IP_Pricing%20Condition%20records%20conversion.pptx?d=wba8d35da8abe48a18038705b48f3156a&csf=1&web=1&e=l2JaKS | 02.No | 01.Yes |  | 2024-10-11 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-26 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-10 | 2025-03-18 | 2025-06-24 | 100% | 2025-07-21 | 2025-03-26 | 2025-07-18 | 2025-09-10 | 100% | 2025-09-10 | [15 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-16 07:18 | 10 | 2024-10-11 | 01.S4 |  |  | 4 | 5.8 | 0717 |  | R3 ITC1 | [6 empty] | 2025-06-26 | 2025-06-26 | 2025-06-26 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [13 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2025-02-28 | 2025-03-18 |  |  | 2025-05-23 |  |  |  | 0 | 08. Not Applicable | 2293 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/17: Alignment in progress on conditional approval 11/14 - Defect 4563 is created for Internal CR. But getting conditional approval for the object 11/11:CR in proposal . But ITC1 can be executed without CR as well. Alignment discussion in progress | 2025-07-18 | N | 05. OTC IP |  |  |  | 5.1 Complete. Awaiting Approval 1211 ETA - 1118 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-10 | Yes | XREF Table need to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2207 | OTCC0679 | 03.Conversion | 05.CFIN | Open Dispute Case Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2207_OTC_RICEFW%20Open%20Dispute%20Case%20Conversion%20R3.pptx?d=w8229dc0c4c314d13a7c98c0341300ce9&csf=1&web=1&e=Soqa3y | 02.No | 02.No |  | 2024-09-30 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-30 | 2025-06-06 | 100% | 2025-06-09 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-28 | 2025-08-15 | 2025-08-29 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 2 | 2.9 | 0679 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-05 | [12 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | [5 empty] | 2025-05-16 | 2025-06-03 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 1610 | [7 empty] | 4. Completed | 1. Approved no action | 11/17:Approved. 11/14 - Awaiting approval (no defects). FUT Approval by 11/17 11/11:Awaiting Approval 11/4:Awaiting approval 10/30:Awaiting Intel approval 10/22 - Will be sent for approval today 10/17: defect 3554 10/10: Defect 3554 under fix | 2025-08-15 | N | 05. OTC IP |  |  |  | Awaiting Approval 1211 ETA Approved |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2208 | OTCC0678 | 03.Conversion | 05.CFIN | Collection Master Conversion | 05. OTC IP | 5.6 OTC IP - Credit and Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2208_OTC_RICEFW%20Collection%20Data.pptx?d=wab1c476205a84731a7a75148e50f0a3e&csf=1&web=1&e=2zwNaE | 02.No | 02.No |  | 2024-09-30 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-10 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-04-28 | 2025-05-06 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-14 | 2025-06-14 | 2025-06-06 | 100% | 2025-05-30 | [15 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-14 | 2025-06-14 | 2025-06-14 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 2 | 2.9 | 0678 |  | R3 ITC1 | [6 empty] | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-05-30 | [12 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | [5 empty] | 2025-04-18 | 2025-05-06 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 1611 | [9 empty] | 9/1: FUT sent for approval | 2025-06-14 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-14 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1936 | OTCC0636 | 03.Conversion | 01.IP - Intel Product | Output Condition (Sales) Conversion for IP R3 release | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_1936_OTC_RICEFW%20Intake%20Form_Output%20Condition_conversion%20IP.pptx?d=wb3404ffe2e8645269382fac14ad10d94&csf=1&web=1&e=RuhH9p | 02.No | 01.Yes |  | 2024-09-11 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-05-27 | 2025-05-27 | 100% | 2025-06-10 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-23 | 2025-07-01 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-09 | 2025-08-09 | 2025-08-29 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-09 | 2025-08-09 | 2025-08-09 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-11 22:25 | 10 | 2024-09-17 | 01.S4 |  |  | 4 | 5.8 | 0636 |  | R3 ITC1 | [6 empty] | 2025-06-10 | 2025-06-10 | 2025-06-10 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | [5 empty] | 2025-05-27 | 2025-07-01 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 2736 | [7 empty] | 1. On Track | 3. Awaiting Approval | Sent for approval .Awaiting Intel approval | 2025-08-09 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | Yes | XREF Table need to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-12 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1910 | OTCC0564 | 03.Conversion | 01.IP - Intel Product | Customer Material Info Record Conversion for IP R3 release | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA27E48CA-1ECF-4A79-9F86-33A907F97A3C%7D&file=Console%20ID_1910_OTC_IP_RICEFW%20Intake%20Form_Customer%20Master%20info%20rec%20conversion%20IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-24 | 2025-01-31 | 2024-10-11 | 100% | 2024-11-22 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-12-16 | 2024-12-20 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-24 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-04 | [15 empty] | 2025-04-04 | 2025-04-04 |  |  | 2025-07-09 | 2025-07-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-20 | 2025-07-14 | 2025-07-14 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2024-09-03 | 01.S4 |  |  | 1 | 1.45 | 0564 |  | R3 ITC1 | [6 empty] | 2024-11-22 | 2025-01-31 | 2024-11-22 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-04 | [12 empty] | 2025-04-04 | 2025-04-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-31 | 2024-12-20 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 1707 | [10 empty] | 2025-03-21 | N | 05. OTC IP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-04 | 2025-04-04 | Yes | XREF Table need to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1931 | OTCC0563 | 03.Conversion | 01.IP - Intel Product | Open Sales Order Conversion for IP R3 release | 05. OTC IP | 5.11 OTC IP - Order Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_1931_OTC_RICEFW%20Intake%20Form_Sales%20order%20conversion%20IP.pptx?d=w8182ba3371f949349247eeec0f0bd0c6&csf=1&web=1&e=OZ2Wmh | 02.No | 01.Yes |  | 2024-08-26 | Shelly Lafree | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-18 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-23 | 2025-08-15 | 2025-08-01 | 100% | 2025-08-18 | [15 empty] | 2025-08-18 | 2025-08-18 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2024-09-03 | 01.S4 |  |  | 2 | 2.9 | 0563 |  | R3 ITC1 | [6 empty] | 2025-06-04 | 2025-06-04 | 2025-06-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-08-18 | [12 empty] | 2025-08-18 | 2025-08-18 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | [5 empty] | 2025-02-28 | 2025-05-02 |  |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2734 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/16: awaiting intel approval. 12/11: Business reviews still in progress 12/9:There is a BY Dependent open came up-Getting the same addressed. Team working with BY Team 12/8:There is a BY Dependent open came up-Getting the same addressed 12/2:considering criticality and complexity -Multiple walkthrough's in Progress with Intel 11/28:Awaiting approval. Walkthrough discussions in progress 11/25: Intel review and approval in progress. 11/21:Awaiting approval 11/17:FUT In progress 11/14 - Defect 3921. ETA from Conversion team is 11/14. FUT Completion by 11/18 11/11:Defect 3921 went with Multiple iteration of fix. Currently retesting 11/6: Defect retest in progress 11/4:Defect 3921 10/30: Defect 3921 fix in progress. ETA is 10/31 10/23 - Load and Post Load are in progress. ETA to send for approval is 10/24 10/17: Defect 3753 | 2025-08-15 | N | 05. OTC IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-18 | 2025-08-18 | Yes | XREF Table need to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 |  | MDGM1332 | 12.Manual Conversion | 02.IF - Intel Foundry | IMO Materials | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N | [6 empty] | 2025-07-29 | Candice S Linnell | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | N/A | [6 empty] | NA | 2025-06-02 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-19 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-06-02 | 2025-06-13 |  | 0% | 2025-06-13 | [15 empty] | 2025-06-13 | 2025-06-13 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-09-10 | 2025-09-05 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-03-31 12:05 | jenoronha@deloitte.com | 2026-03-10 21:47 | 10 | 2025-07-29 | 01.S4 |  |  |  | 0 | 1332 |  | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-08-19 | 2025-08-19 | [25 empty] | 2025-09-09 | 2025-09-10 | 2025-09-09 | [5 empty] | 2025-06-13 | 2025-06-13 |  |  | 2025-09-10 |  |  |  | 0 |  | 2841 | [7 empty] | 2. At Risk | 25. Requirement Change | Dates to be adjusted in object tracker | 2025-06-13 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCR0025 | 01.Report | 07.MDG | Alternate/Preferred BOM Component Change in S4 | 09A. Master Data | 9A.2 Master Data - BOM | 09. FUT Overdue | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 100% | 2026-03-06 | [15 empty] | 2026-03-06 | 2026-03-06 |  |  | 2026-01-02 | 2026-01-07 |  | 10% | 100% |  |  |  | 02. In Progress | 04. Completed |  |  | 2025-12-15 | 2026-01-07 | 2026-01-07 | N | 55% | 2026-03-31 | Not Applicable | R3 Build & UT Sprint 23+ | 2026-02-04 | 2026-02-04 | 2026-02-04 | hasshah@deloitte.com | 2025-10-31 03:47 | cell-link@smartsheet.com | 2026-03-31 10:40 | 9 |  | 02.MDG |  |  | 1 | 0.85 |  |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2026-03-06 | [12 empty] | 2026-03-06 | 2026-03-06 |  |  |  | 2026-03-31 | 2026-03-31 | [5 empty] | 2025-11-28 | 2026-02-04 |  |  | 2026-01-07 |  |  |  | 0 |  | 3344 | [10 empty] | 2026-02-04 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 23 |  | 2026-03-06 | 2026-03-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0024 | 04.Enhancement | 07.MDG | Supplier Hierarchy | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-12-01 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-13 | [15 empty] | 2026-01-13 | 2026-01-13 |  |  | 2026-01-02 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2026-01-07 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2026-02-04 | 2026-02-04 | 2026-02-04 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2026-01-13 | [12 empty] | 2026-01-13 | 2026-01-13 |  |  | 2025-12-23 | 2026-01-07 | 2025-12-23 | [5 empty] | 2025-11-28 | 2026-02-04 |  |  | 2025-11-28 |  |  |  | 0 |  | 3343 | [10 empty] | 2026-02-04 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0023 | 04.Enhancement | 07.MDG | Sales Organization - Extended Itego datamodel + UI to govern assignment to Sales Regions | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3342 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0022 | 04.Enhancement | 07.MDG | Sales Region - Custom Itego Object to govern Sales Regions | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3341 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0021 | 04.Enhancement | 07.MDG | Customer Planning Hierarchy -IF | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-08 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3340 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0020 | 04.Enhancement | 07.MDG | Customer Planning Hierarchy -IP | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3339 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0019 | 04.Enhancement | 07.MDG | Product Planning Hierarchy -IF | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3346 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0018 | 04.Enhancement | 07.MDG | Product Planning Hierarchy -IP | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | 2025-11-17 | 2025-11-28 | 2025-11-28 | 100% | 2025-11-20 | [15 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-28 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-17 | 2025-11-28 | 2025-11-28 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | hasshah@deloitte.com | 2025-10-31 03:47 | jenoronha@deloitte.com | 2026-03-10 21:54 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | 2025-11-20 | [12 empty] | 2025-11-20 | 2025-11-20 |  |  | 2025-11-20 | 2025-11-28 | 2025-11-20 | [5 empty] | 2025-11-28 | 2025-11-28 |  |  | 2025-11-28 |  |  |  | 0 |  | 3345 | [7 empty] | 4. Completed |  |  | 2025-11-28 | Y | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-28 | 2025-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0017 | 04.Enhancement | 07.MDG | Commodity- Custom Itego Object with ~100 customer fields + UI to support governance | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  |  |  | 01.Yes |  | 2024-10-14 | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2025-01-27 | 2025-02-03 | 2025-07-25 | 100% | 2025-07-22 | 2025-01-27 | 2025-02-04 | 2025-11-21 | 100% | 2025-11-20 | 2025-07-21 | 2025-07-25 | 2025-07-25 | 100% | 2025-07-22 | 2025-02-10 | 2025-02-14 | 2025-07-25 | 100% | 2025-07-22 | [15 empty] | 2025-07-22 | 2025-07-22 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-10-27 | Not Applicable | R3 Build & UT Sprint 19 | 2025-02-14 | 2025-02-14 | 2025-02-14 | logoldstein@deloitte.com | 2024-10-15 08:23 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2025-07-22 | 2025-07-25 | 2025-07-22 |  | 2025-11-20 | 2025-11-21 | 2025-11-20 |  | 2025-07-22 | 2025-07-25 | 2025-07-22 | 2025-07-22 | [12 empty] | 2025-07-22 | 2025-07-22 |  |  | 2025-10-27 | 2025-11-07 | 2025-10-27 | [5 empty] | 2025-02-03 | 2025-02-14 | [6 empty] | 0 | 08. Not Applicable | 2226 | [7 empty] | 4. Completed |  |  | 2025-02-14 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 16 |  | 2025-07-25 | 2025-07-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0015 | 04.Enhancement | 07.MDG | Asset Location - Extended Itego datamodel with 22 custom fields + UI to support governance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-10-21 | 2024-10-11 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-28 | 2024-11-01 | 2024-11-01 | 100% | 2024-12-06 | 2024-12-16 | 2024-12-27 | 2024-11-08 | 100% | 2025-01-10 | 2025-01-27 | 2025-02-03 | 2025-02-07 | 100% | 2025-02-10 | [15 empty] | 2025-02-10 | 2025-02-10 |  |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-10 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-02-14 | Not Applicable | R3 Build & UT Sprint 10 | 2025-02-03 | 2025-02-03 | 2025-02-03 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-06 | 2024-12-06 | 2024-12-06 |  | 2025-01-10 | 2025-01-10 | 2025-01-10 | 2025-02-10 | [12 empty] | 2025-02-10 | 2025-02-10 |  |  | 2025-02-14 | 2025-02-21 | 2025-02-14 | [5 empty] | 2024-10-25 | 2025-02-03 | [6 empty] | 0 | 08. Not Applicable | 2225 | [10 empty] | 2025-02-03 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 10 |  | 2025-02-10 | 2025-02-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0014 | 04.Enhancement | 07.MDG | Storage Location - Extended Itego datamodel with 11 custom fields + UI to support governance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-10-07 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-09 | 2024-10-14 | 2024-10-18 | 2024-10-18 | 100% | 2024-10-18 | 2024-10-21 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-28 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-15 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-11 | 2024-11-15 | 2024-11-15 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-11-08 | 2024-11-08 | 2024-11-08 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-10-09 | 2024-10-11 | 2024-10-09 |  | 2024-10-18 | 2024-10-18 | 2024-10-18 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-10-11 | 2024-11-08 | [6 empty] | 0 | 08. Not Applicable | 2224 | [10 empty] | 2024-11-08 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0013 | 04.Enhancement | 07.MDG | Plant - Extended Itego datamodel with 13 custom fields + UI to support governance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-10-07 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-11 | 2024-10-14 | 2024-10-18 | 2024-10-18 | 100% | 2024-10-18 | 2024-10-21 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-28 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-15 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-11 | 2024-11-15 | 2024-11-15 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-11-08 | 2024-11-08 | 2024-11-08 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-10-11 | 2024-10-11 | 2024-10-11 |  | 2024-10-18 | 2024-10-18 | 2024-10-18 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-10-11 | 2024-11-08 | [6 empty] | 0 | 08. Not Applicable | 2223 | [10 empty] | 2024-11-08 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0012 | 04.Enhancement | 07.MDG | Sales Org Association - Custom Itego Object with 4 customer fields + UI to support goverance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-09-23 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-03 | 2024-09-30 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-03 | 2024-10-07 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-08 | 2024-10-14 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-01 | 2024-11-01 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-28 | 2024-11-01 | 2024-11-01 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-25 | 2024-10-25 | 2024-10-25 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-10-03 | 2024-10-03 | 2024-10-03 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 |  | 2024-10-08 | 2024-10-11 | 2024-10-08 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-09-27 | 2024-10-25 | [6 empty] | 0 | 08. Not Applicable | 2222 | [10 empty] | 2024-10-25 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0011 | 04.Enhancement | 07.MDG | Holiday Calendar - Custom goveranance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-09-09 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-09-16 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-09-23 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-09 | [15 empty] | 2024-10-09 | 2024-10-09 |  |  | 2024-10-18 | 2024-10-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-14 | 2024-10-18 | 2024-10-18 | N | 100% | 2024-11-06 | Not Applicable | R3 Build & UT Sprint 7 | 2024-10-11 | 2024-10-11 | 2024-10-11 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-10-09 | [12 empty] | 2024-10-09 | 2024-10-09 |  |  | 2024-11-06 | 2024-11-06 | 2024-11-06 | [5 empty] | 2024-09-13 | 2024-10-11 | [6 empty] | 0 | 08. Not Applicable | 2221 | [10 empty] | 2024-10-11 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 6 |  | 2024-10-11 | 2024-10-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
04. IAO Data | 03.R3 |  | MDCE0009 | 04.Enhancement | 07.MDG | Shipping Point- Custom Itego Object with 6 customer fields + UI to support goverance | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  |  |  | 01.Yes |  |  | Candice S Linnell | 01.Approved |  | Std. |  | 02.Intel |  | 02.Intel | 03.Medium |  | 02.No |  |  | MDG |  | NA | 2024-10-07 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | 2024-10-14 | 2024-10-18 | 2024-10-18 | 100% | 2024-10-18 | 2024-10-21 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-28 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-22 | 2024-11-22 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-18 | 2024-11-22 | 2024-11-22 | N | 100% | 2024-11-25 | Not Applicable | R3 Build & UT Sprint 8 | 2024-11-15 | 2024-11-15 | 2024-11-15 | logoldstein@deloitte.com | 2024-09-10 08:53 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 10 |  | 02.MDG |  |  | 1 | 1 |  |  | R3 ITC1 | [6 empty] | 2024-10-07 | 2024-10-11 | 2024-10-07 |  | 2024-10-18 | 2024-10-18 | 2024-10-18 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-25 | 2024-11-25 | 2024-11-25 | [5 empty] | 2024-10-11 | 2024-11-15 | [6 empty] | 0 | 08. Not Applicable | 2220 | [10 empty] | 2024-11-15 | N | 09A. Master Data | [8 empty] | N/A | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1078_IP | 06.Workflow | 01.IP - Intel Product | ISM Workflows - Capital/AMT | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-31 | 2025-11-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-03 | 2025-11-07 | 2025-11-07 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.05 | 1078 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2804 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/11: Awaiting for approval from Intel IT and PS. 10/31: Partially fixed and in retest but the issue is not fixed. we can not move any further on FUT. Defect 3751/3744 10/24 - Defect 3751 10/22: TUT is still not completed | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1078_IF | 06.Workflow | 02.IF - Intel Foundry | ISM Workflows - Capital/AMT | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-19 | 2025-09-26 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 | LOGW1078_IP | 03.Medium | 0.5 | 0.525 | 1078 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2803 | [7 empty] | 4. Completed | 3. Awaiting Approval | 112/1: Submitted for Intel review and approval. 1/24: Tech is working on defect 4370, 4847. ETA for FUT completion 11/28. 11/18: Tech team is working on defect 4370. 11/11: Tech team is working on defect 4370. 10/31: Partially fixed and in retest but the issue is not fixed. we can not move any further on FUT. Defect 3751 10/24 - Defect 3751 10/22: TUT is still not completed | 2025-12-05 | Y | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1077_IP | 06.Workflow | 01.IP - Intel Product | ISM Workflows - EIMS/Lab | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.05 | 1077 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2806 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 12/1: Submitted for Intel review and approval. 11/24: Tech working on defect 4370, 4847. ETA 11/25 to start FUT 11/18: Defect 4370 in progress with tech 11/14: Defect 4370 in progress with tech | 2025-10-08 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1077_IF | 06.Workflow | 02.IF - Intel Foundry | ISM Workflows - EIMS/Lab | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 | LOGW1077_IP | 03.Medium | 0.5 | 0.525 | 1077 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2805 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 12/1: Submitted for Intel review and approval. 11/24: Tech working on defect 4370, 4847. ETA 11/25 to start FUT . 11/18: Defect 4370 in progress with tech 11/14: Defect 4370 in progress with tech | 2025-10-08 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1076_IP | 06.Workflow | 01.IP - Intel Product | ISM Workflows - Non-inventory | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-11-27 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-11-27 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-11-27 | [15 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-10-31 | 2025-11-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-14 | 2025-11-07 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 |  |  | 2 | 2.1 | 1076 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | [12 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2808 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14: IT conditionally approved. Awaiting business confirmation. 11/11: Awaiting for approval from Intel IT and PS. 10/31: Partially fixed and in retest but the issue is not fixed. we can not move any further on FUT. Defect 3751 10/24 - Defect 3744 10/22: TUT is still not completed | 2025-10-03 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-27 | 2025-11-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2525 | LOGW1076_IF | 06.Workflow | 02.IF - Intel Foundry | ISM Workflows - Non-inventory | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2525_FTS-LE-RICEFW%20intake%20form%20of%20ISM%20Workflows.pptx?d=w1d51b05011e646ed92ad0a52cfb0e6e3&csf=1&web=1&e=gOVAej | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-02 | 01.S4 | LOGW1076_IP | 02.High | 1 | 1.05 | 1076 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-20 | 2025-06-13 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2807 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/1: Submitted for Intel review and approval. 11/24: Tech is working on defect 4370, 4847. ETA for FUT completion 11/28. 11/18: Tech team is working on defect 4370. 11/11: Tech team is working on defect 4370. 10/31: Partially fixed and in retest but the issue is not fixed. we can not move any further on FUT. Defect 3751 10/24 - Defect 3751 10/22: TUT is still not completed | 2025-10-03 | N | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2346 | LOGW0978_IP | 06.Workflow | 01.IP - Intel Product | Workflow for processing Goods Receipt and tracking and tracing of non-inventory goods - IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/2%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Logistics/Final%20Deliverables/LI-120-130/RICEFWs/Workflow%20at%20107%20movement%20type.pptx?d=w37cab36378c44593ac355be3171180e9&csf=1&web=1&e=oWDaX8 | 02.No | 01.Yes |  | 2024-12-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-06-06 | 2025-06-06 | 100% | 2025-06-05 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-21 | 2025-12-01 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-01 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-12-06 07:21 | cell-link@smartsheet.com | 2026-03-09 03:41 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.05 | 0978 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-06 | 2025-06-05 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-01 |  |  |  | 1 |  | 2288 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: All Review comments are addressed, Awaiting further feedback/approval from Intel IT & Business/PS. No Action item as of now on DT 11/18 - New Review Comments received, Defect# 4656 is raised, 3 TCs need to be restested ETA 11/19 11/14 - 4 out of 10 TCs are completed, Defect# 4591 is raised, Awaiting ETA from Tech. Blocking rest of the TCs | 2025-10-03 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_PARAMS | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2346 | LOGW0978_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow for processing Goods Receipt and tracking and tracing of non-inventory goods - IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/2%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Logistics/Final%20Deliverables/LI-120-130/RICEFWs/Workflow%20at%20107%20movement%20type.pptx?d=w37cab36378c44593ac355be3171180e9&csf=1&web=1&e=oWDaX8 | 02.No | 01.Yes |  | 2024-12-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-06-06 | 2025-06-06 | 100% | 2025-06-05 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-31 | 2025-11-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-06 | 2025-11-06 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-11-21 05:57 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | LOGW0978_IP | 03.Medium | 0.5 | 0.525 | 0978 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-06 | 2025-06-05 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-01 |  |  |  | 1 |  | 3386 | [7 empty] | 4. Completed | 1. Approved no action | 12/08 - Conditional Approval received from Intel IT & Business/PS. Will seek Full Approval once Reversal process is aligned with GFM & Ariba Team 12/01: Intel Approval pending. No action on Deloitte 11/24: Sent for approval on 11/22 (extended support). There is one feedback received today. Team is working on it. | 2025-10-03 | N | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  |  | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2642 | LOGR1252 | 01.Report | 01.IP - Intel Product | 2DN - Inbound Escort Report | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3%20IP%20OTC%20LE_Inbound%20Escort%20Report%20RICEFW%20Intake%20Form.pptx?d=wc1143be57711415cbb02f9437570e7c7&csf=1&web=1&e=OS3iac | 02.No | 02.No |  | 2025-02-28 | Jorge Sanchez | 01.Approved |  | Std. | 01.Yes |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-24 | 2025-10-17 | 2025-10-24 | 2025-12-12 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-10 | Sprint 22 Week 2 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-02-10 13:45 | cell-link@smartsheet.com | 2026-03-10 04:39 | 10 | 2025-05-06 | 01.S4 |  |  | 2 | 1.7 | 1252 |  | R3 ITC1 | [6 empty] | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | [5 empty] | 2025-07-18 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 1 |  | 1834 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/02: Defect#7380 is re-assigned to tech, ETA 03/02 . Defect#7879 is created for the issue of mapping for MAWB to FO and FO to deliveries, which was working previously but post recent defect fixes, this issue is occurring blocking all scenarios, Tech ETA 03/02. If issues fixed by 03/02. 02/27: Defect#7359 is fixed and retest in progress, Defect#7380 & 7738 is with tech, ETA 02/27. 02/23: Defect#7234 is fixed, however has dependency on 7328 which was re-assigned to tech, ETA 02/23. Defect#7301 is fixed & retest is in progress, ETA 02/23. Defect#7359 was partailly fixed and assigned for test, hence re-assigned to tech, 7380 with tech, ETA 02/24 02/16: Defect#7234, 7301, 7328 & 7359 with tech, no ETA 01/19: TUT approval is pending, ETA from tech is 01/20 01/12: Awaiting TUT approval, no ETA from tech 01/05: Awaiting TUT approval 12/22: Awaiting TUT approval, new ETA 12/23 12/15: TUT is still in progress, ETA is 12/17 | 2025-12-05 | N | 99. Logistics |  |  |  | 12/10 : Build in progress by Tech team. |  |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2643 | LOGR1236 | 01.Report | 01.IP - Intel Product | 2DN - Outbound Escort Report | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 06. Dev In Progress | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3%20IP%20OTC%20LE_Outbound%20Escort%20Report%20RICEFW%20Intake%20Form.pptx?d=wc1bec7d904d14c0684e8ee4c5ce2d581&csf=1&web=1&e=IWQtqj | 02.No | 02.No |  | 2025-02-28 | Jorge Sanchez | 01.Approved |  | Std. | 01.Yes |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-24 | 2025-10-17 | 2025-10-24 | 2025-12-12 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 75% | 2026-01-07 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 95% | 2026-01-07 | [15 empty] | 2026-01-07 | 2026-01-07 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-09 | Sprint 22 Week 2 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-02-10 13:45 | automation@smartsheet.com | 2026-03-09 04:39 | 6 | 2025-05-06 | 01.S4 |  |  | 2 | 1.7 | 1236 |  | R3 ITC1 | [6 empty] | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  |  | 2026-01-07 | [17 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2025-07-18 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 1 |  | 1835 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 03/02: Defect#7874 with tech, ETA 03/02 . Defect#7797 is with tech, ETA 03/02 . If issues fixed by 03/02, FUT can be sent for approval by 03/04 02/27: Defect#7491 is fixed & retest is completed, 14/15 points are working as expected, 1 issue needs to be re-checked by tech. Defect#7793 is created on 02/26, no ETA from tech 02/23: Defect#7491 is with tech, ETA 02/24 02/16: Awaiting TUT approval, no ETA 01/19: TUT approval is pending, ETA from tech is 01/22 01/12: Awaiting TUT approval, no ETA from tech 01/05: Awaiting TUT approval 12/22: Awaiting TUT approval, new ETA 12/23 12/15: TUT is still in progress, ETA is 12/18 | 2025-12-05 | N | 99. Logistics |  |  |  | Dev in progress |  |  |  | Defects | Complete | R3 Build & UT Sprint 21 |  | 2026-01-07 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2646 | LOGR1176_IP | 01.Report | 01.IP - Intel Product | ISM - International Traffic Report | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_LOG_International_Traffic_Report.pptx?d=wdcd90e2376a64ca6b755c1a6d56141e5&csf=1&web=1&e=pJ62jd | 02.No | 01.Yes |  | 2025-01-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-12-05 | 2025-05-16 | 2025-08-01 | 100% | 2025-09-09 | 2025-02-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-09 | 2025-02-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-29 | 01.S4 |  |  | 2 | 1.7 | 1176 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-04-18 | 2025-06-13 | [6 empty] | 1 |  | 1836 | [7 empty] | 4. Completed | 1. Approved no action | 12/15: 12/15: Defect 4696 fixed, FUT resent for Business approval. 12/8: Based on the intel feedback--4696 is with Tech to fix the alignment of the report. ETA 12/8 12/1 working with tech on defect 4696. 11/24: Working with tech team to get the defect resolved. ETA:11/26. 11/18: Under intel review. 11/11: Tech team is working on the defects. 10/31: 4016 defect in progress. 10/24 - Defect 3903 | 2025-06-13 | N | 99. Logistics |  |  |  |  | 12/02 - Defects fix and still on track for 12/05 |  |  |  | Complete | R3 Build & UT Sprint 17 |  | 2025-09-09 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2646 | LOGR1176_IF | 01.Report | 02.IF - Intel Foundry | ISM - International Traffic Report | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_LOG_International_Traffic_Report.pptx?d=wdcd90e2376a64ca6b755c1a6d56141e5&csf=1&web=1&e=pJ62jd | 02.No | 01.Yes |  | 2025-01-29 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-12-05 | 2025-05-16 | 2025-08-01 | 100% | 2025-09-09 | 2025-02-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-09 | 2025-02-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-05 | 01.S4 | LOGR1176_IP | 02.High | 0.4 | 0.34 | 1176 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-04-18 | 2025-06-13 | [6 empty] | 1 |  | 1837 | [7 empty] | 4. Completed | 1. Approved no action | 12/15: Defect 4696 fixed, FUT resent for Business approval. 12/8: Based on the intel feedback--4696 is with Tech to fix the alignment of the report. ETA 12/8 12/1 working with tech on defect 4696. 11/24: Working with tech team to get the defect resolved. ETA:11/26. 11/18: Under intel review. 11/11: Tech team is working on the defects. 10/31: 4016 defect in progress. 10/24 - Defect 3903 | 2025-06-13 | N | 99. Logistics |  |  |  |  | 12/02 - Defects fix and still on track for 12/05 |  |  |  | Complete | R3 Build & UT Sprint 17 |  | 2025-09-09 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2641 | LOGR1173 | 01.Report | 01.IP - Intel Product | 2DN - Outbound Manifest Report | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3%20IP%20OTC%20LE_Outbound%20Manifest%20Report%20RICEFW%20Intake%20Form.pptx?d=wb78f4b71b3ca4a378482d32c84da3d58&csf=1&web=1&e=i5dj68 | 02.No | 01.Yes |  | 2025-01-28 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-23 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-10-07 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | 2025-09-28 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 0.85 | 1173 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-07-18 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-10 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-07-18 | 2025-10-10 | [6 empty] | 1 |  | 2302 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/19: Intel IT approval received. Awaiting approval from Intel business, defect#6233 & 5434 is for new requirments, it is fixed & retest is in progress. 01/12: Awaiting approval, as the pending open points are new requirements which will be worked upon in parallel 01/05: Awaiting inputs on the pricing logic, reminder sent 12/22:Awaiting inputs on STO pricing from FTS team ETA 12/22 based on intel feedback. 12/15: Defect 5457 is fixed and tested. Will document the screenshots and re-send to Business for approval. ETA 12/15 12/08:Recevied the intel feedback. based on the feedabck Defect#5237 is resolved. One pending item- Awaiting logic from TM team (Nikhil) for X-Route and Truck name as asked by Ramesh Govindan. 12/01: FUT sent for approval on 11/26, working on the queries raised by Intel, ETA 12/02 11/24: FUT defect 4822,4798 open with dev, TC 5/6 Completed. ETA 11/26 for intel review. 11/18- Defect 4690 raised with dev | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2640 | LOGR1172 | 01.Report | 01.IP - Intel Product | 2DN - Inbound Manifest Report | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3%20IP%20OTC%20LE_Inbound%20Manifest%20Report%20RICEFW%20Intake%20Form.pptx?d=wc6150eaec7cd4a1a819c12ab10a08e11&csf=1&web=1&e=5DOdjR | 02.No | 01.Yes |  | 2025-01-28 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-11 | 2025-05-23 | 100% | 2025-05-23 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-10-07 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | 2025-09-28 | 2025-10-10 | 2025-09-05 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-28 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 0.85 | 1172 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-07-11 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-10 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-07-11 | 2025-10-10 | [6 empty] | 1 |  | 2301 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 01/19: Intel IT approval received. Awaiting approval from Intel business, defect#6233 & 5434 is for new requirments, it is fixed & retest is in progress. 01/12: Awaiting approval, as the pending open points are new requirements which will be worked upon in parallel 01/05: Inputs provided to tech team for defect#5434, ETA for fix is 01/05 12/22:Defect 5434 with Tech team ETA is past due ,no new ETA has been provided 12/15: Defect#5434 raised for the open points raised by intel, defect is with tech, ETA 12/15 12/08: Sent for approval on 12/04, FUT review call scheduled on 12/09 12/1: Testing in progress for pending scenarios. ETA 12/1 for sending the FUT for review 11/24: FUT is in progress. ETA To send for Intel review by 11/28. 11/18 - Defect 4585 is raised with dev. | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2420 | LOGR0856 | 01.Report | 02.IF - Intel Foundry | Capital Call Ahead GAP Report​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD282F2BC-F567-4DE3-8A50-3263A239C292%7D&file=2420_R3_PTP_IP&IF_LI-030-160_Call%20Ahead%20Reports_Intake%20Form.pptx=&wdLOR=c73D0D5BB-A902-4205-B484-F495B3BFCC8F&action=edit&mobileredirect=true&CID=3273593A-2C14-46F1-9927-DB05E2D6D117 | 02.No | 01.Yes |  | 2024-11-12 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-28 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 0.85 | 0856 |  | R3 ITC1 | [6 empty] | 2025-07-28 | 2025-08-15 | 2025-07-28 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | [5 empty] | 2025-08-15 | 2025-10-03 |  |  | 2025-12-05 | TM |  |  | 1 | 08. Not Applicable | 1440 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/15: New requirement added during FUT review. Discussion ongoing 12/08: Intel review scheduled this week along with LOGE0854 & LOGE0855 12/01: FUT complete, Intel Review call to be scheduled 11/24: FUT document sent for Intel review, ETA 03/12 11/18:FUT WIP 11/14:FUT WIP | 2025-10-03 | N | 99. Logistics |  |  |  | Adjustment in the Object id |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1751 | LOGR0833_IP | 01.Report | 01.IP - Intel Product | Email Notification for deletion of Shipping Memos | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8B796C6-44DB-4A01-86A3-8FD971BD7C5C%7D&file=R3_FTS_IP_LOGISTICS_L-060-080_Report%20-%2020_V1%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true&previoussessionid=815c783d-1d48-426e-4121-54a02a0e3a70&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Ckarthp%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA5MTIyMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | 02.No | 02.No |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-28 | 2025-02-28 | 100% | 2025-02-27 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-08 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-10-31 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-10-30 03:51 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 0.85 | 0833 |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-02-28 | 2025-02-27 |  | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2025-09-09 | 2025-09-12 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-07 | 2025-10-31 | [5 empty] | 2025-02-28 | 2025-08-15 |  |  | 2025-08-22 |  |  |  | 1 | 08. Not Applicable | 1992 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/24 - Defect 3888 | 2025-09-12 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1751 | LOGR0833_IF | 01.Report | 02.IF - Intel Foundry | Email Notification for deletion of Shipping Memos | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8B796C6-44DB-4A01-86A3-8FD971BD7C5C%7D&file=R3_FTS_IP_LOGISTICS_L-060-080_Report%20-%2020_V1%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true&previoussessionid=815c783d-1d48-426e-4121-54a02a0e3a70&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Ckarthp%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA5MTIyMTMxOCIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | 02.No | 02.No |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-28 | 2025-02-28 | 100% | 2025-02-27 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-08 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-10-29 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jenoronha@deloitte.com | 2024-12-16 05:13 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-13 | 01.S4 | LOGR0833_IP | 03.Medium | 0.2 | 0.17 | 0833 |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-02-28 | 2025-02-27 |  | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2025-09-09 | 2025-09-12 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-29 | 2025-11-07 | 2025-10-29 | [5 empty] | 2025-02-28 | 2025-08-15 |  |  | 2025-08-22 |  |  |  | 1 | 08. Not Applicable | 1991 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 10/24 - Defect 3888 | 2025-09-12 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM024_IP | 12.Manual Conversion | 01.IP - Intel Product | Create/Upload Vehicle resource | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 024_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-23 | 2025-08-29 |  |  | 2025-10-17 | TM |  |  | 1 | 08. Not Applicable | 2258 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM024_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Create/Upload Vehicle resource | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 024_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-16 | 2025-08-29 |  |  | 2025-08-29 | TM |  |  | 1 |  | 2870 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM023_IP | 12.Manual Conversion | 01.IP - Intel Product | Update Business Share | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-20 | 01.S4 |  |  |  | 0 | 023_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-17 | TM |  |  | 1 | 08. Not Applicable | 2247 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM023_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Update Business Share | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 023_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-09-26 | TM |  |  | 1 |  | 2869 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM022_IP | 12.Manual Conversion | 01.IP - Intel Product | Upload Transportation Allocation | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 022_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-17 | TM |  |  | 1 | 08. Not Applicable | 2197 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM022_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Upload Transportation Allocation | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 022_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-09-26 | TM |  |  | 1 |  | 2868 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM021_IP | 12.Manual Conversion | 01.IP - Intel Product | Upload Schedules | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 021_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-23 | 2025-08-29 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2250 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM021_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Upload Schedules | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-08-01 | 100% | 2025-07-22 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 021_ |  | R3 ITC1 | [6 empty] | 2025-07-22 | 2025-08-01 | 2025-07-22 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-16 | 2025-08-29 |  |  | 2025-08-29 | TM |  |  | 1 |  | 2867 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM019_IP | 12.Manual Conversion | 01.IP - Intel Product | Default Routes | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [5 empty] | S4 | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 019_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-23 | 2025-08-29 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 2206 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM019_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Default Routes | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 019_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-16 | 2025-08-29 |  |  | 2025-08-29 | TM |  |  | 1 |  | 2882 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM018_IP | 12.Manual Conversion | 01.IP - Intel Product | Upload Rate Table | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | N/A |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-08 09:51 | jenoronha@deloitte.com | 2026-03-04 09:32 | 10 |  | 01.S4 |  |  |  | 0 | 018_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-31 | TM |  |  | 1 |  | 2885 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM018_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Upload Rate Table | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | N/A |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-03-04 09:32 | 10 |  | 01.S4 |  |  |  | 0 | 018_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-09-26 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-09-26 | TM |  |  | 1 |  | 2879 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM016_IP | 12.Manual Conversion | 01.IP - Intel Product | Create and review Charge Calculation Sheet | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [5 empty] | S4 | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 016_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2246 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM016_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Create and review Charge Calculation Sheet | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 016_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 |  | 2877 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM015_IP | 12.Manual Conversion | 01.IP - Intel Product | Create and review Freight Agreement | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [5 empty] | S4 | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 015_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2244 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM015_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Create and review Freight Agreement | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 015_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 |  | 2876 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM012_IP | 12.Manual Conversion | 01.IP - Intel Product | Creation of Location based on BP, Shipping points, plants | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | ECC | S4 | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 012_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-23 | 2025-08-29 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2217 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM012_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Creation of Location based on BP, Shipping points, plants | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 012_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-16 | 2025-08-29 |  |  | 2025-08-29 | TM |  |  | 1 |  | 2874 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM008_IP | 12.Manual Conversion | 01.IP - Intel Product | Location creation-ocean ports, airports | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | 008_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-23 | 2025-08-29 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2240 | [10 empty] | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM008_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Location creation-ocean ports, airports | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-20 | 2025-05-19 | 2025-05-26 |  | 0% | 2025-05-26 | 2025-06-02 | 2025-06-27 |  | 0% | 2025-06-27 | 2025-08-04 | 2025-08-29 |  | 0% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-08-18 | 2025-08-29 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 008_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-05-26 |  |  |  | 2025-06-27 | [18 empty] | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-05-16 | 2025-08-29 |  |  | 2025-08-29 | TM |  |  | 1 |  | 2871 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-08-29 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM007_IP | 12.Manual Conversion | 08.EWM | Storage Bin Upload | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N | [8 empty] | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  |  | WIINGS | EWM | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-16 | 2025-06-30 |  | 0% | 2025-06-30 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | [13 empty] | 0% |  | 2025-08-15 | 2025-08-15 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | anntam@deloitte.com | 2025-06-06 08:54 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  |  | 0 | 007_ |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-06-30 |  |  |  | 2025-08-15 | [18 empty] | 2025-09-29 | 2025-10-08 | 2025-09-29 | [5 empty] | 2025-07-16 | 2025-08-15 |  |  | 2025-10-08 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 3081 |  |  | WIINGS | [7 empty] | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 |  | LOGM007_IF | 12.Manual Conversion | 08.EWM | Storage Bin Upload | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N | [8 empty] | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | WIINGS | WIINGS | EWM | NA | 2025-04-21 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-16 | 2025-06-30 |  | 0% | 2025-06-30 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | [13 empty] | 0% |  | 2025-08-15 | 2025-08-15 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 03:49 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  |  | 0 | 007_ |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-06-30 |  |  |  | 2025-08-15 | [18 empty] | 2025-10-06 | 2025-10-10 | 2025-10-06 | [5 empty] | 2024-11-29 | 2024-12-02 |  |  | 2025-12-31 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 2245 |  |  | WIINGS | [7 empty] | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 |  | LOGM006_IP | 12.Manual Conversion | 08.EWM | Product Master conversion (additional EWM attribution) | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  |  | WIINGS, ECC WM | EWM | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-16 | 2025-06-30 |  | 0% | 2025-06-30 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | [13 empty] | 0% |  | 2025-08-15 | 2025-08-15 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | anntam@deloitte.com | 2025-06-06 08:54 | cell-link@smartsheet.com | 2026-03-16 04:51 | 10 |  | 01.S4 |  |  |  | 0 | 006_ |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-06-30 |  |  |  | 2025-08-15 | [18 empty] | 2025-09-29 | 2025-10-08 | 2025-09-29 | [5 empty] | 2025-07-16 | 2025-08-15 |  |  | 2025-10-08 | TM |  |  | 1 | 08. Not Applicable | 3082 |  |  | WIINGS |  |  |  |  | 3. Off Track | 8. Blocked by CR/Design change |  | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 |  | Yes | Impact on Product Master Extension---Assess the impact of a change in the configuration for the ‘Party Entitled to Dispose’. | No |  | No |  | 2026-03-09 | 2026-04-01 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 |  | LOGM006_IF | 12.Manual Conversion | 08.EWM | Product Master conversion (additional EWM attribution) | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | WIINGS | WIINGS, ECC WM | EWM | NA | 2025-04-21 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-16 | 2025-06-30 |  | 0% | 2025-06-30 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | 2025-07-21 | 2025-08-15 |  | 0% | 2025-08-15 | [13 empty] | 0% |  | 2025-08-15 | 2025-08-15 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 03:49 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  |  | 0 | 006_ |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | 2025-06-30 |  |  |  | 2025-08-15 | [18 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2024-12-01 | 2024-11-01 |  |  | 2025-12-12 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 2252 |  |  | WIINGS | [7 empty] | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 |  | LOGM005_IP | 12.Manual Conversion | 01.IP - Intel Product | UPLOAD TRANSPORTATION ZONES (TM) | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  | TMS | TMS | S4 | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  |  | 0 | 005_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 2266 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM005_IF | 12.Manual Conversion | 02.IF - Intel Foundry | UPLOAD TRANSPORTATION ZONES (TM) | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 005_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 |  | 2881 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM004_IP | 12.Manual Conversion | 01.IP - Intel Product | UPLOAD TRANSPORTATION LANES | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | TMS | TMS | S4 | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-07-21 | 2025-07-31 |  | 0% | 2025-07-31 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [13 empty] | 0% |  | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  |  | 0 | 004_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-07-31 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-05-23 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 2236 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | LOGM004_IF | 12.Manual Conversion | 02.IF - Intel Foundry | UPLOAD TRANSPORTATION LANES | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-20 | 2025-06-16 | 2025-06-23 |  | 0% | 2025-06-23 | 2015-07-01 | 2025-08-14 |  | 0% | 2025-08-14 | 2025-08-18 | 2025-09-30 |  | 0% | 2025-09-30 | [15 empty] | 2025-09-30 | 2025-09-30 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-09-15 | 2025-10-10 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | jonsanders@deloitte.com | 2025-04-07 12:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 004_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-06-23 |  |  |  | 2025-08-14 | [18 empty] | 2025-09-25 | 2025-10-10 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-09-30 |  |  | 2025-10-10 | TM |  |  | 1 |  | 2880 | [10 empty] | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-30 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3202 | LOGI1726 | 02.Interface | 01.IP - Intel Product | GR replication for raw materials for Straddle Sites from ECC to S4 IP via ECA​ | 06. PTP | 6.4 PTP - Logistics Management Inbound | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/PTP/3202_PTP_LE_CR1662_GR%20replication%20for%20raw%20materials%20for%20Straddle%20Sites%20from%20ECC%20to%20S4%20IP%20via%20ECA.pptx?d=w960ccca75ca04e29a2f893c7a64a84b4&csf=1&web=1&e=SSHPXD | 02.No | 01.Yes |  | 2026-02-19 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT |  |  | 2026-04-03 | 100% | 2026-03-27 |  |  | 2026-04-03 | 99% | 2026-04-07 |  |  | 2026-04-22 | 100% | 2026-04-07 |  |  | 2026-04-22 | 100% | 2026-04-07 |  |  | 2026-04-03 | 100% | 2026-04-03 |  |  | 2026-04-03 | 95% | 2026-04-03 | [5 empty] | 2026-04-07 | 2026-04-07 | [17 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-02-19 04:22 | cell-link@smartsheet.com | 2026-04-08 05:38 | 6 | 2026-02-19 | 01.S4 |  |  | 1 | 1.45 | 1726 | INT-CR1662 | R3 ITC1* | [6 empty] | 2026-03-27 | 2026-04-03 | 2026-03-27 |  |  | 2026-04-07 | 2026-04-07 |  | 2026-04-07 | 2026-04-22 | 2026-04-07 | 2026-04-07 |  | 2026-04-03 |  | 2026-04-03 |  | 2026-04-03 | [6 empty] | 2026-04-07 | 2026-04-07 | [18 empty] | 1 |  | 3431 | [11 empty] | N | 99. Logistics | [6 empty] | Approved Exception (ITC1) |  | N/A | R3 Build & UT Sprint 23+ |  | 2026-04-22 | 2026-04-07 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3194 | LOGI1718 | 02.Interface | 02.IF - Intel Foundry | To align on batch attributes for straddle in S4 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/3194_FTS_IF_Batch%20Attribute%20update%20for%20Straddle_RICEFW%20Intake%20form.pptx?d=w63f3f97a4e7e48ad8391d001c7813b20&csf=1&web=1&e=tjABb6 | 02.No | 01.Yes |  | 2026-01-27 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-13 | 2026-02-09 | 2026-02-27 | 2026-03-19 | 100% | 2026-03-17 | 2026-02-16 | 2026-02-20 | 2026-03-19 | 100% | 2026-03-17 | 2026-02-16 | 2026-02-20 | 2026-03-19 | 100% | 2026-03-17 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | [5 empty] | 2026-03-17 | 2026-03-17 |  |  | 2026-03-25 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-01 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-20 | jenoronha@deloitte.com | 2026-01-27 09:47 | automation@smartsheet.com | 2026-04-01 10:44 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1718 | INT-CR1463 | R3 ITC1 | [6 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 |  | 2026-03-17 | 2026-03-19 | 2026-03-17 |  | 2026-03-17 | 2026-03-19 | 2026-03-17 | 2026-03-17 |  | 2026-02-27 |  |  |  | 2026-02-27 | [6 empty] | 2026-03-17 | 2026-03-17 |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | [5 empty] | 2026-02-06 | 2026-02-20 | 2026-02-27 |  | 2026-03-04 |  |  |  | 1 |  | 3417 | [7 empty] | 4. Completed | 3. Awaiting Approval | 3/27: FUT submitted for Intel review and approval. 3/27: defect fixed, documentation in progress- to be sent for review by EOD. 3/26:dump error resolved by tech, retest in progress- ETA- 03/27 3/25:data trigger and defect fixes currently being validated/retested. ETA to send FUT for review-03/27 3/24:Data to be pushed from ECA . FUT started today.Defect raised 8583 for AIF log issue and query parameter.ETA to send for intel review-03/27. 3/23: Awaiting Data trigger from ECA requested on 03/20. Call scheduled with Prashant from ECA team. 3/19:B FUT in progress. Targetting to complete FUT by 3/27 3/18:Build completed on 3/18 and FUT in progress. Targetting to complete FUT by 3/27 3/17:Awaiting confirmation on build. ECA Build is completed, S4 Build ETA 3/20. 03/12:SoS :at risk of going beyond 03/27 3/12: Awaiting confirmation on build.Following up with the Tech. 3/11:Build in progress. ETA 03/12 3/10: ECA/S4 build in progress, Build ETA is 3/11 3/09: ECA Build not completed. ETA is 3/11 3/05: Following with MW team for confirmation on MW changes. 3/02: S4 Build ETA 3/4. 2/26: S4 Build ETA 3/4. 2/24: Build in progress ETA for build completion 3/4 2/19:S4 Build ETA 3/4. 2/16: Build is In Progress 2/12: Build in Progress by Tech 2/11: Dev WIP 3/23: Awaiting Data trigger from ECA requested on 03/20, meanwhile validating the S4 end. 3/20: Testing in progress. 3/18:Build completed and FUT will be taken up by ??? 3/17:Awaiting confirmation on build.Build ETA 3/20. 3/16:Awaiting confirmation on build.Build ETA 3/20. 3/13:Awaiting confirmation on build.Build ETA 3/20. 3/12: Awaiting confirmation on build. 3/11:Build in progress. ETA 03/12 3/10: ECA/S4 build in progress, tentative ETA 03/12. 3/9: ECA Build not completed. 3/6: S4 tech working to update the connectivity issues 3/5: Following with MW team for confirmation on MW changes. 3/3: S4 Build ETA 3/4. 2/27: S4 Build ETA 3/4. 2/26: S4 Build ETA 3/4. 2/25:S4 Build ETA 3/4. 2/16: Dev WIP, Dev ETA? 2/12: Dev WIP 2/11: Dev WIP 2/9: Dev WIP3/20: Build 3/18 FUT in progress 3/13:Awaiting confirmation on build. 3/6: S4 tech working to update the connectivity issues.S4 Build ETA 3/4. 2/24: S4 Build will be completed by 3/4 2/20: S4 Build ETA 3/4, MW ETA ?? 2/16: Build in Progress. Awaiting ETA confirmation from Tech team. | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/24 : Awaiting Data trigger from ECA requested on 03/20, meanwhile validating the S4 end. | 0131 FS complete. Client call on Monday | 2. Risk | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-19 | 2026-03-17 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | TBD | LOGI1708 | 02.Interface | 08.EWM | Wrapper program for Inbound interface from Kommand AS to SAP | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA5A4E369-28F4-494B-BC7D-9A313D45C04A%7D&file=INT-CR1548-%20Wrapper%20program%20for%20Inbound%20interface.pptx&wdLOR=c22C6B057-46C9-4A53-ACA6-05FE2F00573C&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-12-06 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 63174 | Kommand Autostore |  |  | Apigee | 2026-01-12 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-23 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-05 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-07 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-07 | 2025-12-15 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-20 | 2026-03-09 | 2026-03-09 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-28 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-12-05 23:00 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 10 |  | 03.Mulesoft |  |  | 1 | 1.45 | 1708 | INT-CR1548 | R3 ITC1 | [6 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 2026-01-05 | 2026-01-07 | 2026-01-05 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-14 | 2026-02-14 |  | 2026-01-07 |  | 2026-01-07 |  | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 2026-01-23 | 2026-01-20 | 2026-01-20 | 2026-03-09 | 2026-03-09 |  |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | [5 empty] | 2026-01-23 | 2026-02-20 | 2026-01-07 |  | 2026-02-20 | TM | WIINGS Only | TRUE | 1 |  | 3395 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/27: FUT review contents are addressed. Intel review in progress. 02/23: FUT document sent to Intel for review. 02/16 : Offline testing conducted. Need to document the FUT. | 2026-02-20 | Y | 99. Logistics |  |  |  | 02/24: FUT sent to Business for approval. Awaiting IT & PS approval. Current status: Awaiting approval Issue: N/A Next steps: N/A Help needed: N/A FUT ETA: 0306 |  | 5. Review Closed |  |  | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-20 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 3137 | LOGI1688 | 02.Interface | 02.IF - Intel Foundry | To capture correct Country of Assembly and Country of Fabrication on FVR and AVR managed batches, EWM will need to connect directly to DBAAS (SCTRE) to pull managed data | 04. OTC IF | 4.8 OTC IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC093EE4C-D3F6-4C98-BADA-78D23164F737%7D&file=INT-CR1281_IF_EWM%20connection%20to%20DBAAS.pptx&action=edit&mobileredirect=true&CID=27E855CE-04BE-442B-B423-3EED7C9DEB82&wdLOR=cE44AE20C-D27D-4863-A671-C7C25FD4DCB4 | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 53494 | Supply Chain Trade Re-engineering Data Container for Intel Foundry |  |  | MuleSoft | 2025-12-08 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-12 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-02-24 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-18 | 2025-12-01 | 2026-02-06 | 2026-02-06 | 100% | 2026-02-28 | 2026-03-09 | 2026-03-09 |  |  | 2026-02-13 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-13 | 2026-02-20 | N | 100% | 2026-03-09 | Sprint 23 Week 1 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-11-05 05:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1.45 | 1688 | INT-CR1281 | R3 ITC1 | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-02-04 | 2026-01-22 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-14 | 2026-03-09 | 2026-03-09 | 2026-02-24 | 2026-02-14 | 2026-02-14 |  | 2026-02-20 |  | 2026-02-20 | 2026-02-18 | 2026-02-20 | 2026-02-18 | 2026-02-18 |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-03-09 | 2026-03-09 |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-02-04 | 2026-02-06 | 2026-02-20 |  | 2026-02-13 | TM |  |  | 1 |  | 3370 | [7 empty] | 3. Off Track | 19. Incomplete Build | 02/16: Build in progress, pending with teach team. 02/03: Development is planned for Sprint 23 which needs to be expedited to perform FUT | 2026-02-20 | Y | 99. Logistics | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-24 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3128 | LOGI1679 | 02.Interface | 01.IP - Intel Product | Receive 4C1 Inventory movement Stock type change and cycle count from IF | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/3128%20R3_FTS_Receive%204C1%20Inventory%20movement%20Stock%20type%20change%20and%20cycle%20count%20from%20IF.pptx?d=wd29853a5d1e14a2fb8d497451895c1fe&csf=1&web=1&e=qpCHgA | 02.No | 01.Yes |  | 2025-11-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | SFT | 2025-12-08 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-27 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-20 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-24 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-20 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-04 04:16 | cell-link@smartsheet.com | 2026-03-20 09:25 | 10 | 2025-11-24 | 01.S4 |  |  | 1 | 1.45 | 1679 | INT-CR1334 | R3 ITC1 | [6 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-03-09 | 2026-03-09 | 2026-02-21 | 2026-02-21 | 2026-03-09 | 2026-03-09 | 2026-02-24 | 2026-02-21 | 2026-02-21 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 |  |  |  |  | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | [5 empty] | 2026-01-23 | 2026-02-13 | 2026-02-20 |  | 2026-03-06 |  |  |  | 1 | 02. IF Customers | 3361 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: follwoing up for approvals from respective teams. FUT all TC and walkthorugh completed 3/13: defect # raised and is fixed by tech last night, restest inprogress, post that documentaion to resume. 3/6:Had working session with tech yestyerday based on the fixes retest in progress 2/24: Fileshare path is shared with MW team, they are working on SFT integration. 2/20: Build ETA- 2/20 2/16: Build in Progress. ETA: 2/13. Awaiting confirmation from Tech team. 2/10: FS walk through completed. Build in progress | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/11: E2E FUT in progress along with defect fixes. Current status: E2E FUT in progress Issue: FUT delayed Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-24 | 2026-03-09 | Yes |  | Yes | Regression testing impact | No |  |  |  | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3127 | LOGI1678 | 02.Interface | 01.IP - Intel Product | Receive 4C1 Inventory Reconciliation Snapshot from IF | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/3127%20R3_FTS_Receive%204C1%20Inventory%20Reconciliation%20Snapshot%20from%20IF.pptx?d=w46c19d40b24b4dec9f11ddfbe81fba75&csf=1&web=1&e=glkN3V | 02.No | 01.Yes |  | 2025-11-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | SFT | 2025-12-08 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-22 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-23 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-24 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-20 | N | 100% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-04 04:16 | krbajoria@deloitte.com | 2026-03-23 06:11 | 10 | 2025-11-24 | 01.S4 |  |  | 1 | 1.45 | 1678 | INT-CR1334 | R3 ITC1 | [5 empty] | 2026-01-22 | 2026-01-22 | 2026-01-23 | 2026-01-22 | 2026-03-09 | 2026-03-09 | 2026-02-22 | 2026-02-22 | 2026-03-09 | 2026-03-09 | 2026-02-24 | 2026-02-22 | 2026-02-22 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 |  |  |  |  | 2026-03-09 | 2026-03-09 |  |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | [5 empty] | 2026-01-23 | 2026-02-13 | 2026-02-23 |  | 2026-03-06 |  |  |  | 1 | 02. IF Customers | 3359 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: follwoing up for approvals from respective teams. FUT all TC and walkthorugh completed 3/13:tested and found the interface working properly will resume the documentation once LOGI1677 is tested completly testing by EOD. 3/6: issues has been identified and based on that Defect has been raised to onsite tech team 2/24: Fileshare path is shared with MW team, they are working on SFT integration. 2/20: Build ETA- 2/20. 2/16: Build in Progress. ETA: 2/13. Awaiting confirmation from Tech team. 2/10: FS walk through completed. Build in progress | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/11: E2E FUT in progress along with defect fixes. Current status: E2E FUT in progress Issue: FUT delayed Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-24 | 2026-03-09 | Yes |  | Yes | Regression testing impact | No |  |  |  | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3126 | LOGI1677 | 02.Interface | 02.IF - Intel Foundry | Send 4C1 Inventory Reconciliation Snapshot to IP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/3126%20R3_FTS_Send%204C1%20Inventory%20Reconciliation%20Snapshot%20to%20IP%20-%20.pptx?d=w27fcd89a6f084704ae75c513b0c9178d&csf=1&web=1&e=DPPXoq | 02.No | 01.Yes |  | 2025-11-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | SFT | 2025-12-08 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-27 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-23 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-25 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-20 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-04 04:16 | cell-link@smartsheet.com | 2026-03-20 09:19 | 10 | 2025-11-24 | 01.S4 |  |  | 1 | 1.45 | 1677 | INT-CR1334 | R3 ITC1 | [6 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-03-09 | 2026-03-09 | 2026-02-17 | 2026-02-17 | 2026-03-09 | 2026-03-09 | 2026-02-24 | 2026-02-17 | 2026-02-17 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 |  |  |  |  | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | [5 empty] | 2026-01-23 | 2026-02-13 | 2026-02-23 |  | 2026-03-06 |  |  |  | 1 | 02. IF Customers | 3357 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: follwoing up for approvals from respective teams. FUT all TC and walkthorugh completed 3/13:New test data created , retest in progress. Target to complete testing by EOD. 3/6: issues has been identified and based on that Defect has been raised to onsite tech team 2/24: Fileshare path is shared with MW team, they are working on SFT integration. No ETA yet 2/20: MW ETA 2/27,MW ETA 2/27 2/16: Build in Progress. ETA: 2/13. Awaiting confirmation from Tech team. 2/10: FS walk through completed. Build in progress | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/11: E2E FUT in progress along with defect fixes. Current status: E2E FUT in progress Issue: FUT delayed Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-24 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3125 | LOGI1676 | 02.Interface | 02.IF - Intel Foundry | Send 4C1 Inventory movement Stock type change and cycle count to IP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/3125%20R3_FTS_Send%204C1%20Inventory%20Reconciliation%20Snapshot%20to%20IP.pptx?d=w2ec9125675024f72920838e490476880&csf=1&web=1&e=d69CzV | 02.No | 01.Yes |  | 2025-11-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | SFT | 2025-12-08 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-19 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-23 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-25 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-20 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-04 04:16 | cell-link@smartsheet.com | 2026-03-20 09:13 | 10 | 2025-11-24 | 01.S4 |  |  | 1 | 1.45 | 1676 | INT-CR1334 | R3 ITC1 | [5 empty] | 2026-01-19 | 2026-01-19 | 2026-01-23 | 2026-01-19 | 2026-03-09 | 2026-03-09 | 2026-02-17 | 2026-02-17 | 2026-03-09 | 2026-03-09 | 2026-02-24 | 2026-02-17 | 2026-02-17 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 |  |  |  |  | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | [5 empty] | 2026-01-23 | 2026-02-13 | 2026-02-23 |  | 2026-03-06 |  |  |  | 1 | 02. IF Customers | 3355 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: follwoing up for approvals from respective teams. FUT all TC and walkthorugh completed 3/13: based on internal review document updated, to be sent out for approval by EOD. 3/6: Had working session with tech yestyerday based on the fixes retest in progress 2/24: Fileshare path is shared with MW team, they are working on SFT integration. No ETA yet 2/20: MW ETA 2/27,MW ETA 2/27 2/16: Build in Progress. ETA: 2/13. Awaiting confirmation from Tech team. 2/10: FS walk through completed. Build in progress | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/11: E2E FUT in progress along with defect fixes. Current status: E2E FUT in progress Issue: FUT delayed Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-24 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3070 | LOGI1675 | 02.Interface | 02.IF - Intel Foundry | Interface for SiGaC to extract inventory data from EWM to meet their existing business needs​ | 07. FTS IF | 7.4 FTS IF - EWM | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3070_R3_FTS%20IF_Chems%20%26%20Gases_Interface%20for%20SiGaC%20to%20extract%20inventory%20data%20from%20EWM%20to%20meet%20their%20existing%20business%20needs%E2%80%8B.pptx?d=w54a5670e8d1148aa85e9e4ee93297017&csf=1&web=1&e=sSkvDG | 02.No | 01.Yes |  | 2025-11-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 01.Yes | 12015 | SiGaC (Site Gas and Chemical) |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-01-07 | 100% | 2026-02-05 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-06 |  |  | 2026-02-06 | 2026-02-02 | 2026-02-06 |  |  | 2026-02-06 | 2026-02-02 | 2026-04-30 | 2026-04-30 | 36% | 2026-04-30 | 2026-03-09 | 2026-04-30 |  | 2026-02-20 | 2026-02-27 | 2026-03-12 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-04-30 | 2026-04-30 | jenoronha@deloitte.com | 2025-11-04 04:16 | ryapark@deloitte.com | 2026-04-07 12:27 | 6 | 2025-11-24 | 01.S4 |  |  | 1 | 1.45 | 1675 | INT-CR1375 | R3 ITC1 | [6 empty] | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-02 |  | 2026-02-06 |  |  |  | 2026-02-06 |  |  |  | 2026-04-30 | 2026-04-27 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | [5 empty] | 2026-02-06 | 2026-02-20 | 2026-02-06 |  | 2026-03-04 | TM | WIINGS Only | TRUE | 1 |  | 3368 | [7 empty] | 4. Completed | 1. Approved no action | 03/12: FUT is conditionally approved by IT & Biz, based on understanding that actual Bapp testing will done in ITC1. 03/10: Defect is resolved and tested, awaiting biz approval on existing requirement. For new field addition on payload defect as CR # 8175 created and assigned to tech. Tech ETA 03/11. 03/09: Defect 8017 is fixed by tech team, call is scheduled with devloper in US time as defect will be tested in debugger. New defect will be created to add new field in payload as per biz request. 03/06: Defect # 8017 created for issue while running failed batch job. Also based on discussion on yesterday's call with biz, SIGAC is expecting new field to be added payload. Checking tech efforts and will revert to Biz by EOD. 03/02: S4 FUT results shared with Biz, awaiting feedback. Will plan to schedule call this week for document overview based on SIGAC team availability. 02/27: S4 FUT completed and sent for business approval. document shared with B App PS and IT 02/23: Awaiting tech team confirmation on build completion. 02/20: Build in progress, no further update from tech. 02/16: Awaiting ETA from tech team for FUT execution. 2/10: FS walk through completed. Build in progress | 2026-04-30 | Y | 99. Logistics |  |  |  | 03/11: FUT completed and sent for approval and validation for SiGac team Current state: FUT completed and sent for approval and validation for SiGac team Issue: FUT delayed Next steps: Awaiting Approval Help needed: N/A FUT - 03/13 | 0204 FS Approved | 2. Risk | At risk for S23 | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint OB1 | 2026-03-09 | 2026-03-02 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 3088 | LOGI1626 | 02.Interface | 02.IF - Intel Foundry | Inventory adjustment data in XML format from Kommand auto-store to SAP EWM | 07. FTS IF | 7.4 FTS IF - EWM | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/3088-R3_FTS_IF_L-060-180_Inventory%20adjustment_RICEFW%20Intake%20Form.pptx?d=w80c2a9f15b2c4f5caedc7c9dad1a5793&csf=1&web=1&e=clocoe | 02.No | 01.Yes |  | 2025-10-27 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-10-13 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-29 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-16 | 2025-11-10 | 2026-01-23 | 2026-01-23 | 80% | 2026-05-03 | 2025-12-16 | 2026-05-03 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-28 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-19 | 2026-01-23 | 2026-01-23 | jenoronha@deloitte.com | 2025-09-28 03:35 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 6 | 2025-10-27 | 01.S4 |  |  | 1 | 1.45 | 1626 |  | R3 ITC1 | [6 empty] | 2025-10-29 | 2025-11-05 | 2025-10-29 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-19 | 2025-12-16 | 2025-12-16 |  | 2026-05-03 | 2026-05-03 |  | 2025-12-16 | 2025-12-16 |  |  | 2026-03-28 | 2026-03-28 | 2026-03-28 | [5 empty] | 2025-11-05 | 2025-12-05 | 2025-12-03 |  | 2026-03-04 | TM | GXO WIINGS Only | TRUE | 1 |  | 3300 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 03/20: Business/Intel is doing FUT review and daily calls are setup for addressing the comments. Serial Number Fix from BApp 5/5. 03/12: ETA for the serial number fix(by B-App) is not given by Intel. FUT is on hold. RAID# 03640. 03/04 The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27 FUT is in progress. 4th Working Session planned today with BApp + M/W + EW 03/06:The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27: FUT is in progress with B-App 02/16: FUT is in progress. 01/19: Awaiting the BApp to trigger the inbound messages to SAP 01/05: Awaiting build completion of LOGI1708 12/22 Dependent on the Object LOGI1708 | 2026-01-23 | N | 99. Logistics | GXO |  |  | 03/24: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Current status: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Issue: E2E FUT on hold. Next steps: B-App team upgrade will be completed by 05/03. Testing will resume from 05/05 Help needed: Wait for the B-App Upgrade to be completed FUT ETA: 05/15 |  | 5. Review Closed | At risk for S23+ |  | Complete | R3 Build & UT Sprint OB1 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 3058 | LOGI1595 | 02.Interface | 02.IF - Intel Foundry | Summary Reconciliation and Inventory Snapshot data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B59D2938A-860D-4A08-85E3-2D12752BFB5D%7D&file=3058__R3_FTS_IF_L-060-180_Inventory%20snapshot_SummaryReconciliation_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-22 | 2025-08-22 | 100% | 2025-08-18 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2026-01-06 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2026-01-06 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-28 | 2025-11-10 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-09 | 2026-01-06 | 2026-01-09 |  |  | 2026-01-07 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-11-07 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 10 | 2025-08-30 | 01.S4 |  |  | 2 | 2.9 | 1595 |  | R3 ITC1 | [6 empty] | 2025-08-18 | 2025-08-22 | 2025-08-18 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-06 | 2026-01-09 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-08-22 | 2025-09-26 | 2025-10-24 |  | 2026-01-23 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3242 |  |  | WIINGS |  |  |  |  | 4. Completed |  | 01/19 : Defect 6194 is created to fix certain bugs after business review. 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 11/13 EP: Roadblock - RAID02864 due 11/14 | 2026-01-09 | Y | 99. Logistics | GXO | [7 empty] | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3057 | LOGI1594 | 02.Interface | 02.IF - Intel Foundry | Pickresult(Pick Warehouse task confirmation) data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD77B6A83-9EBB-44F2-B15B-2A3C422A0A3F%7D&file=3057__R3_FTS_IF_LO-160-080_Pickresult_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-22 | 2025-08-22 | 100% | 2025-08-18 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-30 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-28 | 2025-11-10 | 2026-01-23 | 2026-01-23 | 80% | 2026-05-03 | 2025-10-30 | 2026-05-03 |  | 2026-02-02 | 2026-03-27 | 2026-03-27 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-11-07 | 2026-01-23 | 2026-01-23 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 6 | 2025-08-30 | 01.S4 |  |  | 2 | 2.9 | 1594 |  | R3 ITC1 | [6 empty] | 2025-08-18 | 2025-08-22 | 2025-08-18 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-11-07 | 2025-10-28 | 2025-10-28 |  | 2026-05-03 | 2026-05-03 |  | 2025-10-30 | 2025-10-30 |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-08-22 | 2025-09-26 | 2025-10-24 |  | 2026-03-04 | TM | GXO WIINGS Only | TRUE | 1 |  | 3240 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 03/20: Business/Intel is doing FUT review and daily calls are setup for addressing the comments. Serial Number Fix from BApp 5/5. 03/12: ETA for the serial number fix(by B-App) is not given by Intel. FUT is on hold. RAID# 03640. 03/04 The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27 FUT is in progress. 4th Working Session planned today with BApp + M/W + EW 03/06:The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27: FUT is in progress with B-App 02/16: Defects fixed. Working with Security team for Authoirization issues 01/19: Awaiting the BApp to trigger the inbound messages to SAP 01/05: Awaiting build completion of LOGI1708 12/22 Dependent on the Object LOGI1708 | 2026-01-23 | N | 99. Logistics | GXO |  |  | 03/24: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Current status: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Issue: E2E FUT on hold. Next steps: B-App team upgrade will be completed by 05/03. Testing will resume from 05/05 Help needed: Wait for the B-App Upgrade to be completed FUT ETA: 05/15 |  | 5. Review Closed | At risk for S23+ |  | Complete | R3 Build & UT Sprint OB1 |  | 2025-10-30 | 2025-10-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3056 | LOGI1593 | 02.Interface | 02.IF - Intel Foundry | Replenresult(Putaway warehouse task confirmation) data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDB3F5DA9-79F9-4FBD-8141-2F622C62273D%7D&file=3056__R3_FTS_IF_L-040-160_Replenresult_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-22 | 2025-08-22 | 100% | 2025-08-18 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-30 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-30 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-19 | 2025-09-30 | 2025-10-08 | 100% | 2025-10-10 | 2025-11-10 | 2026-01-23 | 2026-01-23 | 80% | 2026-05-03 | 2025-10-30 | 2026-05-03 |  | 2026-03-02 | 2026-03-27 | 2026-03-27 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-09-30 | 2026-01-23 | 2026-01-23 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 6 | 2025-08-30 | 01.S4 |  |  | 2 | 2.9 | 1593 |  | R3 ITC1 | [6 empty] | 2025-08-18 | 2025-08-22 | 2025-08-18 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2026-05-03 | 2026-05-03 |  | 2025-10-30 | 2025-10-30 | 2026-03-09 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-08-22 | 2025-09-26 | 2025-10-24 |  | 2026-03-04 | TM | GXO WIINGS Only | TRUE | 1 |  | 3251 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 03/20: Business/Intel is doing FUT review and daily calls are setup for addressing the comments. Serial Number Fix from BApp 5/5. 03/12: ETA for the serial number fix(by B-App) is not given by Intel. FUT is on hold. RAID# 03640. 03/04 The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27 FUT is in progress. 4th Working Session planned today with BApp + M/W + EW 03/06:The FUT for Non-serial scenarios are sent for review, serial number scenarios are dependent on B App readiness 02/27: FUT is in progress with B-App 02/16: Defect 7127 is still in progress 01/19: Awaiting the BApp to trigger the inbound messages to SAP 01/05: Awaiting build completion of LOGI1708 12/22 Dependent on the Object LOGI1708 10/23 EP: Share reason for Roadblock 10/16 EP: Share reason for Roadblock and Revise FUT due date JAN276 | 2026-01-23 | N | 99. Logistics | GXO |  |  | 03/24: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Current status: 50% of FUT is complete. Remaining FUT is on hold due to fix from KPI BApp undergoing upgrade for Serial Numbers. Issue: E2E FUT on hold. Next steps: B-App team upgrade will be completed by 05/03. Testing will resume from 05/05 Help needed: Wait for the B-App Upgrade to be completed FUT ETA: 05/15 |  | 5. Review Closed | At risk for S23+ |  | Complete | R3 Build & UT Sprint OB1 |  | 2025-10-30 | 2025-10-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3055 | LOGI1591 | 02.Interface | 02.IF - Intel Foundry | MergePick (Pick Warehouse task)data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B007318A6-A2AA-4F0F-8E84-6602A15320D5%7D&file=3055__R3_FTS_IF_LO-160-050_MergePick_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-22 | 2025-08-22 | 100% | 2025-08-18 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-19 | 2025-09-30 | 2025-10-08 | 100% | 2025-11-28 | 2025-11-10 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-07 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-28 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-09-30 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1591 |  | R3 ITC1 | [6 empty] | 2025-08-18 | 2025-08-22 | 2025-08-18 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | [5 empty] | 2025-08-22 | 2025-09-26 | 2025-10-24 |  | 2026-01-23 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3246 |  |  | WIINGS |  |  |  |  | 4. Completed |  | 01/19: Business asking new req on AIF re-processing. Working with dev on feasibility. 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 10/23 EP: Share reason for Roadblock 10/16 EP: Share reason for Roadblock and Revise FUT due date JAN276 | 2026-01-09 | Y | 99. Logistics | GXO |  |  | 0107: E2E FUT completed and awaiting approval Current Status: DBaaS remote database setup was complete and Kommand Center application is up and running. Issue: BAPP (KPI) team need to provide API end point and credential details once their services are up Next Steps: Once the DB issue is resolved and KPI team shares the credential details, MW team can continue with development to complete the build and TUT of the service. Help Needed: N/A |  |  |  |  | Complete | R3 Build & UT Sprint 21 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3054 | LOGI1589 | 02.Interface | 02.IF - Intel Foundry | MergeReplen(Putaway Warehouse task) data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB45AC483-B67A-48FE-9AE5-86656129E736%7D&file=3054_R3_FTS_IF_L-040-120_MergeReplen_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-14 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-20 | 2025-10-24 | 2025-10-08 | 100% | 2025-11-28 | 2025-11-10 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-17 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-24 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1589 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-17 | 2026-01-17 | 2026-01-17 | [5 empty] | 2025-08-01 | 2025-09-26 | 2025-10-24 |  | 2026-01-07 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3243 |  |  | WIINGS |  |  |  |  | 1. On Track |  | 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 10/23 EP: Share reason for Roadblock 10/16 EP: Share reason for Roadblock and Revise FUT due date JAN276 | 2026-01-09 | Y | 99. Logistics | GXO |  |  | 0107: E2E FUT completed and awaiting approval Current Status: DBaaS remote database setup was complete and Kommand Center application is up and running. Issue: BAPP (KPI) team need to provide API end point and credential details once their services are up Next Steps: Once the DB issue is resolved and KPI team shares the credential details, MW team can continue with development to complete the build and TUT of the service. Help Needed: N/A |  | 5. Review Closed |  |  | Complete | R3 Build & UT Sprint 21 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3053 | LOGI1587 | 02.Interface | 02.IF - Intel Foundry | MergeItem (Product master)data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B05E3F4BE-5C81-4872-AE2B-71D823366E0C%7D&file=3053_R3_FTS_IF_L-060-220_MergeItem_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 63174 | Kommand Autostore |  |  | APIGEE | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-15 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-10-13 | 2025-10-24 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-19 | 2025-09-30 | 2025-10-08 | 100% | 2025-11-28 | 2025-11-10 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-30 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-11 01:04 | rishabhx.ashok.bhapkar@intel.com | 2026-04-08 07:01 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1587 |  | R3 ITC1 | [6 empty] | 2025-08-15 | 2025-08-15 | 2025-08-15 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-09-24 | 2025-10-03 | 2025-09-24 | 2025-09-24 |  | 2025-10-24 |  | 2025-09-26 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2025-11-28 | 2026-01-09 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-08-01 | 2025-09-26 | 2025-10-24 |  | 2026-01-07 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3239 |  |  | WIINGS |  |  |  |  | 4. Completed | 17. FUT In progress | 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 12/19 : Awaiting Defect 5544 | 2026-01-09 | Y | 99. Logistics | GXO |  |  | 0107: E2E FUT completed and awaiting approval Current Status: DBaaS remote database setup was complete and Kommand Center application is up and running. Issue: BAPP (KPI) team need to provide API end point and credential details once their services are up Next Steps: Once the DB issue is resolved and KPI team shares the credential details, MW team can continue with development to complete the build and TUT of the service. Help Needed: N/A |  | 5. Review Closed |  |  | Complete | R3 Build & UT Sprint 21 |  | 2025-10-03 | 2025-09-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3052 | LOGI1576 | 02.Interface | 01.IP - Intel Product | ECD_Interface between S4 to ECD for inventory status response | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1F713A14-7391-4A1F-B938-3E9BE1D1C6F5%7D&file=3052_R3_IP_Interfaces%20from%20ECD%20to%20S4%20for%20Inventory%20status%20and%20response%20back%20to%20ECD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 8785 | Excursion Containment Disposition |  |  | MuleSoft | 2025-08-18 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-10-28 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-05 | 2025-10-01 | 2026-01-27 | 2026-01-27 | 100% | 2026-01-27 | 2025-12-05 | 2026-01-27 |  |  | 2026-02-20 | 2026-03-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-27 | 2026-03-25 | N | 100% | 2026-03-25 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-12-03 | 2026-01-27 | 2026-01-27 | jenoronha@deloitte.com | 2025-07-24 22:21 | cell-link@smartsheet.com | 2026-03-24 23:01 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1576 |  | R3 ITC1 | [6 empty] | 2025-09-26 | 2025-09-26 | 2025-09-26 |  | 2025-10-28 | 2025-11-05 | 2025-10-28 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2025-12-05 | 2026-01-27 |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | [5 empty] | 2025-09-10 | 2025-10-24 | 2025-11-07 |  | 2026-02-27 |  |  |  | 1 |  | 3210 | [7 empty] | 4. Completed | 1. Approved no action | 3/18: Approved by IT/PS. 3/13: Walkthrough completed and awaiting approval. 3/6: Tech is analysing the defect 8039. 2/24:FUT in retest after port issue resolution. ETA 24/2 2/20: Mock payload prep in progress. 2/18: Dependent on LOGI1575 complete execution 2/16: Defect 7277 is open with tech. Tech team is working on the defect. 1/16: Dependent enhancement LOGE1327 is still in progress with tech. Tech ETA for LOGE1327 is 1/23. Build ETA: 1/30" | 2026-01-27 | Y | 99. Logistics |  |  |  | 03/24 : Submitted for Approval. |  | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-11-05 | 2025-10-27 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3052 | LOGI1575 | 02.Interface | 01.IP - Intel Product | ECD_Interface between S4 to 3PL for inventory status webservice​ | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1F713A14-7391-4A1F-B938-3E9BE1D1C6F5%7D&file=3052_R3_IP_Interfaces%20from%20ECD%20to%20S4%20for%20Inventory%20status%20and%20response%20back%20to%20ECD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MuleSoft | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2025-09-26 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2025-09-26 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-12 | [5 empty] | 2026-02-12 | 2026-02-12 |  |  | 2026-02-20 | 2026-03-25 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-27 | 2026-03-25 | N | 100% | 2026-03-25 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-07-24 22:21 | cell-link@smartsheet.com | 2026-03-24 23:01 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1575 |  | R3 ITC1 | [6 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-12 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 | 2026-02-12 | 2026-02-12 |  |  |  |  | 2026-02-12 | 2026-02-12 |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | [5 empty] | 2025-09-10 | 2026-02-06 | 2026-02-20 |  | 2026-02-27 |  |  |  | 1 |  | 3209 | [7 empty] | 4. Completed | 1. Approved no action | 3/18: Approved by IT/PS. 3/13: Walkthrough completed and awaiting approval. 3/6: Following up with Intel for approval 2/24: Defect# 7647 created for failure during the demo call today. Port set up was incorrect and is now corrected. validation in progress. 2/20: Documenation in progress and ETA 2/20 2/18: Retest in progress as 7277 is fixed. 2/16: Defect 7277 is open with tech. Tech team is working on the defect. 1/16: Dependent enhancement LOGE1327 is still in progress with tech. Tech ETA for LOGE1327 is 1/23. Build ETA: 1/30" | 2026-02-20 | Y | 99. Logistics |  |  |  | 03/24 : Submitted for Approval. |  |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-26 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3052 | LOGI1571 | 02.Interface | 01.IP - Intel Product | ECD_Interface from ECD to S4 for Inventory status call​ | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1F713A14-7391-4A1F-B938-3E9BE1D1C6F5%7D&file=3052_R3_IP_Interfaces%20from%20ECD%20to%20S4%20for%20Inventory%20status%20and%20response%20back%20to%20ECD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 8785 | Excursion Containment Disposition |  |  | MuleSoft | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-10-28 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-17 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-17 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-05 | 2025-10-01 | 2026-01-27 | 2026-01-27 | 100% | 2026-01-27 | 2025-12-05 | 2026-01-27 |  |  | 2025-12-12 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-19 | 2026-01-07 | N | 100% | 2025-12-24 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-03 | 2026-01-27 | 2026-01-27 | jenoronha@deloitte.com | 2025-07-24 03:57 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1571 |  | R3 ITC1 | [6 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-10-28 | 2025-11-05 | 2025-10-28 |  | 2025-10-17 | 2025-11-05 | 2025-10-17 | 2025-10-17 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2025-12-05 | 2026-01-27 |  |  | 2025-12-24 | 2026-01-07 | 2025-12-24 | [5 empty] | 2025-09-10 | 2025-10-24 | 2025-11-07 |  | 2025-12-19 |  |  |  | 1 |  | 3202 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/22: Submitted for review and approval 12/15: Working session scehduled with ECD, Mule and tech. TC 0/4 | 2026-01-27 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-11-05 | 2025-10-17 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2906 | LOGI1555 | 02.Interface | 02.IF - Intel Foundry | Straddle Plant to be automatically complete the Goods Receipt and write of the inventory | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2906_RX_FTS_IP%20IF_LOGL-060_080_Straddle%20Receiving%20and%20write%20off_RICEFW%20Intake%20form.pptx?d=waa94a6a1ad5b4515ad0ab73f3b50fa5a&csf=1&web=1&e=sxKoXy | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MuleSoft | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2025-10-08 | 2025-09-12 | 2025-09-19 | 2026-03-04 | 100% | 2026-03-09 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-11-28 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-06 | [5 empty] | 2026-03-06 | 2026-03-06 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-20 | N | 100% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-07-24 03:57 | cell-link@smartsheet.com | 2026-03-27 03:32 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1555 | INT-CR1586 | R3 ITC1 | [6 empty] | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-02-24 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 |  | 2026-03-04 |  | 2026-03-04 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 |  |  |  |  | 2026-03-06 | 2026-03-06 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-09-26 | 2025-12-05 | 2026-03-04 |  | 2026-03-04 |  |  |  | 1 |  | 3204 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 3/20: 8291 reopened as facing new issues like dump errors, issues in processing multiple payloads, escalated to tech and is WIP. 3/13:Defect 8291 being fixed by tech, issues related to processing of data received from ECA and others. FUT blocked till defect is fixed. 3/6: Middleware has completed the TUT on 3/5. FUT to be started from today 2/24: ECA completed the development and details are shared with MW team to complete middleware changes. No ETA 2/20: Dev in progress 2/16: Build in Progress. Awaiting ETA confirmation from Tech team. | 2026-03-04 | Y | 99. Logistics |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | Defects | Complete | R3 Build & UT Sprint 23 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2974 | LOGI1534_IP | 02.Interface | 01.IP - Intel Product | BRF+ Extractor( API interface) to fetch the data saved in the BRF+ decision tables in S4 system for consumption in ECA. Send the Data to ECA system.​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B788C41F4-F5A2-4248-B6F7-776A97DAA950%7D&file=2974_R3_IPIF-%20BRF%20%20Extractors%20for%20the%20ECA%20Spec%20requirement.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cgakumaresan%40deloitte.ca&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA0MTcxOTMxNiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-11 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-24 | 2025-11-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-07 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1.45 | 1534 | INT-CR0892 | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-08-12 | 2025-09-26 |  |  | 2025-11-07 | TM |  |  | 1 |  | 3152 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 11/04: Under intel review. Review done on 11/04 10/31: Internal review WIP, to be review with Intel next week 10/22: Defect 3821 open 10/10: Development is still in progress. FUT dates most likely will be in SP21 post Dev confirmation on TUT completion and handover for FUT Development is still in progress. FUT dates most likely will be in SP21 post Dev confirmation on TUT completion and handover for FUT | 2025-09-26 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2974 | LOGI1534_IF | 02.Interface | 02.IF - Intel Foundry | BRF+ Extractor( API interface) to fetch the data saved in the BRF+ decision tables in S4 system for consumption in ECA. Send the Data to ECA system.​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B788C41F4-F5A2-4248-B6F7-776A97DAA950%7D&file=2974_R3_IPIF-%20BRF%20%20Extractors%20for%20the%20ECA%20Spec%20requirement.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cgakumaresan%40deloitte.ca&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA0MTcxOTMxNiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-11 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-26 | 2025-09-26 | 2025-09-26 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 | LOGI1534_IP | 03.Medium | 0.3 | 0.435 | 1534 | INT-CR0892 | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-08-12 | 2025-09-26 |  |  | 2025-11-07 | TM |  |  | 1 |  | 3153 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 11/04: Under intel review. Review done on 11/04 10/31: Internal review WIP, to be review with Intel next week 10/24 - Defect 3822 10/22: FUT planned in sprint 20 and FUT testing in progress | 2025-09-26 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2748 | LOGI1427_IP | 02.Interface | 01.IP - Intel Product | Interface between S4 to Boundary Apps (PEGA-ISMQ) for real time data on Delivery details from both S4 IF & IP system | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2748_PTP_S4%20interface%20Delivery%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w65848fdc27a841b2a42d65d3fdbd7b98&csf=1&web=1&e=pyy3GV | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 37510 | PEGA Integrated Shipping Memo Questionnaires | S/4 | PEGA | APIGEE | 2025-05-19 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-23 | 2025-06-09 | 2025-06-13 | 2025-06-27 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-06-09 | 2025-06-13 | 2025-06-27 | 100% | 2025-06-27 | 2025-07-14 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-15 | 100% | 2025-08-15 | 2025-07-24 | 2025-08-15 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-04-21 02:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-05-05 | 01.S4 |  |  | 1 | 1.45 | 1427 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-05-30 | 2025-05-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-07-24 | 2025-08-15 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | Trade Apps | 2025-05-30 | 2025-07-18 | 2025-06-13 |  | 2025-10-08 |  |  |  | 1 |  | 2979 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2748 | LOGI1427_IF | 02.Interface | 02.IF - Intel Foundry | Interface between S4 to Boundary Apps (PEGA-ISMQ) for real time data on Delivery details from both S4 IF & IP system | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2748_PTP_S4%20interface%20Delivery%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w65848fdc27a841b2a42d65d3fdbd7b98&csf=1&web=1&e=pyy3GV | 02.No | 01.Yes |  | 2025-04-24 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 37510 | PEGA Integrated Shipping Memo Questionnaires | S/4 | PEGA | APIGEE | 2025-05-19 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-23 | 2025-06-09 | 2025-06-13 | 2025-06-27 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-06-09 | 2025-06-13 | 2025-06-27 | 100% | 2025-06-27 | 2025-07-14 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-24 | 2025-08-15 | 2025-08-15 | 100% | 2025-08-15 | 2025-07-24 | 2025-08-15 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-04-21 02:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-05-05 | 01.S4 | LOGI1427_IP | 03.Medium | 0.3 | 0.435 | 1427 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-05-30 | 2025-05-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-07-24 | 2025-08-15 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | Trade Apps | 2025-05-30 | 2025-07-18 | 2025-06-13 |  | 2025-10-08 |  |  |  | 1 |  | 2980 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2863 | LOGI1312 | 02.Interface | 08.EWM | Label printing data in XML format from SAP EWM to Spectrum/Loftware | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B535FFC56-07EA-489C-A498-B871111C3522%7D&file=R3_IP_Returns_Label_spectrum.pptx&wdLOR=c7C5E9B37-89A3-4A53-B96D-9C10B3F21FDC&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-03-10 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 64181 | Loftware Spectrum (IP) | S/4 | SPECTRUM | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2026-02-17 | 2025-08-29 | 2025-09-26 | 2025-10-08 | 100% | 2026-02-18 | 2025-08-29 | 2025-09-26 | 2025-10-08 | 100% | 2026-02-18 | [10 empty] | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-01 | 2026-02-18 | 2026-02-18 |  | 2025-12-19 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-03-07 08:15 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-10 | 01.S4 |  |  | 2 | 2.9 | 1312 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | [9 empty] | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2026-02-18 | 2026-02-18 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-05-16 | 2025-09-26 |  |  | 2026-02-04 | TM |  |  | 1 |  | 1637 | [7 empty] | 2. At Risk | 17. FUT In progress | 02/02: Defect 6074 fix is in progress. ETA for fix 01/30 (revised ETA 02/02). 3/10 TC Completed. 01/29: TUT is not yet approved. Raised defect # 6074 to address the IT review comments 01/22: Defect #6074 is fixed. Def resolution testing is in progress 01/19: Defect # 6074 reopened and reassigned to tech team. 3/10 TC Completed. 01/13: Defect # 6074 fixed by tech team. Testing will be started today. 2/10 TC Completed 01/05: Dev is completed on 01/02. FUT is in progress. 12/22: Dev is in progress. Revised Dev ETA : 12/22. 12/15: Dev is in progress. Dev ETA : 12/19. | 2025-09-26 | N | 99. Logistics |  |  |  | 1211: Development in progress. ETA by Tech is 12/22. Will be picked up for FUT in S22 |  |  |  | Defects | Complete | R3 Build & UT Sprint 23 |  | 2026-02-18 | 2026-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 584 | LOGI1309 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Finished Goods Advanced Shipping notifications from ODM suppliers via E2Open boundary application to S4 IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-160-0006_Receive_FG_ASN_From_ODM_Intel_Foundary.pptx?d=w3016b655516441e982cb507ae2db05bd&csf=1&web=1&e=B5HGdD | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-02 | 2025-02-21 | 2025-01-24 | 100% | 2025-02-20 | 2025-03-07 | 2025-03-14 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-03-07 | 100% | 2025-09-02 | 2025-04-07 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-02 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-04 | 2025-05-30 | 2025-09-01 | 2025-09-01 | 100% | 2025-09-10 | 2025-09-02 | 2025-09-10 |  | 2025-10-08 | 2025-10-24 | 2025-10-31 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-09-01 | 2025-09-01 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 4 | 5.8 | 1309 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-02-21 | 2025-02-20 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-13 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-02 | 2025-09-10 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 |  |  |  |  | B2B - E2open | 2025-02-21 | 2025-04-18 | 2025-04-18 |  | 2025-10-31 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2055 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14: All review comments are addressed, Awaiting further feedback/approval from ATDM IT & Business/PS 11/11 - Review comments received from Intel IT, Defect# 4442 created for the same ETA 11/12 11/04: Requires change in config. SIMS not in scope for R3 10/31: Under 5.1 testing. 9 out of 75 TC's completed 10/22: S4 15 out 75 TC's completed, and has open defects from S4 and E2Open. Time consuming due to high number of TC's. Defect 3860 10/17- 15 TC tested out of 75 10/09- FUT in progress , 4 TC tested out of 75 | 2025-09-01 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-02 | 2025-09-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2862 | LOGI1300 | 02.Interface | 01.IP - Intel Product | Discrepancy check for FAC receipts | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF302DF68-F28B-4E45-8C70-323C1D06C464%7D&file=R3_IP_Returns_Discrepency_checks_for_FAC_Receipts.pptx&wdLOR=c3F23B494-DE4C-43F4-A410-D26942865D56&action=edit&mobileredirect=true |  |  |  | 2025-03-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 9425 | Customer Quality & Reliability 360 |  |  | MULESOFT | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2025-07-16 | 100% | 2025-07-29 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-07-11 | 2025-07-25 | 2025-07-16 | 100% | 2025-07-16 | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-12 | 2025-07-21 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2025-12-31 | 2025-12-31 |  | 2025-12-19 | 2026-02-20 | 2026-03-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-03-11 | N | 100% | 2026-03-11 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-09-26 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-02-28 07:22 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-05 | 01.S4 |  |  | 2 | 2.9 | 1300 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-29 | 2025-08-22 | 2025-07-29 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-07-25 |  | 2025-07-16 |  | 2025-08-13 | 2025-08-12 | 2025-08-12 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-31 | 2025-12-31 |  | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | [5 empty] | 2025-05-16 | 2025-09-26 | 2025-07-25 |  | 2026-02-27 | TM |  |  | 1 |  | 1635 | [7 empty] | 4. Completed | 3. Awaiting Approval | 03/06: All defects have been fixed by the Tech team, and the FUT has been submitted to the Business for review and approval. 02/27: First FUT walkthrough completed with Bus. on 02/25. Bus. Review feedback WIP. Defect # 7762, 7776 raised.Tech ETA : 02/26. Unexpected Process Scenarios code is not working as expected. Working TUT+FUT for Unexpected Process. Tentative ETA: 3/4 to send for intel. 02/20: 4/15 TC is Completed. Defect #7505, #7555 is being worked upon by Tech. Defect 7351,7393 are closed. FUT is in roadblock 02/16: 2TC/15 TC Completed. New defect created #7351 is created for the DAM Integration. 01/19: FUT is on hold. Dependent on LOGI1262/63/71. Will be spilled over to Sprint 22 01/13: FUT is on hold. Dependent on LOGI1262/63/71. Will be spilled over to Sprint 22 12/22: FUT is on hold. Dependent on LOGI1262/63/71. Will be spilled over to Sprint 22 12/15: FUT is on hold. Dependent on LOGI1262/63/71. Waiting for FUT to finished for dependent objects. | 2025-09-30 | N | 99. Logistics |  |  |  | 1211: TUT approved. 5.1 in S21, 5.2 in S22 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | Yes | Plant needs to be updated in table ZTOTC_PARAMS | Yes | Regression Testing Only | No |  | 2026-02-16 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2682 | LOGI1295 | 02.Interface | 01.IP - Intel Product | ECD_Interface between S/4 and ECD for completion status | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2682_R3_IP_Interface%20between%20ECD%20and%20S4.pptx?d=wc402c54e8c8541feacb38a86991ca527&csf=1&web=1&e=0Zr2dW | 02.No | 02.No |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 8785 | Excursion Containment Disposition |  |  | MULESOFT | 2025-06-30 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-11 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-10-23 | 2025-08-29 | 2025-09-26 | 2025-10-08 | 100% | 2025-10-27 | 2025-08-29 | 2025-09-26 | 2025-10-08 | 100% | 2025-10-27 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | 2025-10-01 | 2026-01-27 | 2026-01-27 | 100% | 2026-01-27 | 2025-12-01 | 2026-01-27 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-03 | 2026-01-27 | 2026-01-27 | pgaroo@deloitte.com | 2025-02-28 07:22 | cell-link@smartsheet.com | 2026-03-27 02:45 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1295 |  | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-12-03 | 2025-12-01 | 2025-12-01 |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2025-12-01 | 2026-01-27 |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-08-13 | 2025-09-26 | 2025-10-08 |  | 2026-03-04 |  |  |  | 1 |  | 2144 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW | 3/20:Dependent on LOGI1291 which has defect#8497 in progress with tech. 3/13: Trigger response to ECD from S4 is not working and is being worked upon by MW team. 3/6: Dependant on LOGI1291 completion. 2/24: 2/20: dependent on complete execution of LOGI1575 and LOGI1576 2/18: dependent on complete execution of LOGI1575 and LOGI1576 2/16: Dependent on LOGI1290. Testing in progress for LOGI1290. 1/16: Dependent enhancement LOGE1327 is still in progress with tech. Tech ETA for LOGE1327 is 1/23. Build ETA: | 2026-01-27 | Y | 99. Logistics |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 22 |  | 2025-10-27 | 2025-10-27 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2682 | LOGI1291 | 02.Interface | 01.IP - Intel Product | ECD_Interface between S/4 and 3PL to send plant/batch level hold/unhold information for webservice plants to hold/unhold inventory in 3PL | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2682_R3_IP_Interface%20between%20ECD%20and%20S4.pptx?d=wc402c54e8c8541feacb38a86991ca527&csf=1&web=1&e=0Zr2dW | 02.No | 02.No |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-11 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2025-08-29 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2025-08-29 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-16 | [5 empty] | 2026-02-16 | 2026-02-16 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-31 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | pgaroo@deloitte.com | 2025-02-28 07:22 | cell-link@smartsheet.com | 2026-03-31 08:23 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1291 |  | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-16 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 | 2026-02-16 | 2026-02-16 |  |  |  |  | 2026-02-16 | 2026-02-16 |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | [5 empty] | 2025-05-16 | 2026-02-06 | 2026-02-20 |  | 2026-03-04 |  |  |  | 1 |  | 2143 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 3/27: Negative test case is not completed in workshop. 3/26: Business is reviewing the document. 3/25: Under Intel review. additional ask from workshop are being addressed. ETA 3/25. 3/24: FUT sent out for review 3/23: all defects resolved, retest in progress- ETA to send for review- 03/23 3/20:Defect#8476 still in progress with tech. working session in place with tech ETA 3/20. 3/18:Defect#8476 in progress with tech. working session in place with tech ETA 3/18. 3/17: Defect to be raised for sloc impact on goods mvt. Alignement in progress with tech. 3/13:Defect 7858,8343 is being worked upon by tech and will be then revalidated in workshop 3/16 3/12: ETE FUT will be triggered by ECD 3/13 for testing the hold/unhold request. 3/10: Retest to be validated against LOGI1290 and Inventory status FUTs. TC?? 3/9:Defect#7858 ETA: ??? 3/6: Tech is working on the defect 7858 3/5: QTY calculation issue when response from 3PL is recieved. Defect# 8039 ETA?? 3/04: Defect #7858 is reopened and tech is workingon it. 3/02:Defect#7858 is reopened as response from 3PL is not getting updated in S4. Tech ETA:??? 2/27: Defect 7858 is created and assigned to tech. dependent on LOGI1290 adn shoulkd trigger automatically. 2/26: Payload not reaching to end points and ECD due to missing authroization. Security team to update the auth (3Defect - 7745). ETA ?? 2/25: Defect #7724 is created where the request is not reaching to mulesoft correctly. (Awaiting tech ETA) 2/24:Testing in progress for S4 to 3PL webservice plants 24/2. 2/23:S4 testing in progrees with the mocked data from LOGI1290. Also have asked ECD to trigger real time data for hold/unhold request. 2/20:dependent on complete execution of LOGI1575 and LOGI1576. S4 testing with mock data is in progress. 2/19: dependent on complete execution of LOGI1575 and LOGI1576 2/17: Test push from gateway client is in progress. 2/16: Dependant on LOGI1290. 2/12: Blocked due to Defect 7219 raised for LOGI1290. Getting ABAP dump. Mule is not able to connect to S/4. ETA: Not provided. 2/10: Defect 7041 is still with Tech. Basic functionality of the Enhancement is still not working and other interfaces on ECD cannot be tested. Development not ready and tech ETA 2/63/20:Defect#8467 still in progress with tech. working session in place with tech ETA 3/20. 3/13:Defect is being worked upon by tech and will be then revalidated in workshop 3/16 3/6: Tech is working on the defect 7858 2/24:Testing in progress for S4 to 3PL webservice plants 24/2. 2/20:dependent on complete execution of LOGI1575 and LOGI1576. S4 testing with mock data is in progress. 2/18: dependent on complete execution of LOGI1575 and LOGI1576 2/16: Dependent on LOGI1290. Testing in progress for LOGI1290. 1/16: Dependent enhancement LOGE1327 is still in progress with tech. Tech ETA for LOGE1327 is 1/23. Build ETA: 2/6" | 2026-02-20 | Y | 99. Logistics |  |  |  | 03/24 : Submitted for Approval. |  | 2. Risk | On track for S23+ | Defects | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-26 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2682 | LOGI1290 | 02.Interface | 01.IP - Intel Product | ECD_Interface from ECD to S4 for Inventory Hold/unhold request | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2682_R3_IP_Interface%20between%20ECD%20and%20S4.pptx?d=wc402c54e8c8541feacb38a86991ca527&csf=1&web=1&e=0Zr2dW | 02.No | 02.No |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 8785 | Excursion Containment Disposition |  |  | MULESOFT | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-07-24 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-10-23 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-15 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-15 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | 2025-10-01 | 2026-01-27 | 2026-01-27 | 100% | 2026-01-27 | 2025-12-01 | 2026-01-27 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-25 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-03 | 2026-01-27 | 2026-01-27 | pgaroo@deloitte.com | 2025-02-28 07:22 | cell-link@smartsheet.com | 2026-03-24 23:01 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1290 |  | R3 ITC1 | [6 empty] | 2025-07-24 | 2025-07-24 | 2025-07-24 |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-12-03 | 2025-12-01 | 2025-12-01 |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2025-12-01 | 2026-01-27 |  |  | 2026-03-25 | 2026-03-27 | 2026-03-25 | [5 empty] | 2025-05-16 | 2025-09-26 | 2025-10-08 |  | 2026-03-04 |  |  |  | 1 |  | 2148 | [7 empty] | 4. Completed | 1. Approved no action | 3/18: Approved by IT/PS. 3/13: Walkthrough completed. Approval will be done together with LOGI1291/95. 3/6: Updated FUT documentation was shared. Intel team will only validate once LOGI1575 and LOGI1576 are completed. 2/24: Demo is plannned 26/2 and there is failure for which defect#7676 raised. 2/20: Documenation in progress. ETA 2/20 2/18: Test case documenation in progress 2/16: 7219 defect is fixed, data is now landing in the MRB table. Testing in progress. "1/16: Dependent enhancement LOGE1327 is still in progress with tech. Tech ETA for LOGE1327 is 1/23. Build ETA: 2/6" | 2026-01-27 | Y | 99. Logistics |  |  |  | 03/24 : Submitted for Approval. |  | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-10-15 | 2025-10-15 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2118 | LOGI1272 | 02.Interface | 01.IP - Intel Product | Response to goods receipt posting from SAP to 3PL - EDI 4C1B | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_LI-120_190_Enhancement%20-%2040_%20RICEFW%20Intake%20form.pptx?d=w0f5beaf6af8447eea8bf80b71ebac433&csf=1&web=1&e=DC8Sq8 | 02.No | 01.Yes | LOGE0945 | 2024-12-18 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | WMS (3PL) | MULESOFT | 2025-01-20 | 2025-02-28 | 2025-02-28 | 100% | 2025-02-28 | 2025-03-17 | 2025-03-21 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-11 | 2025-04-25 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-15 | 2025-05-15 | 100% | 2025-05-15 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-22 | 2025-08-13 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.45 | 1272 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-15 | 2025-05-15 | 2025-05-15 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-04-18 | 2025-04-25 |  | 2025-08-22 |  |  |  | 1 | 03. IP Customers | 2717 | [9 empty] | 9/5: FUT completed and Approved. EP: 09/03: Neetu update 09/02 this object is FUT Complete 8/29: conditional approval from IT. Awaiting PS approval 8/25: In progress. ETA: 8/26 | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | Yes | Param table entry addition. | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2861 | LOGI1271 | 02.Interface | 08.EWM | Duplicate ULT checks for Non-CPU returned products | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Duplicate_ULT_Check_ECA_API.pptx?d=wc14298572e064955ba94fbeb84242aa3&csf=1&web=1&e=3wTdmR | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  | 03. NA | 01.Deloitte | 02.High |  | 02.No | NA | NA | S/4 | ECA | NA | 2025-02-24 | 2025-04-11 | 2025-04-11 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  | 2025-10-08 | 2025-12-19 | 2026-01-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-22 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-02-19 08:26 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-28 | 01.S4 |  |  | 2 | 2.9 | 1271 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | [5 empty] | 2025-04-11 | 2025-07-18 |  |  | 2026-01-23 | TM |  |  | 1 |  | 1634 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 01/19: One round of review completed 01/16. Waiting for business response. 01/13: Team is working on business review comments. Raised defect # 6221 to fix the review comments. Tech ETA: 01/13. 01/05:MW team has fixed the issues. FUT is in progress for remaining scenarios. 12/22: Issue identified in MW mapping to ECA. Email communication is in place with Intel MW team. ETA for fix 12/22. Defect 5770 defect resolution testing is in progress 12/15: 2/13 TC Completed. Defect # #5594 and 5595 raised to Tech Team. Dev ETA: Waiting | 2025-07-18 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2858 | LOGI1270 | 02.Interface | 08.EWM | IWRAP interface for CWP availibilty check(Inbound interface) | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_IWRAP_for_CWP%20availability.pptx?d=wbcc09753bcdd4ed98c6d3dff684c4567&csf=1&web=1&e=6cKGZF | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 11215 | Integrated Warranty Requirements and Planning | IWRAP | S/4 | APIGEE | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-24 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-24 | 2025-08-08 | 2025-08-22 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-01 | 2025-09-26 | 2025-08-13 | 100% | 2025-08-04 | 2025-09-27 | 2026-02-06 | 2026-02-06 | 100% | 2026-02-04 | 2025-09-24 | 2026-02-04 |  | 2025-12-19 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-09 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2026-02-06 | 2026-02-06 | pgaroo@deloitte.com | 2025-02-19 08:26 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-28 | 01.S4 |  |  | 2 | 2.9 | 1270 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 |  | 2025-08-22 |  | 2025-07-16 |  | 2025-09-26 | 2025-08-04 | 2025-08-04 |  | 2026-02-06 | 2026-02-04 | 2026-02-04 | 2025-09-24 | 2026-02-04 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  |  |  |  | Return for Credit | 2025-05-16 | 2025-09-12 | 2025-08-22 |  | 2026-02-04 | TM |  |  | 1 |  | 1631 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02: Intel Biz Approval received on 01/30. Reminder mail t be sent for Intel IT Approval 01/29: FUT for remaining scenarios started today. Planned for FUT Walkthrough tomorrow in the workshop. 01/22: Def 6197 is closed. A new def Req Chnge #6557 is created to address biz requirement provided in workshop yesterday. Tech ETA to close def:01/22 01/19:Defect # 6197 reopened as functionality is not working as expected. 01/13: Defect #6197 raised for additional issues identified in API2 for updation of Custom fields 01/05: TC 2/9 Completed.FUT is in progress for remaining scenarios 12/22: A new defect 5871 raised based on FUT along with B-App team. ETA 12/23 12/15:Raised defect #5584 to fix the issue in API response processing. EP: 09/11: No Ext FUT; Why is this status red - will object close 09/12? | 2026-02-06 | Y | 99. Logistics |  |  |  | 1211: TUT approved. 5.1 in S21, 5.2 in S22 |  |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2025-09-24 | 2025-09-24 | Yes | Maintain new "Ship to Plant" Entries in ZTOTC_PARAMS | Yes | Regression Testing Only | No |  | 2026-03-09 | 2026-04-01 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2168 | LOGI1267 | 02.Interface | 01.IP - Intel Product | Inventory Reconciliation with Consignment hub – EDI 4C1 with version control | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B970E6AFF-DEAB-4BD2-BA85-AB31260C499D%7D&file=R3_FTS_IP_LOGISTICS_LI-120_190_Enhancement%20-%2050_%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true | 02.No | 02.No | LOGE1253 | 2025-02-19 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-02-21 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-05-11 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-20 | 2025-06-02 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-06-02 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-20 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-21 | 2025-08-15 | 2025-06-11 | 100% | 2025-06-03 | 2025-05-23 | 2025-07-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-05 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-02-18 21:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1267 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-20 |  | 2025-06-06 |  | 2025-08-15 | 2025-06-03 | 2025-06-03 |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-08-04 | 2025-08-04 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  |  |  |  | B2B - OpenText | 2025-03-28 | 2025-06-13 | 2025-06-20 |  | 2025-09-19 |  |  |  | 1 |  | 1603 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: Awaiting approvals from IT 10/3: Under Intel Review 9/29: Defect 3167 in progress. Call scheduled with business on 9/30 to align on payload issues. 9/22: FUT Blocked due to AIF Processing Errors. Defect - 3167 raised | 2025-08-15 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2851 | LOGI1263 | 02.Interface | 08.EWM | Retrieve the GES scanned CPU entitlement check details | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Retrieve_Entitlement_Details_CPU.pptx?d=wd17fce2ee38b451f9423c1d728f7a659&csf=1&web=1&e=UY2R99 | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  | 03. NA | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 39609 | Entitlement Orchestration Service | Entitlement Orchestration Layer | S/4 | NA | 2025-02-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-08-15 | 2025-09-12 | 2025-08-13 | 100% | 2025-08-09 | 2025-09-01 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-01 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | [10 empty] | 2025-09-17 | 2026-01-30 | 2026-01-30 | 100% | 2026-01-30 | 2025-07-21 | 2026-01-30 |  | 2025-10-08 | 2025-11-21 | 2026-02-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-02-13 | 2026-02-13 | N | 100% | 2026-02-26 | Sprint 23 Week 1 | R3 Build & UT Sprint 23 | 2025-09-12 | 2026-01-30 | 2026-01-30 | pgaroo@deloitte.com | 2025-02-17 06:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-28 | 01.S4 |  |  | 2 | 2.9 | 1263 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-09-12 | 2025-08-09 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [9 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2025-07-21 | 2026-01-30 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  |  |  |  | Return for Credit | 2025-04-18 | 2025-09-12 |  |  | 2026-02-13 | TM |  |  | 1 |  | 1577 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 02/20: Defect #7743 is fixed. Defect resolution testing is in progress. 02/16:Tech team is working on defect 7311, 7331. Func team is supporting Tech team on defect resolution. 01/19: Fiori changes are still pending. Defect # 6281 raised to fix the fiori issues 01/13: Defect #6096- Fixed by Tech, Func Team to test the defect. #6155- Pending with fiori Team. Additional Test cases received from business 01/05: Follow-up mail sent to Intel for review and approval. 12/22: New Defect 5883 raised to fix the determination of DR's.18/30 TC Completed. 12/15: 14/25 TC Completed. Remaining TC require data in B.Apps System. Mail sent to B.apps team for data. 12/01: Dev Team has raised Service request # to change the PULL endpoints to connect the B-App system.FUT is in progress for POST functionality. 11/24: Defect 4860 with dev, ETA 11/26. Two week is required to complete the FUT as ~30 test case to be FUTed. This will spill over to next sprint. 11/18: Data not populating on the GR Fiori App, And data is not getting stored at table level. 11/14: Data not found in BA system. Asked boundary apps team to check the issue from BA apps side. | 2026-01-30 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 22 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2850 | LOGI1262 | 02.Interface | 08.EWM | Entitlement Output processing to perform discrepancy checks | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Entitlement_Output_Processing.pptx?d=w8e59dd10d3a944d18ec5696621ce1f70&csf=1&web=1&e=VyI1Em | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 39609 | Entitlement Orchestration Service | Entitlement Orchestration Layer | S/4 | NA | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | [10 empty] | 2025-09-15 | 2026-01-30 | 2026-01-30 | 100% | 2026-01-20 | 2025-07-21 | 2026-01-20 |  | 2025-10-08 | 2026-02-20 | 2026-03-12 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 23 Week 2 | R3 Build & UT Sprint 23+ | 2025-07-18 | 2026-01-30 | 2026-01-30 | pgaroo@deloitte.com | 2025-02-17 06:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1262 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2026-01-30 | 2026-01-20 | 2026-01-20 | 2025-07-21 | 2026-01-20 |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 |  |  |  |  | Return for Credit | 2025-04-18 | 2025-07-18 |  |  | 2026-02-27 | TM |  |  | 1 |  | 1576 | [7 empty] | 4. Completed | 3. Awaiting Approval | 03/12: Revised FUT document sent to Intel for review and approval on 03/11. FUT under Intel IT Review. 1 TC is pending due to unavailability of test data from B-App 03/06: Aligned with biz for conditional approval, Intel IT sent new feedback points on the FUT today. 02/27: 6/9 Opens closed. Defect # 7706 raised to fix the DR's determination for multiple sublines. Tech ETA: 02/27.Revised FUT will be sent for intel review by 02/27. 02/23: FUT sent to Intel for Review and approval on 02/21 02/20:5/18 TC Completed. FUT is in progress. Defect # 7571 Retesting is in progress. There was issue with BA system for 2 days so we couldn't able to test the TC. 02/16: 5/18 TC Completed. FUT is in progress. Defect #7156 Retesting is in progress 01/19: There is issue in getting the data from B.Apps. Mail to be sent to B.apps to check the data issue. 01/13: Defect #6154 is being worked upon by tech today. ETA to be prpvided by Tech 01/05: Email sent to B-App team to send relvant test data for Testing 12/22: Awaiting confirmation from OTC team on the object completion. Reminder mail sent to OM team. 12/15: Dependent on OTC tower object OTCI1598, Tech ETA on defect 5333 resolution by 12/15. Waiting for OM team to confirm the test result. 12/08- 4:30 pm--Token issue resolved, FUT To be started. 12/08: B-APP product request is pending for approval to perform testing. And we also requested to B.Apps team to load required data in B-Apps system. Token authorization related issue is coming for functional team. 15 TC. 12/05: B-APP product request is pending for approval to perform testing. And we also requested to B.Apps team to load required data in B-Apps system. 12/01: Dev team has raised Service Request on 11/28 to change the POST endpoints to connect the B-App system. 11/24: CR changes done but issue while doing FUT as auth issue coming. Tech team to raise Service Request to Intel Basis team. 11/18: CR#0833 raised to fix the core functionality and it is planned in S20 build 11/14: CR#0833 raised to fix the core functionality and it is planned in S20 build | 2026-01-30 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2847 | LOGI1261 | 02.Interface | 08.EWM | Discrepancy resolution results to be sent from Salesforce to SAP | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Discrepency_Resolution_update_from_SF.pptx?d=wdea30ce6e1bc4cb1aa3353d5be3c388b&csf=1&web=1&e=micEuQ | 02.No | 01.Yes |  | 2025-02-28 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 36446 | Return For Credit | SalesForce | S/4 | APIGEE | 2025-02-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2026-01-07 | 100% | 2025-12-18 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-08-08 | 2025-07-15 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-20 | 2025-10-24 | 2025-12-11 | 100% | 2025-12-10 | 2025-09-27 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-12-10 | 2026-01-16 |  | 2025-12-19 | 2026-01-07 | 2026-01-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-05 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-24 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2025-02-17 06:31 | cell-link@smartsheet.com | 2026-04-01 01:51 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1261 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-18 | 2026-01-07 | 2025-12-18 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-12-11 | 2025-12-10 | 2025-12-10 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2025-12-10 | 2026-01-16 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  |  |  |  | Return for Credit | 2025-04-18 | 2025-09-26 | 2025-07-15 |  | 2026-01-30 | TM |  |  | 1 |  | 1573 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02: Intel Biz Approval received on 01/30. Reminder mail sent for Intel IT Approval 01/29: FUT sent to Intel again for approval today. Waiting for Business approval. 01/22: Intel biz has provided feedback on the FUT. Team is working on closing the open feedbacks 01/19: One round of review completed with business on 01/16.Tech team is working on Defect # 6376 to address the feedback comments. Tech ETA: 01/20. 01/13: Defect #6196 is raised for Unexpected Scenarios to be picked by Tech team today 01/05: FUT is in progress.Debugging the issue with Tech team for Unexpected Scenarios. 12/22: Revised Payload Testing is in progress for Expected Scenario. FUT started for Expected Sceanrios. Unexpected Scenarios is still giving errors. 12/15: DLT tech team has provided their analysis to Salesforce Team. Defect 5103 is fixed. SF team to provide revised payload to Deloitte. | 2026-01-16 | Y | 99. Logistics |  |  |  | 1211: TUT approved. 5.1 in S21, 5.2 in S22 |  |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | Yes |  | 2026-02-23 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2786 | LOGI1206_IP | 02.Interface | 01.IP - Intel Product | S4 sending 3B2 ASN information to supplier as outbound signal for return delivery. | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE6449C17-C689-47C9-83AB-75BECF7EE340%7D&file=Outbound%203B2%20signal%20send%20to%20supplier%20via%20e2open%20for%20return%20delivery.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-27 | 100% | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-05-23 | 100% | 2025-05-20 | 2025-05-20 | 2025-05-23 | 2025-05-23 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-30 | 2025-06-09 | 2025-06-30 | 2025-06-11 | 100% | 2025-06-17 | 2025-06-17 | 2025-08-26 | 2025-08-26 | 100% | 2025-09-08 | 2025-06-17 | 2025-09-08 |  | 2025-10-08 | 2025-10-23 | 2025-10-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-30 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-30 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2025-01-30 07:28 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1206 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-20 | 2025-08-18 | 2025-05-20 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-30 |  | 2025-05-30 |  | 2025-06-30 | 2025-06-17 | 2025-06-17 |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-06-17 | 2025-09-08 |  |  | 2025-10-30 | 2025-10-31 | 2025-10-30 |  |  |  |  | B2B - E2open | 2025-03-28 | 2025-05-16 | 2025-05-30 |  | 2025-10-31 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 1709 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/24 - Defect 3814 post review comments. 18/22 scenarios are completed 10/17 - IT approval received, Awaiting business approval | 2025-08-26 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-05-24 | 2025-05-24 | Yes | Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2786 | LOGI1206_IF | 02.Interface | 02.IF - Intel Foundry | S4 sending 3B2 ASN information to supplier as outbound signal for return delivery. | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE6449C17-C689-47C9-83AB-75BECF7EE340%7D&file=Outbound%203B2%20signal%20send%20to%20supplier%20via%20e2open%20for%20return%20delivery.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-27 | 100% | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-05-23 | 100% | 2025-05-20 | 2025-05-20 | 2025-05-23 | 2025-05-23 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-30 | 2025-06-09 | 2025-06-30 | 2025-06-06 | 100% | 2025-06-03 | 2025-06-17 | 2025-08-26 | 2025-08-26 | 100% | 2025-09-08 | 2025-06-03 | 2025-09-08 |  | 2025-10-08 | 2025-10-23 | 2025-10-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-30 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-30 | 2025-08-26 | 2025-08-26 | pgaroo@deloitte.com | 2025-01-30 07:28 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-04 | 01.S4 | LOGI1206_IP | 03.Medium | 0.3 | 0.435 | 1206 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-20 | 2025-08-18 | 2025-05-20 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-30 |  | 2025-05-30 |  | 2025-06-30 | 2025-06-03 | 2025-06-03 |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-06-03 | 2025-09-08 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | B2B - E2open | 2025-03-28 | 2025-05-16 | 2025-05-30 |  | 2025-10-31 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 1708 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Defect 3814 post review comments. 18/22 scenarios are completed 10/17 - 1 TC restest is pending out of 22, Supplier is not available in S/4 working with MDG Supplier master team, defect#3814 | 2025-08-26 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2748 | LOGI1136_IP | 02.Interface | 01.IP - Intel Product | Interface between S4 to Boundary Apps (Customs Tracker) for real time data on Delivery details from both IP system | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2748_PTP_S4%20interface%20Delivery%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w65848fdc27a841b2a42d65d3fdbd7b98&csf=1&web=1&e=pyy3GV |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 42860 | Customs Tracker | S/4 | Boundary Apps (Customs Tracker) | APIGEE | 2025-04-21 | 2025-05-30 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-19 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-21 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-11 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-11 | 2025-07-21 | 2025-09-11 |  | 2025-10-24 | 2025-10-30 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 |  |  | 0.5 | 0.725 | 1136 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-30 | 2025-09-11 | 2025-09-11 | 2025-07-21 | 2025-09-11 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 |  |  |  |  | Trade Apps | 2025-05-23 | 2025-06-13 | 2025-05-16 | S4 |  |  |  |  | 1 |  | 1655 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/24 - Defect 3885 10/17- All test case tested, documentationin progress | 2025-09-30 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2748 | LOGI1136_IF | 02.Interface | 02.IF - Intel Foundry | Interface between S4 to Boundary Apps (Customs Tracker) for real time data on Delivery details from both IF system | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2748_PTP_S4%20interface%20Delivery%20details%20to%20Trade%20Boundary%20app_IP_IF.pptx?d=w65848fdc27a841b2a42d65d3fdbd7b98&csf=1&web=1&e=pyy3GV |  |  |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 42860 | Customs Tracker | S/4 | Boundary Apps (Customs Tracker and PEGA-ISMQ | APIGEE | 2025-04-21 | 2025-05-30 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-19 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-21 | 2025-06-02 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-11 | 2025-09-08 | 2025-09-30 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-11 | 2025-07-21 | 2025-09-11 |  | 2025-10-24 | 2025-10-30 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-30 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-01-20 06:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 | LOGI1136_IP | 04.Low | 0.15 | 0.2175 | 1136 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-09-30 | 2025-07-21 | 2025-07-21 |  | 2025-09-30 | 2025-09-11 | 2025-09-11 | 2025-07-21 | 2025-09-11 |  |  | 2025-10-30 | 2025-11-05 | 2025-10-30 |  |  |  |  | Trade Apps | 2025-05-23 | 2025-06-13 | 2025-06-13 | S4 |  |  |  |  | 1 |  | 1656 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/24 - Defect 3886 10/17 - Testing in progress | 2025-09-30 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2382 | LOGI1129 | 02.Interface | 01.IP - Intel Product | TM: RICEFW 1:Carrier selection and Charges calculation for IRG/ISCG( Intel routing Guide & Intel Supplier routing guide)via external IRG tool. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB601AC00-DC29-4E02-904E-D8D88733C781%7D&file=R3%20PTP%20%20LI-030-160%20Manage%20In-bound%20Transportation-%20IRGI%20SCG(Intel%20supplier%20carrier%20guide).pptx&wdLOR=c3EC3141C-614B-4619-9D54-47267C88E6A2&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-23 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 59275 | SAP TM - IRG (Intel Routing Guide) | IRG/IRSG | S/4 | MULESOFT | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-17 | 2025-06-15 | 2025-06-15 | 100% | 2026-01-23 | 2025-08-04 | 2026-01-23 | Yes |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-06-15 | 2025-06-15 | jonsanders@deloitte.com | 2025-01-16 13:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-24 | 01.S4 |  |  | 1 | 1.45 | 1129 |  | R3 ITC1 | [6 empty] | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2025-08-04 | 2026-01-23 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-03-21 | 2025-05-16 | 2025-04-18 | S4 | 2025-06-20 | TM |  |  | 1 |  | 2406 | [7 empty] | 4. Completed |  |  | 2025-06-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 22 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2617 | LOGI1091 | 02.Interface | 02.IF - Intel Foundry | STO based Outbound Delivery Notification Confirmation for Delivery Note Deletion | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/3B14C%20-%20R3_FTS_IP_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=wa07165f2956a43e09197418384b298e5&csf=1&web=1&e=pldyv6 | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-01-27 | 2025-03-11 | 2025-03-11 | 100% | 2025-05-16 | 2025-06-09 | 2025-06-13 | 2025-07-04 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-25 | 2025-07-11 | 100% | 2025-07-11 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-21 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-05 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-27 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1091 |  | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-27 | 2025-09-27 | 2025-09-27 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-07-18 | 2025-07-18 | S4 | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 1500 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2634 | LOGI1084 | 02.Interface | 08.EWM | Interface to SiGac for capturing the consumption of Chems and Gases against a cost center | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2634_R3_FTS%20IF_Chems%20%26%20Gases_Interface%20to%20SiGac%20for%20capturing%20the%20consumption%20of%20Chems%20and%20Gases%20against%20a%20cost%20center.pptx?d=w96a68853f5e34b8fa125baccd0cc6b71&csf=1&web=1&e=a3GMAr | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 12015 | SiGaC (Site Gas and Chemical) | SIGAC | S/4 | APIGEE | 2025-02-10 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-21 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-03-31 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-04-28 | 2025-05-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2026-04-30 | 2026-04-30 | 100% | 2026-02-06 | 2025-08-04 | 2026-02-06 |  | 2025-07-25 | 2026-01-30 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-05-30 | 2026-04-30 | 2026-04-30 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1084 | INT-CR1375 | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2026-04-30 | 2026-02-06 | 2026-02-06 | 2025-08-04 | 2026-02-06 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-06-27 | S4 | 2025-06-20 | TM | WIINGS Only | TRUE | 1 |  | 1952 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 02/02: SIGAC team to confirm on readiness date for FUT testing. RAID 1782. 01/30: SIGAC team to confirm on readiness date for FUT testing. RAID 1782. 01/19: SIGAC team to confirm on readiness date for FUT testing. RAID 1782. 01/14: SIGAC team to confirm on readiness date for FUT testing. RAID 1782. 01/12:Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782, currently its ITC2 Item, will be pulled back to ITC1 upon SIGAC rediness. 01/05:Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782, currently its ITC2 Item, will be pulled back to ITC1 upon SIGAC rediness. 12/15:Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782, its ITC2 Item. 11/24:Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782, its ITC2 Item. 11/18: Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782 11/14: Sigac readiness is further pushed to January, Object will stay on hold. RAID# 1782 11/11: BA committed to be ready by Dec of this year, object will be on hold. RAID# 1782. FUT can be planned S21 10/22: BA committed to be ready by Dec of this year, object will be on hold. RAID# 1782. FUT can be planned S21 10/10: BA committed tobe ready by end of year, object will be on hold. RAID# 1782. 10/06: Call will be setup with Process steward for availability of BA. 09/29: On Hold till Oct. 09/19: On Hold till Oct. 09/12: On Hold till Oct. 09/05: On Hold till Oct. 08/25: On Hold till Oct. 08/18: S/4 FUT has been completed. SIGAC has provided an estimated date of 10/08 for FUT testing. Until then, FUT will remain on hold. RAID item #1782 has been created to track this issue. | 2026-04-30 | Y | 99. Logistics |  |  |  | 02/04: Testing completed using postman and sent for approval. SiGac is also performing tests using postman | 12/02 - ITC2 Object | 3. Watch item | 1 | BA Readiness | Complete | R3 Build & UT Sprint 22 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2581 | LOGI1081_IP | 02.Interface | 01.IP - Intel Product | Interface + Enhancement - Reprinting of Carrier Label | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_LE_Interface%20_Reprinting%20Carrier%20Label.pptx?d=wd072e6a676504f46833836829356713c&csf=1&web=1&e=eSnLAH | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 56974 | Redwood | S/4 | Redwood | APIGEE | 2025-03-03 | 2025-04-25 | 2025-04-25 | 100% | 2025-04-24 | 2025-07-04 | 2025-07-11 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-07-21 | 2025-08-15 | 2025-06-27 | 100% | 2025-06-27 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-09-21 | 2025-08-04 | 2025-09-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-11-30 | 2025-11-30 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-30 | 01.S4 |  |  | 1 | 1.45 | 1081 |  | R3 ITC1 | [6 empty] | 2025-04-24 | 2025-04-25 | 2025-04-24 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-08-15 |  | 2025-06-27 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-11-30 | 2025-09-21 | 2025-09-21 | 2025-08-04 | 2025-09-21 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | [5 empty] | 2025-04-30 | 2025-08-15 | 2025-08-15 | S4 | 2025-09-05 |  |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1561 | [10 empty] | 2025-11-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-08-04 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2581 | LOGI1081_IF | 02.Interface | 02.IF - Intel Foundry | Interface + Enhancement - Reprinting of Carrier Label | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_LE_Interface%20_Reprinting%20Carrier%20Label.pptx?d=wd072e6a676504f46833836829356713c&csf=1&web=1&e=eSnLAH | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 56974 | Redwood | S/4 | Redwood | APIGEE | 2025-03-03 | 2025-04-30 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-06-30 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-09-21 | 2025-08-04 | 2025-09-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-11-30 | 2025-11-30 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-30 | 01.S4 | LOGI1081_IP | 03.Medium | 0.3 | 0.435 | 1081 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-06-27 |  | 2025-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-30 | 2025-09-21 | 2025-09-21 | 2025-08-04 | 2025-09-21 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | [5 empty] | 2025-04-30 | 2025-08-15 | 2025-08-29 | S4 | 2025-09-19 |  |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1560 | [10 empty] | 2025-11-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2529 | LOGI1079_IP | 02.Interface | 01.IP - Intel Product | Interface from S4 ISM to Service Now | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2529_R3_FTS_IP_LOGISTICS_INTERFACE_S4%20ISM%20to%20Service%20Now.pptx?d=wb95c5d1544534947a0af7bed8549098e&csf=1&web=1&e=eVgia0 | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 23476 | ServiceNow Cloud | S/4 ISM | Service Now | NA | 2025-02-24 | 2025-05-30 | 2025-05-30 | 100% | 2025-08-04 | 2025-07-18 | 2025-07-25 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-29 | 2025-08-29 | 2025-05-30 | 100% | 2025-05-23 | 2025-08-29 | 2025-08-29 | 2025-05-30 | 100% | 2025-05-23 | 2025-08-11 | 2025-08-26 |  |  | 2025-08-26 | 2025-08-28 | 2025-09-26 |  |  | 2025-09-26 | 2025-08-29 | 2025-10-26 | 2025-10-26 | 100% | 2025-10-26 | 2025-09-26 | 2025-10-26 |  |  | 2025-10-08 | 2025-10-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-17 | 2025-10-17 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-26 | 2025-10-26 | 2025-10-26 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.45 | 1079 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-05-23 | 2025-08-29 | 2025-05-23 | 2025-05-23 |  | 2025-08-26 |  |  |  | 2025-09-26 |  |  |  | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-05-23 | 2025-10-26 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-16 | [5 empty] | 2025-05-30 | 2025-08-29 | 2025-09-26 | MW | 2025-10-03 |  |  |  | 1 |  | 2812 | [7 empty] | 4. Completed |  |  | 2025-10-26 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-08-29 | 2025-05-23 | No |  | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2529 | LOGI1079_IF | 02.Interface | 02.IF - Intel Foundry | Interface from S4 ISM to Service Now | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2529_R3_FTS_IP_LOGISTICS_INTERFACE_S4%20ISM%20to%20Service%20Now.pptx?d=wb95c5d1544534947a0af7bed8549098e&csf=1&web=1&e=eVgia0 | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 23476 | ServiceNow Cloud | S/4 ISM | Service Now | NA | 2025-02-03 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-20 | 2025-07-18 | 2025-07-25 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-22 | 2025-08-29 | 2025-05-30 | 100% | 2025-05-23 | 2025-08-22 | 2025-08-29 | 2025-05-30 | 100% | 2025-05-23 | [10 empty] | 2025-09-05 | 2025-10-26 | 2025-10-26 | 100% | 2025-10-26 | 2025-05-23 | 2025-10-26 |  |  | 2025-10-08 | 2025-10-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-17 | 2025-10-17 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-29 | 2025-10-26 | 2025-10-26 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-02 | 01.S4 | LOGI1079_IP | 03.Medium | 0.3 | 0.435 | 1079 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-05-23 | 2025-08-29 | 2025-05-23 | 2025-05-23 | [9 empty] | 2025-10-26 | 2025-10-26 | 2025-10-26 | 2025-05-23 | 2025-10-26 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-16 | [5 empty] | 2025-05-30 | 2025-08-29 | 2025-09-26 | S4 | 2025-10-10 |  |  |  | 1 |  | 2811 | [10 empty] | 2025-10-26 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-08-29 | 2025-05-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2463 | LOGI1074_IP | 02.Interface | 01.IP - Intel Product | Send data via API to retrieve the tracking ID - interface + Enhancement | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_LE_Interface_VTRC_Activities_Intake%20Form.pptx?d=w957f056c5cf5473c8de54630450d5a28&csf=1&web=1&e=LVoS9m | 02.No | 01.Yes |  | 2024-12-20 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 56974 | Redwood | S/4 | Redwood | APIGEE | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-07-04 | 2025-07-11 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-05-15 | 100% | 2025-05-15 | 2025-07-21 | 2025-08-15 | 2025-05-15 | 100% | 2025-05-15 | 2025-07-21 | 2025-08-15 | 2025-06-27 | 100% | 2025-06-27 | 2025-07-14 | 2025-08-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-09-21 | 2025-07-21 | 2025-09-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-11-30 | 2025-11-30 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-30 | 01.S4 |  |  | 1 | 1.45 | 1074 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-15 | 2025-08-15 | 2025-05-15 | 2025-05-15 |  | 2025-08-15 |  | 2025-06-27 |  | 2025-08-08 | 2025-07-21 | 2025-07-21 |  | 2025-11-30 | 2025-09-21 | 2025-09-21 | 2025-07-21 | 2025-09-21 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-04-30 | 2025-08-15 | 2025-08-15 | MW | 2025-09-19 |  |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 2427 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 10/16 EP: Update FUT Revised End date to 10/24 10/10: Payload 2 non mandatory elements requested and 2 field logic to be updated raised a defect for that tech is looking into the defect. ETA for fixing the defect 10/10/2025 10/09 EP: What is the expected FUT end date / Reason for delay | 2025-11-30 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-05-15 | Yes | Param table entry addition. | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2463 | LOGI1074_IF | 02.Interface | 02.IF - Intel Foundry | Send data via API to retrieve the tracking ID - interface + Enhancement | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_LE_Interface_VTRC_Activities_Intake%20Form.pptx?d=w957f056c5cf5473c8de54630450d5a28&csf=1&web=1&e=LVoS9m | 02.No | 01.Yes |  | 2024-12-20 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 56974 | Redwood | S/4 | Redwood | APIGEE | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-07-04 | 2025-07-11 | 2025-06-27 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-05-15 | 100% | 2025-05-15 | 2025-07-21 | 2025-08-15 | 2025-05-15 | 100% | 2025-05-15 | 2025-07-21 | 2025-08-15 | 2025-06-27 | 100% | 2025-06-27 | 2025-07-14 | 2025-08-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-09-21 | 2025-07-21 | 2025-09-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-11-30 | 2025-11-30 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-30 | 01.S4 | LOGI1074_IP | 03.Medium | 0.3 | 0.435 | 1074 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-15 | 2025-08-15 | 2025-05-15 | 2025-05-15 |  | 2025-08-15 |  | 2025-06-27 |  | 2025-08-08 | 2025-07-21 | 2025-07-21 |  | 2025-11-30 | 2025-09-21 | 2025-09-21 | 2025-07-21 | 2025-09-21 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-04-30 | 2025-08-15 | 2025-08-15 | MW | 2025-09-19 |  |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 2426 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 10/16 EP: Update FUT Revised End date to 10/24 10/10: Payload 2 non mandatory elements requested and 2 field logic to be updated raised a defect for that tech is looking into the defect. ETA for fixing the defect 10/10/2025 10/09 EP: What is the expected FUT end date / Reason for delay | 2025-11-30 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-05-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2576 | LOGI1067 | 02.Interface | 01.IP - Intel Product | 2DN - S4 – Interface from S/4 to MPL for packing list. | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Interface%20to%20send%20Data%20of%201st%20Delivery%20to%20MPL%20in%202DN%20X-Dock%20Model.pptx?d=w7b6c671f1408490eb3783c8250b947c5&csf=1&web=1&e=FC84Py | 02.No | 01.Yes |  | 2025-01-02 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 57576 | Mark Pack Label Suite (IP) | S/4 | MPL | SFT | 2025-03-03 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-02 | 2025-05-09 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-11-05 | 100% | 2026-01-07 | 2025-06-27 | 2025-07-10 | 2025-07-10 | 100% | 2025-07-10 | 2026-01-07 | 2026-01-07 |  | 2025-11-21 | 2025-12-03 | 2026-01-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-30 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-09-15 | 2025-09-15 | 2025-09-15 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.45 | 1067 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2026-01-07 | 2026-01-07 |  |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | [5 empty] | 2025-03-21 | 2025-06-13 | 2025-06-27 | MW | 2025-07-18 |  |  |  | 1 | 04.5 Logistics - 2DN | 2324 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 01/29: Approved by Intel business & IT, pending with MPL team, ETA 01/30 01/22: OM team facing issues with IC SO creation, defect with tech team, ETA not provided 01/19: Additional scenario for ZKB order pending for testing, Test data creation in progress by OM team, Customer sales order & IC SO is not getting created for ZKB. 01/12: Defect#6156 is fixed & retest is in progress, facing data creation issues with SO, checking with OM team 01/05: FUT review call completed on 12/22, Additional queries raised by Intel for which follow up call planned on 01/08 12/22:FUT review call scheduled on 12/22. 12/15: S/4 FUT is completed, E2E FUT is in progress. Defect#5565 is fixed, retest is blocked due to posting period, checking with FPR team 12/08: Blocked by cost element issue, checking with FPR team. FUT is planned in S21. 12/01: Open defects 5083, no ETA 11/24: Defect#4592 is with tech, no ETA 11/18: Defect#4592 is with tech, awaiting RFC creation for defect fix | 2025-09-15 | N | 99. Logistics |  |  |  | 0127: FUT impacted due to system outage |  | 3. Watch item | Outage | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2566 | LOGI1066 | 02.Interface | 01.IP - Intel Product | 2DN - Interface to capture Data for 1st Delivery in 2DN X-Dock Model | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Interface%20to%20capture%20Data%20for%201st%20Delivery%20in%202DN%20X-Dock%20Model.pptx?d=w3033acae8de04e99884e25d04e1cfdfa&csf=1&web=1&e=sqPZaD | 02.No | 01.Yes |  | 2025-01-02 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-02-10 | 2025-02-21 | 2025-02-28 | 100% | 2025-03-05 | 2025-05-02 | 2025-05-09 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-23 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-08-04 | 2025-08-04 |  | 2025-10-08 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-07-16 | 2025-07-16 | jonsanders@deloitte.com | 2024-12-20 08:42 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 1.45 | 1066 |  | R3 ITC1 | [6 empty] | 2025-03-05 | 2025-03-05 | 2025-03-05 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-06-13 |  |  |  | 2025-06-13 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-08-04 | 2025-08-04 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 |  |  |  |  | B2B - OpenText | 2025-03-14 | 2025-06-13 | 2025-06-13 | MW | 2025-06-23 |  |  |  | 1 | 04.5 Logistics - 2DN | 2622 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24- Awaiting intel IT approval (Sent for approval on 11/21), Business approval received. 11/13 EP: Provide revised FUT end date 11/11: GTS issues are fixed, TM configs are still pending, however payload triggered for LAFI case which was received at OT, but failed due to AS2 header , defect#4426 created 10/31: 4127 defect for port creation, ETA 10/31. E2E FUT to be progressed in the coming week 10/24 - FUT in progress | 2025-07-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | No | ZTOTC_DH table impact | No | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2616 | LOGI1062 | 02.Interface | 02.IF - Intel Foundry | STO based outbound delivery notification request for delivery note cancellation | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2616%20(3B14R)%20-%20R3_FTS_IF_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=wb9cf63b0d3834058b44b36d0e9b03538&csf=1&web=1&e=gQOeot | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-27 | 2025-03-11 | 2025-03-11 | 100% | 2025-05-16 | 2025-06-09 | 2025-06-13 | 2025-07-04 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-25 | 2025-07-11 | 100% | 2025-07-11 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-21 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1062 |  | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-16 | 2025-07-16 | 2025-07-16 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-25 | 2025-09-26 | 2025-09-25 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-07-18 | 2025-07-18 | S4 | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 1499 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2603 | LOGI1053 | 02.Interface | 02.IF - Intel Foundry | STO based Outbound Delivery Notification from 3PL to S/4 for confirming Pick/Pack - 3B13 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2603%20-%20R3_FTS_IP_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=w07c9fbb25453430bb23398d8b548a5a2&csf=1&web=1&e=2OgREs | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-02-17 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-03-07 | 2025-03-14 | 2025-05-30 | 100% | 2025-05-20 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-30 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-30 | 2025-02-24 | 2025-03-21 | 2025-06-06 | 100% | 2025-06-06 | 2025-03-24 | 2025-04-18 | 2025-06-11 | 100% | 2025-06-11 | 2025-04-21 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-06-11 | 2025-06-11 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-05-09 | 2025-05-09 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1053 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-05-30 | 2025-05-30 |  |  |  | 2025-06-06 |  | 2025-06-06 |  | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-06-11 | 2025-06-11 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-04-18 | 2025-03-21 | MW | 2025-05-30 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 2364 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change | 9/12: B2B approval received and expecting approval from IT/PS. EP: 09/11: ETC 09/10, Ext FUT Req, no impact to Rinchem ext FUT end date is 11/15 9/5: OT is not available for ETE testing EP: 09/03: Update on expected FUT completion 8/29: Functionality is not working checking with the tech team. Packing issue. 8/25: Defect 1990 was reassigned to mule team. 8/18: Tech team is checking the defect ETA 8/19 8/14: Defect 1990 is with tech team | 2025-05-09 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2599 | LOGI1043 | 02.Interface | 02.IF - Intel Foundry | Inventory Movement from 3PL to S/4 - 4C1 Cycle Count | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B200D873C-0A93-4574-A07F-B671F7522A1A%7D&file=2599%20-%20R3_FTS_IP_LOGISTICS_L-060_050_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true&previoussessionid=8b068b64-b3a3-895d-8cda-b59bb6f5acaf | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-18 | 2025-04-25 | 2025-07-18 | 100% | 2025-07-21 | 2025-05-19 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-05 | 2025-07-04 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-05 | 2025-04-21 | 2025-05-16 | 2025-07-18 | 100% | 2025-07-18 | 2025-05-19 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1043 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-07-21 | 2025-07-21 |  |  | 2025-10-16 | 2025-10-16 | 2025-10-16 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-06-13 | 2025-05-16 | MW | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 1762 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: Awaiting IT approval 10/09 EP: Has this been approved? 10/3: Awaiting approvals 9/29: Sent for Intel review on 9/26 Friday EOD | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-06-13 | 2025-06-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2604 | LOGI1041 | 02.Interface | 02.IF - Intel Foundry | STO based Outbound Delivery PGI confirmation from 3PL to S/4 - 3B2 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2604%20-%20R3_FTS_IP_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=w4c23fabf41e441c3b7bf70adca3a4319&csf=1&web=1&e=IsChWF | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-27 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-16 | 2025-03-17 | 2025-03-21 | 2025-07-18 | 100% | 2025-07-21 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-06-12 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-06-12 | 2025-04-11 | 2025-04-25 | 2025-07-18 | 100% | 2025-07-18 | 2025-05-19 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-21 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-19 13:32 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1041 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-07-21 | 2025-07-21 |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-06-13 | 2025-06-13 | MW | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 2365 | [9 empty] | 9/29: IT approval received. Addressing open comments from OeS4 team. | 2025-06-13 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-06-12 | 2025-06-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2605 | LOGI1040 | 02.Interface | 02.IF - Intel Foundry | STO based Outbound Delivery PGI confirmation for returns from S/4 to 3PL - 3B2 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2605%20-%20R3_FTS_IP_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=w71dd5adff5de4d8eb88b320ec6a8c3eb&csf=1&web=1&e=zYIBcn | 02.No | 01.Yes |  | 2024-12-18 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-03-03 | 2025-04-04 | 2025-04-04 | 100% | 2025-05-16 | 2025-03-17 | 2025-03-21 | 2025-08-13 | 100% | 2025-08-11 | 2025-04-07 | 2025-04-18 | 2025-09-05 | 100% | 2025-09-05 | 2025-04-07 | 2025-04-18 | 2025-09-05 | 100% | 2025-09-05 | 2025-04-11 | 2025-04-25 | 2025-08-13 | 100% | 2025-08-13 | 2025-05-19 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-07-10 | 2025-08-31 | 2025-08-31 | 100% | 2025-08-31 | 2025-09-05 | 2025-09-05 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-16 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-08-31 | 2025-08-31 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-04-06 09:17 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1.45 | 1040 |  | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-16 | 2025-05-16 |  | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-09-05 | 2025-09-05 |  |  |  | 2025-08-13 |  | 2025-08-13 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-08-31 | 2025-08-31 | 2025-08-31 | 2025-09-05 | 2025-09-05 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 |  |  |  |  | B2B - OpenText | 2025-03-07 | 2025-06-13 | 2025-06-13 | S4 | 2025-08-22 |  |  |  | 1 | 02. IF Customers | 2367 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/16: Proof of delivery not relevant. Following wioth Kate for approval. 01/05: Defect marked resolved and retest in progress. Mule changes are in progress. 12/22:AMQ issue RITM13618960- Ticket has been raised by mule to fix this 12/15: Based on the feedback from business during Bus./IT review payload is updated and shared with business awaiting approval. 12/8: Tech has fixed today the defect 5325 testing in progress. Plan to send the FUT for intel review by 12/10 12/1: FUT to be started from 12/2. Conversion object given priority. 11/24: defect resolved ETA to complete FUT 11/27. 11/18: Defect is fixed testing in progress 11/14: Defect 4540 in progress with tech | 2025-08-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | Yes | Mapping of IP plant to IF | Yes | Param table need to update. | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-04-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2602 | LOGI1038 | 02.Interface | 02.IF - Intel Foundry | STO based Outbound Delivery Notification from S/4 to 3PL - 3B12 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N | 2024-12-19 | 02. Pending (Need clarifications) | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2602%20-%20R3_FTS_IP_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx?d=w66f3f739a0ca4427b89d7e0c100b075c&csf=1&web=1&e=DT4OA1 | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-02-03 | 2025-03-14 | 2025-03-14 | 100% | 2025-03-14 | 2025-03-17 | 2025-03-21 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-25 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-06 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-19 13:32 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1038 |  | R3 ITC1 | [6 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-06-13 | 2025-06-13 | S4 | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 2362 | [7 empty] | 2. At Risk | 14. B-App Under Test | 8/18: All the opens have been addressed Intel team is checking on this following for approval. 08/14: All the opens have been addressed following with business for approval 08/11: Sent for approval on 8/7 Under review with OES4 and Wiings team. 08/04- Testing completed for all scenarios. Documentation process in progress. ETA 08/05 Connectivity issues found during testing. Currently tech team is working on resolving inter system connectivity issues. | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2600 | LOGI1037 | 02.Interface | 02.IF - Intel Foundry | Inventory Movement from S/4 to 3PL – 4C1 (Outbound) | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB4AF1C3C-BA45-4071-A2B6-84C79707BD09%7D&file=2600%20-%20R3_FTS_IF_LOGISTICS_L-060_030_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-11 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-02-10 | 2025-05-02 | 2025-05-02 | 100% | 2025-04-28 | 2025-05-02 | 2025-05-09 | 2025-07-04 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-21 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-11 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1037 |  | R3 ITC1 | [6 empty] | 2025-04-28 | 2025-05-02 | 2025-04-28 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-07-21 | 2025-07-21 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-06-13 | 2025-05-16 | S4 | 2025-08-22 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 1763 | [9 empty] | 9/5: Walkthrough call scheduled with Steve and Wade to approve. Under Review. EP: 09/03: Update on expected FUT completion 8/29: UOM issue as per B2B. In progress 8/25: Sent for Intel Review on Friday 8/25 8/18: Defect 2253 has been raised with Tech team. 8/14: Under Intel review. Sent for approval on 8/13. | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2502 | LOGI0956 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive OSAT Finished Goods and Return rework FG “Goods Receipt” (4B2) signal sent by 3PL warehouses via Open Text and post in S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B73AF98C0-BCA8-491C-8B4A-F3E068A41C7E%7D&file=2502_PTP_LE%20-Inbound%20interface%20to%20receive%20OSAT%20%20Finished%20Goods%2C%20Return%20Rework%20FG-%20%25u201cGoods%20Receipt%25u201d%20(4B2)%20signal%20sent%20by%203PL%20warehouses%20via%20Open%20Text%20%20in%20S4%25u00a0%20IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-02 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-27 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-09 | 100% | 2025-08-04 | 2025-05-20 | 2025-07-14 | 2025-07-14 | 100% | 2025-07-14 | 2025-08-04 | 2025-08-04 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-09 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-06-13 | 2025-07-14 | 2025-07-14 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 1 | 1.45 | 0956 |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-02-28 | 2025-02-27 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-08-04 | 2025-08-04 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 |  |  |  |  | B2B - OpenText | 2025-01-31 | 2025-04-18 | 2025-04-18 | MW | 2025-06-20 |  |  |  | 1 | 04.6 Logistics - GLO | 2499 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/23 - FUT sent for Approval, Awaiting further feedback/Approval from Intel IT and Business/PS 02/20- Sent for approval 02/18, (Malaysis team is on leave) 02/16 - Defect#7260, BOL is not updating in GR, ETA 02/16, 17 TC completed out of 18, Testing in progress with OpentText, ETA- 02/17 02/12 - 16 TC completed out of 20, Testing in progress with OpentText, ETA- 02/17 01/05 - CR Changes completed, TUT is in progress. FUT to be started post TUT competion from tech. 12/22 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 12/24 12/15 - Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech | 2025-07-14 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11: E2E FUT in progress. 14/20 test cases are completed. |  | 5. Review Closed | E2O | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | Yes | Change in Custom Table entries for Plant Table - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-05 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2501 | LOGI0955 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Box CPU Finished Goods and Return Rework FG “Goods Receipt” (4B2) signal sent by 3PL warehouses via Open Text and post in S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6AB7CD40-BF2E-4C8A-A458-03E85AF66B1B%7D&file=2501_PTP_LE%20-Inbound%20interface%20to%20receive%20Box%20CPU%20Finished%20Goods%2C%20Return%20Rework%20FG-%20%25u201cGoods%20Receipt%25u201d%20(4B2)%20signal%20sent%20by%203PL%20warehouses%20via%20Open%20Text%20%20in%20S4%25u00a0%20IP%20.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-02 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2024-12-02 | 2025-02-14 | 2025-01-24 | 100% | 2025-02-10 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-24 | 2025-04-04 | 2025-04-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-04-07 | 2025-04-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-17 | 2025-05-17 | 100% | 2025-05-17 | 2025-08-04 | 2025-08-04 |  | 2025-11-14 | 2025-11-26 | 2026-01-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-30 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1.45 | 0955 |  | R3 ITC1 | [6 empty] | 2025-02-10 | 2025-02-14 | 2025-02-10 |  | 2025-03-24 | 2025-03-24 | 2025-03-24 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-08-04 | 2025-08-04 |  |  | 2026-01-30 | 2026-01-30 | 2026-01-30 |  |  |  |  | B2B - OpenText | 2025-01-10 | 2025-04-18 | 2025-04-18 | MW | 2025-05-16 |  |  |  | 1 | 04.6 Logistics - GLO | 2509 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/19 - Defect# 6365 is open, 4-5 TCs need to be retested post defect resolution. Rest all review comments are addressed. 01/05- 24 TCs are completed out of 25 for E2E FUT. Defect#5964 Supplier field is optional but marked as mandatory, 12/22 - 8 TCs are completed out of 25 for E2E FUT. Defect# 5819 is still open, blocking 2 TCs. FUT is in-progress for rest of the TCs 12/15 - E2E FUT is started, 1 TC is completed out of 25. Defect# 5600 & 5601 are raised, blocking 4 TCs and rest of the TCs are in progress. 12/08 - 9 TCs are completed out of 25 for S/4 FUT. Defect# 5337 is newly raised. E2E FUT is blocked, as Authoriztion issue while processing payload in AIF from Mulesoft. Support Ticket is raised to Intel, ETA for the same in 12/08. FUT ETA 12/12. 12/01 - 8 TCs completed out of 25 for S/4 FUT. Defect# 5082 is raised, blocking rest all the TCs. E2E FUT will start with BApp- OpenText once the respective defect is resolved 12/01 - S/4 FUT is completed. E2E FUT with Web Suite is blocked, due to multiple issues observed from BApp side, BApp team is working to fix the same. Awaiting ETA on the same. 11/24: Defects 4845 with dev, hard blocker to proceed on FU. 2/25 TC completed so far. 11/18 - Defects# 4480 & 4583 are still open, Blocking rest of the TCs. ETA from Tech is 11/20. 11/14 - Defects# 4478 is resolved, Defects 4479 & 4480 are still open, New Defect# 4583 is raised. Blocking rest of the TCs. Still awaiting ETA from Tech on Defects | 2025-06-13 | N | 99. Logistics |  |  |  | 0127: FUT impacted due to system outage |  | 3. Watch item | Outage | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2445 | LOGI0954 | 02.Interface | 02.IF - Intel Foundry | Bailment Process: Inbound 4B2 from 3PL to IF via OpenText for Receipt of Bailed Material | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20LE/2445_Bailment%20Process%20Inbound%204B2%20from%203PL%20to%20IF%20via%20OpenText%20for%20Receipt%20of%20Bailed%20Material%20Copy.pptx?d=w2fc09dde568f41a2b67ab95801871fde&csf=1&web=1&e=DjJgp1 | 02.No | 01.Yes |  | 2024-12-03 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-20 | 2025-02-21 | 2025-02-12 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-07-18 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-18 | 2025-05-15 | 100% | 2025-05-15 | 2025-04-07 | 2025-04-18 | 2025-05-15 | 100% | 2025-05-15 | 2025-03-24 | 2025-04-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-03 | 2025-05-19 | 2025-06-18 | 2025-06-18 | 100% | 2025-06-18 | 2025-06-03 | 2025-06-18 |  | 2026-02-27 | 2026-02-27 | 2026-03-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-03-13 | N | 100% | 2026-03-11 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-06-13 | 2025-06-18 | 2025-06-18 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1.45 | 0954 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-15 | 2025-05-15 |  |  |  | 2025-07-18 |  | 2025-07-18 |  | 2025-06-13 | 2025-06-03 | 2025-06-03 |  | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-03 | 2025-06-18 | 2026-03-09 |  | 2026-03-11 | 2026-03-13 | 2026-03-11 |  |  |  |  | B2B - OpenText | 2025-02-14 | 2025-04-18 | 2025-04-18 | MW | 2025-05-30 |  |  |  | 1 |  | 2523 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 02/23 - FUT sent for Approval, Awaiting further feedback/Approval from Intel IT and Business/PS 02/20- Sent for approval today 02/20 02/16- 29 TCs completed out of 34, facing GTS blocked, ETA- 02/18. 02/12 - 27 TCs completed out of 34, defect#7067 Fixed, testing in progress, ETA- 02/18 01/05 - 11 TCs are completed out of 34 for S/4 FUT. Defect# 5720, 5957 is still in progress, blocking 10 TCs. ETA from Tech is 01/06. FUT is in-progress rest of the TCs 12/22 - 8 TCs are completed out of 34 for S/4 FUT. Defect# 5720 is still in progress, blocking 2 TCs. ETA from Tech is 12/22. FUT is in-progress rest of the TCs 12/15 - 7 TCs are completed out of 34 for S/4 FUT. Defect# 5553 is raised, Blocking E2E FUT. S4 FUT is in-progress. Bapp-Open Text | 2025-06-18 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11: E2E FUT in progress. 27/34 test cases are completed. Defect fixes in progress by Tech team |  | 5. Review Closed | E2O | Awaiting approval | Complete | R3 Build & UT Sprint 15 |  | 2025-05-15 | 2025-05-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2443 | LOGI0953 | 02.Interface | 02.IF - Intel Foundry | Bailment Process: Generated Outbound 4B2 from IF to OpenText for Bailed Material | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20LE/2443-Bailment%20Process%20Generated%20Outbound%204B2%20from%20IF%20to%20OpenText%20for%20Bailed%20Material.pptx?d=w1c1ac5888656436c99ae3fb1ce4096c1&csf=1&web=1&e=VVWqJL | 02.No | 01.Yes |  | 2024-12-03 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-12-09 | 2025-02-21 | 2025-02-04 | 100% | 2025-02-17 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-04-11 | 2025-04-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-30 | 2025-07-10 | 2025-07-10 | 100% | 2025-07-10 | 2025-08-04 | 2025-08-04 |  | 2025-10-24 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-07-10 | 2025-07-10 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1.45 | 0953 |  | R3 ITC1 | [6 empty] | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-10 | 2025-07-10 | 2025-07-10 | 2025-08-04 | 2025-08-04 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 |  |  |  |  | B2B - OpenText | 2025-01-17 | 2025-04-18 | 2025-04-18 | S4 | 2025-05-30 |  |  |  | 1 |  | 2522 | [7 empty] | 4. Completed | 1. Approved no action | 12/08 - Aligned with Syed. Since there is no physical logistics movement in IF and this is purely interface to trigger virtual posting in IP, then there will not be any business approvals required. Marking this as completed as IT has already approved 12/01: IT Approved on 12/01, Business Pending. No action on Deloitte 11/24:Sent for approval on 11/21. Team is working on the feedback received on 11/24. 11/14- All defect resolved, FUT is in-progress with OpenText. 6 TC out of 17 completed 11/11 - E2E FUT has started with OpenText, Defect# 2249 is raised with Mulesoft team blocking FUT TCs, ETA 11/11 10/31: Defect 4112 is created and under fix 10/24 - 5/13 scenarios are tested so far 10/17 - Will be started from 10/22 | 2025-07-10 | N | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  |  | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Change in Condition Records and Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-12 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2390 | LOGI0951 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Finished Goods “Goods Receipt” (4B2) signal from 3PL for interplant shipments to post the Goods Receipt in S/4. | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2390_FTS-LE-RICEFW%20intake%20form%20of%204B2%20GR%20signal%20from%203PLs%20to%20S4.pptx?d=wce5a14763f10479ab09775dee517229b&csf=1&web=1&e=khzqrw | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-20 | 2025-02-28 | 2025-02-28 | 100% | 2025-04-11 | 2025-03-07 | 2025-03-14 | 2025-05-30 | 100% | 2025-05-20 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-06-06 | 100% | 2025-06-06 | 2025-03-24 | 2025-04-18 | 2025-06-06 | 100% | 2025-06-03 | 2025-05-02 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-28 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-05-09 | 2025-05-09 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 1 | 1.45 | 0951 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-06 |  | 2025-06-06 |  | 2025-06-06 | 2025-06-03 | 2025-06-03 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-28 | 2025-08-28 | 2025-08-28 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-23 |  |  |  | 1 |  | 1915 | [9 empty] | 8/25: Sent for Intel Review. 8/18: Data sent by OT is stuck in AIF, same we are validating with Tech team 8/14: Data sent by OT is incorrect and we have requested for correct set of data again. | 2025-05-09 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2389 | LOGI0950 | 02.Interface | 01.IP - Intel Product | Interface to receive 4B2 signal from Factory and return shipments from ODM/OSAT/Boxing in S4 | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2389_FTS-LE-RICEFW%20intake%20form%20of%204B2%20GR%20signal%20from%20Factory%20to%20S4.pptx?d=w63e3d3a415e340b5b10a0a37b127b963&csf=1&web=1&e=qIycQr | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | OpenText | S/4 | MULESOFT | 2025-01-20 | 2025-02-28 | 2025-02-28 | 100% | 2025-04-11 | 2025-03-07 | 2025-03-14 | 2025-07-18 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-07-18 | 100% | 2025-07-18 | 2025-03-24 | 2025-04-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-26 | 2025-06-25 | 2025-06-25 | 100% | 2025-06-25 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-06-25 | 2025-06-25 | pgaroo@deloitte.com | 2024-11-20 03:14 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 1 | 1.45 | 0950 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-09 | 2025-09-09 | 2025-09-09 |  |  |  |  | B2B - OpenText | 2025-02-28 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-23 |  |  |  | 1 | 04.6 Logistics - GLO | 1914 | [9 empty] | 9/5: Batch split is failing in AIF when new sceanrio got identified. EP: 09/03: Update on expected FUT completion 8/29: Retest in progress. GTS block was there and there are multiple scenarios. 8/25: Impact issue from LOGE0936. Defect 2449 raised. 8/18: Data sent by OT is stuck in AIF, same we are validating with Tech team 8/14: Data sent by OT is incorrect and we have requested for correct set of data again. | 2025-06-25 | N | 99. Logistics | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes |  | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-20 | 2026-03-13 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1753 | LOGI0933 | 02.Interface | 01.IP - Intel Product | W-lot inventory error handling | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060_130_Enhancement%20-%2010_%20RICEFW%20Intake%20form.pptx?d=wd0b3d3fbf604402aafeecfa8f532d2c8&csf=1&web=1&e=bhASdo | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-13 | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-27 | 2025-06-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-04 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-06-20 | 2025-07-15 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-17 | 2025-09-30 | 2025-09-30 | 100% | 2025-10-07 | [5 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-30 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2024-12-19 | 01.S4 |  |  | 1 | 1.45 | 0933 |  | R3 ITC1 | [6 empty] | 2025-03-27 | 2025-03-28 | 2025-03-27 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  |  |  |  | 2025-10-07 | 2025-10-07 |  |  | 2025-10-01 | 2025-10-08 | 2025-10-01 | [5 empty] | 2025-03-28 | 2025-07-18 | 2025-07-15 |  | 2025-10-08 |  |  |  | 1 |  | 1993 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-30 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | Yes |  | Yes |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2372 | LOGI0875 | 02.Interface | 01.IP - Intel Product | Interface from WOM to S4 HANA to fetch the list of Deliveries for a particular customer | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_Interface%20from%20WOM%20to%20S4%20to%20fetch%20list%20of%20Deliveries%20.pptx?d=wdf381205b317427195cf1e16b7365ee5&csf=1&web=1&e=lhl5BF | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | WOM | S/4 | MULESOFT | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-21 | 2025-08-15 | 2025-07-18 | 100% | 2025-07-18 | 2025-08-18 | 2025-09-12 | 2025-06-11 | 100% | 2025-06-03 | 2025-08-25 | 2025-10-10 | 2025-10-10 | 100% | 2025-09-15 | 2025-06-03 | 2025-09-15 |  | 2025-10-09 | 2025-09-26 | 2025-10-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-03 | 2025-10-03 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 1 | 1.45 | 0875 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 |  | 2025-08-15 |  | 2025-07-18 |  | 2025-09-12 | 2025-06-03 | 2025-06-03 |  | 2025-10-10 | 2025-09-15 | 2025-09-15 | 2025-06-03 | 2025-09-15 |  |  | 2025-10-06 | 2025-10-06 | 2025-10-06 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | MW | 2025-09-19 |  |  |  | 1 |  | 1856 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2373 | LOGI0874 | 02.Interface | 01.IP - Intel Product | Interface from WOM to S4 HANA to fetch the ASN information of delivery. | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_Interface%20from%20WOM%20to%20S4%20to%20fetch%20the%20ASN%20information%20of%20delivery.pptx?d=wb265d8d3bcd64c8ca6ae5c806d87c102&csf=1&web=1&e=CY2ewg | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | WOM | S/4 | MULESOFT | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-04 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-21 | 2025-08-15 | 2025-07-16 | 100% | 2025-07-16 | 2025-08-18 | 2025-09-12 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-25 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-01 | 2025-07-29 | 2025-10-01 |  | 2025-10-24 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0874 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-08-15 | 2025-07-24 | 2025-07-24 |  | 2025-08-15 |  | 2025-07-16 |  | 2025-09-12 | 2025-07-29 | 2025-07-29 |  | 2025-10-10 | 2025-10-01 | 2025-10-01 | 2025-07-29 | 2025-10-01 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | MW | 2025-09-19 |  |  |  | 1 |  | 1857 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/31: FUT in progress, E2E FUT session with Intel team planned on 11/04 10/24 - Defect 3849 | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-15 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2021 | LOGI0871 | 02.Interface | 08.EWM | Interface for Label printing, So in this interface when user will click on print button from /SCWM/PACK transaction in EWM, an response will be received from Spectrum and then user will select which label to be printed. Loftware should share an image of label to SAP which would be previewed before printing. | 04. OTC IF | 4.8 OTC IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA44BC4AE-90DE-404A-BC6F-C7A8DCEC55AD%7D&file=R3_2021_IF_OTC_EWM_Label_Printing_interface_with_Spectrum.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 38292 | Loftware Spectrum (IF) | SPECTRUM | S/4 | NA | 2025-01-13 | 2025-02-21 | 2025-02-07 | 100% | 2025-02-04 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-04-25 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-25 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | [10 empty] | 2025-06-16 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-04 | 2025-08-04 | 2025-08-04 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-26 | 2025-06-11 | 2025-06-11 | N | 100% | 2025-08-05 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-07-04 | 2025-07-04 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0871 |  | R3 ITC1 | [6 empty] | 2025-02-04 | 2025-02-21 | 2025-02-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [9 empty] | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | S4 | 2025-12-19 | TM |  |  | 1 | 08. Not Applicable | 2024 | [10 empty] | 2025-07-04 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2387 | LOGI0852_IP | 02.Interface | 01.IP - Intel Product | Outbound Interface to send freight forwarder rates from TM to CTSI. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3EB1D112-0D02-4329-80D6-D14F8AE573ED%7D&file=R3%20PTP%20%20LI-030%20-060%20Manage%20In-bound%20Transportation-Outbound%20Interface%20to%20send%20freight%20forwarder%20rates%20from%20TM%20to%20CTSI.pptx&wdLOR=cAF7500C7-103A-4757-9BC9-DAB2B468E3B2&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 21170 | CTSI Global | S/4 | CTSI | NA | 2025-01-13 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-20 | 2025-05-02 | 2025-05-09 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | [10 empty] | 2025-06-18 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-08-04 | 2025-09-12 | Yes |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-24 | 2025-10-24 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0852 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-20 | 2025-03-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [9 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-08-04 | 2025-09-12 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-03-07 | 2025-06-13 | 2025-06-13 | S4 | 2025-12-31 | TM |  |  | 1 |  | 1911 | [7 empty] | 2. At Risk | 7. FUT Defect Retesting | 11/04: IT approval received, Business approval pending 10/30 EP: LOGI0852_IF/IP: Intel review during Nov 3 week (Rev FUT due date 11/07) 10/24 - Defects+CR 10/22: Non CR defect 3190 fixed and working. Awaiting fix for Defect 3623 and 3334 for commodity code and min/max weight to test. | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2387 | LOGI0852_IF | 02.Interface | 02.IF - Intel Foundry | Outbound Interface to send freight forwarder rates from TM to CTSI | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3EB1D112-0D02-4329-80D6-D14F8AE573ED%7D&file=R3%20PTP%20%20LI-030%20-060%20Manage%20In-bound%20Transportation-Outbound%20Interface%20to%20send%20freight%20forwarder%20rates%20from%20TM%20to%20CTSI.pptx&wdLOR=cAF7500C7-103A-4757-9BC9-DAB2B468E3B2&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 21170 | CTSI Global | S/4 | CTSI | NA | 2025-01-13 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-20 | 2025-05-02 | 2025-05-09 | 2025-08-13 | 100% | 2025-08-09 | 2025-06-06 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | [10 empty] | 2025-06-18 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-08-04 | 2025-09-12 | Yes |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-24 | 2025-10-24 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 | LOGI0852_IP | 03.Medium | 0.3 | 0.435 | 0852 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-20 | 2025-03-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [9 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-08-04 | 2025-09-12 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-03-07 | 2025-06-13 | 2025-06-13 | S4 | 2025-12-31 | TM |  |  | 1 |  | 1910 | [7 empty] | 2. At Risk | 8. Blocked by CR/Design change | 11/04: IT approval received, Business approval pending 10/30 EP: LOGI0852_IF/IP: Intel review during Nov 3 week (Rev FUT due date 11/07) 10/24 - Defects + CR 10/22: Non CR defect 3190 fixed and working. Awaiting fix for Defect 3623 and 3334 for commodity code and min/max weight to test. | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2392 | LOGI0842_IP | 02.Interface | 01.IP - Intel Product | Interface from SAP S4 to DBaaS to Fetch Actual COF for FVR batch and COA for AVR batch. | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6BAFF48E-9F89-40AB-A75E-4A2A1A872504%7D&file=R3_IP%20IF_OTC_interface%20to%20DBaaS_RICEFW%20Intake%20Form%20-.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 53470 | Supply Chain Trade Re-engineering Data Container for Intel Products | S/4 | DBaaS | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-07-11 | 100% | 2025-10-02 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-10-02 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-16 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-10 | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2026-01-23 | 2025-10-10 | 2026-01-23 |  | 2025-12-12 | 2026-01-31 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-25 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0842 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-07-18 |  | 2025-07-16 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2025-10-10 | 2026-01-23 |  |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-07-18 | MW | 2025-10-17 |  |  |  | 1 | 08. Not Applicable | 1900 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 02/16: Defect#7355 raised as payload is sent incorrectly (data structure) from MW to DBass, picked up by Mulesoft team, no ETA 02/09: Defect#6827 is with tech, ETA 02/11 02/02: Working session completed, defect#6827 created payload structure issue in S/4 01/29: Awaiting material master creation as per data shared by the Dbass team, Apigee configuration to be done by Muelsoft. Once these setups are done E2E testing can be progressed. If no further no issues, then FUT can be completed in one day 01/22: Request details sent successfully. Dbass is unable to send the response file, Dbass team checking on the same 01/19: Defect 6286 is fixed. Retest in progress with B2B team. 01/12: Defect 6217 related to LIKP/LIPS and MSEG details not being received in DBaaS raised to tech team. No ETA provided yet. 01/05: Defect#5815 & 5911 is still with tech, working session scheduled for the same. No ETA on fix 12/22: defect 5815 is with tech team. No TC executed as initial testing is blocked in this defect. | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2392 | LOGI0842_IF | 02.Interface | 02.IF - Intel Foundry | Interface from SAP S4 to DBaaS to Fetch Actual COF for FVR batch and COA for AVR batch. | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6BAFF48E-9F89-40AB-A75E-4A2A1A872504%7D&file=R3_IP%20IF_OTC_interface%20to%20DBaaS_RICEFW%20Intake%20Form%20-.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 53494 | Supply Chain Trade Re-engineering Data Container for Intel Foundry | S/4 | DBaaS | MULESOFT | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-07-04 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-07-11 | 100% | 2025-08-26 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-08-26 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-16 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-10 | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2026-01-23 | 2025-10-10 | 2026-01-23 |  | 2025-12-12 | 2026-01-31 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-13 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 | LOGI0842_IP | 03.Medium | 0.3 | 0.435 | 0842 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-07-18 |  | 2025-07-16 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2025-10-10 | 2026-01-23 |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-07-18 | MW | 2025-09-22 |  |  |  | 1 | 08. Not Applicable | 1899 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 02/09: Defect#7062 is with tech, ETA 02/09 02/02: Awaiting Data from MDG team. New set of materials provided by Dbass team. Defect#6827 created payload structure issue in S/4 01/29: Awaiting material master creation as per data shared by the Dbass team, Apigee configuration to be done by Muelsoft. Once these setups are done E2E testing can be progressed. If no further no issues, then FUT can be completed in one day 01/22: Request details sent successfully. Dbass is unable to send the response file, Dbass team checking on the same 01/19: Defect 6286 is fixed. Retest in progress with B2B team. 01/12: Defect 6218 related to LIKP/LIPS and MSEG details not being received in DBaaS raised to tech team. No ETA provided yet. 01/05: Defect#5912 is fixed & retest is in progress, ETA 01/05 to close the defect 12/22: Defect 5813 is fixed will be retested on 12/23,No TC yet executed because of this initial blocker. 12/15: Object is likely to be cancelled, awaiting confirmation from Intel, post which Cancellation CR will be raised. | 2025-10-08 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 22 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2057 | LOGI0836_IP | 02.Interface | 01.IP - Intel Product | Interface from S4 to NDA (IPLA –Intel Pre Release License Agreements) | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_IP_Logistics_LO-180-050_Interface%20-%20NDA%20System%20IPLA%20-%20RICEFW%20Intake%20form.pptx?d=w1091fd3e7e5e48be94297f793f765ec3&csf=1&web=1&e=Bu4j3C | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 35641 | LAWMAS Agiloft Contract Lifecycle Management | S/4 | NDA | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-03-28 | 2025-07-04 | 2025-07-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-01 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | [10 empty] | 2025-01-01 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-31 | 2025-07-21 | 2025-07-21 |  |  | 2025-10-03 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-04-01 10:06 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0836 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-04-18 | 2025-03-28 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-07-21 | 2025-07-21 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 | 2025-10-03 |  |  |  | 1 | 08. Not Applicable | 2700 | [7 empty] | 4. Completed | 19. Incomplete Build | 1/20: Retested and documented. Walkthrough is set today. 1/16: Fiori changes are in progress with Tech(Anjana) 01/05: Retest in progress and dependency on LOGE0935 12/22: Destination issue is there AMQ is checking on this 12/15: dependency on LOGE0935 tech is working on it 12/8: Defect 5051 with tech for the destination issue. This also has dependency on LOGE0935 which is currently under development till 5/12. Now FUT started for log9035. There is a defect raised for LOGE9035 with ~30 issues. 12/1: LOGE0935 is with development and FUT is yet to start. 11/24: Dependent on LOGE0935. TUT ETA completion is 11/25. 11/11: Dependent on LOGE0935 10/24 - TUT ETA completion is 11/1. Potential risk for this sprint completion 10/10: This object was incorrectly planned in S18, since it has a dependency on LOGE0935_IF. We have planned the FUT in S19 | 2025-08-15 | N | 99. Logistics |  |  |  |  | 12/02 - Dependent with LOGE0935 and TUT+FUT object. Not for S20. |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | Yes |  | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-04-01 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2057 | LOGI0836_IF | 02.Interface | 02.IF - Intel Foundry | Interface from S4 to NDA (IPLA –Intel Pre Release License Agreements) | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_IP_Logistics_LO-180-050_Interface%20-%20NDA%20System%20IPLA%20-%20RICEFW%20Intake%20form.pptx?d=w1091fd3e7e5e48be94297f793f765ec3&csf=1&web=1&e=Bu4j3C | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 35641 | LAWMAS Agiloft Contract Lifecycle Management | S/4 | NDA | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-03-26 | 2025-07-04 | 2025-07-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-08 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-08 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | [10 empty] | 2025-01-01 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-31 | 2025-07-21 | 2025-07-21 |  |  | 2025-10-03 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 | LOGI0836_IP | 03.Medium | 0.3 | 0.435 | 0836 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-04-18 | 2025-03-26 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-07-21 | 2025-07-21 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-04-18 | 2025-08-15 | 2025-08-15 | S4 | 2025-10-03 |  |  |  | 1 | 08. Not Applicable | 2699 | [7 empty] | 4. Completed | 19. Incomplete Build | 1/20: Retested and documented. Walkthrough is set today. 1/16: Fiori changes are in progress with Tech(Anjana) 01/05: Documenation in progress. ETA:01/05 12/22: Destination set up fixed and in retest. (0/4 TC) 12/15: dependency on LOGE0935 tech is working on it 12/8: Defect 5051 with tech for the destination issue. This also has dependency on LOGE0935 which is currently under development till 5/12. Now FUT started for log9035. There is a defect raised for LOGE9035 with ~30 issues. 12/1: LOGE0935 is with development and FUT is yet to start. 11/24: Dependent on LOGE0935. TUT ETA completion is 11/25. 11/11: Dependent on LOGE0935 10/24 - TUT ETA completion is 11/1. Potential risk for this sprint completion 10/10: This object was incorrectly planned in S18, since it has a dependency on LOGE0935_IF. We have planned the FUT in S19 | 2025-08-15 | N | 99. Logistics |  |  |  |  | 12/02 - Dependent with LOGE0935 and TUT+FUT object. Not for S20. |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2406 | LOGI0834 | 02.Interface | 01.IP - Intel Product | Inbound interface for WLA Hold scenario to trigger Outbound ASN with Non-Valuated material iDoc up on receiving Inbound ASN with Valuated material from IP-SAP System to e2open system for FTS-IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE81C80D5-3808-45F9-BDAF-88DB998C6A58%7D&file=M-100-140_FTS_IP_Inbound%20interface%20for%20WLA%20Hold%20scenario%20to%20trigger%20Outbound%20ASN%20with%20Non-Valuated%20material%20iDoc%20up%20on%20receiving%20Inbound%20ASN%20with%20Valuated%20material%20from%20IP-SAP%20System%20to%20e2open.pptx&wdLOR=c57D3FA36-BF3B-4F94-B1E3-F633BB1CA3E4&action=edit&mobileredirect=true | 02.No | 02.No |  | 2025-02-03 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-02-10 | 2025-03-07 | 2025-03-05 | 100% | 2025-03-07 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-15 | 100% | 2025-05-15 | 2025-04-07 | 2025-04-18 | 2025-05-15 | 100% | 2025-05-15 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-23 | 2025-06-16 | 2025-10-10 | 2025-10-10 | 100% | 2025-11-17 | 2025-05-23 | 2025-11-17 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-02-25 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-06 | 01.S4 |  |  | 1 | 1.45 | 0834 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-15 | 2025-05-16 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-06-13 | 2025-05-23 | 2025-05-23 |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-05-23 | 2025-11-17 | 2026-03-09 |  | 2026-02-25 | 2026-02-27 | 2026-02-25 |  |  |  |  | B2B - E2open | 2025-03-07 | 2025-04-18 | 2025-04-18 |  | 2026-02-27 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 1784 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 02/23 - Review comments received today for depend WRICEF - LOGI0834, will be addresed by EOD today 02/20- Sent for approval on 02/13. Awaiting Feedback and approval from Intel IT and Business 02/16- Sent for approval on 02/13. Awaiting Feedabck and approval from Intel IT and Business 02/12- 9 TCs are completd out of 10, 1TC testing in progress with E2OPEN , ETA- 02/12 01/05 - CR Changes completed, TUT is in progress. FUT to be started post TUT competion from tech. 12/22 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 12/23 12/15 - Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-05-15 | 2025-05-15 | Yes | Change in Condition Records and Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-05 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2224 | LOGI0800_IP | 02.Interface | 01.IP - Intel Product | Interface to send shipment information to custom broker | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9715E3D8-9116-4658-B36E-F207488F6CAF%7D&file=R3_IP_OTC_LE_Interface%20to%20send%20shipment%20details%20to%20CB.pptx&wdLOR=c43B1E664-F0D7-48B8-9BCA-6180696ECDAC&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-12-16 | 2025-02-19 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-08-04 | 2025-08-04 |  | 2025-08-13 | 2025-09-03 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0800 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-25 | 2025-10-09 | 2025-09-25 |  |  |  |  | B2B - OpenText | 2025-02-19 | 2025-04-18 | 2025-04-18 | MW | 2025-05-30 |  |  |  | 1 | 04.6 Logistics - GLO | 2459 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2224 | LOGI0800_IF | 02.Interface | 02.IF - Intel Foundry | Interface to send shipment information to custom broker | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9715E3D8-9116-4658-B36E-F207488F6CAF%7D&file=R3_IP_OTC_LE_Interface%20to%20send%20shipment%20details%20to%20CB.pptx&wdLOR=c43B1E664-F0D7-48B8-9BCA-6180696ECDAC&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-12-16 | 2025-02-19 | 2025-02-21 | 100% | 2025-02-24 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2025-04-02 | 2025-04-11 | 2025-04-18 | 2025-04-02 | 100% | 2025-04-02 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-05 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-08-04 | 2025-08-04 |  | 2025-08-13 | 2025-09-03 | 2025-10-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-03 | 2025-10-09 | 2025-10-03 | N | 100% | 2025-09-18 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-13 | 01.S4 | LOGI0800_IP | 03.Medium | 0.3 | 0.435 | 0800 |  | R3 ITC1 | [6 empty] | 2025-02-24 | 2025-02-24 | 2025-02-24 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-02 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-18 | 2025-10-09 | 2025-09-18 |  |  |  |  | B2B - OpenText | 2025-02-19 | 2025-04-18 | 2025-04-18 | MW | 2025-05-30 |  |  |  | 1 | 04.6 Logistics - GLO | 2458 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2142 | LOGI0755 | 02.Interface | 01.IP - Intel Product | PTP-LE: ASN (Inbound 3B2) from SIFO Suppliers - E2Open to S/4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE689DD5B-B9D6-4CE3-9097-13CA8ED922A8%7D&file=2142_PTP_LE%20-%20ASN%20(Inbound%203B2)%20from%20SIFO%20Suppliers%20-%20E2Open%20to%20S4%20IP-%20Copy.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2OPEN | S/4 | MULESOFT | 2024-11-11 | 2025-02-21 | 2024-12-13 | 100% | 2025-02-10 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-12 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-23 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-23 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-07-08 | 2025-10-09 | 2025-10-09 | 100% | 2025-11-17 | 2025-08-04 | 2025-11-17 |  | 2025-08-13 | 2025-09-10 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-10-09 | 2025-10-09 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0755 |  | R3 ITC1 | [6 empty] | 2025-02-10 | 2025-02-21 | 2025-02-10 |  | 2025-03-12 | 2025-03-21 | 2025-03-12 |  | 2025-05-23 | 2025-05-30 | 2025-05-23 | 2025-05-23 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-08-04 | 2025-11-17 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | B2B - E2open | 2024-12-06 | 2025-04-18 | 2025-03-21 | MW | 2025-06-23 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2739 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/31: Sent for Intel review 10/24 - 13/15 scenarios are completed. 10/09- 9 TC tested out of 17, rest all are blocked due to delay in E2act delivery/M2M execution (E2OPEN Blocker)- E2ACT Defect#5666,6139 | 2025-10-09 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-05-30 | 2025-05-23 | Yes | Change in Custom Table entries for Plant Table - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2104 | LOGI0753_IP | 02.Interface | 01.IP - Intel Product | The process involves sending a Real time consumption signal from a supplier on boarded on e2open to S/4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20LE/2104%20%26%202108_PTP_LE%20-%20Realtime%20Consumption%20Signal%20from%20ODM%20Subcon%20Supplier%20-%20E2Open%20to%20S4%20IP%20%26%20IF.pptx?d=w647f95148ba44ae2814206a4ca4d25ef&csf=1&web=1&e=LkgXMT | 02.No | 01.Yes |  | 2024-10-29 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2OPEN | S/4 | MULESOFT | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-12 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-07 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-08 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-08 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-28 | 100% | 2025-05-05 | 2025-05-30 | 2025-08-28 | 2025-08-28 | 100% | 2025-09-01 | 2025-05-05 | 2025-09-01 |  | 2025-07-16 | 2025-09-19 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-08-28 | 2025-08-28 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1.45 | 0753 |  | R3 ITC1 | [6 empty] | 2024-12-12 | 2024-12-13 | 2024-12-12 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-08 | 2025-03-21 | 2025-03-08 | 2025-03-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-05-05 | 2025-09-01 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  |  |  |  | B2B - E2open | 2024-12-13 | 2025-03-21 | 2025-01-24 | MW | 2025-07-18 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2272 | [10 empty] | 2025-08-28 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2327 | LOGI0749_IP | 02.Interface | 01.IP - Intel Product | TM –CTSI integration – Freight details to CTSI for Liability validation | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B729BB56F-BE0C-402D-A2FE-5F7FD176E533%7D&file=R3%20PTP%20LI-030-240%20-%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)-%20FRO%20details%20to%20CTSI.pptx&action=edit&mobileredirect=true&previoussessionid=0e34497d-1e09-815f-774a-55e4f3353193&CID=C8C34B9C-9AC3-4844-9D01-3CF79A7E2857&wdLOR=cF01526B0-6E42-45F2-ABDC-7CAF446C0AFF | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 21170 | CTSI Global | S/4 | CTSI | SFT | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-19 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-11-06 | 2025-06-18 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-11-06 | 2025-11-06 | Yes |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-24 | 2025-10-24 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-15 | 2025-09-15 | 2025-09-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-23 | 01.S4 |  |  | 1 | 1.45 | 0749 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-11 | 2025-05-16 |  |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-11-06 | 2025-11-06 | 2025-11-06 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-11-06 | 2025-11-06 |  |  | 2025-10-17 | 2025-10-24 | 2025-10-17 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | MW | 2025-12-31 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1875 | [7 empty] | 5. Not Dispositioned |  |  | 2025-09-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2327 | LOGI0749_IF | 02.Interface | 02.IF - Intel Foundry | TM –CTSI integration – Freight details to CTSI for Liability validation | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B729BB56F-BE0C-402D-A2FE-5F7FD176E533%7D&file=R3%20PTP%20LI-030-240%20-%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)-%20FRO%20details%20to%20CTSI.pptx&action=edit&mobileredirect=true&previoussessionid=0e34497d-1e09-815f-774a-55e4f3353193&CID=C8C34B9C-9AC3-4844-9D01-3CF79A7E2857&wdLOR=cF01526B0-6E42-45F2-ABDC-7CAF446C0AFF | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 21170 | CTSI Global | S/4 | CTSI | SFT | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-19 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-09 | 2025-05-16 | 2025-04-02 | 100% | 2025-04-02 | 2025-05-09 | 2025-05-16 | 2025-04-02 | 100% | 2025-04-02 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-09-23 | 2025-06-18 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-09-23 | 2025-09-23 | Yes |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-24 | 2025-10-24 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-15 | 2025-09-15 | 2025-09-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-23 | 01.S4 | LOGI0749_IP | 03.Medium | 0.3 | 0.435 | 0749 |  | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-02 | 2025-05-16 |  |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-23 | 2025-09-23 |  |  | 2025-10-17 | 2025-10-24 | 2025-10-17 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | MW | 2025-12-31 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1874 | [10 empty] | 2025-09-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-05-16 | 2025-04-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1706 | LOGI0664 | 02.Interface | 01.IP - Intel Product | Trigger ZCUS (export customs clearance output) and ZXCI to send outputs - ZSIS,CL,PL,IPLA to carrier/customers broker xml with attachment to customs broker and carrier | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/842_R3_IP_OTC_FTS_LO-180-150-020_OTC_ZCUS_RICEFW%20Intake%20Form.pptx?d=w61d72cfee2934e43bc54aa7d0c15a6ce&csf=1&web=1&e=jzrGYa | 02.No | 01.Yes |  | 2024-09-22 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-20 | 2025-03-03 | 2025-03-07 | 2025-08-13 | 100% | 2025-08-09 | 2025-03-10 | 2025-03-21 | 2025-09-26 | 100% | 2025-09-23 | 2025-03-10 | 2025-03-21 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-14 | 2025-03-28 | 2025-05-16 | 100% | 2025-05-16 | 2025-04-21 | 2025-05-16 | 2025-05-09 | 100% | 2025-08-04 | 2025-05-07 | 2025-05-14 | 2025-05-14 | 100% | 2025-05-14 | 2025-08-04 | 2025-08-04 | Yes |  | 2026-02-04 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-05-16 | 2025-05-16 | 2025-05-16 | vasamohan@deloitte.com | 2024-09-22 21:04 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-04 | 01.S4 |  |  | 2 | 2.9 | 0664 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-02-21 | 2025-02-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-08-04 | 2025-08-04 |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 |  |  |  |  | B2B - OpenText | 2025-02-21 | 2025-03-21 | 2025-03-28 |  | 2026-02-04 | TM |  |  | 1 | 08. Not Applicable | 1799 | [7 empty] | 3. Off Track | 20. Connection Issue | 2/16: TUT + FUT WIP. SR is raised for Soamanager setup (RFC connection) 2/11: SOAMANAGER setup in progress. Workaround available to continue testing. ETA for establishing connection is 2/12 02/09: S4 TUT+FUT in progress. SOAMANAGER Setup in progress with MuleSoft& Intel Basis 02/02: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. 01/30: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. Field validation steps started and in progress 01/22: Destination config from Mulesoft WIP, Working session to continue. XML issue yet to be fixed 01/19: Working session in progress with tech team, till now not able to trigger a single xml. 01/12: TUT in progress . FUT yet to start , Working session for XML trigger scheduled 01/05: CR( 1008,0624) TUT+FUT working session requested with dev team . Raid 03306 for DEV/TUT ETA pending. 12/22: FUT in progress During TUT additional fields were identified which were required, there is an ongoing CR on this, FUT will be picked up post the CR is approved and build is done. | 2025-05-16 | N | 99. Logistics |  |  |  | 2/24: FUT in progress. 18/20 test scenarios completed. Review call planned on 02/25 Current status: FUT in progress Issue: FUT delayed due to connectivity issue between S4 and E2O Next steps: Complete FUT Help needed: N/A FUT: 0227 |  | 3. Watch item |  | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-04-11 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1706 | LOGI0663_IP | 02.Interface | 01.IP - Intel Product | Trigger ZCUS (export customs clearance output) and ZXCI to send outputs - ZSIS,CL,PL,IPLA to carrier/customers broker xml with attachment to customs broker and carrier | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/842_R3_IP_OTC_FTS_LO-180-150-020_OTC_ZCUS_RICEFW%20Intake%20Form.pptx?d=w61d72cfee2934e43bc54aa7d0c15a6ce&csf=1&web=1&e=jzrGYa | 02.No | 01.Yes |  | 2024-09-22 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-25 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-25 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-09 | 100% | 2025-08-04 | 2025-07-03 | 2025-09-13 | 2025-09-13 | 100% | 2025-08-29 | 2025-08-04 | 2025-08-29 | Yes |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-09-13 | 2025-09-13 | vasamohan@deloitte.com | 2024-09-22 21:04 | cell-link@smartsheet.com | 2026-03-31 19:15 | 10 | 2024-10-04 | 01.S4 |  |  | 2 | 2.9 | 0663 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-05-16 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-13 | 2025-08-29 | 2025-08-29 | 2025-08-04 | 2025-08-29 |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 |  |  |  |  | B2B - OpenText | 2025-02-21 | 2025-05-16 | 2025-05-16 | MW | 2025-06-20 | TM |  |  | 1 | 03. IP Customers | 1801 | [7 empty] | 3. Off Track | 20. Connection Issue | 2/16: TUT + FUT WIP. SR is raised for Soamanager setup (RFC connection) 2/11: SOAMANAGER setup in progress. Workaround available to continue testing. ETA for establishing connection is 2/12 02/09: S4 TUT+FUT in progress. SOAMANAGER Setup in progress with MuleSoft& Intel Basis 02/02: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. 01/30: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. Field validation steps started and in progress 01/22: Destination config from Mulesoft WIP, Working session to continue. XML issue yet to be fixed 01/19: Working session in progress with tech team, till now not able to trigger a single xml. 01/12: TUT in progress + Defect fixing 01/05: Working session with Tech for TUT+FUT in progress 12/22: CR Build still in progress, we are trying to do TUT+FUT along with build. 12/15: CR build yet to complete. TUT in progress | 2025-09-13 | N | 99. Logistics |  |  |  | 2/24: FUT in progress. 18/20 test scenarios completed. Review call planned on 02/25 Current status: FUT in progress Issue: FUT delayed due to connectivity issue between S4 and E2O Next steps: Complete FUT Help needed: N/A FUT: 0227 |  | 3. Watch item |  | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-27 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 1706 | LOGI0663_IF | 02.Interface | 02.IF - Intel Foundry | Trigger ZCUS (export customs clearance output) and ZXCI to send outputs - ZSIS,CL,PL,IPLA to carrier/customers broker xml with attachment to customs broker and carrier | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/842_R3_IP_OTC_FTS_LO-180-150-020_OTC_ZCUS_RICEFW%20Intake%20Form.pptx?d=w61d72cfee2934e43bc54aa7d0c15a6ce&csf=1&web=1&e=jzrGYa | 02.No | 01.Yes |  | 2024-09-22 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-28 | 2025-03-17 | 2025-03-21 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-11 | 2025-04-25 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-09 | 100% | 2025-08-04 | 2025-07-03 | 2025-09-13 | 2025-09-13 | 100% | 2025-08-29 | 2025-08-04 | 2025-08-29 | Yes |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-09-13 | 2025-09-13 | vasamohan@deloitte.com | 2024-09-22 21:04 | cell-link@smartsheet.com | 2026-03-31 19:15 | 10 | 2024-10-04 | 01.S4 | LOGI0663_IP | 02.High | 0.6 | 0.87 | 0663 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-13 | 2025-08-29 | 2025-08-29 | 2025-08-04 | 2025-08-29 |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 |  |  |  |  | B2B - OpenText | 2025-02-21 | 2025-06-13 | 2025-06-13 | MW | 2025-07-18 | TM |  |  | 1 |  | 1800 | [7 empty] | 3. Off Track | 20. Connection Issue | 2/16: TUT + FUT WIP. SR is raised for Soamanager setup (RFC connection) 2/11: SOAMANAGER setup in progress. Workaround available to continue testing. ETA for establishing connection is 2/12 02/09: S4 TUT+FUT in progress. SOAMANAGER Setup in progress with MuleSoft& Intel Basis 02/02: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. 01/30: BASIS RFC connection established today, DEV team continue to work on the development + RFC dev set up completion. Field validation steps started and in progress 01/22: Destination config from MuleSoft WIP, Working session to continue. XML issue yet to be fixed 01/19: Working session in progress with tech team, till now not able to trigger a single xml. 01/12: TUT in progress + Defect fixing 01/05: Working session with Tech for TUT+FUT in progress 12/22: CR Build still in progress, we are trying to do TUT+FUT along with build. 12/15: CR build yet to complete. TUT in progress | 2025-09-13 | N | 99. Logistics |  |  |  | 2/24: FUT in progress. 18/20 test scenarios completed. Review call planned on 02/25 Current status: FUT in progress Issue: FUT delayed due to connectivity issue between S4 and E2O Next steps: Complete FUT Help needed: N/A FUT: 0227 |  | 3. Watch item |  | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-04-18 | 2025-04-11 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-27 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 2078 | LOGI0630_IP | 02.Interface | 01.IP - Intel Product | TM - GTT: GXS sending carrier events back to GTT app “Shipment Tracking”. IP | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/GTT-GSX_InterfaceIntake%20Form.pptx?d=wdba0a633a8a5465d9afb0b2cf6c78277&csf=1&web=1&e=uhmw5h | 01.Yes | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | NA | 2025-03-10 | 2025-04-04 | 2025-04-04 | 100% | 2025-04-04 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-09 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | [10 empty] | 2025-05-26 | 2025-07-07 | 2025-07-07 | 100% | 2025-07-07 | 2025-08-04 | 2025-08-04 | No |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-04 | 2025-08-16 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-07-07 | 2025-07-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-25 | 01.S4 |  |  | 1 | 1.45 | 0630 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [9 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  |  |  |  | B2B - OpenText | 2025-03-21 | 2025-05-16 | 2025-05-16 | S4 | 2025-06-30 | TM |  |  | 1 | 03. IP Customers | 2516 | [9 empty] | 8/25: In progress, ETA 8/29. 8/18: FUT is in progress with Open Text and GXS team, event count is high so taking more time than expected. | 2025-07-07 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2078 | LOGI0630_IF | 02.Interface | 02.IF - Intel Foundry | TM - GTT: GXS sending carrier events back to GTT app “Shipment Tracking”. IF. | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/GTT-GSX_InterfaceIntake%20Form.pptx?d=wdba0a633a8a5465d9afb0b2cf6c78277&csf=1&web=1&e=uhmw5h | 01.Yes | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12842 | OpenText |  |  | NA | 2025-03-10 | 2025-04-04 | 2025-04-04 | 100% | 2025-04-04 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | [10 empty] | 2025-05-26 | 2025-07-07 | 2025-07-07 | 100% | 2025-07-07 | 2025-08-04 | 2025-08-04 | No |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-04 | 2025-08-16 | 2025-08-13 | N | 100% | 2025-08-26 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-07-07 | 2025-07-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-25 | 01.S4 | LOGI0630_IP | 03.Medium | 0.3 | 0.435 | 0630 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [9 empty] | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-08-04 | 2025-08-04 |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 |  |  |  |  | B2B - OpenText | 2025-03-21 | 2025-05-16 | 2025-05-16 | S4 | 2025-06-30 | TM |  |  | 1 |  | 2515 | [9 empty] | 8/25: In progress, ETA 8/29. 8/18: FUT is in progress with Open Text and GXS team, event count is high so taking more time than expected. | 2025-07-07 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2203 | LOGI0612_IP | 02.Interface | 01.IP - Intel Product | Customer ASN interface from outbound delivery | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B172E6626-D78F-41DB-AFBF-0809BBE5DFA8%7D&file=R2_IF_OTC_ASN%20interface_RICEFW%20Intake%20Form%20-%20Copy.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-07 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-01-04 | 2025-02-21 | 2025-01-31 | 100% | 2025-02-04 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-09 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-08-04 | 2025-08-04 |  | 2025-08-13 | 2025-09-03 | 2025-10-09 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-10-09 | 2025-10-09 | N | 100% | 2025-10-02 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-30 11:12 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1.45 | 0612 |  | R3 ITC1 | [6 empty] | 2025-02-04 | 2025-02-21 | 2025-02-04 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-08-04 | 2025-08-04 |  |  | 2025-10-02 | 2025-10-09 | 2025-10-02 |  |  |  |  | B2B - OpenText | 2025-02-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-30 |  |  |  | 1 | 03. IP Customers | 1781 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW | Defects found during testing. Currently defect fix in progress with tech team | 2025-04-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | ZTOTC_DH table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-30 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1920 | LOGI0610 | 02.Interface | 01.IP - Intel Product | 3B2 Post goods issue interface for Outbound delivery to SAP | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_3B2%20PGI%20interface%20from%203PL%20to%20SAP_RICEFW%20Intake%20Form.pptx?d=wa8b5b56f4fb3485d9033921395eef7c6&csf=1&web=1&e=3oWOjU | 02.No | 01.Yes |  | 2024-09-09 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2025-01-04 | 2025-02-21 | 2025-01-31 | 100% | 2025-02-06 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-19 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-23 | 2025-07-31 | 2025-07-31 | 100% | 2025-07-31 | 2025-08-04 | 2025-08-04 |  | 2025-08-29 | 2025-11-14 | 2025-11-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-21 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-07-31 | 2025-07-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-26 23:51 | 10 | 2024-09-14 | 01.S4 |  |  | 1 | 1.45 | 0610 |  | R3 ITC1 | [6 empty] | 2025-02-06 | 2025-02-21 | 2025-02-06 |  | 2025-03-19 | 2025-03-21 | 2025-03-19 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-08-04 | 2025-08-04 |  |  | 2025-11-20 | 2025-12-05 | 2025-11-20 |  |  |  |  | B2B - OpenText | 2025-02-21 | 2025-04-18 | 2025-04-18 | S4 | 2025-06-03 |  |  |  | 1 | 03. IP Customers | 1469 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Awaiting approval following up with PS | 2025-07-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | ZTOTC_PARAMS table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-27 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1919 | LOGI0609 | 02.Interface | 01.IP - Intel Product | 3B13 interface for pick/pack updates for outbound delivery to SAP | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_3B13%20pack%20update%20to%20SAP_RICEFW%20Intake%20Form.pptx?d=w02464056659847a39fabf5e66e0ef764&csf=1&web=1&e=S5pzdW | 02.No | 01.Yes |  | 2024-09-09 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-12-16 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-09 | 100% | 2025-08-04 | 2025-05-08 | 2025-05-09 | 2025-05-09 | 100% | 2025-05-09 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 | 2025-11-14 | 2025-11-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-21 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-26 23:51 | 10 | 2024-09-14 | 01.S4 |  |  | 1 | 1.45 | 0609 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | 2025-08-04 | 2025-08-04 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 |  |  |  |  | B2B - OpenText | 2025-01-31 | 2025-04-18 | 2025-04-18 | MW | 2025-06-03 |  |  |  | 1 | 03. IP Customers | 1468 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/12: Defect 6113 is fixed. Awaiting B2B team to trigger 3B13 to test the defect. 01/05: B2B wants to re-test with fresh set of data to check the behaviour of one field, ETA 01/06 12/22:Defect 5790 is fixed and will be retested on 12/23. 12/15: B2B team wants to test 4048 and 4058 plants. which has limited test data. Checking if data can be created and tested for these. 12/8: FUT is completed. Marking as approved no action. 11/24: New plant as per OT request to be tested. ETA for FUT completion 11/26. 11/14: Defect 601 open with Tech team. Defect fix ETA in 11/14 | 2025-06-13 | N | 99. Logistics |  |  |  |  | ETA 0312 |  |  | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | Yes | ZTOTC_PARAMS table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-27 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1439 | LOGI0607 | 02.Interface | 01.IP - Intel Product | 3B14R Cancellation Request from S/4 to 3PL | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_Logistics_LO-180-170_3B14R%20Cancellation%20Request_RICEFW_Intake%20Form.pptx?d=w6715cbfaa8c2436c824de15a37e4a7a0&csf=1&web=1&e=eR6Vpx | 02.No | 01.Yes |  | 2024-09-09 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 9329; 12842; 7196 | Logistics Customers Service Request; OpenText; Customer Master Database | S/4 | 3PL | MULESOFT | 2024-12-16 | 2025-01-31 | 2025-01-10 | 100% | 2024-12-19 | 2025-02-07 | 2025-02-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-07 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-14 | 2025-03-07 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-14 | 2025-01-27 | 2025-01-31 | 2025-03-21 | 100% | 2025-03-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2024-10-21 | 2024-11-21 | 2024-11-21 | 100% | 2024-11-21 | 2025-03-19 | 2025-03-19 |  | 2025-10-08 | 2025-11-14 | 2025-11-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-21 | 2025-11-21 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-03-21 | 2025-03-21 | vasamohan@deloitte.com | 2024-09-09 11:38 | cell-link@smartsheet.com | 2026-03-31 19:17 | 10 | 2024-09-14 | 01.S4 |  |  | 1 | 1.45 | 0607 |  | R3 ITC1 | [6 empty] | 2024-12-19 | 2025-01-31 | 2024-12-19 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-03-14 | 2025-03-21 | 2025-03-14 | 2025-03-14 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2024-11-21 | 2024-11-21 | 2024-11-21 | 2025-03-19 | 2025-03-19 |  |  | 2025-11-26 | 2025-11-26 | 2025-11-26 |  |  |  |  | B2B - OpenText | 2025-01-31 | 2025-03-21 | 2025-01-31 | MW | 2025-12-31 |  |  |  | 1 | 03. IP Customers | 2487 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24: Received intel B2B approval following up for IT/PS approval. 11/18: Awaiting intel B2B Approval. 10/10: S4 FUT completed, E2E FUT planned in S19 10/09 EP: Push FUT dates right based on 1624 dependency to complete E2E FUT by 10/17 EP: 09/25: E2E FUT will be done after 1624 is completed. Recommend Roadblock be removed 09/24: can the FUT dates for LOGI0607 be pushed right & Roadblock removed based on the LOGE0613/LOGE1624 "Development of LCSR tool in Fiori" FUT completing 11/07? Can LOGI0607 be tested in parallel with the two enhancements? 09/18 No Ext FUT; Dependent on the development of LCSR tool which is planned to be completed in S16. | 2025-03-21 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-03-14 | Yes | ZTOTC_DH table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1821 | LOGI0516_IP | 02.Interface | 01.IP - Intel Product | PTP IF​Fetch Integrators rate in TM via an API call to Redwood and leverage it for carrier selection and charge calculation .​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA8E15C19-F04F-4FC5-B53C-92F05F08B776%7D&file=R3%20PTP%20L3%20-%20030-060%20%20Integrator%20interface%20-Rate%20Integrators%20with%20Redwood.pptx&wdLOR=cC3781B9E-FD79-4F33-9CE5-D4E8A7F1AB55&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 56974 | Redwood | ECD | S/4 | APIGEE | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-09-26 | 100% | 2025-09-24 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-06-16 | 2025-05-30 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-08-15 | 100% | 2025-08-15 | 2025-07-21 | 2025-08-15 | No |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-30 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-08-06 08:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-21 | 01.S4 |  |  | 1 | 1.45 | 0516 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-09-24 | 2025-09-26 | 2025-09-24 |  |  | 2025-06-27 |  | 2025-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-07-21 | 2025-08-15 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-08-01 | MW | 2025-06-27 | TM |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1541 | [9 empty] | EP: 09/11: ETC 09/12 per Jeet | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1821 | LOGE0515_IF | 04.Enhancement | 02.IF - Intel Foundry | TM : Fetch Integrators rate in TM via an API call to Redwood and leverage it for carrier selection and charge calculation. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA8E15C19-F04F-4FC5-B53C-92F05F08B776%7D&file=R3%20PTP%20L3%20-%20030-060%20%20Integrator%20interface%20-Rate%20Integrators%20with%20Redwood.pptx&wdLOR=cC3781B9E-FD79-4F33-9CE5-D4E8A7F1AB55&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-04 | 01.S4 | LOGE0515_IP | 03.Medium | 0.2 | 0.2 | 0515 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-23 | TM |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1542 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | EP: 09/11: ETC 09/12 per Jeet | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1821 | LOGI0516_IF | 02.Interface | 02.IF - Intel Foundry | PTP IP​Fetch Integrators rate in TM via an API call to Redwood and leverage it for carrier selection and charge calculation. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA8E15C19-F04F-4FC5-B53C-92F05F08B776%7D&file=R3%20PTP%20L3%20-%20030-060%20%20Integrator%20interface%20-Rate%20Integrators%20with%20Redwood.pptx&wdLOR=cC3781B9E-FD79-4F33-9CE5-D4E8A7F1AB55&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 56974 | Redwood | ECD | S/4 | APIGEE | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-09 | 2025-05-16 | 2025-09-26 | 100% | 2025-09-24 | 2025-05-09 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-06-09 | 2025-06-27 | 2025-06-27 | 100% | 2025-06-27 | 2025-06-16 | 2025-05-30 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-21 | 2025-08-15 | 2025-08-15 | 100% | 2025-08-15 | 2025-07-21 | 2025-08-15 | No |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-30 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-08-06 08:30 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-21 | 01.S4 | LOGI0516_IP | 03.Medium | 0.3 | 0.435 | 0516 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-09-24 | 2025-09-26 | 2025-09-24 |  |  | 2025-06-27 |  | 2025-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-07-21 | 2025-08-15 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-08-01 | MW | 2025-06-27 | TM |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1540 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | EP: 09/11: ETC 09/12 per Jeet | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1745 | LOGI0503_IP | 02.Interface | 01.IP - Intel Product | Outboundinterface GR data send to NIT as WIINGS gets replaced by S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBF8FB03F-2561-46BC-8180-10F69B7C44D3%7D&file=1745_PTP-LE-%20RICEFW%20intake%20form%20for%20GR%20information%20from%20S4%20to%20NIT.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 1130 | Non Inventory Tracking | S/4 | NIT | MULESOFT | 2025-02-17 | 2025-04-18 | 2025-04-14 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-11 | 2025-07-18 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-30 | 2025-05-02 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-30 | 2025-03-24 | 2025-04-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-06-09 | 2025-06-30 | 2025-06-20 | 100% | 2025-07-21 | 2025-01-29 | 2025-08-31 | 2025-08-31 | 100% | 2025-08-31 | 2025-07-21 | 2025-08-31 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-30 | 2025-08-31 | 2025-08-31 | vasamohan@deloitte.com | 2024-08-02 09:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1.45 | 0503 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-30 | 2025-06-11 | 2025-05-30 | 2025-05-30 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-31 | 2025-08-31 | 2025-08-31 | 2025-07-21 | 2025-08-31 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | WIINGS | 2025-04-18 | 2025-05-16 | 2025-04-18 |  | 2025-10-08 |  |  |  | 1 | 08. Not Applicable | 1983 | [7 empty] | 3. Off Track | 17. FUT In progress |  | 2025-08-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-06-11 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1745 | LOGI0503_IF | 02.Interface | 02.IF - Intel Foundry | Outboundinterface GR data send to NIT as WIINGS gets replaced by S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBF8FB03F-2561-46BC-8180-10F69B7C44D3%7D&file=1745_PTP-LE-%20RICEFW%20intake%20form%20for%20GR%20information%20from%20S4%20to%20NIT.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 1130 | Non Inventory Tracking | S/4 | NIT | MULESOFT | 2025-02-17 | 2025-04-18 | 2025-04-14 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-11 | 2025-07-18 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-30 | 2025-05-02 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-30 | 2025-03-24 | 2025-04-18 | 2025-07-18 | 100% | 2025-07-18 | 2025-06-09 | 2025-06-30 | 2025-06-20 | 100% | 2025-07-21 | 2025-01-29 | 2025-08-31 | 2025-08-31 | 100% | 2025-08-31 | 2025-07-21 | 2025-08-31 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-30 | 2025-08-31 | 2025-08-31 | jenoronha@deloitte.com | 2025-02-27 05:57 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-08-12 | 01.S4 | LOGI0503_IP | 03.Medium | 0.3 | 0.435 | 0503 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-30 | 2025-06-11 | 2025-05-30 | 2025-05-30 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-31 | 2025-08-31 | 2025-08-31 | 2025-07-21 | 2025-08-31 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | WIINGS | 2025-04-18 | 2025-05-16 | 2025-04-18 |  | 2025-10-08 |  | WIINGS Only | TRUE | 1 | 08. Not Applicable | 1982 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2025-08-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-06-11 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1754 | LOGI0502 | 02.Interface | 01.IP - Intel Product | Inbound Interface to receive and process 4B2 Goods receipt signal from 3PL to S/4 via OpenText | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://secure-web.cisco.com/1vCf3DmjV1qFx38G7Q8dNmJaCn6bz4_OyKm4bHXl1QEsTopIRpjlQ6kX8X99acw657L_KxfG9xvx3uHGs6aFB7tVI-1pb9PVLuHYVB553fgxEujS7qhhSm8g7dzNSLwRlDS1bmVy2nsEmziJTR3qUXYuaEimWYMbTHdCebxCb72JFiH9WJCeYAt_UJhXkbTwWbtdQeRcIHTWldklfrkGbHO6UzYVrMhS5lLbVTi3D5c3t95pspODsW5zbOk1GaVYdIV2pVNErJ15CfHduqypV2MsGXHim-bJiVaT-KmhZ0a9j3wnecyuMtsWMn7bbL-7dQ7N9JIb11NxaYaaYvoC4dsXP2hxw7hffpTi2osUhQXpQ0o9XLDegDRbSB2iBpbAthrkVc7vf8M0xu3KXEQQsNOx9YHJPQPflPJAW13S0jZHett3tYU8J-gVVClqk5UmWWyc6k5GBHDJMPmlxetmlpuHd06pK0MCWsjJ5VeSAcE9ILVnfIiEwbz5b37oHj4Aasib4oiNAsIvOWSSrWUNe0Q/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2F1754_PTP-LE-RICEFW%2520intake%2520form%2520of%2520GR%2520signals%2520from%2520GXO%2520to%2520S4%2520New%2520Consoles.pptx%3Fd%3Dw40670d2f54144b3a88eb841450ae64b8%26csf%3D1%26web%3D1%26e%3DtnEnLp | 02.No | 01.Yes |  | 2024-08-02 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | E2Open | S/4 | MULESOFT | 2025-01-27 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-11 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-21 | 2025-06-16 | 2025-06-16 | 100% | 2025-06-16 | 2025-08-04 | 2025-08-04 |  | 2025-10-17 | 2025-10-30 | 2026-01-23 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-02 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-06-16 | 2025-06-16 | vasamohan@deloitte.com | 2024-08-02 09:51 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1.45 | 0502 | INT-CR0297 | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-11 | 2025-03-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-08-04 | 2025-08-04 |  |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  |  |  |  | B2B - OpenText | 2025-03-07 | 2025-04-18 | 2025-04-18 | MW | 2025-05-23 |  | WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 2130 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02 - Conditional Approval received from Intel IT Team. 01/30- FUT send for approval, addressed all comments, Awaiting Approval/Feedback 01/19 - Defect# 6284 is resolved. New Defect# 6420 is raised, ETA from tech is 01/19. This is blocking retesting of 3 TCs. Once Defect is resolved, retesting will be completed and submitted for review 01/05 - All comments addressed, One new TC added and in progress, ETA 01/06 12/22 - FUT sent for Review and Approval, will be discussed in today's WS call with GFM Team 12/15 - E2E FUT is in progress, 21 out of 23 TCs are completed. Non blocker Defect# 5620 & 5592 raised, Awaiting ETA from Tech 12/08 - 18 TCs are completed out of 25 for S/4 FUT. Defect# 5336 is still open, blocking 2 TCs. Defect# 5342 is newly raised, it is blocking E2E (25 TC) FUT as S/4 is returning status 400 on API call from OpenText via MuleSoft. 12/01: Open text has mapping issues and being fixed. S/4 open defect. Delay due to internal CR (change in API structure in align with new mapping) 11/24: Defect 4759 is open with Dev ETA was 11/21. Siddhartha is following up with the Dev. Planning to complete the FUT 12/3 if the FUT is started 11/24. 11/14 - Checked the revised API Payload shared by Tech, it's not matching as per updated mapping sheet of CR0345. Aligned with Jashan, it will be fixed by Defect Team, Defect# 3908 is raised for the same, Awaiting ETA from Tech 11/13 EP: Provide revised FUT end date 11/11 - Awaiting revised Payload from Tech for validating the changes for CR0345. Defect# 1146 for CR0345 is alreay completed by Tech (confirmed by Jashan), Tech to share the revised API Payload that is to be used post CR0345 fix. 11/04 EP: Defect# 1146 for CR0345 is not fixed, FUT is blocked because of this. Awaiting alignment on when CR can be delivered by Tech. Imran Update: FUT to complete early S21, end date pending from Tech Team 10/17 - Defect#3807, 3810 | 2025-06-16 | N | 99. Logistics |  |  |  |  | 12/02 - Defects at Open Text and S4 end. Risk for S20 completion |  |  | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1755 | LOGI0501 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive ASN (3B2) from fab material suppliers via E2Open to S4 IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://secure-web.cisco.com/1lGHKjvP1DGa3-4cgqqHCT9WCYLiHs5jOWcTR9pZ6ZJoNL1MHrVxea2svhyfpcJkyAxxXkMQkcW6HfMysk2bjnhBh3ze5VmXZzb8QHB0cVupmGfSAxkNCdBO4cOoKdYOFxktPs19HhtPxW1P_hFG-ILqcp_uWemO-Qe9v2_KA9usO_ROI8UVlzI-IiAoML9HNOSIJ6Wy8sXU0Wq0LND3NWrbM3VMVEKSNXIkQQa7FoIkhHKH-ZPGOZfteWGOfCRxNew9L9EDgm4VpWc6s-MXdAnGudUcwO-kzwZOQq9ZqyhSGmfHrOFIjim7mwQA2BjFZ78WKfCekLVNdoUxdi-yE_ZfI1_9q6i-6p8IzAGBOlXyz1x6KvQeXl6sD6Mw3RcaLgD8VSZP3sVog1lZaZZbhcCGfE7RV5TsyfKA4ushV2-cPWr4-xQBrefq9obh5RuAsTobCmHMT4Q6RKPEOHdLr4cNxkUfHez05wR4a2XK6_r66BSsbIX1qTO7HBnmLfJpFqK_kfNqqjqLT98-ntlpLdw/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2F1755_PTP-LE-RICEFW%2520intake%2520form%2520for%2520ASN%2520sending%2520from%2520supplier%2520to%2520S4%2520to%2520GXO.pptx%3Fd%3Dwcd8fb67f7ab34e768758c2a7cee8e426%26csf%3D1%26web%3D1%26e%3DWMBP7A | 02.No | 01.Yes |  | 2024-08-02 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-27 | 2025-03-07 | 2025-03-06 | 100% | 2025-03-12 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-18 | 2025-08-21 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-04 | 2025-08-21 |  | 2025-08-13 | 2025-09-10 | 2025-09-19 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-08-21 | 2025-08-21 | vasamohan@deloitte.com | 2024-08-02 09:51 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-08-12 | 01.S4 |  |  | 2 | 2.9 | 0501 | INT-CR0508 | R3 ITC1 | [6 empty] | 2025-03-12 | 2025-03-12 | 2025-03-12 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-05-16 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-04 | 2025-08-21 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  |  |  |  | B2B - E2open | 2025-03-07 | 2025-05-16 | 2025-05-16 | MW | 2025-06-27 |  | WIINGS Only | TRUE | 1 | 01.4 Suppliers that engage with E2Open | 2131 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/03- Awaiting supplier extension to EI1 250 system from MDG team 09/29- Testing in Progress with E2OPEN, ETA 09/30 09/26- Received 5 new Test cases from GFM team, Testing in progress with E2OPEN 09/22- Awaiting approval | 2025-08-21 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-04-18 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1388 | LOGI0418 | 02.Interface | 01.IP - Intel Product | 3B12 Request to 3PL on FO creation | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LOGITICS_LO-180-080_3B12%20Request%20to%203PL%20on%20FO%20creation_RICEFW%20Intake%20Form.pptx?d=wf1c20876cc05485599fbad23232f5ac8&csf=1&web=1&e=D3s63o | 02.No | 01.Yes |  | 2024-06-26 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | 3PL | S/4 | MULESOFT | 2024-07-12 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-08 | 2024-11-15 | 2025-02-21 | 100% | 2025-02-07 | 2025-03-03 | 2025-03-21 | 2025-02-28 | 100% | 2025-02-09 | 2025-03-03 | 2025-03-21 | 2025-02-28 | 100% | 2025-03-07 | 2024-12-16 | 2025-01-16 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-05-05 | 2025-04-16 | 2025-04-21 | 2025-04-21 | 100% | 2025-04-21 | 2025-05-05 | 2025-05-05 |  | 2025-08-13 | 2025-11-14 | 2025-11-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-21 | 2025-11-21 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-04-21 | 2025-04-21 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0418 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-09 | 2025-03-21 | 2025-02-09 | 2025-03-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-05-05 | 2025-05-05 |  |  | 2025-11-26 | 2025-11-26 | 2025-11-26 |  |  |  |  | B2B - OpenText | 2024-09-20 | 2025-03-21 | 2025-01-16 | MW | 2025-05-16 |  |  |  | 1 | 03. IP Customers | 2485 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24: FUT completion ETA 11/26. New test data to be validated with OT team. 11/18: FUT in progress. defect 4641 with dev team. 11/14: FUT under Intel Approval, call scheduled on 11/18 for FUT review 10/10: E2E FUT in progress, dependent on Port setup by tech team 10/09 ETA for approval/is this object approved? 10/06: E2E FUT in progress, ETA is 10/08 for completion 10/03: EP: No Ext FUT – Is Defect 3140 resolved? If not please update FUT comment 09/29: Defect 3140 is still open with tech team, ETA 09/29 09/26: Delay due to defects. Defect 3140 open with Tech team. ETA 09/29. 09/12: Delay due to defects. FUT in progress. ETA 09/18 09/08: Defect#2827, currently with tech team and awaiting fix | 2025-04-21 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 13 |  | 2025-03-21 | 2025-03-07 | Yes | ZTOTC_DH table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1440 | LOGI0415 | 02.Interface | 01.IP - Intel Product | 3B14C Cancellation Confirmation from 3PL to S/4 | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LOGITICS_LO-180-170_3B14%20Cancellation%20Confirmation%20from%203PL_RICEFW%20Intake%20Form.pptx?d=w332cb14e45b04e61875bd82e677f5df3&csf=1&web=1&e=Anr3D5 | 02.No | 01.Yes |  | 2024-06-26 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | 3PL | S/4 | MULESOFT | 2024-07-12 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-11-29 | 2024-12-06 | 2025-01-24 | 100% | 2025-01-17 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-16 | 2025-04-30 | 2025-04-30 | 100% | 2025-04-30 | 2025-03-21 | 2025-04-30 |  |  | 2025-11-14 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-11-21 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-02-21 | 2025-04-30 | 2025-04-30 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0415 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-17 | 2025-01-24 | 2025-01-17 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-03-21 | 2025-04-30 |  |  | 2025-11-18 | 2025-12-05 | 2025-11-18 |  |  |  |  | B2B - OpenText | 2024-08-30 | 2025-01-31 | 2025-01-24 | MW | 2025-03-28 |  |  |  | 1 | 03. IP Customers | 2488 | [7 empty] | 4. Completed |  |  | 2025-04-30 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-01-31 | 2025-01-07 | Yes | ZTOTC_PARAMS table impact | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 702 | LOGI0335 | 02.Interface | 01.IP - Intel Product | Outbound PIP signal to 3PL for material document transfer – EDI 4C1 | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-050_Interface%20-%2020_%20RICEFW%20Intake%20form.pptx?d=wc31e3cf4b3f34f3595268190ecf61975&csf=1&web=1&e=vYFiNH | 02.No | 02.No |  | 2024-06-14 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | S/4 | OpenText | MULESOFT | 2024-06-17 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-12 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-11-18 | 2024-12-13 | 2025-01-10 | 100% | 2025-01-17 | 2024-11-18 | 2024-12-13 | 2025-01-10 | 100% | 2025-01-17 | 2024-11-08 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-15 | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-16 | 2025-04-16 | 2025-04-22 | 2025-04-22 | 100% | 2025-04-22 | 2025-01-17 | 2025-04-22 |  | 2025-03-14 | 2025-03-07 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-13 | 2025-04-22 | 2025-04-22 | pgaroo@deloitte.com | 2024-06-14 00:11 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0335 |  | R3 ITC1 | [6 empty] | 2024-07-12 | 2024-07-12 | 2024-07-12 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2025-01-17 | 2025-01-17 | 2025-01-17 | 2025-01-17 |  | 2024-11-15 |  | 2024-11-15 |  | 2024-12-16 | 2024-12-16 | 2024-12-16 |  | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-01-17 | 2025-04-22 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  |  |  | B2B - OpenText | 2024-07-12 | 2024-12-13 | 2024-11-15 | S4 | 2025-02-21 |  |  |  | 1 | 08. Not Applicable | 2575 | [9 empty] | S4 FUT is completed in S15. Delayed due to Open text readiness. Currently FUT in progress in S16 | 2025-04-22 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-01-17 | 2025-01-17 | Yes | Param table entry addition. | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 582 | LOGI0267 | 02.Interface | 01.IP - Intel Product | Inbound Interface to receive Advanced Shipment Notice (ASN) data in txt file format, Custom Flatfile for Intel Foundary Customer Orders | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-160-0004_Receive_ASN_In_TXT_Flat_File_Intel_Products.pptx?d=w35d92733beba4537b12cbddf50613d13&csf=1&web=1&e=eFV3jp | 02.No | 01.Yes |  | 2024-05-24 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | GXS | S/4 | MULESOFT | 2024-12-02 | 2025-02-21 | 2024-07-26 | 100% | 2025-01-10 | 2025-02-07 | 2025-02-14 | 2025-05-30 | 100% | 2025-05-20 | 2025-02-28 | 2025-03-21 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-06-06 | 100% | 2025-06-06 | 2025-05-19 | 2025-06-13 | 2025-04-25 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-06-13 | 100% | 2025-06-13 | 2025-08-04 | 2025-08-04 |  | 2025-12-12 | 2026-02-20 | 2026-02-20 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-03-06 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0267 | INT-CR0168 | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-02-21 | 2025-01-10 |  | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-06 |  | 2025-06-06 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-08-04 | 2025-08-04 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 |  |  |  |  | B2B - OpenText | 2024-12-20 | 2025-03-21 | 2025-03-21 | S4 | 2025-04-25 |  |  |  | 1 |  | 2053 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/20- Defect#7438, 7466(Primary Qty, Primary UoM field change in Payload) still working with Mulesoft Team and Tech team, ETA- 02/20. Working on comments from Intel DM team, Will send the updated document, Tech ETA- 02/23 02/16- Received further comments from Intel DM team, Will send the updated document, ETA- 02/17 02/12- Delayed. 2 TC need to be tested. Open text team in noit able make the required changes(From DUNS field from uppercase to lower case) by Next week. 01/05 - There is an internal CR within Mulesoft team CR#0808 for updating the DUNS number in E2OPEN, Testing will be started post CR completion, Call is scheduled with Mulesoft team for ETA. 12/22 - 14 TCs completed out of 17 for S/4 FUT. Defect# 5762 is reopened, 3 TCs are blocked because of this Defect. E2E FUT is started from today (12/22) 12/15 - 4 TCs completed out of 17 for S/4 FUT. Defect# 5603 is raised, blocking rest all TCs. Bapp-Open Text | 2025-06-13 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11 : FUT Review comments under progress. Will be resent for approval by 02/12 |  | 5. Review Closed | E2O | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_PARAMS | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-03 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 583 | LOGI0253 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Finished Goods Advanced Shipping notifications from ODM suppliers via E2Open boundary application to S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-160-0005_Receive_FG_ASN_From_ODM_Intel_Products.pptx?d=w7295b2f393e34d998b70bd56c32ff091&csf=1&web=1&e=5Ierbs | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-07-08 | 2024-07-26 | 2024-07-26 | 100% | 2024-09-05 | 2024-11-18 | 2024-12-13 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-07 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-07 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-07 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-15 | 2025-03-21 | 2025-09-15 |  | 2025-07-11 | 2025-08-11 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0253 |  | R3 ITC1 | [6 empty] | 2024-09-05 | 2024-09-05 | 2024-09-05 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-21 | 2025-02-21 |  |  |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-09-26 | 2025-09-15 | 2025-09-15 | 2025-03-21 | 2025-09-15 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 |  |  |  |  | B2B - E2open | 2024-07-26 | 2025-02-21 | 2025-01-24 |  | 2025-09-10 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2054 | [9 empty] | 09/12- Received IT approval, Mail sent to Kalyan for PS/Business approval | 2025-09-26 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-02-21 | 2025-02-21 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_ROUTING & ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 587 | LOGI0252 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive “Goods Receipt” (4B2) signal for Raw Materials/FG Components/Rework Materials from BOX CPU subcontractors via E2Open to S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-030-0002_Receive_GR_4B2_For_FHS_From_3PL_Intel_Products.pptx?d=w4426a5bf77d049088be7ce72922bec9f&csf=1&web=1&e=TVadqu | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | OpenText | S/4 | MULESOFT | 2024-08-02 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2024-11-08 | 2024-11-15 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-03 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-03 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2024-12-16 | 2025-01-16 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-03-10 | 2025-06-20 | 2025-06-20 | 100% | 2025-06-20 | 2025-03-19 | 2025-06-20 |  | 2025-06-02 | 2025-08-04 | 2025-08-01 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-03-28 | 2025-07-18 | 2025-08-01 | N | 100% | 2025-08-08 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-06-20 | 2025-06-20 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0252 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-03-19 | 2025-06-20 |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  |  |  |  | B2B - E2open | 2024-09-02 | 2025-02-21 | 2025-01-16 | MW | 2025-05-16 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2415 | [7 empty] | 2. At Risk | 13. Blocked by Other RICEFW | 8/4- Awaiting approval FUT is submitted. Awaiting Intel Approvals. | 2025-06-20 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-02-21 | 2025-02-21 | Yes |  | No |  | No |  |  |  | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 593 | LOGI0249 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Realtime consumption (4B3) of raw materials/FG Components from BOX CPU subcontractors via E2Open to S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-050-0001_Receive_4B2_For_RM_Consumption_From_Box_CPU_Intel_Products.pptx?d=wb7116e608c74495c9d86ae7c949be042&csf=1&web=1&e=F4TH1Z | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | OpenText | S/4 | MULESOFT | 2024-09-02 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-21 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-07 | 2025-02-21 | 2025-05-23 | 100% | 2025-05-24 | 2025-02-07 | 2025-02-21 | 2025-05-23 | 100% | 2025-05-24 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-05-05 | 2025-06-13 | 2025-08-28 | 2025-08-28 | 100% | 2025-09-01 | 2025-05-24 | 2025-09-01 |  | 2025-06-11 | 2025-09-19 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-09-25 | 2025-09-26 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-08-28 | 2025-08-28 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0249 |  | R3 ITC1 | [6 empty] | 2024-11-21 | 2024-11-21 | 2024-11-21 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-05-24 | 2025-09-01 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  |  |  |  | B2B - E2open | 2024-10-18 | 2025-02-21 | 2025-01-24 | S4 | 2025-04-18 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2778 | [9 empty] | 10/03- Received new comments, Working to address the comments. 3 scenario need to be retested 09/29- Addressed all DM review comments received till date; Awaiting approval form Intel 09/26- Defect #3298 changes implemented by tech team today afternoon, Need to validate and re-test 1 TC, ETA: 9/26 8/4- At Risk:5. S/4 FUT Completed. E2Open planned FUT start date for the same is 8/25 8/1- At Risk:5. S/4 FUT Completed. E2Open planned FUT start date for the same is 8/25 The FUT is delayed because of E2Open readiness. E2Open will be ready for E2E testing on August 25th, S4 FUT is complete | 2025-08-28 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 595 | LOGI0245 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Finished Goods ASN (3B2) from BOX CPU subcontractors via E2Open to S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-060-0003_Send_ASN_3B2_After_Manufacturing_Intel_Products.pptx?d=wdbf9c932a3354e11bee249eb93734fa1&csf=1&web=1&e=IIN1FT | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | OpenText | S/4 | MULESOFT | 2024-08-02 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-07 | 2025-02-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-02-07 | 2025-02-21 | 2025-05-02 | 100% | 2025-08-04 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-07 | 2025-08-28 | 2025-08-28 | 100% | 2025-09-01 | 2025-08-04 | 2025-09-01 |  | 2025-06-11 | 2025-09-19 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-08-28 | 2025-08-28 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0245 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-18 | 2025-03-21 | 2025-03-21 |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-08-04 | 2025-09-01 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  |  |  |  | B2B - E2open | 2024-09-02 | 2025-02-21 | 2025-01-24 |  | 2025-09-26 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2779 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/03- Review comments addressed, Will send the update FUT by 10/06 09/29- Testing in progress with E2OPEN for additional test cases, ETA- 01/10 8/4- S/4 FUT in-progress, Out of 19 TCs, 10 TCs blocked due to S/4 defects 1817, 1942, 17 TCS are yet to be executed The FUT is delayed because of E2Open readiness. E2Open will be ready for E2E testing on August 25th. S4 FUT to be completed on August 8th. Initial delay was due to batch split CR development. 8/1- S/4 FUT in-progress, Out of 19 TCs, 10 TCs blocked due to S/4 defects 1837, 19 TCS are yet to be executed The FUT is delayed because of E2Open readiness. E2Open will be ready for E2E testing on August 25th. S4 FUT to be completed on August 8th. Initial delay was due to batch split CR development. | 2025-08-28 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | Yes |  | No |  | No |  |  |  | Yes |  | 2026-02-20 | 2026-03-06 | 2026-03-06 | 100% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-23 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 599 | LOGI0244 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive ODM Finished Goods “Goods Receipt” (4B2) signal sent by 3PL warehouses via Open Text and post in S4 IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-060-0007_Receive_GR_For_ODM_FG_From_3PL_Intel_Products.pptx?d=wa346cc39c3e74aef970ca7a38fc003ca&csf=1&web=1&e=sFIrDa | 02.No | 01.Yes |  | 2024-05-22 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | GSX | S/4 | MULESOFT | 2025-01-06 | 2025-01-24 | 2024-09-02 | 100% | 2024-12-13 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-17 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-25 | 2025-05-02 | 2025-05-17 | 2025-05-17 | 100% | 2025-05-17 | 2025-08-04 | 2025-08-04 |  | 2025-10-17 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-18 | 2025-05-17 | 2025-05-17 | pgaroo@deloitte.com | 2024-05-21 03:17 | cell-link@smartsheet.com | 2026-04-05 23:16 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0244 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-24 | 2024-12-13 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 |  | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-08-04 | 2025-08-04 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | B2B - OpenText | 2025-01-24 | 2025-03-21 | 2025-01-24 | S4 | 2025-04-25 |  |  |  | 1 | 04.6 Logistics - GLO | 2780 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/01: Business approval pending. No open items with Deloitte. Intel IT approval 11/24: FUT sent for approval on 11/11. Received one feedback on 11/21.Team is checking on this. 11/14 - 4522 & 4523 are resolved, New Defects# 4576 & 4577 are raised based on Review Comments, 4-5 TCs need to be retested with OpenText once Defects are reoslved ETA 11/18 11/13 - Review Comments are received, Defect# 4522 & 4523 are raised, 2 TCs need to be retested post resolution of the defects 11/13 EP: Confirm if FUT has been approved 11/11 - Documentation is completed for 12 TCs, remaining is in-progress. FUT will be sent for approval by EOD 11/11 11/04: 10/22 TC completed. Defect fix WIP 10/31: Defect 4064 under fix. 20 TC's to be executed in less than a week 10/24 - Defect 3905 with Tech team as payloads are not processing 10/17- E2E Testing is in-progress, Payloads not reaching mulesoft checking RCA 8/4- At Risk: S/4 FUT in-progress, Out of 22 TCs, 6 TCs are completed, 11 TCs blocked due to S/4 defects 1922, 1913, 16 TCs are yet to be executed Delayed due to batch split CR development. Handed over for testing on 07/24. Testing in progress 8/1- At Risk: S/4 FUT in-progress, Out of 22 TCs, 3 TCs are completed, 11 TCs blocked due to S/4 defects 1796, 1830, 1834(UOM,QTY), 19 TCs are yet to be executed Delayed due to batch split CR development. Handed over for testing on 07/24. Testing in progress. | 2025-05-17 | N | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-13 | 100% | Yes | 2026-03-13 | 2026-03-04 | 2026-04-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 608 | LOGI0237_IP | 02.Interface | 01.IP - Intel Product | Inventory Reconciliation snapshot (4C1) from 3PL WMS to SAP S/4 | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-030%20-%2010_%20Report_Interface_RICEFW%20Intake%20form.pptx?d=wa805d00e760d4db1a846630b9f93980d&csf=1&web=1&e=63rNpn | 02.No | 02.No | LOGE0239_IP | 2024-05-22 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12842 | OpenText | 3PL | S/4 | MULESOFT | 2024-06-10 | 2024-06-21 | 2024-06-21 | 100% | 2024-07-02 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-12-16 | 2025-01-24 | 2025-01-10 | 100% | 2025-01-03 | 2024-12-16 | 2025-01-24 | 2025-01-10 | 100% | 2025-01-03 | 2024-10-25 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2025-05-07 | 2025-05-21 | 2025-05-21 | 100% | 2025-05-21 | 2025-01-03 | 2025-05-21 |  | 2025-01-24 | 2025-01-17 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-02-17 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-01-24 | 2025-05-21 | 2025-05-21 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0237 |  | R3 ITC1 | [6 empty] | 2024-07-02 | 2024-07-02 | 2024-07-02 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2025-01-03 | 2025-01-24 | 2025-01-03 | 2025-01-03 |  | 2024-11-01 |  | 2024-11-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-01-03 | 2025-05-21 |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 |  |  |  |  | B2B - OpenText | 2024-06-21 | 2025-01-24 | 2024-11-01 | S4 | 2025-02-14 |  |  |  | 1 | 08. Not Applicable | 2309 | [9 empty] | 8/29: Auth. issue. Tech team working on raising SR for access 8/25: MuleSoft checking on the mapping error. 8/18: Defect 2213 in progress with Tech Team 8/14: Defect 2213 is with the tech team S4 FUT is completed in S15. Delayed due to Open text readiness. Currently FUT in progress in S16 | 2025-05-21 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-01-24 | 2025-01-03 | No |  | No |  | No |  |  |  | Yes |  | 2026-03-02 | 2026-03-31 | 2026-03-31 | 100% | Yes |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 608 | LOGI0237_IF | 02.Interface | 02.IF - Intel Foundry | Inventory Reconciliation snapshot (4C1) from 3PL WMS to SAP S/4 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-030%20-%2010_%20Report_Interface_RICEFW%20Intake%20form.pptx?d=wa805d00e760d4db1a846630b9f93980d&csf=1&web=1&e=63rNpn | 02.No | 02.No | LOGE0239_IF | 2024-05-22 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText | 3PL | S/4 | MULESOFT | 2024-06-10 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-28 | 2024-08-16 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-12-16 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-07 | 2024-10-25 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-01 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2025-05-19 | 2025-06-10 | 2025-06-10 | 100% | 2025-06-10 | 2025-01-07 | 2025-06-10 |  | 2025-01-24 | 2025-09-10 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-23 | Not Applicable | R3 Build & UT Sprint 18 | 2025-01-24 | 2025-06-10 | 2025-06-10 | pgaroo@deloitte.com | 2024-05-21 03:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | LOGI0237_IP | 02.High | 0.6 | 0.87 | 0237 |  | R3 ITC1 | [6 empty] | 2024-06-28 | 2024-06-28 | 2024-06-28 |  | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2025-01-07 | 2025-01-24 | 2025-01-07 | 2025-01-07 |  | 2024-11-01 |  | 2024-11-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-01-07 | 2025-06-10 |  |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  |  |  |  | B2B - OpenText | 2024-06-21 | 2025-01-24 | 2024-11-01 | S4 | 2025-02-14 |  |  |  | 1 | 04.7 Logistics - GFM | 2308 | [10 empty] | 2025-06-10 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-01-24 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 200 | LOGI0197_IP | 02.Interface | 01.IP - Intel Product | Create Inbound Delivery Note from ASN in IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/200_LI-120-080-0002_PTP_WebASN_B2B_Create%20IDN%20from%20ASN_IF.pptx?d=w6e184ec1df414d3c9bb65df61775018e&csf=1&web=1&e=dFgB66 | 01.Yes | 01.Yes |  | 2024-05-10 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 821; 24834 | Intel WebSuite - ASN; B2B Staging Database | WebASN | S/4 | MULESOFT | 2025-02-17 | 2025-05-05 | 2025-04-15 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-07-04 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-08-26 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-08-26 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-11 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-13 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-08-26 | 2025-10-31 |  | 2025-11-17 | 2025-11-27 | 2026-01-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-29 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-07-18 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-02-17 07:56 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0197 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-07-18 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-08-26 | 2025-10-31 |  |  | 2026-01-29 | 2026-01-30 | 2026-01-29 |  |  |  |  | B2B - Intel WebSuite | 2025-05-05 | 2025-06-13 | 2025-07-18 |  | 2026-01-30 |  |  |  | 1 | 01.10 Suppliers - WebSuite | 2816 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/19 - FUT approval is blocked as Intel IT is awaiting confirmation of validity of ATDM scenarios for this FUT which is already tested, Call scheduled with Stagging DB architect tomorrow to align on this. 01/05 - 12 TCs are completed out of 13 for E2E FUT. FUT is in-progress for rest of the TCs 12/22 - E2E FUT is in-progress. 2 TCs are completed out of 13. 12/15 - S/4 FUT completed. E2E FUT is blocked. POs have been shared for E2E FUT TCs, Web Suite team will validate the POs. Awaiting the Web Suite team for ASNs to be triggered, ETA 12/15 12/08 - S/4 FUT completed. E2E FUT is blocked as Web ASN records are not getting updated in correct Stored Procedure when ASN is submitted in Web Suited. Web Suite team is working on the same, Awaiting ETA from them 12/01 - S/4 FUT is completed. E2E FUT with Web Suite is blocked, due to multiple issues observed from BApp side, BApp team is working to fix the same. Awaiting ETA on the same. 11/25: FUT in progress. Master data issue resolved. 11/24:: Dependency with Master data team on material master creation. This is blocking 5 TC. Awaiting response from Master data team since 11/17. 4 follow up sent. Plan to complete the FUT 12/3. approval may spill over to next sprint. 11/18 - S/4 FUT has started, 1 out of 13 TCs are completed 11/14 - TCs are being drafted for E2E Testing ETA 11/14, FUT will start from Monday 11/17 | 2025-12-05 | Y | 99. Logistics |  |  |  | 0128: AR: Check the latest status |  | 3. Watch item |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-26 | 2025-08-26 | Yes | Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 200 | LOGI0197_IF | 02.Interface | 02.IF - Intel Foundry | Create Inbound Delivery Note from ASN in IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/200_LI-120-080-0002_PTP_WebASN_B2B_Create%20IDN%20from%20ASN_IF.pptx?d=w6e184ec1df414d3c9bb65df61775018e&csf=1&web=1&e=dFgB66 | 01.Yes | 01.Yes |  | 2024-05-10 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 821; 24834 | Intel WebSuite - ASN; B2B Staging Database | WebASN | S/4 | MULESOFT | 2025-02-17 | 2025-05-05 | 2025-04-15 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-07-04 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-08-26 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-08-26 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-11 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-13 | 2025-12-05 | 2025-12-05 | 100% | 2025-10-31 | 2025-08-26 | 2025-10-31 |  | 2025-11-14 | 2026-01-30 | 2026-01-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-12 | Sprint 22 Week 3 | R3 Build & UT Sprint 23 | 2025-07-18 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-05-10 02:45 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | LOGI0197_IP | 03.Medium | 0.3 | 0.435 | 0197 | INT-CR0297 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-07-18 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-05 | 2025-10-31 | 2025-10-31 | 2025-08-26 | 2025-10-31 |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 |  |  |  |  | B2B - Intel WebSuite | 2025-05-05 | 2025-06-13 | 2025-07-18 |  | 2026-01-30 |  |  |  | 1 | 01.10 Suppliers - WebSuite | 2815 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/09- Received DM IT and Business approval, Awaiting approval form GFM IT and Business(All comments addressed) 1/30 - Defect resloved, will be sent for approval by today EOD 01/19 - StaggingDB issue is now resolved and POs are reaching to StaggingDB. E2E FUT is in-progress. Defect# 6354 is still open which is blocking 8 TCs, E2E FUT is in-progress for rest of the TCs. 10 TCs are completed out of 22. 01/05 - 5 TCs are completed out of 22 for E2E FUT. FUT is in-progress for rest of the TCs 12/22 - Authorization issue while processing the payload in AIF, Working with Deloitte security on the same. Awaiting response from DT Security team 12/15 - S/4 FUT completed. E2E FUT is blocked. POs have been shared for E2E FUT TCs, Web Suite team will validate the POs. Awaiting the Web Suite team for ASNs to be triggered, ETA 12/15 12/08 - S/4 FUT completed. E2E FUT is blocked as Web ASN records are not getting updated in correct Stored Procedure when ASN is submitted in Web Suited. Web Suite team is working on the same, Awaiting ETA from them. 12/01 - S/4 FUT is in Progress, 20 TCs are completed out of 22 for S/4 FUT. Defect# 5080 is blocking rest of the TCs. E2E FUT with Web Suite is blocked, due to multiple issues observed from BApp side, BApp team is working to fix the same. Awaiting ETA on the same 24/11:Two defects 4865,4872 with Dev with ETA 11/21. 2/22 TCs are completed. 5/12 is ETC to send for intel review 12/3 11/18 - S/4 FUT has started, 1 out of 22 TCs are completed 11/14 - TCs are being drafted for E2E Testing ETA 11/14, FUT will start from Monday 11/17 | 2025-12-05 | N | 99. Logistics |  |  |  | 02/11 - Received DM approval. Awaiting IT, Biz and GFM approvals |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 497 | LOGI0163_IP | 02.Interface | 01.IP - Intel Product | Inbound interface to receive consignment inventory adjustments (manual postings) from ODMs suppliers from E2Open boundary app to S4 - IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 02.No |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-08-12 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-15 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-21 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-21 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-01-13 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-06-11 | 2025-07-16 | 2025-09-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-19 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0163 |  | R3 ITC1 | [6 empty] | 2024-10-15 | 2024-10-15 | 2024-10-15 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 |  |  |  |  | B2B - E2open | 2024-09-27 | 2025-02-21 | 2025-01-24 | S4 | 2025-05-02 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2009 | [9 empty] | 9.8- Review comments are addressed, CR will be raised for AIF & Document Date related changes which will be tested in later sprint. Awaiting Feedback/Approval 8/4- Sent for Approval 8/1- S/4 FUT Completed. FUT with E2Open is in-progress. Out of 34 TCs - 31 TCs are completed, 3 TCs are yet to be executed​ S4 FUT is completed. FUT with E2Open in progress. 2 defects identified with E2Open. | 2025-03-21 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-03-21 | Yes |  | No |  | No |  |  |  | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 602 | LOGI0163_IF | 02.Interface | 02.IF - Intel Foundry | Inbound interface to receive consignment inventory adjustments (manual postings) from ODMs suppliers from E2Open boundary app to S4 - IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-110-0005_Receive_Consignement_Inventory_Details_From_ODMs_Intel_Foundary.pptx?d=w01cd1f2bb74f43f2a559b6fb490f8f6e&csf=1&web=1&e=L1XDog | 02.No | 02.No |  | 2024-06-06 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-02 | 2025-02-07 | 2025-01-29 | 100% | 2025-02-07 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-04-11 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-17 | 2025-07-09 | 2025-07-09 | 100% | 2025-07-09 | 2025-08-04 | 2025-08-04 |  | 2025-07-16 | 2025-08-29 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-07-09 | 2025-07-09 | pgaroo@deloitte.com | 2024-06-05 23:12 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | LOGI0163_IP | 03.Medium | 0.3 | 0.435 | 0163 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-02-07 | 2025-02-07 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-12 | 2025-09-10 |  |  |  |  | B2B - E2open | 2025-01-24 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-30 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2303 | [10 empty] | 2025-07-09 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 495 | LOGI0161 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive ODM Finished Goods “Goods Receipt” (4B2) signal sent by 3PL warehouses and post in S4 IP. from E2Open Boundary application to S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-110-060-0004_Receive_GR_For_ODM_FG_From_3PL_Intel_Products.pptx?d=wb662bf00d06f44d3998f7beae2a07d28&csf=1&web=1&e=BxzpPn | 02.No | 02.No |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-08-02 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-21 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-21 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-12 | 2025-03-17 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-10 | 2025-03-21 | 2025-10-10 |  | 2025-06-11 | 2025-07-16 | 2025-09-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-04 | 2025-09-04 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-04-23 04:10 | cell-link@smartsheet.com | 2026-04-02 23:23 | 10 | 2024-10-23 | 01.S4 |  |  | 1 | 1.45 | 0161 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-12 | 2025-03-12 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-03-21 | 2025-10-10 |  |  | 2025-09-04 | 2025-09-04 | [5 empty] | B2B - E2open | 2024-09-02 | 2025-02-21 | 2025-01-24 |  | 2025-09-04 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2008 | [7 empty] | 5. Not Dispositioned |  | 8/4- At Risk: S/4 FUT Competed. FUT with E2Open has started. Out of 19 TCs, 14TCs are completed, 5 TCs are yet to be executed, 1 TC is blocked due to S/4 defect 1837 8/1- At Risk: S/4 FUT Competed. FUT with E2Open has started. Out of 19 TCs, 8 TCs are completed, 11 TCs are yet to be executed, 1 TC is blocked due to S/4 defect 1837 S4 FUT is completed. Delayed due to defects found during testing. All defects are currently resolved and testing is in progress with E2Open. | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-03-21 | 2025-03-21 | Yes |  | No |  | No |  |  |  | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-04-03 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 492 | LOGI0158 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive “Goods Receipt” (4B2) signal from OSATs for semi-finished goods. From E2Open boundary application to S4 - IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-01-28 | 100% | 2025-02-07 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-18 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-18 | 2025-10-09 | 2025-10-09 | 100% | 2025-11-07 | 2025-08-04 | 2025-11-07 |  |  | 2026-02-27 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-02-16 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-10-09 | 2025-10-09 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0158 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-08-04 | 2025-11-07 |  |  | 2026-02-16 | 2026-02-27 | 2026-02-16 |  |  |  |  | B2B - E2open | 2025-01-31 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-23 |  |  |  | 1 |  | 2007 | [7 empty] | 3. Off Track | 1. Approved no action | 02/16 - Approved 02/12- B2B and DM approved, awaiting approval from E2OPEN(Bhargav is on leave) , Awaiting busienss approval 01/05 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 01/06 12/22 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 12/22 12/15 - Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech | 2025-10-09 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11 : FUT sent for approval |  | 5. Review Closed | E2O | CR/Design change | Complete | R3 Build & UT Sprint 19 |  | 2025-08-04 | 2025-08-04 | Yes | Change in Custom Table entries for Plant Table - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 491 | LOGI0157_IP | 02.Interface | 01.IP - Intel Product | Inbound interface to receive raw materials “Goods Receipt” (4B2) signal for components sent by 3rd party vendors to ODM and post in S4 IP. from E2Open Boundary application to S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-08-02 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2024-11-08 | 2024-11-15 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-03-17 | 2025-08-23 | 2025-08-23 | 100% | 2025-08-23 | 2025-03-21 | 2025-08-23 |  | 2025-05-30 | 2025-08-05 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-13 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-08-23 | 2025-08-23 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0157 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-21 | 2025-02-21 |  |  |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-03-21 | 2025-08-23 |  |  | 2025-09-13 | 2025-09-13 | 2025-09-13 |  |  |  |  | B2B - E2open | 2024-09-02 | 2025-02-21 | 2025-01-24 | MW | 2025-04-18 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2006 | [9 empty] | 09/12- E2O FUT completed and sent for approval- IT approval received, awaiting business approval 8/4- S/4 FUT completed. FUT with E2Open has started, Execution is blocked currently as POs not reaching correctly to E2Open, dependency on resolution of CR0583 for PTPI0136 8/1- S/4 FUT completed. FUT with E2Open has started, Execution is blocked currently as POs not reaching correctly to E2Open, dependency on resolution of CR0583 for PTPI0136 S4 FUT is completed. E2Open testing is currently blocked due to master data issues. ETA for resolution is 07/28 | 2025-08-23 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-02-21 | 2025-02-21 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 588 | LOGI0157_IF | 02.Interface | 02.IF - Intel Foundry | Inbound interface to receive raw materials “Goods Receipt” (4B2) signal for components sent by 3rd party vendors to ODM and post in S4 IF. from E2Open Boundary application to S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-06-12 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2024-08-02 | 2024-09-30 | 2024-09-30 | 100% | 2024-09-05 | 2024-11-08 | 2024-11-15 | 2025-02-21 | 100% | 2025-02-07 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2024-12-16 | 2025-01-16 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-03 | 2025-08-11 | 2025-08-11 | 100% | 2025-08-11 | 2025-03-21 | 2025-08-11 |  | 2025-06-06 | 2025-09-08 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-03-21 | 2025-08-11 | 2025-08-11 | pgaroo@deloitte.com | 2024-06-12 03:45 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | LOGI0157_IP | 03.Medium | 0.3 | 0.435 | 0157 |  | R3 ITC1 | [6 empty] | 2024-09-05 | 2024-09-30 | 2024-09-05 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-02-21 | 2025-03-21 |  |  |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-03-21 | 2025-08-11 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  |  |  |  | B2B - E2open | 2024-09-30 | 2025-03-21 | 2025-01-16 | MW | 2025-05-16 |  |  |  | 1 |  | 1873 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22: IT approved, Biz approval pending 10/09- Addressed all comments, awaiting approval 10/03- Received comments for 4 test cases, WIP 09/29- New TC tested and Sent for approval, Awiating Feedback 09/26: Review comments received, 3 TCs need to be restested. Facing E2Open issue while retesting 09/22- Testing completed, documentation in progress, ETA 9/23 09/19- Testing completed, documentation in progress, ETA 9/23 09/12- 16 TC executed out of 31, Facing GL account issue, while executing the data in S/4 8/4- At Risk: S/4 FUT Complete, E2Open planned FUT start date for the same is 8/10 8/1- At Risk: S/4 FUT Complete, E2Open planned FUT start date for the same is 8/10 The FUT is delayed because of E2Open readiness. E2Open will be ready for E2E testing on August 8th, S4 FUT is complete | 2025-08-11 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-03-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 490 | LOGI0156 | 02.Interface | 01.IP - Intel Product | Outbound interface to send “Advanced Shipment Notification” signal (3B2) for incoming materials to OSAT suppliers – IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-11-11 | 2025-02-14 | 2024-08-07 | 100% | 2024-12-06 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-12 | 2025-04-04 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-25 | 100% | 2025-08-04 | 2025-06-09 | 2025-10-08 | 2025-10-08 | 100% | 2025-11-07 | 2025-08-04 | 2025-11-07 |  | 2025-07-16 | 2026-02-20 | 2026-02-20 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-16 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0156 | INT-CR0168 | R3 ITC1 | [6 empty] | 2024-12-06 | 2025-02-14 | 2024-12-06 |  | 2025-03-12 | 2025-03-21 | 2025-03-12 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-08-04 | 2025-11-07 | 2026-02-16 |  | 2026-02-16 | 2026-02-20 | 2026-02-16 |  |  |  |  | B2B - E2open | 2024-12-06 | 2025-04-18 | 2025-03-21 | S4 | 2025-06-20 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2005 | [7 empty] | 4. Completed | 1. Approved no action | 02/16- Approved 02/12- Approved by DM, Biz/PS approval, Awaiting B2B approval(Bhargav is on leave) 01/05 - E2OPEN is not able to receive PO from Mulesoft , PTP team is checking on this 12/22 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 12/23 12/15 - Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech | 2025-10-08 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11: E2E FUT completed and awaiting approval. |  | 5. Review Closed | E2O | CR/Design change | Complete | R3 Build & UT Sprint 19 |  | 2025-08-04 | 2025-08-04 | Yes | Change in Condition Records and Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 489 | LOGI0155 | 02.Interface | 01.IP - Intel Product | Inbound interface to receive Semi-Finished Goods Advanced Shipping notifications from OSAT suppliers from E2Open Boundary application to S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-01-30 | 100% | 2025-02-19 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-11 | 2025-02-24 | 2025-03-21 | 2025-05-16 | 100% | 2025-05-16 | 2025-05-19 | 2025-06-13 | 2025-05-09 | 100% | 2025-08-04 | 2025-07-08 | 2025-10-10 | 2025-10-10 | 100% | 2025-11-07 | 2025-08-04 | 2025-11-07 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-17 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0155 | INT-CR0168 | R3 ITC1 | [6 empty] | 2025-02-19 | 2025-02-21 | 2025-02-19 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-08-04 | 2025-11-07 |  |  | 2026-02-17 | 2026-02-20 | 2026-02-17 |  |  |  |  | B2B - E2open | 2025-01-31 | 2025-04-18 | 2025-03-21 | MW | 2025-06-23 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2004 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 02/16- B2B/DM Approved, Since Bhagav is not available it is aligned with Syed to send it to business approval, Sent for Business approval 02/12- 1 TC is in progress with E2OPEN, ETA- 02/13, PO release issue(Defect #7202) is there from PTP Procurement team 01/05 - Mulesoft is checking, "Ship from and Ship to field" is not comoing correctly in S4 12/22 - New Defect# 5847 is raised, Payloads are not reaching S/4 from MuleSoft once ASNs are submitted in E2Open. ETA from MuleSoft is 12/22. 12/15 - FUT is blocked. CR0856 changes are completed by Tech. Payloads are not getting processed correctly, fields are not getting updated correctly in OBD. Working Session is in-progress for TUT & fixing the identified issues. | 2025-10-10 | N | 99. Logistics |  |  |  | 0211 - Closing as per discussion with Jose 02/11: Review comments received, 2TC execution in progress. PO is not reaching E2O, due to connectivity issues between Mulesoft-AMQ-SFT |  | 5. Review Closed | E2O | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-04-18 | 2025-04-11 | Yes | Change in Custom Table entries for Plant Table - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 488 | LOGI0154 | 02.Interface | 02.IF - Intel Foundry | Inbound interface to receive Finished Goods Advanced Shipping notifications from OSAT suppliers from E2Open Boundary application to S4 | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-06 | 2025-02-21 | 2025-02-03 | 100% | 2025-02-11 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-14 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-06-03 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-06-03 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-06-09 | 2025-07-08 | 2025-10-10 | 2025-10-10 | 100% | 2025-11-07 | 2025-06-09 | 2025-11-07 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-10 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0154 | INT-CR0168 | R3 ITC1 | [6 empty] | 2025-02-11 | 2025-02-21 | 2025-02-11 |  | 2025-03-14 | 2025-03-21 | 2025-03-14 |  | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-06-13 | 2025-06-09 | 2025-06-09 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-06-09 | 2025-11-07 |  |  | 2026-02-10 | 2026-02-20 | 2026-02-10 |  |  |  |  | B2B - E2open | 2025-01-31 | 2025-04-18 | 2025-03-21 | MW | 2025-06-23 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 2003 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 01/05 - Testing in progress with E2OPEN 12/22 - New Defect# 5812 is raised, dump is coming while processing the payload in S/4. It blocking all of the TCs for E2E FUT. ETA from Tech is 12/22. 12/15 - FUT is blocked. CR0856 changes are completed by Tech. Payloads are not getting processed correctly, fields are not getting updated correctly in OBD. Working Session is in-progress for TUT & fixing the identified issues. | 2025-10-10 | N | 99. Logistics |  |  |  | 02/04: E2E FUT completed. Approval from DM team is received and waiting for B2B team approval |  | 3. Watch item | E2O | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-06-03 | 2025-06-03 | Yes | Change in Custom Table entries for Plant Table - ZTPTP_3B2_4B2 | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 481 | LOGI0150_IP | 02.Interface | 01.IP - Intel Product | Outbound interface to send “Goods Receipt” signal (4B2) for Raw materials & OSAT suppliers from S4 to E2Open boundary application – IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2024-08-02 | 2024-09-02 | 2024-09-02 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-03-21 | 100% | 2025-03-18 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-10 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-01-27 | 2025-01-31 | 2024-12-06 | 100% | 2024-12-06 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-01-21 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-01 | 2025-03-19 | 2025-09-01 |  | 2025-07-11 | 2025-09-19 | 2025-09-26 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-08-29 | 2025-08-29 | pgaroo@deloitte.com | 2024-04-23 04:10 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0150 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 |  | 2025-01-31 |  | 2024-12-06 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-03-19 | 2025-09-01 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  |  |  |  | B2B - E2open | 2024-09-02 | 2025-02-21 | 2025-01-31 | MW | 2025-06-20 |  |  |  | 1 | 01.4 Suppliers that engage with E2Open | 1964 | [7 empty] | 1. On Track | 7. FUT Defect Retesting | 10/10- IT Approval received, awaiting business approval 10/03- 3 TC tested out of 10, Defect resolved 09/29- Review comments received, defect#3379 raised for the changes logic where Gr should trigger at subcon PO for ODM , ETA 01/10 | 2025-08-29 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-02-21 | 2025-02-17 | Yes | Change in Condition Records and Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | Yes | Regression testing impact | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 482 | LOGI0150_IF | 02.Interface | 02.IF - Intel Foundry | Outbound Interface to send 4B2 Goods receipt acknowledgement from S/4 to E2Open – IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20RAICEFW%20Intake%20E2O%20Interfaces%204_22_2024.pdf?csf=1&web=1&e=zcUREy | 02.No | 01.Yes |  | 2024-04-23 | Cari H Shim | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2025-01-02 | 2025-02-21 | 2025-01-31 | 100% | 2025-02-07 | 2025-02-24 | 2025-02-28 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | 2025-01-27 | 2025-01-31 | 2024-12-06 | 100% | 2024-12-06 | 2025-03-24 | 2025-04-18 | 2025-03-14 | 100% | 2025-03-19 | 2025-05-10 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-12 | 2025-03-19 | 2025-09-12 |  | 2025-08-13 | 2025-09-09 | 2025-09-19 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-28 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-04-23 04:10 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 | LOGI0150_IP | 03.Medium | 0.3 | 0.435 | 0150 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-02-18 | 2025-03-21 | 2025-02-18 | 2025-02-18 |  | 2025-01-31 |  | 2024-12-06 |  | 2025-04-18 | 2025-03-19 | 2025-03-19 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-03-19 | 2025-09-12 |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 |  |  |  |  | B2B - E2open | 2025-01-24 | 2025-02-21 | 2025-01-31 | MW | 2025-06-20 |  | WIINGS Only | TRUE | 1 | 01.4 Suppliers that engage with E2Open | 1966 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Awaiting approval 10/09- Dependency on PTP RICEFW PTP0136, Customer no. from delivery address not flowing to E2OPEN as part of PO sharing. Can't proceed further without this completion 10/03- Dependency on PTP/OTC team for data creation 09/29- Awaiting new Test Data creation from MDG team to retest the 14 Scenarios for SIMS with E2Open 09/26- Awaiting new Test Data creation from MDG team to retest the 14 Scenarios for SIMS with E2Open 09/22- FUT Completed with E2OPEN Documentation in progress, ETA- 9/23 | 2025-09-12 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 3152 | LOGF1673 | 05.Form | 02.IF - Intel Foundry | Consolidated Export CI for Wafer Die (Ireland) | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCE53DCB9-4AAA-48D1-8C03-F157F0B4DDB7%7D&file=3152_R3_IF_OTC_Logistics_Ireland%20Specific%20Consolidated%20Export%20CI.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-12 | 2026-01-30 | 2026-01-30 | 100% | 2026-01-16 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-09 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-11-04 01:53 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 0.69 | 1673 | INT-CR1071 | R3 ITC1 | [6 empty] | 2026-01-16 | 2026-01-30 | 2026-01-16 | 2026-03-09 | 2026-03-09 | 2026-02-21 | 2026-02-21 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-02-21 | 2026-02-21 | [12 empty] | 2026-03-09 | 2026-03-09 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-01-30 | 2026-03-04 |  |  | 2026-03-06 |  |  |  | 1 |  | 3353 | [7 empty] | 4. Completed | 3. Awaiting Approval | 03/02: FUT sent for approval on 02/27. Defect #7922 created for the feedback points, awaiting tech ETA for the same 02/27: Defect#7759 is with tech. All 10 scnearios completed, once defect is fixed, form to be re-printed and FUT will be sent for approval 02/23: FUT started on 02/20, 5/10 TCs completed 02/16: Build is in progress, no ETA from tech 2/10: Build in progress | 2026-03-04 | Y | 99. Logistics |  |  |  | 03/04: TUT+FUT in progress. 7/10 test scenarios are completed. Current status: TUT+FUT in progress post Build Issue: N/A Next steps: Complete FUT and send for approval. Help needed: N/A FUT ETA: TBD" |  | 2. Risk | At risk for S23 | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3152 | LOGF1672 | 05.Form | 02.IF - Intel Foundry | Consolidated Export CI for Finished Goods (Ireland) | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCE53DCB9-4AAA-48D1-8C03-F157F0B4DDB7%7D&file=3152_R3_IF_OTC_Logistics_Ireland%20Specific%20Consolidated%20Export%20CI.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-12 | 2026-01-30 | 2026-01-30 | 100% | 2026-01-16 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | [15 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-02-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 01:53 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 0.69 | 1672 | INT-CR1071 | R3 ITC1 | [6 empty] | 2026-01-16 | 2026-01-30 | 2026-01-16 |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 2026-02-05 | 2026-02-06 | 2026-02-05 | 2026-02-05 | [12 empty] | 2026-02-05 | 2026-02-05 |  |  | 2026-02-27 | 2026-03-06 | 2026-02-27 | [5 empty] | 2026-01-30 | 2026-02-06 |  |  | 2026-03-06 |  |  |  | 1 |  | 3352 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/23: Sent for Intel Review on 02/20 02/16: Defect#7365 raised for FO with multiple deliveries, yet to be picked by tech 2/10: Defect#7147 under fix | 2026-02-06 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3105 | LOGF1632 | 05.Form | 01.IP - Intel Product | TM:Trigger order details/collection details email from a freight order to the customer based on customer preferred language after carrier confirms the booking request. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CB88867-151B-4CD8-B23B-0CF82628249B%7D&file=3105_R3_Returns_IP_Freight%20order%20output.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-10-27 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-01-07 | 100% | 2026-01-30 | 2026-01-12 | 2026-01-16 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-06 | 2026-03-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-09-28 03:35 | cell-link@smartsheet.com | 2026-03-16 11:50 | 10 | 2025-10-27 | 01.S4 |  |  | 1 | 0.69 | 1632 | INT-CR1014 | R3 ITC1 | [5 empty] | 2026-01-30 | 2026-01-30 | 2026-02-06 | 2026-01-30 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | [5 empty] | 2026-02-06 | 2026-03-04 |  |  | 2026-03-06 | TM |  |  | 1 |  | 3312 | [7 empty] | 2. At Risk | 19. Incomplete Build | 2/16: Build in progress. 2/12: Build in progress, FS walk through completed | 2026-03-04 | Y | 99. Logistics |  |  |  | 03/04: TUT+FUT in progress. 7/10 test scenarios are completed. Current status: TUT+FUT in progress post Build Issue: N/A Next steps: Complete FUT and send for approval. Help needed: N/A FUT ETA: TBD" |  |  | At risk for S23 | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3100 | LOGF1630 | 05.Form | 01.IP - Intel Product | COO Label - print a Country of Origin (COO) label for the outbound shipment of the returned items (after disposition is decided in EWM). | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/3100_R3_IP_OTC_COO%20Label%20for%20IP%20returns%20outbound.pptx?d=w06ce8f0b80704968b47b921d87a14c0c&csf=1&web=1&e=lmupDp | 02.No | 01.Yes |  | 2025-10-27 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-26 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-28 03:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-10-27 | 01.S4 |  |  | 1 | 0.69 | 1630 |  | R3 ITC1 | [6 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-11-05 | 2025-12-05 |  |  | 2026-03-06 |  |  |  | 1 |  | 3310 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/02: FUT sent for approval on 03/02 02/27:Defect#7610 is with tech, as it was partially fixed, no ETA 02/23: Defect# 7616 created today, yet to be picked up by tech 02/16: Defect#7230 is re-assigned to tech as it is partially fixed, no ETA 01/12: Awaiting tech build completion 01/05:Awaiting tech build completion. Only 5.1 planned in current sprint 12/22: Awaiting tech build completion, no ETA on the same. Only 5.1 planned in current sprint 12/15: Only 5.1 planned in the current sprint, 5.2 planned in future sprint. Tech build is still in progress | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: Development in progress. ETA by Tech is 0109. Will be picked up for FUT in S22 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3087 | LOGF1614_IP | 05.Form | 01.IP - Intel Product | TM-Bill of lading print output ( NSO/ Prospal STO's) | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3087_R3_FTS_IPIF-%20Bill%20of%20lading%20print%20output.pptx?d=w0b05903e9e3145e3ae9e4b188aa13366&csf=1&web=1&e=JedbdQ | 02.No | 01.Yes |  |  | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-03 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-19 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-22 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 0.69 | 1614 |  | R3 ITC1 | [6 empty] | 2025-10-03 | 2025-10-08 | 2025-10-03 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | [5 empty] | 2025-10-08 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 |  | 3261 | [7 empty] | 1. On Track | 17. FUT In progress | 01/19: Defect fix in progress. 01/12: Initial review complete, 2nd session scheduled for 1/13 for the final review of open points. Identified defect fix by dev team to be fixed 01/05: FUT to resume, test data creation & defect 5987 retest in progress 12/22: FUT in progress 12/15: FUT WIP, blocker defect 5513 | 2025-12-05 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3087 | LOGF1614_IF | 05.Form | 02.IF - Intel Foundry | TM-Bill of lading print output ( NSO/ Prospal STO's) | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3087_R3_FTS_IPIF-%20Bill%20of%20lading%20print%20output.pptx?d=w0b05903e9e3145e3ae9e4b188aa13366&csf=1&web=1&e=JedbdQ | 02.No | 01.Yes |  |  | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-03 | 2025-10-17 | 2025-10-24 | 2025-12-03 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-19 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-24 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-30 | 01.S4 | LOGF1614_IP | 03.Medium | 0.2 | 0.138 | 1614 |  | R3 ITC1 | [6 empty] | 2025-10-03 | 2025-10-08 | 2025-10-03 |  | 2025-11-13 | 2025-12-03 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-24 | 2026-01-24 | 2026-01-24 | [5 empty] | 2025-10-08 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 |  | 3262 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Updated documentation to be sent once BI1 system is up(BI1 system down since 01/21). High priority OSS raised with SAP to resolve system issue 01/19: Defect fix in progress. 01/05: FUT WIP, 7 of 8 TC completed target for Internal review 6th 12/22: FUT in progress 12/15: FUT WIP, blocker defect 5513 | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 689 | LOGF1583 | 05.Form | 01.IP - Intel Product | Consolidated Export Commercial Invoice – Finished Goods (IP) | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-11-10 | 2025-11-21 | 2025-11-21 | 100% | 2025-11-12 | 2025-10-17 | 2025-10-24 | 2025-12-11 | 100% | 2025-12-18 | 2025-12-08 | 2026-01-09 | 2025-12-19 | 100% | 2025-12-18 | 2025-12-08 | 2026-01-09 | 2025-12-19 | 100% | 2025-12-18 | [15 empty] | 2025-12-18 | 2025-12-18 |  |  | 2026-01-30 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-08 06:09 | cell-link@smartsheet.com | 2026-03-09 05:35 | 10 | 2025-08-08 | 01.S4 |  |  | 1 | 0.69 | 1583 |  | R3 ITC1 | [6 empty] | 2025-11-12 | 2025-11-21 | 2025-11-12 |  | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 2025-12-18 | 2026-01-09 | 2025-12-18 | 2025-12-18 | [12 empty] | 2025-12-18 | 2025-12-18 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2025-11-21 | 2026-01-09 |  |  | 2026-01-30 |  |  |  | 1 | 08. Not Applicable | 3218 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/19: Sent for Intel review on 01/16, FUT review call scheduled on 01/20. 01/12: Defect#5877 is fixed & retest is kept open till other defects are fixed, 6034 & 6094 is with tech ETA 01/12, 6143 is with tech, no ETA 01/05: Defect#5877 is with tech, no ETA on fix. 12/22:Defect#5543 will be closed today ,and testing further scenario is in progress ETA 01/05 1/9 TC has been executed due to field level issue. 15/15: Defect#5543 is with tech, no ETA on fix Development is still in progress. The FUT dates are to be corrected. | 2026-01-09 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2025-12-18 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3038 | LOGF1525 | 05.Form | 02.IF - Intel Foundry | Consolidated Commercial Invoice for WIP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B15EA7BEE-7836-46DE-8786-D565F2374F8C%7D&file=3038%20Commercial%20invoice%2C%20Consolidated%20commercial%20invoice%20and%20packing%20list%20for%20WIP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-25 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-14 07:37 | cell-link@smartsheet.com | 2026-03-03 23:54 | 10 | 2025-08-30 | 01.S4 |  |  | 0.5 | 0.345 | 1525 |  | R3 ITC1 | [6 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 1 |  | 3177 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 2/24: Addressing the walkthrough comments. ETA 24/2 2/20: Call to be scheduled with Taili on 2/23. Other open questions are responded. 2/16: Defect 7114 few points are still under fix. Awaiting ETA from tech team.. 2/9: Defect 6914 in progress. ETA: 2/9 EOD. 2/5: Defect 6432 and 6914 in progress. ETA: 2/5 EOD. 2/2: Defect has been fixed. Retest in progress. 1/29: Defect#6432 in progress with tech. 1/27: Defect in progress with tech 1/23: Defect in progress with tech. 1/22: Defect in progress. Delay in retest as BI1 system is down. 1/20: Tech working on defect#6377. 1/16: Carrier/service level/HAWB not getting updated on FO. Tech support required. 01/05: FUT started today. 12/22: FUT has not been started. 12/15: FUT has not been started , Validating with tech on the build status. | 2025-12-05 | N | 99. Logistics |  |  |  | 1210: Build is complete. 5.2 to be added to S21 plan |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3038 | LOGF1524 | 05.Form | 02.IF - Intel Foundry | Commercial Invoice for WIP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B15EA7BEE-7836-46DE-8786-D565F2374F8C%7D&file=3038%20Commercial%20invoice%2C%20Consolidated%20commercial%20invoice%20and%20packing%20list%20for%20WIP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-20 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-11-28 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-07 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-14 07:37 | sdeolalikar@deloitte.com | 2026-02-24 12:08 | 10 | 2025-08-30 | 01.S4 |  |  | 0.5 | 0.345 | 1524 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 1 |  | 3176 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/5: Sent for Intel Review on 2/4.. Call scheduled for today. Few comments to be addressed today. 2/2: Defect reopened 6731 for alignment changes. Checking with pricing team for correct logic. 1/29: Walkthrough completed and new defect raised for alignment related open issues. 1/27: Defect in progress with tech. ETA 1/27 1/23: Defect in progress with tech. ETA 1/27 for defect completion. 1/22: Defect in progress. Delay in retest as BI1 system is down. 1/20: Form print is working. Retest in progress 1/16: Form printing not working and tech is checking. 12/22: Defect 5796 is with tech team . TC 0/9 12/15: Defect 5579 yet to be started by tech team. TC 0/9 | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3038 | LOGF1523 | 05.Form | 02.IF - Intel Foundry | Packing list for WIP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B15EA7BEE-7836-46DE-8786-D565F2374F8C%7D&file=3038%20Commercial%20invoice%2C%20Consolidated%20commercial%20invoice%20and%20packing%20list%20for%20WIP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-20 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-14 07:37 | sdeolalikar@deloitte.com | 2026-02-24 12:08 | 10 | 2025-08-30 | 01.S4 |  |  | 0.5 | 0.345 | 1523 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 1 |  | 3175 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 1/5: Call has been scheduled for 2/5 for final walkthrough 12/22: Call scheduled 12/22 for review and approval 12/15: Based on the intel FUT feedback, defect 5310 (ETA 12/15) defect is with tech 12/8: Based on the intel feedback received some cosmetic changes as per alignment in the FDS. Tech is working on the defect 5031 and a walkthrough call scheduled for today with business. 12/1: Submitted for intel review. 11/24: Working TM team to complete the TM config. FUT ETA 11/27. 11/18: Defect 4603 is resolved testing in progress 11/14: S21 FUT | 2025-12-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2867 | LOGF1283 | 05.Form | 01.IP - Intel Product | Packing list form for IP returns (outbound) | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_OTC_Packing%20list%20form%20for%20IP%20returns%20outbound.pptx?d=w74e75d345d334612a3690ddd37275841&csf=1&web=1&e=poF77R |  |  |  | 2025-03-11 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-17 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-17 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-11 | 01.S4 |  |  | 1 | 0.69 | 1283 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-10-17 | 2025-10-17 | 2025-10-17 |  | 2025-10-17 | 2025-11-05 | 2025-10-17 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | [5 empty] | 2025-06-13 | 2025-10-31 |  |  | 2025-12-03 |  |  |  | 1 |  | 1640 | [7 empty] | 3. Off Track | 1. Approved no action | 12/22:Conditionally approved, Defects 5288,5517,5729 is fixed will be retested on 12/23 and responded to Intel for final approval 12/15: Defect#5288 is with tech, Defect#5213 awaiting alignment with GTS on trade logic, call scheduled on same for today. Defect#5517, hand over to be given to tech. Since these defects impact only 2 fields in form, requesting for conditional approval from Intel 12/08: Intel IT review in progress. Defect#5213 is reassigned to tech. Defect#5288 is with tech, ETA 12/08. (Related to Trade data and couple of formatting changes) 12/01: Defect#5010 & 5065 is fixed and retest in progress, ETA 12/01. Defect#5107 yet to be picked by tech 11/24: Defect#4836 is closed, defect#4878 is created, yet to be picked by tech. ETC to send for intel review 12/1 11/18: Defect 4616 with dev team | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2866 | LOGF1282 | 05.Form | 01.IP - Intel Product | Commercial invoice form for IP returns (outbound) | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_OTC_Commercial%20invoice%20form%20for%20IP%20returns%20outbound%20.pptx?d=w7716437b21cd4326a4ebc1efe6651194&csf=1&web=1&e=Dmh2tT |  |  |  | 2025-02-28 | Jorge Sanchez | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-02 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 0.69 | 1282 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-16 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | [5 empty] | 2025-07-18 | 2025-11-05 |  |  | 2025-12-03 |  |  |  | 1 |  | 1639 | [7 empty] | 3. Off Track | 1. Approved no action | 12/22:Conditionally approved ,Defects 5288,5517,5729 is fixed will be retested on 12/23 and responded to Intel for final approval 12/15: Defect#5288 is with tech, Defect#5213 awaiting alignment with GTS on trade logic, call scheduled on same for today. Defect#5517, hand over to be given to tech. Since these defects impact only 2 fields in form, requesting for conditional approval from Intel 12/08: Intel IT review in progress. Defect#5213 is reassigned to tech. Defect#5288 is with tech, ETA 12/08. (Related to Trade data and couple of formatting changes) 12/01: Defect#5010 & 5065 is fixed and retest in progress, ETA 12/01. Defect#5107 yet to be picked by tech 11/24: Defect#4600 is closed, defect#4836 is closed, FUT in progress. ETC to send for intel review 12/1 11/18: 4600 defect raised with Dev | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2827 | LOGF1258 | 05.Form | 01.IP - Intel Product | Commercial invoice form for returns logistics | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_OTC_Process%20CI%20forms%20for%20RTC%20inbound.pptx?d=waaff002f4fe34c39817e4cb6a0e1d112&csf=1&web=1&e=ubwPp7 | 02.No | 01.Yes |  | 2025-03-11 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-08-21 | 100% | 2025-11-27 | 2025-09-15 | 2025-09-19 | 2025-09-05 | 100% | 2025-11-27 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-11-27 | [15 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-10-24 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-22 | 2025-10-31 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-02-17 06:31 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-11 | 01.S4 |  |  | 2 | 1.38 | 1258 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | [12 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-04-25 | 2025-10-10 |  |  | 2025-10-22 |  |  |  | 1 |  | 1817 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 11/04: Defect#4169 is with tech, ETA 11/04, once fixed updated FUT document can be sent by 11/05 10/31: Sent for Intel review 10/22: TUT pending approval | 2025-10-10 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-11-27 | 2025-11-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2826 | LOGF1257 | 05.Form | 01.IP - Intel Product | Packing list form for Returns Logistics | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_OTC_Process%20PL%20forms%20for%20RTC%20inbound.pptx?d=wbc805e0e5f3e48f795b00686d0660b92&csf=1&web=1&e=xkbrWS | 02.No | 01.Yes |  | 2025-03-11 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-03-21 | 100% | 2025-04-04 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-11-27 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-11-27 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-11-27 | [15 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-06 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2025-02-17 06:31 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-11 | 01.S4 |  |  | 2 | 1.38 | 1257 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | [12 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-03-28 | 2025-10-03 |  |  | 2025-10-08 |  |  |  | 1 |  | 1460 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/31: Under Intel review 10/22: TUT is still not approved. FUT to be sent for offline review 10/10: TUT is not approved yet | 2025-10-03 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-27 | 2025-11-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2802 | LOGF1224 | 05.Form | 01.IP - Intel Product | Enhancement to create Scrapping form Document | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Scrapping_Document.pptx?d=wbcf2c30f58c54b71a3e132c49985744a&csf=1&web=1&e=FI8yrd | 02.No | 02.No |  | 2025-02-05 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-22 | 2025-10-29 | 2025-10-16 | 100% | 2025-11-03 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-19 | 01.S4 |  |  | 1 | 0.69 | 1224 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-03 | 2025-11-03 | 2025-11-03 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-12-05 | TM |  |  | 1 |  | 1721 | [7 empty] | 1. On Track | 1. Approved no action | 12/22: FUT Conditional Approval received from Business with few opens which are in discussion with tech team. 12/15: Defect #4349,4469 raised to fix the Intel review feedback. 12/08: FUT under Intel review. Tech is working on Defect #5197 is raised for Fiori Issues based on Intel Feedback. 12/01: FUT document has been sent for review and approval .Plan to walkthrough the FUT document in tomorrow's workshop call. 11/24:Defect #4469 is still with Dev. Defect is open since 6 days. 0/9 TCs completed so far. Need dev team utmost attention here. 11/18: Development is in progress. FUT is in roadblock, since Fiori app is not developed. Defect #4469 raised on tech 11/14:FUT is in roadblock, since Fiori app is not developed. Defect #4469 raised on tech | 2025-11-05 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2793 | LOGF1220 | 05.Form | 01.IP - Intel Product | Enhancement to generate Shipping labels | 05. OTC IP | 5.13 OTC IP - Returns (Logistics Management) | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Shipping%20label.pptx?d=w0fa7a4e971d14dd0bddecccf285e5755&csf=1&web=1&e=qaFgPW | 02.No | 02.No |  | 2025-02-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-01 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-08 | 01.S4 |  |  | 1 | 0.69 | 1220 |  | R3 ITC1 | [6 empty] | 2025-09-01 | 2025-09-01 | 2025-09-01 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 1 |  | 1714 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/05: FUT review call scheduled on 01/06 12/22:Sent for FUT approval on 12/19 12/15: Defect#5393 & 5431 is closed, FUT in progress, ETA for FUT completion 12/16, if no further issues 12/08: Defect#5141 is closed, FUT in progress, 5.2 is in S21. 12/01 Waiting on TM team to complete PPF action config for all FO types 11/24: Waiting on TM team to complete PPF action config for all FO types 11/18: Waiting on TM team to complete PPF action config for all FO types, reminder sent 11/17: Waiting on TM team to complete PPF action config for all FO types 11/14: Defect#4528 is closed 11/13: Defect#4528 raised for issue with form field 11/12: Will be started from 11/12 11/11: Will be started from 11/11 | 2025-12-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2792 | LOGF1219 | 05.Form | 08.EWM | Enhancement to create Physical inventory form | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Physical%20Inventory%20form.pptx?d=w756ea2cbc83947babac6fbb0bda8f99a&csf=1&web=1&e=njjG7W | 02.No | 02.No |  | 2025-02-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-01 | 2025-08-01 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-10-15 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-10-15 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-04 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-08 | 01.S4 |  |  | 1 | 0.69 | 1219 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-08-01 | 2025-07-21 |  | 2025-10-15 | 2025-10-17 | 2025-10-15 |  | 2025-10-15 | 2025-11-07 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-04 | 2025-11-07 | 2025-11-04 | [5 empty] | 2025-08-01 | 2025-11-07 |  |  | 2025-11-07 | TM |  |  | 1 |  | 1713 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/04: Reminder email sent to intel, Awaiting Approval 10/24 - Awaiting approval | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2788 | LOGF1216 | 05.Form | 08.EWM | Enhancement to generate picklist | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Picklist.pptx?d=wc5dc6cc994534b78813383df24fb0b41&csf=1&web=1&e=Ju9bbg | 02.No | 02.No |  | 2025-02-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-26 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-19 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-19 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-19 | [15 empty] | 2025-09-19 | 2025-09-19 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-06 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2025-02-03 06:19 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-02-08 | 01.S4 |  |  | 1 | 0.69 | 1216 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-19 | 2025-09-19 | 2025-09-19 |  | 2025-09-19 | 2025-10-03 | 2025-09-19 | 2025-09-19 | [12 empty] | 2025-09-19 | 2025-09-19 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-07-18 | 2025-10-03 |  |  | 2026-02-27 | TM |  |  | 1 |  | 1710 | [7 empty] | 1. On Track | 17. FUT In progress | 02/27:09/15 TC Completed. Defect # 7761 raised to fix the printing issue for multiple lines . Tech ETA : 02/27.Plan to send FUT document to intel by 03/02. 02/20: 3TC/15 Completed. Form layout issues are being worked upon through defect. Remaining scenarios are dependent upon LOGE1221 02/16: 3TC/15 Completed. Form layout issues are being worked upon through defect. Remaining scenarios are dependent upon LOGE1221 01/19: This object will be tested along with LOGE1221 becuase of dependency 01/05: Object to be worked up on Sprint 22, after FUT completion of LOGE1221 12/22: Object to be worked up on Sprint 22, after FUT completion of LOGE1221 12/15:Depenedent on FUT completion for core scenarios of LOGE1221 | 2025-10-03 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2698 | LOGF1149_IP | 05.Form | 01.IP - Intel Product | Consolidated Packing list for Chengdu | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC4271000-1462-40F3-BE2C-F82AE0FE2931%7D&file=R3_IP_OTC_LE_Packing%20List%20for%20Chengdu_Intake_Form.pptx&action=edit&mobileredirect=true |  |  |  | 2025-01-23 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-22 | 2025-04-14 | 2025-04-18 | 2025-08-13 | 100% | 2025-08-22 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-03 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-17 | 2025-10-31 | N | 100% | 2025-11-19 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-01-20 06:30 | cell-link@smartsheet.com | 2026-03-09 05:35 | 10 | 2025-01-30 | 01.S4 |  |  | 2 | 1.38 | 1149 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | [5 empty] | 2025-04-30 | 2025-04-18 | [6 empty] | 1 |  | 2600 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/14: Logic provided by TM team, defect#4266 with tech for the fix, ETA 11/14 11/11: Internal CR has been created and details updated in Defect#4226, tech team to work on fix, no ETA 11/04: TM to provide updated logic for HK-U Turn and CD DSW shipments, following which a requirment change defect to be raised 10/31: Working on the open points raised by Intel post review 10/24 - Awaiting approval 10/22: Defects resolved and FUT in progress 10/10: Defect#3618 raised as form output is not visible in FO, 6/14 scenarios completed 10/06: FUT is in progress, no defects as of now, ETA 10/09 to complete FUT execution if no defects are encountered 09/29: FUT is in progress, Defect#3373 is opened and currently with tech team, ETA is 09/30 09/22 - FUT in progress. Ebook serial no. point is till open. ETA 10/03 | 2025-08-15 | N | 99. Logistics |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-22 | 2025-08-22 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2698 | LOGF1149_IF | 05.Form | 02.IF - Intel Foundry | Consolidated Packing list for Chengdu | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC4271000-1462-40F3-BE2C-F82AE0FE2931%7D&file=R3_IP_OTC_LE_Packing%20List%20for%20Chengdu_Intake_Form.pptx&action=edit&mobileredirect=true |  |  |  | 2025-01-23 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-08-22 | 2025-04-14 | 2025-04-18 | 2025-08-13 | 100% | 2025-08-22 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-01-20 06:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-30 | 01.S4 | LOGF1149_IP | 02.High | 0.4 | 0.276 | 1149 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-05-29 | 2025-04-18 | [6 empty] | 1 |  | 2599 | [7 empty] | 3. Off Track | 17. FUT In progress | 10/10: Review completed, Feedback received from Intel to add one additional test case and change no. of packages logic(defect#3612), ETA 10/14 to respond to Intel queries | 2025-08-15 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-08-22 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2354 | LOGF1100_IP | 05.Form | 01.IP - Intel Product | Printing of Standard Shipping Label | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_LO-170-090_Standard%20shipping%20label.pptx?d=w44f7cce072fe4fc5958c885b2abbd64a&csf=1&web=1&e=y1ScWN | 02.No | 01.Yes |  | 2025-01-15 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-25 | 2025-04-25 | 100% | 2025-04-24 | 2025-09-26 | 2025-10-03 | 2025-05-20 | 100% | 2025-05-27 | 2025-10-24 | 2025-11-07 | 2025-05-30 | 100% | 2025-05-27 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-05 | [15 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2025-01-08 08:37 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-30 | 01.S4 |  |  | 2 | 1.38 | 1100 |  | R3 ITC1 | [6 empty] | 2025-04-24 | 2025-04-25 | 2025-04-24 |  | 2025-05-27 | 2025-10-03 | 2025-05-27 |  | 2025-05-27 | 2025-11-07 | 2025-05-27 | 2025-06-05 | [12 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2476 | [9 empty] | 9/12: Aditya: Awaiting PS approval | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-06-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2354 | LOGF1100_IF | 05.Form | 02.IF - Intel Foundry | Printing of Standard Shipping Label | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_LO-170-090_Standard%20shipping%20label.pptx?d=w44f7cce072fe4fc5958c885b2abbd64a&csf=1&web=1&e=y1ScWN | 02.No | 01.Yes |  | 2025-01-15 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-09-26 | 2025-10-03 | 2025-05-20 | 100% | 2025-05-27 | 2025-10-31 | 2025-11-07 | 2025-05-30 | 100% | 2025-05-27 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-05 | [15 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2025-01-08 08:37 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-30 | 01.S4 | LOGF1100_IP | 02.High | 0.4 | 0.276 | 1100 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-27 | 2025-10-03 | 2025-05-27 |  | 2025-05-27 | 2025-11-07 | 2025-05-27 | 2025-06-05 | [12 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 |  | 2477 | [9 empty] | 9/12: Aditya: Awaiting PS approval | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-06-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2148 | LOGF1089 | 05.Form | 08.EWM | Creation of Forms for Cycle count | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2148_FTS%20EWM_Physical%20Inventory%20Cycle%20Counting%20Forms.pptx?d=wd723dd47178b4f6499b56ae186310593&csf=1&web=1&e=1EnR2V | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-02 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 0.69 | 1089 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-09 | 2025-11-07 |  |  | 2025-12-12 | TM | WIINGS Only | TRUE | 1 |  | 1605 | [9 empty] | 09/05: FUT sent to business & IT for approval. 09/01: New 2 defects created and assigned to tech team. 08/25: Defect resolved and FUT send for approval on 08/25. 08/25: Defect are resolved today, testing in progress. 08/18: Planned in S16 and in Roadblock due to defect with tech team | 2025-07-18 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2647 | LOGF1085 | 05.Form | 08.EWM | Enhancement to print the Bin Location label in SAP EWM. | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC4BC12AC-ABEB-4ECF-BA0D-5866C9D03E6C%7D&file=R3_L-040-080_%20Record%20Receipt%20and%20tracking%20label_Bin%20Locations%20Label.pptx&wdLOR=c4BBEA3FA-6B8E-4269-AD6D-12A3003CFDAE&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-26 | 2025-10-03 | 2025-07-25 | 100% | 2025-08-01 | 2025-10-24 | 2025-11-07 | 2025-08-08 | 100% | 2025-08-01 | 2025-10-24 | 2025-11-07 | 2025-08-08 | 100% | 2025-08-01 | [15 empty] | 2025-08-01 | 2025-08-01 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-02 | 01.S4 |  |  | 1 | 0.69 | 1085 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-01 | 2025-10-03 | 2025-08-01 |  | 2025-08-01 | 2025-11-07 | 2025-08-01 | 2025-08-01 | [12 empty] | 2025-08-01 | 2025-08-01 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | [5 empty] | 2025-05-02 | 2025-11-07 |  |  | 2025-11-28 | TM | WIINGS Only | TRUE | 1 |  | 1838 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-11-07 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-11-07 | 2025-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2152 | LOGF1057 | 05.Form | 08.EWM | Print Pick List | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IF_PM_EWM_L-060-070_Print%20Pick%20List.pptx?d=wfcc987bdc8b740c5981fceec8e85f6c4&csf=1&web=1&e=1uTXsN | 02.No | 01.Yes |  | 2025-01-02 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-02 | 2025-06-06 | 100% | 2025-06-09 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 |  |  | 2 | 1.38 | 1057 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-18 | 2025-09-12 |  |  | 2025-10-10 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 1597 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: All comments are addressed and aligned with IT team, Biz is holding approval on process related queries which are already addressed. 12/15:All business comments are addressed, awaiting business & IT approval. 12/8: Business IT review updates are in progress. Defect 5340/41 raised today. 5340-Cosmectic Change (Batch to be in bold letter), 5041--Sequencing Issue. ETA 12/9. 12/01: FUT sent to business for review and approval on 11/28. 11/24: Defect 4389 with dev, ETA from Dev 11/24. ETC to send for intel approval by 11/28. 11/18 Defect 4398 raised to dev team | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2150 | LOGF1056 | 05.Form | 08.EWM | Print Return Label | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2150_R3_FTS_IF_PM_EWM_Reprint%20Return%20Label.pptx?d=wd270bd03426c4b7fb18d5172e5969191&csf=1&web=1&e=gkTq1E | 02.No | 01.Yes |  | 2025-01-02 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-16 | 2025-06-06 | 100% | 2025-05-30 | 2025-09-26 | 2025-10-03 | 2025-08-01 | 100% | 2025-07-24 | 2025-10-24 | 2025-11-07 | 2025-08-13 | 100% | 2025-07-24 | 2025-10-24 | 2025-11-07 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-23 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 0.69 | 1056 |  | R3 ITC1 | [6 empty] | 2025-05-30 | 2025-06-06 | 2025-05-30 |  | 2025-07-24 | 2025-10-03 | 2025-07-24 |  | 2025-07-24 | 2025-11-07 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | [5 empty] | 2025-05-23 | 2025-11-07 |  |  | 2025-12-12 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 1607 | [9 empty] | 09/19: All comments are addressed on FUT, approval pending with Biz & IT. 09/12: Awaiting business approval, all open comments are addressed. | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-11-07 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2149 | LOGF1055 | 05.Form | 08.EWM | Print Pick Label (PM-EWM) | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IF_PM_EWM_L-060-070_Print%20Pick%20Label.pptx?d=wa11aad1740684312a148b5c0fa387097&csf=1&web=1&e=w0L0jh | 02.No | 01.Yes |  | 2025-01-02 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-16 | 2025-06-06 | 100% | 2025-06-09 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-29 | 2025-10-31 | 2025-10-24 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 |  |  | 2 | 1.38 | 1055 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-09-12 | 2025-10-10 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-04-25 | 2025-09-12 |  |  | 2025-10-10 | TM | WIINGS Only | TRUE | 1 |  | 1606 | [7 empty] | 1. On Track | 1. Approved no action | 12/08: FUT approved by Biz & IT. 12/01: all open comments are addressed, awaiting business approval. 11/24: Business review comments updates are in progress. Once document is updated, will be resent for approval. ETC 11/25 to send for intel approval. 11/18: Defect 4255 is open with technical team for resolution. 11/11: Defect 4255 is open with technical team. 11/03: defect is closed, design question raised by business on 10/31. Checking internally how that can be taken up. 10/31: Requires change in the triggering mechanism. WIP with Intel biz to decide if this change is required 10/24 - Awaiting approval | 2025-10-10 | Y | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1770 | LOGF1045 | 05.Form | 08.EWM | Goods Receipt Label Print triggered at the point of completion of the GR | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B41E26E81-040B-40A9-AB72-EA2215227754%7D&file=R3_IF_PTP_LOGISTICS_EWM_L-040-080_RICEFW%20Intake%20(1).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-18 | cari.h.shim@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-31 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-27 | 2025-11-21 | 2025-12-03 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 0.69 | 1045 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | [5 empty] | 2025-04-25 | 2025-09-12 |  |  | 2025-10-10 | TM | WIINGS |  | 1 | 08. Not Applicable | 1997 | [7 empty] | 1. On Track | 1. Approved no action | 12/18: Approved 12/17: Defect resolved. Awaiting approval from business. Reminder shared with business, 12/15: Awaiting business approval. Defect 5537 for layout was opened as per bsuiness review feedback, defect fic ETA is 15Dec-fixed 12/08: Intel is reviewing and providing comments. Defect 5215 created for layout changes 12/01: Sent for Biz review on 28th Nov 11/24:FUT is in progress. Defect 4897 is with dev, ETA 24/11. ETC to send for intel review is 11/27. 11/10: Roadblock defect 3856 11/04: Under roadblock for Defect #3856. Tech team will pick up in sprint 20 start | 2025-10-24 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 2086 | LOGF0920_IP | 05.Form | 01.IP - Intel Product | Form for printing Goods receipt label in IM - IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2789DB23-5D09-4441-9057-7C7451D1F691%7D&file=LI-120-180-Print%20label%203.pptx&wdLOR=c72D7BF9E-060A-49F0-98D2-692C0A5DB15E&action=edit&mobileredirect=true | 02.No | 02.No |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-25 | 2025-04-16 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-07 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-11-28 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-09 03:41 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 1.38 | 0920 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-07 | 2025-09-19 | 2025-08-07 |  | 2025-09-23 | 2025-10-10 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-04-04 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 |  | 2089 | [7 empty] | 4. Completed | 1. Approved no action | 12/08: Approved by Intel IT & Business/PS 12/01: All Review comments are addressed, Awaiting further feedback/approval from Intel IT. No Action item as of now on DT 11/24: FUT sent for approval on 11/22 (Extended support) with business update 11/18 - Defect# 4618 is resolved, FUT is in-progress. Defect# 4630 is still open, blocking 5 TCs 11/14 - All TCs needs to be Retested. FUT is blocked, CR0289 needs to be implemented to unblock the FUT. CR0289 sent for Approval | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-23 | Yes | Change in Condition Records and Change in Custom Table entries for Plant Tables - ZTPTP_3B2_4B2 | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2086 | LOGF0920_IF | 05.Form | 02.IF - Intel Foundry | Form for printing Goods receipt label in IM - IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2789DB23-5D09-4441-9057-7C7451D1F691%7D&file=LI-120-180-Print%20label%203.pptx&wdLOR=c72D7BF9E-060A-49F0-98D2-692C0A5DB15E&action=edit&mobileredirect=true | 02.No | 02.No |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-25 | 2025-04-16 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-07 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-11-28 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-11-20 03:23 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-12 | 01.S4 | LOGF0920_IP | 02.High | 0.4 | 0.276 | 0920 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-07 | 2025-09-19 | 2025-08-07 |  | 2025-09-23 | 2025-10-10 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-04-04 | 2025-09-12 |  |  | 2025-10-10 |  | WIINGS Only | TRUE | 1 |  | 2088 | [7 empty] | 4. Completed | 1. Approved no action | 12/08: Approved by Intel IT & Business/PS 12/01: All Review comments are addressed, Awaiting further feedback/approval from Intel IT & Business/PS. No Action item as of now on DT 11/24: FUT sent for approval on 11/22 (Extended support) with business update. 11/18 - Defect# 4618 is resolved, FUT is in-progress. 12 TCs need to be completed 11/14 - All TCs needs to be Retested. FUT is blocked, CR0289 needs to be implemented to unblock the FUT. CR0289 sent for Approval | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2314 | LOGF0873 | 05.Form | 02.IF - Intel Foundry | CI/PL document should be printed based on R3 process. | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v1.pptx?d=wc8d399637f0d4792971984b0a84d8b1a&csf=1&web=1&e=lHW5Gn | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-02 | 2025-06-20 | 2025-07-11 | 100% | 2025-08-08 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-06 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-06 | [15 empty] | 2026-03-06 | 2026-03-06 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-18 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-01-02 | 01.S4 |  |  | 2 | 1.38 | 0873 |  | R3 ITC1 | [6 empty] | 2025-08-08 | 2025-08-08 | 2025-08-08 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | [12 empty] | 2026-03-06 | 2026-03-06 |  |  | 2026-02-18 | 2026-02-20 | 2026-02-18 | [5 empty] | 2025-02-21 | 2025-09-12 |  |  | 2025-10-01 |  |  |  | 1 |  | 2110 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/16: Sent for Intel review on 02/13 01/12: FUT is in progress, started on 01/09, delayed due to TUT completion delay 01/05: TUT is in progress. Additional test data requirement was blocked due to dependency with LOGI0842_IF, which has been resolved and test data will be provided by 01/05 12/22:TUT in progress. 12/15: TUT is still in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-03-06 | 2026-03-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2184 | LOGF0805 | 05.Form | 01.IP - Intel Product | EIAJ form to be generated for OEM customers (Japan) | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_EIAJ%20Form_Intake_Form.pptx?d=wc320921349484ba59b4e05f1b4e94ee3&csf=1&web=1&e=FPAnfx | 01.Yes | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-02 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-19 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-19 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-19 | [15 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-13 | 01.S4 |  |  | 2 | 1.38 | 0805 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-19 | 2025-10-17 | 2025-09-19 |  | 2025-09-19 | 2025-11-07 | 2025-09-19 | 2025-09-19 | [12 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2025-05-30 | 2025-11-07 |  |  | 2025-12-12 |  |  |  | 1 | 08. Not Applicable | 2540 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14: Intel Business approved, awaiting Intel IT approval 11/11: FUT review completed, the open points were addressed, awaiting Intel Feedback 10/31: FUT in progress. Multiple issues on the form build, Defect#3834 is fixed and currently being retested 10/24 - Defect 3834 | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-11-07 | 2025-09-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 695 | LOGF0359_IP | 05.Form | 01.IP - Intel Product | ISM - Generate Commercial Invoice - IF/IP | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-05-06 | Not Applicable | R3 Build & UT Sprint 13 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0359 |  | R3 ITC1 | [6 empty] | 2024-09-27 | 2024-09-27 | 2024-09-27 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-05-06 | 2025-05-06 | 2025-05-06 | [5 empty] | 2024-09-27 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2570 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes |  | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 695 | LOGF0359_IF | 05.Form | 02.IF - Intel Foundry | ISM - Generate Commercial Invoice - IF/IP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-06 | Not Applicable | R3 Build & UT Sprint 13 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGF0359_IP | 02.High | 0.4 | 0.276 | 0359 |  | R3 ITC1 | [6 empty] | 2024-09-27 | 2024-09-27 | 2024-09-27 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-05-06 | 2025-05-06 | 2025-05-06 | [5 empty] | 2024-09-27 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2569 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 694 | LOGF0358_IP | 05.Form | 01.IP - Intel Product | ISM - Generate Traveler Document - IF/IP | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-27 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-26 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-05-02 | Not Applicable | R3 Build & UT Sprint 13 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0358 |  | R3 ITC1 | [6 empty] | 2024-09-27 | 2024-09-27 | 2024-09-27 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | [5 empty] | 2024-09-27 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2558 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 694 | LOGF0358_IF | 05.Form | 02.IF - Intel Foundry | ISM - Generate Traveler Document - IF/IP | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-09-27 | 2024-09-27 | 100% | 2024-09-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-02 | Not Applicable | R3 Build & UT Sprint 13 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGF0358_IP | 02.High | 0.4 | 0.276 | 0358 |  | R3 ITC1 | [6 empty] | 2024-09-26 | 2024-09-27 | 2024-09-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | [5 empty] | 2024-09-27 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2557 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 692 | LOGF0356 | 05.Form | 02.IF - Intel Foundry | Generate Consolidated Bailment Commercial Invoice - Finished Goods (IF and IP) | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-07-01 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-01-31 | 100% | 2025-02-26 | 2024-10-07 | 2024-12-20 | 2025-01-31 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-10-24 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2026-01-14 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0356 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-10-31 |  |  |  | 1 | 08. Not Applicable | 2556 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: All open points addressed, awaiting Intel IT approval 01/05: Defect 5771 is fixed and retest is in progress, ETA 01/06, additional inputs requested by tech for defect 5772, which will be provided by 01/06. 12/22: Intel IT has some open points for which Defect 5771, 5772 is open which with tech team ETA 12/23. 12/15: Intel business approval received, awaiting Intel IT approval 12/08: Working on the feedback received from Intel, on 12/5. Team is analyzing the feedback to categorizing them into defect and change request. ETA 12/09 to respond to the feedback. 12/01: FUT sent for approval on 11/27. No open items with Deloitte 11/24: One open defect 4839, Dev ETA-11/24. 23/28 TC completed, will be sent for Intel approval by 11/26. ETC to send for Intel Review -11/26. 11/14: Defects 3906 & 3957 is fixed, retest in progress, defect 3958 & 3959 is open, working session with tech scheduled for the same 11/11: Defects 3906, 3957, 3958, 3959 are picked up by tech, ETA is 11/11 10/31: 4 open defects 3906, 3957, 3958, 3959 which cannot be progressed unless dump issue captured in 3976 is resolved 10/24 - Defect 3906 10/22: FUT in progress and on track | 2024-12-20 | N | 99. Logistics |  |  |  |  | 12/02 - Awaiting approval. ETA is 12/05 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 691 | LOGF0355 | 05.Form | 02.IF - Intel Foundry | Generate Consolidated Bailment Commercial Invoice - Wafer/Die (IF and IP) | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-01 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-23 | 2024-08-30 | 2024-09-06 | 2024-11-08 | 100% | 2024-11-26 | 2025-03-14 | 2025-03-21 | 2025-02-14 | 100% | 2025-02-26 | 2025-03-14 | 2025-03-21 | 2025-02-14 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-10-24 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-31 | 2025-10-31 | N | 100% | 2026-01-14 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0355 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-26 | 2025-03-21 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | [5 empty] | 2024-08-16 | 2025-03-21 |  |  | 2025-10-31 |  |  |  | 1 | 08. Not Applicable | 2555 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: All open points addressed, awaiting Intel IT approval 01/05: Defect 5771 is fixed and retest is in progress, ETA 01/06, additional inputs requested by tech for defect 5772, which will be provided by 01/06. 12/22:Intel IT has some open points for which Defect 5771, 5772 is open which with tech team ETA 12/23. 12/15: Intel business approval received, awaiting Intel IT approval 12/08: Working on the feedback received from Intel, on 12/5. Team is analyzing the feedback to categorizing them into defect and change request. ETA 12/09 to respond to the feedback. 12/01: Defect#5039 is with tech, ETA 12/01 11/24-No open defects. Targeting to send for the intel approval by 11/26. 11/14: Defect#4415 is closed, FUT in progress, ETA for FUT execution completion 11/21 11/13: Defect#4415 re-assigned to tech 11/11: Defect#4263 is closed, new defect#4415 raised not ETA from tech, part of priority list 10/31: 3976 defect open for authorization / Fiori app issue 10/22: FUT in progress and on track. ETA is 10/27 | 2025-03-21 | N | 99. Logistics |  |  |  |  | 12/02 - Will be sent for approval on 1203. Approval in this sprint is risk. |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 689 | LOGF0353_IP | 05.Form | 01.IP - Intel Product | Generate Consolidated Export Commercial Invoice - Finished Goods (IF and IP) | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-12 | 2024-08-16 | 2024-08-16 | 100% | 2024-11-29 | 2025-07-02 | 2025-07-09 | 2025-08-01 | 100% | 2025-09-09 | 2025-04-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-09 | 2025-04-04 | 2025-04-18 | 2025-08-13 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-30 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-28 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0353 |  | R3 ITC1 | [6 empty] | 2024-11-29 | 2024-11-29 | 2024-11-29 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-28 | 2026-01-30 | 2026-01-28 | [5 empty] | 2024-08-16 | 2025-04-18 |  |  | 2025-05-23 |  |  |  | 1 | 08. Not Applicable | 2554 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/19: Sent for Intel review on 01/16, FUT review call scheduled on 01/20. 01/12: Defect#5877 is fixed & retest is kept open till other defects are fixed, 6034 & 6094 is with tech ETA 01/12, 6143 is with tech, no ETA 01/05: Defect#5877 is with tech, no ETA on fix. 12/22:Defect#5543 will be closed today, and testing further scenario is in progress. 15/15: Defect#5543 is with tech, no ETA on fix Dependent on LOGF1583 build completion | 2025-04-18 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-09 | 2025-09-09 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 806 | LOGF0352_IP | 05.Form | 01.IP - Intel Product | ISM - IPLA | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-04-17 | Not Applicable | R3 Build & UT Sprint 12 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-10-03 07:41 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-08 | 01.S4 |  |  | 2 | 1.38 | 0352 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-17 | 2025-04-18 | 2025-04-17 | [5 empty] | 2024-10-11 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 1648 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 806 | LOGF0352_IF | 05.Form | 02.IF - Intel Foundry | ISM - IPLA | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-12-01 | 2024-09-27 | 100% | 2024-09-27 | 2025-08-01 | 2025-08-08 | 2025-04-29 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-17 02:08 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 | LOGF0352_IP | 02.High | 0.4 | 0.276 | 0352 |  | R3 ITC1 | [6 empty] | 2024-09-27 | 2024-12-01 | 2024-09-27 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-01 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 1647 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 805 | LOGF0351_IP | 05.Form | 01.IP - Intel Product | ISM - Custom China Special label | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-04-18 | Not Applicable | R3 Build & UT Sprint 12 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-10-03 07:41 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-08 | 01.S4 |  |  | 2 | 1.38 | 0351 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-18 | 2025-04-18 | [6 empty] | 2024-10-11 | 2025-01-31 |  |  | 2025-02-21 |  |  |  | 1 | 08. Not Applicable | 1646 | [7 empty] | 1. On Track | 5. Object to be Cancelled |  | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 805 | LOGF0351_IF | 05.Form | 02.IF - Intel Foundry | ISM - Custom China Special label | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-12-01 | 2024-09-27 | 100% | 2024-09-26 | 2025-08-01 | 2025-08-08 | 2025-04-29 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-17 02:08 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 | LOGF0351_IP | 02.High | 0.4 | 0.276 | 0351 |  | R3 ITC1 | [6 empty] | 2024-09-26 | 2024-12-01 | 2024-09-26 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-01 | 2025-09-12 |  |  | 2025-10-03 |  |  |  | 1 | 08. Not Applicable | 1645 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 804 | LOGF0350_IP | 05.Form | 01.IP - Intel Product | ISM - India GST DC | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-04-18 | Not Applicable | R3 Build & UT Sprint 12 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-10-03 07:41 | sdeolalikar@deloitte.com | 2026-02-24 12:08 | 10 | 2024-11-08 | 01.S4 |  |  | 2 | 1.38 | 0350 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-04-18 | 2025-04-18 | [6 empty] | 2024-10-11 | 2025-01-31 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 1644 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 804 | LOGF0350_IF | 05.Form | 02.IF - Intel Foundry | ISM - India GST DC | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-30 | 2024-12-01 | 2024-09-27 | 100% | 2024-10-01 | 2025-08-01 | 2025-08-08 | 2025-04-29 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-05 | 2025-09-12 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-17 02:08 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 | LOGF0350_IP | 02.High | 0.4 | 0.276 | 0350 |  | R3 ITC1 | [6 empty] | 2024-10-01 | 2024-12-01 | 2024-10-01 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-01 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 1643 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 696 | LOGF0349_IP | 05.Form | 01.IP - Intel Product | ISM - Generate Packing List - IF/IP | 05. OTC IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | Integrated Shipping Memo | NA | NA | NA | 2024-09-02 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-21 | 2024-09-23 | 2024-09-23 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-30 | 2024-11-22 | 2025-02-21 | 100% | 2025-02-26 | 2024-09-30 | 2024-11-22 | 2025-02-21 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-04-18 | N | 100% | 2025-05-05 | Not Applicable | R3 Build & UT Sprint 13 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-17 02:08 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0349 |  | R3 ITC1 | [6 empty] | 2024-08-21 | 2024-08-21 | 2024-08-21 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | [5 empty] | 2024-08-02 | 2024-11-22 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2572 | [10 empty] | 2024-11-22 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 696 | LOGF0349_IF | 05.Form | 02.IF - Intel Foundry | ISM - Generate Packing List - IF/IP | 04. OTC IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | Integrated Shipping Memo | NA | NA | NA | 2024-09-02 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-21 | 2024-09-23 | 2024-09-23 | 2024-10-04 | 100% | 2024-10-01 | 2024-09-30 | 2024-11-22 | 2025-02-21 | 100% | 2025-02-26 | 2024-09-30 | 2024-11-22 | 2025-02-21 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-05 | Not Applicable | R3 Build & UT Sprint 13 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-17 02:08 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | LOGF0349_IP | 02.High | 0.4 | 0.276 | 0349 |  | R3 ITC1 | [6 empty] | 2024-08-21 | 2024-08-21 | 2024-08-21 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-05-05 | 2025-05-05 | 2025-05-05 | [5 empty] | 2024-08-02 | 2024-11-22 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2571 | [10 empty] | 2024-11-22 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 787 | LOGF0348_IP | 05.Form | 01.IP - Intel Product | Shipper Letter of instruction (Localization requirement for US) | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-07-22 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-08 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0348 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2355 | [9 empty] | 09/05: Defect #2251 is assigned back to tech team as the Currency conversion issue is still persisting | 2024-12-20 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 447 | LOGF0345_IP | 05.Form | 01.IP - Intel Product | Bailment CI and End-Customer CI for IF/IP | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-12 | 2024-08-16 | 2024-08-16 | 100% | 2024-11-07 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-08-13 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-14 | Not Applicable | R3 Build & UT Sprint 19 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0345 |  | R3 ITC1 | [6 empty] | 2024-11-07 | 2024-11-07 | 2024-11-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | [5 empty] | 2024-08-16 | 2025-01-31 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2775 | [7 empty] | 3. Off Track | 17. FUT In progress | 10/10: Awaiting Intel approval, all open points clarified 10/06: Resent for approval, feedback received from Intel, however the request changes are CRs & Additional TCs which as per alignment should not hold FUT approval, call scheduled on 10/07 to align on the same. 09/29: All requested corrections from Intel post review is completed and will be resent for approval by 09/29 09/22: New Changes to be taken under new CR. 09/12: Revision required post Intel review, updated ETA-09/17 | 2025-01-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 446 | LOGF0344_IP | 05.Form | 01.IP - Intel Product | Generate Export CI for IF/IP | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-08-12 | 2024-08-16 | 2024-08-16 | 100% | 2024-11-22 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-08-13 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0344 |  | R3 ITC1 | [6 empty] | 2024-11-22 | 2024-11-22 | 2024-11-22 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2024-08-16 | 2025-01-31 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2774 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/22: IT approval pending, Business approved. Sundari was on PTO 10/10: Intel has requested for a change in Incoterms logic which is to be taken up as a CR, mail will be sent to Intel to approve FUT considering this change was not part of original FSD, 10/06: Resent for approval, feedback received from Intel, however the request changes are CRs & Additional TCs which as per alignment should not hold FUT approval, call scheduled on 10/07 to align on the same. 09/29: Defect#3393 is open 09/22: New changes to be taken under new CR.. 09/12: Revision required post Intel review, updated ETA-09/17 | 2025-01-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 445 | LOGF0343_IP | 05.Form | 01.IP - Intel Product | Generate Itemised Packing Lists | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-22 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-07-04 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-07-11 | N | 100% | 2025-07-24 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 1 | 0.69 | 0343 |  | R3 ITC1 | [6 empty] | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2773 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 444 | LOGF0342_IP | 05.Form | 01.IP - Intel Product | Generate Packing Lists for Finished Goods - IP and IF | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B52B59E35-FC49-4489-83D0-A5F13F882CA5%7D&file=R2_IF_OTC_Logistics_LO-170_Process%20regulatory%20Document_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-07-22 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-10-07 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-07-04 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-07-11 | N | 100% | 2025-08-01 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0342 |  | R3 ITC1 | [6 empty] | 2024-08-22 | 2024-08-22 | 2024-08-22 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2772 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW | FUT is submitted and currently under Intel Approval. | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | Yes | ZTOTC_PARAMS & ZTOTC_COO table impacts | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3204 | LOGE1728 | 04.Enhancement | 02.IF - Intel Foundry | Automate Outbound delivery note creation for 250K annual Subcon POs for repair/rework including Quench returns. | 06. PTP | 6.4 PTP - Logistics Management Inbound | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B4C0E00F3-1BDF-4B83-A46E-6312D7D581EC%7D&file=CR1604_PTP%20LE_Automate%20Outbound%20delivery%20creation%20for%20Repair%20Rework%20Subcon%20PO.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-04-03 | 100% | 2026-04-03 |  |  | 2026-03-31 | 74% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 | [17 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-02-21 03:09 | ryapark@deloitte.com | 2026-04-07 12:27 | 6 |  | 01.S4 |  |  | 1 | 1 | 1728 | INT-CR1604 | R3 ITC2 | R3 ITC2 | [5 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [32 empty] | WIINGS Only | TRUE | 1 |  | 3433 | [11 empty] | N | 99. Logistics | [6 empty] | Approved Exception (ITC2) |  | N/A | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 3193 | LOGE1713 | 04.Enhancement | 01.IP - Intel Product | Copy Control Routine for Customer Master Special Instructions | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2026-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFC3E0FCC-F003-4A99-9E9F-8943E133CEE5%7D&file=3193_OTC_IP_LE_Copy%20Control%20Routine%20for%20Customer%20Master%20Special%20Instructions.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-20 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-04 | 2026-02-04 | 100% | 2026-02-06 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-23 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-27 |  | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2026-01-19 20:13 | cell-link@smartsheet.com | 2026-03-27 06:33 | 10 |  | 01.S4 |  |  | 1 | 1 | 1713 | INT-CR1547 | R3 ITC1 | [6 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2026-02-04 | 2026-03-04 |  |  | 2026-03-04 |  |  |  | 1 |  | 3410 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 03/20: FUT walkthrough completed, Intel is not ready to provide conditional approval till Defect#7953 & 8329 is fixed. Defect#7953 & 8329 is marked as fixed by tech, however when retesting was done, issue still persits. 03/13: Sent for Intel review on 03/12. FUT walkthrough scheduled on 03/16. Defect#7953 -Partially Fixed & 8329 is still with tech, no ETA 03/02: Received confirmation from tech to proceeed with FUT, FUT started on 03/02 02/27: Awaiting Build Completion 02/23: Awaiting Build completion 02/16: Build has started on 02/13, no ETA on build completion | 2026-03-04 | Y | 99. Logistics |  |  |  | 03/24 : Defect fix in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3170 | LOGE1691 | 04.Enhancement | 08.EWM | Custom Enhancement for Storage Location and Storage Type Restriction LOG IF and LOG EWM IF Security Roles | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console%20ID_3170_Custom%20Enhancement%20for%20Storage%20Location%20and%20Storage%20Type%20Restriction%20LOG%20IF%20and%20LOG%20EWM%20IF%20Business%20Roles.pptx?d=wda2b4c65065f44cd984e5131afd49f16&csf=1&web=1&e=dGKM4zhttps://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console%20ID_3170_Custom%20Enhancement%20for%20Storage%20Location%20and%20Storage%20Type%20Restriction%20LOG%20IF%20and%20LOG%20EWM%20IF%20Business%20Roles.pptx?d=wda2b4c65065f44cd984e5131afd49f16&csf=1&web=1&e=dGKM4z | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-13 | 100% | 2026-02-13 | 2026-02-09 | 2026-02-27 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-03-04 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-27 | Sprint 23 Week 2 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-05 05:23 | cell-link@smartsheet.com | 2026-04-06 21:14 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1 | 1691 | INT-CR1292 | R3 ITC1* | [6 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-08 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 | [6 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-03-04 | TM |  |  | 1 |  | 3374 | [7 empty] | 1. On Track | 3. Awaiting Approval | 04/03: FUT sent to business for review and approval. 03/27: FUT documentation in progress, few scenarios are not working where tech & security team is checking further. 03/20: Testing resumed today as authenticator issue fixed by tech team. Few more issues encountered which we are checking with security team. 03/12: Credentials provided by security team are not working, cordinating with team to start FUT. 03/10: Awaiting test IDs from security team to initiate the FUT (Mail has been shared with Security team on this) 03/09: Build confirmation received from tech on 03/07, FUT will be started upon cordinating with security team for test ID. 03/06: Development in progress, awaiting new ETA from tech. For 1 transaction Tech is taking SAP support for development. 03/02: Build completion planned EOD by tech, support being provided by test data and tcode demos. 02/27: Awaiting tech team confirmation on build completion. 02/23: Awaiting tech team confirmation on build completion. 02/20: Build in progress, no further update from tech. 02/16: Awaiting ETA from tech team for FUT execution. | 2026-02-06 | N | 99. Logistics |  |  |  | 03/24 : Defect fix in progress. ETA to share for approval is 03/27 | 0131 Approved | 2. Risk | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-08 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3170 | LOGE1690 | 04.Enhancement | 02.IF - Intel Foundry | Custom Enhancement for Storage Location and Storage Type Restriction LOG IF and LOG EWM IF Security Roles | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console%20ID_3170_Custom%20Enhancement%20for%20Storage%20Location%20and%20Storage%20Type%20Restriction%20LOG%20IF%20and%20LOG%20EWM%20IF%20Business%20Roles.pptx?d=wda2b4c65065f44cd984e5131afd49f16&csf=1&web=1&e=dGKM4zhttps://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console%20ID_3170_Custom%20Enhancement%20for%20Storage%20Location%20and%20Storage%20Type%20Restriction%20LOG%20IF%20and%20LOG%20EWM%20IF%20Business%20Roles.pptx?d=wda2b4c65065f44cd984e5131afd49f16&csf=1&web=1&e=dGKM4z | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-02 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-03 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-05 05:23 | cell-link@smartsheet.com | 2026-04-03 07:08 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1 | 1690 | INT-CR1292 | R3 ITC1* | [6 empty] | 2026-02-02 | 2026-02-06 | 2026-02-02 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-08 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | [5 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-04 |  |  |  | 1 |  | 3373 | [7 empty] | 4. Completed | 1. Approved no action | 4/03: approved. 3/27: walkthorough completed, awaiting approval. 3/26: Following up with OTC for test completion. FUT walthrough schedules with Rudy 3/26. 3/25:Defect# 8592 is open for OTC access issues. 3/23: documentation inprogress- ETA to send for review- 03/23 3/20: 6/20 completed, rest testing in progress. ETA: 03/24 to send for intel review. 3/18: Retest in progress. 3/17:Defect#8397 raised. validation on sloc is not working or not properly developed. 3/16: Recieved user id from security and will start FUT today. 3/13: following u with Security, ETA given was 03/12 FUT will start once security team provided the test user ids. Test user id creation in progress. 3/12: FUT will start once security team provided the test user ids. Test user id creation in progress. ETA 3/12. 3/10: dev in progress, checking for ETA from tech. Mail sent to Vivek. 3/9: following with tech for sloc validation. Build in progress. 3/6: Auth issue raised by tech needs to be aligned by Sri and Imran. ETA 6/3 3/05: Awaiting build completion. Build ETA 2/27 3/02: Test data provided to tech team. FUT expected to start by 3/04. 3/02: Test data to be provided for 1 sceario to tech team. 2/27: Dev WIP. ETA: 2/27 2/26: Dev WIP. ETA: 2/27 2/25: Dev WIP. ETA: 2/27 2/13: Dev WIP. ETA: 2/27 2/12: Dev WIP 2/11: Dev WIP 2/9: Dev WIP3/20: 6/20 completed, rest testing in progress. ETA: 03/24 3/18: Retest in progress.3/13: following u with Security, ETA given was 03/12 FUT will start once security team provided the test user ids. Test user id creation in progress. 3/6: Auth issue raised by tech needs to be aligned by Sri and Imran. ETA 6/3 2/24: Development in progress ETA 2/27 2/20: Dev WIP. ETA: 2/27 2/16: Build in Progress. ETA: 2/27 from Tech team | 2026-02-27 | Y | 99. Logistics |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 03/27 | 0131 Approved | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-08 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3129 | LOGE1686 | 04.Enhancement | 02.IF - Intel Foundry | IP custom table for reconciliation data | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/CR%20Intake%20Form/3129%20R3_FTS_IP%20custom%20table%20for%20reconciliation%20data.pptx?d=wad8678f9006346a6983fc2f5cb5aaf4a&csf=1&web=1&e=LijXwf | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-23 | 2026-01-23 | 100% | 2026-01-27 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-02 | 2026-02-13 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-20 | N | 100% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-13 | 2026-02-13 | 2026-02-13 | jenoronha@deloitte.com | 2025-11-04 04:38 | cell-link@smartsheet.com | 2026-03-23 00:36 | 10 |  | 01.S4 |  |  | 1 | 1 | 1686 | INT-CR1334 | R3 ITC1 | [6 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-23 | 2026-03-23 | 2026-03-23 | [5 empty] | 2026-01-23 | 2026-02-13 |  |  | 2026-03-06 |  |  |  | 1 |  | 3369 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 3/20: follwoing up for approvals from respective teams. FUT all TC and walkthorugh completed 3/13:Dependent on interface objects LOGI1676/77/78/79. 3/5:Dependent on interface objects LOGI1676/77/78/79. 2/24: Not getting decsoped.The enhnacement will be tested with all 4C1 bailment FUTs. Dependent on LOGI1676/77/78/79 2/20: To be tested along with 4C1 FUTs. No descope required. 2/16: As suggested by Tech team, this enhancement is no longer required since logics are covered under interface object. Functional team is checking if this needs to be cancelled. | 2026-02-13 | Y | 99. Logistics |  |  |  | 03/11: E2E FUT in progress along with defect fixes. Current status: E2E FUT in progress Issue: FUT delayed Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/27 |  | 2. Risk |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1971 | LOGE1624 | 04.Enhancement | 02.IF - Intel Foundry | Development of LCSR tool in Fiori | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LCSR_Fiori_App_Development.pptx?d=w89ffaa4261e343c3a0c5f1e47e9b10cf&csf=1&web=1&e=W0nVeb | 02.No | 01.Yes |  | 2024-09-09 | jorge.sanchez@intel.com | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-12-31 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-12-31 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-03 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-03 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-01 | 01.S4 |  |  | 4 | 4 | 1624 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | [5 empty] | 2025-05-02 | 2025-11-05 |  |  | 2026-02-04 |  |  |  | 1 | 08. Not Applicable | 1923 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02: Defect#6761 is with tech for fix, ETA 02/03 for backend, no ETA from Fiori 01/29: All review sessions completed, call scheduled today with Intel PS on way forward for the feedback points 01/22: Third review session completed today morning, additional session planned today evening. Once all review sessions completed. Feedback points will be categorized as Issues/Changes and defects will be raised for the issues 01/19: Additional review sessions scheduled on 01/21 & 01/22. Defect#6378 with tech, no eta 01/12: FUT sent for approval on 01/12 01/05: Defect#5712 is closed, defect#5830 is fixed & retest is in progress ETA 01/05. Defect#5929 yet to be picked up by tech team 12/22:Defect#5712 is with tech team ,backed changes are completed, Defect#5830 is with tech. ETC 01/02.13 TC executed out of 20. 12/15: Defect#5557 is with tech, handover given to tech, no ETA. FUT Approval is planned in S21. 12/08: Defect#5293 is closed, defect#5165, 5136 with tech, no ETA. FUT Approval is planned in S21. 12/01: Open defects 4909, 5025, 5050 11/24: Defect#4518 & 4565 reassigned to tech as still some issues are open 11/18: Defect#4518, 4565, 4612 with tech, FUT started | 2025-11-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3079 | LOGE1609 | 04.Enhancement | 08.EWM | Enhancement for Fiori App development to maintain business rules for Dynamic Disposition process. | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/New%20RICEF%20disposition/R3_IP_Returns_Dynamic%20Disposition%20Fiori%20app.pptx?d=w7cfd5be67cc041a38e39ddd9cfa4a98c&csf=1&web=1&e=gEuFeB | 02.No | 01.Yes |  |  |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-09 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-12-19 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-03-16 04:51 | 10 | 2025-09-03 | 01.S4 |  |  | 4 | 4 | 1609 | INT-CR1005 | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-10 | 2025-09-09 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-02-04 | TM |  |  | 1 |  | 3279 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 02/02: Defect Fix is in progress. Tech ETA to Fix 6612 and 6724 -02/02. Requirement change #6615- ETA 02/05 and #6729 ETA 02/05 01/29: FUT walkthrough completed with business 01/28.Raised 2-deefcts to address the business review comments 02/02. 01/22: FUT document sent to Intel for Review and approval 01/19: FUT document sent to business on 01/16 for review. Additionally, there 3-defects are with tech team to close the feedback comments. 01/13: Tech team still working on Defect #5937 & #5938. Defect #5939 has been re-assigned back to Tech. 5 TC completed. FUT will be on Hold until defects are fixed 01/05:Tech team is working on defects 5423, 5937, 5938 and 5939 (Fiori+Backend) 12/22: Working session is scheduled in Mexico time zone with Abap and Fiori team for faster resolution of defects 12/15: Backend issues are fixed, Fiori changes are still pending. AR: Defect needs to be assigned to Fiori Team. 5423, 5446, 5450 (All Fiori)--Dev ETA: 12/15 | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | Yes | Maintain new "Ship to Plant" Entries in ZTOTC_PARAMS | No |  | No |  | 2026-02-16 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3078 | LOGE1608 | 04.Enhancement | 08.EWM | Enhancement for Fiori App development to maintain business rules for Static Disposition process. | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/New%20RICEF%20disposition/R3_IP_Returns_Static%20Disposition%20Fiori%20App.pptx?d=w7f26dce17d8f42e4807d183ce3ec724f&csf=1&web=1&e=pLHSb3 | 02.No | 01.Yes |  |  |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-09 | 2025-09-12 | 2025-09-19 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-19 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-18 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2025-09-03 | 01.S4 |  |  | 4 | 4 | 1608 | INT-CR1004 | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-10 | 2025-09-09 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-02-18 | 2026-02-18 | 2026-02-18 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-02-04 | TM |  |  | 1 |  | 3278 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 02/16: Intel IT Conditional Approval Received. Awaiting Intel Biz Approval. Minor defects 7089, 7177 are open are being worked on 2/10: Defects 6921 (02/5),7032 are raised based on Intel Feedbacks. Tech team is working on fixes 02/09: Intel IT has provided feedback on 02/06. Team is working to close them on priority 6921 (02/5),7032 defects are raised for Intel Feedbacks. Tech team is working on fixes. 02/02: Defect 6740 is fixed by tech team testing under progress. Defect 6672 (ETA-02/02) is under fix. 01/29: Defect # 6672 is with Tech team for resolution. Tech ETA: 02/02. 01/22: 2 pending scenarios are completed. Defect 6060, 6248, 6302 are closed. Def #6547 is under fix 01/19: Team is working on addressing the business feedback comments. Defects # 6248,6302 are still open with tech team for closing the opens feedback 01/13: Call is scheduled with Intel IT team for open question on the Fiori application and FUT document. 40/42 TC Completed. 01/05: 3 new defects are open 5917, 5923 and 5924. FUT is in progress. 12/22: 1 TC completed today. Other 2 are WIP for today. 26/45 TC Completed. Defects 5721, 5791, 5800 raised to fix the issues. Waiting for Dev ETA. 12/15: FUT is in progress. 2/45 TC Completed. | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | Yes | Maintain new "Ship to Plant" Entries in ZTOTC_PARAMS | No |  | No |  | 2026-02-16 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2684 | LOGE1601 | 04.Enhancement | 08.EWM | Interface between ECD (Excursion Containment Disposition) and SAP S/4 EWM for Inventory status and change (Block/Un-block) | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2684_R3_Interface%20between%20ECD%20and%20S4.pptx?d=w4503a31eb86f449b8e3b632a3c002599&csf=1&web=1&e=Ib73hy | 02.No | 01.Yes |  |  | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-13 | 2025-09-12 | 2025-09-19 | 2026-02-13 | 100% | 2026-04-06 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-04-06 | 2026-02-02 | 2026-02-13 | 2026-02-24 | 100% | 2026-04-06 | 2026-02-02 | 2026-02-06 |  |  | 2026-02-06 | 2026-02-02 | 2026-02-06 |  |  | 2026-02-06 | [5 empty] | 2026-04-06 | 2026-04-06 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-27 | N | 100% | 2026-03-30 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-13 | 2026-02-13 | 2026-02-13 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-04-06 07:13 | 10 | 2025-08-30 | 01.S4 |  |  | 2 | 2 | 1601 |  | R3 ITC1 | [6 empty] | 2025-10-13 | 2025-10-13 | 2025-10-13 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 |  | 2026-02-06 |  |  |  | 2026-02-06 | [6 empty] | 2026-04-06 | 2026-04-06 |  |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | [5 empty] | 2025-10-08 | 2026-02-13 | 2026-02-06 |  | 2026-02-04 | TM |  |  | 1 |  | 3264 | [7 empty] | 4. Completed | 1. Approved no action | 03/27: Approved by IT & Biz. 03/20: FUT completed and shared with business & IT for approval. 03/12: Total 20/32 test cases completed testing.Remaining 12 cases are related automatic reversal of picking.Technical team working on this and working session scheduled with Tech team to complete remaining 12 cases. 03/10: Total 12/32 test cases completed testing.Scheduled daily call with Tech team to complete remaining cases (FUT+TUT). 03/09: Total 8/32 test cases completed testing, Scheduled daily call with Tech team to complete FUT+TUT. 03/06: TUT+ FUT in progress parallely, encountered few issues for which call is scheduled with tech team. Total scenario tested 06/32. 03/02: Received object from tech on 02/28. FUT to initiate from today. 02/27: Awaiting tech team confirmation on build completion. 02/23: Awaiting tech team confirmation on build completion. 02/20: Build in progress, no further update from tech. 2/16: Build is in progress. Build ETA 2/20. 2/10: FS walk through completed. Build in progress | 2026-02-13 | Y | 99. Logistics |  |  |  | 03/24 : Submitted for Approval. |  | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2026-04-06 | 2026-04-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3058 | LOGE1596 | 04.Enhancement | 02.IF - Intel Foundry | Summary Reconciliation and Inventory Snapshot data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B59D2938A-860D-4A08-85E3-2D12752BFB5D%7D&file=3058__R3_FTS_IF_L-060-180_Inventory%20snapshot_SummaryReconciliation_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-09-19 | 2025-09-19 | 100% | 2025-09-17 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-15 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1596 |  | R3 ITC1 | [6 empty] | 2025-09-17 | 2025-09-19 | 2025-09-17 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | [5 empty] | 2025-09-19 | 2025-12-05 |  |  | 2026-01-07 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3245 |  |  | WIINGS |  |  |  |  | 1. On Track | 17. FUT In progress | 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 11/24: S4 FUT is in progress. 5.1/5.2 is planned for S21 11/18: FUT planned in S21. | 2025-12-05 | Y | 99. Logistics | GXO | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3055 | LOGE1592 | 04.Enhancement | 02.IF - Intel Foundry | MergePick (Pick Warehouse task)data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B007318A6-A2AA-4F0F-8E84-6602A15320D5%7D&file=3055__R3_FTS_IF_LO-160-050_MergePick_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-09-19 | 2025-09-19 | 100% | 2025-09-17 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1592 |  | R3 ITC1 | [6 empty] | 2025-09-17 | 2025-09-19 | 2025-09-17 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-09-19 | 2025-12-05 |  |  | 2026-01-23 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3249 |  |  | WIINGS |  |  |  |  | 4. Completed | 17. FUT In progress | 01/19 Awaiting approval as the review comments are addressed 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 11/24: S4 FUT is in progress. 5.1/5.2 is planned for S21 11/18: FUT planned in S21. | 2025-12-05 | Y | 99. Logistics | GXO | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3054 | LOGE1590 | 04.Enhancement | 02.IF - Intel Foundry | MergeReplen(Putaway Warehouse task) data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB45AC483-B67A-48FE-9AE5-86656129E736%7D&file=3054_R3_FTS_IF_L-040-120_MergeReplen_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-09-19 | 2025-09-19 | 100% | 2025-09-17 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1590 |  | R3 ITC1 | [6 empty] | 2025-09-17 | 2025-09-19 | 2025-09-17 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | [5 empty] | 2025-09-19 | 2025-12-05 |  |  | 2026-01-07 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3244 |  |  | WIINGS |  |  |  |  | 1. On Track | 17. FUT In progress | 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 11/24: S4 FUT is in progress. 5.1/5.2 is planned for S21 11/18: FUT planned in S21. | 2025-12-05 | Y | 99. Logistics | GXO | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3053 | LOGE1588 | 04.Enhancement | 02.IF - Intel Foundry | MergeItem (Product master)data in XML format from SAP EWM to Kommand auto-store | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B05E3F4BE-5C81-4872-AE2B-71D823366E0C%7D&file=3053_R3_FTS_IF_L-060-220_MergeItem_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-09-19 | 2025-09-19 | 100% | 2025-09-17 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1588 |  | R3 ITC1 | [6 empty] | 2025-09-17 | 2025-09-19 | 2025-09-17 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-09-19 | 2025-12-05 |  |  | 2026-01-07 | TM | GXO WIINGS Only | TRUE | 1 | 04.7 Logistics - GFM | 3241 |  |  | WIINGS |  |  |  |  | 4. Completed | 17. FUT In progress | 01/05: Awaiting approval from business 12/22: FUT Sent to Intel Review 11/24: S4 FUT is in progress. 5.1/5.2 is planned for S21 11/18: FUT planned in S21. | 2025-12-05 | Y | 99. Logistics | GXO | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 3060 | LOGE1572_IP | 04.Enhancement | 01.IP - Intel Product | SAP GUI T-code to Move stock from Blocked to unblock Status | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B11A34652-8CDD-4AE7-94BC-A55191138020%7D&file=Console%203060_Intransit%20Inventory.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-09 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-02 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-19 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-09-02 | 01.S4 |  |  | 2 | 2 | 1572 |  | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-26 | 2025-09-09 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | [5 empty] | 2025-09-26 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 1 |  | 3203 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 1/16: Following for approval. 01/05: Basic functionality working. Defect 5751 has open issues. Call set with tech team for a working session. 12/22: tech has fixed defect 5751 retest in progress. TC 0/6 12/15: FUT started today 12/15. No blocker as such. TC 0/6 | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3060 | LOGE1572_IF | 04.Enhancement | 02.IF - Intel Foundry | SAP GUI T-code to Move stock from Blocked to unblock Status | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B11A34652-8CDD-4AE7-94BC-A55191138020%7D&file=Console%203060_Intransit%20Inventory.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2025-10-09 | 2025-09-19 | 2025-09-26 | 2025-11-20 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-07 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-09-02 | 01.S4 | LOGE1572_IP | 02.High | 0.4 | 0.4 | 1572 |  | R3 ITC1 | [6 empty] | 2025-10-09 | 2025-10-09 | 2025-10-09 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | [5 empty] | 2025-09-26 | 2025-12-05 |  |  | 2026-01-23 |  |  |  | 1 |  | 3205 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 2/5: New comments provided by IT. Comments are being addressed and call scheduled for today 9PM IST. 2/2: All the review comments have been addressed and resent for approval 1/29: defect fixed and retest in progress. 1/27: Tech still working on Defect 6524. EAT 1/27 1/23: Defect in progress with tech. 1/22: Addressing review comments. Delay in closure as BI1 system is down. 1/20: following for IT /PS approval. 1/19: under Intel review. 1/16: Defect retest in progress. 01/05: Basic functionality working. Defect 5751 has open issues. Call set with tech team for a working session. 12/22: tech has fixed defect 5751 retest in progress. TC 0/6 12/15: FUT started today 12/15. No blocker as such. TC 0/6 | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3040 | LOGE1570 | 04.Enhancement | 01.IP - Intel Product | CR0856 - Enhancement required (a report) to post the goods receipt for the additional line items of the text PO once the first line item of the text PO​, if fully received or delivery complete indicator is set. | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3B0E14F5-345A-4B6E-9BCC-5AAD58C5F726%7D&file=3040_PTP_LE%20-%20CR0856_Enhancement%20required%20(a%20report)%20to%20post%20GR%20for%20the%20remaining%20line%20items%20of%20the%20text%20PO%20based%20on%20GR%20or%20Delivery%20completion%20of%20first%20PO%20line.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-10-10 | 2025-09-26 | 100% | 2025-09-29 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 |  |  | 2025-11-26 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1570 | INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-29 | 2025-10-10 | 2025-09-29 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | [5 empty] | 2025-10-10 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 1 |  | 3200 | [7 empty] | 4. Completed | 1. Approved no action | 12/15 - Received approval from Intel 12/08 - All Review comments are addressed, Awaiting further feedback/approval from Intel IT & Business/PS 12/01 - 5 TCs are completed out of 12. Defect# 5106 is raised, blocking rest of the TCs ETA from Tech is 12/01. 11/25: Build completion ETA is 11/26. 10+ TC's to be started post build 11/24: Dev has shared the ETA 11/26 to complete the build. Post that FUT can be started. Plan to complete the FUT 12/5. 11/18 - Raid ID:- 03058 is raised as Object Delivery is delayed from Tech, FUT is in roadblock 11/14 - TCs are being drafted for E2E Testing ETA 11/14 Today. Tech confirmed the ETA for this Object Delivery as 11/17 | 2025-12-05 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3039 | LOGE1569_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to change billing status based on ship reason in ISM | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCE448874-5697-4B2C-99C3-09B3CED2EAB2%7D&file=3039%20-%20Enhancement%20to%20change%20billing%20status%20based%20on%20ship%20reason%20in%20ISM.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-11 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2025-10-30 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1 | 1569 |  | R3 ITC1 | [6 empty] | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-09-10 | 2025-11-05 |  |  | 2025-12-03 |  |  |  | 1 |  | 3198 | [7 empty] | 4. Completed | 19. Incomplete Build | 11/24: Defect 4550,4854 completed. Retest in progress ETA 11/ 28 11/18: Development of the object is not complete 11/14: Partially developed. Defect 4550 | 2025-11-05 | N | 99. Logistics | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3039 | LOGE1569_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to change billing status based on ship reason in ISM | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCE448874-5697-4B2C-99C3-09B3CED2EAB2%7D&file=3039%20-%20Enhancement%20to%20change%20billing%20status%20based%20on%20ship%20reason%20in%20ISM.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-11 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2025-10-30 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-30 | 01.S4 | LOGE1569_IP | 03.Medium | 0.2 | 0.2 | 1569 |  | R3 ITC1 | [6 empty] | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-09-10 | 2025-11-05 |  |  | 2025-12-03 |  |  |  | 1 |  | 3199 | [7 empty] | 4. Completed | 19. Incomplete Build | 12/1: Working with tech on defect 4854. 11/24: Defect 4550,4854 completed. Retest in progress ETA 11/ 28 11/18: Development of the object is not complete 11/14: Partially developed. Defect 4550 | 2025-11-05 | N | 99. Logistics | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3018 | LOGE1567 | 04.Enhancement | 01.IP - Intel Product | TM - GTT: SAP S/4 Return Deliveries relevant for TM are not propagating to BN4L GTT under “Monitor Outbound Deliveries” | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6CBEA0C6-F7D9-4FB9-8960-05C33BAC6AC2%7D&file=Propagate%20S4%20Returns%20Delivery%20to%20GTT.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-10-10 | 2025-10-17 | 2025-12-12 | 100% | 2026-01-02 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-02 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-02 | [15 empty] | 2026-01-02 | 2026-01-02 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-09-02 | 01.S4 |  |  | 1 | 1 | 1567 |  | R3 ITC1 | [6 empty] | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 2026-01-02 | 2026-01-09 | 2026-01-02 | 2026-01-02 | [12 empty] | 2026-01-02 | 2026-01-02 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-10-03 | 2026-01-09 |  |  | 2026-01-09 | TM |  |  | 1 |  | 3195 | [7 empty] | 3. Off Track | 17. FUT In progress | 01/05: FUT in progress, TUT document received on 2nd Jan. TC 2 of 8 completed 12/15: Build yet to start | 2026-01-09 | Y | 99. Logistics |  |  |  | Adjustment in the Object id |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2026-01-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2906 | LOGE1554 | 04.Enhancement | 02.IF - Intel Foundry | Straddle Plant to be automatically complete the Goods Receipt and write of the inventory | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2906_RX_FTS_IP%20IF_LOGL-060_080_Straddle%20Receiving%20and%20write%20off_RICEFW%20Intake%20form.pptx?d=waa94a6a1ad5b4515ad0ab73f3b50fa5a&csf=1&web=1&e=sxKoXy | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-26 | 2025-09-26 | 100% | 2025-10-08 | 2025-09-12 | 2025-09-19 | 2025-12-12 | 100% | 2026-01-02 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-01-02 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-01-02 | [15 empty] | 2026-01-02 | 2026-01-02 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-20 | N | 100% | 2026-03-27 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | cell-link@smartsheet.com | 2026-03-27 03:32 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1 | 1554 |  | R3 ITC1 | [6 empty] | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 2026-01-02 | 2026-01-07 | 2026-01-02 | 2026-01-02 | [12 empty] | 2026-01-02 | 2026-01-02 |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-09-26 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 1 |  | 3201 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 3/20: 8291 reopened as facing new issues like dump errors, issues in processing multiple payloads, escalated to tech and is WIP. 3/13:Defect 8291 being fixed by tech, issues related to processing of data received from ECA and others. FUT blocked till defect is fixed. 3/6: Middleware has completed the TUT on 3/5. FUT to be started from today 2/24: Middleware following up with ECA for access issue. No ETA yet 2/20: 2 test case documenation in progress. ETA 2/20 2/16: Defect 7319 raised on 2/13 for Enhancement not triggering. Awaiting ETA from tech team. 2/9: Dependency on ECA development CR1195. Middleware development in progress. ETA: 02/11 2/5: Dependency on ECA development CR1195. ETA: 02/11 2/2: Dependency on ECA development CR1195. ETA: 02/11 1/30: Dependency on ECA development CR1195. ETA: 02/11 1/27: ECA development is in progress and ETA awaited from ECA team. 1/22: ECA development is in progress and ETA awaited from ECA team. 1/20: Dependent ECA development in progress. No ETA committed by ECA team. CR - 1195 in progress. 1/16: Dependent ECA development in progress. No ETA committed by ECA team. CR - 1195 in progress. | 2025-12-05 | N | 99. Logistics |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | Defects | Complete | R3 Build & UT Sprint 21 |  | 2026-01-07 | 2026-01-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3046 | LOGE1535 | 04.Enhancement | 01.IP - Intel Product | New custom Fiori application for Undo Disposition and Confirm Disposition | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/3046_R3_IP_Returns_SAQ%20and%20Undo-Disposition.pptx?d=wf34aca32dfee42ac9b724e7e33f13aa3&csf=1&web=1&e=msNl49 | 02.No | 01.Yes |  |  |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-09-08 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2026-02-03 | 2025-10-08 | 2025-11-05 | 2026-03-20 | 100% | 2026-03-29 | 2025-10-08 | 2025-11-05 | 2026-03-20 | 100% | 2026-03-29 | [15 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-02-27 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-16 | 2026-03-04 | 2026-03-20 | N | 100% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | cell-link@smartsheet.com | 2026-03-28 21:33 | 10 | 2025-07-26 | 01.S4 |  |  | 2 | 2 | 1535 |  | R3 ITC1 | [6 empty] | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2026-02-03 | 2026-02-03 | 2026-02-03 |  | 2026-03-29 | 2026-03-29 | 2026-03-29 | 2026-03-29 | [12 empty] | 2026-03-29 | 2026-03-29 |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | [5 empty] | 2025-08-12 | 2025-11-05 |  |  | 2026-03-04 | TM |  |  | 1 |  | 3154 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/18: Defect #8315 fix is in progress by Tech Team. Tech ETA 3/18.Func Team is workimg on Intel IT feedback Opens and supporting Tech team in defect fix.03/12: Intel IT has provided additional feedback comments on the FUT document. Defect 8180 is being worked upon by tech with ETA 03/13 03/06: FUT document sent for intel review and apporval. 02/27: Build is in progress by Tech team. POC is in progress for posting the inspection document to S4 from EWM . 02/20: Func Team is working with Tech team on the solution suggested by SAP 02/16: Functional and Tech team is working together with SAP on the POC for WT Creation 02/10: FS walkthrough given to Tech team on 02/09. Next Action: Tech to start the build 01/19: Team is performing the POC on the alternate solution. We have debug the queue. Looks like there is a field called FU_CODE_ERP in the queue and that has a value "S". We think the system is looking for Scrap (0012) because of this indictor although the code is 0031. We are not sure yet. POC will be continue today based on availability of technical team. 01/13: Team is Working on the alternate solution. GR was not possible due to SAP note implemntation and dump issue 01/05: Waiting for SAP response. Reminder sent to SAP. 12/22: FM is not working as expected. Shared our analysis to SAP. Waiting for SAP response. 12/15:SAP has provided FM under OSS message-1309946/2025. Team is doing the POC with onsite tech team. | 2025-11-05 | N | 99. Logistics |  |  |  | 03/11: Awaiting Approval Current status: Awaiting Approval. Issue: N/A Next steps: Awaiting Approval Help needed: N/A FUT ETA: 03/13 |  | 2. Risk |  | Defects | Complete | R3 Build & UT Sprint 23+ |  | 2026-03-29 | 2026-03-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3003 | LOGE1526_IP | 04.Enhancement | 01.IP - Intel Product | Automatic HAWB assignment for Freight Forwarders( ISM/ Prospal STO's) | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3003_R3_FTS_IPIF-%20Automatic%20assignment%20of%20HAWB.pptx?d=wca31f899dddc42128c23a68148547777&csf=1&web=1&e=YVCEnc | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-14 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-14 | [15 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-28 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 |  |  | 2 | 2 | 1526 | INT-CR0748 | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14 | [12 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 |  | 3139 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: All A/Rs addressed. Follow up approval request mail to be sent today 01/19: Intel review call on 1/20. 01/12: FUT In progress (10 /11 TC completed) 01/05: Defect 5823 (internal CR) WIP, TC 9 of 11 completed 12/22: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 23 |  | 2026-02-14 | 2026-02-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3003 | LOGE1526_IF | 04.Enhancement | 02.IF - Intel Foundry | Automatic HAWB assignment for Freight Forwarders( ISM/ Prospal STO's) | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3003_R3_FTS_IPIF-%20Automatic%20assignment%20of%20HAWB.pptx?d=wca31f899dddc42128c23a68148547777&csf=1&web=1&e=YVCEnc | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-02-17 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-17 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-17 | [15 empty] | 2026-02-17 | 2026-02-17 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-28 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 | LOGE1526_IP | 02.High | 0.4 | 0.4 | 1526 | INT-CR0748 | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | [12 empty] | 2026-02-17 | 2026-02-17 |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 |  | 3140 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: All A/Rs addressed. Follow up approval request mail to be sent today 01/19: Intel review call on 1/20. 01/05: Working session for TUT+FUT in progress 12/22: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 23 |  | 2026-02-17 | 2026-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3027 | LOGE1522 | 04.Enhancement | 08.EWM | WIP HU overpacking validation for unique TU | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3027_R3_IF_FTS_EWM_WIP%20HU%20overpacking%20validation%20for%20unique%20TU.pptx?d=w1743d8a9a1264c2cb9980b2d67782026&csf=1&web=1&e=Z6G0Tm | 01.Yes | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-05 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-14 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1 | 1522 | INT-CR0846 | R3 ITC1 | [6 empty] | 2025-09-05 | 2025-09-05 | 2025-09-05 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | [5 empty] | 2025-08-29 | 2025-12-05 |  |  | 2026-01-07 | TM |  |  | 1 |  | 3157 | [7 empty] | 4. Completed | 1. Approved no action | 01/14: FUT approved on 01/13 and marked as completed. 01/12: All comments are addressed, awaiting biz approval. 01/05: FUT sent to business and IT for review & approval. 12/15: FUT doc pending due to Defect 5575. Will be sent for intel approval today. Business workshop scheduled for today. Defect 5575 open for this. Committed date to business was 12/13. 12/8: TC 4/8 Tested. FUT in Process based on material received from Core FTS team. Rest of the test case, need to be tested with MPL Boundary app which is not yet ready. 11/24-Connect with business & Loftware happening tomorrow as per R2 design. ETC to send for intel review 11/28. 11/18- FUT to be started on 11/19. | 2025-12-05 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3026 | LOGE1521 | 04.Enhancement | 08.EWM | WIP Overpack Label Printing | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3026_R3_IF_FTS_EWM_WIP%20Overpack%20Label.pptx?d=wc24b790e476b4fc5a03209c107c801f8&csf=1&web=1&e=u43dEQ | 01.Yes | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-05 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1 | 1521 | INT-CR0846 | R3 ITC1 | [6 empty] | 2025-09-05 | 2025-09-05 | 2025-09-05 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | [5 empty] | 2025-08-29 | 2025-12-05 |  |  | 2026-01-09 | TM |  |  | 1 |  | 3156 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 01/05: 4 out of 8 TC tested, Rest of the test cases, need to be tested with MPL Boundary app which is not yet ready. BApp--Loftware, Defect 5359 (Defect open since 2 weeks now) 12/15: TC 4/8 Tested. FUT in Process based on material received from Core FTS team. Rest of the test case, need to be tested with MPL Boundary app which is not yet ready. BApp--Loftware, Defect 5359 (Defect open since a week now) 11/24-Connect with business & Loftware happening tomorrow as per R2 design. ETC to send for intel review 11/28. 11/18- FUT to be started on 11/19. | 2025-12-05 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2992 | LOGE1520 | 04.Enhancement | 08.EWM | Enhancement to enable WIP movement for receiving between Factory to EWM Warehouse and STO from Warehouse to Factory location.​ | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2992_R3_IF_FTS_EWM_L3name_WIP%20movement%20for%20receiving%20between%20Factory%20to%20Warehouse%20and%20Warehouse%20to%20Factory.pptx?d=wafb39386237640a08778d5895dd6bda9&csf=1&web=1&e=18LcVf | 01.Yes | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-05 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-07-12 10:06 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-30 | 01.S4 |  |  | 1 | 1 | 1520 |  | R3 ITC1 | [6 empty] | 2025-09-05 | 2025-09-05 | 2025-09-05 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-08-29 | 2025-10-31 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3155 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: All open comments are addressed, awaiting business & IT approval. 12/15: All open comments are addressed, awaiting business & IT approval. Call scheduled on 12/15 for follow-up. 12/08: Business IT review updates are in progress, workshop is planned again to go through the FUT, FUT sent on 12/01. 12/01: FUT sent to business for review and approval on 12/01. 11/24: FUT in progress (4/6 TCs done). ETC 11/27 to send for Intel review. 11/18: Defect 4459 is still with technical team for resolution. | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1509_IP | 04.Enhancement | 01.IP - Intel Product | Tendering- FIORI app for Approval Hierarchy (Assign Delegate) | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-22 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-07-01 06:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-25 | 01.S4 |  |  | 0.5 | 0.5 | 1509 |  | R3 ITC1 | [6 empty] | 2025-07-22 | 2025-08-13 | 2025-07-22 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 |  | 2025-09-12 | 2025-10-10 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-26 | 2025-10-08 | 2025-09-26 | [5 empty] | 2025-04-18 | 2025-10-10 |  |  | 2025-10-08 | TM |  |  | 1 | 08. Not Applicable | 3110 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1509_IF | 04.Enhancement | 02.IF - Intel Foundry | Tendering- FIORI app for Approval Hierarchy (Assign Delegate) | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-22 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-07-01 06:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-25 | 01.S4 | LOGE0625_IP | 04.Low | 0.1 | 0.1 | 1509 |  | R3 ITC1 | [6 empty] | 2025-07-22 | 2025-08-13 | 2025-07-22 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 |  | 2025-09-12 | 2025-10-10 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-26 | 2025-10-08 | 2025-09-26 | [5 empty] | 2025-04-18 | 2025-10-10 |  |  | 2025-10-08 | TM |  |  | 1 | 08. Not Applicable | 3109 | [7 empty] | 1. On Track | 14. B-App Under Test |  | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3024 | LOGE1507 | 04.Enhancement | 08.EWM | Custom enhancement to enable the integration of both IF(BI1) /IP(DI0) TM system and decentralized EWM system (EI1). | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/FS%20Drafts%20-%20OTC%20IP%20Returns%20EWM/EWM-TM%20Integration/TM_EWM_RICEFW%20Intake%20Form.pptx?d=wc9275210495048069910bddea2f4caa7&csf=1&web=1&e=kEXGQs | 02.No | 01.Yes |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-04 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-27 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-27 | [15 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-06-27 04:28 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-08-30 | 01.S4 |  |  | 2 | 2 | 1507 | INT-CR0834 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-13 | 2025-08-04 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-11-27 | 2025-12-05 | 2025-11-27 | 2025-11-27 | [12 empty] | 2025-11-27 | 2025-11-27 |  |  | 2025-11-06 | 2025-11-07 | 2025-11-06 | [5 empty] | 2025-08-12 | 2025-12-05 |  |  | 2025-11-07 | TM |  |  | 1 |  | 3107 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/31: Under Intel review 10/24 - FUT completed but TUT is not approved yet. Working in offline | 2025-12-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2650 | LOGE1506 | 04.Enhancement | 08.EWM | Enhancement to bring attachments of images from Material master (MM03) to the Product Master in EWM and display them in RFUI screen | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB588A845-FB2C-461F-9B67-2BE108F811D1%7D&file=RICEFW%20console%20for%20fetching%20Images%20from%20material%20master.pptx&wdLOR=c0538172F-3B63-4E68-8778-17F5753FDDE8&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-11-04 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-04 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-04 | [15 empty] | 2025-11-04 | 2025-11-04 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-31 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jonsanders@deloitte.com | 2024-12-19 08:23 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-18 | 01.S4 |  |  | 2 | 2 | 1506 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-04 | 2025-11-04 | 2025-11-04 |  | 2025-11-04 | 2025-11-05 | 2025-11-04 | 2025-11-04 | [12 empty] | 2025-11-04 | 2025-11-04 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-16 | 2025-10-31 |  |  | 2025-12-05 | TM | WIINGS Only | TRUE | 1 |  | 1841 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Awaiting approval, reminder sent 4 times. 11/24: sent for intel approval around 12th nov. Following up on approval.Reminder sent. 11/04: Defect 4013 open with tech team | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1928 | LOGE1488_IP | 04.Enhancement | 01.IP - Intel Product | Invoice notification- Notification to carrier for POD and internal notification for carrier response | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-07-18 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-11-20 | 100% | 2026-02-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-02 | [15 empty] | 2026-02-02 | 2026-02-02 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-23 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-06-04 21:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1488 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-08-15 | 2025-07-21 |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | [12 empty] | 2026-02-02 | 2026-02-02 |  |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | [5 empty] | 2025-08-15 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 | 08. Not Applicable | 3080 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed 01/19:Intel Review on 01/21 01/12: TUT+FUT WIP and 72/102 TC completed 01/05: Tech build completed, FUT started 5th Jan 12/22: Issue in tech build. Build yet to complete | 2025-12-05 | N | 99. Logistics |  |  |  | 1210: Build ETA 1219. TUT and FUT to be planned in parallel. Add 5.2 activity in S21. |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-02 | 2026-02-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1488_IF | 04.Enhancement | 02.IF - Intel Foundry | Invoice notification- Notification to carrier for POD and internal notification for carrier response | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-07-18 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-11-20 | 100% | 2025-12-23 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-27 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-06-04 21:48 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1488_IP | 02.High | 0.4 | 0.4 | 1488 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | [5 empty] | 2025-08-15 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 | 08. Not Applicable | 3079 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed 01/19: Intel review planned for 1/21 01/12: TUT+FUT WIP and 72/102 TC completed 01/05: Issue in tech build. Build yet to complete 12/22: Issue in tech build. Build yet to complete | 2025-12-05 | N | 99. Logistics |  |  |  | 1210: Build ETA 1219. TUT and FUT to be planned in parallel. Add 5.2 activity in S22. |  |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1487_IP | 04.Enhancement | 01.IP - Intel Product | Carrier notification- Carrier contact table BRF+ maintenance | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-21 | [15 empty] | 2025-08-21 | 2025-08-21 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1487 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-09-19 | 2025-08-21 |  | 2025-08-21 | 2025-10-10 | 2025-08-21 | 2025-08-21 | [12 empty] | 2025-08-21 | 2025-08-21 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3077 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1487_IF | 04.Enhancement | 02.IF - Intel Foundry | Carrier notification- Carrier contact table BRF+ maintenance | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-21 | [15 empty] | 2025-08-21 | 2025-08-21 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1487_IP | 02.High | 0.4 | 0.4 | 1487 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-09-19 | 2025-08-21 |  | 2025-08-21 | 2025-10-10 | 2025-08-21 | 2025-08-21 | [12 empty] | 2025-08-21 | 2025-08-21 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3076 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1486_IP | 04.Enhancement | 01.IP - Intel Product | Carrier notification- Cancellation email | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1486 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-22 | 2025-10-31 | 2025-10-22 | [5 empty] | 2025-07-16 | 2025-10-03 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3075 | [10 empty] | 2025-10-03 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-29 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1486_IF | 04.Enhancement | 02.IF - Intel Foundry | Carrier notification- Cancellation email | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1486_IP | 02.High | 0.4 | 0.4 | 1486 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-22 | 2025-10-31 | 2025-10-22 | [5 empty] | 2025-07-16 | 2025-10-03 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3074 | [10 empty] | 2025-10-03 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1485_IP | 04.Enhancement | 01.IP - Intel Product | Carrier notification- Acceptance and Rejection email | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-01 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-27 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1485 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-01 | 2025-10-01 | 2025-10-01 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-27 | 2025-12-05 | 2025-11-27 | [5 empty] | 2025-07-16 | 2025-10-08 |  |  | 2025-12-05 | TM |  |  | 1 | 08. Not Applicable | 3073 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24: FUT document sent for final review post all the corrections addressed 11/18: FUT done. Under Internal review. Intel review targeted- 11/19 11/14: FUT done. Under Internal review. Intel review targeted- 11/18 11/11: 4/8 TC-passed ,3 failed and Defect 4418 raised. Rest WIP 11/04: Dependent on CR work to complete. CR yet to be taken up by DEV team 10/10: Dependent RICEFWs delivered for FUT in S18. Hence FUT will be executed in S19. Dependent RICEFWs delivered for FUT in S18. Hence FUT will be executed in S19. | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1485_IF | 04.Enhancement | 02.IF - Intel Foundry | Carrier notification- Acceptance and Rejection email | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-01 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-27 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-05-30 05:00 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1485_IP | 02.High | 0.4 | 0.4 | 1485 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-01 | 2025-10-01 | 2025-10-01 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-27 | 2025-12-05 | 2025-11-27 | [5 empty] | 2025-07-16 | 2025-10-08 |  |  | 2025-12-05 | TM |  |  | 1 | 08. Not Applicable | 3072 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24: FUT document sent for final review post all the corrections addressed 11/18: FUT done. Under Internal review. Intel review targeted- 11/19 11/14: FUT done. Under Internal review. Intel review targeted- 11/18 11/11: 4/8 TC-passed ,3 failed and Defect 4418 raised. Rest WIP 11/04: Dependent on CR work to complete. CR yet to be taken up by DEV team 10/10: Dependent RICEFWs delivered for FUT in S18. Hence FUT will be executed in S19. Dependent RICEFWs delivered for FUT in S18. Hence FUT will be executed in S19. | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1484_IP | 04.Enhancement | 01.IP - Intel Product | Invoice notification- Notification to carrier for Invoice | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-23 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1484 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | [5 empty] | 2025-07-16 | 2025-10-31 |  |  | 2026-01-23 | TM |  |  | 1 | 08. Not Applicable | 3070 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed 01/19:Intel Review on 01/21 01/12: Defect fix complete, Documentation in progress 01/05: Tech build completed, FUT started 5th Jan 12/22: Dependency on LOGE1488 | 2025-10-31 | N | 99. Logistics |  |  |  | 1211: Dependency with LOGE1488_IP. To be tested together. 5.1 is planned in S21. 5.2 activity is S22 |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1484_IF | 04.Enhancement | 02.IF - Intel Foundry | Invoice notification- Notification to carrier for Invoice | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-11-13 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-13 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-27 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1484_IP | 02.High | 0.4 | 0.4 | 1484 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | [5 empty] | 2025-07-16 | 2025-10-31 |  |  | 2026-01-23 | TM |  |  | 1 | 08. Not Applicable | 3069 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed. Updated documentation to be sent once BI1 system is up(BI1 system down since 01/21). High priority OSS raised with SAP to resolve system issue 01/19: Defect fix in progress 01/12: Defect fix complete, Documentation in progress 01/05: Issue in tech build. Build yet to complete 12/22: Dependency on LOGE1488 | 2025-10-31 | N | 99. Logistics |  |  |  | 1211: Dependency with LOGE1488_IF. To be tested together. 5.1 is planned in S21. 5.2 activity is S22 |  |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1483_IP | 04.Enhancement | 01.IP - Intel Product | Invoice notification- Notification to carrier for dispute | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2026-01-06 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2026-01-06 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-23 | N | 100% | 2026-01-27 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1483 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | [5 empty] | 2025-07-16 | 2025-10-31 |  |  | 2026-01-09 | TM |  |  | 1 | 08. Not Applicable | 3066 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed 01/19 Defect fix in progress. 01/12: Defect fix complete, Documentation in progress 01/05: Tech build completed, FUT started 5th Jan 12/22: Dependency on LOGE1488 | 2025-10-31 | N | 99. Logistics |  |  |  | 1211: Dependency with LOGE1488_IP. To be tested together. 5.1 is planned in S21. 5.2 activity is S22 |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1483_IF | 04.Enhancement | 02.IF - Intel Foundry | Invoice notification- Notification to carrier for dispute | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-27 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-02-21 | 01.S4 | LOGE1483_IP | 02.High | 0.4 | 0.4 | 1483 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | [5 empty] | 2025-07-16 | 2025-10-31 |  |  | 2026-01-23 | TM |  |  | 1 | 08. Not Applicable | 3065 | [7 empty] | 1. On Track | 17. FUT In progress | 01/22: Intel review call done in IST morning. A/R being addressed. Updated documentation to be sent once BI1 system is up(BI1 system down since 01/21). High priority OSS raised with SAP to resolve system issue 01/19: Defect fix in progress 01/12: Defect fix complete, Documentation in progress 01/05: Issue in tech build. Build yet to complete 12/22: Dependency on LOGE1488 | 2025-10-31 | N | 99. Logistics |  |  |  | 1211: Dependency with LOGE1488_IF. To be tested together. 5.1 is planned in S21. 5.2 activity is S22 |  |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1482_IP | 04.Enhancement | 01.IP - Intel Product | Tendering- Internal Notification mail | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-25 | 01.S4 |  |  | 1 | 1 | 1482 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2025-07-16 | 2025-10-03 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3068 | [7 empty] | 4. Completed | 17. FUT In progress | 10/31 : Final document sent to Intel. Awaiting approval 10/22: TC added post review, WIP to be sent for approval | 2025-10-03 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1482_IF | 04.Enhancement | 02.IF - Intel Foundry | Tendering- Internal Notification mail | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-25 | 01.S4 | LOGE1482_IP | 03.Medium | 0.2 | 0.2 | 1482 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2025-07-16 | 2025-10-03 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3067 | [7 empty] | 4. Completed | 17. FUT In progress | 10/31 : Final document sent to Intel. Awaiting approval 10/22: TC added post review, WIP to be sent for approval | 2025-10-03 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1481_IP | 04.Enhancement | 01.IP - Intel Product | Tendering- Approval Process with Purchase group determination | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-25 | 01.S4 |  |  | 1 | 1 | 1481 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3071 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/31 : Final document sent to Intel. Awaiting approval 10/22: TC added post review, WIP to be sent for approval | 2025-11-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1481_IF | 04.Enhancement | 02.IF - Intel Foundry | Tendering- Approval Process with Purchase group determination | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-05-29 04:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-25 | 01.S4 | LOGE1481_IP | 03.Medium | 0.2 | 0.2 | 1481 | INT-CR0764 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 3064 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/31 : Final document sent to Intel. Awaiting approval 10/22: TC added post review, WIP to be sent for approval | 2025-11-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2967 | LOGE1462_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Send Event # Estimated Time of Arrival (ETA) as a separate event from GTT to S/4 TM FO. Unplanned events needs to be propagated to S/4 along with IATA Code and Reason codes | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Sending%20events%20from%20GTT%20to%20S4%20based%20on%20message%20source%20type%5B39%5D%20%20-%20%20Read-Only.pptx?d=wb9e48591a61840feab1f9915237d8dbc&csf=1&web=1&e=ih383B | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1462 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-14 | 2025-12-05 | 2025-11-14 | [5 empty] | 2025-07-18 | 2025-10-03 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3036 | [7 empty] | 4. Completed | 1. Approved no action | 11/14: Approval received 11/11: IT approval received, business approval pending 11/04: FUT done. Documentation WIP. internal review in progress. Intel review by 11/07 | 2025-10-03 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2967 | LOGE1462_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: Send Event # Estimated Time of Arrival (ETA) as a separate event from GTT to S/4 TM FO. Unplanned events needs to be propagated to S/4 along with IATA Code and Reason codes | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Sending%20events%20from%20GTT%20to%20S4%20based%20on%20message%20source%20type%5B39%5D%20%20-%20%20Read-Only.pptx?d=wb9e48591a61840feab1f9915237d8dbc&csf=1&web=1&e=ih383B | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 | LOGE1462_IP | 03.Medium | 0.2 | 0.2 | 1462 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-14 | 2025-12-05 | 2025-11-14 | [5 empty] | 2025-07-18 | 2025-10-03 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3037 | [7 empty] | 4. Completed | 1. Approved no action | 11/14: Approval received 11/11: IT approval received, business approval pending 11/04: FUT done. Documentation WIP. internal review in progress. Intel review by 11/07 | 2025-10-03 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2967 | LOGE1461_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: To propagate events to S/4 TM Freight order reported by GXS by Bypassing value (Message type mapping) | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Sending%20events%20from%20GTT%20to%20S4%20based%20on%20message%20source%20type%5B39%5D%20%20-%20%20Read-Only.pptx?d=wb9e48591a61840feab1f9915237d8dbc&csf=1&web=1&e=ih383B | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1461 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-14 | 2025-12-05 | 2025-11-14 | [5 empty] | 2025-07-18 | 2025-10-03 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3034 | [7 empty] | 4. Completed | 1. Approved no action | 11/14: Approval received 11/11: IT approval received, business approval pending 11/04: FUT done. Documentation WIP. internal review in progress. Intel review by 11/07 | 2025-10-03 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2967 | LOGE1461_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: To propagate events to S/4 TM Freight order reported by GXS by Bypassing value (Message type mapping) | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Sending%20events%20from%20GTT%20to%20S4%20based%20on%20message%20source%20type%5B39%5D%20%20-%20%20Read-Only.pptx?d=wb9e48591a61840feab1f9915237d8dbc&csf=1&web=1&e=ih383B | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 | LOGE1461_IP | 03.Medium | 0.2 | 0.2 | 1461 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-14 | 2025-12-05 | 2025-11-14 | [5 empty] | 2025-07-18 | 2025-10-03 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3035 | [7 empty] | 4. Completed | 1. Approved no action | 11/14: Approval received 11/11: IT approval received, business approval pending 11/04: FUT done. Documentation WIP. internal review in progress. Intel review by 11/07 | 2025-10-03 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2966 | LOGE1460_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Additional field needs to be captured in S/4 TM Freight Order “Note Type”. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Additional%20fields%20in%20GTT-ETA%20script%20to%20send%20fields%20to%20S4%20TM%20FO%20%20-%20%20Read-Only.pptx?d=we8975c5c88594cfe9968cb89c01f9d51&csf=1&web=1&e=x53US3 | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-12 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-12 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-12 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1460 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-12 | 2025-10-17 | 2025-09-12 |  | 2025-09-12 | 2025-11-07 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-12 | 2025-12-05 | 2025-11-12 | [5 empty] | 2025-07-08 | 2025-11-07 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3032 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11: Business approval received, IT approval pending 11/04: FUT done. Intel review by 11/07 | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2966 | LOGE1460_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: Additional field needs to be captured in S/4 TM Freight Order “Note Type”. | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Additional%20fields%20in%20GTT-ETA%20script%20to%20send%20fields%20to%20S4%20TM%20FO%20%20-%20%20Read-Only.pptx?d=we8975c5c88594cfe9968cb89c01f9d51&csf=1&web=1&e=x53US3 | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-12 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-12 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-12 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 | LOGE1460_IP | 03.Medium | 0.2 | 0.2 | 1460 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-12 | 2025-10-17 | 2025-09-12 |  | 2025-09-12 | 2025-11-07 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-12 | 2025-12-05 | 2025-11-12 | [5 empty] | 2025-07-08 | 2025-11-07 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3033 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11: Business approval received, IT approval pending 11/04: FUT done. Intel review by 11/07 | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2966 | LOGE1459_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Additional field values sent by carrier through GXS are required in GTT. Write ETA script to send the values to S/4 TM | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Additional%20fields%20in%20GTT-ETA%20script%20to%20send%20fields%20to%20S4%20TM%20FO%20%20-%20%20Read-Only.pptx?d=we8975c5c88594cfe9968cb89c01f9d51&csf=1&web=1&e=x53US3 | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-13 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-13 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-13 | [15 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-11-28 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1459 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-13 | 2025-10-17 | 2025-09-13 |  | 2025-09-13 | 2025-11-07 | 2025-09-13 | 2025-09-13 | [12 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-11 | 2025-12-03 | 2025-11-11 | [5 empty] | 2025-07-08 | 2025-11-07 |  |  | 2025-12-03 | TM |  |  | 1 |  | 3030 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11: Business approval received, IT approval pending 11/04: FUT WIP. 1 TC remaining. Defect 4163 raised | 2025-11-07 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2966 | LOGE1459_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: Additional field values sent by carrier through GXS are required in GTT. Write ETA script to send the values to S/4 TM | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Intake%20Forms_NEW/Additional%20fields%20in%20GTT-ETA%20script%20to%20send%20fields%20to%20S4%20TM%20FO%20%20-%20%20Read-Only.pptx?d=we8975c5c88594cfe9968cb89c01f9d51&csf=1&web=1&e=x53US3 | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-13 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-13 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-13 | [15 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-05 | 2025-11-28 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-11-28 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 | LOGE1459_IP | 03.Medium | 0.2 | 0.2 | 1459 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-13 | 2025-10-17 | 2025-09-13 |  | 2025-09-13 | 2025-11-07 | 2025-09-13 | 2025-09-13 | [12 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-11 | 2025-12-05 | 2025-11-11 | [5 empty] | 2025-07-08 | 2025-11-07 |  |  | 2025-12-05 | TM |  |  | 1 |  | 3031 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11: Business approval received, IT approval pending 11/04: FUT WIP. 1 TC remaining. Defect 4163 raised | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2936 | LOGE1453 | 04.Enhancement | 02.IF - Intel Foundry | Trigger the request for cancellation 3B14R and cancel the demand on STO based on the 3B14C cancellation confirmation | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2936%203B14R%20and%203B14C%20trigger%20and%20accept%20R3_FTS_IF_LOGISTICS_L-060_080_Confirm%20Material%20Request%20By%20Requester_%20RICEFW%20Intake%20form1.pptx?d=w10431c4784e54a29a592e7471c0a7dce&csf=1&web=1&e=2sNvRi | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-04 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-06 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-05-17 02:08 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1453 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-07-04 | 2025-11-05 |  |  | 2026-02-27 |  | WIINGS Only | TRUE | 1 |  | 3024 | [7 empty] | 4. Completed | 3. Awaiting Approval | 2/27: Approved by IT/PS. 2/24: Following up with IT/PS for approval 2/20: Walkthrough completed. additional sceario tetsing in progress ETA 2/20. defeect#7520 in progress with tech. 2/18: Defect 7275 is still with tech and no ETA commited. 2/16: 2 defects - 7197 and 7275 in progress with Tech. ETA: 7197 - 2/16 EOD. 7275 - To be started post 7197. 1/16: RAID 03294 created on FTS team (Factory Portal build pending from FTS Team) 12/16: RAID 03294 created on FTS team (Factory Portal build pending from FTS Team) 12/22: RAID 03294 created on FTS team 12/15: Dependent on FTSE1467 which is in dev. FTS core object is not ready yet to start the FUT 12/8: Dependent on FTSE1467 which is in dev. FTS core object is not ready yet to start the FUT 12/1: Dev in progress for the FTS object. 11/24: Dependent on FTSE1467 which is in dev. FUT can start on11/27. 11/18: Mail sent to Chaitanya. The dependency is on FTS object FTSE1467. No update so far. 11/14: In progress | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2922 | LOGE1450 | 04.Enhancement | 02.IF - Intel Foundry | Inbound idoc processing logic during 3B2 and 3B13 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2922%20Update%20Delivery%20Qty%20based%20on%203B13%20and%203B2%20PGI%20Signal_FTS-LE-RICEFW%20intake%20form%20%20.pptx?d=w735167fbfde24dda80ed8d7407a97043&csf=1&web=1&e=p7sJti | 01.Yes | 01.Yes |  | 2025-05-19 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-04 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-10-16 | 100% | 2025-11-03 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2026-01-02 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-28 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-05-17 02:08 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1450 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-03 | 2025-11-03 | 2025-11-03 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | [5 empty] | 2025-07-04 | 2025-11-05 |  |  | 2026-01-23 |  | Rinchem WIINGS Only | TRUE | 1 |  | 3020 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 1/27: Awaiting IT/PS approval. No opens on the FUT. 1/23: Defect closed and IT walkthrough provided. Awaiting approval. 1/22: Addressing review comments. Delay in closure as BI1 system is down. 1/20: Following for IT approval. Defect 6459 in progress with tech tro address review comments. 1/16:Working on shipping error. 01/05:1/5: Defect 5818 is worked upon by tech to fix the partner ID issue and 5698 is also in progress as the text is not geting populated in the payload 12/22: Shared with intel to review 5/6 TC. Defect 5818 is with tech for the remaining 1 test case. No ETA on the defect yet 12/15: Tech is fixing the defect 5496 ETA for defect 12/15. TC 2/6 | 2025-11-05 | N | 99. Logistics | Rinchem |  |  | 0127: FUT impacted due to system outage |  | 3. Watch item | Outage | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 3. WIINGS Only - Not PAID, but CR Approved with $
01. IAO ERP | 03.R3 | 2758 | LOGE1415 | 04.Enhancement | 02.IF - Intel Foundry | Suppress Batch and serial number validation in MIGO/MB26 for movement type 261 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/FTS%20LE%20Slide%20for%20New%20L3%27s/2758%20-%20R3_FTS_IF_LOGISTICS_Supressing%20Batch%20and%20Serial%20number%20validation%20for%20261%20movt%20type_%20RICEFW%20Intake%20form.pptx?d=wdab8e83617e34e6287a81289645726df&csf=1&web=1&e=OkFgGy | 02.No | 01.Yes |  | 2025-04-24 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-09-23 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-03-27 | N | 100% | 2026-03-27 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2025-04-18 05:48 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1415 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2026-03-27 | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-07-11 | 2025-10-03 |  |  | 2026-02-27 |  | WIINGS Only | TRUE | 1 | 08. Not Applicable | 2962 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 3/27: defect fixed, retest in progress, workshop scheduled for today for conditional approval 3/26: tech working on CU/NCU case, ETA awaited from them. 3/25: Sequence change discussion in progress and may bring change. 51/56 TC completed. 3/23: 45 TC completed, additional 9 TC added by business, ETA- 03/24 for review in workshop 3/20: Remaining 1 TC ,tech WIP ETA 3/23, 39/45 documented rest in progress . 3/18: 44 TC walkthrough completed and documenation in progress for 5. Tech working one requirement date. Tech ETA 3/23 3/17: Target to complete walkthrough for 6 more scearios in workshop today. Partial delivery/Requirement dates/non valuation type scenario development still open with tech. Tech ETA 3/23 3/16: working with tech on CU/NCU cases build. Workshop schedueld for 3/17. 3/13: tech confirmed ETA for today, 30 cases walkthrough completed with GFM/WINGS team. Awaiting tech development on copper vs non copper. 3/12: 30 cases walkthrough completed with GFM/WINGS team. Awaiting tech development on copper vs non copper. ETA 3/12. 3/10: CR FUT in progress for the new built scearios. Walkthrough planned for 3/10. CR TC completed so far: 21/41, doc in progress for 6 TCs. 3/9:CR FUT in progress for the new built scearios. Walkthrough planned for 3/10. 3/6:CR FUT in progress for the new built scearios. Walkthrough planned for 3/10. 3/5: CR: 18/41 walkthrough provided. 6 sceanrios to be presented today consodering if tech fix the code issue on valuation type. 3/04: FUT submitted for Intel review. as per Niamh, approval will go together with CR. CR#478- 16/41- completed 18 sceanrios walkthrough with Intel stakeholders 3/02: FUT submitted for Intel review. as per Niamh, approval will go together with CR. CR#478- 12/41-completed 15 sceanrios walkthrough with Intel stakeholders. 2/27: All the opens has been addressed. Checking whether approavl can be received. 2/26: All the defects are fixed and documentation in progress for the last case. walkthrough planned on 2/26 and target Intel approval 2/25: Defect is fixed retesting in progress . 2/24: Working session scheduled with tech for 6797 defect. Tech ETA 2/23: Tech working on POC for 262 mvt type,serial number supression in MB26(defect#6797). Tech is ETA 2/23. 2/20: Under intel review. Tech working on defect#6797 for MB26 mvt type 262(serial number) 2/19:Submitted for Intel approval. Walkthrough completed. 2/18: FUT documentation will send today with one open point. 2/17: FUT documenation is progress. Tech team is working on 1 case for MB26 returns. 2/16: All the defects are fixed. One open point 262 serial no. not populating in MB26. Testing and documentation in progress. 2/13: Serial number fix is in progress with Tech and retest started for the other fixed points. ETA: 2/17 2/12: Testing in progress. 2/11: Defect 6797 fixed. Testing in progress. 2/10: Defect 3792 and 6797 reopened. Will follow for ETAs with Tech team. 2/9: Defect 3792 and 6797 are fixed. Testing in progress. 2/6: Batch and Serial issue has been resolved. Defect 3792 and 6797 for 2 points fixes in progress. Shivam is following up with Tech. ETA: 2/5: Tech is working on 3792 and 6797 defect. Batch part is fixed and tested. Serial number issue is still in progress. ETA: 2/5 EOD. 2/4: Tech is working on 3792 and 6797 defect. Batch part is fixed and tested. Serial number issue is still in progress. No ETA provided. 2/3: Abhishek to connect with Tech on defects and have working session. 2/2: Two defects (6797 & 3792) are open with Tech. No ETA provided. 1/30: Delivery distribution issue resolved. Testing for batch/serial with EWM in progress. ETA 1/31 1/29: Batch testing is stuck since no data is flowing from EWM to S/4. Serial Number related changes completed by Tech, testing in progress. 1/28: Configuration for batch testing completed. Testing in progress. ETA 1/27: Configuration in progress for batch tetsing. ETA 1/27. 1/23: Workimg EWM for batch test. Config is being mainatined as highlighted by EWM tea | 2025-10-03 | N | 99. Logistics |  |  |  | 03/24 : Additional 9 Test cases are added by Business. ETA to share for approval is 03/27 | 12/02 - OSS note 1315595.Additional details are provided. | 5. Review Closed | On track for S23+ | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2718 | LOGE1414 | 04.Enhancement | 02.IF - Intel Foundry | Creation of outbound Delivery for WIP inventory from STO | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_LOG_Creation%20of%20outbound%20Delivery%20for%20WIP%20inventory%20from%20STO.pptx?d=w72ff43a045d640b58e7b24b0bbb0a7af&csf=1&web=1&e=V3Tbi6 | 02.No | 01.Yes |  | 2025-04-24 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-09 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-09 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-31 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-21 | 2025-11-21 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-04-18 05:48 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-17 | 01.S4 |  |  | 1 | 1 | 1414 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-10-17 | 2025-09-09 |  | 2025-09-09 | 2025-11-07 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-11-13 | 2025-11-21 | 2025-11-13 | [5 empty] | 2025-07-11 | 2025-11-07 |  |  | 2025-11-21 |  |  |  | 1 |  | 2961 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/11: Awaiting IT and PS approval | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2917 | LOGE1337 | 04.Enhancement | 01.IP - Intel Product | Enhancement to generate outbound IDOC for 3B2 ASN information to RMA suppliers as outbound signal for return delivery via E2Open. | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2025-04-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7D2A5E66-EFD1-49D4-828F-FCEC0816E949%7D&file=2917_PTP_LE%20-%20Enhancement%20to%20generate%20outbound%20IDOC%20for%203B2%20ASN%20information%20to%20RMA%20suppliers%20as%20outbound%20signal%20for%20return%20delivery%20via%20E2Open..pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-04-02 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-02 | 2025-04-29 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-16 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-24 | 2025-10-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-29 | 2025-10-31 | 2025-10-30 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-03-31 21:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-04-30 | 01.S4 |  |  | 1 | 1 | 1337 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | [5 empty] | 2025-05-02 | 2025-07-18 |  |  | 2025-10-31 |  |  |  | 1 |  | 2846 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/11 - Approval received from GFM IT & Business. IT approval received for ATDM & SIMS as well, Awaiting further feedaback/approval from ATDM & SIMS Business/PS 10/22: Documentation is in process, to be sent for Intel review on 10/27 10/17 - S/4 Testing is completed, Documentation is in-progress | 2025-07-18 | N | 99. Logistics |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2683 | LOGE1327 | 04.Enhancement | 01.IP - Intel Product | ECD_Enhancement to retrieve plant details for material/batch and update custom table | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 09. FUT Overdue | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2683_R3_IP_Enhancement%20to%20retrive%20plants%20carrying%20the%20batch%20or%20BOX%20ID%20to%20be%20blocked.pptx?d=wfe10a1436555479f8f919541934b8485&csf=1&web=1&e=QOtcHB | 02.No | 02.No |  | 2025-08-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-06 | 2025-06-06 | 100% | 2025-10-03 | 2025-09-12 | 2025-09-19 | 2025-12-12 | 100% | 2026-02-17 | 2025-09-26 | 2026-02-06 | 2026-01-16 | 100% | 2026-02-24 | 2025-09-26 | 2026-02-06 | 2026-01-16 | 100% | 2026-02-24 | [15 empty] | 2026-02-24 | 2026-02-24 |  |  | 2026-03-27 | 2026-03-27 |  | 90% | 90% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-01-12 | 2026-02-27 | 2026-03-27 | N | 90% | 2026-03-27 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | pgaroo@deloitte.com | 2025-03-19 10:46 | pusrai@deloitte.com | 2026-04-03 02:24 | 9 | 2025-08-30 | 01.S4 |  |  | 2 | 2 | 1327 |  | R3 ITC1 | [6 empty] | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | [12 empty] | 2026-02-24 | 2026-02-24 |  |  |  | 2026-03-27 | [6 empty] | 2025-06-06 | 2026-02-06 |  |  | 2026-02-27 |  |  |  | 1 |  | 2150 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 4/03: Concern raised by IT on design. In progress with functional team to address concerns. 3/27: Recieved IT approval and following with Randall for PS approval. 3/26: Business is reviewing the document 3/25: Under Intel review. additional ask from workshop are being addressed. ETA 3/25. 3/24: FUT sent out for review 3/23: all defects resolved, retest in progress- ETA to send for review- 03/23 3/20:Defect#8476 still in progress with tech. working session in place with tech ETA 3/20. 3/18:Defect#8476 in progress with tech. working session in place with tech ETA 3/18. 3/17: Defect to be raised for sloc impact on goods mvt. Alignement in progress with tech. 3/13:Defect 7858,8343 is being worked upon by tech and will be then revalidated in workshop 3/16 3/12: ETE FUT will be triggered by ECD 3/13 for testing the hold/unhold request. 3/10: Retest to be validated against LOGI1290 and Inventory status FUTs. TC?? 3/9:Defect#7858 ETA: ??? 3/6: Tech is working on the defect 7858 3/5: QTY calculation issue when response from 3PL is recieved. Defect# 8039 ETA?? 3/04: Defect #7858 is reopened and tech is workingon it. 3/02:Defect#7858 is reopened as response from 3PL is not getting updated in S4. Tech ETA:??? 2/27: Defect 7858 is created and assigned to tech. dependent on LOGI1290 adn shoulkd trigger automatically. 2/26: Payload not reaching to end points and ECD due to missing authroization. Security team to update the auth (3Defect - 7745). ETA ?? 2/25: Defect #7724 is created where the request is not reaching to mulesoft correctly. (Awaiting tech ETA) 2/24:Testing in progress for S4 to 3PL webservice plants 24/2. 2/23:S4 testing in progrees with the mocked data from LOGI1290. Also have asked ECD to trigger real time data for hold/unhold request. 2/17: Test push from gateway client is in progress. 2/16: Dependant on LOGI1290. 2/12: Blocked due to Defect 7219 raised for LOGI1290. Getting ABAP dump. Mule is not able to connect to S/4. ETA: Not provided. 2/10: Defect 7041 is still with Tech. Basic functionality of the Enhancement is still not working and other interfaces on ECD cannot be tested. Development not ready and tech ETA 2/6 3/25: FUT sent out for Intel review 3/25: E2E testing done in the workshop, will sent out the FUT document today 3/24: Testing in progress. 3/23: Retest in progress. Targetting to send for intel review 3/23. 3/20:Dependent on LOGI1291 which has defect#8497 in progress with tech. 3/18:Dependent on LOGI1291 which has defect#8497 in progress with tech. 3/17: Defect to be raised for sloc impact on goods mvt. Alignement in progress with tech. 3/13: Defect# 8343, Trigger response to ECD from S4 is not working and is being worked upon by MW team. 3/12:Being tested together with LOGI1290/91. ETA for trigger 3/13. 3/10: Retest to be validated against LOGI1290 and Inventory status FUTs. 3/9: Dependant on LOGI1291 completion. 3/6: Dependant on LOGI1291 completion. 3/05: Dependant on LOGI1291 completion. 3/04: Dependant on LOGI1291 completion. 3/02: Dependent on LOGI1291 completion. 2/26: Dependent on LOGI1291. S4 payload not reaching to Mule due to authorization issue. Security team to update the auth. ETA ?? 2/25: Dependent on LOGI1291 FUT 2/23: dependent on LOGI1291 FUT. 2/19: dependent on complete execution of LOGI1575 and LOGI1576 2/17: Interface can not be tested till the previous interfaces are executed and data getting save in custom table. 2/16: Dependant on LOGI1290. 2/12: Blocked due to Defect 7219 raised for LOGI1290. Getting ABAP dump. Mule is not able to connect to S/4. ETA: Not provided. 2/10: Defect 7041 is still with Tech. Basic functionality of the Enhancement is still not working and other interfaces on ECD cannot be tested. Development not ready and tech ETA 2/63/20: new defect found during workshop, Documentation to resume once fixed. Target completion ETA 3/20. 3/12: Cases completed 3/11. In progress under ECD bun | 2026-02-06 | Y | 99. Logistics |  |  |  | 03/24 : Defect fix in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | Awaiting approval | Delayed - Past Sprint | R3 Build & UT Sprint 23 |  | 2026-02-24 | 2026-02-24 | No | Param table entry addition. | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2915 | LOGE1316 | 04.Enhancement | 01.IP - Intel Product | Mass Upload Program for HAWB/MAWB/ETA update in Freight order | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2025-04-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2915_R3_OTC%20IP%20TM-HAWB%20Upload%20Program_RICEFW%20Intake%20Form.pptx?d=wf48e6dca5f494310bd19cf8abf0db9e4&csf=1&web=1&e=uSoxSD | 02.No | 01.Yes |  | 2025-03-22 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-16 | 2025-08-13 | 100% | 2025-07-30 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-12-19 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-22 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-03-19 10:46 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-04-24 | 01.S4 |  |  | 2 | 2 | 1316 |  | R3 ITC1 | [6 empty] | 2025-07-30 | 2025-08-16 | 2025-07-30 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-01-22 | 2026-01-23 | 2026-01-22 | [5 empty] | 2025-08-16 | 2025-12-05 |  |  | 2026-01-23 | TM |  |  | 1 |  | 1630 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/19: Defect fix in progress. 01/12 : Defect 6167 fix in progress 01/05: Intel review call to be scheduled, 7th Jan 12/22: Awaiting Intel approval. 12/15: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2887 | LOGE1314 | 04.Enhancement | 01.IP - Intel Product | Enhancement to create Credit Memo Request for the Goods Receipt quantity on posting GR upon updating the Return Delivery in S/4 from EWM. | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-03-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAB41AC8B-749C-4587-ABFA-F85CA1CD5863%7D&file=Return%20Console_IP_R-190-040_Enhancement%20to%20Create%20Credit%20Memo%20Request%20on%20Goods%20Receipt.pptx&wdLOR=cB9501351-A43F-4485-9151-D5778A32FDF9&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-03-13 | Stacey Carter | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-06 | 2025-08-01 | 100% | 2025-08-21 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-21 | 2025-11-21 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-03-13 01:20 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-03-21 | 01.S4 |  |  | 1 | 1 | 1314 | INT-CR0300 | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | [5 empty] | 2025-08-06 | 2025-10-31 |  |  | 2025-11-21 | TM |  |  | 1 |  | 2282 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/24: Reminder email sent for Approval today. 11/18: One open feedback received, Team is working on it to close. 11/11: FUT under intel review. | 2025-10-31 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2860 | LOGE1311 | 04.Enhancement | 01.IP - Intel Product | Virtual Receiving | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-03-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC494E241-E903-4DF8-B39E-AE6938EBA151%7D&file=R3_IP_Returns_Virtual_Receiving.pptx&wdLOR=c99507871-37C7-46E9-B9CA-760F3A2DFA76&action=edit&mobileredirect=true | 02.No | 02.No |  | 2025-03-10 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-11 | 2025-08-01 | 100% | 2025-08-06 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-06 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-03-07 08:15 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-03-21 | 01.S4 |  |  | 1 | 1 | 1311 |  | R3 ITC1 | [6 empty] | 2025-08-06 | 2025-08-06 | 2025-08-06 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-07-11 | 2025-11-05 |  |  | 2026-02-27 | TM |  |  | 1 |  | 1633 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 03/06: Revised FUT document sent for review and approval on 03/05. #defect 7845 testing is in progress. 02/27: Business reivew feedback work in progress. Defect#7633 raised, Tech ETA 02/27.Revised FUT will be sent to Intel for review by 02/27. 02/20: 42/47 TC Completed. FUT is in Roadblock. Defect #7514 needs to be fixed for Integration scenarios 02/16: FUT is in progress for Integration testing 01/19: Object is in roadblock as standalone test scenarios are completed and dependent scenarios are being tracked under respective objects.Integration scenarios are still open as there is a dependency on other objects LOGI12213/61/62/71 FUT completion. 01/13: Object is in roadblock as standalone test scenarios are completed and dependent scenarios are being tracked under respective objects.Integration scenarios are still open as there is a dependency on other objects LOGI12213/61/62/71 FUT completion. 01/05: FUT is in hold for remaining scenarios due to integration scenarios. 12/22: 32/41 TC Completed.FUT is in progress. 12/15: 28 TC Completed. One Integration Testing (RSM) scenario completed other stuck, Defect #5632 raised for 19th RSM Scenario. #5346 raised for DAM Integration testing. Integration scenarios dependent on other objects LOGE1260(Integration testing wip)/1298(Dev In-progress)/LOGI1261- S21 FUT/62 (FUT WIP)/63 (FUT WIP)/71- S21 FUT. Tentative ETA: 12/24 to complete the FUT testing. Fiori app for GR Customer Returns. 12/08: Defect #5256 is worked upon by Tech. Defect resolution ETA :12/08. FUT testing is progress for remaining 2 core scenarios. Integration scenarios dependent on other objects LOGE1260(Integration testing wip)/1298(Dev In-progress)/LOGI1261- S21 FUT/62 (FUT WIP)/63 (FUT WIP)/71- S21 FUT. Tentative ETA: 12/24 to complete the FUT testing. Fiori app for GR Customer Returns.. 12/01:Defect#5040 raised to fix the remaining 3 core scenarios (ETA-12/01). 24/27 TC completed. Integration scenarios dependent on other objects LOGE1260/1298/LOGI1261/62/71. 11/24: Core Scenarios 22/41 TC Completed. Integration scenarios testing on dependent objects LOGE1298/60 and LOGI1262/63/71 11/18: FUT for Core Scenarios are in Progress. Integration scenarios testing is dependent on other object # LOGE1266 to complete the E2E testing. 11/14: Dependency on other object # LOGE1266 to complete the E2E testing. 11/11: There is dependency on other object # LOGE1266 to complete the E2E testing. 11/04: Dependent on LOGE1266, which is currently under development and is supported by RAID #02372 | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2856 | LOGE1310 | 04.Enhancement | 01.IP - Intel Product | Batch job to determine disposition based on static disposition rule table | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-03-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Batch_Job_Static_Disposition.pptx?d=wff37be6e28af4fee8518738adfa81fbf&csf=1&web=1&e=dtyZsd | 02.No | 01.Yes |  | 2025-03-10 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-05 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-03-07 08:15 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-21 | 01.S4 |  |  | 1 | 1 | 1310 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-05-16 | 2025-10-31 |  |  | 2026-01-30 | TM |  |  | 1 |  | 1580 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02: Call is scheduled with Intel IT for Walkthrough on the feedback opens.Mail sent to Business for FUT approval. 01/29: Defect#6648 raised to fix the issues. Tech ETA: 01/29.Updated FUT document will be sent once defect resolution done 01/22: Def #6415, 6444 is fixed. Defect resolution testing is in progress. Planned for a demo session with Intel on 01/23 01/19: Revised FUT document sent to business for final approval (01/16)after addressing all the opens. Received review comments from business and raised defect # 6415 01/13: 8 Review comments are pending out of 14. A new defect #6134 is created 01/05: Reminder sent to Intel for review and approval. 12/22: FUT doc sent to Intel for Review and Approval on 12/19. 12/13: FUT on Hold. Defect 5440 raised to update the fields in the Disposition Table. ETA for 5440 -12/15. Defect 5211 is assigned back to Tech 12/08: Discussion with Tech on adding an extra filter to the existing logic captured in the FS. To be handled through Missed/Change requirement Defect.5211. 0/12 TC completed so far. Tentative FUT closure ETA 12/12. 12/01:Business wants to change the logic to determine disposition from static rule. 2-Objects will be get impacted- LOGE1608/1310. 11/24: Defect 4639, dev ETA 24/11. Planning to complete the FUT by 12/2. Approval may spill over. 11/18: FUT Blocker, Defect #4517 is raised , since data is being fetched from incorrect table 11/14: FUT Blocker, Defect #4517 is raised , since data is being fetched from incorrect table | 2025-10-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2874 | LOGE1301 | 04.Enhancement | 01.IP - Intel Product | Enhancement for updating HAWB (House Air waybill) information in EWM Transportation Unit (TU). | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B57EED89F-F656-4193-AF6F-560295442FE0%7D&file=R3_IP_Returns_HAWB%20number.pptx&action=edit&mobileredirect=true |  |  |  | 2025-03-04 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-10-16 | 100% | 2025-10-30 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-10-31 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-28 07:22 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-05 | 01.S4 |  |  | 1 | 1 | 1301 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-18 | 2025-12-05 | 2025-11-18 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-12-05 | TM |  |  | 1 |  | 2435 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: FUT Under Intel review 11/14: FUT Walkthrough given in workshop and sent for Intel Review and Approval | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2859 | LOGE1298 | 04.Enhancement | 01.IP - Intel Product | Receiving unexpected returned products in the Custom Receiving Screen | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Receive%20Unexpected%20Products.pptx?d=w2700272aba8f4f0d8067cfe7d0769f6e&csf=1&web=1&e=jWRxXH |  |  |  | 2025-03-04 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-09 | 2025-05-09 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-17 | 100% | 2026-03-05 | 2025-10-08 | 2025-11-05 | 2025-11-21 | 100% | 2026-03-05 | 2025-10-08 | 2025-11-05 | 2025-11-21 | 100% | 2026-03-05 | [15 empty] | 2026-03-05 | 2026-03-05 |  |  | 2026-02-06 | 2026-02-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2023-02-09 | 2026-02-13 | 2026-02-13 | N | 100% | 2026-02-26 | Sprint 23 Week 1 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-28 07:22 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-03-05 | 01.S4 |  |  | 2 | 2 | 1298 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | [12 empty] | 2026-03-05 | 2026-03-05 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | [5 empty] | 2025-05-09 | 2025-11-05 |  |  | 2026-02-13 | TM |  |  | 1 |  | 1632 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 02/20: All defects are being worked upon by Tech team. ETA by Tech 02/20. 7078, 7276,7439,7440, 7460 02/16: FUT is under Intel Review. Team is working on Intel feedbacks received during workshop demo and a defect is created for the same. 02/02: 4 TC Completed. Total 17 TC/35 Completed. FUT Testing is in progress for remaining scenarios. Defect #6787 created. Call is scheduled with TM team for TU issues in Unexpected product scenarios. 01/29: Defect Fix 5993 is in progress. 12/35 TC Completed. TUT/FUT is in progress. 01/22: 12/35 TC Completed. Defect Walkthrough was transferred form US to USI defect team. Def #5993, 6331, -ETA 01/23 01/19: 12/35 TC Completed. Defect # 5993, 6331, 6363 are created for issues identified during the TUT/FUT. 01/13: 12/36 TC Completed. Defect # 5902,5993 is till with Tech under fix. 01/05: Defect #5902 is being worked upon by Tech. FUT is in progress for remaining scenarios 12/22: FUT is in progress for 15 independent TC, where it is not dependent on development CR#4432. 12/15: Dev is in Progress. Raised TUT defect # 4432 to fix the incomplete development. 12/08: Dev is still in progress. Mail sent to Tech team lead to get the update on development. Earlier Dev shared revised the ETA as 12/5. TC 0/25 12/01:Integration with LOGE1266 under development. ETA-12/03. FUT can not start without integration. 11/24: 1st test case of FUT started with integration LOG1266. Issues are observed. Defect 4432- Hard blocker, dev ETA 11/24. 0/25 TCs 11/19: The Tech Team has provided an ETA of 11/21 to complete the development and we will begin FUT from 11/21. 11/18:FUT can't be started as Integration with LOGE1266 is not done yet. Defect #4432 raised 11/14 : FUT can't be started as Integration with LOGE1266 is not done yet. Defect #4432 | 2025-11-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-03-05 | 2026-03-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2828 | LOGE1297_IP | 04.Enhancement | 01.IP - Intel Product | Disable the Amount field within Subcontracting tab in Freight Order for CW Load Planner. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2506E94F-463F-42E9-8E67-35B5395F6AE4%7D&file=2828_R3_IP_TM_Amount%20Field%20Disable_CW%20Load%20Planner_Intake%20Form.pptx&wdLOR=cD3A056C5-7260-4EEC-BA58-B8CC687C820F&action=edit&mobileredirect=true | 02.No | 02.No |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-02 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-02-28 07:22 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-05 | 01.S4 |  |  | 1 | 1 | 1297 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-06-27 | 2025-12-05 |  |  | 2025-12-05 | TM |  |  | 1 |  | 1819 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Intel review rescheduled from 11/27 to 2nd dec due to holidays & Intel unavailibility 11/24: FUT document sent for internal review, ETA 27/11 11/18: Not yet ready for FUT | 2025-12-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2828 | LOGE1297_IF | 04.Enhancement | 02.IF - Intel Foundry | Disable the Amount field within Subcontracting tab in Freight Order for CW Load Planner. | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2506E94F-463F-42E9-8E67-35B5395F6AE4%7D&file=2828_R3_IP_TM_Amount%20Field%20Disable_CW%20Load%20Planner_Intake%20Form.pptx&wdLOR=cD3A056C5-7260-4EEC-BA58-B8CC687C820F&action=edit&mobileredirect=true | 02.No | 02.No |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-02 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-02-28 07:22 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-05 | 01.S4 | LOGE1297_IP | 03.Medium | 0.2 | 0.2 | 1297 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-06-27 | 2025-12-05 |  |  | 2025-12-05 | TM |  |  | 1 |  | 1818 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Intel review rescheduled from 11/27 to 2nd dec due to holidays & Intel unavailibility 11/24: FUT document sent for internal review, ETA 27/11 11/18: Not yet ready for FUT | 2025-12-05 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2855 | LOGE1281 | 04.Enhancement | 08.EWM | Batch job to determine disposition based on dynamic disposition rule table | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Batch_Job_Dynamic_disposition.pptx?d=w0750162f722d4b37913ae92615ea3ecc&csf=1&web=1&e=UUenS8 |  |  |  | 2025-02-26 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-09 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-01-26 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-06 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 1 | 1 | 1281 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-05-16 | 2025-10-31 |  |  | 2026-01-30 | TM |  |  | 1 |  | 1579 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 02/02: 2 FUT/ 10 is completed and remaining 5 TC FUT is in progress. Defect #6689 fix is in progress: ETA 02/02 01/29: Raised defects # 6689,6552 (ETA 1/29) to fix the FUT defects.7/10 TC Completed. 01/22: Def #6351 is re-assigned back to Tech. Def #6552 created to get the status as Awaiting Manual Disposition 01/19: Defects #6039 and #6351 are raised for issues identified during FUT. FUT document sent to business for review for completed 7-TC. 7/10 TC Completed. 01/13: Defect #6039 is re-assigned to tech for fix , as issues identified.2/10TC Completed 01/05: Defect fixed by Tech team. Testing is in progress. 12/22: Requirement Change Defect #5856 raised for logic change as the determination table is to be changed. 12/15: FUT testing is in progress. | 2025-10-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2854 | LOGE1280 | 04.Enhancement | 08.EWM | Custom screen to request assignment of OPID to planner and capture the details in custom table. | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Custom_Planner_relationship.pptx?d=w841339200a964b719d43d4ce2e48b1a9&csf=1&web=1&e=HYAwYJ |  |  |  | 2025-02-26 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-17 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  |  | 2026-01-07 | 2026-02-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-13 | 2026-02-13 | N | 100% | 2026-02-11 | Sprint 23 Week 1 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-02-25 07:38 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-02-27 | 01.S4 |  |  | 4 | 4 | 1280 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2026-02-11 | 2026-02-13 | 2026-02-11 | [5 empty] | 2025-06-27 | 2025-12-05 |  |  | 2026-02-13 | TM |  |  | 1 |  | 1578 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 01/19: Tech team is working on defects 6313 , 6374. Tech ETA: 01/19.Received Business approval. IT approval is pending. 01/13: Defect #6040 is closed and tech is working on #6134. New defect #6247 is created for feedback. Tech ETA is 01/13. 01/05:Received feedback comments from business. Raised defect 5941 to address the business feedback comments. 12/22:FUT is in progress. 33/54 TC Completed 12/15: FUT is in progress. 9/47 TC Completed. | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: TUT pending approval. 5.1 in S21, 5.2 in S22 |  |  |  | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2848 | LOGE1277 | 04.Enhancement | 08.EWM | Generate Docking report | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Docking_report.pptx?d=w96349fee70c9404eb5ce6371e2a245e7&csf=1&web=1&e=hukkVW |  |  |  | 2025-02-26 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2026-01-06 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-01-06 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 2 | 2 | 1277 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-06-20 | 2025-10-31 |  |  | 2026-01-07 | TM |  |  | 1 | 08. Not Applicable | 1574 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/05: New defect # 5970 raised to change the table logic (ZTOTC_RETURN_TB) and Defect 5858 re-assigned back to tech to fix the business feedback review comments. 12/22: FUT walkthrough given to business on 12/19 workshop. Defect # 5858 raised to fix the feedback review comments. 12/15: 10/25 TC Completed today. Defect# 5394 is with Tech Team. Dev ETA: 12/15. | 2025-10-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2710 | LOGE1276_IP | 04.Enhancement | 01.IP - Intel Product | TM:Replace VTRC and integrate with parcel carrier to retrieve the package level tracking( HAWB) information ( US sites only). Determine the header HAWB from the HU level tracking ids and update the same to TM freight order( Header document reference) | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEE66B104-5905-414D-A993-E58647079463%7D&file=2710_R3_IP&IF_FTS_LO-190-100_RICEFW%20for%20HAWB%20determination%20from%20Redwood%20Intake%20Form.pptx=&wdLOR=cBBE26090-E03E-45AB-B732-48967851C1D1&action=edit&mobileredirect=true |  |  |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-05 | 01.S4 |  |  | 1 | 1 | 1276 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-06-13 | 2025-10-24 |  |  | 2025-12-05 | TM |  |  | 1 |  | 2179 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/1: Working with tech on defect 4854. 12/01: FUT complete, Intel Review call scheduled on 12/02 11/24: FUT WIP and defect 4874 raised, ETA 27/11 11/18: FUT WIP | 2025-10-24 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2710 | LOGE1276_IF | 04.Enhancement | 02.IF - Intel Foundry | TM:Replace VTRC and integrate with parcel carrier to retrieve the package level tracking( HAWB) information ( US sites only). Determine the header HAWB from the HU level tracking ids and update the same to TM freight order( Header document reference) | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | Y | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEE66B104-5905-414D-A993-E58647079463%7D&file=2710_R3_IP&IF_FTS_LO-190-100_RICEFW%20for%20HAWB%20determination%20from%20Redwood%20Intake%20Form.pptx=&wdLOR=cBBE26090-E03E-45AB-B732-48967851C1D1&action=edit&mobileredirect=true |  |  |  | 2025-03-04 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-02-25 07:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-05 | 01.S4 | LOGE1276_IP | 03.Medium | 0.2 | 0.2 | 1276 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-06-13 | 2025-10-24 |  |  | 2025-12-05 | TM |  |  | 1 |  | 2180 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: FUT complete, Intel Review call scheduled on 12/02 11/24: FUT WIP and defect 4871 is raised, ETA 27/11 11/18: FUT WIP | 2025-10-24 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2857 | LOGE1269 | 04.Enhancement | 08.EWM | To Perform Undisposition for already dispositioned RMA | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6D846FD9-4622-4D05-9F00-78D80C1E69E3%7D&file=R3_IP_Returns_Undo_disposition.pptx&wdLOR=c5CB2F226-210B-4AF6-BF26-98B25F8D0E99&action=edit&mobileredirect=true | 02.No | 02.No |  | 2025-02-20 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-11-21 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-23 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-19 08:26 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 4 | 4 | 1269 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | [5 empty] | 2025-06-27 | 2025-10-31 |  |  | 2026-01-23 | TM |  |  | 1 |  | 2352 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/23: Intel Biz and It Approval received today. Object complete 01/19: 6360, 6398 defects are created to address the feedback comments. Tech ETA: 01/19 01/13: Defect 5950 is working as expected. Team is closing the Business feedback and few open question to be addressed in the workshop today. 01/05: New defect# 5950 Created for modification of CWP Field in both Fiori and Custom Disposition Table 12/22: New defect to be created after impact analysis to fix the concerned highlighted by intel team during the review. This defect impact 3-objects. 12/15: Raised Defect to fix the intel review comments. 12/08: FUT under Intel Review. Raised defect 5179 to fix the issues based on intel feedback review comments. 12/01: FUT document sent for review and approval. 11/24: Defect 4818 with dev, ETA 11/24. FUT will be sent for Intel by 11/28. 22/27 TCs tested. 11/18: Defect #4589 resolution is in progress. ETA for Resolution EOD | 2025-10-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2844 | LOGE1268 | 04.Enhancement | 08.EWM | Enhancement to create Ship instruction screen.​ | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-26 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7A325DE7-D9FD-4BF9-BEB5-F8241E0368F4%7D&file=R3_IP_Returns_Ship_Instruction_screen.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Csjulury%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTAxMDYyMDQxMiIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | 02.No | 01.Yes |  | 2025-02-20 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-11 | 2025-08-01 | 100% | 2025-08-01 | 2025-10-10 | 2025-10-17 | 2025-10-14 | 100% | 2025-11-03 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-10-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-19 08:26 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-27 | 01.S4 |  |  | 1 | 1 | 1268 |  | R3 ITC1 | [6 empty] | 2025-08-01 | 2025-08-01 | 2025-08-01 |  | 2025-11-03 | 2025-11-03 | 2025-11-03 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | [5 empty] | 2025-07-11 | 2025-11-05 |  |  | 2025-12-05 | TM |  |  | 1 |  | 1571 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 01/02: Defect 5453 is being worked upon by Tech. Revised ETA by Tech : 01/05. Once thse issue are fixed, FUT will be sent to Intel for approval again 12/22: Defect #5453 re-opened and assigned back to Tech to fix the business comments' ETA: 12/23. 12/15: Defect #5453 raised to fix the Intel review feedback. 12/08: FUT under Intel review. FUT sent for approval on 12/05. Workshop planned for 12/10. 12/01: Defect 4925 (ETA-12/01) reassigned back to Tech team to fix the 5/10 core issues. 4726-To fix Security related issues (ETA-11/28) 11/24: FUT is in progress, good to send for intel approval 11/28. 11/18:Defect #4462 resolution is in progress. Team is checking on workaround to run the other scenarios 11/14: FUT is on roadblock, #4403 raised to fix the core functionality | 2025-11-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2839 | LOGE1266 | 04.Enhancement | 08.EWM | Custom Receiving screen (ZPRDI) to have functionalities to process receiving of customer Returned Materials | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B99D3E1CE-F776-4DDA-87C9-5001B31AD2DD%7D&file=R3_IP_OTC_Custom%20Screen%20%20Funtionalities_Of_Custom_Receiving_Screen.pptx&wdLOR=c6BF8263B-916C-4F4B-B3AE-3F0FB727C6F4&action=edit&mobileredirect=true&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEyMDEwMDIyMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2025-02-18 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-12-31 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-12-31 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-09 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2025-02-18 06:27 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2025-02-21 | 01.S4 |  |  | 4 | 4 | 1266 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2025-04-18 | 2025-09-12 |  |  | 2026-02-27 | TM |  |  | 1 |  | 1994 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/06: Revised FUT document sent for review and approval on 3/5. Defect for cosmetic changes 8023(ETA-03/06), 8061 In progress. 02/27:11/15 Opens are fixed. Defects # 7804 Tech ETA: 02/27.Revised FUT document will be sent by 02/27. 02/20:53/64 TC Tech team is working on Active defects on the issues identified on the Receiving Screen 02/16: FUT for Integration scenarios are in progress. 01/19: Tech team is working on duplicate subline getting created after verification step. Defects # 6368,6401 are raised.Additionally, Working on feedback review comments and additional test cases which business has shared. Integration scenarios are still open as there is a dependency on other objects LOGI1213/61/62/71/ FUT completion. 01/13: Working on feedback review comments and additional test cases which business has shared. Integration scenarios are still open as there is a dependency on other objects LOGI1213/61/62/71/ FUT completion. 01/05: Team is working on closing the remaining Open feedbacks received from Intel 12/22: Defect 5775 is tested and closed. 5781 is worked upon by Tech. Def 5851 is raised for Discrepancy codes to be fetched along with Description .Team is working on feedback from Intel IT. Dev ETA: 12/24. 12/15: 41/62 more TC case completed. Defect # 5587 raised for status is not getting updated as discrepant. ETA .Dependency on other object integration testing to be completed. 12/08: 37 TC Completed. Integration Testing (RSM) is in progress. Defect #5346 raised for DAM Integration testing. Integration scenarios dependent on other objects LOGE1260(Integration testing wip)/1298(Dev In-progress)/LOGI1261- S21 FUT/62 (FUT WIP)/63 (FUT WIP)/71- S21 FUT. Tentative ETA: 12/24 to complete the FUT testing. Fiori app for GR Customer Returns. 12/01:Received the feedback from business on 13 Points. Closed-12, 1-Point requires the discussion with business. Identified additional 3-new negative scenarios. Raised defect # 4809. Defect # 4599 reopened to fix the integration related issue LOGE1260. Another12/08: 37 TC Completed. Integration Testing (RSM) is in progress. Defect #5346 raised for DAM Integration testing12/08: 37 TC Completed. Integration Testing (RSM) is in progress. Defect #5346 raised for DAM Integration testing 11/25: test cases 26 /30 core scenarios completed. FUT is in progress. Defect raised for partial delivery #4809. Integration development started being tracked through defect #4599 and #4432. Total TC 62 11/24: Core Scenarios 22/26 Completed. 4 Scenarios are pending due to defects # 4599, 4196, 4610,4809. Other integration scenarios 36 are pending due to other integration objects dependency. 11/14: Integration FUT is in Progress for completed dependent object. Other Integration objects are under development and FUT | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | Yes | Need to test one E2E scenario to check th | No |  | No |  | 2026-03-09 | 2026-04-01 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2838 | LOGE1265 | 04.Enhancement | 08.EWM | Custom screen to capture shipment unloading details (Docking) | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_OTC_Custom_Docking_Screen+GTS%20block.pptx?d=w12a8d71cdeb848468ffe6b798559f53f&csf=1&web=1&e=JPfgG1 | 01.Yes | 01.Yes |  | 2025-02-18 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-12-31 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-12-31 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-27 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2025-02-18 06:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1265 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-11-27 | 2025-11-27 | 2025-11-27 | [5 empty] | 2025-04-18 | 2025-09-12 |  |  | 2025-11-07 | TM |  |  | 1 |  | 1515 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24: Received review comments on 11/24. Team is analyzing the feedback comments. 11/14: Defect 4417 and 4486 fix is in progress. Team is supporting tech with logic and test data 11/11: Defect # 4417 has been raised. It is with tech team. 10/31: FUT in progress. Defect 4138 is open 10/24 - Defect 3851 | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2845 | LOGE1260 | 04.Enhancement | 08.EWM | Resolution for Discrepancy to be determined based on Business Rules | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Discrepency_Resolution_Business_Rules.pptx?d=w141866ef1f9e47219a097eb8b314ff47&csf=1&web=1&e=cBun0B | 02.No | 01.Yes |  | 2025-02-18 | shelly.lafree@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-05-09 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2026-01-06 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2026-01-06 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-02-17 06:31 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 4 | 4 | 1260 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-09 | 2025-10-24 |  |  | 2025-12-05 | TM |  |  | 1 |  | 1572 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/05: Intel IT approval received, Awaiting Biz Approval. Reminder Email Sent 12/22: Intel IT approval received, Awaiting Biz Approval. 12/15: Raised Defect to fix the intel review comments. Backend issues are fixed, Fiori changes are pending. Defect # 5526 resolution is in progress.Dev ETA 12/15. 12/15: 4 new TC Completed. Remaining TC require data in B.Apps System. Mail sent to B.apps team for data. 12/08: Defect 4607 defect resolution is in progress. defects priority has been made URGENT. 60 TC Completed. 2 TC are critical for resolution. 12/01: 54/62 TC Completed. Defect 4629/4607 raised to fix the excel upload related issues (8-TC). 11/24: 44/68 TC completed. 4629 (ETA-11/26), 4607(11/24) raised to unlock the remaining TC. 11/18: 7 TC completed today with total completed TC-37/62. Defect 4458 Resolution is in progress with ETA for resolution EOD. CR #4607- ETA 11/21. FUT to resume after defect resolution 11/14 : 30/68 TC completed, FUT is in progress. Defect # 4357, 4358, 4458 raised. | 2025-10-24 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2026-01-06 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2751 | LOGE1256_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Document type T54 (House Airway Bill) number to GTT | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/T54%20Document%20Type%20in%20GTT%20.pptx?d=w43cd1a910dc4439ebce53a4088a53609&csf=1&web=1&e=KHFG3I | 01.Yes | 01.Yes | LOGI0630_IP | 2025-02-20 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-07 | 2025-07-14 | 2025-07-18 | 2025-06-17 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-02-17 06:31 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-26 | 01.S4 |  |  | 1 | 1 | 1256 |  | R3 ITC1 | [6 empty] | 2025-04-07 | 2025-04-18 | 2025-04-07 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-31 | 2025-08-13 | 2025-07-31 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-08-13 | TM |  |  | 1 |  | 2344 | [10 empty] | 2025-08-15 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2751 | LOGE1256_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: Document type T54 (House Airway Bill) number to GTT | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/T54%20Document%20Type%20in%20GTT%20.pptx?d=w43cd1a910dc4439ebce53a4088a53609&csf=1&web=1&e=KHFG3I | 01.Yes | 01.Yes | LOGI0630_IF | 2025-02-20 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-07 | 2025-07-14 | 2025-07-18 | 2025-06-17 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-02-17 06:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-26 | 01.S4 | LOGE1256_IP | 03.Medium | 0.2 | 0.2 | 1256 |  | R3 ITC1 | [6 empty] | 2025-04-07 | 2025-04-18 | 2025-04-07 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-15 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-31 | 2025-08-13 | 2025-07-31 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-08-13 | TM |  |  | 1 |  | 2343 | [10 empty] | 2025-08-15 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2817 | LOGE1255 | 04.Enhancement | 08.EWM | Visibility of New & Old Part Number during RF picking/ issue process | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2817_R3_FTS_IF_Visibility%20of%20New%20%26%20Old%20Part%20Number%20during%20RF%20picking%20issue%20process.pptx?d=wab99aec55fcf45ec9aa0fff9674eead2&csf=1&web=1&e=IUI3zM | 01.Yes | 01.Yes |  | 2025-02-18 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-02 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-02-17 06:31 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-05 | 01.S4 |  |  | 1 | 1 | 1255 |  | R3 ITC1 | [6 empty] | 2025-06-02 | 2025-06-13 | 2025-06-02 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-10-08 | TM | WIINGS Only | TRUE | 1 |  | 1452 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2816 | LOGE1254 | 04.Enhancement | 08.EWM | Print Product Label in SAP EWM after physical inventory document posting | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2816_R3_FTS-EWM_Print%20Product%20Label%20in%20SAP%20EWM%20after%20physical%20inventory%20document%20posting.pptx?d=w2076d8d6fbe944ee9e4c9725af3c1339&csf=1&web=1&e=IqpPX9 | 01.Yes | 01.Yes |  | 2025-02-18 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-17 06:31 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-05 | 01.S4 |  |  | 1 | 1 | 1254 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  | 2026-02-20 | 2026-02-20 | 2026-03-04 | 2026-02-20 | [5 empty] | 2025-06-13 | 2025-10-31 |  |  | 2026-03-04 | TM | WIINGS Only | TRUE | 1 |  | 2389 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/16: All comments are addressed and discussed in workshop, pending approval since 1/20. 01/19: Defect 5353 is still open for printing multiple labels 01/14: Defect 5353 is still open with tech, new ETA by tech 01/16. 01/12: 1 of 3 defects # 5353 is open with tech team as label is not getting printed from RFUI. 01/05: Retesting of defect in progress. Opened new 2 defects. 12/15: Defect as CR #5353 with tech team, ETA by tech 12/18. 12/19.12/08: With reference to 4439, Dev has asked to raise a new defect with change category to do POC and come with tech solution. ETA to be received 12/01 :Defect 4439 with Dev. TUT was not done with RFUI screen shots, 4439 is to address those fixes. ETA was from Dev 11/20. yet to receive the ETA. 11/24: Defect 4439 with Dev. TUT was not done with RFUI screen shots, 4439 is to address those fixes. ETA from Dev 11/20. yet to receive the ETA. 11/18 Defect 4439 | 2025-10-31 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 2168 | LOGE1253 | 04.Enhancement | 01.IP - Intel Product | Inventory Reconciliation with Consignment hub – EDI 4C1 with version control | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-03-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B970E6AFF-DEAB-4BD2-BA85-AB31260C499D%7D&file=R3_FTS_IP_LOGISTICS_LI-120_190_Enhancement%20-%2050_%20RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true | 02.No | 02.No | LOGI1267 | 2025-02-05 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-16 | 2025-12-05 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-02-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-02-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-05 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2025-02-05 09:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1 | 1253 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-18 | 2025-04-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-09-19 |  |  |  | 1 |  | 1604 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: Awaiting approvals from IT 10/3: Under Intel Review 9/29: Defect 3167 in progress. Call scheduled with business on 9/30 to align on payload issues. 9/22: FUT Blocked due to AIF Processing Errors. Defect - 3167 raised | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE1251_IP | 04.Enhancement | 01.IP - Intel Product | More determinization of input entry criteria to be added for dedicated carrier determination for IBDR scenarios.​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2025-02-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-04-04 | 2025-04-14 | 2025-04-18 | 2025-07-25 | 100% | 2025-07-24 | 2025-05-05 | 2025-05-16 | 2025-08-08 | 100% | 2025-07-24 | 2025-05-05 | 2025-05-16 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-17 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-02-13 12:39 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1 | 1251 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | [5 empty] | 2025-03-29 | 2025-05-16 |  |  | 2025-09-10 | TM |  |  | 1 | 08. Not Applicable | 1967 | [7 empty] | 1. On Track | 3. Awaiting Approval | 09/15 : Intel IT approved FUT on 09/12 and Waiting for BZ approval. | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE1251_IF | 04.Enhancement | 02.IF - Intel Foundry | More determinization of input entry criteria to be added for dedicated carrier determination for IBDR scenarios.​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2025-02-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-04-04 | 2025-03-31 | 2025-04-04 | 2025-07-25 | 100% | 2025-07-24 | 2025-06-16 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-06-16 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-17 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-02-13 12:39 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 | LOGE1251_IP | 03.Medium | 0.2 | 0.2 | 1251 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-17 | 2025-09-17 | 2025-09-17 | [5 empty] | 2025-03-29 | 2025-07-18 |  |  | 2025-09-10 | TM |  |  | 1 | 08. Not Applicable | 1968 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 09/15 : Intel IT approved FUT on 09/12 and Waiting for BZ approval. | 2025-07-18 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE1250_IP | 04.Enhancement | 01.IP - Intel Product | Creating new Carrier selection strategy methods ZPRE_TAL and ZPOST_TAL to call commodity code to MTR mapping BRF+ table to replace MTR and further to clear it.​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2025-02-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-03-27 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-13 | [15 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-02-13 12:39 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1 | 1250 |  | R3 ITC1 | [6 empty] | 2025-03-27 | 2025-03-29 | 2025-03-27 |  | 2025-09-13 | 2025-09-19 | 2025-09-13 |  | 2025-09-13 | 2025-10-10 | 2025-09-13 | 2025-09-13 | [12 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2025-03-29 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1969 | [7 empty] | 4. Completed | 1. Approved no action | 11/18:Conditional approved, schedule a call with Ramesh on the BS/TAL technical approach; REDWOOD issue is persisting 11/14: IT approval received. ETA for full approval- 11/14 11/11: 2 TC not working for Business share and allocation update. defect being worked on by tech team. ETA- 11/14 11/04: FUT WIP. Target ETA for intel review 11/07. At risk for approval task 10/31: FUT in progress, to be reviewed with Intel ETA 7th Nov 10/22: Working session with Tech team scheduled to close the blocker defect. | 2025-10-10 | Y | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE1250_IF | 04.Enhancement | 02.IF - Intel Foundry | Creating new Carrier selection strategy methods ZPRE_TAL and ZPOST_TAL to call commodity code to MTR mapping BRF+ table to replace MTR and further to clear it.​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2025-02-13 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-03-27 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-13 | [15 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-02-13 12:39 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 | LOGE1250_IP | 03.Medium | 0.2 | 0.2 | 1250 |  | R3 ITC1 | [6 empty] | 2025-03-27 | 2025-03-29 | 2025-03-27 |  | 2025-09-13 | 2025-09-19 | 2025-09-13 |  | 2025-09-13 | 2025-10-10 | 2025-09-13 | 2025-09-13 | [12 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2025-03-29 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1970 | [7 empty] | 4. Completed | 1. Approved no action | 11/18:Conditional approved, schedule a call with Ramesh on the BS/TAL technical approach; REDWOOD issue is persisting 11/14: IT approval received. ETA for full approval- 11/14 11/11: 2 TC not working for Business share and allocation update. defect being worked on by tech team. ETA- 11/14 11/04: FUT WIP. Target ETA for intel review 11/07. At risk for approval task 10/31: FUT in progress, to be reviewed with Intel ETA 7th Nov 10/24 - Dependent with 459 & 765 approval 10/22: Working session with Tech team scheduled to close the blocker defect . | 2025-10-10 | Y | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2799 | LOGE1221 | 04.Enhancement | 08.EWM | Custom Fiori screen to capture shipping details and start the shipping process. | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Ship%20Item%20screen.pptx?d=w098638b585844ec28245d03ee2890f64&csf=1&web=1&e=yeCHOe | 02.No | 02.No |  | 2025-02-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-27 | 2025-06-27 | 100% | 2025-08-25 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2026-02-03 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-03 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-06 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-03 06:19 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1221 |  | R3 ITC1 | [6 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2026-02-03 | 2026-02-03 | 2026-02-03 |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-03 | [12 empty] | 2025-12-03 | 2025-12-03 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-06-27 | 2025-10-31 |  |  | 2026-02-27 | TM |  |  | 1 |  | 1718 | [7 empty] | 4. Completed | 3. Awaiting Approval | 03/06: New defect 8071 raised. Defect 7938 ,7939 - Tech fix WIP. Aligned with biz conditional business approval; For Conditional IT Apporval 5 points raised in defect #8097 to be fixed by USI EOD. 02/27: 27/32 TC Completed. Tech is working on defects-7694, 7694-ETA 02/26 and 7763-ETA 02/27. TUT/FUT is in progress. FUT will be sent for intel review by 03/03 22/32 TC Completed. FUT is in progress. Tech team is working on the active defects, Func team is supporting tech team in the TUT and FUT tigether.7128, 6971, 7311, 7331, 7537. 02/16: 18/32 TC Completed. Tech team is working on defect 7311, 7331. Func team is supporting Tech team on defect resolution. 01/19: TUT and FUT is being done together in working session. 12/40 TC Completed. 01/13: TUT and FUT is in progress with Tech team. 01/05: 12/36 TC Completed. FUT Testing is in progress 12/22 :8 TC Completed. TUT and FUT is in progress with dev. team. 12/15: TUT/FUT is in progress. Recurring call has been scheduled to complete the TUT/FUT. | 2025-10-31 | N | 99. Logistics |  |  |  | 1211: TUT pending approval. 5.1 in S21, 5.2 in S22 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-03 | 2025-12-03 | Yes | Maintain new "Ship to Plant" Entries in ZTOTC_PARAMS | No |  | No |  | 2026-03-09 | 2026-04-01 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2770 | LOGE1214 | 04.Enhancement | 08.EWM | Update price variance category and its reason in Difference Analyzer | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Variance_Category-physical%20inventory.pptx?d=w27b7d8fc9df64254bc6f958a1a86ade4&csf=1&web=1&e=cgo5Pa | 02.No | 02.No |  | 2025-02-04 | shelly.lafree@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-08-01 | 100% | 2025-08-25 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-11-13 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-19 | 01.S4 |  |  | 1 | 1 | 1214 |  | R3 ITC1 | [6 empty] | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-24 | 2025-12-05 | 2025-11-24 | [5 empty] | 2025-05-16 | 2025-11-05 |  |  | 2025-12-05 | TM |  |  | 1 | 08. Not Applicable | 2317 | [7 empty] | 4. Completed |  | 11/24: FUT marked as completed as received Intel approval. 11/18: Feedback received from Intel on renaming certain output fileds, Report Names and addition of Input fields. Defect #4670 raised 11/14: FUT is under intel review | 2025-11-05 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1197_IP | 04.Enhancement | 01.IP - Intel Product | Carrier notification- Tendering initiation email | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-25 | 2025-05-09 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-30 03:53 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1197 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-09 | 2025-09-19 | 2025-09-09 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-04-25 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2731 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1197_IF | 04.Enhancement | 02.IF - Intel Foundry | Carrier notification- Tendering initiation email | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-20 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-30 03:53 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-21 | 01.S4 | LOGE1197_IP | 02.High | 0.4 | 0.4 | 1197 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-09-09 | 2025-09-19 | 2025-09-09 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2730 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1196_IP | 04.Enhancement | 01.IP - Intel Product | Invoice notification- Notification to carrier for POD and internal notification for carrier response | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-25 | 2025-05-09 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2026-02-02 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-01-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-01-31 | [15 empty] | 2026-01-31 | 2026-01-31 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-01-30 03:53 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-21 | 01.S4 |  |  | 2 | 2 | 1196 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | [12 empty] | 2026-01-31 | 2026-01-31 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-25 | 2025-10-31 |  |  | 2026-01-09 | TM |  |  | 1 | 08. Not Applicable | 2727 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Intel review call to be scheduled, 7th Jan 12/24: Sent for review 12/22: TUT+ FUT in progress, working session planned on 12/22 on 7:30 PM IST. | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-31 | 2026-01-31 | No | Subject line in tendering email trigger to carrier contains " Intel Product". Subject line nees to be corrected | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE1196_IF | 04.Enhancement | 02.IF - Intel Foundry | Invoice notification- Notification to carrier for POD and internal notification for carrier response | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-03 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-28 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-23 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-01-30 03:53 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-21 | 01.S4 | LOGE1196_IP | 02.High | 0.4 | 0.4 | 1196 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-05-30 | 2025-05-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-30 | 2025-10-31 |  |  | 2026-01-09 | TM |  |  | 1 | 08. Not Applicable | 2726 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Intel review call to be scheduled, 7th Jan 12/22: TUT+ FUT in progress, working session planned on 12/22 on 7:30 PM IST. | 2025-10-31 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2806 | LOGE1193_IP | 04.Enhancement | 01.IP - Intel Product | S4 – Enhancement to stop GR for Purchase Order for which Delivery Completed indicator is set | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAEA460AC-9476-487D-AC2F-25CA7E19C3F4%7D&file=2806_PTP_LE%20-%20Enhancement%20to%20stop%20GR%20for%20Purchase%20Order%20for%20which%20Delivery%20Completed%20indicator%20is%20Set_S4%20IP%20&%20IF.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-07 | 2025-05-07 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-25 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2025-01-29 09:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1 | 1193 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-05-07 | 2025-07-18 |  |  | 2025-09-10 |  |  |  | 1 |  | 1725 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2806 | LOGE1193_IF | 04.Enhancement | 02.IF - Intel Foundry | S4 – Enhancement to stop GR for Purchase Order for which Delivery Completed indicator is set | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAEA460AC-9476-487D-AC2F-25CA7E19C3F4%7D&file=2806_PTP_LE%20-%20Enhancement%20to%20stop%20GR%20for%20Purchase%20Order%20for%20which%20Delivery%20Completed%20indicator%20is%20Set_S4%20IP%20&%20IF.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-10 | cari.h.shim@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-07 | 2025-05-23 | 100% | 2025-05-20 | 2025-07-21 | 2025-07-25 | 2025-07-25 | 100% | 2025-08-01 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-01 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-08-01 | [15 empty] | 2025-08-01 | 2025-08-01 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jenoronha@deloitte.com | 2025-03-13 08:56 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-12 | 01.S4 | LOGE1193_IP | 03.Medium | 0.2 | 0.2 | 1193 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-23 | 2025-05-20 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-01 | [12 empty] | 2025-08-01 | 2025-08-01 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-05-07 | 2025-07-18 |  |  | 2025-09-10 |  |  |  | 1 |  | 1726 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2732 | LOGE1177_IP | 04.Enhancement | 01.IP - Intel Product | India GST E-invoicing | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2732_FTS-LE-RICEFW%20intake%20form%20India%20GST%20E-invoicing.pptx?d=w94eabb403d914f0c9888779d5759bb04&csf=1&web=1&e=crvzcP | 02.No | 01.Yes |  | 2025-01-29 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No | Deloitte 'Bolt On' |  |  |  | NA | 2025-05-05 | 2025-05-30 | 2025-12-03 | 100% | 2025-11-24 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-12-05 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-29 | 2025-08-29 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-29 | 2025-08-29 | 2025-08-29 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-13 | 01.S4 |  |  | 1 | 1 | 1177 |  | R3 ITC1 | [6 empty] | 2025-11-24 | 2025-12-03 | 2025-11-24 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-09-05 | 2025-12-05 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-05-30 | 2025-08-29 | [6 empty] | 1 |  | 2057 | [7 empty] | 4. Completed |  |  | 2025-08-29 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2732 | LOGE1177_IF | 04.Enhancement | 02.IF - Intel Foundry | India GST E-invoicing | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2732_FTS-LE-RICEFW%20intake%20form%20India%20GST%20E-invoicing.pptx?d=w94eabb403d914f0c9888779d5759bb04&csf=1&web=1&e=crvzcP | 02.No | 01.Yes |  | 2025-01-29 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No | Deloitte 'Bolt On' |  |  |  | NA | 2025-05-05 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-20 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-23 15:43 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-13 | 01.S4 | LOGE1177_IP | 03.Medium | 0.2 | 0.2 | 1177 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-09-05 | 2025-10-10 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-05-30 | 2025-10-10 | [6 empty] | 1 |  | 2058 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2749 | LOGE1150 | 04.Enhancement | 01.IP - Intel Product | TM:Custom BRF+ table for choosing the right the MTR ( Means of transport) during Freight order save to get the correct X-Route ( Cross route , applicable for Amsterdam & can be extended to other locations in future) | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B9C16A0D7-E7D5-4387-AF8E-9D05BB179ADC%7D&file=R3_IP_OTC_LO-180-090_Schedule_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true&CID=C7BB528A-789A-48E9-9DBE-F28B4FE68BAD&wdLOR=cBE3401A0-703B-455D-8E2D-7E50A96EADB4 | 02.No | 01.Yes |  | 2025-01-22 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-01-20 06:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 0.5 | 0.5 | 1150 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-09-30 | TM |  |  | 1 |  | 1657 | [7 empty] | 4. Completed | 17. FUT In progress | 12/01: Additional TC being executed, ETA 12/02 11/24: FUT review call on 11/25 with Intel, ETA 27/11 11/18: FUT WIP 11/14: FUT started and WIP | 2025-10-31 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2639 | LOGE1148 | 04.Enhancement | 01.IP - Intel Product | 2DN - Trigger Auto packing in 2nd DN of 2DN X-Dock Model | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Enhancement%20to%20trigger%20Auto%20packing%20in%202nd%20DN%203B13.pptx?d=w751d99fc660943b691adf5204508dd42&csf=1&web=1&e=QTyRnN |  |  |  | 2025-01-22 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-05 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-05 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-07 | 2025-10-31 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2025-01-20 06:30 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1148 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-03-21 | 2025-05-16 |  |  | 2025-11-07 |  |  |  | 1 | 04.5 Logistics - 2DN | 2300 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/04: Intel first review call is done, 4 open points have been provided by Intel, 2 points addressed, remaining 2 points to be addressed, Defect #4212 is raised 10/31: Sent for Intel Review, review call with Intel scheduled on 11/04 10/24 - Defect 3879. 2/5 are tested 10/10: Blocked with defect#3487 10/09 EP: Update FUT end date based on 2DN design closure was delayed which led to delay in subsequent deliverables. 2DN FUTs are planned in future sprints. Dates to be updated. | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2638 | LOGE1147 | 04.Enhancement | 01.IP - Intel Product | 2DN - S4 – Error Handling program in 2DN X-Dock Model | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Error%20Handling%20Program.pptx?d=wf7b2fa7ea73c4b9aa35a66ad09e27bd6&csf=1&web=1&e=VbUfg0 | 02.No | 01.Yes |  | 2025-01-22 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-04-25 | 2025-05-23 | 100% | 2025-05-28 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-19 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-19 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-19 | [15 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-01-20 06:30 | mafrozkhursheed@deloitte.com | 2026-02-19 06:23 | 10 | 2025-01-23 | 01.S4 |  |  | 2 | 2 | 1147 |  | R3 ITC1 | [6 empty] | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | 2025-09-19 | 2025-09-19 | 2025-09-19 |  | 2025-09-19 | 2025-10-10 | 2025-09-19 | 2025-09-19 | [12 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | [5 empty] | 2025-05-30 | 2025-06-13 | [6 empty] | 1 | 04.5 Logistics - 2DN | 1609 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/22: Defect#5752 is closed ,email sent to intel for Open points ,awaiting feedback from Intel 12/15: FUT was sent for review on 12/12 12/8- 5:30 pm- FPR issue resolved, Retest is in progress. ETA 12/9 to send for intel review 12/08: Blocked by cost element issue, checking with FPR team 12/01: Defect# 5064 is fixed, retest is blocked by issue with IC SO creation. 11/24: New defects 4885, 4886 has been created, yet to be picked by Tech. ETC to complete FUT 12/2. 11/18: Defect 4473/4570 re-assinged to dev team. EP: 09/18: No Ext FUT (2DN Object) | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-19 | No | ZTOTC_PARAMS table impact | No |  | No |  | 2026-03-09 | 2026-04-03 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1750 | LOGE1130 | 04.Enhancement | 01.IP - Intel Product | Enhancement to Re-Plan the De-linked Freight Units based on Hawb Numbers | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-190-100_IP_Freight%20Order%20Execution_3PL_TM_RICEFW%20Intake%20Form.pptx?d=w5019ee05f4bd498ea9fa378c8560eb93&csf=1&web=1&e=vaGb4m | 02.No | 01.Yes |  | 2025-01-17 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-01-17 00:58 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-12 | 01.S4 |  |  | 2 | 2 | 1130 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | [5 empty] | 2025-05-16 | 2025-07-18 |  |  |  | TM |  |  | 1 | 08. Not Applicable | 1987 | [7 empty] | 1. On Track | 17. FUT In progress | 02/02: Review call scheduled for 02/03 01/30: FUT 9 of 10 TC completed, 1 TC WIP. POC successful. Potential change (8hrs), 3 TC from 1131 to be added 01/22: Call with Technical team at 1.15 pm IST for the feasiblity check post which Intel alignment call to happen 01/19: FUT in progress, 2/10 tcs completed. 01/12: Dev Fix WIP, TUT + FUT to start from 13th 12/22: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2609 | LOGE1118_IP | 04.Enhancement | 01.IP - Intel Product | ISM – MY Security Check Fiori app - IF | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/2609_R3_FTS_LOGISTICS_My%20Security%20approval.pptx?d=w13c5a1923f8e419c823296c03ae80b28&csf=1&web=1&e=Ebdhoh | 02.No | 01.Yes |  | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-17 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jenoronha@deloitte.com | 2025-03-13 02:43 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 |  |  | 2 | 2 | 1118 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-08-15 |  |  |  | 1 |  | 2368 | [7 empty] | 1. On Track | 3. Awaiting Approval | 8/29: Conditional approval received from IT. Awaiting PS approval 8/25: Under Intel Review 08/18: Raised a new defect 2225 not able to approve ISM.Tech ETA is 19/08 | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2609 | LOGE1118_IF | 04.Enhancement | 02.IF - Intel Foundry | ISM – MY Security Check Fiori app - IF | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/2609_R3_FTS_LOGISTICS_My%20Security%20approval.pptx?d=w13c5a1923f8e419c823296c03ae80b28&csf=1&web=1&e=Ebdhoh | 02.No | 01.Yes |  | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-17 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-01-16 12:46 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 | LOGE1118_IP | 02.High | 0.4 | 0.4 | 1118 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-08-15 |  |  |  | 1 |  | 2369 | [7 empty] | 1. On Track | 3. Awaiting Approval | 8/29: Conditional approval received from IT. Awaiting PS approval 8/25: All Defect resolved. Retesting in progress. ETA: 8/26 08/18: Raised a new defect 2225 not able to approve ISM.Tech ETA is 19/08 | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2610 | LOGE1117_IP | 04.Enhancement | 01.IP - Intel Product | ISM – Employee acknowledgement - IP | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/Employee%20acknowledgement%20intake%20form.pptx?d=waa0e989fc73b433f8c104d2e65a087cc&csf=1&web=1&e=INTbvw | 02.No | 01.Yes |  | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-30 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jenoronha@deloitte.com | 2025-03-13 02:43 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 |  |  | 2 | 2 | 1117 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-08-15 |  |  |  | 1 |  | 2370 | [9 empty] | 8/29: Conditional approval received from IT. Awaiting PS approval 8/25: Under Intel Review. Walkthrough scheduled on 8/26 08/18: Defect 2192 in progress with Tech Team | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2610 | LOGE1117_IF | 04.Enhancement | 02.IF - Intel Foundry | ISM – Employee acknowledgement - IF | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/Employee%20acknowledgement%20intake%20form.pptx?d=waa0e989fc73b433f8c104d2e65a087cc&csf=1&web=1&e=INTbvw | 02.No | 01.Yes |  | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-30 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2025-01-16 12:46 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 | LOGE1117_IP | 02.High | 0.4 | 0.4 | 1117 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | [5 empty] | 2025-04-18 | 2025-06-13 |  |  | 2025-08-15 |  |  |  | 1 |  | 2371 | [9 empty] | 8/29: Conditional approval received from IT. Awaiting PS approval 8/25: Under Intel Review. Walkthrough scheduled on 8/26 08/18: Defect 2192 in progress with Tech Team | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2565 | LOGE1116 | 04.Enhancement | 01.IP - Intel Product | 2DN - Enhancement to capture required fields of 1st Delivery in 2DN X-Dock Model | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Enhancement%20to%20Capture%20Essential%20fields%20in%201st%20Delivery.pptx?d=w1e9c8ea8a7e343778eeea7e67239449c&csf=1&web=1&e=B01whR | 02.No | 01.Yes | LOGI1148 | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-02-28 | 2025-02-28 | 100% | 2025-03-10 | 2025-06-16 | 2025-06-20 | 2025-05-20 | 100% | 2025-05-24 | 2025-06-23 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-02-05 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-28 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1116 |  | R3 ITC1 | [6 empty] | 2025-03-10 | 2025-03-10 | 2025-03-10 |  | 2025-05-24 | 2025-06-20 | 2025-05-24 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | [5 empty] | 2025-03-28 | 2025-07-18 | [6 empty] | 1 | 04.5 Logistics - 2DN | 2621 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/22: Sent for Intel review and approval 10/16 EP: Update FUT Revised End date 10/10: sent back for approval on 10/08, awaiting Intel approval, reminder sent 10/09 ETA for approval/is this object approved? 10/06: Defect#3339 is fixed and retest in progress, if no further issues encountered, one pending scenario will be completed and re-sent for approval by 10/06 09/29: Defect 3339 is open and awaiting logic from order management team 09/12: Delayed due to Defects.2/5 pending to be tested. Defect 3006 open with Tech team. ETA 9/15 | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2637 | LOGE1114 | 04.Enhancement | 01.IP - Intel Product | 2DN - Post 3PL 3B2 or manual Goods Issue from CW or IW - Wrapper Program to complete processing of subsequent documents in the first leg of 2DN X-Dock Model. ​ | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2DN%20X-Dock%20Model/R3_IP_OTC_Wrapper%20Program.pptx?d=w319348274eee4e7e85501f871deceb55&csf=1&web=1&e=8yXhhs | 02.No | 01.Yes |  | 2025-01-21 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-02-28 | 2025-02-28 | 100% | 2025-03-10 | 2025-06-16 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-02-05 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-16 12:46 | mafrozkhursheed@deloitte.com | 2026-02-19 06:23 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1 | 1114 |  | R3 ITC1 | [6 empty] | 2025-03-10 | 2025-03-10 | 2025-03-10 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | [5 empty] | 2025-03-28 | 2025-07-18 | [6 empty] | 1 | 04.5 Logistics - 2DN | 1608 | [7 empty] | 1. On Track | 4. Smartsheet Hygiene(5.1) | 11/11 - 5.1 status is still open. Please mark it as completed 11/06 EP: Update Status to FUT Complete. FUT Review & Approval complete per IDM 2.0 Build Sprint Plan (R3 Past R&A 2) | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No | ZTOTC_PARAMS table impact | No |  | No |  | 2026-03-09 | 2026-04-03 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1645 | LOGE1090_IP | 04.Enhancement | 01.IP - Intel Product | PGI confirmation for non-inventory Intel freight shipments via email | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-080_Form%20-%2010_%20RICEFW%20Intake%20form.pptx?d=w9951cca0aad04a16b7a3b72072c06d48&csf=1&web=1&e=WFzgUz | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-26 | 2025-08-29 | 2025-09-05 | 2025-04-29 | 100% | 2025-08-04 | 2025-09-26 | 2025-10-10 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-20 08:42 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 | 2025-01-18 | 01.S4 |  |  | 1 | 1 | 1090 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-04-18 | 2025-03-26 |  | 2025-08-04 | 2025-09-05 | 2025-08-04 |  | 2025-08-04 | 2025-10-10 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1746 | [10 empty] | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1645 | LOGE1090_IF | 04.Enhancement | 02.IF - Intel Foundry | PGI confirmation for non-inventory Intel freight shipments via email | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-080_Form%20-%2010_%20RICEFW%20Intake%20form.pptx?d=w9951cca0aad04a16b7a3b72072c06d48&csf=1&web=1&e=WFzgUz | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-25 | 2025-08-29 | 2025-09-05 | 2025-03-25 | 100% | 2025-08-04 | 2025-10-03 | 2025-10-10 | 2025-04-02 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-04-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-20 08:42 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 | 2025-01-18 | 01.S4 | LOGE1090_IP | 03.Medium | 0.2 | 0.2 | 1090 |  | R3 ITC1 | [6 empty] | 2025-03-25 | 2025-04-18 | 2025-03-25 |  | 2025-08-04 | 2025-09-05 | 2025-08-04 |  | 2025-08-04 | 2025-10-10 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1745 | [10 empty] | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2649 | LOGE1087 | 04.Enhancement | 08.EWM | Enhancement on the RF screen to auto populate the HU number for receiving. | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD8503BDD-9321-42DA-8277-39C95C76C5DA%7D&file=RICEFW_INTAKE_FORM_RF_ENHANCEMENT_TO%20AUTO%20POPULATE%20THE%20HU%20NUMBER.pptx&wdLOR=cEFCBFB39-F2D4-428C-94B8-A8879A8FD107&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-25 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1087 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-08-15 | 2025-08-13 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-22 | TM | WIINGS Only | TRUE | 1 |  | 1840 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2648 | LOGE1086 | 04.Enhancement | 08.EWM | Enhancement on the RF screen for identifying the correct inbound delivery based on the vendor label with reference of PO number, material etc. | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF6E7EE3F-5D3F-46BD-BEEC-D4C48227CF23%7D&file=RICEFW_INTAKE_FORM_RF_ENHANCEMENT_TO%20IDENTIFY%20CORRECT%20IBD%20BY%20VENDOR%20LABEL.pptx&wdLOR=cC0E1DB83-97E6-400F-9A50-452D2358E679&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-17 | 2025-03-14 | 2025-03-14 | 100% | 2025-03-14 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-13 | [15 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-10-08 | 2025-10-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-10-24 | 2025-10-24 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-20 08:42 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1086 |  | R3 ITC1 | [6 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | [12 empty] | 2025-09-13 | 2025-09-13 |  |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | [5 empty] | 2025-03-14 | 2025-07-18 |  |  | 2025-08-22 | TM | WIINGS Only | TRUE | 1 |  | 1839 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Awaiting approval | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-13 | 2025-09-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2579 | LOGE1080_IP | 04.Enhancement | 01.IP - Intel Product | Email notifications to be triggered as part of ISM Workflows | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2579_FTS-LE-RICEFW%20intake%20form%20for%20email%20notifications%20to%20be%20triggered%20as%20part%20of%20ISM%20Workflows.pptx?d=w7e892c942f98482db161c2ec1a230527&csf=1&web=1&e=ubpilD | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-30 | 2025-05-30 | 100% | 2025-08-04 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-03 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 2 | 2 | 1080 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-11-14 |  |  |  | 1 |  | 1558 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/11: Awaiting for Approval from Intel IT and PS. 10/31: ISM workflow defects are not resolved. 10/22: Dependency on LOGW1078 | 2025-10-08 | N | 99. Logistics |  |  |  | 5.1 Complete. Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2579 | LOGE1080_IF | 04.Enhancement | 02.IF - Intel Foundry | Email notifications to be triggered as part of ISM Workflows | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2579_FTS-LE-RICEFW%20intake%20form%20for%20email%20notifications%20to%20be%20triggered%20as%20part%20of%20ISM%20Workflows.pptx?d=w7e892c942f98482db161c2ec1a230527&csf=1&web=1&e=ubpilD | 02.No | 01.Yes |  | 2025-01-02 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-20 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2024-12-20 08:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 | LOGE1080_IP | 02.High | 0.4 | 0.4 | 1080 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1557 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/11: Awaiting for Approval from Intel IT and PS. 10/31: ISM workflow defects are not resolved. 10/22: Dependency on LOGW1078 | 2025-10-08 | N | 99. Logistics |  |  |  | 5.1 Complete. Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2532 | LOGE1061 | 04.Enhancement | 08.EWM | Enhancement for Pop-Up message during Decontamination Process (Copper to Non-Copper) | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2532_R3_FTS_IF_PM_EWM_Enhancement%20for%20Pop-up%20during%20Cu%20to%20Non_Cu%20Movement.pptx?d=wf67d34c6c9874a209a248c60b189a3c7&csf=1&web=1&e=Rp8scM | 02.No | 01.Yes |  | 2024-12-18 | cari.h.shim@intel.com | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-28 | 2025-02-21 | 100% | 2025-02-07 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-20 | 2025-07-11 | 2025-07-16 | N | 100% | 2025-08-11 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 1 | 1 | 1061 |  | R3 ITC1 | [6 empty] | 2025-02-07 | 2025-02-28 | 2025-02-07 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | [5 empty] | 2025-02-07 | 2025-06-13 |  |  | 2025-06-23 | TM | WIINGS Only | TRUE | 1 |  | 1668 | [9 empty] | Delay due to defects found during testing. Defects are resolved and the object was handed back for FUT on 07/24. Currently testing is in progress and scheduled to be sent to business on 07/28 | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2158 | LOGE1059 | 04.Enhancement | 08.EWM | RF Capability for Rejection of the Returns to Factory and send notification | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2158_R3_FTS_IF_PM_EWM_RF%20RF%20Capability%20for%20Rejection%20of%20the%20Returns%20to%20Factory%20and%20send%20notification.pptx?d=w32f1049a44394fd08da17e372bbfa09b&csf=1&web=1&e=lSQuho | 02.No | 01.Yes |  | 2025-01-02 | cari.h.shim@intel.com | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-11 | 2025-04-04 | 100% | 2025-04-16 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-06 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-06 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-06 | [15 empty] | 2025-09-06 | 2025-09-06 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 1 | 1 | 1059 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | 2025-09-06 | 2025-09-06 | 2025-09-06 |  | 2025-09-06 | 2025-09-12 | 2025-09-06 | 2025-09-06 | [12 empty] | 2025-09-06 | 2025-09-06 |  | 2026-02-23 | 2026-02-23 | 2026-03-04 | 2026-02-23 | [5 empty] | 2025-03-14 | 2025-07-18 |  |  | 2025-08-22 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 1599 | [7 empty] | 4. Completed | 1. Approved no action | 02/23: FUT approved by PS & IT. 02/20: Awaiting business approval, reminder 3 sent. 02/16: All comments are addressed and discussed in workshop, pending approval since 1/30. 01/19: Defect 5370 & 6406 is with tech team, defect is still open to start FUT. 01/14: Defect # 5370 is open with tech team, new ETA by tech 01/16. 01/12: Defect # 5370 is open with tech team, awaiting ETA. 01/05: Defect as CR #5370 with tech team, no new ETA given as defect status is stalled. 12/15: Defect as CR #5370 with tech team, ETA by tech 12/19. 12/12: Defect as CR #5370 with tech team, ETA by tech 12/19. | 2025-09-12 | N | 99. Logistics |  |  |  | 1210: Build is complete. 5.2 to be added to S21 plan |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2157 | LOGE1058 | 04.Enhancement | 08.EWM | Determine Warehouse Process type for PM Returns | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2157_R3_FTS_IF_PM_EWM_Determine%20Warehouse%20Process%20type%20for%20PM%20Returns.pptx?d=wfcd8efbf58db46a2bbba3285fd6fe027&csf=1&web=1&e=qA1tFn | 02.No | 01.Yes |  | 2025-01-02 | cari.h.shim@intel.com | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-01 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-11 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-11 | 2025-07-18 | 2025-07-11 | 100% | 2025-08-26 | [15 empty] | 2025-08-26 | 2025-08-26 |  |  | 2026-02-04 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-27 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 0.5 | 0.5 | 1058 |  | R3 ITC1 | [6 empty] | 2025-04-01 | 2025-04-01 | 2025-04-01 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-08-26 | [12 empty] | 2025-08-26 | 2025-08-26 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-03-07 | 2025-07-18 |  |  | 2025-08-22 | TM | WIINGS Only | TRUE | 1 | 08. Not Applicable | 1598 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: All comments are addressed, expect new scenarios which business requested to test where new config values required by business. 12/15:FUT re-sent to business for review & approval on 12/11. 12/12: FUT sent to business for review & approval on 12/11. 12/08: Defect 5053 (11/27) is created for incorrect WPT determination. Defect under resolution with tech team., ETA 8/12.Total TC 8. One more observation- The reason code is not flowing correctly from S4 to EWM in case of multiple line items in PM. This is related to LOG1052. 12/01: LE defect is closed, but new defect for this object is with tech team for resolution. Defect# 4958. 11/24: Dependent on object LOG1052 which has defect open. 11/18: Dependent on object LOG1052 which has defect open. 10/10: This object is planned in sprint 19, revised FUT date is shared with PMO. 10/06: This object is planned in sprint 19, revised FUT date is shared with PMO. | 2025-07-18 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2124 | LOGE1054 | 04.Enhancement | 08.EWM | Email/Text Trigger to Factory Technician and Post Goods Issue upon all WO confirmation when delivered at passthrough | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2124_R3_FTS_IF_PM_EWM_L-040-080_Email%20or%20Text%20Trigger%20to%20Factory%20Technician%20when%20delivered%20at%20passthrough.pptx?d=wa022c633ae39413f899a7123c129fa24&csf=1&web=1&e=ITQCkR | 02.No | 01.Yes |  | 2024-12-18 | cari.h.shim@intel.com | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-31 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-02 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-02 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-11-28 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-15 | 01.S4 |  |  | 2 | 2 | 1054 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 |  | 2025-10-02 | 2025-10-03 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-04-11 | 2025-08-15 |  |  | 2025-09-19 |  | WIINGS Only | TRUE | 1 | 08. Not Applicable | 2719 | [7 empty] | 4. Completed | 3. Awaiting Approval | 1/20: All opens are addressed and awaiting approval from IT. 1/16: Test involving EWM is being tested and we will respond back to open question on negative test. 01/05: 1 test case in progress. ETA 01/05. 12/15:Business review comments are being addressed. Tech is fixing the defect 5552. 12/8: Walkthrough sessions are completed and opens are addressed. Imran is following up with Niamh for final approval 12/1: Open comments to be addressed today. 11/24: Documentation in progress. ETA 11/25. 11/18: Defect 4502 is with the tech team. | 2025-10-03 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2612 | LOGE1052_IP | 04.Enhancement | 01.IP - Intel Product | Custom fields required on delivery screen | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2612_R3_FTS_IP_LOGISTICS_Custom%20fields%20on%20delivery%20screen.pptx?d=w6cd4391e737243f485d0f222b75c05d6&csf=1&web=1&e=LOOTwx | 02.No | 01.Yes |  | 2024-12-18 | Jorge Sanchez | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-01 | 2025-08-08 | 2025-06-17 | 100% | 2025-07-21 | 2025-09-05 | 2025-09-12 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1052 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-30 | 2025-10-30 | 2025-10-30 | [5 empty] | 2025-05-30 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 |  | 1493 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/24 - 2/9 test scenarios are completed. Defect 3861. Dependent with 1074 10/10: Payload 2 non mandatory elements requested and 2 field logic to be updated raised a defect for that tech is looking into the defect. ETA for fixing the defect 10/10/2025 | 2025-06-13 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2612 | LOGE1052_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom fields required on delivery screen | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2612_R3_FTS_IP_LOGISTICS_Custom%20fields%20on%20delivery%20screen.pptx?d=w6cd4391e737243f485d0f222b75c05d6&csf=1&web=1&e=LOOTwx | 02.No | 01.Yes |  | 2024-12-18 | Jorge Sanchez | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-26 | 2025-08-01 | 2025-08-08 | 2025-06-17 | 100% | 2025-07-21 | 2025-09-05 | 2025-09-12 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-18 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jenoronha@deloitte.com | 2025-02-24 04:54 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-01-15 | 01.S4 | LOGE1052_IP | 03.Medium | 0.2 | 0.2 | 1052 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-03-28 | 2025-03-26 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | [5 empty] | 2025-03-28 | 2025-06-13 |  |  | 2025-10-08 |  |  |  | 1 |  | 1494 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/18: Following up for approval 11/11: CR to be created for text field. Defect created for requirement time 10/24 - 14/15 scenarios completed. Working with last scenario 10/10: Payload 2 non mandatory elements requested and 2 field logic to be updated raised a defect for that tech is looking into the defect. ETA for fixing the defect 10/10/2025 | 2025-06-13 | N | 99. Logistics |  |  |  | 5.1 Complete. Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2233 | LOGE1048 | 04.Enhancement | 08.EWM | To Identify Priority Inbound Deliveries in EWM and display the details of these deliveries in form of Report and SAP Warehouse Monitor. | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2233_R3_IF_PTP_LOGISTICS_EWM_L-040-040_Report%20for%20Priority%20Inbound%20Delivery.pptx?d=w8960efe98dca40aebd3d9f31d54d2d04&csf=1&web=1&e=MIL8of | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-11 | 2025-04-11 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-11 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-25 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-25 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 2 | 2 | 1048 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-15 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-11 | 2025-09-12 | 2025-09-11 | [5 empty] | 2025-04-11 | 2025-08-15 |  |  | 2025-09-19 | TM | WIINGS Only | TRUE | 1 |  | 2470 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-08-15 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2232 | LOGE1047 | 04.Enhancement | 08.EWM | RF Scanner -Inbound Process Screen to enhanced to show the Delivery Priority Indicator field against Inbound Delivery | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2232_R3_IF_PTP_LOGISTICS_EWM_L-040-040_RF%20Scanner%20with%20Priority%20Indicator.pptx?d=w77c78fb8f4e8457f8d2d4d9c943a8dd8&csf=1&web=1&e=j4u2RX | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-15 | 2025-05-02 | 2025-05-09 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-23 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-23 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 2 | 2 | 1047 |  | R3 ITC1 | [6 empty] | 2025-02-15 | 2025-02-15 | 2025-02-15 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-02-14 | 2025-06-13 |  |  | 2025-06-23 | TM | WIINGS Only | TRUE | 1 |  | 2469 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2231 | LOGE1046 | 04.Enhancement | 08.EWM | Enhancement to capture Priority Indicator field in EWM Inbound Delivery from S/4 Inbound Delivery. | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2231_R3_IF_PTP_LOGISTICS_EWM_L-040-040_Inbound%20Delivery%20with%20Priority.pptx?d=wf11c3cf1ec50410b81c86d1987226e20&csf=1&web=1&e=DG1hAb | 02.No | 01.Yes |  | 2024-12-19 | Cari H Shim | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-14 | 2025-05-02 | 2025-05-09 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-21 | 01.S4 |  |  | 2 | 2 | 1046 |  | R3 ITC1 | [6 empty] | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-02-07 | 2025-06-13 |  |  | 2025-06-23 | TM | WIINGS Only | TRUE | 1 |  | 2468 | [10 empty] | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2660 | LOGE1035 | 04.Enhancement | 08.EWM | Inventory update program for Stock type updates | 06. PTP | 6.3 PTP - EWM | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP-EWM/XXXX_RICEFW_QI-130-010_Inventory%20Update%20Program%20for%20Stock%20type%20updates_IF.pptx?d=w70ffcadd3c624043be4059cbf9b396c9&csf=1&web=1&e=T8lcY2 | 02.No | 01.Yes |  | 2025-01-02 | Cari H Shim | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-31 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1035 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 |  |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | [5 empty] | 2025-04-25 | 2025-08-15 |  |  | 2025-09-19 | TM | WIINGS Only | TRUE | 1 |  | 1844 | [7 empty] | 1. On Track | 1. Approved no action | 12/18: Approved 12/17: Approval received from Intel and QM business. Approval from Graeme pending. Reminder sent to Graeme. 12/15: PTP QM defect was holding the approval, the defect 5639 has been fixed Email for the same is sent to business. 10/12: Sent for intel approval on 12/9. Workshop is planned with intel Business &IT on 12/12. 12/08: FUT documentation in progress. Defect 5062 is still open. ETA to submit to business for review is 9th Dec 12/01: CR defect 5062 created on Friday after SAP response. 11/25: New Defect 4899 created. OSS note 1329087 opened on 14th Nov and awaiting resolution from SAP. 11/24: Defect 4606 is with Dev Team, ETA ?. MATDOC is not getting updated with correct stock type post stock type change via MIGO. OSS raised on 11/17, awaiting feedback. TC 9/21 completed so far. 11/18: LOGE1035 the FUT is in progress, also we raised one defect 4606.there are around 21, 22 scenarios out which 9 have been tested | 2025-10-24 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2659 | LOGE1034 | 04.Enhancement | 01.IP - Intel Product | Delivery creation enhancement to update Stock type | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP-EWM/XXXX_RICEFW_QI-130-010_Delivery%20creation%20enhancement%20to%20update%20Stock%20Type_IF.pptx?d=w0fcc05ea643e41ed99a06f995102022c&csf=1&web=1&e=b7Wbxe | 02.No | 01.Yes |  | 2025-01-02 | Cari H Shim | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-27 | 2025-06-27 | 100% | 2025-07-24 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-11 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | [15 empty] | 2025-10-11 | 2025-10-11 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-16 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-15 | 01.S4 |  |  | 1 | 1 | 1034 |  | R3 ITC1 | [6 empty] | 2025-07-24 | 2025-07-24 | 2025-07-24 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [12 empty] | 2025-10-11 | 2025-10-11 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | [5 empty] | 2025-04-25 | 2025-08-15 |  |  | 2025-09-19 |  | WIINGS Only | TRUE | 1 |  | 1843 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05 - Review comments are received, Defect# 5931 is raised for the same. ETA from Tech is 01/06. 12/22 - FUT sent for Review and Approval, Awaiting further feedback/Approval from Intel IT & Business/PS 12/15 - FUT is in-progress, 38 TCs are completed out of 56. Dependency on LOGI0954 (FUT is in-progress) which is blocking 7 TCs. Defect# 5598 is raised, blocking 9 TCs 12/08 - 21 TCs are completed out of 56. Defect# 5332 is raised, blocking 13 TCs. Dependency on LOGI0502 & LOGI0954 which is blocking 12 TCs.. 12/01- FUT is in-progress, 12 TCs are completed out of 56. Dependency on LOGI0502 & LOGI0954 which is blocking 12 TCs. Defect# 5104 is raised, blocking rest of the TCs. ETA from Tech is 12/01 11/24: This has 60 TCs . FUT is in-progress, 8 TCs are completed out of 56. Dependency on LOGI0502 & LOGI0954 which is blocking 12 TCs. ETA for FUT 12/04 11/18 - FUT Started, 4 TCs are completed. Majority of TCs dependent on multiple Interface WRICEF for which FUT is till in-progress with defects or blocked 11/14 - TCs are being drafted for E2E Testing, ETA today 11/14 | 2025-10-03 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2204 | LOGE0979 | 04.Enhancement | 01.IP - Intel Product | Pre-alert summary report for the EMEA customer | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B141FEA67-3CA4-4862-9293-1563D6FB0349%7D&file=R3_IP_OTC_Pre%20alert%20to%20EU%20customer_RICEFW%20Intake%20Form%20.pptx&wdLOR=cC7C9A5E6-2191-4105-8034-D09CE16D42AA&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | Jorge Sanchez | 01.Approved | 2024-12-16 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-26 | 2025-06-20 | 2025-06-20 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-08-25 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-25 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-25 | [15 empty] | 2025-08-25 | 2025-08-25 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-26 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-12-10 22:28 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-19 | 01.S4 |  |  | 1 | 1 | 0979 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-25 | 2025-10-17 | 2025-08-25 |  | 2025-08-25 | 2025-11-07 | 2025-08-25 | 2025-08-25 | [12 empty] | 2025-08-25 | 2025-08-25 |  |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | [5 empty] | 2025-03-07 | 2025-06-13 |  |  | 2025-08-22 |  |  |  | 1 |  | 1782 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24: Still Awaiting for intel approval. On 11/21review call happened with Intel. 11/14: Defect#4443 is closed, defect#4549 is partially fixed, ETA 11/14, if fixed FUT can be sent out today 11/11: Defect#4266 & 4347 is still open, ETA 11/12 10/31: Defect open for more than a week 3771, no clear ETA 10/24 - Defect 3771 | 2025-11-07 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-08-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2087 | LOGE0976_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to enable delivery priority Indicator in Inbound delivery Document-IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/2%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Logistics/Final%20Deliverables/Priority_Indicator_LE.pptx?d=w471f4f30e3a8454b9f46ecf0a631cd79&csf=1&web=1&e=kuJzf8 | 02.No | 02.No |  | 2024-12-11 | cari.h.shim@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-13 | 2025-05-01 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-28 | 2025-11-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-04 | 2025-11-04 | N | 100% | 2025-10-28 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-12-06 07:21 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-19 | 01.S4 |  |  | 1 | 1 | 0976 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-28 | 2025-11-04 | 2025-10-28 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-19 |  | WIINGS Only | TRUE | 1 |  | 1827 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Awaiting approval 10/17 - Recieved review comments, working on the update | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | Yes | Change in Custom Table entries for Plant Tables - ZTPTP_PARAMS | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed |  | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2087 | LOGE0976_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to enable delivery priority Indicator in Inbound delivery Document-IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/06.%20PTP/2%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Logistics/Final%20Deliverables/Priority_Indicator_LE.pptx?d=w471f4f30e3a8454b9f46ecf0a631cd79&csf=1&web=1&e=kuJzf8 | 02.No | 02.No |  | 2024-12-11 | cari.h.shim@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-13 | 2025-05-01 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-28 | 2025-11-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-04 | N | 100% | 2025-10-27 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-12-06 07:30 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-19 | 01.S4 | LOGE0976_IP | 03.Medium | 0.2 | 0.2 | 0976 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-19 |  | WIINGS Only | TRUE | 1 |  | 1826 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Awaiting approval 10/17 - Recieved review comments, working on the update | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2294 | LOGE0952 | 04.Enhancement | 01.IP - Intel Product | Generate Outbound 3B2 Message from S4 to OSAT supplier E2Open onboarded Suppliers- S4 IP to E2Open | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PTP%20LE/Generate%20Outbound%203B2%20Message%20from%20S4%20to%20OSAT%20supplier%20E2Open%20onboarded%20Suppliers-%20S4%20IP%20to%20E2Open.pptx?d=w2298c6a5e4da4c449a67297de45edb45&csf=1&web=1&e=lUokUZ | 02.No | 01.Yes |  | 2024-12-19 | cari.h.shim@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-17 | 2025-02-28 | 2025-03-21 | 100% | 2025-02-27 | 2025-04-14 | 2025-04-18 | 2025-03-25 | 100% | 2025-04-10 | 2025-05-05 | 2025-05-16 | 2025-04-03 | 100% | 2025-04-03 | 2025-05-05 | 2025-05-16 | 2025-04-03 | 100% | 2025-04-03 | [15 empty] | 2025-04-03 | 2025-04-03 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-02-24 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-11-20 03:14 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2024-12-20 | 01.S4 |  |  | 1 | 1 | 0952 |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-03-21 | 2025-02-27 |  | 2025-04-10 | 2025-04-18 | 2025-04-10 |  | 2025-04-03 | 2025-05-16 | [14 empty] | 2025-04-03 | 2025-04-03 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-22 |  |  |  | 1 |  | 2593 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/20 - Addressed all comments, Awaiting further feedback from Intel IT /Business. Business PS/Intel ITY(Malaysia team is on Holiday) 02/16- Defect#7242(Need to validate the applied logic) still open, ETA- 02/16, will send the updated document once defect is fixed 02/12- Received approval from Natalyn, Received addtional feedback today from DM team, will reply back by today EOD. ETA - 02/12 01/05 - CR Changes completed, TUT is in progress. FUT to be started post TUT competion from tech. 12/22 - CR Changes completed, Dev to start the TUT, TUT Completion ETA - 12/23 12/15 - Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-03 | Yes | Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-04 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2250 | LOGE0945 | 04.Enhancement | 01.IP - Intel Product | Update COF, COA and FVR in 3PL WMS - EDI 4C1B | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_LI-120_190_Enhancement%20-%2060_%20RICEFW%20Intake%20form.pptx?d=wa74f352b0f404734a8d36e4208c15a45&csf=1&web=1&e=xEcvc5 | 02.No | 01.Yes | LOGI1272 | 2024-11-20 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-26 | 2025-03-31 | 2025-04-01 | 2025-04-01 | 100% | 2025-08-04 | 2025-07-14 | 2025-07-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-29 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-18 08:44 | 10 | 2025-02-13 | 01.S4 |  |  | 1 | 1 | 0945 |  | R3 ITC1 | [6 empty] | 2025-03-26 | 2025-03-28 | 2025-03-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | [5 empty] | 2025-05-02 | 2025-07-18 | [6 empty] | 1 |  | 2297 | [7 empty] | 2. At Risk | 12. Blocked by SAP OSS | 8/25: Defect Resolved. Testing in progress. ETA: 8/26 08/18: Defect is still with Tech team in progress. | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Param table entry addition. | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-18 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2119 | LOGE0936 | 04.Enhancement | 01.IP - Intel Product | Validate receiving consigned materials into consignment hub – EDI 4B2 CSGN | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_LI-120_190_Enhancement%20-%2010_%20RICEFW%20Intake%20form.pptx?d=w01017a75e1c3419bb4ad4589b48c514b&csf=1&web=1&e=ycciVb | 02.No | 01.Yes | LOGI1267 | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-29 | 2025-09-05 | 2025-05-20 | 100% | 2025-05-21 | 2025-09-26 | 2025-10-10 | 2025-05-30 | 100% | 2025-05-21 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-21 | [15 empty] | 2025-05-21 | 2025-05-21 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-28 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-04-06 09:17 | 10 | 2025-01-18 | 01.S4 |  |  | 1 | 1 | 0936 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-05-21 | 2025-09-05 | 2025-05-21 |  | 2025-05-21 | 2025-10-10 | 2025-05-21 | 2025-05-21 | [12 empty] | 2025-05-21 | 2025-05-21 |  |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 | 08. Not Applicable | 2718 | [9 empty] | 8/25: New defect 2449 raised on Friday. 08/18: Due to preceding process GAP, we are unable to get correct data to process this object's scenarios. | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-21 | Yes |  | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-04-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2089 | LOGE0935_IP | 04.Enhancement | 01.IP - Intel Product | Fiori App - Shipping Memo | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 09. FUT Overdue | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2089_R3_FTS_IP_LOGISTICS_LO-180-050_Enhancement%20-%20Fiori%20App_%20RICEFW%20Intake%20form.pptx?d=w39182c638eea4b0fbc8ad972e8a83159&csf=1&web=1&e=FJ6a1K | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-10 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2026-02-02 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-03-13 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-03-13 | [15 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-03-20 | 2026-03-20 |  | 95% | 90% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-20 | N | 92% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-11-20 03:23 | pusrai@deloitte.com | 2026-04-03 02:27 | 9 | 2025-01-08 | 01.S4 |  |  | 4 | 4 | 0935 |  | R3 ITC1 | [6 empty] | 2025-06-10 | 2025-06-10 | 2025-06-10 |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [12 empty] | 2026-03-13 | 2026-03-13 |  |  |  | 2026-03-20 | [6 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1829 | [7 empty] | 2. At Risk | 17. FUT In progress | 04/03: tech yet to make all teh fixes , once completed we can for approvals. ETA provided by Sanket-04/03 3/27: 4 points required for conditional approval in fix by tech ETA-03/27, documentation in progress. 3/26: All cases tested, tech fixing the high priority issues for conditional approval, meanwhile documentation in progress. ETA 3/27 3/25:39/43 TC tested, fixes in progress, target to sent the FUT for Intel approval for all TC's by 3/25. 3/24:35/43 TC tested, fixes in progress, target to sent the FUT for Intel approval for all TC's by 3/25. 3/23:33/43 TC. remaining issues in fix from 8294 defect, 10/30 points are yet to be fixed.8300- 20/42 points yet to be fixed. Target to sent the FUT for intel approval all TCs by 3/25. 3/19: TC completed 33/43 points fixed from 8294 defect, 10 Points are yet to be fixed.8300- Testing in progress. Target to sent the FUT for intel approval all TCs by 3/25. 3/18: Defect#8294,8300 in progress with tech. ETA 3/18. 3 TC demo in plan for today. 3/17: 29 TC completed. Defect#8294,8300,Revised Tech ETA-3/17, These two defects are blocker currently to test further test cases.5 TC demo in plan for today. 3/12: 22 TC cases completed. Defect# 8294 and 8300 raised for create and report. Testing in progress. Targetting to send the FUT for intel review by 3/18 3/11:21 test cases completed and documenation in progress. Defect#5045 assigned back but the build is not complete. 3/10- Walkthrough in progress. TC 20/43 Tested ( 17 documentation completed) .IF side of fixes to be moved today as per comment from teceh(ETA- today) to resume the documnetation 3/09: 17/43 TC completed. Walkthrough with business in progress. 2/19: Walkthrough completed for 4 cases and work in progress with tech for the remaining fixes. 2/17: Tech will confirm some part of the defect today (2/17) as commited and FUT can start. 2/16: Open Defect - 5045 blocking core functions FUT. Once fixed, FUT will start. Defect fix ETA was 2/13. Test Case walkthorugh to start from 2/18. 2/12: Open Defect - 5045 blocking core functions FUT. Once fixed, FUT will start. Defect fix ETA: 2/13 02/10: Few fixes in progress and core functionality fix in progress with tech. Defect#5045 is open 3/23:33/43 TC. remaining issues in fix from 8294 defect, 10/30 points are yet to be fixed.8300- 20/42 points yet to be fixed. Target to sent the FUT for intel approval all TCs by 3/25. 3/20: TC completed 33/43 points, fixed from 8294 defect, 10/30 points are yet to be fixed.8300- 20/42 points yet to be fixed. Target to sent the FUT for intel approval all TCs by 3/25. 3/19: TC completed 33/43 points fixed from 8294 defect, 10 Points are yet to be fixed.8300- Testing in progress. Target to sent the FUT for intel approval all TCs by 3/25. 3/18: Defect#8294,8300 in progress with tech. 3 TC demo in plan for today. 3/17: Defect#8294,8300 .5 TC demo in plan for today. 3/16: Defect#8294,8300 Tech ETA???. 5 TC demo in plan for today. 3/13: 24 cases completed. Defect# 8294 and 8300 raised for create and report. Testing in progress. documentation as well being completed parallely. 3/12: 22 cases completed. Defect# 8294 adn 8300 raised for create and report. Testing in progress. 3/11:21 test cases completed and documenation in progress. Defect#5045 assigned back but the build is not complete. 3/10- Walkthrough in progress. TC 20/43 Tested ( 17 documentation completed) .IF side of fixes to be moved today as per comment from teceh(ETA- today) to resume the documnetation 3/9:Walkthrough in progress. 3/6: Walkthrough + Documentation in progress. 3/5: Walkthroug | 2025-10-08 | N | 99. Logistics |  |  |  | 03/24 : Defect fix in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-03-13 | 2026-03-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2089 | LOGE0935_IF | 04.Enhancement | 02.IF - Intel Foundry | Fiori App - Shipping Memo | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 09. FUT Overdue | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2089_R3_FTS_IP_LOGISTICS_LO-180-050_Enhancement%20-%20Fiori%20App_%20RICEFW%20Intake%20form.pptx?d=w39182c638eea4b0fbc8ad972e8a83159&csf=1&web=1&e=FJ6a1K | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-05-30 | 2025-05-30 | 100% | 2025-06-09 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2026-02-02 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-03-13 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2026-03-13 | [15 empty] | 2026-03-13 | 2026-03-13 |  |  | 2026-03-27 | 2026-03-27 |  | 90% | 90% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 90% | 2026-03-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-11-20 03:23 | pusrai@deloitte.com | 2026-04-03 02:27 | 9 | 2024-12-21 | 01.S4 | LOGE0935_IP | 01.Very High | 0.8 | 0.8 | 0935 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [12 empty] | 2026-03-13 | 2026-03-13 |  |  |  | 2026-03-27 | [6 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1828 | [7 empty] | 2. At Risk | 17. FUT In progress | 04/03: tech yet to make all teh fixes , once completed we can for approvals. ETA provided by Sanket-04/03 3/27: 33/43 completed, rest in progress. Additionally,the fix in IP need to be coped to IF to proceed further. - ETA to complete- 03/27 3/25:20/43 TC completed, rest in retest , documentation in progress. Need ETA to be replanned to 4/07 as conveyed by Imran. 3/24:19/43 TC completed, rest in retest , documentation in progress. 3/23:15/43 TC completed. IPLA and other issues fixed by tech on friday, currently in retest. ETA 3/27 3/19: Points fixed in defect 8294 for IP are not working for IF. Dev team is working on fixes.7/43 TC completed. 3/18:7/43 TC completed. Workflow error resolved and retest in progress. Defect#8294,8300 ETA by tech 3/18 3/17:Defect#8294,8300 in progress with tech. ETA 3/17. 3/12: 2 new defect 8294,8300 created today for report. Testing in progress for all scearios after report changes were moved. 3/11:Code for report changes are moved to IF. Testing in progress from today. 3/10- Walkthrough in progress. TC 20/43 Tested but yet to be documented.IF side of fixes to be moved today as per comment from teceh(ETA- today) to resume the documnetation 3/09: 17/43 TC completed. Walkthrough in progress. Report fixes will be done in IP and tested then only the changes will be moved to IF. 3/05:16/43 TC completed.Walkthrough with business in progress. Tech is working on missing field values issue.Further FUT will start after the fix today. 3/02: Daily session with buisness team for FUT and getting reviews done together. 15/50 completed 2/19: Walkthrough completed for 4 cases and work in progress with tech for the remaining fixes. 2/17: Tech will confirm some part of the defect today (2/17) as commited and FUT can start. 2/16: Open Defect - 5045 blocking core functions FUT. Once fixed, FUT will start. Defect fix ETA was 2/13. Test Case walkthorugh to start from 2/18. 2/12: Open Defect - 5045 blocking core functions FUT. Once fixed, FUT will start. Defect fix ETA: 2/13 02/10: Few fixes in progress and core functionality fix in progress with tech. Defect#5045 is open 3/23:15/43 TC completed. IPLA and other issues fixed by tech on friday, currently in retest. 3/20:15/43 TC completed. IPLA and other issues in fix with tech and retest in progress. 3/18:7/43 TC completed. Workflow error resolved and retest in progress. 3/17:Defect#8294,8300 needs help and is blocker for FUT. Tech committed ETA passed and resolution still awaited. ETA- 3/17 on ALM 3/16: Defect#8294,8300 Tech ETA???. 3/13: Testing in progress and defect raised for create and report. Defect#8294,8300 3/12: Testing in progress post report changes were moved. 3/11:Code for report changes are moved to IF. Testing in progress from today. 3/10- Walkthrough in progress. TC 20/43 Tested but yet to be documented.IF side of fixes to be moved today as per comment from teceh(ETA- today) to resume the documnetation 3/9:Walkthrough in progress. Report fixes will be done in IP and tested then only the changes will be moved to IF. 3/6: Walkthrough + Documentation in progress. 3/5: Walkthrough with business in progress. Tech is working on missing field values issue.Further FUT will start after the fix today. 3/3: Daily session with buisness team for FUT and getting reviews done together. 2/27: Fixes are in progress next walkthrough planned for 3/2. 2/26: Based on walkthorugh tech is working on the issues. 5th walkthrough planned for today. 2/25: 4th walkthrough is on 2/25.ETA of completion of FUT is 3rd week of March as aligned with Imran and tech. 2/24: Defect fix is in progress. 2/23: Multiple line delivery creation failed in last walktjhrough and the same is being worked upon by tech team. 2/20: 2nd walkthrogh in plan today with Intel IT. approach on the FUT remains same. 2/19: Walkthrough completed f | 2025-10-08 | N | 99. Logistics |  |  |  | 03/24 : Defect fix in progress. ETA to share for approval is 03/27 |  | 2. Risk | On track for S23+ | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-03-13 | 2026-03-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2442 | LOGE0858_IP | 04.Enhancement | 01.IP - Intel Product | Determine mode in freight order and charge calculation​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B94A50EE3-D564-4C26-8FAF-C9D0BAB10C33%7D&file=R3%20PTP%20%20LI-030%20-060%20-%20Determine%20mode%20in%20freight%20order%20and%20charge%20calculation.pptx&action=edit&mobileredirect=true&CID=2C58FF8B-A878-4E2D-8467-511AB7E6006B&wdLOR=c832F1A79-C300-4333-AC0E-932967AAC704 | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-05-26 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0858 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2025-06-27 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2521 | [7 empty] | 1. On Track | 1. Approved no action | 11/24: FUT document approved 11/18: Defect 4293 blocking approval task. Target ETA- 11/21 11/11: Defect still in work by tech team. Target-11/13 11/04: 3 defect fixed- retest in progress. CR defect yet to be raised. Final version to be shared by 11/05 10/31:CR is required for default route determination, 2 Defects(4122,4124) raised for 2 pending TC. 10/22: FUT WIP. 6/10 TC done | 2025-10-31 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2442 | LOGE0858_IF | 04.Enhancement | 02.IF - Intel Foundry | Determine mode in freight order and charge calculation​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B94A50EE3-D564-4C26-8FAF-C9D0BAB10C33%7D&file=R3%20PTP%20%20LI-030%20-060%20-%20Determine%20mode%20in%20freight%20order%20and%20charge%20calculation.pptx&action=edit&mobileredirect=true&CID=2C58FF8B-A878-4E2D-8467-511AB7E6006B&wdLOR=c832F1A79-C300-4333-AC0E-932967AAC704 | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-05 | 2025-05-26 | 2025-06-27 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-03 | 2025-10-31 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | LOGE0858_IP | 03.Medium | 0.2 | 0.2 | 0858 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2025-06-27 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 2520 | [7 empty] | 1. On Track | 1. Approved no action | 11/24: FUT document approved 11/18: Defect 4293 blocking approval task. Target ETA- 11/21 11/11: Defect still in work by tech team. Target-11/13 11/04: 3 defect fixed- retest in progress. CR defect yet to be raised. Final version to be shared by 11/05 10/31:CR is required for default route determination, 2 Defects(4122,4124) raised for 2 pending TC. 10/24 - FUT in progress 10/22: Defect 3241 and dependency on PO (core PTP) blocking all 10 test cases | 2025-10-31 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-31 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2420 | LOGE0855 | 04.Enhancement | 02.IF - Intel Foundry | Capital Call Ahead Report​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD282F2BC-F567-4DE3-8A50-3263A239C292%7D&file=2420_R3_PTP_IP&IF_LI-030-160_Call%20Ahead%20Reports_Intake%20Form.pptx=&wdLOR=c73D0D5BB-A902-4205-B484-F495B3BFCC8F&action=edit&mobileredirect=true&CID=3273593A-2C14-46F1-9927-DB05E2D6D117 | 02.No | 01.Yes |  | 2024-11-12 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1 | 0855 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-19 | 2026-01-09 | 2025-12-19 | [5 empty] | 2025-07-18 | 2025-10-08 |  |  | 2026-01-09 | TM |  |  | 1 | 08. Not Applicable | 1442 | [7 empty] | 1. On Track | 17. FUT In progress | 12/15: New requirement raised by Intel. Discussion with business ongoing 11/11: Tech team working on updated logic since original logic not working for finding gap reason. ETA for Intel review- 11/14 11/04: FUT WIP. Defect retested. Documentation in progress. ETA for internal review- 11/06 | 2025-10-08 | N | 99. Logistics |  |  |  | Adjustment in the Object id |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2420 | LOGE0854 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori Application development to generate Call Ahead Reports for Capital Purchase Order.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD282F2BC-F567-4DE3-8A50-3263A239C292%7D&file=2420_R3_PTP_IP&IF_LI-030-160_Call%20Ahead%20Reports_Intake%20Form.pptx=&wdLOR=c73D0D5BB-A902-4205-B484-F495B3BFCC8F&action=edit&mobileredirect=true&CID=3273593A-2C14-46F1-9927-DB05E2D6D117 | 02.No | 01.Yes |  | 2024-11-12 | jorge.sanchez@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-05 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-18 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-13 | 01.S4 |  |  | 1 | 1 | 0854 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-18 | 2026-01-09 | 2025-12-18 | [5 empty] | 2025-07-18 | 2025-10-08 |  |  | 2026-01-09 | TM |  |  | 1 | 08. Not Applicable | 1438 | [7 empty] | 1. On Track | 17. FUT In progress | 12/15: New requirement raised by Intel. Discussion with business ongoing 11/11: Tech team working on updated logic since original logic not working for finding gap reason. ETA for Intel review- 11/14 11/04: FUT WIP. Defect retested. Documentation in progress. ETA for internal review- 11/06 | 2025-10-08 | N | 99. Logistics |  |  |  | Adjustment in the Object id |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2388 | LOGE0853_IP | 04.Enhancement | 01.IP - Intel Product | Inbound Carrier selection over-ride and exclusion rules to be considered during IRG/ISCG/CTTR​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD784CED2-8F59-4FA3-812F-8595E64687EA%7D&file=R3%20PTP%20%20LI-030-190%20-%20Manage%20In-bound%20Transportation-%20Inbound%20Carrier%20selection%20rules%20(1).pptx&wdLOR=cACD70274-ACA2-430E-AD30-A18976C72799&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-03-07 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-12-10 | 01.S4 |  |  | 1 | 1 | 0853 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1913 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/02:FUT WIP for the remaining scenarios. Review on 03/04 02/23:FUT WIP 10/30 TC done. 2 defects open-7500, 7556 02/20: FUT WIP 6/30 TC done.3 defect #7455, #7476 #7500 raised with Tech team. Defects targeted to get resolved EOD. 4 more defect open on IRG. Will get conditional approval if defects are fixed 02/16-Awaiting defect fix for defect #7207 to continue with FUT 02/12: FUT in progress, Defect 7167 fix in progress 01/12: FUT in progress, carrier selection not working as expected. Defect fix in progress 01/05: FUT in progress, carrier selection not working as expected. Defect fix in progress 12.22: Issues faced with Inbound carrier selection, working to resolve those and make progress. 12/15: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2388 | LOGE0853_IF | 04.Enhancement | 02.IF - Intel Foundry | Inbound Carrier selection over-ride and exclusion rules to be considered during IRG/ISCG/CTTR​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD784CED2-8F59-4FA3-812F-8595E64687EA%7D&file=R3%20PTP%20%20LI-030-190%20-%20Manage%20In-bound%20Transportation-%20Inbound%20Carrier%20selection%20rules%20(1).pptx&wdLOR=cACD70274-ACA2-430E-AD30-A18976C72799&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-02-20 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-20 | 2026-02-20 | N | 100% | 2026-03-07 | Sprint 23 Week 2 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-12-10 | 01.S4 | LOGE0853_IP | 03.Medium | 0.2 | 0.2 | 0853 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1912 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/02:FUT WIP for the remaining scenarios. Review on 03/04 02/23-FUT WIP 8/17 TC done. 2 defects open-7500,7556 02/20-FUT WIP 6/30 TC done.3 defect #7455, #7476 #7500 raised with Tech team. Defects targeted to get resolved EOD. 4 more defect open on IRG. 02/16- Blocker defect #7167 resolved on 2/13.TC passed - 2/30, FUT in progress 02/12: FUT in progress, Defect 7168 fix in progress 01/12: FUT in progress, carrier selection not working as expected. Defect fix in progress 01/05: FUT in progress, carrier selection not working as expected. Defect fix in progress 12.22: Issues faced with Inbound carrier selection, working to resolve those and make progress. 12/15: FUT in progress | 2025-12-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2386 | LOGE0851_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to store + transform + trigger freight forwarder rates to CTSI. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEE2C4B21-F546-4D00-B3C1-77876BE357F6%7D&file=R3%20PTP%20%20LI-030%20-060%20Manage%20In-bound%20Transportation-Enhancement%20to%20store%20%20%20transform%20%20%20trigger%20freight%20forwarder%20rates%20to%20CTSI.pptx&wdLOR=c7E1712ED-84F2-4731-A8DA-0124ED39F22F&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-06-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-06-27 | 2025-07-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-19 | 2025-06-13 |  |  | 2025-06-13 | 2025-06-16 | 2025-07-18 |  |  | 2025-07-18 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2 | 0851 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-13 |  |  |  | 2025-07-18 | [6 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-03-21 | 2025-07-18 | 2025-06-13 |  | 2025-09-10 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1909 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2386 | LOGE0851_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to store + transform + trigger freight forwarder rates to CTSI. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEE2C4B21-F546-4D00-B3C1-77876BE357F6%7D&file=R3%20PTP%20%20LI-030%20-060%20Manage%20In-bound%20Transportation-Enhancement%20to%20store%20%20%20transform%20%20%20trigger%20freight%20forwarder%20rates%20to%20CTSI.pptx&wdLOR=c7E1712ED-84F2-4731-A8DA-0124ED39F22F&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-26 | Jorge Sanchez | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-06-06 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-04 | 2025-07-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-19 | 2025-06-13 |  |  | 2025-06-13 | 2025-06-16 | 2025-07-18 |  |  | 2025-07-18 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-10 | 01.S4 | LOGE0851_IP | 02.High | 0.4 | 0.4 | 0851 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-13 |  |  |  | 2025-07-18 | [6 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | [5 empty] | 2025-03-21 | 2025-07-18 | 2025-06-13 |  | 2025-09-10 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1908 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2385 | LOGE0850_IP | 04.Enhancement | 01.IP - Intel Product | Order management for inbound ASN and Non ASN scenarios using automatic optimizer-based planning and Interactive planning. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF48B88CD-3130-4D6F-A233-797A6EB07BE3%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-FU%20Creation.pptx=&wdLOR=c42E5276D-D85A-4F5A-93C3-DA456E7BF8A8&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-17 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-17 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 |  |  | 1 | 1 | 0850 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-17 | 2025-10-17 | 2025-10-17 |  | 2025-10-17 | 2025-11-05 | 2025-10-17 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 1907 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: FUT WIP TC 6 for 10 completed and defect raised, ETA 03/12 11/18: FUT WIP. 4 TC complete, 6 TC remaining 11/14:FUT WIP | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2385 | LOGE0850_IF | 04.Enhancement | 02.IF - Intel Foundry | Order management for inbound ASN and Non ASN scenarios using automatic optimizer-based planning and Interactive planning. ​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF48B88CD-3130-4D6F-A233-797A6EB07BE3%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-FU%20Creation.pptx=&wdLOR=c42E5276D-D85A-4F5A-93C3-DA456E7BF8A8&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 | LOGE0850_IP | 03.Medium | 0.2 | 0.2 | 0850 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 1906 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: FUT WIP TC 3 for 10 completed, ETA 03/12 11/18: FUT WIP. 1 TC complete, 9 TC remaining 11/14:FUT WIP | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2384 | LOGE0849_IP | 04.Enhancement | 01.IP - Intel Product | Introduce HAWB in Transportation Cockpit, FRO worklist and selection criteria to Identify and filter Freight units for transportation planning via interactive/Manual planning , Carry out actions from worklist and additional selection attributes. ​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B95CD07FE-677D-43A5-AA2F-A0ED6D44AF23%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-Transportation%20cockpit.pptx=&wdLOR=c520FD86E-18BC-4667-8211-DE6DF5200DD3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 |  |  | 1 | 1 | 0849 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1905 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: FUT document sent for internal review, ETA 03/12 11/18: Internal review in progress 11/14:FUT WIP | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2384 | LOGE0849_IF | 04.Enhancement | 02.IF - Intel Foundry | introduce HAWB in Transportation Cockpit, FRO worklist and selection criteria to Identify and filter Freight units for transportation planning via interactive/Manual planning , Carry out actions from worklist and additional selection attributes. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B95CD07FE-677D-43A5-AA2F-A0ED6D44AF23%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-Transportation%20cockpit.pptx=&wdLOR=c520FD86E-18BC-4667-8211-DE6DF5200DD3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 | LOGE0849_IP | 03.Medium | 0.2 | 0.2 | 0849 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 | TM |  |  | 1 | 08. Not Applicable | 1904 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: FUT document sent for internal review, ETA 03/12 11/18:FUT WIP. On track 11/14:FUT WIP | 2025-10-08 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2383 | LOGE0848_IP | 04.Enhancement | 01.IP - Intel Product | Planning for inbound ASN, Non ASN. ODM/OSAT scenarios using automatic optimizer-based planning and Interactive/Manual planning. ​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B49EAB293-8003-458F-9847-6E4B4143BB1B%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-Consolidation.pptx=&wdLOR=cD8779D02-517A-4DC4-B2F8-D82D81C7562B&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 |  |  | 1 | 1 | 0848 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 1903 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/31 - Defects 3829/3829 is blocking execution 10/22: Roadblock Defect 3827/3828 created. | 2025-10-24 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2383 | LOGE0848_IF | 04.Enhancement | 02.IF - Intel Foundry | Planning for inbound ASN, Non ASN. ODM/OSAT scenarios using automatic optimizer-based planning and Interactive/Manual planning.. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-12-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B49EAB293-8003-458F-9847-6E4B4143BB1B%7D&file=R3%20PTP%20%20LI-030-170%20Manage%20In-bound%20Transportation-ASN%20&%20NON%20_ASN-Consolidation.pptx=&wdLOR=cD8779D02-517A-4DC4-B2F8-D82D81C7562B&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved | 2024-12-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-10 | 01.S4 | LOGE0848_IP | 03.Medium | 0.2 | 0.2 | 0848 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 1902 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 11/04: Intel review done. Comments being addressed. Final version to be sent by 11/05 10/31 - Defects 3825/3827/3859 are fixed today and tested. Walkthrough planned for 10/31 10/22: 2Tc passed, 2 Tc has roadblock defects 3825/3827 | 2025-10-24 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2382 | LOGE0847 | 04.Enhancement | 01.IP - Intel Product | TM: RICEFW 1:Carrier selection and Charges calculation for IRG/ISCG( Intel routing Guide & Intel Supplier routing guide)via external IRG tool. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB601AC00-DC29-4E02-904E-D8D88733C781%7D&file=R3%20PTP%20%20LI-030-160%20Manage%20In-bound%20Transportation-%20IRGI%20SCG(Intel%20supplier%20carrier%20guide).pptx&wdLOR=c3EC3141C-614B-4619-9D54-47267C88E6A2&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-11 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-20 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-04 | 2025-08-15 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0847 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-02-21 | 2025-02-20 |  | 2025-05-24 | 2025-07-11 | 2025-05-24 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-02-21 | 2025-08-15 |  |  | 2025-08-22 | TM |  |  | 1 | 08. Not Applicable | 2407 | [9 empty] | 09/12: FUT walkthrough completed. Conditionally Approved but Defect 2950 open based on Review comments. Awaiting defect closure to close the FUT Approval. | 2025-08-15 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2016 | LOGE0841 | 04.Enhancement | 08.EWM | Enhancement to display an error message in the pack transaction within SAP Extended Warehouse Management (EWM) when an incorrect Handling Unit (HU) is scanned for a delivery. | 04. OTC IF | 4.8 OTC IF - EWM | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2016_IF_OTC_EWM_Enhancement_Packing_Screen.pptx?d=w51edc0134db04c53ab536ba79889588f&csf=1&web=1&e=p1K79J | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-28 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-12 | 2025-05-02 | 2025-05-09 | 2025-05-20 | 100% | 2025-06-13 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-13 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-13 | [15 empty] | 2025-06-13 | 2025-06-13 |  |  | 2025-06-27 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-20 | 2025-07-11 | 2025-07-16 | N | 100% | 2025-07-24 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-12 | 01.S4 |  |  | 1 | 1 | 0841 |  | R3 ITC1 | [6 empty] | 2025-03-12 | 2025-03-12 | 2025-03-12 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | [12 empty] | 2025-06-13 | 2025-06-13 |  |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | [5 empty] | 2025-01-31 | 2025-06-13 |  |  | 2025-07-04 | TM |  |  | 1 | 08. Not Applicable | 2022 | [10 empty] | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-06-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2103 | LOGE0838 | 04.Enhancement | 01.IP - Intel Product | Enhancement to update the address and bp form the Custom Partner Function to TM source location without creating aa One time location | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B772D119F-7E91-4DF3-B412-3298601B0C1D%7D&file=R3_IP_OTC_TM_Returns_R-220-020-TM%20Order%20Management_Enhancement_OTL.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | jorge.sanchez@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-02-07 | 2025-02-07 | 100% | 2025-01-30 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-06 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-20 | 2025-08-13 | 2025-08-13 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0838 |  | R3 ITC1 | [6 empty] | 2025-01-30 | 2025-02-07 | 2025-01-30 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-02-07 | 2025-06-13 |  |  | 2025-06-23 | TM |  |  | 1 | 08. Not Applicable | 1556 | [7 empty] | 4. Completed | 8. Blocked by CR/Design change | 12/22: One issue still persists but it is not consistent, we have documented al the test cases and sent for Internal review, while the tech team is working on the issue in parallel. 12/08: TUT documentation in progress, FUT to be started 12/01: CR (due to OTC core change, TM needed code change) build in progress, TUT + FUT to start 12/03 11/24: FS walkthrough completed with tech and tech build in progress, ETA 3/12 11/18 - CR Approved. Working on FS updates. To be shared for build by next week. 10/22: CR to be prepared and presented, effort estimate pending . development analysis is in progress for the feasibility 10/10 :Original requirement is completed but have encountered 2 major issues: 10/9 :Original requirement is completed but have encountered 2 major issues: 1. Change in YC/YR BP process in sales order. (Alignment in progress with OTC team) 2. Even for delivery-based integration change in sales order address impacted TM Integration (CR defect to copy same logic as delivery update) 10/03: Defect 1647 - Reopened Tech changes in progress. 9/29: Technical team has confirmed on the fix and testing is in progress Defect 1647 9/22: Technical team has confirmed on the fix and testing is in progress Defect 1647 9/15: SAP has provided a BAdI, Tech team is exploring on that. We are providing data from our end 9/8: Same as 9/5 9/5: SAP has provided a BAdI, Tech team is exploring on that. We have provided data from our end 9/1: Tech team has raised OSS on this awaiting response 8/25: Same status as 8/18, tech team is raising an OSS to SAP for this issue. 8/18: FUT is blocked with a defect. Defect 1647 has been created on 7/22 and ETA as of today shows 8/19. | 2025-06-13 | N | 99. Logistics |  |  |  |  | TUT in Progress 1203 |  |  | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2191 | LOGE0835_IP | 04.Enhancement | 02.IF - Intel Foundry | Interface to get the AMT (Asset Management Tool) data on the ISM | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_IP_LOGISTICS_INTERFACE_ISM_AMT_V2.pptx?d=w3632741a950e4ba3875e308cc670d756&csf=1&web=1&e=n3XAM7 | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | 14310 | Asset Management Tool 2.0 |  |  | NA | 2025-03-31 | 2025-05-30 | 2025-05-30 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-21 | 01.S4 |  |  | 1 | 1 | 0835 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-08-29 | 2025-10-10 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-06 | 2025-10-08 | 2025-10-06 | [5 empty] | 2025-05-30 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 2542 | [10 empty] | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2191 | LOGE0835_IF | 04.Enhancement | 01.IP - Intel Product | Interface to get the AMT (Asset Management Tool) data on the ISM | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/ISM%20IF%20and%20IP/Documents/RICEFW%20Intake%20forms/R3_FTS_IP_LOGISTICS_INTERFACE_ISM_AMT_V2.pptx?d=w3632741a950e4ba3875e308cc670d756&csf=1&web=1&e=n3XAM7 | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved | 2024-12-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No | 14310 | Asset Management Tool 2.0 |  |  | NA | 2025-03-31 | 2025-05-30 | 2025-05-30 | 100% | 2025-05-20 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-01-15 | 01.S4 | LOGE0835_IP | 03.Medium | 0.2 | 0.2 | 0835 |  | R3 ITC1 | [6 empty] | 2025-05-20 | 2025-05-30 | 2025-05-20 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-08-29 | 2025-10-10 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-06 | 2025-10-08 | 2025-10-06 | [5 empty] | 2025-05-30 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 2541 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change |  | 2025-10-10 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2202 | LOGE0797_IP | 04.Enhancement | 01.IP - Intel Product | Pre alert notification to Customer | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B02D7271C-AEC2-426F-8C83-84E2D4F1DE6F%7D&file=R3_IP%20and%20IF_OTC_ZPRE_RICEFW%20Intake%20Form%20-.pptx&wdLOR=c3C9E86D6-E55E-433E-B6DB-7465735D51A7&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-01 | 2025-05-30 | 2025-07-11 | 100% | 2025-07-25 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0797 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 | 08. Not Applicable | 1849 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 01/05: Additional call requested by Intel IT for FUT review, which will be setup by Intel early this week 12/22: For open point defect is closed ,email sent to Intel for approval. 12/15: Defect#5547 raised for the open points raised by intel, defect is with tech, ETA 12/15 12/10: Sent for approval on 12/10 12/08: Defect#5069 & 5189 is closed, FUT will be sent by 12/08 12/01: Defect#5069 with tech, ETA 12/01. 11/24: 2/13 TC completed, defect 4855 open with Dev. ETC to send for intel review 12/3. 11/18- Defect 4601 raised to dev. | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2202 | LOGE0797_IF | 04.Enhancement | 02.IF - Intel Foundry | Pre alert notification to Customer | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B02D7271C-AEC2-426F-8C83-84E2D4F1DE6F%7D&file=R3_IP%20and%20IF_OTC_ZPRE_RICEFW%20Intake%20Form%20-.pptx&wdLOR=c3C9E86D6-E55E-433E-B6DB-7465735D51A7&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-01 | 2025-05-30 | 2025-07-11 | 100% | 2025-08-01 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-16 |  | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | LOGE0797_IP | 03.Medium | 0.2 | 0.2 | 0797 |  | R3 ITC1 | [6 empty] | 2025-08-01 | 2025-08-01 | 2025-08-01 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 | 08. Not Applicable | 1848 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 01/12: Intel business approved, awaiting Intel IT approval 01/07:FUT sent for intel review 01/05: Defect#5864 is with tech, ETA 01/05, once defect is fixed, FUT can be completed by 01/06 12/22:Defect 5385 is closed but while retesting found issue which has been raised in defect #5864 ETA 12/24. 5/13 TC passed. 12/15: Defect#5385 is re-assigned to tech today, no ETA 12/08: Defect#5069 & 5189 retest in progress, if all issues fixed, FUT can be sent on 12/10 12/01: Defect#5069 with tech, ETA 12/01. 11/24: 2/13 TC completed, defect 4855 open with Dev. ETC to send for intel review 12/3. 11/18- Defect 4601 raised to dev. | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2223 | LOGE0796_IP | 04.Enhancement | 01.IP - Intel Product | Custom transaction to trigger CUSDEC | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B16BFCEED-FB12-4939-824A-2711EF5DB2B7%7D&file=R3_IP_OTC_LE_Custom_T_Code%20for%20CUSDEC.pptx&wdLOR=cB0D88B52-86CE-40A5-B3A1-E54E0B748D8F&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-02-28 | 2025-02-28 | 100% | 2025-03-03 | 2025-08-29 | 2025-09-05 | 2025-08-13 | 100% | 2025-08-09 | 2025-09-19 | 2025-10-10 | 2025-04-11 | 100% | 2025-08-04 | 2025-02-05 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-19 | 2025-09-19 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 2 | 2 | 0796 |  | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-03 | 2025-03-03 |  | 2025-08-09 | 2025-09-05 | 2025-08-09 |  | 2025-08-04 | 2025-10-10 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-15 | 2025-09-19 | 2025-09-15 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-31 |  |  |  | 1 |  | 1627 | [7 empty] | 1. On Track | 17. FUT In progress | 09/08: FUT is approved, approval task was missed to be added in sprint plan for Sprint 17, task has been added in Sprint 18 and will be closed on 09/15 | 2025-05-16 | N | 99. Logistics | [7 empty] | Incorrect plan | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2223 | LOGE0796_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom transaction to trigger CUSDEC | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B16BFCEED-FB12-4939-824A-2711EF5DB2B7%7D&file=R3_IP_OTC_LE_Custom_T_Code%20for%20CUSDEC.pptx&wdLOR=cB0D88B52-86CE-40A5-B3A1-E54E0B748D8F&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-02-28 | 2025-02-28 | 100% | 2025-03-06 | 2025-08-01 | 2025-08-08 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-29 | 2025-09-12 | 2025-04-02 | 100% | 2025-08-04 | 2025-02-05 | 2025-05-16 | 2025-04-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-06-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-06-20 | N | 100% | 2025-07-24 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | LOGE0796_IP | 02.High | 0.4 | 0.4 | 0796 |  | R3 ITC1 | [6 empty] | 2025-03-06 | 2025-03-06 | 2025-03-06 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-24 | 2025-07-24 | 2025-07-24 | [5 empty] | 2025-05-02 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 |  | 1626 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1848 | LOGE0793 | 04.Enhancement | 01.IP - Intel Product | Upload program to update pick/pack information in sap in case of 3B13 PIP failure for BCP process | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2025-01-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_BCP%20Process_Update%20Pick%20Pack%20from%20uplaod%20program_RICEFW%20Intake%20Form.pptx?d=w134dd3fc41a5470aa797ea51aa06404d&csf=1&web=1&e=NozNot | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-24 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-20 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-10-23 09:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-18 | 01.S4 |  |  | 1 | 1 | 0793 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-20 | 2025-08-22 | 2025-08-20 |  | 2025-08-20 | 2025-09-12 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | [5 empty] | 2025-04-24 | 2025-08-15 |  |  | 2025-09-19 |  |  |  | 1 | 08. Not Applicable | 2167 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14: Defect 4352 reopened. Defect 4285 still with Tech team. 11/11: Defect 4285 & 4352 with Tech team. No ETA provided. Defects are part of priority list 10/31: defect 3876 is open for more than a week 10/24 - Defect 3876. To be picked by Tech team | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2364 | LOGE0792_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to Update Custom Table form Master data and Manage SOP Data Communication for CMDB | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B39D4861B-18E5-46FF-9DCF-1968A80BEA9A%7D&file=R3_IP%20and%20IF_OTC_Enhancement%20to%20fetch%20SOP%20data%20and%20store%20in%20custom%20table%20for%20CMDB%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-16 | 2025-03-28 | 100% | 2025-04-05 | 2025-08-01 | 2025-08-08 | 2025-07-25 | 100% | 2025-07-24 | 2025-08-29 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-29 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-19 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-09-19 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0792 |  | R3 ITC1 | [6 empty] | 2025-04-05 | 2025-05-16 | 2025-04-05 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 |  | 2025-07-24 | 2025-09-12 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-06 | 2025-10-10 | 2025-10-06 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-09-22 |  |  |  | 1 | 08. Not Applicable | 1853 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-12 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2364 | LOGE0792_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to Update Custom Table form Master data and Manage SOP Data Communication for CMDB | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B39D4861B-18E5-46FF-9DCF-1968A80BEA9A%7D&file=R3_IP%20and%20IF_OTC_Enhancement%20to%20fetch%20SOP%20data%20and%20store%20in%20custom%20table%20for%20CMDB%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-08 | 2025-07-25 | 100% | 2025-07-24 | 2025-09-05 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | 2025-09-05 | 2025-09-12 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | LOGE0792_IP | 03.Medium | 0.2 | 0.2 | 0792 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 |  | 2025-07-24 | 2025-09-12 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 1852 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: FUT review is completed, one additional scenario requested for which defect#3617, ETA 10/10 for fix and if fixed can be sent back for approval by 10/13 | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2315 | LOGE0791_IP | 04.Enhancement | 01.IP - Intel Product | Creation of Proforma Invoice ZF8 from Freight Order and Save ITN Number in Delivery Special Instruction Text on CI Reprint | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IF_OTC_ZF8%20for%20AES%20declaration_RICEFW%20Intake%20Form.pptx?d=w05e1f67b730b4e23ac60a2d562c48825&csf=1&web=1&e=w7D4TE | 02.No | 01.Yes |  | 2024-10-28 | Jorge Sanchez | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-11-13 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-08 | 01.S4 |  |  | 1 | 1 | 0791 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-27 |  |  |  | 1 | 08. Not Applicable | 2112 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Reverted on queries raised by Intel post FUT review, awaiting Intel approval 11/24: FUT sent for approval on 11/24 11/18: Data dependency with GTS Team. Development is still in progress. FS was approved on 05/20 | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2315 | LOGE0791_IF | 04.Enhancement | 02.IF - Intel Foundry | Creation of Proforma Invoice ZF8 from Freight Order and Save ITN Number in Delivery Special Instruction Text on CI Reprint | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IF_OTC_ZF8%20for%20AES%20declaration_RICEFW%20Intake%20Form.pptx?d=w05e1f67b730b4e23ac60a2d562c48825&csf=1&web=1&e=w7D4TE | 02.No | 01.Yes |  | 2024-10-28 | Jorge Sanchez | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-11-13 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-19 | 01.S4 | LOGE0791_IP | 03.Medium | 0.2 | 0.2 | 0791 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2025-05-30 | 2025-10-10 |  |  | 2025-10-27 |  |  |  | 1 | 08. Not Applicable | 2111 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/08: Approved by Junior, awaiting approval from Intel IT. 12/01: Awaiting Intel approval, sent for Intel review on 11/28 11/24: 3/7 TC completed. ETC to send for intel review 11/26. 11/18- FUT in progress, no open defect at present. 11/10-Development is still in progress. FS was approved on 05/20 | 2025-11-05 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2068 | LOGE0782 | 04.Enhancement | 08.EWM | Enhancement to RF Loading Screen for 3PV Validation | 04. OTC IF | 4.8 OTC IF - EWM | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2068_IF_OTC_EWM_3PV_Validation.pptx?d=w09e8e898f9444ea9aed4d10bba8f409b&csf=1&web=1&e=OBWWZG | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-14 | 2025-05-02 | 2025-05-09 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-27 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-20 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-07-22 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 2 | 2 | 0782 |  | R3 ITC1 | [6 empty] | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | [5 empty] | 2025-01-31 | 2025-06-13 |  |  | 2025-07-18 | TM |  |  | 1 | 08. Not Applicable | 2507 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2019 | LOGE0775 | 04.Enhancement | 08.EWM | Enhancement in packing transaction. Should allow user to launch Interface for label printing transaction from /scwm/pack transaction | 04. OTC IF | 4.8 OTC IF - EWM | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2019_IF_OTC%20EWM_Lable%20Print%20Interface%20from%20EWM%20pack.pptx?d=w59a4854d898e4d52a63f5382159af8de&csf=1&web=1&e=lkuGw9 | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2024-12-27 | 2025-01-10 | 100% | 2025-01-10 | 2025-04-04 | 2025-04-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0775 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-06-11 | 2025-06-13 | 2025-06-11 | [5 empty] | 2024-12-27 | 2025-05-16 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 2023 | [10 empty] | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2393 | LOGE0772_IP | 04.Enhancement | 01.IP - Intel Product | Develop Fiori app to View/Edit/Add SOP data(CMDB). | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD9DC09DC-554D-4BE7-AB77-8DFBB04924BB%7D&file=R3_IP%20and%20IF_OTC_Enhancement%20to%20update%20data%20for%20CMDB%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-08 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-11-05 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-30 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 2 | 2 | 0772 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-08 | 2025-09-19 | 2025-09-08 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-30 | 2026-01-30 | 2026-01-30 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-10 |  |  |  | 1 | 08. Not Applicable | 2398 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/29: Conditionally approved by Intel Business, awaiting Intel IT approval 01/22: Defect#6463 is with tech, ETA 01/23. IF fixed by 01/23, will be sent for final approval by 01/27 01/19:Feedback points will be categorised as CR/Defects. Defect will be raised for issues by 01/19 01/12: Additional session will be scheduled by Intel this week as review is not complete. Meanwhile working on feedback points 01/05: FUT review call scheduled on 01/06 12/22: FUT sent for approval, call scheduled at 01/06. 12/15: Defect#5240 is still with tech, no updated ETA. 12/08: Defect#5105 is re-opened & Defect 5240 is still with tech, no ETA 12/01: Defect#4685 is fixed and retest in progress, ETA 12/01. Defect#5105 yet to be picked up by tech 11/24- Defect 4685 is still open with Dev. Defect ETA not available, ETA for FUT execution completion is 12/3 11/18: Defect 3815/4685 with dev team. ETA to be shared. 11/11: Defect#3815is still open, no ETA, part of priority list | 2025-10-10 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2393 | LOGE0772_IF | 04.Enhancement | 02.IF - Intel Foundry | Develop Fiori app to View/Edit/Add SOP data(CMDB). | 04. OTC IF | 4.10 OTC IF - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD9DC09DC-554D-4BE7-AB77-8DFBB04924BB%7D&file=R3_IP%20and%20IF_OTC_Enhancement%20to%20update%20data%20for%20CMDB%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-08 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-30 | 2026-01-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-29 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | LOGE0772_IP | 02.High | 0.4 | 0.4 | 0772 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-08 | 2025-09-08 | 2025-09-08 |  | 2025-09-09 | 2025-09-12 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2026-01-29 | 2026-01-30 | 2026-01-29 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-17 |  |  |  | 1 | 08. Not Applicable | 2397 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/29: Conditionally approved by Intel Business, awaiting Intel IT approval 01/22: Defect#6463 is with tech, ETA 01/23. IF fixed by 01/23, will be sent for final approval by 01/27 01/19: Feedback points received, will revert by 01/19 01/12: Defect#5111 is still with tech, no clear ETA on the fix 01/05: Defect#5111 is still with tech, ETA 01/06, once it is fixed need 1 day time to complete FUT 12/22:Defect 5111 is with tech team no ETA.8/13 TC executed. 12/15: Defect#5240 is still with tech, no updated ETA. 12/08: Defect#5105 is re-opened & Defect 5111, 5240 is still with tech, no ETA 12/01: Defect#4685 is fixed and retest in progress, ETA 12/01. Defect#5105 yet to be picked up by tech 11/24- Defect 4685 is still open with Dev. Defect ETA not available, ETA for FUT execution completion is 12/3 11/18: Defect 3815/4685 with dev team. ETA to be shared. 11/11: Defect#3815is still open, no ETA, part of priority list | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2326 | LOGE0769_IP | 04.Enhancement | 01.IP - Intel Product | TM: Distribute the freight cost to R&D/OCOS/PCOS/Capital cost objects based on the intel pre-defined rule set | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B12FB83C9-0D9D-4CCE-95FB-F69819DA06EE%7D&file=R3%20PTP%20%20LI-030-040%20-%20Manage%20In-bound%20Transportation-%20Define%20Product%20Cost%20Structure.pptx&wdLOR=c69A9534D-51B2-477F-B28B-CA580892E27A&action=edit&mobileredirect=true&CID=1EB57143-78DF-4EAB-9103-A9E89E08F695 | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-09 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-02 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-02 | [15 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-01-23 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-03-05 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0769 |  | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-06-21 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 2432 | [7 empty] | 3. Off Track | 17. FUT In progress | 03/02-IP FUT documentation in progress, Review to be planned this week 02/23:FUT in progress from today 02/23 02/20: Test data in progress. TUT+FUT to be started next week 02/12: Dev in progress 1/19: This object has been replanned for S23. | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: Development in progress. Dependency with Service master config (PTP& MDG teams). Trying to get exception for ITC 2. 5.1 in S21 & 5.2 in S22 |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 23 |  | 2026-03-02 | 2026-03-02 | No | S/4 code change might be needed to determine correct company code during freight cost distribution. Company code determination is dependent on plant. | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2326 | LOGE0769_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Distribute the freight cost to R&D/OCOS/PCOS/Capital cost objects based on the intel pre-defined rule set | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B12FB83C9-0D9D-4CCE-95FB-F69819DA06EE%7D&file=R3%20PTP%20%20LI-030-040%20-%20Manage%20In-bound%20Transportation-%20Define%20Product%20Cost%20Structure.pptx&wdLOR=c69A9534D-51B2-477F-B28B-CA580892E27A&action=edit&mobileredirect=true&CID=1EB57143-78DF-4EAB-9103-A9E89E08F695 | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-09 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-02 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2026-03-02 | [15 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-01-23 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-02-26 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-10-24 | 01.S4 | LOGE0769_IP | 03.Medium | 0.2 | 0.2 | 0769 |  | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-09 | 2025-09-09 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-02-26 | 2026-02-27 | 2026-02-26 | [5 empty] | 2025-06-21 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 2431 | [7 empty] | 3. Off Track | 17. FUT In progress | 02/23:FUT in progress from today 02/23 02/20: Test data in progress. TUT+FUT to be started next week 02/12: Dev in progress 1/19: This object has been replanned for S23. | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: Development in progress. Dependency with Service master config (PTP& MDG teams). Trying to get exception for ITC 2. 5.1 in S21 & 5.2 in S22 |  |  |  | CR/Design change | Complete | R3 Build & UT Sprint 23 |  | 2026-03-02 | 2026-03-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2325 | LOGE0768_IP | 04.Enhancement | 01.IP - Intel Product | TM: Identify correct Company code, Purchase org, Purchase group, Virtual GLO carrier and plant during freight settlement document/PO/SES creation. ​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B32A1D1E0-658E-4AD4-8406-8C181115B9D5%7D&file=R3%20PTP%20%20LI-030-240%20-%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB).pptx&wdLOR=c9CDF1792-D61E-42D6-8C21-82678BBA55B1&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-02 | 2025-05-31 | 2025-06-06 | 100% | 2025-06-09 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0768 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-31 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 2430 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: Sent for intel approval 11/22. Awaiting feedback from intel 11/18: 4 TC complete 1 TC WIP, SPO issue checked by PTP core 11/14:FUT WIP | 2025-10-24 | N | 99. Logistics |  |  |  | Pending config and Build is not yet completed, these objects (LOGE0769_IF and LOGE0769_IP) are not picked for S21 FUT. |  | 4. To be discussed |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No | Associated fit change. New purchase org might need to be created with respect to company code. | No |  | No |  | 2026-01-21 | 2026-02-13 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2325 | LOGE0768_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Identify correct Company code, Purchase org, Purchase group, Virtual GLO carrier and plant during freight settlement document/PO/SES creation. ​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B32A1D1E0-658E-4AD4-8406-8C181115B9D5%7D&file=R3%20PTP%20%20LI-030-240%20-%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB).pptx&wdLOR=c9CDF1792-D61E-42D6-8C21-82678BBA55B1&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-05-02 | 2025-05-31 | 2025-06-06 | 100% | 2025-06-09 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 | LOGE0768_IP | 03.Medium | 0.2 | 0.2 | 0768 |  | R3 ITC1 | [6 empty] | 2025-06-09 | 2025-06-09 | 2025-06-09 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-31 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 2429 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Review comments being updated, Documentation to be sent for approval ETA EOD 11/24: FUT sent for Intel review 11/18: 4 TC complete 1 TC WIP, SPO issue checked by PTP core 11/14:FUT WIP | 2025-10-24 | N | 99. Logistics |  |  |  | Pending config and Build is not yet completed, these objects (LOGE0769_IF and LOGE0769_IP) are not picked for S21 FUT. |  | 4. To be discussed |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2308 | LOGE0767_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: GTT to S4 for IF and IP data split | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/GTT%20to%20S4%20for%20IF%20and%20IP%20data%20split.pptx?d=w8d7ebc4be8dd4d18bd812ae34bab7c42&csf=1&web=1&e=6fvVyX | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-02-26 | 2025-06-06 | 2025-06-13 | 2025-05-20 | 100% | 2025-06-05 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-06-05 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-06-05 | [15 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-06-20 | 2025-06-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-08 | 2025-09-05 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 |  |  | 1 | 1 | 0767 |  | R3 ITC1 | [6 empty] | 2025-02-26 | 2025-03-21 | 2025-02-26 |  | 2025-06-05 | 2025-06-13 | 2025-06-05 |  | 2025-06-05 | 2025-07-18 | 2025-06-05 | 2025-06-05 | [12 empty] | 2025-06-05 | 2025-06-05 |  |  | 2025-07-21 | 2025-09-05 | 2025-07-21 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-29 | TM |  |  | 1 | 08. Not Applicable | 2100 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-06-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2308 | LOGE0767_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: GTT to S4 for IF and IP data split | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/GTT%20to%20S4%20for%20IF%20and%20IP%20data%20split.pptx?d=w8d7ebc4be8dd4d18bd812ae34bab7c42&csf=1&web=1&e=6fvVyX | 01.Yes | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-02-26 | 2025-06-06 | 2025-06-13 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-11 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-11 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-06-20 | 2025-06-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-08 | 2025-09-05 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 | LOGE0767_IP | 03.Medium | 0.2 | 0.2 | 0767 |  | R3 ITC1 | [6 empty] | 2025-02-26 | 2025-03-21 | 2025-02-26 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-09-05 | 2025-07-21 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-29 | TM |  |  | 1 | 08. Not Applicable | 2099 | [10 empty] | 2025-07-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2306 | LOGE0766_IP | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Routing of events from GTT to correct S4 system | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Routing%20Events%20from%20GTT%20to%20S4.pptx?d=w80e181cf24624ec2b1c5dc7cbffe41cc&csf=1&web=1&e=qWWZnh | 02.No | 01.Yes |  | 2024-10-22 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-21 | 2025-08-01 | 2025-08-08 | 2025-04-22 | 100% | 2025-08-04 | 2025-05-30 | 2025-09-12 | 2025-04-24 | 100% | 2025-08-04 | 2025-05-30 | 2025-09-12 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-04-04 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-11 | 2025-04-11 | N | 100% | 2025-04-03 | Not Applicable | R3 Build & UT Sprint 12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-16 | 01.S4 |  |  | 1 | 1 | 0766 |  | R3 ITC1 | [6 empty] | 2025-01-21 | 2025-01-24 | 2025-01-21 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-04-03 | 2025-04-11 | 2025-04-03 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-07-04 | TM |  |  | 1 | 08. Not Applicable | 2098 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2306 | LOGE0766_IF | 04.Enhancement | 02.IF - Intel Foundry | TM - GTT: Routing of events from GTT to correct S4 system | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/Routing%20Events%20from%20GTT%20to%20S4.pptx?d=w80e181cf24624ec2b1c5dc7cbffe41cc&csf=1&web=1&e=qWWZnh | 02.No | 01.Yes |  | 2024-10-22 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-21 | 2025-08-01 | 2025-08-08 | 2025-04-22 | 100% | 2025-08-04 | 2025-06-06 | 2025-09-12 | 2025-04-24 | 100% | 2025-08-04 | 2025-06-06 | 2025-09-12 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-04-04 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-11 | 2025-04-11 | N | 100% | 2025-04-03 | Not Applicable | R3 Build & UT Sprint 12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 01.S4 | LOGE0766_IP | 03.Medium | 0.2 | 0.2 | 0766 |  | R3 ITC1 | [6 empty] | 2025-01-21 | 2025-01-24 | 2025-01-21 |  | 2025-08-04 | 2025-08-08 | 2025-08-04 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-04-03 | 2025-04-11 | 2025-04-03 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-07-04 | TM |  |  | 1 | 08. Not Applicable | 2097 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE0765_IP | 04.Enhancement | 01.IP - Intel Product | Calling a new BRF+ for Carrier exclusion during Carrier Selection process. Eg. US to CA FedEx is preferred or exclude for certain cities or service levels | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2024-10-22 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-03-27 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0765 |  | R3 ITC1 | [6 empty] | 2025-03-27 | 2025-03-29 | 2025-03-27 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-03-29 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 1972 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/04: Pending Intel approval. Follow up sent 10/31: Under Intel review 10/24 - Documentation to be sent for approval 10/22: defect 3824 open, FUT to be sent for approval post defect fix | 2025-10-03 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2331 | LOGE0765_IF | 04.Enhancement | 02.IF - Intel Foundry | Calling a new BRF+ for Carrier exclusion during Carrier Selection process. Eg. US to CA FedEx is preferred or exclude for certain cities or service levels | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BB2AD733E-E58F-4C24-ABA2-F236461F2CF2%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Fiori%20App%20for%20Custom%20Lane%20table%20for%20CS.pptx&wdLOR=c0E809115-A4D5-45C7-B4A5-45EFE7349B43&action=edit&mobileredirect=true&CID=F3F173CC-7FCC-4379-B8AC-15C4A928EABB | 02.No | 01.Yes |  | 2024-10-22 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-29 | 2025-03-28 | 100% | 2025-03-27 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 | LOGE0765_IP | 03.Medium | 0.2 | 0.2 | 0765 |  | R3 ITC1 | [6 empty] | 2025-03-27 | 2025-03-29 | 2025-03-27 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-03-29 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 1971 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/04: Business approval received, pending IT approval. Follow up sent 10/31: Under Intel review 10/24 - Documentation to be sent for approval 10/22: 1st Intel review completed, WIP for review comments. to be sent for approval along with IP | 2025-10-03 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2135 | LOGE0754_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to enable Outbound Interface to send 4B2 Goods receipt acknowledgement from S/4 to E2Open-IP | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://secure-web.cisco.com/19fC_OrnaVbacjnvAzX6fr6x56CDazvBXtTPRcG_an2UxiiD3iqAG8LPBU12LFZNO45BwBVyrZXXFAPscA-jckKyAX7qNaEaHVTfuLJavBsiqoQg6aecxmv9VhWqIOk93QwIaBBbAzcIsMXhEjokXv0kK3tOfn7m21Ervzs3_1tH1qpUCtv1DQkwqTOUT6COFOip48uwX5fH0PT4TDBgIy03rhevKBUlOT2c4rdDNwTFMVuIaFQQXE_jkKlJlNvZncORNp68WEqD61uepgUNFRh8719iV7xA0DeNIk9gv9WremRxfrd3RS6PkxsAFY_Z4YaFa2RfPPYvI_YLwYd0MF0QtWCtEzirs7aCSGX3FMaDQaeU1gcu8_gKpyz0h4krgwxxuqyy6jlWWHRvd7vKQjLKKIvCCTR_fzWj7jzkLL7VZ75mNRve9QLLNQQQF-NSF4ZHBPHXJFUiICBvvWpR03JMKWi4ws_bKiBaESsD_u7Dtfv5lgLqhscpQdIABrhiS/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2FPTP%2520LE%2F2135%2520%2526%25202136_PTP-LE%2520Generate%2520Outbound%25204B2%2520Message%2520from%2520S4%2520for%2520the%2520GRs%2520performed%2520at%25203PL%2520for%2520E2Open%2520onboarded%2520Suppliers%2520Subcon%2520-%2520S4%2520IP%2526IF%2520to%2520E2Open.pptx%3Fd%3Dw89fec9332e4f472e81e5bdde7ddc63b5%26csf%3D1%26web%3D1%26e%3DyaGfGV | 02.No | 01.Yes |  | 2024-10-23 | Cari H Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-10 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-27 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-28 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-28 | [15 empty] | 2025-03-28 | 2025-03-28 |  |  | 2026-02-27 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-02-27 | 2026-02-27 | N | 100% | 2026-02-25 | Sprint 23 Week 3 | R3 Build & UT Sprint 23 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2024-12-19 | 01.S4 |  |  | 1 | 1 | 0754 |  | R3 ITC1 | [6 empty] | 2024-12-10 | 2024-12-13 | 2024-12-10 |  | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | 2025-03-28 | 2025-04-18 | [14 empty] | 2025-03-28 | 2025-03-28 |  |  | 2026-02-25 | 2026-02-27 | 2026-02-25 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-23 |  |  |  | 1 |  | 2737 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 02/23 - Review comments received today for depend WRICEF - LOGI0834, will be addresed by EOD today 02/20- Sent for approval on 02/13. Awaiting Feedback and approval from Intel IT and Business(Awaiting Malaysian team to come back) 02/16- Sent for approval on 02/13. Awaiting Feedabck and approval from Intel IT and Business 02/12- 29 TCs are completd out of 30, 1TC testing in progress with E2OPEN , ETA- 02/12 01/05 - CR Changes completed, TUT is in progress. FUT to be started post TUT competion from tech. 12/22 - CR 856 Changes completed, Dev to start the TUT, TUT Completion ETA - 12/23 12/15 - This CR0856 is a big risk for SP21, 8 FUTs are dep on this CR. Changes are still in progress for CR0856. Discussed with Tech, Awaiting ETA from Tech 12/08 -Changes are still in progress for CR0856. Awaiting ETA from Tech on the same. 12/01: CR856 still under build, ETA by end of Sprint 20. FUT will commence from S21 11/24:Tech confirmed CR0856 will be completed in S20. FUT will be resumed in S21 once CR implementation is completed by Tech. FUT will be started in S21 and tentative ETA 12/24 11/14: Tech confirmed CR0856 will be completed in S20. FUT will be resumed in S21 once CR implementation is completed by Tech 11/11 - Approval is received on updated FSD from IT, E2O SA & B2B. Awaiting alignment on when CR can be delivered by Tech. 10/31: Blocked due to CR. and CR changes are planned for S20. 50% TC's are dependent on CR logic 10/22: CR0856. CR is impacting core function and FUT can proceed only after CR is implemented. FS pending approval, ETA for FS approval 27th Oct 10/17 - S/4 Testing is completed for half of the Scenarios, Other half are blocked due to CR0856 changes, FSD under approval for the same | 2025-04-18 | N | 99. Logistics |  |  |  |  | 12/02 - CR Build in progress. Will be tested in S21 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-28 | Yes | Change in Custom Table entries for Plant Tables -ZTPTP_PARAMS, ZTPTP_DH and ZTPTP_ROUTING | No |  | No |  | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-06 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2136 | LOGE0754_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to enable Outbound Interface to send 4B2 Goods receipt acknowledgement from S/4 to E2Open-IF | 06. PTP | 6.4 PTP - Logistics Management Inbound | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://secure-web.cisco.com/19fC_OrnaVbacjnvAzX6fr6x56CDazvBXtTPRcG_an2UxiiD3iqAG8LPBU12LFZNO45BwBVyrZXXFAPscA-jckKyAX7qNaEaHVTfuLJavBsiqoQg6aecxmv9VhWqIOk93QwIaBBbAzcIsMXhEjokXv0kK3tOfn7m21Ervzs3_1tH1qpUCtv1DQkwqTOUT6COFOip48uwX5fH0PT4TDBgIy03rhevKBUlOT2c4rdDNwTFMVuIaFQQXE_jkKlJlNvZncORNp68WEqD61uepgUNFRh8719iV7xA0DeNIk9gv9WremRxfrd3RS6PkxsAFY_Z4YaFa2RfPPYvI_YLwYd0MF0QtWCtEzirs7aCSGX3FMaDQaeU1gcu8_gKpyz0h4krgwxxuqyy6jlWWHRvd7vKQjLKKIvCCTR_fzWj7jzkLL7VZ75mNRve9QLLNQQQF-NSF4ZHBPHXJFUiICBvvWpR03JMKWi4ws_bKiBaESsD_u7Dtfv5lgLqhscpQdIABrhiS/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2FPTP%2520LE%2F2135%2520%2526%25202136_PTP-LE%2520Generate%2520Outbound%25204B2%2520Message%2520from%2520S4%2520for%2520the%2520GRs%2520performed%2520at%25203PL%2520for%2520E2Open%2520onboarded%2520Suppliers%2520Subcon%2520-%2520S4%2520IP%2526IF%2520to%2520E2Open.pptx%3Fd%3Dw89fec9332e4f472e81e5bdde7ddc63b5%26csf%3D1%26web%3D1%26e%3DyaGfGV | 02.No | 01.Yes |  | 2024-10-23 | Cari H Shim | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-17 | 2025-02-14 | 2025-02-07 | 100% | 2025-02-17 | 2025-04-14 | 2025-04-18 | 2025-03-24 | 100% | 2025-03-27 | 2025-05-05 | 2025-05-16 | 2025-03-28 | 100% | 2025-03-28 | 2025-05-05 | 2025-05-16 | 2025-03-28 | 100% | 2025-03-28 | [15 empty] | 2025-03-28 | 2025-03-28 |  |  | 2025-11-26 | 2025-12-02 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-28 | 2025-12-02 | N | 100% | 2025-12-17 | Not Applicable | R3 Build & UT Sprint 21 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-19 | 01.S4 | LOGE0754_IP | 03.Medium | 0.2 | 0.2 | 0754 |  | R3 ITC1 | [6 empty] | 2025-02-17 | 2025-02-17 | 2025-02-17 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 |  | 2025-03-28 | 2025-05-16 | [14 empty] | 2025-03-28 | 2025-03-28 |  |  | 2025-12-17 | 2025-12-17 | 2025-12-17 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-22 |  |  |  | 1 |  | 2738 | [7 empty] | 4. Completed | 1. Approved no action | 12/15 - Received approval from Intel 12/08 - Review comments received on from Intel IT on LOGI0953 related enhancement TCs, will be addressed by today 12/08. Approval received from Intel IT for LOGI0150_IF & LOGF0920_IF related enhancement Scenarios. 12/01: Review comments received, will be addressed by tomorrow 12/02 11/24: High number of TCs. 32/57 are completed. ETC to send for intel review 11/27 11/18 - FUT is in-progress, 28 TCs are completed out of 50 11/14 - FUT is in-progress, 18 TCs are completed out of 50 | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-03-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2330 | LOGE0752_IP | 04.Enhancement | 01.IP - Intel Product | TM: Auto-approve dispute doc for CTSI based invoices to update pass invoice charges in the freight order.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD3433B0F-3D98-4DB3-AC3B-840EE54302CA%7D&file=R3%20PTP%20%20LI-030-240%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)%20-%20Auto-approve%20Dispute%20for%20CTSI.pptx&wdLOR=c1572D7F4-553D-439B-BEC9-34A7362BB49E&action=edit&mobileredirect=true&CID=29678413-51AE-41DB-BE2A-6E38D1F6D0FE | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-11 | 2026-02-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-13 | 2026-02-13 | N | 100% | 2026-02-09 | Sprint 23 Week 1 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0752 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-15 | 2025-08-13 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-09 | 2026-02-13 | 2026-02-09 | [5 empty] | 2025-06-30 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1881 | [7 empty] | 4. Completed | 8. Blocked by CR/Design change |  | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: Development in progress. Dependency with Service master config (PTP& MDG teams). Trying to get exception for ITC 2. 5.1 in S21 & 5.2 in S22 |  |  |  |  | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2330 | LOGE0752_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Auto-approve dispute doc for CTSI based invoices to update pass invoice charges in the freight order.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD3433B0F-3D98-4DB3-AC3B-840EE54302CA%7D&file=R3%20PTP%20%20LI-030-240%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)%20-%20Auto-approve%20Dispute%20for%20CTSI.pptx&wdLOR=c1572D7F4-553D-439B-BEC9-34A7362BB49E&action=edit&mobileredirect=true&CID=29678413-51AE-41DB-BE2A-6E38D1F6D0FE | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-13 | 2026-02-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-13 | 2026-02-20 | N | 100% | 2026-02-09 | Sprint 23 Week 1 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-11-02 | 01.S4 | LOGE0752_IP | 03.Medium | 0.2 | 0.2 | 0752 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-15 | 2025-08-13 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-09 | 2026-02-20 | 2026-02-09 | [5 empty] | 2025-06-30 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1880 | [7 empty] | 4. Completed |  |  | 2025-12-05 | N | 99. Logistics |  |  |  | 1211: Development in progress. Dependency with Service master config (PTP& MDG teams). Trying to get exception for ITC 2. 5.1 in S21 & 5.2 in S22 |  |  |  |  | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2329 | LOGE0751_IP | 04.Enhancement | 01.IP - Intel Product | TM: Shortcut planning and optimizer-based planning for Capital PO to perform carrier selection, charge calculation, cost distribution and settlement.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B40F38BEB-DB7F-4F31-8445-0AFF90B3B926%7D&file=R3%20PTP%20%20LI-030-160%20Manage%20In-bound%20Transportation-%20Capital%20PO%20planning_.pptx&wdLOR=cC550F2B4-6419-41CE-B4A9-111C82F0726F&action=edit&mobileredirect=true&CID=F38D34F6-A9AA-4FDF-96EA-DF67E44E42EF | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-03 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-15 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-01 | 01.S4 |  |  | 1 | 1 | 0751 |  | R3 ITC1 | [6 empty] | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | [5 empty] | 2025-06-30 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 1879 | [7 empty] | 4. Completed | 17. FUT In progress | 01/12: Documentation to be shared by 12th EOD, Intel review scheduled on 14th 01/05: MTR issue blocking 6 TC, 11 TC completed. TUT + FUT to continue 12/22: 10/19 test cases completed in TUT+FUT. 12/15: TUT+FUT session scheduled together | 2025-12-05 | N | 99. Logistics | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2329 | LOGE0751_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Shortcut planning and optimizer-based planning for Capital PO to perform carrier selection, charge calculation, cost distribution and settlement.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B40F38BEB-DB7F-4F31-8445-0AFF90B3B926%7D&file=R3%20PTP%20%20LI-030-160%20Manage%20In-bound%20Transportation-%20Capital%20PO%20planning_.pptx&wdLOR=cC550F2B4-6419-41CE-B4A9-111C82F0726F&action=edit&mobileredirect=true&CID=F38D34F6-A9AA-4FDF-96EA-DF67E44E42EF | 02.No | 01.Yes |  | 2024-10-23 | Randy Eck | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-03 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-12-19 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-15 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-01 | 01.S4 | LOGE0751_IP | 03.Medium | 0.2 | 0.2 | 0751 |  | R3 ITC1 | [6 empty] | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | [5 empty] | 2025-06-30 | 2025-04-18 |  |  | 2025-06-20 | TM |  |  | 1 | 08. Not Applicable | 1878 | [7 empty] | 4. Completed | 17. FUT In progress | 01/12: Documentation to be shared by 12th EOD, Intel review scheduled on 14th 01/05: MTR issue blocking 6 TC, 11 TC completed. TUT + FUT to continue 12/22: 10/19 test cases completed in TUT+FUT. 12/15: TUT+FUT session scheduled together | 2025-12-05 | N | 99. Logistics | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2328 | LOGE0750_IP | 04.Enhancement | 01.IP - Intel Product | TM: Update Pass invoice amount including prompt payment discount from CTSI to freight order and leverage the same for cost distribution.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAB622B9E-2191-4CB7-89CD-468123297AD1%7D&file=R3%20PTP%20%20LI-030-240%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)-%20Pass%20invoice%20via%20CTSI.pptx&action=edit&mobileredirect=true&CID=1C7C9C74-83F0-4708-B925-DEF156A47E30&wdLOR=c40EDCFA9-4925-4632-B540-DD2A56C15F14 | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-01-13 | 2025-02-28 | 2025-02-21 | 100% | 2025-03-07 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2026-02-02 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2026-02-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-19 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-01 | 01.S4 |  |  | 4 | 4 | 0750 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-02-28 | 2025-06-13 |  |  | 2025-08-22 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1877 | [7 empty] | 1. On Track | 17. FUT In progress | 02/02: FUT sent to Intel for review. Call to be scheduled for a walkthrough on 02/03 01/30: FUT Documentation in progress. To be sent for review by today EOD 01/19: Defect fix in progress. 01/12 :Awaiting Tech confirmation, FUT to start 01/12 01/05: Issue in tech build. Build yet to complete 12/22: Build yet to complete by tech team, ETA given by Alisha is 8th Jan. 12/15: Build yet to complete by tech team 11/03 EP: LOGE750 IP: Will be FUT executed in S21 as per latest, as corresponding defect fix + CR in its IF FUT is being performed and will be reviewed approved in S20. | 2025-10-03 | N | 99. Logistics |  |  |  | Pipe Delimiter changes are not required. ETA is 12/19. |  |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2328 | LOGE0750_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Update Pass invoice amount including prompt payment discount from CTSI to freight order and leverage the same for cost distribution.​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAB622B9E-2191-4CB7-89CD-468123297AD1%7D&file=R3%20PTP%20%20LI-030-240%20Manage%20In-bound%20Transportation-%20Audit%20and%20Pay%20Freight%20Bills%20(NMDB)-%20Pass%20invoice%20via%20CTSI.pptx&action=edit&mobileredirect=true&CID=1C7C9C74-83F0-4708-B925-DEF156A47E30&wdLOR=c40EDCFA9-4925-4632-B540-DD2A56C15F14 | 02.No | 01.Yes |  | 2024-10-28 | Randy Eck | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-13 | 2025-02-28 | 2025-02-21 | 100% | 2025-03-07 | 2025-08-22 | 2025-08-29 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2026-01-15 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-01 | 01.S4 | LOGE0750_IP | 01.Very High | 0.8 | 0.8 | 0750 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | [5 empty] | 2025-02-28 | 2025-06-13 |  |  | 2025-08-22 | TM |  |  | 1 | 04.2 Logistics - B-App: CTSI Supplier | 1876 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 01/12: Doc shared with IT + Business, review call scheduled on 13th 12/22: Defect 5702 has been opened with tech team after one round of review with Intel. :12/15:Defect 5585 raised with Tech 12/01: INT-CR1545 to be presented on 12/02 for alignment on the new file format 11/24: Defect still in work by Tech team. Revised FUT due date- 11/28 11/18: Defect still in work by Tech team. Revised FUT due date- 11/28 11/13 EP: Provide defect update & revised FUT due date 11/11: Roadblock defect 3709, 4316+CR 11/04: Roadblock defect 3709-block due to enhancement not being complete- separate radio button missing for separate programs 11/03 EP CR3709 blocker defect open in progress, aligned with Tech team with build CR1426 to fix blocker defect Wk 1 S20 10/31: Still in roadblock. 1 blocker defect open in progress by Dev. 10/24 - Tech Team update - FUT defect 3709 is in progress. ETA - 10/28, FUT defect 3750 is is progress. ETA - 10/28 10/24 - Defect 3709. Tech team to provide the ETA 10/23 EP: Provide ETA for Defect Resolution / New FUT Revised Finish Date 10/22: Defect blocking testing all the test cases - 3709, 3750 | 2025-10-03 | N | 99. Logistics |  |  |  | 0107: Team working on the feedback post FUT Review | 12/02 - Comma Delimiter to Pipe Delimiter. Design change is being asked. | 5. Review Closed | 3 | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2075 | LOGE0690 | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Boundary App - MySample for GTT: re-purposing. Applicable for Intel Product. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0B9C1EA8-82BF-42AD-B202-2CCF70745BDA%7D&file=WOM-MySample_GTT_InterfaceIntake%20Form.pptx&wdLOR=cE514C1B4-AA5F-49DA-9120-2FA549A3167A&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-22 | 2025-05-30 | 2025-06-06 | 2025-06-20 | 100% | 2025-08-22 | 2025-05-30 | 2025-07-11 | 2025-07-11 | 100% | 2025-08-22 | 2025-05-30 | 2025-09-12 | 2025-07-11 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-05 | 01.S4 |  |  | 1 | 1 | 0690 |  | R3 ITC1 | [6 empty] | 2025-01-22 | 2025-01-24 | 2025-01-22 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-08-29 | TM |  |  | 1 | 08. Not Applicable | 2077 | [7 empty] | 2. At Risk | 17. FUT In progress | 9/8: Made the changes as per SFDC Feedback and sent email for review once they will confirm ..will start FUT preparation 9/5: Yesterday for 690 1 round of walkthrough has been done, few changes they have suggest we are working on that and after that will sent the FUT document to them 9/1: FUT has been successfully completed for all tested scenarios, with two fields—ETA (pending defect 2438 resolution by September 2nd) and COO (dependent on object LOGF0344/OTC LE)—still outstanding due to dependencies on other RICFEWs dur to which it is delayed. | 2025-09-12 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2076 | LOGE0673_IP | 04.Enhancement | 01.IP - Intel Product | Data code extractor to be extended on S4 TM side​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/CRF%20Freight%20order%20-%20Shipped%20CRF%20as%20an%20Event.pptx?d=wec610d4c2da44b2b99ab4cfb021b9a68&csf=1&web=1&e=akaX3O | 01.Yes | 01.Yes |  | 2024-09-25 | Randy Eck | 01.Approved | 2024-10-04 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-08 | 2024-12-13 | 2024-12-20 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-04 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 |  |  | 1 | 1 | 0673 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2024-12-20 | 2024-12-18 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-08-13 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-06-27 | TM |  |  | 1 | 08. Not Applicable | 2081 | [10 empty] | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2076 | LOGE0673_IF | 04.Enhancement | 02.IF - Intel Foundry | Data code extractor to be extended on S4 TM side​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/CRF%20Freight%20order%20-%20Shipped%20CRF%20as%20an%20Event.pptx?d=wec610d4c2da44b2b99ab4cfb021b9a68&csf=1&web=1&e=akaX3O | 01.Yes | 01.Yes |  | 2024-09-25 | Randy Eck | 01.Approved | 2024-10-04 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-08 | 2024-12-13 | 2024-12-20 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-04 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 | LOGE0673_IP | 03.Medium | 0.2 | 0.2 | 0673 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2024-12-20 | 2024-12-18 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-06-27 | TM |  |  | 1 | 08. Not Applicable | 2080 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2109 | LOGE0665_IP | 04.Enhancement | 01.IP - Intel Product | Calculation base and Associated charge calculation logic for field creation and logic determination - commodity code, delivery time, movement type | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCF9F6021-2F08-468C-8D69-90A2526BF5FD%7D&file=R3%20PTP%20%20L3%20-%20030-060%20TM%20Charge%20Management%20-Calculation%20base%20and%20Associated%20charge%20calculation.pptx&action=edit&mobileredirect=true&wdLOR=c5B8A4377-327F-4DB2-84FD-1B4776EE7BD8 | 02.No | 01.Yes |  | 2024-09-22 | Randy Eck | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-03-03 | 2025-04-04 | 2025-04-04 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-09-27 | 01.S4 |  |  | 1 | 1 | 0665 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 2280 | [7 empty] | 1. On Track | 17. FUT In progress | 11/24: FUT WIP. Data preparation ongoing ETA 03/12 11/18: FUT to be started from 11/18 11/14: Not yet ready for FUT | 2025-10-31 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2109 | LOGE0665_IF | 04.Enhancement | 02.IF - Intel Foundry | Calculation base and Associated charge calculation logic for field creation and logic determination - commodity code, delivery time, movement type | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCF9F6021-2F08-468C-8D69-90A2526BF5FD%7D&file=R3%20PTP%20%20L3%20-%20030-060%20TM%20Charge%20Management%20-Calculation%20base%20and%20Associated%20charge%20calculation.pptx&action=edit&mobileredirect=true&wdLOR=c5B8A4377-327F-4DB2-84FD-1B4776EE7BD8 | 02.No | 01.Yes |  | 2024-09-22 | Randy Eck | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-03-03 | 2025-04-04 | 2025-04-04 | 100% | 2025-08-04 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-09-27 | 01.S4 | LOGE0665_IP | 03.Medium | 0.2 | 0.2 | 0665 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 2279 | [7 empty] | 1. On Track | 17. FUT In progress | 11/24: FUT WIP. Data preparation ongoing ETA 03/12 11/18: FUT to be started from 11/18 11/14: Not yet ready for FUT | 2025-10-31 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1820 | LOGE0655_IP | 04.Enhancement | 01.IP - Intel Product | TM :PTP IP/IF​ - Weekly Milk run Charge calculation (Local Trucking)​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B69C2A63E-8E86-4147-8CFE-F752A791F006%7D&file=R3%20PTP%20L3%20-%20030-060%20TM-Milk%20run%20process%20-%20Local%20Trucking.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-18 | Cari H Shim | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-15 | 2025-09-19 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | vasamohan@deloitte.com | 2024-09-18 14:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 |  |  | 2 | 2 | 0655 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 1539 | [7 empty] | 4. Completed | 7. FUT Defect Retesting | 11/04:24/32 passed. rest WIP. At risk for approval 10/31: 14 of 32 TC passed. Defect 4004 open, defect 4075 fixed- being retested 10/24 - Auth issue resolved. to be checked with team. 10/22: Roadblock due to Auth issues. Dev team informed SR needs to be raised to intel security to get the access- RITM13533626 created | 2025-10-10 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1820 | LOGE0655_IF | 04.Enhancement | 02.IF - Intel Foundry | TM :PTP IP/IF​ - Weekly Milk run Charge calculation (Local Trucking)​ | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B69C2A63E-8E86-4147-8CFE-F752A791F006%7D&file=R3%20PTP%20L3%20-%20030-060%20TM-Milk%20run%20process%20-%20Local%20Trucking.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-18 | Cari H Shim | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-15 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-15 | 2025-09-19 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | vasamohan@deloitte.com | 2024-09-18 14:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 | LOGE0655_IP | 02.High | 0.4 | 0.4 | 0655 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-09-12 | 2025-09-19 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 1538 | [7 empty] | 4. Completed | 7. FUT Defect Retesting | 11/04:30/32 TC passed. 2 WIP. defect fixed- retest in progress. At risk for approval task 10/31: 17 of 32 TC passed. 2 security defects. rest WIP 10/24 - Auth issue resolved. to be checked with team. 10/22: Roadblock due to Auth issues. Dev team informed SR needs to be raised to intel security to get the access- RITM13533626 created | 2025-10-10 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2080 | LOGE0632_IP | 04.Enhancement | 01.IP - Intel Product | TM: Custom Determination Class to access Source and Destination country in FUBR determination condition in BRF+ decision table. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B28CA63C9-A7C8-479F-9E69-ECB4A3BAFDDD%7D&file=R3_IP_IF_OTC_LO-180-010_Enhancement_Determination%20Class%20for%20Source%20&%20Determination%20Country.pptx=&action=edit&mobileredirect=true&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA3MTEyODgyNSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9&CID=197322BA-27F0-49A6-8181-B3C578AD02DC&wdLOR=c0F28C9E1-34E9-46AB-8A51-B22B0DC2FC4A | 02.No | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-04-01 | 2025-04-29 | 2024-12-20 | 100% | 2025-01-03 | 2025-07-02 | 2025-07-09 | 2025-08-01 | 100% | 2025-09-11 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-11 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-11 | [15 empty] | 2025-09-11 | 2025-09-11 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 |  |  | 0.5 | 0.5 | 0632 |  | R3 ITC1 | [6 empty] | 2025-01-03 | 2025-04-29 | 2025-01-03 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | [12 empty] | 2025-09-11 | 2025-09-11 |  |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | [5 empty] | 2025-04-29 | 2025-09-12 |  |  | 2025-10-03 | TM |  |  | 1 | 08. Not Applicable | 2519 | [10 empty] | 2025-08-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-11 | 2025-09-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2080 | LOGE0632_IF | 04.Enhancement | 02.IF - Intel Foundry | TM: Custom Determination Class to access Source and Destination country in FUBR determination condition in BRF+ decision table. | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B28CA63C9-A7C8-479F-9E69-ECB4A3BAFDDD%7D&file=R3_IP_IF_OTC_LO-180-010_Enhancement_Determination%20Class%20for%20Source%20&%20Determination%20Country.pptx=&action=edit&mobileredirect=true&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA3MTEyODgyNSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9&CID=197322BA-27F0-49A6-8181-B3C578AD02DC&wdLOR=c0F28C9E1-34E9-46AB-8A51-B22B0DC2FC4A | 02.No | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-01 | 2025-04-29 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-02 | 2025-07-09 | 2025-08-01 | 100% | 2025-09-11 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-11 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-11 | [15 empty] | 2025-09-11 | 2025-09-11 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 | LOGE0632_IP | 04.Low | 0.1 | 0.1 | 0632 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | [12 empty] | 2025-09-11 | 2025-09-11 |  |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | [5 empty] | 2025-04-29 | 2025-09-12 |  |  | 2025-10-03 | TM |  |  | 1 | 08. Not Applicable | 2518 | [10 empty] | 2025-08-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-11 | 2025-09-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2079 | LOGE0631 | 04.Enhancement | 01.IP - Intel Product | TM - GTT: ETA calculated date to be captured in GTT Delivery App. IP | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/ETA%20Calculation_Enhancement%20Intake%20Form.pptx?d=wd99a3faf674e4784bbca71d83f62d570&csf=1&web=1&e=epTSVj | 01.Yes | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-10 | 2025-03-14 | 2025-03-14 | 100% | 2025-03-20 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-05 | 01.S4 |  |  | 0.5 | 0.5 | 0631 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-20 | 2025-03-20 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-03-14 | 2025-09-12 |  |  | 2025-09-10 | TM |  |  | 1 | 08. Not Applicable | 2517 | [10 empty] | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2076 | LOGE0628_IP | 04.Enhancement | 01.IP - Intel Product | CRF freight orders, should have a custom event type “Shipped –CRF". This custom event type gets updated in Freight order at the time of Post goods issue in delivery document in S/4​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/CRF%20Freight%20order%20-%20Shipped%20CRF%20as%20an%20Event.pptx?d=wec610d4c2da44b2b99ab4cfb021b9a68&csf=1&web=1&e=akaX3O | 01.Yes | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-08 | 2024-12-13 | 2024-12-20 | 100% | 2024-12-17 | 2025-04-04 | 2025-04-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-06-27 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 |  |  | 0.5 | 0.5 | 0628 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-20 | 2024-12-17 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-06-27 | TM |  |  | 1 | 08. Not Applicable | 2079 | [10 empty] | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2076 | LOGE0628_IF | 04.Enhancement | 02.IF - Intel Foundry | CRF freight orders, should have a custom event type “Shipped –CRF". This custom event type gets updated in Freight order at the time of Post goods issue in delivery document in S/4​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Logistic/Logistics%20GTT/RICEFW%20Intake%20forms/CRF%20Freight%20order%20-%20Shipped%20CRF%20as%20an%20Event.pptx?d=wec610d4c2da44b2b99ab4cfb021b9a68&csf=1&web=1&e=akaX3O | 01.Yes | 01.Yes |  | 2024-09-25 | Randy Eck | 01.Approved | 2024-10-04 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-08 | 2024-12-13 | 2024-12-20 | 100% | 2024-12-17 | 2025-03-07 | 2025-03-14 | 2025-05-20 | 100% | 2025-05-24 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-04-04 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-04 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-25 | 2025-05-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 | LOGE0628_IP | 04.Low | 0.1 | 0.1 | 0628 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-20 | 2024-12-17 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-30 | TM |  |  | 1 | 08. Not Applicable | 2078 | [10 empty] | 2025-04-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2075 | LOGE0627 | 04.Enhancement | 01.IP - Intel Product | TM - GTT: Boundary App - WOM fields in GTT for WOM/MySample re-purposing. Applicable for Intel Product. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0B9C1EA8-82BF-42AD-B202-2CCF70745BDA%7D&file=WOM-MySample_GTT_InterfaceIntake%20Form.pptx&wdLOR=cE514C1B4-AA5F-49DA-9120-2FA549A3167A&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-25 | Randy Eck | 01.Approved | 2024-10-04 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-22 | 2025-08-01 | 2025-08-08 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-09-12 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-05 | 01.S4 |  |  | 1 | 1 | 0627 |  | R3 ITC1 | [6 empty] | 2025-01-22 | 2025-01-24 | 2025-01-22 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 |  | 2025-07-21 | 2025-09-12 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-08-13 | TM |  |  | 1 | 08. Not Applicable | 2076 | [7 empty] | 2. At Risk | 13. Blocked by Other RICEFW | 9/8: FUT sent for Approval 9/5 :One round of walkthrough done by today EOD we are going to send FUT document to Intel 9/1: Same status as 8/25 8/25: Same status as 8/18 8/18: FUT is blocked with defects. Defect 1783 and 2107 is open for this FUT. | 2025-09-12 | Y | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-09-12 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE0626_IP | 04.Enhancement | 01.IP - Intel Product | FO subcontracting screen for tendering enhancement. Fields include- send for approval Button, RFQ response approval status​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-25 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 |  |  | 0.5 | 0.5 | 0626 |  | R3 ITC1 | [6 empty] | 2025-04-25 | 2025-04-25 | 2025-04-25 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 2733 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-09-12 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE0626_IF | 04.Enhancement | 02.IF - Intel Foundry | FO subcontracting screen for tendering enhancement. Fields include- send for approval Button, RFQ response approval status​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Randy Eck | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-25 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-18 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-05 | 01.S4 | LOGE0626_IP | 04.Low | 0.1 | 0.1 | 0626 |  | R3 ITC1 | [6 empty] | 2025-04-25 | 2025-04-25 | 2025-04-25 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-18 | 2025-10-31 | 2025-10-18 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-19 | TM |  |  | 1 | 08. Not Applicable | 2732 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-09-12 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE0625_IP | 04.Enhancement | 01.IP - Intel Product | Tendering- FIORI app for Approval Hierarchy (Assign Delegate) | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-05-09 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-25 | 01.S4 |  |  | 0.5 | 0.5 | 0625 |  | R3 ITC1 | [6 empty] | 2025-05-09 | 2025-05-09 | 2025-05-09 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-04 | 2025-09-10 | 2025-09-04 | [5 empty] | 2025-04-18 | 2025-09-12 |  |  | 2025-09-10 | TM |  |  | 1 | 08. Not Applicable | 2729 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-09-12 | Y | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1928 | LOGE0625_IF | 04.Enhancement | 02.IF - Intel Foundry | Tendering- FIORI app for Approval Hierarchy (Assign Delegate) | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-10-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B30C5F38D-0CC6-4CF6-9099-8B6246A7DC26%7D&file=R3_IP_OTC_LO-190-080_Tendering_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-11 | Jorge Sanchez | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-05-09 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-07-04 | 2025-07-11 | 2025-09-05 | 100% | 2025-08-22 | 2025-06-30 | 2025-07-11 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-04 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-11 | 2025-07-11 | 2025-07-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-25 | 01.S4 | LOGE0625_IP | 04.Low | 0.1 | 0.1 | 0625 |  | R3 ITC1 | [6 empty] | 2025-05-09 | 2025-05-09 | 2025-05-09 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-05 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-04 | 2025-09-10 | 2025-09-04 | [5 empty] | 2025-04-18 | 2025-07-11 |  |  | 2025-09-10 | TM |  |  | 1 | 08. Not Applicable | 2728 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-07-11 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1971 | LOGE0613 | 04.Enhancement | 01.IP - Intel Product | Development of LCSR tool in Fiori | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LCSR_Fiori_App_Development.pptx?d=w89ffaa4261e343c3a0c5f1e47e9b10cf&csf=1&web=1&e=W0nVeb | 02.No | 01.Yes |  | 2024-09-09 | jorge.sanchez@intel.com | 01.Approved | 2024-09-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  | Logistics Customers Service Request |  |  | NA | 2025-03-03 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2026-01-02 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2026-01-02 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2026-01-02 | [15 empty] | 2026-01-02 | 2026-01-02 |  |  | 2025-12-03 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-01 | 01.S4 |  |  | 4 | 4 | 0613 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | [12 empty] | 2026-01-02 | 2026-01-02 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | [5 empty] | 2025-05-02 | 2025-11-05 |  |  | 2026-02-04 |  |  |  | 1 | 08. Not Applicable | 1924 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/02: Defect#6761 is with tech for fix, ETA 02/03 for backend, no ETA from Fiori 01/29: All review sessions completed, call scheduled today with Intel PS on way forward for the feedback points 01/22: Third review session completed today morning, additional session planned today evening. Once all review sessions completed. Feedback points will be categorized as Issues/Changes and defects will be raised for the issues 01/19: Additional review sessions scheduled on 01/21 & 01/22. Defect#6378 with tech, no eta 01/12: FUT sent for approval on 01/09 01/05: Defect#5712 is closed, defect#5830 is fixed & retest is in progress ETA 01/05. Defect#5929 yet to be picked up by tech team 12/22:Defect#5712 is with tech team ,backed changes are completed, Defect#5830 is with tech. Defect#5779 retest is in progress. ETC 01/02.13 TC executed out of 20. 12/15: Defect#5557 is with tech, handover given to tech, no ETA. FUT Approval is planned in S21. 12/08: Defect#5293 is closed, defect#5165, 5136 with tech, no ETA. 5.2 is planned in S21. 12/01: Open defects 4909, 5025, 5050 11/24: Defect#4518 & 4565 reassigned to tech as still some issues are open IMP 11/18: Defect#4518, 4565, 4612 with tech, FUT started | 2025-11-05 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2026-01-02 | 2026-01-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1959 | LOGE0611 | 04.Enhancement | 01.IP - Intel Product | 1. Custom fields in Delivery to store Number of Pallets & IPLA indicator fields 2. Email notification to 3PL upon 3B13 interface rejection in SAP | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-09-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_Custom%20fields%20in%20Delivery_Email_Notification_for_3B13_failure.pptx?d=wdb3585e75858412f86ff0bc795fa030d&csf=1&web=1&e=cgCM4p | 02.No | 01.Yes |  | 2024-09-09 | Randy Eck | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-07 | 2025-04-04 | 2025-04-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-14 | 01.S4 |  |  | 1 | 1 | 0611 |  | R3 ITC1 | [6 empty] | 2025-01-07 | 2025-01-10 | 2025-01-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 1 | 08. Not Applicable | 2340 | [9 empty] | 10/06: Intel IT approved, awaiting Intel Business approval 09/29: Will be resent for approval by 09/29, calling out the additional scenario as a new requirement. 09/22: Currently under Intel Approval. Additional Test scenarios tested and sent for approval. 09/12: Delayed due to dpendency on LOGI0609, which had defects. Defect 3013 for 1 scenario with Tech team. FUT plan to complete by 09/15 | 2025-05-16 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1874 | LOGE0608 | 04.Enhancement | 01.IP - Intel Product | Custom logic to fetch the details from different source and save in the custom field of table LIKP/LIPS during delivery creation. | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-09-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_Text%20Id%20mapping%20with%20Table%20Field_RICEFW%20Intake%20Form.pptx?d=wa618deec877d4614b948a1fa2b1d37cd&csf=1&web=1&e=nvngvs | 02.No | 01.Yes |  | 2024-09-09 | Randy Eck | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-09 | 2025-04-04 | 2025-04-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | vasamohan@deloitte.com | 2024-09-09 11:38 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-14 | 01.S4 |  |  | 1 | 1 | 0608 |  | R3 ITC1 | [6 empty] | 2025-01-09 | 2025-01-10 | 2025-01-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-06-13 | [6 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 1 | 08. Not Applicable | 1685 | [10 empty] | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1705 | LOGE0581 | 04.Enhancement | 01.IP - Intel Product | Incoterm Location 1 ID field update for Outbound delivery | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-09-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_Z3PC_RICEFW%20Intake%20Form.pptx?d=w8ddd20f3fd6c49f9a64642e1842c5e5b&csf=1&web=1&e=huZGj2 | 02.No | 01.Yes |  | 2024-09-05 | Randy Eck | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-09 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-03-24 | 2025-05-09 | 2025-05-16 | 2025-04-03 | 100% | 2025-03-24 | 2025-05-09 | 2025-05-16 | 2025-04-03 | 100% | 2025-03-24 | [15 empty] | 2025-03-24 | 2025-03-24 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-30 04:42 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-14 | 01.S4 |  |  | 0.5 | 0.5 | 0581 |  | R3 ITC1 | [6 empty] | 2025-01-09 | 2025-01-10 | 2025-01-09 |  | 2025-03-24 | 2025-04-11 | 2025-03-24 |  | 2025-03-24 | 2025-05-16 | 2025-03-24 | 2025-03-24 | [12 empty] | 2025-03-24 | 2025-03-24 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 1 | 08. Not Applicable | 1797 | [10 empty] | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-03-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0547_IP | 04.Enhancement | 01.IP - Intel Product | Mass upload – Custom TM program for below items. Resource Downtime upload.Note: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-20 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-17 | 100% | 2025-07-21 | 2025-04-11 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-11 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-07 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-14 11:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 0.5 | 0.5 | 0547 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-07 | 2025-08-13 | 2025-08-07 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2614 | [7 empty] | 1. On Track | 13. Blocked by Other RICEFW | FUT planned in S16, since FS were being prioritized in the earlier sprints, on track to complete in S16 | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0547_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass upload – Custom TM program for below items. Resource Downtime upload.Note: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-20 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-07 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-14 11:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 | LOGE0547_IP | 04.Low | 0.1 | 0.1 | 0547 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-07 | 2025-08-13 | 2025-08-07 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2613 | [7 empty] | 1. On Track | 3. Awaiting Approval | FUT planned in S16, since FS were being prioritized in the earlier sprints, on track to complete in S16 | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0546_IP | 04.Enhancement | 01.IP - Intel Product | Mass upload – Custom TM program for below items. Schedule and Default Routes Mass upload, Update & deletion(departure schedules) - IP only however transaction will be available in both instancesBuild Road Schedule upload program that also considers customer calendar.Note: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-20 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-14 11:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 0.5 | 0.5 | 0546 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2616 | [7 empty] | 1. On Track | 3. Awaiting Approval | 09/22: Presenting to Intel review on 9/22 09/15 : Multiple issues observed and Defect 2960 and 2963 are open. Testing is in progress. Multiple observed during FUT due this it was delayed. Testing in Progress | 2025-05-16 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0546_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass upload – Custom TM program for below items. Schedule and Default Routes Mass upload, Update & deletion(departure schedules) - IP only however transaction will be available in both instancesBuild Road Schedule upload program that also considers customer calendar.Note: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-20 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-24 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-14 11:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 | LOGE0546_IP | 04.Low | 0.1 | 0.1 | 0546 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2615 | [9 empty] | 09/22: Presenting to Intel review on 9/22 09/15 : Multiple issues observed and Defect 2960 and 2963 are open. Testing is in progress. Multiple observed during FUT due this it was delayed. Testing in Progress | 2025-05-16 | N | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1821 | LOGE0515_IP | 04.Enhancement | 01.IP - Intel Product | TM : Fetch Integrators rate in TM via an API call to Redwood and leverage it for carrier selection and charge calculation. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA8E15C19-F04F-4FC5-B53C-92F05F08B776%7D&file=R3%20PTP%20L3%20-%20030-060%20%20Integrator%20interface%20-Rate%20Integrators%20with%20Redwood.pptx&wdLOR=cC3781B9E-FD79-4F33-9CE5-D4E8A7F1AB55&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-01-06 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-05-02 | 2025-05-09 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-04 | 01.S4 |  |  | 1 | 1 | 0515 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-23 | TM |  |  | 1 | 04.3 Logistics - Redwood 3rd Party Integrator | 1543 | [9 empty] | EP: 09/11: ETC 09/12 per Jeet | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1750 | LOGE0514 | 04.Enhancement | 01.IP - Intel Product | After 3B13 is triggered and Pick & Pack is completed in deliveries, and the Hawb Numbers updated in DN>Enhancement to Update Hawb numbers in FU and Unblock FU and Update Hawb no in FO | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-190-100_IP_Freight%20Order%20Execution_3PL_TM_RICEFW%20Intake%20Form.pptx?d=w5019ee05f4bd498ea9fa378c8560eb93&csf=1&web=1&e=vaGb4m | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-15 | 2025-05-20 | 2025-05-23 | 100% | 2025-08-04 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-24 | 2025-11-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-07 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 1 | 1 | 0514 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-05-20 | 2025-09-12 |  |  | 2025-10-03 | TM |  |  | 1 | 08. Not Applicable | 1988 | [7 empty] | 4. Completed | 17. FUT In progress | 11/04: TM team to work with Tech team to finish the remaining Test case. Target ETA- 11/05 10/31: To be sent for Internal review EOD. Review call with Intel next week | 2025-10-24 | Y | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1750 | LOGE0513 | 04.Enhancement | 01.IP - Intel Product | After 3B12 is triggered and YDN0 output type is triggered in the deliveries, enhancement to trigger change controller strategy in TM to de-link all the FUs from the Freight Orders except for one and add a Planning Block in FU with reason code | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-190-100_IP_Freight%20Order%20Execution_3PL_TM_RICEFW%20Intake%20Form.pptx?d=w5019ee05f4bd498ea9fa378c8560eb93&csf=1&web=1&e=vaGb4m | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-04-08 | 2025-05-27 | 2025-05-23 | 100% | 2025-05-23 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-24 | 2025-11-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-07 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 1 | 1 | 0513 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-05-27 | 2025-05-23 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-05-27 | 2025-09-12 |  |  | 2025-10-10 | TM |  |  | 1 | 08. Not Applicable | 1986 | [7 empty] | 4. Completed | 17. FUT In progress | 11/04: TM team to work with Tech team to finish the remaining Test case. Target ETA- 11/05 10/31: To be sent for Internal review EOD. Review call with Intel next week 10/22: 3 of 5 completed, no open defects. | 2025-10-08 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1750 | LOGE0512 | 04.Enhancement | 01.IP - Intel Product | Update Freight Order Number to the delivery documents after carrier is assigned in FO | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | N | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-190-100_IP_Freight%20Order%20Execution_3PL_TM_RICEFW%20Intake%20Form.pptx?d=w5019ee05f4bd498ea9fa378c8560eb93&csf=1&web=1&e=vaGb4m | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | 8785 | Excursion Containment Disposition | ECD | S4 | NA | 2025-03-03 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-04 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-04 | 2025-06-02 | 2025-06-13 | 2025-09-05 | 100% | 2025-09-04 | 2025-06-02 | 2025-06-13 | 2025-09-05 | 100% | 2025-09-04 | [15 empty] | 2025-09-04 | 2025-09-04 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-08 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-08-06 08:30 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-08-21 | 01.S4 |  |  | 1 | 1 | 0512 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-09-04 | 2025-09-04 | 2025-09-04 |  | 2025-09-04 | 2025-09-05 | 2025-09-04 | 2025-09-04 | [12 empty] | 2025-09-04 | 2025-09-04 |  |  | 2025-09-08 | 2025-09-12 | 2025-09-08 | [5 empty] | 2025-03-28 | 2025-06-13 |  |  | 2025-09-12 | TM |  |  | 1 | 08. Not Applicable | 1989 | [10 empty] | 2025-06-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0511_IP | 04.Enhancement | 01.IP - Intel Product | Mass upload – Custom TM program for below items. Mass upload program to create Customer calendar resource in SAP TMNote: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-07 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 0.5 | 0.5 | 0511 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-07 | 2025-08-13 | 2025-08-07 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2612 | [7 empty] | 1. On Track | 17. FUT In progress | FUT planned in S16, since FS were being prioritized in the earlier sprints, on track to complete in S16 | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1699 | LOGE0511_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass upload – Custom TM program for below items. Mass upload program to create Customer calendar resource in SAP TMNote: This upload functionality will be used by business post cutover/initial load i.e during steady state as well to update, edit or upload the entries | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B31742C6D-252F-4B67-86C3-E7C534CAD094%7D&file=R3_PTP_LI-030-090(120-130-150)_Master%20Data%20Upload_Intake%20Form.pptx&wdLOR=cB4E3481E-1847-40E2-81CD-B3F9D79C6CB3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-11-18 | 2024-12-06 | 2024-11-29 | 100% | 2024-12-02 | 2025-04-04 | 2025-04-11 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-23 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-07 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 | LOGE0511_IP | 04.Low | 0.1 | 0.1 | 0511 |  | R3 ITC1 | [6 empty] | 2024-12-02 | 2024-12-06 | 2024-12-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-07 | 2025-08-13 | 2025-08-07 | [5 empty] | 2024-12-06 | 2025-05-16 |  |  | 2025-06-13 | TM |  |  | 1 | 08. Not Applicable | 2611 | [9 empty] | FUT planned in S16, since FS were being prioritized in the earlier sprints, on track to complete in S16 | 2025-05-16 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1573 | LOGE0510 | 04.Enhancement | 01.IP - Intel Product | TM: To show TPT of each stage in a multileg Shipment (Default Routes) and fill the dates of each stage correspondingly for ET, HK & CD Scenarios | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDEF762FB-1BC9-4621-9460-722560BB7EB3%7D&file=R3_IP_OTC_LO-180-010_IP_Default%20Route_TPT_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-08-15 | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-09-02 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2025-02-14 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-17 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-17 | [15 empty] | 2025-03-17 | 2025-03-17 |  |  | 2025-04-04 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-07 | 2025-03-28 | 2025-04-11 | N | 100% | 2025-05-16 | Not Applicable | R3 Build & UT Sprint 13 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-21 | 01.S4 |  |  | 1 | 1 | 0510 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | [12 empty] | 2025-03-17 | 2025-03-17 |  |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-03-14 | TM |  |  | 1 | 08. Not Applicable | 1736 | [10 empty] | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-17 | 2025-03-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1733 | LOGE0478_IP | 04.Enhancement | 01.IP - Intel Product | Generate Automated Carrier Pre-Alert (ZPRC) from SAP TM. | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB468CC64-3B00-4F35-87D8-D503C3950ADF%7D&file=R3_IF_LOGISTICS_TM_LO-180-150_RICEFW%20Intake%20form%20ZPRC%20Output%20R3.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-23 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-01-06 | 2025-02-21 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2024-07-23 10:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-16 | 01.S4 |  |  | 1 | 1 | 0478 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-23 | TM |  |  | 1 | 08. Not Applicable | 2189 | [7 empty] | 4. Completed | 17. FUT In progress | 12/01: 4 of 15 TC completed, blocker defect open. 11/24: FUT WIP and defect fix in progress TC 3 of 15 completed, ETA 27/11 11/18: Roadblock defect 4613 raised 11/14: FUT started and WIP | 2025-12-05 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1733 | LOGE0478_IF | 04.Enhancement | 02.IF - Intel Foundry | Generate Automated Carrier Pre-Alert (ZPRC) from SAP TM. | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB468CC64-3B00-4F35-87D8-D503C3950ADF%7D&file=R3_IF_LOGISTICS_TM_LO-180-150_RICEFW%20Intake%20form%20ZPRC%20Output%20R3.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-23 | Randy Eck | 01.Approved | 2024-08-15 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-01-06 | 2025-02-21 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2024-07-23 10:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-16 | 01.S4 | LOGE0478_IP | 03.Medium | 0.2 | 0.2 | 0478 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-06-23 | TM |  |  | 1 | 08. Not Applicable | 2190 | [7 empty] | 4. Completed | 17. FUT In progress | 12/01: 9 of 15 TC completed, blocker defect open for remaining TC 11/24: FUT WIP and defect fix in progress TC 5 of 15 completed ETA 27/11 11/18: Roadblock defect 4613 raised 11/14: FUT started and WIP | 2025-12-05 | Y | 99. Logistics | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0459_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- TPT Determination for Carriers | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-31 | 2025-04-04 | 2025-08-01 | 100% | 2025-07-24 | 2025-04-07 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-24 | 2025-04-07 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0459 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1754 | [7 empty] | 1. On Track | 17. FUT In progress | 10/31: Under Intel review, Open comments WIP 10/24 - Documentation to be sent for approval 10/22: Returns TC in progress, to be completed by 22nd EOD. | 2025-04-18 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0459_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- TPT Determination for Carriers | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Randy Eck | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-31 | 2025-04-04 | 2025-08-01 | 100% | 2025-07-24 | 2025-05-19 | 2025-06-13 | 2025-08-13 | 100% | 2025-07-24 | 2025-05-19 | 2025-06-13 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-07-25 09:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0459_IP | 03.Medium | 0.2 | 0.2 | 0459 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2024-09-20 | 2025-04-18 |  |  | 2025-05-16 | TM |  |  | 1 | 08. Not Applicable | 1753 | [7 empty] | 1. On Track | 17. FUT In progress | 10/31: Under Intel review, Open comments WIP 10/24 - Documentation to be sent for approval 10/22: 1st Intel review completed, WIP for review comments. to be sent for approval along with IP | 2025-06-13 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0458_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- Dedicated Carrier Selection ​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-07-25 | 100% | 2025-07-24 | 2025-02-14 | 2025-02-21 | 2025-08-08 | 100% | 2025-07-24 | 2025-02-14 | 2025-02-21 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-08 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0458 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-17 | 2025-10-31 | 2025-10-17 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1748 | [7 empty] | 2. At Risk | 17. FUT In progress | Carrier selection objects to be consolidated and tested together in future sprints. | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0458_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- Dedicated Carrier Selection ​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Randy Eck | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-07-25 | 100% | 2025-07-24 | 2025-02-14 | 2025-02-21 | 2025-08-08 | 100% | 2025-07-24 | 2025-02-14 | 2025-02-21 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-09 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-31 | 2025-10-31 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-25 09:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0458_IP | 03.Medium | 0.2 | 0.2 | 0458 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-17 | 2025-10-31 | 2025-10-17 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1747 | [7 empty] | 1. On Track | 3. Awaiting Approval | Carrier selection objects to be consolidated and tested together in future sprints. | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0457_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- Local Truck selection​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-14 | 2025-02-14 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-14 | [15 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-06-20 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-23 | 2025-07-18 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0457 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-03-14 | 2025-03-14 | [14 empty] | 2025-03-14 | 2025-03-14 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1750 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-14 | 2025-03-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0457_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, Custom carrier selection strategy - Carrier Selection -Custom Strategy- Local Truck selection​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Randy Eck | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-21 | 2025-02-14 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-21 | [15 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-06-20 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-23 | 2025-07-18 | 2025-07-11 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-25 09:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0457_IP | 03.Medium | 0.2 | 0.2 | 0457 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2025-03-21 | [12 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1749 | [10 empty] | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-21 | 2025-03-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0456_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Custom carrier selection strategy - Carrier Selection UI enhancement. ​ | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2025-02-14 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-18 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-18 | [15 empty] | 2025-03-18 | 2025-03-18 |  |  | 2025-06-20 | 2025-06-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-06-27 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0456 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | [12 empty] | 2025-03-18 | 2025-03-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1752 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-18 | 2025-03-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1655 | LOGE0456_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, Custom carrier selection strategy - Carrier Selection UI enhancement. ​ | 04. OTC IF | 4.12 OTC IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B203196C7-832F-44B4-8F8D-D5AC59A6D83D%7D&file=R3_OTC%20TM_LOGISTICS_TM-LO-180-090_RICEFW%20TM%20Custom%20Carrier%20Selection.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-28 | Randy Eck | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2025-02-14 | 2025-02-14 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-17 | 2025-02-14 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-17 | [15 empty] | 2025-03-17 | 2025-03-17 |  |  | 2025-06-20 | 2025-06-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-06-27 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-07-25 09:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0456_IP | 03.Medium | 0.2 | 0.2 | 0456 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2025-03-17 | 2025-03-17 | 2025-03-17 | 2025-03-17 | [12 empty] | 2025-03-17 | 2025-03-17 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-04-04 | TM |  |  | 1 | 08. Not Applicable | 1751 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-02-21 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-17 | 2025-03-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1559 | LOGE0455 | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Post schedule lines updated, enhancement to unblock the Freight unit | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBD33D425-932B-4C49-B398-5A9208DA991D%7D&file=R3_IP_OTC_LO-180-010_020_IP_Planning%20Failed%20Msg_field%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-17 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-02-28 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-03-06 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-12-11 07:34 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-08 | 01.S4 |  |  | 1 | 1 | 0455 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-03-06 | 2025-03-21 | 2025-03-06 | [5 empty] | 2024-09-20 | 2025-01-31 |  |  | 2025-03-14 | TM |  |  | 1 | 08. Not Applicable | 2361 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1559 | LOGE0454 | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Enhancement to add a Planning Block in the Freight Unit with the Block Reason code “Missing Schedules” during the optimizer run, when there is a custom failure message for missing Schedules | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BBD33D425-932B-4C49-B398-5A9208DA991D%7D&file=R3_IP_OTC_LO-180-010_020_IP_Planning%20Failed%20Msg_field%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-09 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-02-28 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-03-06 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-07 | 2025-02-07 | 2025-02-07 | pgaroo@deloitte.com | 2024-12-11 07:34 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-08 | 01.S4 |  |  | 1 | 1 | 0454 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-02-09 | 2025-02-21 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-03-06 | 2025-03-21 | 2025-03-06 | [5 empty] | 2024-09-20 | 2025-02-07 |  |  | 2025-03-14 | TM |  |  | 1 | 08. Not Applicable | 2360 | [10 empty] | 2025-02-07 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1556 | LOGE0453 | 04.Enhancement | 01.IP - Intel Product | In SAP TM, When the Incoterm Location1 ID field is populated in the delivery document, the delivery dates in the 1st stage (Incoterm Location) to be populated with the destination dates | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-180-010_IP_Z3PC_RICEFW%20Intake%20Form.pptx?d=wc3623ea7b9c54976ba091440c619340e&csf=1&web=1&e=5FhNtZ | 02.No | 01.Yes |  | 2024-07-19 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-11 | 2025-01-06 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-11 | [15 empty] | 2025-02-11 | 2025-02-11 |  |  | 2025-02-28 | 2025-03-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-03-14 | N | 100% | 2025-03-14 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-31 | 2025-01-31 | 2025-01-31 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0453 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-02-11 | 2025-02-21 | 2025-02-11 | 2025-02-11 | [12 empty] | 2025-02-11 | 2025-02-11 |  |  | 2025-03-14 | 2025-03-21 | 2025-03-14 | [5 empty] | 2024-09-20 | 2025-01-31 |  |  | 2025-03-14 | TM |  |  | 1 | 08. Not Applicable | 2042 | [10 empty] | 2025-01-31 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1722 | LOGE0450_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Custom BRF+ and enhancement to populate the commodity code in the FU creation at Item level. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2368CD39-3EE5-4395-BBEC-48F00066A1A0%7D&file=R3_PTP_LI-030-090(120-130-150)_Commodity%20Code%20at%20FU%20Level.pptx&wdLOR=cC25DEE38-347F-4876-BB96-3167054B0AE3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-16 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-25 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-07-16 03:28 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0450 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2024-12-13 | 2024-12-13 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | [5 empty] | 2024-09-20 | 2025-04-18 |  |  | 2025-05-23 | TM |  |  | 1 |  | 2186 | [9 empty] | 01/09: FUT is IT Approved, awaiting Biz approval 8/25: 1 test case open because of a defect 2403, once defect is closed, FUT document will be sent for approval. FUT Doc walkthrough with Intel is done already. 8/18: Open defects have been fixed and currently FUT is in progress | 2025-04-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1722 | LOGE0450_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, Custom BRF+ and enhancement to populate the commodity code in the FU creation at Item level. | 06. PTP | 6.5 PTP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2368CD39-3EE5-4395-BBEC-48F00066A1A0%7D&file=R3_PTP_LI-030-090(120-130-150)_Commodity%20Code%20at%20FU%20Level.pptx&wdLOR=cC25DEE38-347F-4876-BB96-3167054B0AE3&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-16 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-11 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-01 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-25 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | jenoronha@deloitte.com | 2024-07-23 03:02 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0450_IP | 03.Medium | 0.2 | 0.2 | 0450 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2024-12-13 | 2024-12-13 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | [5 empty] | 2024-09-20 | 2025-04-18 |  |  | 2025-05-23 | TM |  |  | 1 |  | 2185 | [9 empty] | 01/09: FUT is IT Approved, awaiting Biz approval 8/25: Open defect 2362, because of which FUT is in roadblock 8/18: Open defects have been fixed and currently FUT is in progress | 2025-04-18 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 555 | LOGE0405_IP | 04.Enhancement | 01.IP - Intel Product | Dangerous Goods indicator from the delivery header text to be transmitted to the existing DG field in Freight Unit | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_IF-LOGISTICS_TM_LO-180-010-070%20TM%20Freight%20unit%20update.pptx?d=w587ee231aec14479ba5111d76203179a&csf=1&web=1&e=wWnnJQ | 02.No | 01.Yes |  | 2024-06-21 | Dan Mahoney | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-09 | 2024-08-19 | 2024-08-19 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-26 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-01-17 | 2025-01-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-01-31 | N | 100% | 2025-01-21 | Not Applicable | R3 Build & UT Sprint 9 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0405 |  | R3 ITC1 | [6 empty] | 2024-08-09 | 2024-08-16 | 2024-08-09 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-01-21 | 2025-03-21 | 2025-01-21 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-02-28 | TM |  |  | 1 | 08. Not Applicable | 1681 | [7 empty] | 2. At Risk | 17. FUT In progress |  | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 555 | LOGE0405_IF | 04.Enhancement | 02.IF - Intel Foundry | Dangerous Goods indicator from the delivery header text to be transmitted to the existing DG field in Freight Unit | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_IF-LOGISTICS_TM_LO-180-010-070%20TM%20Freight%20unit%20update.pptx?d=w587ee231aec14479ba5111d76203179a&csf=1&web=1&e=wWnnJQ | 02.No | 01.Yes |  | 2024-06-21 | Dan Mahoney | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-09 | 2024-08-19 | 2024-08-19 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-26 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-26 | [15 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-01-17 | 2025-01-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-01-31 | N | 100% | 2025-01-21 | Not Applicable | R3 Build & UT Sprint 9 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | LOGE0405_IP | 03.Medium | 0.2 | 0.2 | 0405 |  | R3 ITC1 | [6 empty] | 2024-08-09 | 2024-08-16 | 2024-08-09 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-26 | 2025-02-26 | 2025-02-26 | 2025-02-26 | [12 empty] | 2025-02-26 | 2025-02-26 |  |  | 2025-01-21 | 2025-03-21 | 2025-01-21 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-02-28 | TM |  |  | 1 | 08. Not Applicable | 1680 | [7 empty] | 1. On Track | 5. Object to be Cancelled |  | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-26 | 2025-02-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 728 | LOGE0403_IP | 04.Enhancement | 01.IP - Intel Product | In SAP TM, update FU and FO Transportation Cockpit w/ custom fields Purchase Org, Purchase Group, Planning & Execution Org, Planning & Execution Group.Planning Field Missing Fields, Purchase Org, Purchase Group, Planning & Execution Org, Planning & Execution Group | 08. FTS IP | 8.7 FTS IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LOGISTICS_TM_LO-180-130-050_RICEFW%20Intake%20Form.pptx?d=w94073c48d5b548efa8c0545aef083539&csf=1&web=1&e=Xocwgu | 02.No | 01.Yes |  | 2024-06-21 | Dan Mahoney | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-13 | 2024-08-19 | 2024-08-19 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-30 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-30 | [15 empty] | 2025-01-30 | 2025-01-30 |  |  | 2024-12-20 | 2024-12-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-10 | 2025-02-28 | 2024-12-20 | N | 100% | 2025-01-09 | Not Applicable | R3 Build & UT Sprint 9 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 2 | 2 | 0403 |  | R3 ITC1 | [6 empty] | 2024-08-13 | 2024-08-16 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-30 | 2025-01-31 | 2025-01-30 | 2025-01-30 | [12 empty] | 2025-01-30 | 2025-01-30 |  |  | 2025-01-09 | 2025-02-28 | 2025-01-09 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-02-28 | TM |  |  | 1 | 08. Not Applicable | 2378 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-01-31 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 728 | LOGE0403_IF | 04.Enhancement | 02.IF - Intel Foundry | In SAP TM, update FU and FO Transportation Cockpit w/ custom fields Purchase Org, Purchase Group, Planning & Execution Org, Planning & Execution Group.Planning Field Missing Fields, Purchase Org, Purchase Group, Planning & Execution Org, Planning & Execution Group | 07. FTS IF | 7.5 FTS IF - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LOGISTICS_TM_LO-180-130-050_RICEFW%20Intake%20Form.pptx?d=w94073c48d5b548efa8c0545aef083539&csf=1&web=1&e=Xocwgu | 02.No | 01.Yes |  | 2024-06-21 | Dan Mahoney | 01.Approved | 2024-06-28 | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-16 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | 2024-11-11 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | [15 empty] | 2025-01-03 | 2025-01-03 |  |  | 2024-12-13 | 2024-12-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-24 | 2025-02-14 | 2024-12-20 | N | 100% | 2025-01-24 | Not Applicable | R3 Build & UT Sprint 9 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | LOGE0403_IP | 02.High | 0.4 | 0.4 | 0403 |  | R3 ITC1 | [6 empty] | 2024-08-16 | 2024-08-16 | 2024-08-16 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-03 | 2025-01-10 | 2025-01-03 | 2025-01-03 | [12 empty] | 2025-01-03 | 2025-01-03 |  |  | 2025-01-24 | 2025-02-14 | 2025-01-24 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-02-14 | TM |  |  | 1 | 08. Not Applicable | 2377 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-10 | 2025-01-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 729 | LOGE0402 | 04.Enhancement | 01.IP - Intel Product | In SAP TM, Goods Value to be populated in the Alternate Quantity in the Freight Unit | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LO-180-010_RICEFW%20Intake%20Form_Goods%20Value.pptx?d=wc64bdca182dd4e4fa1fd539709889947&csf=1&web=1&e=8fvZtc | 02.No | 01.Yes |  | 2024-06-21 | Dan Mahoney | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-30 | 2024-08-30 | 100% | 2024-11-26 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-19 | 2024-11-11 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-19 | [15 empty] | 2025-02-19 | 2025-02-19 |  |  | 2025-01-17 | 2025-01-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-01-31 | N | 100% | 2025-01-30 | Not Applicable | R3 Build & UT Sprint 10 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-21 03:27 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0402 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-19 | 2025-02-21 | 2025-02-19 | 2025-02-19 | [12 empty] | 2025-02-19 | 2025-02-19 |  |  | 2025-01-30 | 2025-03-21 | 2025-01-30 | [5 empty] | 2024-08-30 | 2024-12-20 |  |  | 2025-02-28 | TM |  |  | 1 | 08. Not Applicable | 2379 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 788 | LOGE0341_IP | 04.Enhancement | 01.IP - Intel Product | Billing document creation to be triggered from the Output of outbound delivery | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B083102DC-CCB4-46F0-A436-CCBBBAFDDDA6%7D&file=R2_IF_OTC_Logistics_LO-170_Enhancement%20to%20create%20billing%20for%20output_RICEFW%20Intake%20Form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-18 | Randy Eck | 01.Approved | 2024-06-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | NA | NA | NA | 2024-07-01 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-22 | 2024-07-15 | 2024-07-15 | 2024-08-16 | 100% | 2024-08-14 | 2024-08-19 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | 2024-08-19 | 2024-12-20 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-03-14 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-28 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-17 02:08 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 1 | 1 | 0341 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-07-12 | 2024-12-20 |  |  | 2025-02-28 |  |  |  | 1 | 08. Not Applicable | 2356 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 39 | LOGE0281_IP | 04.Enhancement | 01.IP - Intel Product | Add custom fields Customer Window, Back Dated order fields in Freight Unit Stages Quadrant of Transportation Cockpit | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-06-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B94073C48-D5B5-48EF-A8C0-545AEF083539%7D&file=R3_IP_OTC_LOGISTICS_TM_LO-180-130-050_RICEFW%20Intake%20Form.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-08 | Randy Eck | 01.Approved | 2024-06-07 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-08-19 | 2024-08-19 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-07 | 2024-10-07 | 2024-12-20 | 2025-01-31 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-01-31 | 2025-02-14 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-07 | 2025-02-28 | 2025-02-14 | N | 100% | 2025-02-06 | Not Applicable | R3 Build & UT Sprint 10 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-08-08 03:02 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 | 2024-08-21 | 01.S4 |  |  | 0.5 | 0.5 | 0281 |  | R3 ITC1 | [6 empty] | 2024-08-14 | 2024-08-16 | 2024-08-14 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-02-06 | 2025-02-28 | 2025-02-06 | [5 empty] | 2024-08-16 | 2024-12-20 |  |  | 2025-02-14 | TM |  |  | 1 | 08. Not Applicable | 1432 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 608 | LOGE0239_IP | 04.Enhancement | 01.IP - Intel Product | Inventory Reconciliation snapshot (4C1) from 3PL WMS to SAP S/4 - Table Creation | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2024-06-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-030%20-%2010_%20Report_Interface_RICEFW%20Intake%20form.pptx?d=wa805d00e760d4db1a846630b9f93980d&csf=1&web=1&e=63rNpn | 02.No | 02.No |  | 2024-05-22 | Randy Eck | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-10 | 2024-06-21 | 2024-06-21 | 100% | 2024-07-02 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-17 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-14 | 2025-01-24 | N | 100% | 2025-01-31 | Not Applicable | R3 Build & UT Sprint 10 | 2024-09-13 | 2024-09-13 | 2024-09-13 | pgaroo@deloitte.com | 2024-05-21 03:17 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 1 | 1 | 0239 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-31 | 2025-02-14 | 2025-01-31 | [5 empty] | 2024-06-21 | 2024-09-13 |  |  | 2025-02-14 |  |  |  | 1 | 08. Not Applicable | 2307 | [10 empty] | 2024-09-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | Yes |  | No |  | No |  | 2026-02-09 | 2026-03-03 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 608 | LOGE0239_IF | 04.Enhancement | 02.IF - Intel Foundry | Inventory Reconciliation snapshot (4C1) from 3PL WMS to SAP S/4 - Table Creation | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2024-06-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_FTS_IP_LOGISTICS_L-060-030%20-%2010_%20Report_Interface_RICEFW%20Intake%20form.pptx?d=wa805d00e760d4db1a846630b9f93980d&csf=1&web=1&e=63rNpn | 02.No | 02.No | LOGI0237_IF | 2024-05-22 | Randy Eck | 01.Approved | 2024-05-31 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-10 | 2024-06-21 | 2024-06-21 | 100% | 2024-07-02 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-17 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-14 | 2025-01-24 | N | 100% | 2025-01-24 | Not Applicable | R3 Build & UT Sprint 9 | 2024-09-13 | 2024-09-13 | 2024-09-13 | pgaroo@deloitte.com | 2024-05-21 03:17 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | LOGE0239_IP | 03.Medium | 0.2 | 0.2 | 0239 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-24 | 2025-02-14 | 2025-01-24 | [5 empty] | 2024-06-21 | 2024-09-13 |  |  | 2025-02-14 |  |  |  | 1 | 08. Not Applicable | 2306 | [10 empty] | 2024-09-13 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 458 | LOGE0190_IP | 04.Enhancement | 01.IP - Intel Product | Delivery Split for STO in S/4 | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | Y | 2024-05-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0575C922-FF89-4DE9-B961-3A47CED3F2F2%7D&file=R3_FTS_IP_LOGISTICS_LO-180-030%20-%2010_%20Enhancement_RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true | 02.No | 02.No |  | 2024-05-03 | Randy Eck | 01.Approved | 2024-05-08 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-05-27 | 2024-06-14 | 2024-06-14 | 100% | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2024-08-16 | 100% | 2024-08-14 | 2024-08-19 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | 2024-08-19 | 2024-12-20 | 2025-01-10 | 100% | 2025-01-03 | [15 empty] | 2025-01-03 | 2025-01-03 |  |  | 2025-01-17 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-14 | 2025-01-24 | N | 100% | 2025-01-21 | Not Applicable | R3 Build & UT Sprint 9 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-05-03 03:09 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 01.S4 |  |  | 1 | 1 | 0190 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-18 | 2024-06-18 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 |  | 2025-01-03 | 2025-01-10 | 2025-01-03 | 2025-01-03 | [12 empty] | 2025-01-03 | 2025-01-03 |  |  | 2025-01-21 | 2025-02-14 | 2025-01-21 | [5 empty] | 2024-06-14 | 2024-12-20 |  |  | 2025-02-14 |  |  |  | 1 | 08. Not Applicable | 2828 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-10 | 2025-01-03 | Yes |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 458 | LOGE0190_IF | 04.Enhancement | 02.IF - Intel Foundry | Delivery Split for STO in S/4 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | Y | 2024-05-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0575C922-FF89-4DE9-B961-3A47CED3F2F2%7D&file=R3_FTS_IP_LOGISTICS_LO-180-030%20-%2010_%20Enhancement_RICEFW%20Intake%20form.pptx&action=edit&mobileredirect=true | 02.No | 02.No |  | 2024-05-17 | Randy Eck | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-05-20 | 2024-06-14 | 2024-06-14 | 100% | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-12-20 | 2025-01-31 | 100% | 2025-02-03 | 2024-08-14 | 2024-12-20 | 2025-01-31 | 100% | 2025-02-03 | [15 empty] | 2025-02-03 | 2025-02-03 |  |  | 2025-04-11 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-04-18 | N | 100% | 2025-04-02 | Not Applicable | R3 Build & UT Sprint 12 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-05-17 06:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | LOGE0190_IP | 03.Medium | 0.2 | 0.2 | 0190 |  | R3 ITC1 | [6 empty] | 2024-06-17 | 2024-06-17 | 2024-06-17 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2025-02-03 | 2025-02-03 | 2025-02-03 | 2025-02-03 | [12 empty] | 2025-02-03 | 2025-02-03 |  |  | 2025-04-02 | 2025-04-18 | 2025-04-02 | [5 empty] | 2024-06-14 | 2024-12-20 |  |  | 2025-03-07 |  |  |  | 1 | 08. Not Applicable | 2827 | [10 empty] | 2024-12-20 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-03 | 2025-02-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 70 | LOGE0065_IP | 04.Enhancement | 01.IP - Intel Product | Create single line delivery for a confirmed sales order confirmed schedule line | 05. OTC IP | 5.10 OTC IP - Logistics Management Outbound | 10. Object Complete | Y | 2024-04-16 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/LO-180-170_IF_OTC_Split%20delivery.pdf?csf=1&web=1&e=JWdNmb | 02.No | 01.Yes |  | 2024-04-15 | Shelly Lafree | 01.Approved | 2024-04-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-05-27 | 2024-06-10 | 2024-06-10 | 100% | 2024-06-07 | 2024-06-11 | 2024-06-11 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-09-10 | 2024-09-10 | 100% | 2024-11-26 | 2024-08-14 | 2024-09-10 | 2024-09-10 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-08 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-14 | 2024-11-15 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-09-10 | 2024-09-10 | 2024-09-10 | pgaroo@deloitte.com | 2024-04-15 04:19 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0065 |  | R3 ITC1 | [6 empty] | 2024-06-07 | 2024-06-10 | 2024-06-07 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2025-02-14 | 2024-11-26 | [5 empty] | 2024-06-10 | 2024-09-10 |  |  | 2025-02-14 |  |  |  | 1 | 08. Not Applicable | 1479 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-09-10 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 555 | LOGE0064_IP | 04.Enhancement | 01.IP - Intel Product | Add custom fields Customer Window, Back Dated order fields(And its date change) in Freight Unit Document | 05. OTC IP | 5.12 OTC IP - TM | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_IF-LOGISTICS_TM_LO-180-010-070%20TM%20Freight%20unit%20update.pptx?d=w587ee231aec14479ba5111d76203179a&csf=1&web=1&e=wWnnJQ | 02.No | 01.Yes |  | 2024-07-05 | Dan Mahoney | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-09 | 2024-08-19 | 2024-08-19 | 2025-02-14 | 100% | 2025-02-09 | 2024-09-16 | 2024-11-08 | 2025-02-28 | 100% | 2025-02-09 | 2024-09-16 | 2024-11-08 | 2025-02-28 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 |  |  | 2024-11-29 | 2024-12-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-07 | 2025-03-28 | 2024-12-13 | N | 100% | 2025-01-24 | Not Applicable | R3 Build & UT Sprint 9 | 2024-11-08 | 2024-11-08 | 2024-11-08 | pgaroo@deloitte.com | 2024-07-05 01:42 | jenoronha@deloitte.com | 2026-03-10 22:06 | 10 |  | 01.S4 |  |  | 1 | 1 | 0064 |  | R3 ITC1 | [6 empty] | 2024-08-09 | 2024-08-16 | 2024-08-09 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-02-09 | 2025-02-28 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-01-24 | 2025-03-28 | 2025-01-24 | [5 empty] | 2024-08-16 | 2024-11-08 |  |  | 2025-02-14 | TM |  |  | 1 | 08. Not Applicable | 1682 | [10 empty] | 2024-11-08 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-28 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3002 | LOGC1500 | 03.Conversion | 01.IP - Intel Product | IM Stock conversion from Non SAP system to S4 system | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/16.%20Logistics%20(LE+TM+EWM)/Conversions/3002-IM%20Stock%20conversion%20from%20Non%20SAP%20system%20to%20S4%20system.pptx?d=w0291666117994a4682245cc792c697b2&csf=1&web=1&e=U8kGcY |  |  |  | 2025-06-10 | Jorge Sanchez | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-12 | 2025-08-13 | 100% | 2025-08-01 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-18 | 2025-09-22 | 2025-09-24 | 2025-09-24 | 100% | 2025-10-03 | 2025-09-25 | 2025-10-20 | 2025-10-20 | 100% | 2025-10-14 | [15 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-12 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-19 | 2026-01-07 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-10-20 | 2025-10-20 | 2025-10-20 | jenoronha@deloitte.com | 2025-06-09 06:12 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2025-06-17 | 01.S4 |  |  | 2 | 2.9 | 1500 |  | R3 ITC1 | [6 empty] | 2025-08-01 | 2025-08-13 | 2025-08-01 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-14 | [12 empty] | 2025-10-14 | 2025-10-14 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-08-12 | 2025-10-20 |  |  | 2025-12-19 |  |  |  | 1 |  | 3086 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Following up with business for approval. 12/22: Following up with business for approval. 12.15: Fut in progress we are resolving the issues faced by bods team target loading of materials by today | 2025-10-20 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-20 | 2025-10-14 | Yes |  | No |  | Yes | Regression Testing | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2891 | LOGC1313 | 03.Conversion | 01.IP - Intel Product | Conversion of stock upload program | 05. OTC IP | 5.8 OTC IP - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/6%20Detail%20Design%20Workshops/IP_Returns/Filled%20RICEFW%20Template/R3_IP_Returns_Conversion%20Stock%20upload.pptx?d=wc73b55544cbd4a919b3e5a65a438d008&csf=1&web=1&e=o7UA75 | 02.No | 01.Yes |  | 2025-03-10 | shelly.lafree@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-18 | 2025-09-15 | 2025-09-17 | 2025-09-24 | 100% | 2025-09-25 | 2025-09-19 | 2025-10-10 | 2025-11-05 | 100% | 2025-11-07 | [15 empty] | 2025-11-07 | 2025-11-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2025-03-07 08:15 | cell-link@smartsheet.com | 2026-03-20 07:35 | 10 | 2025-03-10 | 01.S4 |  |  | 1 | 1.45 | 1313 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-11-07 | [12 empty] | 2025-11-07 | 2025-11-07 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-07-11 | 2025-10-10 |  |  | 2025-12-05 | TM |  |  | 1 |  | 2283 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: FUT approved by Intel IT . Waiting for PS approval. 11/24:on track, plan to send the FUT by 11/28. 11/18: FUT is in progress TC-3/10 Completed 11/14: FUT is in progress | 2025-10-10 | N | 99. Logistics | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | Yes | Change in XREF file https://intel.sharepoint.com/:x:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/05.%20OTC%20-%20Intel%20Products/4%20Working%20Documents/IP%20Returns-EWM/FS%20Drafts%20-%20OTC%20IP%20Returns%20EWM/LOGC1313_Stock_Conversion/Conversion%20mapping%20sheet.xlsx?d=w8567af74b97c4b26b8a30c8ef0391c5c&csf=1&web=1&e=QgASTn | No |  | Yes | Regression Testing | 2026-02-16 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-13 | 2026-02-27 | 2026-03-20 | 100% | 04. Completed | 100% | 06. Cancelled
01. IAO ERP | 03.R3 | 2447 | LOGC0972_IP | 03.Conversion | 01.IP - Intel Product | Open Inventory Conversion for IP and IF (as applicable) , Batch Characteristics Upload program | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-25 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-20 | 2025-07-29 | 100% | 2025-08-01 | 2025-06-23 | 2025-08-15 | 2025-08-29 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-14 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-11-21 | 2025-11-21 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-12-04 07:15 | cell-link@smartsheet.com | 2026-03-18 10:41 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0972 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-05 | [12 empty] | 2025-09-05 | 2025-09-05 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-30 | 2025-05-16 |  |  | 2025-09-12 |  |  |  | 1 |  | 2417 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Reminders and follow ups in progress for approval. 12/22: Open comments addressed and following with buisness. 2 commodity approval recieved. 12/15: One commodity (Bailed material inventory) is pending. Call has been scheduled for that. FUT is in progress. 12/8: TUT is in progress for the CR CR0969. Test data has been provided for feq commodities and rest of the commodities test data will be provided. 12/01: Working closely with BODS team for development completion. ETA 12/10 for development completion. 11/24:Extraction logic changed for all conversion object. Working with BODS team and development started. ETA 12/03 11/18: FDS has been drafted and sent for business 11/14: Extraction logic changed for all conversion logic. FS update in progress. 10/10: This was incorrectly planned. The FUT is planned for S19. | 2025-08-15 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | Yes |  | No |  | Yes | Regression Testing | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2447 | LOGC0972_IF | 03.Conversion | 02.IF - Intel Foundry | Open Inventory Conversion for IP and IF (as applicable) , Batch Characteristics Upload program | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-23 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-24 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-12-04 07:15 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-12 | 01.S4 | LOGC0972_IP | 02.High | 0.6 | 0.87 | 0972 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-05-30 | 2025-05-16 |  |  | 2025-07-31 |  | WIINGS Only | TRUE | 1 |  | 2416 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/31: Still waiting Intel approval 10/24 - Awaiting approval 10/10: ECC Batch master Load is in progress. Data validation will be done post load of data in S/4. | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | Yes |  | No |  | Yes | Regression Testing |  |  | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed |  | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 03.R3 | 2447 | LOGC0971 | 03.Conversion | 08.EWM | Open Inventory Conversion for IP and IF (as applicable) , WIINGs to EWM | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-11 | 2025-07-07 | 2025-07-20 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-28 | 2025-09-12 | 2025-10-24 | 100% | 2025-10-29 | [15 empty] | 2025-10-29 | 2025-10-29 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-12-04 07:15 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0971 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-20 |  |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-10-29 | [12 empty] | 2025-10-29 | 2025-10-29 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-06-20 | 2025-09-12 |  |  | 2025-12-05 | TM | WIINGS Only | TRUE | 1 |  | 2418 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 12/01: Awaiting business review and approval. For batch- legacy batch logic connected with LE team. Logic to be discussed with BODs team, call set up for 12/02 11/24: Sent for Intel approval on 11/18 post feedback. Awaiting approval. One batch topic is open- Mayank is closely working with FTS LE deloitte team 11/18: Biz has requested to use different set of data, redocumenting FUT.. 11/11: Documentation in progress. ETA to submit to business for approval is Tuesday 11-Nov. | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-29 | 2025-10-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2447 | LOGC0970 | 03.Conversion | 08.EWM | Open Inventory Conversion for IP and IF (as applicable) , ECC/WM to EWM | 07. FTS IF | 7.4 FTS IF - EWM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-06-20 | 2025-06-11 | 100% | 2025-06-11 | 2025-07-07 | 2025-07-20 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-28 | 2025-09-12 | 2025-10-24 | 100% | 2025-10-29 | [15 empty] | 2025-10-29 | 2025-10-29 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-20 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-12-04 07:15 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0970 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-20 |  |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-10-29 | [12 empty] | 2025-10-29 | 2025-10-29 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-06-20 | 2025-09-12 |  |  | 2025-12-05 | TM | WIINGS Only | TRUE | 1 |  | 2422 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/01: Awaiting business review and approval. For batch- legacy batch logic connected with LE team. Logic to be discussed with BODs team, call set up for 12/02 11/24: Sent for intel approval on 11/22. Awaiting approval/review comments.Mayank is closely working with FTS LE deloitte team 11/18: Biz has requested to use different set of data, redocumenting FUT. 11/11: Documentation in progress. ETA to submit to business for approval is Wednesday 12-Nov | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-29 | 2025-10-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2447 | LOGC0946_IP | 03.Conversion | 01.IP - Intel Product | Open Inventory Conversion for IP and IF (as applicable) , ECC to S4 | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-23 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-24 | 2025-09-12 | 2025-10-10 | 100% | 2025-10-10 | [15 empty] | 2025-10-10 | 2025-10-10 |  |  | 2025-11-14 | 2025-11-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-21 | 2025-11-21 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:31 | cell-link@smartsheet.com | 2026-03-10 08:12 | 10 | 2024-12-12 | 01.S4 |  |  | 2 | 2.9 | 0946 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-10-10 | [12 empty] | 2025-10-10 | 2025-10-10 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-05-30 | 2025-06-06 |  |  | 2025-07-25 |  |  |  | 1 |  | 2421 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Reminders and follow ups in progress for approval. . 12/22:Open comments addressed and following with buisness. 12/15: One commodity (Bailed material inventory) is pending. Call has been scheduled for that. FUT is in progress. 12/8: TUT is in progress for the CR CR0969. Test data has been provided for feq commodities and rest of the commodities test data will be provided. 12/01: Working closely with BODS team for development completion. ETA 12/10 for development completion. 11/24:Extraction logic changed for all conversion object. Working with BODS team and development started. ETA 12/03 11/18: FDS has been drafted and sent for business 11/14: Extraction logic changed for all conversion logic. FS update in progress. 10/10: This was incorrectly planned. The FUT is planned for S19. | 2025-09-12 | N | 99. Logistics | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-10 | Yes |  | No |  | Yes | Regression Testing | 2026-03-09 | 2026-04-08 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2447 | LOGC0946_IF | 03.Conversion | 02.IF - Intel Foundry | Open Inventory Conversion for IP and IF (as applicable) , ECC to S4 | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2447%20-%20R3_FTS_IP_LOGISTICS_L-040_180_Inventory_Conversion_%20RICEFW%20Intake%20form.pptx?d=w5d251314b85946418385795863aae9a9&csf=1&web=1&e=hZh77H | 02.No | 01.Yes |  | 2024-12-03 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-04-25 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-23 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-24 | 2025-09-12 | 2025-11-14 | 100% | 2025-11-12 | [15 empty] | 2025-11-12 | 2025-11-12 |  |  | 2025-11-14 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:31 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-12 | 01.S4 | LOGC0946_IP | 02.High | 0.6 | 0.87 | 0946 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-11-12 | [12 empty] | 2025-11-12 | 2025-11-12 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-05-30 | 2025-05-16 |  |  | 2025-07-18 |  | WIINGS Only | TRUE | 1 |  | 2420 | [7 empty] | 3. Off Track | 17. FUT In progress | 1/20 Following for PS approval from Greame. 1/16: Recieved IT approval and awaiting PS approval. 01/05:01/05: Reminders and follow ups in progress for approval. Walkthrough call scheduled 01/05. 12/22: BODS development in progress and provided ETA 12/24 12/15: One commodity (Bailed material inventory) is pending. Call has been scheduled for that. FUT is in progress. 12/8: TUT is in progress for the CR CR0969. Test data has been provided for feq commodities and rest of the commodities test data will be provided. 12/01: Working closely with BODS team for development completion. ETA 12/10 for development completion. 11/24:Extraction logic changed for all conversion object. Working with BODS team and development started. ETA 12/03 11/18: FDS has been drafted and sent for business 11/14: Extraction logic changed for all conversion logic. FS update in progress. 10/10: This was incorrectly planned. The FUT is planned for S19. | 2025-09-12 | N | 99. Logistics | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-11-14 | 2025-11-12 | Yes |  | No |  | Yes | Regression Testing |  |  | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-10 | 100% | 04. Completed | 100% | 04. Completed |  | 5. New WIINGS since Oct 25 Paid with CR
01. IAO ERP | 04.R4 | 2923 | FTSW1372 | 06.Workflow | 02.IF - Intel Foundry | Factory Portal - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT)​) Workflow for check in reminder | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 03. FS Not Started | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 |  | 0% | 2025-08-13 | 2025-10-22 | 2025-10-29 |  | 0% | 2025-10-29 | 2025-11-05 | 2025-12-03 |  | 0% | 2025-12-03 | 2025-11-05 | 2025-12-03 |  | 0% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 | [14 empty] | 2025-12-08 | 2026-01-07 |  | Y | 0% | 2026-01-07 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 3 | 2025-05-20 | 01.S4 |  |  | 1 | 1.05 | 1372 | INT-CR0870 | R4 ITC1 | [7 empty] | 2025-08-13 |  |  |  | 2025-10-29 |  |  |  | 2025-12-03 | [19 empty] | 2026-01-07 | [6 empty] | 2025-08-13 | 2025-12-03 |  |  | 2026-01-07 |  | WIINGS Only eDFIT | TRUE | 0 |  | 2914 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  | 2025-12-03 | N | 07. FTS IF | eDFIT | [7 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-03 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2950 | FTSR1466 | 01.Report | 02.IF - Intel Foundry | Custom ABAP report for SIMS PO Exceptions​ | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2950_FTS_IF_Custom%20ABAP%20report%20for%20SIMS%20PO%20Exceptions%E2%80%8B.pptx?d=weff6fae0405d4a61898185d8242f111d&csf=1&web=1&e=EZniRE | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-18 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-19 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 0.85 | 1466 | INT-CR0597 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-09-05 | 2025-10-10 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-11-05 |  |  |  | 0 |  | 3053 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 11/14: Awaiting approval from Intel ETA 11/18 | 2025-10-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2923 | FTSR1364 | 01.Report | 02.IF - Intel Foundry | Factory Portal - Warranty Claim (Warranty Dashboard​​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-16 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-31 | [15 empty] | 2026-01-31 | 2026-01-31 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-05 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 2 | 1.7 | 1364 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | [12 empty] | 2026-01-31 | 2026-01-31 |  |  | 2026-01-05 | 2026-01-07 | 2026-01-05 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-07 |  | WIINGS Only | TRUE | 0 |  | 2904 |  |  | WIINGS |  |  |  |  | 4. Completed | 17. FUT In progress | 12/23 - FUT Review planned today with Intel. 12/19 : FUT in progress | 2025-12-05 | N | 07. FTS IF | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-01-31 | 2026-01-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2578 | FTSR1011 | 01.Report | 02.IF - Intel Foundry | Report- Custom Fiori report to show full parts tracking status dashboard (workbench reporting) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-12 | 2025-06-06 | 2025-06-13 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-04 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-05 | 2025-08-13 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | vasamohan@deloitte.com | 2024-12-16 13:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 2 | 1.7 | 1011 |  | R3 ITC1 | [6 empty] | 2025-03-12 | 2025-03-21 | 2025-03-12 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-11-14 |  | WIINGS Only | TRUE | 0 |  | 2152 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 10/31:Dev fixed the issue: Working on the Open issue in the fixed defects | 2025-07-18 | N | 07. FTS IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2515 | FTSM0986 | 12.Manual Conversion | 02.IF - Intel Foundry | Convert Equipment Warranty information to SAP S/4 Equipment Master – reusable mass upload | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High | [6 empty] | NA | 2025-02-03 | 2025-03-21 | 2025-06-11 | 100% | 2025-06-05 |  |  |  | 0% |  | 2025-05-09 | 2025-05-16 |  | 0% | 2025-05-16 | 2025-05-30 | 2025-06-29 |  | 0% | 2025-06-29 | [15 empty] | 2025-06-29 | 2025-06-29 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-06-30 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-29 | 2025-06-29 | 2025-06-29 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 2 | 0 | 0986 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-11 | 2025-06-05 | [6 empty] | 2025-05-16 | [18 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-03-21 | 2025-06-29 |  |  | 2025-07-18 |  | WIINGS Only | TRUE | 0 |  | 1769 | [10 empty] | 2025-06-29 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-06-29 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 |  | FTSM019 | 12.Manual Conversion | 02.IF - Intel Foundry | Conversion of Inflight Work Orders | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N | [8 empty] | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | N/A |  | 01.Yes |  | ME, XEUS, MARS |  |  | NA | 2025-01-08 | 2025-02-21 | 2025-06-06 | 100% | 2025-06-05 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-05-19 | 2025-06-06 |  | 0% | 2025-06-06 | [13 empty] | 0% |  | 2025-06-06 | 2025-06-06 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-06-16 | 2025-06-27 | 2025-06-27 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-06 | 2025-06-06 | 2025-06-06 | anntam@deloitte.com | 2025-01-30 21:37 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 |  |  |  | 0 | M019 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-06 | 2025-06-05 | [25 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-02-21 | 2025-06-06 |  |  | 2025-06-27 |  |  |  | 0 |  | 2202 | [10 empty] | 2025-06-06 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-06 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM018 | 12.Manual Conversion | 02.IF - Intel Foundry | Conversion of General Task List | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N | [8 empty] | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | N/A |  | 01.Yes |  | ME, EMS |  |  | NA | 2024-12-19 | 2025-01-24 | 2025-01-17 | 100% | 2025-08-20 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-04-21 | 2025-05-09 |  | 0% | 2025-05-09 | [13 empty] | 0% |  | 2025-05-09 | 2025-05-09 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-05-26 | 2025-06-06 | 2025-06-06 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-09 | 2025-05-09 | 2025-05-09 | anntam@deloitte.com | 2025-01-30 21:34 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  |  | 0 | M018 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 | [25 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-01-24 | 2025-05-09 |  |  | 2025-06-06 |  | WIINGS Only | TRUE | 0 |  | 2203 |  |  | WIINGS | [7 empty] | 2025-05-09 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-05-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 |  | FTSM017_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Manual Conversion of Functional Locations (FLOC) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | 03.Medium |  | 01.Yes |  | ME, EMS |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-04-18 | 100% | 2025-08-04 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-03-31 | 2025-04-25 |  | 0% | 2025-04-25 | [13 empty] | 0% |  | 2025-04-25 | 2025-04-25 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-04-28 | 2025-05-09 | 2025-05-09 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-25 | 2025-04-25 | 2025-04-25 | miranwhite@deloitte.com | 2025-01-24 14:57 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-01-25 | 01.S4 |  |  | 1 | 0 | 017_ |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [25 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-02-21 | 2025-04-25 | [6 empty] | 0 | 08. Not Applicable | 2201 | [10 empty] | 2025-04-25 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-04-25 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM016 | 12.Manual Conversion | 02.IF - Intel Foundry | Equipment Master | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | MES, SAP ME, EMS, EDFIT, Workstream, NIT, ECM | MES, SAP ME, EMS, EDFIT, Workstream, NIT, ECM | S4 | NA | 2025-01-27 | 2025-02-21 | 2025-05-20 | 100% | 2025-08-11 | 2025-04-07 | 2025-04-07 |  | 0% | 2025-04-07 |  |  |  | 0% |  | 2025-03-31 | 2025-05-09 |  | 0% | 2025-05-09 | [13 empty] | 0% |  | 2025-05-09 | 2025-05-09 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-05-12 | 2025-05-30 | 2025-05-30 | N | 100% | 2025-08-11 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-09 | 2025-05-09 | 2025-05-09 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  |  | 0 | M016 |  | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-11 | 2025-08-11 |  |  | 2025-04-07 | [22 empty] | 2025-08-11 | 2025-08-11 | 2025-08-11 | [5 empty] | 2025-02-21 | 2025-05-09 |  |  | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 2241 | [9 empty] | 8/11: We received the complete approval. Will need to adjust past sprint activities as 100%. | 2025-05-09 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-05-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM011 | 12.Manual Conversion | 02.IF - Intel Foundry | Catalogs | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  |  | S4 | NA | 2024-12-16 | 2025-01-24 | 2025-02-07 | 100% | 2025-08-20 | 2025-03-03 | 2025-03-03 |  | 0% | 2025-03-03 |  |  |  | 0% |  | 2025-03-24 | 2025-04-11 |  | 0% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-04-14 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-04-16 | Not Applicable | R3 Build & UT Sprint 12 | 2025-04-11 | 2025-04-11 | 2025-04-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-20 | 01.S4 |  |  |  | 0 | M011 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-03-03 | [22 empty] | 2025-04-16 | 2025-04-18 | 2025-04-16 | [5 empty] | 2025-01-24 | 2025-04-11 |  |  | 2025-04-18 |  |  |  | 0 |  | 2242 | [10 empty] | 2025-04-11 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-11 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM010 | 12.Manual Conversion | 02.IF - Intel Foundry | Maintenance Plans | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | ME | ME | S4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-08-20 | 2025-03-24 | 2025-03-24 |  | 0% | 2025-03-24 |  |  |  | 0% |  | 2025-05-05 | 2025-05-23 |  | 0% | 2025-05-23 | [13 empty] | 0% |  | 2025-05-23 | 2025-05-23 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-06-02 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-23 | 2025-05-23 | 2025-05-23 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-08-20 | 01.S4 |  |  |  | 0 | M010 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-03-24 | [22 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-01-24 | 2025-05-23 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2243 | [7 empty] | 1. On Track | 13. Blocked by Other RICEFW |  | 2025-05-23 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-23 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM009 | 12.Manual Conversion | 02.IF - Intel Foundry | Maintenance Items | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | NA | S4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-08-20 | 2025-03-24 | 2025-03-24 |  | 0% | 2025-03-24 |  |  |  | 0% |  | 2025-05-05 | 2025-05-23 |  | 0% | 2025-05-23 | [15 empty] | 2025-05-23 | 2025-05-23 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-06-02 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-23 | 2025-05-23 | 2025-05-23 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | M009 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-03-24 | [22 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-01-24 | 2025-05-23 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2216 | [7 empty] | 1. On Track | 13. Blocked by Other RICEFW |  | 2025-05-23 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-23 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM008 | 12.Manual Conversion | 02.IF - Intel Foundry | Equipment Class | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | NA | S4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-10 | 100% | 2025-08-20 | 2025-02-17 | 2025-02-17 |  | 0% | 2025-02-17 |  |  |  | 0% |  | 2025-03-24 | 2025-04-11 |  | 0% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-04-14 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-04-17 | Not Applicable | R3 Build & UT Sprint 12 | 2025-04-11 | 2025-04-11 | 2025-04-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | M008 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-02-17 | [22 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 | [5 empty] | 2025-01-24 | 2025-04-11 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2271 | [10 empty] | 2025-04-11 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-11 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM007 | 12.Manual Conversion | 02.IF - Intel Foundry | Characteristics | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | NA | S4 | NA | 2024-12-16 | 2025-01-24 | 2025-01-10 | 100% | 2025-08-20 | 2025-02-17 | 2025-02-17 |  | 0% | 2025-02-17 |  |  |  | 0% |  | 2025-03-24 | 2025-04-11 |  | 0% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-04-14 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-04-17 | Not Applicable | R3 Build & UT Sprint 12 | 2025-04-11 | 2025-04-11 | 2025-04-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | M007 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-02-17 | [22 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 | [5 empty] | 2025-01-24 | 2025-04-11 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2254 | [10 empty] | 2025-04-11 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-11 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM002_IP | 12.Manual Conversion | 01.IP - Intel Product | Work Center | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  | 2024-11-19 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | NA | S4 | NA | 2024-11-18 | 2024-12-13 | 2025-03-21 | 100% | 2025-02-27 | 2025-01-27 | 2025-03-21 |  | 0% | 2025-03-21 |  |  |  | 0% |  | 2024-11-18 | 2024-12-13 |  | 0% | 2024-12-13 | [15 empty] | 2024-12-13 | 2024-12-13 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2024-12-13 | 2025-01-13 | 2025-03-21 | N | 100% | 2025-02-27 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-13 | 2024-12-13 | 2024-12-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | 002_ |  | R3 ITC1 | [6 empty] | 2025-02-27 | 2025-03-21 | 2025-02-27 |  |  | 2025-03-21 | [22 empty] | 2025-02-27 | 2025-03-21 | 2025-02-27 | [5 empty] | 2024-12-13 | 2024-12-13 |  |  | 2025-01-13 |  |  |  | 0 | 08. Not Applicable | 2230 | [10 empty] | 2024-12-13 | N | 08. FTS IP | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-13 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FTSM002_IF | 12.Manual Conversion | 02.IF - Intel Foundry | Work Center | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 01.Yes |  | ME | Fuzion, ME, Manual | S4 | NA | 2024-11-25 | 2025-01-03 | 2025-01-10 | 100% | 2025-08-20 | 2025-02-17 | 2025-02-17 |  | 0% | 2025-02-17 |  |  |  | 0% |  | 2025-03-24 | 2025-04-11 |  | 0% | 2025-04-11 | [13 empty] | 0% |  | 2025-04-11 | 2025-04-11 | [7 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-04-21 | 2025-05-02 | 2025-05-02 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-11 | 2025-04-11 | 2025-04-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  |  | 0 | 002_ |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-02-17 | [22 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-01-03 | 2025-04-11 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 2229 | [10 empty] | 2025-04-11 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-11 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1702 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer Vendor details from S4 to DMRA on a daily basis | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-10-24 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT |  |  |  | 0% |  |  |  |  | 0% |  | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  | 2025-12-05 | 2025-12-05 | [17 empty] | N | 0% |  | Not Applicable |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-24 05:06 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 |  | 01.S4 |  |  | 1 | 1.45 | 1702 |  | R4 ITC1 | [15 empty] | 2025-12-05 | [27 empty] | 2025-12-05 | [6 empty] | 0 |  | 3338 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | Y | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3177 | FTSI1693 | 02.Interface | 01.IP - Intel Product | Interface for Reporting Scrap of Semi Finished Goods at OSAT and IF manufacturing location | 08. FTS IP | 8.5 FTS IP - Manufacturing | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3177_Reporting%20Scrap%20of%20Semi%20Finished%20Goods%20at%20OSAT%20and%20IF%20manufacturing%20location.pptx?d=w3645387ed1bc4344b373f48322c1c764&csf=1&web=1&e=2Y8jCb | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | BODS | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-12 | 2026-02-09 | 2026-02-27 | 2026-03-31 | 96% | 2026-03-31 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-05 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-02-16 | 2026-02-27 | 2026-03-31 | 95% | 2026-03-31 | 2026-02-23 | 2026-02-27 | 2026-03-31 | 95% | 2026-03-31 | [5 empty] | 2026-03-31 | 2026-03-31 |  |  | 2026-03-31 | 2026-03-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-31 | N | 100% | 2026-04-02 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-05 05:23 | cell-link@smartsheet.com | 2026-04-02 08:33 | 6 | 2025-11-20 | 01.S4 |  |  | 1 | 1.45 | 1693 | INT-CR1362 | R3 ITC1 | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 |  |  | 2026-03-31 | 2026-03-27 | 2026-02-05 | 2026-02-05 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-03-31 |  |  |  | 2026-03-31 | 2026-03-27 | [5 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | [5 empty] | 2026-01-07 | 2026-02-06 | 2026-02-27 |  | 2026-03-04 |  |  |  | 0 |  | 3376 | [7 empty] | 1. On Track | 17. FUT In progress | 03/27 : BODS Dev is completed on 03/25 and FUT is in Progress. 03/20 : BODS Dev in WIP for CR 03/13 : Dev in WIP with New CR INT-CR1739 03/05 - Design change CR - BODS will not be used for this and will be changed to File based interface. 02/20 : Off track and will be spill over to S24. | 2026-02-27 | Y | 08. FTS IP |  |  |  | 03/23: CR for change in the mode of data transfer via BODS was approved. MW build is in progress. Build ETA 03/27 Current status: S4 FUT complete. MW build is in progress. Issue: FUT on HOLD. Change in the data transfer approach as per GPO/IT leads direction. Next steps: Complete build and FUT Help needed: n/a FUT ETA: 04/03 | Potential Spill over due to CR |  | On track for S23+ | FUT In Progress | Complete | R3 Build & UT Sprint 23+ |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3177 | FTSI1692 | 02.Interface | 01.IP - Intel Product | Interface for Reporting Scrap of Semi Finished Goods at OSAT and IF manufacturing location | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3177_Reporting%20Scrap%20of%20Semi%20Finished%20Goods%20at%20OSAT%20and%20IF%20manufacturing%20location.pptx?d=w3645387ed1bc4344b373f48322c1c764&csf=1&web=1&e=2Y8jCb | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 59283 | PDF Sapience Manufacturing Hub Integration Platform - IP |  |  | APIGEE | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2025-12-09 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 100% | 2026-02-04 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-04 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-13 | 2025-12-01 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2026-01-26 | 2026-01-26 |  |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-26 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-05 05:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1.45 | 1692 | INT-CR1362 | R3 ITC1 | [6 empty] | 2025-12-09 | 2026-01-07 | 2025-12-09 |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-06 |  | 2026-02-04 |  | 2026-02-06 | 2026-01-13 | 2026-01-13 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-26 | 2026-01-26 |  | 2026-02-26 | 2026-02-26 | 2026-03-04 | 2026-02-26 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2026-01-07 | 2026-02-06 | 2026-02-06 |  | 2026-03-04 |  |  |  | 0 |  | 3375 | [7 empty] | 4. Completed | 17. FUT In progress | 2/23 -Testing with PDF SMH planned on 2/24. 02/20 : E2E FUT is planned on 02/24 and ETA 02/27 | 2026-02-06 | N | 08. FTS IP |  |  |  | 02/23: FUT walkthru scheduled in W9 Current status:FUT walkthru scheduled in W9 Issue: n/a Next steps: Complete walkthru and send for approval Help needed: n/a FUT ETA: 02/27 | Week 3 Target | 3. Watch item | 4. PDF SMH S23 | BA Readiness | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3148 | FTSI1681 | 02.Interface | 01.IP - Intel Product | Enhancement to create Zero Lead Time Order to convert Sorted Wafers into Sorted Dies to consume against Assembly order using DLCP & Non-DLCP scenarios.​ | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3148_Enhancement%20to%20create%20Zero%20Lead%20Time%20Order%20to%20convert%20Sorted%20Wafers%20into%20Sorted%20Dies%20to%20consume%20against%20Assembly%20order%20using%20DLCP%20%26%20Non-DLCP%20scenarios.%E2%80%8B.pptx?d=we08dd1d5432a47a5b2cdf5085e478916&csf=1&web=1&e=LXccrD | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 59283 | PDF Sapience Manufacturing Hub Integration Platform - IP |  |  | MULESOFT | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-08 | 2026-01-12 | 2026-02-04 | 2026-02-04 | 100% | 2026-02-04 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-04 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-04 | 2025-12-01 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2026-02-04 | 2026-02-04 |  |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-20 | N | 100% | 2026-03-24 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 04:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1681 | INT-CR1198 | R3 ITC1 | [5 empty] | 2026-01-08 | 2026-01-08 | 2025-12-19 | 2025-12-19 |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-06 |  | 2026-02-04 |  | 2026-02-06 | 2026-02-04 | 2026-02-04 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-04 | 2026-02-04 |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-12-05 | 2026-02-06 | 2026-02-06 |  | 2026-03-04 |  |  |  | 0 |  | 3364 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 03/20 : FUT sent for approval and awaiting for approval ETA 03/23 03/13 - SMH team Build is still in progress. Spill over object and ETA 03/19 2/26 - E2E FUT planned on 03/03. S/4 FUT Completed. 02/23 : S/4 FUT completed. PDF SMH planned next week. | 2026-02-06 | N | 08. FTS IP |  |  |  | 03/23 - FUT approved. SS will be updated today. | Week 3 Target |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3136 | FTSI1680 | 02.Interface | 02.IF - Intel Foundry | An interface from Prospal to create lot level STO in S4 for the straddle solution from Non-S4 to S4 sites An interface from Synergy to create lot level STO in S4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3136_An%20interface%20from%20Prospal%20to%20create%20lot%20level%20STO%20in%20S4%20for%20the%20straddle%20solution%20from%20Non-S4%20to%20S4%20sites.pptx?d=w0d5965a83b2741728adec429e94ee0fb&csf=1&web=1&e=HnGQkp | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 12630; 16134 | Prospal-Product Shipment Planning and Logistics; Global Master Production Control aka Synergy |  |  | APIGEE | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-08 | 2025-12-08 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-04 | 2026-02-02 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-04 | 2026-02-09 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | 2026-02-04 | 2026-02-27 | No |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-02-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-04 04:16 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 1.45 | 1680 | INT-CR1155 | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-12-03 | 2025-11-17 | 2026-01-12 | 2026-01-12 | 2026-02-04 | 2026-02-03 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-06 |  | 2026-02-04 |  | 2026-02-06 | 2026-02-04 | 2026-02-04 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-04 | 2026-02-27 |  | 2026-02-20 | 2026-02-20 | 2026-03-06 | 2026-02-20 |  |  |  |  | WIP Inventory Shipping | 2025-12-03 | 2026-02-06 | 2026-02-06 |  | 2026-03-06 |  |  |  | 0 |  | 3362 | [7 empty] | 4. Completed | 3. Awaiting Approval | 2/13: awaiting approval | 2026-02-27 | Y | 07. FTS IF |  |  |  |  | Week 2 Target |  |  |  | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1667 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer BOM details from S4 to DMRA on a daily basis | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-10-24 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT |  |  |  | 0% |  |  |  |  | 0% |  | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  | 2025-12-05 | 2025-12-05 | [17 empty] | N | 0% |  | Not Applicable |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-24 05:06 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 |  | 01.S4 |  |  | 1 | 1.45 | 1667 |  | R4 ITC1 | [15 empty] | 2025-12-05 | [27 empty] | 2025-12-05 | [6 empty] | 0 |  | 3337 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | Y | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1654 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer Material Master details from S4 to DMRA on a daily basis | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT |  |  |  | 0% |  | 2025-09-12 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 |  |  |  | 0% |  | 2025-12-05 | 2025-12-05 | [14 empty] | 2025-12-08 | 2026-01-09 |  | Y | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-08 22:58 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 | 2025-04-30 | 01.S4 |  |  | 0.5 | 0.725 | 1654 | INT-CR1475 | R4 ITC1 | [11 empty] | 2025-09-19 |  |  |  | 2025-12-05 |  |  |  | 2025-12-03 |  |  |  | 2025-12-03 | [11 empty] | 2026-01-09 | [7 empty] | 2025-12-05 | 2025-12-03 |  | 2026-01-09 |  |  |  | 0 |  | 3324 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | N | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1652 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer STO Change & Delete from S4 to DMRA on a daily basis | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT |  |  |  | 0% |  | 2025-09-12 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 |  |  |  | 0% |  | 2025-12-05 | 2025-12-05 | [14 empty] | 2025-12-08 | 2026-01-09 |  | Y | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-08 22:58 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 | 2025-04-30 | 01.S4 |  |  | 0.5 | 0.725 | 1652 | INT-CR1475 | R4 ITC1 | [11 empty] | 2025-09-19 |  |  |  | 2025-12-05 |  |  |  | 2025-12-03 |  |  |  | 2025-12-03 | [11 empty] | 2026-01-09 | [7 empty] | 2025-12-05 | 2025-12-03 |  | 2026-01-09 |  |  |  | 0 |  | 3325 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | N | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1651 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer STO details from S4 to DMRA on a daily basis - STO create | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT |  |  |  | 0% |  | 2025-09-12 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-10 | 2025-12-05 |  | 0% | 2025-12-05 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 |  |  |  | 0% |  | 2025-12-05 | 2025-12-05 | [14 empty] | 2025-12-08 | 2026-01-09 |  | Y | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-08 22:58 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 | 2025-04-30 | 01.S4 |  |  | 0.5 | 0.725 | 1651 | INT-CR1475 | R4 ITC1 | [11 empty] | 2025-09-19 |  |  |  | 2025-12-05 |  |  |  | 2025-12-03 |  |  |  | 2025-12-03 | [11 empty] | 2026-01-09 | [7 empty] | 2025-12-05 | 2025-12-03 |  | 2026-01-09 |  |  |  | 0 |  | 3323 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-05 | N | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3124 | FTSI1647 | 02.Interface | 02.IF - Intel Foundry | New Interface required from APPS/XEUS for each different site with S/4 using BODS for Material Staging | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3124_FTS-IF_Interface%20from%20APPS%20for%20Lot%20level%20Material%20Staging_WLA.pptx?d=w3a8a1a0d41c44c568668986a66009b61&csf=1&web=1&e=essnDr | 02.No | 01.Yes |  | 2025-10-22 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 32287 | FFS / APPS |  |  | BODS | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-07 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-23 | 2025-11-13 | 2026-02-26 | 2026-02-26 | 100% | 2026-02-26 | 2026-02-23 | 2026-02-26 |  |  | 2026-02-27 | 2026-03-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-09 | N | 100% | 2026-03-03 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2026-02-20 | 2026-02-26 | 2026-02-26 | jenoronha@deloitte.com | 2025-09-28 03:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-10-22 | 01.S4 |  |  | 1 | 1.45 | 1647 | INT-CR1145 | R3 ITC1 | [6 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-20 |  | 2026-01-12 | 2026-02-06 | 2026-01-12 | 2026-01-12 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-23 | 2026-02-26 |  |  | 2026-03-03 | 2026-03-09 | 2026-03-03 | [5 empty] | 2025-11-07 | 2026-02-06 | 2026-02-20 |  | 2026-02-04 |  |  |  | 0 |  | 3309 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27: Awaiting approval 2/18 - Awaiting Tech team to confirm once the build is completed. | 2026-02-26 | Y | 07. FTS IF |  |  |  | 02/23: FUT complete. Sent for approval. Current status: CR1656 build is complete. Sent for approval. Issue: n/a Next steps: Awaiting approval.. Help needed: n/a E2E ETA: 3/6 | Week 3 Target |  | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3123 | FTSI1646 | 02.Interface | 02.IF - Intel Foundry | New Interface required from FFS/MARS for each different site with S/4 using BODS for Material Staging | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3123_FTS-IF_Interface%20from%20FFS%20for%20Lot%20level%20Material%20Staging.pptx?d=w8150a7cabbbd4dffbd51468fa2a74c57&csf=1&web=1&e=cY1JZK | 02.No | 01.Yes |  | 2025-10-22 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 32287 | FFS / APPS |  |  | BODS | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-07 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-11 | 2025-11-13 | 2026-02-26 | 2026-02-26 | 100% | 2026-02-26 | 2026-02-11 | 2026-02-26 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-04 | N | 100% | 2026-03-03 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2026-02-20 | 2026-02-26 | 2026-02-26 | jenoronha@deloitte.com | 2025-09-28 03:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-10-22 | 01.S4 |  |  | 1 | 1.45 | 1646 | INT-CR1145 | R3 ITC1 | [6 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-11 |  | 2026-01-12 | 2026-02-06 | 2026-01-12 | 2026-01-12 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 | 2026-02-11 | 2026-02-11 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-11 | 2026-02-26 |  |  | 2026-03-03 | 2026-03-04 | 2026-03-03 | [5 empty] | 2025-11-07 | 2026-02-06 | 2026-02-20 |  | 2026-02-04 |  |  |  | 0 |  | 3306 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27: Awaiting approval 2/13: CR in progress from S4 side. 2/2:CR to be raised for exception 01/21: Build completed, Testing in Progress. 01/14: Replanned for S22 | 2026-02-26 | Y | 07. FTS IF |  |  |  | 02/23: FUT complete. Sent for approval. Current status: CR1656 build is complete. Sent for approval. Issue: n/a Next steps: Awaiting approval.. Help needed: n/a E2E ETA: 3/6 | Week 3 Target |  | 1 | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3104 | FTSI1631 | 02.Interface | 01.IP - Intel Product | Interface to update Remnants in production order | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3104_FTS_IP_Manufacturing_Interface%20to%20update%20Remnants%20in%20production%20order.pptx?d=wdb569af300134cb6a149e51df38ff59e&csf=1&web=1&e=3NcIRV | 02.No | 01.Yes |  | 2025-10-14 | kumar.vytla@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 59283 | PDF Sapience Manufacturing Hub Integration Platform - IP |  |  | APIGEE | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-10 | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-16 | 2025-09-29 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-22 | 2025-12-16 | 2025-12-22 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | jenoronha@deloitte.com | 2025-09-28 03:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-10-14 | 01.S4 |  |  | 1 | 1.45 | 1631 | INT-CR1108 | R3 ITC1 | [6 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2025-12-01 | 2025-12-03 | 2025-12-01 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-19 | 2025-12-16 | 2025-12-16 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-16 | 2025-12-22 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-10-08 | 2025-12-05 | 2025-12-03 |  | 2026-02-04 |  |  |  | 0 |  | 3311 | [7 empty] | 4. Completed | 17. FUT In progress | 02/02 : E2E FUT started with PDF SMH ETA 02/06. 01/21 : E2E FUT is planned in Sprint 22. 01/06 : S/4 FUT is completed and will be risk to complete by 01/09 due PDF SMH readiness. | 2025-12-19 | N | 08. FTS IP |  |  |  | 02/03 : E2E FUT in progress. MW changes are in progress. ETA is 2/6 Current state: Build complete. E2E FUT planned on 01/29 Issue: None Next steps: To conduct E2E FUT as per plan. Help needed: N/A | Testing planned in WW05 | 2. Risk | 1. PDF SMH S22 | BA Readiness | Complete | R3 Build & UT Sprint 21 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3093 | FTSI1619 | 02.Interface | 01.IP - Intel Product | Interface to capture Sales Order 3B2 ASN and Virtual 3B2 ASN signals from Intel Foundry to Intel Products | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3093_Interface%20to%20capture%20Sales%20Order%203B2%20ASN%20and%20Virtual%203B2%20ASN%20from%20Intel%20Foundry%20to%20Intel%20Products_.pptx?d=w5c4a62e08b844a93b0e5b920010dcd68&csf=1&web=1&e=3e2ASd | 02.No | 01.Yes |  | 2025-10-14 | kumar.vytla@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High |  | 01.Yes | 59283 | PDF Sapience Manufacturing Hub Integration Platform - IP |  |  | APIGEE | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-13 | 2025-09-12 | 2025-09-19 | 2025-12-03 | 100% | 2025-12-03 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-16 | 2025-10-13 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-22 | 2025-12-31 | 2025-12-31 | Yes |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-19 | 2025-12-19 | 2025-12-19 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-04-03 08:07 | 10 | 2025-10-14 | 01.S4 |  |  | 2 | 2.9 | 1619 | INT-CR0958 | R3 ITC1 | [6 empty] | 2025-10-13 | 2025-10-13 | 2025-10-13 |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-19 | 2025-12-16 | 2025-12-16 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-31 | 2025-12-31 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-10-08 | 2025-12-05 | 2025-12-03 |  | 2026-03-04 |  |  |  | 0 |  | 3271 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/05 - Conditional approval for the current design. Additional requirements to be handled through CR INT-CR1739 2/27 - Defect - 7757, 7827 WIP 02/26 : E2E testing is started with SMH team and ETA 02/04 2/23 - E2E FUT planned on 2/26. S/4 FUT in progress 02/20 : E2E FUT is planned on 02/24 and ETA 02/27 02/12 : FUT is in WIP. 01/13 : E2E FUT is planned in Sprint 23. 01/06 : S/4 FUT is in WIP and will be risk to complete by 01/09 due PDF SMH readiness.. | 2025-12-19 | N | 08. FTS IP |  |  |  | 03/04: E2E FUT in progress. Defect fix ongoing. Current status: E2E FUT in progress Issue: n/a Next steps: Expedite Defect fixes and E2E FUT completion Help needed: n/a FUT ETA: TBD | Week 3 Target | 2. Risk | 4. PDF SMH S23 | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | Yes |  | 2026-02-17 | 2026-03-27 | 2026-04-10 | 85% | Yes |  |  |  | 0% | 06. Cancelled | 0% | 06. Cancelled
01. IAO ERP | 03.R3 | 3083 | FTSI1610 | 02.Interface | 02.IF - Intel Foundry | Interface from SMH to S/4 to Transfer DP and Stack Orders from Interim Location to TRDI (Transfer Die To Reel Process) | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3083_FTS-IF_Transfer_Die_To_Reel.pptx?d=w856d3c1f45474ed09f5c78c0662bb680&csf=1&web=1&e=xNI4yj | 02.No | 01.Yes |  | 2025-09-18 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF |  |  | APIGEE | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-09-16 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-11-04 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-17 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-17 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-11-17 | 2025-09-29 | 2025-11-21 | 2025-11-21 | 100% | 2025-11-21 | 2025-11-17 | 2025-11-21 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-03 | 2025-12-03 | 2025-12-03 | jenoronha@deloitte.com | 2025-08-23 03:09 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-18 | 01.S4 |  |  | 1 | 1.45 | 1610 | INT-CR1029 | R3 ITC1 | [6 empty] | 2025-09-16 | 2025-10-10 | 2025-09-16 |  | 2025-11-04 | 2025-11-05 | 2025-11-04 |  | 2025-10-17 | 2025-11-05 | 2025-10-17 | 2025-10-17 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-03 | 2025-11-17 | 2025-11-17 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-17 | 2025-11-21 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-10-10 | 2025-10-24 | 2025-11-07 |  | 2026-02-04 |  |  |  | 0 |  | 3255 | [7 empty] | 1. On Track | 14. B-App Under Test | 2/2: Testing with SMH in progress. 01/06: Defect 5895 raised to tech team. 01/14: Replanned for S22 | 2025-12-03 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-11-05 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3010 | FTSI1602 | 02.Interface | 02.IF - Intel Foundry | Interface from SGP to S4 to get Inventory status | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3010_FTS_IF_Interface%20from%20SGP%20to%20S4%20to%20get%20inventory%20status.pptx?d=wed3a0cb460504e909ee368d90f81175f&csf=1&web=1&e=ftU3Mu | 02.No | 01.Yes |  | 2025-09-18 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 31279 | Starts Game Planner |  |  | APIGEE | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-09-16 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-10-16 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-03 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-03 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-01 | 2025-08-11 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-13 | 2025-12-01 | 2026-02-13 |  |  | 2026-01-07 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-03 | 2026-02-13 | 2026-02-13 | jenoronha@deloitte.com | 2025-08-23 03:09 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-18 | 01.S4 |  |  | 1 | 1.45 | 1602 | INT-CR0807 | R3 ITC1 | [6 empty] | 2025-09-16 | 2025-10-10 | 2025-09-16 |  | 2025-10-16 | 2025-11-05 | 2025-10-16 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-03 | 2025-12-01 | 2025-12-01 |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2025-12-01 | 2026-02-13 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-10-10 | 2025-10-24 | 2025-11-07 |  | 2026-03-04 |  |  |  | 0 |  | 3267 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27: FUT In progress 2/23:Defect # 7599 raised to make the structure changes in error response payload from MW to SGP. 2/13: FUT in progress 01/06: FUT in progress. 01/14: Replanned for S23 | 2026-02-13 | Y | 07. FTS IF |  |  |  | 03/04: Awaiting approval. Current status: Awaiting approval Next steps: N/A Help needed: N/A FUT ETA: N/A | Week 3 Target | 3. Watch item |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3037 | LOGI1584 | 02.Interface | 01.IP - Intel Product | Interface to post inventory in SAP S/4HANA from ECA via MuleSoft. | 08. FTS IP | 8.4 FTS IP - Logistics & Inventory Management | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3037_M-100-050_FTS_IP_Interface%20to%20post%20inventory%20in%20SAP%20S4HANA%20using%20a%20custom%20movement%20type%20from%20ECA%20to%20S4...pptx?d=wadbfb784923642978045a91aa6445c00&csf=1&web=1&e=CvDE2G | 02.No | 01.Yes |  | 2025-08-13 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MuleSoft | 2025-07-21 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-11 | 2025-09-12 | 2025-09-19 | 2026-04-10 | 100% | 2026-04-06 | 2025-09-26 | 2025-10-24 | 2026-04-22 | 100% | 2026-03-23 | 2025-09-26 | 2025-10-24 | 2026-04-22 | 100% | 2026-03-23 | 2026-03-02 | 2026-03-04 | 2026-04-10 | 95% | 2026-04-10 | 2026-03-02 | 2026-03-04 | 2026-04-10 | 97% | 2026-04-10 | [5 empty] | 2026-04-10 | 2026-04-10 |  | 2026-01-30 | 2026-01-31 | 2026-03-27 | 100% | 0% | 0% |  |  | 05. In Roadblock | 05. In Roadblock | 05. In Roadblock |  |  | 2026-01-12 | 2026-02-04 | 2026-03-27 | N | 0% | 2026-03-27 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-08-11 01:04 | cell-link@smartsheet.com | 2026-04-08 04:42 | 6 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1584 | INT-CR1711, INT-CR0902, INT-CR1586 | R3 ITC2 | R3 ITC2 | [5 empty] | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2026-04-06 | 2026-04-10 | 2026-04-06 |  | 2026-03-23 | 2026-04-22 | 2026-03-23 | 2026-03-23 |  | 2026-04-10 |  |  |  | 2026-04-10 | [6 empty] | 2026-03-23 | 2026-03-23 |  |  |  | 2026-03-27 | [6 empty] | 2025-09-10 | 2025-10-24 | 2026-03-04 |  | 2026-02-04 |  |  |  | 1 |  | 3236 | [7 empty] | 1. On Track | 24. Incorrect plan | 04/03: Following for FS approval. 2/23 - CR not approved yet 1/21 -CR raised for descoping 12/18 : Object is to be descoped 12/12 : Object is marked for ITC2 due ECA readiness. | 2026-03-04 | Y | 99. Logistics |  |  |  | 03/23: CR1711 approved for the Logistics team to take over the FTSI1584 object. It was approved as an exception. Final FUT date is 4/24 |  |  | Approved Exception (ITC2) | Incorrect plan | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-04-22 | 2026-03-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3064 | FTSI1580 | 02.Interface | 02.IF - Intel Foundry | Interface between SMH to S/4 to Trigger UNDO START event, which will Reverse the Component Consumption of previous stage and Technically Complete Production Order | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9aa20245-b46f-4b13-beec-16eb7c996d4e%7D&action=edit&wdPreviousSession=3789b989-4be9-329d-775d-38445bcd0362 | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF |  |  | APIGEE | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-19 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-25 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-09-15 | 2025-10-08 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-30 | 2025-06-02 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-30 | 2025-09-30 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-08-01 01:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1580 | INT-CR0875 | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-09-10 | 2025-08-19 |  | 2025-09-25 | 2025-09-26 | 2025-09-25 |  | 2025-09-24 | 2025-10-03 | 2025-09-24 | 2025-09-24 |  | 2025-10-08 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-30 | 2025-09-30 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-30 | 2025-09-30 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-09-10 | 2025-09-26 | 2025-10-08 |  | 2025-11-05 |  |  |  | 0 |  | 3214 | [7 empty] | 1. On Track | 17. FUT In progress | 10/30 - FUT in progress 10/24 - PDF is yet to begin FUT on this object. | 2025-10-08 | N | 07. FTS IF | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 3022 | FTSI1578 | 02.Interface | 02.IF - Intel Foundry | Interface to send Lot attribute signal to Workstream from SAP S4 - Mulesoft Requirement | 07. FTS IF | 7.1 FTS IF - ALL | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3022_FTS_IF_Interface%20to%20trigger%20Set%20lot%20attribute%20signal%20from%20S4%20to%20Workstream%20-%20Mulesoft.pptx?d=w89c277f6027c41018c1e2dbc9e89efd2&csf=1&web=1&e=HLKz9M | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 05. N/A | 02.High |  | 01.Yes | 31348 | Workstream |  |  | MuleSoft | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-09-25 |  |  |  | 0% |  |  |  |  | 0% |  | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-10-06 | 2025-10-08 |  | 0% | 2025-10-08 |  |  |  | 0% |  | 2025-10-08 | 2025-10-08 | [14 empty] | 2025-12-08 | 2026-01-09 |  | Y | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-08-01 01:50 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 6 | 2025-09-05 | 03.Mulesoft |  |  | 2 | 2.9 | 1578 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-09-25 | 2025-10-08 | 2025-09-25 | [6 empty] | 2025-10-08 |  | 2025-10-08 |  | 2025-10-08 | [11 empty] | 2026-01-09 | [6 empty] | 2025-09-10 |  | 2025-10-08 |  | 2026-01-09 |  |  |  | 0 |  | 3212 | [7 empty] | 5. Not Dispositioned |  |  | 2025-10-08 | N | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 18 |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3072 | FTSI1574 | 02.Interface | 02.IF - Intel Foundry | A new interface for the Believe Handheld application will allow users to fetch lot list from S4 using either RSQ Batch ID or STO# | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2AF50E23-C75A-439A-8D79-ACFC3E61DE71%7D&file=3072_FTS_IF_interface%20for%20the%20Believe%20Handheld%20application%20will%20allow%20users%20to%20fetch%20lot%20list%20from%20S4%20using%20either%20RSQ%20Batch%20ID%20or%20STO.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 5881 | Believe |  |  | APIGEE | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-21 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-10-09 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-29 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-29 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-10-06 | 2025-10-08 | 2025-11-05 | 100% | 2025-11-03 | 2025-09-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-12-05 | 2025-11-03 | 2025-12-05 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2025-12-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-11-30 | 2025-11-30 | jenoronha@deloitte.com | 2025-07-24 03:57 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1574 | INT-CR0874 | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-09-10 | 2025-08-21 |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-11-05 | 2025-11-03 | 2025-11-03 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-03 | 2025-12-05 |  |  | 2025-12-10 | 2026-01-09 | 2025-12-10 | [5 empty] | 2025-09-10 | 2025-09-26 | 2025-10-08 |  | 2026-01-09 |  |  |  | 0 |  | 3185 | [7 empty] | 4. Completed | 5. Object to be Cancelled |  | 2025-11-30 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-10-03 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3065 | FTSI1573 | 02.Interface | 02.IF - Intel Foundry | interface between S4 and ECA via BODS to post consumption of DTC and EMIB Die to Product Cost Collector | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC8220EC-0695-4187-8998-1B30276F309F%7D&file=3065_FTS_IF_Anafi_substrate_management.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | 2025-09-12 | 2025-09-19 | 2026-03-04 | 100% | 2026-03-09 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-10-27 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-06 | [5 empty] | 2026-03-06 | 2026-03-06 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-07-24 03:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1573 | INT-CR0873, INT-CR1586 | R3 ITC1 | [6 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 |  | 2026-03-04 |  | 2026-03-04 |  | 2026-03-06 | 2026-03-06 | 2026-03-06 |  |  |  |  | 2026-03-06 | 2026-03-06 |  | 2026-03-05 | 2026-03-05 | 2026-03-04 | 2026-03-04 | [5 empty] | 2025-09-10 | 2025-10-24 | 2026-03-04 |  | 2026-03-04 |  |  |  | 0 |  | 3208 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27 - Middleware build completed today as per confirmation by them. Testing to be initiated today. 2/23 - Middleware build in progress. Planned to be completed by this week. (Delayed due to decision on BODS/Mulesoft. 2/13: ECA view not ready ETA 2/20 2/13: ECA view not ready ETA 2/20 01/06: CR open 01/14: Planned for S23 | 2026-03-04 | Y | 07. FTS IF |  |  |  | 02/23: ECA View dependency for MW team to complete Build. Current status: Build is still in progress for ECA view readiness post which MW will pick up for build Issue: FUT on hold due to ECA & MW dependency Next steps: Expedite ECA Build Help needed: ECA team to expedite build (Venessa) FUT ETA: TBD | Week 4 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 3035 | FTSI1538 | 02.Interface | 02.IF - Intel Foundry | CMMS – get location info from CMMS | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 30889 | Collateral MMS |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [14 empty] | 0% | [20 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1538 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3172 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSI1537 | 02.Interface | 02.IF - Intel Foundry | CMMS – Get Collateral Details | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 30889 | Collateral MMS |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [14 empty] | 0% | [20 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1537 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3171 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSI1536 | 02.Interface | 02.IF - Intel Foundry | CMMS – Collateral Conversion | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 30889 | Collateral MMS |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [14 empty] | 0% | [20 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1536 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3170 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2997 | FTSI1527 | 02.Interface | 02.IF - Intel Foundry | Interface to get Cu flag from XEUS | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N | 2025-07-23 | 00. Pending (Default) | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_Interface_Cu%20Flag%20from%20XEUS.pptx?d=w90fd9160e4b24dad9fbb51627a267ec5&csf=1&web=1&e=fWrQJ3 | 02.No | 01.Yes |  | 2025-07-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 35612 | XEUS Loader Framework |  |  | MULESOFT | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-05 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-23 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-23 | 2025-09-08 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-30 | 2025-10-20 | 2026-02-28 | 2026-02-28 | 100% | 2026-02-28 | 2025-09-30 | 2026-02-28 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2026-02-28 | 2026-02-28 | jenoronha@deloitte.com | 2025-07-12 10:06 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-08-01 | 01.S4 |  |  | 1 | 1.45 | 1527 | INT-CR0758 | R3 ITC1 | [6 empty] | 2025-08-05 | 2025-08-15 | 2025-08-05 |  | 2025-09-10 | 2025-09-26 | 2025-09-10 |  | 2025-09-23 | 2025-10-03 | 2025-09-23 | 2025-09-23 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-30 | 2025-09-30 |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2025-09-30 | 2026-02-28 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-08-15 | 2025-09-26 | 2025-09-26 |  | 2025-11-05 |  |  |  | 0 |  | 3141 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 11/4 - Review in progress with Intel | 2026-02-28 | Y | 07. FTS IF |  |  |  | BA Build is planned to complete on 26th December. So the FUT will be spilled over beyond Jan 9th |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 23 |  | 2025-10-03 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2981 | FTSI1473 | 02.Interface | 02.IF - Intel Foundry | MDG to S4 for SFP, Stage, UPI | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6D5625C5-F7E2-4DE6-BC0F-4EE44F1CB76A%7D&file=2981_M-100-080-MDG%20to%20S4%20for%20SFP%2C%20Stage%2C%20UPI.pptx&wdLOR=c30337ABF-5000-4C50-8E71-219B0C6141F9&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | BODS | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-21 | 2025-08-15 | 2025-08-22 | 2025-10-08 | 100% | 2025-10-09 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-07 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-08 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-23 | [5 empty] | 2025-10-23 | 2025-10-23 |  |  | 2026-01-07 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-28 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-23 06:17 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1.45 | 1473 |  | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | 2025-10-09 | 2025-10-09 | 2025-10-09 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-08 |  | 2025-10-08 |  | 2025-11-07 | 2025-10-23 | 2025-10-23 |  |  |  |  | 2025-10-23 | 2025-10-23 |  |  | 2026-01-28 | 2026-02-04 | 2026-01-28 | [5 empty] | 2025-08-13 | 2025-09-26 | 2025-10-08 |  | 2026-02-04 |  |  |  | 0 |  | 3044 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 01/21: Tech team working on defect 5777 | 2025-11-07 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2979 | FTSI1471 | 02.Interface | 02.IF - Intel Foundry | MDG to S4 for MES Site Code to Plant | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC346E4EB-02B9-499F-9C41-1415AD481675%7D&file=2979_M-100-080-MDG%20to%20S4%20for%20MES%20site%20code%20to%20plant.pptx&wdLOR=c28E1D4D1-131C-4A7A-8752-4D9FAD855E6D&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-10-07 | 2025-09-15 | 2025-10-08 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-20 | 2025-10-24 | 2025-10-08 | 100% | 2025-10-10 | [5 empty] | 2025-10-10 | 2025-10-10 |  |  | 2026-01-07 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jenoronha@deloitte.com | 2025-05-23 06:17 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1.45 | 1471 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-08 |  | 2025-09-26 |  | 2025-10-24 | 2025-10-10 | 2025-10-10 |  |  |  |  | 2025-10-10 | 2025-10-10 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 | [5 empty] | 2025-07-16 | 2025-09-26 | 2025-10-08 |  | 2026-02-04 |  |  |  | 0 |  | 3042 | [7 empty] | 4. Completed | 7. FUT Defect Retesting | 01/06:Awaiting approval from desmond team 01/14: Replanned for S22 | 2025-10-24 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2969 | FTSI1469 | 02.Interface | 02.IF - Intel Foundry | Inventory Conversion for R3 | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2969_M-090-110-Inventory%20Conversion%20for%20R3.pptx?d=w3a98aee70ab24c7082c6b61338056126&csf=1&web=1&e=OaPg6o | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF |  |  | APIGEE | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-09-01 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-12 | 2025-09-01 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-12 | 2025-08-18 | 2025-09-10 | 2025-08-13 | 100% | 2025-08-13 | 2025-09-15 | 2025-10-08 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-12 | 2025-09-10 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-05-23 06:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1.45 | 1469 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-09-10 |  | 2025-08-13 |  | 2025-10-08 | 2025-07-29 | 2025-07-29 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-08-12 | 2025-09-10 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-07-16 | 2025-08-08 | 2025-09-10 |  | 2026-02-04 |  |  |  | 0 |  | 3059 | [7 empty] | 1. On Track | 14. B-App Under Test | 2/2: Testing with SMH in progress. 01/21: Awaiting Integrated testing with SMH 01/14: Replanned for S22 10/06: CR in progress. | 2025-10-08 | N | 07. FTS IF | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 17 |  | 2025-08-12 | 2025-08-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2948 | FTSI1455 | 02.Interface | 02.IF - Intel Foundry | Interface from FSCO for lot level material staging by shift​ | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2948_FTS_IF_Interface%20from%20FSCO%20for%20lot%20level%20material%20staging%20by%20shift%E2%80%8B.pptx?d=w756ae04eeff5447a86c92c52de0f417a&csf=1&web=1&e=c9qh1u | 01.Yes | 01.Yes |  | 2025-05-19 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply / Demand Planning | 01.Yes | 14349 | FSM Tactical Planning+FS (Potential: FSCO) |  |  | BODS | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-15 | 2025-08-22 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-24 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-24 | 2025-08-18 | 2025-09-10 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-06 | 2025-10-08 | 2025-10-24 | 100% | 2025-10-24 | 2025-07-05 | 2026-01-09 | 2026-01-09 | 100% | 2026-01-09 | 2025-10-24 | 2026-01-09 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-05-17 02:08 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1.45 | 1455 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-08-22 | 2025-08-14 |  | 2025-09-24 | 2025-09-26 | 2025-09-24 | 2025-09-24 |  | 2025-09-10 |  | 2025-08-13 |  | 2025-10-24 | 2025-10-24 | 2025-10-24 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2025-10-24 | 2026-01-09 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | [5 empty] | 2025-07-16 | 2025-09-26 | 2025-09-10 |  | 2025-12-03 |  |  |  | 0 |  | 3026 | [7 empty] | 2. At Risk | 19. Incomplete Build | 12/12:Awaiting FUT approval | 2026-01-09 | Y | 07. FTS IF |  |  |  | FUT in Progress. Roadblock removed. MW Issue: Datastore connection between FSCO and BODS for Data services to access the view. Next Steps: @Chan, Ken K to share the details for System account request. Enable access to the system account once the request is placed and share credentials to establish connectivity. Help Needed : Help needed from Ken to expedite the resolution of this blocker. E2E FUT ETA: 12/03 |  | 3. Watch item |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2947 | FTSI1454 | 02.Interface | 02.IF - Intel Foundry | Interface from PDH to S4 for lot level STR assignment​ | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2947_FTS_IF_Interface%20from%20PDH%20to%20S4%20for%20lot%20level%20STR%20assignment%E2%80%8B.pptx?d=wf03d27b91745403883d10fc0c9e26971&csf=1&web=1&e=zNzemT | 01.Yes | 01.Yes |  | 2025-05-19 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | MULESOFT | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-18 | 2025-08-22 | 2025-08-29 | 100% | 2025-10-23 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-15 | 2025-09-26 | 2025-08-29 | 100% | 2025-08-29 | 2025-12-08 | 2025-12-19 | 2026-01-07 | 100% | 2026-01-07 | [5 empty] | 2026-01-07 | 2026-01-07 |  |  | 2026-02-04 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | jenoronha@deloitte.com | 2025-05-17 02:08 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1.45 | 1454 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-23 | 2025-10-23 | 2025-10-23 |  | 2025-09-05 | 2025-09-12 |  |  |  | 2025-09-26 |  | 2025-08-29 |  | 2026-01-07 | 2026-01-07 | 2026-01-07 |  |  |  |  | 2026-01-07 | 2026-01-07 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-07-16 | 2025-09-12 | 2025-09-26 |  | 2026-02-04 |  |  |  | 0 |  | 3025 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/4:Awaiting approval 2/2- Tech Team working on Defect Number 6811 01/21: Dropped an email to Intel MW for autosys job, awaiting Intel to respond 01/14: Planned for S22 | 2025-12-19 | N | 07. FTS IF |  |  |  | 0120: Added to S22 plan Current status: SCP FUT dates are provided. E2E FUT planned in S22. Issue: Parallel FUT to be planned due to SCP FUT pushout Next steps: SCP FUT dates are 1/30. E2E FUT planned to be done in parallel. Help needed: SCP team to expedite SCP FUT as much as possible |  |  |  |  | Complete | R3 Build & UT Sprint 21 |  | 2025-09-12 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2942 | FTSI1431 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer batch SLED details from S4 to DMRA on a daily basis | 07. FTS IF | 7.1 FTS IF - ALL | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2942_FTS_IF_DMRA-Interface%20to%20transfer%20batch%20and%20STO%20details%20from%20S4%20to%20DMRA%20on%20a%20daily%20basis.pptx?d=we0da59d07fa440668c048775e6a97ad9&csf=1&web=1&e=liQhIK | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | S/4 | DMRA | MULESOFT | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-15 | 2025-09-12 | 2025-09-19 | 2025-11-05 | 100% | 2025-10-16 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-10-15 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-12-08 | 2025-12-19 |  | 0% | 2025-12-19 |  |  |  | 0% |  | 2025-12-19 | 2025-12-19 | [14 empty] | 2025-12-08 | 2026-01-09 |  | Y | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-19 | 2025-12-19 | 2025-12-19 | pgaroo@deloitte.com | 2025-04-25 04:38 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 6 | 2025-04-30 | 01.S4 |  |  | 1 | 1.45 | 1431 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-09-15 | 2025-09-15 | 2025-09-15 |  | 2025-10-16 | 2025-11-05 | 2025-10-16 |  | 2025-10-15 | 2025-10-24 | 2025-10-15 | 2025-10-15 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-12-19 | [6 empty] | 2025-10-15 | 2025-10-15 |  |  |  | 2026-01-09 | [6 empty] | 2025-08-13 | 2025-10-24 | 2025-11-07 |  | 2026-01-09 |  |  |  | 0 |  | 2989 | [7 empty] | 5. Not Dispositioned |  |  | 2025-12-19 | Y | 07. FTS IF | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2025-10-24 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2923 | FTSI1371 | 02.Interface | 02.IF - Intel Foundry | CMMS – Equipment create and update (status and collateral name) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 04. FS In Progress | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 30889 | Collateral MMS |  | S/4 | MULESOFT | 2025-05-19 | 2025-06-27 |  | 66% | 2025-06-27 | 2025-07-14 | 2025-07-18 |  | 0% | 2025-07-18 | 2025-07-21 | 2025-10-10 |  | 0% | 2025-10-10 | 2025-07-21 | 2025-10-10 |  | 0% | 2025-10-10 | 2025-07-28 | 2025-08-08 |  | 0% | 2025-08-08 | 2025-08-11 | 2025-09-05 |  | 0% | 2025-09-05 |  |  |  | 0% |  | 2025-10-10 | 2025-10-10 | Yes | [13 empty] | 2026-05-18 | 2026-06-12 |  | N | 0% | 2026-06-12 | Not Applicable |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 4 | 2025-05-02 | 01.S4 |  |  | 1 | 1.45 | 1371 | INT-CR0870 | R4 ITC1 | [7 empty] | 2025-06-27 |  |  |  | 2025-07-18 |  |  |  | 2025-10-10 |  |  |  | 2025-08-08 |  |  |  | 2025-09-05 | [11 empty] | 2026-06-12 | [6 empty] | 2025-06-27 | 2025-10-10 | 2025-08-08 |  | 2026-06-12 |  | WIINGS Only eDFIT | TRUE | 0 |  | 2913 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  | 2025-10-10 | N | 07. FTS IF | eDFIT | [7 empty] | N/A | R3 Build & UT Sprint 18 |  | 2025-10-10 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 2923 | FTSI1370 | 02.Interface | 02.IF - Intel Foundry | Factory Portal - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT)​) Interface to Factory Comm | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 04. FS In Progress | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 11807 | Factory Communications |  | S/4 | MULESOFT | 2025-05-19 | 2025-06-27 |  | 66% | 2025-06-27 | 2025-09-12 | 2025-09-19 |  | 0% | 2025-09-19 | 2025-09-26 | 2025-10-24 |  | 0% | 2025-10-24 | 2025-09-26 | 2025-10-24 |  | 0% | 2025-10-24 | 2025-11-03 | 2025-11-07 |  | 0% | 2025-11-07 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 |  |  |  | 0% |  | 2025-12-03 | 2025-12-03 | No | [13 empty] | 2025-12-08 | 2026-01-07 |  | Y | 0% | 2026-01-07 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-03 | 2025-12-03 | 2025-12-03 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 4 | 2025-05-02 | 01.S4 |  |  | 1 | 1.45 | 1370 | INT-CR0870 | R4 ITC1 | [7 empty] | 2025-06-27 |  |  |  | 2025-09-19 |  |  |  | 2025-10-24 |  |  |  | 2025-11-07 |  |  |  | 2025-12-03 | [11 empty] | 2026-01-07 | [6 empty] | 2025-06-27 | 2025-10-24 | 2025-11-07 |  | 2026-01-07 |  | WIINGS Only eDFIT | TRUE | 0 |  | 2912 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  | 2025-12-03 | N | 07. FTS IF | eDFIT | [7 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-10-24 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 2923 | FTSI1355 | 02.Interface | 02.IF - Intel Foundry | CMMS – Equipment with MMS flag (S4 to CMMS) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 06. Dev Not Started | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 30889 | Collateral MMS |  | S/4 | MULESOFT | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-07-14 | 2025-07-18 |  | 0% | 2025-07-18 | 2025-07-21 | 2025-10-10 |  | 0% | 2025-10-10 | 2025-07-21 | 2025-10-10 |  | 0% | 2025-10-10 | 2025-07-28 | 2025-08-08 |  | 0% | 2025-08-08 | 2025-08-11 | 2025-09-05 |  | 0% | 2025-09-05 |  |  |  | 0% |  | 2025-10-10 | 2025-10-10 | No | [13 empty] | 2026-05-18 | 2026-06-12 |  | N | 0% | 2026-06-12 | Not Applicable |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 6 | 2025-05-02 | 01.S4 |  |  | 1 | 1.45 | 1355 | INT-CR0870 | R4 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 |  |  |  | 2025-07-18 |  |  |  | 2025-10-10 |  |  |  | 2025-08-08 |  |  |  | 2025-09-05 | [11 empty] | 2026-06-12 | [6 empty] | 2025-06-13 | 2025-10-10 | 2025-08-08 |  | 2026-06-12 |  | WIINGS Only eDFIT | TRUE | 0 |  | 2888 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  | 2025-10-10 | N | 07. FTS IF | eDFIT | [7 empty] | N/A | R3 Build & UT Sprint 18 |  | 2025-10-10 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 2843 | FTSI1326 | 02.Interface | 02.IF - Intel Foundry | Interface to send Lot create & Lot attribute signal to Workstream from SAP S4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2843_L-120-150_FTS_IF_Custom%20Table%20for%20storing%20Lot%20attributes%20when%20sent%20from%20SAP%20to%20Workstream.pptx?d=wb6f89c56e20e4a3f9384b3378586893b&csf=1&web=1&e=tggHBM | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 31348 | Workstream |  |  | MULESOFT | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-14 | 2025-07-14 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-04 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-28 | 2025-08-04 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-28 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-15 | 2025-09-30 | 2025-08-13 | 100% | 2025-08-12 |  |  |  | 0% |  | 2025-08-12 | 2025-08-12 | No | 2025-09-10 |  |  | 100% |  |  |  |  | 04. Completed |  |  |  |  | 2026-04-03 | 2026-04-28 |  | N | 0% | 2026-04-28 | Not Applicable | R3 Build & UT Sprint OB1 | 2025-09-30 | 2025-09-30 | 2025-09-30 | pgaroo@deloitte.com | 2025-03-19 10:46 | cell-link@smartsheet.com | 2026-03-06 01:58 | 6 | 2025-03-23 | 01.S4 |  |  | 2 | 2.9 | 1326 |  | R4 ITC1 | [6 empty] | 2025-06-14 | 2025-06-14 | 2025-06-14 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-28 | 2025-08-15 | 2025-07-28 | 2025-07-28 |  | 2025-09-12 |  | 2025-07-16 |  | 2025-09-30 | 2025-08-12 | 2025-08-12 |  |  |  |  | 2025-08-12 | 2025-08-12 |  |  |  | 2026-04-28 | [6 empty] | 2025-06-13 | 2025-08-15 | 2025-09-12 |  | 2026-04-28 |  |  |  | 0 |  | 1953 | [5 empty] | 01584 | TD Automation | 5. Not Dispositioned |  |  | 2025-09-30 | N | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | Moved to R4 |  |  |  |  | N/A | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2894 | FTSI1323 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API 9 is to provide Shipping details Ship Server | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API%209%20is%20to%20provide%20Shipping%20details%20Ship%20Server%20.pptx?d=w198530a6641048ea998f59bada1b1bfd&csf=1&web=1&e=WC0S21 | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 7129 | ShipServer |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-24 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-16 | 2025-10-01 | 2026-02-13 | 2026-02-13 | 100% | 2026-04-03 | 2025-12-16 | 2026-04-03 | No |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2026-02-13 | 2026-02-13 | pgaroo@deloitte.com | 2025-03-19 10:46 | cell-link@smartsheet.com | 2026-04-06 21:15 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1323 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-24 | 2025-10-03 | 2025-09-24 | 2025-09-24 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2025-12-16 | 2026-04-03 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  |  |  |  | WIP Inventory Shipping | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-02-04 |  |  |  | 0 |  | 1872 | [5 empty] | 01584 | TD Automation | 1. On Track | 25. Requirement Change | 2/2: Payload structure changes in progress TUT/FUT in progress. Also, Testing scheduled with Shipserver team on 2/3. 01/21: Payload structure changes in progress 01/14: Replanned for S22 01/06: CR 1543 development in progress. | 2026-02-13 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 02/04: E2E FUT is completed and submitted for approval. Current Status: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 02/06. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: Testing scheduled with Shipserver team on 2/3. Help Needed: N/A |  | 2. Risk | 2/Outage |  | Complete | R3 Build & UT Sprint 23+ |  | 2025-10-03 | 2025-09-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2896 | FTSI1321 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API 6 is to get Shippable lots from Work Stream | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API%206%20is%20to%20get%20Shippable%20lots%20from%20TD%20apps.pptx?d=w839c39b10a1f4dd3b95e617b400b780a&csf=1&web=1&e=bZkBRs | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 31348 | Workstream |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-11 |  |  |  | 0% |  | 2025-12-11 | 2025-12-11 | No |  | 2026-01-07 | 2026-01-07 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-03-19 10:46 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 6 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1321 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 | 2025-09-16 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | 2025-12-11 | 2025-12-11 |  |  |  | 2026-01-09 | [6 empty] | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-01-09 |  |  |  | 0 |  | 1870 | [5 empty] | 01584 | TD Automation | 5. Not Dispositioned |  | 01/06: CR 1543 development in progress | 2025-09-26 | N | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 0106: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 0109. Current Status: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 0109. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: S4 and MW teams to make changes suggested by the B-App team and change the mapping files. Help Needed: N/A |  | 2. Risk | 2 |  | N/A | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2897 | FTSI1320 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API 7 is for Precheck Request and Response to Ship Server | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API%207%20is%20for%20Precheck%20Request%20and%20Response%20to%20Ship%20Server.pptx?d=wc763e1b38cca4898acf65b5141ee0524&csf=1&web=1&e=gzKm1d | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 7129 | ShipServer |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-16 | 2025-10-01 | 2026-02-13 | 2026-02-13 | 100% | 2026-04-03 | 2025-12-16 | 2026-04-03 | No |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2026-02-13 | 2026-02-13 | pgaroo@deloitte.com | 2025-03-19 10:46 | cell-link@smartsheet.com | 2026-04-06 21:15 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1320 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 | 2025-09-16 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2025-12-16 | 2026-04-03 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  |  |  |  | WIP Inventory Shipping | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-02-04 |  |  |  | 0 |  | 1869 | [5 empty] | 01584 | TD Automation | 1. On Track | 25. Requirement Change | 2/2: Payload structure changes in progress TUT/FUT in progress,Also .Testing scheduled with Shipserver team on 2/3 01/21: Payload structure changes in progress 01/14: Replanned for S22 01/06: CR 1543 development in progress. | 2026-02-13 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 02/04: E2E FUT is completed and submitted for approval. Server. MW changes complete. S4 changes in progress. ETA 02/06. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: Testing scheduled with Shipserver team on 2/3. Help Needed: N/A |  | 2. Risk | 2/Outage |  | Complete | R3 Build & UT Sprint 23+ |  | 2025-09-26 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2898 | FTSI1319 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API4 is to provide Shipping details to ULT from S4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API4%20is%20to%20provide%20Shipping%20details%20to%20ULT%20from%20S4.pptx?d=w5009341f6e984536b85fcaad50bb2251&csf=1&web=1&e=P99jUQ | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 16110 | Unit Level Traceability |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-11 | 2025-09-01 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-12-11 | 2026-01-16 | No |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2025-03-19 10:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1319 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 | 2025-09-16 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2025-12-11 | 2026-01-16 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  |  |  |  | WIP Inventory Shipping | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-02-04 |  |  |  | 0 |  | 1868 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/2: Payload structure changes in progress TUT/FUT in progress,Also .Testing scheduled with Shipserver team on 2/3 01/21: Payload structure changes in progress 01/14: Replanned for S22 01/06: CR 1543 development in progress. | 2026-01-16 | Y | 07. FTS IF |  |  |  | 2/3: FUT Documentation completed. Walkthrough planned. Current Status: Payload changes are ready from ShipServer. MW changes complete. Complete. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: S4 and MW teams to make changes suggested by the B-App team and change the mapping files. Help Needed: N/A |  | 2. Risk | 2/Outage |  | Complete | R3 Build & UT Sprint 22 |  | 2025-09-26 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2899 | FTSI1318 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API3 is to provide Shipping details to WorkStream from S4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API3%20is%20to%20provide%20Shipping%20details%20to%20WorkStream%20from%20S4.pptx?d=wff52eebba8aa451aae152b1f4161924e&csf=1&web=1&e=Fpvq0Q | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 31348 | Workstream |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-11 |  |  |  | 0% |  | 2025-12-11 | 2025-12-11 | No |  | 2026-01-07 | 2026-01-07 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 0% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-03-19 10:46 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 6 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1318 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 | 2025-09-16 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-11 | 2025-12-11 | 2025-12-11 |  |  |  |  | 2025-12-11 | 2025-12-11 |  |  |  | 2026-01-09 | [6 empty] | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-01-09 |  |  |  | 0 |  | 1981 | [5 empty] | 01584 | TD Automation | 5. Not Dispositioned |  | 01/06: CR 1543 development in progress | 2025-09-26 | N | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 0106: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 0109. Current Status: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 0109. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: S4 and MW teams to make changes suggested by the B-App team and change the mapping files. Help Needed: N/A |  | 2. Risk | 2 |  | N/A | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2901 | FTSI1317 | 02.Interface | 02.IF - Intel Foundry | M-100-170_API 11 is to get Shippable lots from Ship server | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_API%206%20is%20to%20get%20Shippable%20lots%20from%20Ship%20server.pptx?d=w0edcca2b35944c359d4694cb0db7e5d8&csf=1&web=1&e=Dc3kOj | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 02.Intel | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 7129 | ShipServer |  |  | MULESOFT | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-15 | 2025-08-29 | 2025-09-26 | 2025-09-17 | 100% | 2025-09-15 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-12-16 | 2025-08-18 | 2026-02-13 | 2026-02-13 | 100% | 2026-04-03 | 2025-12-16 | 2026-04-03 | No |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-26 | 2026-02-13 | 2026-02-13 | pgaroo@deloitte.com | 2025-03-19 10:46 | cell-link@smartsheet.com | 2026-04-06 21:15 | 10 | 2025-03-23 | 01.S4 |  |  | 1 | 1.45 | 1317 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-09-15 | 2025-09-26 | 2025-09-15 | 2025-09-15 |  | 2025-09-12 |  | 2025-08-29 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2025-12-16 | 2026-04-03 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 |  |  |  |  | WIP Inventory Shipping | 2025-07-18 | 2025-09-26 | 2025-09-12 |  | 2026-02-04 |  |  |  | 0 |  | 1780 | [5 empty] | 01584 | TD Automation | 1. On Track | 25. Requirement Change | 2/2: Payload structure changes in progress TUT/FUT in progress. Also, testing scheduled with Shipserver team on 2/3 01/21: Payload structure changes in progress 01/14: Replanned for S22 01/06: CR 1543 development in progress. | 2026-02-13 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 02/04: E2E FUT is completed and submitted for approval. Current Status: Payload changes are ready from ShipServer. MW changes complete. S4 changes in progress. ETA 0130. Issue: Revised Payload changes from Shipserver is Impacting 8 API Interfaces. Next Steps: S4 and MW teams to make changes suggested by the B-App team and change the mapping files. Help Needed: N/A |  | 2. Risk | 2/Outage |  | Complete | R3 Build & UT Sprint 23+ |  | 2025-09-26 | 2025-09-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2783 | FTSI1159 | 02.Interface | 02.IF - Intel Foundry | Interface from ECA to S4 to maintain POLP table | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2783_M-100-030_FTS_IF_Interface%20from%20FSCO%20to%20S4%20to%20maintain%20POLP%20table.pptx?d=w3568b6b5cb094730ad1eb4f5b19140a1&csf=1&web=1&e=NVqqz4 | 02.No | 01.Yes |  | 2025-01-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply / Demand Planning | 02.No | NA | NA | ECA | S/4 | BODS | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-12 | 2025-05-16 | 2025-08-13 | 100% | 2025-08-21 | 2025-08-20 | 2025-09-05 | 2025-09-05 | 100% | 2025-09-10 | 2025-05-30 | 2025-06-13 | 2025-09-05 | 100% | 2025-09-10 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-06 | 2025-10-08 | 2025-10-24 | 100% | 2025-10-24 | [5 empty] | 2025-10-24 | 2025-10-24 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-08 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-01-23 15:43 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1159 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 |  | 2025-08-13 |  | 2025-08-13 |  | 2025-10-24 | 2025-10-24 | 2025-10-24 |  |  |  |  | 2025-10-24 | 2025-10-24 |  | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | [5 empty] | 2025-04-18 | 2025-06-13 | 2025-08-13 | [5 empty] | 0 |  | 1815 | [7 empty] | 4. Completed | 3. Awaiting Approval | 3/6:Awaiting approval pending 2/27:Awaiting approval pending 2/23: FUT walkthrough planned 2/24 2/13:Defect in progress 01/06: FUT in progress. 01/14: Replanned for S23 | 2025-10-08 | N | 07. FTS IF |  |  |  |  | Week 4 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-09-10 | 2025-09-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2681 | FTSI1158 | 02.Interface | 02.IF - Intel Foundry | Interface from SMH to S4 to handle movement of lots from Revenue to TD | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2681_M-100-220_FTS_IF_S4%20Interface%20from%20SMH%20to%20S4%20to%20handle%20movement%20of%20lots%20from%20Revenue%20to%20TD%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w64a451d16cb14d10b4b3561d3d929aa2&csf=1&web=1&e=fNJTou | 02.No | 01.Yes |  | 2025-01-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | PDF | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-05 | 2025-03-17 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-18 | 2025-02-26 | 2025-04-23 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-04 | 2025-09-10 | Yes | 2025-08-13 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-09-10 | 2025-09-10 | jonsanders@deloitte.com | 2025-01-23 15:43 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1158 |  | R3 ITC1 | [6 empty] | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-08-04 | 2025-09-10 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-02-21 | 2025-04-18 | 2025-04-18 | S4 |  |  |  |  | 0 |  | 2142 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/09: Awaiting confirmation | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2680 | FTSI1157 | 02.Interface | 02.IF - Intel Foundry | Custom program for STO generation for Raw Silicon | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2680_L-060-060_FTS_IF_Custom%20program%20for%20STO%20generation%20for%20Raw%20Silicon.pptx?d=w907ecdaa6574415a86b080f0e2698904&csf=1&web=1&e=EyKDiT | 02.No | 01.Yes |  | 2025-01-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 31279 | Starts Game Planner | 3PL | S/4 | APIGEE | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-19 | 2025-05-12 | 2025-05-16 | 2025-07-04 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-07-11 | 2025-07-11 | 100% | 2025-07-11 | 2025-07-14 | 2025-08-08 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-11 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-13 | 2025-07-21 | 2026-02-13 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-08-08 | 2026-02-13 | 2026-02-13 | jonsanders@deloitte.com | 2025-01-23 15:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1.45 | 1157 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-19 | 2025-04-19 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-08-08 | 2025-07-21 | 2025-07-21 |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2025-07-21 | 2026-02-13 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-04-18 | 2025-06-13 | 2025-07-11 | S4 |  |  | WIINGS |  | 0 |  | 2141 | [5 empty] | 01584 | TD Automation | 1. On Track | 3. Awaiting Approval | 2/27:FUT In progress 2/23-Defect # 7600 raised to make the structure changes in error response payload from MW to SGP 2/20: new defect to be raised to make the changes in error response payload from MW and S4 tech end. 2/13: Defect created to S4 team 01/06: FUT in progress 01/14: Replanned for S23 | 2026-02-13 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | 03/04: Awaiting approval. Current status: Awaiting approval Next steps: N/A Help needed: N/A FUT ETA: N/A | Week 3 Target | 3. Watch item |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 1. WIINGS but not Only WIINGS
01. IAO ERP | 03.R3 | 2663 | FTSI1023 | 02.Interface | 01.IP - Intel Product | Interface to Transfer stock from Unrestricted stock to Block stock and vice versa based on quality Disposition | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2663_FTS_IP_S4_Interface%20to%20Transfer%20stock%20from%20Unrestricted%20stock%20to%20Block%20stock%20and%20vice%20versa%20based%20on%20quality%20Disposition.pptx?d=wbd05055fbed144c296f919cba1207bc8&csf=1&web=1&e=U3e6Xy | 02.No | 01.Yes |  | 2024-12-18 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208; 59283 | E2open; PDF Sapience Manufacturing Hub Integration Platform - IP | E2OPEN | S/4 | APIGEE | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-07-16 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-08-22 | 2025-04-04 | 2025-05-16 | 2025-08-08 | 100% | 2025-08-22 | 2025-02-24 | 2025-03-21 | 2025-07-16 | 100% | 2025-07-16 | 2025-05-26 | 2025-06-27 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-04 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-01 | 2025-08-22 | 2025-12-01 | Yes | 2025-08-13 | 2026-01-31 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-06-27 | 2025-11-26 | 2025-11-26 | jonsanders@deloitte.com | 2024-12-17 15:18 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-03 | 01.S4 |  |  | 1 | 1.45 | 1023 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-08-13 | 2025-07-29 | 2025-07-29 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-08-22 | 2025-12-01 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-04-18 | 2025-04-18 | 2025-03-21 | S4 | 2025-06-30 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1847 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 02/02 : Defect #6791 Fix in WIP 01/21 : E2E FUT is planned in Sprint 22. 01/06 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 01/09.Completing this task by 01/09 is at risk due to outstanding readiness issues with PDF SMH. 12/18 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/19. 12/12 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/15. | 2025-11-26 | N | 08. FTS IP |  |  |  | 02/04 : E2E FUT is in progress. PDF fix is required. ETA is 2/6 Current state: Build complete. E2E FUT planned on 02/04 Issue: None Next steps: To conduct E2E FUT as per plan. Help needed: N/A | Testing planned in WW06 | 2. Risk | 1. PDF SMH S22 | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-08-22 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2662 | FTSI1022 | 02.Interface | 01.IP - Intel Product | Inbound Interface to update projected release quantity and date for lots on quality hold in S4 | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2662_FTS_IP_S4%20Inbound%20Interface%20to%20update%20projected%20release%20quantity%20and%20date%20for%20lots%20on%20quality%20hold%20in%20S4.pptx?d=wc3bf74f2467d472ab7fef41a3fe67540&csf=1&web=1&e=6M996H | 02.No | 01.Yes |  | 2024-12-18 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | FLAT FILE | S/4 | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-08-13 | 100% | 2025-08-09 | 2025-04-04 | 2025-05-16 | 2025-05-30 | 100% | 2025-06-12 | 2025-04-04 | 2025-05-16 | 2025-05-30 | 100% | 2025-06-12 | [15 empty] | 2025-06-12 | 2025-06-12 | Yes |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2024-12-17 15:18 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-03 | 01.S4 |  |  | 1 | 1.45 | 1022 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | [12 empty] | 2025-06-12 | 2025-06-12 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-16 | 2025-04-18 | 2025-03-21 |  | 2025-06-30 |  |  |  | 0 |  | 1846 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change | 09/12 : Walkthrough provide and Awaiting for approval ETA 09/15. | 2025-05-16 | N | 08. FTS IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 14 |  | 2025-06-12 | 2025-06-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2661 | FTSI1021 | 02.Interface | 02.IF - Intel Foundry | Interface to be developed from ECA to SAP which helps to upload PIR via BAPI | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5E807953-79EA-4C12-BC75-39B376636A5F%7D&file=_M-100-220_FTS_IF_Interface%20from%20PDH%20to%20S4%20to%20create-maintain%20PIR%20in%20S4.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | SIMS BI Portal | ECA | S/4 | APIGEE | 2025-03-24 | 2025-04-18 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-09 | 2025-06-13 |  | 66% | 2025-06-13 | 2025-03-10 | 2025-03-21 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-07 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-11-03 | 2025-11-07 |  | 50% | 2025-11-07 | 2025-11-24 | 2025-12-03 |  | 0% | 2025-12-03 | [5 empty] | 2025-12-03 | 2025-12-03 | Yes | 2025-08-13 |  |  | 100% |  |  |  |  | 04. Completed |  |  |  |  | 2026-04-03 | 2026-04-28 |  | N | 0% | 2026-04-28 | Not Applicable | R3 Build & UT Sprint OB1 | 2025-12-03 | 2025-12-03 | 2025-12-03 | jonsanders@deloitte.com | 2024-12-17 15:18 | cell-link@smartsheet.com | 2026-03-06 01:58 | 6 | 2024-12-23 | 01.S4 |  |  | 1 | 1.45 | 1021 |  | R4 ITC1 | [6 empty] | 2025-03-21 | 2025-04-18 | 2025-03-21 |  |  | 2025-06-13 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-07 |  |  |  | 2025-12-03 | [6 empty] | 2025-08-04 | 2025-08-04 |  |  |  | 2026-04-28 | [6 empty] | 2025-04-25 | 2025-03-21 | 2025-03-21 |  | 2025-12-05 |  |  |  | 0 |  | 1845 | [5 empty] | 01584 | SIMS | 5. Not Dispositioned |  |  | 2025-12-03 | N | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | Moved to R4 |  |  |  |  | N/A | R3 Build & UT Sprint 20 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2625 | FTSI1020 | 02.Interface | 02.IF - Intel Foundry | IMO - Interface from NBS to S4 to induct stock from IMO plant to S4 | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2625_M-100-170_FTS_IF_IMO%20-%20Interface%20from%20NBS%20to%20S4%20to%20induct%20stock%20from%20IMO%20plant%20to%20S4.pptx?d=w897357e09e5b4e268e4c32a4d342e6f7&csf=1&web=1&e=Jg3eWq | 02.No | 01.Yes |  | 2024-12-20 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 4982 | IMO - NBS | NBS | S/4 | APIGEE | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-07-04 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-09 | 2025-06-27 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-11 | 2025-09-05 | 2025-07-16 | 100% | 2025-07-21 | 2026-01-01 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-13 | 2025-07-21 | 2026-02-13 | No | 2025-08-13 | 2026-02-27 | 2026-03-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-09-05 | 2026-02-13 | 2026-02-13 | jonsanders@deloitte.com | 2024-12-17 15:18 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-23 | 01.S4 |  |  | 1 | 1.45 | 1020 | INT-CR1318 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-09-05 | 2025-07-21 | 2025-07-21 |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2025-07-21 | 2026-02-13 |  |  | 2026-02-23 | 2026-03-04 | 2026-02-23 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-27 | S4 | 2025-09-26 |  |  |  | 0 |  | 2564 | [5 empty] | 01584 | IMO | 1. On Track | 3. Awaiting Approval | 2/20: awaiting approval | 2026-02-13 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2620 | FTSI1016 | 02.Interface | 02.IF - Intel Foundry | IMR - Interface between SAP S/4 and SAP ME to replicate production orders. This will be an Outbound IDOC from SAP S/4 to send production orders to SAP ME | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2620_M-090-130-LOIPRO%20IDOC.pptx?d=w2a0e9e5a249b4d5c9266493a880707b3&csf=1&web=1&e=YxKzby | 02.No | 01.Yes |  | 2024-12-20 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 14162 | SAP Manufacturing Execution | S/4 | SAP ME | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-19 | 2025-05-02 | 2025-05-09 | 2025-09-26 | 100% | 2025-09-16 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [10 empty] | 2025-07-01 | 2025-10-25 | 2025-10-25 | 100% | 2025-10-25 | 2025-07-21 | 2025-10-25 | No | 2025-08-13 | 2026-01-07 | 2026-01-07 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-05 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-10-25 | 2025-10-25 | jonsanders@deloitte.com | 2024-12-17 15:18 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-23 | 01.S4 |  |  | 1 | 1.45 | 1016 |  | R3 ITC1 | [6 empty] | 2025-04-19 | 2025-04-19 | 2025-04-19 |  | 2025-09-16 | 2025-09-26 | 2025-09-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [9 empty] | 2025-10-25 | 2025-10-25 | 2025-10-25 | 2025-07-21 | 2025-10-25 |  |  | 2026-01-05 | 2026-01-09 | 2026-01-05 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-27 | S4 | 2025-10-24 |  |  |  | 0 |  | 2560 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/22: FUT in progress | 2025-10-25 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2559 | FTSI1008 | 02.Interface | 02.IF - Intel Foundry | Interface S/4 with EMS | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System | EMS | S/4 | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-13 | 2025-05-02 | 2025-05-09 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-04-11 | 100% | 2025-04-11 | 2025-05-30 | 2025-06-13 | 2025-04-11 | 100% | 2025-04-21 | 2025-05-19 | 2025-06-13 | 2025-05-16 | 100% | 2025-05-16 | 2025-06-16 | 2025-07-18 | 2025-05-09 | 100% | 2025-08-04 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 100% | 2025-12-21 | 2025-08-04 | 2025-12-21 | Yes | 2025-08-13 | 2025-07-16 | 2025-07-16 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2026-01-06 | Not Applicable | R3 Build & UT Sprint 21 | 2025-07-18 | 2025-11-25 | 2025-11-25 | vasamohan@deloitte.com | 2024-12-16 13:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 1 | 1.45 | 1008 |  | R3 ITC1 | [6 empty] | 2025-03-13 | 2025-03-21 | 2025-03-13 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-11 | 2025-06-13 |  | 2025-04-21 |  | 2025-06-13 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-21 | 2025-12-21 | 2025-12-21 | 2025-08-04 | 2025-12-21 |  |  | 2026-01-06 | 2026-01-06 | 2026-01-06 | [5 empty] | 2025-03-21 | 2025-06-13 | 2025-06-13 | MW | 2025-07-04 |  | WIINGS Only | TRUE | 0 |  | 1464 | [7 empty] | 1. On Track | 3. Awaiting Approval | 1/2: Sent for Approval | 2025-11-25 | Y | 07. FTS IF |  |  |  | Current Status: S4 FUT is completed. Awaiting for BA Readiness. Issue: Awaiting for EMS readiness. ETA is 11/21. Next Steps: E2E FUT will be picked up once BA is ready Help Needed: |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-06-13 | 2025-04-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2556 | FTSI1007 | 02.Interface | 02.IF - Intel Foundry | Interface S/4 with XEUS | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 35612; 32079 | XEUS Loader Framework; ATM MARS | XEUS/Mars | S/4 | APIGEE | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-06 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-28 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-28 | 2025-06-16 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-16 | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-08-04 | 2025-03-03 | 2026-02-28 | 2026-02-28 | 100% | 2026-02-28 | 2025-08-04 | 2026-02-28 | Yes | 2025-09-10 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2026-02-28 | 2026-02-28 | vasamohan@deloitte.com | 2024-12-16 13:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 2 | 2.9 | 1007 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-28 | 2025-08-08 | 2025-07-28 | 2025-07-28 |  | 2025-07-18 |  | 2025-07-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2025-08-04 | 2026-02-28 |  |  | 2025-09-25 | 2025-10-08 | 2025-09-25 |  |  |  |  | TD Apps | 2025-03-21 | 2025-07-18 | 2025-07-18 | MW | 2025-07-11 |  | WIINGS Only | TRUE | 0 |  | 1510 | [5 empty] | 01584 | PM | 5. Not Dispositioned |  | 8/29: Activity 5.0 for this object will be complete in Sprint 17, but cannot close FUT due to dependency on completion of B-App build set for March 2026 (RAID 2009) | 2026-02-28 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | S/4 and MW build completed, BApps completing 03/31/26,FUT Dates planned in April |  |  |  |  | Complete | R3 Build & UT Sprint 23 |  | 2025-08-08 | 2025-07-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2514 | FTSI0985 | 02.Interface | 02.IF - Intel Foundry | Claim Status Update from e2open to SAP S4 (Inbound Interface) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | E2Open | S/4 | MULESOFT | 2025-01-16 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-20 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-04-04 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-04-04 | 2025-02-24 | 2025-03-21 | 2025-05-16 | 100% | 2025-05-16 | 2025-03-24 | 2025-04-18 | 2025-05-09 | 100% | 2025-08-04 | 2025-05-20 | 2025-08-12 | 2025-08-12 | 100% | 2025-08-12 | 2025-08-04 | 2025-08-12 | Yes | 2025-08-13 | 2025-07-16 | 2025-07-16 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-18 | 2025-08-12 | 2025-08-12 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 1 | 1.45 | 0985 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-02-21 | 2025-02-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-04 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-04 | 2025-08-12 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | B2B - E2open | 2025-02-21 | 2025-04-18 | 2025-03-21 | MW | 2025-08-08 |  | WIINGS Only | TRUE | 0 |  | 1768 | [7 empty] | 4. Completed | 17. FUT In progress | 12/1: To be Presented to Intel in 12/1 | 2025-08-12 | Y | 07. FTS IF |  |  |  | Current Status: Build due to Requirement clarification in progress. Issue: FUT on hold due to design change Next Steps: FUT to resume once the CR is completed. ETA is TBD Help Needed: |  |  |  | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-04-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2513 | FTSI0983 | 02.Interface | 02.IF - Intel Foundry | SAP Warranty Claim Document to e2open (Outbound Interface) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes | FTSE0984 | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2025-01-16 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-20 | 2025-03-07 | 2025-03-14 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-04-04 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-04-04 | 2025-03-31 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-06-16 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-09-05 | 2025-09-05 | 100% | 2025-09-05 | 2025-07-21 | 2025-09-05 | Yes | 2025-09-10 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-09-05 | 2025-09-05 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2024-12-18 | 01.S4 |  |  | 1 | 1.45 | 0983 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-02-21 | 2025-02-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-04 | 2025-04-18 |  |  |  | 2025-05-16 |  | 2025-05-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-07-21 | 2025-09-05 |  |  | 2025-09-19 | 2025-10-08 | 2025-09-19 |  |  |  |  | B2B - E2open | 2025-02-21 | 2025-04-18 | 2025-08-01 | MW | 2025-08-01 |  | WIINGS Only | TRUE | 0 | 01.4 Suppliers that engage with E2Open | 2381 | [10 empty] | 2025-09-05 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-04-18 | 2025-04-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2037 | FTSI0924 | 02.Interface | 02.IF - Intel Foundry | Interface: SAP ME to S/4 to Create & Maintain Notifications | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Sprint%206_Consolidated%20Review_sent%20for%20approval.pptx?d=w089c25e3e662433ea2fdc8964a8862be&csf=1&web=1&e=nfZ6OH | 02.No | 01.Yes |  | 2024-12-02 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 14162 | SAP Manufacturing Execution | SAP ME | S/4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-19 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-19 | [10 empty] | 2025-03-31 | 2025-12-26 | 2025-12-26 | 100% | 2025-12-26 | 2025-04-19 | 2025-12-26 | Yes | 2025-10-08 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-05-16 | 2025-12-26 | 2025-12-26 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0924 | INT-CR0907 | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-19 | 2025-05-16 | 2025-04-19 | 2025-04-19 | [9 empty] | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-04-19 | 2025-12-26 |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-23 | S4 | 2025-10-22 |  |  |  | 0 |  | 2013 | [5 empty] | 01584 | PM | 1. On Track | 3. Awaiting Approval | 1/2: Sent for Approval | 2025-12-26 | Y | 07. FTS IF |  | 07/09/25 | Sateesh Kumar |  |  |  |  | CR/Design change | Complete | R3 Build & UT Sprint 21 |  | 2025-05-16 | 2025-04-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 1924 | FTSI0860 | 02.Interface | 02.IF - Intel Foundry | Interface to create Kanban trigger from DMRA and get Reservation created and shared to 3 PL to get inventory to shop floor. | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE34F4DC1-F845-40D8-991B-7C1F01A7E8CA%7D&file=L-120-150_FTS_IF%20Kanban%20-%20WIP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Manufacturing Integration | 01.Yes | 12918 | Direct Materials Replenishment Automation - DMRA | DMRA | S/4 | MULESOFT | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-08-18 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-08 | 2025-08-29 | 2025-09-26 |  | 0% | 2025-09-26 | 2025-08-29 | 2025-09-26 |  | 0% | 2025-09-26 | 2025-08-18 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-16 |  |  |  | 0% |  | 2025-09-26 | 2025-09-26 | No | [13 empty] | 2026-03-23 | 2026-04-17 |  | N | 0% | 2026-04-17 | Not Applicable | R3 Build & UT Sprint OB1 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-06 01:58 | 6 | 2024-11-12 | 01.S4 |  |  | 4 | 5.8 | 0860 |  | R4 ITC1 | [6 empty] | 2025-08-18 | 2025-08-18 | 2025-08-18 |  | 2025-09-08 | 2025-09-26 | 2025-09-08 |  |  | 2025-09-26 |  |  |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-16 | 2025-09-16 |  |  |  |  | 2025-09-16 | 2025-09-16 |  |  |  | 2026-04-17 | [6 empty] | 2025-03-21 | 2025-06-13 | 2025-06-13 |  | 2025-08-25 |  |  |  | 0 | 08. Not Applicable | 1472 | [5 empty] | 01584 | TD Automation | 5. Not Dispositioned |  | R4 | 2025-10-08 | N | 07. FTS IF |  | 07/09/25 | Sateesh Kumar | Moved to R4 |  |  |  |  | N/A | R3 Build & UT Sprint 18 |  | 2025-09-26 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2366 | FTSI0830 | 02.Interface | 02.IF - Intel Foundry | Shipserver Interface to S4 to get handling units for the logical ship | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2366_FTS_IF_MPL%20Interface%20to%20S4%20to%20get%20handling%20units%20for%20the%20logical%20ship.pptx?d=w56e77c0332c94d109577d75113ecb870 | 02.No | 01.Yes |  | 2024-11-08 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 7129 | ShipServer | MPL | S/4 | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-12 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-03 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-01 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-10-01 | 2025-08-18 | 2025-09-12 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-16 | 2025-11-03 | 2026-02-13 | 2026-02-13 | 100% | 2026-04-03 | 2025-10-01 | 2026-04-03 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-04 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2026-02-13 | 2026-02-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-04-06 21:15 | 10 | 2024-11-12 | 01.S4 |  |  | 1 | 1.45 | 0830 |  | R3 ITC1 | [6 empty] | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-09-03 | 2025-09-26 | 2025-09-03 |  | 2025-10-01 | 2025-10-03 | 2025-10-01 | 2025-10-01 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-16 | 2025-09-16 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2025-10-01 | 2026-04-03 |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 |  |  |  |  | WIP Inventory Shipping | 2025-03-21 | 2025-06-13 | 2025-06-13 | S4 | 2025-09-26 |  |  |  | 0 | 08. Not Applicable | 1855 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27:Awaiting approval 2/23:Defect 7585 fix in progress 2/13: Defect 7071 open to tech team 01/06: CR 1543 development in progress 01/14: Replanned for S23 | 2026-02-13 | Y | 07. FTS IF |  |  |  | 02/23: FUT in progress. Defect fixes ongoing. Current Status: FUT in progress. Defect fixes ongoing. Issue: n/a Next Steps: Complete FUT and send for approval.. Help Needed: N/A FUT ETA: 03/06 | Week 3 Target |  | CR1401 | Awaiting approval | Complete | R3 Build & UT Sprint 23+ |  | 2025-10-03 | 2025-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2359 | FTSI0725 | 02.Interface | 01.IP - Intel Product | Inbound interface to capture Yield Confirmation and Goods Receipt against Production Order and Text Purchase Order from e2open to IP SAP S4 HANA system for OSATs | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B966E3BC5-288C-4AC5-A2E6-545216F9E96F%7D&file=M-100-140_FTS_IP_Inbound%20Interface%20to%20capture%20Yield%20Confirmation%20and%20Goods%20Receipt%20against%20Production%20Order%20in%20IP%20SAP%20S4%20HANA%20based%20on%20trigger%20from%20OSAT%20via%20E2Open.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208; 59283 | E2open; PDF Sapience Manufacturing Hub Integration Platform - IP | E2OPEN | S/4 | APIGEE | 2025-01-27 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-31 | 2025-04-07 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-21 | 2025-02-24 | 2025-03-21 | 2025-07-16 | 100% | 2025-07-16 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-04 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-01 | 2025-07-21 | 2025-12-01 | Yes |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-19 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-11-26 | 2025-11-26 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-04-03 08:07 | 10 | 2024-10-16 | 01.S4 |  |  | 1 | 1.45 | 0725 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-03-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 | 2025-07-21 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-07-21 | 2025-12-01 |  |  | 2026-02-19 | 2026-03-04 | 2026-02-19 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-10 | 2025-04-18 | 2025-03-21 | S4 | 2025-06-27 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1850 | [7 empty] | 1. On Track | 17. FUT In progress | 02/16 : E2E FUT is planned on 02/17 and ETA 02/20. 02/12 : FUT is in WIP. 01/13 : E2E FUT is planned in Sprint 23. 01/06 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 01/09.Completing this task by 01/09 is at risk due to outstanding readiness issues with PDF SMH. 12/18 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/19. 12/12 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/15. | 2025-11-26 | N | 08. FTS IP |  |  |  |  | Week 2 Target |  | 4. PDF SMH S23 | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-08-08 | 2025-07-21 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | Yes |  | 2026-02-17 | 2026-03-27 | 2026-04-10 | 85% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2360 | FTSI0724 | 02.Interface | 01.IP - Intel Product | Inbound interface from e2open to IP SAP S4 HANA system to update Die Quantity attribute value in the batch master record for OSATs | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B91A8D3BB-E759-4CA8-A44D-3C51C61C2A13%7D&file=M-100-140_FTS_IP_Inbound%20Interface%20from%20e2open%20to%20IP%20SAP%20S4%20HANA%20System%20to%20update%20Die%20quantity%20attribute%20value%20in%20the%20batch%20master%20record%20for%20OSATs.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-15 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 12208; 59283 | E2open; PDF Sapience Manufacturing Hub Integration Platform - IP | E2OPEN | S/4 | APIGEE | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-20 | 2025-03-31 | 2025-04-07 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-21 | 2025-02-24 | 2025-03-21 | 2025-07-16 | 100% | 2025-07-16 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-04 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-01 | 2025-07-21 | 2025-12-01 | Yes | 2025-08-13 | 2026-03-04 | 2026-03-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-26 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-06-13 | 2025-11-26 | 2025-11-26 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-16 | 01.S4 |  |  | 2 | 2.9 | 0724 |  | R3 ITC1 | [6 empty] | 2025-02-20 | 2025-03-21 | 2025-02-20 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-08-08 | 2025-07-21 | 2025-07-21 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-07-21 | 2025-12-01 |  | 2026-02-26 | 2026-02-26 | 2026-03-04 | 2026-02-26 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-10 | 2025-04-18 | 2025-03-21 | S4 | 2025-06-27 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1851 | [7 empty] | 4. Completed | 17. FUT In progress | 2/23 - FUT with PDF-SMH planned on 2/24. 02/20 : E2E Session is done and Defect fix in WIP. 02/16 : E2E FUT is planned on 02/17 and ETA 02/20. 02/12 : FUT is in WIP. 01/13 : E2E FUT is planned in Sprint 23. 01/06 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 01/09.Completing this task by 01/09 is at risk due to outstanding readiness issues with PDF SMH. 12/18 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/19. 12/12 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/15. | 2025-11-26 | N | 08. FTS IP |  |  |  | 02/23: FUT walkthru scheduled in W9 Current status:FUT walkthru scheduled in W9 Issue: n/a Next steps: Complete walkthru and send for approval Help needed: n/a FUT ETA: 02/27 | Week 2 Target | 3. Watch item | 4. PDF SMH S23 | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-08-08 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1991 | FTSI0689 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle DLCP update in S4 based on the DLCP UPDATE event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1991_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20DLCP%20UPDATE%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w9b75c12cad634fc58eef95cacb1a8193&csf=1&web=1&e=4rfp6X | 02.No | 01.Yes |  | 2024-10-03 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | MULESOFT | 2024-12-02 | 2025-01-31 | 2024-11-15 | 100% | 2025-01-08 | 2025-02-07 | 2025-02-14 | 2025-03-21 | 100% | 2025-03-19 | 2025-03-07 | 2025-03-21 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-17 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-04 | 2025-09-10 | No | 2025-08-13 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-04-18 | 2025-09-10 | 2025-09-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-16 | 01.S4 |  |  | 1 | 1.45 | 0689 |  | R3 ITC1 | [6 empty] | 2025-01-08 | 2025-01-31 | 2025-01-08 |  | 2025-03-19 | 2025-03-21 | 2025-03-19 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-04-18 | 2025-04-17 | 2025-04-17 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-08-04 | 2025-09-10 |  |  | 2025-12-04 | 2025-12-05 | 2025-12-04 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-31 | 2025-03-21 | 2025-03-21 | S4 | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1932 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Sent email to Intel for approval | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1988 | FTSI0686 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle production order merge events in S4 based on the MERGE event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1988_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20MERGE%20events%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w77f1b0acd3724cb39c5d0a1e600e3cc5&csf=1&web=1&e=MBs0nX | 02.No | 01.Yes |  | 2024-10-03 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-12-02 | 2025-01-31 | 2024-11-15 | 100% | 2024-12-11 | 2025-01-10 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-07 | 2025-01-31 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-15 | 2025-01-31 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-15 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-28 | 2025-09-10 | No | 2025-08-13 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-27 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-16 | 01.S4 |  |  | 2 | 2.9 | 0686 |  | R3 ITC1 | [6 empty] | 2024-12-11 | 2025-01-31 | 2024-12-11 |  | 2025-02-07 | 2025-02-21 | 2025-02-07 |  | 2025-03-15 | 2025-03-15 | 2025-03-15 | 2025-03-15 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-28 | 2025-09-10 |  |  | 2025-11-27 | 2025-11-27 | 2025-11-27 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-31 | 2025-02-21 | 2025-01-24 | MW | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1930 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/18: Sent to intel for approval 11/14 - Awaiting approval (no open defects). FUT Approval ETA 11/18 10/30 - Awaiting approval 10/24 - FUT in progress 10/17: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF |  |  |  | Current Status: Awaiting approval Issue: FUT was delayed from past sprint Next Steps: Awaiting approval Help Needed: N/A Awaiting Approval 1211 ETA 1120 |  | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-15 | 2025-03-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2216 | FTSI0677 | 02.Interface | 02.IF - Intel Foundry | API from SHIP server to validate shipment readiness” | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 09. FUT Overdue | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2216_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20PACK%20and%20MOVE%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=wcdb4724ef86346f18c67f4ef2f6e6e0e&csf=1&web=1&e=2KHOMV | 02.No | 01.Yes |  | 2024-09-30 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 01.Very High | Manufacturing Integration | 01.Yes | 7129 | ShipServer | PDF | S/4 | MULESOFT | 2025-02-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-12 | 2025-08-15 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-03 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-12-31 | 2025-08-18 | 2025-09-12 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-29 | 2025-07-01 | 2026-02-13 | 2026-02-13 | 100% | 2026-04-03 | 2025-12-31 | 2026-04-03 | No |  | 2026-03-23 | 2026-03-23 |  | 100% | 90% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-23 | N | 95% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-08 | 2026-02-13 | 2026-02-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-04-06 21:15 | 9 | 2024-10-01 | 01.S4 |  |  | 4 | 5.8 | 0677 |  | R3 ITC1 | [6 empty] | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-09-03 | 2025-09-26 | 2025-09-03 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-29 | 2025-09-29 |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2025-12-31 | 2026-04-03 |  |  |  | 2026-03-23 | 2026-03-06 |  |  |  |  | WIP Inventory Shipping | 2025-02-21 | 2025-04-18 | 2025-03-21 | S4 | 2025-05-25 |  |  |  | 0 | 08. Not Applicable | 1615 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 4/3: Defect fix with tech tech nical team, walkthrough in progress 3/27: working with Tech Team on defects 3/20: working with Tech Team on defects 3/13: 3 defects created to tech team, team working on it 3/6:Very high complexity with several complicated use cases, currently working through final set of defects 2/23 - Defect fix in progress 2/20:CR1081 in progress 2/13:02/12: CR 1543 development in progress 02/12: CR 1543 development in progress 01/06: CR 1543 development in progress 01/14: Replanned for S23 | 2026-02-13 | Y | 07. FTS IF |  |  |  | 03/23: Defect fix and S4 FUT in progress. Issue: FUT delayed Next Steps: Expedite S4 FUT completion and continue FUT once defects are fixed. Help Needed: N/A FUT ETA: 04/03 | Spill over |  | On track for S23+ | Defects | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2217 | FTSI0676 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle undo complete in S4 based on the UNDO COMPLETE event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2217_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20UNDO%20COMPLETE%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w9cda88ef95a5423ca35be31b33e833fd&csf=1&web=1&e=dTXPYo | 02.No | 01.Yes |  | 2024-09-30 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | PDF | S/4 | APIGEE | 2024-12-02 | 2025-01-31 | 2024-12-13 | 100% | 2024-12-10 | 2024-12-17 | 2024-12-24 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-07 | 2025-02-21 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-07 | 2025-02-21 | 2025-04-23 | 100% | 2025-08-04 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-04 | 2025-09-10 | Yes | 2025-07-16 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-03-21 | 2025-09-10 | 2025-09-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 |  |  | 1 | 1.45 | 0676 |  | R3 ITC1 | [6 empty] | 2024-12-10 | 2025-01-31 | 2024-12-10 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-08-04 | 2025-09-10 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-31 | 2025-02-21 | 2025-01-24 | S4 | 2025-05-25 |  |  |  | 0 | 08. Not Applicable | 1616 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/09: Awaiting confirmation | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2220 | FTSI0675 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle mid stage transfers in S4 based on the MID STAGE TRANSFER event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2220_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20MID%20STAGE%20TRANSFER%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=wf5edbb5657dd4dbb8bc6cf2f6fd9123a&csf=1&web=1&e=78vp6W | 02.No | 01.Yes |  | 2024-09-30 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-11-18 | 2025-01-15 | 2024-12-13 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-07-04 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-04 | 2025-04-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-03-24 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-11 | 2025-04-21 | 2025-05-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-21 | 2025-09-10 | No | 2025-07-16 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-05-16 | 2025-09-10 | 2025-09-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 |  |  | 1 | 1.45 | 0675 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-15 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-07-21 | 2025-09-10 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-15 | 2025-04-18 | 2025-04-18 | S4 | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 1624 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Sent email to Intel for approval | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2221 | FTSI0674 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle undo move and scrap in S4 based on the UNDO MOVE event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2221_M-100-220_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20UNDO%20MOVE%20or%20SCRAP%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w3c5e297e9e9349b9b1de9151a42d2a58&csf=1&web=1&e=pbOgjP | 02.No | 01.Yes |  | 2024-09-30 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-12-02 | 2025-01-31 | 2024-12-13 | 100% | 2024-12-17 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 100% | 2025-08-20 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-08 | 2025-03-07 | 2025-03-21 | 2025-03-07 | 100% | 2025-03-08 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-19 | 2025-09-10 | Yes | 2025-07-16 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 |  |  | 1 | 1.45 | 0674 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2025-01-31 | 2024-12-17 |  | 2025-08-20 | 2025-08-20 | 2025-08-20 |  | 2025-03-08 | 2025-03-21 | 2025-03-08 | 2025-03-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-19 | 2025-09-10 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2025-01-31 | 2025-03-21 | 2025-01-24 | MW | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 1625 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - Awaiting approval 10/17: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1888 | FTSI0492 | 02.Interface | 01.IP - Intel Product | Interface between E2Open and S4 for goods issue against production order | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B600930A4-B0AA-49B2-A0F0-19A90CBFE1BA%7D&file=M-090FTS_IP_S4%20Inbound%20Interface%20to%20update%20Goods%20Consumption%20against%20Production%20Order%20in%20S4%20based%20on%20trigger%20from%20OSAT%20via%20E2Open.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-31 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208; 59283 | E2open; PDF Sapience Manufacturing Hub Integration Platform - IP | E2Open | S/4 | APIGEE | 2025-02-24 | 2025-03-21 | 2024-09-20 | 100% | 2024-11-29 | 2024-12-16 | 2025-04-18 | 2025-11-05 | 100% | 2025-10-28 | 2025-04-21 | 2025-05-16 | 2025-01-17 | 100% | 2025-01-08 | 2025-04-21 | 2025-05-16 | 2025-01-17 | 100% | 2025-01-08 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-28 | 2025-08-04 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-01 | 2025-10-28 | 2025-12-01 | Yes | 2025-07-16 | 2026-01-31 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-07 | 2025-11-26 | 2025-11-26 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-04-03 08:07 | 10 | 2024-11-19 | 01.S4 |  |  | 1 | 1.45 | 0492 |  | R3 ITC1 | [6 empty] | 2024-11-29 | 2025-03-21 | 2024-11-29 |  | 2025-10-28 | 2025-11-05 | 2025-10-28 |  | 2025-01-08 | 2025-05-16 | 2025-01-08 | 2025-01-08 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-11-07 | 2025-10-28 | 2025-10-28 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-10-28 | 2025-12-01 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-05-16 | 2025-01-16 | MW | 2025-06-02 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1697 | [7 empty] | 1. On Track | 17. FUT In progress | 02/02 : E2E FUT started with PDF SMH ETA 02/06. 01/21 : E2E FUT is planned in Sprint 22. 01/06 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 01/09.Completing this task by 01/09 is at risk due to outstanding readiness issues with PDF SMH. 12/18 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/19. 12/12 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/15. | 2025-11-26 | N | 08. FTS IP |  |  |  | 02/04 : E2E FUT is in progress. Defect S4 fixes in progress. ETA is 2/6 Current state: Build complete. E2E FUT planned on 01/28 Issue: None Next steps: To conduct E2E FUT as per plan. Help needed: N/A | Testing planned in WW04 but not started | 2. Risk | 1. PDF SMH S22 | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-05-16 | 2025-01-08 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | Yes |  | 2026-02-17 | 2026-03-27 | 2026-04-10 | 85% | Yes | 2026-03-13 | 2026-03-04 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1889 | FTSI0491 | 02.Interface | 01.IP - Intel Product | Interface between E2Open and S4 for capturing confirmation of scrap against production order | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1DA2AEB7-6031-4C6B-896D-1DA49E2F05E9%7D&file=M-090FTS_IP_S4%20Inbound%20Interface%20to%20update%20Scrap%20Quantity%20against%20Prod%20Order%20in%20S4%20based%20on%20trigger%20from%20OSAT%20via%20E2Open.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-31 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208; 59283 | E2open; PDF Sapience Manufacturing Hub Integration Platform - IP | E2Open | S/4 | APIGEE | 2025-02-24 | 2025-03-21 | 2024-09-20 | 100% | 2024-11-29 | 2024-12-16 | 2025-04-18 | 2025-11-05 | 100% | 2025-10-28 | 2025-04-21 | 2025-05-16 | 2025-01-31 | 100% | 2025-01-07 | 2025-04-21 | 2025-05-16 | 2025-01-31 | 100% | 2025-01-07 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-05 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-28 | 2025-08-04 | 2025-11-26 | 2025-11-26 | 100% | 2025-12-01 | 2025-10-28 | 2025-12-01 | Yes | 2025-07-16 | 2026-03-04 | 2026-03-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-19 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-11-07 | 2025-11-26 | 2025-11-26 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-04-03 08:07 | 10 | 2024-07-31 | 01.S4 |  |  | 1 | 1.45 | 0491 |  | R3 ITC1 | [6 empty] | 2024-11-29 | 2025-03-21 | 2024-11-29 |  | 2025-10-28 | 2025-11-05 | 2025-10-28 |  | 2025-01-07 | 2025-05-16 | 2025-01-07 | 2025-01-07 |  | 2025-11-07 |  | 2025-11-05 |  | 2025-11-07 | 2025-10-28 | 2025-10-28 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-10-28 | 2025-12-01 |  |  | 2026-02-19 | 2026-03-04 | 2026-02-19 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-05-16 | 2025-01-16 | MW | 2025-03-28 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1698 | [7 empty] | 1. On Track | 17. FUT In progress | 02/16 : E2E FUT is planned on 02/17 and ETA 02/20. 02/12 : Defect Fix in progress #7193. 01/13 : E2E FUT is planned in Sprint 23. 01/06 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 01/09.Completing this task by 01/09 is at risk due to outstanding readiness issues with PDF SMH. 12/18 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/19. 12/12 :CR INT-CR1107 Dev is WIP and Per our PDF SMH team, the TUT and Build completion date be 12/15. | 2025-11-26 | N | 08. FTS IP |  |  |  |  | Week 2 Target |  | 4. PDF SMH S23 | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-05-16 | 2025-01-07 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | Yes |  | 2026-02-17 | 2026-03-27 | 2026-04-10 | 85% | Yes | 2026-03-20 | 2026-03-13 | 2026-03-13 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1835 | FTSI0484 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle quantity or batch attribute updates based on the ADJUST (Quantity/Batch attributes) event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1835_M-100-080_FTS_IF_S4%20Inbound%20Interface%20to%20adjust%20quantity%20or%20batch%20attributes%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w6477dec4b905411a8bdd4ac85dfa2bd8&csf=1&web=1&e=M6X5c5 | 02.No | 01.Yes |  | 2024-07-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-09-02 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-01-24 | 100% | 2025-01-23 | 2025-03-10 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2025-03-10 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-19 | 2025-09-10 | Yes | 2025-08-13 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-07-26 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-15 | 01.S4 |  |  | 1 | 1.45 | 0484 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-23 | 2025-02-21 | 2025-01-23 |  | 2025-01-30 | 2025-03-21 | 2025-01-30 | 2025-01-30 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-19 | 2025-09-10 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-03-21 | 2025-01-24 | MW | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2155 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - Awaiting approval 10/17: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1836 | FTSI0483 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle production order split events in S4 based on the SPLIT event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1836_M-100-080_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20Split%20events%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w4381e578b73e4b3bb52c52f06352130e&csf=1&web=1&e=Dbhr8H | 02.No | 01.Yes |  | 2024-07-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-09-02 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-01-24 | 100% | 2025-01-17 | 2025-02-24 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2025-02-24 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-03-19 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-19 | 2025-09-10 | Yes | 2025-06-11 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-07-26 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-15 | 01.S4 |  |  | 2 | 2.9 | 0483 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-17 | 2025-02-21 | 2025-01-17 |  | 2025-01-30 | 2025-03-21 | 2025-01-30 | 2025-01-30 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-19 | 2025-03-19 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-19 | 2025-09-10 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-03-21 | 2025-01-24 | MW | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2156 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Sent email to Intel for approval | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1841 | FTSI0481 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 to handle production order complete events in S4 based on the COMPLETE event triggered by MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1841_M-100-080_FTS_IF_S4%20Inbound%20Interface%20to%20handle%20Complete%20event%20in%20S4%20based%20on%20trigger%20from%20MES%20via%20PDF.pptx?d=w417ca6ebb00642bbbc2996a9ce6bbf6a&csf=1&web=1&e=mYpGHW | 02.No | 01.Yes |  | 2024-07-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-08-12 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-01-24 | 100% | 2025-01-17 | 2025-02-24 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2025-02-24 | 2025-03-21 | 2025-01-31 | 100% | 2025-01-30 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2025-02-24 | 2025-03-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-28 | 2025-09-10 | Yes | 2025-07-16 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-07-26 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-15 | 01.S4 |  |  | 1 | 1.45 | 0481 | INT-CR0472 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-17 | 2025-02-21 | 2025-01-17 |  | 2025-01-30 | 2025-03-21 | 2025-01-30 | 2025-01-30 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-28 | 2025-09-10 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-03-21 | 2025-01-24 | MW | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2161 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Sent email to Intel for approval | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-03-21 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1686 | FTSI0422 | 02.Interface | 02.IF - Intel Foundry | Interface between PDF and S4 for production order process in S4 based on the START/ASSM event trigger from MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1686_M-090-110_FTS_IF_Interface%20between%20PDF%20and%20S4%20for%20production%20order%20process%20in%20S4%20based%20on%20the%20START%20or%20ASSM%20event%20trigger%20from%20MES.pptx?d=we7237b129fd9453289db340a59bccc65&csf=1&web=1&e=lJopeB | 02.No | 01.Yes |  | 2024-06-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | PDF | S/4 | APIGEE | 2024-07-29 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-02-14 | 100% | 2024-12-23 | 2025-01-31 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-08 | 2025-01-31 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-14 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-21 | 2025-09-10 | No | 2025-08-13 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-03-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0422 | INT-CR0472 | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-23 | 2025-02-14 | 2024-12-23 |  | 2025-03-08 | 2025-03-14 | 2025-03-08 |  |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-21 | 2025-09-10 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-02-21 | 2025-01-24 | MW | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 2722 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18: Sent to intel for approval 11/14: FUT in progress . FUT completion ETA is 11/19 10/30 - FUT in progress 10/24: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF |  |  |  | Current Status: Awaiting Approval Issue: FUT was delayed from past sprint Next Steps: Awaiting approval Help Needed :N/A ETA 1121 |  | 5. Review Closed |  | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-03-14 | 2025-03-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1691 | FTSI0421 | 02.Interface | 02.IF - Intel Foundry | Custom RFC triggered in S4 by PDF to determine activity values and post confirmation in S4 based on the MOVE/REJECT event for WIP from MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1691_M-100-080_FTS_IF_Custom%20RFC%20triggered%20in%20S4%20by%20PDF%20to%20determine%20activity%20values%20and%20post%20confirmation%20in%20S4%20based%20on%20the%20MOVEREJECT%20event%20for%20WIP%20from%20MES.pptx?d=wc7078f096e394dc887062a017d6b51bb&csf=1&web=1&e=f1F6lf | 02.No | 01.Yes |  | 2024-06-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | PDF | S/4 | APIGEE | 2024-09-02 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-01-24 | 100% | 2024-12-23 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-21 | 2025-09-10 | Yes | 2025-06-11 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-02-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0421 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-23 | 2025-01-24 | 2024-12-23 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-21 | 2025-09-10 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-01-31 | 2025-01-24 | MW | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 2723 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - Awaiting approval 10/17: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1692 | FTSI0420 | 02.Interface | 02.IF - Intel Foundry | Custom RFC triggered in S4 by PDF to post goods movement in S4 based on the REJECT event for Inventory from MES | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1692_M-100-080_FTS_IF_Custom%20RFC%20triggered%20in%20S4%20by%20PDF%20to%20post%20goods%20movement%20in%20S4%20based%20on%20the%20REJECT%20event%20for%20Inventory%20from%20MES.pptx?d=wc33806c35c8b496eb0a3481ff6d37587&csf=1&web=1&e=VzpAQf | 02.No | 01.Yes |  | 2024-06-26 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | PDF | S/4 | APIGEE | 2024-07-22 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-18 | 2024-12-13 | 2025-01-24 | 100% | 2024-12-23 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-25 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-25 | 2025-09-10 | Yes | 2025-06-11 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-02-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-06-25 21:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0420 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-23 | 2025-01-24 | 2024-12-23 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-25 | 2025-09-10 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-09-20 | 2025-01-31 | 2025-01-24 | MW | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 2724 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - Awaiting approval 10/17: Testing in progress from SMH | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 92 | FTSI0338 | 02.Interface | 02.IF - Intel Foundry | Interface from MES staging database to S/4 to create/update reference operation sets | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-090-290_FTS_Interface%20Automate%20Reference%20Operation%20Sets.pptx?d=w0e7618c89d2a4681899eff373b0b11a7&csf=1&web=1&e=dFuIuk | 02.No | 01.Yes |  | 2024-06-14 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-08-01 | 2024-08-23 | 2024-08-23 | 100% | 2024-10-18 | 2024-11-18 | 2024-12-13 | 2025-01-24 | 100% | 2024-12-23 | 2025-02-03 | 2025-02-21 | 2025-01-31 | 100% | 2025-01-30 | 2025-02-03 | 2025-02-21 | 2025-01-31 | 100% | 2025-01-30 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-25 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-25 | 2025-09-10 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-02-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-06-14 00:11 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0338 |  | R3 ITC1 | [6 empty] | 2024-10-18 | 2024-10-18 | 2024-10-18 |  | 2024-12-23 | 2025-01-24 | 2024-12-23 |  | 2025-01-30 | 2025-02-21 | 2025-01-30 | 2025-01-30 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-03-25 | 2025-09-10 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-08-23 | 2025-02-21 | 2025-01-24 | MW | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 1485 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18: Sent email to Intel for approval | 2025-09-10 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-02-21 | 2025-01-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 664 | FTSI0311 | 02.Interface | 02.IF - Intel Foundry | Production plan from ECA planning data hub (PDH) to S/4 to create planned Orders | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/664_PLB-020-120_FTS_IF_Interface%20Production%20Plan%20from%20ECA%20to%20S4%20to%20create%20Planned%20Orders,%20PO,%20Subcon%20PO.pptx?d=wa3d93313b8204070a96e62c567c06d22&csf=1&web=1&e=nGwcnR | 02.No | 01.Yes |  | 2024-06-07 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | PDH (ECA) | S/4 | BODS | 2024-12-02 | 2025-01-31 | 2024-10-18 | 100% | 2024-10-18 | 2025-02-15 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-13 | 2025-02-21 | 2025-03-07 | 2025-03-14 | 100% | 2025-03-08 | 2025-02-21 | 2025-03-07 | 2025-03-14 | 100% | 2025-03-08 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | [5 empty] | 2025-03-21 | 2025-03-21 | No | 2025-09-10 | 2026-03-04 | 2026-03-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-08 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-07 06:50 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0311 | INT-CR0472 | R3 ITC1 | [6 empty] | 2024-10-18 | 2025-01-31 |  |  | 2025-02-13 | 2025-02-21 | 2025-02-13 |  | 2025-03-08 | 2025-03-14 | 2025-03-08 | 2025-03-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-03-21 |  | 2025-03-21 |  |  |  |  | 2025-03-21 | 2025-03-21 |  | 2026-03-08 | 2026-03-08 | 2026-03-08 | 2026-03-08 | [5 empty] | 2025-01-31 | 2025-03-07 | 2025-01-24 |  | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 1939 | [7 empty] | 4. Completed | 3. Awaiting Approval | 3/6:Awaiting approval pending 2/27: FUT In progress PDH CR in WIP. MW is making changes 6230 ALM 7250 defect closed, AIF functionality tested and working fine, Email id getting setup for receiving mail. Visible in SOST. | 2025-03-21 | N | 07. FTS IF |  |  |  | 0106: Added to S22 plan Current status: SCP FUT dates are provided. E2E FUT planned in S22. Issue: Parallel FUT to be planned due to SCP FUT pushout Next steps: SCP FUT dates are 1/30. E2E FUT planned to be done in parallel. Help needed: SCP team to expedite SCP FUT as much as possible | Week 4 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 11 |  | 2025-03-14 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 665 | FTSI0310 | 02.Interface | 02.IF - Intel Foundry | Network Plan from ECA Planning Data Hub to S/4 for STO Creation | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BDE51A0D3-D99B-4A25-BBE7-74244AD8AC04%7D&file=665_PLB-020-120_FTS_IF_Network%20Plan%20from%20ECA%20Planning%20Data%20Hub%20to%20S4%20for%20STO%20creation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-06-07 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | PDH (ECA) | S/4 | BODS | 2024-12-02 | 2025-01-31 | 2024-08-23 | 100% | 2024-07-30 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-13 | 2025-02-21 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-08 | 2025-02-21 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-08 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-05-16 | 100% | 2025-08-04 | [5 empty] | 2025-08-04 | 2025-08-04 | No | 2025-08-13 | 2026-02-20 | 2026-03-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-07 06:50 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0310 | INT-CR0472 | R3 ITC1 | [6 empty] | 2024-07-30 | 2025-01-31 | 2024-07-30 |  | 2025-02-13 | 2025-02-21 | 2025-02-13 |  | 2025-03-08 | 2025-03-08 | 2025-03-08 | 2025-03-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  |  |  | 2025-08-04 | 2025-08-04 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-01-31 | 2025-03-07 | 2025-01-24 |  | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 1940 | [7 empty] | 4. Completed | 3. Awaiting Approval | 2/27:Awaiting approval Pending 2/23 - FUT to be reviewed on 2/24. 2/20: FUT document preparation in progress, walkthrough planned 2/24 2/13: FUT in progress, awaiting BODS changes to be completed | 2025-03-21 | N | 07. FTS IF |  |  |  | 0106: Added to S22 plan Current status: SCP FUT dates are provided. E2E FUT planned in S22. Issue: Parallel FUT to be planned due to SCP FUT pushout Next steps: SCP FUT dates are 1/30. E2E FUT planned to be done in parallel. Help needed: SCP team to expedite SCP FUT as much as possible | Week 3 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-03-08 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 667 | FTSI0308 | 02.Interface | 02.IF - Intel Foundry | Interface from PDF to S/4 to update Lot level out date on Production orders | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/667_M-170-210-110_FTS_IF_Interface%20from%20PDF%20to%20S4%20to%20update%20Lot%20level%20out%20date%20on%20prod%20orders.pptx?d=wbb8de012f04d46358b83b4dcc945f559&csf=1&web=1&e=H2k2RU | 02.No | 01.Yes |  | 2024-06-07 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Manufacturing Integration | 01.Yes | 41627 | PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF | MES | S/4 | APIGEE | 2024-06-24 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-05 | 2024-11-18 | 2024-12-13 | 2024-12-20 | 100% | 2024-12-20 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-24 | 2024-12-20 | 100% | 2024-12-20 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-01-28 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-01-28 | 2025-09-10 | Yes | 2025-06-11 | 2025-11-05 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-02-21 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-06-07 06:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0308 |  | R3 ITC1 | [6 empty] | 2024-08-05 | 2024-08-23 | 2024-08-05 |  | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 |  | 2025-01-24 |  | 2024-12-20 |  | 2025-02-21 | 2025-01-28 | 2025-01-28 |  | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-01-28 | 2025-09-10 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 |  |  |  |  | PDF-SMH (CIBR Replacement) | 2024-08-23 | 2025-01-31 | 2025-01-24 | MW | 2025-03-28 |  |  |  | 0 | 08. Not Applicable | 1941 | [7 empty] | 2. At Risk | 12. Blocked by SAP OSS | 12/4:FUT completed marked 100& in sprint plan | 2025-09-10 | N | 07. FTS IF |  |  |  | FUT in Progress. Roadblock removed OSS Current Status: SAP reverted with Note (OSS 1143956). Note implemented. FUT in progress. Issue: Std. API is not working for changing prod. order dates. Next Steps: SAP engaged their developers to further look into the issue. If the issue is not getting resolved, then API to be replaced with BAPI. Help Needed: N/A ETA - TBD (based on response from SAP in next 2-3 days) |  | 3. Watch item | 1 | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 626 | FTSI0268 | 02.Interface | 01.IP - Intel Product | Interface to be developed from S/4 to E2Open to transmit Build Instruction​ detail to Supplier(IP) | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/626_PM-110-010-0001_PTP_Interface%20from%20S4%20to%20E2OPen%20to%20transmit%20Build%20Instruction_IP.pptx?d=wf7fc46e16d36499abf1f1524fd57d858&csf=1&web=1&e=XHjNvh | 02.No | 01.Yes |  | 2024-05-24 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12208 | E2open | S/4 | E2Open | MULESOFT | 2025-01-27 | 2025-02-07 | 2024-09-20 | 100% | 2024-11-22 | 2025-03-14 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-24 | 2025-02-07 | 2025-02-21 | 2025-03-28 | 100% | 2025-04-10 | 2025-02-07 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-10 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-05-19 | 2025-06-13 | 2025-04-11 | 100% | 2025-04-10 | 2025-10-20 | 2025-12-01 | 2025-12-01 | 100% | 2025-12-01 | 2025-04-10 | 2025-12-01 | Yes | 2026-01-26 | 2026-01-30 | 2026-01-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-01-24 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-06-13 | 2025-12-01 | 2025-12-01 | pgaroo@deloitte.com | 2024-05-24 01:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0268 |  | R3 ITC1 | [6 empty] | 2024-11-22 | 2025-02-07 | 2024-11-22 |  | 2025-02-24 | 2025-03-21 | 2025-02-24 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-06-13 | 2025-04-10 | 2025-04-10 |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-04-10 | 2025-12-01 |  |  | 2026-01-24 | 2026-01-30 | 2026-01-24 |  |  |  |  | B2B - E2open | 2025-02-07 | 2025-04-18 | 2025-02-21 |  | 2026-01-30 |  |  |  | 0 | 01.4 Suppliers that engage with E2Open | 1596 | [7 empty] | 1. On Track | 25. Requirement Change | 01/21 : Defect fix in WIP and parallelly FUT testing in progress. 01/13 : E2E FUT is in WIP and sprint 22. 12/15 : Testing is in progress and Defect #5599 is with Dev team for changes. 11/18 - Dependency on INT-CR0582. ETA from tech team for CR completion - 11/28. | 2025-12-01 | N | 08. FTS IP |  |  |  | 0106 Current status: CR development complete, E2E FUT initiated Issue: Defect fix in progress Next steps:E2E FUT to be completed for build instructions from IP S4 to IF S4 Help needed: Tech team to complete defect fixes on priority |  | 3. Watch item |  | CR/Design change | Complete | R3 Build & UT Sprint 20 |  | 2025-04-18 | 2025-04-10 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-12 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 216 | FTSI0210 | 02.Interface | 01.IP - Intel Product | Interface Function to Create Purchase Requisitions from ECA to S/4 | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PLB-020-040_FTS_IP_Interface%20Purchase%20Requisitions%20and%20STR%20into%20S4.pptx?d=w669d467978e4438a99f7c303976867f7&csf=1&web=1&e=aZTAop | 02.No | 01.Yes |  | 2024-05-27 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA (PDH) | S/4 | BODS | 2025-04-21 | 2025-05-16 | 2024-07-26 | 100% | 2024-07-22 | 2025-05-19 | 2025-05-22 | 2025-02-21 | 100% | 2025-02-13 | 2025-05-23 | 2025-05-27 | 2025-03-14 | 100% | 2025-03-08 | 2025-05-28 | 2025-06-06 | 2025-03-14 | 100% | 2025-03-08 | 2025-05-23 | 2025-05-27 | 2025-02-21 | 100% | 2025-02-21 | 2025-06-09 | 2025-06-11 | 2025-05-16 | 100% | 2025-08-04 | [5 empty] | 2025-08-04 | 2025-08-04 | Yes | 2025-09-10 | 2026-01-31 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-05 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-06-11 | 2025-06-11 | 2025-06-11 | pgaroo@deloitte.com | 2024-05-15 07:19 | cell-link@smartsheet.com | 2026-03-12 08:23 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0210 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2025-05-16 | 2024-07-22 |  | 2025-02-13 | 2025-05-22 | 2025-02-13 |  | 2025-03-08 | 2025-05-27 | 2025-03-08 | 2025-03-08 |  | 2025-05-27 |  | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2024-07-26 | 2025-03-07 | 2025-01-24 |  | 2025-04-11 |  |  |  | 0 | 08. Not Applicable | 2819 | [7 empty] | 4. Completed | 14. B-App Under Test | 02/02 : E2E FUT call scheduled on 02/02 and will complete by 02/06. 01/21 : Awaiting for PDH build and S/4 FUT Completed. Planning to complete in sprint 22. | 2025-06-11 | N | 08. FTS IP |  |  |  | 02/04 : E2E FUT is in progress and call scheduled today. ETA is 2/6 Current state: Build complete. E2E FUT planned on 02/03 Issue: None Next steps: To conduct E2E FUT as per plan. Help needed: N/A | MW changes are needed. Effort Estimate is 2-3 days | 3. Watch item | 2. PDH S22 | BA Readiness | Complete | R3 Build & UT Sprint 16 |  | 2025-06-06 | 2025-03-08 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | Yes | Regression testing impact | No |  | 2026-03-09 | 2026-04-10 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-12 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 217 | FTSI0209 | 02.Interface | 01.IP - Intel Product | Interface to create Production Order from ECA to S/4 | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-090-110_FTS_RFC%20Interface%20to%20create%20Production%20Order%20from%20ECA%20to%20S4.pptx?d=w457b9a9d813b4104971bf7feb7886e92&csf=1&web=1&e=IWpEM7 | 02.No | 01.Yes |  | 2024-05-27 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA (PDH) | S/4 | BODS | 2024-06-24 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-14 | 2024-12-16 | 2025-04-07 | 2025-02-21 | 100% | 2025-02-13 | 2025-03-24 | 2025-04-18 | 2025-01-17 | 100% | 2025-01-08 | 2025-03-24 | 2025-04-18 | 2025-01-17 | 100% | 2025-01-08 | 2024-12-16 | 2025-01-16 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | [5 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-07 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-15 07:19 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0209 | INT-CR0314 | R3 ITC1 | [6 empty] | 2024-08-14 | 2024-08-23 | 2024-08-14 |  | 2025-02-13 | 2025-04-07 | 2025-02-13 |  | 2025-01-08 | 2025-04-18 | 2025-01-08 | 2025-01-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | [5 empty] | 2024-08-23 | 2025-04-18 | 2025-01-16 |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2820 | [7 empty] | 1. On Track | 14. B-App Under Test | 02/02 : S/4 FUT completed and E2E FUT call scheduled on 02/04 and will complete by 02/06. One session had completed by Bapp on 01/30. 01/21 : Awaiting for PDH build and S/4 FUT WIP. | 2025-05-16 | N | 08. FTS IP |  |  |  | 02/04 : E2E FUT call scheduled today. ETA is 2/6 Current state: Build complete. Defect fix is in progress. E2E FUT planned on 01/30 Issue: None Next steps: To conduct E2E FUT as per plan. Help needed: N/A | PDH Build is pending | 3. Watch item | 2. PDH S22 | BA Readiness | Complete | R3 Build & UT Sprint 16 |  | 2025-04-18 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 111 | FTSI0050 | 02.Interface | 02.IF - Intel Foundry | Interface to transfer Purchase Requisitions created in IBP/MAPPS/other systems from ECA to S/4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/PLB-020-040_FTS_Interface%20Purchase%20Requisitions%20into%20S4.pdf?csf=1&web=1&e=xjmcuP | 02.No | 01.Yes |  | 2024-04-09 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA | S/4 | BODS | 2024-06-24 | 2024-08-23 | 2024-08-23 | 100% | 2024-07-30 | 2024-08-06 | 2024-08-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-07 | 2025-02-21 | 2025-09-26 | 100% | 2025-09-23 | 2025-02-07 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-08 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-04-18 | 2025-02-21 | 100% | 2025-02-25 | [5 empty] | 2025-03-08 | 2025-03-08 | No | 2025-09-10 | 2026-01-30 | 2026-01-30 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-30 | N | 100% | 2026-02-03 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-04-09 01:36 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0050 |  | R3 ITC1 | [6 empty] | 2024-07-30 | 2024-08-23 | 2024-07-30 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 | 2025-03-08 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-18 | 2025-02-25 | 2025-02-25 |  |  |  |  | 2025-03-08 | 2025-03-08 |  |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | [5 empty] | 2024-08-23 | 2025-02-21 | 2025-01-24 |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 1529 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/2:Awaiting approval, presented on 01/29 01/21: Defect fix completed, AIF Email functionality is still in progress 01/06 - FUT in progress, BODS raised defect to S4 tech team. 01/14: Replanned for S22 | 2025-04-18 | N | 07. FTS IF |  |  |  | 0106: Added to S22 plan Current status: SCP FUT dates are provided. E2E FUT planned in S22. Issue: Parallel FUT to be planned due to SCP FUT pushout Next steps: SCP FUT dates are 1/30. E2E FUT planned to be done in parallel. Help needed: SCP team to expedite SCP FUT as much as possible |  |  |  |  | Complete | R3 Build & UT Sprint 11 |  | 2025-03-08 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2923 | FTSF1361 | 05.Form | 02.IF - Intel Foundry | Factory Portal - Returns Order Flow (Form-Based (CRD) Return Order​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-05 | 2025-08-11 | 2025-08-15 | 2025-08-01 | 100% | 2025-08-26 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-26 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-26 | [15 empty] | 2025-08-26 | 2025-08-26 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-13 | 2025-08-13 | 2025-08-13 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-02 | 01.S4 |  |  | 1 | 0.69 | 1361 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-13 | 2025-06-05 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | [12 empty] | 2025-08-26 | 2025-08-26 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | [5 empty] | 2025-06-13 | 2025-08-13 |  |  | 2025-10-08 |  | WIINGS Only | TRUE | 0 |  | 2899 |  |  | WIINGS | [7 empty] | 2025-08-13 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 3131 | FTSE1701 | 04.Enhancement | 01.IP - Intel Product | Enhancement to automate updation of Routing_Prod versions with reference to S4 BoMs & S4 PIRs for IP products ordered on IF | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3131_FTS_IP_Manufacturing_Enhancement%20to%20automate%20creation%20of%20Routing_Prod%20versions%20with%20reference%20to%20S4%20BoM.pptx?d=wcf5e96fde7fa455eb23bc6b135f97109&csf=1&web=1&e=MLKDDg | 02.No | 01.Yes |  | 2025-10-03 | Kumar Vytla | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-12-12 | 100% | 2025-12-08 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 |  |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-11-14 03:30 | cell-link@smartsheet.com | 2026-03-30 21:18 | 10 | 2025-10-17 | 01.S4 |  |  | 1 | 1 | 1701 | INT-CR1193 | R3 ITC1 | [6 empty] | 2025-12-08 | 2025-12-12 | 2025-12-08 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | [12 empty] | 2026-01-09 | 2026-01-09 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-11-07 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3385 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/06 : Awaiting for approval ETA 03/06. 2/27 - Defect 7826 WIP 02/26 : Defect is fixed and FUT is in WIP 02/23 : Defect #7486 fix is in progress. 02/16 : FUT is in WIP 02/20 01/13 : Still Dev is WIP ETA 01/20 and will planned in S23. 12/12 : Dev is WIP ETA 12/19. | 2026-01-09 | N | 08. FTS IP |  |  |  |  | Week 3 Target |  | 5. S23 | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2026-01-09 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-31 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3178 | FTSE1694 | 04.Enhancement | 01.IP - Intel Product | Enhancement to Introduction of additional restrictions by MRP Area for S4 IP MRP related T-codes | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3178_FTS_IP_Manufacturing_Enhancement%20to%20Introduction%20of%20additional%20restrictions%20by%20MRP%20Area%20for%20S4%20IP%20MRP%20related%20Tcodes.pptx?d=w7a1fb01900a94553a83e1fbc814bba02&csf=1&web=1&e=LuhSfJ | 02.No | 01.Yes |  | 2025-10-29 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-09 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-03-04 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-18 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-11-05 05:23 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2025-11-24 | 01.S4 |  |  | 1 | 1 | 1694 |  | R3 ITC1 | [6 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-18 | 2026-03-04 | 2026-02-18 | [5 empty] | 2026-01-09 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3377 | [7 empty] | 1. On Track | 19. Incomplete Build | 02/18 : Approved. Smartsheet update pending. 02/16 : Defect is fixed and call scheduled for E2E FUT on 02/16. 02/12 : Defect Fix and testing in progress. | 2026-01-09 | N | 08. FTS IP |  |  |  |  | Week 2 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-26 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-02-19 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3131 | FTSE1653 | 04.Enhancement | 01.IP - Intel Product | Enhancement to automate creation of Routing_Prod versions with reference to S4 BoMs & S4 PIRs for IP products ordered on IF | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3131_FTS_IP_Manufacturing_Enhancement%20to%20automate%20creation%20of%20Routing_Prod%20versions%20with%20reference%20to%20S4%20BoM.pptx?d=wcf5e96fde7fa455eb23bc6b135f97109&csf=1&web=1&e=MLKDDg | 02.No | 01.Yes |  | 2025-10-03 | Kumar Vytla | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-30 | 2025-11-21 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2026-02-24 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-24 | [15 empty] | 2026-02-24 | 2026-02-24 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-07 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-03 05:27 | cell-link@smartsheet.com | 2026-03-30 06:37 | 10 | 2025-10-17 | 01.S4 |  |  | 2 | 2 | 1653 | INT-CR1193 | R3 ITC1 | [6 empty] | 2025-10-30 | 2025-11-07 | 2025-10-30 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | [12 empty] | 2026-02-24 | 2026-02-24 |  |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | [5 empty] | 2025-11-07 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3319 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/06 : Awaiting for approval ETA 03/06. 2/27- Defect 7832 - WIP 2/26- Defect 7561 in progress. 02/20 : Defect fix and Walkthrough Done and awaiting for approval 02/09 : Defect fix is in progress and ETA 02/13. 02/02 : FUT documentation is WIP and ETA 02/06 for approval. 01/21 : Defect Fix in progress. 01/06 : Testing is in progress. 12/18 : Still Dev is WIP ETA 12/19. 12/12 : Dev is WIP ETA 12/19. | 2025-12-05 | N | 08. FTS IP |  |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-24 | 2026-02-24 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-20 | 2026-03-13 | 2026-03-30 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 3122 | FTSE1645 | 04.Enhancement | 02.IF - Intel Foundry | Wafer Stock management for Reclaim Purposes | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3122_FTS-IF_WaferStock%20Creation_ReclaimPurpose.pptx?d=wa93a4d3df1c64637a9547d3b06c8af44&csf=1&web=1&e=hh9rHm | 02.No | 01.Yes |  | 2025-10-22 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2026-01-12 | 2026-01-16 | 2025-12-12 | 100% | 2026-01-29 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-12 | [15 empty] | 2026-01-12 | 2026-01-12 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-07 | 2026-01-07 | N | 100% | 2026-01-11 | Not Applicable | R3 Build & UT Sprint 21 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-22 | 01.S4 |  |  | 1 | 1 | 1645 | INT-CR0811 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-12 | 2026-02-06 | 2026-01-12 | 2026-01-12 | [12 empty] | 2026-01-12 | 2026-01-12 |  |  | 2026-01-11 | 2026-01-11 | 2026-01-11 | [5 empty] | 2025-11-07 | 2026-02-06 |  |  | 2026-01-07 |  |  |  | 0 |  | 3304 | [7 empty] | 2. At Risk | 19. Incomplete Build | 01/06 - FUT in progress | 2026-02-06 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3119 | FTSE1642 | 04.Enhancement | 01.IP - Intel Product | Enhancement to create a user exit (or) Business Add In to update Components and Operations against a Production Order. | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3119_M-090-110_FTS_IP_Enhancement%20to%20create%20a%20user%20exit%20(or)%20Business%20Add%20In%20to%20update%20Components%20and%20Operations%20against%20a%20Production%20Order.pptx?d=w40e8220b14674e3aa9dc0379f34fad77&csf=1&web=1&e=7rOYHk | 02.No | 01.Yes |  | 2025-10-14 | kumar.vytla@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-30 | 2026-01-12 | 2026-01-16 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-28 03:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-17 | 01.S4 |  |  | 1 | 1 | 1642 | INT-CR1159 | R3 ITC1 | [6 empty] | 2025-09-30 | 2025-10-08 | 2025-09-30 |  | 2025-12-06 | 2026-01-16 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | [5 empty] | 2025-10-08 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3297 | [7 empty] | 1. On Track | 17. FUT In progress | 02/02 : Walkthrough schedule on 02/02 01/30 : FUT In progress 01/21 : FUT is in progress and planned to complete by 01/30 01/13 : E2E FUT is planned in Sprint 22. 01/06 : Testing is in progress. . | 2025-12-05 | N | 08. FTS IP |  |  |  | 02/04: FUT walkthrough is completed. Feedback needs to be addressed which requires a code fix. Still targeting for 2/6 Current state: FUT and defect fixes in progress. Issue: Defect #6658 Next steps: Fix defects and complete FUT. Help needed: N/A ETA: 02/02 | User Exit primarily updates the Components into the Production Order. | 3. Watch item | 2. User Exit S22 | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 3118 | FTSE1641 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to create a program which can query on Master Data, Batch & STO details | 07. FTS IF | 7.1 FTS IF - ALL | 02. FS Unplanned | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF7F0B553-2624-47DF-A793-C684825BE092%7D&file=3118_Enhancement%20to%20create%20a%20program%20which%20can%20query%20on%20%20Master%20Data%2C%20Batch%20&%20STO%20details.pptx=&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-11-04 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-09-28 03:35 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 2 | 2025-11-04 | 01.S4 |  |  | 1 | 1 | 1641 | INT-CR1067 | R4 ITC1 | [50 empty] | 0 |  | 3296 | [7 empty] | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | [8 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3073 | FTSE1597 | 04.Enhancement | 01.IP - Intel Product | Develop a utility for mass creation of production orders via load file in SAP S4 system. | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3073_Develop%20a%20utility%20for%20mass%20creation%20of%20engineering%20production%20orders%20via%20load%20file%20in%20SAP%20S4%20system.pptx?d=w350fe5c4e8a248bf84815127bfc6f02f&csf=1&web=1&e=T12GZ4 | 02.No | 01.Yes |  | 2025-08-13 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-14 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-14 | [15 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-23 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 2 | 2 | 1597 | INT-CR1193, INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2026-02-14 | 2026-02-14 | 2026-02-14 | 2026-02-14 | [12 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3247 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 02/20 : Defect fixed and Testing in WIP. 02/16 : Walkthrough given on 02/12 and defect fix is WIP. ETA 02/20 02/12 : Defect fix and Walkthrough call schedule on 02/12 and ETA 02/20 02/09 : FUT documentation is WIP and ETA 02/13 for approval. 02/02 : Defect fix is in WIP and parallelly FUT is WIP. 01/21 : E2E FUT is planned in Sprint 22. | 2025-12-05 | N | 08. FTS IP |  |  |  |  | Week 2 Target |  |  | Defects | Complete | R3 Build & UT Sprint 23 |  | 2026-02-14 | 2026-02-14 | No | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3048 | FTSE1586 | 04.Enhancement | 01.IP - Intel Product | Text Purchase Requisition while creating with reference to Production Order Operation for External processing by implementing a user exit | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3048_Enhancement%20of%20Text%20Purchase%20Requisition%20while%20creating%20with%20reference%20to%20Production%20Order%20Operation%20for%20External%20processing%20by%20implementing%20a%20user%20exit.%E2%80%8B.pptx?d=w4579dbc740ff4a77bb47c4a3397f3ea1&csf=1&web=1&e=9BgYr0 | 02.No | 01.Yes |  | 2025-08-13 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1586 | INT-CR1193, INT-CR0856 | R3 ITC1 | [6 empty] | 2025-09-10 | 2025-09-10 | 2025-09-10 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3238 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18 - FUT in progress | 2025-12-05 | Y | 08. FTS IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3071 | FTSE1582 | 04.Enhancement | 02.IF - Intel Foundry | A Custom table to map and capture the relationship between RSQ Batch ID/STO# and the associated lots. | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3071_FTS_IF_A%20Custom%20table%20to%20map%20and%20capture%20the%20relationship%20between%20RSQ%20Batch%20IDSTO%20and%20the%20associated%20lots.pptx?d=wc3ce0eef39ba403da1c4b1b4e7a09fc2&csf=1&web=1&e=ZjHEtv | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-21 | 2025-10-10 | 2025-10-17 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-24 | 2025-10-17 | 2025-10-17 | 100% | 2025-10-15 | 2025-10-24 | 2025-10-17 | 2025-10-17 | 100% | 2025-10-15 | 2025-10-13 | 2025-11-05 |  |  | 2025-11-05 | 2025-11-10 | 2025-12-03 |  |  | 2025-12-03 | [5 empty] | 2025-12-03 | 2025-12-03 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-03 | 2025-12-03 | 2025-10-17 | jenoronha@deloitte.com | 2025-08-01 01:50 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 0.5 | 0.5 | 1582 | INT-CR0874 | R3 ITC1 | [6 empty] | 2025-08-21 | 2025-09-10 | 2025-08-21 |  | 2025-10-15 | 2025-10-17 | 2025-10-15 |  | 2025-10-15 | 2025-10-17 | 2025-10-15 | 2025-10-15 |  | 2025-11-05 |  |  |  | 2025-12-03 | [6 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-10-23 | 2025-11-05 | 2025-10-23 | [5 empty] | 2025-09-10 | 2025-10-17 | 2025-11-05 |  | 2025-11-05 |  |  |  | 0 |  | 3216 | [7 empty] | 4. Completed |  |  | 2025-12-03 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-10-17 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3068 | FTSE1581 | 04.Enhancement | 02.IF - Intel Foundry | Automated Batch Status Update Based on MRB Release Date using custom program. | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3068_Automated%20Batch%20Status%20Update%20Based%20on%20MRB%20Release%20Date.pptx?d=w29f0a3ab17cd406c84bb6323233b5c92&csf=1&web=1&e=ZPI4Nn | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-19 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | 2025-10-13 | 2025-11-05 |  |  | 2025-11-05 | 2025-11-10 | 2025-12-03 |  |  | 2025-12-03 | [5 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-07 | 2026-01-07 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-01 01:50 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1581 | INT-CR0977 | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-09-10 | 2025-08-19 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 |  | 2025-11-05 |  |  |  | 2025-12-03 | [6 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-16 | 2026-01-07 | 2025-12-16 | [5 empty] | 2025-09-10 | 2025-12-05 | 2025-11-05 |  | 2026-01-07 |  |  |  | 0 |  | 3215 | [7 empty] | 4. Completed |  |  | 2025-12-05 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3042 | FTSE1579 | 04.Enhancement | 02.IF - Intel Foundry | Custom tables to store Board Failure Form details | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B306F2FA4-FA76-466E-BFB7-8BF7F40DCB20%7D&file=RICEFW_Enhancement_Custom%20Table%20to%20Store%20BFF%20Details.pptx&wdLOR=c5435D0A8-8892-4ED9-B267-9C0A2949EBC5&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-08-25 | 2025-08-25 | 100% | 2025-09-05 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-01 01:50 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1579 |  | R3 ITC1 | [6 empty] | 2025-09-05 | 2025-09-05 | 2025-09-05 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-24 | 2025-12-05 | 2025-11-24 | [5 empty] | 2025-08-25 | 2025-12-05 |  |  | 2025-12-05 |  | WIINGS Only | TRUE | 0 |  | 3213 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 11/21: Awaiting approval | 2025-12-05 | Y | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 2941 | FTSE1577 | 04.Enhancement | 02.IF - Intel Foundry | Perform Auto batch determination at the time of STO creation – DMRA | 07. FTS IF | 7.1 FTS IF - ALL | 09. FUT Overdue | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2941_FTS_IF_DMRA-Perform%20Auto%20Batch%20Determination%20at%20the%20time%20of%20STO%20Creation.pptx?d=w9ebab06358834dadb7d7a182b93ac9d3&csf=1&web=1&e=5Kupoh | 02.No | 01.Yes |  | 2025-08-13 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-10-10 | 2025-10-17 | 2025-10-14 | 100% | 2025-12-31 | 2025-10-24 | 2025-11-05 | 2025-10-24 | 100% | 2025-12-31 | 2025-10-24 | 2025-11-05 | 2025-10-24 | 100% | 2025-12-31 | 2025-10-13 | 2025-11-05 |  |  | 2025-11-05 | 2025-11-10 | 2025-12-03 |  |  | 2025-12-03 | [5 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-11-05 | 2025-11-05 |  | 90% | 0% |  |  |  | 02. In Progress | 01. Not Started |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 45% | 2025-11-21 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-03 | 2025-12-03 | 2025-11-05 | jenoronha@deloitte.com | 2025-08-01 01:50 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 9 | 2025-09-05 | 01.S4 |  |  | 2 | 2 | 1577 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-09-10 | 2025-09-10 |  |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-11-05 |  |  |  | 2025-12-03 | [6 empty] | 2025-12-31 | 2025-12-31 |  |  |  | 2025-11-21 | 2025-11-21 | [5 empty] | 2025-09-10 | 2025-11-05 | 2025-11-05 |  | 2025-11-05 |  |  |  | 0 |  | 3211 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 11/18: Team team working on defect ETA 11/18. FUT completion ETA is 11/24 11/7: Team team working on defect 10/24 - Defect 3620. | 2025-12-03 | Y | 07. FTS IF | [7 empty] | Defects | N/A | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 3035 | FTSE1549 | 04.Enhancement | 02.IF - Intel Foundry | Custom Attributes for AMT/ISM | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1549 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3166 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1548 | 04.Enhancement | 02.IF - Intel Foundry | Automation for Product Conversions – Equipment Structure update | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1548 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3165 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1547 | 04.Enhancement | 02.IF - Intel Foundry | Automation for Product Conversions – Work Order Closure | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1547 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3164 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1546 | 04.Enhancement | 02.IF - Intel Foundry | Automation for Product Conversions – Parts Request and Return | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1546 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3163 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1545 | 04.Enhancement | 02.IF - Intel Foundry | Automation for Product Conversions – Explode BOM | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1545 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3162 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1544 | 04.Enhancement | 02.IF - Intel Foundry | Automation for Product Conversions – create Work Order | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1544 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3161 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1543 | 04.Enhancement | 02.IF - Intel Foundry | PM inbound from AMT | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1543 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3160 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1542 | 04.Enhancement | 02.IF - Intel Foundry | PM outbound to AMT | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1542 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3159 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1541 | 04.Enhancement | 02.IF - Intel Foundry | Send SAP notification on Work Order update | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1541 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3158 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1540 | 04.Enhancement | 02.IF - Intel Foundry | Send SAP notification on Equipment update | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1540 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3174 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | FTSE1539 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori UI – Move Equipment SRoom to SRoom (screen) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 02. FS Unplanned | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1 | 1539 | INT-CR0870 | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3173 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2998 | FTSE1528 | 04.Enhancement | 02.IF - Intel Foundry | Warranty claim for non E2O supplier | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_Enhancement_Warranty%20claim%20Output%20for%20non%20E2O%20supplier%20.pptx?d=w9d240c78c76d4b8298adddaebc17ca11&csf=1&web=1&e=dyf8mv | 02.No | 01.Yes |  | 2025-07-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-26 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-12 10:06 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-07-29 | 01.S4 |  |  | 1 | 1 | 1528 | INT-CR0759 | R3 ITC1 | [6 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-02 | 2025-12-05 | 2025-12-02 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 3142 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 12/1: Awaiting Approval | 2025-12-05 | Y | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2988 | FTSE1480 | 04.Enhancement | 02.IF - Intel Foundry | B2B SLOC Mapping Table | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2988_M-100-080-UI%20for%20scanning%20lots%20for%20KM2KM5.pptx?d=wa28f425badb6498f997ba48f08a6bcd3&csf=1&web=1&e=1zFGH8 | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-09-13 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-29 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-10 | 2025-10-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-10 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1480 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-13 | 2025-10-17 | 2025-09-13 |  | 2025-09-29 | 2025-11-07 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-07-16 | 2025-11-07 |  |  | 2025-10-10 |  |  |  | 0 |  | 3058 | [7 empty] | 1. On Track | 14. B-App Under Test |  | 2025-11-07 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-11-07 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2987 | FTSE1479 | 04.Enhancement | 02.IF - Intel Foundry | Table for SFP/Operation for KM2/KM5 | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2987_M-100-080-Table%20for%20SFPOperation%20for%20KM2KM5.pptx?d=w290c006fe1f7451fb1141057c9f00895&csf=1&web=1&e=eJrmmW | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-08-20 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-20 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-14 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1479 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-20 | 2025-10-17 | 2025-08-20 |  | 2025-08-20 | 2025-11-07 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-14 | 2025-11-05 | 2025-10-14 | [5 empty] | 2025-07-16 | 2025-11-07 |  |  | 2025-11-05 |  |  |  | 0 |  | 3056 | [10 empty] | 2025-11-07 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2986 | FTSE1478 | 04.Enhancement | 02.IF - Intel Foundry | Table for All Shippable Mid Stage and End Stage Operations | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2986_M-100-080-Table%20for%20all%20shippable%20mid%20stage%20and%20end%20stage%20operations.pptx?d=wb4233ab192a14e7b850082772707181b&csf=1&web=1&e=TQnizg | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-10-07 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-10-07 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-30 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1478 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-17 | 2025-10-07 |  | 2025-10-07 | 2025-11-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-09-30 | 2025-10-08 | 2025-09-30 | [5 empty] | 2025-07-16 | 2025-11-07 |  |  | 2025-10-08 |  |  |  | 0 |  | 3054 | [10 empty] | 2025-11-07 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-11-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2985 | FTSE1477 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement - Lot Level Exception UI | 07. FTS IF | 7.1 FTS IF - ALL | 09. FUT Overdue | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2985_M-100-080-Lot%20Level%20Exception%20UI.pptx?d=w3f1802382af04f0b87a4bf5439f93695&csf=1&web=1&e=gOTxEf | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-22 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-03-23 | 2026-03-23 |  | 100% | 90% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-23 | N | 95% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-05-23 06:17 | cell-link@smartsheet.com | 2026-04-08 06:03 | 9 | 2025-06-10 | 01.S4 |  |  | 4 | 4 | 1477 |  | R3 ITC1 | [6 empty] | 2025-09-22 | 2025-09-22 | 2025-09-22 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  |  | 2026-03-23 | [6 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3052 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 4/3:awaiting approval 3/27:Walkthrough completed, awaiting approval 3/20: Working with development team on defects 3/13: Working with development team on defects 3/6:Very high complexity with several complicated use cases, currently working through final set of defects. 2/27:Defect in progress. TUT/FUT in parallel. 2/12:Still Development not completed. 02/12: Still Development not completed. 01/06: Still Development not completed. 01/14: Replanned for S23 | 2025-12-05 | N | 07. FTS IF |  |  |  | 03/23: FUT complete. Current Status: FUT complete. Demo pending. Issue: FUT delayed Next Steps: Complete demo and approval. Help Needed: n/a ETA - 03/27 | Spill over |  | On track for S23+ | Awaiting approval | Delayed - Past Sprint | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2984 | FTSE1476 | 04.Enhancement | 02.IF - Intel Foundry | Lot to STR Mapping table | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2984_M-100-080-Lot%20to%20STR%20Mapping%20Table.pptx?d=we48e6352853044459367be3cf09cee6c&csf=1&web=1&e=P6o38H | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-11 | 2025-08-13 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-30 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1476 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-10-10 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-30 | 2025-10-08 | 2025-09-30 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-10-08 |  |  |  | 0 |  | 3050 | [10 empty] | 2025-10-10 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2983 | FTSE1475 | 04.Enhancement | 02.IF - Intel Foundry | Non Revenue Shipping Demand Screen (Custom Table) | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2983_M-100-080-Non%20Revenue%20Shipping%20Demand%20Screen%20-%20Custom%20Table.pptx?d=w0b49aac51b5349e0916e61bf7462b601&csf=1&web=1&e=hfCqj2 | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-25 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-08-20 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-20 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1475 |  | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-08-20 | 2025-10-17 | 2025-08-20 |  | 2025-08-20 | 2025-11-07 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-06 | 2025-10-08 | 2025-10-06 | [5 empty] | 2025-07-16 | 2025-11-07 |  |  | 2025-10-08 |  |  |  | 0 |  | 3048 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-11-07 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2982 | FTSE1474 | 04.Enhancement | 02.IF - Intel Foundry | Non Revenue Shipping Demand Screen | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2982_M-100-080-Non%20Revenue%20Shipping%20Demand%20Screen.pptx?d=w7da983b8ca054fdfb114526ff6bacd89&csf=1&web=1&e=5Ny9a7 | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-08-13 | 100% | 2025-08-08 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 2 | 2 | 1474 |  | R3 ITC1 | [6 empty] | 2025-08-08 | 2025-08-13 | 2025-08-08 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3046 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/06:Awaiting approval from desmond team | 2025-12-05 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2980 | FTSE1472 | 04.Enhancement | 02.IF - Intel Foundry | Custom Table for SFP, Stage, UPI Mapping | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B99E75C52-C5B9-4A73-BAE7-2EB1720DF77B%7D&file=2980_M-100-080-Custom%20table%20for%20SFP%2C%20Stage%2C%20UPI%20Mapping.pptx&wdLOR=cE5582589-FFC4-4CD9-905E-0F710C5E0FA5&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-30 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1472 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 | 2025-09-19 | 2025-08-22 |  | 2025-08-22 | 2025-10-10 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-30 | 2025-10-08 | 2025-09-30 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-10-08 |  |  |  | 0 |  | 3043 | [7 empty] | 2. At Risk | 8. Blocked by CR/Design change |  | 2025-10-10 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2978 | FTSE1470 | 04.Enhancement | 02.IF - Intel Foundry | Custom Table for MES Facility, MES Site Code to Plant | 07. FTS IF | 7.1 FTS IF - ALL | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E48A47D-FC9F-4E51-B3AA-21EC520EA071%7D&file=2978_M-100-080-Custom%20table%20for%20MES%20facility%2C%20MES%20Site%20code%20and%20plant.pptx&wdLOR=cF686910C-15A8-40B3-9463-FA64F2EFA7B4&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1470 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-22 | 2025-09-19 | 2025-08-22 |  | 2025-08-22 | 2025-10-10 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-06 | 2025-10-08 | 2025-10-06 | [5 empty] | 2025-07-16 | 2025-10-10 |  |  | 2025-10-08 |  |  |  | 0 |  | 3060 | [10 empty] | 2025-10-10 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2965 | FTSE1468 | 04.Enhancement | 02.IF - Intel Foundry | Custom table to store PO Lot Pegging (POLP) | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2965_FTS_IF_Custom%20table%20to%20store%20PO%20Lot%20Pegging.pptx?d=w9c31f37b32244ad7ab3fcebaa669b811&csf=1&web=1&e=qPaSjz | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-13 | 2025-06-27 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-30 | 2025-07-04 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-16 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-16 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-16 | 2025-07-16 | 2025-07-16 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1468 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-06-27 | 2025-07-16 |  |  | 2025-09-10 |  |  |  | 0 | 08. Not Applicable | 3057 | [10 empty] | 2025-07-16 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2951 | FTSE1467 | 04.Enhancement | 02.IF - Intel Foundry | Custom Report for Operating Supplies Reservations​ | 07. FTS IF | 7.1 FTS IF - ALL | 06. Dev In Progress | Y | 2025-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2951_FTS_IF_Custom%20Report%20for%20Operating%20Supplies%20Reservations%E2%80%8B.pptx?d=w74505c3f50e047c39405cf12d3e0f9a0&csf=1&web=1&e=YoCspc | 01.Yes | 01.Yes |  | 2025-05-29 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-25 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 75% | 2025-10-03 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 75% | 2025-10-03 | [15 empty] | 2025-10-03 | 2025-10-03 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-25 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-05-23 06:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 6 | 2025-07-24 | 01.S4 |  |  | 2 | 2 | 1467 | INT-CR0696 | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-07-25 | 2025-07-25 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  |  | 2025-10-03 | [18 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25 | [5 empty] | 2025-07-16 | 2025-10-03 |  |  | 2026-02-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 | 08. Not Applicable | 3055 | [7 empty] | 1. On Track | 1. Approved no action | 2/27:FUT Approved. TDD activity showing open in plan 2/23:Awaiting Approval 2/13: awaiting approval 2/9: Tech team working on defects logged 6655, 6881,6883, 6888 2/5:4 defects logged 6655, 6881,6883, 6888 2/2 - 6655 is being worked upon 01/21: 5854, 5857 defect fix in progress 01/06 - FUT in progress. 01/14: Replanned for S22 | 2025-10-03 | N | 07. FTS IF | Factory Portal UI |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2949 | FTSE1456 | 04.Enhancement | 02.IF - Intel Foundry | Custom Table to store FSCO lot level material staging​ | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2949_FTS_IF_Custom%20Table%20to%20store%20FSCO%20lot%20level%20material%20staging%E2%80%8B.pptx?d=wf0edd36ceb3040449a8ea06e2ee888ad&csf=1&web=1&e=ylgVyr | 01.Yes | 01.Yes |  | 2025-05-19 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-13 | 2025-06-27 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-30 | 2025-07-04 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-16 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-07 | 2025-07-16 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-16 | 2025-07-16 | 2025-07-16 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-10 | 01.S4 |  |  | 0.5 | 0.5 | 1456 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-06-27 | 2025-07-16 |  |  | 2025-09-10 |  |  |  | 0 |  | 3027 | [9 empty] | 9/12: Sent for itel approval | 2025-07-16 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2930 | FTSE1451 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement required for triggering Interface between S4 and SAP ME from the save user exit of a work order with conditions to check the Order Type and Release Status | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_Enhancement_Trigger%20Interface%20between%20S4%20and%20SAP%20ME.pptx?d=w082d153a01784741a25681637b292a93&csf=1&web=1&e=gix1f2 | 01.Yes | 01.Yes |  | 2025-05-19 | Shamin A Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-05-17 02:08 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 1451 | INT-CR0510 | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-09-16 | 2025-09-16 | 2025-09-16 |  | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-10-06 | 2025-10-08 | 2025-10-06 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-10-08 |  |  |  | 0 | 08. Not Applicable | 3021 | [10 empty] | 2025-10-08 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2946 | FTSE1435 | 04.Enhancement | 02.IF - Intel Foundry | Custom Table - Cross Site Ref Op sets will be maintained at a higher level in the product hierarchy than UPI, however business wants to able to maintain UPI level exceptions in some cases​​ | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2946_FTS_IF_Custom%20Table%20-%20Cross%20Site%20Ref%20Op%20sets%20will%20be%20maintained%20at%20a%20higher%20level%20in%20the%20product%20hierarchy%20than%20UPI.pptx?d=w543f6b8923c44658bccdf579db166991&csf=1&web=1&e=BMbcfG | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-05 | 2025-08-11 | 2025-08-15 | 2025-08-01 | 100% | 2025-08-14 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | [15 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-09-23 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2025-04-25 04:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1435 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-13 | 2025-06-05 |  | 2025-08-14 | 2025-08-15 | 2025-08-14 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | [12 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-09-23 | 2025-10-10 | 2025-09-23 | [5 empty] | 2025-06-13 | 2025-08-13 |  |  | 2025-10-10 |  |  |  | 0 |  | 2993 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-08-13 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-14 | 2025-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2944 | FTSE1433 | 04.Enhancement | 02.IF - Intel Foundry | Custom Program to assign Routings to Items based on Item Characteristics​​ | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2944_FTS_IF_Custom%20Program%20to%20assign%20Routings%20to%20Items%20based%20on%20Item%20Characteristics%E2%80%8B%E2%80%8B.pptx?d=w77d9de462a684ff1bf777e67739ff199&csf=1&web=1&e=93ppgc | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-14 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2025-04-25 04:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1433 |  | R3 ITC1 | [6 empty] | 2025-06-14 | 2025-06-14 | 2025-06-14 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2026-02-04 |  |  |  | 0 |  | 2991 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/2:Awaiting approval, presented on 01/29 01/21: Issue fix in progress, defect "6537" 01/06: Defect is open | 2025-10-08 | N | 07. FTS IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2943 | FTSE1432 | 04.Enhancement | 02.IF - Intel Foundry | Custom Enhancement to Issue out stock in S4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2943_FTS_IF_Enhancement%20to%20deduct%20UNBW%20material%20once%20it%20has%20arrived%20at%20destination%20prod%20sloc%E2%80%8B.pptx?d=w1fd06054bfce4a7c8c0a731cf1029423&csf=1&web=1&e=7wmvtb | 02.No | 01.Yes |  | 2025-04-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-03 | 2025-08-11 | 2025-08-15 | 2025-08-01 | 100% | 2025-08-05 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-05 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-05 | [15 empty] | 2025-08-05 | 2025-08-05 |  | 2025-09-10 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2025-04-25 04:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1432 |  | R3 ITC1 | [6 empty] | 2025-06-03 | 2025-06-13 | 2025-06-03 |  | 2025-08-05 | 2025-08-15 | 2025-08-05 |  | 2025-08-05 | 2025-08-13 | 2025-08-05 | 2025-08-05 | [12 empty] | 2025-08-05 | 2025-08-05 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-06-13 | 2025-08-13 |  |  | 2025-10-10 |  |  |  | 0 |  | 2990 | [10 empty] | 2025-08-13 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2916 | FTSE1413 | 04.Enhancement | 02.IF - Intel Foundry | Reusable Mass Upload Program for Equipment Master Warranty | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-04-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_Enhancement_Reusable%20Mass%20Upload%20for%20Equip%20Master%20Warranty%20Details.pptx?d=w9a0ebe695d044351abec3ca6f37d63e0&csf=1&web=1&e=G8DgGR | 02.No | 02.No |  | 2025-04-25 | shamin.a.shirodkar@intel.com | 01.Approved | 2025-04-17 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-25 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-04-16 08:12 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-01 | 01.S4 |  |  | 1 | 1 | 1413 | INT-CR0458 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2025-11-24 | 2025-12-05 | 2025-11-24 | [5 empty] | 2025-07-18 | 2025-11-05 |  |  | 2025-12-05 |  | WIINGS Only | TRUE | 0 |  | 2956 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 11/21: Awaiting approval | 2025-11-05 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1385 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Preventative Maintenance (AT) (Schedule Maintenance Plan) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1385 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2026-03-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2927 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 3/5: Awaiting Approval | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks | Week 3 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1383 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Preventative Maintenance (AT) (Set Maintenance Counte) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-08-14 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1383 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 | [5 empty] | 2025-07-16 | 2025-12-05 |  |  | 2025-12-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2926 |  |  | WIINGS |  |  |  |  | 4. Completed |  | 11/14: Review completed. Sent for approval | 2025-12-05 | Y | 07. FTS IF | Factory Portal UI | [7 empty] | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1382 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Preventative Maintenance (AT) (Set Maintenance Cycle​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-17 | 100% | 2026-01-29 | 2025-10-08 | 2025-11-05 | 2025-11-21 | 100% | 2026-01-29 | 2025-10-08 | 2025-11-05 | 2025-11-21 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-12-19 | 2025-12-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-26 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1382 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2025-12-23 | 2025-12-26 | 2025-12-23 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-12-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2925 |  |  | WIINGS |  |  |  |  | 1. On Track | 2. Smartsheet Hygiene(5.2) | 12/23 - Approval received. Smartsheet update pending. 12/19 : FUT in progress | 2025-11-05 | N | 07. FTS IF | Factory Portal UI | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1381 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Preventative Maintenance (AT) (Create Maintenance Plan) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-16 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-16 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1381 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-16 | 2025-08-16 | 2025-08-16 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2924 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 12/12: Sent for approval | 2025-12-05 | Y | 07. FTS IF | Factory Portal UI | [6 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1379 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Part list (Part list creation / modify (IA05​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-07 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-12-10 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-12-10 | [15 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1379 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-07 | 2025-08-13 | 2025-08-07 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | [12 empty] | 2025-12-10 | 2025-12-10 |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | [5 empty] | 2025-08-13 | 2025-10-08 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2921 |  |  | WIINGS |  |  |  |  | 1. On Track | 17. FUT In progress | 1/2: Review complete with Intel | 2025-10-08 | N | 07. FTS IF | Factory Portal UI | [6 empty] | CR/Design change | Complete | R3 Build & UT Sprint 21 |  | 2025-12-10 | 2025-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1378 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Functional Location​ (FLOC creation / Update (IL01 and IL02)​​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-16 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2026-01-31 | [15 empty] | 2026-01-31 | 2026-01-31 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1378 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-16 | 2025-08-16 | 2025-08-16 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | [12 empty] | 2026-01-31 | 2026-01-31 |  |  | 2025-12-04 | 2025-12-05 | 2025-12-04 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2920 |  |  | WIINGS |  |  |  |  | 4. Completed | 1. Approved no action | 12/4: Approved | 2025-12-05 | Y | 07. FTS IF | Factory Portal UI | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-31 | 2026-01-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1376 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Admin (Notifications​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-08-15 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-04 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-04 | [15 empty] | 2025-10-04 | 2025-10-04 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1376 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-15 | 2025-08-15 | 2025-08-15 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-10-04 | 2025-10-08 | 2025-10-04 | 2025-10-04 | [12 empty] | 2025-10-04 | 2025-10-04 |  |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2918 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 12/1: Awaiting Approval | 2025-10-08 | N | 07. FTS IF | Factory Portal UI | [6 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1374 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Admin (Admin Screen - My Profile) - Contacts custom Table Enhancement | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-23 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-23 | [15 empty] | 2025-08-23 | 2025-08-23 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1374 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-08-23 | 2025-09-19 | 2025-08-23 |  | 2025-08-23 | 2025-10-10 | 2025-08-23 | 2025-08-23 | [12 empty] | 2025-08-23 | 2025-08-23 |  |  | 2025-09-25 | 2025-10-08 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-10-08 |  | WIINGS Only | TRUE | 0 |  | 2916 |  |  | WIINGS | [7 empty] | 2025-10-10 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1373 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Admin (Admin Screen - My Profile) - Fiori Enhancement | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-14 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1373 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-14 | 2025-06-14 | 2025-06-14 |  | 2025-08-21 | 2025-09-19 |  |  | 2025-09-05 | 2025-10-10 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-09-25 | 2025-10-08 | 2025-09-25 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-10-08 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2915 |  |  | WIINGS | [7 empty] | 2025-10-10 | Y | 07. FTS IF | Factory Portal UI | [7 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 04.R4 | 2923 | FTSE1369 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Equipment to Parts Management (Custom Fields – Part Check out & Part Check in (eDFIT)​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 04. FS In Progress | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 |  | 66% | 2025-08-13 | 2025-10-10 | 2025-10-17 |  | 0% | 2025-10-17 | 2025-10-24 | 2025-11-21 |  | 0% | 2025-11-21 | 2025-10-24 | 2025-11-21 |  | 0% | 2025-11-21 | [15 empty] | 2025-11-21 | 2025-11-21 | [14 empty] | 2025-11-10 | 2025-12-03 |  | Y | 0% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-21 | 2025-11-21 | 2025-11-21 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 4 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1369 | INT-CR0870 | R4 ITC1 | [7 empty] | 2025-08-13 |  |  |  | 2025-10-17 |  |  |  | 2025-11-21 | [19 empty] | 2025-12-03 | [6 empty] | 2025-08-13 | 2025-11-21 |  |  | 2025-12-03 |  | WIINGS Only eDFIT | TRUE | 0 |  | 2911 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  | 2025-11-21 | Y | 07. FTS IF | eDFIT | [7 empty] | N/A | R3 Build & UT Sprint 20 |  | 2025-11-21 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1368 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Equipment to Parts Management (Equipment Management (details screen: update / FLOC install / User status update)) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-26 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-27 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-27 | [15 empty] | 2026-02-27 | 2026-02-27 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1368 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-02-27 | [12 empty] | 2026-02-27 | 2026-02-27 |  |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-02-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2910 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 2/9: Review completed with Intel; Sent for approval | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks |  |  |  | Defects | Complete | R3 Build & UT Sprint 23 |  | 2026-02-27 | 2026-02-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1367 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Equipment to Parts Management (Equipment/ Entity/ Sub-Entity Search Screen​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-12-10 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-10 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-10 | [15 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1367 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | [12 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | [5 empty] | 2025-07-16 | 2025-11-05 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2909 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 11/21: Awaiting Approval | 2025-11-05 | Y | 07. FTS IF | Factory Portal UI | [6 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-10 | 2025-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1366 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Operating Supply (Reserve Ops Suppl​​​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-12 | 2025-09-19 | 2025-11-20 | 100% | 2025-12-03 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1366 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-03 | 2025-12-03 | [12 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-07-18 | 2025-12-05 |  |  | 2026-02-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2908 |  |  | WIINGS |  |  |  |  | 1. On Track | 17. FUT In progress | 2/2: Ready for review | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks |  |  |  | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1365 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Operating Supply (Search for Ops Supply​​​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-12 | 2025-09-19 | 2025-10-14 | 100% | 2025-12-10 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-12-10 | 2025-09-26 | 2025-10-24 | 2025-10-24 | 100% | 2025-12-10 | [15 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1365 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | [12 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | [5 empty] | 2025-07-18 | 2025-10-24 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2906 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 12/1: Presented to Intel on 11/24; Working on Post Review ARs | 2025-10-24 | Y | 07. FTS IF | Factory Portal UI | [6 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-12-10 | 2025-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1363 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Warranty Claim (Create Warranty Claim – Detailed Vie​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-26 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-12-10 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-12-10 | [15 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1363 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | [12 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | [5 empty] | 2025-07-18 | 2025-10-08 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2902 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 12/1: Awaiting Approval | 2025-10-08 | N | 07. FTS IF | Factory Portal UI | [6 empty] | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-10 | 2025-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1360 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori UI – HAZMAT Enhancement to pull data | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-06-27 | 2025-07-16 | 100% | 2025-11-06 | 2025-10-22 | 2025-10-29 | 2025-12-12 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-02 | 01.S4 |  |  | 1 | 1 | 1360 | INT-CR0728 | R3 ITC1 | [6 empty] | 2025-11-06 | 2025-11-06 | 2025-11-06 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-06-27 | 2025-12-05 |  |  | 2026-03-04 |  | WIINGS Only | TRUE | 0 |  | 2896 |  |  | WIINGS |  |  |  |  | 4. Completed | 2. Smartsheet Hygiene(5.2) | 3/5: Approved | 2025-12-05 | N | 07. FTS IF |  |  |  | 03/04: Awaiting approval. Current status: Awaiting approval Next steps: N/A Help needed: N/A FUT ETA: N/A | Spill over | 3. Watch item | At risk for S23 | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1359 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Returns Order Flow (Prevent TECO until after parts have been accepted from WH in case of rejection​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-12-31 | 2025-10-03 | 2025-10-31 | 2025-10-24 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-02 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1359 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-02 | 2025-12-05 | 2025-12-02 | [5 empty] | 2025-06-13 | 2025-10-31 |  |  | 2025-12-05 |  | WIINGS Only | TRUE | 0 |  | 2894 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 12/1: Awaiting Approval | 2025-10-31 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1358 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Returns Order Flow (Form-Based (CRD) Return Order​) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-07-18 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1358 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-18 | 2025-07-18 | 2025-07-18 |  | 2025-09-16 | 2025-09-16 | 2025-09-16 |  | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-10-08 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2892 |  |  | WIINGS |  |  |  |  | 4. Completed | 17. FUT In progress | 11/7: Awaiting Intel approval | 2025-10-08 | Y | 07. FTS IF | Factory Portal UI |  |  | Current Status: FUT on hold due to dependency with FTSE1579 Issue: Working with tech team for Board Failure Form development to be done in FTSE1579 Next Steps: Once the development is completed on the dependent object, FUT will be resumed Help Needed: |  |  |  | CR/Design change | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1354 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Confirm and Submit Parts (Table Extension Enhancement) ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-25 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-12-10 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-10 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-10 | [15 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1354 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-25 | 2025-08-13 | 2025-07-25 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | [12 empty] | 2025-12-10 | 2025-12-10 |  |  | 2025-11-24 | 2025-12-03 | 2025-11-24 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-12-03 |  | WIINGS Only | TRUE | 0 |  | 2887 |  |  | WIINGS |  |  |  |  | 4. Completed | 3. Awaiting Approval | 11/21 : Awaiting Approval | 2025-11-05 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-10 | 2025-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1353 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Confirm and Submit Parts (Fiori Enhancement) ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-03 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1353 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-03 | 2025-12-03 | [12 empty] | 2025-12-03 | 2025-12-03 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-07-18 | 2025-12-05 |  |  | 2026-03-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2922 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 3/5: Awaiting Approval | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1351 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Add component to work order ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-29 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-09-29 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-31 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1351 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-08 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-31 | 2025-11-05 | 2025-10-31 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-11-05 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2905 |  |  | WIINGS |  |  |  |  | 1. On Track | 2. Smartsheet Hygiene(5.2) | 10/29 - Smartsheet pending updates | 2025-10-08 | N | 07. FTS IF | Factory Portal UI | [6 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1350 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Search Parts ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1350 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-07-18 | 2025-10-08 |  |  | 2026-03-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2903 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 3/5: Awaiting Approval | 2025-10-08 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks | Week 3 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1349 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Change Color of WO, Equipment, and CRD & eCUDL based on Cu/HM​ ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-05-23 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1349 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-06-13 | 2025-05-23 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-10-08 |  | WIINGS Only | TRUE | 0 |  | 2901 |  |  | WIINGS | [7 empty] | 2025-10-10 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2923 | FTSE1348 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Show Work Order – Single Work Order View + Edit work order ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-08-13 | 2025-08-13 | 100% | 2025-09-11 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1348 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-03-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2898 |  |  | WIINGS |  |  |  |  | 1. On Track | 6. FUT Defect Under Fix | 3/5: Awaiting Approval pending a defect fix | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  | 0120: No roadblocks | Week 4 Target |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1347 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Search work orders - ​List View ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1347 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-09-16 | 2025-09-16 | 2025-09-16 |  | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-10-08 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2897 |  |  | WIINGS |  |  |  |  | 1. On Track | 17. FUT In progress |  | 2025-10-08 | Y | 07. FTS IF | Factory Portal UI | [7 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2923 | FTSE1344 | 04.Enhancement | 02.IF - Intel Foundry | Factory Portal - Work Order Flow ( Home Page - View S/4 work orders ) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://amedeloitte.sharepoint.com/:p:/r/sites/IntelIDM2.0AccelerationRFP/_layouts/15/doc2.aspx?sourcedoc=%7BDAC887E4-5D6A-44FA-9C56-9CAC1AE1A3FB%7D&file=INT-CR0486%20-%20New%20RICEFWs%20for%20Custom%20Fiori%20UI%20-%20%20(console%20ID%202923)%20.pptx&action=edit&mobileredirect=true&previoussessionid=e96125d9-ae2e-1ae6-1b8b-b92e17365e2d | 02.No | 01.Yes |  | 2025-03-28 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-19 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-19 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-19 | [15 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jonsanders@deloitte.com | 2025-04-08 10:05 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-05-20 | 01.S4 |  |  | 4 | 4 | 1344 | INT-CR0486 | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-09-19 | 2025-09-19 | 2025-09-19 |  | 2025-09-19 | 2025-10-08 | 2025-09-19 | 2025-09-19 | [12 empty] | 2025-09-19 | 2025-09-19 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | [5 empty] | 2025-06-13 | 2025-10-08 |  |  | 2025-10-08 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2891 |  |  | WIINGS |  |  |  |  | 1. On Track | 6. FUT Defect Under Fix |  | 2025-10-08 | Y | 07. FTS IF | Factory Portal UI | [7 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2892 | FTSE1325 | 04.Enhancement | 02.IF - Intel Foundry | M-100-170_Create Manual ship FIORI UI in S4 | 07. FTS IF | 7.1 FTS IF - ALL | 06. Dev In Progress | Y | 2025-04-17 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-170_Create%20Manual%20ship%20FIORI%20UI%20in%20S4.pptx?d=w557d4dcb05324cda98d484e714a2b77e&csf=1&web=1&e=HB0154 | 02.No | 01.Yes |  | 2025-03-22 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-09-22 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 50% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 50% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  |  | 2026-03-23 | 2026-03-23 |  | 100% | 90% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-23 | N | 95% | 2026-03-23 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-03-19 10:46 | cell-link@smartsheet.com | 2026-04-08 06:03 | 6 | 2025-04-18 | 01.S4 |  |  | 4 | 4 | 1325 |  | R3 ITC1 | [6 empty] | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  |  | 2025-12-05 | [19 empty] | 2026-03-23 | [6 empty] | 2025-08-15 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 2675 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 4/3: Awaiting approval 3/20:Working with fiori and tech team in defects 03/20: Working with technical team on defect 03/13: combine TUT/FUT in progress, sent email to Boundary app for test data for some interfaces from FIORI 03/06: combine TUT/FUT in progress, sent email to Boundary app for test data 02/27: Development in progress ETA 03/03 02/12: Development in progress ETA 03/03 01/06: CR 1543 development in progress. 01/14: Replanned for S23 | 2025-12-05 | N | 07. FTS IF |  |  |  | 03/23: FUT in progress Current status: Testing in progress for Manual Ship Fiori App which calls all the Outbound Interfaces from S4 to Ship Server/ULT/Workstream. Issue: N/a. Next steps: Complete FUT and approval Help needed: n/a FUT ETA: 03/27 | Spill over |  | On track for S23+ | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 20 |  | 2025-12-05 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2807 | FTSE1194 | 04.Enhancement | 01.IP - Intel Product | Enhancement in IP SAP HANA system to re-assign the first operation plant to Consumption materials | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2807_FTS_IP_Enhancement%20in%20IP%20SAP%20HANA%20System%20to%20re-assign%20the%20operation%20number%20in%20the%20first%20operation%20to%20last%20operation%20to%20allocate%20BoM%20Components%20against%20production%20order.pptx?d=w47ffbb3e65cb4cfa9f56b02c945f0011&csf=1&web=1&e=NIbgpv | 02.No | 01.Yes |  | 2025-01-29 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA |  |  | NA | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-07-21 | 2025-07-25 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-28 | 2025-08-08 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-21 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-03 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2025-01-29 09:20 | cell-link@smartsheet.com | 2026-03-09 04:44 | 10 | 2025-02-03 | 01.S4 |  |  | 1 | 1 | 1194 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | [5 empty] | 2025-06-13 | 2025-08-15 |  |  | 2025-09-10 |  |  |  | 0 |  | 1727 | [9 empty] | 09/26 : Defect is fixed and Walkthrough is provided to Intel IT. Awaiting for approval ETA 09/30. 9/19- Defect 2615 is in progress. Aligned with tech team on 9/18 on the next step. ETA - 9/26 09/12 : Defect #2615 fixed in progress after review and ETA 09/23. | 2025-08-15 | N | 08. FTS IP | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-24 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-09 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2784 | FTSE1160 | 04.Enhancement | 02.IF - Intel Foundry | Custom Utility for Engineering Planners to create Rev Eng Planned Orders in S4 | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 10. Object Complete | Y | 2025-02-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2784-PLB-020-120_FTS_IF_Custom%20Utility%20for%20Engineering%20Planners%20to%20create%20Rev%20Eng%20Planned%20Orders%20in%20S4.pptx?d=waea5b465eb804edebf26725d50d26484&csf=1&web=1&e=2evNmQ | 02.No | 01.Yes |  | 2025-01-29 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-04-14 | 2025-04-18 | 2025-04-29 | 100% | 2025-08-04 | 2025-04-30 | 2025-05-02 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-23 15:43 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 | 2025-02-13 | 01.S4 |  |  | 1 | 1 | 1160 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-03-21 | 2025-05-16 | [6 empty] | 0 |  | 1816 | [9 empty] | 09/08: Awaiting SharePoint location to place sample files for intel IT 09/01: Defect raised 2189,2630, awaiting defect to fix 8/22:Waiting for feedback from Intel IT to make corrections. 8/18:Waiting for feedback from Intel IT to make corrections. 8/11- Defect 1823 and 2046 in progress 8/4- Defect # 1823 being worked upon. Awaiting approval . Delayed due to - defects 1188,1272,1299. | 2025-05-16 | N | 07. FTS IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2750 | FTSE1146 | 04.Enhancement | 01.IP - Intel Product | Enhancement to link KB sales orders / STR to purchase requisition generated by central warehouse to X-dock. | 08. FTS IP | 8.6 FTS IP - MRP & Planning Integration | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2750_PLB-020-040_FTS_IP_Enhancement%20to%20link%20KB%20sales%20orders%20%20STR%20to%20purchase%20requisition%20generated%20by%20central%20warehouse%20to%20X-dock.pptx?d=w3448e6049e5f41b5b9cf8208b05aba8f&csf=1&web=1&e=gvKv2D |  |  |  | 2025-01-22 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA |  |  | NA | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-13 | 2025-07-21 | 2025-08-01 | 2025-08-01 | 100% | 2025-07-24 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-24 | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2025-01-20 06:30 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-01 | 01.S4 |  |  | 0.5 | 0.5 | 1146 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | [5 empty] | 2025-06-13 | 2025-08-15 | [6 empty] | 0 |  | 2342 | [9 empty] | 10/03 :Awaiting for Approval from business. 09/26 : Defect fixed and awaiting for Intel IT approval. 9/19 - Defect 3146 created and assigned to tech team. 09/12 : Defect #2978 fixed in progress after review and ETA 09/16. | 2025-08-15 | N | 08. FTS IP | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-24 | No | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2746 | FTSE1144 | 04.Enhancement | 01.IP - Intel Product | Total Quantity’ update for Parent Production Order with reference to Actual Goods Consumption data against the same order | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2746_FTS_IP_Total%20Quantity%E2%80%99%20update%20for%20Parent%20Production%20Order%20with%20reference%20to%20Actual%20Goods%20Consumption%20data%20against%20the%20same%20order.pptx?d=w1eb705bf65f54212bcd42c8460eec149&csf=1&web=1&e=JXIRkt |  |  |  | 2025-01-22 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-08-01 | 100% | 2025-08-15 | 2025-07-07 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-15 | 2025-07-07 | 2025-07-18 | 2025-08-13 | 100% | 2025-08-15 | [15 empty] | 2025-08-15 | 2025-08-15 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-19 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-01-20 06:30 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1 | 1144 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | [12 empty] | 2025-08-15 | 2025-08-15 |  |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | [5 empty] | 2025-04-18 | 2025-07-18 | [6 empty] | 0 |  | 2072 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18 - Walkthrough completed with Intel IT. Awaiting approval ETA is 11/21 11/14 - Walkthrough completed with Intel IT. Awaiting approval ETA is 11/21 11/11 : Defect is fixed and walkthrough provide to Intel IT. Awaiting for approval. 11/05 : Defect and internal CR is in progress revised ETA 11/14. 10/30- Defect # 3450 is still in progress. Revised ETA - 10/31 | 2025-07-18 | N | 08. FTS IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-15 | No | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2560 | FTSE1125 | 04.Enhancement | 02.IF - Intel Foundry | Custom table in S4 to store merging orders and surviving order association from MES(SMH) | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-100-220_FTS_IF_Enhancement%20in%20S4%20to%20create%20custom%20table%20to%20store%20merging%20production%20orders%20and%20surviving%20production%20orders%20in%20S4.pptx?d=w683fc57ba64a4b1ca7b7162e19cecbb9&csf=1&web=1&e=ovzggJ | 02.No | 01.Yes |  | 2025-01-21 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-14 | 2025-04-18 | 2025-03-24 | 100% | 2025-04-05 | 2025-05-05 | 2025-05-16 | 2025-03-25 | 100% | 2025-04-05 | 2025-05-05 | 2025-05-16 | 2025-03-25 | 100% | 2025-04-05 | [15 empty] | 2025-04-05 | 2025-04-05 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-16 12:46 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-31 | 01.S4 |  |  | 0.5 | 0.5 | 1125 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-04-05 | 2025-04-18 | 2025-04-05 |  | 2025-04-05 | 2025-05-16 | 2025-04-05 | 2025-04-05 | [12 empty] | 2025-04-05 | 2025-04-05 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-04-25 | 2025-09-12 | [6 empty] | 0 |  | 1465 | [10 empty] | 2025-05-16 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 2611 | FTSE1119 | 04.Enhancement | 02.IF - Intel Foundry | Custom Table required to support enhancement to store lot attributes when Lot create signal sent S4 to Workstream”. | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 07. FUT Roadblock | Y | 2025-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/_L-120-150_FTS_IF_Enhancement%20in%20Lot%20creation%20signal%20to%20be%20sent%20from%20SAP%20to%20Workstream.pptx?d=w58d7bddd887b44d29b06ccedc03b52cf&csf=1&web=1&e=sVnGdB |  |  |  | 2025-01-21 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | 31348 | Workstream |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-04-29 | 100% | 2025-08-04 | 2025-05-12 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-11 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No | 2025-09-10 | 2025-09-10 | 2025-09-10 | 0% | 50% | 0% |  |  | 05. In Roadblock | 05. In Roadblock | 05. In Roadblock |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 25% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-05-16 | 2025-05-16 | jonsanders@deloitte.com | 2025-01-16 12:46 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 7 | 2025-02-01 | 01.S4 |  |  | 1 | 1 | 1119 | INT-CR1475 | R4 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  |  | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-03-28 | 2025-05-16 | [6 empty] | 0 |  | 2372 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW | 11/18 - Dependent on FTSI1326. Its R4 object no ETA as of now | 2025-05-16 | N | 07. FTS IF |  |  |  | Closed |  | 5. Review Closed |  | Dev In Progress/Dependency | N/A | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2664 | FTSE1024 | 04.Enhancement | 01.IP - Intel Product | Create a custom table and a custom Fiori app in S4 to manually update the release quantity and date for lots on quality hold. | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | Y | 2024-12-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2664_FTS_IP_S4_Create%20a%20custom%20table%20and%20a%20custom%20Fiori%20app%20in%20S4%20to%20manually%20update%20the%20release%20quantity%20and%20date%20for%20lots%20on%20quality%20hold.pptx?d=wf347e4f079f242b7871a7cafd7f88be4&csf=1&web=1&e=LexrVa | 02.No | 01.Yes |  | 2024-12-18 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-06 | 2025-06-13 | 2025-07-25 | 100% | 2025-07-24 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | 2025-07-04 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-02-01 | 01.S4 |  |  | 1 | 1 | 1024 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-08 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | [5 empty] | 2025-05-16 | 2025-07-18 |  |  | 2025-04-08 |  |  |  | 0 | 08. Not Applicable | 2457 | [7 empty] | 1. On Track | 17. FUT In progress | 09/01 : Defect is fixed and sent to Intel IT for approval on 09/04. 08/26 : Awaiting for approval ETA 08/29 08/22 : Defect is fixed and walkthrough provided to Intel IT on 08/21. Awaiting for approval ETA 08/25. 08/18: Defects # 2212 and #2249 are created and defect fix is in progress. ETA 08/22 08/04 - FUT in progress. Planned to be completed in current sprint. | 2025-07-18 | N | 08. FTS IP | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2624 | FTSE1019 | 04.Enhancement | 02.IF - Intel Foundry | WIINGS factory portal UI to send signal for raw material consumption in S4 | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2624_M-100-170_FTS_IF_IMO%20-%20Interface%20from%20WIINGS%20factory%20portal%20UI%20to%20S4%20to%20consume%20raw%20materials%20in%20S4.pptx?d=w95504943d27247058f4122f436158286&csf=1&web=1&e=L7wmuU | 02.No | 01.Yes |  | 2024-12-20 | shamin.a.shirodkar@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-24 | 2025-10-01 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2026-02-07 | 2025-05-19 | 2025-06-13 |  |  | 2025-06-13 | 2025-08-11 | 2025-09-05 |  |  | 2025-09-05 | [5 empty] | 2026-02-07 | 2026-02-07 | No |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-10 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jonsanders@deloitte.com | 2024-12-17 15:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-10 | 01.S4 |  |  | 2 | 2 | 1019 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 2025-06-13 |  |  |  | 2025-09-05 | [6 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | [5 empty] | 2025-05-16 | 2025-12-05 | 2025-06-13 |  | 2026-02-04 |  | Factory Portal UI WIINGS Only | TRUE | 0 |  | 2563 | [7 empty] | 1. On Track | 3. Awaiting Approval | 2/27:Awaiting Approval 2/23:Awaiting Approval 2/13:7222,7265,7273 defects in progress 2/9: Defect 6412 raised to tech team 2/2: Defect 6412 raised to tech team. 01/06: Defect 4985 raised to tech team. 01/14: Replanned for S22 | 2025-12-05 | N | 07. FTS IF | Factory Portal UI |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 2577 | FTSE1010 | 04.Enhancement | 02.IF - Intel Foundry | Update the Copper/Heavy Metal flag (User Status) for the tools on placement at pass through . | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-07-04 | 2025-07-11 | 2025-07-25 | 100% | 2025-08-09 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-08-09 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-08-09 | [15 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-12-16 13:18 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-06 | 01.S4 |  |  | 1 | 1 | 1010 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 |  | 2025-08-09 | 2025-08-15 | 2025-08-09 | 2025-08-09 | [12 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-14 |  | WIINGS Only | TRUE | 0 |  | 2151 | [9 empty] | 9/12 : Reviewed with client on 9/11. Sent for Approval - awaiting response | 2025-08-15 | N | 07. FTS IF | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2543 | FTSE0996 | 04.Enhancement | 02.IF - Intel Foundry | Create Purchase Requisition with multiple purchase req document types from Work Order | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-17 | 2025-06-06 | 2025-06-13 | 2025-04-29 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-08 | 2025-08-13 | N | 100% | 2025-07-25 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-06 | 01.S4 |  |  | 1 | 1 | 0996 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-21 | 2025-03-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-10-10 |  | WIINGS Only | TRUE | 0 |  | 1509 | [10 empty] | 2025-07-18 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2541 | FTSE0995 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to update rejection reason and text in maintenance work order from IBD on delivery rejection | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-03-21 | 100% | 2025-03-17 | 2025-07-04 | 2025-07-11 | 2025-04-29 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-15 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-06 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-06 | 01.S4 |  |  | 1 | 1 | 0995 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-04-18 | 2025-03-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-06 | 2025-10-06 | 2025-10-06 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-19 |  | WIINGS Only | TRUE | 0 |  | 2403 | [9 empty] | This FUT is complete and reflecting as complete in the Object Tracker | 2025-08-15 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2524 | FTSE0993 | 04.Enhancement | 02.IF - Intel Foundry | Auto Roll Function to add Item/Part through Batch job in Master Warranty | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-07 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-13 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-24 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-24 | [15 empty] | 2025-09-24 | 2025-09-24 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-10 | 2025-10-10 | 2025-10-10 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 0993 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-13 | 2025-09-19 | 2025-09-13 |  | 2025-09-24 | 2025-10-10 | 2025-09-24 | 2025-09-24 | [12 empty] | 2025-09-24 | 2025-09-24 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-08-15 |  | WIINGS Only | TRUE | 0 |  | 2802 | [7 empty] | 4. Completed | 17. FUT In progress | 10/31: Started Review with Intel | 2025-10-10 | Y | 07. FTS IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2522 | FTSE0992 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fields Enhancement in WTY Claim | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-07-04 | 2025-07-11 | 2025-07-25 | 100% | 2025-07-24 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | 2025-08-01 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 0992 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-07-24 | 2025-07-25 | 2025-07-24 |  | 2025-07-24 | 2025-08-15 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-10-03 |  | WIINGS Only | TRUE | 0 |  | 2113 | [9 empty] | 9/11 : Conditional approval received from Intel. The developer is still working on it | 2025-08-15 | N | 07. FTS IF | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2521 | FTSE0991 | 04.Enhancement | 02.IF - Intel Foundry | Claim Generation from Maintenance Work Order per Item | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-04 | 2025-07-25 | 100% | 2025-08-09 | 2025-08-29 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-09 | 2025-08-29 | 2025-08-08 | 2025-08-08 | 100% | 2025-08-09 | [15 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-08 | 2025-08-08 | 2025-08-08 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 0991 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-08-09 | [12 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-24 |  | WIINGS Only | TRUE | 0 |  | 1867 | [9 empty] | 10/9: have reviewed with Intel & only pending final approvals | 2025-08-08 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-09 | 2025-08-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2519 | FTSE0990 | 04.Enhancement | 02.IF - Intel Foundry | Create PR with Free of Charge from approved claim status – MMID & Non-MMID | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-05 | 2025-07-02 | 2025-07-09 | 2025-08-01 | 100% | 2025-09-13 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-10-02 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-10-02 | [15 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-13 | 2025-08-13 | 2025-08-13 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-06-10 | 01.S4 |  |  | 1 | 1 | 0990 |  | R3 ITC1 | [6 empty] | 2025-06-05 | 2025-06-13 | 2025-06-05 |  | 2025-09-13 | 2025-09-13 | 2025-09-13 |  | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | [12 empty] | 2025-10-02 | 2025-10-02 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-06-13 | 2025-08-13 |  |  | 2025-10-08 |  | WIINGS Only | TRUE | 0 |  | 1866 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 12/4 - Reviewed with Intel. Received approval; waiting for a defect 4884 to close to mark 100% | 2025-08-13 | N | 07. FTS IF |  |  |  | Current Status: Build due to Requirement clarification in progress. Issue: FUT on hold due to design change Next Steps: FUT to resume once the CR is completed. ETA is TBD Help Needed: |  |  |  | Defects | Complete | R3 Build & UT Sprint 18 |  | 2025-10-02 | 2025-10-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2518 | FTSE0989 | 04.Enhancement | 02.IF - Intel Foundry | Warranty validation at Equipment level & Item/Part level in Work Order | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 0989 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-09-05 | 2025-09-12 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-10-03 |  | WIINGS Only | TRUE | 0 |  | 1865 | [7 empty] | 1. On Track | 1. Approved no action | 10/23 - Object approved. Smartsheet Updated | 2025-09-12 | N | 07. FTS IF | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2517 | FTSE0988 | 04.Enhancement | 02.IF - Intel Foundry | Convert Item/Part Warranty information upload to SAP S/4 Master Warranty | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-17 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-17 | 2025-09-12 | 2025-09-19 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-08-14 | 01.S4 |  |  | 2 | 2 | 0988 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-21 | 2025-03-17 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | [5 empty] | 2025-03-21 | 2025-12-05 |  |  | 2026-02-04 |  | WIINGS Only | TRUE | 0 |  | 1864 |  |  | WIINGS |  |  |  |  | 1. On Track | 3. Awaiting Approval | 2/2: Waiting for approval | 2025-12-05 | N | 07. FTS IF |  |  |  | 0120: No roadblocks |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2513 | FTSE0984 | 04.Enhancement | 02.IF - Intel Foundry | SAP Warranty Claim Document to e2open (Outbound Interface) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-14 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved | 2025-01-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-31 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-01 | 2025-08-08 | 2025-05-20 | 100% | 2025-05-24 | 2025-08-29 | 2025-09-12 | 2025-05-23 | 100% | 2025-05-24 | 2025-08-29 | 2025-09-12 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-07-25 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-31 | 01.S4 |  |  | 1 | 1 | 0984 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-24 | 2025-08-08 | 2025-05-24 |  | 2025-05-24 | 2025-09-12 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-25 | 2025-08-13 | 2025-07-25 | [5 empty] | 2025-05-16 | 2025-09-12 |  |  | 2025-10-03 |  | WIINGS Only | TRUE | 0 |  | 2382 | [10 empty] | 2025-09-12 | Y | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-09-12 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2031 | FTSE0982 | 04.Enhancement | 02.IF - Intel Foundry | SAP PM enhancement to capture reason codes for returns (dropdown) | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2024-12-19 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Intake%20Forms_GPO%20alignment%2012.11.2024.pptx?d=wbb4888df4169425bb459cb24b2baa0b7&csf=1&web=1&e=8CXFpE | 02.No | 01.Yes |  | 2024-12-17 | Shamin Shirodkar | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-10 | 2025-06-06 | 2025-06-13 | 2025-04-29 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | 2025-06-27 | 2025-07-18 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-05 | 2025-08-13 | N | 100% | 2025-09-25 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | vasamohan@deloitte.com | 2024-12-16 12:43 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-06 | 01.S4 |  |  | 2 | 2 | 0982 | INT-CR0870 | R3 ITC1 | [6 empty] | 2025-03-10 | 2025-03-21 | 2025-03-10 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-25 | 2025-09-25 | 2025-09-25 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-07-18 |  | WIINGS Only | TRUE | 0 |  | 2010 | [9 empty] | 9/19 : Dependent on INT-CR0757 (overdue from S15); & development of work order management (FTSE1348) screen, which won't be developed until November (will be at 90% complete until then); working to find work around of screen testing to complete sooner; attempted to test but ran into issues so raised defect; Defect 2961 - ZTFTS_PM_RESB is not updating | 2025-07-18 | N | 07. FTS IF | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2038 | FTSE0925 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement: Batch process to create Equipment from Material BOM after GR | 07. FTS IF | 7.9 FTS IF - Plant Maintenance | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW%20Sprint%206_Consolidated%20Review_sent%20for%20approval.pptx?d=w089c25e3e662433ea2fdc8964a8862be&csf=1&web=1&e=nfZ6OH | 02.No | 01.Yes |  | 2024-12-17 | shamin.a.shirodkar@intel.com | 01.Approved | 2024-12-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-04 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:23 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-01-24 | 01.S4 |  |  | 1 | 1 | 0925 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-07-25 |  | WIINGS Only | TRUE | 0 |  | 2014 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change | 10/31: GPO Approval received for CR 0923. Need to incorporate CR changes. | 2025-09-12 | N | 07. FTS IF | [7 empty] | CR/Design change | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2012 | FTSE0593 | 04.Enhancement | 01.IP - Intel Product | Enhancement of standard iDoc to capture and transfer Build Instructions from S4 HANA to E2Open | 08. FTS IP | 8.5 FTS IP - Manufacturing | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B105B4B76-C6E9-4690-940B-FAA3092E7803%7D&file=M-090-110_FTS_IP_Enhancement%20of%20Standard%20iDoc%20to%20transfer%20Build%20Instructions.pptx&wdLOR=c719BE076-40E2-45B2-B49C-8C0599A2B06E&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-04 | Thomas M Sanger | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA |  |  | NA | 2025-01-27 | 2025-02-07 | 2024-11-15 | 100% | 2024-12-12 | 2025-03-14 | 2025-03-21 | 2025-03-25 | 100% | 2025-04-05 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-05 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-04-05 | [15 empty] | 2025-04-05 | 2025-04-05 |  |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-09 | 2025-06-11 | N | 100% | 2025-08-05 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-12 10:12 | 10 | 2025-02-01 | 01.S4 |  |  | 2 | 2 | 0593 |  | R3 ITC1 | [6 empty] | 2024-12-12 | 2025-02-07 | 2024-12-12 |  | 2025-04-05 | 2025-04-05 | 2025-04-05 |  | 2025-04-05 | 2025-04-18 | 2025-04-05 | 2025-04-05 | [12 empty] | 2025-04-05 | 2025-04-05 |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-23 |  |  |  | 0 | 08. Not Applicable | 2020 | [9 empty] | 8/4- Defect 1809 in progress. FUT in progress. Delayed due to defect fixes | 2025-04-18 | N | 08. FTS IP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-05 | Yes | ZTFTS_PARAMS table entries will be impacted with reference to new enterprise structure​ | No |  | No |  | 2026-02-09 | 2026-03-04 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-12 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1863 | FTSE0507 | 04.Enhancement | 02.IF - Intel Foundry | Custom Program to read planned orders and build instruction data and generate replenishment orders from 3PL or local warehouse and raise alert if materials/batches needed for production plan are missing | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1863_L-060-190_FTS_IF_Enhancement%20in%20S4%20to%20replenish%20bailed%20and%20direct%20material%20to%20factory%20floor%20from%203PL.pptx?d=wfd347d2be78d4e2585c0c7ceb5964b79&csf=1&web=1&e=T7bSeB | 02.No | 01.Yes |  | 2024-08-20 | Shamin A Shirodkar | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-06 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-30 | 2025-07-04 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-30 | 2025-07-04 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-30 | [15 empty] | 2025-07-30 | 2025-07-30 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-08-06 08:30 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-22 | 01.S4 |  |  | 1 | 1 | 0507 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-07-30 | 2025-08-01 | 2025-07-30 |  | 2025-07-30 | 2025-08-13 | 2025-07-30 | 2025-07-30 | [12 empty] | 2025-07-30 | 2025-07-30 |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2176 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 11/18: FUT in progress after defect resolution 11/14: Defect in progress ETA 11/17 11/12: - Defect 3354. | 2025-07-18 | N | 07. FTS IF | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1897 | FTSE0506 | 04.Enhancement | 02.IF - Intel Foundry | Custom table to store planned orders and pegged sales orders in S4 | 07. FTS IF | 7.8 FTS IF - MRP & Planning Integration | 10. Object Complete | Y | 2024-08-21 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1897_L-060-190_FTS_IF_Enhancement%20in%20S4%20to%20create%20custom%20table%20to%20store%20planned%20orders%20and%20pegged%20sales%20orders%20in%20S4.pptx?d=wdaf6fd05ac9d45c08c0f8cf8e9632c5b&csf=1&web=1&e=MZb1aQ | 02.No | 01.Yes |  | 2024-08-20 | Shamin A Shirodkar | 01.Approved | 2024-08-21 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-11-15 | 2024-12-13 | 100% | 2024-11-21 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | 2025-01-06 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-02 | 2025-06-27 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-01-31 | 2025-01-31 | 2025-01-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 | 2024-08-22 | 01.S4 |  |  | 1 | 1 | 0506 |  | R3 ITC1 | [6 empty] | 2024-11-21 | 2024-12-13 | 2024-11-21 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-31 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-11-15 | 2025-01-31 |  |  | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 1702 | [10 empty] | 2025-01-31 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-31 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1703 | FTSE0424 | 04.Enhancement | 01.IP - Intel Product | Conversion of Production Versions data into S4 | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-090-430_FTS_IP_Schedule%20Production_Process%20Production%20Versions.pptx?d=w22540dacac20494eb5bb6ddb9545a636&csf=1&web=1&e=xKtN7t | 02.No | 01.Yes |  | 2024-06-26 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | S4 HANA | S4 HANA | NA | 2025-02-07 | 2025-02-21 | 2024-10-18 | 100% | 2024-11-26 | 2024-12-03 | 2025-03-07 | 2025-03-24 | 100% | 2025-04-05 | 2025-02-07 | 2025-02-21 | 2025-03-25 | 100% | 2025-04-05 | 2025-02-07 | 2025-03-21 | 2025-03-25 | 100% | 2025-04-05 | [15 empty] | 2025-04-05 | 2025-04-05 |  |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-04 | 2025-04-18 | N | 100% | 2025-04-18 | Not Applicable | R3 Build & UT Sprint 12 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-25 21:51 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0424 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-02-21 | 2024-11-26 |  | 2025-04-05 | 2025-04-05 | 2025-04-05 |  | 2025-04-05 | 2025-04-05 | 2025-04-05 | 2025-04-05 | [12 empty] | 2025-04-05 | 2025-04-05 |  |  | 2025-04-18 | 2025-04-18 | [6 empty] | 2024-10-18 | 2025-02-21 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 1796 | [10 empty] | 2025-03-21 | N | 08. FTS IP | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-05 | 2025-04-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1685 | FTSE0423 | 04.Enhancement | 02.IF - Intel Foundry | Create custom table in SAP to store the build instruction data | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1685_M-100-030_FTS_IF_Custom%20table%20creation%20in%20S4%20for%20storing%20build%20instructions%20in%20unified%20data%20format.pptx?d=w761d492163f94b53a57894b86d54e86b&csf=1&web=1&e=pYjgdf | 02.No | 01.Yes |  | 2024-06-26 | Shamin A Shirodkar | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-07-29 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-01-17 | 2025-01-17 | 2025-01-17 | pgaroo@deloitte.com | 2024-06-25 21:51 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0423 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-01-17 |  |  | 2025-03-31 |  |  |  | 0 | 08. Not Applicable | 2721 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2025-01-17 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 318 | FTSE0198 | 04.Enhancement | 01.IP - Intel Product | Conversion Program for Routings | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/M-090-280_FTS_Conversion%20Program%20for%20Routings.pptx?d=w495b6eb87080414b9668b93ccaefb230&csf=1&web=1&e=74AiS3 | 02.No | 01.Yes |  | 2024-05-28 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | S4 HANA | NA | 2025-02-03 | 2025-02-21 | 2024-10-18 | 100% | 2024-11-26 | 2024-12-03 | 2025-03-07 | 2025-02-14 | 100% | 2025-02-09 | 2025-02-07 | 2025-02-21 | 2025-03-14 | 100% | 2025-03-08 | 2025-04-21 | 2025-05-09 | 2025-03-14 | 100% | 2025-03-08 | [15 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-12 | 2025-05-23 | 2025-07-16 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-09 | 2025-05-09 | 2025-05-09 | pgaroo@deloitte.com | 2024-05-10 03:08 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 |  | 01.S4 |  |  | 1 | 1 | 0198 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2025-02-21 | 2024-11-26 |  | 2025-02-09 | 2025-03-07 | 2025-02-09 |  | 2025-03-08 | 2025-03-14 | 2025-03-08 | 2025-03-08 | [12 empty] | 2025-03-08 | 2025-03-08 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2024-10-18 | 2025-02-21 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 1825 | [9 empty] | 8/11- Submitted. Awaiting approval. FUT in progress. Delayed due to multiple defects. Latest defect - 1683 | 2025-05-09 | N | 08. FTS IP | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-05-09 | 2025-03-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3149 | FTSC1682 | 03.Conversion | 01.IP - Intel Product | Conversion of Intel Products Bailed Inventory & Lot Attributes | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3149_Conversion%20of%20Intel%20Products%20Bailed%20Inventory%20%26%20Lot%20Attributes%E2%80%8B.pptx?d=wbf6b399c56f648ecb708166fd4bc4275&csf=1&web=1&e=jAU20J | 02.No | 01.Yes |  | 2025-11-04 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-14 | 2025-11-19 | 2025-11-19 | 2026-01-07 | 100% | 2026-01-05 | 2025-11-20 | 2025-11-21 | 2026-01-07 | 100% | 2026-01-05 | 2025-11-12 | 2025-11-24 | 2026-01-07 | 100% | 2026-01-05 | [15 empty] | 2026-01-05 | 2026-01-05 |  |  | 2026-03-13 | 2026-03-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-13 | N | 100% | 2026-03-17 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-11-24 | 2025-11-24 | 2025-11-24 | jenoronha@deloitte.com | 2025-11-04 04:16 | automation@smartsheet.com | 2026-03-16 14:51 | 10 | 2025-11-20 | 01.S4 |  |  | 1 | 1.45 | 1682 | INT-CR1356 | R3 ITC1 | [6 empty] | 2025-11-14 | 2025-12-05 | 2025-11-14 |  | 2026-01-05 | 2026-01-07 | 2026-01-05 |  | 2026-01-05 | 2026-01-07 | 2026-01-05 | 2026-01-05 | [12 empty] | 2026-01-05 | 2026-01-05 |  | 2026-03-17 | 2026-03-17 | 2026-03-13 | [6 empty] | 2025-12-05 | 2025-11-24 |  |  | 2026-03-04 |  |  |  | 0 |  | 3366 | [7 empty] | 2. At Risk | 17. FUT In progress | 03/13 : Awaiting for approval ETA 03/19 03/05 - Walkthrough is planned tomorrow. ETA 03/06 2/27 - ETA from ECA team is 2/28. S/4 build completed and S/4 FUT is done. P1 RAID raised for ECA team 03614 02/20 : Off track and will be spill over to S24. 01/13 : Dev is in progress. 12/18 : Waiting on ECA team response. P1Raid item #03134 | 2025-11-24 | N | 08. FTS IP |  |  |  | 03/11: Addressing Feedback comments. Will be reshared for approval by 03/17 Current status: Addressing Feedback comments Issue: FUT on hold due to ECA dependency Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/20 | ECA Dependency ( Intel) | 2. Risk | At risk for S23 | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2026-01-07 | 2026-01-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3004 | FTSC1559 | 03.Conversion | 01.IP - Intel Product | Conversion of Open PO/Engineering/Rework Orders into Production orders from IF to IP | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3004_M-090-110_FTS_IP_Schedule%20Production_Conversion%20of%20Open%20POEngineeringRework%20Orders%20into%20Production%20orders%20from%20IF%20to%20IP.pptx?d=w2e642f38fd4b4b10b41c1365a6445641&csf=1&web=1&e=SfDFio | 02.No | 01.Yes |  | 2025-08-13 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-23 | 2025-09-15 | 2025-09-16 | 2025-09-15 | 100% | 2025-09-18 | 2025-09-16 | 2025-09-18 | 2025-09-24 | 100% | 2025-09-26 | 2025-09-19 | 2025-10-10 | 2025-12-04 | 100% | 2026-01-12 | [15 empty] | 2026-01-12 | 2026-01-12 |  |  | 2026-01-31 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-07-24 03:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1559 | INT-CR0770 | R3 ITC1 | [6 empty] | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2026-01-12 | [12 empty] | 2026-01-12 | 2026-01-12 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-09-10 | 2025-10-10 |  |  | 2026-02-04 |  |  |  | 0 |  | 3187 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/06 : Awaiting for approval ETA 03/06. 2/27 - Walkthrough completed. 2/26 - Build completed for CR. FUT started for changes. 02/20 : FUT is in WIP 02/16: Internal CR is created and Dev WIP ETA 02/20 02/02 : FUT documentation is WIP and ETA 02/06 for approval. 01/21 : FUT is in Progress. 01/13 : E2E FUT is planned in Sprint 22. 01/06 : TUT - Blocker due to defect in user exit (FTSE1642) .Defect # 5574. Vineeta to check- May have to raise SAP message | 2025-10-10 | N | 08. FTS IP |  |  |  |  | Week 3 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-12 | 2026-01-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 04.R4 | 3035 | FTSC1550 | 03.Conversion | 02.IF - Intel Foundry | Inventory Conversion | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Shamin Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 2 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1550 |  | R4 ITC1 | [48 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3167 |  |  | WIINGS |  |  |  |  | 5. Not Dispositioned |  |  |  | N | 07. FTS IF | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | Not Dispositioned |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 1756 | FTSC0434 | 03.Conversion | 01.IP - Intel Product | Conversion of Open Production Orders from ECC purchase order data into S4 | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9F4E9A91-8228-48B6-BE16-B65188DCCE67%7D&file=M-090-110_FTS_IP_Schedule%20Production_Process%20Production%20Order%20(Conversion).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-07-09 | Thomas M Sanger | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | ECC | S4 HANA | NA | 2025-03-03 | 2025-04-18 | 2024-08-23 | 100% | 2024-08-21 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-09-23 | 2024-09-30 | 2024-10-04 | 100% | 2024-10-03 | 2025-04-28 | 2025-05-16 | 2024-12-06 | 100% | 2024-12-09 | [15 empty] | 2024-12-09 | 2024-12-09 |  |  | 2025-10-31 | 2025-10-31 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-10-31 | N | 100% | 2025-11-21 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-07-09 00:12 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0434 | INT-CR0168 | R3 ITC1 | [6 empty] | 2024-08-21 | 2025-04-18 | 2024-08-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-10-03 | 2024-10-04 | 2024-10-03 | 2024-12-09 | [12 empty] | 2024-12-09 | 2024-12-09 |  |  | 2025-11-21 | 2025-11-21 | 2025-11-21 | [5 empty] | 2024-08-23 | 2024-09-30 |  |  | 2025-01-31 |  |  |  | 0 | 08. Not Applicable | 2132 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/18- Walkthrough completed with Intel IT. FUT Awaiting approval ETA is 11/21 11/14 -Walkthrough completed with Intel IT. FUT Awaiting approval ETA is 11/21 11/11 : FUT Walkthrough is done and Awaiting for Intel IT approval. 11/6- FUT in progress. Review in progress with Intel IT team. 10/24 - FUT in progress post CR development | 2025-05-16 | N | 08. FTS IP |  |  |  | 5.1 Complete. Awaiting Approval 1211 ETA 1121 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 8 |  | 2025-05-16 | 2024-12-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 90 | FTSC0052_IP | 03.Conversion | 01.IP - Intel Product | Conversion of Reference Operation Sets to S/4 | 08. FTS IP | 8.1 FTS IP - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20MySamples%20-%20Sample%20Order%20Change.pdf?csf=1&web=1&e=u3gdh8 | 02.No | 01.Yes |  | 2024-04-09 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | ECC | ECC | S4 | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-18 | 2025-08-19 | 2025-08-19 | 100% | 2025-08-18 | 2025-08-19 | 2025-08-21 | 2025-08-22 | 100% | 2025-08-22 | 2025-08-22 | 2025-09-10 | 2025-09-19 | 100% | 2025-09-18 | [15 empty] | 2025-09-18 | 2025-09-18 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-10 | 2025-09-10 | 2025-09-10 | jenoronha@deloitte.com | 2025-05-01 22:16 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0052 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-18 | 2025-08-19 | 2025-08-18 |  | 2025-08-22 | 2025-08-22 |  | 2025-09-18 | [12 empty] | 2025-09-18 | 2025-09-18 |  |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | [5 empty] | 2025-07-16 | 2025-09-10 |  |  | 2025-10-08 |  |  |  | 0 | 08. Not Applicable | 3008 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 : Walkthrough provide to Intel IT team. Awaiting for approval. | 2025-09-10 | N | 08. FTS IP | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-19 | 2025-09-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 90 | FTSC0052_IF | 03.Conversion | 02.IF - Intel Foundry | Conversion of Reference Operation Sets to S/4 | 07. FTS IF | 7.7 FTS IF - Manufacturing & MES Integration | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/IPG_Enable%20MySamples%20-%20Sample%20Order%20Change.pdf?csf=1&web=1&e=u3gdh8 | 02.No | 01.Yes |  | 2024-04-09 | Shamin A Shirodkar | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | ECC | ECC | S4 | NA | 2024-11-25 | 2025-01-31 | 2024-08-23 | 100% | 2024-07-30 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-08-05 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-08 | 2024-08-12 | 2024-10-04 | 2024-10-04 | 100% | 2024-10-07 | [15 empty] | 2024-10-07 | 2024-10-07 | No |  | 2024-11-15 | 2024-12-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-03 | 2025-02-21 | 2024-12-13 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-04 | 2024-10-04 | 2024-10-04 | pgaroo@deloitte.com | 2024-04-09 01:42 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 | FTSC0052_IP | 03.Medium | 0.3 | 0.435 | 0052 |  | R3 ITC1 | [6 empty] | 2024-07-30 | 2025-01-31 | 2024-07-30 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-08-08 | 2024-08-09 | 2024-08-08 | 2024-10-07 | [12 empty] | 2024-10-07 | 2024-10-07 |  |  | 2024-12-13 | 2025-02-21 | [6 empty] | 2025-01-31 | 2024-10-04 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 1483 | [10 empty] | 2024-10-04 | N | 07. FTS IF | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-07 | 2024-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 514 | FPRW1449 | 06.Workflow | 05.CFIN | TPR : Workflow to handle Memo creation and cancellation process | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B580759F0-2843-4492-8FD6-A28C3D42DDD4%7D&file=MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_TPR.pptx&wdLOR=c7E05ECCF-D468-4A49-BAFB-569FEF939098&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRI0224 | 2024-05-21 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-06-16 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-19 21:54 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1.05 | 1449 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-07-11 | 2025-10-10 |  |  | 2025-11-07 |  |  |  | 0 | 06. Banks | 3039 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/13 EP: Confirm if FUT has been conditionally signed off/approved 11/12: Sent for Conditional Signoff along with 240 as child Object. | 2025-10-10 | N | 03. FPR |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1586 | FPRW1444 | 06.Workflow | 05.CFIN | TFR: Workflow to handle Memo creation and cancellation process | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_CFR.pptx?d=wde49673c21924b2c82c2fb99e792c491&csf=1&web=1&e=W3IPRW | 02.No | 01.Yes | FPRI0224 | 2025-05-08 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-03 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-20 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-09-05 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-08 02:50 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-09 | 01.S4 |  |  | 1 | 1.05 | 1444 |  | R3 ITC1 | [6 empty] | 2025-06-03 | 2025-06-13 | 2025-06-03 |  | 2025-08-20 | 2025-09-19 | 2025-08-20 |  | 2025-08-20 | 2025-10-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2025-06-13 | 2025-10-10 |  |  | 2025-10-08 |  |  |  | 0 |  | 3013 | [7 empty] | 1. On Track | 1. Approved no action | 12/10: Conditionally Approved by Shira | 2025-10-10 | Y | 03. FPR |  |  |  |  | 1119: ETA 1125. Long pending critical object. Nishant to follow up. |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRW1064_IP | 06.Workflow | 01.IP - Intel Product | Custom Workflow will also be created with some predefined process/rules for approval/rejection. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N | 2025-01-09 | 02. Pending (Need clarifications) | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2026-01-31 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-02-12 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2026-02-12 | [15 empty] | 2026-02-12 | 2026-02-12 | No |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-31 | 2025-10-31 | 2025-10-31 | jonsanders@deloitte.com | 2024-12-19 13:32 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-12-21 | 01.S4 |  |  | 4 | 4.2 | 1064 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | [12 empty] | 2026-02-12 | 2026-02-12 |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 |  | 2759 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/09: Satavisa is working on the Tech updates. Need to check with her on the latest status. | 2025-10-31 | N | 03. FPR |  |  |  |  | On track for 3/6 completion |  |  | Defects | Complete | R3 Build & UT Sprint 23 |  | 2026-02-12 | 2026-02-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRW1064_IF | 06.Workflow | 02.IF - Intel Foundry | Custom Workflow will also be created with some predefined process/rules for approval/rejection. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N | 2025-01-09 | 02. Pending (Need clarifications) | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-12-24 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-24 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 | No |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-10-31 | 2025-10-31 | 2025-10-31 | jonsanders@deloitte.com | 2024-12-19 13:32 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-12-21 | 01.S4 | FPRW1064_IP | 01.Very High | 2 | 2.1 | 1064 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 |  | 2758 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 03/09: Satavisa is working on the Tech updates. Need to check with her on the latest status. | 2025-10-31 | N | 03. FPR |  |  |  |  | On track for 3/6 completion |  |  | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2399 | FPRW0930 | 06.Workflow | 05.CFIN | Workflow for Counterparty Approval | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2399_FPR_Workflow%20for%20CounterParty.pptx?d=w6b134e8bf04142c3879f55bdc9736e56&csf=1&web=1&e=wMhAjS | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-04-04 | 100% | 2025-04-04 | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-06 | 2025-10-13 | 2025-11-07 | 2025-12-12 | 100% | 2025-12-13 | 2025-10-13 | 2025-11-07 | 2025-12-12 | 100% | 2025-12-13 | [15 empty] | 2025-12-13 | 2025-12-13 | No |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-06 | 2026-01-02 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 02.MDG |  |  | 1 | 1.05 | 0930 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-11-06 | 2025-11-07 | 2025-11-06 |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | [12 empty] | 2025-12-13 | 2025-12-13 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-02-21 | 2025-10-17 |  |  | 2025-12-05 |  |  |  | 0 |  | 2402 | [7 empty] | 5. Not Dispositioned | 24. Incorrect plan | 01/08: Sprint 21 object planned in S20. More details are yet to be received | 2025-11-07 | N | 03. FPR | [7 empty] | Incorrect plan | Complete | R3 Build & UT Sprint 21 |  | 2025-12-13 | 2025-12-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2490 | FPRW0906_IP | 06.Workflow | 01.IP - Intel Product | Custom workflow: Change Order Create and Change Approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B49E0E32F-3413-47AE-A573-77B3EB1604F4%7D&file=2490_FPR_DC-050-680-%20Custom%20workflow%20Change%20Order%20Create%20and%20Change%20Approval%20Workflow.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2026-01-30 | 2026-03-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-16 12:23 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.05 | 0906 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-21 |  |  |  | 0 |  | 1774 | [7 empty] | 1. On Track | 17. FUT In progress | 03/11: Documentation in Progress , all issues fixed. | 2025-12-05 | N | 03. FPR |  |  |  |  | Walkthrough planned today |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2490 | FPRW0906_IF | 06.Workflow | 02.IF - Intel Foundry | Custom workflow: Change Order Create and Change Approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B49E0E32F-3413-47AE-A573-77B3EB1604F4%7D&file=2490_FPR_DC-050-680-%20Custom%20workflow%20Change%20Order%20Create%20and%20Change%20Approval%20Workflow.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2026-01-30 | 2026-03-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2024-11-20 03:23 | cell-link@smartsheet.com | 2026-03-16 12:23 | 10 | 2024-12-11 | 01.S4 | FPRW0906_IP | 03.Medium | 0.5 | 0.525 | 0906 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-11-21 |  |  |  | 0 |  | 1773 | [7 empty] | 1. On Track | 17. FUT In progress | 03/11: Documentation in Progress , all issues fixed. | 2025-12-05 | N | 03. FPR |  |  |  |  | Walkthrough planned today |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2471 | FPRW0904_IP | 06.Workflow | 01.IP - Intel Product | Custom Workflow - WBS Element Request approval with WBS Element creation | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFBF8097C-E25B-48C8-93C3-1BD82AFF16ED%7D&file=2471_FPR_DC-050-500-Custom%20workflow-%20WBS%20Element%20Request%20Approval%20with%20WBS%20Element%20Creation.pptx&wdLOR=cFB2BEE09-EA6C-49E4-8923-749D099B1111&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-04 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | [15 empty] | 2025-10-11 | 2025-10-11 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.05 | 0904 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-04 | 2025-10-04 | 2025-10-04 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [12 empty] | 2025-10-11 | 2025-10-11 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-07 |  |  |  | 0 | 08. Not Applicable | 1892 | [7 empty] | 1. On Track | 1. Approved no action | 01/09: FUT Approved. | 2025-10-03 | N | 03. FPR |  |  |  |  | 12/09 - ETA 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2471 | FPRW0904_IF | 06.Workflow | 02.IF - Intel Foundry | Custom Workflow - WBS Element Request approval with WBS Element creation | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BFBF8097C-E25B-48C8-93C3-1BD82AFF16ED%7D&file=2471_FPR_DC-050-500-Custom%20workflow-%20WBS%20Element%20Request%20Approval%20with%20WBS%20Element%20Creation.pptx&wdLOR=cFB2BEE09-EA6C-49E4-8923-749D099B1111&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-04 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | [15 empty] | 2025-10-11 | 2025-10-11 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRW0904_IP | 03.Medium | 0.5 | 0.525 | 0904 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-04 | 2025-10-04 | 2025-10-04 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [12 empty] | 2025-10-11 | 2025-10-11 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-07 |  |  |  | 0 | 08. Not Applicable | 1891 | [7 empty] | 1. On Track | 1. Approved no action | 01/09: FUT Approved. | 2025-10-03 | N | 03. FPR |  |  |  |  | 12/09 - ETA 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRW0900_IP | 06.Workflow | 01.IP - Intel Product | Custom Workflow: Approval for Project creation and create a Project def and level n1 after approval using template | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-09-05 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.05 | 0900 |  | R3 ITC1 | [6 empty] | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-09-05 | 2025-09-05 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-10-10 |  |  |  | 0 |  | 1886 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 11/06: Tejasvi defect is open with Dev & FUT in progress. | 2025-08-13 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRW0900_IF | 06.Workflow | 02.IF - Intel Foundry | Custom Workflow: Approval for Project creation and create a Project def and level n1 after approval using template | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-09-05 | 2025-08-04 | 2025-08-13 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-13 | 2025-08-13 | 2025-08-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRW0900_IP | 03.Medium | 0.5 | 0.525 | 0900 |  | R3 ITC1 | [6 empty] | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-09-05 | 2025-09-05 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-09-26 |  |  |  | 0 |  | 1885 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/12: New Scenario requested by Doris which is not part of the design. | 2025-08-13 | N | 03. FPR |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1363 | FPRW0445_IP | 06.Workflow | 01.IP - Intel Product | Project budget approval workflow (Capex)​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Project%20Approval%20Workflow.pptx?d=wea0146b2d490499487876c5093528a26&csf=1&web=1&e=Bwb7WK | 02.No | 01.Yes |  | 2024-07-12 | Angela Wolf | 01.Approved | 2024-07-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-05 | 2024-08-23 | 2024-08-23 | 100% | 2025-08-29 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | vasamohan@deloitte.com | 2024-07-12 10:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1.05 | 0445 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-12 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2024-08-23 | 2025-03-21 |  |  | 2025-10-27 |  |  |  | 0 | 08. Not Applicable | 1767 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1363 | FPRW0445_IF | 06.Workflow | 02.IF - Intel Foundry | Project budget approval workflow (Capex)​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Project%20Approval%20Workflow.pptx?d=wea0146b2d490499487876c5093528a26&csf=1&web=1&e=Bwb7WK | 02.No | 01.Yes |  | 2024-07-12 | Angela Wolf | 01.Approved | 2024-07-12 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-05 | 2024-08-23 | 2024-08-23 | 100% | 2025-08-29 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | vasamohan@deloitte.com | 2024-07-12 10:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | FPRW0445_IP | 03.Medium | 0.5 | 0.525 | 0445 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-12 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2024-08-23 | 2025-03-21 |  |  | 2025-10-27 |  |  |  | 0 | 08. Not Applicable | 1766 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 709 | FPRW0325_IP | 06.Workflow | 01.IP - Intel Product | Custom workflow to manage the approval process in bulk/individual requests | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-070-0002_FPR_AMT_Custom%20workflow%20to%20manage%20the%20approval%20process%20in%20bulk_individual%20requests.pptx?d=w3348fa2df9ab48ea8ce5e6916566cef6&csf=1&web=1&e=ZiADHv | 02.No | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-09-13 | 100% | 2024-11-26 | 2025-01-31 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-01-31 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-09 | Not Applicable | R3 Build & UT Sprint 13 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 2.1 | 0325 |  | R3 ITC1 | [6 empty] | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | [5 empty] | 2024-07-26 | 2025-02-21 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2590 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 709 | FPRW0325_IF | 06.Workflow | 02.IF - Intel Foundry | Custom workflow to manage the approval process in bulk/individual requests | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-070-0002_FPR_AMT_Custom%20workflow%20to%20manage%20the%20approval%20process%20in%20bulk_individual%20requests.pptx?d=w3348fa2df9ab48ea8ce5e6916566cef6&csf=1&web=1&e=ZiADHv | 02.No | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-08-02 | 2024-08-09 | 2024-09-13 | 100% | 2024-11-26 | 2025-02-07 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-07 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRW0325_IP | 02.High | 1 | 1.05 | 0325 |  | R3 ITC1 | [6 empty] | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-21 | 2025-02-21 | [14 empty] | 2025-02-21 | 2025-02-21 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2025-02-21 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2589 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 295 | FPRW0165_IP | 06.Workflow | 01.IP - Intel Product | Workflow is required to trigger the approvers based on the business requirement for Journal entry | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-010-030_Workflow%20_RICEFW_Form.pptx?d=w2fd8b49300dd49cd802e977763c72471&csf=1&web=1&e=HnlX4g | 02.No | 01.Yes |  | 2024-04-26 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-03 | 2024-07-05 | 2024-05-10 | 100% | 2024-06-06 | 2024-05-13 | 2024-05-13 | 2024-06-21 | 100% | 2024-06-19 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-19 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-16 | 2024-08-16 | 2024-08-16 | vasamohan@deloitte.com | 2024-04-26 10:39 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRW0165_CFIN | 02.High | 1 | 1.05 | 0165 |  | R3 ITC1 | [6 empty] | 2024-06-06 | 2024-07-05 | 2024-06-06 |  | 2024-06-19 | 2024-06-21 | 2024-06-19 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-12-13 | 2024-12-13 | 2024-12-13 | [5 empty] | 2024-07-05 | 2024-08-16 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2823 | [10 empty] | 2024-08-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-16 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 295 | FPRW0165_IF | 06.Workflow | 02.IF - Intel Foundry | Workflow is required to trigger the approvers based on the business requirement for Journal entry | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-010-030_Workflow%20_RICEFW_Form.pptx?d=w2fd8b49300dd49cd802e977763c72471&csf=1&web=1&e=HnlX4g | 02.No | 01.Yes |  | 2024-04-26 | Shane Bethune | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-03 | 2024-07-05 | 2024-05-10 | 100% | 2024-06-06 | 2024-05-13 | 2024-05-13 | 2024-06-21 | 100% | 2024-06-19 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-19 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-16 | 2024-08-16 | 2024-08-16 | vasamohan@deloitte.com | 2024-04-26 09:20 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRW0165_CFIN | 02.High | 1 | 1.05 | 0165 |  | R3 ITC1 | [6 empty] | 2024-06-06 | 2024-07-05 | 2024-06-06 |  | 2024-06-19 | 2024-06-21 | 2024-06-19 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-12-13 | 2024-12-13 | 2024-12-13 | [5 empty] | 2024-07-05 | 2024-08-16 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2822 | [10 empty] | 2024-08-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-16 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 295 | FPRW0165_CFIN | 06.Workflow | 05.CFIN | Workflow is required to trigger the approvers based on the business requirement for Journal entry | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-010-030_Workflow%20_RICEFW_Form.pptx?d=w2fd8b49300dd49cd802e977763c72471&csf=1&web=1&e=HnlX4g | 02.No | 01.Yes |  | 2024-04-26 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-03 | 2024-07-05 | 2024-05-10 | 100% | 2024-06-06 | 2024-05-13 | 2024-05-13 | 2024-06-21 | 100% | 2024-06-19 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-06-24 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-19 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-16 | 2024-08-16 | 2024-08-16 | vasamohan@deloitte.com | 2024-04-26 10:39 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 2.1 | 0165 |  | R3 ITC1 | [6 empty] | 2024-06-06 | 2024-07-05 | 2024-06-06 |  | 2024-06-19 | 2024-06-21 | 2024-06-19 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-12-13 | 2024-12-13 | 2024-12-13 | [5 empty] | 2024-07-05 | 2024-08-16 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2821 | [10 empty] | 2024-08-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-16 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRR1514_IP | 01.Report | 01.IP - Intel Product | To generate reports out of the ITT documents that was created | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 0.85 | 1514 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3115 | [7 empty] | 4. Completed | 1. Approved no action | 12/10: FUT Approved. | 2025-12-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRR1514_IF | 01.Report | 02.IF - Intel Foundry | To generate reports out of the ITT documents that was created | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-22 | 2025-10-29 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRR1514_IP | 03.Medium | 0.2 | 0.17 | 1514 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-11 | 2025-12-11 | 2025-12-11 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3118 | [7 empty] | 4. Completed | 1. Approved no action | 12/10: FUT Approved. | 2025-12-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2669 | FPRR1240 | 01.Report | 02.IF - Intel Foundry | Custom report for Revenue Recognition by Stage for Product/Services Sale​ actual revenue vs planned revenue | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2669_FPR_DC-100-020-Custom%20Report%20for%20Revenue%20Recognition%20by%20Stage%20Product%20%26%20Services%20actual%20revenue%20vs%20planned%20revenue.pptx?d=wc1ae11b925ff4e26bfb09c467a17461c&csf=1&web=1&e=qydP3O |  |  |  | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-14 | 2025-09-12 | 2025-09-19 | 2025-10-16 | 100% | 2025-11-13 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-13 | 2025-09-26 | 2025-10-24 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-10 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-02-07 07:16 | cell-link@smartsheet.com | 2026-03-09 01:06 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 0.85 | 1240 |  | R3 ITC1 | [6 empty] | 2025-03-14 | 2025-03-21 | 2025-03-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-02-10 | 2026-03-04 | 2026-02-10 | [5 empty] | 2025-03-21 | 2025-10-24 |  |  | 2026-03-04 |  |  |  | 0 |  | 2044 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | Approved. | 2025-10-24 | N | 03. FPR |  |  |  |  | 12/09 - Watch item for 12/11. Do we need this report for ITC1 |  |  | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2805 | FPRR1211 | 01.Report | 01.IP - Intel Product | Report for searching on and viewing government contract timesheets for Intel Federal. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2805_FPR_DC-050-640B_Intel%20Federal%20Report%20for%20searching%20government%20contract%20timesheets.pptx?d=w506380961ee449eeaae2e3213b9ee60f&csf=1&web=1&e=lzJgbK | 02.No | 01.Yes |  | 2025-02-03 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-11-13 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-13 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 0.85 | 1211 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-04-18 | 2025-11-05 |  |  | 2025-12-05 |  | Federal |  | 0 |  | 1724 | [7 empty] | 1. On Track | 1. Approved no action | 01/16: FUT Approved. | 2025-11-05 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/15 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2804 | FPRR1210 | 01.Report | 01.IP - Intel Product | Report for searching on and viewing government contract timesheet changes for Intel Federal.​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2804_FPR_DC-050-640B_Intel%20Federal%20SAP%20Timekeeping%20WDC%20Timesheet%20Changes%20Report%20RICEFW_r1.pptx?d=w1450364c28fd4fe7b79639ceeede7165&csf=1&web=1&e=LawXiO | 02.No | 01.Yes |  | 2025-02-03 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-17 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 0.85 | 1210 |  | R3 ITC1 | [6 empty] | 2025-04-17 | 2025-04-18 | 2025-04-17 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | [5 empty] | 2025-04-18 | 2025-11-05 |  |  | 2026-02-04 |  | Federal |  | 0 |  | 1723 | [7 empty] | 4. Completed | 1. Approved no action | 02/09: FUT Approved | 2025-11-05 | N | 03. FPR |  |  |  |  | S22 Week 3 Target |  |  | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2491 | FPRR0907_IP | 01.Report | 02.IF - Intel Foundry | Workflow Status Report ( Order Request / Approval Request / Others ) | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA6AB22DC-71D1-48DC-89F0-ECDBF540F43C%7D&file=2491_FPR_DC-050-680-Workflow%20Status%20Report%20(Order%20Request%2C%20Approval%20Request%2C%20Others).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-08-01 | 100% | 2025-08-29 | 2025-06-02 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-26 | 2025-06-02 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-26 | [15 empty] | 2025-08-26 | 2025-08-26 | No |  | 2025-08-13 | 2025-10-01 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-10-01 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 0.85 | 0907 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | [12 empty] | 2025-08-26 | 2025-08-26 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-14 |  |  |  | 0 |  | 1776 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 10/06: Sent for approval, will follow-up for the same. | 2025-06-13 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2491 | FPRR0907_IF | 01.Report | 01.IP - Intel Product | Workflow Status Report ( Order Request / Approval Request / Others ) | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA6AB22DC-71D1-48DC-89F0-ECDBF540F43C%7D&file=2491_FPR_DC-050-680-Workflow%20Status%20Report%20(Order%20Request%2C%20Approval%20Request%2C%20Others).pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-08-01 | 100% | 2025-08-29 | 2025-06-02 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-26 | 2025-06-02 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-26 | [15 empty] | 2025-08-26 | 2025-08-26 | No |  | 2025-08-13 | 2025-10-01 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-10-01 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRR0907_IP | 03.Medium | 0.2 | 0.17 | 0907 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | [12 empty] | 2025-08-26 | 2025-08-26 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-11-14 |  |  |  | 0 |  | 1775 | [7 empty] | 1. On Track | 17. FUT In progress | 10/08: Call setup today to check on any discussion points. | 2025-06-13 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-26 | 2025-08-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1857 | FPRR0497 | 01.Report | 05.CFIN | CFR - Report to support multiple Treasury Funding requests from Multiple Intel teams | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8DD9574C-496A-4113-BF26-69C5F04292BB%7D&file=MR-070-0011_FPR_RICEFW%20Intake%20Form_v1.0_CFR%20Report.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-07-14 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-08-02 09:51 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-07 | 01.S4 |  |  | 1 | 0.85 | 0497 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-15 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2170 | [7 empty] | 1. On Track | 1. Approved no action | 11/11: Shira provided conditional sign off. | 2025-08-15 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1858 | FPRR0496 | 01.Report | 05.CFIN | TPR-Report to support multiple Treasury Payment Requests from Multiple Intel teams | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B80D46527-340D-4826-BB06-2DDFC38A27BB%7D&file=MR-070-0012_FPR_RICEFW%20Intake%20Form_v1.0_TPR%20Report.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-07-14 | 2025-07-18 | 2025-07-25 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-15 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-10-08 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-08-02 09:51 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-07 | 01.S4 |  |  | 1 | 0.85 | 0496 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-07-23 | 2025-07-25 | 2025-07-23 |  | 2025-07-23 | 2025-08-15 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2171 | [7 empty] | 1. On Track | 1. Approved no action | 11/17 - FUT approved. | 2025-08-15 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1560 | FPRR0461 | 01.Report | 01.IP - Intel Product | Inter-company Outage Pre-consolidate Report (ACDOCA) | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B20DCC031-D5DF-414F-8931-C9D3C4B1BFE1%7D&file=DC-110-080-IDM-0006_FPR_Intercompany_Outage%20report.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-07-19 | Shane Bethune | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-19 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-28 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2025-01-17 | 100% | 2024-12-19 | 2024-11-11 | 2024-12-20 | 2025-01-17 | 100% | 2024-12-19 | [15 empty] | 2024-12-19 | 2024-12-19 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-04-25 | Not Applicable | R3 Build & UT Sprint 13 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 0.85 | 0461 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-28 | 2024-08-28 | 2024-08-28 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-19 | 2025-01-17 | 2024-12-19 | 2024-12-19 | [12 empty] | 2024-12-19 | 2024-12-19 |  |  | 2025-04-25 | 2025-04-25 | 2025-04-25 | [5 empty] | 2024-08-23 | 2024-12-20 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 1730 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2024-12-19 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 765 | FPRR0380 | 01.Report | 05.CFIN | GL Interface – Reconciliation Report/Dashboard | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes |  | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-13 | 2024-08-05 | 2024-08-05 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-09 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-09 | [15 empty] | 2024-12-09 | 2024-12-09 | Yes |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-08-25 | Not Applicable | R3 Build & UT Sprint 17 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-18 05:17 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 1.7 | 0380 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-08-13 | 2024-08-13 | 2024-08-13 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-09 | 2025-02-14 | 2024-12-09 | 2024-12-09 | [12 empty] | 2024-12-09 | 2024-12-09 |  |  | 2025-08-25 | 2025-09-11 | 2025-08-25 | [5 empty] | 2024-08-02 | 2024-12-20 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2634 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2025-02-14 | 2024-12-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 713 | FPRR0327_IP | 01.Report | 01.IP - Intel Product | Report to display the requests/change IDs and status of the workflow approval and Error handling | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-070-0006_FPR_AMT_Report%20to%20display%20the%20requests_change%20IDs%20and%20status%20of%20the%20workflow%20approval%20and%20Error%20handling.pptx?d=w2565886e9f5d426a9552c366ed45ee4b&csf=1&web=1&e=syNXdO | 02.No | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-17 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-17 | [15 empty] | 2024-12-17 | 2024-12-17 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 1.7 | 0327 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2024-12-17 | [12 empty] | 2024-12-17 | 2024-12-17 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-07-26 | 2024-12-20 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2376 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-02-14 | 2024-12-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 713 | FPRR0327_IF | 01.Report | 02.IF - Intel Foundry | Report to display the requests/change IDs and status of the workflow approval and Error handling | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-070-0006_FPR_AMT_Report%20to%20display%20the%20requests_change%20IDs%20and%20status%20of%20the%20workflow%20approval%20and%20Error%20handling.pptx?d=w2565886e9f5d426a9552c366ed45ee4b&csf=1&web=1&e=syNXdO | 02.No | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-17 | 2024-09-16 | 2024-12-20 | 2025-02-14 | 100% | 2024-12-17 | [15 empty] | 2024-12-17 | 2024-12-17 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-02 | Not Applicable | R3 Build & UT Sprint 13 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRR0327_IP | 02.High | 0.4 | 0.34 | 0327 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-17 | 2025-02-14 | 2024-12-17 | 2024-12-17 | [12 empty] | 2024-12-17 | 2024-12-17 |  |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | [5 empty] | 2024-07-26 | 2024-12-20 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2375 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-02-14 | 2024-12-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 703 | FPRR0288_IP | 01.Report | 01.IP - Intel Product | Operational Report to display whether supporting documents are attached to JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/703_DC-010-030_Report%20for%20supporting%20document%20_RICEFW_Form.pptx?d=w1fb848faeac04c7cbbf1ffb48b04bb4e&csf=1&web=1&e=ULDAbl | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-21 | 2024-06-24 | 2024-06-24 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2024-09-02 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-26 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-11 | 2024-10-11 | 2024-10-11 | vasamohan@deloitte.com | 2024-05-31 11:06 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRR0288_CFIN | 02.High | 0.4 | 0.34 | 0288 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-10-11 |  |  | 2024-11-26 |  |  |  | 0 | 08. Not Applicable | 2578 | [7 empty] | 2. At Risk | 18. FUT Not Started |  | 2024-10-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 703 | FPRR0288_IF | 01.Report | 02.IF - Intel Foundry | Operational Report to display whether supporting documents are attached to JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/703_DC-010-030_Report%20for%20supporting%20document%20_RICEFW_Form.pptx?d=w1fb848faeac04c7cbbf1ffb48b04bb4e&csf=1&web=1&e=ULDAbl | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-21 | 2024-06-24 | 2024-06-24 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2024-09-02 | 2024-11-11 | 2024-10-11 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-26 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-11-11 | 2024-11-11 | 2024-11-11 | vasamohan@deloitte.com | 2024-06-03 08:09 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRR0288_CFIN | 02.High | 0.4 | 0.34 | 0288 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-10-11 |  |  | 2024-11-26 |  |  |  | 0 | 08. Not Applicable | 2577 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-11-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 703 | FPRR0288_CFIN | 01.Report | 05.CFIN | Operational Report to display whether supporting documents are attached to JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/703_DC-010-030_Report%20for%20supporting%20document%20_RICEFW_Form.pptx?d=w1fb848faeac04c7cbbf1ffb48b04bb4e&csf=1&web=1&e=ULDAbl | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-21 | 2024-06-24 | 2024-06-24 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2024-09-02 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-26 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-11 | 2024-10-11 | 2024-10-11 | vasamohan@deloitte.com | 2024-06-03 08:09 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 1.7 | 0288 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-10-11 |  |  | 2024-11-26 |  |  |  | 0 | 08. Not Applicable | 2576 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2024-10-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 45 | FPRR0027 | 01.Report | 05.CFIN | In House Cash – Loan Account balance Detailed report | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-03-26 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/MR-070-0001_FPR_RICEFW%20Intake%20Form_v1.01.pdf?csf=1&web=1&e=bYKqbx | 02.No | 01.Yes |  | 2024-03-26 | Shane Bethune | 01.Approved | 2024-03-26 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  | NA | NA | NA | NA | 2024-05-06 | 2024-05-31 | 2024-05-31 | 100% | 2024-05-09 | 2024-06-03 | 2024-06-03 | 2024-05-31 | 100% | 2024-06-02 | 2024-06-03 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | 2024-06-03 | 2024-08-16 | 2024-08-16 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-10-04 | 2024-10-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-18 | 2024-09-12 | 2024-10-18 | N | 100% | 2025-03-14 | Not Applicable | R3 Build & UT Sprint 11 | 2024-08-16 | 2024-08-16 | 2024-08-16 | jenoronha@deloitte.com | 2024-03-26 05:26 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 4 | 3.4 | 0027 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-05-09 | 2024-05-31 | 2024-05-09 |  | 2024-06-02 | 2024-06-03 | 2024-06-02 |  | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | [5 empty] | 2024-05-31 | 2024-08-16 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 1474 | [10 empty] | 2024-08-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-16 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FPRM003 | 12.Manual Conversion | 05.CFIN | Revenue Recognition Rules | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2024-10-18 | 2025-01-10 | 2024-11-15 | 100% | 2024-12-13 | 2024-10-28 | 2024-10-28 |  | 0% | 2024-10-28 |  |  |  | 0% |  | 2024-10-18 | 2025-01-10 |  | 0% | 2025-01-10 | [15 empty] | 2025-01-10 | 2025-01-10 | Yes | [6 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2024-12-16 | 2024-12-27 | 2024-11-15 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2025-01-10 | 2025-01-10 | 2025-01-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | M003 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-10 | 2024-12-13 |  |  | 2024-10-28 | [22 empty] | 2024-12-13 | 2024-12-27 | 2024-12-13 | [5 empty] | 2025-01-10 | 2025-01-10 |  |  | 2024-12-27 |  |  |  | 0 | 08. Not Applicable | 2270 | [10 empty] | 2025-01-10 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-10 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FPRM002 | 12.Manual Conversion | 05.CFIN | Revenue Contracts | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A | [6 empty] | NA | 2024-10-18 | 2025-01-10 | 2024-11-15 | 100% | 2024-12-13 | 2024-10-28 | 2024-10-28 |  | 0% | 2024-10-28 |  |  |  | 0% |  | 2024-10-18 | 2025-01-10 |  | 0% | 2025-01-10 | [15 empty] | 2025-01-10 | 2025-01-10 | Yes | [6 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2024-12-16 | 2024-12-27 | 2024-11-15 | N | 100% | 2024-12-13 | Not Applicable | R3 Build & UT Sprint 8 | 2025-01-10 | 2025-01-10 | 2025-01-10 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  |  | 0 | M002 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-10 | 2024-12-13 |  |  | 2024-10-28 | [22 empty] | 2024-12-13 | 2024-12-27 | 2024-12-13 | [5 empty] | 2025-01-10 | 2025-01-10 |  |  | 2024-12-27 |  |  |  | 0 | 08. Not Applicable | 2208 | [10 empty] | 2025-01-10 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-10 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 |  | FPRM001 | 12.Manual Conversion | 05.CFIN | Bank Master | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  |  |  | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | N/A |  | 02.No |  |  | ECC | CFIN | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-08-20 | 2025-01-27 | 2025-01-27 |  | 0% | 2025-01-27 |  |  |  | 0% |  | 2025-01-27 | 2025-02-21 |  | 0% | 2025-02-21 | [15 empty] | 2025-02-21 | 2025-02-21 | No | [6 empty] | 100% | 100% |  |  |  | 04. Completed | 04. Completed | 2025-02-03 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-02-26 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  |  | 0 | M001 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  | 2025-01-27 | [22 empty] | 2025-02-26 | 2025-02-26 | 2025-02-26 | [5 empty] | 2025-04-18 | 2025-02-21 | [6 empty] | 0 | 08. Not Applicable | 2209 | [10 empty] | 2025-02-21 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3200 | FPRI1725_IP | 02.Interface | 01.IP - Intel Product | Interface to be developed to transfer the files from Denodo to FS share path in excel format | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1444%20-%20Interface%20to%20transfer%20the%20Denodo%20workday%20details%20to%20FD%20share%20path%20in%20excel%20format%20to%20be%20processed%20by%20S4%20program%20.pptx?d=w9175933ce5be414683dac642ab73d00b&csf=1&web=1&e=eeV1pc | 02.No | 01.Yes |  | 2026-02-05 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 02.Intel | 03.Medium |  | 01.Yes | 12245 | Workday |  |  | Intel MW | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-20 |  |  | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-23 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-23 | 2026-03-05 | 2026-03-05 | 100% | 2026-03-09 |  | 2026-02-11 | 2026-02-11 | 100% | 2026-02-11 | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-09 |  | R3 Build & UT Sprint 23+ | 2026-03-05 | 2026-03-05 | 2026-03-05 | jenoronha@deloitte.com | 2026-02-05 04:48 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1725 | INT-CR1444 | R3 ITC1 | [6 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-22 | 2026-02-22 | 2026-03-09 | 2026-03-09 | 2026-02-22 | 2026-02-22 | 2026-02-22 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-03-09 | 2026-03-09 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-02-13 | 2026-02-20 | 2026-02-23 |  | 2026-03-04 |  |  |  | 0 |  | 3426 | [7 empty] | 4. Completed | 17. FUT In progress | 03/06: Build is completed and FUT in progress. Will be completed by today EOD. | 2026-03-05 | Y | 03. FPR |  |  |  | 02/24: Intel owned object (FS, Build, FUT). New object added in S22. Current status: FS is still in progress. Issue: FUT at Risk. Next steps: Expedite FS and Build completion. Help needed: N/A FUT ETA: 03/06 | Intel owned object |  | New Object | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-22 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3200 | FPRI1725_IF | 02.Interface | 02.IF - Intel Foundry | Interface to be developed to transfer the files from Denodo to FS share path in excel format | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1444%20-%20Interface%20to%20transfer%20the%20Denodo%20workday%20details%20to%20FD%20share%20path%20in%20excel%20format%20to%20be%20processed%20by%20S4%20program%20.pptx?d=w9175933ce5be414683dac642ab73d00b&csf=1&web=1&e=eeV1pc | 02.No | 01.Yes |  | 2026-02-05 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 02.Intel | 04.Low |  | 01.Yes | 12245 | Workday |  |  | Intel MW | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-20 |  |  | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-19 | 2026-02-23 | 2026-02-23 | 100% | 2026-02-23 | 2026-02-23 | 2026-03-05 | 2026-03-05 | 100% | 2026-03-09 |  | 2026-02-11 | 2026-02-11 | 100% | 2026-02-11 | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-09 |  | R3 Build & UT Sprint 23+ | 2026-03-05 | 2026-03-05 | 2026-03-05 | jenoronha@deloitte.com | 2026-02-05 04:48 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | FPRI1725_IP | 03.Medium | 0.3 | 0.435 | 1725 | INT-CR1444 | R3 ITC1 | [6 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-22 | 2026-02-22 | 2026-03-09 | 2026-03-09 | 2026-02-22 | 2026-02-22 | 2026-02-22 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-03-09 | 2026-03-09 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-02-13 | 2026-02-20 | 2026-02-23 |  | 2026-03-04 |  |  |  | 0 |  | 3425 | [7 empty] | 4. Completed | 17. FUT In progress | 03/06: Build is completed and FUT in progress. Will be completed by today EOD. | 2026-03-05 | Y | 03. FPR |  |  |  | 02/24: Intel owned object (FS, Build, FUT). New object added in S22. Current status: FS is still in progress. Issue: FUT at Risk. Next steps: Expedite FS and Build completion. Help needed: N/A FUT ETA: 03/06 | Intel owned object |  | New Object | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-22 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3186 | FPRI1704 | 02.Interface | 02.IF - Intel Foundry | Automated Tool MUP Excess Capacity calculation and associated PCOS/OCOS Split for the forecast. | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB99BA92D-2AFA-40C4-9B17-3B2AC44E4205%7D&file=INT-CR1319%20Excess%20capacity%20related%20RICEFWs.pptx&wdLOR=cAB147DDF-4ACC-47E9-B5E5-0D39441782DB&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-11-22 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | BODS | 2025-12-08 | 2026-01-07 | 2026-02-18 | 100% | 2026-02-19 |  |  | 2026-02-27 | 100% | 2026-03-09 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-19 | 2026-02-04 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-23 | 2026-02-27 | 2026-02-27 | 100% | 2026-02-27 | 2026-02-23 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-05 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-11-22 01:33 | cell-link@smartsheet.com | 2026-03-17 08:33 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1704 | INT-CR1319 | R3 ITC1 | [6 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-24 | 2026-03-09 | 2026-03-09 | 2026-02-21 | 2026-02-21 | 2026-02-21 |  | 2026-02-27 |  | 2026-02-27 |  | 2026-03-05 | 2026-03-05 | 2026-03-05 |  |  |  |  | 2026-03-09 | 2026-03-09 |  |  | 2026-03-05 | 2026-03-06 | 2026-03-05 | [5 empty] | 2026-01-07 | 2026-02-04 | 2026-02-27 |  | 2026-03-06 |  |  |  | 0 |  | 3387 | [7 empty] | 3. Off Track | 1. Approved no action | 03/04: Smarsheet is updated. | 2026-02-27 | Y | 03. FPR |  |  |  | 03/04: TUT+FUT is in progress. ETA for FUT completion is 03/20 Current status: TUT+FUT is in progress Issue: FUT delayed Next steps: Expedite FUT completion. Help needed: N/A FUT ETA: 03/20 | Smartsheet update pending | 2. Risk | At risk for S23 - ECA | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-21 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3150 | FPRI1670 | 02.Interface | 02.IF - Intel Foundry | Import Dot process/stage details from MDG into S4. ​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3150_IF_ECA%20view%20for%20Xesus%20Mars%20Volumes%20and%20non-burden%20%26%20Non-dep%20allocation%20to%20PCOS%20OCOS.pptx?d=we97bfb47774e43f28e13e2103762cb30&csf=1&web=1&e=xFeD87 | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 |  |  | 2026-02-20 | 100% | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-01-16 | 100% | 2026-01-26 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | [5 empty] | 2026-02-27 | 2026-02-27 |  |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2026-02-27 | 2026-02-27 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 01:53 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 1.45 | 1670 | INT-CR1337 | R3 ITC1 | [6 empty] | 2025-12-03 | 2025-12-03 | 2025-12-03 | 2026-01-12 | 2026-01-12 | 2026-02-21 | 2026-02-21 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 |  |  |  | 2026-02-27 | [6 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-02 | 2026-02-04 | 2026-02-02 | [5 empty] | 2025-12-03 | 2026-02-06 | 2026-02-27 |  | 2026-02-04 |  |  |  | 0 |  | 3350 | [7 empty] | 3. Off Track | 1. Approved no action | 02/02: IT approved it , Biz approval expected today. | 2026-02-27 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3150 | FPRI1669 | 02.Interface | 02.IF - Intel Foundry | Import Xeus/Mars volumes from ECA into S4.​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3150_IF_ECA%20view%20for%20Xesus%20Mars%20Volumes%20and%20non-burden%20%26%20Non-dep%20allocation%20to%20PCOS%20OCOS.pptx?d=we97bfb47774e43f28e13e2103762cb30&csf=1&web=1&e=xFeD87 | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | BODS | 2025-11-10 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-12 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-26 | [5 empty] | 2026-02-26 | 2026-02-26 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-27 | N | 100% | 2026-04-01 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-11-04 01:53 | cell-link@smartsheet.com | 2026-03-31 19:31 | 10 | 2025-11-05 | 01.S4 |  |  | 1 | 1.45 | 1669 | INT-CR1337 | R3 ITC1 | [6 empty] | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2026-03-09 | 2026-03-09 | 2026-02-26 | 2026-02-26 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-26 | 2026-02-26 | 2026-02-26 |  |  |  |  | 2026-02-26 | 2026-02-26 |  |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | [5 empty] | 2025-12-03 | 2026-02-06 | 2026-02-20 |  | 2026-03-06 |  |  |  | 0 |  | 3349 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 03/31: Walkthrough with Intel planned for today and approval expected post that. | 2026-02-20 | Y | 03. FPR |  |  |  | 03/24 : Awaiting approval. ETA for approval is 03/27 | Change in design from Custom table to File upload thru AL11. MW Build ETA is 3/20. FUT ETA is 3/27 | 2. Risk | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2902 | FPRI1504 | 02.Interface | 02.IF - Intel Foundry | Asset Delete from EMS to S4 through APIGEE | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IINT-Build-CR0233%20EMS%20Mulesoft-Asset%20Create.pptx?d=wc132efa32f5a4e93b4c371269d5e9cc2&csf=1&web=1&e=BpBl0E | 02.No | 01.Yes |  | 2025-03-22 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System |  |  | APIGEE | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-15 | 2025-08-22 | 2025-09-10 | 100% | 2025-09-08 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-10-13 | 2025-11-07 | 2025-09-10 | 100% | 2025-09-10 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-29 | 2025-10-10 | 2025-11-25 | 2025-11-25 | 100% | 2025-12-22 | 2025-09-29 | 2025-12-22 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-11-25 | 2025-11-25 | jenoronha@deloitte.com | 2025-06-12 02:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-24 | 01.S4 |  |  | 1 | 1.45 | 1504 |  | R3 ITC1 | [6 empty] | 2025-07-29 | 2025-08-15 | 2025-07-29 |  | 2025-09-08 | 2025-09-10 | 2025-09-08 |  | 2025-09-20 | 2025-09-26 | 2025-09-20 | 2025-09-20 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-10-08 | 2025-09-29 | 2025-09-29 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-09-29 | 2025-12-22 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-08-15 | 2025-09-26 | 2025-11-07 |  | 2025-12-05 |  |  |  | 0 |  | 3099 | [7 empty] | 1. On Track | 1. Approved no action | 12/03: FUT Approved. | 2025-11-25 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2902 | FPRI1503 | 02.Interface | 02.IF - Intel Foundry | Asset Display from EMS to S4 through APIGEE | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IINT-Build-CR0233%20EMS%20Mulesoft-Asset%20Create.pptx?d=wc132efa32f5a4e93b4c371269d5e9cc2&csf=1&web=1&e=BpBl0E | 02.No | 01.Yes |  | 2025-03-22 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System |  |  | APIGEE | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-31 | 2025-08-15 | 2025-08-22 | 2025-09-10 | 100% | 2025-09-08 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-10-13 | 2025-11-07 | 2025-09-10 | 100% | 2025-09-10 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-29 | 2025-10-10 | 2025-11-25 | 2025-11-25 | 100% | 2025-12-22 | 2025-09-29 | 2025-12-22 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-11-25 | 2025-11-25 | jenoronha@deloitte.com | 2025-06-12 02:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-24 | 01.S4 |  |  | 1 | 1.45 | 1503 |  | R3 ITC1 | [6 empty] | 2025-07-31 | 2025-08-15 | 2025-07-31 |  | 2025-09-08 | 2025-09-10 | 2025-09-08 |  | 2025-09-20 | 2025-09-26 | 2025-09-20 | 2025-09-20 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-10-08 | 2025-09-29 | 2025-09-29 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-09-29 | 2025-12-22 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-08-15 | 2025-09-26 | 2025-11-07 |  | 2025-12-05 |  |  |  | 0 |  | 3098 | [7 empty] | 1. On Track | 1. Approved no action | 12/03: FUT Approved. | 2025-11-25 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2902 | FPRI1502 | 02.Interface | 02.IF - Intel Foundry | Asset Change from EMS to S4 through APIGEE | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IINT-Build-CR0233%20EMS%20Mulesoft-Asset%20Create.pptx?d=wc132efa32f5a4e93b4c371269d5e9cc2&csf=1&web=1&e=BpBl0E | 02.No | 01.Yes |  | 2025-03-22 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System |  |  | APIGEE | 2025-07-21 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-29 | 2025-08-15 | 2025-08-22 | 2025-09-10 | 100% | 2025-09-08 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-08-29 | 2025-09-26 | 2025-09-22 | 100% | 2025-09-20 | 2025-10-13 | 2025-11-07 | 2025-09-10 | 100% | 2025-09-10 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-29 | 2025-10-10 | 2025-11-25 | 2025-11-25 | 100% | 2025-12-22 | 2025-09-29 | 2025-12-22 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-11-25 | 2025-11-25 | jenoronha@deloitte.com | 2025-06-12 02:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-24 | 01.S4 |  |  | 1 | 1.45 | 1502 |  | R3 ITC1 | [6 empty] | 2025-07-29 | 2025-08-15 | 2025-07-29 |  | 2025-09-08 | 2025-09-10 | 2025-09-08 |  | 2025-09-20 | 2025-09-26 | 2025-09-20 | 2025-09-20 |  | 2025-11-07 |  | 2025-09-10 |  | 2025-10-08 | 2025-09-29 | 2025-09-29 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-09-29 | 2025-12-22 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-08-15 | 2025-09-26 | 2025-11-07 |  | 2025-12-05 |  |  |  | 0 |  | 3097 | [7 empty] | 4. Completed | 1. Approved no action | 12/03: FUT Approved. | 2025-11-25 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-09-26 | 2025-09-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2976 | FPRI1463 | 02.Interface | 01.IP - Intel Product | Interface to upload payroll data from Workday to S/4 IP for legal entity 199 employees to support actual labor costing for government contracts | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/DRAFT%20Intel%20Federal%20Payroll%20Interface%20INT157%20RICEFW%20Intake%20Form.pptx?d=we06e6583918b4449a2bc5feda32a7d29&csf=1&web=1&e=LPSj49 | 01.Yes | 01.Yes |  | 2025-05-19 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 12245 | Workday |  |  | MULESOFT | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-20 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-20 | 2025-09-08 | 2025-09-26 | 2025-08-13 | 100% | 2025-08-13 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-17 | 2025-06-01 | 2025-11-14 | 2025-11-14 | 100% | 2025-12-05 | 2025-09-17 | 2025-12-05 |  |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-11-14 | 2025-11-14 | jenoronha@deloitte.com | 2025-05-17 02:08 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-03 | 01.S4 |  |  | 1 | 1.45 | 1463 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-08-20 | 2025-09-12 | 2025-08-20 | 2025-08-20 |  | 2025-09-26 |  | 2025-08-13 |  | 2025-09-17 | 2025-09-17 | 2025-09-17 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-09-17 | 2025-12-05 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-07-16 | 2025-09-12 | 2025-09-26 |  | 2025-11-05 |  | Federal |  | 0 |  | 3038 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/06: FUT review with Business in progress. | 2025-11-14 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-09-12 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 762 | FPRI1447 | 02.Interface | 02.IF - Intel Foundry | GL Interface –Create Inbound IDOCs to CFIN from IF system | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes |  | 2025-03-03 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | IF | CFIN | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-13 | 2025-07-14 | 2025-07-16 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No | 2025-08-13 | 2025-12-24 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-08-19 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | jenoronha@deloitte.com | 2025-05-15 02:44 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1447 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-19 | 2025-09-11 | 2025-08-19 | [5 empty] | 2025-06-11 | 2025-08-13 |  |  | 2025-09-11 |  |  |  | 0 |  | 3016 | [7 empty] | 4. Completed |  |  | 2025-08-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 762 | FPRI1446 | 02.Interface | 01.IP - Intel Product | GL Interface –Create Inbound IDOCs to CFIN from IP system | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes |  | 2025-03-03 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | IP | CFIN | NA | 2025-05-19 | 2025-06-11 | 2025-06-11 | 100% | 2025-06-13 | 2025-07-14 | 2025-07-16 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No | 2025-08-13 | 2025-12-24 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-08-19 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | jenoronha@deloitte.com | 2025-05-15 02:44 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1446 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-19 | 2025-09-11 | 2025-08-19 | [5 empty] | 2025-06-11 | 2025-08-13 |  |  | 2025-09-11 |  |  |  | 0 |  | 3017 | [7 empty] | 4. Completed |  |  | 2025-08-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2900 | FPRI1439 | 02.Interface | 02.IF - Intel Foundry | Receive planned production quantities per production version from ECA to S/4 for mixed costing | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2900_FPR_RICEFW%20Intake%20Form_Enhancement%20Cross%20Site%20transfer%20%20Mixed%20costing.pptx?d=wcb64a67c627e48e7b0d11e48c0936159&csf=1&web=1&e=8LEipN | 02.No | 01.Yes |  | 2025-04-29 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | APIGEE | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-15 | 2025-08-22 | 2026-02-20 | 100% | 2026-03-09 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-26 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-26 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-23 | [5 empty] | 2026-02-23 | 2026-02-23 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-05 | Not Applicable | R3 Build & UT Sprint 19 | 2026-02-20 | 2026-02-20 | 2026-02-20 | pgaroo@deloitte.com | 2025-04-29 03:20 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1.45 | 1439 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-17 |  | 2025-09-26 | 2025-10-03 | 2025-09-26 | 2025-09-26 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-23 | 2026-02-23 | 2026-02-23 |  |  |  |  | 2026-02-23 | 2026-02-23 |  |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | [5 empty] | 2025-07-16 | 2025-09-26 | 2026-02-20 |  | 2025-11-05 |  |  |  | 0 |  | 3001 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/04: Additional scenario also tested , awaiting approval by 11/4 | 2026-02-20 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2025-10-03 | 2025-09-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2924 | FPRI1338 | 02.Interface | 05.CFIN | Outbound Interface to view the Cleared Customer Invoices from CFIN System to WOM ( Web Order Management System) | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD245FCB1-3927-4E50-8873-515B43FCDE8C%7D&file=2924_FPR_RICEFW%20Intake%20Form_OR-140-140_WOM_Interface%20for%20Cleared%20Invoice.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0785 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-07-11 | 2025-07-25 | 2025-07-16 | 100% | 2025-07-16 | 2025-08-18 | 2025-09-12 | 2025-08-13 | 100% | 2025-08-04 | 2025-08-25 | 2025-10-10 | 2025-10-10 | 100% | 2025-10-01 | 2025-08-04 | 2025-10-01 | No |  | 2025-09-12 | 2025-09-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-12 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-04-01 02:36 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 1338 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 |  | 2025-07-25 |  | 2025-07-16 |  | 2025-09-12 | 2025-08-04 | 2025-08-04 |  | 2025-10-10 | 2025-10-01 | 2025-10-01 | 2025-08-04 | 2025-10-01 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-16 | 2025-07-18 | 2025-07-25 |  | 2025-09-12 |  |  |  | 0 |  | 2847 | [10 empty] | 2025-10-10 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2902 | FPRI1315 | 02.Interface | 02.IF - Intel Foundry | Asset Create from EMS to S4 through APIGEE | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IINT-Build-CR0233%20EMS%20Mulesoft-Asset%20Create.pptx?d=wc132efa32f5a4e93b4c371269d5e9cc2&csf=1&web=1&e=BpBl0E | 02.No | 01.Yes |  | 2025-03-22 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 4012 | Equipment Management System |  |  | APIGEE | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-07-07 | 2025-07-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-07-11 | 2025-07-25 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-15 | 2025-11-15 | 2025-11-15 | 100% | 2025-12-23 | 2025-07-23 | 2025-12-23 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-11-15 | 2025-11-15 | pgaroo@deloitte.com | 2025-03-19 10:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-03-24 | 01.S4 |  |  | 1 | 1.45 | 1315 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 |  | 2025-07-25 |  | 2025-07-11 |  | 2025-09-12 | 2025-07-21 | 2025-07-21 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-07-23 | 2025-12-23 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-05-16 | 2025-07-18 | 2025-07-25 |  | 2025-12-05 |  |  |  | 0 |  | 1629 | [7 empty] | 1. On Track | 1. Approved no action | 12/03: FUT Approved. | 2025-11-15 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 762 | FPRI1306 | 02.Interface | 05.CFIN | Interface for importing GL transactional data from SAP CFIN system into SAP IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes |  | 2025-03-03 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | CFIN | S/4 | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-07 | 2025-07-18 | 2025-06-06 | 100% | 2025-05-20 | 2025-07-07 | 2025-07-18 | 2025-06-06 | 100% | 2025-05-20 | [15 empty] | 2025-05-20 | 2025-05-20 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-03-02 23:04 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1306 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-05-20 | 2025-07-18 | 2025-05-20 | 2025-05-20 | [12 empty] | 2025-05-20 | 2025-05-20 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-04-18 | 2025-07-18 |  |  | 2025-07-16 |  |  |  | 0 |  | 2626 | [7 empty] | 1. On Track | 1. Approved no action |  | 2025-07-18 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 762 | FPRI1305 | 02.Interface | 05.CFIN | Interface for importing GL transactional data from SAP CFIN system into SAP IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes |  | 2025-03-03 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | CFIN | S/4 | NA | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-09 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-07-07 | 2025-07-18 | 2025-06-06 | 100% | 2025-05-20 | 2025-07-07 | 2025-07-18 | 2025-06-06 | 100% | 2025-05-20 | [15 empty] | 2025-05-20 | 2025-05-20 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-03-02 23:04 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1305 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-05-20 | 2025-07-18 | 2025-05-20 | 2025-05-20 | [12 empty] | 2025-05-20 | 2025-05-20 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-04-18 | 2025-07-18 |  |  | 2025-07-16 |  |  |  | 0 |  | 2625 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-07-18 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2358 | FPRI1288 | 02.Interface | 01.IP - Intel Product | Activity Inbound interface from ECA to S4 IP | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2358_FPR_RICEFW%20Intake%20Form_Interface%20to%20recieve%20activity%20%26%20Prodn%20quantity%20data%20from%20ECA%20to%20update%20in%20SAP%20S4.pptx?d=w8f7aeffe71b44d8abafeee9a79cdceb4&csf=1&web=1&e=VdDBDY |  |  | ECAFPRV884 | 2025-02-28 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA | S/4 | MuleSoft | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-16 | 2025-06-09 | 2025-06-13 | 2025-12-03 | 100% | 2025-11-27 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-11-17 | 2025-11-21 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-22 | [5 empty] | 2025-12-22 | 2025-12-22 | No | 2025-11-05 | 2025-09-05 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | pgaroo@deloitte.com | 2025-02-26 22:05 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1288 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-18 | 2025-04-16 |  | 2025-11-27 | 2025-12-03 | 2025-11-27 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 |  |  |  |  | 2025-12-22 | 2025-12-22 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 | [5 empty] | 2025-04-18 | 2025-07-18 | 2025-11-21 |  | 2026-02-04 |  |  |  | 0 |  | 2480 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/19: Product Costing team closely working with ECA team and will close the testing. | 2025-12-19 | Y | 03. FPR |  |  |  | 0107: E2E FUT in progress. ETA is 1/9 Current Status: ECA views build complete. E2E FUT in progress. ETA is 1/9 Issue: Next Steps: E2E FUT in progress. ETA is 1/9 Help needed: N/A | S22 Week2 Target | 5. Review Closed |  | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2358 | FPRI1287 | 02.Interface | 02.IF - Intel Foundry | Production quantity update in WAC custom table from ECA to S4 IF | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2358_FPR_RICEFW%20Intake%20Form_Interface%20to%20recieve%20activity%20%26%20Prodn%20quantity%20data%20from%20ECA%20to%20update%20in%20SAP%20S4.pptx?d=w8f7aeffe71b44d8abafeee9a79cdceb4&csf=1&web=1&e=VdDBDY |  |  | FPRE0549 ECAFPRV884 | 2025-02-28 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA | S/4 | MuleSoft | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-16 | 2025-06-09 | 2025-06-13 | 2025-12-03 | 100% | 2025-11-27 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-11-17 | 2025-11-21 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-23 | [5 empty] | 2025-12-23 | 2025-12-23 | No | 2025-11-05 | 2025-09-05 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | pgaroo@deloitte.com | 2025-02-25 07:38 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1287 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-18 | 2025-04-16 |  | 2025-11-27 | 2025-12-03 | 2025-11-27 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 |  |  |  |  | 2025-12-23 | 2025-12-23 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 | [5 empty] | 2025-04-18 | 2025-07-18 | 2025-11-21 |  | 2026-02-04 |  |  |  | 0 |  | 2482 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/19: Product Costing team closely working with ECA team and will close the testing. | 2025-12-19 | Y | 03. FPR |  |  |  | 0107: E2E FUT in progress. ETA is 1/9 Current Status: ECA views build complete. E2E FUT in progress. ETA is 1/9 Issue: Next Steps: E2E FUT in progress. ETA is 1/9 Help needed: N/A | S22 Week2 Target | 5. Review Closed |  | Defects | Complete | R3 Build & UT Sprint 21 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2313 | FPRI1286_IP | 02.Interface | 01.IP - Intel Product | Interface between SAP IP and IF boxes for Outbound IDOC flow_IP | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2836CC77-EDC6-4432-8B97-E7DE238EF951%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Interface%20between%20Mulesoft%20and%20SAP%20S4%20Hana.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | MULESOFT | S/4 | SFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-12 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-04-11 | 100% | 2025-04-18 | 2025-02-21 | 2025-03-07 | 2025-04-11 | 100% | 2025-04-18 | 2025-03-07 | 2025-03-21 | 2025-10-03 | 100% | 2025-10-03 | 2025-03-24 | 2025-04-18 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | jenoronha@deloitte.com | 2025-02-26 08:12 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 1286 |  | R3 ITC1 | [6 empty] | 2025-03-12 | 2025-03-21 | 2025-03-12 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-10-03 |  | 2025-10-03 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-03-21 | 2025-03-07 | 2025-03-21 |  | 2025-09-11 |  |  |  | 0 |  | 2107 | [7 empty] | 1. On Track | 1. Approved no action | 10/16: Approved, no further actions required | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-04-18 | 2025-04-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2313 | FPRI1286_IF | 02.Interface | 02.IF - Intel Foundry | Interface between SAP IP and IF boxes for Outbound IDOC flow_IF | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2836CC77-EDC6-4432-8B97-E7DE238EF951%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Interface%20between%20Mulesoft%20and%20SAP%20S4%20Hana.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low |  | 02.No | NA | NA | MULESOFT | S/4 | SFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-12 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-28 | 2025-03-07 | 2025-04-02 | 100% | 2025-04-18 | 2025-02-28 | 2025-03-07 | 2025-04-02 | 100% | 2025-04-18 | 2025-03-07 | 2025-03-21 | 2025-10-03 | 100% | 2025-10-03 | 2025-03-24 | 2025-04-18 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | jenoronha@deloitte.com | 2025-02-26 08:12 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRI1286_IP | 03.Medium | 0.3 | 0.435 | 1286 |  | R3 ITC1 | [6 empty] | 2025-03-12 | 2025-03-21 | 2025-03-12 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-10-03 |  | 2025-10-03 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2025-03-21 | 2025-03-07 | 2025-03-21 |  | 2025-09-11 |  |  |  | 0 |  | 2106 | [7 empty] | 1. On Track | 1. Approved no action | 10/16: Approved, no further actions required | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-04-18 | 2025-04-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2358 | FPRI1273 | 02.Interface | 02.IF - Intel Foundry | Activity Quantity Inbound interface from ECA to S4 IF | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2358_FPR_RICEFW%20Intake%20Form_Interface%20to%20recieve%20activity%20%26%20Prodn%20quantity%20data%20from%20ECA%20to%20update%20in%20SAP%20S4.pptx?d=w8f7aeffe71b44d8abafeee9a79cdceb4&csf=1&web=1&e=VdDBDY |  |  | ECAFPRV884 | 2025-02-28 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA | S/4 | MuleSoft | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-16 | 2025-06-09 | 2025-06-13 | 2025-12-03 | 100% | 2025-11-27 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-23 | 100% | 2025-05-24 | 2025-11-17 | 2025-11-21 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-22 | [5 empty] | 2025-12-22 | 2025-12-22 | No | 2025-11-05 | 2025-09-05 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | pgaroo@deloitte.com | 2025-02-25 07:38 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-04 | 01.S4 |  |  | 1 | 1.45 | 1273 |  | R3 ITC1 | [6 empty] | 2025-04-16 | 2025-04-18 | 2025-04-16 |  | 2025-11-27 | 2025-12-03 | 2025-11-27 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 |  |  |  |  | 2025-12-22 | 2025-12-22 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 | [5 empty] | 2025-04-18 | 2025-07-18 | 2025-11-21 |  | 2026-02-04 |  |  |  | 0 |  | 2481 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/20: FUT sent for Intel Review. | 2025-12-19 | Y | 03. FPR |  |  |  | 0107: E2E FUT in progress. ETA is 1/9 Current Status: ECA views build complete. E2E FUT in progress. ETA is 1/9 Issue: Next Steps: E2E FUT in progress. ETA is 1/9 Help needed: N/A | S22 Week2 Target | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1896 | FPRI1241 | 02.Interface | 01.IP - Intel Product | Disti Rebate percentage of gross for Unissued Returns and Intransit Deferral | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B43271539-D45B-4810-8B59-63040DD25EA6%7D&file=Rev%20DC-100-020%20Disti%20Rebate%20-%201896.pptx&action=edit&mobileredirect=true |  |  | FPRE0475; FPRE0477 | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | ECA | S/4 | BODS | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-07-14 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-30 | 2025-08-04 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-08-04 | 2025-08-15 | 2025-05-15 | 100% | 2025-08-04 | 2025-08-08 | 2025-08-22 | 2025-06-06 | 100% | 2025-06-06 | 2025-09-01 | 2025-09-26 | 2025-06-11 | 100% | 2025-06-11 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-26 | 2025-09-26 | 2025-09-26 | pgaroo@deloitte.com | 2025-02-07 07:16 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1241 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-05-30 | 2025-07-18 |  |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-08-22 |  | 2025-06-06 |  | 2025-09-26 |  | 2025-06-11 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-03-21 | 2025-08-15 | 2025-08-22 |  | 2025-07-16 |  |  |  | 0 |  | 1701 | [10 empty] | 2025-09-26 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2842 | FPRI1238 | 02.Interface | 01.IP - Intel Product | Pull Foundry WBS from HAT and create in LE 199 in IP S/4 for Foundry Employees moved to LE 199. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2842_%20FPR_IF%20WBS%20to%20IP%20WBS%20Creation%20-%20Intel%20Federal_%20RICEFW%20%20Intake%20Form.pptx?d=w2c2bd653e3c04e55894a963839f90118&csf=1&web=1&e=yCA4gJ |  |  |  | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | Head Count Assignment Tool | Head Count Assignment Tool | S/4 | BODS | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-09 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-30 | 2025-07-07 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-07-07 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-07-11 | 2025-07-25 | 2025-06-06 | 100% | 2025-06-06 | 2025-08-18 | 2025-09-12 | 2025-06-06 | 100% | 2025-06-06 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-07-28 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2025-02-07 07:16 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-02-12 | 01.S4 |  |  | 1 | 1.45 | 1238 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-05-30 | 2025-06-13 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-25 |  | 2025-06-06 |  | 2025-09-12 |  | 2025-06-06 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2025-07-28 | 2025-08-13 | 2025-07-28 | [5 empty] | 2025-03-21 | 2025-07-18 | 2025-07-25 |  | 2025-08-13 |  | Federal |  | 0 |  | 1674 | [10 empty] | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2630 | FPRI1105 | 02.Interface | 05.CFIN | Interface for automatic creation of B2B customer related payment advice | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2630_FPR_RICEFW%20Intake%20Form_OR-140-140_Interface%20for%20automatic%20creation%20of%20B2B%20cust%20payment%20advice%20v1.0.pptx?d=w142d243d8e344fe6a647d88e0c32a4a4&csf=1&web=1&e=4doebd |  |  |  | 2025-01-23 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No |  | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 12842 | OpenText |  |  | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-04-14 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-23 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-24 | 2025-05-05 | 2025-05-16 | 2025-06-11 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-23 | 2025-06-06 | 100% | 2025-06-06 | 2025-06-02 | 2025-06-27 | 2025-06-11 | 100% | 2025-06-17 |  | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-06-17 | 2025-06-17 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-27 | 2025-06-27 | 2025-06-27 | jonsanders@deloitte.com | 2025-01-16 12:46 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1.45 | 1105 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-05-23 | 2025-05-30 | 2025-05-23 |  | 2025-05-24 | 2025-06-11 | 2025-05-24 | 2025-05-24 |  | 2025-06-06 |  | 2025-06-06 |  | 2025-06-27 | 2025-06-17 | 2025-06-17 |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-06-17 | 2025-06-17 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  |  |  |  | B2B - OpenText | 2025-04-18 | 2025-08-29 | 2025-08-15 | MW | 2025-10-17 |  |  |  | 0 |  | 1949 | [7 empty] | 1. On Track | 5. Object to be Cancelled | 08/18 Part of Sprint 16, FUT in progress | 2025-06-27 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-06-11 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2425 | FPRI0981_IP | 02.Interface | 01.IP - Intel Product | Interface of SAP PPM module to SPEED | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2424_FPR_DC-050-300_PPM%20Interface%20with%20Atlas.pptx?d=wb7e49791c77b4d94899cd3c40f530986&csf=1&web=1&e=VU1tde | 02.No | 01.Yes | FPRI0942_IP, FPRE0315_IP | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | SPEED | ECA | S/4 | BODS | 2025-01-27 | 2025-02-24 | 2025-02-21 | 100% | 2025-08-29 | 2025-06-06 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-04-04 | 100% | 2025-04-18 | 2025-07-04 | 2025-07-18 | 2025-04-04 | 100% | 2025-04-18 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-05-09 | 100% | 2025-08-04 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jenoronha@deloitte.com | 2024-12-13 02:28 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0981 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 | 2025-07-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2025-09-05 | 2025-09-10 | 2025-09-05 | [5 empty] | 2025-02-24 | 2025-07-18 | 2025-07-18 |  | 2025-08-29 |  |  |  | 0 |  | 1450 | [10 empty] | 2025-08-15 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-18 | 2025-04-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2425 | FPRI0981_IF | 02.Interface | 02.IF - Intel Foundry | Interface of SAP PPM module to SPEED | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2424_FPR_DC-050-300_PPM%20Interface%20with%20Atlas.pptx?d=wb7e49791c77b4d94899cd3c40f530986&csf=1&web=1&e=VU1tde | 02.No | 01.Yes | FPRI0942_IF, FPRE0315_IF | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low |  | 02.No | NA | SPEED | ECA | S/4 | BODS | 2025-01-27 | 2025-02-24 | 2025-02-21 | 100% | 2025-08-29 | 2025-06-06 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-07-04 | 2025-07-18 | 2025-04-02 | 100% | 2025-04-18 | 2025-07-04 | 2025-07-18 | 2025-04-02 | 100% | 2025-04-18 | 2025-06-16 | 2025-07-18 | 2025-05-16 | 100% | 2025-05-16 | 2025-07-21 | 2025-08-15 | 2025-05-09 | 100% | 2025-08-04 | [5 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-08 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-05 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jenoronha@deloitte.com | 2024-12-13 02:28 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRI0981_IP | 03.Medium | 0.3 | 0.435 | 0981 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 | 2025-07-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-18 |  | 2025-05-16 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  |  |  |  | 2025-08-04 | 2025-08-04 |  |  | 2025-09-05 | 2025-09-10 | 2025-09-05 | [5 empty] | 2025-02-24 | 2025-07-18 | 2025-07-18 |  | 2025-08-29 |  |  |  | 0 |  | 1449 | [10 empty] | 2025-08-15 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-18 | 2025-04-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2174 | FPRI0913_IP | 02.Interface | 01.IP - Intel Product | Export the Planning data from the SAC table to PPM standard tables using the AL11 folders and ABAP custom program. | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2174_FPR_Export%20the%20project%20plan%20data%20from%20SAC%20into%20PPM%20tables%20using%20AL11%20(1).pptx?d=w5890f8f3d70943b1b76795286aae914b&csf=1&web=1&e=eehaWX | 02.No | 01.Yes |  | 2024-12-11 | Angela Wolf | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No | NA | NA | SAC | S/4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-19 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-31 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2.9 | 0913 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 |  | 2025-07-18 |  |  |  | 0 |  | 2755 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Call scheduled with INTEL today for approval. | 2025-06-13 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2174 | FPRI0913_IF | 02.Interface | 02.IF - Intel Foundry | Export the Planning data from the SAC table to PPM standard tables using the AL11 folders and ABAP custom program. | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2174_FPR_Export%20the%20project%20plan%20data%20from%20SAC%20into%20PPM%20tables%20using%20AL11%20(1).pptx?d=w5890f8f3d70943b1b76795286aae914b&csf=1&web=1&e=eehaWX | 02.No | 01.Yes |  | 2024-12-11 | Angela Wolf | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | SAC | S/4 | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-08-13 | 100% | 2025-08-09 | 2025-05-02 | 2025-05-16 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-19 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-31 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRI0913_IP | 02.High | 0.6 | 0.87 | 0913 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 |  | 2025-07-18 |  |  |  | 0 |  | 2754 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Call scheduled with INTEL today for approval. | 2025-06-13 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2299 | FPRI0909_IP | 02.Interface | 01.IP - Intel Product | Interface for importing the Headcount details by Person# and WBS element combination from HAT to S4 for burden allocation. ​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2299_FPR_DC-050-680-Enhancement%20for%20Headcount%20allocation%20to%20Opex%20WBS%20elements.pptx?d=wdb06376e98464502bf93c356f7436de6&csf=1&web=1&e=6d2mwq | 02.No | 01.Yes | FPRE0891_IP, Interface b/w S/4->ECA->HAT and vice versa | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | Head Count Assignment Tool | ECA | S/4 | BODS | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-07-04 | 100% | 2025-08-25 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-04-21 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-10 | [5 empty] | 2025-09-10 | 2025-09-10 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0909 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-09-12 | 2025-09-10 | 2025-09-10 |  |  |  |  | 2025-09-10 | 2025-09-10 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 |  | 2026-01-23 |  |  |  | 0 |  | 2598 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2299 | FPRI0909_IF | 02.Interface | 02.IF - Intel Foundry | Interface for importing the Headcount details by Person# and WBS element combination from HAT to S4 for burden allocation. ​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2299_FPR_DC-050-680-Enhancement%20for%20Headcount%20allocation%20to%20Opex%20WBS%20elements.pptx?d=wdb06376e98464502bf93c356f7436de6&csf=1&web=1&e=6d2mwq | 02.No | 01.Yes | FPRE0891_IF, Interface b/w S/4->ECA->HAT and vice versa | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low |  | 02.No | NA | Head Count Assignment Tool | ECA | S/4 | BODS | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-07-04 | 100% | 2025-08-25 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-05-09 | 2025-05-16 | 2025-05-30 | 100% | 2025-05-24 | 2025-04-21 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-11 | 2025-08-18 | 2025-09-12 | 2025-09-10 | 100% | 2025-09-10 | [5 empty] | 2025-09-10 | 2025-09-10 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRI0909_IP | 03.Medium | 0.3 | 0.435 | 0909 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-05-24 | 2025-05-30 | 2025-05-24 | 2025-05-24 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-09-12 | 2025-09-10 | 2025-09-10 |  |  |  |  | 2025-09-10 | 2025-09-10 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 |  | 2026-01-23 |  |  |  | 0 |  | 2597 | [10 empty] | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-05-30 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2295 | FPRI0895 | 02.Interface | 02.IF - Intel Foundry | Import Tool Sharing Forecasted Data from FCS to S4 & derive FTQ data by Capex WBS L2 & Mfr. Process Node CC | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx?d=w8ca1e6ad7aa64be6bbfa0439483a2785&csf=1&web=1&e=HrQiTJ | 02.No | 01.Yes |  | 2024-12-11 | Angela Wolf | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 15799 | MOR/FCS/SCS | FCS | S/4 | BODS | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-04 | 2025-04-11 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-09 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-06-09 | 2025-06-16 | 2025-06-16 | 100% | 2025-06-16 | 2025-08-04 | 2025-08-04 | No | 2025-09-10 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-07 | 2025-12-03 | N | 100% | 2025-12-04 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-06-16 | 2025-06-16 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2.9 | 0895 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-03-21 | 2025-04-11 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-08-04 | 2025-08-04 |  |  | 2025-12-04 | 2025-12-07 | 2025-12-04 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 |  | 2025-12-07 |  |  |  | 0 |  | 2594 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/04: Team will do follow up today for approval | 2025-06-16 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2296 | FPRI0894 | 02.Interface | 02.IF - Intel Foundry | Planned Volume from IP-BY will be utilized as a KP26 quantity to split 'Overhead Costs' within IF at a stage level | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-11 | Angela Wolf | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply / Demand Planning | 01.Yes | 25596; 38908; 36453 | JDA/Blue Yonder ESP/OP (ALTR); Module Planning for Supply Chain on Blue Yonder; Tactical Planning for Supply Chain on Blue Yonder | ICS | S/4 | BODS | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-04-11 | 2025-04-04 | 2025-04-11 | 2025-07-04 | 100% | 2025-07-21 | 2025-05-09 | 2025-05-16 | 2025-06-06 | 100% | 2025-05-20 | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-05-20 | 2025-04-21 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-11 | 2025-05-19 | 2025-06-13 | 2025-07-16 | 100% | 2025-07-21 |  | 2025-07-13 | 2025-07-13 | 100% | 2025-07-13 | 2025-07-21 | 2025-07-21 | No | 2025-08-13 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-07 | 2025-12-03 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2025-06-13 | 2025-07-13 | 2025-07-13 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2.9 | 0894 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-20 | 2025-06-06 | 2025-05-20 | 2025-05-20 |  | 2025-07-11 |  | 2025-07-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-13 | 2025-07-13 | 2025-07-13 | 2025-07-21 | 2025-07-21 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-05-16 |  | 2025-12-07 |  |  |  | 0 |  | 2595 | [7 empty] | 1. On Track | 1. Approved no action | 12/22: FUT Approved. | 2025-07-13 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-06-13 | 2025-05-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2268 | FPRI0869 | 02.Interface | 05.CFIN | Interface for automatic creation of WOM related payment advice | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2268_FPR_RICEFW%20Intake%20Form_OR-140-140_Interface%20for%20automatic%20creation%20of%20WOM%20payment%20advice%20v1.0.pptx?d=wefdeded92ed140de93079b59d7445fa3&csf=1&web=1&e=gY9ISz | 02.No | 01.Yes | FPRE0786 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-11-18 | 2024-12-20 | 2024-12-13 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-03-21 | 100% | 2025-03-05 | 2025-05-09 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-28 | 2025-06-12 | 2025-06-12 | 100% | 2025-06-12 | 2025-08-04 | 2025-08-04 | Yes | 2025-06-11 | 2025-07-16 | 2025-07-16 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-06-12 | 2025-06-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-08 | 01.S4 |  |  | 1 | 1.45 | 0869 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-05 | 2025-04-11 | 2025-03-05 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-08-04 | 2025-08-04 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2024-12-20 | 2025-05-16 | 2025-04-18 | S4 | 2025-08-22 |  |  |  | 0 |  | 1512 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24: Clara need to connect with Intel for Clarification on append SY to the 18 character Payment Advice. | 2025-06-12 | N | 03. FPR |  |  |  | Awaiting Approval 1211. ETA 1121 | 1119: ETA 1125 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2273 | FPRI0867 | 02.Interface | 05.CFIN | Outbound Interface to view the open & Cleared Customer Invoices from CFIN System to WOM ( Web Order Management System) | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2273_FPR_RICEFW%20Intake%20Form_OR-140-140_WOM_Interface%20for%20Open%20%26%20Cleared%20Invoice.pptx?d=wcfb1576fb24d408c92886e7963bc3411&csf=1&web=1&e=7Ij3TW | 02.No | 01.Yes | FPRE0785 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-03-21 | 100% | 2025-03-11 | 2025-05-02 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-04-18 | 2025-05-19 | 2025-06-13 | 2025-04-18 | 100% | 2025-08-04 | 2025-05-26 | 2025-07-04 | 2025-07-04 | 100% | 2025-07-04 | 2025-08-04 | 2025-08-04 | No | 2025-06-11 | 2025-08-13 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-07-04 | 2025-07-04 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-08 | 01.S4 |  |  | 1 | 1.45 | 0867 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-03-11 | 2025-04-11 | 2025-03-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-09 | 2025-09-09 | 2025-09-09 | [5 empty] | 2025-01-10 | 2025-05-16 | 2025-05-16 | S4 | 2025-09-05 |  |  |  | 0 |  | 2565 | [9 empty] | 09/08- Awaiting FUT sign-off. Will be closed by mid of the week. Calls scheduled with Business and WOM team. | 2025-07-04 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2274 | FPRI0866 | 02.Interface | 05.CFIN | Interface to Obtains the payer associated to the sold to from CFIN System to WOM ( Web Order Management System) | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B11B241B3-463C-4B52-AC94-361B98842EB7%7D&file=2274_FPR_RICEFW%20Intake%20Form_OR-140-140_WOM_Interface%20for%20Payer%20Details.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0785 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2024-12-20 | 2025-01-24 | 2025-01-31 | 2025-03-21 | 100% | 2025-02-28 | 2025-02-21 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-21 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-07 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-18 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-08-04 | 2025-03-31 | 2025-05-16 | 2025-05-16 | 100% | 2025-05-16 | 2025-08-04 | 2025-08-04 | Yes | 2025-06-11 | 2025-07-16 | 2025-07-16 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-08 | 01.S4 |  |  | 1 | 1.45 | 0866 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2025-01-10 | 2024-12-20 |  | 2025-02-28 | 2025-03-21 | 2025-02-28 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-10 | 2025-03-07 | 2025-03-21 | S4 | 2025-08-15 |  |  |  | 0 |  | 2566 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2276 | FPRI0865 | 02.Interface | 05.CFIN | Interface to transfer the Uploaded WCP Grant Amount from CFIN to WOM and Defer the payment by update of baseline date for the selected Invoice in CFIN system. | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2276_FPR_RICEFW%20Intake%20Form_OR-140-140_WOM_Interface%20for%20Uploaded%20WCP%20Grant%20Amount%20%26%20Defer%20of%20Baseline%20Date.pptx?d=w992ee0eac7204b269105e1f6a2aa7e3f&csf=1&web=1&e=XJHwyN | 02.No | 01.Yes | FPRE0785 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | S/4 | WOM | MULESOFT | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-02-04 | 2025-06-06 | 2025-06-13 | 2025-03-21 | 100% | 2025-03-11 | 2025-05-02 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-02 | 2025-07-18 | 2025-04-23 | 100% | 2025-08-04 | 2025-06-16 | 2025-07-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-21 | 2025-08-15 | 2025-04-25 | 100% | 2025-08-04 | 2025-06-23 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-02 | 2025-08-04 | 2025-09-02 | Yes | 2025-06-11 | 2025-09-05 | 2025-10-01 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-10-01 | N | 100% | 2025-10-15 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-08 | 01.S4 |  |  | 1 | 1.45 | 0865 |  | R3 ITC1 | [6 empty] | 2025-02-04 | 2025-02-04 | 2025-02-04 |  | 2025-03-11 | 2025-06-13 | 2025-03-11 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 |  | 2025-04-18 |  | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-09-12 | 2025-09-02 | 2025-09-02 | 2025-08-04 | 2025-09-02 |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | [5 empty] | 2025-01-24 | 2025-07-18 | 2025-07-18 | S4 | 2025-10-01 |  |  |  | 0 |  | 2441 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: Conditionally Signed off received. FUT Approved. | 2025-09-12 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2313 | FPRI0864_IP | 02.Interface | 01.IP - Intel Product | Interface between SAP IP and IF boxes for Inbound IDOC flow_IP | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2836CC77-EDC6-4432-8B97-E7DE238EF951%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Interface%20between%20Mulesoft%20and%20SAP%20S4%20Hana.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | MULESOFT | S/4 | SFT | 2024-11-18 | 2024-12-20 | 2024-12-13 | 100% | 2025-01-10 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-03-24 | 100% | 2025-04-10 | 2025-02-21 | 2025-03-07 | 2025-03-24 | 100% | 2025-04-10 | 2025-03-07 | 2025-03-21 | 2025-10-03 | 100% | 2025-10-03 | 2025-03-24 | 2025-04-18 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0864 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-10-03 |  | 2025-10-03 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2024-12-20 | 2025-03-07 | 2025-03-21 |  | 2025-08-15 |  |  |  | 0 |  | 2109 | [7 empty] | 1. On Track | 1. Approved no action | 10/16: conditionally approved by Intel | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-04-10 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2313 | FPRI0864_IF | 02.Interface | 02.IF - Intel Foundry | Interface between SAP IP and IF boxes for Inbound IDOC flow_IF | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2836CC77-EDC6-4432-8B97-E7DE238EF951%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Interface%20between%20Mulesoft%20and%20SAP%20S4%20Hana.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low |  | 02.No | NA | NA | MULESOFT | S/4 | SFT | 2024-11-18 | 2024-12-20 | 2024-12-13 | 100% | 2025-01-10 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-28 | 2025-03-07 | 2025-03-24 | 100% | 2025-04-10 | 2025-02-28 | 2025-03-07 | 2025-03-24 | 100% | 2025-04-10 | 2025-03-07 | 2025-03-21 | 2025-10-03 | 100% | 2025-10-03 | 2025-03-24 | 2025-04-18 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-09-05 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-19 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRI0864_IP | 03.Medium | 0.3 | 0.435 | 0864 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-10-03 |  | 2025-10-03 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | [5 empty] | 2024-12-20 | 2025-03-07 | 2025-03-21 |  | 2025-08-15 |  |  |  | 0 |  | 2108 | [7 empty] | 1. On Track | 1. Approved no action | 10/16: conditionally approved by Intel | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-04-10 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2412 | FPRI0863_IP | 02.Interface | 01.IP - Intel Product | Interface between SAP & ECA to provide information for auto certification in Blackline | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | ECA | BLACKLINE | APIGEE;DENODO | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2026-11-28 | 2026-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-04-21 | 2025-06-30 | 2025-09-10 | 100% | 2025-09-10 | 2025-05-19 | 2025-07-31 | 2025-09-30 | 100% | 2025-09-09 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-05 | 2025-09-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-24 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-12 | 03.Mulesoft | FPRI0863_CFIN | 03.Medium | 0.3 | 0.435 | 0863 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2026-11-28 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-09 | 2025-09-09 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | S4 | 2026-01-23 |  |  |  | 0 |  | 1787 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 09/26: FUT Approved. | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2412 | FPRI0863_IF | 02.Interface | 02.IF - Intel Foundry | Interface between SAP & ECA to provide information for auto certification in Blackline | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 04.Low | Corporate Functions | 01.Yes | 23557 | Task - Blackline | ECA | BLACKLINE | APIGEE;DENODO | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2026-11-28 | 2026-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-04-21 | 2025-06-30 | 2025-09-10 | 100% | 2025-09-10 | 2025-05-19 | 2025-07-31 | 2025-09-30 | 100% | 2025-09-09 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-05 | 2025-09-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-24 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-12 | 03.Mulesoft | FPRI0863_CFIN | 03.Medium | 0.3 | 0.435 | 0863 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2026-11-28 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-09 | 2025-09-09 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2025-02-21 | 2025-05-16 | 2025-05-16 | S4 | 2026-01-23 |  |  |  | 0 |  | 1786 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 09/26: FUT Approved. | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2412 | FPRI0863_CFIN | 02.Interface | 05.CFIN | Interface between SAP & ECA to provide information for auto certification in Blackline | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-12 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | ECA | BLACKLINE | APIGEE;DENODO | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-05-11 | 2025-05-16 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-06-06 | 2025-06-30 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-11 | 2025-07-31 | 2025-08-04 | 100% | 2025-08-13 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-05 | 2025-09-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-24 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-02-11 07:33 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-02-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0863 |  | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-21 | 2025-03-03 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2025-03-21 | 2025-11-28 | 2025-06-30 |  | 2025-09-11 |  |  |  | 0 |  | 1788 | [7 empty] | 1. On Track | 14. B-App Under Test | 09/26: FUT Approved. | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2415 | FPRI0862 | 02.Interface | 05.CFIN | Interface to transfer the details of selected invoice from WOM to CFIN ( Inbound Interface to CFIN sys ) for which the Baseline Date needs to be deferred. | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE63BA87E-64CA-472C-BA1F-D972902EA679%7D&file=2415_FPR_RICEFW%20Intake%20Form_OR-140-140_WOM_Interface%20from%20WOM%20to%20CFIN%20for%20Defering%20of%20the%20Baseline%20date%20in%20CFIN%20sys.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0785 | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Supply Chain | 01.Yes | 31717 | SAP Commerce Cloud | WOM | S/4 | MULESOFT | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-30 | 2025-04-04 | 2025-04-11 | 2025-03-21 | 100% | 2025-03-07 | 2025-05-02 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-23 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-04-21 | 2025-05-16 | 2025-04-18 | 100% | 2025-08-04 | 2025-04-28 | 2025-06-12 | 2025-06-12 | 100% | 2025-06-12 | 2025-08-04 | 2025-08-04 | Yes | 2025-06-11 | 2025-07-16 | 2025-07-16 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-23 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-06-12 | 2025-06-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-11-12 | 01.S4 |  |  | 1 | 1.45 | 0862 |  | R3 ITC1 | [6 empty] | 2025-01-30 | 2025-01-30 | 2025-01-30 |  | 2025-03-07 | 2025-04-11 | 2025-03-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-04-18 |  | 2025-04-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | [5 empty] | 2025-01-24 | 2025-05-16 | 2025-04-18 | S4 | 2025-10-31 |  |  |  | 0 |  | 1792 | [10 empty] | 2025-06-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0778_IP | 02.Interface | 01.IP - Intel Product | Continue to auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0777 | 2025-01-13 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-28 | 2025-05-12 | 2025-05-16 | 2025-07-16 | 100% | 2025-08-08 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-06 | 2025-06-20 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-15 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2024-10-21 | 2025-09-14 | 2025-09-14 | 100% | 2025-09-14 | 2025-08-20 | 2025-09-14 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-14 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-10-22 10:04 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-15 | 01.S4 | FPRI0778_CFIN | 02.High | 0.6 | 0.87 | 0778 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-10-10 | 2025-08-20 | 2025-08-20 |  | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-08-20 | 2025-09-14 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-02-21 | 2025-08-15 | 2025-08-15 | MW | 2025-10-10 |  |  |  | 0 | 08. Not Applicable | 1623 | [9 empty] | 10/10: Conditionally Approved. FUT Approved. | 2025-10-10 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0778_IF | 02.Interface | 02.IF - Intel Foundry | Continue to auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0777 | 2025-01-13 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-28 | 2025-05-12 | 2025-05-16 | 2025-07-16 | 100% | 2025-08-08 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-06 | 2025-06-20 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-15 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2024-10-21 | 2025-09-14 | 2025-09-14 | 100% | 2025-09-14 | 2025-08-20 | 2025-09-14 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-14 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-10-22 10:04 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-15 | 01.S4 | FPRI0778_CFIN | 02.High | 0.6 | 0.87 | 0778 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-10-10 | 2025-08-20 | 2025-08-20 |  | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-08-20 | 2025-09-14 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-02-21 | 2025-08-15 | 2025-08-15 | MW | 2025-10-10 |  |  |  | 0 | 08. Not Applicable | 1622 | [9 empty] | 10/10: Conditionally Approved. FUT Approved. | 2025-10-10 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0778_CFIN | 02.Interface | 05.CFIN | Continue to auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRE0777 | 2025-01-13 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-05 | 2025-05-12 | 2025-05-16 | 2025-07-16 | 100% | 2025-08-08 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-02 | 2025-06-13 | 2025-08-08 | 100% | 2025-07-23 | 2025-06-06 | 2025-06-20 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-15 | 2025-10-10 | 2025-08-29 | 100% | 2025-08-20 | 2024-10-21 | 2025-09-14 | 2025-09-14 | 100% | 2025-09-14 | 2025-08-20 | 2025-09-14 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-14 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-10-10 | 2025-10-10 | 2025-10-10 | pgaroo@deloitte.com | 2024-10-22 10:04 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-15 | 01.S4 |  |  | 2 | 2.9 | 0778 |  | R3 ITC1 | [6 empty] | 2025-02-05 | 2025-02-21 | 2025-02-05 |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-10-10 | 2025-08-20 | 2025-08-20 |  | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-08-20 | 2025-09-14 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-02-21 | 2025-08-15 | 2025-08-15 | MW | 2025-10-10 |  |  |  | 0 | 08. Not Applicable | 1621 | [9 empty] | 10/10: Conditionally Approved. FUT Approved. | 2025-10-10 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0770_IP | 02.Interface | 01.IP - Intel Product | To enable auto-certify a BL [Blackline] task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2219_Auto%20certification%20of%20Tasks_%20S4%20to%20BL.pptx?d=w6fee1d7643f84f23b0399bc249c3279d&csf=1&web=1&e=SQoy9z | 02.No | 01.Yes |  | 2024-10-21 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | ECA | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2026-11-28 | 2026-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-08-04 | 2025-08-15 |  |  | 2025-08-15 | 2025-08-18 | 2025-09-12 |  |  | 2025-09-12 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-25 | 03.Mulesoft | FPRI0770_CFIN | 02.High | 0.6 | 0.87 | 0770 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2026-11-28 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-08-15 |  |  |  | 2025-09-12 |  |  |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-13 | S4 | 2026-01-23 |  |  |  | 0 | 08. Not Applicable | 1620 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) | 09/12: INTEL to provide approval today | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0770_IF | 02.Interface | 02.IF - Intel Foundry | To enable auto-certify a BL [Blackline] task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2219_Auto%20certification%20of%20Tasks_%20S4%20to%20BL.pptx?d=w6fee1d7643f84f23b0399bc249c3279d&csf=1&web=1&e=SQoy9z | 02.No | 01.Yes |  | 2024-10-21 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | ECA | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2026-11-28 | 2026-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-08-04 | 2025-08-15 |  |  | 2025-08-15 | 2025-08-18 | 2025-09-12 |  |  | 2025-09-12 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-25 | 03.Mulesoft | FPRI0770_CFIN | 02.High | 0.6 | 0.87 | 0770 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2026-11-28 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-08-15 |  |  |  | 2025-09-12 |  |  |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-13 | S4 | 2026-01-23 |  |  |  | 0 | 08. Not Applicable | 1619 | [7 empty] | 5. Not Dispositioned |  | 09/12: INTEL to provide approval today | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2219 | FPRI0770_CFIN | 02.Interface | 05.CFIN | To enable auto-certify a BL [Blackline] task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2219_Auto%20certification%20of%20Tasks_%20S4%20to%20BL.pptx?d=w6fee1d7643f84f23b0399bc249c3279d&csf=1&web=1&e=SQoy9z | 02.No | 01.Yes |  | 2024-10-21 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 05. N/A | 02.High | Corporate Functions | 01.Yes | 23557 | Task - Blackline | BLACKLINE | ECA | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2026-11-28 | 2026-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-08-04 | 2025-08-15 |  |  | 2025-08-15 | 2025-08-18 | 2025-09-12 |  |  | 2025-09-12 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-25 | 03.Mulesoft |  |  | 2 | 2.9 | 0770 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2026-11-28 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-08-15 |  |  |  | 2025-09-12 |  |  |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-10-22 | 2025-11-05 | 2025-10-22 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-13 | S4 | 2026-01-23 |  |  |  | 0 | 08. Not Applicable | 1618 | [7 empty] | 1. On Track | 17. FUT In progress | 10/17: FUT in progress. | 2025-11-28 | Y | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2146 | FPRI0704 | 02.Interface | 01.IP - Intel Product | IF-IP Integration Actual Cost - Inbound Interface | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2146_FPR_RICEFW%20Intake%20Form_Interface_IF-IP%20-%20Actual%20Costing%20-%20Inbound%20Interface.pptx?d=w91ccca0462674b1886261a43e8d9c58d&csf=1&web=1&e=asfSmO | 02.No | 01.Yes | FPRI0703 | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High |  | 02.No | NA | NA | OpenText | S/4 | SFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-03 | 2025-03-07 | 2025-08-13 | 100% | 2025-08-09 | 2025-03-10 | 2025-03-21 | 2025-04-11 | 100% | 2025-04-16 | 2025-03-10 | 2025-03-21 | 2025-04-11 | 100% | 2025-04-16 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-11-08 | [5 empty] | 2025-11-08 | 2025-11-08 | Yes | 2025-11-05 | 2025-06-11 | 2025-06-11 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-06-11 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-15 | 2025-09-15 | 2025-09-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-10-08 | 01.S4 |  |  | 2 | 2.9 | 0704 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  |  |  |  | 2025-11-08 | 2025-11-08 |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | [5 empty] | 2025-02-21 | 2025-03-21 | 2025-08-25 |  | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2742 | [7 empty] | 3. Off Track | 11. Blocked By ECA Readiness | 11/24: Dependent on SFT Readiness and Intel IT team 10/28 - FUT 100% approved | 2025-09-15 | Y | 03. FPR |  |  |  | Current Status: Intel team is building the ECA views ETA (Nov End) Issue: E2E FUT on HOLD Next Steps: Team can pickup E2E FUT once the ECA Build is completed Help needed: Intel to expedite ECA build |  | 2. Risk |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 19 |  | 2025-04-16 | 2025-04-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2145 | FPRI0703 | 02.Interface | 02.IF - Intel Foundry | IF-IP Integration Actual Cost - Outbound Interface | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2145_FPR_RICEFW%20Intake%20Form_Interface_IF-IP%20-%20Actual%20Costing%20-%20Outbound%20Interface.pptx?d=w192b34a3ed034432900ca0df248b2fd6&csf=1&web=1&e=tKkBc2 | 02.No | 01.Yes | FPRE0702 | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High |  | 02.No | NA | NA | S/4 | OpenText | SFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-17 | 2025-03-21 | 2025-08-13 | 100% | 2025-08-09 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-14 | 2025-04-07 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-14 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-11-08 | [5 empty] | 2025-11-08 | 2025-11-08 | Yes | 2025-08-13 | 2025-07-16 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-15 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-15 | 2025-09-15 | 2025-09-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-10-08 | 01.S4 |  |  | 2 | 2.9 | 0703 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-14 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  |  |  |  | 2025-11-08 | 2025-11-08 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2025-02-21 | 2025-04-18 | 2025-08-25 |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 2741 | [7 empty] | 3. Off Track | 11. Blocked By ECA Readiness | 11/24: - Dependent on SFT Readiness and Intel IT team 10/28 - FUT 100% approved | 2025-09-15 | Y | 03. FPR |  |  |  | Current Status: Intel team is building the ECA views ETA (Nov End) Issue: E2E FUT on HOLD Next Steps: Team can pickup E2E FUT once the ECA Build is completed Help needed: Intel to expedite ECA build |  | 2. Risk |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 19 |  | 2025-04-18 | 2025-04-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2214 | FPRI0696_IP | 02.Interface | 01.IP - Intel Product | Interface between ONESOURCE and Readsoft Process Director built on the back of Global Next | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2214_Readsoft%20Integration_RICEFW%20Intake%20For_Interface.pptx?d=w4e44ae1f7b184bbc9f07a248d0e3c9b6&csf=1&web=1&e=iMPi2c | 01.Yes | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 03. NA | 02.Intel | 02.High | Corporate Functions | 01.Yes | 37261; 64229 | OneSource Indirect Tax Suite; Readsoft - Process Director Accounts Payable IP | ONESOURCE | READSOFT | NA | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-11-20 | 100% | 2025-11-26 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-26 | [10 empty] | 2025-08-15 | 2025-11-10 | 2025-11-10 | 100% | 2025-11-10 | 2025-11-26 | 2025-11-26 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-08 | 01.S4 |  |  | 2 | 2.9 | 0696 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-26 | 2025-11-26 | [9 empty] | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-26 | 2025-11-26 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 |  |  |  |  | Readsoft | 2025-01-24 | 2025-03-21 | 2025-03-21 | S4 | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1614 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: India and China team are reviewing the FUT. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2214 | FPRI0696_IF | 02.Interface | 02.IF - Intel Foundry | Interface between ONESOURCE and Readsoft Process Director built on the back of Global Next | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2214_Readsoft%20Integration_RICEFW%20Intake%20For_Interface.pptx?d=w4e44ae1f7b184bbc9f07a248d0e3c9b6&csf=1&web=1&e=iMPi2c | 01.Yes | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 01.Yes | 01.Deloitte | 03. NA | 02.Intel | 03.Medium | Corporate Functions | 01.Yes | 37261; 64228 | OneSource Indirect Tax Suite; Readsoft - Process Director Accounts Payable IF | ONESOURCE | READSOFT | NA | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-11-20 | 100% | 2025-11-26 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-26 | [10 empty] | 2025-08-15 | 2025-11-10 | 2025-11-10 | 100% | 2025-11-10 | 2025-11-26 | 2025-11-26 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-08 | 01.S4 | FPRI0696_IP | 02.High | 0.6 | 0.87 | 0696 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-26 | 2025-11-26 | [9 empty] | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-26 | 2025-11-26 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 |  |  |  |  | Readsoft | 2025-01-24 | 2025-03-21 | 2025-03-21 | S4 | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1613 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: India and China team are reviewing the FUT. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2198 | FPRI0695 | 02.Interface | 05.CFIN | Reference Interest Rates - S4 converted data from MDG to CFIN | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2198_S4%20Converted%20Reference%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w66191de204e844e0bdcda0358e940eb8&csf=1&web=1&e=E0Oe2b | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | S/4 MDG | CFIN | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-02-14 | 2025-06-06 | 2025-06-13 | 2026-01-07 | 100% | 2026-01-09 | 2025-05-02 | 2025-07-18 | 2026-01-07 | 100% | 2026-01-09 | 2025-05-02 | 2025-07-18 | 2026-02-04 | 100% | 2026-01-13 | [10 empty] | 2025-10-01 | 2025-11-30 | 2025-11-30 | 100% | 2025-09-30 | 2026-01-13 | 2026-01-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2025-07-18 | 2025-11-30 | 2025-11-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-08 | 02.MDG |  |  | 1 | 1.45 | 0695 |  | R3 ITC1 | [6 empty] | 2025-02-14 | 2025-02-14 | 2025-02-14 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-13 | [9 empty] | 2025-11-30 | 2025-09-30 | 2025-09-30 | 2026-01-13 | 2026-01-13 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 | [5 empty] | 2025-01-24 | 2025-07-18 | 2025-07-18 | S4 | 2025-09-05 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 2549 | [7 empty] | 4. Completed | 1. Approved no action | 11/20: FUT approved | 2025-11-30 | Y | 03. FPR | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2197 | FPRI0694 | 02.Interface | 05.CFIN | Exchange Rates N - S4 converted data from MuleSoft to Treasury Suite | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2197_S4%20Converted%20N%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w4014c046f42743ae9a0864015c3d0625&csf=1&web=1&e=rZ6Vu9 | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | MULESOFT | TREASURY SUITE | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-28 | 2026-01-07 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-05-19 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2026-02-03 | 2025-12-22 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-03 | 2026-02-20 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-10 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-01-07 | 2026-02-20 | 2026-02-20 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-08 | 03.Mulesoft |  |  | 1 | 1.45 | 0694 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2025-09-10 |  | 2025-09-10 |  | 2026-02-03 | 2026-02-03 | 2026-02-03 |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-03 | 2026-02-20 |  |  | 2026-02-10 | 2026-03-04 | 2026-02-10 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-06-13 | MW | 2025-08-15 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 2548 | [7 empty] | 1. On Track | 3. Awaiting Approval | 01/19: Defect to be logged for removing the Hardcoding | 2026-02-20 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-01-09 | 2026-01-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2196 | FPRI0693 | 02.Interface | 05.CFIN | Exchange Rates L - S4 converted data from MuleSoft to Treasury Suite | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2196_S4%20Converted%20L%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w8284afe7396042f6b5639789e1cbce5f&csf=1&web=1&e=LOXJhS | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | Treasury Suite | MULESOFT | MULESOFT | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-02-17 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-18 | 2025-03-05 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-25 | 2025-03-05 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-25 | 2025-06-16 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-21 | 2025-09-10 | 2025-09-30 | 100% | 2025-10-08 | 2025-09-22 | 2025-12-15 | 2025-12-15 | 100% | 2025-12-10 | 2025-10-08 | 2025-12-10 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-10 | 2025-12-15 | 2025-12-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-08 | 03.Mulesoft |  |  | 1 | 1.45 | 0693 |  | R3 ITC1 | [6 empty] | 2025-02-17 | 2025-02-17 | 2025-02-17 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-08-25 | 2025-09-10 | 2025-08-25 | 2025-08-25 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-12-15 | 2025-12-10 | 2025-12-10 | 2025-10-08 | 2025-12-10 |  |  | 2025-11-14 | 2025-12-05 | 2025-11-14 | [5 empty] | 2025-01-24 | 2025-07-18 | 2025-07-18 | MW | 2025-09-05 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 2547 | [7 empty] | 1. On Track | 1. Approved no action | 11/20: FUT approved | 2025-12-15 | Y | 03. FPR | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-09-10 | 2025-08-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2058 | FPRI0600_IP | 02.Interface | 01.IP - Intel Product | Continuation to use Blackline Account Reconciliations Tool (ART), Blackline Match and Clear (MNC) and Blackline Task as SAP S4 does not have the capabilities or using it as a tool to supplement standard SAP matching capability.​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2058_FPR_Perform%20Closing_Blackline%20Connector%20Intake%20form.pptx?d=wee4cb59b7453484db5114749d4030082&csf=1&web=1&e=m9S02k | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 20824;15513; 23557 | Matching - Blackline; Close Reconciliation Tool - Blackline; Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-03-24 | 2025-04-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-09 | 2025-09-26 | 100% | 2025-09-23 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-09-10 | 100% | 2025-09-10 | 2025-06-16 | 2025-07-18 | 2025-09-30 | 100% | 2025-10-08 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-10-08 | 2025-10-08 | No | 2025-08-13 | 2025-12-24 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-30 | 2025-07-30 | jenoronha@deloitte.com | 2025-05-26 08:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 | FPRI0600_CFIN | 03.Medium | 0.3 | 0.435 | 0600 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-18 | 2025-06-13 | 2025-06-13 |  | 2025-09-11 |  |  |  | 0 | 08. Not Applicable | 3062 | [7 empty] | 4. Completed |  |  | 2025-07-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2058 | FPRI0600_IF | 02.Interface | 02.IF - Intel Foundry | Continuation to use Blackline Account Reconciliations Tool (ART), Blackline Match and Clear (MNC) and Blackline Task as SAP S4 does not have the capabilities or using it as a tool to supplement standard SAP matching capability.​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2058_FPR_Perform%20Closing_Blackline%20Connector%20Intake%20form.pptx?d=wee4cb59b7453484db5114749d4030082&csf=1&web=1&e=m9S02k | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 20824;15513; 23557 | Matching - Blackline; Close Reconciliation Tool - Blackline; Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-03-24 | 2025-04-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-09 | 2025-09-26 | 100% | 2025-09-23 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-09-10 | 100% | 2025-09-10 | 2025-06-16 | 2025-07-18 | 2025-09-30 | 100% | 2025-10-08 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-10-08 | 2025-10-08 | No | 2025-08-13 | 2025-12-24 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-30 | 2025-07-30 | jenoronha@deloitte.com | 2025-05-26 08:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 | FPRI0600_CFIN | 03.Medium | 0.3 | 0.435 | 0600 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-18 | 2025-06-13 | 2025-06-13 |  | 2025-09-11 |  |  |  | 0 | 08. Not Applicable | 3061 | [7 empty] | 4. Completed | 3. Awaiting Approval |  | 2025-07-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2058 | FPRI0600_CFIN | 02.Interface | 05.CFIN | Continuation to use Blackline Account Reconciliations Tool (ART), Blackline Match and Clear (MNC) and Blackline Task as SAP S4 does not have the capabilities or using it as a tool to supplement standard SAP matching capability.​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2058_FPR_Perform%20Closing_Blackline%20Connector%20Intake%20form.pptx?d=wee4cb59b7453484db5114749d4030082&csf=1&web=1&e=m9S02k | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 20824;15513; 23557 | Matching - Blackline; Close Reconciliation Tool - Blackline; Task - Blackline | BLACKLINE | S/4 | MULESOFT | 2025-03-24 | 2025-04-18 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-09 | 2025-09-26 | 100% | 2025-09-23 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-05-19 | 2025-06-13 | 2025-09-10 | 100% | 2025-09-10 | 2025-06-16 | 2025-07-18 | 2025-09-30 | 100% | 2025-10-08 | 2024-10-21 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-10-08 | 2025-10-08 | No | 2025-08-13 | 2025-12-24 | 2025-09-10 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-30 | 2025-07-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-10-01 | 01.S4 |  |  | 1 | 1.45 | 0600 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-18 | 2025-06-13 | 2025-06-13 |  | 2025-09-11 |  |  |  | 0 | 08. Not Applicable | 2701 | [7 empty] | 4. Completed |  |  | 2025-07-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1031 | FPRI0599_IP | 02.Interface | 01.IP - Intel Product | ServiceNow Asset change | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0001_FPR_Asset%20inventory%20and%20serial%20number%20update.pptx?d=w68230ca66fb743128ff74ad67537e4f4&csf=1&web=1&e=TJgwkv | 02.No | 01.Yes | FPRE0324_IP | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 35464 | ServiceNow Cloud Lab | SERVICENOW | S/4 | MULESOFT | 2024-10-21 | 2024-12-13 | 2024-11-15 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-24 | 2025-02-28 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-28 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-30 | 2025-06-30 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-08-04 | 2025-08-04 | Yes | 2025-06-11 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-07-30 | 2025-07-30 | pgaroo@deloitte.com | 2024-11-05 06:03 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 01.S4 |  |  | 1 | 1.45 | 0599 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-12-13 | 2024-11-26 |  | 2025-02-24 | 2025-02-24 | 2025-02-24 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-30 | 2025-04-30 | 2025-04-30 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-04 | 2025-08-04 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2024-12-13 | 2025-03-07 | 2025-02-21 | S4 | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 1519 | [7 empty] | 4. Completed | 2. Smartsheet Hygiene(5.2) | 10/23 - FUT approved. Smartsheet update to be done | 2025-07-30 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1031 | FPRI0599_IF | 02.Interface | 02.IF - Intel Foundry | ServiceNow Asset change | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0001_FPR_Asset%20inventory%20and%20serial%20number%20update.pptx?d=w68230ca66fb743128ff74ad67537e4f4&csf=1&web=1&e=TJgwkv | 02.No | 01.Yes | FPRE0324_IF | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 35464 | ServiceNow Cloud Lab | SERVICENOW | S/4 | MULESOFT | 2024-10-21 | 2024-12-13 | 2024-11-15 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-24 | 2025-02-28 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-02-28 | 2025-03-07 | 2025-04-23 | 100% | 2025-08-04 | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-03-24 | 2025-04-18 | 2025-04-11 | 100% | 2025-04-30 | 2025-06-30 | 2025-07-30 | 2025-07-30 | 100% | 2025-07-30 | 2025-08-04 | 2025-08-04 | Yes | 2025-06-11 | 2025-10-08 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-07-30 | 2025-07-30 | vasamohan@deloitte.com | 2024-09-04 08:05 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 01.S4 | FPRI0599_IP | 03.Medium | 0.3 | 0.435 | 0599 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-12-13 | 2024-11-26 |  | 2025-02-24 | 2025-02-24 | 2025-02-24 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-30 | 2025-04-30 | 2025-04-30 |  | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-04 | 2025-08-04 |  |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | [5 empty] | 2024-12-13 | 2025-03-07 | 2025-02-21 | S4 | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 1518 | [7 empty] | 1. On Track | 1. Approved no action | 10/17; FUT Approved | 2025-07-30 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2047 | FPRI0598 | 02.Interface | 05.CFIN | N rate from Mulesoft to MDG | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2047_N%20Rates%20from%20MuleSoft%20to%20S4%20MDG.pptx?d=w741c47baead4432396ae382437c7da5e&csf=1&web=1&e=7gADKH | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 04.Low | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | MULESOFT | S/4 MDG | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2025-04-21 | 2025-05-16 | 2026-01-07 | 100% | 2026-01-09 | 2025-05-19 | 2025-06-13 | 2026-01-07 | 100% | 2026-01-09 | 2025-05-19 | 2025-06-13 | 2026-01-07 | 100% | 2026-01-09 | 2025-04-21 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-19 | 2025-09-30 | 2025-09-30 | 100% | 2026-02-03 | 2025-09-15 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2026-02-03 | 2026-02-03 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-29 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 02.MDG |  |  | 0.5 | 0.725 | 0598 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2025-09-10 |  | 2025-09-10 |  | 2026-02-03 | 2026-02-03 | 2026-02-03 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2026-02-03 | 2026-02-03 |  |  | 2026-01-29 | 2026-02-04 | 2026-01-29 | [5 empty] | 2025-02-21 | 2025-06-13 | 2025-05-16 | MW | 2025-07-18 |  |  |  | 0 | 08. Not Applicable | 2690 | [7 empty] | 1. On Track | 1. Approved no action | 01/29: FUT Approved. | 2025-09-30 | N | 03. FPR |  |  |  |  | S22 Week2 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-01-09 | 2026-01-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2048 | FPRI0597 | 02.Interface | 05.CFIN | N rate from Mulesoft to Bloomberg | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2048_N%20rates%20from%20Mulesoft%20to%20Bloomberg.pptx?d=w24e8c01d23dc4baf8044c9a4f73da702&csf=1&web=1&e=Wz1fhv | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | MULESOFT | BLOOMBERG | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-03-07 | 2025-04-21 | 2025-05-16 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-04-21 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-21 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-30 | 2025-09-15 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-04 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 03.Mulesoft |  |  | 1 | 1.45 | 0597 |  | R3 ITC1 | [6 empty] | 2025-03-07 | 2025-03-07 | 2025-03-07 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-11-04 | 2025-11-05 | 2025-11-04 | [5 empty] | 2025-02-21 | 2025-11-28 | 2025-05-16 | S4 | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 2691 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 11/04: 2 Internal CR to be raised by Treasury Team | 2025-11-28 | Y | 03. FPR | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2050 | FPRI0596 | 02.Interface | 05.CFIN | N rate from Mulesoft to Treasury Suite | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2050_N%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w60ca2e371cff41aca8fbe6d42117fb9d&csf=1&web=1&e=wHAafa | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | MULESOFT | TREASURY SUITE | MULESOFT | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-28 | 2025-04-21 | 2025-05-16 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-14 | 2025-04-21 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-21 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-30 | 2025-12-22 | 2026-02-20 | 2026-02-20 | 100% | 2026-02-20 | 2026-02-14 | 2026-02-20 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-04 | Not Applicable | R3 Build & UT Sprint 19 | 2026-02-20 | 2026-02-20 | 2026-02-20 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-23 | 03.Mulesoft |  |  | 1 | 1.45 | 0596 |  | R3 ITC1 | [6 empty] | 2025-02-28 | 2025-02-28 | 2025-02-28 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-02-14 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-14 | 2026-02-20 |  |  | 2025-11-04 | 2025-11-05 | 2025-11-04 | [5 empty] | 2025-02-21 | 2026-02-20 | 2025-05-16 | S4 | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 2692 | [7 empty] | 3. Off Track | 9. Blocked by B-App Readiness | 11/04: 2 Internal CR to be raised by Treasury Team | 2026-02-20 | Y | 03. FPR | [7 empty] | BA Readiness | Complete | R3 Build & UT Sprint 23 | 2026-02-14 | 2026-02-20 | 2026-02-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1915 | FPRI0554 | 02.Interface | 02.IF - Intel Foundry | SKF Interface to get file from ECA and send to S4 via BODS - IF | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1915_FPR_RICEFW%20Intake%20Form_Interface%20SKF%20PlanActual%20for%20WSPW%20(Wafer).pptx?d=we7466ed2e0ee4657bc850c480ca9dd91&csf=1&web=1&e=sXEfJu | 02.No | 01.Yes | FPRE0549 | 2024-08-20 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply / Demand Planning | 01.Yes | 4119; 15170; 13284; 9332; 31348; 35612; 32079; 41627; 25596; 38908; 36453; 15799 | Wafer Starts Per Week; ISA-VS2012 US (MAPPS); ISA-VS2008 Asia (ATMPS CR and DPCR); Phoenix (ICS); Workstream; XEUS Loader Framework; ATM MARS; PDF-SMH (Sapience Manufacturing Hub) Integration Platform - IF; JDA/Blue Yonder ESP/OP (ALTR); Module Planning for Supply Chain on Blue Yonder; Tactical Planning for Supply Chain on Blue Yonder; MOR/FCS/SCS | ECA | S/4 | MuleSoft | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-20 | 2025-04-14 | 2025-04-18 | 2025-12-03 | 100% | 2025-11-27 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-05-30 | 2025-06-13 | 2025-05-15 | 100% | 2025-08-04 | 2025-11-17 | 2025-11-21 | 2025-12-03 | 100% | 2025-12-03 | 2025-12-08 | 2025-12-19 | 2025-12-19 | 100% | 2025-12-22 |  | 2025-08-18 | 2025-08-18 | 100% | 2025-08-18 | 2025-12-22 | 2025-12-22 | No | 2025-08-13 | 2025-11-05 | 2026-02-04 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-21 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-19 | 2025-12-19 | 2025-12-19 | arpitsharma@deloitte.com | 2024-11-19 02:35 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-22 | 01.S4 |  |  | 2 | 2.9 | 0554 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-21 | 2025-03-20 |  | 2025-11-27 | 2025-12-03 | 2025-11-27 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-12-22 | 2025-12-22 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 |  |  |  |  | WIP Inventory Shipping | 2025-06-13 | 2025-06-13 | 2025-06-13 | MW | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 1901 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/20: FUT sent for Intel Review. | 2025-12-19 | Y | 03. FPR |  |  |  | 0107: E2E FUT in progress. ETA is 1/9 Current Status: ECA views build complete. E2E FUT in progress. ETA is 1/9 Issue: Next Steps: E2E FUT in progress. ETA is 1/9 Help needed: N/A | S22 Week2 Target | 5. Review Closed |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1517 | FPRI0545 | 02.Interface | 02.IF - Intel Foundry | IF-IP Integration - Interface to send Cost Idoc from S4 If to S4 IP | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1517_FPR_RICEFW%20Intake%20Form_Interface%20between%20IF%20and%20IP%20-%20Outbound.pptx?d=w9d55e9d604744dd1917935fae06b86ab&csf=1&web=1&e=awQMUF | 01.Yes | 01.Yes | FPRE0549 FPRI0544 | 2024-08-23 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | S/4 | S/4 | SFT | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 100% | 2025-03-26 | 2025-02-21 | 2025-03-07 | 2025-03-28 | 100% | 2025-03-26 | 2025-09-01 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-15 | 2025-10-09 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-10-09 | 2025-10-09 | 2025-10-09 | pgaroo@deloitte.com | 2024-08-14 08:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-08-31 | 01.S4 |  |  | 1 | 1.45 | 0545 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-03-26 | 2025-03-28 | 2025-03-26 | 2025-03-26 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-09 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-09-20 | 2025-03-07 | 2025-09-10 |  | 2025-11-07 |  |  |  | 0 | 08. Not Applicable | 2036 | [10 empty] | 2025-10-09 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-03-28 | 2025-03-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1864 | FPRI0544 | 02.Interface | 01.IP - Intel Product | IF-IP Integration - Interface to receive Cost Idoc from S4 If to S4 IP | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1864_FPR_RICEFW%20Intake%20Form_Interface%20between%20IF%20and%20IP%20-%20Inbound.pptx?d=wd36f51de245d4982830b87e2b72729b9&csf=1&web=1&e=t2dzQe | 02.No | 01.Yes | FPRE0549 | 2024-08-20 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | S/4 | S/4 | SFT | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-24 | 2025-01-31 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-21 | 2025-03-07 | 2025-03-27 | 100% | 2025-03-25 | 2025-02-21 | 2025-03-07 | 2025-03-27 | 100% | 2025-03-25 | 2025-09-01 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-15 | 2025-10-09 | 2025-09-30 | 100% | 2025-09-23 | [5 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-10-09 | 2025-10-09 | 2025-10-09 | pgaroo@deloitte.com | 2024-08-14 08:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-08-22 | 01.S4 |  |  | 1 | 1.45 | 0544 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-03-25 | 2025-03-27 | 2025-03-25 | 2025-03-25 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-09 | 2025-09-23 | 2025-09-23 |  |  |  |  | 2025-09-23 | 2025-09-23 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-09-20 | 2025-03-07 | 2025-09-10 |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2177 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-10-09 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-03-27 | 2025-03-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1815 | FPRI0533 | 02.Interface | 05.CFIN | Reference Interest Rates from MuleSoft to S4 MDG | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1815_Reference%20Rates%20from%20MuleSoft%20to%20S4%20MDG.pptx?d=w20d28a6b2abc4b679345a680d1d47e56&csf=1&web=1&e=kX8xLD | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | Bloomberg | S/4 MDG | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2025-08-29 | 2024-12-16 | 2025-01-24 | 2025-03-21 | 100% | 2025-03-19 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-01-27 | 2025-01-31 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-24 | 2025-09-10 | 2025-09-30 | 100% | 2025-10-07 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-30 | 2025-10-07 | 2025-10-07 | No | 2025-08-13 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 02.MDG |  |  | 1 | 1.45 | 0533 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-03-19 | 2025-03-21 | 2025-03-19 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-07 | 2025-10-07 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 | [5 empty] | 2024-09-20 | 2025-04-18 | 2025-01-31 | MW | 2025-05-16 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 1534 | [7 empty] | 4. Completed | 1. Approved no action | 11/17: FUT approved | 2025-09-10 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1816 | FPRI0532 | 02.Interface | 05.CFIN | Request for Reference Interest Rates from MuleSoft to Bloomberg | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1816_Reference%20Rates%20from%20MuleSoft%20to%20Bloomberg.pptx?d=w061056a3476143cf8e8f693cb123f24e&csf=1&web=1&e=aXcj0O | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | MULESOFT | BLOOMBERG | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-30 | 2025-09-15 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2026-01-16 | 2026-01-16 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-16 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0532 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2026-01-16 | 2026-01-16 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 | [5 empty] | 2024-09-20 | 2026-01-16 | 2025-04-04 | S4 | 2025-11-07 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 1535 | [7 empty] | 4. Completed | 1. Approved no action | 11/17: FUT approved | 2026-01-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-16 | 2026-01-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1818 | FPRI0531 | 02.Interface | 05.CFIN | L Rates from MuleSoft to S4 MDG | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1818_L%20Rates%20from%20MuleSoft%20to%20S4%20MDG.pptx?d=we47ff0a4bd364525aa734449e9817beb&csf=1&web=1&e=k9SvYX | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | Bloomberg | S/4 MDG | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-27 | 2025-02-21 | 2025-03-07 | 100% | 2025-02-07 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-03-28 | 2025-03-24 | 2025-04-18 | 2025-04-18 | 100% | 2025-03-28 | 2025-01-27 | 2025-01-31 | 2025-09-10 | 100% | 2025-09-10 | 2025-03-24 | 2025-09-10 | 2025-09-30 | 100% | 2025-10-08 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-30 | 2025-10-08 | 2025-10-08 | No | 2025-08-13 | 2025-10-08 | 2025-09-19 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-10 | 2025-10-05 | 2025-09-19 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 02.MDG |  |  | 1 | 1.45 | 0531 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-07 | 2025-03-07 | 2025-02-07 |  | 2025-03-28 | 2025-04-18 | 2025-03-28 | 2025-03-28 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-08 | 2025-10-08 | 2025-10-08 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-08 | 2025-10-08 |  |  | 2025-10-01 | 2025-10-05 | 2025-10-01 | [5 empty] | 2024-09-20 | 2025-04-18 | 2025-01-31 | MW | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1536 | [7 empty] | 2. At Risk | 14. B-App Under Test |  | 2025-09-10 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-04-18 | 2025-03-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1819 | FPRI0530 | 02.Interface | 05.CFIN | Request for L Rates from MuleSoft to Bloomberg | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1819_L%20rates%20from%20Mulesoft%20to%20Bloomberg.pptx?d=w2548e474e8ca4e049bfb1a20efa2c126&csf=1&web=1&e=R5BpKN | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 18830 | Bloomberg Professional | MULESOFT | BLOOMBERG | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-30 | 2025-09-15 | 2025-09-30 | 2025-09-30 | 100% | 2025-09-30 | 2025-12-06 | 2025-12-06 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0530 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-12-06 | 2025-12-06 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2024-09-20 | 2025-11-28 | 2025-04-04 | S4 | 2025-11-07 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 1537 | [7 empty] | 1. On Track | 1. Approved no action | 11/20: FUT approved | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1828 | FPRI0529 | 02.Interface | 05.CFIN | L Rates from MuleSoft to Quantum | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1828_L%20Rates%20from%20MuleSoft%20to%20Quantum.pptx?d=w0f2e7fef74084cdd997b666c2b3deeff&csf=1&web=1&e=TdZftG | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 6922 | FIS Quantum | MULESOFT | QUANTUM | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-10-09 | 100% | 2025-09-30 | 2025-10-01 | 2025-11-07 | 2025-11-07 | 100% | 2025-12-05 | 2026-01-16 | 2026-01-16 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2026-01-16 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0529 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-10-09 | 2025-09-30 | 2025-09-30 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2026-01-16 | 2026-01-16 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 |  |  |  |  | FIS Quantum | 2024-09-20 | 2026-01-16 | 2025-04-04 | S4 | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 1544 | [7 empty] | 4. Completed | 1. Approved no action | 11/20: FUT approved | 2026-01-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-16 | 2026-01-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1829 | FPRI0528 | 02.Interface | 05.CFIN | L Rates from MuleSoft to Treasury Suite | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1829_L%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w917ac11b628a4699bc1923056288533e&csf=1&web=1&e=ULKbOz | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | MULESOFT | TREASURY SUITE | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-30 | 2025-09-22 | 2025-12-15 | 2025-12-15 | 100% | 2025-12-10 | 2026-01-16 | 2026-01-16 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2026-01-16 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0528 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-30 | 2025-09-30 |  | 2025-12-15 | 2025-12-10 | 2025-12-10 | 2026-01-16 | 2026-01-16 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2024-09-20 | 2026-01-16 | 2025-04-04 | S4 | 2025-10-17 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 1545 | [7 empty] | 4. Completed | 1. Approved no action | 11/20: FUT approved | 2026-01-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-16 | 2026-01-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1830 | FPRI0527 | 02.Interface | 05.CFIN | Reference Interest Rates from MuleSoft to Quantum | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1830_Reference%20Rates%20from%20MuleSoft%20to%20Quantum.pptx?d=w46bc44888ded4b3788b12650405a7b14&csf=1&web=1&e=KMVA2M | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 6922 | FIS Quantum | MULESOFT | QUANTUM | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-24 | 2025-09-22 | 2025-11-07 | 2025-11-07 | 100% | 2025-12-05 | 2026-01-16 | 2026-01-16 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-16 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0527 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-24 | 2025-09-24 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2026-01-16 | 2026-01-16 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 |  |  |  |  | FIS Quantum | 2024-09-20 | 2026-01-16 | 2025-04-04 | S4 | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 1546 | [7 empty] | 4. Completed | 1. Approved no action | 11/20: FUT approved | 2026-01-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-16 | 2026-01-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1831 | FPRI0526 | 02.Interface | 05.CFIN | Reference Interest Rates from MuleSoft to Treasury Suite | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1831_Reference%20Rates%20from%20MuleSoft%20to%20Treasury%20Suite.pptx?d=w732a6df05bf44bdf9e474e8eadbb0e1e&csf=1&web=1&e=ax6jTU | 02.No | 01.Yes |  | 2024-08-09 | Shane Bethune | 01.Approved |  | Std. | 02.No | 02.Intel | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 8121 | Treasury Suite | MULESOFT | TREASURY SUITE | MULESOFT | 2024-09-09 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-24 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-09 | 2025-12-08 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-16 | 2025-03-17 | 2025-07-14 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-16 | 2025-09-10 | 2025-09-30 | 100% | 2025-09-24 | 2025-09-22 | 2025-11-30 | 2025-11-30 | 100% | 2025-12-10 | 2026-01-16 | 2026-01-16 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-16 | 2026-01-16 | 2026-01-16 | pgaroo@deloitte.com | 2024-08-09 08:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-12 | 03.Mulesoft |  |  | 1 | 1.45 | 0526 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-24 | 2025-09-24 |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2026-01-16 | 2026-01-16 |  |  | 2025-11-17 | 2025-12-05 | 2025-11-17 | [5 empty] | 2024-09-20 | 2026-01-16 | 2025-04-04 | S4 | 2025-11-07 |  |  |  | 0 | 07.2. FPR - B-App: Bloomberg | 1547 | [7 empty] | 4. Completed | 1. Approved no action | 11/20: FUT approved | 2026-01-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-16 | 2026-01-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1217 | FPRI0505 | 02.Interface | 05.CFIN | Interface – Copp Clark Holiday Calendar Integration with SAP | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared Documents/General/Implementation/11. Technology/RICEFW/10 RICEFW Inbox/MR-070-0005_FPR_RICEFW Intake Form_v1.0_Copp Clark Interface.pptx?d=w1143bb198b44480ea5162a39d0f4b700&csf=1&web=1&e=sQhjGg | 02.No | 01.Yes |  | 2024-08-02 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 35822 | Copp Clark Holiday Data Service | Copp Clark | S/4 | SFT | 2025-04-07 | 2025-04-25 | 2026-01-07 | 100% | 2025-12-11 | 2025-08-14 | 2025-09-10 | 2026-02-04 | 100% | 2026-01-26 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 100% | 2026-03-09 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-11-18 | 2025-01-01 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-31 | 2026-03-09 | 2026-03-09 |  |  | 2026-01-02 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2026-02-20 | 2026-02-20 | 2026-02-20 | vasamohan@deloitte.com | 2024-08-02 09:51 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-08-27 | 02.MDG |  |  | 1 | 1.45 | 0505 |  | R3 ITC1 | [6 empty] | 2025-12-11 | 2026-01-07 | 2025-12-11 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 | 2026-03-09 | 2026-03-09 | 2026-02-20 | 2026-02-14 | 2026-02-14 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-11-18 | 2025-11-18 | 2025-11-18 |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2026-03-09 | 2026-03-09 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-04-25 | 2026-02-20 | 2025-08-25 |  | 2026-01-09 |  |  |  | 0 | 07.3. FPR - B-App: Copp Clark | 1570 | [7 empty] | 1. On Track | 1. Approved no action | 01/12: FUT Approved. | 2026-02-20 | Y | 03. FPR |  |  |  | 1209: Add to S21 plan. To be approved by 12/12 |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-20 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 757 | FPRI0379 | 02.Interface | 05.CFIN | GL Interface – File processing in MuleSoft-Payroll | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes | FPRE0372 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 05. N/A | 02.High |  | 02.No | NA | NA | PAYROLL | S/4 | MULESOFT | 2024-06-24 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-25 | [5 empty] | 2025-11-07 | 2025-11-07 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-23 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-06-18 05:17 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 03.Mulesoft |  |  | 2 | 2.9 | 0379 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 |  |  |  |  | 2025-11-07 | 2025-11-07 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-09-20 | 2025-11-05 | 2025-01-24 |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2531 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-11-05 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 758 | FPRI0378_IP | 02.Interface | 01.IP - Intel Product | GL Interface - SAP API IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes | FPRE0372 | 2024-06-19 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 8902; 602 | Design and Sales Acceleration E-Commerce (Demo Depot); Flex One-Stop Tool | API | S/4 | MULESOFT | 2024-06-24 | 2024-09-20 | 2024-09-20 | 100% | 2025-01-07 | 2024-09-06 | 2024-09-13 | 2025-03-21 | 100% | 2025-03-18 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-07-01 | 2025-11-14 | 2025-11-14 | 100% | 2025-11-10 | 2025-03-03 | 2025-11-10 | Yes |  | 2025-12-24 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-02-21 | 2025-11-14 | 2025-11-14 | jenoronha@deloitte.com | 2024-12-13 05:52 | meenalx.goel@intel.com | 2026-04-08 06:11 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0378 |  | R3 ITC1 | [6 empty] | 2025-01-07 | 2025-01-07 | 2025-01-07 |  | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-08 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-03-21 | 2025-03-03 | 2025-03-03 |  | 2025-11-14 | 2025-11-10 | 2025-11-10 | 2025-03-03 | 2025-11-10 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2024-09-20 | 2025-01-31 | 2025-02-21 | MW | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 2534 | [7 empty] | 4. Completed | 9. Blocked by B-App Readiness | 12/09: E2E FUT to begin once BA Build is completed. 10/27 - BA Build is still ongoing | 2025-11-14 | Y | 03. FPR |  |  |  | Current Status: S4 FUT, BA build is completed. E2E FUT is in progress Issue: E2E FUT delayed Next Steps: E2E FUT in progress Help needed: N/A E2E FUT ETA: 12/03 | 1119 Rahul to check status in offline tracker | 1. Emerging risk |  | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-01-31 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 758 | FPRI0378_IF | 02.Interface | 02.IF - Intel Foundry | GL Interface - SAP API IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes | FPRE0372 | 2024-06-19 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 8902; 602 | Design and Sales Acceleration E-Commerce (Demo Depot); Flex One-Stop Tool | API | S/4 | MULESOFT | 2024-06-24 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-09-06 | 2024-09-13 | 2025-03-21 | 100% | 2025-03-19 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-27 | 2025-01-31 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-01-27 | 2025-02-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-07-01 | 2025-11-14 | 2025-11-14 | 100% | 2025-11-10 | 2025-03-03 | 2025-11-10 | Yes |  | 2025-12-24 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-02-21 | 2025-11-14 | 2025-11-14 | jenoronha@deloitte.com | 2024-12-13 05:52 | meenalx.goel@intel.com | 2026-04-08 06:11 | 10 |  | 01.S4 | FPRI0378_IP | 02.High | 0.6 | 0.87 | 0378 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-19 | 2025-03-21 | 2025-03-19 |  | 2025-01-08 | 2025-01-31 | 2025-01-08 | 2025-01-08 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-03-21 | 2025-03-03 | 2025-03-03 |  | 2025-11-14 | 2025-11-10 | 2025-11-10 | 2025-03-03 | 2025-11-10 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2024-09-20 | 2025-01-31 | 2025-02-21 | MW | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 2533 | [7 empty] | 4. Completed | 9. Blocked by B-App Readiness | 12/09: E2E FUT to begin once BA Build is completed. 10/27 - BA Build is still ongoing | 2025-11-14 | Y | 03. FPR |  |  |  | Current Status: S4 FUT, BA build is completed. E2E FUT is in progress Issue: E2E FUT delayed Next Steps: E2E FUT in progress Help needed: N/A E2E FUT ETA: 12/03 | 1119 Rahul to check status in offline tracker | 1. Emerging risk |  | BA Readiness | Complete | R3 Build & UT Sprint 20 |  | 2025-01-31 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 759 | FPRI0377 | 02.Interface | 05.CFIN | GL Interface - File Processing in Mulesoft | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes | FPRE0372 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 05. N/A | 02.High | Corporate Functions | 01.Yes | 12245; 5159; 19882; 7440; 5187; 20452; 6922; 19323; 10719 | Workday; ADP Payroll GAR; ADP Payroll EMEA; ICOST - Integrated Cost of Sales tool; Hilan Israel Payroll, Employee Info (TimeIn and Payslips) and Mobile App; Wizdom Costa Rica Payroll System; FIS Quantum; SIRVA; Concur Travel and Expense | CONCUR | S/4 | MULESOFT | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-28 | 100% | 2025-04-25 | 2024-10-21 | 2025-04-21 | 2025-04-21 | 100% | 2025-04-21 | 2025-11-07 | 2025-11-07 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-23 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-06-18 05:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 03.Mulesoft |  |  | 2 | 2.9 | 0377 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-11-07 | 2025-11-07 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  |  |  | FIS Quantum | 2024-07-26 | 2025-11-05 | 2025-01-24 | S4 | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2535 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix |  | 2025-11-05 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 760 | FPRI0376 | 02.Interface | 05.CFIN | GL Interface - File Processing in Mulesoft | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | N | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PM-080-210-0001_PTP_RICEFW%20Intake%20Form%20-%20Copy.pptx?d=w50f7c9df9098450999f93a2c8bfcf015&csf=1&web=1&e=OSAC9o | 02.No | 01.Yes | FPRE0372 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte | 01. Deloitte | 05. N/A | 02.High | Corporate Functions | 01.Yes | 12245; 5159; 19882; 7440; 5187; 20452; 6922; 19323; 10719 | Workday; ADP Payroll GAR; ADP Payroll EMEA; ICOST - Integrated Cost of Sales tool; Hilan Israel Payroll, Employee Info (TimeIn and Payslips) and Mobile App; Wizdom Costa Rica Payroll System; FIS Quantum; SIRVA; Concur Travel and Expense | ICOST | S/4 | MULESOFT | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-09-06 | 2024-09-13 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2025-02-24 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-07 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-05-21 | 2025-01-01 | 2025-01-31 | 2025-01-31 | 100% | 2025-01-31 | 2025-11-07 | 2025-11-07 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-23 | Not Applicable | R3 Build & UT Sprint 14 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-06-18 05:17 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 03.Mulesoft |  |  | 2 | 2.9 | 0376 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-21 | 2025-05-21 | 2025-05-21 |  | 2025-01-31 | 2025-01-31 | 2025-01-31 | 2025-11-07 | 2025-11-07 |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 |  |  |  |  | FIS Quantum | 2024-07-26 | 2025-11-05 | 2025-01-24 | S4 | 2026-01-27 |  |  |  | 0 | 08. Not Applicable | 2536 | [7 empty] | 5. Not Dispositioned |  |  | 2025-11-05 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 712 | FPRI0323_IP | 02.Interface | 01.IP - Intel Product | Create a common API for Asset updates, transfer, retire and Mass upload | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes | FPRE0324_IP | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 23476 | ServiceNow Cloud |  |  | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2025-01-27 | 2025-02-21 | 2024-12-20 | 100% | 2024-12-16 | 2025-07-21 | 2025-08-15 | 2025-01-31 | 100% | 2025-01-08 | 2025-07-21 | 2025-08-15 | 2025-01-31 | 100% | 2025-01-08 | [10 empty] | 2025-08-01 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-09 | 2025-01-08 | 2025-09-09 | Yes | 2025-11-05 | 2025-03-21 | 2025-03-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-11 10:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0323 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-12-16 | 2025-02-21 | 2024-12-16 |  | 2025-01-08 | 2025-08-15 | 2025-01-08 | 2025-01-08 | [9 empty] | 2025-09-12 | 2025-09-09 | 2025-09-09 | 2025-01-08 | 2025-09-09 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2024-07-26 | 2025-08-15 | 2025-02-21 | S4 | 2025-10-03 |  |  |  | 0 | 08. Not Applicable | 2374 | [7 empty] | 3. Off Track | 18. FUT Not Started | 11/14 - Need to check on Service Now Readiness to begin E2E FUT. FUT Completion ETA is 11/12 - E2E FUT to begin | 2025-09-12 | Y | 03. FPR |  |  |  | Current Status: E2E FUT is in progress. No roadblock. Issue: FUT delayed Next Steps: Complete the E2E FUT Help needed: N/A E2E FUT ETA: 11/21 |  | 2. Risk |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 17 |  | 2025-08-15 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 712 | FPRI0323_IF | 02.Interface | 02.IF - Intel Foundry | Create a common API for Asset updates, transfer, retire and Mass upload | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes | FPRE0324_IF | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 23476 | ServiceNow Cloud |  |  | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2025-01-27 | 2025-02-21 | 2024-12-20 | 100% | 2024-12-16 | 2025-07-21 | 2025-08-15 | 2025-01-31 | 100% | 2025-01-08 | 2025-07-21 | 2025-08-15 | 2025-01-31 | 100% | 2025-01-08 | [10 empty] | 2025-08-01 | 2025-09-12 | 2025-09-12 | 100% | 2025-09-09 | 2025-01-08 | 2025-09-09 | Yes | 2025-11-05 | 2025-03-21 | 2025-03-21 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-15 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-06-11 10:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 | FPRI0323_IP | 02.High | 0.6 | 0.87 | 0323 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-12-16 | 2025-02-21 | 2024-12-16 |  | 2025-01-08 | 2025-08-15 | 2025-01-08 | 2025-01-08 | [9 empty] | 2025-09-12 | 2025-09-09 | 2025-09-09 | 2025-01-08 | 2025-09-09 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2024-07-26 | 2025-08-15 | 2025-02-21 | S4 | 2025-10-03 |  |  |  | 0 | 08. Not Applicable | 2373 | [7 empty] | 3. Off Track | 18. FUT Not Started | 11/14 - Need to check on Service Now Readiness to begin E2E FUT. FUT Completion ETA is 11/12 - E2E FUT to begin | 2025-09-12 | Y | 03. FPR |  |  |  | Current Status: E2E FUT is in progress. No roadblock. Issue: FUT delayed Next Steps: Complete the E2E FUT Help needed: N/A E2E FUT ETA: 11/21 |  | 2. Risk |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 17 |  | 2025-08-15 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 569 | FPRI0227 | 02.Interface | 05.CFIN | Outbound Interface from CFIN to QTM in relation to not only QTM payment acknowledgement files and MT message response files ( MT199 (pain.002), MT 5XX, MT3XX) and but also Prior day(CAMT.053) and Intraday(CAMT.052) EBS bank statements. | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-020-002_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wcc7a4e2680e04866b3abff67073d2bbc&csf=1&web=1&e=OHvhDQ | 02.No | 01.Yes |  | 2024-05-21 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 6922 | FIS Quantum | S/4 | Quantum | SFT | 2024-06-24 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-23 | 2025-04-28 | 2025-05-09 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-06-05 | 2025-06-09 | 2025-09-10 | 100% | 2025-09-10 | 2025-06-16 | 2025-07-07 | 2025-09-30 | 100% | 2025-09-23 | 2025-07-31 | 2025-08-19 | 2025-08-19 | 100% | 2025-08-19 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-19 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2024-05-17 09:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 03.Mulesoft |  |  | 1 | 1.45 | 0227 |  | R3 ITC1 | [6 empty] | 2024-07-23 | 2024-07-23 | 2024-07-23 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-12-06 | 2025-12-06 |  |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  |  |  |  | FIS Quantum | 2024-07-12 | 2025-11-28 | 2025-05-23 | S4 | 2025-08-15 |  |  |  | 0 | 06. Banks | 1660 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/23 EP: Provide ETA for Approval 10/17: Team to followup and expedite the approval. | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 568 | FPRI0226 | 02.Interface | 05.CFIN | Inbound Interface from QTM to CFIN in relation to QTM payment files and MT messages | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-020_001_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wee625128aceb40b1b0279059d9646e4d&csf=1&web=1&e=9YQuWq | 02.No | 01.Yes |  | 2024-05-21 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 05. N/A | 03.Medium | Corporate Functions | 01.Yes | 6922 | FIS Quantum | Quantum | S/4 | SFT | 2024-06-24 | 2024-07-17 | 2024-07-17 | 100% | 2024-07-23 | 2025-04-28 | 2025-05-09 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-11-10 | 2025-11-28 | 2025-11-28 | 100% | 2025-12-06 | 2025-06-05 | 2025-06-09 | 2025-09-10 | 100% | 2025-09-10 | 2025-06-16 | 2025-07-07 | 2025-09-30 | 100% | 2025-09-23 | 2025-07-31 | 2025-08-19 | 2025-08-19 | 100% | 2025-08-19 | 2025-12-06 | 2025-12-06 | No |  | 2025-09-19 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-30 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2024-05-17 09:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 03.Mulesoft |  |  | 1 | 1.45 | 0226 |  | R3 ITC1 | [6 empty] | 2024-07-23 | 2024-07-23 | 2024-07-23 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-12-06 | 2025-12-06 |  |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  |  |  |  | FIS Quantum | 2024-07-17 | 2025-11-28 | 2025-05-23 | S4 | 2025-08-15 |  |  |  | 0 | 06. Banks | 1659 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/23 EP: Provide ETA for Approval 10/16 EP: Share reason for Roadblock and Revise FUT due date JAN276"10/17: Team to followup and expedite the approval. | 2025-11-28 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 512 | FPRI0224 | 02.Interface | 05.CFIN | Outbound Interface - SAP to Quantum for Transmitting Cash Management Relevant data via Hubspan | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-070-0006_FPR_RICEFW%20Intake%20form_v1.0.pptx?d=w43b8ad36050e46b3b36386dd1b73ab90&csf=1&web=1&e=ACFwnT | 02.No | 01.Yes |  | 2024-05-30 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 02. Intel | 01.Deloitte | 02.High | Corporate Functions | 01.Yes | 6922 | FIS Quantum | S/4 | Quantum | SFT | 2024-10-21 | 2024-11-08 | 2024-11-15 | 100% | 2025-08-29 | 2025-01-24 | 2025-01-31 | 2025-02-21 | 100% | 2025-02-14 | 2025-02-14 | 2025-03-07 | 2025-03-07 | 100% | 2025-02-27 | 2025-02-14 | 2025-03-07 | 2025-03-07 | 100% | 2025-02-27 | 2025-08-18 | 2025-08-25 | 2025-09-10 | 100% | 2025-09-10 | 2025-08-29 | 2025-09-15 | 2025-09-30 | 100% | 2025-09-23 | 2025-07-31 | 2025-08-19 | 2025-08-19 | 100% | 2025-08-19 | 2025-09-23 | 2025-09-23 |  | 2025-08-13 | 2025-11-05 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-30 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2024-05-17 09:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0224 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-02-14 | 2025-02-21 | 2025-02-14 |  | 2025-02-27 | 2025-03-07 | 2025-02-27 | 2025-02-27 |  | 2025-09-10 |  | 2025-09-10 |  | 2025-09-30 | 2025-09-23 | 2025-09-23 |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-09-23 | 2025-09-23 |  |  | 2025-10-16 | 2025-11-07 | 2025-10-16 |  |  |  |  | FIS Quantum | 2024-11-08 | 2025-03-07 | 2025-04-18 | MW | 2025-06-13 |  |  |  | 0 | 06. Banks | 2392 | [9 empty] | EP: 09/11 No Ext FUT | 2025-09-15 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-03-07 | 2025-02-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1361 | FPRI0188 | 02.Interface | 02.IF - Intel Foundry | Inbound Interface from EMS to S/4 to create WBS element and Update WBS element attributes | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/S4HANA_EMS_INTERFACE.pptx?d=w963c2261f0d242cd9d5d6bb1d87a89f3&csf=1&web=1&e=T6QlsI | 02.No | 01.Yes | FPRE0495 | 2024-05-03 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Supply Chain | 01.Yes | 4012 | Equipment Management System | XEUS | S/4 | APIGEE | 2024-05-27 | 2024-06-17 | 2024-06-14 | 100% | 2024-07-02 | 2024-09-06 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-10-04 | 2024-11-01 | 2024-11-01 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-25 | 2024-10-25 | 100% | 2024-10-25 | 2024-10-11 | 2024-11-08 | 2024-11-08 | 100% | 2024-11-26 | 2025-02-05 | 2025-03-05 | 2025-03-05 | 100% | 2025-03-05 | 2024-11-26 | 2025-03-05 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-28 | Not Applicable | R3 Build & UT Sprint 14 | 2024-11-08 | 2025-03-05 | 2025-03-05 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0188 |  | R3 ITC1 | [6 empty] | 2024-07-02 | 2024-07-02 | 2024-07-02 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-25 |  | 2024-10-25 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-05 | 2025-03-05 | 2025-03-05 | 2024-11-26 | 2025-03-05 |  |  | 2025-05-28 | 2025-05-28 | 2025-05-28 | [5 empty] | 2024-06-17 | 2024-11-01 | 2024-10-25 | S4 | 2026-01-30 |  |  |  | 0 |  | 2439 | [10 empty] | 2025-03-05 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 336 | FPRF0230 | 05.Form | 01.IP - Intel Product | Invoice output Layout - America | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8524BFBE-EBCC-40EE-A865-D4C60EE070B1%7D&file=DC-110-080-IDM-0004_FPR_Intercompany_Invoice%20Output%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-05-21 | Shane Bethune | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-03 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-25 | 2024-06-24 | 2024-06-24 | 2024-08-13 | 100% | 2024-08-14 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-14 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-10-18 | 2024-10-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-21 | 2025-02-28 | 2024-10-18 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-09-13 | 2024-09-13 | 2024-09-13 | pgaroo@deloitte.com | 2024-05-17 09:21 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 1.38 | 0230 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 |  | 2024-08-14 | 2024-08-14 | 2024-08-14 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2025-02-28 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-09-13 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 2607 | [10 empty] | 2024-09-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3199 | FPRE1723_IP | 04.Enhancement | 01.IP - Intel Product | Intel BRF+ - Create Function Modules in S/4HANA(FM and BRF+) | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC9C3AC3-6ACC-44A4-94C7-D82A20AE1C2B%7D&file=INT-CR1570_Intel%20BRF%20-%20Create%20Function%20Modules%20in%20S-4HANA.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-27 | 100% | 2026-02-20 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-08 |  | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2026-02-13 20:49 | cell-link@smartsheet.com | 2026-04-07 15:28 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 1723 | INT-CR1570 | R3 ITC1 | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-02-26 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | [5 empty] | 2026-02-06 | 2026-02-20 |  |  | 2026-03-04 |  |  |  | 0 |  | 3427 | [7 empty] | 2. At Risk | 19. Incomplete Build | 04/07: Development is still in progress. | 2026-02-20 | Y | 03. FPR |  |  |  | 03/31 - Development in progress. FUT ETA: 04/24 | No Requirements and no testing approach. Reverse Engineering in progress. Need to get ITC1 exception with CR Approval. | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-27 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3199 | FPRE1723_IF | 04.Enhancement | 02.IF - Intel Foundry | Intel BRF+ - Create Function Modules in S/4HANA(FM and BRF+) | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC9C3AC3-6ACC-44A4-94C7-D82A20AE1C2B%7D&file=INT-CR1570_Intel%20BRF%20-%20Create%20Function%20Modules%20in%20S-4HANA.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-27 | 100% | 2026-02-20 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-08 |  | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2026-02-13 20:49 | cell-link@smartsheet.com | 2026-04-07 15:28 | 10 |  | 01.S4 | FPRE1723_IP | 04.Low | 0.1 | 0.1 | 1723 | INT-CR1570 | R3 ITC1 | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-02-26 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | [5 empty] | 2026-02-06 | 2026-02-20 |  |  | 2026-03-04 |  |  |  | 0 |  | 3429 | [7 empty] | 2. At Risk | 19. Incomplete Build | 04/07: Development is still in progress. | 2026-02-20 | Y | 03. FPR |  |  |  | 03/31 - Development in progress. FUT ETA: 04/24 | No Requirements and no testing approach. Reverse Engineering in progress. Need to get ITC1 exception with CR Approval. | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-27 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3199 | FPRE1722_IP | 04.Enhancement | 01.IP - Intel Product | Intel BRF+ - Create Function Modules in S/4HANA (FM and components) | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2026-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC9C3AC3-6ACC-44A4-94C7-D82A20AE1C2B%7D&file=INT-CR1570_Intel%20BRF%20-%20Create%20Function%20Modules%20in%20S-4HANA.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-27 | 100% | 2026-02-20 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-08 |  | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2026-02-13 20:49 | cell-link@smartsheet.com | 2026-04-07 15:28 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 1722 | INT-CR1570 | R3 ITC1 | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-02-26 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | [5 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-04 |  |  |  | 0 |  | 3428 | [7 empty] | 2. At Risk | 19. Incomplete Build | 04/07: Development is still in progress. | 2026-02-27 | Y | 03. FPR |  |  |  | 03/31 - Development in progress. FUT ETA: 04/24 | No Requirements and no testing approach. Reverse Engineering in progress. Need to get ITC1 exception with CR Approval. | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-27 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3199 | FPRE1722_IF | 04.Enhancement | 02.IF - Intel Foundry | Intel BRF+ - Create Function Modules in S/4HANA (FM and components) | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2026-01-30 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAC9C3AC3-6ACC-44A4-94C7-D82A20AE1C2B%7D&file=INT-CR1570_Intel%20BRF%20-%20Create%20Function%20Modules%20in%20S-4HANA.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-27 | 100% | 2026-02-20 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-09 | 2026-02-16 | 2026-02-27 | 2026-02-27 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-08 |  | R3 Build & UT Sprint 23+ | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2026-02-13 20:49 | cell-link@smartsheet.com | 2026-04-07 15:28 | 10 |  | 01.S4 | FPRE1722_IP | 04.Low | 0.1 | 0.1 | 1722 | INT-CR1570 | R3 ITC1 | [5 empty] | 2026-02-20 | 2026-02-20 | 2026-02-27 | 2026-02-20 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-03-09 | 2026-03-09 | 2026-02-27 | 2026-02-23 | 2026-02-26 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | [5 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-04 |  |  |  | 0 |  | 3430 | [7 empty] | 2. At Risk | 19. Incomplete Build | 04/07: Development is still in progress. | 2026-02-27 | Y | 03. FPR |  |  |  | 03/31 - Development in progress. FUT ETA: 04/24 | No Requirements and no testing approach. Reverse Engineering in progress. Need to get ITC1 exception with CR Approval. | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-02-27 | 2026-03-09 | [8 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3188 | FPRE1711 | 04.Enhancement | 05.CFIN | BADI Enhancement to change Order Type from Product cost Collector from IP & IF system to Internal Order in CFIN in R3 | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE4D9B4C4-418A-482C-BE8D-9E10815B1B3F%7D&file=PCC%20to%20IO%20Cost%20Obejct%20Mapping.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-12-08 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-06 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-19 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-19 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-12 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-04 | 2026-02-04 | 2026-02-04 | jenoronha@deloitte.com | 2025-12-08 09:10 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 1711 | INT-CR1161 | R3 ITC1 | [5 empty] | 2026-01-06 | 2026-01-06 | 2026-01-07 | 2026-01-06 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-12 | 2026-03-04 | 2026-02-12 | [5 empty] | 2026-01-07 | 2026-02-04 |  |  | 2026-03-04 |  |  |  | 0 |  | 3398 | [7 empty] | 1. On Track | 1. Approved no action | 02/12: FUT Approved | 2026-02-04 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3185 | FPRE1706 | 04.Enhancement | 05.CFIN | Enhancement to create Cash Management relevant data from F110 Payment Run for Invoice based payments to be sent to Quantum | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/TREASURY%20NEW%20CR.pptx?d=w6091f8166d544846bba6c380c53ec8cb&csf=1&web=1&e=c9cbsT | 02.No | 01.Yes |  | 2025-11-22 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-29 | 2026-02-09 | 2026-03-04 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-09 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-09 | 2026-03-04 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-03-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-11-22 01:33 | cell-link@smartsheet.com | 2026-03-19 19:18 | 10 |  | 01.S4 |  |  | 1 | 1 | 1706 | INT-CR1288 | R3 ITC1 | [6 empty] | 2026-01-29 | 2026-02-06 | 2026-01-29 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-08 | 2026-03-08 | 2026-03-08 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-20 | 2026-03-27 | 2026-03-20 | [5 empty] | 2026-02-06 | 2026-03-04 |  |  | 2026-03-04 |  |  |  | 0 |  | 3389 | [7 empty] | 3. Off Track | 19. Incomplete Build | 03/19: Phanni to check and confirm on the latest update on this. Vivek is handling this from Onshore. | 2026-03-04 | Y | 03. FPR |  |  |  | 03/11: FUT in progress. ETA is 03/20. Current status: FUT in progress Issue: FUT delayed. Next steps: Expedite FUT completion Help needed: N/A FUT ETA: 03/20 | FUT in progress. ETA is 3/20 | 2. Risk | On track for S23+ | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-08 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3187 | FPRE1705 | 04.Enhancement | 05.CFIN | Enhancement to do Cash App post EBS load with the corresponding payment advice. | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/FPR/INT-CR1168%20OR-140-140_Enhancement%20to%20Cash%20App%20Post%20EBS%20load%20v1.0.pptx?d=wca05fd06082141fe8200f838db198d3b&csf=1&web=1&e=acfOkb | 02.No | 01.Yes |  | 2025-11-22 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-30 | 2026-01-12 | 2026-01-16 | 2026-02-20 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-03-04 | 100% | 2026-03-09 | [15 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-11 | N | 100% | 2026-03-17 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-11-22 01:33 | cell-link@smartsheet.com | 2026-03-16 21:35 | 10 |  | 01.S4 |  |  | 1 | 1 | 1705 | INT-CR1168 | R3 ITC1 | [6 empty] | 2026-01-30 | 2026-02-06 | 2026-01-30 | 2026-03-09 | 2026-03-09 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-03-02 | 2026-03-02 | [12 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | [5 empty] | 2026-02-06 | 2026-02-20 |  |  | 2026-03-04 |  |  |  | 0 |  | 3388 | [7 empty] | 1. On Track | 3. Awaiting Approval | 03/13: Additional scenarios requested by Intel for Conditional sign-off. Clara is tetsing the same. | 2026-02-20 | Y | 03. FPR |  |  |  |  | Feedback received post review. Walkthrough planned for final sign off tomorrow (3/11) |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2470 | FPRE1695 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori app - Change WBS Element Request Form with ALV Input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2470_FPR_DC-050-500-Custom%20Fiori%20App%20-%20WBS%20Element%20Request%20%20Form%20with%20ALV%20input%E2%80%8B.pptx?d=wfb78e17c71e44c3a9dfa0a142636bd9a&csf=1&web=1&e=ySn6uP | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-12-03 | 100% | 2025-11-28 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-12-24 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-24 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-07-17 05:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1695 |  | R3 ITC1 | [6 empty] | 2025-11-28 | 2025-12-03 | 2025-11-28 | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-03-21 | 2025-10-31 |  |  | 2026-01-09 |  |  |  | 0 | 08. Not Applicable | 3178 | [7 empty] | 4. Completed | 1. Approved no action | 01/16: FUT Approved. | 2025-10-31 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3150 | FPRE1671_IP | 04.Enhancement | 01.IP - Intel Product | S4, Perform required calculations, summarizations, mappings and post the allocation​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3150_IF_ECA%20view%20for%20Xesus%20Mars%20Volumes%20and%20non-burden%20%26%20Non-dep%20allocation%20to%20PCOS%20OCOS.pptx?d=we97bfb47774e43f28e13e2103762cb30&csf=1&web=1&e=xFeD87 | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-12 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-02-27 | N | 100% | 2026-03-09 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-11-04 01:53 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 1671 | INT-CR1337 | R3 ITC1 | [6 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-01-07 | 2026-02-06 |  |  | 2026-03-06 |  |  |  | 0 |  | 3351 | [7 empty] | 4. Completed | 17. FUT In progress | 03/06: Amit needs to check with Akshatha on the scenario and walkthrough planned today with Intel. | 2026-02-06 | N | 03. FPR |  |  |  |  | Dependent on FPRI1669 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3150 | FPRE1671_IF | 04.Enhancement | 02.IF - Intel Foundry | S4, Perform required calculations, summarizations, mappings and post the allocation​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3150_IF_ECA%20view%20for%20Xesus%20Mars%20Volumes%20and%20non-burden%20%26%20Non-dep%20allocation%20to%20PCOS%20OCOS.pptx?d=we97bfb47774e43f28e13e2103762cb30&csf=1&web=1&e=xFeD87 | 02.No | 01.Yes |  | 2025-11-04 |  | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-01-07 | 2026-01-07 | 100% | 2026-01-12 | 2026-01-12 | 2026-01-16 | 2026-01-16 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-02-20 | 2026-02-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-02-27 | N | 100% | 2026-03-09 | Sprint 23 Week 3 | R3 Build & UT Sprint 23+ | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-12-05 21:56 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 | FPRE1671_IP | 03.Medium | 0.2 | 0.2 | 1671 | INT-CR1337 | R3 ITC1 | [6 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2026-01-07 | 2026-02-06 |  |  | 2026-03-06 |  |  |  | 0 |  | 3394 | [7 empty] | 4. Completed | 17. FUT In progress | 03/06: Amit needs to check with Akshatha on the scenario and walkthrough planned today with Intel. | 2026-02-06 | N | 03. FPR |  |  |  |  | Dependent on FPRI1669 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRE1661_IP | 04.Enhancement | 01.IP - Intel Product | WBS transfer tool | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-12-03 | 100% | 2025-12-03 | 2025-08-18 | 2025-08-22 | 2025-12-12 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 | No |  | 2026-03-20 | 2026-03-20 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-20 | N | 100% | 2026-04-03 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-10-16 07:16 | cell-link@smartsheet.com | 2026-04-03 04:03 | 10 | 2025-01-11 | 01.S4 |  |  | 2 | 2 | 1661 |  | R3 ITC1 | [6 empty] | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  | 2026-04-03 | 2026-04-03 | 2026-04-03 | [5 empty] | 2025-03-21 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3330 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 04/03: Sent for Sign off. | 2026-01-09 | N | 03. FPR |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 04/03 | Build in progress. Requirements are not clearly defined. ETA is TBD |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-01-26 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRE1661_IF | 04.Enhancement | 02.IF - Intel Foundry | WBS transfer tool | 03. FPR | 3.11 FPR - Project Accounting | 09. FUT Overdue | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2026-01-07 | 100% | 2025-12-10 | 2025-08-18 | 2025-08-22 | 2026-02-04 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | 2025-12-08 | 2026-01-09 | 2026-02-04 | 100% | 2026-01-26 | [15 empty] | 2026-01-26 | 2026-01-26 | No |  | 2026-03-20 | 2026-03-20 |  | 100% | 90% |  |  |  | 04. Completed | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-20 | N | 95% | 2026-03-20 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-10-16 07:16 | cell-link@smartsheet.com | 2026-04-07 22:40 | 9 | 2025-01-11 | 01.S4 | FPRE1661_IP | 02.High | 0.4 | 0.4 | 1661 |  | R3 ITC1 | [6 empty] | 2025-12-10 | 2026-01-07 | 2025-12-10 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 |  | 2026-01-26 | 2026-02-04 | 2026-01-26 | 2026-01-26 | [12 empty] | 2026-01-26 | 2026-01-26 |  |  |  | 2026-03-20 | 2026-03-20 | [5 empty] | 2025-03-21 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 |  | 3329 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 04/08: 50% FUT Done , Defcet 8888 still open , will be addressed and rest testing will be completed and signoff by 04/08. | 2026-01-09 | N | 03. FPR |  |  |  | 03/24 : FUT in progress. ETA to share for approval is 04/03 | Build in progress. Requirements are not clearly defined. ETA is TBD |  | On track for S23+ | Awaiting approval | Delayed - Past Sprint | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-01-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2668 | FPRE1660 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for Revenue Recognition by Stage postings for Product/Services Sale​ - RMA | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-11-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2668_FPR_DC-100-020-Revenue%20Recognition%20by%20Stage%20for%20Product%20%26%20Services%20Sale.pptx?d=w6b44b42a54df4086a47f1d4d0ce22b33&csf=1&web=1&e=doKT0x |  |  |  | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-12-03 | 100% | 2025-11-18 | 2025-09-19 | 2025-09-26 | 2025-12-12 | 100% | 2026-01-29 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-29 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 | No |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-26 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-10-16 02:12 | cell-link@smartsheet.com | 2026-03-09 01:06 | 10 | 2025-02-17 | 01.S4 |  |  | 2 | 2 | 1660 |  | R3 ITC1 | [6 empty] | 2025-11-18 | 2025-12-03 | 2025-11-18 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-26 | 2026-03-04 | 2026-02-26 | [5 empty] | 2025-03-21 | 2026-01-09 |  |  | 2026-03-04 |  |  |  | 0 | 08. Not Applicable | 3327 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/26: FUT doc shared with Mani , she will do the walkthough with Stacey. | 2026-01-09 | N | 03. FPR |  |  |  | 1209: Add to S21 plan. Already approved spec, no change needed |  |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2668 | FPRE1659 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for Revenue Recognition by Stage postings for Product/Services Sale​ - POC / PIT | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-11-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2668_FPR_DC-100-020-Revenue%20Recognition%20by%20Stage%20for%20Product%20%26%20Services%20Sale.pptx?d=w6b44b42a54df4086a47f1d4d0ce22b33&csf=1&web=1&e=doKT0x |  |  |  | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-12-03 | 100% | 2025-11-18 | 2025-09-19 | 2025-09-26 | 2025-12-12 | 100% | 2026-01-06 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-06 | 2025-12-08 | 2026-01-09 | 2026-01-07 | 100% | 2026-01-06 | [15 empty] | 2026-01-06 | 2026-01-06 | No |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-10-16 02:12 | cell-link@smartsheet.com | 2026-02-20 06:32 | 10 | 2025-02-17 | 01.S4 |  |  | 2 | 2 | 1659 |  | R3 ITC1 | [6 empty] | 2025-11-18 | 2025-12-03 | 2025-11-18 |  | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 2026-01-06 | 2026-01-09 | 2026-01-06 | 2026-01-06 | [12 empty] | 2026-01-06 | 2026-01-06 |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | [5 empty] | 2025-03-21 | 2026-01-09 |  |  | 2026-02-04 |  |  |  | 0 | 08. Not Applicable | 3328 | [7 empty] | 1. On Track | 1. Approved no action | 02/20: Intel approved | 2026-01-09 | N | 03. FPR |  |  |  | 1209: Add to S21 plan. Already approved spec, no change needed | S22 Week2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-09 | 2026-01-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE1650_IP | 04.Enhancement | 01.IP - Intel Product | (FTQ Input to drive Disaggregation to Allocation Cycle) for Forecast.​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-11-05 | 100% | 2025-10-23 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-01-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-07 07:51 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 1650 |  | R3 ITC1 | [6 empty] | 2025-10-23 | 2025-11-05 | 2025-10-23 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-20 | 2026-02-04 | 2026-01-20 | [5 empty] | 2025-03-21 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3320 | [7 empty] | 4. Completed | 1. Approved no action | 01/19: Conditionally Approved. | 2025-12-05 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/15 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE1650_IF | 04.Enhancement | 02.IF - Intel Foundry | (FTQ Input to drive Disaggregation to Allocation Cycle) for Forecast.​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-11-05 | 100% | 2025-10-23 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-04 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-10-07 07:51 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-01 | 01.S4 | FPRE1650_IP | 03.Medium | 0.2 | 0.2 | 1650 |  | R3 ITC1 | [6 empty] | 2025-10-23 | 2025-11-05 | 2025-10-23 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | [5 empty] | 2025-03-21 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3321 | [7 empty] | 1. On Track | 1. Approved no action | 02/04: FUT Approved | 2025-12-05 | N | 03. FPR |  |  |  |  | S22 Week2 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3094 | FPRE1620_IP | 04.Enhancement | 01.IP - Intel Product | Implement OSS Note 2358961 to allow COGS split based on Aux CCS at time of delivery/PGI transaction. | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 99. Rejected/Cancelled/On Hold | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/ID_3094_COGS%20Split%20break%20up%20as%20per%20CCS%20durign%20the%20PGI.pptx?d=w17adada1ab4c48c8a153860afffd7636&csf=1&web=1&e=nWbvui | 02.No | 01.Yes |  |  |  | 04.Cancelled |  | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 |  | 0% | 2025-10-08 |  |  |  | 0% |  | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | [14 empty] | 2025-11-10 | 2025-12-03 |  | Y | 0% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 |  | 01.S4 |  |  | 1 | 1 | 1620 | INT-CR1009 | R3 ITC1 | [7 empty] | 2025-10-08 | [7 empty] | 2026-01-09 | [19 empty] | 2025-12-03 | [6 empty] | 2025-10-08 | 2026-01-09 |  |  | 2025-12-03 |  |  |  | 0 |  | 3272 | [10 empty] | 2026-01-09 | Y | 03. FPR | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3094 | FPRE1620_IF | 04.Enhancement | 02.IF - Intel Foundry | Implement OSS Note 2358961 to allow COGS split based on Aux CCS at time of delivery/PGI transaction. | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 99. Rejected/Cancelled/On Hold | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/ID_3094_COGS%20Split%20break%20up%20as%20per%20CCS%20durign%20the%20PGI.pptx?d=w17adada1ab4c48c8a153860afffd7636&csf=1&web=1&e=nWbvui | 02.No | 01.Yes |  |  |  | 04.Cancelled |  | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-08 |  | 0% | 2025-10-08 |  |  |  | 0% |  | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | 2025-12-08 | 2026-01-09 |  | 0% | 2026-01-09 | [15 empty] | 2026-01-09 | 2026-01-09 | [14 empty] | 2025-11-10 | 2025-12-03 |  | Y | 0% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2026-01-09 | 2026-01-09 | 2026-01-09 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 99 |  | 01.S4 | FPRE1620_IP | 03.Medium | 0.2 | 0.2 | 1620 | INT-CR1009 | R3 ITC1 | [7 empty] | 2025-10-08 | [7 empty] | 2026-01-09 | [19 empty] | 2025-12-03 | [6 empty] | 2025-10-08 | 2026-01-09 |  |  | 2025-12-03 |  |  |  | 0 |  | 3275 | [10 empty] | 2026-01-09 | Y | 03. FPR | [8 empty] | N/A | R3 Build & UT Sprint 21 |  | 2026-01-09 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2470 | FPRE1600 | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori app - Create WBS Element Request Form with ALV Input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2470_FPR_DC-050-500-Custom%20Fiori%20App%20-%20WBS%20Element%20Request%20%20Form%20with%20ALV%20input%E2%80%8B.pptx?d=wfb78e17c71e44c3a9dfa0a142636bd9a&csf=1&web=1&e=ySn6uP | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-09-10 | 100% | 2025-09-09 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-09-24 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1600 |  | R3 ITC1 | [6 empty] | 2025-09-09 | 2025-09-10 | 2025-09-09 |  | 2025-09-16 | 2025-09-16 | 2025-09-16 |  | 2025-09-16 | 2025-10-08 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2025-03-21 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 1889 | [7 empty] | 1. On Track | 1. Approved no action | 12/08: Conditionally Approved. | 2025-10-08 | N | 03. FPR |  |  |  |  | 1119: ETA 1125 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3080 | FPRE1599_IP | 04.Enhancement | 01.IP - Intel Product | Update existing custom table ZTFPR_ACRENG02 to store the calculation of PO line items accrual details that will be used for ECA reports | 03. FPR | 3.1 FPR - GL Close & Consolidate | 09. FUT Overdue | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3080%20-%20Update%20existing%20custom%20table%20ZTFPR_ACRENG02%20to%20store%20the%20calculation%20of%20PO%20line%20items%20accrual%20details%20that%20will%20be%20used%20for%20ECA%20reports%201.pptx?d=w1d4d444052754e048f0c4d52f646b864&csf=1&web=1&e=bq4hAo | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-26 | 2025-11-10 | 2025-12-05 | 2025-11-13 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-27 | 2026-03-27 |  | 50% | 60% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 55% | 2026-03-27 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | sdeolalikar@deloitte.com | 2026-04-07 07:38 | 9 | 2025-10-10 | 01.S4 |  |  | 1 | 1 | 1599 | INT-CR0685 | R3 ITC1 | [6 empty] | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  |  | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3250 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 04/07: Defects 8597, 8629 raised with Tech Team. Prathiba is working on the defects raised for this and ETA is tomorrow. | 2025-12-05 | N | 03. FPR |  |  |  | 0407: CR160 being implemented related to PAT objects (320-322). Defect fixes in progress. FUT ETA 04/17 | PAT CR will be completed by 3/13. Post the CR, this object will be picked up for build. ETA is 3/20. FUT ETA is 3/27 | 2. Risk | At risk for S23+ | Defects | Delayed - Past Sprint | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3080 | FPRE1599_IF | 04.Enhancement | 02.IF - Intel Foundry | Update existing custom table ZTFPR_ACRENG02 to store the calculation of PO line items accrual details that will be used for ECA reports | 03. FPR | 3.1 FPR - GL Close & Consolidate | 09. FUT Overdue | Y | 2025-10-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3080%20-%20Update%20existing%20custom%20table%20ZTFPR_ACRENG02%20to%20store%20the%20calculation%20of%20PO%20line%20items%20accrual%20details%20that%20will%20be%20used%20for%20ECA%20reports%201.pptx?d=w1d4d444052754e048f0c4d52f646b864&csf=1&web=1&e=bq4hAo | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-26 | 2025-11-10 | 2025-12-05 | 2025-11-13 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-27 | 2026-03-27 |  | 50% | 60% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 55% | 2026-03-27 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-11 01:04 | sdeolalikar@deloitte.com | 2026-04-07 07:38 | 9 | 2025-10-10 | 01.S4 | FPRE1599_IP | 03.Medium | 0.2 | 0.2 | 1599 | INT-CR0685 | R3 ITC1 | [6 empty] | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  |  | 2026-03-27 | 2026-03-27 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3252 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 04/07: Defects 8597, 8629 raised with Tech Team. Prathiba is working on the defects raised for this and ETA is tomorrow. | 2025-12-05 | N | 03. FPR |  |  |  | 0407: CR160 being implemented related to PAT objects (320-322). Defect fixes in progress. FUT ETA 04/17 | PAT CR will be completed by 3/13. Post the CR, this object will be picked up for build. ETA is 3/20. FUT ETA is 3/27 | 2. Risk | At risk for S23+ | Defects | Delayed - Past Sprint | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3015 | FPRE1564 | 04.Enhancement | 01.IP - Intel Product | Employee Notification for timesheet entry | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3015_IP%20Intel%20Federal%20Employee%20Notification%20for%20Timesheet%20Entry.pptx?d=w350b5a2a8546425fb205f1c54c357f71&csf=1&web=1&e=l8Kugv | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-10 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-11-03 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | 2025-11-10 | 2025-11-05 | 2025-11-05 | 100% | 2025-11-03 | [15 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-14 | 01.S4 |  |  | 1 | 1 | 1564 |  | R3 ITC1 | [6 empty] | 2025-09-10 | 2025-09-10 | 2025-09-10 |  | 2025-11-03 | 2025-11-03 | 2025-11-03 |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | 2025-11-03 | [12 empty] | 2025-11-03 | 2025-11-03 |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | [5 empty] | 2025-09-10 | 2025-11-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3192 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/05: Defect 5174 is closed. Approval receieved from Karen. | 2025-11-05 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-11-03 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3014 | FPRE1563 | 04.Enhancement | 01.IP - Intel Product | Manager notification for timesheet approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3014_IP%20Intel%20Federal%20Manager%20Notification%20for%20Timesheet%20Approval.pptx?d=wb71a6495854e4c7595e2948a6360d8c0&csf=1&web=1&e=w78OLj | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-10-09 | 2025-09-24 | 2025-10-01 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-14 | 01.S4 |  |  | 1 | 1 | 1563 |  | R3 ITC1 | [6 empty] | 2025-10-09 | 2025-10-09 | 2025-10-09 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3191 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/16: Defect 6125 is Re-open, 6124 is open. Tech team is working on it. | 2025-12-05 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3013 | FPRE1562 | 04.Enhancement | 01.IP - Intel Product | Manage Delegates for approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3013_IP%20Intel%20Federal%20Manage%20Delegates%20for%20Approval.pptx?d=wf913da8e2dc542aa89d831083c2ed284&csf=1&web=1&e=7uGIji | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-22 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-12-24 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-20 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | automation@smartsheet.com | 2026-02-20 06:42 | 10 | 2025-08-14 | 01.S4 |  |  | 1 | 1 | 1562 |  | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-09-10 | 2025-08-22 | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | [5 empty] | 2025-09-10 | 2025-11-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3190 | [7 empty] | 4. Completed | 1. Approved no action | 02/20: FUT Approved. | 2025-11-05 | N | 03. FPR |  |  |  |  | S22 Week2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3012 | FPRE1561 | 04.Enhancement | 01.IP - Intel Product | Timesheet approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3012_IP%20Intel%20Federal%20Timesheet%20Approval.pptx?d=wa8d7b37181a448cb92265cbcc933f1a9&csf=1&web=1&e=q86TMY | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-22 | 2025-11-10 | 2025-11-11 | 2025-11-11 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-14 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-14 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-14 | 01.S4 |  |  | 2 | 2 | 1561 |  | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-09-10 | 2025-08-22 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2025-09-10 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3189 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/08: Waiting on approval from Erica. Will get by 12/8 | 2025-12-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3011 | FPRE1560 | 04.Enhancement | 01.IP - Intel Product | Timesheet entry for Intel Federal employees | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-08-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3011_IP%20Intel%20Federal%20Timesheet%20Entry.pptx?d=w4193104cabac4a378762e6ba8d222d5c&csf=1&web=1&e=lKhaGa | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-22 | 2025-10-13 | 2025-10-17 | 2025-10-17 | 100% | 2025-12-31 | 2025-10-20 | 2025-11-21 | 2025-11-21 | 100% | 2025-12-05 | 2025-09-15 | 2025-10-08 | 2025-11-21 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 |  |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-03-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 23 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-07-24 03:57 | automation@smartsheet.com | 2026-03-02 01:28 | 10 | 2025-08-14 | 01.S4 |  |  | 4 | 4 | 1560 |  | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-09-10 | 2025-08-22 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | [5 empty] | 2025-09-10 | 2025-10-08 |  |  | 2026-02-04 |  |  |  | 0 |  | 3188 | [7 empty] | 4. Completed | 1. Approved no action | 03/02: Conditionally Approved. | 2025-10-08 | N | 03. FPR |  |  |  |  | S23 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2470 | FPRE1553 | 04.Enhancement | 01.IP - Intel Product | Custom Fiori app - Change WBS Element Request Form with ALV Input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2470_FPR_DC-050-500-Custom%20Fiori%20App%20-%20WBS%20Element%20Request%20%20Form%20with%20ALV%20input%E2%80%8B.pptx?d=wfb78e17c71e44c3a9dfa0a142636bd9a&csf=1&web=1&e=ySn6uP | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-12-05 | 100% | 2025-12-08 | 2025-09-19 | 2025-09-26 | 2025-10-14 | 100% | 2025-11-13 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-13 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | jenoronha@deloitte.com | 2025-07-17 05:27 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1553 |  | R3 ITC1 | [5 empty] | 2025-12-08 | 2025-12-08 | 2025-12-05 | 2025-11-28 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-03-21 | 2025-10-31 |  |  | 2025-12-03 |  |  |  | 0 | 08. Not Applicable | 3179 | [7 empty] | 1. On Track | 4. Smartsheet Hygiene(5.1) | 01/12: Minor defects exists with Fiori team. 6186 (New Defect). Team will get conditional approval from Doris on Monday. | 2025-10-31 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-11-13 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1519_IP | 04.Enhancement | 01.IP - Intel Product | Project Change Order - Edit and Submit of draft request with change functionality of Project Change Order | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | cell-link@smartsheet.com | 2026-03-09 01:06 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 1519 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2026-02-27 | 2026-03-04 | 2026-02-27 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3132 | [7 empty] | 2. At Risk | 1. Approved no action | 02/26: Conditionally Approved by Steven | 2025-12-05 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1519_IF | 04.Enhancement | 02.IF - Intel Foundry | Project Change Order - Edit and Submit of draft request with change functionality of Project Change Order | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 | No |  | 2026-03-02 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-02-27 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | cell-link@smartsheet.com | 2026-03-09 01:06 | 10 | 2024-12-11 | 01.S4 | FPRE1519_IP | 02.High | 0.4 | 0.4 | 1519 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-02-27 | 2026-03-04 | 2026-02-27 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-03-04 |  |  |  | 0 |  | 3130 | [7 empty] | 2. At Risk | 1. Approved no action | 02/26: Conditionally Approved by Steven | 2025-12-05 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1518_IP | 04.Enhancement | 01.IP - Intel Product | Project Change Order - Change existing Purchase Orders during creation of Project Change Order in custom app | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 1518 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3135 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/12: Fiori team is working on the defect. | 2025-12-05 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1518_IF | 04.Enhancement | 02.IF - Intel Foundry | Project Change Order - Change existing Purchase Orders during creation of Project Change Order in custom app | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-10 | 2025-10-17 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE1518_IP | 02.High | 0.4 | 0.4 | 1518 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3134 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 01/12: Fiori team is working on the defect. | 2025-12-05 | N | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1517_IP | 04.Enhancement | 01.IP - Intel Product | Project Change Order - Create Purchase Orders during creation of Project Change Order in custom app | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-22 | 2025-10-29 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 1517 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3133 | [7 empty] | 4. Completed | 1. Approved no action | 01/09: FUT Approved. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE1517_IF | 04.Enhancement | 02.IF - Intel Foundry | Project Change Order - Create Purchase Orders during creation of Project Change Order in custom app | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-22 | 2025-10-29 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 21:25 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE1517_IP | 02.High | 0.4 | 0.4 | 1517 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3131 | [7 empty] | 4. Completed | 1. Approved no action | 01/09: FUT Approved. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRE1516_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to enable user decision action to be taken from email directly for project creation workflow | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 04:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1516 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-02-02 | 2026-02-04 | 2026-02-02 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3129 | [7 empty] | 3. Off Track | 17. FUT In progress | 01/30: Testing Complete , walkthrough planned for today. Expecting the sign-off. | 2025-12-05 | N | 03. FPR |  |  |  |  | S22 Week 3 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRE1516_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to enable user decision action to be taken from email directly for project creation workflow | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-02 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | [15 empty] | 2025-12-02 | 2025-12-02 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-02 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 04:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE1516_IP | 03.Medium | 0.2 | 0.2 | 1516 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 | [12 empty] | 2025-12-02 | 2025-12-02 |  |  | 2026-02-02 | 2026-02-04 | 2026-02-02 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-02-04 |  |  |  | 0 |  | 3128 | [7 empty] | 3. Off Track | 17. FUT In progress | 01/30: Testing Complete , walkthrough planned for today. Expecting the sign-off. | 2025-12-05 | N | 03. FPR |  |  |  |  | S22 Week 3 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRE1515_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to display popup screen to trigger project creation workflow | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 04:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1515 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3127 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: Intel requested the walkthrough on Monday. Doris will be back and will approve it. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2467 | FPRE1515_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to display popup screen to trigger project creation workflow | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2467_FPR_DC-050-500-Approval%20for%20project%20creation%20and%20create%20a%20project%20definition%20and%20level%201%20after%20approval%20using%20template%E2%80%8B.pptx?d=w4da231627f994ad999b112a8738a94c2&csf=1&web=1&e=eRRbeb | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-13 | 2025-10-17 | 2025-10-24 | 2025-11-20 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-06 | [15 empty] | 2025-12-06 | 2025-12-06 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-09 04:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE1515_IP | 03.Medium | 0.2 | 0.2 | 1515 |  | R3 ITC1 | [6 empty] | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | [12 empty] | 2025-12-06 | 2025-12-06 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  |  |  | 0 |  | 3126 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/12: Intel requested the walkthrough on Monday. Doris will be back and will approve it. | 2025-12-05 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-06 | 2025-12-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1513_IP | 04.Enhancement | 01.IP - Intel Product | Generate and download JV file for JE posting | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | jenoronha@deloitte.com | 2026-03-05 07:53 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1513 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3113 | [7 empty] | 4. Completed | 1. Approved no action | 01/12: FUT Approved. | 2025-12-05 | Y | 03. FPR |  |  |  |  | 12/09 - Watch item for 12/11. Build completion, check in Nishant's file |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1513_IF | 04.Enhancement | 02.IF - Intel Foundry | Generate and download JV file for JE posting | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | jenoronha@deloitte.com | 2026-03-05 07:53 | 10 | 2024-12-11 | 01.S4 | FPRE1513_IP | 03.Medium | 0.2 | 0.2 | 1513 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3116 | [7 empty] | 4. Completed | 1. Approved no action | 01/12: FUT Approved. | 2025-12-05 | Y | 03. FPR |  |  |  |  | 12/09 - Watch item for 12/11. Build completion, check in Nishant's file |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1513_CFIN | 04.Enhancement | 05.CFIN | Generate and download JV file for JE posting | 03. FPR | 3.2 FPR - Tax | 99. Rejected/Cancelled/On Hold | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 04.Cancelled |  | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-10 | 2025-10-17 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  |  | 2025-12-03 |  |  | 100% |  |  |  |  | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-03-06 | Not Applicable | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 99 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1513 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3114 | [7 empty] | 4. Completed | 5. Object to be Cancelled | 01/12: Sathya is working with the Business to cancel this. 03/04 - Object cancelled - CRID - INT-CR1482 | 2025-12-05 | Y | 03. FPR | [7 empty] | Incorrect plan | N/A | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1512_IP | 04.Enhancement | 01.IP - Intel Product | Query confirm ITT document to determine the Capital/Expense and tax code manual for each of the transactions | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1512 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 3119 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect 4201 is open also Fiori launchpad is down | 2025-12-05 | Y | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1512_IF | 04.Enhancement | 02.IF - Intel Foundry | Query confirm ITT document to determine the Capital/Expense and tax code manual for each of the transactions | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 | FPRE1512_IP | 03.Medium | 0.2 | 0.2 | 1512 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 3121 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect 4201 is open also Fiori launchpad is down | 2025-12-05 | Y | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1511_IP | 04.Enhancement | 01.IP - Intel Product | Query existing draft ITT document and make changes | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1511 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 3122 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect 4200 is open also Fiori launchpad is down. Sathya to check with Pragya and get latest information. | 2025-11-05 | Y | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1511_IF | 04.Enhancement | 02.IF - Intel Foundry | Query existing draft ITT document and make changes | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-31 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 | FPRE1511_IP | 03.Medium | 0.2 | 0.2 | 1511 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-11-05 |  |  |  | 0 |  | 3124 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect 4200 is open also Fiori launchpad is down. Sathya to check with Pragya and get latest information. | 2025-11-05 | Y | 03. FPR | [7 empty] | Defects | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1510_IP | 04.Enhancement | 01.IP - Intel Product | ITT document creation | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-03 | 2025-10-03 | 2025-10-03 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 1510 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-10-03 |  |  | 2025-11-05 |  |  |  | 0 |  | 3125 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect is fixed and FUT in progress. | 2025-10-03 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-07 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE1510_IF | 04.Enhancement | 02.IF - Intel Foundry | ITT document creation | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2025-10-03 | 100% | 2025-10-07 | [15 empty] | 2025-10-07 | 2025-10-07 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-07-04 06:20 | tanhan@deloitte.com | 2026-03-04 17:53 | 10 | 2024-12-11 | 01.S4 | FPRE1510_IP | 03.Medium | 0.2 | 0.2 | 1510 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | 2025-10-07 | [12 empty] | 2025-10-07 | 2025-10-07 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-08-13 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 |  | 3112 | [7 empty] | 4. Completed | 1. Approved no action | 11/06: Defect is fixed and FUT in progress. | 2025-10-08 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 514 | FPRE1448 | 04.Enhancement | 05.CFIN | FIORI screen to take care of TPR Display/ Change/ cancellation options | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B580759F0-2843-4492-8FD6-A28C3D42DDD4%7D&file=MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_TPR.pptx&wdLOR=c7E05ECCF-D468-4A49-BAFB-569FEF939098&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRI0224 | 2024-05-21 | Shane Bethune | 01.Approved | 2024-05-31 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-06-16 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-09-15 | 2025-09-19 | 2025-08-21 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | 2025-09-29 | 2025-10-10 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-14 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-05-19 21:54 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 1448 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-19 | 2025-09-09 |  | 2025-09-09 | 2025-10-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | [5 empty] | 2025-07-11 | 2025-10-10 |  |  | 2025-11-07 |  |  |  | 0 | 06. Banks | 3040 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/13 EP: Confirm if FUT has been conditionally signed off/approved 11/12: Sent for Conditional Signoff along with 240 as child Object. | 2025-10-10 | N | 03. FPR |  |  |  | Awaiting Approval 1211 |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1586 | FPRE1443 | 04.Enhancement | 05.CFIN | FIORI screen to take care of TFR Display/ Change/ cancellation options | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_CFR.pptx?d=wde49673c21924b2c82c2fb99e792c491&csf=1&web=1&e=W3IPRW | 02.No | 01.Yes | FPRI0224 | 2025-05-08 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-03 | 2025-07-14 | 2025-07-18 | 2025-08-01 | 100% | 2025-08-08 | 2025-07-21 | 2025-08-01 | 2025-08-13 | 100% | 2025-08-08 | 2025-07-21 | 2025-08-01 | 2025-08-13 | 100% | 2025-08-08 | [15 empty] | 2025-08-08 | 2025-08-08 |  |  | 2025-09-10 | 2025-10-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-10-03 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-01 | 2025-08-01 | 2025-08-01 | jenoronha@deloitte.com | 2025-05-08 02:50 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-09 | 01.S4 |  |  | 1 | 1 | 1443 |  | R3 ITC1 | [6 empty] | 2025-06-03 | 2025-06-13 | 2025-06-03 |  | 2025-08-08 | 2025-08-08 | 2025-08-08 |  | 2025-08-08 | 2025-08-13 | 2025-08-08 | 2025-08-08 | [12 empty] | 2025-08-08 | 2025-08-08 |  |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | [5 empty] | 2025-06-13 | 2025-08-01 |  |  | 2025-09-10 |  |  |  | 0 |  | 3012 | [9 empty] | 09/26: FUT Approved. | 2025-08-01 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2900 | FPRE1438 | 04.Enhancement | 02.IF - Intel Foundry | Update mixing ratio for Procurement alternative for Cross site transfer based on production volume from BY | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2900_FPR_RICEFW%20Intake%20Form_Enhancement%20Cross%20Site%20transfer%20%20Mixed%20costing.pptx?d=wcb64a67c627e48e7b0d11e48c0936159&csf=1&web=1&e=8LEipN | 02.No | 01.Yes |  | 2025-04-29 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-11 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-17 | 2025-08-21 | 100% | 2025-08-21 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-05 | 2025-10-27 | 2025-11-07 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-04-29 03:20 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1438 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-21 | 2025-10-17 |  |  | 2025-09-05 | 2025-11-07 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-07-11 | 2025-11-07 |  |  | 2025-12-05 |  |  |  | 0 |  | 3000 | [7 empty] | 1. On Track | 1. Approved no action | 01/12: FUT Approved. | 2025-11-07 | Y | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-07 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2900 | FPRE1419 | 04.Enhancement | 02.IF - Intel Foundry | Update Procurement alternatives based on production version & PIR for cross site transfer scenario | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2900_FPR_RICEFW%20Intake%20Form_Enhancement%20Cross%20Site%20transfer%20%20Mixed%20costing.pptx?d=wcb64a67c627e48e7b0d11e48c0936159&csf=1&web=1&e=8LEipN | 02.No | 01.Yes |  | 2025-04-29 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-09-29 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 | No |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2025-04-18 05:48 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 1419 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 |  | 2025-09-29 | 2025-10-03 | 2025-09-29 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | [5 empty] | 2025-06-13 | 2025-10-03 |  |  | 2025-12-05 |  |  |  | 0 |  | 2969 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/08: Working with Tech team to fix the dump for additional scenarios. | 2025-10-03 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-03 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2063 | FPRE1328 | 04.Enhancement | 01.IP - Intel Product | Legal Valuation standard cost calculation enhancement | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 99. Rejected/Cancelled/On Hold | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2063_FPR_RICEFW%20Intake%20Form_%20Enhancement%20for%20Legal%20Valuation%20Standard%20Cost%20calculation.pptx?d=w38465b28f4c4431ea9eb20f46fc364b6&csf=1&web=1&e=el6PnZ | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 04.Cancelled | 2024-10-10 | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-18 | 2025-04-18 | 2025-03-25 | 100% | 2025-03-27 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-03-27 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-03-27 | [15 empty] | 2025-03-27 | 2025-03-27 | Yes | [13 empty] | 2025-09-15 | 2025-10-08 |  | Y | 0% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 99 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 1328 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 |  | 2025-03-27 | 2025-05-16 | 2025-03-27 | 2025-03-27 | [12 empty] | 2025-03-27 | 2025-03-27 |  |  |  | 2025-10-08 | [6 empty] | 2025-02-21 | 2025-05-16 |  |  | 2025-10-08 |  |  |  | 0 | 08. Not Applicable | 2704 | [7 empty] | 1. On Track | 3. Awaiting Approval | 08/25 - Dev In progress | 2025-05-16 | N | 03. FPR | [8 empty] | N/A | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2668 | FPRE1239 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for Revenue Recognition by Stage postings for Product/Services Sale​ - Accrual Posting / COPA | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-11-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2668_FPR_DC-100-020-Revenue%20Recognition%20by%20Stage%20for%20Product%20%26%20Services%20Sale.pptx?d=w6b44b42a54df4086a47f1d4d0ce22b33&csf=1&web=1&e=doKT0x |  |  |  | 2025-02-10 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-24 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2026-01-29 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2026-01-29 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2026-01-29 | [15 empty] | 2026-01-29 | 2026-01-29 | No |  | 2026-01-23 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-06 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2025-02-07 07:16 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-17 | 01.S4 |  |  | 2 | 2 | 1239 |  | R3 ITC1 | [6 empty] | 2025-03-24 | 2025-03-24 | 2025-03-24 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | [12 empty] | 2026-01-29 | 2026-01-29 |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | [5 empty] | 2025-03-21 | 2025-10-31 |  |  | 2026-02-04 |  |  |  | 0 | 08. Not Applicable | 2043 | [7 empty] | 4. Completed | 6. FUT Defect Under Fix | 02/05: 6916 is Fixed, Pranav to continue on the FUT. 6980 for Error handling is still open. | 2025-10-31 | N | 03. FPR |  |  |  |  | S22 Week2 Target |  |  | Defects | Complete | R3 Build & UT Sprint 22 |  | 2026-01-29 | 2026-01-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2794 | FPRE1235_IP | 04.Enhancement | 01.IP - Intel Product | Add custom fields to CJI3 and CJI5 reports (SAP S/4HANA Project Systems module).​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA385DDCF-66AD-402F-BA08-CA25CAF99424%7D&file=2794_FPR_DC-050-640_PS%20Report%20Custom%20Fields%20Enhancement%20RICEFW.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-02-05 | shane.bethune@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-10 | 2025-06-09 | 2025-06-13 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-07 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-02-03 06:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-11 | 01.S4 |  |  | 1 | 1 | 1235 |  | R3 ITC1 | [6 empty] | 2025-03-10 | 2025-03-21 | 2025-03-10 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  | Federal |  | 0 |  | 1716 | [9 empty] | 08/18 - Defect 1878 is with Tech team. | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2794 | FPRE1235_IF | 04.Enhancement | 02.IF - Intel Foundry | Add custom fields to CJI3 and CJI5 reports (SAP S/4HANA Project Systems module).​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA385DDCF-66AD-402F-BA08-CA25CAF99424%7D&file=2794_FPR_DC-050-640_PS%20Report%20Custom%20Fields%20Enhancement%20RICEFW.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-02-05 | shane.bethune@intel.com | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-10 | 2025-06-09 | 2025-06-13 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-14 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-14 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-02-04 07:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-11 | 01.S4 | FPRE1235_IP | 03.Medium | 0.2 | 0.2 | 1235 |  | R3 ITC1 | [6 empty] | 2025-03-10 | 2025-03-21 | 2025-03-10 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  | Federal |  | 0 |  | 1715 | [9 empty] | 08/18 - FUT Approved. Smartsheet will be updated by sub team. | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2803 | FPRE1209 | 04.Enhancement | 01.IP - Intel Product | Upload adjustments to time sheet entries in bulk for Intel Federal. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-02-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2803_FPR_DC-050-680B_Intel%20Federal%20SAP%20Timekeeping%20Bulk%20Upload%20RICEFW_r1.pptx?d=w43613494cff14939ad1013ff0e665570&csf=1&web=1&e=NhOwyx | 02.No | 01.Yes |  | 2025-02-05 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-12-31 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-31 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 | No | 2025-11-05 | 2025-11-05 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-17 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-07 | 01.S4 |  |  | 2 | 2 | 1209 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | [5 empty] | 2025-03-21 | 2025-11-05 |  |  | 2025-11-05 |  | Federal |  | 0 |  | 1722 | [7 empty] | 1. On Track | 1. Approved no action | 11/17 - FUT approved. | 2025-11-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2173 | FPRE1104_IP | 04.Enhancement | 01.IP - Intel Product | WBS with custom attributes will be created in the PS module. The master data from S4 will be loaded along with the custom attributes using the custom Built CDS view. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2173_FPR_WBS%20Masterdata%20Import%20into%20SAC%20using%20Custom%20CDS.pptx?d=we105213affc345ab9abaf4a78bcb06ee&csf=1&web=1&e=NvfYCu | 02.No | 01.Yes |  | 2025-01-22 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-15 | 2025-07-14 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-23 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-26 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jonsanders@deloitte.com | 2025-01-16 12:46 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-01-23 | 01.S4 |  |  | 2 | 2 | 1104 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-18 | 2025-04-15 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-15 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 | 08. Not Applicable | 2752 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: FUT approved by INTEL IT. Business will approved by US time. | 2025-08-15 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2173 | FPRE1104_IF | 04.Enhancement | 02.IF - Intel Foundry | WBS with custom attributes will be created in the PS module. The master data from S4 will be loaded along with the custom attributes using the custom Built CDS view. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-01-22 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2173_FPR_WBS%20Masterdata%20Import%20into%20SAC%20using%20Custom%20CDS.pptx?d=we105213affc345ab9abaf4a78bcb06ee&csf=1&web=1&e=NvfYCu | 02.No | 01.Yes |  | 2025-01-22 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-15 | 2025-07-14 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-23 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | 2025-08-01 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-26 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | jenoronha@deloitte.com | 2025-03-04 07:01 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-01-23 | 01.S4 | FPRE1104_IP | 02.High | 0.4 | 0.4 | 1104 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-18 | 2025-04-15 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-15 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 | 08. Not Applicable | 2753 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: FUT approved by INTEL IT. Business will approved by US time. | 2025-08-15 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRE1025_IP | 04.Enhancement | 01.IP - Intel Product | Custom Fiori app will be created using Free style model to display WBS/AUC required data to process WBS intercompany and intracompany transfers, | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 | No |  | 2025-10-08 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-19 13:32 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-11 | 01.S4 |  |  | 1 | 1 | 1025 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 |  | 2761 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/31: Extended call scheduled today and will be closed today. | 2025-09-12 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2475 | FPRE1025_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori app will be created using Free style model to display WBS/AUC required data to process WBS intercompany and intracompany transfers, | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/Intake%20Deck/AMT%20(WBS%20Cost%20Transfer)%20Enhancement%20(3).pptx?d=w11efec8b3a694b1899c32771bc6c1dae&csf=1&web=1&e=CfHHNB | 02.No | 01.Yes |  | 2024-12-20 | Shane Bethune | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 | No |  | 2025-10-08 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jonsanders@deloitte.com | 2024-12-19 13:32 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-11 | 01.S4 | FPRE1025_IP | 03.Medium | 0.2 | 0.2 | 1025 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 2025-08-22 | 2025-09-12 | 2025-08-22 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-11-03 | 2025-11-05 | 2025-11-03 | [5 empty] | 2025-04-18 | 2025-08-15 |  |  | 2025-09-11 |  |  |  | 0 |  | 2760 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/31: Extended call scheduled today and will be closed today. | 2025-09-12 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2424 | FPRE0942_IP | 04.Enhancement | 01.IP - Intel Product | Interface of SAP PPM module to ATLAS | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2424_FPR_DC-050-300_PPM%20Interface%20with%20Atlas.pptx?d=wb7e49791c77b4d94899cd3c40f530986&csf=1&web=1&e=VU1tde | 02.No | 01.Yes | FPRI0981_IP | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | S4 | ATLAS | NA | 2024-12-16 | 2025-01-24 | 2025-09-10 | 100% | 2025-08-20 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-29 | 2025-04-21 | 2025-05-16 |  |  | 2025-05-16 | 2025-05-19 | 2025-06-13 |  |  | 2025-06-13 | [5 empty] | 2025-08-29 | 2025-08-29 | Yes |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-29 | 2025-08-29 | 2025-08-29 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 0942 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-09-10 | 2025-08-20 |  | 2025-08-21 | 2025-08-21 |  |  | 2025-08-29 | 2025-08-29 |  |  |  | 2025-05-16 |  |  |  | 2025-06-13 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-01 | 2025-10-10 | 2025-10-01 | [5 empty] | 2025-01-24 | 2025-08-29 | 2025-05-16 |  | 2025-10-10 |  |  |  | 0 |  | 1448 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-08-29 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2424 | FPRE0942_IF | 04.Enhancement | 02.IF - Intel Foundry | Interface of SAP PPM module to ATLAS | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2424_FPR_DC-050-300_PPM%20Interface%20with%20Atlas.pptx?d=wb7e49791c77b4d94899cd3c40f530986&csf=1&web=1&e=VU1tde | 02.No | 01.Yes | FPRI0981_IF | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No | NA | NA | S4 | ATLAS | NA | 2024-12-16 | 2025-01-24 | 2025-09-10 | 100% | 2025-08-20 | 2025-08-18 | 2025-08-18 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-29 | 2025-04-21 | 2025-05-16 |  |  | 2025-05-16 | 2025-05-19 | 2025-06-13 |  |  | 2025-06-13 | [5 empty] | 2025-08-29 | 2025-08-29 | Yes |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-29 | 2025-08-29 | 2025-08-29 | pgaroo@deloitte.com | 2024-11-20 03:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-11 | 01.S4 | FPRE0942_IP | 03.Medium | 0.2 | 0.2 | 0942 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-09-10 | 2025-08-20 |  | 2025-08-21 | 2025-08-21 |  |  | 2025-08-29 | 2025-08-29 |  |  |  | 2025-05-16 |  |  |  | 2025-06-13 | [6 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-01 | 2025-10-10 | 2025-10-01 | [5 empty] | 2025-01-24 | 2025-08-29 | 2025-05-16 |  | 2025-10-10 |  |  |  | 0 |  | 1447 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-08-29 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE0931_IP | 04.Enhancement | 01.IP - Intel Product | Rebuild Boundary Application ITT in S/4 | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-08-13 | 100% | 2025-08-14 | 2025-06-09 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jenoronha@deloitte.com | 2025-06-14 08:54 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE0931_CFIN | 02.High | 0.4 | 0.4 | 0931 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-10-09 |  |  |  | 0 |  | 3104 | [7 empty] | 2. At Risk | 17. FUT In progress | 10/10: FUT In progress, Dev team to align on number range creation. Targeted to be completed by 10/10. | 2025-07-18 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE0931_IF | 04.Enhancement | 02.IF - Intel Foundry | Rebuild Boundary Application ITT in S/4 | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-08-13 | 100% | 2025-08-14 | 2025-06-09 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | jenoronha@deloitte.com | 2025-06-14 08:54 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 | FPRE0931_CFIN | 02.High | 0.4 | 0.4 | 0931 |  | R3 ITC1 | [6 empty] | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-10-09 |  |  |  | 0 |  | 3105 | [7 empty] | 2. At Risk | 17. FUT In progress | 10/10: FUT In progress, Dev team to align on number range creation. Targeted to be completed by 10/10. | 2025-07-18 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2025 | FPRE0931_CFIN | 04.Enhancement | 05.CFIN | Rebuild Boundary Application ITT in S/4 | 03. FPR | 3.2 FPR - Tax | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR%20-%20Indirect%20Tax%20-%20ITT%20tool%20-%20RICEFW.pptx?d=w717199e94b614d779097632a02b67835&csf=1&web=1&e=Igdzb7 | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-09 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | 2025-07-18 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-20 03:23 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 0931 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-28 | 2025-03-21 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-16 | 2025-10-16 | 2025-10-16 | [5 empty] | 2025-03-28 | 2025-07-18 |  |  | 2025-10-08 |  |  |  | 0 |  | 1581 | [7 empty] | 2. At Risk | 17. FUT In progress | 10/10: FUT In progress, Dev team to align on number range creation. Targeted to be completed by 10/10. | 2025-07-18 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2398 | FPRE0929 | 04.Enhancement | 05.CFIN | Fiori UI for Counterparty Maintenance and User Exit to trigger replication to CFIN | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2398_FPR_Fiori%20UI%20for%20CounterParty.pptx?d=w9904cabb44124c04b6067ae780a716b7&csf=1&web=1&e=wC6tRx | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-04-18 | 100% | 2025-04-04 | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-06 | 2025-10-13 | 2025-11-07 | 2025-12-12 | 100% | 2025-12-13 | 2025-10-13 | 2025-11-07 | 2025-12-12 | 100% | 2025-12-13 | [15 empty] | 2025-12-13 | 2025-12-13 | No |  | 2025-12-03 | 2026-01-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-01-09 | N | 100% | 2026-01-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 21 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 02.MDG |  |  | 2 | 2 | 0929 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-18 | 2025-04-04 |  | 2025-11-06 | 2025-11-07 | 2025-11-06 |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | [12 empty] | 2025-12-13 | 2025-12-13 |  |  | 2026-01-09 | 2026-02-04 | 2026-01-09 | [5 empty] | 2025-04-18 | 2025-08-22 |  |  | 2025-10-10 |  |  |  | 0 |  | 2401 | [7 empty] | 3. Off Track | 5. Object to be Cancelled | 02/05: Akshara to check with Shreejith and raise a Cancellation CR. | 2025-11-07 | N | 03. FPR |  |  |  |  | Object Cancellation. Shane Approval pending |  |  | Incorrect plan | Complete | R3 Build & UT Sprint 21 |  | 2025-12-13 | 2025-12-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1694 | FPRE0928 | 04.Enhancement | 05.CFIN | Enhancement for automatic derivation and population of Purpose Of Payment (POP) codes in the payment file (Pain.001) required by various countries. | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-020-005_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=w41163487cefd4d919a35e77831f7412f&csf=1&web=1&e=HgJC8t | 02.No | 01.Yes |  | 2024-12-02 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-02-14 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-12-24 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-12-23 | [15 empty] | 2025-12-23 | 2025-12-23 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 0928 |  | R3 ITC1 | [6 empty] | 2025-02-14 | 2025-02-14 | 2025-02-14 | 2025-12-24 | 2025-12-24 | 2025-12-23 | 2025-12-23 |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | [12 empty] | 2025-12-23 | 2025-12-23 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-09-05 |  |  |  | 0 | 06. Banks | 2408 | [7 empty] | 1. On Track | 17. FUT In progress | 01/12: File received from Grishma yesterday. Phanni will get conditional approval today. | 2025-11-05 | N | 03. FPR |  |  |  |  | ETA is 12/12 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 21 |  | 2025-12-23 | 2025-12-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE0899_IP | 04.Enhancement | 01.IP - Intel Product | Custom Enhancement to disaggregate: Owner CC-DPN $ to WBS elements using Capex proportions WBS-level DPN across Tool sharing CCs using FTQ data by Capex WBS L2 & CC | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-20 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-19 | 2025-09-26 | 2025-10-17 | 100% | 2025-10-30 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-11-13 | 2025-10-03 | 2025-10-31 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 2 | 2 | 0899 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | 2025-11-13 | 2025-11-21 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-11 | 2026-01-09 | 2025-12-11 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-07-25 |  |  |  | 0 |  | 415 | [7 empty] | 4. Completed | 1. Approved no action | 12/11: Conditionally Approved. | 2025-10-31 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-11-21 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE0899_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Enhancement to disaggregate:Owner CC-DPN $ to WBS elements using Capex proportions WBS-level DPN across Tool sharing CCs using FTQ data by Capex WBS L2 & CC | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-20 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-09-19 | 2025-09-26 | 2025-10-16 | 100% | 2025-10-17 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-17 | 2025-10-03 | 2025-10-31 | 2025-11-05 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-31 | 2025-10-31 | 2025-10-31 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | FPRE0899_IP | 02.High | 0.4 | 0.4 | 0899 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-17 | 2025-10-17 | 2025-10-17 |  | 2025-10-17 | 2025-11-05 | 2025-10-17 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-23 | 2026-01-09 | 2025-12-23 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-07-25 |  |  |  | 0 |  | 414 | [7 empty] | 1. On Track | 1. Approved no action | 12/22: FUT Approved. | 2025-10-31 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2488 | FPRE0892 | 04.Enhancement | 02.IF - Intel Foundry | Derive ICS FTQ data by Capex WBS L2 & Mfr. Process Node CC​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx?d=w8ca1e6ad7aa64be6bbfa0439483a2785&csf=1&web=1&e=HrQiTJ | 02.No | 01.Yes | FPRI0894 | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-11 | 2025-06-09 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-18 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-07-18 | 2025-07-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No | 2025-09-10 | 2025-12-03 | 2025-12-03 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0892 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-12-05 |  |  |  | 0 |  | 1772 | [7 empty] | 3. Off Track | 1. Approved no action | 12/22: FUT Approved. | 2025-07-18 | N | 03. FPR |  |  |  |  | 12/09 - BODS Dependency |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2300 | FPRE0891 | 04.Enhancement | 02.IF - Intel Foundry | Split from primary Cost centers to PCOS & R&D/OCOS | 03. FPR | 3.11 FPR - Project Accounting | 99. Rejected/Cancelled/On Hold | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2300_FPR_DC-050-680-Enhancement%20to%20automate%20universal%20allocation%20for%20Headcount.pptx?d=w20204d292be54bd88e46d10a0c04be55&csf=1&web=1&e=eP7Hxk | 02.No | 01.Yes | FPRI0909_IF | 2024-11-07 | shane.bethune@intel.com | 04.Cancelled | 2024-11-19 | RICEFW Descoped | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-18 | 2025-07-04 | 2025-07-11 | 2025-08-01 | 100% | 2025-07-23 | 2025-07-11 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | 2025-07-11 | 2025-08-15 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 |  |  | 100% |  |  |  |  | 04. Completed |  |  |  | 2025-07-21 | 2025-08-13 |  | Y | 50% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 99 | 2025-01-06 | 01.S4 |  |  | 0.5 | 0.5 | 0891 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-15 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  |  | 2025-08-13 | [6 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-08-13 |  |  |  | 0 |  | 2114 | [7 empty] | 1. On Track | 5. Object to be Cancelled | 09/19. Cancelled by Team. Mail sent to Jeson | 2025-08-15 | Y | 03. FPR | [7 empty] | Incorrect plan | N/A | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2302 | FPRE0890_IP | 04.Enhancement | 01.IP - Intel Product | Investment type creation and automatic settlement rule generation for Opex Project WBS Elements | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2302_FPR_DC-050-160-Investment%20Type%20Creation%20and%20Automatic%20Settlement%20rule%20generation%20for%20Opex%20Project%20WBS%20elements.pptx?d=w46c251b0ef184db687db3e9f2efdee57&csf=1&web=1&e=3j5vic | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-25 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-15 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-04-09 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-10 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-12 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0890 |  | R3 ITC1 | [6 empty] | 2025-01-15 | 2025-01-15 | 2025-01-15 |  | 2025-04-09 | 2025-04-11 | 2025-04-09 |  | 2025-04-10 | 2025-05-16 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-13 |  |  |  | 0 |  | 2117 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2302 | FPRE0890_IF | 04.Enhancement | 02.IF - Intel Foundry | Investment type creation and automatic settlement rule generation for Opex Project WBS Elements | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2302_FPR_DC-050-160-Investment%20Type%20Creation%20and%20Automatic%20Settlement%20rule%20generation%20for%20Opex%20Project%20WBS%20elements.pptx?d=w46c251b0ef184db687db3e9f2efdee57&csf=1&web=1&e=3j5vic | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-25 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-15 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-04-09 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | 2025-05-09 | 2025-05-16 | 2025-04-10 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-12 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | FPRE0890_IP | 03.Medium | 0.2 | 0.2 | 0890 |  | R3 ITC1 | [6 empty] | 2025-01-15 | 2025-01-15 | 2025-01-15 |  | 2025-04-09 | 2025-04-11 | 2025-04-09 |  | 2025-04-10 | 2025-05-16 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-13 |  |  |  | 0 |  | 2116 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2182 | FPRE0889_IP | 04.Enhancement | 01.IP - Intel Product | Custom table needs to be created to hold allocation %s based on LOB Profit center and Investment type Combination | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2182_FPR_Custom%20table%20needs%20to%20be%20created%20to%20hold%20allocation%20%25s%20based%20on%20%20LOB%20Profit%20center%20and%20Investment%20type%20Combination.pptx?d=wb66378a00a0d468ba4550feedb25a575&csf=1&web=1&e=FlgeBI | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-25 | 2025-06-09 | 2025-06-13 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0889 |  | R3 ITC1 | [6 empty] | 2025-01-25 | 2025-01-25 | 2025-01-25 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-08-22 |  |  |  | 0 |  | 2539 | [10 empty] | 2025-07-18 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2182 | FPRE0889_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom table needs to be created to hold allocation %s based on LOB Profit center and Investment type Combination | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2182_FPR_Custom%20table%20needs%20to%20be%20created%20to%20hold%20allocation%20%25s%20based%20on%20%20LOB%20Profit%20center%20and%20Investment%20type%20Combination.pptx?d=wb66378a00a0d468ba4550feedb25a575&csf=1&web=1&e=FlgeBI | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-25 | 2025-06-09 | 2025-06-13 | 2025-05-20 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | 2025-07-07 | 2025-07-18 | 2025-05-30 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | FPRE0889_IP | 04.Low | 0.1 | 0.1 | 0889 |  | R3 ITC1 | [6 empty] | 2025-01-25 | 2025-01-25 | 2025-01-25 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 |  | 2025-05-24 | 2025-07-18 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-08-29 |  |  |  | 0 |  | 2538 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-07-18 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-07-18 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2492 | FPRE0888_IP | 04.Enhancement | 01.IP - Intel Product | Mass Update Fields in WBS Elements | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B42E3205C-7653-4D45-8015-D72565A738FB%7D&file=2492_FPR_DC-050-680-Mass%20Update%20Fields%20in%20WBS%20element.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-27 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-04-08 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-11 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-05-30 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 2 | 2 | 0888 |  | R3 ITC1 | [6 empty] | 2025-01-27 | 2025-01-27 | 2025-01-27 |  | 2025-04-08 | 2025-04-11 | 2025-04-08 |  | 2025-04-11 | 2025-05-16 | 2025-04-11 | 2025-04-11 | [12 empty] | 2025-04-11 | 2025-04-11 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-24 | 2025-05-16 |  |  | 2025-08-29 |  |  |  | 0 |  | 1778 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2492 | FPRE0888_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass Update Fields in WBS Elements | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B42E3205C-7653-4D45-8015-D72565A738FB%7D&file=2492_FPR_DC-050-680-Mass%20Update%20Fields%20in%20WBS%20element.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-27 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-04-08 | 2025-05-09 | 2025-05-16 | 2025-04-03 | 100% | 2025-04-11 | 2025-05-09 | 2025-05-16 | 2025-04-03 | 100% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-05-30 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | FPRE0888_IP | 02.High | 0.4 | 0.4 | 0888 |  | R3 ITC1 | [6 empty] | 2025-01-27 | 2025-01-27 | 2025-01-27 |  | 2025-04-08 | 2025-04-11 | 2025-04-08 |  | 2025-04-11 | 2025-05-16 | 2025-04-11 | 2025-04-11 | [12 empty] | 2025-04-11 | 2025-04-11 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-24 | 2025-05-16 |  |  | 2025-08-29 |  |  |  | 0 |  | 1777 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2477 | FPRE0887_IP | 04.Enhancement | 01.IP - Intel Product | WBS Element field synchronization to AUC and Fixed assets - Construction ID - UEID | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/System%20code%20field%20automation.pptx?d=w0116e0f97ed44cd1961ddb86763a3cb0&csf=1&web=1&e=isFwAt | 02.No | 01.Yes | FPRI0188 | 2024-11-15 | shane.bethune@intel.com | 01.Approved | 2024-11-15 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-17 | 2025-06-06 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-24 | 2025-07-11 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-24 | 2025-07-11 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-06 | 01.S4 |  |  | 1 | 1 | 0887 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-21 | 2025-03-17 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-09-19 |  |  |  | 0 |  | 2765 | [9 empty] | 08/11 Opex conditionally approved and Capex was sent for approval but an issue was identified for which the defect 2089 is open with tech team. | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2477 | FPRE0887_IF | 04.Enhancement | 02.IF - Intel Foundry | WBS Element field synchronization to AUC and Fixed assets - Construction ID - UEID | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/System%20code%20field%20automation.pptx?d=w0116e0f97ed44cd1961ddb86763a3cb0&csf=1&web=1&e=isFwAt | 02.No | 01.Yes | FPRI0188 | 2024-11-15 | shane.bethune@intel.com | 01.Approved | 2024-11-15 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-17 | 2025-06-06 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-24 | 2025-07-11 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-24 | 2025-07-11 | 2025-07-18 | 2025-08-13 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-06 | 01.S4 | FPRE0887_IP | 03.Medium | 0.2 | 0.2 | 0887 |  | R3 ITC1 | [6 empty] | 2025-03-17 | 2025-03-21 | 2025-03-17 |  | 2025-07-24 | 2025-08-01 | 2025-07-24 |  | 2025-07-24 | 2025-08-13 | 2025-07-24 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-09-19 |  |  |  | 0 |  | 2764 | [9 empty] | 08/11 Opex conditionally approved and Capex was sent for approval but an issue was identified for which the defect 2089 is open with tech team. | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE0886_IP | 04.Enhancement | 01.IP - Intel Product | Project Change Order - Create Project Change Order via custom Fiori Screens with multiple levels of data display and line level edit in UI. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-18 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | 2025-08-18 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-10-08 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 0886 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-21 | 2025-08-22 |  |  | 2025-09-05 | 2025-09-12 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-11-28 |  |  |  | 0 |  | 2767 | [7 empty] | 1. On Track | 1. Approved no action | 11/11: Conditionally Approved by Steven. | 2025-09-12 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2479 | FPRE0886_IF | 04.Enhancement | 02.IF - Intel Foundry | Project Change Order - Create Project Change Order via custom Fiori Screens with multiple levels of data display and line level edit in UI. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7E45333F-B7E9-4FD8-9993-F1DDA8F927DF%7D&file=2479_FPR_DC-050-680-%20Custom%20Fiori%20App%20Change%20Order%20Create%20and%20Change%20with%20ALV%20input.pptx&wdLOR=c192FBB99-C2C0-4545-81CB-B99AAC6F9A5A&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-08-18 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | 2025-08-18 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRE0886_IP | 02.High | 0.4 | 0.4 | 0886 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-08-21 | 2025-08-22 |  |  | 2025-09-05 | 2025-09-12 | [14 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-11-28 |  |  |  | 0 |  | 2766 | [7 empty] | 4. Completed | 17. FUT In progress | 11/06:FUT completed in Bi1 & Dio in progress review is set with biz today and tomorrow. | 2025-09-12 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2470 | FPRE0885 | 04.Enhancement | 01.IP - Intel Product | Custom Fiori app - Create WBS Element Request Form with ALV Input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2470_FPR_DC-050-500-Custom%20Fiori%20App%20-%20WBS%20Element%20Request%20%20Form%20with%20ALV%20input%E2%80%8B.pptx?d=wfb78e17c71e44c3a9dfa0a142636bd9a&csf=1&web=1&e=ySn6uP | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-10-08 | 100% | 2025-09-22 | 2025-08-27 | 2025-09-03 | 2025-09-16 | 100% | 2025-09-15 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-15 | 2025-09-10 | 2025-10-08 | 2025-09-18 | 100% | 2025-09-15 | [15 empty] | 2025-09-15 | 2025-09-15 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 0885 |  | R3 ITC1 | [6 empty] | 2025-09-22 | 2025-10-08 | 2025-09-22 |  | 2025-09-15 | 2025-09-16 | 2025-09-15 |  | 2025-09-15 | 2025-10-08 | 2025-09-15 | 2025-09-15 | [12 empty] | 2025-09-15 | 2025-09-15 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2025-03-21 | 2025-10-08 |  |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 1890 | [7 empty] | 1. On Track | 1. Approved no action | 12/08: Conditional approval received. | 2025-10-08 | N | 03. FPR |  |  |  |  | 1119: ETA 1125 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-08 | 2025-09-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2468 | FPRE0884_IP | 04.Enhancement | 01.IP - Intel Product | Custom Fiori app - CPA (Project Budget) approval request using PPM Item decision point with ALV input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/Budget%20update%20automation.pptx?d=wc7e312e5332f42a09182d7dc58bfb3df&csf=1&web=1&e=n9Ray3 | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-08-01 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2 | 0884 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-21 | 2025-09-10 | 2025-08-21 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-10-31 |  |  |  | 0 |  | 1888 | [10 empty] | 2025-08-13 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2468 | FPRE0884_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori app - CPA (Project Budget) approval request using PPM Item decision point with ALV input​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/Budget%20update%20automation.pptx?d=wc7e312e5332f42a09182d7dc58bfb3df&csf=1&web=1&e=n9Ray3 | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-04-14 | 2025-04-18 | 2025-08-01 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-23 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-21 | Not Applicable | R3 Build & UT Sprint 17 | 2025-08-13 | 2025-08-13 | 2025-08-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRE0884_IP | 02.High | 0.4 | 0.4 | 0884 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-21 | 2025-09-10 | 2025-08-21 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-10-31 |  |  |  | 0 |  | 1887 | [10 empty] | 2025-08-13 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE0883_IP | 04.Enhancement | 01.IP - Intel Product | (FTQ Input to drive Disaggregation to Allocation Cycle) for Actuals.​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-24 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0883 |  | R3 ITC1 | [6 empty] | 2025-03-24 | 2025-03-24 | 2025-03-24 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-08-22 |  |  |  | 0 |  | 2596 | [7 empty] | 3. Off Track | 17. FUT In progress | 01/12: Documentation in progress and will be sent for approval by EOD today | 2025-11-05 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/15 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2297 | FPRE0883_IF | 04.Enhancement | 02.IF - Intel Foundry | (FTQ Input to drive Disaggregation to Allocation Cycle) for Actuals.​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8CA1E6AD-7AA6-4BE6-BBFA-0439483A2785%7D&file=2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx&wdLOR=c821116B9-2EC3-473A-87CA-DE463740DD46&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | Angela Wolf | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-11-05 | 100% | 2025-10-23 | 2025-09-24 | 2025-10-01 | 2025-10-16 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | 2025-10-08 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-27 | [15 empty] | 2025-10-27 | 2025-10-27 | No |  | 2026-01-30 | 2026-02-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-02-04 | 2026-02-04 | N | 100% | 2026-02-03 | Sprint 22 Week 4 | R3 Build & UT Sprint 22 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-10-07 07:51 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 | FPRE0883_IP | 03.Medium | 0.2 | 0.2 | 0883 |  | R3 ITC1 | [6 empty] | 2025-10-23 | 2025-11-05 | 2025-10-23 |  | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-10-27 | 2025-11-05 | 2025-10-27 | 2025-10-27 | [12 empty] | 2025-10-27 | 2025-10-27 |  |  | 2026-02-03 | 2026-02-04 | 2026-02-03 | [5 empty] | 2025-03-21 | 2025-08-15 |  |  | 2025-08-22 |  |  |  | 0 |  | 3322 | [7 empty] | 1. On Track | 1. Approved no action | 02/03: FUT Approved. | 2025-11-05 | N | 03. FPR |  |  |  |  | S22 Week2 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2487 | FPRE0882 | 04.Enhancement | 02.IF - Intel Foundry | Derive FCS FTQ data by Capex WBS L2 & Mfr. Process Node CC​ | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2295_FPR_Import%20Tool%20Usage%20Data%20from%20FCS%20and%20ICS%20to%20S4.pptx?d=w8ca1e6ad7aa64be6bbfa0439483a2785&csf=1&web=1&e=HrQiTJ | 02.No | 01.Yes | FPRI0895 | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-25 | 2025-09-24 | 2025-10-01 | 2025-10-14 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | 2025-10-08 | 2025-11-05 | 2025-10-24 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-22 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-05 | 2025-11-05 | 2025-11-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-01 | 01.S4 |  |  | 1 | 1 | 0882 |  | R3 ITC1 | [6 empty] | 2025-01-25 | 2025-01-25 | 2025-01-25 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 |  | 2025-10-15 | 2025-11-05 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | [5 empty] | 2025-01-24 | 2025-11-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 2768 | [7 empty] | 1. On Track | 1. Approved no action | 12/22: FUT Approved. | 2025-11-05 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2422 | FPRE0881 | 04.Enhancement | 05.CFIN | DMEE User Exits Required in the payment files- APAC​ | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2422_DMEE%20User%20Exits%20required%20for%20Payment%20Files.pptx?d=wb7fffeb57d3d41de865036a6eafddd86&csf=1&web=1&e=cbj0Iz | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-31 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-07 | 2026-02-16 | 2026-02-20 | 2025-10-03 | 100% | 2026-02-14 | 2026-02-16 | 2026-02-20 | 2025-10-03 | 100% | 2026-02-14 | [15 empty] | 2026-02-14 | 2026-02-14 | No |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-09 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 09:46 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0881 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2026-02-14 | 2026-02-14 | 2026-02-20 | 2026-02-14 | 2026-02-14 | [12 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-10-03 |  |  |  | 0 | 06. Banks | 1446 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 03/09: OSS note raised with SAP and waiting for an update on from SAP. | 2026-02-20 | Y | 03. FPR |  |  |  | 02/24: Build in progress. ETA is 03/03. Current status: Build is in progress and TUT+FUT will be followed post Build Issue: FUT delayed. Next steps: Expedite Build completion Help needed: N/A FUT ETA: TBD | Ticket raised with MBC.File extensions are not working automatically. Treasury team is closely working on this |  |  | Defects | Complete | R3 Build & UT Sprint 23 | 2026-02-14 | 2026-02-20 | 2026-02-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2421 | FPRE0880 | 04.Enhancement | 05.CFIN | Cash concentration functionality for cross-currency current accounts | 03. FPR | 3.9 FPR - Treasury and Cash Management | 09. FUT Overdue | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2421_DMEE%20User%20Exits%20required%20for%20Payment%20Files.pptx?d=wa910ed1470d345dc807882aa54dda150&csf=1&web=1&e=vwZOUr | 02.No | 01.Yes |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-24 | 2025-04-18 | 2025-01-24 | 100% | 2025-01-31 | 2025-09-24 | 2025-10-01 | 2026-02-20 | 100% | 2026-02-17 | 2026-02-16 | 2026-02-20 | 2026-01-07 | 100% | 2026-02-14 | 2026-02-16 | 2026-02-20 | 2026-01-07 | 100% | 2026-02-14 | [15 empty] | 2026-02-14 | 2026-02-14 | No |  | 2026-03-27 | 2026-03-27 |  | 50% | 50% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 50% | 2026-03-27 | Sprint 22 Week 4 | R3 Build & UT Sprint 23+ | 2026-02-20 | 2026-02-20 | 2026-02-20 | pgaroo@deloitte.com | 2024-11-20 03:31 | shreyananand@deloitte.com | 2026-04-07 00:23 | 9 | 2025-04-11 | 01.S4 |  |  | 0.5 | 0.5 | 0880 | INT-CR1804 | R3 ITC1* | [6 empty] | 2025-01-31 | 2025-04-18 | 2025-01-31 |  | 2026-02-17 | 2026-02-20 | 2026-02-17 | 2026-02-14 | 2026-02-14 | 2026-02-20 | 2026-02-14 | 2026-02-14 | [12 empty] | 2026-02-14 | 2026-02-14 |  |  |  | 2026-03-27 | 2026-03-20 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-10-03 |  |  |  | 0 | 06. Banks | 419 | [7 empty] | 3. Off Track | 6. FUT Defect Under Fix | 04/07: Defect: 8754. Issues addressed by developer, Akshara to continue with the testing. | 2026-02-20 | Y | 03. FPR |  |  |  | 03/24 : Build is in progress. ETA for Build completion is 03/25. FUT Completion ETA is 04/10 | Build is still in progress | 2. Risk | On track for S23+ | Defects | Delayed - Past Sprint | R3 Build & UT Sprint 23 | 2026-02-14 | 2026-02-20 | 2026-02-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2251 | FPRE0879 | 04.Enhancement | 05.CFIN | File Formatting and processing to support MBC and APM integration | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2251_DMEE%20User%20Exits%20required%20for%20Payment%20Files.pptx?d=wccf2f004a5214643a5a3b85324f154f0&csf=1&web=1&e=AV6BJH | 02.No | 01.Yes |  | 2024-11-07 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-31 | 2025-08-27 | 2025-09-03 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-10 | 2025-10-08 | 2026-02-20 | 100% | 2026-02-14 | 2025-09-10 | 2025-10-08 | 2026-02-20 | 100% | 2026-02-14 | [15 empty] | 2026-02-14 | 2026-02-14 | No |  | 2026-01-07 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-07 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-08 | 2025-10-08 | 2025-10-08 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 01:42 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0879 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2026-02-14 | 2026-02-14 | 2026-02-20 | 2026-02-14 | 2026-02-14 | [12 empty] | 2026-02-14 | 2026-02-14 |  |  | 2026-01-07 | 2026-01-09 | 2026-01-07 | [5 empty] | 2025-01-24 | 2025-09-12 |  |  | 2025-10-03 |  |  |  | 0 | 06. Banks | 2298 | [7 empty] | 3. Off Track | 5. Object to be Cancelled | 01/07: Potentially be cancelled. Cheena to confirm on this. 12/19: Revisiting the functional design. 12/18-Will discuss and get confirmation from business 12/17 - Waiting for some information from business. Once received, we will raise a request to cancel this object. 12/12- Object on hold | 2025-10-08 | N | 03. FPR | [7 empty] | Incorrect plan | Complete | R3 Build & UT Sprint 23 | 2026-02-14 | 2026-02-20 | 2026-02-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2476 | FPRE0877_IP | 04.Enhancement | 01.IP - Intel Product | Automation to set TECO and CLSD status on Project/ WBS | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2476_FPR_DC-050-120-Automation%20for%20project%20closure%20with%20TECO%20and%20CLSD%20status.pptx?d=wc08803a7eee640b4bdb3b056ccba9472&csf=1&web=1&e=CpdLqq | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-11-25 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-20 | 2025-04-04 | 2025-04-11 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-25 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-25 | 2025-05-16 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-06 | 2025-07-16 | N | 100% | 2025-08-20 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-18 | 01.S4 |  |  | 2 | 2 | 0877 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 |  | 2763 | [9 empty] | 08/18 - 2210 Defect with developer ETA 18/08 | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2476 | FPRE0877_IF | 04.Enhancement | 02.IF - Intel Foundry | Automation to set TECO and CLSD status on Project/ WBS | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-11-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2476_FPR_DC-050-120-Automation%20for%20project%20closure%20with%20TECO%20and%20CLSD%20status.pptx?d=wc08803a7eee640b4bdb3b056ccba9472&csf=1&web=1&e=CpdLqq | 02.No | 01.Yes |  | 2024-11-12 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-25 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-20 | 2025-04-04 | 2025-04-11 | 2025-06-20 | 100% | 2025-08-14 | 2025-05-02 | 2025-05-16 | 2025-07-11 | 100% | 2025-08-14 | 2025-05-02 | 2025-05-16 | 2025-07-11 | 100% | 2025-08-14 | [15 empty] | 2025-08-14 | 2025-08-14 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-06 | 2025-07-16 | N | 100% | 2025-08-20 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-12-18 | 01.S4 | FPRE0877_IP | 02.High | 0.4 | 0.4 | 0877 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | [12 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | [5 empty] | 2024-12-13 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 |  | 2762 | [9 empty] | 08/18 - 2210 Defect with developer ETA 18/08 | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-14 | 2025-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2206 | FPRE0870 | 04.Enhancement | 05.CFIN | Smart Exporter Interface to CFIN | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2206_FPR_RICEFW%20Intake%20form%20for%20Smart%20Exporter%20Interface%20to%20CFIN.pptx?d=w43fdfd490fd64e6787cd1571e809780e&csf=1&web=1&e=je49BG | 01.Yes | 01.Yes |  | 2024-11-06 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 02.Intel | 04.Low |  | 02.No |  | EY Smart Exporter Tool | EY Smart Exporter Tool | S4 | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-19 | 2025-10-24 | 2025-10-31 | 2025-11-20 | 100% | 2025-11-26 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-26 | [15 empty] | 2025-11-26 | 2025-11-26 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0870 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-03-21 | 2025-03-19 |  | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-26 | 2025-11-26 | [12 empty] | 2025-11-26 | 2025-11-26 |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-22 |  |  |  | 0 |  | 1783 | [7 empty] | 4. Completed | 16. Intel Owned | 10/23 - Intel owned object. Awaiting approval | 2025-12-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2333 | FPRE0827 | 04.Enhancement | 05.CFIN | MT3xx and MT5xx Files - Adjust SWIFT Parameters for MBC | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-08 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC0BF6714-60C8-4DC4-9533-1D87FDC38712%7D&file=2253_MT3xx%20and%20MT5xx%20Files%20-%20Adjust%20SWIFT%20Parameters%20for%20MBC.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-08 | shane.bethune@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2025-01-24 | 2025-09-19 | 2025-09-26 | 2025-11-13 | 100% | 2025-11-13 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [15 empty] | 2025-11-13 | 2025-11-13 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-12 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-01 | 01.S4 |  |  | 0.5 | 0.5 | 0827 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-01-24 | 2025-01-24 |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [12 empty] | 2025-11-13 | 2025-11-13 |  |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | [5 empty] | 2025-02-21 | 2025-06-13 |  |  | 2025-07-18 |  |  |  | 0 | 06. Banks | 1973 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/11: Business is requesting for some additional functionality. Still in pending approval. | 2025-12-05 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2270 | FPRE0786 | 04.Enhancement | 05.CFIN | Enhancement to Mass upload of WOM payment advice. | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2270_FPR_RICEFW%20Intake%20Form_OR-140-140_Enhancement%20to%20Mass%20upload%20of%20WOM%20payment%20advice%20v1.0.pptx?d=wf2c7b490ab7348e8a4daf07b5a155c3c&csf=1&web=1&e=3lA0mY | 02.No | 01.Yes | FPRI0869 | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-20 | 2024-12-13 | 100% | 2025-01-31 | 2025-07-02 | 2025-07-09 | 2025-08-01 | 100% | 2025-08-09 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-09 | 2025-08-04 | 2025-08-13 | 2025-08-13 | 100% | 2025-08-09 | [15 empty] | 2025-08-09 | 2025-08-09 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-08-13 | 2025-08-13 | 2025-08-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 |  |  | 1 | 1 | 0786 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-08-09 | 2025-08-09 | 2025-08-09 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 | 2025-08-09 | [12 empty] | 2025-08-09 | 2025-08-09 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2024-12-20 | 2025-06-13 |  |  | 2025-07-10 |  |  |  | 0 | 08. Not Applicable | 2140 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/24: Clara need to connect with Intel for Clarification on append SY to the 18 character Payment Advice. | 2025-08-13 | Y | 03. FPR |  |  |  | Awaiting Approval 1211. ETA 1121 | 1119: ETA 1121 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2275 | FPRE0785 | 04.Enhancement | 05.CFIN | Enhancement to upload WCP Grant Amount in CFIN sys | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2275_FPR_RICEFW%20Intake%20Form_OR-140-140WOM_Enhancement%20for%20WCP%20Grant%20Upload.pptx?d=w2d775bf9ab8b4a5981d0ebaeb4609735&csf=1&web=1&e=Vu0QFJ | 02.No | 01.Yes | FPRI0862,FPRI0866,FPRI0865,FPRI0867 | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-20 | 2024-12-13 | 100% | 2024-12-20 | 2025-04-04 | 2025-04-11 | 2025-03-25 | 100% | 2025-03-25 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-03-25 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-03-25 | [15 empty] | 2025-03-25 | 2025-03-25 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 |  |  | 1 | 1 | 0785 |  | R3 ITC1 | [6 empty] | 2024-12-20 | 2024-12-20 | 2024-12-20 |  | 2025-03-25 | 2025-04-11 | 2025-03-25 |  | 2025-03-25 | 2025-05-16 | 2025-03-25 | 2025-03-25 | [12 empty] | 2025-03-25 | 2025-03-25 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-12-20 | 2025-05-16 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2440 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2025-05-16 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-03-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2309 | FPRE0784_IP | 04.Enhancement | 01.IP - Intel Product | Reclass program for XIU/ SIU to reclass expense to inventory accounts (cost center to profit center) within same LEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://secure-web.cisco.com/1VRtBsNN6ojjpAmOEPn6-0p2hrgwVpwlFmpUmainuv7eUyfHLj3AcgICGkflUBWJS8tAXE2MQIfsJxXJw68vmlqcXGWkGW6LMd08_TXF2U7zMCfXCm6UhuSWoxv7rygy1WEfu8rjNcS4AnfqQ6saeXFqJzuRj35L7KYoiDqMJaEVnQjaVjFifXtADcXwvYl45cCc8uDOlHeKK2K0o37v2817rihzmkkh8_AO56A20mOy5jMxrMICQ00i_jyQ4x1wdp8Pvla573XLlf7kK7B3jx6yCqkMJ19Y5dySfPlC0xmuzyTBBPk1hGMtH5AJgwsvIeeaKCHJsymTY-apQ4fMmYUKnyAocqD9h5KGDiV1BVq-bNkYDK1iF8gE5kI0-oafSD9dGn-oQETqZHm8HON9KbKOXoVR83nTckPEi4uCIJxA4zCvbvFrdZHp048JoXwLZLcZhaz0Y35UFwNtJauSx4V4xew0vBclBl5VPFahoelZAKgQY11JTUxUceYDgJSkqxWo1IZN2FJ2ApIlGZshggg/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2FFPR_Reclass%2520Program%2520for%2520R3.pptx%3Fd%3Dw757e2a4435c84e1eb1ae5875db6c0120%26csf%3D1%26web%3D1%26e%3DcbWP15%26isSPOFile%3D1 | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-21 | 01.S4 |  |  | 1 | 1 | 0784 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-08-13 | [6 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-21 |  |  |  | 0 | 08. Not Applicable | 2102 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2309 | FPRE0784_IF | 04.Enhancement | 02.IF - Intel Foundry | Reclass program for XIU/ SIU to reclass expense to inventory accounts (cost center to profit center) within same LEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://secure-web.cisco.com/1VRtBsNN6ojjpAmOEPn6-0p2hrgwVpwlFmpUmainuv7eUyfHLj3AcgICGkflUBWJS8tAXE2MQIfsJxXJw68vmlqcXGWkGW6LMd08_TXF2U7zMCfXCm6UhuSWoxv7rygy1WEfu8rjNcS4AnfqQ6saeXFqJzuRj35L7KYoiDqMJaEVnQjaVjFifXtADcXwvYl45cCc8uDOlHeKK2K0o37v2817rihzmkkh8_AO56A20mOy5jMxrMICQ00i_jyQ4x1wdp8Pvla573XLlf7kK7B3jx6yCqkMJ19Y5dySfPlC0xmuzyTBBPk1hGMtH5AJgwsvIeeaKCHJsymTY-apQ4fMmYUKnyAocqD9h5KGDiV1BVq-bNkYDK1iF8gE5kI0-oafSD9dGn-oQETqZHm8HON9KbKOXoVR83nTckPEi4uCIJxA4zCvbvFrdZHp048JoXwLZLcZhaz0Y35UFwNtJauSx4V4xew0vBclBl5VPFahoelZAKgQY11JTUxUceYDgJSkqxWo1IZN2FJ2ApIlGZshggg/https%3A%2F%2Fintel.sharepoint.com%2F%3Ap%3A%2Fr%2Fsites%2Finteldeloitteiao%2FShared%2520Documents%2FGeneral%2FImplementation%2F11.%2520Technology%2FRICEFW%2F10%2520RICEFW%2520Inbox%2FFPR_Reclass%2520Program%2520for%2520R3.pptx%3Fd%3Dw757e2a4435c84e1eb1ae5875db6c0120%26csf%3D1%26web%3D1%26e%3DcbWP15%26isSPOFile%3D1 | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-31 | 2025-04-04 | 2025-04-11 | 2025-04-01 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | No |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-13 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-21 | 01.S4 | FPRE0784_IP | 03.Medium | 0.2 | 0.2 | 0784 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-08-13 | [6 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-21 |  |  |  | 0 | 08. Not Applicable | 2101 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2042 | FPRE0783_IP | 04.Enhancement | 01.IP - Intel Product | Asset creation from PO (S4 / Ariba / EMS, etc.) | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0007-Asset%20Creation%20through%20EMS_ARIBA.pptx?d=w38f1ad1c71764191a0ac418cc9813c6b&csf=1&web=1&e=rBy3nD | 02.No | 01.Yes | FPRI1315_IP, PTPI0709_IP | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | Ariba | S4 | NA | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-03-25 | 100% | 2025-03-25 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-03-25 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-03-25 | [15 empty] | 2025-03-25 | 2025-03-25 | Yes |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 |  |  | 1 | 1 | 0783 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2025-01-10 | 2024-12-13 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-04-18 | 2025-03-25 | 2025-03-25 | [12 empty] | 2025-03-25 | 2025-03-25 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-01-10 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2019 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/05: FUT Sent for approval. | 2025-04-18 | N | 03. FPR |  |  |  |  | Defect 2208 and 4716, 4614 (Keerti to priortize fix) |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2042 | FPRE0783_IF | 04.Enhancement | 02.IF - Intel Foundry | Asset creation from PO (S4 / Ariba / EMS, etc.) | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0007-Asset%20Creation%20through%20EMS_ARIBA.pptx?d=w38f1ad1c71764191a0ac418cc9813c6b&csf=1&web=1&e=rBy3nD | 02.No | 01.Yes | FPRI1315_IF, PTPI0709_IF | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | Ariba | S4 | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-13 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-03-25 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-03-25 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-03-25 | [15 empty] | 2025-03-25 | 2025-03-25 | Yes |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 | FPRE0783_IP | 03.Medium | 0.2 | 0.2 | 0783 |  | R3 ITC1 | [6 empty] | 2024-12-13 | 2024-12-13 | 2024-12-13 |  | 2025-03-25 | 2025-04-01 | 2025-03-25 |  | 2025-03-25 | 2025-04-18 | 2025-03-25 | 2025-03-25 | [12 empty] | 2025-03-25 | 2025-03-25 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2018 | [7 empty] | 4. Completed | 17. FUT In progress | 12/05: Testing in progress and will be sent for approval by today. | 2025-04-18 | N | 03. FPR |  |  |  |  | Defect 2208 and 4716, 4614 (Keerti to priortize fix) |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2180 | FPRE0781_IP | 04.Enhancement | 01.IP - Intel Product | Import Standard Cost from S4 tables into SAC using Custom CDS view. | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2180_FPR_Import%20Standard%20Cost%20from%20S4%20tables%20into%20SAC%20using%20Custom%20CDS%20view.pptx?d=w783640c68c9340b8b3733c1ae139e3a7&csf=1&web=1&e=eiXNi0 | 02.No | 01.Yes |  | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-25 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-23 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-09-10 | 2025-09-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-30 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0781 |  | R3 ITC1 | [6 empty] | 2025-01-25 | 2025-01-25 | 2025-01-25 |  | 2025-05-24 | 2025-07-11 | 2025-05-24 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-01-24 | 2025-07-11 |  |  | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 1666 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10: INTEL IT team approved this and will be sent for Business approval. | 2025-08-15 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2180 | FPRE0781_IF | 04.Enhancement | 02.IF - Intel Foundry | Import Standard Cost from S4 tables into SAC using Custom CDS view. | 03. FPR | 3.8 FPR - Financial Planning & Analysis | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2180_FPR_Import%20Standard%20Cost%20from%20S4%20tables%20into%20SAC%20using%20Custom%20CDS%20view.pptx?d=w783640c68c9340b8b3733c1ae139e3a7&csf=1&web=1&e=eiXNi0 | 02.No | 01.Yes |  | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-25 | 2025-07-04 | 2025-07-11 | 2025-05-20 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-23 | 100% | 2025-05-24 | 2025-08-01 | 2025-08-15 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-22 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 | FPRE0781_IP | 03.Medium | 0.2 | 0.2 | 0781 |  | R3 ITC1 | [6 empty] | 2025-01-25 | 2025-01-25 | 2025-01-25 |  | 2025-05-24 | 2025-07-11 | 2025-05-24 |  | 2025-05-24 | 2025-08-15 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | [5 empty] | 2025-01-24 | 2025-07-11 |  |  | 2025-07-25 |  |  |  | 0 | 08. Not Applicable | 1665 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/17: INTEL IT is still working on the FUT. | 2025-08-15 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 14 |  | 2025-08-15 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2192 | FPRE0780_IP | 04.Enhancement | 01.IP - Intel Product | Read the workday file from AL11 in IP, IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE63E8C76-662D-457A-89F9-FC28BA38EF51%7D&file=2192_2193_FPR_Read%20the%20workday%20file%20from%20AL11%20in%20IP%2C%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 0780 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-06-21 | 2025-06-13 |  |  | 2025-07-04 |  |  |  | 0 | 08. Not Applicable | 2544 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2192 | FPRE0780_IF | 04.Enhancement | 02.IF - Intel Foundry | Read the workday file from AL11 in IP, IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE63E8C76-662D-457A-89F9-FC28BA38EF51%7D&file=2192_2193_FPR_Read%20the%20workday%20file%20from%20AL11%20in%20IP%2C%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRE0780_IP | 03.Medium | 0.2 | 0.2 | 0780 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-06-21 | 2025-06-13 |  |  | 2025-07-04 |  |  |  | 0 | 08. Not Applicable | 2543 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2193 | FPRE0779_IP | 04.Enhancement | 01.IP - Intel Product | Enhance the details in workday file to meet AE format in IP, IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE63E8C76-662D-457A-89F9-FC28BA38EF51%7D&file=2192_2193_FPR_Read%20the%20workday%20file%20from%20AL11%20in%20IP%2C%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1 | 0779 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-06-21 | 2025-06-13 |  |  | 2025-07-04 |  |  |  | 0 | 08. Not Applicable | 2546 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2193 | FPRE0779_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhance the details in workday file to meet AE format in IP, IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BE63E8C76-662D-457A-89F9-FC28BA38EF51%7D&file=2192_2193_FPR_Read%20the%20workday%20file%20from%20AL11%20in%20IP%2C%20IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-05-12 | 2025-05-16 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-30 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRE0779_IP | 03.Medium | 0.2 | 0.2 | 0779 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-06-21 | 2025-06-13 |  |  | 2025-07-04 |  |  |  | 0 | 08. Not Applicable | 2545 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2413 | FPRE0777_IP | 04.Enhancement | 01.IP - Intel Product | Add a field in ACDOCA to store Cert ID to continue auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-23 | 2025-06-09 | 2025-06-13 | 2025-03-25 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | [15 empty] | 2025-04-09 | 2025-04-09 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 | FPRE0777_CFIN | 04.Low | 0.1 | 0.1 | 0777 |  | R3 ITC1 | [6 empty] | 2025-01-23 | 2025-01-24 | 2025-01-23 |  | 2025-04-09 | 2025-06-13 | 2025-04-09 |  | 2025-04-09 | 2025-07-18 | 2025-04-09 | 2025-04-09 | [12 empty] | 2025-04-09 | 2025-04-09 |  |  | 2025-06-11 | 2025-08-15 | [6 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 1791 | [10 empty] | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-07-18 | 2025-04-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2413 | FPRE0777_IF | 04.Enhancement | 02.IF - Intel Foundry | Add a field in ACDOCA to store Cert ID to continue auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | shane.bethune@intel.com | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-23 | 2025-06-09 | 2025-06-13 | 2025-03-25 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | [15 empty] | 2025-04-09 | 2025-04-09 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 | FPRE0777_CFIN | 04.Low | 0.1 | 0.1 | 0777 |  | R3 ITC1 | [6 empty] | 2025-01-23 | 2025-01-24 | 2025-01-23 |  | 2025-04-09 | 2025-06-13 | 2025-04-09 |  | 2025-04-09 | 2025-07-18 | 2025-04-09 | 2025-04-09 | [12 empty] | 2025-04-09 | 2025-04-09 |  |  | 2025-06-11 | 2025-08-15 | [6 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 1790 | [10 empty] | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-07-18 | 2025-04-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2413 | FPRE0777_CFIN | 04.Enhancement | 05.CFIN | Add a field in ACDOCA to store Cert ID to continue auto-certify a BL task when the related JE is approved | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6FEE1D76-43F8-4F23-B039-9BC249C3279D%7D&file=XXXX_TBD.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-28 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-23 | 2025-06-09 | 2025-06-13 | 2025-03-25 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | 2025-07-07 | 2025-07-18 | 2025-04-03 | 100% | 2025-04-09 | [15 empty] | 2025-04-09 | 2025-04-09 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-06-11 | N | 100% | 2025-06-16 | Not Applicable | R3 Build & UT Sprint 15 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-12 | 01.S4 |  |  | 0.5 | 0.5 | 0777 |  | R3 ITC1 | [6 empty] | 2025-01-23 | 2025-01-24 | 2025-01-23 |  | 2025-04-09 | 2025-06-13 | 2025-04-09 |  | 2025-04-09 | 2025-07-18 | 2025-04-09 | 2025-04-09 | [12 empty] | 2025-04-09 | 2025-04-09 |  |  | 2025-06-16 | 2025-08-15 | 2025-06-16 | [5 empty] | 2025-01-24 | 2025-08-15 |  |  | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 1789 | [10 empty] | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-07-18 | 2025-04-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2261 | FPRE0764_IP | 04.Enhancement | 01.IP - Intel Product | Import Headcount details by cost center and update in S4 for HR benefits spend allocation | 03. FPR | 3.6 FPR - Cost and Profitability Analysis | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2261%20FPR_RICEFW-Import%20Headcount%20from%20HRMM%20and%20update%20as%20SKF%20in%20S4.pptx?d=w08f15798c4554a5b895a451a933f932b&csf=1&web=1&e=j3lPOQ | 02.No | 02.No | DATI0959 | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-17 | 2025-05-12 | 2025-05-16 | 2025-05-20 | 100% | 2025-05-24 | 2025-06-02 | 2025-06-13 | 2025-05-23 | 100% | 2025-05-24 | 2025-06-02 | 2025-06-13 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-15 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0764 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-17 | 2024-12-17 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1508 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2261 | FPRE0764_IF | 04.Enhancement | 02.IF - Intel Foundry | Import Headcount details by cost center and update in S4 for HR benefits spend allocation | 03. FPR | 3.6 FPR - Cost and Profitability Analysis | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2261%20FPR_RICEFW-Import%20Headcount%20from%20HRMM%20and%20update%20as%20SKF%20in%20S4.pptx?d=w08f15798c4554a5b895a451a933f932b&csf=1&web=1&e=j3lPOQ | 02.No | 02.No | DATI0959 | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-17 | 2025-05-12 | 2025-05-16 | 2025-05-20 | 100% | 2025-05-24 | 2025-06-02 | 2025-06-13 | 2025-05-23 | 100% | 2025-05-24 | 2025-06-02 | 2025-06-13 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-15 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 | FPRE0764_IP | 03.Medium | 0.2 | 0.2 | 0764 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-17 | 2024-12-17 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-06-13 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1507 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2252 | FPRE0763 | 04.Enhancement | 05.CFIN | Placeholder - BADI for Memo Records with different Planning Levels/Types generated by APM | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B82CBBD53-2B7E-40CA-A57E-ED1F7752E9DE%7D&file=2252_Enhancement%20for%20Memo%20Records%20with%20different%20Planning%20Levels%2C%20Types%20generated%20by%20APM%20-%20Copy.pptx&action=edit&mobileredirect=true | 02.No | 02.No | FPRI0224 | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2025-01-10 | 2024-12-13 | 100% | 2025-01-10 | 2025-05-12 | 2025-05-16 | 2025-07-25 | 100% | 2025-07-23 | 2025-07-21 | 2025-08-01 | 2025-08-08 | 100% | 2025-07-23 | 2025-07-21 | 2025-08-01 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-10-16 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-01 | 2025-08-01 | 2025-08-01 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0763 |  | R3 ITC1 | [6 empty] | 2025-01-10 | 2025-01-10 | 2025-01-10 |  | 2025-07-23 | 2025-07-25 | 2025-07-23 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-10-16 | 2025-11-07 | 2025-10-16 | [5 empty] | 2025-01-10 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 | 06. Banks | 2299 | [10 empty] | 2025-08-01 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2199 | FPRE0761 | 04.Enhancement | 05.CFIN | Branch Name and Address for Payments instead of entity Name and Address | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B50E7254F-CCC2-464D-B2C9-88786075AF9D%7D&file=MR-010-0003_Additional%20Custom%20field.pptx&action=edit&mobileredirect=true&CID=B1110FDA-F688-4039-B5BB-2C0FAAF4D76E&wdLOR=cDDFBF3F1-6724-4180-9932-378F42DEA115&previoussessionid=cf47e7f4-3c22-ee88-fd3a-a01bd36581a7 | 02.No | 01.Yes |  | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-12 | 2025-05-12 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-06-02 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | 2025-06-02 | 2025-06-13 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-15 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0761 |  | R3 ITC1 | [6 empty] | 2024-12-12 | 2024-12-13 | 2024-12-12 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 06. Banks | 2550 | [7 empty] | 1. On Track | 2. Smartsheet Hygiene(5.2) |  | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2082 | FPRE0760_IP | 04.Enhancement | 01.IP - Intel Product | SAP RAR and TM Integration to trigger POD Event | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-100-IDM-USID-%20RAR%20TM%20integration.pptx?d=w7e6ccb246f354d44a9fac6162d783be1&csf=1&web=1&e=dZz7cE | 02.No | 01.Yes |  | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2024-12-18 | 2025-01-24 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-04-22 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | 2025-05-02 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-12 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-02 | 01.S4 |  |  | 1 | 1 | 0760 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-06-12 | [6 empty] | 2024-12-18 | 2025-05-16 |  |  | 2025-06-12 |  |  |  | 0 | 08. Not Applicable | 2087 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2082 | FPRE0760_IF | 04.Enhancement | 02.IF - Intel Foundry | SAP RAR and TM Integration to trigger POD Event | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-11-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-100-IDM-USID-%20RAR%20TM%20integration.pptx?d=w7e6ccb246f354d44a9fac6162d783be1&csf=1&web=1&e=dZz7cE | 02.No | 01.Yes |  | 2024-10-21 | Shane Bethune | 01.Approved | 2024-11-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2024-12-18 | 2025-01-24 | 100% | 2024-12-18 | 2025-04-04 | 2025-04-11 | 2025-04-22 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | 2025-05-09 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-12 | 2025-06-11 | N | 100% | 2025-06-11 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-11-02 | 01.S4 | FPRE0760_IP | 03.Medium | 0.2 | 0.2 | 0760 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-11 | 2025-06-12 | [6 empty] | 2024-12-18 | 2025-05-16 |  |  | 2025-06-12 |  |  |  | 0 | 08. Not Applicable | 2086 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2144 | FPRE0702 | 04.Enhancement | 02.IF - Intel Foundry | Calculation of variance to be loaded for Group Actual Costing | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2144_FPR_RICEFW%20Intake%20Form_Enhancement_IF-IP%20-%20Actual%20Costing%20-Amount%20calculation.pptx?d=wf19365dd26e84a6f9273c1b8ac58c368&csf=1&web=1&e=gE0BDm | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-04-14 | 2025-04-18 | 2025-03-25 | 100% | 2025-04-10 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-10 | 2025-05-02 | 2025-05-16 | 2025-04-04 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-14 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0702 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-04-10 | 2025-04-18 | 2025-04-10 |  | 2025-04-10 | 2025-05-16 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | [5 empty] | 2025-02-21 | 2025-08-15 |  |  | 2025-09-05 |  |  |  | 0 | 08. Not Applicable | 2740 | [7 empty] | 1. On Track | 17. FUT In progress | 08/18 - FUT Approved. Smartsheet will be updated by sub team. | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2113 | FPRE0701_IP | 04.Enhancement | 01.IP - Intel Product | Mixed Costing ratio auto update | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2113_FPR_RICEFW%20Intake%20Form_Enhancement%20Automatic%20Update%20of%20Mixed%20Costing.pptx?d=wa10486d11b2a4888a5de4608b63b5e61&csf=1&web=1&e=rAOW9d | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-23 | 2025-05-02 | 2025-05-09 | 2025-05-20 | 100% | 2025-05-27 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-27 | 2025-05-30 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-27 | [15 empty] | 2025-05-27 | 2025-05-27 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-07-25 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0701 |  | R3 ITC1 | [6 empty] | 2025-01-23 | 2025-01-24 | 2025-01-23 |  | 2025-05-27 | 2025-05-27 | 2025-05-27 |  | 2025-05-27 | 2025-06-13 | 2025-05-27 | 2025-05-27 | [12 empty] | 2025-05-27 | 2025-05-27 |  |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | [5 empty] | 2025-01-24 | 2025-06-13 |  |  | 2025-07-10 |  |  |  | 0 | 08. Not Applicable | 2786 | [10 empty] | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2113 | FPRE0701_IF | 04.Enhancement | 02.IF - Intel Foundry | Mixed Costing ratio auto update | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2113_FPR_RICEFW%20Intake%20Form_Enhancement%20Automatic%20Update%20of%20Mixed%20Costing.pptx?d=wa10486d11b2a4888a5de4608b63b5e61&csf=1&web=1&e=rAOW9d | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-23 | 2025-05-02 | 2025-05-09 | 2025-05-20 | 100% | 2025-05-27 | 2025-06-06 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-27 | 2025-06-06 | 2025-06-13 | 2025-05-30 | 100% | 2025-05-27 | [15 empty] | 2025-05-27 | 2025-05-27 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-10 | 2025-07-16 | N | 100% | 2025-07-25 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-12 | 01.S4 | FPRE0701_IP | 03.Medium | 0.2 | 0.2 | 0701 |  | R3 ITC1 | [6 empty] | 2025-01-23 | 2025-01-24 | 2025-01-23 |  | 2025-05-27 | 2025-05-27 | 2025-05-27 |  | 2025-05-27 | 2025-06-13 | 2025-05-27 | 2025-05-27 | [12 empty] | 2025-05-27 | 2025-05-27 |  |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | [5 empty] | 2025-01-24 | 2025-06-13 |  |  | 2025-07-10 |  |  |  | 0 | 08. Not Applicable | 2785 | [10 empty] | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-13 | 2025-05-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2112 | FPRE0700_IP | 04.Enhancement | 01.IP - Intel Product | Representative material ID – Q2-Q8 Forecast | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2112_FPR_RICEFW%20Intake%20Form_Enhancement_Automate%20Costing%20Run%20with%20representative%20Materials.pptx?d=w4cbf4387e480469d8ae7f92cff2b4d3a&csf=1&web=1&e=DeSTAG | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-02-12 | 2025-04-18 | 2025-04-18 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-18 | 2025-06-12 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0700 |  | R3 ITC1 | [6 empty] | 2025-02-12 | 2025-02-12 | 2025-02-12 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-24 | 2025-06-13 |  |  | 2025-07-10 |  |  |  | 0 | 08. Not Applicable | 2784 | [7 empty] | 2. At Risk | 17. FUT In progress |  | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2112 | FPRE0700_IF | 04.Enhancement | 02.IF - Intel Foundry | Representative material ID – Q2-Q8 Forecast | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2112_FPR_RICEFW%20Intake%20Form_Enhancement_Automate%20Costing%20Run%20with%20representative%20Materials.pptx?d=w4cbf4387e480469d8ae7f92cff2b4d3a&csf=1&web=1&e=DeSTAG | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-31 | 2025-04-18 | 2025-04-18 | 2025-05-20 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | 2025-05-02 | 2025-05-16 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | No |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-18 | 2025-06-12 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 | FPRE0700_IP | 03.Medium | 0.2 | 0.2 | 0700 |  | R3 ITC1 | [6 empty] | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-01-24 | 2025-06-13 |  |  | 2025-07-10 |  |  |  | 0 | 08. Not Applicable | 2783 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1869 | FPRE0699 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for Excess Capacity – Fixed Spending Adjustment | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1869_FPR_RICEFW%20Intake%20Form_Report%20Program_Excess%20Capacity%20Adjustment.pptx?d=w9e645ffa89fc4022ace9e8a5fdbf237b&csf=1&web=1&e=THV4Fi | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-12-05 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-12-05 | [15 empty] | 2025-12-05 | 2025-12-05 | No |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-09 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | pgaroo@deloitte.com | 2024-10-08 05:36 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-12 | 01.S4 |  |  | 2 | 2 | 0699 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-05 | [12 empty] | 2025-12-05 | 2025-12-05 |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | [5 empty] | 2025-02-21 | 2025-10-03 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 2770 | [7 empty] | 4. Completed | 1. Approved no action | 12/08: FUT Approved. | 2025-10-03 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2063 | FPRE0698 | 04.Enhancement | 02.IF - Intel Foundry | Legal Valuation standard cost calculation enhancement | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-10-10 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2063_FPR_RICEFW%20Intake%20Form_%20Enhancement%20for%20Legal%20Valuation%20Standard%20Cost%20calculation.pptx?d=w38465b28f4c4431ea9eb20f46fc364b6&csf=1&web=1&e=el6PnZ | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-10 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-08-29 | 2025-04-18 | 2025-04-18 | 2025-04-01 | 100% | 2025-03-27 | 2025-05-02 | 2025-05-16 | 2025-04-10 | 100% | 2025-03-27 | 2025-05-02 | 2025-05-16 | 2025-04-10 | 100% | 2025-03-27 | [15 empty] | 2025-03-27 | 2025-03-27 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-10-12 | 01.S4 |  |  | 0.5 | 0.5 | 0698 | INT-CR0537 | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 |  | 2025-03-27 | 2025-05-16 | 2025-03-27 | 2025-03-27 | [12 empty] | 2025-03-27 | 2025-03-27 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2025-02-21 | 2025-05-16 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2703 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/06: FUT was submitted for review. ETA 11/07. | 2025-05-16 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-05-16 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2249 | FPRE0697 | 04.Enhancement | 01.IP - Intel Product | RAR Balance sheet posting with MM & Sold To ID | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-10-11 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-100-IDM-USID-%20Capture%20MMID%20%26%20Customer%20ID%20level%20for%20FI-GL%20posting%20in%20RAR%20integration.pptx?d=w2a537662806f4c48b8bd4a1d10562038&csf=1&web=1&e=RLOWf8 | 02.No | 01.Yes |  | 2024-10-08 | Shane Bethune | 01.Approved | 2024-10-11 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-04 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-25 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-25 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-25 | [15 empty] | 2025-03-25 | 2025-03-25 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-15 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0697 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-25 | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | 2025-04-18 | 2025-03-25 | 2025-03-25 | [12 empty] | 2025-03-25 | 2025-03-25 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-11-15 | 2025-04-18 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2296 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2041 | FPRE0648_IP | 04.Enhancement | 01.IP - Intel Product | RD04 - Intercompany invoice billing posting to different GL accounts | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB0583904-D5DA-40D8-B3AA-068EA27D43A1%7D&file=DC-110-080-IDM-0008_FPR_Intercompany_RD04%20-%20Intercompany%20Invoice%20billing%20GL%20accounts.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes | FPRI1286_IP and FPRI0864_IP | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-03-25 | 100% | 2025-03-26 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-03-26 | 2025-04-04 | 2025-04-18 | 2025-04-04 | 100% | 2025-03-26 | [15 empty] | 2025-03-26 | 2025-03-26 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0648 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-26 | 2025-03-26 | 2025-03-26 |  | 2025-03-26 | 2025-04-18 | 2025-03-26 | 2025-03-26 | [12 empty] | 2025-03-26 | 2025-03-26 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 2017 | [7 empty] | 1. On Track | 9. Blocked by B-App Readiness | 09/26: Conditionally Approved. | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2041 | FPRE0648_IF | 04.Enhancement | 02.IF - Intel Foundry | RD04 - Intercompany invoice billing posting to different GL accounts | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB0583904-D5DA-40D8-B3AA-068EA27D43A1%7D&file=DC-110-080-IDM-0008_FPR_Intercompany_RD04%20-%20Intercompany%20Invoice%20billing%20GL%20accounts.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes | FPRI1286_IF and FPRI0864_IF | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-03-26 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-03-26 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-03-26 | [15 empty] | 2025-03-26 | 2025-03-26 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-09-26 | Not Applicable | R3 Build & UT Sprint 18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 | FPRE0648_IP | 03.Medium | 0.2 | 0.2 | 0648 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-26 | 2025-04-01 | 2025-03-26 |  | 2025-03-26 | 2025-04-18 | 2025-03-26 | 2025-03-26 | [12 empty] | 2025-03-26 | 2025-03-26 |  |  | 2025-09-26 | 2025-09-26 | 2025-09-26 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 2016 | [7 empty] | 1. On Track | 3. Awaiting Approval | 09/26: Conditionally Approved. | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2107 | FPRE0647_IP | 04.Enhancement | 01.IP - Intel Product | Intercompany - Subledger Posting template & Approval Workflow | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7D0C7AF3-5E6A-444E-8643-17045FDCCEB1%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Subledger%20Posting%20template%20%26%20Approval%20Workflow.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-11-15 | 100% | 2024-11-27 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-27 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | [15 empty] | 2025-03-27 | 2025-03-27 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-04 | 01.S4 | FPRE0647_CFIN | 03.Medium | 0.2 | 0.2 | 0647 |  | R3 ITC1 | [6 empty] | 2024-11-27 | 2024-11-27 | 2024-11-27 |  | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 | 2025-03-27 | [12 empty] | 2025-03-27 | 2025-03-27 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2278 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2107 | FPRE0647_IF | 04.Enhancement | 02.IF - Intel Foundry | Intercompany - Subledger Posting template & Approval Workflow | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7D0C7AF3-5E6A-444E-8643-17045FDCCEB1%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Subledger%20Posting%20template%20%26%20Approval%20Workflow.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-11-15 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-03-24 | 100% | 2025-03-27 | 2025-04-11 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | 2025-04-11 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | [15 empty] | 2025-03-27 | 2025-03-27 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-04 | 01.S4 | FPRE0647_CFIN | 03.Medium | 0.2 | 0.2 | 0647 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 | 2025-03-27 | [12 empty] | 2025-03-27 | 2025-03-27 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2277 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2107 | FPRE0647_CFIN | 04.Enhancement | 05.CFIN | Intercompany - Subledger Posting template & Approval Workflow | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B7D0C7AF3-5E6A-444E-8643-17045FDCCEB1%7D&file=DC-110-080-IDM-0009_FPR_Intercompany_Subledger%20Posting%20template%20%26%20Approval%20Workflow.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-11-15 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-03-25 | 100% | 2025-03-27 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | 2025-04-04 | 2025-04-18 | 2025-03-28 | 100% | 2025-03-27 | [15 empty] | 2025-03-27 | 2025-03-27 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0647 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-03-27 | 2025-03-27 | 2025-03-27 |  | 2025-03-27 | 2025-04-18 | 2025-03-27 | 2025-03-27 | [12 empty] | 2025-03-27 | 2025-03-27 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2276 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-03-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2056 | FPRE0646_IP | 04.Enhancement | 01.IP - Intel Product | An automated solution to record the depreciation amount in a monthly basis for the AUC's that have passed their DSD | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IDM-USID-3185_FPR%20_Depreciation%20Accrual.pptx?d=w0ad50b2911fd42c69018207870bdf5f1&csf=1&web=1&e=OPdD83 | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-17 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-15 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 |  |  | 1 | 1 | 0646 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-17 | 2024-12-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-12 |  |  |  | 0 | 08. Not Applicable | 2698 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2056 | FPRE0646_IF | 04.Enhancement | 02.IF - Intel Foundry | An automated solution to record the depreciation amount in a monthly basis for the AUC's that have passed their DSD | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-10-03 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/IDM-USID-3185_FPR%20_Depreciation%20Accrual.pptx?d=w0ad50b2911fd42c69018207870bdf5f1&csf=1&web=1&e=OPdD83 | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-12-13 | 100% | 2024-12-17 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-03-26 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-04-21 | 2025-04-11 | 2025-04-18 | 2025-04-10 | 100% | 2025-04-21 | [15 empty] | 2025-04-21 | 2025-04-21 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-15 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-04 | 01.S4 | FPRE0646_IP | 03.Medium | 0.2 | 0.2 | 0646 |  | R3 ITC1 | [6 empty] | 2024-12-17 | 2024-12-17 | 2024-12-17 |  | 2025-03-26 | 2025-04-01 | 2025-03-26 |  | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | [12 empty] | 2025-04-21 | 2025-04-21 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-12-13 | 2025-04-18 |  |  | 2025-05-12 |  |  |  | 0 | 08. Not Applicable | 2697 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-04-21 | 2025-04-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1096 | FPRE0645_IP | 04.Enhancement | 01.IP - Intel Product | Need to identify a Mass settlement upload tool. Today, the capital life cycle (PEGA & Winshuttle) is used to mass update the settlement rule creation and update on the WBS. | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0005_FPR_Capital%20life%20cycle%20process%20in%20PEGA.pptx?d=w3e9dfaa2f0484dffab33886c1cf032bb&csf=1&web=1&e=tCkMtT | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-12-31 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-12-31 | [15 empty] | 2025-12-31 | 2025-12-31 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-11 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | vasamohan@deloitte.com | 2024-09-18 14:57 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-27 | 01.S4 |  |  | 4 | 4 | 0645 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | [12 empty] | 2025-12-31 | 2025-12-31 |  |  | 2025-12-11 | 2026-01-09 | 2025-12-11 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 1521 | [7 empty] | 1. On Track | 1. Approved no action | 12/11: FUT Approved. | 2025-10-03 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-31 | 2025-12-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1096 | FPRE0645_IF | 04.Enhancement | 02.IF - Intel Foundry | Need to identify a Mass settlement upload tool. Today, the capital life cycle (PEGA & Winshuttle) is used to mass update the settlement rule creation and update on the WBS. | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0005_FPR_Capital%20life%20cycle%20process%20in%20PEGA.pptx?d=w3e9dfaa2f0484dffab33886c1cf032bb&csf=1&web=1&e=tCkMtT | 01.Yes | 01.Yes |  | 2024-09-18 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-10-07 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2026-02-24 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2026-02-24 | [15 empty] | 2026-02-24 | 2026-02-24 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | vasamohan@deloitte.com | 2024-09-18 14:57 | cell-link@smartsheet.com | 2026-02-23 22:43 | 10 | 2024-09-27 | 01.S4 | FPRE0645_IP | 01.Very High | 0.8 | 0.8 | 0645 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | [12 empty] | 2026-02-24 | 2026-02-24 |  |  | 2025-12-05 | 2026-01-09 | 2025-12-05 | [5 empty] | 2025-04-04 | 2025-08-15 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 1520 | [7 empty] | 1. On Track | 1. Approved no action | 12/11: FUT Approved. | 2025-10-03 | N | 03. FPR |  |  |  |  | 12/09 - ETA is 12/12 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23 |  | 2026-02-24 | 2026-02-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0624 | 04.Enhancement | 05.CFIN | Portal Remittance Automation- Retrofitting | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0624 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2496 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0623 | 04.Enhancement | 05.CFIN | Payment Advice Bot Success & Exception Report | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0623 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2497 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0622 | 04.Enhancement | 05.CFIN | Exception Handling & Trigger Set up | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0622 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2498 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0621 | 04.Enhancement | 05.CFIN | Payment Advice CSV Creation & Upload | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0621 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2495 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0620 | 04.Enhancement | 05.CFIN | Model Integration & Export | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0620 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2491 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0619 | 04.Enhancement | 05.CFIN | UiPath OCR - Model Validation | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0619 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2494 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0618 | 04.Enhancement | 05.CFIN | UiPath OCR - Iterative Model Training | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0618 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2490 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0617 | 04.Enhancement | 05.CFIN | UiPath OCR - Classification & Extraction | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0617 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2492 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1493 | FPRE0616 | 04.Enhancement | 05.CFIN | UiPath OCR - Taxonomy & Digitize | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-11-19 | Shane Bethune | 01.Approved | 2024-09-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-22 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-10 14:33 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-09-19 | 04.S4 BOT |  |  | 0.5 | 0.5 | 0616 | INT-CR0068 | R3 ITC1 | [6 empty] | 2025-03-22 | 2025-03-22 | 2025-03-22 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2025-03-21 | 2025-04-18 |  |  | 2025-08-14 |  |  |  | 0 | 08. Not Applicable | 2493 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2051 | FPRE0605_IP | 04.Enhancement | 01.IP - Intel Product | H2RA - 13th month bonus & Quarterly Performance Bonus (QPB) bonus accrual postings | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2051_2052_FPR_Transaction%20Processing_H2RA%20Custom%20program%20Intake%20form.pptx?d=w8cfa94db53ce44f8b80bfe26f79e1725&csf=1&web=1&e=TxtLCt | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-23 | 01.S4 |  |  | 1 | 1 | 0605 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2693 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2051 | FPRE0605_IF | 04.Enhancement | 02.IF - Intel Foundry | H2RA - 13th month bonus & Quarterly Performance Bonus (QPB) bonus accrual postings | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2051_2052_FPR_Transaction%20Processing_H2RA%20Custom%20program%20Intake%20form.pptx?d=w8cfa94db53ce44f8b80bfe26f79e1725&csf=1&web=1&e=TxtLCt | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | jenoronha@deloitte.com | 2025-03-04 06:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-23 | 01.S4 | FPRE0605_IP | 03.Medium | 0.2 | 0.2 | 0605 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2694 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2052 | FPRE0604_IP | 04.Enhancement | 01.IP - Intel Product | H2RA - Annual Performance Bonus (APB) ER taxes accrual & Quarterly Performance Bonus (QPB) ER taxes accrual | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2051_2052_FPR_Transaction%20Processing_H2RA%20Custom%20program%20Intake%20form.pptx?d=w8cfa94db53ce44f8b80bfe26f79e1725&csf=1&web=1&e=TxtLCt | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-23 | 01.S4 |  |  | 1 | 1 | 0604 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2695 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2052 | FPRE0604_IF | 04.Enhancement | 02.IF - Intel Foundry | H2RA - Annual Performance Bonus (APB) ER taxes accrual & Quarterly Performance Bonus (QPB) ER taxes accrual | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2051_2052_FPR_Transaction%20Processing_H2RA%20Custom%20program%20Intake%20form.pptx?d=w8cfa94db53ce44f8b80bfe26f79e1725&csf=1&web=1&e=TxtLCt | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2025-03-07 | 2025-03-14 | 2025-04-01 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | 2025-04-04 | 2025-04-18 | 2025-04-11 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | jenoronha@deloitte.com | 2025-03-04 06:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-09-23 | 01.S4 | FPRE0604_IP | 03.Medium | 0.2 | 0.2 | 0604 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2696 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2030 | FPRE0602 | 04.Enhancement | 05.CFIN | Reclassification of Vendor transactions from Default to Actual within CFIN | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B39E63587-052A-45B9-88A7-E06A0DC1B74E%7D&file=2030_Reclassification%20of%20VendorCustomer%20transactions%20from%20Default%20to%20Actual%20within%20CFIN.pptx&wdLOR=c7A60F320-C627-4316-8BE8-61FF1245ABDD&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-07-17 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-15 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-15 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-15 | [15 empty] | 2025-10-15 | 2025-10-15 | No |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 0602 |  | R3 ITC1 | [6 empty] | 2025-07-17 | 2025-07-17 | 2025-07-17 |  | 2025-09-15 | 2025-09-17 | 2025-09-15 |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [12 empty] | 2025-10-15 | 2025-10-15 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-03-21 | 2025-10-03 |  |  | 2025-12-05 |  |  |  | 0 | 08. Not Applicable | 1586 | [7 empty] | 4. Completed | 1. Approved no action | 12/08: FUT Approved. | 2025-10-03 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-15 | 2025-10-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2060 | FPRE0601 | 04.Enhancement | 05.CFIN | Reclassification of Customer transactions from Default to Actual within CFIN | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B39E63587-052A-45B9-88A7-E06A0DC1B74E%7D&file=2030_Reclassification%20of%20VendorCustomer%20transactions%20from%20Default%20to%20Actual%20within%20CFIN.pptx&wdLOR=c7A60F320-C627-4316-8BE8-61FF1245ABDD&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-09-04 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-07-30 | 2025-08-22 | 2025-08-29 | 2025-09-17 | 100% | 2025-09-16 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | 2025-09-05 | 2025-10-03 | 2025-10-03 | 100% | 2025-10-11 | [15 empty] | 2025-10-11 | 2025-10-11 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-03 | 2025-10-03 | 2025-10-03 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 01.S4 |  |  | 1 | 1 | 0601 |  | R3 ITC1 | [6 empty] | 2025-07-30 | 2025-07-30 | 2025-07-30 |  | 2025-09-16 | 2025-09-17 | 2025-09-16 |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [12 empty] | 2025-10-11 | 2025-10-11 |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | [5 empty] | 2025-03-21 | 2025-10-03 |  |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 2702 | [7 empty] | 1. On Track | 1. Approved no action | 11/24: FUT approved. | 2025-10-03 | N | 03. FPR |  |  |  |  | 1119 - SS update pending |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-11 | 2025-10-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1957 | FPRE0574_IP | 04.Enhancement | 01.IP - Intel Product | Margin analysis Dimensions creation | 03. FPR | 3.6 FPR - Cost and Profitability Analysis | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR_RICEFW-Margin%20analysis%20dimensions%20creation%20Intake%20Form%20.pptx?d=w8db17063a1584217be04b16ca44cfdda&csf=1&web=1&e=hTlQU0 | 01.Yes | 01.Yes |  | 2024-08-27 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2024-12-13 | 2024-10-18 | 100% | 2024-11-26 | 2024-11-25 | 2024-11-29 | 2024-11-29 | 100% | 2024-11-25 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | Yes |  | 2024-11-01 | 2024-11-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-20 | 2025-02-07 | 2024-11-08 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2025-01-17 | 2025-01-17 | 2025-01-17 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0574 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-12-13 | 2024-11-26 |  | 2024-11-25 | 2024-11-29 | 2024-11-25 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2024-11-26 | 2025-02-07 | 2024-11-26 | [5 empty] | 2024-12-13 | 2025-01-17 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 2339 | [10 empty] | 2025-01-17 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1956 | FPRE0573_IP | 04.Enhancement | 01.IP - Intel Product | Mass Asset Documents Reversal | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-080_0002_FPR_Mass%20Asset%20Documents%20Reversal.pptx?d=wdf53ff7c412f4733b492787eedfb3951&csf=1&web=1&e=W2D6gq | 01.Yes | 01.Yes |  | 2024-09-30 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-18 | 2024-10-18 | 100% | 2024-10-25 | 2025-03-07 | 2025-03-14 | 2025-07-25 | 100% | 2025-07-23 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-12 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-02 | 01.S4 |  |  | 2 | 2 | 0573 |  | R3 ITC1 | [6 empty] | 2024-10-25 | 2024-10-25 | 2024-10-25 |  | 2025-07-23 | 2025-07-25 | 2025-07-23 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-12 | 2025-08-15 | 2025-08-12 | [5 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 2338 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1956 | FPRE0573_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass Asset Documents Reversal | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-080_0002_FPR_Mass%20Asset%20Documents%20Reversal.pptx?d=wdf53ff7c412f4733b492787eedfb3951&csf=1&web=1&e=W2D6gq | 01.Yes | 01.Yes |  | 2024-08-27 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-11 | 2024-10-18 | 100% | 2024-10-25 | 2025-03-07 | 2025-03-14 | 2025-07-25 | 100% | 2025-07-23 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-23 | 2025-04-04 | 2025-04-18 | 2025-08-08 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-12 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-31 | 01.S4 | FPRE0573_IP | 02.High | 0.4 | 0.4 | 0573 |  | R3 ITC1 | [6 empty] | 2024-10-25 | 2024-10-25 | 2024-10-25 |  | 2025-07-23 | 2025-07-25 | 2025-07-23 |  | 2025-07-23 | 2025-08-08 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-12 | 2025-08-15 | 2025-08-12 | [5 empty] | 2024-10-11 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 2337 | [7 empty] | 1. On Track | 5. Object to be Cancelled |  | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-08 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1572 | FPRE0572_IP | 04.Enhancement | 01.IP - Intel Product | Mass Asset Capitalization | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-050-150_0002_FPR_Mass%20Asset%20Capitalization.pptx?d=wf52e1d627c0543558563d7c8878c03ad&csf=1&web=1&e=oP92my | 01.Yes | 01.Yes |  | 2024-09-30 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-15 | 2025-03-07 | 2025-03-14 | 2025-08-01 | 100% | 2025-08-29 | 2025-04-04 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-23 | 2025-04-04 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-09-30 11:25 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-10-02 | 01.S4 |  |  | 2 | 2 | 0572 | INT-CR0145 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-11-15 | 2024-11-15 | 2024-11-15 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2024-10-18 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 1735 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1572 | FPRE0572_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass Asset Capitalization | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-050-150_0002_FPR_Mass%20Asset%20Capitalization.pptx?d=wf52e1d627c0543558563d7c8878c03ad&csf=1&web=1&e=oP92my | 01.Yes | 01.Yes |  | 2024-08-27 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-23 | 2024-10-11 | 2024-10-18 | 100% | 2024-11-15 | 2025-03-07 | 2025-03-14 | 2025-08-01 | 100% | 2025-08-29 | 2025-03-28 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-23 | 2025-03-28 | 2025-04-18 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-10 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-08-27 08:04 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2024-08-31 | 01.S4 | FPRE0572_IP | 02.High | 0.4 | 0.4 | 0572 | INT-CR0145 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-11-15 | 2024-11-15 | 2024-11-15 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-09-10 | 2025-09-10 | [6 empty] | 2024-10-11 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 1734 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1548 | FPRE0571_IP | 04.Enhancement | 01.IP - Intel Product | DSD Matrix Rules to Update Depreciation Start Date in the Direct Cap Asset Master based on Goods Receipt | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-10-11 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-050-150-0001_FPR_Update%20DSD%20in%20Asset%20based%20on%20Goods%20Receipt.pptx?d=w204672185d6a43ce8167d4b482c23d39&csf=1&web=1&e=G7vGe2 | 01.Yes | 01.Yes |  | 2024-08-27 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-09 | 2025-06-13 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-11-05 06:26 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 |  |  | 1 | 1 | 0571 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-22 | 2025-09-10 | 2025-08-22 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2041 | [10 empty] | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1548 | FPRE0571_IF | 04.Enhancement | 02.IF - Intel Foundry | DSD Matrix Rules to Update Depreciation Start Date in the Direct Cap Asset Master based on Goods Receipt | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-10-11 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-050-150-0001_FPR_Update%20DSD%20in%20Asset%20based%20on%20Goods%20Receipt.pptx?d=w204672185d6a43ce8167d4b482c23d39&csf=1&web=1&e=G7vGe2 | 01.Yes | 01.Yes |  | 2024-08-27 | Shane Bethune | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-06-09 | 2025-06-13 | 2025-06-17 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | 2025-07-04 | 2025-07-18 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-08-27 08:04 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-12 | 01.S4 | FPRE0571_IP | 03.Medium | 0.2 | 0.2 | 0571 |  | R3 ITC1 | [6 empty] | 2025-03-21 | 2025-03-21 | 2025-03-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-22 | 2025-09-10 | 2025-08-22 | [5 empty] | 2025-03-21 | 2025-07-18 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 2040 | [10 empty] | 2025-07-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1913 | FPRE0551 | 04.Enhancement | 02.IF - Intel Foundry | SKF Actual Driver volume update from actual activity confirmation Automation | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1913_FPR_RICEFW%20Intake%20Form_Enhancement%20SKF%20PlanActual%20Volume.pptx?d=w4615d45b45624ced8c3a02dbf2c07ba5&csf=1&web=1&e=IRuLsX | 02.No | 01.Yes |  | 2024-08-16 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-01-31 | 2025-01-20 | 2025-02-07 | 2025-02-21 | 100% | 2025-01-31 | [15 empty] | 2025-01-31 | 2025-01-31 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-05-02 | Not Applicable | R3 Build & UT Sprint 13 | 2025-02-07 | 2025-02-07 | 2025-02-07 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-19 | 01.S4 |  |  | 1 | 1 | 0551 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-31 | 2025-02-21 | 2025-01-31 | 2025-01-31 | [12 empty] | 2025-01-31 | 2025-01-31 |  |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | [5 empty] | 2024-09-20 | 2025-02-07 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2045 | [10 empty] | 2025-02-07 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-01-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1866 | FPRE0550 | 04.Enhancement | 01.IP - Intel Product | Enhancement to update additive cost in IP based on Idoc of IF cost | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1519_FPR_RICEFW%20Intake%20Form_IF-IP_Populate%20cost%20data%20and%20Calculate%20WAC.pptx?d=wc73a896e7c394462a8debc10c0ddee7e&csf=1&web=1&e=SEP4tU | 02.No | 01.Yes |  | 2024-08-16 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-03-17 | 2025-03-21 | 2025-05-20 | 100% | 2025-05-27 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-27 | 2025-04-07 | 2025-04-18 | 2025-05-30 | 100% | 2025-05-27 | [15 empty] | 2025-05-27 | 2025-05-27 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-04-18 | 2025-04-18 | vasamohan@deloitte.com | 2024-08-16 13:52 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-19 | 01.S4 |  |  | 1 | 1 | 0550 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-05-27 | 2025-05-27 | 2025-05-27 |  | 2025-05-27 | 2025-05-30 | 2025-05-27 | 2025-05-27 | [12 empty] | 2025-05-27 | 2025-05-27 |  |  | 2025-08-13 | 2025-08-15 | 2025-08-13 | [5 empty] | 2024-09-20 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2178 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-30 | 2025-05-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1519 | FPRE0549 | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to a) update Cost and Production volume in custom table, b) calculate WAC in Custom table and send Idoc to IP system | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | Y | 2024-08-15 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1519_FPR_RICEFW%20Intake%20Form_IF-IP_Populate%20cost%20data%20and%20Calculate%20WAC.pptx?d=wc73a896e7c394462a8debc10c0ddee7e&csf=1&web=1&e=SEP4tU | 02.No | 01.Yes |  | 2024-08-16 | Shane Bethune | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | BY-PDH |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-02-24 | 2025-02-28 | 2025-03-24 | 100% | 2025-04-10 | 2025-03-03 | 2025-03-07 | 2025-03-28 | 100% | 2025-04-10 | 2025-03-03 | 2025-03-07 | 2025-03-28 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-03-07 | 2025-03-07 | 2025-03-07 | vasamohan@deloitte.com | 2024-08-16 13:52 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-08-19 | 01.S4 |  |  | 1 | 1 | 0549 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-09-20 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 2037 | [10 empty] | 2025-03-07 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-10 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1891 | FPRE0500_IP | 04.Enhancement | 01.IP - Intel Product | Rule for Transaction Price Allocation in BRIM vs SD | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B04B39B4A-C9C0-4E3F-AF2F-E5B8C272D761%7D&file=Allocation%20of%20Transaction%20Price.pptx&wdLOR=c7C46024D-9CAA-4DA8-BE62-572D66FEDF3F&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-04 | 2024-11-04 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-09 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-09 | [15 empty] | 2024-12-09 | 2024-12-09 | Yes |  | 2025-02-28 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-10 | 01.S4 |  |  | 1 | 1 | 0500 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-09 | 2024-12-20 | 2024-12-09 | 2024-12-09 | [12 empty] | 2024-12-09 | 2024-12-09 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-09-20 | 2024-12-20 |  |  | 2025-03-23 |  |  |  | 0 | 08. Not Applicable | 2330 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-12-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1891 | FPRE0500_IF | 04.Enhancement | 02.IF - Intel Foundry | Rule for Transaction Price Allocation in BRIM vs SD | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B04B39B4A-C9C0-4E3F-AF2F-E5B8C272D761%7D&file=Allocation%20of%20Transaction%20Price.pptx&wdLOR=c7C46024D-9CAA-4DA8-BE62-572D66FEDF3F&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-11-04 | 2024-11-04 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-09 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-12-09 | [15 empty] | 2024-12-09 | 2024-12-09 | Yes |  | 2025-02-28 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-03 | 01.S4 | FPRE0500_IP | 03.Medium | 0.2 | 0.2 | 0500 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-09 | 2024-12-20 | 2024-12-09 | 2024-12-09 | [12 empty] | 2024-12-09 | 2024-12-09 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-09-20 | 2024-12-20 |  |  | 2025-03-23 |  |  |  | 0 | 08. Not Applicable | 2329 | [7 empty] | 1. On Track | 13. Blocked by Other RICEFW |  | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-12-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1902 | FPRE0499_IP | 04.Enhancement | 01.IP - Intel Product | Substitution and Validation rule user exit | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8E397D9A-D731-48FE-99BC-E72D104F1508%7D&file=DC-040-010-0006_FPR_Assets%20subsitution%20and%20validation%20rule%20user%20exit.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-07 | 2025-02-21 | N | 100% | 2025-03-07 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-15 00:48 | 10 | 2024-08-12 | 01.S4 |  |  | 1 | 1 | 0499 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | [5 empty] | 2024-09-20 | 2025-01-17 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 1704 | [10 empty] | 2025-01-17 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | Yes | Remove company code 102 in substitution and validation | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-15 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1902 | FPRE0499_IF | 04.Enhancement | 02.IF - Intel Foundry | Substitution and Validation rule user exit | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-08-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8E397D9A-D731-48FE-99BC-E72D104F1508%7D&file=DC-040-010-0006_FPR_Assets%20subsitution%20and%20validation%20rule%20user%20exit.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-08-02 | Shane Bethune | 01.Approved | 2024-08-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | 2024-12-16 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-07 | [15 empty] | 2025-01-07 | 2025-01-07 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-07 | 2025-02-21 | N | 100% | 2025-03-07 | Not Applicable | R3 Build & UT Sprint 11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-12 | 01.S4 | FPRE0499_IP | 03.Medium | 0.2 | 0.2 | 0499 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 |  | 2025-01-07 | 2025-01-17 | 2025-01-07 | 2025-01-07 | [12 empty] | 2025-01-07 | 2025-01-07 |  |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | [5 empty] | 2024-09-20 | 2025-01-17 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 1703 | [10 empty] | 2025-01-17 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-17 | 2025-01-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1516 | FPRE0495_IP | 04.Enhancement | 01.IP - Intel Product | Custom Fields in WBS element Master Data | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/687_FPR_%20WBS%20Custom%20field%20Enhancement.pptx?d=wa2c497078bca4781aeaf7cca92cc9f3c&csf=1&web=1&e=WF0U0A | 02.No | 01.Yes |  | 2024-08-01 | Shane Bethune | 01.Approved | 2024-08-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-05 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-07 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-11-08 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-05 | 2024-11-25 | 2024-11-15 | N | 100% | 2025-01-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-10-25 | 2024-10-25 | 2024-10-25 | vasamohan@deloitte.com | 2024-08-01 09:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-07 | 01.S4 |  |  | 1 | 1 | 0495 |  | R3 ITC1 |  |  | 14966 (FPRE0495-Custom Fields in WBS element Master Data_DI0) |  |  |  | 2024-08-15 | 2024-08-15 | 2024-08-15 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | [5 empty] | 2024-08-09 | 2024-10-25 |  |  | 2024-11-25 |  |  |  | 0 | 08. Not Applicable | 2035 | [10 empty] | 2024-10-25 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1516 | FPRE0495_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Fields in WBS element Master Data | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/687_FPR_%20WBS%20Custom%20field%20Enhancement.pptx?d=wa2c497078bca4781aeaf7cca92cc9f3c&csf=1&web=1&e=WF0U0A | 02.No | 01.Yes | FPRI0188 | 2024-08-01 | Shane Bethune | 01.Approved | 2024-08-01 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-08-05 | 2024-08-09 | 2024-08-09 | 100% | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-10-07 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-11-08 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-05 | 2024-11-25 | 2024-11-15 | N | 100% | 2025-01-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-10-25 | 2024-10-25 | 2024-10-25 | vasamohan@deloitte.com | 2024-08-01 09:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2024-08-07 | 01.S4 | FPRE0495_IP | 03.Medium | 0.2 | 0.2 | 0495 |  | R3 ITC1 |  |  | 14969 (FPRE0495-Custom Fields in WBS element Master Data_BI1) |  |  |  | 2024-08-15 | 2024-08-15 | 2024-08-15 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-01-20 | 2025-01-20 | 2025-01-20 | [5 empty] | 2024-08-09 | 2024-10-25 |  |  | 2024-11-25 |  |  |  | 0 | 08. Not Applicable | 2034 | [10 empty] | 2024-10-25 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1895 | FPRE0477 | 04.Enhancement | 01.IP - Intel Product | Rebate for Direct Customer to Rebate of Intransit deferrals for Direct & Disti Customers | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR_Team03_RAR_Console%20ID_148.pptx?d=w112126537a33460b9b67a7cc7a404fb2&csf=1&web=1&e=YylJ6T | 02.No | 01.Yes | FPRI1241 | 2024-07-23 | Shane Bethune | 01.Approved | 2024-07-23 | Std. | 02.No | 02.Intel |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-04-04 | 2025-04-11 | 2025-06-17 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | 2025-05-02 | 2025-05-16 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-06 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0477 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2024-09-20 | 2025-05-16 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 1700 | [10 empty] | 2025-05-16 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1894 | FPRE0476 | 04.Enhancement | 01.IP - Intel Product | Accounting for Stock Rotation | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR_Team03_RAR_Console%20ID_147.pptx?d=wb54fac82c1d8400b9e56f01fad1c0094&csf=1&web=1&e=GGKMr5 | 02.No | 01.Yes |  | 2024-07-23 | Shane Bethune | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 02.Intel |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-08-26 | 2024-08-26 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-11-20 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-11-20 | [15 empty] | 2024-11-20 | 2024-11-20 | Yes |  | 2025-02-16 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-03-14 | Not Applicable | R3 Build & UT Sprint 11 | 2024-11-22 | 2024-11-22 | 2024-11-22 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0476 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-20 | 2024-12-20 | 2024-11-20 | 2024-11-20 | [12 empty] | 2024-11-20 | 2024-11-20 |  |  | 2025-03-14 | 2025-03-14 | 2025-03-14 | [5 empty] | 2024-08-23 | 2024-11-22 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 1699 | [10 empty] | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1893 | FPRE0475 | 04.Enhancement | 01.IP - Intel Product | Accounting for reserves for unissued returns credit note & Rebate Return Accrual. | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR_Team03_RAR_Console%20ID_31.pptx?d=wbd60a265b6ce48759153180cce3ba5d2&csf=1&web=1&e=aOdA5w | 02.No | 01.Yes | FPRI1241 | 2024-07-23 | Shane Bethune | 01.Approved | 2024-07-23 | Std. | 02.No | 02.Intel |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-01-13 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | 2025-01-20 | 2025-01-24 | 2025-01-17 | 100% | 2025-01-08 | [15 empty] | 2025-01-08 | 2025-01-08 | Yes |  | 2025-02-28 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-04-30 | Not Applicable | R3 Build & UT Sprint 13 | 2025-01-24 | 2025-01-24 | 2025-01-24 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0475 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-01-08 | 2025-01-24 | 2025-01-08 | 2025-01-08 | [12 empty] | 2025-01-08 | 2025-01-08 |  |  | 2025-04-30 | 2025-04-30 | 2025-04-30 | [5 empty] | 2024-09-20 | 2025-01-24 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 2332 | [10 empty] | 2025-01-24 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-24 | 2025-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1892 | FPRE0474 | 04.Enhancement | 01.IP - Intel Product | Accounting for technical return reserve | 03. FPR | 3.3 FPR - Revenue Recognition & Reporting | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/FPR_Team03_RAR_Console%20ID_30.pptx?d=wd55a958ced76469ab21592413bba38c9&csf=1&web=1&e=DUudSf | 02.No | 01.Yes |  | 2024-07-23 | Shane Bethune | 01.Approved | 2024-07-23 | Non-Std. | 02.No | 02.Intel |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-08-26 | 2024-08-26 | 2024-10-04 | 100% | 2024-10-01 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-11-25 | 2024-10-07 | 2024-11-22 | 2024-12-20 | 100% | 2024-11-25 | [15 empty] | 2024-11-25 | 2024-11-25 | Yes |  | 2025-02-16 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-04-30 | Not Applicable | R3 Build & UT Sprint 13 | 2024-11-22 | 2024-11-22 | 2024-11-22 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0474 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-10-01 | 2024-10-04 | 2024-10-01 |  | 2024-11-25 | 2024-12-20 | 2024-11-25 | 2024-11-25 | [12 empty] | 2024-11-25 | 2024-11-25 |  |  | 2025-04-30 | 2025-04-30 | 2025-04-30 | [5 empty] | 2024-08-23 | 2024-11-22 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 2331 | [10 empty] | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-11-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1530 | FPRE0462 | 04.Enhancement | 05.CFIN | Enhancement to develop automatic creation of payment advice number in the AR company code to clear AR open items automatically for IC Settlements when the payment run is done. | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-08-01 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-110-007_FPR_RICEFW%20Intake%20Form_v2.0%20.pptx?d=wef3f270a918e4a7fb09bf961672cb6f0&csf=1&web=1&e=4Gq3yz | 02.No | 01.Yes |  | 2024-07-19 | Shane Bethune | 01.Approved | 2024-08-01 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-08-05 | 2024-08-16 | 2024-08-16 | 100% | 2024-09-13 | 2025-03-17 | 2025-03-21 | 2025-06-20 | 100% | 2025-07-21 | 2025-04-07 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | 2025-04-07 | 2025-04-18 | 2025-07-11 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-08-13 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-15 | 2025-08-13 | N | 100% | 2025-10-24 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-07-19 07:03 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0462 |  | R3 ITC1 | [6 empty] | 2024-09-13 | 2024-09-13 | 2024-09-13 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | [5 empty] | 2024-08-16 | 2025-03-21 |  |  | 2025-04-17 |  |  |  | 0 | 08. Not Applicable | 2039 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/23 - Awaiting approval. Revised FUT document shared today | 2025-04-18 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1571 | FPRE0430 | 04.Enhancement | 05.CFIN | Enhancement for automatic creation of MT210 (pre-advice) message for IC settlements, B2B, IC loans, etc. | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-020-004_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=w452937c77e2346fe82673e3fadb795df&csf=1&web=1&e=YVC5Cj | 01.Yes | 01.Yes | FPRI1338 | 2024-06-28 | Angela Wolf | 01.Approved | 2024-07-23 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-11-18 | 2024-12-12 | 2024-12-13 | 100% | 2024-12-12 | 2025-03-07 | 2025-03-14 | 2025-03-25 | 100% | 2025-04-02 | 2025-04-04 | 2025-04-18 | 2025-04-03 | 100% | 2025-04-11 | 2025-04-04 | 2025-04-18 | 2025-04-03 | 100% | 2025-04-11 | [15 empty] | 2025-04-11 | 2025-04-11 | Yes |  | 2025-06-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-10-14 | Not Applicable | R3 Build & UT Sprint 19 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-06-28 04:56 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0430 |  | R3 ITC1 | [6 empty] | 2024-12-12 | 2024-12-13 | 2024-12-12 |  | 2025-04-02 | 2025-04-02 | 2025-04-02 |  | 2025-04-11 | 2025-04-18 | 2025-04-11 | 2025-04-11 | [12 empty] | 2025-04-11 | 2025-04-11 |  |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | [5 empty] | 2024-12-12 | 2025-04-18 |  |  | 2025-05-16 |  |  |  | 0 | 06. Banks | 1733 | [7 empty] | 2. At Risk | 17. FUT In progress | 10/10: Call scheduled with Intel today Defect 3579 , Conditional sign-off expected by 10/10 | 2025-04-18 | N | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-11 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1739 | FPRE0429_IP | 04.Enhancement | 01.IP - Intel Product | Utility program to look up inactive cost center and derive replacement cost center | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Replacement%20Cost%20Center_V1.pptx?d=w59dc09223bc74b8687602abb22e75563&csf=1&web=1&e=4h2AeP | 01.Yes | 01.Yes |  | 2024-06-28 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-08 | 2024-08-26 | 2024-08-26 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-02-28 | Not Applicable | R3 Build & UT Sprint 11 | 2024-10-25 | 2024-10-25 | 2024-10-25 | jenoronha@deloitte.com | 2024-06-28 11:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0429_CFIN | 03.Medium | 0.2 | 0.2 | 0429 |  | R3 ITC1 | [6 empty] | 2024-08-08 | 2024-08-23 | 2024-08-08 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | [5 empty] | 2024-08-23 | 2024-10-25 |  |  | 2025-02-21 |  |  |  | 0 |  | 2196 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-10-25 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1739 | FPRE0429_IF | 04.Enhancement | 02.IF - Intel Foundry | Utility program to look up inactive cost center and derive replacement cost center | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Replacement%20Cost%20Center_V1.pptx?d=w59dc09223bc74b8687602abb22e75563&csf=1&web=1&e=4h2AeP | 01.Yes | 01.Yes |  | 2024-06-28 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-08 | 2024-08-26 | 2024-08-26 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-02-28 | Not Applicable | R3 Build & UT Sprint 11 | 2024-10-25 | 2024-10-25 | 2024-10-25 | jenoronha@deloitte.com | 2024-06-28 11:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0429_CFIN | 03.Medium | 0.2 | 0.2 | 0429 |  | R3 ITC1 | [6 empty] | 2024-08-08 | 2024-08-23 | 2024-08-08 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | [5 empty] | 2024-08-23 | 2024-10-25 |  |  | 2025-02-21 |  |  |  | 0 |  | 2195 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-10-25 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1739 | FPRE0429_CFIN | 04.Enhancement | 05.CFIN | Utility program to look up inactive cost center and derive replacement cost center | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Replacement%20Cost%20Center_V1.pptx?d=w59dc09223bc74b8687602abb22e75563&csf=1&web=1&e=4h2AeP | 01.Yes | 01.Yes |  | 2024-06-28 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-08 | 2024-08-26 | 2024-08-26 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-25 | 2024-10-25 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-02-28 | Not Applicable | R3 Build & UT Sprint 11 | 2024-10-25 | 2024-10-25 | 2024-10-25 | pgaroo@deloitte.com | 2024-06-28 04:56 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0429 |  | R3 ITC1 | [6 empty] | 2024-08-08 | 2024-08-23 | 2024-08-08 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-02-28 | 2025-02-28 | 2025-02-28 | [5 empty] | 2024-08-23 | 2024-10-25 |  |  | 2025-02-21 |  |  |  | 0 |  | 2194 | [10 empty] | 2024-10-25 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1358 | FPRE0428_IP | 04.Enhancement | 01.IP - Intel Product | Program to replace inactive cost centers in Assets | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Replacement%20Cost%20Center_V1.pptx?d=w59dc09223bc74b8687602abb22e75563&csf=1&web=1&e=4h2AeP | 02.No | 01.Yes |  | 2024-06-28 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-11-20 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-11-20 | [15 empty] | 2024-11-20 | 2024-11-20 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-03-07 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-28 04:56 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0428 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-20 | 2024-12-20 | 2024-11-20 | 2024-11-20 | [12 empty] | 2024-11-20 | 2024-11-20 |  |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | [5 empty] | 2024-08-23 | 2024-12-20 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2438 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1358 | FPRE0428_IF | 04.Enhancement | 02.IF - Intel Foundry | Program to replace inactive cost centers in Assets | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Replacement%20Cost%20Center_V1.pptx?d=w59dc09223bc74b8687602abb22e75563&csf=1&web=1&e=4h2AeP | 02.No | 01.Yes |  | 2024-06-28 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No | NA | NA | NA | NA | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2024-10-28 | 2024-10-28 | 2024-11-08 | 100% | 2024-11-26 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-11-20 | 2024-11-11 | 2024-12-20 | 2024-12-20 | 100% | 2024-11-20 | [15 empty] | 2024-11-20 | 2024-11-20 | Yes |  | 2025-02-14 | 2025-02-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-01-27 | 2025-02-21 | 2025-02-21 | N | 100% | 2025-03-07 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | jenoronha@deloitte.com | 2024-06-28 11:22 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0428_IP | 03.Medium | 0.2 | 0.2 | 0428 |  | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-20 | 2024-12-20 | 2024-11-20 | 2024-11-20 | [12 empty] | 2024-11-20 | 2024-11-20 |  |  | 2025-03-07 | 2025-03-07 | 2025-03-07 | [5 empty] | 2024-08-23 | 2024-12-20 |  |  | 2025-02-21 |  |  |  | 0 | 08. Not Applicable | 2437 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-11-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1586 | FPRE0425 | 04.Enhancement | 05.CFIN | Treasury Funding - Enhancement to support multiple Treasury Funding scenarios and from Multiple Intel teams | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_CFR.pptx?d=wde49673c21924b2c82c2fb99e792c491&csf=1&web=1&e=W3IPRW | 02.No | 01.Yes | FPRI0224 | 2024-07-01 | Angela Wolf | 01.Approved | 2024-07-23 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2024-10-21 | 2024-11-15 | 2024-11-15 | 100% | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-04-22 | 100% | 2025-08-04 | 2025-02-07 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | 2025-02-07 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-27 07:53 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 2 | 2 | 0425 |  | R3 ITC1 | [6 empty] | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | [5 empty] | 2024-11-15 | 2025-02-21 |  |  | 2025-03-21 |  |  |  | 0 |  | 1739 | [9 empty] | 09/08: Businss is requesting for documentation for the dependent objects. ETA 09/05. Conditional Approval ETA 09/09 | 2025-02-21 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 756 | FPRE0407_IP | 04.Enhancement | 01.IP - Intel Product | Period Close in CFin, IP & IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B27BB68CF-0AD4-4F3A-A17B-5BCB11C641A0%7D&file=756_Period%20Close%20in%20CFin%2C%20IP%20%26%20IF.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-21 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA |  |  | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | [15 empty] | 2024-10-07 | 2024-10-07 | Yes |  | 2024-11-15 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-15 | 2024-11-15 | N | 100% | 2024-12-06 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-11 | 2024-10-11 | 2024-10-11 | pgaroo@deloitte.com | 2024-06-21 03:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0407_CFIN | 03.Medium | 0.2 | 0.2 | 0407 |  | R3 ITC1 | [6 empty] | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-07 | 2024-10-11 | 2024-10-07 | 2024-10-07 | [12 empty] | 2024-10-07 | 2024-10-07 |  |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | [5 empty] | 2024-07-26 | 2024-10-11 |  |  | 2024-11-15 |  |  |  | 0 | 08. Not Applicable | 2530 | [7 empty] | 1. On Track | 16. Intel Owned |  | 2024-10-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-11 | 2024-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 756 | FPRE0407_IF | 04.Enhancement | 02.IF - Intel Foundry | Period Close in CFin, IP & IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B27BB68CF-0AD4-4F3A-A17B-5BCB11C641A0%7D&file=756_Period%20Close%20in%20CFin%2C%20IP%20%26%20IF.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-21 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA |  |  | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | [15 empty] | 2024-10-07 | 2024-10-07 | Yes |  | 2024-11-15 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-15 | 2024-11-15 | N | 100% | 2024-12-06 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-11 | 2024-10-11 | 2024-10-11 | pgaroo@deloitte.com | 2024-06-21 03:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0407_CFIN | 03.Medium | 0.2 | 0.2 | 0407 |  | R3 ITC1 | [6 empty] | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-07 | 2024-10-11 | 2024-10-07 | 2024-10-07 | [12 empty] | 2024-10-07 | 2024-10-07 |  |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | [5 empty] | 2024-07-26 | 2024-10-11 |  |  | 2024-11-15 |  |  |  | 0 | 08. Not Applicable | 2529 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-10-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-11 | 2024-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 756 | FPRE0407_CFIN | 04.Enhancement | 05.CFIN | Period Close in CFin, IP & IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B27BB68CF-0AD4-4F3A-A17B-5BCB11C641A0%7D&file=756_Period%20Close%20in%20CFin%2C%20IP%20%26%20IF.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-21 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA |  |  | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-10-07 | [15 empty] | 2024-10-07 | 2024-10-07 | Yes |  | 2024-11-15 | 2024-11-15 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-11-12 | 2024-11-15 | 2024-11-15 | N | 100% | 2024-12-06 | Not Applicable | R3 Build & UT Sprint 8 | 2024-10-11 | 2024-10-11 | 2024-10-11 | pgaroo@deloitte.com | 2024-06-21 03:27 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0407 |  | R3 ITC1 | [6 empty] | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-07 | 2024-10-11 | 2024-10-07 | 2024-10-07 | [12 empty] | 2024-10-07 | 2024-10-07 |  |  | 2024-12-06 | 2024-12-06 | 2024-12-06 | [5 empty] | 2024-07-26 | 2024-10-11 |  |  | 2024-11-15 |  |  |  | 0 | 08. Not Applicable | 2528 | [7 empty] | 1. On Track | 17. FUT In progress |  | 2024-10-11 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-11 | 2024-10-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 764 | FPRE0375_IP | 04.Enhancement | 01.IP - Intel Product | GL Interface – IDOC status from IF & IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2025-02-07 | 2025-02-14 | 2025-02-14 | 100% | 2025-02-09 | 2025-03-07 | 2025-03-21 | 2025-02-28 | 100% | 2025-02-09 | 2025-03-07 | 2025-03-21 | 2025-02-28 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 | Yes |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-18 05:17 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | FPRE0375_CFIN | 03.Medium | 0.2 | 0.2 | 0375 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-02-09 | 2025-03-21 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | [5 empty] | 2024-07-26 | 2025-03-21 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2633 | [9 empty] | 08/14 Conditionally Approved. | 2025-03-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-03-21 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 764 | FPRE0375_IF | 04.Enhancement | 02.IF - Intel Foundry | GL Interface – IDOC status from IF & IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2025-02-14 | 100% | 2025-02-09 | 2025-02-03 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-09 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 100% | 2025-02-09 | [15 empty] | 2025-02-09 | 2025-02-09 | Yes |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-02-21 | 2025-02-21 | jenoronha@deloitte.com | 2024-12-16 04:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | FPRE0375_CFIN | 03.Medium | 0.2 | 0.2 | 0375 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2025-02-09 | 2025-02-14 | 2025-02-09 |  | 2025-02-09 | 2025-02-28 | 2025-02-09 | 2025-02-09 | [12 empty] | 2025-02-09 | 2025-02-09 |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | [5 empty] | 2024-07-26 | 2025-02-21 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2632 | [9 empty] | 08/14 Conditionally Approved. | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-28 | 2025-02-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 764 | FPRE0375_CFIN | 04.Enhancement | 05.CFIN | GL Interface – IDOC status from IF & IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2025-02-03 | 2025-02-07 | 2025-08-13 | 100% | 2025-08-09 | 2025-02-03 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-02-03 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-17 | [15 empty] | 2025-02-17 | 2025-02-17 | Yes |  | 2025-03-17 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-21 | 2025-02-21 | 2025-02-21 | vasamohan@deloitte.com | 2025-01-23 11:04 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1 | 0375 |  | R3 ITC1 | [6 empty] | 2024-07-26 | 2024-07-26 |  |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-17 | [12 empty] | 2025-02-17 | 2025-02-17 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-07-26 | 2025-02-21 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2631 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 763 | FPRE0374_IP | 04.Enhancement | 01.IP - Intel Product | GL Interface- Managing 999+ GL line items | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-25 | 2024-07-29 | 2024-07-29 | 2025-04-22 | 100% | 2025-08-04 | 2024-09-16 | 2024-12-20 | 2025-04-24 | 100% | 2025-08-04 | 2024-09-16 | 2024-12-20 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-12 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | jenoronha@deloitte.com | 2025-03-04 07:01 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | FPRE0374_CFIN | 03.Medium | 0.2 | 0.2 | 0374 |  | R3 ITC1 | [6 empty] | 2024-07-25 | 2024-07-26 | 2024-07-25 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | [5 empty] | 2024-07-26 | 2024-12-20 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2630 | [7 empty] | 1. On Track | 3. Awaiting Approval | 08/11 FUT conditionally approved | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 763 | FPRE0374_IF | 04.Enhancement | 02.IF - Intel Foundry | GL Interface- Managing 999+ GL line items | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-25 | 2024-07-29 | 2024-07-29 | 2025-04-22 | 100% | 2025-08-04 | 2024-09-16 | 2024-12-20 | 2025-04-24 | 100% | 2025-08-04 | 2024-09-16 | 2024-12-20 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-12 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | jenoronha@deloitte.com | 2025-03-04 07:01 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | FPRE0374_CFIN | 03.Medium | 0.2 | 0.2 | 0374 |  | R3 ITC1 | [6 empty] | 2024-07-25 | 2024-07-26 | 2024-07-25 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | [5 empty] | 2024-07-26 | 2024-12-20 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2629 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix | 08/11 FUT conditionally approved | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 763 | FPRE0374_CFIN | 04.Enhancement | 05.CFIN | GL Interface- Managing 999+ GL line items | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-25 | 2024-07-29 | 2024-07-29 | 2025-08-13 | 100% | 2025-08-09 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2024-12-17 | 2024-09-16 | 2024-12-20 | 2025-01-31 | 100% | 2024-12-17 | [15 empty] | 2024-12-17 | 2024-12-17 | Yes |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-18 05:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0374 |  | R3 ITC1 | [6 empty] | 2024-07-25 | 2024-07-26 | 2024-07-25 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2024-12-17 | 2025-01-31 | 2024-12-17 | 2024-12-17 | [12 empty] | 2024-12-17 | 2024-12-17 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-07-26 | 2024-12-20 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 2628 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 9 |  | 2025-01-31 | 2024-12-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 762 | FPRE0373 | 04.Enhancement | 05.CFIN | GL Interface – Splitting of enriched files and populating staging table | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-07 | 2024-08-14 | 2024-08-21 | 2024-09-13 | 100% | 2024-11-26 | 2025-01-31 | 2025-02-21 | 2025-02-14 | 100% | 2025-02-18 | 2025-01-31 | 2025-02-21 | 2025-02-14 | 100% | 2025-02-18 | [15 empty] | 2025-02-18 | 2025-02-18 | Yes |  | 2025-03-17 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-18 05:17 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 2 | 2 | 0373 |  | R3 ITC1 | [6 empty] | 2024-08-07 | 2024-08-07 | 2024-08-07 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-18 | 2025-02-21 | 2025-02-18 | 2025-02-18 | [12 empty] | 2025-02-18 | 2025-02-18 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-08-02 | 2025-02-21 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2627 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 761 | FPRE0372 | 04.Enhancement | 05.CFIN | GL Interface - Incoming file processing and Simulation | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/761_GL%20Interface%20-%20RICEFW%20Package_V1.pptx?d=w908b4f9c79354546accfc08017300931&csf=1&web=1&e=NdAwjh | 01.Yes | 01.Yes | FPRI0376, FPRI0377, FPRI0379 | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  | NA | NA | NA | 2024-06-24 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-07 | 2024-08-05 | 2024-08-05 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-01-31 | 2024-09-16 | 2024-12-20 | 2025-02-21 | 100% | 2025-01-31 | [15 empty] | 2025-01-31 | 2025-01-31 | Yes |  | 2025-03-17 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-03-21 | N | 100% | 2025-03-21 | Not Applicable | R3 Build & UT Sprint 11 | 2024-12-20 | 2024-12-20 | 2024-12-20 | pgaroo@deloitte.com | 2024-06-18 05:17 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 2 | 2 | 0372 |  | R3 ITC1 | [6 empty] | 2024-08-07 | 2024-08-07 | 2024-08-07 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-01-31 | 2025-02-21 | 2025-01-31 | 2025-01-31 | [12 empty] | 2025-01-31 | 2025-01-31 |  |  | 2025-03-21 | 2025-03-21 | [6 empty] | 2024-08-02 | 2024-12-20 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2537 | [10 empty] | 2024-12-20 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-01-31 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 837 | FPRE0360_IP | 04.Enhancement | 01.IP - Intel Product | Reclassify GL Accounts for Balance Carryforwards - IP | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/837_Reclassify%20GL%20Accounts%20for%20Balance%20Carryforwards.pptx?d=wc7e7270a226f4169878d59dcde67ad70&csf=1&web=1&e=8vbQp8 | 02.No | 01.Yes |  | 2024-06-17 | Shane Bethune | 01.Approved | 2024-06-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-06-24 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-09 | 100% | 2024-11-26 | 2024-08-12 | 2024-09-19 | 2024-09-19 | 100% | 2024-11-26 | 2024-08-12 | 2024-09-19 | 2024-09-19 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-08-30 | 2024-09-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-23 | 2024-09-06 | 2024-09-06 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-09-19 | 2024-09-19 | 2024-09-19 | vasamohan@deloitte.com | 2024-06-17 12:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 0.5 | 0.5 | 0360 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-07-19 | 2024-09-19 |  |  | 2024-09-06 |  |  |  | 0 | 08. Not Applicable | 1517 | [10 empty] | 2024-09-19 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 837 | FPRE0360_IF | 04.Enhancement | 02.IF - Intel Foundry | Reclassify GL Accounts for Balance Carryforwards - IF | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/837_Reclassify%20GL%20Accounts%20for%20Balance%20Carryforwards.pptx?d=wc7e7270a226f4169878d59dcde67ad70&csf=1&web=1&e=8vbQp8 | 02.No | 01.Yes |  | 2024-06-17 | Shane Bethune | 01.Approved | 2024-06-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2024-06-24 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-09 | 100% | 2024-11-26 | 2024-08-12 | 2024-09-19 | 2024-09-19 | 100% | 2024-11-26 | 2024-08-12 | 2024-09-19 | 2024-09-19 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-08-30 | 2024-09-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-23 | 2024-09-06 | 2024-09-06 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-09-19 | 2024-09-19 | 2024-09-19 | vasamohan@deloitte.com | 2024-06-17 12:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | FPRE0360_IP | 04.Low | 0.1 | 0.1 | 0360 |  | R3 ITC1 | [6 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-07-19 | 2024-09-19 |  |  | 2024-09-06 |  |  |  | 0 | 08. Not Applicable | 1516 | [10 empty] | 2024-09-19 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 711 | FPRE0328_IP | 04.Enhancement | 01.IP - Intel Product | Validations on Asset updates, transfer and retirement | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-02 | 2024-11-22 | 2025-01-17 | 100% | 2024-12-12 | 2024-09-02 | 2024-11-22 | 2025-01-17 | 100% | 2024-12-12 | [15 empty] | 2024-12-12 | 2024-12-12 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0328 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-12 | 2025-01-17 | 2024-12-12 | 2024-12-12 | [12 empty] | 2024-12-12 | 2024-12-12 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2024-11-22 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2129 | [10 empty] | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2025-01-17 | 2024-12-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 711 | FPRE0328_IF | 04.Enhancement | 02.IF - Intel Foundry | Validations on Asset updates, transfer and retirement | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-02 | 2024-11-22 | 2025-01-17 | 100% | 2024-12-12 | 2024-09-02 | 2024-11-22 | 2025-01-17 | 100% | 2024-12-12 | [15 empty] | 2024-12-12 | 2024-12-12 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0328_IP | 03.Medium | 0.2 | 0.2 | 0328 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-12 | 2025-01-17 | 2024-12-12 | 2024-12-12 | [12 empty] | 2024-12-12 | 2024-12-12 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2024-11-22 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2128 | [10 empty] | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2025-01-17 | 2024-12-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 710 | FPRE0326_IP | 04.Enhancement | 01.IP - Intel Product | Mass upload tool to asset update, transfer and retire (S4 Fiori functionality only) | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-09-13 | 100% | 2024-11-26 | 2025-02-07 | 2025-02-21 | 2025-02-14 | 100% | 2025-02-10 | 2025-02-07 | 2025-02-21 | 2025-02-14 | 100% | 2025-02-10 | [15 empty] | 2025-02-10 | 2025-02-10 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0326 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-10 | 2025-02-21 | 2025-02-10 | 2025-02-10 | [12 empty] | 2025-02-10 | 2025-02-10 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2025-02-21 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2127 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-21 | 2025-02-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 710 | FPRE0326_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass upload tool to asset update, transfer and retire (S4 Fiori functionality only) | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-29 | 2025-01-13 | 2025-01-17 | 2024-09-13 | 100% | 2024-11-26 | 2025-01-17 | 2025-01-24 | 2025-02-14 | 100% | 2025-02-10 | 2025-01-17 | 2025-01-24 | 2025-02-14 | 100% | 2025-02-10 | [15 empty] | 2025-02-10 | 2025-02-10 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2025-01-24 | 2025-01-24 | 2025-01-24 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0326_IP | 03.Medium | 0.2 | 0.2 | 0326 |  | R3 ITC1 | [6 empty] | 2024-07-29 | 2024-07-29 | 2024-07-29 |  | 2024-11-26 | 2025-01-17 | 2024-11-26 |  | 2025-02-10 | 2025-02-14 | 2025-02-10 | 2025-02-10 | [12 empty] | 2025-02-10 | 2025-02-10 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2025-01-24 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2126 | [10 empty] | 2025-01-24 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-02-14 | 2025-02-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 708 | FPRE0324_IP | 04.Enhancement | 01.IP - Intel Product | Custom Fiori App for Asset update, transfer, scrap, and retire based on Report and selection criteria | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-02 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-10 | 2024-09-02 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-10 | [15 empty] | 2024-12-10 | 2024-12-10 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-09 | Not Applicable | R3 Build & UT Sprint 13 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 2 | 0324 |  | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-10 | 2024-12-20 | 2024-12-10 | 2024-12-10 | [12 empty] | 2024-12-10 | 2024-12-10 |  |  | 2025-05-09 | 2025-05-09 | 2025-05-09 | [5 empty] | 2024-07-26 | 2024-11-22 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2588 | [7 empty] | 1. On Track | 5. Object to be Cancelled |  | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 708 | FPRE0324_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Fiori App for Asset update, transfer, scrap, and retire based on Report and selection criteria | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=i4GGG0&nav=eyJzSWQiOjIxNDc0ODI3MzIsImNJZCI6MTcxOTM5MDU1Mn0&xsdata=MDV8MDJ8fDgzOThmZjRjNzYzYTQ4YTVkY2MzMDhkYzhhYWFiNjIwfDM2ZGE0NWYxZGQyYzRkMWZhZjEzNWFiZTQ2Yjk5OTIxfDB8MHw2Mzg1Mzc3MTI5ODQ0NDgxOTV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPak01WXpjek1XRmpMVEUzT0RJdE5HVXhZeTA1TXpoaExXSXhNRE0xTVRZek5qUTNaVjg0T1dWak5XSTBaQzAxT0RBeUxUUTNNbVV0WWpreE1DMHpNR1k0WTJFNE5HSmxNRGRBZFc1eExtZGliQzV6Y0dGalpYTXZiV1Z6YzJGblpYTXZNVGN4T0RFM05EUTVPREV5TWc9PXw2NzgzMDBhMWQ4ZTU0NTRhZGNjMzA4ZGM4YWFhYjYyMHxjY2EwNzhkMTkxZWE0OTlkOGZkOWI5MGJhODQ3MjUzMA%3D%3D&sdata=c2l2QkdDZlJSVXdUeFNUMzZiUFQ0RVJmWWdIZVJkMERkUG9PUVpNeVJHUT0%3D&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cpgaroo%40deloitte.com&OR=Teams-HL&CT=1718175416545&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyNy8yNDA1MDUwMTYwMSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-07-26 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-02 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-10 | 2024-09-02 | 2024-11-22 | 2024-12-20 | 100% | 2024-12-10 | [15 empty] | 2024-12-10 | 2024-12-10 | Yes |  | 2025-03-21 | 2025-03-21 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-14 | 2025-03-21 | N | 100% | 2025-05-30 | Not Applicable | R3 Build & UT Sprint 14 | 2024-11-22 | 2024-11-22 | 2024-11-22 | pgaroo@deloitte.com | 2024-06-11 10:23 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0324_IP | 02.High | 0.4 | 0.4 | 0324 |  | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-07-26 | 2024-07-26 | 2024-07-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-12-10 | 2024-12-20 | 2024-12-10 | 2024-12-10 | [12 empty] | 2024-12-10 | 2024-12-10 |  |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | [5 empty] | 2024-07-26 | 2024-11-22 |  |  | 2025-03-14 |  |  |  | 0 | 08. Not Applicable | 2587 | [10 empty] | 2024-11-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-12-20 | 2024-12-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 769 | FPRE0322_IP | 04.Enhancement | 01.IP - Intel Product | Fiori Dashboard to display/edit pre-paid amortization for PO​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A885 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2025-01-07 | 2025-04-04 | 2025-04-11 | 2025-04-22 | 100% | 2025-08-04 | 2025-04-25 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | 2025-04-25 | 2025-05-16 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-06-11 10:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 2 | 2 | 0322 | INT-CR0160 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2025-01-07 | 2025-01-07 | 2025-01-07 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-07-26 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2649 | [10 empty] | 2025-05-16 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 769 | FPRE0322_IF | 04.Enhancement | 02.IF - Intel Foundry | Fiori Dashboard to display/edit pre-paid amortization for PO​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A885 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-09-13 | 2025-02-07 | 2025-02-14 | 2025-03-24 | 100% | 2025-04-10 | 2025-03-07 | 2025-03-21 | 2025-03-25 | 100% | 2025-04-10 | 2025-03-07 | 2025-03-21 | 2025-03-25 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 | Yes |  | 2025-04-18 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-30 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-21 | 2025-03-21 | 2025-03-21 | jenoronha@deloitte.com | 2024-12-19 09:38 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 | FPRE0322_IP | 02.High | 0.4 | 0.4 | 0322 | INT-CR0160 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-09-13 | 2024-09-13 | 2024-09-13 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 |  | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-07-26 | 2025-03-21 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2647 | [10 empty] | 2025-03-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-10 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 766 | FPRE0321_IP | 04.Enhancement | 01.IP - Intel Product | Fiori Dashboard to display/edit accruals for PO​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2025-01-07 | 2025-02-24 | 2025-02-28 | 2024-09-13 | 100% | 2024-11-26 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | 2025-03-10 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | [15 empty] | 2025-02-18 | 2025-02-18 | Yes |  | 2024-12-13 | 2024-12-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-25 | 2025-06-20 | 2024-12-13 | N | 100% | 2025-07-18 | Not Applicable | R3 Build & UT Sprint 15 | 2025-03-21 | 2025-03-21 | 2025-03-21 | pgaroo@deloitte.com | 2024-06-11 10:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 2 | 2 | 0321 | INT-CR0160 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2025-01-07 | 2025-01-07 | 2025-01-07 |  | 2024-11-26 | 2025-02-28 | 2024-11-26 |  | 2025-02-18 | 2025-03-21 | 2025-02-18 | 2025-02-18 | [12 empty] | 2025-02-18 | 2025-02-18 |  |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | [5 empty] | 2024-07-26 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2635 | [10 empty] | 2025-03-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-03-21 | 2025-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 766 | FPRE0321_IF | 04.Enhancement | 02.IF - Intel Foundry | Fiori Dashboard to display/edit accruals for PO​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-09 | 2025-02-07 | 2025-02-14 | 2025-08-13 | 100% | 2025-08-09 | 2025-03-07 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | 2025-03-07 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-18 | [15 empty] | 2025-02-18 | 2025-02-18 | Yes |  | 2024-12-13 | 2024-12-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-30 | 2025-04-25 | 2024-12-13 | N | 100% | 2025-07-18 | Not Applicable | R3 Build & UT Sprint 15 | 2025-03-21 | 2025-03-21 | 2025-03-21 | jenoronha@deloitte.com | 2024-12-19 09:38 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 | FPRE0321_IP | 02.High | 0.4 | 0.4 | 0321 | INT-CR0160 | R3 ITC1 |  |  |  | 01.Freestyle Application |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-02-18 | 2025-03-21 | 2025-02-18 | 2025-02-18 | [12 empty] | 2025-02-18 | 2025-02-18 |  |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | [5 empty] | 2024-07-26 | 2025-03-21 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2637 | [10 empty] | 2025-03-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 10 |  | 2025-03-21 | 2025-02-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 767 | FPRE0320_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement to read PO data and create manual accrual object​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2025-01-07 | 2025-04-04 | 2025-04-11 | 2024-09-13 | 100% | 2025-08-29 | 2025-05-02 | 2025-05-16 | 2025-02-14 | 100% | 2025-02-13 | 2025-05-02 | 2025-05-16 | 2025-02-14 | 100% | 2025-02-13 | [15 empty] | 2025-02-13 | 2025-02-13 | Yes |  | 2025-01-20 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-01-24 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-06-11 10:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 0320 | INT-CR0160 | R3 ITC1 | [6 empty] | 2025-01-07 | 2025-01-07 | 2025-01-07 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-02-13 | 2025-05-16 | 2025-02-13 | 2025-02-13 | [12 empty] | 2025-02-13 | 2025-02-13 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | [5 empty] | 2024-07-26 | 2025-05-16 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2639 | [9 empty] | 09/15 : Conditionally approved by Client. Smartsheet update pending. | 2025-05-16 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-05-16 | 2025-02-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 767 | FPRE0320_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement to read PO data and create manual accrual object​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-09 | 2025-02-07 | 2025-02-14 | 2025-08-13 | 100% | 2025-08-29 | 2025-03-14 | 2025-03-21 | 2025-02-14 | 100% | 2025-02-13 | 2025-03-14 | 2025-03-21 | 2025-02-14 | 100% | 2025-02-13 | [15 empty] | 2025-02-13 | 2025-02-13 | Yes |  | 2025-01-20 | 2025-01-24 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-01-24 | N | 100% | 2025-09-15 | Not Applicable | R3 Build & UT Sprint 18 | 2025-03-21 | 2025-03-21 | 2025-03-21 | jenoronha@deloitte.com | 2024-12-19 09:38 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 | FPRE0320_IP | 03.Medium | 0.2 | 0.2 | 0320 | INT-CR0160 | R3 ITC1 | [6 empty] | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 |  | 2025-02-13 | 2025-03-21 | 2025-02-13 | 2025-02-13 | [12 empty] | 2025-02-13 | 2025-02-13 |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | [5 empty] | 2024-07-26 | 2025-03-21 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2641 | [9 empty] | 09/15 : Conditionally approved by Client. Smartsheet update pending. | 2025-03-21 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 10 |  | 2025-03-21 | 2025-02-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 768 | FPRE0319_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement for accrual posting notification​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2025-01-07 | 2024-07-29 | 2024-07-29 | 2025-01-17 | 100% | 2025-01-08 | 2024-09-16 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-24 | 2024-09-16 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-24 | [15 empty] | 2025-02-24 | 2025-02-24 | Yes |  | 2025-05-16 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-16 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-14 | 2025-02-14 | 2025-02-14 | pgaroo@deloitte.com | 2024-06-11 10:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 |  |  | 1 | 1 | 0319 | INT-CR0160 | R3 ITC1 | [6 empty] | 2025-01-07 | 2025-01-07 | 2025-01-07 |  | 2025-01-08 | 2025-01-17 | 2025-01-08 |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | [12 empty] | 2025-02-24 | 2025-02-24 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-07-26 | 2025-02-14 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2645 | [10 empty] | 2025-02-14 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-24 | 2025-02-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 768 | FPRE0319_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement for accrual posting notification​ | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-06-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/IAO%20ERP%20OSC%20-%205.13.2024.pptx?d=w2b846e77fe9f486fa2009ee27a656d26&csf=1&web=1&e=KXUm0J&nav=eyJzSWQiOjM1MCwiY0lkIjozMzQ1NzIzMjkwfQ&CT=1718129869161&OR=Outlook-Body&CID=48582A03-24D2-4412-8D6C-0E4C5474A884 | 01.Yes | 01.Yes |  | 2024-06-12 | Shane Bethune | 01.Approved | 2024-05-14 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-09 | 2024-07-29 | 2024-07-29 | 2025-08-13 | 100% | 2025-08-09 | 2024-09-16 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-24 | 2024-09-16 | 2025-02-14 | 2025-02-21 | 100% | 2025-02-24 | [15 empty] | 2025-02-24 | 2025-02-24 | Yes |  | 2025-05-09 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-07-18 | Not Applicable | R3 Build & UT Sprint 15 | 2025-02-14 | 2025-02-14 | 2025-02-14 | pgaroo@deloitte.com | 2024-12-11 03:38 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 01.S4 | FPRE0319_IP | 03.Medium | 0.2 | 0.2 | 0319 | INT-CR0160 | R3 ITC1 | [6 empty] | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 2025-08-09 | 2025-08-13 | 2025-08-09 |  | 2025-02-24 | 2025-02-24 | 2025-02-24 | 2025-02-24 | [12 empty] | 2025-02-24 | 2025-02-24 |  |  | 2025-07-18 | 2025-07-18 | 2025-07-18 | [5 empty] | 2024-07-26 | 2025-02-14 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2643 | [10 empty] | 2025-02-14 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-02-24 | 2025-02-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 684 | FPRE0315_IP | 04.Enhancement | 01.IP - Intel Product | Activation of custom enhancement tab on portfolio bucket for custom fields. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/684_FPR_Enhancement%20Intake%20form.pptx?d=w65c1a5873bb94788aaaf4875f84bf755&csf=1&web=1&e=Nemj8f | 01.Yes | 01.Yes | FPRI0981_IP | 2024-06-11 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-01 | 2024-09-02 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-01 | [15 empty] | 2024-10-01 | 2024-10-01 | Yes |  | 2024-10-09 | 2024-10-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-12-06 | 2024-10-18 | 2024-10-18 | N | 100% | 2024-12-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-09-27 | 2024-09-27 | 2024-09-27 | pgaroo@deloitte.com | 2024-06-11 10:18 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0315 |  | R3 ITC1 |  |  | 14890 (FPRE0315-Custom enhance tab on port bucket_GAP_DI0) |  |  |  | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | [12 empty] | 2024-10-01 | 2024-10-01 |  |  | 2024-12-20 | 2024-12-20 | 2024-12-20 | [5 empty] | 2024-07-19 | 2024-09-27 |  |  | 2024-10-18 |  |  |  | 0 | 08. Not Applicable | 2687 | [7 empty] | 1. On Track | 6. FUT Defect Under Fix |  | 2024-09-27 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-01 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 684 | FPRE0315_IF | 04.Enhancement | 02.IF - Intel Foundry | Activation of custom enhancement tab on portfolio bucket for custom fields. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-06-28 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/684_FPR_Enhancement%20Intake%20form.pptx?d=w65c1a5873bb94788aaaf4875f84bf755&csf=1&web=1&e=Nemj8f | 01.Yes | 01.Yes | FPRI0981_IF | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-19 | 2024-07-19 | 100% | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-01 | 2024-09-02 | 2024-09-27 | 2024-09-27 | 100% | 2024-10-01 | [15 empty] | 2024-10-01 | 2024-10-01 | Yes |  | 2024-10-11 | 2024-10-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-10-07 | 2024-10-18 | 2024-10-18 | N | 100% | 2024-12-20 | Not Applicable | R3 Build & UT Sprint 9 | 2024-09-27 | 2024-09-27 | 2024-09-27 | pgaroo@deloitte.com | 2024-06-18 01:46 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0315_IP | 03.Medium | 0.2 | 0.2 | 0315 |  | R3 ITC1 |  |  | 14954 (FPRE0315-Custom enhance tab on port bucket_GAP_BI1) |  |  |  | 2024-07-22 | 2024-07-22 | 2024-07-22 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | [12 empty] | 2024-10-01 | 2024-10-01 |  |  | 2024-12-20 | 2024-12-20 | 2024-12-20 | [5 empty] | 2024-07-19 | 2024-09-27 |  |  | 2024-10-18 |  |  |  | 0 | 08. Not Applicable | 2686 | [10 empty] | 2024-09-27 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 6 |  | 2024-10-01 | 2024-10-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 686 | FPRE0314_IP | 04.Enhancement | 01.IP - Intel Product | Smart numbering for portfolio items. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/686_FPR_Enhancement%20Intake%20form.pptx?d=w15436c8034a24797a4c72714dfc18fc3&csf=1&web=1&e=7z8iCm | 01.Yes | 01.Yes |  | 2024-06-11 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-24 | 2024-07-15 | 2024-07-15 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-08-30 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-09-27 | 2024-10-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-23 | 2024-10-04 | 2024-10-04 | N | 100% | 2024-10-22 | Not Applicable | R3 Build & UT Sprint 7 | 2024-09-13 | 2024-09-13 | 2024-09-13 | pgaroo@deloitte.com | 2024-06-11 10:18 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0314 |  | R3 ITC1 |  |  | 14956 (FPRE0314-Smart numbering for portfolio items_GAP_DI0) |  |  |  | 2024-07-24 | 2024-07-24 | 2024-07-24 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-10-22 | 2024-10-22 | 2024-10-22 | [5 empty] | 2024-07-12 | 2024-09-13 |  |  | 2024-10-04 |  |  |  | 0 | 08. Not Applicable | 2689 | [10 empty] | 2024-09-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 686 | FPRE0314_IF | 04.Enhancement | 02.IF - Intel Foundry | Smart numbering for portfolio items. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | Y | 2024-07-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/686_FPR_Enhancement%20Intake%20form.pptx?d=w15436c8034a24797a4c72714dfc18fc3&csf=1&web=1&e=7z8iCm | 01.Yes | 01.Yes |  | 2024-06-19 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-24 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-24 | 2024-07-15 | 2024-07-15 | 2024-08-30 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | 2024-09-02 | 2024-09-13 | 2024-09-13 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 | Yes |  | 2024-09-27 | 2024-10-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-23 | 2024-10-04 | 2024-10-04 | N | 100% | 2024-10-22 | Not Applicable | R3 Build & UT Sprint 7 | 2024-09-13 | 2024-09-13 | 2024-09-13 | pgaroo@deloitte.com | 2024-06-18 01:46 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0314_IP | 03.Medium | 0.2 | 0.2 | 0314 |  | R3 ITC1 |  |  | 14957 (FPRE0314-Smart numbering for portfolio items_GAP_BI1) |  |  |  | 2024-07-24 | 2024-07-24 | 2024-07-24 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2024-10-22 | 2024-10-22 | 2024-10-22 | [5 empty] | 2024-07-12 | 2024-09-13 |  |  | 2024-10-04 |  |  |  | 0 | 08. Not Applicable | 2688 | [10 empty] | 2024-09-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 337 | FPRE0289_IP | 04.Enhancement | 01.IP - Intel Product | Update XREF1, XREF2 and XREF3 fields in subledger line items | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA617FB7B-257C-4F8F-B096-5A0195733A0C%7D&file=DC-110-080-IDM-0005_FPR_Intercompany_Payment%20Currency%20Update.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-05 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-04-22 | 100% | 2025-08-04 | 2025-02-14 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | 2025-02-14 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-06-04 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | jenoronha@deloitte.com | 2025-02-21 04:12 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0289_CFIN | 03.Medium | 0.2 | 0.2 | 0289 |  | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-21 | 2025-03-03 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | [5 empty] | 2025-03-21 | 2025-02-21 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2610 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW |  | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 337 | FPRE0289_IF | 04.Enhancement | 02.IF - Intel Foundry | Update XREF1, XREF2 and XREF3 fields in subledger line items | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA617FB7B-257C-4F8F-B096-5A0195733A0C%7D&file=DC-110-080-IDM-0005_FPR_Intercompany_Payment%20Currency%20Update.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-05 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-04-22 | 100% | 2025-08-04 | 2025-02-14 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | 2025-02-14 | 2025-02-21 | 2025-04-24 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-06-04 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | jenoronha@deloitte.com | 2025-02-21 04:14 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0289_CFIN | 03.Medium | 0.2 | 0.2 | 0289 |  | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-21 | 2025-03-03 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | [5 empty] | 2025-03-21 | 2025-02-21 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2609 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 337 | FPRE0289_CFIN | 04.Enhancement | 05.CFIN | Update XREF1, XREF2 and XREF3 fields in subledger line items | 03. FPR | 3.4 FPR - Intercompany | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA617FB7B-257C-4F8F-B096-5A0195733A0C%7D&file=DC-110-080-IDM-0005_FPR_Intercompany_Payment%20Currency%20Update.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-06-05 | Shane Bethune | 01.Approved | 2024-06-28 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-05-20 | 100% | 2025-05-24 | 2025-02-14 | 2025-02-21 | 2025-05-23 | 100% | 2025-05-24 | 2025-02-14 | 2025-02-21 | 2025-05-23 | 100% | 2025-05-24 | [15 empty] | 2025-05-24 | 2025-05-24 | Yes |  | 2025-04-18 | 2025-04-18 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-04-18 | N | 100% | 2025-06-04 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-06-04 07:05 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0289 |  | R3 ITC1 | [6 empty] | 2025-03-03 | 2025-03-21 | 2025-03-03 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 |  | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | [12 empty] | 2025-05-24 | 2025-05-24 |  |  | 2025-06-04 | 2025-06-04 | 2025-06-04 | [5 empty] | 2025-03-21 | 2025-02-21 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 2608 | [10 empty] | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-05-24 | 2025-05-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 704 | FPRE0287_IP | 04.Enhancement | 01.IP - Intel Product | Need to enhance Fiori screen to capture business process and the approver while submitting the Manual Journal Entry (MJE). | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/704_DC-010-030_Enhancement_Fiori%20Screen_RICEFW_Form.pptx?d=wc197b1c19af145aa8f294464b12c89ae&csf=1&web=1&e=FJTIbs | 02.No | 01.Yes |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-07-18 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-30 | 2024-08-30 | 2024-08-30 | vasamohan@deloitte.com | 2024-05-31 11:06 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0287_CFIN | 03.Medium | 0.2 | 0.2 | 0287 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-14 | 2024-08-30 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2581 | [10 empty] | 2024-08-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-30 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 704 | FPRE0287_IF | 04.Enhancement | 02.IF - Intel Foundry | Need to enhance Fiori screen to capture business process and the approver while submitting the Manual Journal Entry (MJE). | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/704_DC-010-030_Enhancement_Fiori%20Screen_RICEFW_Form.pptx?d=wc197b1c19af145aa8f294464b12c89ae&csf=1&web=1&e=FJTIbs | 02.No | 01.Yes |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-07-18 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-30 | 2024-08-30 | 2024-08-30 | vasamohan@deloitte.com | 2024-06-03 08:09 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRE0287_CFIN | 03.Medium | 0.2 | 0.2 | 0287 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-14 | 2024-08-30 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2580 | [10 empty] | 2024-08-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-30 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 704 | FPRE0287_CFIN | 04.Enhancement | 05.CFIN | Need to enhance Fiori screen to capture business process and the approver while submitting the Manual Journal Entry (MJE). | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/704_DC-010-030_Enhancement_Fiori%20Screen_RICEFW_Form.pptx?d=wc197b1c19af145aa8f294464b12c89ae&csf=1&web=1&e=FJTIbs | 02.No | 01.Yes |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-07-18 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | 2024-07-15 | 2024-08-30 | 2024-08-30 | 100% | 2024-08-14 | [15 empty] | 2024-08-14 | 2024-08-14 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-30 | 2024-08-30 | 2024-08-30 | vasamohan@deloitte.com | 2024-06-03 08:09 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0287 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | 2024-08-14 | 2024-08-30 | 2024-08-14 | 2024-08-14 | [12 empty] | 2024-08-14 | 2024-08-14 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-30 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2579 | [10 empty] | 2024-08-30 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-30 | 2024-08-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 705 | FPRE0286_IP | 04.Enhancement | 01.IP - Intel Product | Mass upload of the same supporting document as an attachment to multiple JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/705_DC-010-030_Enahncement_Mass%20upload%20of%20supporting%20document%20_RICEFW_Form.pptx?d=w7a6330e23f994240999e391a17a2544a&csf=1&web=1&e=jjNUCE | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-06-28 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | [15 empty] | 2024-08-01 | 2024-08-01 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-13 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-12 | 2024-08-12 | 2024-08-12 | vasamohan@deloitte.com | 2024-06-03 08:09 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | FPRE0286_CFIN | 03.Medium | 0.2 | 0.2 | 0286 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-06-28 | 2024-07-12 | 2024-06-28 |  | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-01 | [12 empty] | 2024-08-01 | 2024-08-01 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-12 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2584 | [10 empty] | 2024-08-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-12 | 2024-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 705 | FPRE0286_IF | 04.Enhancement | 02.IF - Intel Foundry | Mass upload of the same supporting document as an attachment to multiple JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/705_DC-010-030_Enahncement_Mass%20upload%20of%20supporting%20document%20_RICEFW_Form.pptx?d=w7a6330e23f994240999e391a17a2544a&csf=1&web=1&e=jjNUCE | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-06-28 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | [15 empty] | 2024-08-01 | 2024-08-01 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-13 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-12 | 2024-08-12 | 2024-08-12 | vasamohan@deloitte.com | 2024-06-03 08:09 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 | FPRE0286_CFIN | 03.Medium | 0.2 | 0.2 | 0286 |  | R3 ITC1 |  |  |  | 02.Template |  |  | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-06-28 | 2024-07-12 | 2024-06-28 |  | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-01 | [12 empty] | 2024-08-01 | 2024-08-01 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-12 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2583 | [10 empty] | 2024-08-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-12 | 2024-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 705 | FPRE0286_CFIN | 04.Enhancement | 05.CFIN | Mass upload of the same supporting document as an attachment to multiple JEs | 03. FPR | 3.1 FPR - GL Close & Consolidate | 10. Object Complete | Y | 2024-05-31 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/705_DC-010-030_Enahncement_Mass%20upload%20of%20supporting%20document%20_RICEFW_Form.pptx?d=w7a6330e23f994240999e391a17a2544a&csf=1&web=1&e=jjNUCE | 02.No | 02.No |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-05-31 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-06-05 | 2024-06-21 | 2024-06-21 | 100% | 2024-06-18 | 2024-06-24 | 2024-06-24 | 2024-07-12 | 100% | 2024-06-28 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | 2024-07-15 | 2024-08-12 | 2024-08-12 | 100% | 2024-08-01 | [15 empty] | 2024-08-01 | 2024-08-01 | Yes |  | 2024-09-11 | 2024-09-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-13 | 2024-09-16 | 2024-09-16 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-12 | 2024-08-12 | 2024-08-12 | vasamohan@deloitte.com | 2024-05-31 11:06 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 1 | 1 | 0286 |  | R3 ITC1 | [6 empty] | 2024-06-18 | 2024-06-21 | 2024-06-18 |  | 2024-06-28 | 2024-07-12 | 2024-06-28 |  | 2024-08-01 | 2024-08-12 | 2024-08-01 | 2024-08-01 | [12 empty] | 2024-08-01 | 2024-08-01 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-08-12 |  |  | 2024-09-16 |  |  |  | 0 | 08. Not Applicable | 2582 | [10 empty] | 2024-08-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-12 | 2024-08-01 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 565 | FPRE0285 | 04.Enhancement | 05.CFIN | Cash App rules engine for matching incoming payments with payment advice | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-06-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/565_OR-140-001_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wfe70b094fd95487b8b9f45cb7eb5e7e6&csf=1&web=1&e=X60TJ4 | 02.No | 01.Yes |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-06-07 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  | NA |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-08-21 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | 2025-09-01 | 2025-09-12 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-24 | 2025-11-05 | N | 100% | 2026-01-12 | Not Applicable | R3 Build & UT Sprint 22 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-05-31 01:40 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 4 | 4 | 0285 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-08-21 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-12 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | [5 empty] | 2024-09-20 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 08. Not Applicable | 1684 | [7 empty] | 4. Completed | 1. Approved no action | 01/12: FUT Approved. | 2025-09-12 | N | 03. FPR |  |  |  |  | 1119: ETA 1125. To be approved w/o CR#? |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 566 | FPRE0284 | 04.Enhancement | 05.CFIN | Mass upload of payment advice | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-06-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/566_OR-140-002_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=w624e05eefb704bb1985f1638e67d2e95&csf=1&web=1&e=ZLsFM9 | 02.No | 01.Yes | FPRI1105 | 2024-05-31 | Shane Bethune | 01.Approved | 2024-06-07 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2025-06-17 | 100% | 2025-07-21 | 2025-02-07 | 2025-02-21 | 2025-06-20 | 100% | 2025-07-21 | 2025-02-07 | 2025-02-21 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-24 | 2025-03-21 | 2025-07-16 | N | 100% | 2025-08-18 | Not Applicable | R3 Build & UT Sprint 17 | 2025-02-21 | 2025-02-21 | 2025-02-21 | pgaroo@deloitte.com | 2024-05-31 01:40 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0284 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | [5 empty] | 2024-09-20 | 2025-02-21 |  |  | 2025-03-21 |  |  |  | 0 | 08. Not Applicable | 1658 | [7 empty] | 2. At Risk | 18. FUT Not Started | 08/14 FUT conditionally approved | 2025-02-21 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 663 | FPRE0282 | 04.Enhancement | 05.CFIN | RPA BOT for collecting and transforming customer payment advice into standard format for SAP | 03. FPR | 3.10 FPR - Accounts Receivable & Collections | 10. Object Complete | Y | 2024-06-07 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/663_OR-140-090_FPR_RICEFW%20Intake%20Form_v2.0.pptx?d=wb96bb6655f7a42b6bc1904d49320878c&csf=1&web=1&e=V0r7Eh | 02.No | 01.Yes |  | 2024-05-31 | Shane Bethune | 01.Approved | 2024-06-07 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA |  |  | NA | 2024-07-29 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-23 | 2025-01-27 | 2025-01-31 | 2025-02-14 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | 2025-02-03 | 2025-04-18 | 2025-04-18 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 | Yes |  | 2025-06-11 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-09 | Not Applicable | R3 Build & UT Sprint 15 | 2025-04-18 | 2025-04-18 | 2025-04-18 | pgaroo@deloitte.com | 2024-05-31 01:40 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 |  | 04.S4 BOT |  |  | 0.5 | 0.5 | 0282 | INT-CR0068 | R3 ITC1 | [6 empty] | 2024-08-23 | 2024-08-23 | 2024-08-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | [5 empty] | 2024-08-23 | 2025-04-18 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 1938 | [10 empty] | 2025-04-18 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 514 | FPRE0240 | 04.Enhancement | 05.CFIN | Treasury Payment/funding Request - Enhancement to support multiple Treasury Payment scenarios and Funding requests from Multiple Intel teams | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-07-25 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B580759F0-2843-4492-8FD6-A28C3D42DDD4%7D&file=MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_TPR.pptx&wdLOR=c7E05ECCF-D468-4A49-BAFB-569FEF939098&action=edit&mobileredirect=true | 02.No | 01.Yes | FPRI0224 | 2024-05-21 | Shane Bethune | 01.Approved | 2024-05-31 | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2024-10-21 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-26 | 2025-05-12 | 2025-05-16 | 2025-08-01 | 100% | 2025-07-23 | 2025-07-21 | 2025-08-01 | 2025-08-13 | 100% | 2025-07-23 | 2025-07-21 | 2025-08-01 | 2025-08-13 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 | No |  | 2025-10-08 | 2025-10-17 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-17 | 2025-10-17 | N | 100% | 2025-12-23 | Not Applicable | R3 Build & UT Sprint 21 | 2025-08-01 | 2025-08-01 | 2025-08-01 | pgaroo@deloitte.com | 2024-05-17 09:21 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 2 | 0240 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-23 | 2025-08-01 | 2025-07-23 |  | 2025-07-23 | 2025-08-13 | 2025-07-23 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | [5 empty] | 2024-11-15 | 2025-04-18 |  |  | 2025-05-15 |  |  |  | 0 | 06. Banks | 2393 | [7 empty] | 1. On Track | 1. Approved no action | 12/22: Conditionally Approved. | 2025-08-01 | N | 03. FPR |  |  |  |  | 1119: ETA 1125 |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 20 | FPRE0049 | 04.Enhancement | 05.CFIN | Enhancement - Custom Fields in Manage bank Accounts | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | Y | 2024-04-16 | 01. Approved | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/MR-010-0001_FPR_RICEFW%20Intake%20Form_v1.0.pdf?csf=1&web=1&e=wpabcY | 01.Yes | 01.Yes |  | 2024-04-09 | Shane Bethune | 01.Approved | 2024-04-18 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-05-05 | 2024-05-31 | 2024-05-31 | 100% | 2024-05-02 | 2024-06-03 | 2024-06-03 | 2024-05-13 | 100% | 2024-05-14 | 2024-05-14 | 2024-05-22 | 2024-05-22 | 100% | 2024-06-07 | 2024-05-14 | 2024-05-22 | 2024-05-22 | 100% | 2024-06-07 | [15 empty] | 2024-06-07 | 2024-06-07 | Yes |  | 2024-08-30 | 2024-09-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-27 | 2024-09-11 | 2024-09-11 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-05-22 | 2024-05-22 | 2024-05-22 | pgaroo@deloitte.com | 2024-04-09 01:36 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1 | 0049 |  | R3 ITC1 | [6 empty] | 2024-05-02 | 2024-05-31 | 2024-05-02 |  | 2024-05-14 | 2024-06-03 | 2024-05-14 |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | [12 empty] | 2024-06-07 | 2024-06-07 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-05-31 | 2024-05-22 |  |  | 2024-09-11 |  |  |  | 0 | 08. Not Applicable | 1424 | [10 empty] | 2024-05-22 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 2 |  | 2024-06-07 | 2024-06-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3190 | FPRC1724_IP | 03.Conversion | 01.IP - Intel Product | Creation of output template with consumption data | 03. FPR | 3.1 FPR - GL Close & Consolidate | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD2EE242A-4881-4FB3-8C6B-8A6D5877D738%7D&file=INT%20CR1441%20-%20Upload%20the%20BODS%20converted%20consumption%20data%20into%20S4.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-13 | 100% | 2026-02-12 | 2026-02-09 | 2026-02-27 | 2026-02-10 | 100% | 2026-02-12 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-17 | 2026-02-09 | 2026-02-13 | 2026-03-27 | 92% | 2026-03-27 | [15 empty] | 2026-03-27 | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 |  | 60% | 50% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 55% | 2026-03-27 |  | R3 Build & UT Sprint 23+ | 2026-02-13 | 2026-02-13 | 2026-02-13 | jenoronha@deloitte.com | 2026-01-30 08:27 | cell-link@smartsheet.com | 2026-04-07 02:36 | 6 |  | 01.S4 |  |  | 2 | 2.9 | 1724 | INT-CR1441 | R3 ITC1 | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-12 |  | 2026-02-12 | 2026-02-27 | 2026-02-12 |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | [18 empty] | 2026-03-27 | 2026-03-27 | [5 empty] | 2026-02-06 | 2026-02-13 |  |  | 2026-03-04 |  |  |  | 0 |  | 3423 | [7 empty] | 3. Off Track | 17. FUT In progress | 04/07: Modification was done on Friday and shared the file. EAT for signoff is 04/08 | 2026-02-13 | Y | 03. FPR |  |  |  | 03/24 : BODS build is in progress. ETA for Build completion is 03/27. FUT completion ETA is 04/10 | Build will be completed by 3/24. | 2. Risk | On track for S23+ | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-03-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3190 | FPRC1724_IF | 03.Conversion | 02.IF - Intel Foundry | Creation of output template with consumption data | 03. FPR | 3.1 FPR - GL Close & Consolidate | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD2EE242A-4881-4FB3-8C6B-8A6D5877D738%7D&file=INT%20CR1441%20-%20Upload%20the%20BODS%20converted%20consumption%20data%20into%20S4.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-01-27 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-28 | 2026-02-06 | 2026-02-13 | 100% | 2026-02-12 | 2026-02-09 | 2026-02-27 | 2026-02-10 | 100% | 2026-02-12 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-02-17 | 2026-02-09 | 2026-02-13 | 2026-03-27 | 92% | 2026-03-27 | [15 empty] | 2026-03-27 | 2026-03-27 |  |  | 2026-03-27 | 2026-03-27 |  | 60% | 50% |  |  |  | 02. In Progress | 02. In Progress |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 55% | 2026-03-27 |  | R3 Build & UT Sprint 23+ | 2026-02-13 | 2026-02-13 | 2026-02-13 | jenoronha@deloitte.com | 2026-01-30 08:27 | cell-link@smartsheet.com | 2026-04-07 02:30 | 6 |  | 01.S4 | FPRC1724_IP | 02.High | 0.6 | 0.87 | 1724 | INT-CR1441 | R3 ITC1 | [5 empty] | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-12 |  | 2026-02-12 | 2026-02-27 | 2026-02-12 |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | [18 empty] | 2026-03-27 | 2026-03-27 | [5 empty] | 2026-02-06 | 2026-02-13 |  |  | 2026-03-04 |  |  |  | 0 |  | 3424 | [7 empty] | 3. Off Track | 17. FUT In progress | 04/07: Modification was done on Friday and shared the file. EAT for signoff is 04/08 | 2026-02-13 | Y | 03. FPR |  |  |  | 03/24 : BODS build is in progress. ETA for Build completion is 03/27. FUT completion ETA is 04/10 | Build will be completed by 3/24. | 2. Risk | On track for S23+ | FUT In Progress | Delayed - Past Sprint | R3 Build & UT Sprint 23+ |  | 2026-03-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3016 | FPRC1565 | 03.Conversion | 01.IP - Intel Product | Convert active delegate relationships for Timesheet approval | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3016_IP%20Intel%20Federal%20Migrate%20Active%20Delegate%20Relationships%20for%20Timesheet%20Approval.pptx?d=w11983748a13d42f6a6c4bcbc748dc392&csf=1&web=1&e=yX7eVT | 02.No | 01.Yes |  | 2025-08-13 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-22 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 100% | 2025-09-18 | 2025-09-16 | 2025-09-24 | 2025-09-24 | 100% | 2025-10-03 | 2025-09-15 | 2025-10-08 | 2025-11-05 | 100% | 2025-10-17 | [15 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-07-24 03:57 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-08-13 | 01.S4 |  |  | 2 | 2.9 | 1565 |  | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-09-10 | 2025-08-22 |  | 2025-09-18 | 2025-09-18 | 2025-09-18 |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-17 | [12 empty] | 2025-10-17 | 2025-10-17 |  |  | 2025-11-13 | 2025-12-05 | 2025-11-13 | [5 empty] | 2025-09-10 | 2025-10-08 |  |  | 2025-12-05 |  |  |  | 0 |  | 3193 | [7 empty] | 4. Completed |  |  | 2025-10-08 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2970 | FPRC1493 | 03.Conversion | 02.IF - Intel Foundry | Conversion of WIP values as per Component structure in S/4 - IP | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/ID_2970_Standard%20Cost%20conversion%20and%20Upload%20WIP%20at%20cost%20comp%20structure%20to%20S4.pptx?d=w0975b786ce9e4bf480de10ed2bdbda32&csf=1&web=1&e=JSwsIb |  |  |  | 2025-06-10 | Shane Bethune | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-14 | 2025-09-15 | 100% | 2025-09-18 | 2025-10-14 | 2025-10-17 | 2025-09-24 | 100% | 2025-09-25 | 2025-10-20 | 2025-11-30 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-30 | 2025-11-30 | 2025-11-30 | jenoronha@deloitte.com | 2025-06-09 06:12 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-19 | 01.S4 |  |  | 2 | 2.9 | 1493 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-18 | 2025-10-14 | 2025-09-18 |  | 2025-09-25 | 2025-10-17 | 2025-09-25 | 2025-11-05 | [12 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-08 | 2026-01-09 | 2025-12-08 | [5 empty] | 2025-07-16 | 2025-11-30 |  |  | 2026-01-09 |  |  |  | 0 |  | 3089 | [7 empty] | 4. Completed | 1. Approved no action | 12/08: FUT approved. | 2025-11-30 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-30 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2970 | FPRC1491 | 03.Conversion | 02.IF - Intel Foundry | Conversion of WIP values as per Component structure in S/4 - Back End IF | 03. FPR | 3.7 FPR - Product Costing and Inventory Valuation | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/ID_2970_Standard%20Cost%20conversion%20and%20Upload%20WIP%20at%20cost%20comp%20structure%20to%20S4.pptx?d=w0975b786ce9e4bf480de10ed2bdbda32&csf=1&web=1&e=JSwsIb |  |  |  | 2025-06-10 | Shane Bethune | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-14 | 2025-09-15 | 100% | 2025-09-18 | 2025-10-14 | 2025-10-17 | 2025-09-24 | 100% | 2025-09-25 | 2025-10-20 | 2025-11-30 | 2025-11-05 | 100% | 2025-11-05 | [15 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2025-12-03 | N | 100% | 2025-12-05 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-30 | 2025-11-30 | 2025-11-30 | jenoronha@deloitte.com | 2025-06-09 06:12 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-19 | 01.S4 |  |  | 2 | 2.9 | 1491 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-18 | 2025-10-14 | 2025-09-18 |  | 2025-09-25 | 2025-10-17 | 2025-09-25 | 2025-11-05 | [12 empty] | 2025-11-05 | 2025-11-05 |  |  | 2025-12-05 | 2026-01-09 | 2025-12-05 | [5 empty] | 2025-07-16 | 2025-11-30 |  |  | 2026-01-09 |  |  |  | 0 |  | 3087 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/04: Some additional screenshot requested by Intel team. Sandeep working with conversion team on this. | 2025-11-30 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-30 | 2025-11-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2991 | FPRC1464_IP | 03.Conversion | 01.IP - Intel Product | Project Actuals Conversion (Non- Intel Federal) | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/XXXX_FPR_DC-050-680%20-%20Project%20Actuals%20Conversion(Non-Intel%20Federal)%20%20-%20Capex.pptx?d=wd9206dd226894b5f9eb131e60c321f73&csf=1&web=1&e=77gFSK | 01.Yes | 01.Yes |  | 2025-05-26 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-14 | 2025-09-15 | 100% | 2025-09-18 | 2025-10-14 | 2025-10-17 | 2025-09-24 | 100% | 2025-09-19 | 2025-10-20 | 2025-11-30 | 2025-11-05 | 100% | 2025-10-14 | [15 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-30 | 2025-11-30 | 2025-11-30 | jenoronha@deloitte.com | 2025-05-23 06:17 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 | 2025-06-03 | 01.S4 |  |  | 2 | 2.9 | 1464 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-18 | 2025-10-14 | 2025-09-18 |  | 2025-09-19 | 2025-10-17 | 2025-09-19 | 2025-10-14 | [12 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-07-16 | 2025-11-30 |  |  | 2025-12-03 |  |  |  | 0 |  | 3045 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/05: Walkthrough is planned for today. | 2025-11-30 | Y | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-30 | 2025-10-14 | Yes | Company code XREF will change | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2991 | FPRC1464_IF | 03.Conversion | 02.IF - Intel Foundry | Project Actuals Conversion (Non- Intel Federal) | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/XXXX_FPR_DC-050-680%20-%20Project%20Actuals%20Conversion(Non-Intel%20Federal)%20%20-%20Capex.pptx?d=wd9206dd226894b5f9eb131e60c321f73&csf=1&web=1&e=77gFSK | 01.Yes | 01.Yes |  | 2025-05-26 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-10-13 | 2025-10-14 | 2025-09-15 | 100% | 2025-09-18 | 2025-10-14 | 2025-10-17 | 2025-09-24 | 100% | 2025-09-19 | 2025-10-20 | 2025-11-30 | 2025-11-05 | 100% | 2025-10-14 | [15 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-03 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-08 | Not Applicable | R3 Build & UT Sprint 21 | 2025-11-30 | 2025-11-30 | 2025-11-30 | jenoronha@deloitte.com | 2025-05-23 06:17 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-06-03 | 01.S4 | FPRC1464_IP | 02.High | 0.6 | 0.87 | 1464 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-18 | 2025-10-14 | 2025-09-18 |  | 2025-09-19 | 2025-10-17 | 2025-09-19 | 2025-10-14 | [12 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | [5 empty] | 2025-07-16 | 2025-11-30 |  |  | 2025-12-03 |  |  |  | 0 |  | 3047 | [7 empty] | 4. Completed | 17. FUT In progress | 12/05: FUT documentation in progress , will be sent for sign-off today. Walkthrough is planned for today. | 2025-11-30 | Y | 03. FPR | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-30 | 2025-10-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2957 | FPRC1442 | 03.Conversion | 01.IP - Intel Product | Conversion of Actual Labor hours for Intel Federal Projects | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF694B71C-7267-4461-AA8D-7DB876EAE058%7D&file=2957_FPR_Intel%20Federal%20Actual%20Labor%20-%20%20Conversion.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-05-08 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-05-30 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-23 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-24 | 2025-09-12 | 2025-08-29 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-09 | 2025-10-08 | N | 100% | 2025-10-01 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jenoronha@deloitte.com | 2025-05-07 21:13 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-09 | 01.S4 |  |  | 2 | 2.9 | 1442 |  | R3 ITC1 | [6 empty] | 2025-05-30 | 2025-06-13 | 2025-05-30 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-01 | 2025-10-09 | 2025-10-01 | [5 empty] | 2025-06-13 | 2025-09-12 |  |  | 2025-10-09 |  | Federal |  | 0 |  | 3011 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2928 | FPRC1441 | 03.Conversion | 01.IP - Intel Product | Conversion of ECC project hierarchy (WBS element master data) to S/4HANA project hierarchy for Intel Federal project profiles USG0001 - USG0005 | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC3234954-AB65-436C-817E-20FB4B7972DF%7D&file=2928_FPR_Intel%20Federal%20WBS_%20CONVERSION_RICEFW%20Intake%20form_v2.0.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-05-08 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-23 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-24 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-08 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jenoronha@deloitte.com | 2025-05-07 21:10 | cell-link@smartsheet.com | 2026-02-25 03:07 | 10 | 2025-05-09 | 01.S4 |  |  | 2 | 2.9 | 1441 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 |  |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-07 | [5 empty] | 2025-06-13 | 2025-09-12 |  |  | 2025-10-08 |  | Federal |  | 0 |  | 3010 | [10 empty] | 2025-09-12 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-09 | No | Company code XREF will change | No |  | No | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2809 | FPRC1212 | 03.Conversion | 01.IP - Intel Product | Project Actuals Conversion including Intel Federal | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2809_FPR_DC-050-580-%20Project%20Actuals%20Conversion.pptx?d=w22dd3cdbc885467aab0192fca749f4be&csf=1&web=1&e=5UPUb1 |  |  |  | 2025-02-03 | shane.bethune@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 02.Intel | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-07-16 | 100% | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-04-18 | 2025-04-25 | 2025-06-24 | 100% | 2025-07-21 | 2025-04-28 | 2025-05-16 | 2025-08-29 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 | No |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-17 | 2025-09-11 | 2025-09-26 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-04 | 01.S4 |  |  | 1 | 1.45 | 1212 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-09-05 | [12 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-11-03 | 2025-11-03 | 2025-11-03 | [5 empty] | 2025-03-21 | 2025-05-16 |  |  | 2025-09-11 |  | Federal |  | 0 |  | 2026 | [7 empty] | 4. Completed | 3. Awaiting Approval | 10/31: Feedback received from the Erica. Sneha to check and respond on the queries. | 2025-05-16 | N | 03. FPR | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-05 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2474 | FPRC0908_IP | 03.Conversion | 01.IP - Intel Product | Project Budget Conversion | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/PPM_Budget%20conversions.pptx?d=wcf77af1d726a443aa5aecedd451f3bf8&csf=1&web=1&e=ee98Bi |  |  |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-01-20 | 2025-01-28 | 2025-06-24 | 100% | 2025-07-21 | 2025-02-05 | 2025-03-08 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-20 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-08 | 2025-03-08 | 2025-03-08 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 |  |  | 1 | 1.45 | 0908 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-20 | 2025-09-10 | 2025-08-20 | [5 empty] | 2025-02-21 | 2025-01-28 |  |  | 2025-06-27 |  |  |  | 0 |  | 1894 | [10 empty] | 2025-03-08 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2474 | FPRC0908_IF | 03.Conversion | 02.IF - Intel Foundry | Project Budget Conversion | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/financeplantoreport/Shared%20Documents/General/Team%2011%20-%20Project%20Accounting/Work%20in%20progress/RICEFW%20Intake%20form/PPM_Budget%20conversions.pptx?d=wcf77af1d726a443aa5aecedd451f3bf8&csf=1&web=1&e=ee98Bi |  |  |  | 2024-12-11 | shane.bethune@intel.com | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-27 | 2025-02-21 | 2025-02-21 | 100% | 2025-02-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-01-20 | 2025-01-28 | 2025-06-24 | 100% | 2025-07-21 | 2025-02-05 | 2025-03-08 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 | No |  | 2025-08-13 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-08-20 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-08 | 2025-03-08 | 2025-03-08 | pgaroo@deloitte.com | 2024-11-20 03:23 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 01.S4 | FPRC0908_IP | 03.Medium | 0.3 | 0.435 | 0908 |  | R3 ITC1 | [6 empty] | 2025-02-21 | 2025-02-21 | 2025-02-21 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-20 | 2025-09-10 | 2025-08-20 | [5 empty] | 2025-02-21 | 2025-01-28 |  |  | 2025-06-27 |  |  |  | 0 |  | 1893 | [10 empty] | 2025-03-08 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 47 | FPRC0196_IP | 03.Conversion | 01.IP - Intel Product | Asset Transaction data conversion | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0003_FPR_Fixed%20Asset%20Master%20and%20Transaction%20data%20conversion.pptx?d=wee2cc38ba039476f8e3281b46a43e10e&csf=1&web=1&e=fVJ1sV | 01.Yes | 01.Yes |  | 2024-05-10 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No | NA | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-02-24 | 2025-02-28 | 2025-05-30 | 100% | 2025-05-30 | 2025-03-03 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-10 08:58 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0196 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | [5 empty] | 2025-02-27 | 2025-02-28 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 1478 | [9 empty] | FUT in progress. FUT to be sent for approval by EOD 08/04 | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No | Update the Xref file for company code and cost centers | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 47 | FPRC0196_IF | 03.Conversion | 02.IF - Intel Foundry | Asset Transaction data conversion | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0003_FPR_Fixed%20Asset%20Master%20and%20Transaction%20data%20conversion.pptx?d=wee2cc38ba039476f8e3281b46a43e10e&csf=1&web=1&e=fVJ1sV | 01.Yes | 01.Yes |  | 2024-05-10 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No | NA | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-02-24 | 2025-02-28 | 2025-05-30 | 100% | 2025-05-30 | 2025-03-03 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jenoronha@deloitte.com | 2024-06-25 09:28 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRC0196_IP | 02.High | 0.6 | 0.87 | 0196 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | [5 empty] | 2025-02-27 | 2025-02-28 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 1477 | [9 empty] | 08/11 FUT sent for approval. Team to follow up today with Business. | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 47 | FPRC0195_IP | 03.Conversion | 01.IP - Intel Product | Asset Master data conversion | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0003_FPR_Fixed%20Asset%20Master%20and%20Transaction%20data%20conversion.pptx?d=wee2cc38ba039476f8e3281b46a43e10e&csf=1&web=1&e=fVJ1sV | 01.Yes | 01.Yes |  | 2024-05-10 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-02-17 | 2025-02-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-24 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-18 | 2025-07-16 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-10 02:45 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0195 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | [5 empty] | 2025-02-27 | 2025-02-21 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 1476 | [9 empty] | 08/11 FUT sent for approval. Team to follow up today with Business. | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No | Update the Xref files for company code and cost centers | No |  | No | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 47 | FPRC0195_IF | 03.Conversion | 02.IF - Intel Foundry | Asset Master data conversion | 03. FPR | 3.5 FPR - Fixed Assets | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DC-040-010-0003_FPR_Fixed%20Asset%20Master%20and%20Transaction%20data%20conversion.pptx?d=wee2cc38ba039476f8e3281b46a43e10e&csf=1&web=1&e=fVJ1sV | 01.Yes | 01.Yes |  | 2024-05-10 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | NA | NA | NA | 2024-06-24 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-02-17 | 2025-02-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-24 | 2025-06-13 | 2025-06-20 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 | No |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-08-13 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | jenoronha@deloitte.com | 2024-06-25 09:28 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 | FPRC0195_IP | 03.Medium | 0.3 | 0.435 | 0195 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | [5 empty] | 2025-02-27 | 2025-02-21 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 1475 | [7 empty] | 1. On Track | 17. FUT In progress | FUT sent for approval on 08/04 | 2025-06-13 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1362 | FPRC0174_IP | 03.Conversion | 01.IP - Intel Product | Conversion of ECC project hierarchy (WBS element master data) to S/4HANA project hierarchy. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/WBS_%20CONVERSION_RICEFW%20Intake%20form_v1.0.pptx?d=wf6660dacbd94468f8496474dc6ead11d&csf=1&web=1&e=aCU4lu | 02.No | 01.Yes |  | 2024-05-01 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | ECC | ECC | S4 | NA | 2024-05-27 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-01 | 2025-08-18 | 2025-08-19 | 2025-08-19 | 100% | 2025-08-18 | 2025-09-15 | 2025-09-19 | 2025-09-24 | 100% | 2025-09-19 | 2025-09-22 | 2025-10-10 | 2025-09-10 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-28 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0174 |  | R3 ITC1 | [6 empty] | 2024-08-01 | 2024-08-02 | 2024-08-01 |  | 2025-08-18 | 2025-08-19 | 2025-08-18 |  | 2025-09-19 | 2025-09-24 | 2025-09-19 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-28 | 2025-11-28 | 2025-11-28 | [5 empty] | 2025-02-07 | 2025-03-28 |  |  | 2025-05-30 |  |  |  | 0 |  | 1765 | [7 empty] | 1. On Track | 1. Approved no action | 11/28: Walkthroughs done and conditionally approved. | 2025-10-10 | N | 03. FPR |  |  |  |  | 1119: ETA 1121 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-10-10 | 2025-09-12 | Yes | 1: Company code XREF will change for Capex 2: Company code XREF will change for Opex 3: 102 company is defaulted in the codes for Project Definition, Level 1 WBS Element & Level 2 WBS Elements, we need to update company code in the codes for Opex 4: Intel team is doing assessment and checking if any other XREF (Profit Center, Investment type code, or other related master data) need to be changed. | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 1362 | FPRC0174_IF | 03.Conversion | 02.IF - Intel Foundry | Conversion of ECC project hierarchy (WBS element master data) to S/4HANA project hierarchy. | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/WBS_%20CONVERSION_RICEFW%20Intake%20form_v1.0.pptx?d=wf6660dacbd94468f8496474dc6ead11d&csf=1&web=1&e=aCU4lu | 02.No | 01.Yes |  | 2024-05-01 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | ECC | ECC | S4 | NA | 2024-05-27 | 2024-08-02 | 2024-08-02 | 100% | 2024-08-01 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-01 | 2025-07-28 | 2025-09-12 | 2025-08-29 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 | No |  | 2025-11-05 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 03:49 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | FPRC0174_IP | 02.High | 0.6 | 0.87 | 0174 |  | R3 ITC1 | [6 empty] | 2024-08-01 | 2024-08-02 | 2024-08-01 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | [5 empty] | 2025-02-07 | 2025-03-28 |  |  | 2025-05-30 |  |  |  | 0 |  | 1764 | [7 empty] | 1. On Track | 1. Approved no action | 11/20: FUT Approved. | 2025-09-12 | N | 03. FPR |  |  |  |  | 1119: ETA 1121 |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 209 | FPRC0117 | 03.Conversion | 05.CFIN | Conversion – In House Cash: Current Account creation and Current Account Balance upload | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/MR-070-0004_FPR_RICEFW%20Intake%20Form_v1.0.pdf?csf=1&web=1&e=ipkDJc | 02.No | 01.Yes |  | 2024-04-23 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | ECC | ECC | CFIN | NA | 2024-06-03 | 2024-06-07 | 2024-06-07 | 100% | 2024-06-27 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-07-05 | 2024-07-10 | 2024-07-10 | 100% | 2024-07-22 | 2024-07-11 | 2024-08-08 | 2024-08-08 | 100% | 2024-08-22 | [15 empty] | 2024-08-22 | 2024-08-22 | Yes |  | 2024-08-30 | 2024-08-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-09-02 | 2024-09-20 | 2024-08-30 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-08 | 2024-08-08 | 2024-08-08 | pgaroo@deloitte.com | 2024-04-22 23:39 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 |  |  | 2 | 2.9 | 0117 |  | R3 ITC1 | [6 empty] | 2024-06-27 | 2024-06-27 | 2024-06-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-08-22 | [12 empty] | 2024-08-22 | 2024-08-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-07 | 2024-07-10 |  |  | 2024-09-20 |  |  |  | 0 | 08. Not Applicable | 2818 | [10 empty] | 2024-08-08 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-22 | 2024-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 303 | FPRC0116 | 03.Conversion | 05.CFIN | Conversion – Migration of Existing Bank Guarantees and Intercompany Loans to CFIN | 03. FPR | 3.9 FPR - Treasury and Cash Management | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/MR-010-0010_FPR_RICEFW%20Intake%20form_v1.0.pdf?csf=1&web=1&e=CIAlH3 | 02.No | 01.Yes |  | 2024-04-23 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | Quantum | Quantum | CFIN | NA | 2024-05-30 | 2024-06-21 | 2024-06-21 | 100% | 2024-07-19 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-07-05 | 2024-07-12 | 2024-07-12 | 100% | 2024-07-25 | 2024-07-15 | 2024-08-23 | 2024-08-23 | 100% | 2024-08-22 | [15 empty] | 2024-08-22 | 2024-08-22 | Yes |  | 2024-08-30 | 2024-09-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2024-08-26 | 2024-09-09 | 2024-09-09 | N | 100% | 2024-11-26 | Not Applicable | R3 Build & UT Sprint 8 | 2024-08-23 | 2024-08-23 | 2024-08-23 | pgaroo@deloitte.com | 2024-04-22 23:39 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0116 |  | R3 ITC1 | [6 empty] | 2024-07-19 | 2024-07-19 | 2024-07-19 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-08-22 | [12 empty] | 2024-08-22 | 2024-08-22 |  |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | [5 empty] | 2024-06-21 | 2024-07-12 |  |  | 2024-09-09 |  |  |  | 0 | 08. Not Applicable | 2825 | [10 empty] | 2024-08-23 | N | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 4 |  | 2024-08-23 | 2024-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 111 | FPRC0035_IP | 03.Conversion | 01.IP - Intel Product | Convert existing ECC & MDG hierarchy to S4HANA PPM hierarchy (Portfolio & buckets)​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/80_OTC_RICEFW%20Intake%20Form_v1.0.pdf?csf=1&web=1&e=MreXzK | 02.No | 01.Yes |  | 2024-04-02 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  | MDG | NA | 2024-04-29 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-17 | 2025-03-21 | 2025-06-24 | 100% | 2025-07-21 | 2025-08-25 | 2025-09-12 | 2025-08-22 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-04-02 03:08 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0035 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-02-07 | 2025-03-21 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1528 | [10 empty] | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 111 | FPRC0035_IF | 03.Conversion | 02.IF - Intel Foundry | Convert existing ECC & MDG hierarchy to S4HANA PPM hierarchy (Portfolio & buckets)​ | 03. FPR | 3.11 FPR - Project Accounting | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:b:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/30%20RICEFW%20Processed%20(Approved)/80_OTC_RICEFW%20Intake%20Form_v1.0.pdf?csf=1&web=1&e=MreXzK | 02.No | 01.Yes |  | 2024-04-02 | Shane Bethune | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  | MDG | NA | 2024-04-29 | 2024-07-26 | 2024-07-26 | 100% | 2024-08-02 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-17 | 2025-03-21 | 2025-06-24 | 100% | 2025-07-21 | 2025-08-25 | 2025-09-12 | 2025-08-22 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 | No |  | 2025-09-10 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-09-12 | 2025-09-12 | 2025-09-12 | jenoronha@deloitte.com | 2024-04-02 08:40 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | FPRC0035_IP | 03.Medium | 0.3 | 0.435 | 0035 |  | R3 ITC1 | [6 empty] | 2024-08-02 | 2024-08-02 | 2024-08-02 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-02-07 | 2025-03-21 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1527 | [10 empty] | 2025-09-12 | Y | 03. FPR | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-08-22 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2798 | DATW1205 | 06.Workflow | 01.IP - Intel Product | Vendor as Customer Workflow | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B0EB71A06-0878-4301-858F-3CB967F48D1C%7D&file=Vendor%20as%20Customer_Workflow_Intake%20form.pptx&wdLOR=c3A5FB9DC-0D34-49B6-ADBB-9A86843AE096&action=edit&mobileredirect=true&CID=22F11C6A-69BB-4491-A596-EAF947C90DAF | 02.No | 01.Yes |  | 2025-02-03 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-04-11 | 100% | 2025-04-25 | 2025-07-21 | 2025-08-21 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-21 | 2025-08-21 | 2025-08-13 | 100% | 2025-08-07 | 2025-07-21 | 2025-08-21 | 2025-08-13 | 100% | 2025-08-07 | [15 empty] | 2025-08-07 | 2025-08-07 |  |  | 2025-09-10 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-01 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-02 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-21 | 2025-08-21 | 2025-08-21 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-04-03 | 02.MDG |  |  | 1 | 1.05 | 1205 |  | R3 ITC1 | [6 empty] | 2025-04-25 | 2025-05-16 | 2025-04-25 |  | 2025-09-10 | 2025-09-10 |  |  | 2025-08-07 | 2025-08-21 | 2025-08-07 | 2025-08-07 | [12 empty] | 2025-08-07 | 2025-08-07 |  |  | 2025-10-02 | 2025-10-08 | 2025-10-02 | [5 empty] | 2025-05-16 | 2025-08-21 |  |  | 2025-10-08 |  |  |  | 0 |  | 407 | [10 empty] | 2025-08-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-21 | 2025-08-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2701 | DATW1203 | 06.Workflow | 01.IP - Intel Product | Workflow Setup for Mark For Delete Reference Material Governance Process | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B462E43D5-0650-48F3-89EF-73193BB00CA5%7D&file=2701_Workflow%20Setup%20for%20Mark%20For%20Delete%20Reference%20Material%20Governance%20Process.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-01 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-04 | 2025-04-11 | 100% | 2025-04-12 | 2025-06-10 | 2025-07-04 | 2025-08-13 | 100% | 2025-08-02 | 2025-06-10 | 2025-07-04 | 2025-08-13 | 100% | 2025-08-02 | 2025-06-10 | 2025-07-04 | 2025-08-13 | 100% | 2025-08-02 | [15 empty] | 2025-08-02 | 2025-08-02 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-04 | 2025-07-04 | 2025-07-04 | pgaroo@deloitte.com | 2025-01-30 07:28 | cell-link@smartsheet.com | 2026-02-13 00:25 | 10 | 2025-02-01 | 02.MDG |  |  | 1 | 1.05 | 1203 |  | R3 ITC1 | [6 empty] | 2025-04-12 | 2025-04-12 | 2025-04-12 |  | 2025-08-02 | 2025-08-13 | 2025-08-02 |  | 2025-08-02 | 2025-08-13 | 2025-08-02 | 2025-08-02 | [12 empty] | 2025-08-02 | 2025-08-02 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-04-04 | 2025-07-04 |  |  | 2025-10-08 |  |  |  | 0 |  | 2603 | [9 empty] | Dates to be adjusted in object tracker | 2025-07-04 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-02 | No |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2700 | DATW1202 | 06.Workflow | 01.IP - Intel Product | Workflow Setup for Change/Extend Reference Material Governance Process | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3DE190B4-6989-40F1-ABD4-23EC1993A7E6%7D&file=2700_Workflow%20Setup%20for%20ChangeExtend%20Reference%20Material%20Governance%20Process.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-01 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-03-28 | 2025-04-11 | 100% | 2025-04-11 | 2025-05-03 | 2025-06-28 | 2025-08-13 | 100% | 2025-08-02 | 2025-05-03 | 2025-06-28 | 2025-08-13 | 100% | 2025-08-05 | 2025-05-03 | 2025-06-28 | 2025-08-13 | 100% | 2025-08-02 | [15 empty] | 2025-08-02 | 2025-08-02 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-28 | 2025-06-28 | 2025-06-28 | pgaroo@deloitte.com | 2025-01-30 07:28 | cell-link@smartsheet.com | 2026-02-13 00:25 | 10 | 2025-02-01 | 02.MDG |  |  | 1 | 1.05 | 1202 |  | R3 ITC1 | [6 empty] | 2025-04-11 | 2025-04-11 | 2025-04-11 |  | 2025-08-02 | 2025-08-13 | 2025-08-02 |  | 2025-08-05 | 2025-08-13 | 2025-08-05 | 2025-08-02 | [12 empty] | 2025-08-02 | 2025-08-02 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-03-28 | 2025-06-28 |  |  | 2025-10-08 |  |  |  | 0 |  | 2602 | [9 empty] | Dates to be adjusted in object tracker | 2025-06-28 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-02 | No |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2699 | DATW1201 | 06.Workflow | 01.IP - Intel Product | Workflow Setup for Create Reference Material Governance Process | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5A9262CD-9F8A-40E9-87C2-1D0CFDA8AB26%7D&file=2699_Workflow%20Setup%20for%20Create%20Reference%20Material%20Governance%20Process.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2025-02-01 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-14 | 100% | 2025-04-04 | 2025-04-24 | 2025-06-21 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-24 | 2025-06-21 | 2025-06-11 | 100% | 2025-06-11 | 2025-04-24 | 2025-06-21 | 2025-06-11 | 100% | 2025-06-11 | [15 empty] | 2025-06-11 | 2025-06-11 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-03 | Not Applicable | R3 Build & UT Sprint 18 | 2025-06-21 | 2025-06-21 | 2025-06-21 | pgaroo@deloitte.com | 2025-01-30 07:28 | cell-link@smartsheet.com | 2026-02-13 00:25 | 10 | 2025-02-01 | 02.MDG |  |  | 1 | 1.05 | 1201 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-11 | 2025-06-21 | 2025-06-11 | 2025-06-11 | [12 empty] | 2025-06-11 | 2025-06-11 |  |  | 2025-10-03 | 2025-10-08 | 2025-10-03 | [5 empty] | 2025-03-21 | 2025-06-21 |  |  | 2025-10-08 |  |  |  | 0 |  | 2601 | [9 empty] | 07/28: FUT in Progress | 2025-06-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-21 | 2025-06-11 | No |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2179 | DATW0748 | 06.Workflow | 07.MDG | Workflow Setup for Material Master Governance Mass Processing | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2179_Master%20Data_Workflow%20Setup%20for%20Material%20Master%20Governance%20Mass%20Processing.pptx?d=wfc40be8e75ed4efca086b791a3bd15a9&csf=1&web=1&e=DLkR6b | 02.No | 01.Yes |  | 2024-11-07 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-10 | 2025-03-07 | 2025-03-14 | 100% | 2025-03-20 | 2025-04-28 | 2025-05-09 | 2025-09-10 | 100% | 2025-09-10 | 2025-05-26 | 2025-06-13 | 2025-08-13 | 100% | 2025-08-14 | 2025-06-16 | 2025-06-30 | 2025-08-13 | 100% | 2025-08-14 | [15 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-09-07 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-30 | 2025-06-30 | 2025-06-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-07 | 02.MDG |  |  | 1 | 1.05 | 0748 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-20 | 2025-03-20 |  | 2025-09-10 | 2025-09-10 |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-14 | [12 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | [5 empty] | 2025-03-07 | 2025-06-13 |  |  | 2025-09-19 |  |  |  | 0 | 08. Not Applicable | 1664 | [9 empty] | Dates to be adjusted in object tracker | 2025-06-30 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-14 | 2025-08-14 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2177 | DATW0747 | 06.Workflow | 07.MDG | Workflow Setup for Material Master Governance in Mark For Delete Process | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2177_Master%20Data_Workflow%20Setup%20for%20Material%20Master%20Governance%20in%20Mark%20For%20Delete%20Process.pptx?d=w16b79d8fb18044c3a831f186878e5050&csf=1&web=1&e=m0reBb | 02.No | 01.Yes |  | 2024-11-07 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-10 | 2025-03-07 | 2025-03-14 | 100% | 2025-03-19 | 2025-04-14 | 2025-04-25 | 2025-03-21 | 100% | 2025-03-20 | 2025-05-05 | 2025-05-23 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-16 | 2025-06-30 | 2025-05-16 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-07 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-30 | 2025-06-30 | 2025-06-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-07 | 02.MDG |  |  | 1 | 1.05 | 0747 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | 2025-03-20 | 2025-04-25 | 2025-03-20 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-03-07 | 2025-05-23 |  |  | 2025-09-19 |  |  |  | 0 | 08. Not Applicable | 1663 | [10 empty] | 2025-06-30 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2176 | DATW0746 | 06.Workflow | 07.MDG | Workflow Setup for Material Master Governance in the Change Process | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2176_Master%20Data_Workflow%20Setup%20for%20Material%20Master%20Governance%20in%20the%20Change%20Process.pptx?d=waf2ec38a354e48d8bf41650ae00a5f36&csf=1&web=1&e=FJuJku | 02.No | 01.Yes |  | 2024-11-07 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-10 | 2025-03-07 | 2025-03-14 | 100% | 2025-03-28 | 2025-04-01 | 2025-04-11 | 2025-04-11 | 100% | 2025-04-10 | 2025-04-14 | 2025-05-02 | 2025-08-13 | 100% | 2025-07-21 | 2025-06-16 | 2025-06-30 | 2025-08-13 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-07 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-30 | 2025-06-30 | 2025-06-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-07 | 02.MDG |  |  | 1 | 1.05 | 0746 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-04-10 | 2025-04-11 | 2025-04-10 |  | 2025-07-21 | 2025-08-13 | 2025-07-21 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-03-07 | 2025-05-02 |  |  | 2025-09-19 |  |  |  | 0 | 08. Not Applicable | 1662 | [9 empty] | Dates to be adjusted in object tracker | 2025-06-30 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-07-21 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1950 | DATW0591 | 06.Workflow | 01.IP - Intel Product | Parallel Approver Workflow Process | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Parallel%20Approver%20Workflow.pptx?d=wbb64bcad285446c5a7fc813783dad7f1&csf=1&web=1&e=ReoOko | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-09-30 | 2024-10-18 | 2024-10-18 | 100% | 2024-11-26 | 2024-10-18 | 2024-10-18 | 2024-10-11 | 100% | 2024-10-30 | 2024-10-28 | 2024-11-11 | 2024-11-15 | 100% | 2024-11-26 | 2024-10-28 | 2024-11-11 | 2024-11-15 | 100% | 2024-11-26 | [15 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-04-18 | 2025-05-02 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-18 | 2025-05-02 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2024-11-11 | 2024-11-11 | 2024-11-11 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-10 | 02.MDG |  |  | 1 | 1.05 | 0591 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2024-10-30 | 2024-10-30 | 2024-10-30 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | [12 empty] | 2024-11-26 | 2024-11-26 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-18 | 2024-11-11 |  |  | 2025-02-14 |  |  |  | 0 | 08. Not Applicable | 2336 | [9 empty] | This FUT is 100% complete.BSPID-40467 | 2024-11-11 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 8 |  | 2024-11-26 | 2024-11-26 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 480 | DATW0207 | 06.Workflow | 01.IP - Intel Product | Create IP Customer process workflow | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/480_Master%20Data_Workflow%20Intake%20Form.pptx?d=wc2d80a17568a444d8d07af05751ae851&csf=1&web=1&e=lCMFCH | 01.Yes | 01.Yes |  | 2024-05-14 | Candice S Linnell | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2025-01-13 | 2025-04-04 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-07 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-21 | 2025-05-23 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-24 | 2025-06-06 | 2025-05-16 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-09-26 | N | 100% | 2025-10-31 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-06 | 2025-06-06 | 2025-06-06 | pgaroo@deloitte.com | 2024-05-13 23:48 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 02.MDG |  |  | 2 | 2.1 | 0207 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | [5 empty] | 2025-04-04 | 2025-05-23 |  |  | 2025-08-15 |  |  |  | 0 | 08. Not Applicable | 1963 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting IT approval 10/24 - Awaiting approval 10/10 : Addressing review comments | 2025-06-06 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes | Update the Account group, BP grouping and CR type descriptions | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 482 | DATW0205_IP | 06.Workflow | 01.IP - Intel Product | Change/Extend/Block/Unblock IP Customer Master process workflow | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | Y | 2024-05-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/482_Master%20Data_Workflow%20Intake%20Form.pptx?d=w0e42ebd8c521471b8906c353b11b4fb7&csf=1&web=1&e=2jfOaM | 01.Yes | 01.Yes |  | 2024-05-14 | Candice S Linnell | 01.Approved | 2024-05-20 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  | NA | NA | NA | NA | 2025-03-10 | 2025-05-30 | 2024-11-08 | 100% | 2025-05-16 | 2025-06-02 | 2025-06-13 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-06 | 2025-08-31 | 2025-09-10 | 100% | 2025-08-29 | 2025-07-06 | 2025-08-31 | 2025-09-10 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-17 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-31 | 2025-08-31 | 2025-08-31 | pgaroo@deloitte.com | 2024-05-13 23:48 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 |  | 02.MDG | DATW0205_IF | 03.Medium | 0.5 | 0.525 | 0205 |  | R3 ITC1 | [6 empty] | 2025-05-16 | 2025-05-30 | 2025-05-16 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-08-29 | 2025-09-10 | 2025-08-29 | 2025-08-29 | [12 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-17 | 2025-10-17 | 2025-10-17 | [5 empty] | 2025-05-30 | 2025-07-04 |  |  | 2025-08-29 |  |  |  | 0 | 08. Not Applicable | 1965 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 : 18/23 test cases approved,awaiting approval on rest | 2025-08-31 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-08-29 | Yes | Update the Account group, BP grouping and CR type descriptions | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 |  | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2940 | DATR1430 | 01.Report | 02.IF - Intel Foundry | Cost Center Approvers report by Supergroup, Group, Division, Subdivision, CCRU, profit center, Expense approver, capital approver or consolidator | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B902B6F4E-C505-42EC-8D3E-30804874DF66%7D&file=2940_Cost%20Center%20Approvers%20report%20by%20Supergroup%2C%20Group%2C%20Division%2C%20Subdivision%2C%20CCRU%2C%20profit%20center%2C%20Expense%20approver%2C%20capital%20approver%20or%20consolidator.pptx&wdLOR=c4D6D2F58-D08F-4301-9186-4191D76A52DA&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-04-29 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-11 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-20 | 2025-08-11 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-20 | 2025-08-11 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-20 | [15 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-09-25 | 2025-09-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-09-30 | 2025-09-30 | N | 100% | 2025-10-07 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2025-04-25 04:38 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 02.MDG |  |  | 1 | 0.85 | 1430 |  | R3 ITC1 | [6 empty] | 2025-06-11 | 2025-06-13 | 2025-06-11 |  | 2025-08-20 | 2025-09-10 | 2025-08-20 |  | 2025-08-20 | 2025-09-10 | 2025-08-20 | 2025-08-20 | [12 empty] | 2025-08-20 | 2025-08-20 |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | [5 empty] | 2025-06-13 | 2025-09-10 |  |  | 2025-09-30 |  |  |  | 0 |  | 2988 | [7 empty] | 1. On Track |  | 10/3-review in progress | 2025-09-10 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-08-20 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1800 | DATR0787 | 01.Report | 07.MDG | Report to send notification to Direct managers about the inactive Cost Center Approvers | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1800_Report%20to%20send%20notification%20when%20approver%20is%20no%20longer%20valid%20and%20is%20cost%20center%20approver.pptx?d=w005bfbaaa05248e48ea58c7440263013&csf=1&web=1&e=uCO2yu | 02.No | 01.Yes |  | 2024-11-08 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-31 | 2025-07-16 | 100% | 2025-07-21 | 2025-05-01 | 2025-06-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-01 | 2025-06-30 | 2025-06-11 | 100% | 2025-06-13 | 2025-05-01 | 2025-06-30 | 2025-06-11 | 100% | 2025-06-13 | [15 empty] | 2025-06-13 | 2025-06-13 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-07-22 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-30 | 2025-06-30 | 2025-06-30 | pgaroo@deloitte.com | 2024-10-22 10:04 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-12-11 | 02.MDG |  |  | 1 | 0.85 | 0787 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-06-13 | 2025-06-30 | 2025-06-13 | 2025-06-13 | [12 empty] | 2025-06-13 | 2025-06-13 |  |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | [5 empty] | 2025-03-31 | 2025-06-30 |  |  | 2025-07-11 |  |  |  | 0 | 08. Not Applicable | 2663 | [10 empty] | 2025-06-30 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-30 | 2025-06-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 826 | DATR0390_IP | 01.Report | 01.IP - Intel Product | Data Monitor Report between MDG and Reltio | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/826_Master%20Data_Intake%20Form.pptx?d=w7249e5a8605f43fca506b1d5477926be&csf=1&web=1&e=ef9ijC | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-06 | 2025-10-14 | 2025-10-18 | 2025-11-05 | 100% | 2025-11-04 | 2025-10-04 | 2025-11-15 | 2025-11-05 | 100% | 2025-11-07 | 2025-10-04 | 2025-11-15 | 2025-11-05 | 100% | 2025-11-07 | [15 empty] | 2025-11-07 | 2025-11-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-16 | 2025-11-28 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-15 | 2025-11-15 | 2025-11-15 | pgaroo@deloitte.com | 2025-04-02 04:07 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-04-03 | 02.MDG | DATR0390 | 03.Medium | 0.2 | 0.17 | 0390 |  | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-13 | 2025-06-06 |  | 2025-11-04 | 2025-11-05 | 2025-11-04 |  | 2025-11-07 | 2025-11-15 | 2025-11-07 | 2025-11-07 | [12 empty] | 2025-11-07 | 2025-11-07 |  |  | 2025-12-03 | 2025-12-03 | 2025-12-03 | [5 empty] | 2025-06-13 | 2025-11-15 |  |  | 2025-11-28 |  |  |  | 0 |  | 2855 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18 - FUT planned to be completed by 11/21 | 2025-11-15 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-15 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 827 | DATR0389_IP | 01.Report | 01.IP - Intel Product | Customer Master Operational Report | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B5674F19D-1447-4DF6-BDC0-76139FB4A78E%7D&file=827_Master%20Data_Customer%20Master%20Operational%20Report.pptx&action=edit&mobileredirect=true&wdsle=0 | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-06 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-05 | 2025-10-13 | 2025-10-24 | 2025-12-12 | 100% | 2025-12-13 | 2025-10-13 | 2025-10-24 | 2025-12-12 | 100% | 2025-12-13 | [15 empty] | 2025-12-13 | 2025-12-13 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-03 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-12-06 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-24 | 2025-10-24 | 2025-10-24 | pgaroo@deloitte.com | 2025-04-02 04:07 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-04-03 | 02.MDG | DATR0389 | 03.Medium | 0.2 | 0.17 | 0389 |  | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-13 | 2025-06-06 |  | 2025-09-05 | 2025-09-05 | 2025-09-05 |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | [12 empty] | 2025-12-13 | 2025-12-13 |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | [5 empty] | 2025-06-13 | 2025-10-24 |  |  | 2025-12-03 |  |  |  | 0 |  | 2854 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/18 - FUT planned to be completed by 11/21 | 2025-10-24 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-13 | 2025-12-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3203 | DATI1727 | 02.Interface | 07.MDG | Automated update to DC Sales Status and other Item Sales Data fields​ | 09A. Master Data | 9A.6 Master Data - Material | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BD069FB35-7860-4C23-85ED-00E905D27ECD%7D&file=INT-CR1612_Master%20Data_Derivation%20of%20DC%20Sales%20Status.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-19 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 01.Yes | 16892 | Product and Customer Data Management Business Process Management Suite |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-25 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [10 empty] | 2026-03-16 | 2026-06-05 | 2026-06-05 | 80% | 2026-06-05 | 2026-05-27 | 2026-06-05 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  | 2026-06-05 | 2026-06-05 | jenoronha@deloitte.com | 2026-02-19 04:22 | cell-link@smartsheet.com | 2026-04-07 20:47 | 6 | 2026-02-19 | 01.S4 |  |  | 1 | 1.45 | 1727 | INT-CR1612 | R3 ITC2 | R3 ITC2 | [5 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [11 empty] | 2026-06-05 | 2026-06-05 | [6 empty] | 2026-06-05 | [14 empty] | 0 |  | 3432 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. | 2026-06-05 | Y | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3150 | DATI1712 | 02.Interface | 07.MDG | Import Dot process/stage details from MDG into IF. ​ | 09A. Master Data | 9A.1 Master Data - ALL | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console%20ID_3150_IF_ECA%20view%20for%20Xesus%20Mars%20Volumes%20and%20non-burden%20%26%20Non-dep%20allocation%20to%20PCOS%20OCOS.pptx?d=we97bfb47774e43f28e13e2103762cb30&csf=1&web=1&e=xFeD87 | 02.No | 01.Yes |  | 2025-11-04 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-11-10 | 2025-12-03 | 2026-02-04 | 100% | 2026-01-30 | 2026-02-09 | 2026-02-13 | 2026-02-13 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-09 | 2026-02-20 | 2026-03-04 | 100% | 2026-03-09 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | 2026-02-23 | 2026-02-27 |  |  | 2026-02-27 | [5 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-02-26 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-27 | 2026-02-27 | 2026-02-20 | jenoronha@deloitte.com | 2026-01-07 06:39 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-11-05 | 02.MDG |  |  | 1 | 1.45 | 1712 | INT-CR1337 | R3 ITC1 | [6 empty] | 2026-01-30 | 2026-02-04 | 2026-01-30 | 2026-03-09 | 2026-03-09 | 2026-02-14 | 2026-02-14 | 2026-03-09 | 2026-03-09 | 2026-03-04 | 2026-02-26 | 2026-02-26 |  | 2026-02-27 |  |  |  | 2026-02-27 | [6 empty] | 2026-03-09 | 2026-03-09 |  |  | 2026-02-26 | 2026-03-06 | 2026-02-26 | [5 empty] | 2025-12-03 | 2026-02-20 | 2026-02-27 |  | 2026-03-06 |  |  |  | 0 |  | 3399 | [7 empty] | 1. On Track | 3. Awaiting Approval | 02/24: TUT Comments to be addressed and approved before FUT is approved. | 2026-02-27 | Y | 09A. Master Data |  |  |  |  | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 23+ | 2026-03-09 | 2026-03-04 | 2026-03-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3092 | DATI1618_IP | 02.Interface | 01.IP - Intel Product | Interface to automate the PROC material master creation to read BOM data from S/4 IF and IP | 09A. Master Data | 9A.6 Master Data - Material | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3089_Master%20Data_Enhancement_Automate%20PROC%20Material%20Creation.pptx?d=wda593c62f0ab46bf986985e18dcbedbb&csf=1&web=1&e=fPvaLB | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-10-13 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-18 | 2026-01-12 | 2026-01-16 | 2026-02-13 | 50% | 2026-02-13 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 50% | 2026-02-24 | 2026-02-09 | 2026-02-20 | 2026-02-24 | 50% | 2026-02-24 | [15 empty] | 2026-02-24 | 2026-02-24 |  |  | 2026-02-27 | 2026-04-30 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-04-30 | N | 0% | 2026-04-30 | Sprint 23 Week 4 | R3 Build & UT Sprint OB1 | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-04-04 13:56 | 6 | 2025-09-03 | 01.S4 |  |  | 1 | 1.45 | 1618 | INT-CR1825, INT-CR0918 | R3 ITC1 | [6 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 |  |  | 2026-02-13 |  |  |  | 2026-02-24 | [19 empty] | 2026-04-30 | 2026-04-30 | [5 empty] | 2026-02-06 | 2026-02-20 |  |  | 2026-03-06 |  |  |  | 0 |  | 3269 | [7 empty] | 2. At Risk | 19. Incomplete Build | 3/27: Build is not started , due to high complexity of object | 2026-02-20 | Y | 09A. Master Data |  |  |  | 03/23: Build in progress. ETA 04/30. CR1825 was presented on 03/20 and was rejected. This object will be tracked as delayed. Current status: Build in progress Issue: FUT at risk of going beyond 4/10 Next steps: Expedite FUT once build completes. Help needed: n/a FUT ETA: 04/30 |  | 2. Risk | At risk for S23+ | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint 23 |  | 2026-02-24 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3092 | DATI1618_IF | 02.Interface | 02.IF - Intel Foundry | Interface to automate the PROC material master creation to read BOM data from S/4 IF and IP | 09A. Master Data | 9A.6 Master Data - Material | 06. Dev In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3089_Master%20Data_Enhancement_Automate%20PROC%20Material%20Creation.pptx?d=wda593c62f0ab46bf986985e18dcbedbb&csf=1&web=1&e=fPvaLB | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-10-13 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-18 | 2026-01-12 | 2026-01-16 | 2026-02-13 | 50% | 2026-02-13 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 50% | 2026-02-20 | 2026-02-09 | 2026-02-20 | 2026-02-20 | 50% | 2026-02-20 | [15 empty] | 2026-02-20 | 2026-02-20 |  |  | 2026-02-27 | 2026-04-30 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-04-30 | N | 0% | 2026-04-30 | Sprint 23 Week 4 | R3 Build & UT Sprint OB1 | 2026-02-20 | 2026-02-20 | 2026-02-20 | jenoronha@deloitte.com | 2025-09-30 22:52 | cell-link@smartsheet.com | 2026-04-04 13:56 | 6 | 2025-09-03 | 01.S4 | DATI1618_IP | 03.Medium | 0.3 | 0.435 | 1618 | INT-CR1825, INT-CR0918 | R3 ITC1 | [6 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18 |  |  | 2026-02-13 |  |  |  | 2026-02-20 | [19 empty] | 2026-04-30 | 2026-04-30 | [5 empty] | 2026-02-06 | 2026-02-20 |  |  | 2026-03-06 |  |  |  | 0 |  | 3318 | [7 empty] | 2. At Risk | 19. Incomplete Build | 3/27: Build is not started , due to high complexity of object | 2026-02-20 | Y | 09A. Master Data |  |  |  | 03/23: Build in progress. ETA 04/30. CR1825 was presented on 03/20 and was rejected. This object will be tracked as delayed. Current status: Build in progress Issue: FUT at risk of going beyond 4/10 Next steps: Expedite FUT once build completes. Help needed: n/a FUT ETA: 04/30 |  | 2. Risk | At risk for S23+ | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint 23 |  | 2026-02-20 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3085 | DATI1612_IP | 02.Interface | 01.IP - Intel Product | 2A1 interface to send Product Catalog to OpenText for 3PL consumption | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2A1_Material%20Master_%20Interface%20S4%20IP_IF%20to%20OpenText.pptx?d=w3ac92b57e9514087aa6f66666345737e&csf=1&web=1&e=cdeefu | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 12842 | OpenText |  |  | MuleSoft | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-27 | 2025-09-12 | 2025-09-19 | 2025-12-03 | 100% | 2025-11-25 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-02 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-05 | 2025-08-15 | 2025-08-28 | 2025-08-28 | 100% | 2025-08-28 | 2025-12-05 | 2025-12-05 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-09 | Sprint 22 Week 2 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-03 | 01.S4 |  |  | 1 | 1.45 | 1612 | INT-CR1010 | R3 ITC1 | [6 empty] | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-12-05 | 2025-12-05 |  |  | 2026-02-09 | 2026-02-09 | 2026-02-09 |  |  |  |  | B2B - OpenText | 2025-10-10 | 2025-12-05 | 2025-12-03 |  | 2026-01-23 |  |  |  | 0 |  | 3258 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/09 : Review comments have been addressed by team, awaiting approval. | 2025-12-05 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3085 | DATI1612_IF | 02.Interface | 02.IF - Intel Foundry | 2A1 interface to send Product Catalog to OpenText for 3PL consumption | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2A1_Material%20Master_%20Interface%20S4%20IP_IF%20to%20OpenText.pptx?d=w3ac92b57e9514087aa6f66666345737e&csf=1&web=1&e=cdeefu | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low |  | 01.Yes | 12842 | OpenText |  |  | MuleSoft | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-27 | 2025-09-12 | 2025-09-19 | 2025-12-03 | 100% | 2025-11-25 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-28 | 100% | 2025-12-02 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-03 | 2025-11-24 | 2025-12-03 | 2025-12-03 | 100% | 2025-12-05 | 2025-08-15 | 2025-08-28 | 2025-08-28 | 100% | 2025-08-28 | 2025-12-05 | 2025-12-05 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-02-09 | Sprint 22 Week 2 | R3 Build & UT Sprint 23 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-03 | 01.S4 | DATI1612_IP | 03.Medium | 0.3 | 0.435 | 1612 | INT-CR1010 | R3 ITC1 | [6 empty] | 2025-10-27 | 2025-10-27 | 2025-10-27 |  | 2025-11-25 | 2025-12-03 | 2025-11-25 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-12-02 | 2025-12-02 |  | 2025-12-03 |  | 2025-12-03 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-12-05 | 2025-12-05 |  |  | 2026-02-09 | 2026-02-09 | 2026-02-09 |  |  |  |  | B2B - OpenText | 2025-10-10 | 2025-12-05 | 2025-12-03 |  | 2026-01-23 |  |  |  | 0 |  | 3259 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/02 : FUT in review,expected to be approved by 02/04 | 2025-12-05 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-12-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3077 | DATI1607 | 02.Interface | 01.IP - Intel Product | Delta updates to OM Position IDs and Relationships | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/3%20Final%20Deliverables/Release%20R3/2.%20Build/6.%20HRMM/RICEFW/Intake%20Forms/IFL%20Intake%20Forms%20for%20Time%20Keeping/HRMM_Delta%20updates%20to%20OM%20Position%20IDs%20and%20Relationships.pptx?d=w631f5bb8b6614b428df2b3de0daa1a9b&csf=1&web=1&e=AlcRel | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 01.Yes | 10772 | Worker Data Services (WDS) |  |  | NA | 2025-09-15 | 2025-10-08 | 2025-10-08 | 100% | 2025-09-22 | 2025-09-12 | 2025-09-19 | 2025-11-21 | 100% | 2025-11-14 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-11-21 | 100% | 2025-11-13 | [11 empty] | 2025-10-01 | 2025-10-01 | 100% | 2025-10-01 | 2025-11-13 | 2025-11-13 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-15 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-09-03 | 01.S4 |  |  | 1 | 1.45 | 1607 |  | R3 ITC1 | [6 empty] | 2025-09-22 | 2025-10-08 | 2025-09-22 |  | 2025-11-14 | 2025-11-21 | 2025-11-14 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-13 | 2025-11-13 | [9 empty] | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-11-13 | 2025-11-13 |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | [5 empty] | 2025-10-08 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3277 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18 - FUT to be submitted for Intel review on 11/21 | 2025-12-05 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-13 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2260 | DATI1508 | 02.Interface | 07.MDG | Program to update weight of material in the material master | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  |  | 02.No | 01.Yes |  | 2025-03-04 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-07-25 | 100% | 2025-07-31 | 2025-09-15 | 2025-10-08 | 2025-08-13 | 100% | 2025-08-05 | 2025-10-13 | 2025-11-05 | 2025-08-13 | 100% | 2025-08-14 | 2025-10-13 | 2025-11-05 | 2025-08-13 | 100% | 2025-08-14 | [15 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-15 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-06-30 04:59 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 02.MDG |  |  | 1 | 1.45 | 1508 |  | R3 ITC1 | [6 empty] | 2025-07-31 | 2025-08-13 | 2025-07-31 |  | 2025-08-05 | 2025-10-08 | 2025-08-05 |  | 2025-08-14 | 2025-11-05 | 2025-08-14 | 2025-08-14 | [12 empty] | 2025-08-14 | 2025-08-14 |  |  | 2025-11-15 | 2025-11-15 | 2025-11-15 | [5 empty] | 2025-08-13 | 2025-11-05 |  |  | 2025-10-08 |  |  |  | 0 |  | 3108 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14 - Awaiting approval (no open defects). FUT Approval ETA is 11/17 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Awaiting approval 10/24 - RFC connection issue is resolved. FUT in progress 10/10 : API Connections were set up recently, hence FUT is delayed | 2025-11-05 | Y | 09A. Master Data |  |  |  | Awaiting Approval 1211 Approved |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-11-05 | 2025-08-14 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2417 | DATI1501 | 02.Interface | 01.IP - Intel Product | Inbound Interface to exchange BOM data between PLM Translator to SAP S/4 – Intel Product | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2417_Master%20Data_Interface%20to%20exchange%20BOM%20data%20between%20PLM%20Translator%20to%20SAP%20S4%20%E2%80%93%20Intel%20Foundry.pptx?d=w0c0f2edf23e044c9ae77405b2de740c8&csf=1&web=1&e=pVqwqu | 02.No | 01.Yes |  | 2024-12-02 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Data & Insights (CDI) | 01.Yes | 41744 | PDM Translator | PLM | S/4 | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-15 | 2025-06-06 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-02 | 2025-07-04 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-04 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-06-16 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-21 | 2025-08-15 | 2025-06-06 | 100% | 2025-06-17 | 2025-06-30 | 2025-07-25 | 2025-07-25 | 100% | 2025-07-25 | 2025-06-17 | 2025-07-25 |  | 2025-08-22 | 2025-09-10 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-10-08 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2.9 | 1501 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-15 | 2025-04-15 |  | 2025-06-02 | 2025-06-13 | 2025-06-02 |  | 2025-06-06 | 2025-07-18 |  |  |  | 2025-07-18 |  | 2025-06-06 |  | 2025-08-15 | 2025-06-17 | 2025-06-17 |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-06-17 | 2025-07-25 |  |  | 2025-10-08 | 2025-10-10 | 2025-10-08 | [5 empty] | 2025-03-21 | 2025-07-18 | 2025-07-18 |  | 2025-10-10 |  |  |  | 0 |  | 1793 | [7 empty] | 1. On Track |  |  | 2025-08-15 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-18 | 2025-06-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2772 | DATI1489 | 02.Interface | 07.MDG | Transfer activity type, WWID data from IFED2.0 to MDG for time keeping employees | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B8DC390B0-CD60-4F6C-833F-48A2E324AA4F%7D&file=HRMM_IT0315-Timekeeping%20data%20Intake%20Form%20(1).pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-18 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 10741 | Intel Federal Employee database |  |  | MULESOFT | 2025-07-21 | 2025-08-13 | 2025-08-01 | 100% | 2025-07-31 | 2025-09-15 | 2025-10-08 | 2025-11-05 | 100% | 2025-10-24 | 2025-10-13 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-24 | 2025-10-13 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-24 | 2025-08-18 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-26 | 2025-10-06 | 2025-10-08 | 2025-10-08 | 100% | 2025-10-10 | 2025-05-01 | 2025-06-25 | 2025-06-25 | 100% | 2025-06-25 | 2025-10-24 | 2025-10-24 |  | 2025-10-31 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-04 | Not Applicable | R3 Build & UT Sprint 19 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-05-17 02:08 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-10 | 02.MDG |  |  | 1 | 1.45 | 1489 |  | R3 ITC1 | [6 empty] | 2025-07-31 | 2025-08-13 | 2025-07-31 |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  | 2025-10-24 | 2025-11-05 | 2025-10-24 | 2025-10-24 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 |  | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-10-24 | 2025-10-24 |  |  | 2025-11-04 | 2025-11-05 | 2025-11-04 | [5 empty] | 2025-08-13 | 2025-11-05 | 2025-09-10 |  | 2025-11-05 |  | Federal |  | 0 |  | 3018 | [7 empty] | 1. On Track | 17. FUT In progress | 10/30 - FUT in progress. ETA for submission if 11/04 10/24 - Background job from WCDS is not triggering successfully We're unable to get data from WCDS through MuleSoft. 1489 is dependent on Worker Snapshot interface. MuleSoft and Intel are working to fix the issue | 2025-11-05 | Y | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-05 | 2025-10-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2417 | DATI1445_IP | 02.Interface | 01.IP - Intel Product | Outbound Interface to exchange BOM data between PLM Translator to SAP S/4 – Intel Product | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2417_Master%20Data_Interface%20to%20exchange%20BOM%20data%20between%20PLM%20Translator%20to%20SAP%20S4%20%E2%80%93%20Intel%20Foundry.pptx?d=w0c0f2edf23e044c9ae77405b2de740c8&csf=1&web=1&e=pVqwqu | 02.No | 01.Yes |  | 2025-05-13 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High | Corporate Data & Insights (CDI) | 01.Yes | 41744 | PDM Translator | S/4 | PLM | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-18 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-23 | 2025-08-04 | 2025-08-13 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-04 | 2025-08-13 | 2025-08-29 | 100% | 2025-08-29 | [10 empty] | 2025-07-28 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-15 | 2025-08-29 | 2025-09-15 |  | 2025-09-19 | 2025-10-03 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-13 | Not Applicable | R3 Build & UT Sprint 19 | 2025-08-13 | 2025-09-26 | 2025-09-26 | jenoronha@deloitte.com | 2025-05-13 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-10 | 01.S4 |  |  | 2 | 2.9 | 1445 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-08-29 | 2025-08-29 | [11 empty] | 2025-09-26 | 2025-09-15 | 2025-09-15 | 2025-08-29 | 2025-09-15 |  |  | 2025-10-13 | 2025-10-13 | 2025-10-13 | [5 empty] | 2025-07-16 | 2025-08-13 |  |  | 2025-10-08 |  |  |  | 0 |  | 3015 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 : Awaiting approval | 2025-09-26 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-08-29 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2418 | DATI1445_IF | 02.Interface | 02.IF - Intel Foundry | Outbound Interface to exchange BOM data between PLM Translator to SAP S/4 – Intel Foundry | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2418_Master%20Data_Interface%20to%20exchange%20BOM%20data%20between%20PLM%20Translator%20to%20SAP%20S4%20%E2%80%93%20Intel%20Product.pptx?d=w7a8a249537b54a3485fb38b224889198&csf=1&web=1&e=3WW4gd | 02.No | 01.Yes |  | 2025-05-13 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Data & Insights (CDI) | 01.Yes | 41744 | PDM Translator | S/4 | PLM | NA | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-21 | 2025-08-18 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-23 | 2025-08-04 | 2025-08-13 | 2025-08-29 | 100% | 2025-08-29 | 2025-08-04 | 2025-08-13 | 2025-08-29 | 100% | 2025-08-29 | [10 empty] | 2025-07-28 | 2025-09-26 | 2025-09-26 | 100% | 2025-09-15 | 2025-08-29 | 2025-09-15 |  | 2025-09-19 | 2025-10-03 | 2025-10-08 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-13 | 2025-09-26 | 2025-09-26 | jenoronha@deloitte.com | 2025-05-13 07:50 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-06-10 | 01.S4 | DATI1445_IP | 02.High | 0.6 | 0.87 | 1445 |  | R3 ITC1 | [6 empty] | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-08-29 | 2025-08-29 | [11 empty] | 2025-09-26 | 2025-09-15 | 2025-09-15 | 2025-08-29 | 2025-09-15 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-07-16 | 2025-08-13 |  |  | 2025-10-08 |  |  |  | 0 |  | 3014 | [7 empty] | 1. On Track |  | approved | 2025-09-26 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-08-29 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2829 | DATI1416 | 02.Interface | 07.MDG | Interface to get MMID from the PLM Translator for the materials created directly in the MDG. | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2829_Material%20Master%20Data_Interface%20for%20UNBW%20Construction%20Materials.pptx?d=w810599f7990b49f9af1d2fa41c66a911&csf=1&web=1&e=ZcbmEH | 02.No | 01.Yes |  | 2025-04-24 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-06 | 2025-08-11 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-18 | 2025-11-10 | 2025-11-28 | 2025-09-19 | 100% | 2025-09-17 | 2025-11-10 | 2025-12-05 | 2025-09-19 | 100% | 2025-09-17 | [15 empty] | 2025-09-17 | 2025-09-17 |  |  | 2025-10-31 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | pgaroo@deloitte.com | 2025-04-18 05:48 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-04-24 | 02.MDG |  |  | 1 | 1.45 | 1416 |  | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-13 | 2025-06-06 |  | 2025-08-18 | 2025-08-29 | 2025-08-18 |  | 2025-09-17 | 2025-11-28 | 2025-09-17 | 2025-09-17 | [12 empty] | 2025-09-17 | 2025-09-17 |  |  | 2025-11-20 | 2025-12-05 | 2025-11-20 | [5 empty] | 2025-06-13 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 2964 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18 - FUT is currently under review , review comments to be addressed by 11/18 | 2025-12-05 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-12-05 | 2025-09-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2260 | DATI1289_IP | 02.Interface | 01.IP - Intel Product | Program to update weight of material in the material master | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_MM%20Weight%20Program.pptx?d=wfe109a97c64e4025bc74fdfc011d02a8&csf=1&web=1&e=9Bm3Ef |  |  |  | 2025-03-04 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | S/4 | S/4 MDG | NA | 2025-04-21 | 2025-05-16 | 2025-05-09 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-23 | 2025-11-04 | 2025-11-05 | 2025-08-29 | 100% | 2025-08-29 | 2025-11-03 | 2025-11-28 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-15 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-02-28 07:22 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-05 | 01.S4 |  |  | 1 | 1.45 | 1289 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-08-29 | 2025-11-05 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-11-15 | 2025-11-15 | 2025-11-15 | [5 empty] | 2025-05-16 | 2025-11-28 |  |  | 2025-10-08 |  |  |  | 0 |  | 1505 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14 - Awaiting approval (no open defects). FUT Approval ETA is 11/17 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Awaiting approval 10/24 - RFC connection issue is resolved. FUT in progress 10/10 : API Connections were set up recently, hence FUT is delayed as multiple issues are coming up while testing | 2025-11-28 | Y | 09A. Master Data |  |  |  | Awaiting Approval 1211 Approved |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-28 | 2025-08-29 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2260 | DATI1289_IF | 02.Interface | 02.IF - Intel Foundry | Program to update weight of material in the material master | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N | 2025-03-04 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_IP_OTC_LE_MM%20Weight%20Program.pptx?d=wfe109a97c64e4025bc74fdfc011d02a8&csf=1&web=1&e=9Bm3Ef |  |  |  | 2025-03-04 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA | S/4 | S/4 MDG | NA | 2025-04-21 | 2025-05-16 | 2025-05-09 | 100% | 2025-08-04 | 2025-08-18 | 2025-08-22 | 2025-09-26 | 100% | 2025-09-23 | 2025-11-04 | 2025-11-05 | 2025-08-29 | 100% | 2025-08-29 | 2025-11-03 | 2025-11-28 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-22 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-15 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-02-28 07:22 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-03-05 | 01.S4 | DATI1289_IP | 03.Medium | 0.3 | 0.435 | 1289 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-23 | 2025-09-26 | 2025-09-23 |  | 2025-08-29 | 2025-11-05 | [14 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-11-15 | 2025-11-15 | 2025-11-15 | [5 empty] | 2025-05-16 | 2025-11-28 |  |  | 2025-10-08 |  |  |  | 0 |  | 1506 | [7 empty] | 1. On Track | 3. Awaiting Approval | 11/14 - Awaiting approval (no open defects). FUT Approval ETA is 11/17 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Awaiting approval 10/24 - RFC connection issue is resolved. FUT in progress 10/10 : API Connections were set up recently, hence FUT is delayed as multiple issues are coming up while testing | 2025-11-28 | Y | 09A. Master Data |  |  |  | Awaiting Approval 1211 Approved |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-11-28 | 2025-08-29 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2672 | DATI1164 | 02.Interface | 02.IF - Intel Foundry | Update Min Max ROP proposals in IF S4 Hana(PDH to MDG to S4) | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/PLB-020-040_FTS_Update%20Min%20Max%20%20ROP%20proposals%20in%20IF%20s4%20Hana.pptx?d=w426fa303f122408eae51202616d8f771&csf=1&web=1&e=SF0cT2 | 02.No | 01.Yes |  | 2025-01-29 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | Supply Management and Materials Requirements Tool; IF Material PDH | S/4 | BODS | 2025-06-02 | 2025-06-20 | 2025-05-16 | 100% | 2025-05-23 | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-09-11 | 2025-09-08 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-14 | 2025-09-08 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-14 | 2025-06-30 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-09-01 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | [5 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-12-24 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-07 | Not Applicable | R3 Build & UT Sprint 21 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2025-01-23 15:43 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-01-29 | 02.MDG |  |  | 1 | 1.45 | 1164 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-06-20 | 2025-05-23 |  | 2025-09-11 | 2025-09-11 | 2025-09-11 |  | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-09-12 | 2025-09-12 | 2025-09-12 |  |  |  |  | 2025-10-14 | 2025-10-14 |  |  | 2026-01-07 | 2026-01-09 | 2026-01-07 | [5 empty] | 2025-06-20 | 2025-10-10 | 2025-07-16 | [5 empty] | 0 |  | 2669 | [7 empty] | 4. Completed | 3. Awaiting Approval | 01/05: Review comments have been addressed | 2025-10-10 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-14 | 2025-10-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2703 | DATI1132_IP | 02.Interface | 01.IP - Intel Product | Interface to exchange Yield and Scrap data between PDH Translator to SAP S/4 – Intel Product | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/8%20BOM/Intake%20Form/Draft%20_Intake%20Form_PDH_S4_IP_BOM.pptx?d=wedafaf43598644ad9060a615918d78f6&csf=1&web=1&e=gyK0Hs |  |  |  | 2025-01-23 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 02.No | NA | NA | PDH | S/4 | BODS | 2025-03-17 | 2025-04-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2025-07-18 | 100% | 2025-11-04 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-30 | 2025-06-16 | 2025-07-16 | 2025-07-18 | 100% | 2025-07-18 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-23 | [5 empty] | 2025-10-23 | 2025-10-23 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-30 | 2026-01-23 | N | 100% | 2026-02-05 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-01-20 06:30 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-01-23 | 01.S4 |  |  | 1 | 1.45 | 1132 | INT-CR0216 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-04 | 2025-11-04 | 2025-11-04 |  | 2025-09-30 | 2025-10-03 | 2025-09-30 | 2025-09-30 |  | 2025-07-18 |  | 2025-07-18 |  | 2025-11-07 | 2025-10-23 | 2025-10-23 |  |  |  |  | 2025-10-23 | 2025-10-23 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-04-30 | 2025-06-13 | 2025-05-16 | [5 empty] | 0 |  | 2605 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/02 : Team is addressing review comments, we are expecting approval by 02/04 | 2025-11-07 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-03 | 2025-09-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2702 | DATI1132_IF | 02.Interface | 02.IF - Intel Foundry | Interface to exchange Yield and Scrap data between PDH Translator to SAP S/4 – Intel Foundry | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/8%20BOM/Intake%20Form/Draft%20_Intake%20Form_PDH_S4_IF_BOM.pptx?d=w7e1d6552ec6c43ffb159697834ab18bb&csf=1&web=1&e=ifpF9S |  |  |  | 2025-01-23 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low |  | 02.No | NA | NA | PDH | S/4 | BODS | 2025-03-17 | 2025-04-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-15 | 2025-08-22 | 2025-07-11 | 100% | 2025-11-04 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-30 | 2025-08-29 | 2025-09-26 | 2025-10-03 | 100% | 2025-09-30 | 2025-06-16 | 2025-07-16 | 2025-07-16 | 100% | 2025-07-16 | 2025-11-03 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-23 | [5 empty] | 2025-10-23 | 2025-10-23 |  |  | 2025-12-24 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-30 | 2026-01-23 | N | 100% | 2026-02-05 | Sprint 22 Week 3 | R3 Build & UT Sprint 22 | 2025-11-07 | 2025-11-07 | 2025-11-07 | pgaroo@deloitte.com | 2025-01-20 06:30 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-01-23 | 01.S4 | DATI1132_IP | 03.Medium | 0.3 | 0.435 | 1132 | INT-CR0216 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-11-04 | 2025-11-04 | 2025-11-04 |  | 2025-09-30 | 2025-10-03 | 2025-09-30 | 2025-09-30 |  | 2025-07-16 |  | 2025-07-16 |  | 2025-11-07 | 2025-10-23 | 2025-10-23 |  |  |  |  | 2025-10-23 | 2025-10-23 |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | [5 empty] | 2025-04-30 | 2025-06-13 | 2025-05-16 | [5 empty] | 0 |  | 2604 | [7 empty] | 4. Completed | 3. Awaiting Approval | 02/02 : Team is addressing review comments, we are expecting approval by 02/04 | 2025-11-07 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-10-03 | 2025-09-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2499 | DATI0960 | 02.Interface | 07.MDG | To transfer HRMM data retrieved by Signature Authority API from source system WCDS to target system MDG & CFIN by Mulesoft | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/3%20Final%20Deliverables/Release%20R3/2.%20Build/6.%20HRMM/RICEFW/Intake%20Forms/HRMM_SignatureAuthority%20API_Intake%20Form.pptx?d=w7a28c8bc413f46cba180acd0efecaa58&csf=1&web=1&e=p1FpHe | 02.No | 01.Yes |  | 2024-12-20 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 10772 | Worker Data Services (WDS) | WCDS | S/4 MDG | MULESOFT | 2024-11-01 | 2024-11-08 | 2025-01-24 | 100% | 2024-12-18 | 2025-02-24 | 2025-03-21 | 2025-02-21 | 100% | 2025-02-17 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-04-11 | 100% | 2025-05-05 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 100% | 2025-05-01 | 2025-08-04 | 2025-08-04 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-17 | 2025-05-31 | 2025-06-11 | N | 100% | 2025-07-31 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-11-26 00:26 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-10 | 02.MDG |  |  | 1 | 1.45 | 0960 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-02-17 | 2025-03-21 | 2025-02-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | [5 empty] | 2024-11-08 | 2025-05-16 | 2025-01-24 | S4 | 2025-05-31 |  |  |  | 0 |  | 2395 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change | This FUT is 100% complete. BSPID-42939 | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2498 | DATI0959 | 02.Interface | 07.MDG | To transfer HRMM data retrieved by Worker snapshot API from source system WCDS to target system MDG & CFIN by Mulesoft | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/3%20Final%20Deliverables/Release%20R3/2.%20Build/6.%20HRMM/RICEFW/Intake%20Forms/HRMM_workersnapshot%20API_Intake%20Form.pptx?d=w4d97bb3ac5c642e38ef32d0b25a908cf&csf=1&web=1&e=30Muv2 | 02.No | 01.Yes |  | 2024-12-20 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Functions | 01.Yes | 10772 | Worker Data Services (WDS) | WCDS | S/4 MDG | MULESOFT | 2024-10-30 | 2024-11-05 | 2025-01-24 | 100% | 2024-12-18 | 2024-11-15 | 2024-11-29 | 2025-02-21 | 100% | 2025-02-17 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2025-03-24 | 2025-04-18 | 2025-05-16 | 100% | 2025-08-04 | 2024-12-16 | 2025-01-24 | 2025-02-21 | 100% | 2025-02-21 | 2025-02-24 | 2025-03-21 | 2025-04-11 | 100% | 2025-05-05 | 2025-03-24 | 2025-05-23 | 2025-05-23 | 100% | 2025-05-23 | 2025-08-04 | 2025-08-04 |  |  | 2025-05-23 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-09 | 2025-06-20 | 2025-06-11 | N | 100% | 2025-07-23 | Not Applicable | R3 Build & UT Sprint 16 | 2025-04-18 | 2025-05-23 | 2025-05-23 | pgaroo@deloitte.com | 2024-11-26 00:26 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-01-10 | 02.MDG |  |  | 1 | 1.45 | 0959 |  | R3 ITC1 | [6 empty] | 2024-12-18 | 2025-01-24 | 2024-12-18 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-02-21 |  | 2025-02-21 |  | 2025-05-05 | 2025-05-05 | 2025-05-05 |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-23 | 2025-07-23 | 2025-07-23 | [5 empty] | 2024-11-05 | 2025-04-18 | 2025-01-24 | S4 | 2025-04-26 |  |  |  | 0 |  | 2394 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change |  | 2025-05-23 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2254 | DATI0944 | 02.Interface | 01.IP - Intel Product | Interface to Send/Receive item master Data Asynchronously between PLM Translator and MDG | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2254_Master%20Data_Interface%20to%20SendReceive%20Material%20Master%20Data%20between%20Translator%20and%20MDG%20(SPEED%EF%83%A0Translator%EF%83%A0MDG)Master%20Data_Asynchronous%20Interface.pptx?d=w60437dd97b5e4809942c2a5ac9dd5b5f&csf=1&web=1&e=xkj3oL | 02.No | 01.Yes |  | 2024-12-02 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium | Corporate Data & Insights (CDI) | 01.Yes | 4092; 11140; 41744; 38775; 17296 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED); PDM Translator; Windchill - Equipment Configuration Management; Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI | PLM | S/4 MDG | NA | 2024-12-10 | 2025-02-28 | 2025-03-14 | 100% | 2025-03-19 | 2025-08-18 | 2025-09-12 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2025-09-12 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-18 | 2025-09-12 | 2025-06-11 | 100% | 2025-06-11 | [10 empty] | 2025-04-07 | 2025-05-02 | 2025-05-02 | 100% | 2025-05-02 | 2025-06-11 | 2025-06-11 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-22 | Not Applicable | R3 Build & UT Sprint 16 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 02.MDG |  |  | 1 | 1.45 | 0944 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | 2025-08-04 | 2025-09-12 | 2025-08-04 |  | 2025-06-11 | 2025-09-12 | 2025-06-11 | 2025-06-11 | [9 empty] | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-06-11 | 2025-06-11 |  |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | [5 empty] | 2025-02-28 | 2025-07-25 | 2025-08-15 | S4 | 2025-09-26 |  |  |  | 0 |  | 2284 | [7 empty] | 1. On Track |  | Approva; Pending | 2025-09-12 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-09-12 | 2025-06-11 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2181 | DATI0943 | 02.Interface | 01.IP - Intel Product | Interface to Send/Receive item master Data between PLM Translator and MDG Synchronously. | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2181_Master%20Data_Interface%20to%20SendReceive%20Material%20Master%20Data%20between%20Translator%20and%20MDG%20(SPEED%EF%83%A0Translator%EF%83%A0MDG)Master%20Data_Interface.pptx?d=w01ee1b8025024f3385b4a5713abbc642&csf=1&web=1&e=QldTQ7 | 02.No | 01.Yes |  | 2024-12-02 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Data & Insights (CDI) | 01.Yes | 4092; 11140; 41744; 38775; 17296 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED); PDM Translator; Windchill - Equipment Configuration Management; Equipment Item BOM Master Data-Factory Equipment Workflow-Pega PSI | S/4 MDG | PLM | APIGEE | 2024-12-10 | 2025-02-28 | 2025-03-14 | 100% | 2025-03-20 | 2025-04-01 | 2025-04-07 | 2025-04-04 | 100% | 2025-03-26 | 2025-07-21 | 2025-08-15 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-21 | 2025-08-15 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-16 | 2025-07-18 | 2025-04-18 | 100% | 2025-04-18 | 2025-09-15 | 2025-06-27 | 2025-03-28 | 100% | 2025-03-28 | 2025-04-07 | 2025-05-02 | 2025-05-02 | 100% | 2025-05-02 | 2025-08-04 | 2025-08-04 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-07-22 | Not Applicable | R3 Build & UT Sprint 16 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-11-20 03:23 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 02.MDG |  |  | 1 | 1.45 | 0943 |  | R3 ITC1 | [6 empty] | 2025-03-20 | 2025-03-20 | 2025-03-20 |  | 2025-03-26 | 2025-04-07 | 2025-03-26 |  | 2025-08-04 | 2025-08-15 | 2025-08-04 | 2025-08-04 |  | 2025-07-18 |  | 2025-04-18 |  | 2025-06-27 | 2025-03-28 | 2025-03-28 |  | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-08-04 | 2025-08-04 |  |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | [5 empty] | 2025-02-28 | 2025-05-09 | 2025-07-18 | S4 | 2025-10-17 |  |  |  | 0 |  | 1667 | [10 empty] | 2025-08-15 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-15 | 2025-08-04 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2418 | DATI0927 | 02.Interface | 02.IF - Intel Foundry | Inbound Interface to exchange BOM data between PLM Translator to SAP S/4 – Intel Foundry | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2418_Master%20Data_Interface%20to%20exchange%20BOM%20data%20between%20PLM%20Translator%20to%20SAP%20S4%20%E2%80%93%20Intel%20Product.pptx?d=w7a8a249537b54a3485fb38b224889198&csf=1&web=1&e=3WW4gd | 02.No | 01.Yes |  | 2024-12-02 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Data & Insights (CDI) | 01.Yes | 41744 | PDM Translator | PLM | S/4 | MULESOFT | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-15 | 2025-06-06 | 2025-06-13 | 2025-05-30 | 100% | 2025-06-02 | 2025-07-11 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-11 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-06-16 | 2025-07-18 | 2025-06-06 | 100% | 2025-06-06 | 2025-07-21 | 2025-08-15 | 2025-06-06 | 100% | 2025-06-11 | 2025-06-30 | 2025-07-25 | 2025-07-25 | 100% | 2025-07-25 | 2025-06-11 | 2025-07-25 |  | 2025-08-01 | 2025-08-08 | 2025-08-13 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | pgaroo@deloitte.com | 2024-11-20 03:31 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-12-11 | 01.S4 |  |  | 2 | 2.9 | 0927 |  | R3 ITC1 | [6 empty] | 2025-04-15 | 2025-04-15 | 2025-04-15 |  | 2025-06-02 | 2025-06-13 | 2025-06-02 |  | 2025-06-06 | 2025-07-18 |  |  |  | 2025-07-18 |  | 2025-06-06 |  | 2025-08-15 | 2025-06-11 | 2025-06-11 |  | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-06-11 | 2025-07-25 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | [5 empty] | 2025-03-21 | 2025-07-18 | 2025-07-18 |  | 2025-08-13 |  |  |  | 0 |  | 1437 | [7 empty] | 1. On Track | 3. Awaiting Approval | 09/29:awaiting approval 09/12: FUT submitted on 09/5 , Review is in progress ETA - 09/16 | 2025-08-15 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 16 |  | 2025-07-18 | 2025-06-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 825 | DATI0657_IP | 02.Interface | 01.IP - Intel Product | RICEFW2 - Interface between MDG and Reltio to fetch details to support pop-up and Data Monitor Report | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/05.%20Scope%20and%20Change%20Control/Change%20Control/Change%20Request%20Decks/Data/45_MDG_CR%20Customer%20Master%20Reltio%20Interfaces.pptx?d=w165bfafdaf1e471185f637d22573c7bc&csf=1&web=1&e=71CDTe | 02.No | 01.Yes | DATI0391 | 2025-07-23 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium |  | 01.Yes | 25490 | Reltio |  |  | MULESOFT | 2025-08-18 | 2025-08-29 | 2025-08-29 | 100% | 2025-08-20 | 2025-08-09 | 2025-11-05 | 2025-11-05 | 100% | 2025-10-29 | 2025-09-15 | 2025-10-08 | 2025-11-05 | 100% | 2025-11-07 | 2025-09-15 | 2025-10-08 | 2025-11-05 | 100% | 2025-11-07 | 2025-08-18 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-15 | 2025-10-08 | 2025-09-26 | 100% | 2025-09-17 | 2025-07-07 | 2025-07-29 | 2025-07-29 | 100% | 2025-07-29 | 2025-11-07 | 2025-11-07 |  |  | 2025-11-21 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-07-23 05:33 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-08-12 | 02.MDG |  |  | 1 | 1.45 | 0657 |  | R3 ITC1 | [6 empty] | 2025-08-20 | 2025-08-29 | 2025-08-20 |  | 2025-10-29 | 2025-11-05 | 2025-10-29 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-17 | 2025-09-17 |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-11-07 | 2025-11-07 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-08-29 | 2025-10-08 | 2025-09-10 |  | 2025-12-05 |  |  |  | 0 |  | 3182 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/18- FUT submitted for review and approval on 11/13 | 2025-10-08 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1999 | DATI0582 | 02.Interface | 01.IP - Intel Product | Interface to pull Vendor Master from Reltio to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/External%20Vendor%20Master_Interface%20between%20Reltio%20%26%20MDG_Intake%20Form.pptx?d=w8eb928757b16409498095bc850be57df&csf=1&web=1&e=LPe1tZ | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 02.High | Corporate Data & Insights (CDI) | 01.Yes | 25490 | Reltio | Reltio | S/4 | MULESOFT | 2024-10-21 | 2024-12-13 | 2024-11-15 | 100% | 2024-12-16 | 2025-01-06 | 2025-01-17 | 2025-02-21 | 100% | 2025-02-17 | 2025-01-20 | 2025-02-14 | 2025-04-18 | 100% | 2025-04-25 | 2025-02-17 | 2025-02-28 | 2025-04-18 | 100% | 2025-04-25 | 2024-12-16 | 2025-01-24 | 2025-01-24 | 100% | 2025-01-24 | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-03-21 | 2025-02-17 | 2025-02-28 | 2025-02-28 | 100% | 2025-04-30 | 2025-04-25 | 2025-04-30 |  |  | 2025-07-16 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-08-13 | 2025-08-13 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2024-09-07 | 02.MDG |  |  | 2 | 2.9 | 0582 |  | R3 ITC1 | [6 empty] | 2024-12-16 | 2024-12-16 | 2024-12-16 |  | 2025-02-17 | 2025-02-21 | 2025-02-17 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 |  | 2025-01-24 |  | 2025-01-24 |  | 2025-03-21 |  | 2025-03-21 |  | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-25 | 2025-04-30 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | [5 empty] | 2024-12-13 | 2025-02-14 | 2025-01-24 | S4 | 2025-07-11 |  |  |  | 0 | 08. Not Applicable | 1947 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 08/29:Review is in progress,comments addressed,awaiting approval 08/18:Bank issue identified and target to complete by 08/18 07/26: FUT in Progress 22/24 test cases tested and shared with Intel for review , | 2025-03-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 13 |  | 2025-04-25 | 2025-04-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 821 | DATI0394_IP | 02.Interface | 01.IP - Intel Product | Inbound Interface from Reltio to MDG to receive BP ID and UCD ID to MDG and update the UCD ID under Identification tab | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/821_Master%20Data_Intake%20Form.pptx?d=w1df8ece63159418eb32a2c2aab1a25b6&csf=1&web=1&e=J6zYdu | 02.No | 01.Yes |  | 2024-06-21 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Data & Insights (CDI) | 01.Yes | 25490 | Reltio | Reltio | S/4 MDG | MULESOFT | 2024-09-06 | 2025-02-07 | 2025-08-29 | 100% | 2025-08-22 | 2025-06-02 | 2025-06-06 | 2025-09-26 | 100% | 2025-09-08 | 2025-06-09 | 2025-06-20 | 2025-10-08 | 100% | 2025-11-07 | 2025-06-23 | 2025-06-30 | 2025-10-08 | 100% | 2025-11-07 | 2025-08-18 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-26 | 2025-09-15 | 2025-10-08 | 2025-09-26 | 100% | 2025-09-17 | 2025-06-09 | 2025-07-29 | 2025-07-29 | 100% | 2025-07-29 | 2025-11-07 | 2025-11-07 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | jenoronha@deloitte.com | 2025-07-23 05:21 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 02.MDG |  |  | 1 | 1.45 | 0394 | INT-CR0034 | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-08-29 | 2025-08-22 |  | 2025-09-08 | 2025-09-26 | 2025-09-08 |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 |  | 2025-09-26 |  | 2025-09-26 |  | 2025-10-08 | 2025-09-17 | 2025-09-17 |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-11-07 | 2025-11-07 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-02-07 | 2025-06-30 | 2025-09-10 |  | 2025-11-05 |  |  |  | 0 | 08. Not Applicable | 3181 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Addressing review comments 10/24 - FUT in progress. ETA for submission is 10/27 | 2025-10-08 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-11-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 821 | DATI0394_IF | 02.Interface | 02.IF - Intel Foundry | Inbound Interface from Reltio to MDG to receive BP ID and UCD ID to MDG and update the UCD ID under Identification tab | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/821_Master%20Data_Intake%20Form.pptx?d=w1df8ece63159418eb32a2c2aab1a25b6&csf=1&web=1&e=J6zYdu | 02.No | 01.Yes |  | 2024-06-21 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Data & Insights (CDI) | 01.Yes | 25490 | Reltio | Reltio | S/4 MDG | MULESOFT | 2024-09-06 | 2025-02-07 | 2025-08-29 | 100% | 2025-08-22 | 2025-06-02 | 2025-06-06 | 2025-03-21 | 100% | 2025-03-25 | 2025-06-09 | 2025-06-20 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-23 | 2025-06-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2025-09-10 | 2025-04-18 | 100% | 2025-04-18 | 2025-09-15 | 2025-10-08 | 2025-04-25 | 100% | 2025-08-04 | 2025-06-23 | 2025-06-30 | 2025-06-30 | 100% | 2025-07-31 | 2025-08-04 | 2025-08-04 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-10 | 2025-10-08 | N | 100% | 2025-11-06 | Not Applicable | R3 Build & UT Sprint 19 | 2025-10-08 | 2025-10-08 | 2025-10-08 | pgaroo@deloitte.com | 2024-06-21 03:27 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 |  | 02.MDG | DATI0394_IP | 03.Medium | 0.3 | 0.435 | 0394 | INT-CR0034 | R3 ITC1 | [6 empty] | 2025-08-22 | 2025-08-29 | 2025-08-22 |  | 2025-03-25 | 2025-06-06 | 2025-03-25 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-09-10 |  | 2025-04-18 |  | 2025-10-08 | 2025-08-04 | 2025-08-04 |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-08-04 | 2025-08-04 |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | [5 empty] | 2025-02-07 | 2025-06-30 | 2025-09-10 |  | 2025-10-10 |  |  |  | 0 | 08. Not Applicable | 1652 | [7 empty] | 1. On Track | 17. FUT In progress | 10/30 - FUT in progress. will be submitted for approval today. 10/24 - Mulesoft changes are in progress. ETA is 10/29 10/10 : FUT needs change in approach. | 2025-10-08 | Y | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 822 | DATI0393_IP | 02.Interface | 01.IP - Intel Product | Replicating Customer Master data from MDG to cFin,IF and IP systems | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/822_Master%20Data_Intake%20Form.pptx?d=w9d3429c1467f4923b84110ce7e3996fa&csf=1&web=1&e=arLMS2 | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No | NA | NA |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-05-23 | 2025-06-02 | 2025-06-13 | 2025-09-10 | 100% | 2025-08-21 | 2025-06-16 | 2025-07-04 | 2025-09-10 | 100% | 2025-08-18 | 2025-06-16 | 2025-07-04 | 2025-09-10 | 100% | 2025-08-18 | [15 empty] | 2025-08-18 | 2025-08-18 |  |  | 2025-08-13 | 2025-09-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-25 | 2025-09-05 | 2025-09-05 | N | 100% | 2025-08-28 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-04 | 2025-07-04 | 2025-07-04 | pgaroo@deloitte.com | 2025-04-02 04:07 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2025-04-03 | 02.MDG | DATI0393 | 04.Low | 0.15 | 0.2175 | 0393 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-06-13 | 2025-05-23 |  | 2025-08-21 | 2025-09-10 | 2025-08-21 |  | 2025-08-18 | 2025-09-10 | 2025-08-18 | 2025-08-18 | [12 empty] | 2025-08-18 | 2025-08-18 |  |  | 2025-08-28 | 2025-09-05 | 2025-08-28 | [5 empty] | 2025-06-13 | 2025-07-04 |  |  | 2025-09-05 |  |  |  | 0 |  | 2851 | [10 empty] | 2025-07-04 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-08-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 824 | DATI0392_IP | 02.Interface | 01.IP - Intel Product | Outbound Interface from MDG to Reltio to send the Name, Address, URL, BP ID and UCD ID (if present) to Reltio | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/824_Master%20Data_Intake%20Form.pptx?d=wecb982030c934a8190d0e7b70d9e1122&csf=1&web=1&e=oSC2SJ | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 03.Medium | Corporate Data & Insights (CDI) | 01.Yes | 25490 | Reltio |  |  | MULESOFT | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-05-23 | 2025-06-09 | 2025-06-27 | 2025-08-13 | 100% | 2025-08-05 | 2025-06-23 | 2025-07-25 | 2025-08-15 | 100% | 2025-08-25 | 2025-06-23 | 2025-07-25 | 2025-08-15 | 100% | 2025-08-25 | 2025-07-14 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-16 | 2025-08-11 | 2025-08-14 | 2025-08-13 | 100% | 2025-08-14 | 2025-06-23 | 2025-07-29 | 2025-07-29 | 100% | 2025-07-29 | 2025-08-25 | 2025-08-25 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-09-26 | N | 100% | 2025-09-23 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-14 | 2025-08-14 | 2025-08-14 | pgaroo@deloitte.com | 2025-04-02 04:07 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-04-03 | 02.MDG | DATI0392 | 03.Medium | 0.3 | 0.435 | 0392 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-06-13 | 2025-05-23 |  | 2025-08-05 | 2025-08-13 | 2025-08-05 |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  | 2025-07-18 |  | 2025-07-16 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-08-25 | 2025-08-25 |  |  | 2025-09-23 | 2025-10-08 | 2025-09-23 | [5 empty] | 2025-06-13 | 2025-07-25 | 2025-07-18 |  | 2025-10-08 |  |  |  | 0 |  | 2857 | [7 empty] | 1. On Track |  |  | 2025-08-14 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-25 | 2025-08-25 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 825 | DATI0391_IP | 02.Interface | 01.IP - Intel Product | Interface between MDG and Reltio to fetch details to support pop-up and Data Monitor Report | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/825_Master%20Data_Intake%20Form.pptx?d=w5ef48e1ddb3d4131ac334f7bbfefbbc6&csf=1&web=1&e=2KuEqr | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte | 01. Deloitte | 01.Deloitte | 04.Low | Corporate Data & Insights (CDI) | 01.Yes | 25490 | Reltio |  |  | MULESOFT | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-05-23 | 2025-06-09 | 2025-06-27 | 2025-07-16 | 100% | 2025-07-21 | 2025-06-23 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-09 | 2025-06-23 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-09 | 2025-07-14 | 2025-07-18 | 2025-07-16 | 100% | 2025-07-16 | 2025-08-11 | 2025-08-14 | 2025-08-13 | 100% | 2025-08-14 | 2025-06-23 | 2025-07-29 | 2025-07-29 | 100% | 2025-07-29 | 2025-09-09 | 2025-09-09 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-23 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2025-04-02 04:07 | sdeolalikar@deloitte.com | 2026-03-24 07:45 | 10 | 2025-04-03 | 02.MDG | DATI0391 | 04.Low | 0.15 | 0.2175 | 0391 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-06-13 | 2025-05-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 |  | 2025-07-18 |  | 2025-07-16 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 |  | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-09-09 | 2025-09-09 |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | [5 empty] | 2025-06-13 | 2025-09-10 | 2025-07-18 |  | 2025-10-08 |  |  |  | 0 |  | 2856 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/15 - Business approval received, awaiting IT approval 10/10 : Reltio team confirmed that the change in Reltio will be completed by 10/17. MDG FUT update would be completed by 10/22 and approval by 10/24 | 2025-09-10 | Y | 09A. Master Data | [7 empty] | Defects | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3205 | DATE1737_IP | 04.Enhancement | 01.IP - Intel Product | Change BOM UI with BOM update Logic that can be run in background & Error processing Logic​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 4 | 4 | 1737 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3442 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1737_IF | 04.Enhancement | 02.IF - Intel Foundry | Change BOM UI with BOM update Logic that can be run in background & Error processing Logic​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1737_IP | 01.Very High | 0.8 | 0.8 | 1737 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3443 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1736_IP | 04.Enhancement | 01.IP - Intel Product | Create BOM UI with Logic to combine Group BOM and MPV Component Table & Error processing Logic​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1736 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3441 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1736_IF | 04.Enhancement | 02.IF - Intel Foundry | Create BOM UI with Logic to combine Group BOM and MPV Component Table & Error processing Logic​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1736_IP | 02.High | 0.4 | 0.4 | 1736 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3451 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1735_IP | 04.Enhancement | 01.IP - Intel Product | Reprocess Errors based on Error Categories (replication ¦ BOM ¦ etc.)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 4 | 4 | 1735 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3440 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1735_IF | 04.Enhancement | 02.IF - Intel Foundry | Reprocess Errors based on Error Categories (replication ¦ BOM ¦ etc.)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1735_IP | 01.Very High | 0.8 | 0.8 | 1735 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3450 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1734_IP | 04.Enhancement | 01.IP - Intel Product | Search BOM using Plant and Parent ( User selects components from entire BOM with ALL components)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1734 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3439 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1734_IF | 04.Enhancement | 02.IF - Intel Foundry | Search BOM using Plant and Parent ( User selects components from entire BOM with ALL components)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1734_IP | 02.High | 0.4 | 0.4 | 1734 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3449 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1733_IP | 04.Enhancement | 01.IP - Intel Product | Search BOM by Keyword and fetch only matching components​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1733 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3438 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1733_IF | 04.Enhancement | 02.IF - Intel Foundry | Search BOM by Keyword and fetch only matching components​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1733_IP | 02.High | 0.4 | 0.4 | 1733 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3448 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1732_IP | 04.Enhancement | 01.IP - Intel Product | Maintain MPV Component table (add, update, inactivate)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1732 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3437 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1732_IF | 04.Enhancement | 02.IF - Intel Foundry | Maintain MPV Component table (add, update, inactivate)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1732_IP | 02.High | 0.4 | 0.4 | 1732 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3447 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1731_IP | 04.Enhancement | 01.IP - Intel Product | Upload records to MPV Keyword or MPV Component table​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1731 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3436 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1731_IF | 04.Enhancement | 02.IF - Intel Foundry | Upload records to MPV Keyword or MPV Component table​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1731_IP | 02.High | 0.4 | 0.4 | 1731 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3446 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1730_IP | 04.Enhancement | 01.IP - Intel Product | Create/Maintain Keyword for Plant / or update multiple Keywords into MPV Keyword Table​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1730 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3435 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1730_IF | 04.Enhancement | 02.IF - Intel Foundry | Create/Maintain Keyword for Plant / or update multiple Keywords into MPV Keyword Table​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1730_IP | 02.High | 0.4 | 0.4 | 1730 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3445 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1729_IP | 04.Enhancement | 01.IP - Intel Product | Custom Tables – 3x (needed to support entire FS)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:25 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 |  |  | 2 | 2 | 1729 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3434 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3205 | DATE1729_IF | 04.Enhancement | 02.IF - Intel Foundry | Custom Tables – 3x (needed to support entire FS)​ | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B3E30321B-0527-4758-A2CA-267D3D123615%7D&file=CR1715_Elaboration%20for%20External_BOM_Automation.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-02-21 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  | 2026-03-20 | 100% | 2026-03-17 |  |  | 2026-03-31 | 99% | 2026-03-31 |  |  | 2026-05-27 | 0% | 2026-05-27 |  |  | 2026-05-27 | 0% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  |  |  | 2026-06-05 | N | 0% | 2026-06-05 |  | R3 Build & UT Sprint OB2 |  |  |  | jenoronha@deloitte.com | 2026-02-21 03:28 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 |  | 01.S4 | DATE1729_IP | 02.High | 0.4 | 0.4 | 1729 | INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-17 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [14 empty] | 0 |  | 3444 | [7 empty] | 1. On Track | 15. Planned for Future Sprint | 4/3 : Dev In-progress. |  | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 | [9 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 04.R4 | 3107 | DATE1633 | 04.Enhancement | 02.IF - Intel Foundry | SIMS External BOM - Update lead time offset for BOM Components | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev Unplanned | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/Console_ID_3107_SIMS%20BOM_Lead%20time%20offset-Enhancement.pptx?d=w97e66190e8aa48099196ffca20ddc44b&csf=1&web=1&e=lwKWcu | 02.No | 01.Yes |  | 2025-10-08 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-12-08 | 2026-02-04 | 2026-02-04 | 100% | 2026-01-12 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-09-28 03:35 | mdfarhan@deloitte.com | 2026-03-05 23:47 | 6 | 2025-10-17 | 01.S4 |  |  | 1 | 1 | 1633 | INT-CR1015 | R4 ITC1 | [5 empty] | 2026-01-12 | 2026-01-12 | 2026-02-06 | 2026-02-06 | [33 empty] | 2026-02-04 | [7 empty] | 0 |  | 3313 | [7 empty] | 5. Not Dispositioned |  |  |  | N | 09A. Master Data | [8 empty] | N/A |  |  |  |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3081 | DATE1623 | 04.Enhancement | 07.MDG | Custom table to store WCDS attributes based on BusinessTitleNm | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | Y | 2025-10-16 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/3%20Final%20Deliverables/Release%20R3/2.%20Build/6.%20HRMM/RICEFW/Intake%20Forms/IFL%20Intake%20Forms%20for%20Time%20Keeping/HRMM_Custom%20table%20to%20store%20WCDS%20attributes%20based%20on%20BusinessTitleNm.pptx?d=w75de842993454a09b7b1f660ebec5fb8&csf=1&web=1&e=azDTK9 | 02.No | 01.Yes |  | 2025-09-16 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-10-17 | 2025-10-31 | 100% | 2025-10-16 | 2025-10-11 | 2025-11-14 | 2025-11-05 | 100% | 2025-11-06 | 2025-11-17 | 2025-12-05 | 2025-11-05 | 100% | 2025-11-06 | 2025-11-17 | 2025-12-05 | 2025-11-05 | 100% | 2025-11-06 | [15 empty] | 2025-11-06 | 2025-11-06 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-03 | Not Applicable | R3 Build & UT Sprint 20 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-09-16 04:57 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-10-17 | 02.MDG |  |  | 0.5 | 0.5 | 1623 | INT-CR1090 | R3 ITC1 | [6 empty] | 2025-10-16 | 2025-10-31 | 2025-10-16 |  | 2025-11-06 | 2025-11-14 | 2025-11-06 |  | 2025-11-06 | 2025-12-05 | 2025-11-06 | 2025-11-06 | [12 empty] | 2025-11-06 | 2025-11-06 |  |  | 2025-12-03 | 2025-12-05 | 2025-12-03 | [5 empty] | 2025-10-17 | 2025-12-05 |  |  | 2025-12-05 |  |  |  | 0 |  | 3283 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18 - FUT to be submitted for Intel review on 11/28 | 2025-12-05 | Y | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-12-05 | 2025-11-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3090 | DATE1616_IP | 04.Enhancement | 01.IP - Intel Product | Automate External BOM | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console_ID_3090_External_BOM_Automation.pptx?d=w7d54b06b37ea4eedb84d2d2ea00fecd5&csf=1&web=1&e=buR0d3 | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-12 | 2026-01-12 | 2026-01-16 | 2026-03-31 | 99% | 2026-03-31 | 2026-02-16 | 2026-02-27 | 2026-05-27 | 45% | 2026-05-27 | 2026-02-16 | 2026-02-27 | 2026-05-27 | 45% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-06-05 | N | 0% | 2026-06-05 | Sprint 23 Week 4 | R3 Build & UT Sprint OB2 | 2026-02-27 | 2026-02-27 | 2026-02-27 | jonsanders@deloitte.com | 2025-08-27 07:43 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 | 2025-09-03 | 01.S4 |  |  | 2 | 2 | 1616 | INT-CR1013, INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-01-12 | 2026-01-12 | 2026-02-09 | 2026-02-09 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [6 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-06 |  |  |  | 0 |  | 3280 | [7 empty] | 2. At Risk | 19. Incomplete Build | 4/3 : Dev In-progress. | 2026-02-27 | Y | 09A. Master Data |  |  |  | 02/24: New object created via a CR INT-CR1013. Build in progress. ETA 03/06 Current status: Build in progress Issue: FUT at risk of going beyond 3/6 Next steps: Expedite FUT once build completes. Help needed: n/a FUT ETA: TBD |  |  | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3090 | DATE1616_IF | 04.Enhancement | 02.IF - Intel Foundry | Automate External BOM | 09A. Master Data | 9A.2 Master Data - BOM | 06. Dev In Progress | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/20%20RICEFW%20Pending%20Approval/Console_ID_3090_External_BOM_Automation.pptx?d=w7d54b06b37ea4eedb84d2d2ea00fecd5&csf=1&web=1&e=buR0d3 | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-01-12 | 2026-01-12 | 2026-01-16 | 2026-03-31 | 99% | 2026-03-31 | 2026-02-16 | 2026-02-27 | 2026-05-27 | 45% | 2026-05-27 | 2026-02-16 | 2026-02-27 | 2026-05-27 | 45% | 2026-05-27 | [15 empty] | 2026-05-27 | 2026-05-27 |  |  | 2026-05-29 | 2026-06-05 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-06-05 | N | 0% | 2026-06-05 | Sprint 23 Week 4 | R3 Build & UT Sprint OB2 | 2026-02-27 | 2026-02-27 | 2026-02-27 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-04-03 16:20 | 6 | 2025-09-03 | 01.S4 | DATE1616_IP | 02.High | 0.4 | 0.4 | 1616 | INT-CR1013, INT-CR1715 | R3 ITC2 | R3 ITC2 |  |  |  |  | 2026-01-12 | 2026-01-12 | 2026-02-09 | 2026-02-09 |  |  | 2026-03-31 |  |  |  | 2026-05-27 | [19 empty] | 2026-06-05 | [6 empty] | 2026-02-06 | 2026-02-27 |  |  | 2026-03-06 |  |  |  | 0 |  | 3265 | [7 empty] | 1. On Track | 19. Incomplete Build | 4/3 : Dev In-progress. | 2026-02-27 | Y | 09A. Master Data |  |  |  | 02/24: New object created via a CR INT-CR1013. Build in progress. ETA 03/06 Current status: Build in progress Issue: FUT at risk of going beyond 3/6 Next steps: Expedite FUT once build completes. Help needed: n/a FUT ETA: TBD |  |  | Approved Exception (ITC2) | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint OB2 |  | 2026-05-27 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3089 | DATE1615 | 04.Enhancement | 07.MDG | Automate the PROC material master creation process based on business rules | 09A. Master Data | 9A.6 Master Data - Material | 06. Dev In Progress | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3089_Master%20Data_Enhancement_Automate%20PROC%20Material%20Creation.pptx?d=wda593c62f0ab46bf986985e18dcbedbb&csf=1&web=1&e=fPvaLB | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-23 | 2025-12-08 | 2026-01-09 | 2026-03-04 | 100% | 2026-02-22 | 2026-02-09 | 2026-03-04 | 2026-03-04 | 50% | 2026-03-04 | 2026-02-09 | 2026-03-04 | 2026-03-04 | 50% | 2026-03-04 | [15 empty] | 2026-03-04 | 2026-03-04 |  |  | 2026-02-27 | 2026-04-30 |  | 0% | 0% |  |  |  | 01. Not Started | 01. Not Started |  |  | 2026-02-09 | 2026-03-06 | 2026-04-30 | N | 0% | 2026-04-30 | Sprint 23 Week 4 | R3 Build & UT Sprint OB1 | 2026-03-04 | 2026-03-04 | 2026-03-04 | jenoronha@deloitte.com | 2025-08-23 03:09 | cell-link@smartsheet.com | 2026-03-27 13:36 | 6 | 2025-09-03 | 02.MDG |  |  | 1 | 1 | 1615 | INT-CR1825, INT-CR0918 | R3 ITC1 | [6 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23 |  | 2026-02-22 | 2026-03-04 | 2026-02-22 |  |  | 2026-03-04 | [19 empty] | 2026-04-30 | 2026-04-30 | [5 empty] | 2026-02-06 | 2026-03-04 |  |  | 2026-03-06 |  |  |  | 0 |  | 3263 | [7 empty] | 2. At Risk | 19. Incomplete Build | 3/27: Build is not started , due to high complexity of object | 2026-03-04 | Y | 09A. Master Data |  |  |  | 03/23: Build in progress. ETA 04/30. CR1825 was presented on 03/20 and was rejected. This object will be tracked as delayed. Current status: Build in progress Issue: FUT at risk of going beyond 4/10 Next steps: Expedite FUT once build completes. Help needed: n/a FUT ETA: 04/30 |  | 2. Risk | At risk for S23+ | Dev In Progress/Dependency | Current Sprint Remaining (Not Delayed) | R3 Build & UT Sprint 23 |  | 2026-03-04 |  | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3086 | DATE1613 | 04.Enhancement | 02.IF - Intel Foundry | HAZMAT Profile UI | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_HAZMAT_Material%20Master_%20MDG.pptx?d=w433be3d881454d808f40d8146de793c3&csf=1&web=1&e=swZgyb | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2025-10-17 | 2025-10-24 | 2025-12-12 | 100% | 2026-01-31 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | 2025-11-10 | 2025-12-05 | 2026-01-07 | 100% | 2026-02-07 | [15 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-02-27 | 2026-03-27 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-27 | N | 100% | 2026-04-02 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-03 | 01.S4 |  |  | 1 | 1 | 1613 | INT-CR0728 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | [12 empty] | 2026-02-07 | 2026-02-07 |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | [5 empty] | 2025-11-07 | 2025-12-05 |  |  | 2026-03-04 |  | Hazmat WIINGS Only | TRUE | 0 |  | 3260 | [7 empty] | 1. On Track | 3. Awaiting Approval | 3/27: Awaiting approval. Addressed additional review comments. | 2025-12-05 | N | 09A. Master Data | Hazmat |  |  | 03/23: FUT in progress. 4 defect fix in progress. FUT ETA 04/10 |  |  | On track for S23+ | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-07 | 2026-02-07 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 3084 | DATE1611_IP | 04.Enhancement | 01.IP - Intel Product | 2A1 Enhancement to send Product Catalog to OpenText | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2A1_Material%20Master_%20Interface%20S4%20IP_IF%20to%20OpenText.pptx?d=w3ac92b57e9514087aa6f66666345737e&csf=1&web=1&e=cdeefu | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-27 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-31 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-03 | 01.S4 |  |  | 1 | 1 | 1611 | INT-CR1010 | R3 ITC1 | [6 empty] | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | [5 empty] | 2025-10-10 | 2025-12-05 |  |  | 2026-01-23 |  |  |  | 0 |  | 3256 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 01/29: Facing connectivity issues. Idoc creation issue. FUT is in progress. ETA for submission 01/29. | 2025-12-05 | N | 09A. Master Data |  |  |  | 0127: FUT impacted due to system outage |  | 3. Watch item |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3084 | DATE1611_IF | 04.Enhancement | 02.IF - Intel Foundry | 2A1 Enhancement to send Product Catalog to OpenText | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2025-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_2A1_Material%20Master_%20Interface%20S4%20IP_IF%20to%20OpenText.pptx?d=w3ac92b57e9514087aa6f66666345737e&csf=1&web=1&e=cdeefu | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-27 | 2025-11-10 | 2025-12-05 | 2025-11-20 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-05 | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-11-28 | [15 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-31 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-08-23 03:09 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-09-03 | 01.S4 | DATE1611_IP | 03.Medium | 0.2 | 0.2 | 1611 | INT-CR1010 | R3 ITC1 | [6 empty] | 2025-10-27 | 2025-10-27 | 2025-10-27 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-12-05 | 2025-12-05 | 2025-12-05 | 2025-11-28 | 2025-11-28 | [12 empty] | 2025-11-28 | 2025-11-28 |  |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | [5 empty] | 2025-10-10 | 2025-12-05 |  |  | 2026-01-23 |  |  |  | 0 |  | 3257 | [7 empty] | 2. At Risk | 6. FUT Defect Under Fix | 01/29: Facing connectivity issues. Idoc creation issue. FUT is in progress. ETA for submission 01/29. | 2025-12-05 | N | 09A. Master Data |  |  |  | 0127: FUT impacted due to system outage |  | 3. Watch item |  | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-12-05 | 2025-11-28 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2999 | DATE1499 | 04.Enhancement | 07.MDG | Capacity Group/Capacity Corridor Item Attribute Data Source​ | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/s/inteldeloitteiao/EU_Gzp808NJLs1LqMWllsUkB_oprXVUH3Cbc2WS-XBPG8g | 02.No | 01.Yes |  | 2025-06-10 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No |  |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-18 | 2025-09-05 | 2025-09-05 | 100% | 2025-08-19 | 2025-08-11 | 2025-09-10 | 2025-08-29 | 100% | 2025-09-09 | 2025-10-13 | 2025-11-05 | 2025-10-08 | 100% | 2025-10-14 | 2025-09-08 | 2025-10-10 | 2025-10-08 | 100% | 2025-10-14 | [15 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-21 | Not Applicable | R3 Build & UT Sprint 20 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jenoronha@deloitte.com | 2025-06-09 06:12 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-06-10 | 02.MDG |  |  | 1 | 1 | 1499 | INT-CR0642 | R3 ITC1 | [6 empty] | 2025-08-19 | 2025-09-05 | 2025-08-19 |  | 2025-09-09 | 2025-09-10 | 2025-09-09 |  | 2025-10-14 | 2025-11-05 | 2025-10-14 | 2025-10-14 | [12 empty] | 2025-10-14 | 2025-10-14 |  |  | 2025-11-21 | 2025-12-03 | 2025-11-21 | [5 empty] | 2025-09-05 | 2025-10-10 |  |  | 2025-12-03 |  |  |  | 0 | 08. Not Applicable | 3085 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18 - FUT planned to be completed on 11/24 | 2025-10-10 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-10-14 | 2025-10-14 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2773 | DATE1490 | 04.Enhancement | 01.IP - Intel Product | Extend 15 days to termination date and roll back to actual termination for timekeeping employees | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | Y | 2025-06-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAA1F10EC-8B32-417A-98AA-97C56B2DC7D6%7D&file=HRMM_IFED%20Transfer%20and%20Termination%20Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2025-05-19 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-07-21 | 2025-08-13 | 2025-08-01 | 100% | 2025-08-11 | 2025-10-16 | 2025-10-17 | 2025-11-21 | 100% | 2025-11-21 | 2025-11-10 | 2025-12-05 | 2025-12-12 | 100% | 2025-12-15 | 2025-11-10 | 2025-12-05 | 2025-12-12 | 100% | 2025-12-15 | [15 empty] | 2025-12-15 | 2025-12-15 |  |  | 2025-12-24 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-05 | Not Applicable | R3 Build & UT Sprint 21 | 2025-12-05 | 2025-12-05 | 2025-12-05 | jenoronha@deloitte.com | 2025-05-17 02:08 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-07-22 | 01.S4 |  |  | 0.5 | 0.5 | 1490 |  | R3 ITC1 | [6 empty] | 2025-08-11 | 2025-08-13 | 2025-08-11 |  | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | [12 empty] | 2025-12-15 | 2025-12-15 |  |  | 2026-01-05 | 2026-01-09 | 2026-01-05 | [5 empty] | 2025-08-13 | 2025-12-05 |  |  | 2026-01-09 |  | Federal |  | 0 |  | 3019 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/23 - Awaiting approval from 12/17 | 2025-12-05 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2025-12-15 | 2025-12-15 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2963 | DATE1457 | 04.Enhancement | 07.MDG | Master Data_Enhancement for Overwriting PC Value Derived from Business Rules | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y |  | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2963_Master%20Data_Enhancement%20for%20Overwriting%20PC%20Value%20Derived%20from%20Business%20Rules.pptx?d=w2d1c2a324f5e4e84a1b8a3e3439d3d05&csf=1&web=1&e=9vvtim | 01.Yes | 01.Yes |  | 2025-05-19 | Candice S Linnell | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-06-30 | 2025-08-13 | 2025-07-25 | 100% | 2025-07-28 | 2025-10-13 | 2025-10-17 | 2025-11-05 | 100% | 2025-10-24 | 2025-10-27 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-14 | 2025-10-27 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-14 | [15 empty] | 2025-11-14 | 2025-11-14 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-03 | 2025-12-03 | N | 100% | 2025-11-24 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-05-17 02:08 | cell-link@smartsheet.com | 2026-02-13 00:25 | 10 | 2025-06-10 | 02.MDG |  |  | 0.5 | 0.5 | 1457 |  | R3 ITC1 | [6 empty] | 2025-07-28 | 2025-08-13 | 2025-07-28 |  | 2025-10-24 | 2025-11-05 | 2025-10-24 |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | [12 empty] | 2025-11-14 | 2025-11-14 |  |  | 2025-11-24 | 2025-12-03 | 2025-11-24 | [5 empty] | 2025-08-13 | 2025-11-07 |  |  | 2025-12-03 |  |  |  | 0 |  | 3028 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18- Draft FUT reviewed with Intel , additional changes needed to be addressed as part of internal CR ETA to submit revised FUT by 11/25 | 2025-11-07 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-11-14 | 2025-11-14 | No | BRF+ needs to be updated | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2913 | DATE1417 | 04.Enhancement | 02.IF - Intel Foundry | UNBW Cross Site | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2025-05-05 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2913_Material%20Master%20Data_Enhancement%20for%20UNBW%20Cross%20Site.pptx?d=wa82f874b473a43ab8c24644f921d75f1&csf=1&web=1&e=2Zf6BG | 02.No | 01.Yes |  | 2025-04-24 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-06 | 100% | 2025-06-13 | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-11-08 | 2025-11-10 | 2025-11-28 | 2025-11-05 | 100% | 2026-01-08 | 2025-11-10 | 2025-11-28 | 2025-11-05 | 100% | 2026-01-08 | [15 empty] | 2026-01-08 | 2026-01-08 |  |  | 2025-12-24 | 2026-01-07 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-12-08 | 2026-01-09 | 2026-01-07 | N | 100% | 2026-01-13 | Not Applicable | R3 Build & UT Sprint 22 | 2025-11-28 | 2025-11-28 | 2025-11-28 | pgaroo@deloitte.com | 2025-04-18 05:48 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-05-06 | 02.MDG |  |  | 1 | 1 | 1417 |  | R3 ITC1 | [6 empty] | 2025-06-13 | 2025-06-13 | 2025-06-13 |  | 2025-11-08 | 2025-11-08 | 2025-11-08 |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | 2026-01-08 | [12 empty] | 2026-01-08 | 2026-01-08 |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | [5 empty] | 2025-06-13 | 2025-11-28 |  |  | 2026-01-09 |  |  |  | 0 |  | 2967 | [7 empty] | 1. On Track | 3. Awaiting Approval | 13/01: Review comments addressed on 1/12. Approval planned in S22 | 2025-11-28 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 21 |  | 2026-01-08 | 2026-01-08 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2631 | DATE1044_IP | 04.Enhancement | 01.IP - Intel Product | Master Data Governance Email Notifications | 09A. Master Data | 9A.1 Master Data - ALL | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2631_Email%20notifications%20RICEFW.pptx?d=wa2178b8aeaae40aaab4f03f70bc2e250&csf=1&web=1&e=mqKPN8 | 02.No | 01.Yes |  | 2024-12-18 | candice.s.linnell@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-04 | 2025-05-01 | 2025-08-31 | 2025-08-29 | 100% | 2025-08-29 | 2025-05-01 | 2025-08-31 | 2025-10-03 | 100% | 2025-09-16 | 2025-09-01 | 2025-10-10 | 2025-10-03 | 100% | 2025-09-16 | [15 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-10-10 | 2025-10-10 | 2025-10-10 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-11 | 02.MDG |  |  | 4 | 4 | 1044 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-08-29 | 2025-08-31 |  |  | 2025-09-16 | 2025-10-03 | 2025-09-16 | 2025-09-16 | [12 empty] | 2025-09-16 | 2025-09-16 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-05-02 | 2025-08-31 |  |  | 2025-09-19 |  |  |  | 0 |  | 1951 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-10-10 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-16 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2631 | DATE1044_IF | 04.Enhancement | 02.IF - Intel Foundry | Master Data Governance Email Notifications | 09A. Master Data | 9A.1 Master Data - ALL | 10. Object Complete | Y | 2025-01-09 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2631_Email%20notifications%20RICEFW.pptx?d=wa2178b8aeaae40aaab4f03f70bc2e250&csf=1&web=1&e=mqKPN8 | 02.No | 01.Yes |  | 2024-12-18 | candice.s.linnell@intel.com | 01.Approved | 2025-01-09 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-04 | 2025-05-01 | 2025-08-31 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-07 | 2025-08-31 | 2025-09-10 | 100% | 2025-09-10 | 2025-07-07 | 2025-08-31 | 2025-09-10 | 100% | 2025-09-05 | [15 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-09-10 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-31 | 2025-08-31 | 2025-08-31 | jonsanders@deloitte.com | 2024-12-17 15:18 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2025-01-11 | 02.MDG | DATE1044_IP | 01.Very High | 0.8 | 0.8 | 1044 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-08-04 | 2025-08-31 | 2025-08-04 |  | 2025-09-10 | 2025-09-10 |  | 2025-09-05 | [12 empty] | 2025-09-05 | 2025-09-05 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-05-02 | 2025-08-31 |  |  | 2025-09-19 |  |  |  | 0 |  | 1950 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/10 : Awaiting approval | 2025-08-31 | Y | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2507 | DATE0926_IP | 04.Enhancement | 01.IP - Intel Product | Enhancement on PROC BOM for Intel Foundry | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9458F4F8-02A1-4929-B77E-765FE3E99D7F%7D&file=Draft_Enhancement_Intake%20Form_PROC_BOM_IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | candice.s.linnell@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-09 | 2025-04-09 | 100% | 2025-05-02 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-23 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-01 | 2025-09-10 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  | 2025-10-17 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-11-20 03:23 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-01-21 | 01.S4 |  |  | 1 | 1 | 0926 | INT-CR0168 | R3 ITC1 | [6 empty] | 2025-05-02 | 2025-05-02 | 2025-05-02 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | [5 empty] | 2025-04-09 | 2025-07-18 |  |  | 2025-11-21 |  |  |  | 0 |  | 2124 | [7 empty] | 3. Off Track | 3. Awaiting Approval | 11/14 - Awaiting approval (no open defects). FUT Approval ETA is 11/19 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Working sessions are in progress. US team is looking into the build 10/24 - Defect 3707 & 3708. Working session to be scheduled on Monday. | 2025-09-10 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2507 | DATE0926_IF | 04.Enhancement | 02.IF - Intel Foundry | Enhancement on PROC BOM for Intel Product | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | Y | 2024-12-13 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B9458F4F8-02A1-4929-B77E-765FE3E99D7F%7D&file=Draft_Enhancement_Intake%20Form_PROC_BOM_IF.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-12-20 | candice.s.linnell@intel.com | 01.Approved | 2024-12-13 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-03-03 | 2025-04-09 | 2025-04-09 | 100% | 2025-05-02 | 2025-08-18 | 2025-08-22 | 2025-08-21 | 100% | 2025-09-23 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-23 | 2025-09-01 | 2025-09-12 | 2025-09-05 | 100% | 2025-09-23 | [15 empty] | 2025-09-23 | 2025-09-23 |  | 2025-10-17 | 2025-10-31 | 2025-11-05 | 100% | 100% | 100% |  |  | 04. Completed | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-20 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-12 | 2025-09-12 | 2025-09-12 | pgaroo@deloitte.com | 2024-11-20 03:31 | vjillela@deloitte.com | 2026-03-09 11:34 | 10 | 2025-01-21 | 01.S4 | DATE0926_IP | 03.Medium | 0.2 | 0.2 | 0926 | INT-CR0168 | R3 ITC1 | [6 empty] | 2025-05-02 | 2025-05-02 | 2025-05-02 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [12 empty] | 2025-09-23 | 2025-09-23 |  |  | 2025-11-20 | 2025-11-20 | 2025-11-20 | [5 empty] | 2025-04-09 | 2025-07-18 |  |  | 2025-10-10 |  |  |  | 0 |  | 2123 | [7 empty] | 4. Completed | 3. Awaiting Approval | 11/14 - Awaiting approval (no open defects). FUT Approval ETA is 11/19 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Working sessions are in progress. US team is looking into the build 10/24 - Defect 3707 & 3708. Working session to be scheduled on Monday. | 2025-09-12 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-09-23 | 2025-09-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1986 | DATE0799 | 04.Enhancement | 07.MDG | RICEFW for Validations and Derivations where enhancement required for all reference master data governed by Itego on MDG | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BAE79E28A-AAC2-4C32-A3E6-228914A0ABED%7D&file=Validations%20and%20Derivations%20RICEFW.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-10-24 | Candice S Linnell | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-01 | 2025-03-31 | 2024-12-13 | 100% | 2025-01-24 | 2025-04-01 | 2025-05-31 | 2025-02-07 | 100% | 2025-02-07 | 2025-04-01 | 2025-05-31 | 2025-03-21 | 100% | 2025-04-04 | 2025-04-01 | 2025-05-31 | 2025-03-21 | 100% | 2025-04-04 | [15 empty] | 2025-04-04 | 2025-04-04 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-02 | 2025-06-30 | 2025-06-11 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-31 | 2025-05-31 | 2025-05-31 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-24 | 02.MDG |  |  | 1 | 1 | 0799 |  | R3 ITC1 | [6 empty] | 2025-01-24 | 2025-03-31 | 2025-01-24 |  | 2025-02-07 | 2025-05-31 | 2025-02-07 |  | 2025-04-04 | 2025-05-31 | 2025-04-04 | 2025-04-04 | [12 empty] | 2025-04-04 | 2025-04-04 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-03-31 | 2025-05-31 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 1929 | [7 empty] | 3. Off Track | 13. Blocked by Other RICEFW |  | 2025-05-31 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-05-31 | 2025-04-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2396 | DATE0759 | 04.Enhancement | 01.IP - Intel Product | Segregation of IF IP workers based on biz segment getting retrieved from WCDS | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/HRMM_Intake%20Form_IF_IP%20segregation.pptx?d=wde19f3815e2943f4ba0ccea47d6279b8&csf=1&web=1&e=QnnZAm | 01.Yes | 01.Yes |  | 2024-10-23 | Candice S Linnell | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-10-21 | 2024-11-15 | 2024-11-15 | 100% | 2024-11-20 | 2025-05-01 | 2025-05-09 | 2025-02-07 | 100% | 2025-02-06 | 2025-05-12 | 2025-05-30 | 2025-05-16 | 100% | 2025-08-04 | 2025-05-26 | 2025-05-30 | 2025-05-16 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-10-08 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-10 | Not Applicable | R3 Build & UT Sprint 20 | 2025-05-30 | 2025-05-30 | 2025-05-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-17 00:17 | 10 | 2024-10-24 | 02.MDG |  |  | 1 | 1 | 0759 |  | R3 ITC1 | [6 empty] | 2024-11-20 | 2024-11-20 | 2024-11-20 |  | 2025-02-06 | 2025-05-09 | 2025-02-06 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | [5 empty] | 2024-11-15 | 2025-05-30 |  |  | 2025-05-29 |  |  |  | 0 | 08. Not Applicable | 2400 | [7 empty] | 2. At Risk | 17. FUT In progress | 10/30 - FUT in progress. ETA is 11/06 10/24 - Open points are to be setup from WCDS. | 2025-05-30 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | Yes |  | No |  | No |  |  |  | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 2395 | DATE0758 | 04.Enhancement | 01.IP - Intel Product | 1)Standard IDOC Enhancement to map WWID same as CP ID and fill PERNR, | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | Y | 2024-10-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/HRMM_Intake%20Form%20WCDS_CP_ISO.pptx?d=w0a1da6e9ceae4de3a9a761823bf13089&csf=1&web=1&e=cae2oB | 01.Yes | 01.Yes |  | 2024-10-23 | Candice S Linnell | 01.Approved | 2024-10-24 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-10-07 | 2024-10-11 | 2024-11-15 | 100% | 2024-11-26 | 2025-03-17 | 2025-03-21 | 2025-02-07 | 100% | 2025-02-06 | 2025-03-27 | 2025-04-17 | 2025-05-16 | 100% | 2025-08-04 | 2025-04-21 | 2025-04-28 | 2025-05-16 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-07-11 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-30 | 2025-07-16 | 2025-07-16 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-04-28 | 2025-04-28 | 2025-04-28 | arpitsharma@deloitte.com | 2024-11-19 02:35 | cell-link@smartsheet.com | 2026-03-09 00:30 | 10 | 2024-10-24 | 02.MDG |  |  | 1 | 1 | 0758 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-02-06 | 2025-03-21 | 2025-02-06 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | [5 empty] | 2024-10-11 | 2025-04-17 |  |  | 2025-05-03 |  |  |  | 0 | 08. Not Applicable | 2399 | [9 empty] | 08/29:FUT in progres,defect resolved. 08/25:Defect still in progress 08/18: Defect 2248 fix in progress ETA -08/18 , ETA for FUT completion 08/20 08/14: FUT is in progress, Defect#2248 created with Tech team for Termination Action determination issue 08/11: FUT in Progress | 2025-04-28 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2125 | DATE0668 | 04.Enhancement | 07.MDG | Customizing Technology Node field while Creating Cost Center in MDG system | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2125_Customizing%20Technology%20Node%20field%20while%20Creating%20Cost%20Center%20in%20MDG%20system.pptx?d=w833812331f564556b82c9aec0f0bc488&csf=1&web=1&e=83ZKCs | 01.Yes | 01.Yes |  | 2024-09-25 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-01 | 2025-02-28 | 2025-03-21 | 100% | 2025-03-28 | 2025-03-01 | 2025-04-30 | 2025-04-04 | 100% | 2025-04-01 | 2024-10-30 | 2024-11-06 | 2025-04-18 | 100% | 2025-04-25 | 2024-11-18 | 2025-02-21 | 2025-04-18 | 100% | 2025-06-27 | [15 empty] | 2025-06-27 | 2025-06-27 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-01 | 02.MDG |  |  | 1 | 1 | 0668 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-04-01 | 2025-04-30 | 2025-04-01 |  | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-06-27 | [12 empty] | 2025-06-27 | 2025-06-27 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-02-28 | 2025-04-30 |  |  | 2025-01-24 |  |  |  | 0 | 08. Not Applicable | 2720 | [10 empty] | 2025-02-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-06-27 | 2025-06-27 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2028 | DATE0667_IF | 04.Enhancement | 02.IF - Intel Foundry | Adding Technology Node while Creating Cost Center in MDG system (cFIn, IF and IP Systems) | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B16A899F9-520F-4094-BBE4-7FDFC976CA08%7D&file=2028_Adding%20Technology%20Node%20while%20Creating%20Cost%20Center%20in%20MDG%20system%20(cFIn%2C%20IF%20and%20IP%20Systems).pptx&action=edit&mobileredirect=true&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA3MTEyODgyNSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | 01.Yes | 01.Yes |  | 2024-09-25 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-01 | 2025-02-28 | 2025-03-21 | 100% | 2025-03-28 | 2025-03-01 | 2025-04-30 | 2025-08-01 | 100% | 2025-08-12 | 2025-03-01 | 2025-04-30 | 2025-08-13 | 100% | 2025-08-12 | 2025-03-01 | 2025-04-30 | 2025-08-13 | 100% | 2025-08-12 | [15 empty] | 2025-08-12 | 2025-08-12 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-04-30 | 2025-04-30 | 2025-04-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-01 | 01.S4 | DATE0667_CFIN | 03.Medium | 0.2 | 0.2 | 0667 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | [12 empty] | 2025-08-12 | 2025-08-12 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-02-28 | 2025-04-30 |  |  | 2025-04-22 |  |  |  | 0 | 08. Not Applicable | 1584 | [10 empty] | 2025-04-30 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2028 | DATE0667_CFIN | 04.Enhancement | 05.CFIN | Adding Technology Node while Creating Cost Center in MDG system (cFIn, IF and IP Systems) | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | Y | 2024-09-27 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B16A899F9-520F-4094-BBE4-7FDFC976CA08%7D&file=2028_Adding%20Technology%20Node%20while%20Creating%20Cost%20Center%20in%20MDG%20system%20(cFIn%2C%20IF%20and%20IP%20Systems).pptx&action=edit&mobileredirect=true&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA3MTEyODgyNSIsIkhhc0ZlZGVyYXRlZFVzZXIiOnRydWV9 | 01.Yes | 01.Yes |  | 2024-09-25 | Shane Bethune | 01.Approved | 2024-09-27 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-01 | 2025-02-28 | 2025-03-21 | 100% | 2025-03-28 | 2025-03-01 | 2025-04-30 | 2025-08-01 | 100% | 2025-08-12 | 2025-03-01 | 2025-04-30 | 2025-08-13 | 100% | 2025-08-12 | 2025-03-01 | 2025-04-30 | 2025-08-13 | 100% | 2025-08-12 | [15 empty] | 2025-08-12 | 2025-08-12 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-04-30 | 2025-04-30 | 2025-04-30 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-10-01 | 01.S4 |  |  | 1 | 1 | 0667 |  | R3 ITC1 | [6 empty] | 2025-03-28 | 2025-03-28 | 2025-03-28 |  | 2025-08-12 | 2025-08-12 | 2025-08-12 |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-12 | [12 empty] | 2025-08-12 | 2025-08-12 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-02-28 | 2025-04-30 |  |  | 2025-04-18 |  |  |  | 0 | 08. Not Applicable | 1583 | [10 empty] | 2025-04-30 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1923 | DATE0590 | 04.Enhancement | 07.MDG | Material extension using reference material | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2024-09-06 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/1923_Master%20Data_Material%20Extension%20using%20Reference%20Material.pptx?d=wfb31227a0fd948af9ac7b509460700e4&csf=1&web=1&e=r9jJMc | 02.No | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved | 2024-09-06 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-12-11 | 2025-04-04 | 2025-04-11 | 100% | 2025-04-18 | 2025-10-21 | 2025-10-31 | 2025-05-16 | 100% | 2025-08-04 | 2025-08-18 | 2025-09-12 | 2025-06-11 | 100% | 2025-06-11 | 2025-08-18 | 2025-09-12 | 2025-06-11 | 100% | 2025-06-11 | [15 empty] | 2025-06-11 | 2025-06-11 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-27 | Not Applicable | R3 Build & UT Sprint 15 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-09-11 | 02.MDG |  |  | 1 | 1 | 0590 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-08-04 | 2025-10-31 | 2025-08-04 |  | 2025-06-11 | 2025-09-12 | 2025-06-11 | 2025-06-11 | [12 empty] | 2025-06-11 | 2025-06-11 |  |  | 2025-06-27 | 2025-06-27 | 2025-06-27 | [5 empty] | 2025-04-04 | 2025-11-21 |  |  | 2025-06-27 |  |  |  | 0 | 08. Not Applicable | 1471 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-09-12 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-09-12 | 2025-06-11 | No | Input File for Reference Material needs to be updated | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1256 | DATE0570 | 04.Enhancement | 02.IF - Intel Foundry | Adding Cost Center Approvers fields while Creating Cost Center in MDG system | 09A. Master Data | 9A.5 Master Data - Finance | 10. Object Complete | Y | 2024-09-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/364_Data_Enhancement%20Intake%20Form_v2.0.pptx?d=wa87e2590aed942b4b6cc39c675a8fa4e&csf=1&web=1&e=dPDZaH | 01.Yes | 01.Yes |  | 2024-08-27 | Candice S Linnell | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-04 | 2025-02-01 | 2025-03-31 | 2025-03-21 | 100% | 2025-04-04 | 2025-02-01 | 2025-03-31 | 2025-04-18 | 100% | 2025-04-10 | 2025-02-01 | 2025-03-31 | 2025-04-18 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-05-09 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-01 | 2025-04-11 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-03-31 | 2025-03-31 | 2025-03-31 | pgaroo@deloitte.com | 2024-08-27 08:04 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-07 | 02.MDG |  |  | 1 | 1 | 0570 |  | R3 ITC1 | [6 empty] | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-04-04 | 2025-04-04 | 2025-04-04 |  | 2025-04-10 | 2025-04-18 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2025-01-31 | 2025-03-31 |  |  | 2025-04-11 |  |  |  | 0 | 08. Not Applicable | 1771 | [10 empty] | 2025-03-31 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1921 | DATE0561 | 04.Enhancement | 07.MDG | Adding DQM Functionality for Address validation | 09A. Master Data | 9A.7 Master Data - Reference | 10. Object Complete | Y | 2024-08-29 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/DQM%20RICEFW.pptx?d=wca9e17665ce3482cae3b3d75e24d144c&csf=1&web=1&e=JruBy9 | 01.Yes | 01.Yes |  | 2024-08-26 | Candice S Linnell | 01.Approved | 2024-08-29 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA | 2024-11-25 | 2024-12-06 | 2024-11-15 | 100% | 2024-12-04 | 2025-08-01 | 2025-08-31 | 2025-03-21 | 100% | 2025-03-03 | 2025-08-01 | 2025-09-30 | 2025-04-18 | 100% | 2025-04-10 | 2025-08-01 | 2025-09-30 | 2025-04-18 | 100% | 2025-04-10 | [15 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-05-09 | 2025-05-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-29 | 2025-05-30 | 2025-05-30 | N | 100% | 2025-05-29 | Not Applicable | R3 Build & UT Sprint 14 | 2025-09-30 | 2025-09-30 | 2025-09-30 | arpitsharma@deloitte.com | 2024-11-19 03:49 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-08-30 | 02.MDG |  |  | 4 | 4 | 0561 |  | R3 ITC1 | [6 empty] | 2024-12-04 | 2024-12-06 | 2024-12-04 |  | 2025-03-03 | 2025-08-31 | 2025-03-03 |  | 2025-04-10 | 2025-09-30 | 2025-04-10 | 2025-04-10 | [12 empty] | 2025-04-10 | 2025-04-10 |  |  | 2025-05-29 | 2025-05-30 | 2025-05-29 | [5 empty] | 2024-12-06 | 2025-09-30 |  |  | 2025-10-31 |  |  |  | 0 | 08. Not Applicable | 1470 | [10 empty] | 2025-09-30 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-09-30 | 2025-04-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1666 | DATE0446 | 04.Enhancement | 01.IP - Intel Product | Derivation of UPI Intelligent description, Material group, Profit center, and Product hierarchy | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2024-07-23 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/818_MDM_150_190_Data_Material%20Group%20Derivation.pptx?d=w6a37738b87bc422ea029e87493553483&csf=1&web=1&e=d82XZO | 02.No | 01.Yes |  | 2024-07-16 | Candice S Linnell | 01.Approved | 2024-07-19 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2024-12-02 | 2025-03-14 | 2025-03-14 | 100% | 2025-05-23 | 2025-08-11 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-18 | 2025-08-11 | 2025-09-10 | 2025-11-05 | 100% | 2025-11-14 | 2025-08-11 | 2025-09-10 | 2025-11-05 | 100% | 2025-11-14 | [15 empty] | 2025-11-14 | 2025-11-14 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-11 | Not Applicable | R3 Build & UT Sprint 20 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-07-16 03:28 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 02.MDG |  |  | 1 | 1 | 0446 |  | R3 ITC1 | [6 empty] | 2025-05-23 | 2025-05-23 | 2025-05-23 |  | 2025-08-18 | 2025-09-10 | 2025-08-18 |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | [12 empty] | 2025-11-14 | 2025-11-14 |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | [5 empty] | 2025-03-14 | 2025-10-03 |  |  | 2025-11-07 |  |  |  | 0 | 08. Not Applicable | 2524 | [7 empty] | 1. On Track | 17. FUT In progress | 10/30 - Will be submitted for approval 10/24 - FUT in progress. ETA for submission is 10/29 | 2025-09-10 | Y | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 20 |  | 2025-11-14 | 2025-11-14 | No | BRF+ needs to be updated | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 823 | DATE0395_IP | 04.Enhancement | 01.IP - Intel Product | Pop Up window to be developed on MDG screen to display “Search before Create” results from Reltio | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | Y | 2024-04-24 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/823_Master%20Data_Intake%20Form.pptx?d=w55a2530591064aee94587615782a1c80&csf=1&web=1&e=FhJ2gM | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  | NA | NA | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-06 | 2025-09-01 | 2025-09-10 | 2025-09-10 | 100% | 2025-08-19 | 2025-09-01 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-09 | 2025-06-23 | 2025-07-25 | 2025-09-10 | 100% | 2025-09-09 | [15 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-09-18 | Not Applicable | R3 Build & UT Sprint 18 | 2025-07-25 | 2025-07-25 | 2025-07-25 | pgaroo@deloitte.com | 2025-04-02 04:07 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-04-09 | 02.MDG | DATE0395 | 03.Medium | 0.2 | 0.2 | 0395 |  | R3 ITC1 | [6 empty] | 2025-06-06 | 2025-06-13 | 2025-06-06 |  | 2025-08-19 | 2025-09-10 | 2025-08-19 |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | 2025-09-09 | [12 empty] | 2025-09-09 | 2025-09-09 |  |  | 2025-09-18 | 2025-10-08 | 2025-09-18 | [5 empty] | 2025-06-13 | 2025-07-25 |  |  | 2025-10-08 |  |  |  | 0 |  | 2852 | [7 empty] | 1. On Track |  |  | 2025-07-25 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-10 | 2025-09-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 628 | DATE0313_IP | 04.Enhancement | 01.IP - Intel Product | Customer Master Validations and Derivations | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | Y | 2024-04-18 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/2%20Customer%20Master/RICEFW%20Intake%20form/Approved%20by%20GPO/628_Master%20Data_RICEFW%20Intake%20Form.pptx?d=w55f6ce45ffbb42fda1321bcbd28066a0&csf=1&web=1&e=iS24L8 | 02.No | 01.Yes |  | 2025-04-02 | candice.s.linnell@intel.com | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-05-19 | 2025-06-13 | 2025-06-11 | 100% | 2025-06-20 | 2025-08-14 | 2025-08-18 | 2025-08-29 | 100% | 2025-08-28 | 2025-08-04 | 2025-09-15 | 2025-10-08 | 100% | 2025-10-10 | 2025-08-04 | 2025-09-15 | 2025-10-08 | 100% | 2025-10-10 | [15 empty] | 2025-10-10 | 2025-10-10 |  |  | 2025-10-24 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-08 | Not Applicable | R3 Build & UT Sprint 19 | 2025-09-15 | 2025-09-15 | 2025-09-15 | pgaroo@deloitte.com | 2025-04-03 10:03 | cell-link@smartsheet.com | 2026-03-09 02:00 | 10 | 2025-04-09 | 02.MDG |  |  | 2 | 2 | 0313 |  | R3 ITC1 | [6 empty] | 2025-06-20 | 2025-06-20 | 2025-06-20 |  | 2025-08-28 | 2025-08-29 | 2025-08-28 |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | [12 empty] | 2025-10-10 | 2025-10-10 |  |  | 2025-11-08 | 2025-11-08 | 2025-11-08 | [5 empty] | 2025-06-13 | 2025-09-15 |  |  | 2025-11-05 |  |  |  | 0 |  | 2866 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - FUT in progress. ETA for submission is 10/27 | 2025-09-15 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-10 | Yes | Update BRF+ tables and Validations to include AM22 and CC:100 | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-02-14 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 12 | DATE0020 | 04.Enhancement | 02.IF - Intel Foundry | Material description generation from Classification data | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | Y | 2024-03-26 | 01. Approved | https://intel.sharepoint.com/sites/inteldeloitteiao/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29%2FM%2D150%2D190%5FData%5FMaterial%20Description%2Epdf&parent=%2Fsites%2Finteldeloitteiao%2FShared%20Documents%2FGeneral%2FImplementation%2F11%2E%20Technology%2FRICEFW%2F30%20RICEFW%20Processed%20%28Approved%29 | 02.No | 01.Yes |  | 2024-03-26 | Rebecca Verette | 01.Approved | 2024-03-26 | Non-Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-07-29 | 2025-01-31 | 2024-08-16 | 100% | 2024-09-13 | 2024-08-26 | 2024-08-19 | 2024-10-11 | 100% | 2025-01-31 | 2025-07-21 | 2025-08-15 | 2024-10-11 | 100% | 2025-06-20 | 2025-07-21 | 2025-08-15 | 2024-10-18 | 100% | 2025-06-24 | [15 empty] | 2025-06-24 | 2025-06-24 |  |  | 2025-05-23 | 2025-05-30 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-05-30 | N | 100% | 2025-07-04 | Not Applicable | R3 Build & UT Sprint 15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | vasamohan@deloitte.com | 2024-03-22 16:09 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 02.MDG |  |  | 0.5 | 0.5 | 0020 |  | R3 ITC1 | [6 empty] | 2024-09-13 | 2025-01-31 | 2024-09-13 |  | 2025-01-31 | 2025-01-31 | 2025-01-31 |  | 2025-06-20 | 2025-08-15 | 2025-06-20 | 2025-06-24 | [12 empty] | 2025-06-24 | 2025-06-24 |  |  | 2025-07-04 | 2025-07-04 | 2025-07-04 | [5 empty] | 2025-01-31 | 2025-09-26 |  |  | 2024-12-15 |  |  |  | 0 | 08. Not Applicable | 1423 | [10 empty] | 2025-08-15 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 15 |  | 2025-08-15 | 2025-06-24 | No | BRF+ needs to be updated | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3138 | DATC1663 | 03.Conversion | 07.MDG | Product Hierarchy File 1 and File 2 | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BF03ED835-6248-442E-98F5-4CF6DF3CF00D%7D&file=3138_Material%20Master%20Data%20Construction%20and%20Cleansing%20Effort.pptx&action=edit&mobileredirect=true&CID=ECCE2C80-57BB-44EA-AF3E-EAE0080368F1&wdLOR=c74A6AD40-690D-4766-997F-542520D8BE5D&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTkwMjkuMjAyNDQiLCAiT1MiIDogIldpbmRvd3MiIH0%3D |  |  |  | 2025-10-24 | Candice S Linnell | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte |  | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA | 2025-11-10 | 2025-12-05 | 2025-12-03 | 100% | 2025-12-04 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100% | 2025-12-16 | 2025-11-20 | 2025-11-21 | 2025-12-08 | 100% | 2025-12-16 | 2025-11-24 | 2025-12-12 | 2025-12-15 | 100% | 2025-12-16 | [15 empty] | 2025-12-16 | 2025-12-16 |  |  | 2026-01-23 | 2026-01-23 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-01-12 | 2026-01-23 | 2026-01-23 | N | 100% | 2026-01-21 | Sprint 22 Week 2 | R3 Build & UT Sprint 22 | 2025-12-12 | 2025-12-12 | 2025-12-12 | jenoronha@deloitte.com | 2025-10-23 21:19 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 02.MDG |  |  | 2 | 2.9 | 1663 |  | R3 ITC1 | [6 empty] | 2025-12-04 | 2025-12-05 | 2025-12-04 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | [12 empty] | 2025-12-16 | 2025-12-16 |  |  | 2026-01-21 | 2026-01-23 | 2026-01-21 | [5 empty] | 2025-12-05 | 2025-12-12 |  |  | 2026-01-23 |  |  |  | 0 |  | 3335 | [7 empty] | 1. On Track | 19. Incomplete Build | 20/01: Dev to be completed by S23 | 2025-12-12 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. |  |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 21 |  | 2025-12-16 | 2025-12-16 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3117 | DATC1640 | 03.Conversion | 02.IF - Intel Foundry | Material Master MRP View WINGS Conversion | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3117-Material%20Master%20Data%20MRP%20View%20WINGs%20Conversion.pptx?d=w8604c010951a40acb3852ac4dd46d9cc&csf=1&web=1&e=Lf91iv | 02.No | 01.Yes |  | 2025-10-08 | Candice S Linnell | 01.Approved |  | Std. | 02.No |  |  |  | 04.Low |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100% | 2025-12-16 | 2025-12-09 | 2025-12-12 | 2025-12-12 | 100% | 2025-12-16 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | [15 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-02-25 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-10-08 | 02.MDG |  |  | 0.5 | 0.725 | 1640 | INT-CR1133 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2026-02-06 | [12 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-25 | 2026-03-06 | 2026-02-25 | [5 empty] | 2025-11-07 | 2026-02-06 |  |  | 2026-03-06 |  | WIINGS |  | 0 |  | 3295 |  |  | X |  |  |  |  | 1. On Track | 17. FUT In progress | 02/24: Awaiting approval. | 2026-02-06 | N | 09A. Master Data |  |  |  |  | Week 3 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 3. WIINGS Only - Not PAID, but CR Approved with $
01. IAO ERP | 03.R3 | 3116 | DATC1639 | 03.Conversion | 02.IF - Intel Foundry | Material Master Plant and Storage Location View WINGS Materials Conversions | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3116-Material%20Master%20Data%20Plant%20and%20Storage%20Location%20View%20WINGs%20Conversion%20-%20Copy.pptx?d=wbcf31ac79d2e47c484c7f1988373e7e3&csf=1&web=1&e=jb7bLY | 02.No | 01.Yes |  | 2025-10-08 | Candice S Linnell | 01.Approved |  | Std. | 02.No |  |  |  | 04.Low |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100% | 2025-12-16 | 2025-12-09 | 2025-12-12 | 2025-12-12 | 100% | 2025-12-16 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | [15 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-06 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-10-08 | 02.MDG |  |  | 0.5 | 0.725 | 1639 | INT-CR1132 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2026-02-06 | [12 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | [5 empty] | 2025-11-07 | 2026-02-06 |  |  | 2026-03-06 |  | WIINGS |  | 0 |  | 3294 |  |  | X |  |  |  |  | 1. On Track | 3. Awaiting Approval | 03/05: Partial FUT approved. Awaiting approval for postloads. | 2026-02-06 | N | 09A. Master Data |  |  |  |  | Week 3 Target |  |  | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 3. WIINGS Only - Not PAID, but CR Approved with $
01. IAO ERP | 03.R3 | 3115 | DATC1638 | 03.Conversion | 02.IF - Intel Foundry | Material Master Accounting and Costing View WINGS Materials Conversions | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3115-Material%20Master%20Data%20Accounting%20and%20Costing%20View%20WINGs%20Conversion%20-%20Copy.pptx?d=wc8e89a45176547d6ab3afd8746c8b008&csf=1&web=1&e=Uvp4h4 | 02.No | 01.Yes |  | 2025-10-08 | Candice S Linnell | 01.Approved |  | Std. | 02.No |  |  |  | 04.Low |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100% | 2025-12-16 | 2025-12-09 | 2025-12-12 | 2025-12-12 | 100% | 2025-12-16 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | [15 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-03-05 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-10-08 | 02.MDG |  |  | 0.5 | 0.725 | 1638 | INT-CR1131 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2026-02-06 | [12 empty] | 2026-02-06 | 2026-02-06 |  | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-05 | [5 empty] | 2025-11-07 | 2026-02-06 |  |  | 2026-03-06 |  | WIINGS |  | 0 |  | 3293 |  |  | X |  |  |  |  | 4. Completed | 3. Awaiting Approval | 03/05: Awaiting approval,review comments addressed.ETA 03/04. Partial FUT approved. | 2026-02-06 | N | 09A. Master Data | [7 empty] | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 3. WIINGS Only - Not PAID, but CR Approved with $
01. IAO ERP | 03.R3 | 3114 | DATC1637 | 03.Conversion | 02.IF - Intel Foundry | Material Master Purchasing View WINGS Materials Conversions | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3114-Material%20Master%20Data%20Purchasing%20View%20WINGs%20Conversion%20-%20Copy.pptx?d=wd380df5d2f5e46cfbc9964c87bbf3eab&csf=1&web=1&e=Ta8hU8 | 02.No | 01.Yes |  | 2025-10-08 | Candice S Linnell | 01.Approved |  | Std. | 02.No |  |  |  | 04.Low |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-22 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100% | 2025-12-16 | 2025-12-09 | 2025-12-12 | 2025-12-12 | 100% | 2025-12-16 | 2026-01-12 | 2026-02-06 | 2026-02-04 | 100% | 2026-02-06 | [15 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-06 | 2026-03-04 | N | 100% | 2026-02-18 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2026-02-06 | 2026-02-06 | 2026-02-06 | jenoronha@deloitte.com | 2025-09-28 03:35 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-10-08 | 02.MDG |  |  | 0.5 | 0.725 | 1637 | INT-CR1130 | R3 ITC1 | [6 empty] | 2025-10-22 | 2025-11-07 | 2025-10-22 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2026-02-06 | [12 empty] | 2026-02-06 | 2026-02-06 |  |  | 2026-02-18 | 2026-03-06 | 2026-02-18 | [5 empty] | 2025-11-07 | 2026-02-06 |  |  | 2026-03-06 |  | WIINGS |  | 0 |  | 3292 |  |  | X |  |  |  |  | 1. On Track | 17. FUT In progress | 02/12 : FUT In Progress ,ETA to complete the draft is 02/25 | 2026-02-06 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 22 |  | 2026-02-06 | 2026-02-06 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 3. WIINGS Only - Not PAID, but CR Approved with $
01. IAO ERP | 03.R3 | 3091 | DATC1617 | 03.Conversion | 02.IF - Intel Foundry | HAZMAT Profile Conversion | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/R3_HAZMAT_Material%20Master_%20MDG.pptx?d=w433be3d881454d808f40d8146de793c3&csf=1&web=1&e=swZgyb | 02.No | 01.Yes |  | 2025-09-03 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-10-13 | 2025-11-07 | 2025-11-05 | 100% | 2026-02-06 | 2025-11-10 | 2025-11-14 | 2026-02-02 | 100% | 2026-01-12 | 2025-11-17 | 2025-11-28 | 2026-02-04 | 100% | 2026-02-06 | 2025-11-10 | 2025-11-28 | 2026-02-27 | 100% | 2026-03-02 | [15 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-02-27 | 2026-03-12 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-16 | 2026-03-04 | 2026-03-12 | N | 100% | 2026-03-12 | Sprint 23 Week 4 | R3 Build & UT Sprint 23+ | 2025-11-28 | 2025-11-28 | 2025-11-28 | jenoronha@deloitte.com | 2025-08-23 03:09 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-09-03 | 01.S4 |  |  | 1 | 1.45 | 1617 |  | R3 ITC1 | [6 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06 |  | 2026-01-12 | 2026-02-02 | 2026-01-12 |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-03-02 | [12 empty] | 2026-03-02 | 2026-03-02 |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | [5 empty] | 2025-11-07 | 2025-11-28 |  |  | 2026-03-04 |  | Hazmat WIINGS Only | TRUE | 0 |  | 3266 | [7 empty] | 1. On Track | 19. Incomplete Build | 03/05 : TDD,TUT review still in progress hence FUT submission on hold. .ETA 03/05. 03/09: No open points from the development team (TDD & TUT ) submitted and approved. Tower team can proceed with the FUT approvals. | 2025-11-28 | N | 09A. Master Data | Hazmat |  |  | 1209: Lilibeth to submit exception approval |  |  |  | Dev In Progress/Dependency | Complete | R3 Build & UT Sprint 23 |  | 2026-03-02 | 2026-03-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 3049 | DATC1604 | 03.Conversion | 01.IP - Intel Product | Initial Load for Objects & Relationships | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/3%20Final%20Deliverables/Release%20R3/2.%20Build/6.%20HRMM/RICEFW/Intake%20Forms/IFL%20Intake%20Forms%20for%20Time%20Keeping/HRMM_Initial%20Load%20for%20OM%20Objects%20%26%20Relationships.pptx?d=w0f3f708ad91149f09095b1fe7954720a&csf=1&web=1&e=GbB21C | 02.No | 01.Yes |  | 2025-09-05 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-03 | 2025-10-03 | 100% | 2025-09-22 | 2025-10-13 | 2025-10-14 | 2025-10-14 | 100% | 2025-10-13 | 2025-10-14 | 2025-10-17 | 2025-10-24 | 100% | 2025-11-05 | 2025-10-20 | 2025-11-07 | 2025-11-05 | 100% | 2025-10-30 | [15 empty] | 2025-10-30 | 2025-10-30 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-11-25 | Not Applicable | R3 Build & UT Sprint 20 | 2025-11-07 | 2025-11-07 | 2025-11-07 | jenoronha@deloitte.com | 2025-08-23 03:09 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-09-05 | 01.S4 |  |  | 1 | 1.45 | 1604 |  | R3 ITC1 | [6 empty] | 2025-09-22 | 2025-10-03 | 2025-09-22 |  | 2025-10-13 | 2025-10-14 | 2025-10-13 |  | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-10-30 | [12 empty] | 2025-10-30 | 2025-10-30 |  |  | 2025-11-25 | 2025-12-05 | 2025-11-25 | [5 empty] | 2025-10-03 | 2025-11-07 |  |  | 2025-12-05 |  |  |  | 0 |  | 3270 | [7 empty] | 4. Completed | 17. FUT In progress | 11/18 - FUT to be submitted for Intel review on 11/21 | 2025-11-07 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 19 |  | 2025-11-07 | 2025-10-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2912 | DATC1556 | 03.Conversion | 07.MDG | Conversion program to load Images of Products in Material Master | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/2912_Material%20Master%20Data_Converion%20for%20Image%20Upload.pptx?d=w79eb8e10d909480cb587145133b560f3&csf=1&web=1&e=pLc8Kq | 02.No | 01.Yes |  | 2025-08-13 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-09-15 | 2025-10-10 | 2025-11-05 | 100% | 2025-11-11 | 2025-10-13 | 2025-10-14 | 2026-01-12 | 100% | 2026-01-16 | 2025-10-14 | 2025-10-17 | 2026-01-13 | 100% | 2026-01-16 | 2025-10-20 | 2025-11-05 | 2026-02-04 | 100% | 2026-02-02 | [15 empty] | 2026-02-02 | 2026-02-02 |  |  | 2026-02-27 | 2026-03-04 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2026-02-09 | 2026-03-04 | 2026-03-04 | N | 100% | 2026-03-02 | Sprint 23 Week 4 | R3 Build & UT Sprint 23 | 2025-11-05 | 2025-11-05 | 2025-11-05 | jenoronha@deloitte.com | 2025-07-24 03:57 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 | 2025-08-15 | 02.MDG |  |  | 1 | 1.45 | 1556 |  | R3 ITC1 | [6 empty] | 2025-11-11 | 2025-11-11 | 2025-11-11 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-02-02 | [12 empty] | 2026-02-02 | 2026-02-02 |  |  | 2026-03-02 | 2026-03-04 | 2026-03-02 | [5 empty] | 2025-10-10 | 2025-11-05 |  |  | 2026-03-04 |  | WIINGS Only | TRUE | 0 |  | 3206 | [7 empty] | 1. On Track | 17. FUT In progress | 02/27 : Awaiting approval. | 2025-11-05 | N | 09A. Master Data |  |  |  | 1209: Add to S21 sprint plan. | Week 2 Target |  |  | Awaiting approval | Complete | R3 Build & UT Sprint 22 |  | 2026-02-04 | 2026-02-02 | No |  | No |  | No |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | DATC1552 | 03.Conversion | 02.IF - Intel Foundry | edFIT - PSI BOM Conversion | 09A. Master Data | 9A.2 Master Data - BOM | 03. FS Not Started | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-25 | 2025-09-10 |  | 0% | 2025-09-10 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 3 | 2025-08-15 | 01.S4 |  |  | 1 | 1.45 | 1552 |  | R4 ITC1 | [7 empty] | 2025-09-10 | [34 empty] | 2025-09-10 | [5 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3169 | [7 empty] | 5. Not Dispositioned |  |  |  | N | 09A. Master Data | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | Not Dispositioned |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 04.R4 | 3035 | DATC1551 | 03.Conversion | 02.IF - Intel Foundry | edFIT - Material Master Conversion | 09A. Master Data | 9A.6 Master Data - Material | 04. FS In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/07.%20FTS%20-%20Intel%20Foundry/10.%20Plant%20Maintenance/3.%20Deliverables/2.%20Final/RICEFWs/RICEFW_eDFIT%20Scope.pptx?d=wf7effb30a53541aea8f0274aee20f5aa&csf=1&web=1&e=4uKaxP | 02.No | 01.Yes |  | 2025-08-13 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-08-25 | 2025-09-10 |  | 50% | 2025-09-10 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% |  | Not Applicable |  |  |  |  | jenoronha@deloitte.com | 2025-07-12 10:17 | ryapark@deloitte.com | 2026-04-07 12:27 | 4 | 2025-08-15 | 01.S4 |  |  | 1 | 1.45 | 1551 |  | R4 ITC1 | [7 empty] | 2025-09-10 | [34 empty] | 2025-09-10 | [5 empty] | WIINGS Only eDFIT | TRUE | 0 |  | 3168 | [7 empty] | 5. Not Dispositioned |  |  |  | N | 09A. Master Data | eDFIT | [7 empty] | N/A |  |  |  |  | No |  | No |  | Not Dispositioned |  |  |  | No | [5 empty] | No | [8 empty] | 4. WIINGS Only - Remaining
01. IAO ERP | 03.R3 | 2820 | DATC1237 | 03.Conversion | 02.IF - Intel Foundry | Material Master Data – Quality Management View Conversion | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/MDM_RICEFW_Material%20Master%20Quality%20Management%20View%20Conversion.pptx?d=w1217b288bec041168e59ece2e3b65c8b&csf=1&web=1&e=id8JVK |  |  |  | 2025-02-28 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-04-21 | 2025-05-16 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-20 | 2025-07-29 | 100% | 2025-08-01 | 2025-06-23 | 2025-07-18 | 2025-08-29 | 100% | 2025-08-29 | [15 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-03 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2025-02-07 07:16 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-28 | 01.S4 |  |  | 1 | 1.45 | 1237 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | [13 empty] | 2025-08-29 | 2025-08-29 |  |  | 2025-09-03 | 2025-09-10 | 2025-09-03 | [5 empty] | 2025-05-16 | 2025-07-18 |  |  | 2025-09-10 |  |  |  | 0 |  | 1453 | [10 empty] | 2025-07-18 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-29 | 2025-08-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2797 | DATC1204 | 03.Conversion | 01.IP - Intel Product | Load Vendor as Customer to MDG System | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B0B5DBADF-E572-4C5B-B3D5-36D6050E2D82%7D&file=Load%20Vendor%20as%20Customer%20to%20MDG%20System.pptx&action=edit&mobileredirect=true&CID=CE6B5F2B-5727-4816-9995-FC249521B132&wdLOR=c22B543C3-3864-4847-B9CF-8CAAFD00AB63 | 02.No | 01.Yes |  | 2025-02-03 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-28 | 2025-03-21 | 100% | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-08-19 | 100% | 2025-08-18 | 2025-08-18 | 2025-08-21 | 2025-08-22 | 100% | 2025-09-05 | 2025-08-22 | 2025-09-10 | 2025-09-26 | 100% | 2025-09-29 | [15 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-09 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2025-01-30 07:28 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-03 | 02.MDG |  |  | 1 | 1.45 | 1204 |  | R3 ITC1 | [6 empty] | 2025-04-07 | 2025-04-07 | 2025-04-07 |  | 2025-08-18 | 2025-08-19 | 2025-08-18 |  | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-29 | [12 empty] | 2025-09-29 | 2025-09-29 |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | [5 empty] | 2025-03-28 | 2025-09-10 |  |  | 2025-10-08 |  |  |  | 0 |  | 1717 | [10 empty] | 2025-09-10 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 18 |  | 2025-09-29 | 2025-09-29 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2257 | DATC0859 | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master Contact Person from ECC system to MDG system_IP | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BB18413E5-9622-437A-82C6-43BB7851C2BA%7D&file=Customer%20Master%20Conversion%20for%20Contact%20Person_IP.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2024-11-07 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-20 | 2025-02-28 | 2025-03-07 | 100% | 2025-03-11 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-05 | 2025-03-11 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-23 | 2025-08-15 | 2025-08-29 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-10 | 2025-09-26 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-26 | 2025-09-26 | N | 100% | 2025-09-29 | Not Applicable | R3 Build & UT Sprint 18 | 2025-08-15 | 2025-08-15 | 2025-08-15 | arpitsharma@deloitte.com | 2024-11-19 02:35 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 | 2024-11-07 | 02.MDG |  |  | 1 | 1.45 | 0859 |  | R3 ITC1 | [6 empty] | 2025-03-11 | 2025-03-11 | 2025-03-11 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | [5 empty] | 2025-02-28 | 2025-03-11 |  |  | 2025-05-16 |  |  |  | 0 | 08. Not Applicable | 1503 | [7 empty] | 1. On Track |  | 9/29 : Awaiting approval | 2025-08-15 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1993 | DATC0589 | 03.Conversion | 01.IP - Intel Product | Vendor Master : General Data conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_General%20Data_Conversion_Intake%20Form.pptx?d=w9ffd51e086e54ef583c9087099ac4e29&csf=1&web=1&e=3fXbf0 | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-10-11 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-30 | 2024-11-06 | 2024-11-04 | 100% | 2024-11-04 | 2024-11-05 | 2025-02-21 | 2025-02-28 | 100% | 2025-03-05 | [15 empty] | 2025-03-05 | 2025-03-05 |  |  | 2025-03-28 | 2025-04-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-10 | 2025-04-11 | 2025-04-11 | N | 100% | 2025-04-14 | Not Applicable | R3 Build & UT Sprint 12 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-11-19 | 01.S4 |  |  | 2 | 2.9 | 0589 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-11-04 | 2024-11-06 | 2024-11-04 | 2025-03-05 | [12 empty] | 2025-03-05 | 2025-03-05 |  |  | 2025-04-14 | 2025-04-14 | 2025-04-14 | [5 empty] | 2024-10-11 | 2024-11-06 |  |  | 2025-02-07 |  |  |  | 0 | 08. Not Applicable | 1933 | [10 empty] | 2025-02-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-05 | 2025-03-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1994 | DATC0588 | 03.Conversion | 01.IP - Intel Product | Vendor Master : Company Code Data conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_Company%20Code_Conversion_Intake%20Form.pptx?d=w0a9862e9473a489dbb26b0bda20cfd04&csf=1&web=1&e=5d2FOo | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-30 | 2024-11-06 | 2024-11-04 | 100% | 2024-11-04 | 2024-12-23 | 2025-02-21 | 2025-02-28 | 100% | 2025-03-05 | [15 empty] | 2025-03-05 | 2025-03-05 |  |  | 2025-04-18 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-03-24 | 2025-04-25 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-11-19 | 01.S4 |  |  | 1 | 1.45 | 0588 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-11-04 | 2024-11-06 | 2024-11-04 | 2025-03-05 | [12 empty] | 2025-03-05 | 2025-03-05 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-09-20 | 2024-11-06 |  |  | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 1934 | [9 empty] | This FUT is 100% complete.BSPID-40552 | 2025-02-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-05 | 2025-03-05 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1995 | DATC0587 | 03.Conversion | 01.IP - Intel Product | Vendor Master : Purchase Org conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_Purchasing%20Org_Conversion_Intake%20Form.pptx?d=w0042d7ecd9d34f0e8b38ec4192599b69&csf=1&web=1&e=MVH40e | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-08-26 | 2024-09-20 | 2024-09-20 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-30 | 2024-11-06 | 2024-11-04 | 100% | 2024-11-04 | 2024-11-18 | 2025-02-21 | 2025-03-07 | 100% | 2025-03-10 | [15 empty] | 2025-03-10 | 2025-03-10 |  |  | 2025-04-18 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-07 | 2025-05-09 | 2025-05-16 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-09-07 | 01.S4 |  |  | 1 | 1.45 | 0587 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-11-04 | 2024-11-06 | 2024-11-04 | 2025-03-10 | [12 empty] | 2025-03-10 | 2025-03-10 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-09-20 | 2024-11-06 |  |  | 2025-03-07 |  |  |  | 0 | 08. Not Applicable | 1935 | [7 empty] | 1. On Track | 1. Approved no action | This FUT is 100% complete.BSPID-40553 | 2025-02-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 11 |  | 2025-03-10 | 2025-03-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1996 | DATC0586 | 03.Conversion | 01.IP - Intel Product | Vendor Master : Partner Function conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_Partner%20Function_Conversion_Intake%20Form.pptx?d=w0b91c9d0c4f346479d469315540051ab&csf=1&web=1&e=XzGdCo | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 02.High |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-12-06 | 2024-11-15 | 100% | 2024-11-26 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-19 | 2024-11-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-24 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-09 | [15 empty] | 2025-04-09 | 2025-04-09 |  |  | 2025-05-16 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-04-21 | 2025-05-23 | 2025-06-11 | N | 100% | 2025-06-12 | Not Applicable | R3 Build & UT Sprint 14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-09-07 | 01.S4 |  |  | 2 | 2.9 | 0586 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-12-06 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-09 | [12 empty] | 2025-04-09 | 2025-04-09 |  |  | 2025-06-12 | 2025-06-12 | 2025-06-12 | [5 empty] | 2024-12-06 | 2024-11-21 |  |  | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 1944 | [10 empty] | 2025-03-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-09 | 2025-04-09 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1997 | DATC0585 | 03.Conversion | 01.IP - Intel Product | Vendor Master : Tax Data conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_Tax%20Data_Conversion_Intake%20Form.pptx?d=wf39fa08df1a84a8a84fea4bbd749c38a&csf=1&web=1&e=dsdlhk | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-01 | 2024-12-06 | 2024-11-15 | 100% | 2024-12-16 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2024-11-19 | 2024-11-21 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-24 | 2025-03-21 | 2025-04-04 | 100% | 2025-04-17 | [15 empty] | 2025-04-17 | 2025-04-17 |  |  | 2025-05-16 | 2025-06-06 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-05 | 2025-06-06 | 2025-06-06 | N | 100% | 2025-06-10 | Not Applicable | R3 Build & UT Sprint 14 | 2025-03-21 | 2025-03-21 | 2025-03-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-09-07 | 01.S4 |  |  | 1 | 1.45 | 0585 |  | R3 ITC1 | [6 empty] | 2024-12-16 | 2024-12-16 | 2024-12-16 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-04-17 | [12 empty] | 2025-04-17 | 2025-04-17 |  |  | 2025-06-10 | 2025-06-10 | 2025-06-10 | [5 empty] | 2024-12-06 | 2024-11-21 |  |  | 2025-04-04 |  |  |  | 0 | 08. Not Applicable | 1945 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-03-21 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-17 | 2025-04-17 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1998 | DATC0584 | 03.Conversion | 01.IP - Intel Product | Vendor Master : Bank Data conversion from ECC to MDG | 09A. Master Data | 9A.4 Master Data - Vendor | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/09.%20Master%20Data/5%20Working%20Documents/9%20Supplier%20(Vendor)%20Master/Intake%20Form/Vendor_Master_Data_Bank%20Data_Conversion_Intake%20Form.pptx?d=wa3d830e94d0b4fb5af1e31d8c9b31693&csf=1&web=1&e=Du04VV | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 03.Medium |  | 02.No |  |  |  |  | NA | 2024-11-18 | 2025-01-10 | 2025-01-24 | 100% | 2025-01-27 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-01-27 | 2025-01-31 | 2025-03-28 | 100% | 2025-03-28 | 2025-02-03 | 2025-02-28 | 2025-05-02 | 100% | 2025-08-04 | [15 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-14 | Not Applicable | R3 Build & UT Sprint 14 | 2025-02-28 | 2025-02-28 | 2025-02-28 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-09-07 | 01.S4 |  |  | 1 | 1.45 | 0584 |  | R3 ITC1 | [6 empty] | 2025-01-27 | 2025-01-27 | 2025-01-27 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-08-04 | [12 empty] | 2025-08-04 | 2025-08-04 |  |  | 2025-06-14 | 2025-06-14 | 2025-06-14 | [5 empty] | 2025-01-10 | 2025-01-31 |  |  | 2025-05-02 |  |  |  | 0 | 08. Not Applicable | 1946 | [10 empty] | 2025-02-28 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-04 | 2025-08-04 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 2024 | DATC0583 | 03.Conversion | 01.IP - Intel Product | Initial load of HRMM data from WCDS to MPipe system, The initial data load will be handled using flat files, no middleware needed in the initial load process , flat files to be provided by WCDS team, WCDS to have control of data including delta files to load into M-Pipe For data privacy SharePoint or OneDrive can be used- the data needs to be shared securely with controlled access | 09A. Master Data | 9A.8 Master Data - HR Mini Master | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BEDDF8EEF-670E-4564-A60B-913695E1FF71%7D&file=HRMM_Initial%20load%20from%20WCDS%20to%20MPipe_Intake%20Formf.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-09-06 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  |  | 02.High |  | 02.No |  |  | RELTIO | S4 | NA | 2024-09-16 | 2024-10-11 | 2024-10-11 | 100% | 2024-11-26 | 2024-11-01 | 2024-11-01 | 2025-06-19 | 100% | 2025-07-21 | 2024-10-28 | 2024-11-01 | 2024-11-04 | 100% | 2024-11-26 | 2024-11-18 | 2025-02-21 | 2025-04-18 | 100% | 2025-04-18 | [15 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-04-25 | 2025-05-09 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-02-02 | 2025-02-28 | 2025-05-09 | N | 100% | 2025-08-04 | Not Applicable | R3 Build & UT Sprint 16 | 2025-02-21 | 2025-02-21 | 2025-02-21 | arpitsharma@deloitte.com | 2024-11-19 03:49 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 | 2024-11-19 | 01.S4 |  |  | 2 | 2.9 | 0583 |  | R3 ITC1 | [6 empty] | 2024-11-26 | 2024-11-26 | 2024-11-26 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2025-04-18 | [12 empty] | 2025-04-18 | 2025-04-18 |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | [5 empty] | 2024-10-11 | 2024-11-01 |  |  | 2025-02-28 |  |  |  | 0 | 08. Not Applicable | 2025 | [10 empty] | 2025-02-21 | Y | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 12 |  | 2025-04-18 | 2025-04-18 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1965 | DATC0562 | 03.Conversion | 01.IP - Intel Product | Conversion of DUNS table from ECC to S/4 for IP | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/04.%20OTC%20-%20Intel%20Foundry/2%20Design%20Sprint%20detailed%20plans/Phase%201%20Detailed%20design%20%26%20Sprint%20Planning/Workshops/Ready%20for%20Review/Console%20ID_IP_OTC_DUNS%20table%20conversion.pptx?d=w02d94fab654342b78769d91ac5d7e070&csf=1&web=1&e=LdHq9p | 02.No | 01.Yes |  | 2025-02-05 | candice.s.linnell@intel.com | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-03-10 | 2025-04-25 | 2025-03-21 | 100% | 2025-04-09 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-20 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-12 | 2025-09-10 | N | 100% | 2025-09-12 | Not Applicable | R3 Build & UT Sprint 17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | arpitsharma@deloitte.com | 2024-11-19 02:35 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 | 2025-02-05 | 01.S4 |  |  | 1 | 1.45 | 0562 |  | R3 ITC1 | [6 empty] | 2025-04-09 | 2025-04-25 | 2025-04-09 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | [5 empty] | 2025-04-25 | 2025-07-18 |  |  | 2025-09-12 |  |  |  | 0 | 08. Not Applicable | 1917 | [7 empty] | 1. On Track | 3. Awaiting Approval |  | 2025-07-18 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1927 | DATC0553 | 03.Conversion | 02.IF - Intel Foundry | Conversion of BOM from SPEED to S4 IF | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA67D9931-F77E-4DA4-8953-5A052132BA46%7D&file=Draft_Conversion%20_Intake%20Form_IF_BOM.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cshrutisingh7%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA2MjcyNDgxNyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2024-08-20 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No | 4092; 11140 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED) |  |  | NA | 2025-03-03 | 2025-04-16 | 2025-04-16 | 100% | 2025-04-18 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-13 | 2025-07-28 | 2025-09-12 | 2025-12-04 | 100% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-19 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 03:49 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-19 | 01.S4 |  |  | 4 | 5.8 | 0553 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-03 | [12 empty] | 2025-12-03 | 2025-12-03 |  |  | 2025-12-19 | 2025-12-19 | 2025-12-19 | [5 empty] | 2025-04-16 | 2025-03-28 |  |  | 2025-04-25 |  |  |  | 0 | 08. Not Applicable | 2725 | [7 empty] | 4. Completed | 3. Awaiting Approval | 12/15-FUT is awaiting approval 11/18 - FUT planned to complete by 11/21( 8/17 test cases sent for Intel review on 11/17) | 2025-09-12 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-04 | 2025-12-03 | No |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 1926 | DATC0552 | 03.Conversion | 01.IP - Intel Product | Conversion of BOM from SPEED to S4 IP | 09A. Master Data | 9A.2 Master Data - BOM | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BA71B9D2C-85C9-4CAF-8405-2A8E42D654EE%7D&file=Draft_Conversion%20_Intake%20Form_IP_BOM.pptx&action=edit&mobileredirect=true&ovuser=36da45f1-dd2c-4d1f-af13-5abe46b99921%2Cshrutisingh7%40deloitte.com&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDA2MjcyNDgxNyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D | 02.No | 01.Yes |  | 2024-08-20 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 01.Very High |  | 02.No | 4092; 11140 | SPEED PDM (Legacy SPEED); SPEED PDM (Next Generation SPEED) |  |  | NA | 2025-03-03 | 2025-04-16 | 2025-04-16 | 100% | 2025-04-18 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-07-21 | 2025-07-25 | 2025-07-29 | 100% | 2025-08-13 | 2025-07-28 | 2025-09-12 | 2025-12-04 | 100% | 2025-12-03 | [15 empty] | 2025-12-03 | 2025-12-03 |  |  | 2025-11-28 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-11-10 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-20 | Not Applicable | R3 Build & UT Sprint 21 | 2025-09-12 | 2025-09-12 | 2025-09-12 | arpitsharma@deloitte.com | 2024-11-19 03:49 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 | 2024-11-19 | 01.S4 |  |  | 4 | 5.8 | 0552 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-12-03 | [12 empty] | 2025-12-03 | 2025-12-03 |  |  | 2025-12-20 | 2025-12-20 | 2025-12-20 | [5 empty] | 2025-04-16 | 2025-03-28 |  |  | 2025-04-25 |  |  |  | 0 |  | 1473 | [7 empty] | 1. On Track | 3. Awaiting Approval | 12/15-FUT is awaiting approval 11/18 - FUT planned to complete by 11/21( 8/17 test cases sent for Intel review on 11/17) | 2025-09-12 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 20 |  | 2025-12-04 | 2025-12-03 | No |  | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 551 | DATC0213 | 03.Conversion | 01.IP - Intel Product | Material Master-Work scheduling view | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/50%20Archive/Intake%20Form%20Archived/378-M-150-190_DATA_Material_Master_Work_scheduling_view_Intake_Form_v1.0.pptx?d=w5360cd3cb2a24bc39c061365e82f6422&csf=1&web=1&e=WnB1tz | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-20 | 2025-03-28 | 2025-05-16 | 100% | 2025-08-04 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-04-21 | 2025-04-25 | 2025-06-24 | 100% | 2025-07-21 | 2025-04-25 | 2025-05-25 | 2025-08-22 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-11 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-25 | 2025-05-25 | 2025-05-25 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-16 10:28 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0213 | INT-CR1575 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | [5 empty] | 2025-03-28 | 2025-04-18 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 1679 | [7 empty] | 3. Off Track | 8. Blocked by CR/Design change |  | 2025-05-25 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-22 | 2025-08-22 | Yes | Plant X-Ref needs to to updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 468 | DATC0184_IP | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master Partner Function view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B85D403D0-C78E-44E2-97F0-44DEC09E319D%7D&file=Customer_Master_Data_Partner_Functions_Conversion_IP_Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-05-01 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-01-13 | 2025-03-07 | 2025-02-21 | 100% | 2025-02-15 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-12 | 2025-03-14 | 2025-05-02 | 100% | 2025-08-04 | 2025-05-23 | 2025-06-13 | 2025-08-01 | 100% | 2025-08-13 | [15 empty] | 2025-08-13 | 2025-08-13 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-28 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-04-30 03:30 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 |  | 01.S4 | DATC0184_IF | 03.Medium | 0.3 | 0.435 | 0184 |  | R3 ITC1 | [6 empty] | 2025-02-15 | 2025-03-07 | 2025-02-15 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-13 | [12 empty] | 2025-08-13 | 2025-08-13 |  |  | 2025-08-28 | 2025-08-29 | 2025-08-28 | [5 empty] | 2025-03-07 | 2025-03-14 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 2836 | [10 empty] | 2025-06-13 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-13 | 2025-08-13 | Yes | Regression testing | No |  | Yes | Regression Test | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 466 | DATC0182_IP | 03.Conversion | 01.IP - Intel Product | Convert the General data view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B207DF1B8-B143-4BFD-939F-7AB510694578%7D&file=Customer_Master_Data_General_Data_Conversion_IP_%20Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-05-01 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2024-11-18 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-11 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-24 | 2025-03-28 | 2025-03-28 | 100% | 2025-04-04 | 2025-03-03 | 2025-05-16 | 2025-06-06 | 100% | 2025-06-10 | [15 empty] | 2025-06-10 | 2025-06-10 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-04-30 03:30 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 | DATC0182_IF | 03.Medium | 0.3 | 0.435 | 0182 |  | R3 ITC1 | [6 empty] | 2025-01-11 | 2025-01-17 | 2025-01-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-04-04 | 2025-04-04 | 2025-04-04 | 2025-06-10 | [12 empty] | 2025-06-10 | 2025-06-10 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-01-17 | 2025-01-31 |  |  | 2025-04-11 |  |  |  | 0 | 08. Not Applicable | 2383 | [10 empty] | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-10 | 2025-06-10 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 469 | DATC0179_IP | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master Sales view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BCA577034-6822-4E97-B03B-3136BE9F8274%7D&file=Customer_Master_Data_Sales_View_Conversion_IP_Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-05-01 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | NA | NA | NA | NA | 2025-01-13 | 2025-03-07 | 2025-02-21 | 100% | 2025-02-15 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-17 | 2025-03-20 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-28 | 2025-06-13 | 2025-08-22 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-13 | 2025-08-29 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-04 | 2025-08-29 | 2025-08-29 | N | 100% | 2025-08-28 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-04-30 03:30 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 |  | 01.S4 | DATC0179_IF | 02.High | 0.6 | 0.87 | 0179 |  | R3 ITC1 | [6 empty] | 2025-02-15 | 2025-03-07 | 2025-02-15 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-22 | [12 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-08-28 | 2025-08-29 | 2025-08-28 | [5 empty] | 2025-03-07 | 2025-03-20 |  |  | 2025-05-09 |  |  |  | 0 | 08. Not Applicable | 1954 | [10 empty] | 2025-06-13 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-08-22 | 2025-08-22 | Yes | Regression testing | No |  | Yes | Regression Test | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 470 | DATC0178_IP | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master Tax view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7BC4D13463-0621-4F9F-9D29-FA410B7D5FB9%7D&file=Customer_Master_Data_Tax%20Code_Conversion_IP_Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-05-01 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | NA | NA | NA | NA | 2024-12-16 | 2025-02-07 | 2025-02-07 | 100% | 2025-01-29 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-03-17 | 2025-03-20 | 2025-06-24 | 100% | 2025-07-21 | 2025-08-22 | 2025-09-10 | 2025-09-10 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-09-26 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-10-10 | Not Applicable | R3 Build & UT Sprint 18 | 2025-09-10 | 2025-09-10 | 2025-09-10 | pgaroo@deloitte.com | 2024-04-30 03:30 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 | DATC0178_IF | 03.Medium | 0.3 | 0.435 | 0178 |  | R3 ITC1 | [6 empty] | 2025-01-29 | 2025-02-07 | 2025-01-29 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | [5 empty] | 2025-02-07 | 2025-03-20 |  |  | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 1956 | [10 empty] | 2025-09-10 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 464 | DATC0120_IP | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master Company Code view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B2262AAD7-E246-4447-B940-A3E73019AFA6%7D&file=Customer_Master_Data_Company%20Code_Conversion_IP_Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-04-23 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  | ECC | ECC | MDG | NA | 2024-11-18 | 2025-01-17 | 2025-01-17 | 100% | 2025-01-11 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-04-21 | 2025-04-25 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-28 | 2025-05-16 | 2025-06-06 | 100% | 2025-06-12 | [15 empty] | 2025-06-12 | 2025-06-12 |  |  | 2025-07-04 | 2025-07-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-11 | 2025-07-16 | N | 100% | 2025-07-21 | Not Applicable | R3 Build & UT Sprint 16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-04-22 23:39 | cell-link@smartsheet.com | 2026-03-17 04:07 | 10 |  | 01.S4 | DATC0120_IF | 03.Medium | 0.3 | 0.435 | 0120 |  | R3 ITC1 | [6 empty] | 2025-01-11 | 2025-01-17 | 2025-01-11 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-06-12 | [12 empty] | 2025-06-12 | 2025-06-12 |  |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | [5 empty] | 2025-01-17 | 2025-01-31 |  |  | 2025-04-11 |  |  |  | 0 | 08. Not Applicable | 2835 | [10 empty] | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-12 | 2025-06-12 | Yes | Regression testing | No |  | Yes | Regression Test | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-17 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 467 | DATC0118_IP | 03.Conversion | 01.IP - Intel Product | Convert the Customer Master In House Cash view from ECC system to MDG system_IP. | 09A. Master Data | 9A.3 Master Data - Customer | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B6A40DDA8-D67F-4F99-BDC2-BC4EED87C69A%7D&file=Customer_Master_Data_In%20House_CashView_Conversion_IP_%20Intake%20Form.pptx&action=edit&mobileredirect=true | 01.Yes | 01.Yes |  | 2024-04-23 | Candice S Linnell | 01.Approved |  | Std. | 01.Yes | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  | ECC | ECC | MDG | NA | 2025-02-10 | 2025-03-07 | 2025-03-07 | 100% | 2025-03-19 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-12 | 2025-03-14 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-28 | 2025-05-16 | 2025-06-06 | 100% | 2025-05-30 | [15 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-05-30 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-04-22 23:39 | mdfarhan@deloitte.com | 2026-02-25 02:52 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0118 |  | R3 ITC1 | [6 empty] | 2025-03-19 | 2025-03-19 | 2025-03-19 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-05-30 | [12 empty] | 2025-05-30 | 2025-05-30 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-03-07 | 2025-03-14 |  |  | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 2385 | [10 empty] | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-06 | 2025-05-30 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 199 | DATC0076_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Classification View | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/128-M-150-190_DATA_Material_Master_Classification_Views_Intake%20Form_v1.0.pptx?d=w1355bd0896e7483aab443b0e21a39776&csf=1&web=1&e=GfD2E0 | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-20 | 2025-04-02 | 2025-04-18 | 100% | 2025-04-21 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-05-19 | 2025-05-23 | 2025-05-30 | 100% | 2025-06-06 | 2025-05-26 | 2025-06-13 | 2025-10-10 | 100% | 2025-10-10 | [15 empty] | 2025-10-10 | 2025-10-10 |  |  | 2025-10-31 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-05 | 2025-11-05 | N | 100% | 2025-11-13 | Not Applicable | R3 Build & UT Sprint 20 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-15 06:11 | vgulhane@deloitte.com | 2026-02-16 03:45 | 10 |  | 01.S4 | DATC0076_IF | 02.High | 0.6 | 0.87 | 0076 |  | R3 ITC1 | [6 empty] | 2025-04-21 | 2025-04-21 | 2025-04-21 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-10-10 | [12 empty] | 2025-10-10 | 2025-10-10 |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | [5 empty] | 2025-03-21 | 2025-04-11 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 2813 | [7 empty] | 2. At Risk | 3. Awaiting Approval | 11/12 - Feedback from Intel post FUT Review in progress. ETA for approval is 11/14 10/30 - Complex object. FUT in progress. ETA is 11/7 10/24 - FUT in progress | 2025-06-13 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-10-10 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 549 | DATC0075_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Accounting & Costing view | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/50%20Archive/Intake%20Form%20Archived/376-M-150-190_DATA_Material_Master_Accounting_Costing_view_Intake_Form_v1.0.pptx?d=w64c72ddff764459b8519741e63b0f282&csf=1&web=1&e=ayIhfo | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-03-21 | 2025-03-21 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-05-19 | 2025-05-23 | 2025-05-30 | 100% | 2025-05-30 | 2025-05-26 | 2025-06-13 | 2025-06-19 | 100% | 2025-07-21 | [15 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-07-04 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-11 | N | 100% | 2025-08-08 | Not Applicable | R3 Build & UT Sprint 16 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-15 06:11 | ryapark@deloitte.com | 2026-04-07 12:27 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0075 | INT-CR1575 | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-07-21 | [12 empty] | 2025-07-21 | 2025-07-21 |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | [5 empty] | 2025-03-21 | 2025-04-11 |  |  | 2025-06-06 |  | WIINGS Only | TRUE | 0 | 08. Not Applicable | 1678 | [9 empty] | Awaiting approval from Nidhi | 2025-06-13 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-07-21 | 2025-07-21 | Yes | Plant X-Ref needs to to updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed |  | 2. WIINGS Only - PAID
01. IAO ERP | 03.R3 | 197 | DATC0074_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Sales Org Views and Sales Text | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/126-M-150-190_DATA_Material_Master_Sales_org_View_sales_text_Intake%20Form_v1.0%20.pptx?d=w755f5bcc943a44eba9dfa0ad8b7b524b&csf=1&web=1&e=JOq6oa | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-03 | 2025-04-04 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-05-19 | 2025-05-23 | 2025-07-25 | 100% | 2025-08-01 | 2025-05-26 | 2025-07-18 | 2025-08-22 | 100% | 2025-08-22 | [15 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-10-03 | 2025-11-05 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-11-07 | 2025-11-05 | N | 100% | 2025-11-03 | Not Applicable | R3 Build & UT Sprint 19 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-16 10:28 | 10 |  | 01.S4 | DATC0074_IF | 02.High | 0.6 | 0.87 | 0074 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | [13 empty] | 2025-08-22 | 2025-08-22 |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | [5 empty] | 2025-04-04 | 2025-04-25 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 1461 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/24 - Awaiting approval | 2025-07-18 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 17 |  | 2025-08-22 | 2025-08-22 | Yes | Sales Org XREF needs to be updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 196 | DATC0073 | 03.Conversion | 01.IP - Intel Product | Material Master-Warehouse Mgmt Views | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/125-M-150-190_DATA_Material_Master_Warehouse_Mgmt_view_%20Intake%20Form_v1.0.pptx?d=wcb82a0cb602849faab426c5fddb85a5a&csf=1&web=1&e=iZvEwH | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-13 | 2025-04-04 | 2025-04-18 | 100% | 2025-04-18 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 100% | 2025-07-23 | 2025-06-16 | 2025-06-18 | 2025-06-24 | 100% | 2025-07-21 | 2025-06-23 | 2025-07-18 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-08 | 2025-08-13 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-07-21 | 2025-08-08 | 2025-08-13 | N | 100% | 2025-12-12 | Not Applicable | R3 Build & UT Sprint 21 | 2025-07-18 | 2025-07-18 | 2025-07-18 | pgaroo@deloitte.com | 2024-05-15 06:11 | jenoronha@deloitte.com | 2026-02-12 06:58 | 10 |  | 01.S4 |  |  | 0.5 | 0.725 | 0073 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-23 | 2025-07-23 | 2025-07-23 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | [5 empty] | 2025-04-04 | 2025-07-18 |  |  | 2025-08-08 |  |  |  | 0 | 08. Not Applicable | 2801 | [7 empty] | 4. Completed | 17. FUT In progress | 12/05: Walkthrough provided,awaiting approval.​ 10/30 - FS submitted for approval. BODS team picked up for build 10/24 - FS to be submitted & Build in Sprint 20. FUT planned in Sprint 21 10/10 : FUT is in progress10/03 : CR #1066 approval is in progress for descope08/18 :CR #1066 approval is in progress for descope 08/14 MS: This Object will be descoped as per confirmation from EWM Team, CR #1066 is created and approval is in progress | 2025-07-18 | N | 09A. Master Data | [5 empty] | 4. To be discussed |  | CR/Design change | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 195 | DATC0072 | 03.Conversion | 01.IP - Intel Product | Material Master-Purchasing View and PO Text | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/124-M-150-190_DATA_Material_Master_Purchasing_View_PO_text%20Intake%20Form_v1.pptx?d=w5c2496892bbc45c28ff24693e08e77f2&csf=1&web=1&e=DFNYvJ | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-04-04 | 2025-04-18 | 100% | 2025-04-18 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-04-21 | 2025-04-25 | 2025-05-02 | 100% | 2025-08-04 | 2025-04-28 | 2025-05-16 | 2025-08-01 | 100% | 2025-07-24 | [15 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-08-29 | 2025-09-10 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-08-18 | 2025-09-10 | 2025-09-10 | N | 100% | 2025-09-09 | Not Applicable | R3 Build & UT Sprint 17 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-16 10:28 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0072 |  | R3 ITC1 | [6 empty] | 2025-04-18 | 2025-04-18 | 2025-04-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-07-24 | [12 empty] | 2025-07-24 | 2025-07-24 |  |  | 2025-09-09 | 2025-09-10 | 2025-09-09 | [5 empty] | 2025-04-04 | 2025-05-16 |  |  | 2025-09-10 |  |  |  | 0 | 08. Not Applicable | 2799 | [10 empty] | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-24 | Yes | Plant X-Ref needs to to updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 194 | DATC0071_IP | 03.Conversion | 01.IP - Intel Product | Material Master-MRP View | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/123-M-150-190_DATA_Material_Master_MRP%20View_%20Intake%20Form_v1.0.pptx?d=w6a87d63e6e17431f9a7d3cd418d2570a&csf=1&web=1&e=Ik5JFu | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-01-20 | 2025-03-28 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-05-19 | 2025-05-23 | 2025-05-30 | 100% | 2025-08-14 | 2025-05-26 | 2025-06-13 | 2025-10-10 | 100% | 2025-09-25 | [15 empty] | 2025-09-25 | 2025-09-25 |  |  | 2025-10-03 | 2025-10-08 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-09-15 | 2025-10-08 | 2025-10-08 | N | 100% | 2025-11-07 | Not Applicable | R3 Build & UT Sprint 19 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-16 10:28 | 10 |  | 01.S4 | DATC0071_IF | 03.Medium | 0.3 | 0.435 | 0071 |  | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-09-25 | [12 empty] | 2025-09-25 | 2025-09-25 |  |  | 2025-11-07 | 2025-11-07 | 2025-11-07 | [5 empty] | 2025-03-28 | 2025-04-18 |  |  | 2025-06-13 |  |  |  | 0 | 08. Not Applicable | 2796 | [7 empty] | 1. On Track | 3. Awaiting Approval | 10/30 - Awaiting approval 10/24 - Review comments are being addressed. Sent for approval Due to defect, the FUT completion got delayed , ETA to submit FUT - 10/10 for Intel review and approval | 2025-06-13 | N | 09A. Master Data | [7 empty] | Awaiting approval | Complete | R3 Build & UT Sprint 18 |  | 2025-10-10 | 2025-09-25 | Yes | Plant X-Ref needs to to updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 193 | DATC0070_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Plant Data/Storage Views | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/122-M-150-190_DATA_Material_Master_Plant_data_storage_views_%20Intake%20Form_v1.0.pptx?d=w6f2f34c42a6b4bef9ab00911b1fbe484&csf=1&web=1&e=ZApD47 | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-06 | 2025-04-04 | 2025-05-16 | 100% | 2025-08-04 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-04-21 | 2025-04-25 | 2025-05-30 | 100% | 2025-06-06 | 2025-04-28 | 2025-06-13 | 2025-08-01 | 100% | 2025-07-23 | [15 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-07-04 | 2025-07-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-06-16 | 2025-07-04 | 2025-07-11 | N | 100% | 2025-08-22 | Not Applicable | R3 Build & UT Sprint 17 | 2025-06-13 | 2025-06-13 | 2025-06-13 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-16 10:28 | 10 |  | 01.S4 | DATC0070_IF | 02.High | 0.6 | 0.87 | 0070 | INT-CR1575 | R3 ITC1 | [6 empty] | 2025-08-04 | 2025-08-04 | 2025-08-04 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-07-23 | [12 empty] | 2025-07-23 | 2025-07-23 |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | [5 empty] | 2025-04-04 | 2025-04-25 |  |  | 2025-06-20 |  |  |  | 0 | 08. Not Applicable | 2351 | [9 empty] | 08/18 : Additional review comments received and plan to submit today 08/18 8/11 : Review by business and IT comments being addressed | 2025-06-13 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 16 |  | 2025-08-01 | 2025-07-23 | Yes | Plant X-Ref needs to to updated | No |  | Yes | Regression Testing | 2026-02-09 | 2026-03-06 | No | [5 empty] | Yes | 2026-03-13 | 2026-03-04 | 2026-03-16 | 100% | 04. Completed | 100% | 04. Completed
01. IAO ERP | 03.R3 | 192 | DATC0069_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Alt UOM | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/121-M-150-190_DATA_Material_Master_Alt_UOM_conversion_%20Intake%20Form_v1.0.pptx?d=wb560fcca1b4a40cfad073e0ff3605d66&csf=1&web=1&e=SORv67 | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA | 2025-02-24 | 2025-03-14 | 2025-03-21 | 100% | 2025-03-14 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-28 | 2025-04-04 | 2025-03-28 | 100% | 2025-04-04 | 2025-04-11 | 2025-05-16 | 2025-06-06 | 100% | 2025-05-23 | [15 empty] | 2025-05-23 | 2025-05-23 |  |  | 2025-06-06 | 2025-06-11 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-05-19 | 2025-06-13 | 2025-06-11 | N | 100% | 2025-06-13 | Not Applicable | R3 Build & UT Sprint 14 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 | DATC0069_IF | 03.Medium | 0.3 | 0.435 | 0069 |  | R3 ITC1 | [6 empty] | 2025-03-14 | 2025-03-21 | 2025-03-14 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-04-04 | 2025-04-04 | 2025-04-04 | 2025-05-23 | [12 empty] | 2025-05-23 | 2025-05-23 |  |  | 2025-06-13 | 2025-06-13 | 2025-06-13 | [5 empty] | 2025-03-14 | 2025-04-04 |  |  | 2025-05-30 |  |  |  | 0 | 08. Not Applicable | 2349 | [10 empty] | 2025-05-16 | N | 09A. Master Data | [8 empty] | Complete | R3 Build & UT Sprint 14 |  | 2025-06-06 | 2025-05-23 | No |  | No |  | No |  |  |  | No | [5 empty] | No
01. IAO ERP | 03.R3 | 542 | DATC0068_IP | 03.Conversion | 01.IP - Intel Product | Material Master-Basic Data- (including description) Views | 09A. Master Data | 9A.6 Master Data - Material | 10. Object Complete | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/50%20Archive/Intake%20Form%20Archived/369-M-150-190_DATA_Material_Master_Basic_Data_conversion_intake_Form_v1.0.pptx?d=wf59e97a28bf142718b8e6a79bdaaf5a8&csf=1&web=1&e=HH0d2C | 02.No | 01.Yes |  | 2024-05-22 | Candice S Linnell | 01.Approved |  | Std. | 02.No | 01.Deloitte |  | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA | 2025-01-06 | 2025-03-18 | 2025-03-21 | 100% | 2025-03-18 | 2025-06-16 | 2025-06-19 | 2025-06-19 | 100% | 2025-07-21 | 2025-03-28 | 2025-04-04 | 2025-03-28 | 100% | 2025-04-02 | 2025-04-11 | 2025-05-16 | 2025-09-10 | 100% | 2025-09-12 | [15 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-11-05 | 2025-12-03 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  | 2025-10-13 | 2025-12-05 | 2025-12-03 | N | 100% | 2025-12-10 | Not Applicable | R3 Build & UT Sprint 21 | 2025-05-16 | 2025-05-16 | 2025-05-16 | pgaroo@deloitte.com | 2024-05-15 06:11 | cell-link@smartsheet.com | 2026-03-09 00:19 | 10 |  | 01.S4 |  |  | 1 | 1.45 | 0068 |  | R3 ITC1 | [6 empty] | 2025-03-18 | 2025-03-21 | 2025-03-18 |  | 2025-07-21 | 2025-07-21 | 2025-07-21 |  | 2025-04-02 | 2025-04-04 | 2025-04-02 | 2025-09-12 | [12 empty] | 2025-09-12 | 2025-09-12 |  |  | 2025-12-10 | 2025-12-10 | 2025-12-10 | [5 empty] | 2025-03-14 | 2025-04-04 |  |  | 2025-06-06 |  |  |  | 0 | 08. Not Applicable | 1677 | [7 empty] | 4. Completed | 17. FUT In progress | 12/05: Walkthroughs completed. Dropped reminder email. ETA for submission and approval 12/05.- FUT In Progress 7/18 test cases under review with Intel, planned ETA to complete rest scenarios 11/21 | 2025-05-16 | N | 09A. Master Data | [7 empty] | FUT In Progress | Complete | R3 Build & UT Sprint 17 |  | 2025-09-12 | 2025-09-12 | No | Assumption: All 3 Divisions will remain As-Is | No |  | No |  | 2026-02-09 | 2026-03-06 | No | [5 empty] | No
01. IAO ERP | 03.R3 | 3206 | LOGI1738 | 02.Interface | 02.IF - Intel Foundry | Interface to send data to Factory Comm to activate the Mobile text receiving capability for technicians | 07. FTS IF | 7.6 FTS IF - Logistics & Inventory Management | 04. FS In Progress | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7BFB329B6D-907E-4053-9FA0-22FCC576105D%7D&file=CR1702%20Interface%20to%20trigger%20the%20Text%20message%20on%20Mobile%20to%20Maintinance%20technicians%20via%20FC.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-11 | Jorge Sanchez | 01.Approved |  | Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 01.Yes | 11807 | Factory Communications |  |  | NA |  |  | 2026-04-10 | 62% | 2026-04-10 |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [14 empty] | 0% | [20 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-11 08:11 | cell-link@smartsheet.com | 2026-04-07 06:40 | 4 |  | 01.S4 |  |  | 2 | 2.9 | 1738 | INT-CR1702 | R3 ITC2 | R3 ITC2 | [6 empty] | 2026-04-10 | [42 empty] | 1 |  | 3453 | [11 empty] | N | 99. Logistics | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3207 | FTSE1739 | 04.Enhancement | 01.IP - Intel Product | Develop Utility for mass change of Production Orders in SAP S4 system | 08. FTS IP | 8.5 FTS IP - Manufacturing | 02. FS Unplanned | Y | 2026-03-12 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/10%20RICEFW%20Inbox/3207_FTS_IP_Utility%20for%20mass%20change%20of%20Production%20Orders%20in%20SAP%20S4%20system.pptx?d=w488f4a90eeeb46a6a2f0cdd3f3ac4a8e&csf=1&web=1&e=UZDGTl | 02.No | 01.Yes |  | 2026-03-20 | Thomas M Sanger | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-20 04:05 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 2 |  | 01.S4 |  |  | 1 | 1 | 1739 | INT-CR1803 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3454 | [11 empty] | N | 08. FTS IP | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3212 | PTPE1740 | 04.Enhancement | 01.IP - Intel Product | Fair Market value Determination using custom code/logic during the replication of the Purchase Order (PO) in GTS | 06. PTP | 6.6 PTP - GTS | 01. Pending Approval | Y |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B5AABC0A6-90DB-4A48-9C75-8356B2998488%7D&file=INT-CR1781%20-%20Fair%20Market%20value%20Determination%20using%20custom%20code%20logic%20during%20the%20replication%20of%20PO%20in%20GTS.pptx&action=edit&mobileredirect=true&CID=96A2EB68-B783-4C11-98E3-3EB89194C1F2&wdLOR=cE43F0A61-E1EA-459B-963E-9F1F10D9ABC5&clickparams=eyAiWC1BcHBOYW1lIiA6ICJNaWNyb3NvZnQgT3V0bG9vayIsICJYLUFwcFZlcnNpb24iIDogIjE2LjAuMTk3MjUuMjAxNzAiLCAiT1MiIDogIldpbmRvd3MiIH0%3D | 02.No | 01.Yes |  | 2026-03-20 | Cari Shim | 01.Approved |  | TBD - RICEFW Pending Approval | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 02.High |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-20 04:05 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 1 |  | 01.S4 |  |  | 2 | 2 | 1740 | INT-CR1781 | R3 ITC2 | R3 ITC2 | [46 empty] | GTS |  |  | 0 |  | 3455 | [11 empty] | N | 06. PTP | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3210 | FPRE1741 | 04.Enhancement | 01.IP - Intel Product | Mobile timesheet approval for Intel Federal employees. | 03. FPR | 3.11 FPR - Project Accounting | 01. Pending Approval | Y |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B1F52747C-731B-4AE9-A9BF-FE6C28C4B280%7D&file=Console%20ID_3210_IP%20Intel%20Federal%20Mobile%20Timesheet%20Approval.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-25 | Shane Bethune | 01.Approved |  | TBD - RICEFW Pending Approval | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 01.Very High |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-24 21:01 | jenoronha@deloitte.com | 2026-04-08 03:02 | 1 |  | 01.S4 |  |  | 4 | 4 | 1741 | INT-CR1682 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3456 | [11 empty] | N | 03. FPR | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3209 | PTPE1742 | 04.Enhancement | 01.IP - Intel Product | Enhancement requirement to read production order changes and automate text purchase order updates for OSAT business | 06. PTP | 6.2 PTP - Procurement | 02. FS Unplanned | Y | 2026-03-20 | 01. Approved | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B51B606A3-8BE8-4212-8842-D3B7BC4C89DF%7D&file=Console_3209%20New%20Enhancement%20required%20to%20read%20production%20order%20status%20and%20changes%20and%20automate%20text%20PO%20%20closure%20for%20OSAT%20process.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-25 | Cari Shim | 01.Approved |  | Non-Std. | 02.No | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-25 02:37 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 2 |  | 01.S4 |  |  | 1 | 1 | 1742 | INT-CR1798 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3457 | [11 empty] | N | 06. PTP | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3213 | DATC1743 | 03.Conversion | 07.MDG | Material Human Readable Description Derivation and Direct Update on the Existing Materials | 09A. Master Data | 9A.6 Master Data - Material | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B36BB40E6-7269-40F9-A28F-444AE7BF813E%7D&file=INT-CR1834_Material%20Human%20Readable%20Description%20Derivation%20and%20Direct%20Update%20on%20the%20Existing%20Materials.pptx&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-25 | Candice S Linnell | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-25 02:53 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 2 | 2026-03-25 | 02.MDG |  |  | 1 | 1.45 | 1743 | INT-CR1834 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3458 | [11 empty] | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
01. IAO ERP | 03.R3 | 3215 | DATC1744_IP | 03.Conversion | 07.MDG | Implement Group BOM conversion functionality for S4 | 09A. Master Data | 9A.2 Master Data - BOM | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B4219D77F-63EC-46BF-8BA1-7DEB555E8626%7D&file=CR1811%20-%20Create%20Group%20BOM.pptx&wdLOR=c9C511CC6-140B-473E-B3F2-B0A13047FF23&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-30 | Candice S Linnell | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte | 03. NA | 01.Deloitte | 03.Medium |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-29 23:59 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 2 | 2026-03-30 | 02.MDG |  |  | 1 | 1.45 | 1744 | INT-CR1811 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3459 | [11 empty] | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned
[9 empty] | 01. Pending Approval | [11 empty] | TBD - RICEFW Pending Approval | [15 empty] | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [20 empty] | 2025-08-13 | 2025-05-16 |  | 100% | 100% |  |  |  | 04. Completed | 04. Completed |  |  |  |  | 2025-05-16 | N | 100% | 2026-03-30 |  | R3 Build & UT Sprint 23+ |  |  |  | jenoronha@deloitte.com | 2026-03-29 23:59 | automation@smartsheet.com | 2026-03-29 23:59 | 1 | [5 empty] | 0 |  |  | R3 ITC1 | [33 empty] | 2026-03-30 | 2026-03-30 | 2025-05-19 | 2025-05-19 | [13 empty] | 0 |  | 3460 | [11 empty] | N | [9 empty] | N/A | [12 empty] | Not Dispositioned | [5 empty] | Not Dispositioned |  |  |  | 0% |  | 0%
01. IAO ERP | 03.R3 | 3215 | DATC1744_IF | 03.Conversion | 07.MDG | Implement Group BOM conversion functionality for S4 | 09A. Master Data | 9A.2 Master Data - BOM | 02. FS Unplanned | N |  |  | https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B4219D77F-63EC-46BF-8BA1-7DEB555E8626%7D&file=CR1811%20-%20Create%20Group%20BOM.pptx&wdLOR=c9C511CC6-140B-473E-B3F2-B0A13047FF23&action=edit&mobileredirect=true | 02.No | 01.Yes |  | 2026-03-30 | Candice S Linnell | 01.Approved |  | TBD - Interim State Missing (Obj. Tracker) |  | 01.Deloitte | 03. NA | 01.Deloitte | 04.Low |  | 02.No |  |  |  |  | NA |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% |  |  |  |  | 0% | [35 empty] | N | 0% | [6 empty] | jenoronha@deloitte.com | 2026-03-30 00:03 | sdeolalikar@deloitte.com | 2026-03-31 08:24 | 2 |  | 02.MDG | DATC1744_IP | 03.Medium | 0.3 | 0.435 | 1744 | INT-CR1811 | R3 ITC2 | R3 ITC2 | [49 empty] | 0 |  | 3461 | [11 empty] | N | 09A. Master Data | [6 empty] | Approved Exception (ITC2) |  | N/A | [12 empty] | No | [5 empty] | Not Dispositioned

## Comments
Row 3 | 17/12/2024 :- Today we have discussed with AT commodity, they requested some correction in logic, we are going to update and send for approval by today EOD | Mohit Chawla | 12/17/24 3:22 AM
Row 4 | 17/12/2024 :- Today we have discussed with AT commodity, they requested some correction in logic, we are going to update and send for approval by today EOD | Mohit Chawla | 12/17/24 3:22 AM
Row 11 | 25/7 - Reminder sent to Jose to mark this as 100% | Mohit Chawla | 07/25/25 3:21 AM
Row 11 | @anantjoshi@deloitte.com : Can we get the latest % updated for FUT and Build for manual objects. the current status is throwing off the burnups. | Prasanna Srikantachar | 06/12/25 7:48 AM
Row 12 | 25/7 - Reminder sent to Jose to mark this as 100% | Mohit Chawla | 07/25/25 3:21 AM
Row 12 | @anantjoshi@deloitte.com : Can we get the latest % updated for FUT and Build for manual objects. the current status is throwing off the burnups. | Prasanna Srikantachar | 06/12/25 7:49 AM
Row 12 | CR for cancellation : INT-CR0446 | Pranay Garoo | 04/08/25 5:00 AM
Row 13 | 25/7 - Reminder sent to Jose to mark this as 100% | Mohit Chawla | 07/25/25 3:21 AM
Row 13 | @anantjoshi@deloitte.com : Can we get the latest % updated for FUT and Build for manual objects. the current status is throwing off the burnups. | Prasanna Srikantachar | 06/12/25 7:48 AM
Row 13 | CR for cancellation : INT-CR0446 | Pranay Garoo | 04/08/25 5:00 AM
Row 14 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:13 PM
Row 33 | Mehak: Boundary Apps are not ready. FUT dates to be adjusted. | Dipti Krishan | 08/08/25 9:40 AM
Row 45 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:21 PM
Row 46 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:21 PM
Row 47 | Object handled through Ariba | Jeson Noronha | 03/26/25 3:23 AM
Row 47 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:25 PM
Row 48 | Object handled through Ariba | Jeson Noronha | 03/26/25 3:23 AM
Row 48 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:25 PM
Row 49 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:25 PM
Row 50 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:25 PM
Row 51 | Sudeepti Nareddy Marking approved based on email from GPO.… More 11/01/24 | Arpit Sharma | 11/20/24 4:47 AM
Row 53 | We need to replan this FUT in Sprint 17 as development is still in progress. In forecasted plan we included this FUT in Sprint 17. | Sugandh Gupta | 07/25/25 3:38 AM
Row 54 | We need to replan this FUT in Sprint 17 as development is still in progress. In forecasted plan we included this FUT in Sprint 17. | Sugandh Gupta | 07/25/25 3:38 AM
Row 55 | Sudeepti Nareddy Marking approved based on email from GPO.… More 11/01/24 | Arpit Sharma | 11/20/24 4:46 AM
Row 67 | EP team planned S4 FUT in Sprint 16. | Sugandh Gupta | 07/25/25 3:36 AM
Row 67 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:29 PM
Row 67 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:17 PM
Row 68 | EP team planned S4 FUT in Sprint 16. | Sugandh Gupta | 07/25/25 3:37 AM
Row 68 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:29 PM
Row 68 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:17 PM
Row 69 | EP team planned S4 FUT in Sprint 16. | Sugandh Gupta | 07/25/25 3:36 AM
Row 69 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:30 PM
Row 69 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:17 PM
Row 70 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:29 PM
Row 70 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:16 PM
Row 71 | Initially for sending the Transactions (Invoices) from IP and IF system to Illumis, we created PTPI0685_IP and PTPI0685_IF. But right place for this development is CFIN system. PTP- EP team want to rename one existing object into CFIN object and the other one to be cancelled. Functionality and requirement from business standpoint remain the same. So team planned CFIN FS approval in Sprint 16. We will plan FUT in Sprint 18 after development. | Sugandh Gupta | 07/25/25 3:35 AM
Row 71 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:30 PM
Row 71 | Marking approved based on email from GPO. https://intel.sharepoint.com/:f:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/11.%20Technology/RICEFW/GPO%20Approval?csf=1&web=1&e=sbGMIN | Sudeepti Nareddy | 10/31/24 2:15 PM
Row 79 | Object renamed to PTPE0473 PTPE0473_IF - Descoped | Jeson Noronha | 05/23/25 4:16 AM
Row 80 | PTPI0470_IP and PTPI0470_IF descoped as per CR INT-CR0975 | Jeson Noronha | 08/07/25 2:31 AM
Row 80 | Object renamed from PTPI0470_CFIN to PTPI0470 | Jeson Noronha | 08/07/25 2:30 AM
Row 81 | FSD is drafted and review is completed with business. We have two open comments from business, team is working for these open comments. | Sugandh Gupta | 12/16/24 11:56 AM
Row 82 | FSD is drafted and review is completed with business. We have two open comments from business, team is working for these open comments. | Sugandh Gupta | 12/16/24 11:56 AM
Row 84 | We need to replan this FUT in Sprint 18 as development is still in progress. In forecasted plan we included this FUT in Sprint 18. We need ReadSoft for performing this FUT. | Sugandh Gupta | 07/25/25 3:39 AM
Row 84 | FSD is drafted and one review is completed with business. We have open comments from business for technical details, team is working for these open comments. | Sugandh Gupta | 12/16/24 11:58 AM
Row 85 | We need to replan this FUT in Sprint 18 as development is still in progress. In forecasted plan we included this FUT in Sprint 18. We need ReadSoft for performing this FUT. | Sugandh Gupta | 07/25/25 3:39 AM
Row 85 | FSD is drafted and one review is completed with business. We have open comments from business for technical details, team is working for these open comments. | Sugandh Gupta | 12/16/24 11:58 AM
Row 88 | 8/11 - Will check with Jose to mark it as 100% | Mohit Chawla | 08/11/25 1:35 AM
Row 88 | 25/7 - Checking with Sean on the UOM issue ETA 6/8 -Wed | Mohit Chawla | 07/25/25 3:18 AM
Row 88 | Change description to "Get material master details from IF to CWB" | Sagar Deolalikar | 07/30/24 10:13 AM
Row 91 | EP team planned S4 FUT in Sprint 16. | Sugandh Gupta | 07/25/25 3:36 AM
Row 91 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:25 PM
Row 92 | EP team planned S4 FUT in Sprint 16. | Sugandh Gupta | 07/25/25 3:36 AM
Row 92 | 3/14/2025 - had a discussion with the FS owning team and need to finish HLTA design after closing several opens with Illumis to be able to engage with Intel IT and configure the MW Build for SFT. | Jeremy M Morrissey | 03/14/25 2:25 PM
Row 99 | @sameer.m.shaikh@intel.com @pooja.gopala.poojary@intel.com - please provide your approval for HLTA if everything looks good. We've got approval from BApp. | Sumit Kumar | 08/06/24 2:57 AM
Row 100 | @sameer.m.shaikh@intel.com @pooja.gopala.poojary@intel.com - please provide your approval for HLTA if everything looks good. We've got approval from BApp. | Sumit Kumar | 08/06/24 2:56 AM
Row 101 | As per Functional Email (attached) : PTPI0269_IF/IP is for Ariba attributes replication from MDG to S4, for the customizations needed will be taking forward with respect to Enhancement RICEFW(In-progress). Hence you can consider PTPI0269_IF/IP as no development required. | Jeson Noronha | 10/06/24 11:13 PM
Row 102 | As per Functional Email (attached) : PTPI0269_IF/IP is for Ariba attributes replication from MDG to S4, for the customizations needed will be taking forward with respect to Enhancement RICEFW(In-progress). Hence you can consider PTPI0269_IF/IP as no development required. | Jeson Noronha | 10/06/24 11:13 PM
Row 103 | 25/7 - This object added recently will work on dates | Mohit Chawla | 07/25/25 2:34 AM
Row 112 | 25/7 - B2B was not ready and the decision to test the E2E came later after scheduling it. | Mohit Chawla | 07/25/25 2:40 AM
Row 113 | 25/7 - B2B was not ready and the decision to test the E2E came later after scheduling it. | Mohit Chawla | 07/25/25 2:40 AM
Row 119 | @kenayak@deloitte.com FYI | Sagar Deolalikar | 06/13/24 4:04 PM
Row 119 | 5/29 MB/SW - This one is being deferred because of "unkown data source". Custom today and do not know how it will be done in future. Sean meeting with Ranju and Eric | Sagar Deolalikar | 06/13/24 3:59 PM
Row 120 | @kenayak@deloitte.com FYI | Sagar Deolalikar | 06/13/24 4:03 PM
Row 120 | Pending KDD on PIR/OA and disposition of OA custom fields. | Sagar Deolalikar | 06/13/24 4:02 PM
Row 128 | Dates revised @kenayak@deloitte.com | Sagar Deolalikar | 06/13/24 5:31 PM
Row 129 | Dates revised @kenayak@deloitte.com | Sagar Deolalikar | 06/13/24 5:32 PM
Row 136 | 17/12-2024 :- Email send to mark this as 100% to Jose. | Mohit Chawla | 12/17/24 1:25 AM
Row 136 | Dates revised @kenayak@deloitte.com | Sagar Deolalikar | 06/13/24 5:32 PM
Row 137 | 17/12-2024 :- Email send to mark this as 100% to Jose. | Mohit Chawla | 12/17/24 1:25 AM
Row 137 | Dates revised @kenayak@deloitte.com | Sagar Deolalikar | 06/13/24 5:32 PM
Row 140 | Mehak: FUT completed and submitted for approval. It will added in Sprint 17 Plan and will be marked complete. | Dipti Krishan | 08/08/25 9:32 AM
Row 140 | 25/7 - Will be taken in next sprint 17 and tracker to be updated | Mohit Chawla | 07/25/25 3:29 AM
Row 141 | @jorge.e.alpizar.jimenez@intel.com - Kindly review and approve the HLTA for PTPF0015. | Jiten Tarai | 06/02/24 9:46 PM
Row 142 | @jorge.e.alpizar.jimenez@intel.com - Kindly review the HLTA and approve it . | Jiten Tarai | 06/02/24 9:07 PM
Row 145 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:13 PM
Row 170 | Object descoped as per CR - CR0903 | Jeson Noronha | 08/14/25 10:05 PM
Row 171 | Object descoped as per CR - CR0903 | Jeson Noronha | 08/14/25 10:05 PM
Row 196 | Mehak: FUT is under progress. It will be added in Sprint 17 and will be marked completed. | Dipti Krishan | 08/08/25 9:36 AM
Row 197 | Object cancelled as per CR : INT-CR0542 | Jeson Noronha | 10/06/25 10:28 PM
Row 197 | Object descoped as per CR : INT-CR0542 | Jeson Noronha | 10/06/25 10:19 PM
Row 205 | Mehak: It will planned in Sprint 18. Dates to be adjusted. | Dipti Krishan | 08/08/25 9:38 AM
Row 205 | Background approval based on Jose request | Vasanth Mohan | 12/19/24 3:22 PM
Row 206 | Mehak: It will planned in Sprint 18. Dates to be adjusted. | Dipti Krishan | 08/08/25 9:37 AM
Row 207 | Mehak - FUT is completed and approved. It will be added in Sprint 17 and will be marked as completed. | Dipti Krishan | 08/08/25 9:31 AM
Row 218 | Design is changed from business and test data is provided in Sprint 16. We need to replan this FUT in Sprint 17 as development is still in progress. In forecasted plan we included this FUT in Sprint 17. | Sugandh Gupta | 07/25/25 3:41 AM
Row 225 | 8/11 - Sent for approval waiting for business review | Mohit Chawla | 08/11/25 1:31 AM
Row 225 | 25/7 - Defect and CR raised to fix layout changes. | Mohit Chawla | 07/25/25 2:49 AM
Row 226 | 8/11 - Sent for approval waiting for business review | Mohit Chawla | 08/11/25 1:31 AM
Row 226 | '25/7 - Defect and CR raised to fix layout changes. | Mohit Chawla | 07/25/25 2:49 AM
Row 226 | 25/7 - Defect and CR raised to fix layout changes. | Mohit Chawla | 07/25/25 2:48 AM
Row 235 | 25/7 - Scheduled for closure in upcoming sprint as this is E2O and require to be close with PTPI0136 | Mohit Chawla | 07/25/25 3:19 AM
Row 236 | 25/7 - Scheduled for closure in upcoming sprint as this is E2O and require to be close with PTPI0136 | Mohit Chawla | 07/25/25 3:19 AM
Row 243 | Object descoped as per CR : INT-CR1378 | Jeson Noronha | 10/23/25 1:29 AM
Row 244 | EP team completed this FUT and reviewed with business. Originally this enhancement is done in FBL1N report but business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. | Sugandh Gupta | 07/25/25 3:45 AM
Row 245 | EP team completed this FUT and reviewed with business. Originally this enhancement is done in FBL1N report but business want to extend this object in FBL1H report also. EP team is working on CR for extending this object. | Sugandh Gupta | 07/25/25 3:45 AM
Row 248 | This FUT is in progress. ETA for this 8/1. | Sugandh Gupta | 07/25/25 3:47 AM
Row 249 | This FUT is in progress. ETA for this 8/1. | Sugandh Gupta | 07/25/25 3:47 AM
Row 252 | Team completed FUT and reviewed with business. But business raised some design change and EP team completed POC on design change and prepared one RICEFW for supporting this enhancement | Sugandh Gupta | 07/25/25 3:43 AM
Row 253 | Team completed FUT and reviewed with business. But business raised some design change and EP team completed POC on design change and prepared one RICEFW for supporting this enhancement. | Sugandh Gupta | 07/25/25 3:43 AM
Row 254 | 8/11 - Defect is there working with tech | Mohit Chawla | 08/11/25 1:35 AM
Row 254 | 25/7 - PR FUT walkthrough given today small issues, defect to be raised to tech | Mohit Chawla | 07/25/25 2:47 AM
Row 254 | 17/12/2024 :- Discussion with business in today call at 8 IST | Mohit Chawla | 12/17/24 3:13 AM
Row 255 | 8/11 - Defect is there working with tech | Mohit Chawla | 08/11/25 1:35 AM
Row 255 | 25/7 - PR FUT walkthrough given today small issues, defect to be raised to tech | Mohit Chawla | 07/25/25 2:47 AM
Row 255 | 17/12/2024 :- Discussion with business in today call at 8 IST | Mohit Chawla | 12/17/24 3:13 AM
Row 256 | 25/7 - Sent reminder to Jose to mark as 100% | Mohit Chawla | 07/25/25 3:08 AM
Row 256 | 17/12/2024 :- Discussion with business in today call at 8 IST | Mohit Chawla | 12/17/24 3:13 AM
Row 257 | 25/7 - Sent reminder to Jose to mark as 100% | Mohit Chawla | 07/25/25 3:08 AM
Row 257 | 17/12/2024 :- Discussion with business in today call at 8 IST | Mohit Chawla | 12/17/24 3:13 AM
Row 258 | @jorge.e.alpizar.jimenez@intel.com - Kindly review and approve the HLTA for PTPE0091. | Jiten Tarai | 06/02/24 9:48 PM
Row 259 | @jorge.e.alpizar.jimenez@intel.com - Kindly review and approve the HLTA for PTPE0090. | Jiten Tarai | 06/02/24 9:48 PM
Row 262 | Object renamed from PTPC0633_IF to PTPC0633 As IP version is descoped | Jeson Noronha | 04/30/25 12:56 AM
Row 267 | 8/11- checking internally on some design items and working with BODS | Mohit Chawla | 08/11/25 1:34 AM
Row 267 | 25/7 - Send for approval - Waiting for Sean approval | Mohit Chawla | 07/25/25 2:48 AM
Row 268 | 25/7 - Send for approval to Intel-Waiting Sean approval | Mohit Chawla | 07/25/25 2:37 AM
Row 271 | 8/11- this is big and lot of cases to be tested -WIP | Mohit Chawla | 08/11/25 1:34 AM
Row 271 | 25/7 - This is scheduled for sprint 16 approval team is working on it. | Mohit Chawla | 07/25/25 2:37 AM
Row 272 | 8/11- this is big and lot of cases to be tested -WIP | Mohit Chawla | 08/11/25 1:33 AM
Row 272 | 25/7 - This is scheduled for sprint 16 approval team is working on it. | Mohit Chawla | 07/25/25 2:37 AM
Row 273 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:55 PM
Row 274 | As per discussion with Matthew Fisher, there only needs to be 1 object (CFIN) for this workflow hence removing _IF and _IP and renaming it to OTCW0638 | Jonah Sanders | 01/31/25 12:41 PM
Row 281 | Approved as Email received from Sarah on 08/14 | Jeson Noronha | 08/13/25 8:57 PM
Row 282 | GPO Approved as per email confirmation by Sarah | Jeson Noronha | 07/31/25 10:04 PM
Row 284 | Approved backend based on sarah miller email - 05/28 | Vasanth Mohan | 05/28/25 8:25 PM
Row 284 | Piyush (pipatil@deloitte.com) confirmed that OTCI1423 is not relevant for B-App but it is relevant for External partner - Expeditor Broker | Meenal Goel | 05/06/25 6:41 AM
Row 292 | 12258 (MuleSoft) is not a Boundary App. Received confirmation from Yashu to change Boundary App Involved? to No. | Meenal Goel | 01/27/25 8:55 PM
Row 293 | 12258 (MuleSoft) is not a Boundary App. Received confirmation from Yashu to change Boundary App Involved? to No. | Meenal Goel | 01/27/25 8:55 PM
Row 295 | NP4/28: @nikitam5@deloitte.com this object has got the approval from Intel and is good to be taken up for the Build | Naman Parti | 04/28/25 2:14 AM
Row 297 | @nikitam5@deloitte.com FSD has approved, Kindly proceed with tech deliverables. | Mathew Abraham | 05/15/25 11:32 PM
Row 298 | MW is BODS- to be taken care by Deloitte MW Team | Danish Abdali | 08/21/25 3:29 AM
Row 301 | Re-development of this object is currently being done by the development team. ETA given them is July End. Defect - 1170, 1239 | Ayan Kundu | 07/02/25 8:57 PM
Row 314 | MuleSoft team is working on the testing for BAPP connection. Once Connection set we will proceed with the BAPP testing and documentation. | Rekha Bhat | 09/28/25 11:43 PM
Row 315 | 8/14 - Intel IT review is ongoing and feedback awaited. BAPP Validation is already in progress and opens addressed. CR INT-Build-CR0634 raised for the changes identified so far. | Eina Gupta | 08/14/25 1:49 AM
Row 316 | MuleSoft team is working on the testing for BAPP connection. Once Connection set we will proceed with the BAPP testing and documentation. Defect 3358 - Issue with the creation of return order in M02/M03 Return reason, error "updating of custom fields" ETA - 09/29 | Rekha Bhat | 09/28/25 11:46 PM
Row 319 | FS In Progress | Pranjal Yadav | 07/11/24 11:29 PM
Row 321 | @ravigupta@deloitte.com @nikitam5@deloitte.com @arijbiswas@deloitte.com FS has been approved. Attaching the same | Priya Sharadchandra Shyamkul | 07/25/24 9:52 PM
Row 322 | @ravigupta@deloitte.com @nikitam5@deloitte.com @arijbiswas@deloitte.com FS has been approved. Attaching the same. | Sashank S | 07/21/24 10:50 PM
Row 324 | Approval email link | Naman Parti | 06/25/24 12:47 AM
Row 324 | @ravigupta@deloitte.com @jenoronha@deloitte.com FSD for this RICEFW is approved and is ready for the build | Naman Parti | 06/25/24 12:40 AM
Row 327 | Approval email link | Naman Parti | 06/25/24 12:48 AM
Row 327 | @ravigupta@deloitte.com @jenoronha@deloitte.com FSD for this RICEFW is approved and is ready for the build | Naman Parti | 06/25/24 12:40 AM
Row 327 | 24/6: Intel has requested for AIF demo before they approve the FSD and SAP will be conducting demo for AIF. Awaiting SAPs schedule confirmation on the demo | Naman Parti | 06/24/24 12:01 AM
Row 336 | As per discussion with Matthew F, only 1 object (CFIN) is required. Hence deleting the _IP/IF and removing the other row. | Jonah Sanders | 01/31/25 12:42 PM
Row 340 | @ravigupta@deloitte.com FS has been approved | Sashank S | 06/11/24 9:37 PM
Row 345 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/OTCE1668%20-%203143%20-%20Enhancement%20to%20transfer%20Customs%20value%20from%20S4%20to%20GTS%20for%20Sales%20orders%20and%20delivery%20documents.msg?csf=1&web=1&e=jMy3kZ | Sagar Deolalikar | 11/14/25 10:49 AM
Row 345 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 346 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/OTCE1668%20-%203143%20-%20Enhancement%20to%20transfer%20Customs%20value%20from%20S4%20to%20GTS%20for%20Sales%20orders%20and%20delivery%20documents.msg?csf=1&web=1&e=jMy3kZ | Sagar Deolalikar | 11/14/25 10:49 AM
Row 346 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 352 | Approved as Email received from Sarah on 08/14 | Jeson Noronha | 08/13/25 8:57 PM
Row 353 | RICEF Type changed from Conversions to Enhancement. aligned by Data and Tech team. | Jeson Noronha | 09/04/25 10:50 PM
Row 354 | RICEF Type changed from Conversions to Enhancement. aligned by Data and Tech team. | Jeson Noronha | 09/04/25 10:50 PM
Row 355 | RICEFW Correction from OTCE1422 to OTCE1505 | Jeson Noronha | 06/12/25 4:33 AM
Row 355 | Approved backend based on sarah miller email - 05/28 | Vasanth Mohan | 05/28/25 8:25 PM
Row 356 | Approved backend based on sarah miller email - 05/28 | Vasanth Mohan | 05/28/25 8:25 PM
Row 357 | Approved backend based on sarah miller email - 05/28 | Vasanth Mohan | 05/28/25 8:25 PM
Row 362 | @nikitam5@deloitte.com FSD has approved, Kindly proceed with tech deliverables. | Mathew Abraham | 05/15/25 11:33 PM
Row 371 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 372 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 373 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 374 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 375 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 376 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 377 | Approved as per email at this link https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/OSC/OSC%20Deck%20Archive/RE%20Automation%20RICEFW%20objects%20-%20Path%20forward.msg?csf=1&web=1&e=ACE8f4 | Sagar Deolalikar | 02/27/25 11:57 AM
Row 403 | 8/14 - Intel IT review is ongoing and feedback awaited. BAPP Validation is already in progress and opens addressed. Business wants to test the customer specific scenarios additionally which is in progress. CR INT-Build-CR0634 raised for the changes identified so far. | Eina Gupta | 08/14/25 1:49 AM
Row 421 | @nikitam5@deloitte.com FS has been approved for OTCE0486 | Sashank S | 09/19/24 12:16 AM
Row 433 | Under GPO review & discussions. Requires more time before OSC review. OTC team will reach out when ready. | Lauren Herschberg | 05/31/24 9:04 AM
Row 434 | Under GPO review & discussions. Requires more time before OSC review. OTC team will reach out when ready. | Lauren Herschberg | 05/31/24 9:04 AM
Row 435 | FS is approved, Ready for development, @nnacode@deloitte.com @ravigupta@deloitte.com @nikitam5@deloitte.com @pgaroo@deloitte.com | Balu Praveen M. | 08/08/24 1:04 AM
Row 436 | 06/08: FS is approved, @ishaprab@deloitte.com @nikitam5@deloitte.com @ravigupta@deloitte.com @jenoronha@deloitte.com | Priya Sharadchandra Shyamkul | 08/06/24 12:47 AM
Row 436 | Under GPO review & discussions. Requires more time before OSC review. OTC team will reach out when ready. | Lauren Herschberg | 05/31/24 9:04 AM
Row 441 | 09/29: Received approval from Intel IT/Biz. Awaiting approval from Luiz. Reminder email has been sent. Following up with Luiz to get the approval. ETA for approval - 09/29 | Raghupathi Balaji R | 09/29/25 12:27 AM
Row 442 | @katprathyusha@deloitte.com : to revise TUT dates and inform Tower and PMO to have their FUT dates revised | Prasanna Srikantachar | 07/31/25 8:14 AM
Row 445 | @erica.nash.wills@intel.com : Business determined, there is no value in conversion. Need to be descoped. cc: @miranwhite@deloitte.com | Prasanna Srikantachar | 05/14/25 10:10 AM
Row 446 | Erica: ETA for FUT completion is 11/26. | Prasanna Srikantachar | 11/20/25 10:29 AM
Row 446 | @erica.nash.wills@intel.com : Business determined, there is no value in conversion. Need to be descoped. cc: @miranwhite@deloitte.com | Prasanna Srikantachar | 05/14/25 10:10 AM
Row 448 | @luis.a.garza@intel.com : Per Akshay, it's only your approval that is pending to close the object's FUT. cc: @shawn.mccarthy@intel.com | Prasanna Srikantachar | 12/15/25 7:15 AM
Row 448 | @katprathyusha@deloitte.com : to revise TUT dates and inform Tower and PMO to have their FUT dates revised | Prasanna Srikantachar | 07/31/25 8:14 AM
Row 455 | @nikhatun@deloitte.com : FUT is completed with few changes (removal) to current program, Need some modifications to remove fields from extraction, transformation and recon reports. cc: @katprathyusha@deloitte.com @vjillela@deloitte.com @mfarook@deloitte.com | Prasanna Srikantachar | 12/15/25 7:11 AM
Row 456 | Received GPO approval over email | Jeson Noronha | 07/29/25 6:22 AM
Row 471 | Should be done. | Virginia Chan | 11/20/24 1:16 PM
Row 471 | Need to work with Deloitte team for the start date | Virginia Chan | 11/20/24 1:15 PM
Row 480 | Object was not descoped. | Jeson Noronha | 05/06/25 12:49 AM
Row 480 | Object Descoped : INT-CR0448 Chronology of events: In the initial design and discussion phase, the decision was made to develop the object under TM, and the resulting object was created. However, during discussions with the LE team, it was confirmed that the object is already accounted for under LE with four separate Intake forms. As a result, there is no need for this object in the IP under the TM sub-tower, leading to the cancellation of the object. TM will assist the LE team for any TM related mapping and FUT support. LE team’s objects. for reference are below: LOGR1173 – 2DN Outbound Manifest report LOGR1172 – 2DN Inbound Manifest report LOGR1236 – 2DN Outbound Escort report LOGR1252 – 2DN Inbound Escort report | Jeson Noronha | 04/17/25 3:26 AM
Row 481 | Object was not descoped. | Jeson Noronha | 05/06/25 12:49 AM
Row 481 | Object Descoped : INT-CR0448 Chronology of events: In the initial design and discussion phase, the decision was made to develop the object under TM, and the resulting object was created. However, during discussions with the LE team, it was confirmed that the object is already accounted for under LE with four separate Intake forms. As a result, there is no need for this object in the IP under the TM sub-tower, leading to the cancellation of the object. TM will assist the LE team for any TM related mapping and FUT support. LE team’s objects. for reference are below: LOGR1173 – 2DN Outbound Manifest report LOGR1172 – 2DN Inbound Manifest report LOGR1236 – 2DN Outbound Escort report LOGR1252 – 2DN Inbound Escort report | Jeson Noronha | 04/17/25 3:26 AM
Row 484 | Object was not descoped. | Jeson Noronha | 05/06/25 12:49 AM
Row 484 | Object Descoped : INT-CR0448 Chronology of events: In the initial design and discussion phase, the decision was made to develop the object under TM, and the resulting object was created. However, during discussions with the LE team, it was confirmed that the object is already accounted for under LE with four separate Intake forms. As a result, there is no need for this object in the IP under the TM sub-tower, leading to the cancellation of the object. TM will assist the LE team for any TM related mapping and FUT support. LE team’s objects. for reference are below: LOGR1173 – 2DN Outbound Manifest report LOGR1172 – 2DN Inbound Manifest report LOGR1236 – 2DN Outbound Escort report LOGR1252 – 2DN Inbound Escort report | Jeson Noronha | 04/17/25 3:26 AM
Row 485 | Object was not descoped. | Jeson Noronha | 05/06/25 12:49 AM
Row 485 | Object Descoped : INT-CR0448 Chronology of events: In the initial design and discussion phase, the decision was made to develop the object under TM, and the resulting object was created. However, during discussions with the LE team, it was confirmed that the object is already accounted for under LE with four separate Intake forms. As a result, there is no need for this object in the IP under the TM sub-tower, leading to the cancellation of the object. TM will assist the LE team for any TM related mapping and FUT support. LE team’s objects. for reference are below: LOGR1173 – 2DN Outbound Manifest report LOGR1172 – 2DN Inbound Manifest report LOGR1236 – 2DN Outbound Escort report LOGR1252 – 2DN Inbound Escort report | Jeson Noronha | 04/17/25 3:26 AM
Row 510 | PMO: Can we update the WIINGS/Federal Tag with "WIINGS" for this object? This is based on Logistics tagging of source system to be WIINGS in Build conversion tracker cc: @miranwhite@deloitte.com | Prasanna Srikantachar | 04/09/25 7:28 AM
Row 512 | PMO: Can we update the WIINGS/Federal Tag with "WIINGS" for this object? This is based on Logistics tagging of source system to be WIINGS in Build conversion tracker cc: @miranwhite@deloitte.com | Prasanna Srikantachar | 04/09/25 7:28 AM
Row 519 | Development System : MuleSoft S4 is not involved in this Interface | Jeson Noronha | 01/06/26 7:06 AM
Row 520 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:14 PM
Row 541 | As per Tower request ( Surendra, Julury). Object type changed from Enhancement to Interface | Jeson Noronha | 05/13/25 4:09 AM
Row 542 | As per the FDS requirement , LOGI0253_IP and LOGI0253_IF are not same objects. Hence LOGI0253_IF is now rebranded to LOGI1309 | Jeson Noronha | 03/04/25 9:45 AM
Row 542 | 09-09-2024- Completed Approved, Merge with LOGI0250 | Vaibhav G Gupta | 09/09/24 2:22 AM
Row 542 | 09-09-2024- Completed and approved by intel on 03-09-2024 | Vaibhav G Gupta | 09/09/24 2:21 AM
Row 542 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Shashank Kale | 08/30/24 4:07 AM
Row 542 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Ruby Singh | 08/28/24 4:10 AM
Row 542 | RAID # 1917 E2E process flow is not finalized , hence FS has to be updated based on E2E flow once confirmed | Aswini S G | 08/20/24 12:55 AM
Row 545 | Action on Shashank to align with Chuen Yang if "ABUS ECD Webservices" should be associated with the interface or not | Meenal Goel | 07/16/25 2:36 AM
Row 551 | MW comment : Already Existing Proxy with BApp (EOL) (No New development required here , need to update object tracker) | Jeson Noronha | 06/26/25 10:03 PM
Row 552 | MW Comment : Already Existing Proxy with BApp (EOL) (No New development required here , need to update object tracker) | Jeson Noronha | 06/26/25 10:03 PM
Row 553 | Salesforce To S/4 integrations are previously developed by Intel MW Team , therefore these integration ownership should belong to Intel | Danish Abdali | 09/16/25 12:38 AM
Row 553 | The updated approach involves creating the API object in SAP EWM and exposing the endpoint for Salesforce to consume hence changing the Middleware team from Intel to Deloitte. | Danish Abdali | 08/19/25 5:35 AM
Row 568 | 02/19: FS to be sent for Intel approval on 19th Feb | Shashank Kale | 02/19/25 2:47 AM
Row 573 | Please update the WIINGS/Federal Tag by removing "WIINGS" for this object | Jim Despain | 06/26/25 10:35 AM
Row 573 | Will you please remove the WIINGS tag value within the WIINGS/Federal Tag column for this object? | Jim Despain | 06/12/25 10:35 AM
Row 574 | Sent for approval on 8/7 Under review with OES4 and Wiings team. | Karthikeyan P P | 08/11/25 1:41 AM
Row 574 | As this is the first FUT for PIP in IF system there was issues with RFC destination setups and Partner profile maintenance. Now the issues have been resolved checking with Intel B2B team on the scenarios | Karthikeyan P P | 07/25/25 4:37 AM
Row 576 | 02/19: Approved | Shashank Kale | 02/19/25 2:51 AM
Row 578 | 02/25: Pending Intel Review. FS submitted for Intel approval | Shashank Kale | 02/25/25 3:05 AM
Row 578 | 02/19: Under draft. FS submission ETA: 02/25 | Shashank Kale | 02/19/25 2:51 AM
Row 582 | Sahana and Shashank confirmed No Boundary App Involved for this interface | Meenal Goel | 03/07/25 12:54 AM
Row 582 | The is an Interface and not an Enhancement. changing the RICEF ID | Jeson Noronha | 03/06/25 12:48 AM
Row 586 | MW Comment : As per Functional Middleware is not applicable (Need to update object tracker) | Jeson Noronha | 06/26/25 10:05 PM
Row 587 | MW Comment : As per Functional Middleware is not applicable (Need to update object tracker) | Jeson Noronha | 06/26/25 10:05 PM
Row 590 | MW comment : Already Existing Proxy with BApp (NDA/ILPA) (No New development required here, need to update object tracker) | Jeson Noronha | 06/26/25 10:05 PM
Row 591 | MW comment : Already Existing Proxy with BApp (NDA/ILPA) (No New development required here, need to update object tracker) | Jeson Noronha | 06/26/25 10:05 PM
Row 592 | Object renamed : LOGI0834_IP to LOGI0834 | Jeson Noronha | 03/26/25 6:10 AM
Row 592 | As LOGI0834_IF is now cancelled : INT-CR0424 ( Approved ). | Jeson Noronha | 03/26/25 6:10 AM
Row 593 | 02/19: Review session planned on Feb 21st. B2B POC - Saufi to return to office on 21st. | Shashank Kale | 02/19/25 2:46 AM
Row 594 | 02/19: Review session planned on 19th Feb. | Shashank Kale | 02/19/25 2:43 AM
Row 597 | 02/21: On Track | Shashank Kale | 02/19/25 2:38 AM
Row 598 | 02/21: On Track | Shashank Kale | 02/19/25 2:38 AM
Row 599 | Marking approved based on Randy's email | Lauren Herschberg | 10/04/24 10:57 AM
Row 600 | Marking approved based on Randy's email | Lauren Herschberg | 10/04/24 10:56 AM
Row 601 | Marking approved based on Randy's email | Lauren Herschberg | 10/04/24 10:57 AM
Row 602 | We have documented the results of the working events in the FUT and submitted them for internal review. 8/26 Tomorrow, we will send this document to the Intel team for conditional approval. Summary of Issues: 1-OSS Note 885209: Issue with capturing the ETA date. 2-Event Reason Code 936611: Not updating in the Shipment APP. 3-OSS Note 877903: Mapping-related issue.- Resolved 4-OSS – Standard delay event: Not functioning as expected. | Aman Tripathi | 08/25/25 5:04 AM
Row 602 | Reason for Change (Middleware-NA) From Lavaughn: Apigee is our API Management tool and our Guidance to use Apigee for any API based communication. In this case there can be an exception based on: OpenText using a Secure Gateway to pass the APIs to GTT. The GTT API will be used by OpenText only. | Danish Abdali | 07/17/25 12:41 AM
Row 602 | FUT for LOGI0630 is not yet started because this Interface is dependent on GXS team to develop the interface (GXS to GTT). We will start the FUT next week 15th July.. | Shameek Dhir | 07/10/25 10:47 AM
Row 603 | We have documented the results of the working events in the FUT and submitted them for internal review. 8/26 Tomorrow, we will send this document to the Intel team for conditional approval. Summary of Issues: 1-OSS Note 885209: Issue with capturing the ETA date. 2-Event Reason Code 936611: Not updating in the Shipment APP. 3-OSS Note 877903: Mapping-related issue.- Resolved 4-OSS – Standard delay event: Not functioning as expected. | Aman Tripathi | 08/25/25 5:05 AM
Row 603 | Reason for Change (Middleware-NA) From Lavaughn: Apigee is our API Management tool and our Guidance to use Apigee for any API based communication. In this case there can be an exception based on: OpenText using a Secure Gateway to pass the APIs to GTT. The GTT API will be used by OpenText only. | Danish Abdali | 07/17/25 12:42 AM
Row 603 | FUT for LOGI0630 is not yet started because this Interface is dependent on GXS team to develop the interface (GXS to GTT). We will start the FUT next week 15th July.. | Shameek Dhir | 07/10/25 10:47 AM
Row 605 | FUT will be taken up in Future Sprints | Ketul Ashokkumar Pitroda | 07/25/25 4:04 AM
Row 606 | 02/19: First round of review completed. Additional points are being addressed in FS. On Track to close on 21st. | Shashank Kale | 02/19/25 2:43 AM
Row 607 | FUT will be taken up in Future Sprints | Ketul Ashokkumar Pitroda | 07/25/25 4:04 AM
Row 608 | 02/21: On Track | Shashank Kale | 02/19/25 2:38 AM
Row 609 | 02/21: On Track | Shashank Kale | 02/19/25 2:37 AM
Row 610 | 02/21: On Track | Shashank Kale | 02/19/25 2:38 AM
Row 614 | not started | Vaibhav G Gupta | 09/09/24 2:26 AM
Row 614 | not started | Vaibhav G Gupta | 09/09/24 2:26 AM
Row 614 | not started | Vaibhav G Gupta | 09/09/24 2:26 AM
Row 615 | 09/02: Open Points raised by business are resolved and sent for approval on 08/30 to Cindy MCGuire and Saufi Bukhari. | Ketul Ashokkumar Pitroda | 09/02/24 2:17 AM
Row 615 | 08/16: Sent to Intel Business & IT for approval. | Ketul Ashokkumar Pitroda | 08/16/24 7:29 AM
Row 615 | 08/16: FS Draft in progress. First draft to be shared with Intel Business and IT on 08/16 | Shashank Kale | 08/16/24 4:15 AM
Row 616 | 08/27: Shared the FSD with Intel for review and approval. | Shashank Shetty K | 08/27/24 1:09 AM
Row 616 | 08/22: Plant mapping and validation based on Plant and Delivery document is updated in the FS and Mapping Sheet. The updated design and logic will be shared with Intel on 08/23 | Shashank Kale | 08/22/24 4:29 AM
Row 616 | 08/20: Internal tech review in progress. Minor updates required in the mapping sheet. | Shashank Kale | 08/20/24 4:11 AM
Row 616 | 08/16: FS Draft in progress. Review with Mulesoft team in progress. To be shared by 08/19 with Intel Business and IT. | Shashank Kale | 08/16/24 4:35 AM
Row 618 | 09-09-2024-blocked E2E team is checking design, RAID is already raised 1917 | Vaibhav G Gupta | 09/09/24 2:21 AM
Row 618 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Shashank Kale | 08/30/24 4:07 AM
Row 618 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Ruby Singh | 08/28/24 4:10 AM
Row 618 | E2E process flow is not finalized , hence FS has to be updated based on E2E flow once confirmed RAID is already raised 1917 | Aswini S G | 08/20/24 12:51 AM
Row 619 | 09-09-2024- Completed and approved by intel on 03-09-2024 | Vaibhav G Gupta | 09/09/24 2:21 AM
Row 619 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Shashank Kale | 08/30/24 4:06 AM
Row 619 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Ruby Singh | 08/28/24 4:10 AM
Row 619 | RAID # 1917 E2E process flow is not finalized , hence FS has to be updated based on E2E flow once confirmed | Aswini S G | 08/20/24 12:54 AM
Row 620 | 09-09-2024- Completed Approved, Merge with LOGI0250 | Vaibhav G Gupta | 09/09/24 2:22 AM
Row 621 | 09-09-2024-Work in progress | Vaibhav G Gupta | 09/09/24 2:24 AM
Row 622 | Discussion in progress in F2F. Updates are expected by 09/06 @siddesai@deloitte.com to provide an update by 09/06. | Shashank Kale | 09/05/24 4:03 AM
Row 623 | 09-09-2024- not started | Vaibhav G Gupta | 09/09/24 2:31 AM
Row 623 | Discussion in progress in F2F. Updates are expected by 09/06 @siddesai@deloitte.com to provide an update by 09/06. | Shashank Kale | 09/05/24 4:04 AM
Row 627 | Mahesh shared the revised FS End dates (see screenshot) | Ridhi Shri | 12/13/24 7:20 AM
Row 627 | 09-09-2024- not started | Vaibhav G Gupta | 09/09/24 2:25 AM
Row 628 | 09-09-2024- not started | Vaibhav G Gupta | 09/09/24 2:29 AM
Row 629 | 09-09-2024-not started | Vaibhav G Gupta | 09/09/24 2:32 AM
Row 630 | LOGI0161 - Cancelled. Email attached for reference. | Jeson Noronha | 10/22/24 10:12 PM
Row 630 | 09-09-2024-Work in progress | Vaibhav G Gupta | 09/09/24 2:29 AM
Row 631 | 09-09-2024- not started | Vaibhav G Gupta | 09/09/24 2:28 AM
Row 632 | 09-09-2024- Completed Approved by intel | Vaibhav G Gupta | 09/09/24 2:27 AM
Row 633 | 09-09-2024- Completed Approved by intel | Vaibhav G Gupta | 09/09/24 2:22 AM
Row 634 | 08/30: Alignment on E2E process in progress | Shashank Kale | 08/30/24 4:06 AM
Row 634 | Alignment on E2E process in progress in the F2F meetings, FS will be progressed by that. | Ruby Singh | 08/28/24 4:10 AM
Row 634 | 08/20: Alignment on E2E process in progress. | Shashank Kale | 08/20/24 4:04 AM
Row 634 | FTS_LE , Aditya is working on Process alignment and Mapping sheets alignment from Intel | Aswini S G | 08/20/24 12:34 AM
Row 637 | 02/19: The FS is approved. Issue with difference in nomenclature in Build Plan v/s Object Tracker | Shashank Kale | 02/19/25 2:53 AM
Row 637 | Mahesh shared the revised FS End dates (see screenshot) | Ridhi Shri | 12/13/24 7:21 AM
Row 637 | 09-09-2024 Completed Approved by intel | Vaibhav G Gupta | 09/09/24 2:25 AM
| Hi Vaibhav- can you pls explain what is open on LOGI0150_IF and LOGI0150_IP and if these are merged with another object. If yes, pls provide the object ID for the object where these are merged. Also pls get these cancelled if the above is true. | Ridhi Shri | 12/13/24 4:31 AM
Row 638 | 09-09-2024-Completed Approved, Merge with LOGI0150 | Vaibhav G Gupta | 09/09/24 2:25 AM
Row 639 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 640 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 671 | 08/16: FS dates to be re-planned after agreement with Intel Process Stewards. ISM forms to be planned after completion of ISM Fiori App FS. | Shashank Kale | 08/16/24 4:30 AM
Row 672 | 08/16 ISM Forms to be re-planned with ISM Fiori App | Shashank Kale | 08/16/24 4:41 AM
Row 673 | 08/16: FS dates to be re-planned after agreement with Intel Process Stewards. ISM forms to be planned after completion of ISM Fiori App FS. | Shashank Kale | 08/16/24 4:29 AM
Row 675 | FUT will be taken up in Future Sprints | Ketul Ashokkumar Pitroda | 07/25/25 4:03 AM
Row 675 | Updated FS will be sent out today with open pricing point | Preetikumari Shringarmani Tiwari | 08/23/24 4:58 AM
Row 675 | 08/22: Inputs were provided by Junior over email. Call is scheduled to discuss the inputs on 08/22. Logic for identification of Bailment Scenario/Bailed Materials to be discussed. | Shashank Kale | 08/22/24 4:27 AM
Row 675 | 08/20: Open items on E2E process flow. RAID# 1950 logged. Assigned to Intel Team for updates. | Shashank Kale | 08/20/24 4:08 AM
Row 675 | 08/19: Open items on E2E process flow. RAID# 1950 logged | Shashank Kale | 08/19/24 4:11 AM
Row 675 | 08/19: Pending with Intel - Junior. FS walkthrough provided on 08/14. COO and Trigger Point are open item. RAID log has been raised for COO. | Shashank Kale | 08/19/24 4:10 AM
Row 675 | 08/16: Pending with Intel - Junior. FS walkthrough provided on 08/14. COO and Trigger Point are open item. RAID log has been raised for COO. | Shashank Kale | 08/16/24 4:40 AM
Row 676 | FUT will be taken up in Future Sprints | Ketul Ashokkumar Pitroda | 07/25/25 4:03 AM
Row 676 | Object LOGF0355_IF , Renamed to LOGF0355 | Jeson Noronha | 04/01/25 11:03 PM
Row 676 | @kpitroda@deloitte.com please update status. | Ruben David Alvarez Carroz | 09/03/24 6:16 PM
Row 676 | 09/02: Conditional Sign off received from Business & Intel IT on 08/30. Development to be started. | Ketul Ashokkumar Pitroda | 09/02/24 1:17 AM
Row 676 | 8/28 : Intel business approval received, IT approval is pending. | Ruby Singh | 08/28/24 4:13 AM
Row 676 | Updated FS will be sent out today with open pricing point | Ruby Singh | 08/23/24 3:54 AM
Row 676 | 08/22: Inputs were provided by Junior over email. Call is scheduled to discuss the inputs on 08/22. Logic for identification of Bailment Scenario/Bailed Materials to be discussed. | Shashank Kale | 08/22/24 4:27 AM
Row 676 | 08/20: Open items on E2E process flow. RAID# 1950 logged. Assigned to Intel Team for updates. | Shashank Kale | 08/20/24 4:07 AM
Row 676 | 08/19: 08/19: Open items on E2E process flow. RAID# 1950 logged | Shashank Kale | 08/19/24 4:11 AM
Row 676 | 08/19: Pending with Intel - Junior. FS walkthrough provided on 08/14. COO and Trigger Point are open item. RAID log has been raised for COO. | Shashank Kale | 08/19/24 4:10 AM
Row 676 | 08/16: Pending with Intel - Junior. FS walkthrough provided on 08/14. COO and Trigger Point are open item. RAID log has been raised for COO. | Shashank Kale | 08/16/24 4:40 AM
Row 676 | 08/13: Business is having queries on E2E-01 Process Flow for trigger of Bailment process | Shashank Kale | 08/13/24 7:57 PM
Row 677 | Fixed value table, Bailment value logic pending for CD plant(Eugene working on it). Pricing logic pending for VN/MY (Business is working with OM team). RAID log 2335 created and assigned to Stacy. | Ketul Ashokkumar Pitroda | 09/24/24 5:16 AM
Row 677 | 09/20: Pricing logic pending with Intel Business and OM team. | Ketul Ashokkumar Pitroda | 09/20/24 5:10 AM
Row 677 | 09/12: Status still remains the same. Intel business (Stacy and Eugene) to align internally on Consolidation logic for CN. Pricing to be discussed next week. | Ketul Ashokkumar Pitroda | 09/12/24 3:46 AM
Row 677 | 09/09: Consolidation in CD based on MAWB to be taken up in R4/R5 as per Eugene's mail confirmation with TM. Mail sent today to Business (Eugene) to provide logic for Consolidation for CD Plant. Pricing to be discussed with Business (Stacy) and OM team on 09/11. | Ketul Ashokkumar Pitroda | 09/09/24 1:52 AM
Row 677 | Consolidation Logic received for MY and VN. Pricing logic is still open. Action on Stacy to provide the logic for Pricing. Deloitte to send the updated FS for approval once the logic is received for Pricing. For consolidation in CD, an internal Deloitte discussion is required to provide a logic for consolidated based on Master Air Way Bill Number (MAWB) as compared to the logic for HAWB. | Shashank Kale | 09/05/24 3:57 AM
Row 677 | Consolidation logic provided by business. Pricing/Ship from still open. To be discussed with business (Stacy. Eugene, Sundari) on 09/05. | Ketul Ashokkumar Pitroda | 09/03/24 7:17 PM
Row 677 | @kpitroda@deloitte.com , what's the outcome of the meeting with the business...? | Ruben David Alvarez Carroz | 09/03/24 6:15 PM
Row 677 | 09/02 Consolidation logic, pricing, ship from, seller, CCI date, GI date field are open. To be discussed with business on 09/03. | Ketul Ashokkumar Pitroda | 09/02/24 1:15 AM
Row 677 | Consolidation logic, pricing, ship from, seller, CCI date, GI date field are open. To be discussed with business on 09/03. | Ketul Ashokkumar Pitroda | 08/30/24 5:01 AM
Row 677 | 8/28: FS walkthrough scheduled for tomorrow. 2 rounds of review already happened on this. | Ruby Singh | 08/28/24 4:12 AM
Row 677 | 8/23" Call on 8/27 for walkthrough of the FS with Intel | Ruby Singh | 08/23/24 3:53 AM
Row 677 | 08/22: Discussion is scheduled with Business and IT on 08/23 for trigger point of the Form. Form to be triggered from Delivery or FO is yet to be confirmed. To be finalized by end of WW34. Intel Business - Eugene | Shashank Kale | 08/22/24 4:26 AM
Row 677 | 08/20: Discussion in progress with Business and IT on trigger point of the Form. Form to be triggered from Delivery or FO is yet to be confirmed. To be finalized by end of WW34 | Shashank Kale | 08/20/24 4:06 AM
Row 677 | 08/19: Discussion in progress with Business and IT on trigger point of the Form. Form to be triggered from Delivery or FO is yet to be confirmed. To be finalized by end of WW34 | Shashank Kale | 08/19/24 4:09 AM
Row 677 | 08/16: Discussion in progress with Business and IT on trigger point of the Form. Form to be triggered from Delivery or FO is yet to be confirmed. | Shashank Kale | 08/16/24 4:22 AM
Row 679 | 08/16 ISM Forms to be re-planned with ISM Fiori App | Shashank Kale | 08/16/24 4:41 AM
Row 681 | 08/16 ISM Forms to be re-planned with ISM Fiori App | Shashank Kale | 08/16/24 4:41 AM
Row 683 | 08/16 ISM Forms to be re-planned with ISM Fiori App | Shashank Kale | 08/16/24 4:41 AM
Row 684 | 08/19: Replanning completed. To be delivered by 09/30 | Shashank Kale | 08/19/24 4:12 AM
Row 684 | 08/16: Intel IT approval is received. Some open business points to be close with Intel. | Shashank Kale | 08/16/24 4:36 AM
Row 685 | 08/19: Replanning completed. To be delivered by 09/30 | Shashank Kale | 08/19/24 4:12 AM
Row 685 | 08/16 ISM Forms to be re-planned with ISM Fiori App | Shashank Kale | 08/16/24 4:41 AM
Row 686 | 08/29: Defect#2251 under retest, however blocked due to the upstream data dependency as we are not able to create a Sales Order with non-USD currency. | Shashank Shetty K | 08/29/25 4:32 AM
Row 686 | 08/25: Defect #2251 pending with tech team to implement currency conversion FM. ETA pending from tech team. Once the fix is implemented the scenario will be tested and resent to Intel for approval. | Shashank Shetty K | 08/25/25 1:44 AM
Row 686 | Open points during the FUT review call to be addressed. ETA 08/19 | Ketul Ashokkumar Pitroda | 08/18/25 6:58 AM
Row 686 | 08/04 - Defect 1831 open with Tech team. ETA provided 08/05 | Ketul Ashokkumar Pitroda | 08/04/25 6:44 AM
Row 686 | 08/22: FS Walkthrough call scheduled on 08/22 with Intel Team. | Shashank Kale | 08/22/24 4:28 AM
Row 686 | 08/20: FS Draft is completed. Call scheduled with Intel Business and IT on 08/22 | Shashank Kale | 08/20/24 4:16 AM
Row 686 | 08/19: FS Draft is completed. Call scheduled with Intel Business and IT on 08/22 | Shashank Kale | 08/19/24 4:13 AM
Row 686 | 08/16: FS draft is completed. Tech and Security Review in Progress. To be sent for Intel Review on 08/19. | Shashank Kale | 08/16/24 4:31 AM
Row 687 | 08/04 - FUT in progress. ETA 08/06 | Ketul Ashokkumar Pitroda | 08/04/25 6:44 AM
Row 687 | FUT will be taken up in Future Sprints | Ketul Ashokkumar Pitroda | 07/25/25 4:05 AM
Row 687 | 09/30: Bailment Pricing pending from Business. RAID log 2335 created and assigned to Stacy. Call Scheduled on 09/30 to discuss Pricing with OM team and Business. | Ketul Ashokkumar Pitroda | 09/30/24 2:51 AM
Row 687 | 09/24: Pricing pending from Business. RAID log 2335 created and assigned to Stacy. | Ketul Ashokkumar Pitroda | 09/24/24 5:14 AM
Row 687 | 09/20: FSD send for Intel Business and Intel IT Approval. | Ketul Ashokkumar Pitroda | 09/20/24 5:09 AM
Row 687 | 09/12: Scheduled call on 09/11 could not happen as Stacy from Intel and Divya from OM, had conflict. Another call will be scheduled by Eugene next week to discuss on the same. | Ketul Ashokkumar Pitroda | 09/12/24 3:43 AM
Row 687 | 09/05: Pricing still remains open. Business in discussion with OM team to finalize on Pricing. Meeting scheduled on 09/11. | Ketul Ashokkumar Pitroda | 09/05/24 2:20 AM
Row 687 | 09/04: Pricing logic provided by Stacy. Consigner, sold to /bill to, for COO, pricing are still open. To be discussed with Business (Stacy, Eugene, Sundari( on 09/05. | Ketul Ashokkumar Pitroda | 09/03/24 7:14 PM
Row 687 | @kpitroda@deloitte.com , What's the outcome of the meeting with business....? | Ruben David Alvarez Carroz | 09/03/24 6:17 PM
Row 687 | 09/02 Consigner, sold to /bill to, for COO one scenario is pending to check if we need to consider intermediate or ultimate pricing (Stacy Chen has forwarded logic). To be discussed on 09/03 with Business. | Ketul Ashokkumar Pitroda | 09/02/24 1:13 AM
Row 687 | Consigner, sold to /bill to, for COO one scenario is pending to check if we need to consider intermediate or ultimate pricing (Stacy Chen has forwarded logic). To be discussed on 09/03. | Ketul Ashokkumar Pitroda | 08/30/24 4:59 AM
Row 687 | 8/28: Call tomorrow for the open points (pricing) | Ruby Singh | 08/28/24 4:12 AM
Row 687 | Change request INT-CR0048 number has been created for this. Working with PMO to replan the design and build both for PTP L3s | Ruby Singh | 08/23/24 3:51 AM
Row 687 | 08/22: Open points include Consigner, Pricing and Trade Data and COO. Action pending on Stacy Chen from Intel. | Shashank Kale | 08/22/24 4:34 AM
Row 687 | 08/20: Call scheduled on 08/21 to review the Functional Spec with Business and IT. Open Items: COO and Trade Data | Shashank Kale | 08/20/24 4:14 AM
Row 687 | 08/19: Could not be discussed in 08/19 session. Follow up call to be scheduled this week. | Shashank Kale | 08/19/24 4:09 AM
Row 687 | 08/16: Planned walkthrough on 08/16 could not be completed. Follow up call scheduled on 08/19 with Intel Business and IT. | Shashank Kale | 08/16/24 4:13 AM
Row 688 | 08/04 Defect 1918 for multiple COO issue raised to tech team. | Ketul Ashokkumar Pitroda | 08/04/25 6:44 AM
Row 688 | FUT is in progress. | Ketul Ashokkumar Pitroda | 07/25/25 4:04 AM
Row 688 | 09/30: Pricing pending from Business. RAID log 2335 created and assigned to Stacy. Call Scheduled on 09/30 to discuss Pricing with OM team and Business. | Ketul Ashokkumar Pitroda | 09/30/24 2:51 AM
Row 688 | 09/24: Pricing pending from Business. RAID log 2335 created and assigned to Stacy. | Ketul Ashokkumar Pitroda | 09/24/24 5:13 AM
Row 688 | 09/20: Pricing Logic pending with Intel Business and OM team. | Ketul Ashokkumar Pitroda | 09/20/24 5:09 AM
Row 688 | 09/12: Scheduled call on 09/11 could not happen as Stacy from Intel and Divya from OM, had conflict. Another call will be scheduled by Eugene next week to discuss on the same. | Ketul Ashokkumar Pitroda | 09/12/24 3:43 AM
Row 688 | 09/05: Pricing still remains open. Business in discussion with OM team to finalize on Pricing. Meeting scheduled on 09/11. | Ketul Ashokkumar Pitroda | 09/05/24 2:19 AM
Row 688 | 09/04: Since Stacy from Business was not available, The open points related to Sold to /bill to, consigner, pricing fields will be discussed on 09/05 call. Also pricing is still open from OM side. Business is in discussion with OM team for Export CI pricing. | Ketul Ashokkumar Pitroda | 09/03/24 7:09 PM
Row 688 | @kpitroda@deloitte.com , What's the outcome of the meeting with business...? | Ruben David Alvarez Carroz | 09/03/24 6:16 PM
Row 688 | 09/02 Sold to /bill to ,consigner, pricing fields are open. To be discussed on 09/03 with Business. | Ketul Ashokkumar Pitroda | 09/02/24 1:13 AM
Row 688 | 08/30 Sold to /bill to ,consigner, pricing fields are open. To be discussed on 09/03 | Ketul Ashokkumar Pitroda | 08/30/24 4:57 AM
Row 688 | 8/28 Call tomorrow for the open points (pricing, incoterm and payment term) | Ruby Singh | 08/28/24 4:11 AM
Row 688 | 8/23 Updated FS has been sent to Intel and Business for approval with open points for pricing field. | Ruby Singh | 08/23/24 3:51 AM
Row 688 | 08/22: Open points include Consigner, Pricing and Trade Data and COO. Action pending on Stacy Chen from Intel. | Shashank Kale | 08/22/24 4:34 AM
Row 688 | 08/20: Conditional approval received from business. Open Points: Sold To, BIll To, COO and Trade Data. Intel IT approval pending. | Shashank Kale | 08/20/24 4:13 AM
Row 688 | 08/19: Discussed on 08/19. Additional open points captured. Follow up call scheduled on 21st to close the open items. | Shashank Kale | 08/19/24 4:08 AM
Row 688 | 08/16: Pending with Intel Business. Partial Review conducted on 08/16. Call scheduled on 08/19 with Intel IT and Business to conclude the walkthrough and close open items. | Shashank Kale | 08/16/24 4:13 AM
Row 689 | 08/22: Conditional approval received from Business and IT. Open Points of COO is still pending. The activity will be marked at 100% with COO as open point. The HLTA should also be approved with COO as open point | Shashank Kale | 08/22/24 4:33 AM
Row 689 | 08/20: Condition approval received from Business. Pending IT approval. Open Field: COO | Shashank Kale | 08/20/24 4:12 AM
Row 689 | 08/19: Pending with Intel Business. Open Item - Trigger point of Form. Business to provide input in WW34 | Shashank Kale | 08/19/24 4:07 AM
Row 689 | 08/16: Pending with Intel Business - Review conducted on 08/14. Open Item - Trigger point of Form. Business to provide input in WW34 | Shashank Kale | 08/16/24 4:11 AM
Row 690 | Additional test cases for FUT tested and sent for approval. | Ketul Ashokkumar Pitroda | 07/25/25 4:35 AM
Row 690 | 08/22: Conditional approval received from Business and IT. Open Points of COO and Trade Data is still pending. The activity will be marked at 100% with COO and Trade Data as open points. The HLTA should also be approved with these open points. | Shashank Kale | 08/22/24 4:32 AM
Row 690 | 08/20: Intel Business Conditional Approval received. Open points: COO and Trade Data. Intel IT approval is pending with Sundari. | Shashank Kale | 08/20/24 4:12 AM
Row 690 | 08/19: Could not be discussed in the session on 08/19. To be discussed in the next session this week. COO and Trade Data are the open points | Shashank Kale | 08/19/24 4:06 AM
Row 690 | 08/16: Pending with Intel Business - FS Walkthrough provided to Intel. Open points are COO and Trade Data. Intel to provide feedback on the open points by 08/19, | Shashank Kale | 08/16/24 4:10 AM
Row 691 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:15 AM
Row 693 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:14 PM
Row 694 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:14 PM
Row 695 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:14 PM
Row 699 | As per email from Jeson, this object is supposed to be cancelled. | Vaidehi Avinash Gulhane | 01/14/26 6:25 AM
Row 720 | Object ID corrected from LOGE1064 to LOGE1506 due to duplicate issue | Jeson Noronha | 06/19/25 2:19 AM
Row 737 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 738 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 739 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 740 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 741 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 742 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 743 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 744 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 745 | Please update the WIINGS/Federal Tag with "WIINGS" for this object | Jim Despain | 06/26/25 10:24 AM
Row 745 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 746 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 747 | Please update the WIINGS/Federal Tag with "WIINGS" for this object | Jim Despain | 06/26/25 10:23 AM
Row 747 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 748 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 750 | As per Tower's request , This Enhancement is not applicable and the requirement has been handled in LOGI1290 | Jeson Noronha | 05/07/25 3:00 AM
Row 789 | FUT will be taken up in Future Sprints along with other 2DN objects | Ketul Ashokkumar Pitroda | 07/25/25 4:04 AM
Row 789 | As per Intake form. This Object is an Enhancement and not Interface. Corrected on 02/05/2025 | Jeson Noronha | 02/04/25 9:35 PM
Row 804 | 7/16 The business has raised concerns about receiving a warning message on the RF-sized screen. Tech team was informed to review it | Marlonx Carrillo | 07/16/25 11:58 AM
Row 837 | 02/21: On Track | Shashank Kale | 02/19/25 2:38 AM
Row 844 | FUT completed. Pending Intel Business approval. Intel IT approved. | Ketul Ashokkumar Pitroda | 07/25/25 4:40 AM
Row 873 | FUT for Objects # LOGE062 (WOM/Mysample/SFDC). As part of this FUT we tested different scenarios (Outbound, Returns and CRF) and all are working as expected. There are 2 open fields which we have not tested yet and they are dependent on other RICFEWS. – Estimated time update – Dependent on Defect # 2439. ETA for defect resolution is 1st Sep. | Aman Tripathi | 09/01/25 3:07 AM
Row 876 | @jeebawra@deloitte.ca @adshinde@deloitte.ca the FS start and end date is not maintained for this object | Ruby Singh | 11/26/24 2:30 AM
Row 877 | @jeebawra@deloitte.ca @adshinde@deloitte.ca the FS start and end date is not maintained for this object | Ruby Singh | 11/26/24 2:30 AM
Row 885 | We received Intel IT approval and waiting for Business Approval, we sent reminder email also to get the BIZ approval(09/11/). | Thirumal Thirumala Reddy | 09/12/25 1:06 AM
Row 885 | FUT for Objects # LOGE062 (WOM/Mysample/SFDC). As part of this FUT we tested different scenarios (Outbound, Returns and CRF) and all are working as expected. There are 2 open fields which we have not tested yet and they are dependent on other RICFEWS. – Estimated time update – Dependent on Defect # 2439. ETA for defect resolution is 1st Sep. | Aman Tripathi | 09/01/25 3:07 AM
Row 885 | Tech Team is working on defects # 1783 and 2107 in progress IMF scenarios # 44 fields working [44/55] CRF scenarios # 35 fields working [35/55] Return # Not working [0/55] | Thirumal Thirumala Reddy | 08/25/25 4:51 AM
Row 898 | 02/21: On Track | Shashank Kale | 02/19/25 2:37 AM
Row 904 | Status: FS draft in progress ETA 09/6 Owner: Oleg/Sunil. Next Action: FS tech review ETA 09/13 and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:23 AM
Row 905 | this objects were going to be rescheduled due dependency with CMDB FS/Design. The tasks should be marked as “ Cancelled” | Deepak Jassal | 10/24/24 3:05 AM
Row 906 | this objects were going to be rescheduled due dependency with CMDB FS/Design. The tasks should be marked as “ Cancelled” | Deepak Jassal | 10/24/24 3:05 AM
Row 906 | @ralvarezcarroz@deloitte.com should this BU be Intel Foundry? | Brianne Ramirez | 08/18/24 10:44 PM
| right should be IF, I have requested the change to fix it | Ruben David Alvarez Carroz | 08/20/24 8:52 AM
Row 907 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:07 AM
Row 908 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 6:50 AM
Row 909 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:07 AM
Row 910 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 6:50 AM
Row 911 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:07 AM
Row 912 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 6:49 AM
Row 913 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:07 AM
Row 914 | Status: FS is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 6:48 AM
Row 917 | Status: FS draft complete, Tech review is in progress. Owner: Sunil. Next Action: FS review and Approval from Intel ETA - 09/20 | Manas Ranjan Ranjan Padhi | 09/03/24 7:12 AM
Row 924 | 08/20: Intel IT approval received. Pending Intel Business Approval. | Shashank Kale | 08/20/24 4:10 AM
Row 924 | 08/16: Pending with Intel Business FS Draft shared with Intel IT and Business. Approval received from IT. | Shashank Kale | 08/16/24 4:32 AM
Row 925 | 09/03: FS is Approved. Development in progress. | Ketul Ashokkumar Pitroda | 09/03/24 5:31 AM
Row 925 | OSC Outcome - Complexity changed from Medium to Low | Jeson Noronha | 06/28/24 7:51 AM
Row 927 | 6/5: Ruben confirmed via email to present 6/14 | Lauren Herschberg | 06/05/24 9:11 PM
Row 928 | 6/5: Ruben confirmed via email to present 6/14 | Lauren Herschberg | 06/05/24 9:11 PM
Row 929 | RICEFW ID changed from FTSE0190 to LOGE0190 | Jeson Noronha | 05/17/24 6:30 AM
Row 931 | RICEFW ID changed from OTCE0066 to LOGE0066 | Jeson Noronha | 05/17/24 6:29 AM
Row 932 | ETA for CR approval 02/20 | Shashank Kale | 02/19/25 2:39 AM
Row 932 | 02/21: Awaiting CR approval | Shashank Kale | 02/19/25 2:39 AM
Row 933 | @anujkumar7@deloitte.com : working with Intel for test data. ETA to be confirmed. cc: @katprathyusha@deloitte.com @vjillela@deloitte.com | Prasanna Srikantachar | 10/08/25 9:24 AM
Row 933 | @salingam@deloitte.com @iathar@deloitte.ca : Can we please work together to have the right tower ownership and object readiness. Looks like the FS is approved and Logistics is not aligned with their ownership. cc: @againda@deloitte.com @bcoffey@deloitte.com @jboyapalli@deloitte.com @priya.kothandaraman@intel.com @nramireddi@deloitte.com @matt.katzorke@intel.com | Prasanna Srikantachar | 09/24/25 9:20 AM
Row 933 | @vipulshah@deloitte.com : to schedule FS walkthrough by 8/1 with @deborshix.dey.sarkar@intel.com . cc: @ralvarezcarroz@deloitte.com | Prasanna Srikantachar | 07/30/25 9:10 AM
Row 933 | @vipulshah@deloitte.com : To get the dates updated working with PMO for Sprint 16. FS walkthrough to be scheduled for week 7/21. cc: @vjillela@deloitte.com | Prasanna Srikantachar | 07/16/25 9:13 AM
Row 933 | @iathar@deloitte.ca / @ralvarezcarroz@deloitte.com : Can you please populate the FS dates in tracker, so that we can plan on build dates at priority. cc: @priya.kothandaraman@intel.com | Prasanna Srikantachar | 07/11/25 12:41 PM
Row 933 | GPO Approval received offline over email | Jeson Noronha | 06/16/25 9:27 PM
Row 934 | @ralvarezcarroz@deloitte.com : Can you please provide an updated or revised date for FS completion. Currently this is falling into Sprint 17 but for all Conversion FS's to be completed by end of May'25 per PMO guidelines. RAID (00958) for the same is upgraded to Medium now. cc: @priya.kothandaraman@intel.com @againda@deloitte.com @bcoffey@deloitte.com @teshih@deloitte.com @sdeolalikar@deloitte.com @jboyapalli@deloitte.com | Prasanna Srikantachar | 05/14/25 8:45 AM
Row 935 | @shikha.srivastava@intel.com / @mcarrillogonzalez@deloitte.com pls update right FUT % complete as it is submitted to Intel for FUT as presently it is around 5% | Mohammed Farook M | 12/17/25 9:18 AM
Row 937 | Marlon: FUT walkthrough is completed, Approval pending. @susan.strathman@intel.com @marloncarrillogonzalez@deloitte.com | Prasanna Srikantachar | 11/19/25 9:18 AM
Row 937 | @marloncarrillogonzalez@deloitte.com @mayankverma4@deloitte.com : Based on conv with team, the FS walkthrough is completed. please work with PMO to get the FS % updated. cc: @psowale@deloitte.com | Prasanna Srikantachar | 07/09/25 7:27 AM
Row 937 | @marloncarrillogonzalez@deloitte.com / @mayankverma4@deloitte.com : to work with PMO on FS dates revision. targeted to close either in Sprint 13 or 14. RAID # 01189 cc: @psowale@deloitte.com | Prasanna Srikantachar | 05/14/25 11:14 AM
Row 937 | PMO: Can we update the WIINGS/Federal Tag with "WIINGS" for this object? This is based on Logistics tagging of source system to be WIINGS in Build conversion tracker cc: @miranwhite@deloitte.com | Prasanna Srikantachar | 04/09/25 7:27 AM
Row 938 | @marloncarrillogonzalez@deloitte.com @mayankverma4@deloitte.com : Based on conv with team, the FS walkthrough is completed. please work with PMO to get the FS % updated. cc: @psowale@deloitte.com | Prasanna Srikantachar | 07/09/25 7:27 AM
Row 938 | Will you please add the WIINGS tag value within the WIINGS/Federal Tag column for this object? | Jim Despain | 06/12/25 10:36 AM
Row 939 | @iathar@deloitte.ca please help to update latest FUT % completion as it is presently at 2% | Mohammed Farook M | 12/17/25 9:20 AM
Row 940 | @andrew.t.austin@intel.com to provide Business FUT approval and IT FUT approvals provided | Mohammed Farook M | 01/14/26 9:11 AM
Row 940 | @iathar@deloitte.ca please help to update latest FUT % completion as it is presently at 2% | Mohammed Farook M | 12/17/25 9:20 AM
Row 942 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 949 | Working with stakeholders to understand the data alignment process between ECM, MES, and EMS to close – awaiting Intel, meeting scheduled for week of 7/28 | Sourav Batabyal | 08/01/25 3:51 AM
Row 955 | This is manual conversion object and work center data load handled by data Migration cockpit fiori app, due to this Functional specification document and development is not required. Hence no need to add TUT/TDD dates for this object. Only FUT need to perform for this object. | Akshay Ramdas Indore | 02/11/25 9:08 AM
Row 955 | This is manual conversion object and work center data load handled by data Migration cockpit Fiori app. Hence the Functional specification document and development is not required. Only FUT need to perform for this object. | Akshay Ramdas Indore | 02/11/25 9:01 AM
Row 957 | RICEFW ID correction from FTSI1668 --> FTSI1702 | Jeson Noronha | 11/14/25 4:18 AM
Row 957 | As per Tower confirmation, release changed from R3 to R4 | Jeson Noronha | 11/03/25 2:06 AM
Row 958 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:13 PM
Row 959 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:13 PM
Row 960 | As requested by FTS tower, Type changed from Enhancement to Interface | Jeson Noronha | 01/06/26 2:04 AM
Row 960 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:55 PM
Row 961 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:55 PM
Row 962 | As per Tower confirmation, release changed from R3 to R4 | Jeson Noronha | 11/03/25 2:06 AM
Row 963 | As per Tower confirmation, release changed from R3 to R4 | Jeson Noronha | 11/03/25 2:06 AM
Row 964 | As per Tower confirmation, release changed from R3 to R4 | Jeson Noronha | 11/03/25 2:06 AM
Row 965 | As per Tower confirmation, release changed from R3 to R4 | Jeson Noronha | 11/03/25 2:06 AM
Row 966 | GPO approval received over email | Jeson Noronha | 10/22/25 12:17 AM
Row 967 | GPO approval received over email | Jeson Noronha | 10/22/25 12:17 AM
Row 970 | Object approved by GPO - As per email | Jeson Noronha | 09/17/25 9:49 PM
Row 971 | Object approved by GPO - As per email | Jeson Noronha | 09/17/25 9:49 PM
Row 981 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 981 | No B-App involved - Confirmed by Venkatesh Kolleru | Meenal Goel | 05/25/25 11:08 PM
Row 982 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 982 | No B-App involved - Confirmed by Venkatesh Kolleru | Meenal Goel | 05/25/25 11:08 PM
Row 983 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 983 | B-App ID and Name are provided by Venkatesh Kolleru | Meenal Goel | 05/25/25 11:08 PM
Row 984 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 985 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 998 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1000 | @salingam@deloitte.com - These are impacting suppler collaboration so FS including approval needs to be before 03/31. karthreddy@deloitte.com | Sagar Deolalikar | 02/12/25 8:37 AM
Row 1001 | karthreddy@deloitte.com | Sagar Deolalikar | 02/12/25 8:37 AM
Row 1001 | @salingam@deloitte.com - These are impacting suppler collaboration so FS including approval needs to be before 03/31. | Sagar Deolalikar | 02/12/25 8:36 AM
Row 1002 | Marking B-App Involved = No for FTSI1021 (as the interface is b/w ECA and S4) - Received confirmation from suresh.kumar.ande@intel.com. | Meenal Goel | 03/03/25 7:01 AM
Row 1004 | MW is SAPMII- tobe done by Intel MW team | Danish Abdali | 08/21/25 3:28 AM
Row 1006 | Cannot close FUT due to dependency on completion of B-App build set for March 2026 | Sourav Batabyal | 08/01/25 3:53 AM
Row 1009 | The GPO Workflow automation was not working, the issue is fixed. I have retrigged the mail today again. We should be getting the approval by today. | Pranay Garoo | 12/11/24 2:09 AM
Row 1009 | Still it is not approved by the GPO, once after approval will update the FSD dates. | Raghavendra Nilugal | 12/10/24 10:48 PM
Row 1014 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:27 AM
Row 1017 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1018 | Mid stage transfer discussion are still in progress with intel team | Kolleru Venkatesh | 01/30/25 6:29 AM
Row 1019 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1022 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1024 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1026 | S4 fut completed | Kolleru Venkatesh | 08/06/25 6:29 AM
Row 1027 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:29 AM
Row 1029 | Discussion on the logical flow vs physical flow in progress with BY. ETA TBD. | Ramya Mathukumilli | 09/18/24 6:20 AM
Row 1030 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1030 | Boundary App Names are confirmed by FTS PoC (Venkatesh Kolleru) | Meenal Goel | 07/10/24 5:23 AM
Row 1031 | S4 FUT completed | Kolleru Venkatesh | 08/06/25 6:30 AM
Row 1032 | Tower moved from PTP to FTS. Email attached. | Jeson Noronha | 08/20/24 1:33 AM
Row 1032 | To be transferred FTS | Sagar Deolalikar | 08/17/24 5:28 AM
Row 1038 | GPO Approval updated as Approved as the object is created via a CR INT-CR1346 | Sagar Deolalikar | 11/24/25 9:33 AM
Row 1040 | GPO approval received over email | Jeson Noronha | 10/22/25 12:17 AM
Row 1060 | Approved in backend based on Hailey's email | Vasanth Mohan | 07/28/25 1:42 PM
Row 1061 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1062 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1063 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1064 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1065 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1066 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1067 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1068 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1069 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1070 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:07 AM
Row 1071 | Object Type changed from Report to Enhancement | Jeson Noronha | 07/16/25 6:30 AM
Row 1071 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1072 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1073 | Recevied Offline approval from GPO | Jeson Noronha | 06/10/25 6:08 AM
Row 1104 | Corrected the Tech complexity as per Intake form alignment | Jeson Noronha | 10/23/25 7:19 AM
Row 1107 | 10/03: Awaiting for Approval from business. | Akshay Ramdas Indore | 10/03/25 12:27 AM
Row 1107 | 09/10: New Defect created as per business observations #3146, issue fixing are in-progress by S4 Tech team. | Akshay Ramdas Indore | 09/19/25 1:10 AM
Row 1112 | The Object Type is an Enhancement It is not an Interface since both the trigger and execution are within the S4 landscape. | Jeson Noronha | 05/23/25 5:11 AM
Row 1121 | Object type changed from Conversion to Enhancement | Jeson Noronha | 07/04/25 2:12 AM
Row 1128 | This RICEFW is not in scope for data conversion through BODS. | Vijayadeep Jillela | 09/10/24 10:30 AM
Row 1129 | FUT completed | Kolleru Venkatesh | 08/06/25 6:29 AM
Row 1129 | Completed | Kolleru Venkatesh | 08/06/25 6:28 AM
Row 1130 | This RICEFW is not in scope for data conversion through BODS. | Vijayadeep Jillela | 09/10/24 10:30 AM
Row 1131 | @mfarook@deloitte.com ECA logic transformation and data availability ETA WW04 | Mohammed Farook M | 01/07/26 10:53 AM
Row 1131 | GPO Approval updated as object is added via a approved CR. | Sagar Deolalikar | 11/19/25 12:13 PM
Row 1132 | @salingam@deloitte.com : Still on roadblock and awaiting ETA for Tech fix on enhancement | Mohammed Farook M | 01/07/26 10:42 AM
Row 1132 | @salingam@deloitte.com : Roadblock on enhancement object completion will be cleared by 11/14. Conversion Build to proceed after this. cc: @nisarora@deloitte.com @vjillela@deloitte.com @mfarook@deloitte.com | Prasanna Srikantachar | 11/07/25 10:44 AM
Row 1132 | @salingam@deloitte.com : RAID #02329 : FTSE01642 enhancement dependency and conversion development is blocked due to non availability of required load fields. cc: @priya.kothandaraman@intel.com @vjillela@deloitte.com @nisarora@deloitte.com @keertix.nayak@intel.com | Prasanna Srikantachar | 10/22/25 11:27 AM
Row 1132 | Due to enhancement dependency, this object gets spills over to sprint 19. | Katta Prathyusha | 10/07/25 8:01 AM
Row 1132 | @vchaudhari@deloitte.com : Sprint 17 FS walkthrough will be completed to ensure ITC1 timeline is met. cc: @salingam@deloitte.com @vkamineni@deloitte.com | Prasanna Srikantachar | 08/14/25 9:42 AM
Row 1132 | @salingam@deloitte.com : Can we have the FS dates populated, so that we can plan on TUT dates and handover to you for FUT dates. cc: @priya.kothandaraman@intel.com @vkamineni@deloitte.com | Prasanna Srikantachar | 07/29/25 11:05 AM
Row 1133 | As requested and approved by GPO, Release changed from R3 to R4 | Jeson Noronha | 09/11/25 7:47 AM
Row 1134 | @vchaudhari@deloitte.com : Can you confirm on the CR walkthrough with @vjillela@deloitte.com and @katprathyusha@deloitte.com . cc: @salingam@deloitte.com | Prasanna Srikantachar | 09/10/25 11:53 AM
Row 1134 | @vchaudhari@deloitte.com : CR walkthrough to be completed by 8/18 week. cc: @salingam@deloitte.com | Prasanna Srikantachar | 08/14/25 9:43 AM
Row 1134 | @salingam@deloitte.com : for 3 use cases, FS and Build needs to be revisited. FTS IP working with PMO to update the new FS planned end date. Completion of FS by May'25 is at risk. Will be brought up by FTS IP during April sprint readout. cc: @kim.holloway@intel.com @vkamineni@deloitte.com | Prasanna Srikantachar | 04/16/25 2:42 PM
Row 1135 | CR Approved for IP Version (INT-Build-CR0331) | Jeson Noronha | 05/01/25 10:16 PM
Row 1150 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:34 AM
Row 1150 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:32 AM
Row 1151 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:34 AM
Row 1151 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:32 AM
Row 1158 | This FDS will be worked in the upcoming Sprint 12 | Boopathi Raja Palanisamy | 03/07/25 3:39 AM
Row 1159 | To be completed by 6th February | Rafael A Quesada Alfaro | 02/04/26 6:48 AM
Row 1159 | This FDS will be worked in the upcoming Sprint 12 | Boopathi Raja Palanisamy | 03/07/25 3:38 AM
Row 1165 | 01/15: This object is dependent on the completion of the RICEFW -FPRE0372,FPRE0373,FPRE0374,FPRE0375. | Shubham Babasaheb Patil | 01/15/25 3:52 AM
Row 1165 | FS Complete Review in progress. On track for ETA (08/02) | Bobby Saha | 07/25/24 11:20 PM
Row 1165 | Draft is in progress. On track for ETA (07/24) | Bobby Saha | 07/17/24 4:31 AM
Row 1166 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1166 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:34 AM
Row 1167 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1167 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:34 AM
Row 1172 | @pramokulkarni@deloitte.com : this is a config and will need to be descoped. cc: @sriram.venkateswaran@intel.com | Prasanna Srikantachar | 09/18/25 10:26 AM
Row 1173 | @pramokulkarni@deloitte.com : This is a manual conversion object cc: @sriram.venkateswaran@intel.com | Prasanna Srikantachar | 09/18/25 10:26 AM
Row 1177 | @rafael.a.quesada.alfaro@intel.com - this does not look related to Treasury. Not sure which sub team owns | Shira Koerbel | 12/03/25 11:32 PM
Row 1178 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 1179 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 1188 | Hi @pgaroo@deloitte.com Could you please add the email of Shane Bethune as GPO approval email, so he can be notified, without an email there in the field he never got the notification for approve. | Rafael A Quesada Alfaro | 03/19/25 1:25 PM
Row 1189 | Boundary App Involved = NO (confirmed by shubhambpatil@deloitte.com) | Meenal Goel | 03/05/25 7:35 AM
Row 1190 | Boundary App Involved = NO (confirmed by shubhambpatil@deloitte.com) | Meenal Goel | 03/05/25 7:35 AM
Row 1191 | Middleware changed as below:- CR # INT-CR0968 created for this change | Danish Abdali | 07/23/25 5:14 AM
Row 1192 | Middleware changed as below:- CR # INT-CR0968 created for this change | Danish Abdali | 07/23/25 5:14 AM
Row 1193 | The Intel SFT MW team has reached to the fspec creator (Noronha, Jason) and Tower Lead (Kunjir, Vijay S). We need to understand the requirements for transfer files to support this interface. | Jeremy M Morrissey | 04/18/25 1:38 PM
Row 1194 | The Intel SFT MW team has reached to the fspec creator (Noronha, Jason) and Tower Lead (Kunjir, Vijay S). We need to understand the requirements for transfer files to support this interface. | Jeremy M Morrissey | 04/18/25 1:38 PM
Row 1195 | Middleware changed as below:- CR # INT-CR0968 created for this change | Danish Abdali | 07/23/25 5:14 AM
Row 1199 | Suresh Avula confirmed that interface is b/w SAP and ECA and Ricardo (ricardo.j.varela.molina@intel.com) confirmed that no work is required by SPEED for this interface. Hence, marking Boundary App Involved = NO. | Meenal Goel | 02/19/25 8:10 AM
Row 1199 | As per Meenal's request Source System updated to ECA | Jeson Noronha | 02/19/25 8:00 AM
Row 1200 | Suresh Avula confirmed that interface is b/w SAP and ECA and Ricardo (ricardo.j.varela.molina@intel.com) confirmed that no work is required by SPEED for this interface. Hence, marking Boundary App Involved = NO. | Meenal Goel | 02/19/25 8:10 AM
Row 1200 | As per Meenal's request Source System updated to ECA | Jeson Noronha | 02/19/25 8:00 AM
Row 1207 | FUT to start on 07/29 | Rahul Ranjan | 07/25/25 2:58 AM
Row 1207 | Majority of the FS are for WOM, Intel team did not receive all of them until 12/12/2024. Expect to complete review with Deloitte by Friday next week. | Eesha Subodh Chitale | 12/17/24 2:21 AM
Row 1211 | The Intel SFT MW team has reached out to Doraiswamy, Jayanth and Singh, Karan and is waiting for file share paths and documentation before the MW Build can start. | Jeremy M Morrissey | 04/18/25 1:35 PM
Row 1211 | Delayed due to decision on approach(Open Text/E2Open) related to Interface between IP and IF | Karan Singh | 12/17/24 1:27 AM
Row 1212 | The Intel SFT MW team has reached out to Doraiswamy, Jayanth and Singh, Karan and is waiting for file share paths and documentation before the MW Build can start. | Jeremy M Morrissey | 04/18/25 1:35 PM
Row 1212 | Delayed due to decision on approach(Open Text/E2Open) related to Interface between IP and IF | Karan Singh | 12/17/24 1:27 AM
Row 1224 | FUT In Progress, part of sprint 16 | Rahul Ranjan | 07/25/25 3:09 AM
Row 1235 | Awaiting Business Confirmation on the open items related to conversion of rates in Mulesoft and ECA | Tushar Sachdeva | 07/10/25 3:28 AM
Row 1238 | Middleware changed as below:- CR # INT-CR0968 created for this change | Danish Abdali | 07/23/25 5:14 AM
Row 1250 | Changes required for FPRI0379: Unmap the BApps​ Not related to B-apps, this is required for semi automated JE for Business use. Please unmap the B-apps for this S4 object.​ Rationale: The files prepared by Knime & Python in the .csv format (Semi Automated general entries) will be placed in Intel Internal File share location which will enable seamless data flow between external systems & SAP CFIN, ensuring that financial transactions are accurately recorded in the SAP system in a timely manner. MuleSoft will be validating and transforming the incoming files before sending them to the SAP directory.​ https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/doc2.aspx?sourcedoc=%7B52FF66E3-AEDB-4D56-A19D-B82DB47F7604%7D&file=5_6_25%20INT-CR0626%20-%20S4%20RICEFW%20FPRI0376%20FPRI0377%20FPRI0378%20FPRI0379%20Change%20Request%20-%20Copy.pptx&action=edit&mobileredirect=true&CID=1CD3F621-8F1D-4F7B-92BA-9AB9B4B9438E&wdLOR=c45FA17A9-A35F-4B16-8113-3E57FF655017 | Jeson Noronha | 06/02/25 5:42 AM
Row 1250 | FS completed. Business review scheduled on 07/26. (ETA – 07/26) | Bobby Saha | 07/25/24 11:17 PM
Row 1250 | FS completed. Business review scheduled on 07/24. (ETA – 07/24) | Bobby Saha | 07/23/24 7:31 AM
Row 1250 | Draft is completed. Additional points to be shared to Mulesoft on 07/12. Business review scheduled on 07/17. (ETA – 09/19) | Bobby Saha | 07/17/24 4:34 AM
Row 1251 | Development completed in S/4 system but still pending from Middleware (MuleSoft) team, so FUT cannot be started till whole development is completed. | Shubham Babasaheb Patil | 01/15/25 3:49 AM
Row 1252 | 01/15: Development completed in S/4 system but still pending from Middleware (MuleSoft) team, so FUT cannot be started till whole development is completed. | Shubham Babasaheb Patil | 01/15/25 3:49 AM
Row 1253 | FS completed. Business review scheduled on 07/26. (ETA – 07/26) | Bobby Saha | 07/25/24 11:17 PM
Row 1253 | FS completed. Business review scheduled on 07/24. (ETA – 07/24) | Bobby Saha | 07/23/24 7:32 AM
Row 1253 | Draft is completed. Additional points to be shared to Mulesoft on 07/12. Business review scheduled on 07/17. (ETA – 09/19) | Bobby Saha | 07/17/24 4:33 AM
Row 1254 | FS completed. Business review scheduled on 07/26. (ETA – 07/26) | Bobby Saha | 07/25/24 11:17 PM
Row 1254 | FS completed. Business review scheduled on 07/24. (ETA – 07/24) | Bobby Saha | 07/23/24 7:32 AM
Row 1254 | Draft is completed. Additional points to be shared to Mulesoft on 07/12. Business review scheduled on 07/17. (ETA – 09/19) | Bobby Saha | 07/17/24 4:26 AM
Row 1255 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1255 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:37 AM
Row 1256 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1256 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:37 AM
Row 1257 | Issues around error handling. Awaiting business approval- ETA-7/24/2024 | Bobby Saha | 07/23/24 4:21 AM
Row 1257 | Pending Business Aproval. ETA - 07/22 | Bobby Saha | 07/19/24 6:51 AM
Row 1257 | Intel IT team to confirm use Hubspan instead of Mulesoft. ETA - 07/22 | Bobby Saha | 07/19/24 4:28 AM
Row 1257 | FS in progress - Process flow needs to be updated (ETA 07/19) | Shourya Jain | 07/16/24 7:33 AM
Row 1258 | Pending business (Shivani & Sampath) approval- ETA-7/24/2024 | Bobby Saha | 07/23/24 4:20 AM
Row 1258 | Intel IT team to confirm use Hubspan instead of Mulesoft. ETA - 07/22 | Bobby Saha | 07/19/24 4:25 AM
Row 1258 | Review in progress by business | Bobby Saha | 07/17/24 4:38 AM
Row 1259 | TUT/Dev In Progress and FUT Planned in Sprint 16 | Tushar Sachdeva | 05/06/25 5:39 AM
Row 1259 | To be moved to Next sprint | Bobby Saha | 07/17/24 4:31 AM
Row 1259 | Technology Team has received the required clarifications from FPR Tower. The Complexity has been updated as High. GPO Approval is triggered on 05/30 | Jeson Noronha | 05/30/24 7:57 AM
| Pending GPO Approval, gated by better data quality c/o Jesse & Prabesh - as per @rafael.a.quesada.alfaro@intel.com | Brian Ochoa | 05/31/24 8:32 AM
Row 1259 | As discussed with FPRl(This object need to be presented again in next session) @mchillarige@deloitte.com | Jeson Noronha | 05/21/24 4:04 AM
Row 1270 | OSC approval not required. This is an integrated design across BA, ECA, and interface with S4. The only enhancement is summarization logic and is not a S4 enhancement tor functionality. E2E design was discussed with core leadership and approved on CL CR meeting. | Sagar Deolalikar | 11/10/25 12:23 PM
Row 1270 | Approved as these objects are created via approved CRs. | Sagar Deolalikar | 11/04/25 4:54 PM
Row 1278 | Removed as per discussion with Prabesh/Nishant with alignment from PMO on 9.3.25 | Jonah Sanders | 09/03/25 1:00 PM
Row 1279 | Removed as per discussion with Prabesh/Nishant with alignment from PMO on 9.3.25 | Jonah Sanders | 09/03/25 1:00 PM
Row 1285 | To be completed by 6th February | Rafael A Quesada Alfaro | 02/04/26 6:48 AM
Row 1301 | Object cancelled as per CR INT-CR1482 | Jeson Noronha | 03/05/26 7:51 AM
Row 1312 | Object Descoped as per CR : INT-CR0652 | Jeson Noronha | 09/12/25 7:42 AM
Row 1312 | Dev In progress - TUT ETA 07/29 | Rahul Ranjan | 07/25/25 3:15 AM
Row 1313 | To be completed by 6th February | Rafael A Quesada Alfaro | 02/04/26 6:48 AM
Row 1328 | As per PMO notes, OSC approval not needed. Object was part of an approved object | Jeson Noronha | 07/30/25 3:13 AM
Row 1329 | As per PMO notes, OSC approval not needed. Object was part of an approved object | Jeson Noronha | 07/30/25 3:13 AM
Row 1331 | Object descoped as per CR : INT-CR1148 | Jeson Noronha | 11/04/25 8:43 PM
Row 1348 | TUT/Dev Replanned to Sprint 14 | Tushar Sachdeva | 05/06/25 5:41 AM
Row 1349 | TUT/Dev Replanned to Sprint 14 | Tushar Sachdeva | 05/06/25 5:41 AM
Row 1349 | Duplicate of FPRE0880 | Vasanth Mohan | 12/11/24 9:42 AM
Row 1350 | TUT/Dev Replanned to Sprint 14 | Tushar Sachdeva | 05/06/25 5:41 AM
Row 1351 | FUT in progress , a new defect 1727,1730 created. Fransisco from Tech Team working on it | Rahul Ranjan | 07/25/25 2:58 AM
Row 1352 | FUT in progress , a new defect 1727,1730 created. Fransisco from Tech Team working on it | Rahul Ranjan | 07/25/25 2:37 AM
Row 1353 | As per Email communication from FPR & Twinkle(Intel) - No Action on Deloitte Team | Jeson Noronha | 03/28/25 5:16 AM
Row 1354 | On-Hold - Swift Connectivity | Tushar Sachdeva | 05/06/25 5:41 AM
Row 1355 | FUT to start on 07/29 | Rahul Ranjan | 07/25/25 2:49 AM
Row 1355 | Majority of the FS are for WOM, Intel team did not receive all of them until 12/12/2024. Expect to complete review with Deloitte by Friday next week. | Eesha Subodh Chitale | 12/17/24 2:24 AM
Row 1356 | Approval pending from Business | Eesha Subodh Chitale | 12/17/24 2:23 AM
Row 1357 | The object is yet to be approved by OSC. Hence the review is not complete. | Shiva Shankar Harikrishnan | 12/17/24 2:50 AM
Row 1358 | The object is yet to be approved by OSC. Hence the review is not complete. | Shiva Shankar Harikrishnan | 12/17/24 2:50 AM
Row 1359 | Reverting back to Enhancement | Jeson Noronha | 03/12/25 9:44 AM
Row 1359 | Object Type Changed from Enhancement to Interface | Jeson Noronha | 03/11/25 4:25 AM
Row 1360 | Reverting back to Enhancement | Jeson Noronha | 03/12/25 9:44 AM
Row 1360 | Object Type Changed from Enhancement to Interface | Jeson Noronha | 03/11/25 4:25 AM
Row 1372 | TUT/Dev Planned in Sprint 14 | Tushar Sachdeva | 05/06/25 5:40 AM
Row 1373 | TUT/Dev Planned in Sprint 14 | Tushar Sachdeva | 05/06/25 5:40 AM
Row 1376 | FUT In Progress, part of sprint 16 | Rahul Ranjan | 07/25/25 3:08 AM
Row 1377 | FUT Approved | Rahul Ranjan | 07/25/25 3:01 AM
Row 1378 | FUT Approved | Rahul Ranjan | 07/25/25 3:01 AM
Row 1382 | Defect 616 & CR - CR0537 in development with Tech Team. ETA for TUT 07/29 | Rahul Ranjan | 07/25/25 2:30 AM
Row 1384 | CR: INT-CR0987 created for the change in the FUT logic. Pending approval from Shane ( FPR GPO) | Rahul Ranjan | 07/25/25 2:57 AM
Row 1385 | CR: INT-CR0987 created for the change in the FUT logic. Pending approval from Shane ( FPR GPO) | Rahul Ranjan | 07/25/25 2:57 AM
Row 1393 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:22 AM
Row 1394 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:22 AM
Row 1395 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:22 AM
Row 1396 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:20 AM
Row 1397 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:20 AM
Row 1398 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:20 AM
Row 1399 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:20 AM
Row 1400 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:20 AM
Row 1401 | Discussions are going on with respect to the ownership of the UIPath objects, will be able to provide the FS dates once we conclude the discussion. | Bobby Saha | 12/10/24 3:22 AM
Row 1406 | As per FPR towers request and aligned with Tech. The RICEFW Type is changed from Conversion to Enhancement | Jeson Noronha | 04/25/25 3:57 AM
Row 1407 | As per FPR towers request and aligned with Tech. The RICEFW Type is changed from Conversion to Enhancement | Jeson Noronha | 04/25/25 3:57 AM
Row 1429 | Bapp testing is in progress - Defect 3433 identified. Tech ETA 10/09 | Biplab Rout | 10/08/25 1:28 PM
Row 1429 | INT-Build-CR0533 is approved. Tech completion ETA – 7/28 | Rahul Ranjan | 07/25/25 2:59 AM
Row 1429 | TUT/Dev Complete and FUT Planned in Sprint 14 | Tushar Sachdeva | 05/06/25 5:37 AM
Row 1435 | TUT in progress for FPRE0425 | Rahul Ranjan | 07/25/25 2:32 AM
Row 1435 | Complexity of FPRE0425 is High due to : We need to build RAP dashboard with Manual and Mass creation of Treasury Funding Requests. Fiori app should have Download Template , Validate and Mass Upload of TFS’s. We have to do it in RAP as per Intel Recommendation. Notification should be sent to stakeholders. | Jeson Noronha | 02/21/25 4:18 AM
Row 1436 | Business Review for approval scheduled for 25/07 - ETA 25/07 | Bobby Saha | 07/25/24 11:16 PM
Row 1436 | Business Review for approval scheduled for 24/07 - ETA 24/07 | Bobby Saha | 07/23/24 4:19 AM
Row 1436 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/23) | Bobby Saha | 07/22/24 8:36 AM
Row 1436 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/19) | Bobby Saha | 07/17/24 4:35 AM
Row 1437 | Business Review for approval scheduled for 25/07 - ETA 25/07 | Bobby Saha | 07/25/24 11:15 PM
Row 1437 | Business Review for approval scheduled for 24/07 - ETA 24/07 | Bobby Saha | 07/23/24 4:18 AM
Row 1437 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/23) | Bobby Saha | 07/22/24 8:37 AM
Row 1437 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/19) | Bobby Saha | 07/17/24 4:35 AM
Row 1438 | Business Review for approval scheduled for 25/07 - ETA 25/07 | Bobby Saha | 07/25/24 11:15 PM
Row 1438 | Business Review for approval scheduled for 24/07 - ETA 24/07 | Bobby Saha | 07/23/24 4:18 AM
Row 1438 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/23) | Bobby Saha | 07/22/24 8:37 AM
Row 1438 | Draft is in progress, and a call with the Intel team has been scheduled for 07/17 on open points (ETA 07/19) | Bobby Saha | 07/17/24 4:35 AM
Row 1439 | The Defect 1583 has been Fixed by tech team on 7/24. FUT in progress. | Rahul Ranjan | 07/25/25 2:53 AM
Row 1439 | FS completed. Business review scheduled on 07/26. (ETA – 07/26) | Bobby Saha | 07/25/24 11:17 PM
Row 1439 | FS completed. Business review scheduled on 07/24. (ETA – 07/24) | Bobby Saha | 07/23/24 7:31 AM
Row 1439 | Draft is in progress. On track for ETA (07/18) | Bobby Saha | 07/17/24 4:25 AM
Row 1440 | The Defect 1582 has been Fixed by tech team on 7/24. FUT in progress. | Rahul Ranjan | 07/25/25 2:53 AM
Row 1442 | Planned for current Build Sprint 16 | Rahul Ranjan | 07/25/25 7:36 AM
Row 1443 | Planned for current Build Sprint 16 | Rahul Ranjan | 07/25/25 7:36 AM
Row 1444 | FS Review Completed, pending approval from Intel IT. | Bobby Saha | 07/17/24 4:25 AM
Row 1445 | FS Complete Review in progress. On track for ETA (08/02) | Bobby Saha | 07/25/24 11:19 PM
Row 1445 | Draft is in progress. On track for ETA (07/24) | Bobby Saha | 07/17/24 4:24 AM
Row 1446 | FS Complete Review in progress. On track for ETA (08/02) | Bobby Saha | 07/25/24 11:19 PM
Row 1446 | Draft is in progress. On track for ETA (07/24) | Bobby Saha | 07/17/24 4:24 AM
Row 1447 | FS Complete and approved | Bobby Saha | 07/23/24 4:17 AM
Row 1447 | Review and approval call scheduled with business on 7/18/2024. ETA-7/19/2024 | Bobby Saha | 07/19/24 6:47 AM
Row 1447 | Release Name changed from R1 to R3 for FPRE0360_IP | Jeson Noronha | 07/18/24 4:26 AM
Row 1447 | Business to confirm on line item transfer requirement and logic by 7/18/2024. ETA-7/19/2024 | Bobby Saha | 07/17/24 4:39 AM
Row 1447 | Additional pointers to be updated for Reclassification. Additional logic to be provided by Business. (Call scheduled on 07/15)- ETA- 7/17/2024 | Bobby Saha | 07/16/24 9:39 AM
Row 1448 | FS Complete and approved | Bobby Saha | 07/23/24 4:17 AM
Row 1448 | Review and approval call scheduled with business on 7/18/2024. ETA-7/19/2024 | Bobby Saha | 07/19/24 6:47 AM
Row 1448 | Release Name changed from R1 to R3 for FPRE0360_IF | Jeson Noronha | 07/18/24 4:26 AM
Row 1448 | Business to confirm on line item transfer requirement and logic by 7/18/2024. ETA-7/19/2024 | Bobby Saha | 07/17/24 4:38 AM
Row 1448 | Additional pointers to be updated for Reclassification. Additional logic to be provided by Business. (Call scheduled on 07/15)- ETA- 7/17/2024 | Bobby Saha | 07/16/24 9:39 AM
Row 1449 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1449 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:37 AM
Row 1450 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1450 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:37 AM
Row 1451 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1451 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:32 AM
Row 1452 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:34 AM
Row 1452 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:32 AM
Row 1453 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1453 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:27 AM
Row 1454 | FS completed and under discussion with Intel for FS review. ETA - 07/25 | Bobby Saha | 07/23/24 7:35 AM
Row 1454 | FS completed and under discussion with Intel for FS review | Bobby Saha | 07/17/24 4:27 AM
Row 1455 | Design finalization pending from business. ETA for FS completion 8/23 | Rafael A Quesada Alfaro | 08/14/24 8:19 AM
Row 1455 | Meeting scheduled with Rea for design confirmation for Interplay between Accruals and Prepaids | Shiva Shankar Harikrishnan | 07/25/24 4:37 AM
Row 1455 | Have set up a meeting with development team for the dash board design validation. ETA - 7/26/2024 | Bobby Saha | 07/23/24 4:17 AM
Row 1455 | Requirements have been briefed, started the FS and still working on the core logic to meet the requirement. Meeting has been schedule with Rea for 7/17/2024 at 6am PST. ETA- 7/26/2024 | Bobby Saha | 07/17/24 4:30 AM
| RAIID opened 1716 | Rafael A Quesada Alfaro | 07/22/24 9:20 AM
Row 1457 | Initial Design of the fiori screens complete. Field logic is in-progress | Shiva Shankar Harikrishnan | 07/25/24 4:38 AM
Row 1457 | Have set up a meeting with development team for the dash board design validation. ETA - 7/26/2024 | Bobby Saha | 07/23/24 4:16 AM
Row 1457 | Requirements have been briefed, started the FS and still working on the core logic to meet the requirement. Meeting has been schedule with Rea for 7/17/2024 at 6am PST. ETA- 7/26/2024 | Bobby Saha | 07/17/24 4:40 AM
| RAIID opened: 1719 | Rafael A Quesada Alfaro | 07/22/24 9:19 AM
Row 1459 | FUT In progress , Defect 1636 with Tech Team | Rahul Ranjan | 07/25/25 2:29 AM
Row 1459 | Technical evaluation is in-progress for fiori design. FS draft is in-progress. All the requirements received from Business. ETA - 07/26 | Bobby Saha | 07/25/24 11:13 PM
Row 1459 | Have set up a meeting with development team for the dash board design validation. ETA - 7/26/2024 | Bobby Saha | 07/23/24 4:16 AM
Row 1459 | Requirements have been briefed, started the FS and still working on the core logic to meet the requirement. Meeting has been schedule with Rea for 7/17/2024 at 6am PST. ETA- 7/26/2024 | Bobby Saha | 07/17/24 4:40 AM
| RAIID opened 1718 | Rafael A Quesada Alfaro | 07/22/24 9:21 AM
Row 1460 | FUT In progress , Defect 1636 with Tech Team | Rahul Ranjan | 07/25/25 2:29 AM
Row 1461 | Technical evaluation is in-progress for fiori design. FS draft is in-progress. All the requirements received from Business. ETA - 07/26 | Bobby Saha | 07/25/24 11:13 PM
Row 1461 | Have set up a meeting with development team for the dash board design validation. ETA - 7/26/2024 | Bobby Saha | 07/23/24 4:17 AM
Row 1461 | Requirements have been briefed, started the FS and still working on the core logic to meet the requirement. Meeting has been schedule with Rea for 7/17/2024 at 6am PST. ETA- 7/26/2024 | Bobby Saha | 07/17/24 4:29 AM
| RAIID opened 1717 | Rafael A Quesada Alfaro | 07/22/24 9:22 AM
Row 1463 | FS is complete | Bobby Saha | 07/23/24 4:21 AM
Row 1463 | Approval received from Opex (IT and Business) and Capex IT, Approval from Capex business is expected on 07/19 | Bobby Saha | 07/19/24 6:49 AM
Row 1463 | Mail sent to business for Approval on 7/16/2024. Awaiting Business Approval | Bobby Saha | 07/17/24 4:30 AM
Row 1464 | FS is complete | Bobby Saha | 07/23/24 4:21 AM
Row 1464 | Approval received from Opex (IT and Business) and Capex IT, Approval from Capex business is expected on 07/19 | Bobby Saha | 07/19/24 6:49 AM
Row 1464 | Mail sent to business for Approval on 7/16/2024. Awaiting Business Approval | Bobby Saha | 07/17/24 4:34 AM
Row 1465 | Opex business has approved it and waiting for approval from Intel Capex side | Bobby Saha | 07/23/24 4:22 AM
Row 1465 | Opex business has approved it and waiting for approval from Intel Capex side, Intel IT team has some queries which they want to discuss with the George on Monday | Bobby Saha | 07/19/24 6:50 AM
Row 1465 | Business Approval Pending (ETA – 07/16) | Shourya Jain | 07/16/24 8:43 AM
Row 1466 | Opex business has approved it and waiting for approval from Intel Capex side | Bobby Saha | 07/23/24 4:22 AM
Row 1466 | Opex business has approved it and waiting for approval from Intel Capex side, Intel IT team has some queries which they want to discuss with the George on Monday | Bobby Saha | 07/19/24 6:50 AM
Row 1466 | Submitted to Dev for Review / Security Review pending (ETA – 07/17) | Shourya Jain | 07/16/24 7:34 AM
Row 1469 | FS Completed. Dev Review is completed.Approval pending from Process Stewards | Bobby Saha | 07/23/24 4:23 AM
Row 1469 | FS Completed. Dev Review is completed. | Bobby Saha | 07/17/24 4:33 AM
Row 1477 | FUT submitted and explanation done to Biz. Awaiting final Sign-off | Rahul Ranjan | 07/25/25 2:58 AM
Row 1479 | TUT/Dev Planned in Sprint 14 | Tushar Sachdeva | 05/06/25 5:41 AM
Row 1479 | Intake form : https://intel.sharepoint.com/:p:/r/sites/inteldeloitteiao/_layouts/15/Doc.aspx?sourcedoc=%7B580759F0-2843-4492-8FD6-A28C3D42DDD4%7D&file=MR-070-0008_FPR_RICEFW%20Intake%20Form_v1.0_TPR.pptx&wdLOR=c7E05ECCF-D468-4A49-BAFB-569FEF939098&action=edit&mobileredirect=true | Jeson Noronha | 07/08/24 3:54 AM
Row 1479 | Complexity for FPRE0239 reduced from Very High to High. Reason : Object FPRE0239 is now split into a 2nd object FPRE425 ( Medium ) | Jeson Noronha | 06/28/24 3:08 AM
Row 1480 | @csilla.i.bolya@intel.com @hema.vennapusala@intel.com HLTA for FPRE0049 is ready for review. In case you need connect to discuss on any query please reach out to @robijain@deloitte.com @vasamohan@deloitte.com or @nmaddi@deloitte.com | Robindra Jain | 05/08/24 4:45 AM
Row 1484 | Approved in backend based on Shane email approval | Vasanth Mohan | 06/18/25 12:54 PM
Row 1485 | Approved in backend based on Shane email approval | Vasanth Mohan | 06/18/25 12:54 PM
Row 1486 | @gbakare@deloitte.com : Please have FS dates added to tracker and complete walkthrough per our SOS meeting. Here is RAID created for same: 01430. cc: @twinkle.shah@intel.com @prabacharya@deloitte.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 06/18/25 7:12 AM
Row 1487 | @gbakare@deloitte.com : Please have FS dates added to tracker and complete walkthrough per our SOS meeting. Here is RAID created for same: 01430. cc: @twinkle.shah@intel.com @prabacharya@deloitte.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 06/18/25 7:12 AM
Row 1489 | @gbakare@deloitte.com : now that the FS is marked 100% complete, please schedule FS walkthrough with Data Conversion Team ( BODS). cc: @sriram.venkateswaran@intel.com @twinkle.shah@intel.com | Prasanna Srikantachar | 06/26/25 10:11 AM
Row 1490 | @manidgupta@deloitte.com : FUT completed, Pending approval. ETA - 10/24. cc: @twinkle.shah@intel.com @sriram.venkateswaran@intel.com | Prasanna Srikantachar | 10/16/25 10:12 AM
Row 1490 | @gbakare@deloitte.com : Can you please work with PMO team to get the % of completion updated along with revised FS completion date. cc: @twinkle.shah@intel.com @prabacharya@deloitte.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 06/18/25 7:10 AM
Row 1490 | @gbakare@deloitte.com : Please have the PMO team update the description to show only Federal. cc: @twinkle.shah@intel.com | Prasanna Srikantachar | 06/12/25 10:14 AM
Row 1490 | Object renamed to FPRC1212 ( IF version descoped ) | Jeson Noronha | 06/02/25 5:24 AM
Row 1493 | The Defect 1582 has been Fixed , FUT in progress | Rahul Ranjan | 07/25/25 2:50 AM
Row 1493 | Open points to be closed to proceed with development, RAID # 2029 | Vijayadeep Jillela | 09/10/24 11:56 AM
Row 1493 | FS completed.Pending Approval ETA - 07/31 | Bobby Saha | 07/25/24 11:21 PM
Row 1493 | FS completed. On open points, need to get details from Intel. Based on that we need to connect with BODS team | Bobby Saha | 07/17/24 4:28 AM
Row 1494 | Defect 1709 with Tech Team | Rahul Ranjan | 07/25/25 2:34 AM
Row 1494 | Open points to be closed to proceed with development, RAID # 2029 | Vijayadeep Jillela | 09/10/24 11:56 AM
Row 1494 | FS completed.Pending Approval ETA - 07/31 | Bobby Saha | 07/25/24 11:21 PM
Row 1494 | FS completed. On open points, need to get details from Intel. Based on that we need to connect with BODS team | Bobby Saha | 07/17/24 4:28 AM
Row 1495 | Defect 1709 with Tech Team | Rahul Ranjan | 07/25/25 2:34 AM
Row 1495 | Raid corrected: # 2030 | Vijayadeep Jillela | 09/10/24 11:57 AM
Row 1495 | Open points to be closed to proceed with development, RAID # 2039 | Vijayadeep Jillela | 09/10/24 11:56 AM
Row 1495 | FS completed.Pending Approval ETA - 07/31 | Bobby Saha | 07/25/24 11:18 PM
Row 1495 | FS completed. On open points, need to get details from Intel. Based on that we need to connect with BODS team | Bobby Saha | 07/17/24 4:27 AM
Row 1496 | The Defect 1673 & 1709 open with Tech Team. | Rahul Ranjan | 07/25/25 2:50 AM
Row 1496 | Raid corrected: # 2030 | Vijayadeep Jillela | 09/10/24 11:57 AM
Row 1496 | Open points to be closed to proceed with development, RAID # 2039 | Vijayadeep Jillela | 09/10/24 11:56 AM
Row 1496 | FS completed.Pending Approval ETA - 07/31 | Bobby Saha | 07/25/24 11:18 PM
Row 1496 | FS completed. On open points, need to get details from Intel. Based on that we need to connect with BODS team | Bobby Saha | 07/17/24 4:27 AM
Row 1497 | @trigopal@deloitte.ca : to update the revised FS completion dates | Prasanna Srikantachar | 12/04/24 10:16 AM
Row 1497 | @snavasthi@deloitte.com FS planned dates to be revised by tower team based on dependency Enhancement build completion. | Katta Prathyusha | 11/22/24 1:11 AM
Row 1498 | @trigopal@deloitte.ca : to update the revised FS completion dates | Prasanna Srikantachar | 12/04/24 10:16 AM
Row 1498 | @snavasthi@deloitte.com FS planned dates to be revised by tower team based on dependency Enhancement build completion. | Katta Prathyusha | 11/22/24 1:11 AM
Row 1501 | @trigopal@deloitte.ca : to update the revised FS completion dates | Prasanna Srikantachar | 12/04/24 10:16 AM
Row 1501 | @snavasthi@deloitte.com FS planned dates to be revised by tower team based on dependency Enhancement build completion | Katta Prathyusha | 11/22/24 1:17 AM
Row 1501 | Enhancement dependency to be completed, Raid # 1490 raised. | Vijayadeep Jillela | 09/10/24 11:58 AM
Row 1501 | FS in progress for added scope and also dependent on FPRE0315_IP. ETA- 7/26/2024 | Bobby Saha | 07/22/24 8:33 AM
Row 1502 | @trigopal@deloitte.ca : to update the revised FS completion dates | Prasanna Srikantachar | 12/04/24 10:16 AM
Row 1502 | @snavasthi@deloitte.com FS planned dates to be revised by tower team based on dependency Enhancement build completion | Katta Prathyusha | 11/22/24 1:17 AM
Row 1502 | Enhancement dependency to be completed, Raid # 1490 raised. | Vijayadeep Jillela | 09/10/24 11:58 AM
Row 1502 | FS in progress for added scope and also dependent on FPRE0315_IP. ETA- 7/26/2024 | Bobby Saha | 07/22/24 8:33 AM
Row 1503 | GPO Status has been reverted from Rejected to Approved. Approval email from Candice | Jeson Noronha | 04/03/25 1:38 AM
Row 1510 | This FUT is 100% complete.BSPID-40467 | Shruti Singh | 08/04/25 12:21 AM
Row 1512 | FUT tasks should be coming in sprint 17. | Miranda White | 08/06/25 10:00 AM
Row 1515 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:01 PM
Row 1516 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:00 PM
Row 1519 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1519 | This is Native b/w mdg, s/4 ip and if | Danish Abdali | 08/29/25 2:19 AM
Row 1520 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1521 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1522 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1523 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1523 | This is Native b/w mdg, s/4 ip and if | Danish Abdali | 08/29/25 2:19 AM
Row 1525 | Object ID renamed as IP and IF versions are not same for DATI0927 | Jeson Noronha | 06/09/25 6:31 AM
Row 1525 | Updated to note that the Interface will involve B-Apps: PLM Translator and SPEED, as work will need on both to support this interface. | Lynn Asbury | 01/07/25 7:08 PM
Row 1525 | nagirreddy@deloitte.com please update FS Dates by EOD | Shruti Singh | 12/10/24 11:59 PM
Row 1525 | pgaroo@deloitte.com - please change the sub-tower to: 9A.2 Master Data - BOM | Lynn Asbury | 12/09/24 8:34 AM
Row 1526 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1526 | Correction to RICEFW ID from DATI1448 to DATI1489 | Jeson Noronha | 06/05/25 10:46 PM
Row 1527 | Middleware changed as per below comment:- As this is a direct call from S4àMDG therefore middleware is not required for below FS’s. | Danish Abdali | 07/23/25 5:12 AM
Row 1527 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1528 | Middleware changed as per below comment:- As this is a direct call from S4àMDG therefore middleware is not required for below FS’s. | Danish Abdali | 07/23/25 5:12 AM
Row 1528 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1529 | MW comment : Bapp (PLM) has already have an Existing APIGEE proxy. So no need of new development | Jeson Noronha | 06/26/25 10:08 PM
Row 1529 | By Shabaz Mohammad on 4/21 - Interface is from MDG to PLM Translator and PLM Translator is a Middleware and not a B-App | Meenal Goel | 04/21/25 3:01 AM
Row 1530 | Object Type changed as per Tower request from Enhancement to Interface | Jeson Noronha | 05/09/25 6:51 AM
Row 1531 | Object Type changed as per Tower request from Enhancement to Interface | Jeson Noronha | 05/09/25 6:51 AM
Row 1532 | Changing B-App Involved to NO (after receiving go ahead from Yashu) as it is a PDH <-> S4 interface (and doesn't fall within B-App scope). | Meenal Goel | 02/19/25 10:24 PM
Row 1535 | FS approval email | Ridhi Shri | 12/13/24 5:25 AM
Row 1535 | Sapna confirmed that FS is approved as of 11/19 - email attached- Sprint 9 will have the activities added for this object | Ridhi Shri | 12/13/24 5:24 AM
Row 1536 | FS approval email | Ridhi Shri | 12/13/24 5:26 AM
Row 1536 | Sapna confirmed that FS is approved as of 11/19 - email attached- Sprint 9 will have the activities added for this object | Ridhi Shri | 12/13/24 5:23 AM
Row 1537 | MW comment : PLM Translator Team will create Proxy (No New development required here ,need to update object tracker) | Jeson Noronha | 06/26/25 10:04 PM
Row 1537 | pgaroo@deloitte.com - please change the sub-tower to: 9A.6 Master Data - Material Master | Lynn Asbury | 12/09/24 8:34 AM
Row 1538 | pgaroo@deloitte.com - please change the sub-tower to: 9A.6 Master Data - Material Master | Lynn Asbury | 12/09/24 8:32 AM
Row 1539 | FUT was previously blocked due to defect #1640. The technical team fixed this issue yesterday. We need to evaluate the bug fix by conducting FUT again. This will result in a one-week delay. FUT is currently in progress. Already part of sprint plan | Shruti Singh | 08/08/25 4:28 AM
Row 1539 | Updated to note that the Interface will involve B-Apps: PLM Translator and SPEED, as work will need on both to support this interface. | Lynn Asbury | 01/07/25 7:08 PM
Row 1539 | pgaroo@deloitte.com - please change the sub-tower to: 9A.2 Master Data - BOM | Lynn Asbury | 12/09/24 8:34 AM
Row 1540 | GPO Approval recieved for DATI0657_IP (over email) | Jeson Noronha | 08/12/25 3:50 AM
Row 1542 | Pending update to sprint plans from PMO to reflect the IP/ IF split. FS is completed for these objects. | Miranda White | 08/14/25 11:44 AM
Row 1542 | Sarvani to add TDD and TUT tasks into sprint 17 and close them out. | Miranda White | 08/06/25 7:07 AM
Row 1543 | Pending update to sprint plans from PMO to reflect the IP/ IF split. FS is completed for these objects. | Miranda White | 08/14/25 11:44 AM
Row 1543 | Sarvani to add TDD and TUT tasks into sprint 17 and close them out. | Miranda White | 08/06/25 7:07 AM
Row 1543 | Lynn and V to work | Virginia Chan | 11/20/24 1:18 PM
Row 1543 | Changing from R2 to R3 per INT-CR0034 | Lauren Herschberg | 08/01/24 1:51 PM
Row 1543 | Delayed due to gap in design that was found WW29 BP Customer FTF, related to the Reltio to MDG integration. Team working on solution. Updated date is 8/2. RAID #1762 raised. | Lynn Asbury | 07/25/24 8:03 AM
Row 1544 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:01 PM
Row 1545 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:01 PM
Row 1546 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:01 PM
Row 1547 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:15 AM
Row 1548 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1549 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1550 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1551 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1552 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1553 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1554 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1555 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1556 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1557 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:14 AM
Row 1558 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1559 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1560 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1561 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1562 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1563 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1564 | Approved offline as per Uzma. Refer email here https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/EXT%20Re%20Agenda%20IAO%20RICEFW%20%20Leadership%20Review%20(0227).msg?csf=1&web=1&e=GgUYaS | Sagar Deolalikar | 02/27/26 8:13 AM
Row 1565 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1567 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1568 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1569 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1570 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1571 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1572 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1573 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1574 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1574 | Correction to RICEFW ID from DATE1449 to DATE1490 | Jeson Noronha | 06/05/25 10:46 PM
Row 1575 | Offline approval received by GPO over email | Jeson Noronha | 06/10/25 9:49 AM
Row 1579 | pgaroo@deloitte.com - please change the sub-tower to: 9A.2 Master Data - BOM | Lynn Asbury | 12/09/24 8:34 AM
Row 1580 | pgaroo@deloitte.com - please change the sub-tower to: 9A.2 Master Data - BOM | Lynn Asbury | 12/09/24 8:34 AM
Row 1582 | Actual FS Approval date was 18th Oct,24. | Shradhashree Nayak | 01/07/25 5:33 AM
Row 1583 | FUT still in progress,ETA 8/15.Already part of sprint plan | Shruti Singh | 08/08/25 4:29 AM
Row 1583 | Actual FS Approval date was 18th Oct,24. | Shradhashree Nayak | 01/07/25 5:33 AM
Row 1585 | Object DATE0668 takes care of the MDG enhancement whereas DATE066_IP will be taken care to enhance the proxy in IP | Jeson Noronha | 03/10/25 2:22 AM
Row 1586 | Object DATE0668 takes care of the MDG enhancement whereas DATE066_CFIN will be taken care to enhance the proxy in CFIN | Jeson Noronha | 03/10/25 2:22 AM
Row 1589 | @sdeolalikar@deloitte.com - Can you change this subteam to Reference data? | Logan Goldstein | 01/30/25 10:49 AM
Row 1590 | @krpasupuleti@deloitte.com @rnazar@deloitte.com need to get a date in for completing this one. | Lynn Asbury | 08/09/24 2:59 PM
Row 1591 | Sarvani to add tasks into sprint 17 and close them out. | Miranda White | 08/06/25 7:08 AM
Row 1591 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/OSC%20Deck%20Archive/RE%20DATE0395_IP%20Approval.msg?csf=1&web=1&e=R1eYU4 | Sagar Deolalikar | 04/08/25 4:46 PM
Row 1591 | mentioned 2 RICEFWs (DATE0395_IP and DATE0313_IP) were build in R2 keeping both IF and IP in mind and we have already completed the build of these objects as part of R2. Being said that we would still… | Sagar Deolalikar | 04/08/25 4:45 PM
Row 1591 | Marking approved as confirmed by MDG Tower The requirement has been approved already, addition of new RICEFW for IP done. | Nishant Arora | 04/02/25 4:00 PM
Row 1592 | Refer link for details | Sagar Deolalikar | 04/08/25 4:43 PM
Row 1592 | mentioned 2 RICEFWs (DATE0395_IP and DATE0313_IP) were build in R2 keeping both IF and IP in mind and we have already completed the build of these objects as part of R2. Being said that we would still be testing them with IP set of data in R3 to check if the functionality, hence for that we would need the “_IP” variants to be added to the R3 object tracker. | Sagar Deolalikar | 04/08/25 4:43 PM
Row 1592 | https://intel.sharepoint.com/:u:/r/sites/inteldeloitteiao/Shared%20Documents/General/Implementation/01.%20PMO/14.%20Governance/OSC/OSC%20Deck%20Archive/RE%20DATE0395_IP%20Approval.msg?csf=1&web=1&e=R1eYU4 | Sagar Deolalikar | 04/08/25 4:43 PM
Row 1593 | Changing release to R3 based on email communication from Lilibeth Lejarde and Jayant Kashikar | Lauren Herschberg | 06/11/24 7:38 AM
Row 1595 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:22 AM
Row 1595 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1596 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:22 AM
Row 1596 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1597 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:22 AM
Row 1597 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1598 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:22 AM
Row 1598 | GPO Approval received over email | Jeson Noronha | 10/08/25 7:49 AM
Row 1599 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:21 AM
Row 1599 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1601 | Per alignment with Lilibeth and MD team, Build is planned for MC2. cc: @lilibethx.lejarde@intel.com @priya.kothandaraman@intel.com | Prasanna Srikantachar | 10/14/25 9:22 AM
Row 1601 | GPO Approval received over email | Jeson Noronha | 09/03/25 5:06 AM
Row 1601 | Approval received by GPO over email. Confirmed by Rahul Nazar | Jeson Noronha | 08/14/25 9:37 PM
Row 1602 | Release changed from R3 to R4 | Jeson Noronha | 08/22/25 7:20 AM
Row 1602 | @llejarde@deloitte.com : Per your confirmation this is R4, Can we get this updated? cc: @priya.kothandaraman@intel.com @umesh.verma@intel.com | Prasanna Srikantachar | 08/20/25 7:28 AM
Row 1602 | Approval received by GPO over email. Confirmed by Rahul Nazar | Jeson Noronha | 08/14/25 9:37 PM
Row 1602 | Lilibeth - This is changed to R4 Scope | Prasanna Srikantachar | 08/12/25 10:18 AM
Row 1603 | Release changed from R3 to R4 as per mail confirmation. | Jeson Noronha | 09/26/25 3:20 AM
Row 1603 | Approval received by GPO over email. Confirmed by Rahul Nazar | Jeson Noronha | 08/14/25 9:37 PM
Row 1603 | This is needed for R3 per Lilibeth. | Prasanna Srikantachar | 08/12/25 10:19 AM
Row 1604 | @lilibethx.lejarde@intel.com / @mghazi@deloitte.com : Please schedule walkthrough of FS ASAP, so that we can progress on build per planning. cc: @umesh.verma@intel.com @virginia.chan@intel.com | Prasanna Srikantachar | 06/12/25 11:16 AM
Row 1608 | This FUT is 100% complete.BSPID-40552 | Shruti Singh | 08/04/25 12:22 AM
Row 1609 | This FUT is 100% complete.BSPID-40553 | Shruti Singh | 08/04/25 12:23 AM
Row 1613 | Actual FS Approval date was 18th Oct,24. | Shradhashree Nayak | 01/07/25 5:34 AM
Row 1613 | LA Lynn Asbury @logoldstein@deloitte.com Please tag as sub-Tower = 9A.8 Master Data - HR Mini Master 09/27/24 Reply LA Lynn Asbury @lyatavakilla@deloitte.com Please help update the sub-tower to 9A.8 Master Data - HR Mini Master 10/10/24 Reply LA Lynn Asbury @logoldstein@deloitte.com this needs to be in HR Mini Master vs Vendor 10/11/24 | Arpit Sharma | 11/20/24 4:46 AM
Row 1615 | Lynn Asbury @lyatavakilla@deloitte.com Please change GPO Approver Email to Candice S Linnell. | Arpit Sharma | 11/20/24 4:43 AM
Row 1616 | Lynn Asbury @lyatavakilla@deloitte.com Please change GPO Approver Email to Candice S Linnell. | Arpit Sharma | 11/20/24 4:43 AM
Row 1617 | @lilibethx.lejarde@intel.com / @mghazi@deloitte.com : Please schedule walkthrough of FS ASAP, so that we can progress on build per planning. cc: @umesh.verma@intel.com @virginia.chan@intel.com | Prasanna Srikantachar | 06/12/25 11:15 AM
Row 1625 | Awaiting approval from Nidhi | Shruti Singh | 08/04/25 12:24 AM
Row 1625 | This RICEFW "DATC0215" is also in R2, changed RICEFW ID to DATC0075_IP as per Tower request. | Jeson Noronha | 01/07/25 3:09 AM
Row 1626 | @lilibethx.lejarde@intel.com / @mghazi@deloitte.com : Please schedule walkthrough of FS ASAP, so that we can progress on build per planning. cc: @umesh.verma@intel.com @virginia.chan@intel.com | Prasanna Srikantachar | 06/12/25 11:16 AM
Row 1626 | @mshabaz@deloitte.com / @mghazi@deloitte.com : Master Data Team: This object FS is delayed and now being delivered (FS Walkthrough to Data Team) on 6/12. cc: @lilibethx.lejarde@intel.com @virginia.chan@intel.com @priya.kothandaraman@intel.com @vjillela@deloitte.com @mfarook@deloitte.com | Prasanna Srikantachar | 06/10/25 1:28 PM
Row 1627 | Pending descope | Lynn Asbury | 08/25/25 2:31 PM
Row 1629 | TDD approved,smartsheet to be updated by Data conversion team | Shruti Singh | 08/04/25 12:26 AM
Row 1629 | @mshabaz@deloitte.com / @mghazi@deloitte.com : Master Data Team: This object FS is delayed and RAID 1283 is created for tracking. ETA - TBD cc: @lilibethx.lejarde@intel.com @virginia.chan@intel.com @priya.kothandaraman@intel.com @vjillela@deloitte.com @mfarook@deloitte.com | Prasanna Srikantachar | 06/10/25 1:30 PM
Row 1630 | Sent for approval on 1st Aug,awaiting Andrew Austin and Sameer for approval | Shruti Singh | 08/04/25 12:19 AM
Row 1632 | This RICEFW "DATC0222" is also in R2, changed RICEFW ID to DATC0068_IP as per Tower request. | Jeson Noronha | 01/07/25 3:05 AM
Row 1634 | Reviewed with Leadership during CR review. No separate OSC review required. | Sagar Deolalikar | 03/25/26 8:47 AM
Row 1635 | RICEF intake form missing. Leadership review required. | Sagar Deolalikar | 03/25/26 8:49 AM
Row 1637 | Reviewed with Leadership during CR review. No separate OSC review required. | Sagar Deolalikar | 03/25/26 8:49 AM